{"text_format":"1","workbook":"xlsx","n_sheets":6,"sheets":["_com.sap.ip.bi.xl.hiddensheet","Tables for document","HX-0014297 - 4012895","TS to NW 4012895","June21 Storm sheet","Positions TS & cons.June21 Stor"],"not_rendered":{"charts":1,"images":2,"macros":0,"external_links":1,"defined_names":13,"comments":0,"pivot_tables":4},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900"}

{"sheet":"_com.sap.ip.bi.xl.hiddensheet","index":0,"n_rows":0,"n_cols":0,"rows_kept":0,"cut":false,"hidden":true,"merged":[]}

{"sheet":"Tables for document","index":1,"n_rows":74,"n_cols":10,"rows_kept":74,"cut":false,"hidden":false,"merged":[]}
["Table 1: Feb Storms incremental costs incurred (nominal)"]
[null,"Capex","Opex","Total"]
["Internal Labour",0,785023.85000000021,785023.85000000021]
["Contracts - emergency works",7391329.6100000255,5067206.479999925,12458536.089999951]
["Contracts - vegetation management",841038.16779999994,604450.25219999999,1445488.42]
["GSLs",null,18621180,18621180]
["Other",null,1859989.9299999997,1859989.9299999997]
["Total ",8232367.7778000254,26937850.512199923,35170218.289999947]
[]
["Table 2: Estimated offset savings in 2022-26 period ($2021)"]
[null,"Capex","Opex"]
["Asset replacement",182038.55,null,182038.55]
["Vegetation management",null,17640,17640]
["Total deductions ",182038.55,17640,199678.55]
[]
["Table 3: Total incremental costs minus deductions ($2021)"]
[null,"Capex","Opex","Total",null,null,null,null,"Conversion factor (nominal to real 2021)",0.9122119904287167]
["Internal Labour",0,716108.16874251456,716108.16874251456]
["Contracts - emergency works",6560420.9454528335,4622366.5090340227,11182787.454486856]
["Contracts - vegetation management",767205.10107535892,533746.76767450175,1300951.8687498607]
["GSLs",0,16986463.671931412,16986463.671931412]
["Other",0,1696705.1162226691,1696705.1162226691]
["Total (no overheads)",7327626.0465281922,24555390.23360512,31883016.280133311]
["Overheads",859653.09857930662,null,859653.09857930662,null,null,null,null," Network overhead rate for 2023-24 (from Final capex model decision)",0.11731672619764866]
["Total (including overheads)",8187279.1451074984,24555390.23360512,32742669.378712617]
[]
[]
["Table 4: Materiality of pass through"]
["$m ($ Jun 2021)","2023-24"]
["Annual revenue requirement (ARR) (smoothed) (2023-24)",657.2442503193854]
["Total costs associated with the Feb Storm (2023-24)",32.74266937871262]
["Materiality of the pass through ",4.981811459408194E-2]
[]
[]
["Table 5: Inputs to PTRM ($2021)"]
[null,"2023-24"]
["Distribution system assets Capex",8187279.1451074984]
["Feb 2024 storm incremental Opex",24555390.23360512]
[]
[]
["Table 6: Eligible pass through amount ($m $ Jun 2021, unsmoothed)"]
["$ Jun 2021","2021-22","2022-23","2023-24","2024-25","2025-26","Total"]
["Return on capital ",0,0,0,0.39530082373207165,0.32609447805873515,0.7213953017908068]
["Return of capital",0,0,0,3.3033930484407392E-3,6.5569307314490288E-3,9.860323779889768E-3]
["Operating expenditure ",0,0,24.555390233605095,0,0,24.555390233605095]
["Revenue adjustments ",0,0,0,0,0,0]
["Tax",0,0,0,0,0,0]
["Building block revenue ",0,0,24.555390233605067,0.39860421678054081,0.33265140879007049,25.286645859175678]
[]
[]
["Table 7: Revenue recovery ($m $ Jun 2021, smoothed)"]
["$ Jun 2021","2021-22","2022-23","2023-24","2024-25","2025-26","Total"]
["Smoothed revenue ",0,0,0,0,26.500431283530816,26.500431283530816]
[]
[]
["Table 8: Revenue per customer analysis"]
[null,"2021-22","2022-23","2023-24","2024-25","2025-26","% change from 2024-25"]
["Customer numbers",797843,811200,825529.97957709583,840148.73841859656,855099.20210268628]
["Revenue"]
["Current PTRM (including VEBM)",669.65829325779146,736.97297756797911,662.90048235634777,665.6942030118322,670.30357648403105,6.9241604498648844E-3]
[" Revenue +100% storm recovery in 2025-26 ",null,null,null,null,696.80400776756187,4.6732876168934755E-2]
[" Revenue +50% recovery in 2025-26 ",null,null,null,null,683.55379212579646,2.6828518309399821E-2]
[" Revenue +33% recovery in 2025-26 ",null,null,null,null,679.13705357854133,2.019373235622151E-2]
["Revenue per customer"]
["Current PTRM (including VEBM)",839.33592606288641,908.4972603155561,802.99988947214217,792.35279727356567,783.88983972357437,-1.0680794690334642E-2]
[" Revenue +100% storm recovery in 2025-26 ",null,null,null,null,814.88090043134525,2.8431909668644218E-2]
[" Revenue +50% recovery in 2025-26 ",null,null,null,null,799.38537007745981,8.8755574891547871E-3]
[" Revenue +33% recovery in 2025-26 ",null,null,null,null,794.22019329283125,2.3567734293248816E-3]
[]
["Graph data","2021-22","2022-23","2023-24","2024-25","2025-26"]
["Current PTRM (including VEBM)",839.33592606288641,908.4972603155561,802.99988947214217,792.35279727356567,783.88983972357437]
[" Revenue +100% storm recovery in 2025-26 ",null,null,null,null,15.495530353885442]
[" Revenue +50% recovery in 2025-26 ",null,null,null,null,5.1651767846285566]
[" Revenue +33% recovery in 2025-26 ",null,null,null,null,10.330353569256886]

{"sheet":"HX-0014297 - 4012895","index":2,"n_rows":134,"n_cols":27,"rows_kept":134,"cut":false,"hidden":true,"merged":[]}
[null,null,null,null,null,null,null,null,null,null,null,"Variance",{"$f":"M134-M2","v":{"$error":"#REF!"}},{"$f":"N134-N2","v":{"$error":"#REF!"}},{"$f":"O134-O2","v":{"$error":"#REF!"}}]
[null,null,null,null,null,null,null,null,null,null,null,"Per SAP",{"$f":"#REF!","v":{"$error":"#REF!"}},{"$f":"#REF!","v":{"$error":"#REF!"}},{"$f":"#REF!","v":{"$error":"#REF!"}}]
["","","","","","","","","","","","","Actual (00/10)","Actual (00/10)","Actual (00/10)","Actual (00/10)"]
["","","","","","","","","","","","Fiscal year/period","2 2025","3 2025","4 2025","Overall Result"]
["WBS Workcode",null,"WBS Element",null,"Network.","Network Activity","Cost Element",null,"Value category","Profit Centre",null,"Hierarchy Area","AUD","AUD","AUD","AUD",null,null,"Coding",null,null,"Row Labels",null,"TX","Total","DX (Assumption)"]
["9999","INTERNAL COST CAPTURE","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","4012895","0010","1000/506401","S&W Proj - NT Adj","Labour Costs","1000/12014","EGM Network Operatio","NO",9421.85,62276.25,35000,106698.1,null,null,{"$f":"VLOOKUP(F6,$V$5:$W$20,2,FALSE)","v":0},null,null,"0010"]
["9999","INTERNAL COST CAPTURE","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","4012895","0010","1000/810100","Dxn Controller NT","Labour Costs","1000/12014","EGM Network Operatio","NO",5525.45,null,null,5525.45,null,null,{"$f":"VLOOKUP(F7,$V$5:$W$20,2,FALSE)","v":0},null,null,"0020","Transmission Labour",{"$f":"SUMIF($F$6:$F$133,$V7,$P$6:$P$133)","v":28562.43},{"$f":"SUMIF($I$6:$I$133,$AA7,$P$6:$P$133)","v":897733.48999999941},{"$f":"Y7-X7","v":869171.05999999936},"Labour Costs"]
["9999","INTERNAL COST CAPTURE","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","4012895","0010","1000/810115","Asset Assesor NT","Labour Costs","1000/12014","EGM Network Operatio","NO",3750.69,null,null,3750.69,null,null,0,null,null,"0030"]
["9999","INTERNAL COST CAPTURE","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","4012895","0010","1000/810118","Project Manager NT","Labour Costs","1000/12014","EGM Network Operatio","NO",876.28,3019.44,null,3895.72,null,null,0,null,null,"0040"]
["9999","INTERNAL COST CAPTURE","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","4012895","0010","1000/810120","Corp Ops Lead NT","Labour Costs","1000/12014","EGM Network Operatio","NO",31068.14,4854.34,null,35922.480000000003,null,null,0,null,null,"0050","Transmission Other",{"$f":"SUMIF($F$6:$F$133,$V10,$P$6:$P$133)","v":63072.86},{"$f":"Y21-Y7","v":1127616.0300000007},{"$f":"Y10-X10","v":1064543.1700000006}]
["9999","INTERNAL COST CAPTURE","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","4012895","0010","1000/810122","Corp Prof Exp NT","Labour Costs","1000/12014","EGM Network Operatio","NO",22064.58,9462.6,null,31527.18,null,null,0,null,null,"0060"]
["9999","INTERNAL COST CAPTURE","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","4012895","0010","1000/810123","Corp Prof NT","Labour Costs","1000/12014","EGM Network Operatio","NO",5702.34,5312.49,null,11014.83,null,null,0,null,null,"0070"]
["9999","INTERNAL COST CAPTURE","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","4012895","0010","1000/810124","Corp Prof Spec NT","Labour Costs","1000/12014","EGM Network Operatio","NO",16052.17,12129.8,null,28181.97,null,null,0,null,null,"0080"]
["9999","INTERNAL COST CAPTURE","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","4012895","0010","1000/810132","Asset Inspector NT","Labour Costs","1000/12014","EGM Network Operatio","NO",9769.4699999999993,null,null,9769.4699999999993,null,null,0,null,null,"0100"]
["9999","INTERNAL COST CAPTURE","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","4012895","0010","1000/810136","Corp Semi Prof NT","Labour Costs","1000/12014","EGM Network Operatio","NO",16203.04,6726.23,null,22929.27,null,null,0,null,null,"0110"]
["9999","INTERNAL COST CAPTURE","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","4012895","0010","1000/810137","Access Coor NT","Labour Costs","1000/12014","EGM Network Operatio","NO",2825.95,812.01,null,3637.96,null,null,0,null,null,"0120"]
["9999","INTERNAL COST CAPTURE","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","4012895","0010","1000/810141","Corp Snr Mngr NT","Labour Costs","1000/12014","EGM Network Operatio","NO",8060,10925.95,null,18985.95,null,null,0,null,null,"0130"]
["9999","INTERNAL COST CAPTURE","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","4012895","0010","1000/810142","Corp Strat Mngr NT","Labour Costs","1000/12014","EGM Network Operatio","NO",1577.97,null,null,1577.97,null,null,0,null,null,"0150"]
["9999","INTERNAL COST CAPTURE","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","4012895","0010","1000/810143","Corp Support NT","Labour Costs","1000/12014","EGM Network Operatio","NO",8883.94,992.34,null,9876.2800000000007,null,null,0,null,null,"0140"]
["9999","INTERNAL COST CAPTURE","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","4012895","0010","1000/810155","Project Snr Eng NT","Labour Costs","1000/12014","EGM Network Operatio","NO",3035.11,null,null,3035.11,null,null,0,null,null,"0160"]
["9999","INTERNAL COST CAPTURE","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","4012895","0010","1000/810160","Corp Manager NT","Labour Costs","1000/12014","EGM Network Operatio","NO",32813.56,35423.879999999997,null,68237.440000000002,null,null,0,null,null,"Grand Total",null,{"$f":"SUM(X7:X20)","v":91635.290000000008},{"$f":"P134","v":2025349.52},{"$f":"SUM(Z7:Z20)","v":1933714.23}]
["9999","INTERNAL COST CAPTURE","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","4012895","0010","1000/810200","Dxn Controller OT","Labour Costs","1000/12014","EGM Network Operatio","NO",6163.08,2550.2399999999998,null,8713.32,null,null,0]
["9999","INTERNAL COST CAPTURE","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","4012895","0010","1000/810215","Asset Assesor OT","Labour Costs","1000/12014","EGM Network Operatio","NO",5700.54,null,null,5700.54,null,null,0]
["9999","INTERNAL COST CAPTURE","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","4012895","0010","1000/810218","Project Manager OT","Labour Costs","1000/12014","EGM Network Operatio","NO",2032.38,null,null,2032.38,null,null,0]
["9999","INTERNAL COST CAPTURE","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","4012895","0010","1000/810220","Corp Ops Lead OT","Labour Costs","1000/12014","EGM Network Operatio","NO",45136.88,5355.4,156.08000000000001,50648.36,null,null,0]
["9999","INTERNAL COST CAPTURE","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","4012895","0010","1000/810222","Corp Prof Exp OT","Labour Costs","1000/12014","EGM Network Operatio","NO",28232.799999999999,7370.4,null,35603.199999999997,null,null,0]
["9999","INTERNAL COST CAPTURE","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","4012895","0010","1000/810223","Corp Prof OT","Labour Costs","1000/12014","EGM Network Operatio","NO",3611.47,12452.47,897.05,16960.990000000002,null,null,0]
["9999","INTERNAL COST CAPTURE","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","4012895","0010","1000/810224","Corp Prof Spec OT","Labour Costs","1000/12014","EGM Network Operatio","NO",22207.9,4907.7700000000004,null,27115.67,null,null,0]
["9999","INTERNAL COST CAPTURE","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","4012895","0010","1000/810232","Asset Inspector OT","Labour Costs","1000/12014","EGM Network Operatio","NO",5554.44,null,null,5554.44,null,null,0]
["9999","INTERNAL COST CAPTURE","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","4012895","0010","1000/810236","Corp Semi Prof OT","Labour Costs","1000/12014","EGM Network Operatio","NO",28550.47,1207.8699999999999,null,29758.34,null,null,0]
["9999","INTERNAL COST CAPTURE","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","4012895","0010","1000/810237","Access Coor OT","Labour Costs","1000/12014","EGM Network Operatio","NO",1370.85,null,null,1370.85,null,null,0]
["9999","INTERNAL COST CAPTURE","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","4012895","0010","1000/810240","Work Planner OT","Labour Costs","1000/12014","EGM Network Operatio","NO",849.25,308.82,null,1158.07,null,null,0]
["9999","INTERNAL COST CAPTURE","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","4012895","0010","1000/810241","Corp Snr Mngr OT","Labour Costs","1000/12014","EGM Network Operatio","NO",22641.14,11495.71,null,34136.85,null,null,0]
["9999","INTERNAL COST CAPTURE","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","4012895","0010","1000/810243","Corp Support OT","Labour Costs","1000/12014","EGM Network Operatio","NO",13554.08,null,null,13554.08,null,null,0]
["9999","INTERNAL COST CAPTURE","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","4012895","0010","1000/810255","Project Snr Eng OT","Labour Costs","1000/12014","EGM Network Operatio","NO",1814.29,null,null,1814.29,null,null,0]
["9999","INTERNAL COST CAPTURE","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","4012895","0010","1000/810260","Corp Manager OT","Labour Costs","1000/12014","EGM Network Operatio","NO",33377.879999999997,33809.379999999997,null,67187.259999999995,null,null,0]
["9999","INTERNAL COST CAPTURE","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","4012895","0010","1000/516413","Light Meals on Site","Other Costs","1000/12014","EGM Network Operatio","NO",null,null,972.13,972.13,null,null,0]
["9999","INTERNAL COST CAPTURE","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","4012895","0020","1000/506401","S&W Proj - NT Adj","Labour Costs","1000/12014","EGM Network Operatio","NO",367.57,11.7,null,379.27,null,null,"Transmission Labour"]
["9999","INTERNAL COST CAPTURE","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","4012895","0020","1000/810115","Asset Assesor NT","Labour Costs","1000/12014","EGM Network Operatio","NO",4586.76,372,null,4958.76,null,null,"Transmission Labour"]
["9999","INTERNAL COST CAPTURE","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","4012895","0020","1000/810118","Project Manager NT","Labour Costs","1000/12014","EGM Network Operatio","NO",738.1,null,null,738.1,null,null,"Transmission Labour"]
["9999","INTERNAL COST CAPTURE","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","4012895","0020","1000/810120","Corp Ops Lead NT","Labour Costs","1000/12014","EGM Network Operatio","NO",0,1066.1199999999999,null,1066.1199999999999,null,null,"Transmission Labour"]
["9999","INTERNAL COST CAPTURE","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","4012895","0020","1000/810141","Corp Snr Mngr NT","Labour Costs","1000/12014","EGM Network Operatio","NO",3940.43,1343.33,null,5283.76,null,null,"Transmission Labour"]
["9999","INTERNAL COST CAPTURE","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","4012895","0020","1000/810202","Txn Controller OT","Labour Costs","1000/12014","EGM Network Operatio","NO",10842.98,null,null,10842.98,null,null,"Transmission Labour"]
["9999","INTERNAL COST CAPTURE","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","4012895","0020","1000/810260","Corp Manager OT","Labour Costs","1000/12014","EGM Network Operatio","NO",5293.44,0,null,5293.44,null,null,"Transmission Labour"]
["9999","INTERNAL COST CAPTURE","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","4012895","0030","1000/506401","S&W Proj - NT Adj","Labour Costs","1000/12014","EGM Network Operatio","NO",341.84,10.88,null,352.72,null,null,0]
["9999","INTERNAL COST CAPTURE","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","4012895","0030","1000/810120","Corp Ops Lead NT","Labour Costs","1000/12014","EGM Network Operatio","NO",null,206.44,null,206.44,null,null,0]
["9999","INTERNAL COST CAPTURE","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","4012895","0030","1000/810124","Corp Prof Spec NT","Labour Costs","1000/12014","EGM Network Operatio","NO",3622.7,null,null,3622.7,null,null,0]
["9999","INTERNAL COST CAPTURE","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","4012895","0030","1000/810136","Corp Semi Prof NT","Labour Costs","1000/12014","EGM Network Operatio","NO",357.88,null,null,357.88,null,null,0]
["9999","INTERNAL COST CAPTURE","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","4012895","0030","1000/810143","Corp Support NT","Labour Costs","1000/12014","EGM Network Operatio","NO",2015.16,null,null,2015.16,null,null,0]
["9999","INTERNAL COST CAPTURE","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","4012895","0030","1000/810243","Corp Support OT","Labour Costs","1000/12014","EGM Network Operatio","NO",631.79999999999995,null,null,631.79999999999995,null,null,0]
["9999","INTERNAL COST CAPTURE","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","4012895","0030","1000/506500","Cont Lab Non-Payroll","Labour - Non-Payroll Costs","1000/12014","EGM Network Operatio","NO",null,177483.64,null,177483.64,null,null,0]
["9999","INTERNAL COST CAPTURE","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","4012895","0030","1000/511202","Maintenance - Asset","Maintenance other","1000/12014","EGM Network Operatio","NO",null,71145.350000000006,null,71145.350000000006,null,null,0]
["9999","INTERNAL COST CAPTURE","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","4012895","0030","1000/516202","H & S certification","Other Costs","1000/12014","EGM Network Operatio","NO",31.5,null,null,31.5,null,null,0]
["9999","INTERNAL COST CAPTURE","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","4012895","0040","1000/506401","S&W Proj - NT Adj","Labour Costs","1000/12014","EGM Network Operatio","NO",268.32,8.5399999999999991,null,276.86,null,null,0]
["9999","INTERNAL COST CAPTURE","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","4012895","0040","1000/810123","Corp Prof NT","Labour Costs","1000/12014","EGM Network Operatio","NO",1765.76,null,null,1765.76,null,null,0]
["9999","INTERNAL COST CAPTURE","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","4012895","0040","1000/810132","Asset Inspector NT","Labour Costs","1000/12014","EGM Network Operatio","NO",2032.34,null,null,2032.34,null,null,0]
["9999","INTERNAL COST CAPTURE","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","4012895","0040","1000/810143","Corp Support NT","Labour Costs","1000/12014","EGM Network Operatio","NO",372.55,null,null,372.55,null,null,0]
["9999","INTERNAL COST CAPTURE","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","4012895","0040","1000/810232","Asset Inspector OT","Labour Costs","1000/12014","EGM Network Operatio","NO",308.58,null,null,308.58,null,null,0]
["9999","INTERNAL COST CAPTURE","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","4012895","0040","1000/810237","Access Coor OT","Labour Costs","1000/12014","EGM Network Operatio","NO",4499.2,null,null,4499.2,null,null,0]
["9999","INTERNAL COST CAPTURE","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","4012895","0040","1000/506500","Cont Lab Non-Payroll","Labour - Non-Payroll Costs","1000/12014","EGM Network Operatio","NO",null,28207,null,28207,null,null,0]
["9999","INTERNAL COST CAPTURE","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","4012895","0040","1000/511100","Svc Prov - Contracts","External Maintenance","1000/12014","EGM Network Operatio","NO",98183.35,-98183.35,null,0,null,null,0]
["9999","INTERNAL COST CAPTURE","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","4012895","0040","1000/511202","Maintenance - Asset","Maintenance other","1000/12014","EGM Network Operatio","NO",null,29690.73,null,29690.73,null,null,0]
["9999","INTERNAL COST CAPTURE","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","4012895","0040","1000/521521","Maint - security cos","Maintenance other","1000/12014","EGM Network Operatio","NO",28125,780.45,54493.74,83399.19,null,null,0]
["9999","INTERNAL COST CAPTURE","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","4012895","0040","1000/521100","Materials","Material Costs","1000/12014","EGM Network Operatio","NO",34011.089999999997,145578.34,164290.65,343880.08,null,null,0]
["9999","INTERNAL COST CAPTURE","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","4012895","0040","1000/521406","Hire - Plant & Equip","Other Costs","1000/12014","EGM Network Operatio","NO",null,85849.62,null,85849.62,null,null,0]
["9999","INTERNAL COST CAPTURE","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","4012895","0040","1000/521505","Vehicle Parking","Other Costs","1000/12014","EGM Network Operatio","NO",null,655.7,null,655.7,null,null,0]
["9999","INTERNAL COST CAPTURE","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","4012895","0040","1000/521506","Transportation","Other Costs","1000/12014","EGM Network Operatio","NO",324.48,66.31,null,390.79,null,null,0]
["9999","INTERNAL COST CAPTURE","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","4012895","0040","1000/521508","Accommodation","Other Costs","1000/12014","EGM Network Operatio","NO",null,232.14,386.83,618.97,null,null,0]
["9999","INTERNAL COST CAPTURE","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","4012895","0040","1000/516401","Office Expenses","Other Costs","1000/12014","EGM Network Operatio","NO",null,null,450.68,450.68,null,null,0]
["9999","INTERNAL COST CAPTURE","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","4012895","0040","1000/516413","Light Meals on Site","Other Costs","1000/12014","EGM Network Operatio","NO",null,28858.06,null,28858.06,null,null,0]
["9999","INTERNAL COST CAPTURE","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","4012895","0040","1000/516416","Entertmnt - Meals","Other Costs","1000/12014","EGM Network Operatio","NO",null,37.54,10.45,47.99,null,null,{"$f":"VLOOKUP(F71,$V$5:$W$20,2,FALSE)","v":0}]
["9999","INTERNAL COST CAPTURE","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","4012895","0050","1000/506401","S&W Proj - NT Adj","Labour Costs","1000/12014","EGM Network Operatio","NO",503.54,16.03,null,519.57000000000005,null,null,"Transmission Other"]
["9999","INTERNAL COST CAPTURE","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","4012895","0050","1000/810136","Corp Semi Prof NT","Labour Costs","1000/12014","EGM Network Operatio","NO",2235.87,null,null,2235.87,null,null,"Transmission Other"]
["9999","INTERNAL COST CAPTURE","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","4012895","0050","1000/810236","Corp Semi Prof OT","Labour Costs","1000/12014","EGM Network Operatio","NO",5614.96,null,null,5614.96,null,null,"Transmission Other"]
["9999","INTERNAL COST CAPTURE","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","4012895","0050","1000/511100","Svc Prov - Contracts","External Maintenance","1000/12014","EGM Network Operatio","NO",23029,-23029,null,0,null,null,"Transmission Other"]
["9999","INTERNAL COST CAPTURE","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","4012895","0050","1000/511202","Maintenance - Asset","Maintenance other","1000/12014","EGM Network Operatio","NO",null,27732.6,null,27732.6,null,null,"Transmission Other"]
["9999","INTERNAL COST CAPTURE","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","4012895","0050","1000/521521","Maint - security cos","Maintenance other","1000/12014","EGM Network Operatio","NO",null,null,26908.14,26908.14,null,null,"Transmission Other"]
["9999","INTERNAL COST CAPTURE","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","4012895","0050","1000/521506","Transportation","Other Costs","1000/12014","EGM Network Operatio","NO",null,61.72,null,61.72,null,null,"Transmission Other"]
["9999","INTERNAL COST CAPTURE","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","4012895","0060","1000/516101","IT Software","Other Costs","1000/12014","EGM Network Operatio","NO",null,72080,null,72080,null,null,0]
["9999","INTERNAL COST CAPTURE","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","4012895","0060","1000/521506","Transportation","Other Costs","1000/12014","EGM Network Operatio","NO",99.27,null,null,99.27,null,null,0]
["9999","INTERNAL COST CAPTURE","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","4012895","0060","1000/516401","Office Expenses","Other Costs","1000/12014","EGM Network Operatio","NO",null,35.64,null,35.64,null,null,0]
["9999","INTERNAL COST CAPTURE","HX-0014297-2","Feb24 Storm Costs dNet PC 12001","4012895","0070","1000/506401","S&W Proj - NT Adj","Labour Costs","1000/12014","EGM Network Operatio","NO",19155,null,null,19155,null,null,0]
["9999","INTERNAL COST CAPTURE","HX-0014297-2","Feb24 Storm Costs dNet PC 12001","4012895","0070","1000/810122","Corp Prof Exp NT","Labour Costs","1000/12014","EGM Network Operatio","NO",969.98,-697.88,544.20000000000005,816.3,null,null,0]
["9999","INTERNAL COST CAPTURE","HX-0014297-2","Feb24 Storm Costs dNet PC 12001","4012895","0070","1000/810124","Corp Prof Spec NT","Labour Costs","1000/12014","EGM Network Operatio","NO",4696.22,null,null,4696.22,null,null,0]
["9999","INTERNAL COST CAPTURE","HX-0014297-2","Feb24 Storm Costs dNet PC 12001","4012895","0070","1000/810141","Corp Snr Mngr NT","Labour Costs","1000/12014","EGM Network Operatio","NO",null,5373.44,null,5373.44,null,null,0]
["9999","INTERNAL COST CAPTURE","HX-0014297-2","Feb24 Storm Costs dNet PC 12001","4012895","0070","1000/810160","Corp Manager NT","Labour Costs","1000/12014","EGM Network Operatio","NO",null,5734.55,null,5734.55,null,null,0]
["9999","INTERNAL COST CAPTURE","HX-0014297-2","Feb24 Storm Costs dNet PC 12001","4012895","0070","1000/810222","Corp Prof Exp OT","Labour Costs","1000/12014","EGM Network Operatio","NO",null,2052.16,null,2052.16,null,null,0]
["9999","INTERNAL COST CAPTURE","HX-0014297-2","Feb24 Storm Costs dNet PC 12001","4012895","0070","1000/516106","IT Outsource Service","Other Costs","1000/12014","EGM Network Operatio","NO",36686.85,null,null,36686.85,null,null,0]
["9999","INTERNAL COST CAPTURE","HX-0014297-2","Feb24 Storm Costs dNet PC 12001","4012895","0080","1000/516101","IT Software","Other Costs","1000/12014","EGM Network Operatio","NO",null,94080,null,94080,null,null,0]
["9999","INTERNAL COST CAPTURE","HX-0014297-2","Feb24 Storm Costs dNet PC 12001","4012895","0080","1000/516204","Professional Fees","Other Costs","1000/12014","EGM Network Operatio","NO",null,null,15000,15000,null,null,0]
["9999","INTERNAL COST CAPTURE","HX-0014297-2","Feb24 Storm Costs dNet PC 12001","4012895","0080","1000/521506","Transportation","Other Costs","1000/12014","EGM Network Operatio","NO",55.03,null,null,55.03,null,null,0]
["9999","INTERNAL COST CAPTURE","HX-0014297-3","Feb24 Storm Costs F&G PC 12516","4012895","0100","1000/506401","S&W Proj - NT Adj","Labour Costs","1000/12014","EGM Network Operatio","NO",297.74,9.48,null,307.22000000000003,null,null,0]
["9999","INTERNAL COST CAPTURE","HX-0014297-3","Feb24 Storm Costs F&G PC 12516","4012895","0100","1000/810132","Asset Inspector NT","Labour Costs","1000/12014","EGM Network Operatio","NO",1140.96,null,null,1140.96,null,null,0]
["9999","INTERNAL COST CAPTURE","HX-0014297-3","Feb24 Storm Costs F&G PC 12516","4012895","0100","1000/810136","Corp Semi Prof NT","Labour Costs","1000/12014","EGM Network Operatio","NO",711.96,null,null,711.96,null,null,0]
["9999","INTERNAL COST CAPTURE","HX-0014297-3","Feb24 Storm Costs F&G PC 12516","4012895","0100","1000/810232","Asset Inspector OT","Labour Costs","1000/12014","EGM Network Operatio","NO",1234.32,null,null,1234.32,null,null,0]
["9999","INTERNAL COST CAPTURE","HX-0014297-3","Feb24 Storm Costs F&G PC 12516","4012895","0100","1000/810236","Corp Semi Prof OT","Labour Costs","1000/12014","EGM Network Operatio","NO",1613.13,null,null,1613.13,null,null,0]
["9999","INTERNAL COST CAPTURE","HX-0014297-3","Feb24 Storm Costs F&G PC 12516","4012895","0100","1000/810260","Corp Manager OT","Labour Costs","1000/12014","EGM Network Operatio","NO",946.76,0,null,946.76,null,null,0]
["9999","INTERNAL COST CAPTURE","HX-0014297-3","Feb24 Storm Costs F&G PC 12516","4012895","0100","1000/521506","Transportation","Other Costs","1000/12014","EGM Network Operatio","NO",153.72,45.19,null,198.91,null,null,0]
["9999","INTERNAL COST CAPTURE","HX-0014297-4","Feb24 Storm Costs SR&CA PC 12006","4012895","0110","1000/506307","S&W - Adj","Labour Costs","1000/12014","EGM Network Operatio","NO",null,7616.34,null,7616.34,null,null,0]
["9999","INTERNAL COST CAPTURE","HX-0014297-4","Feb24 Storm Costs SR&CA PC 12006","4012895","0110","1000/506401","S&W Proj - NT Adj","Labour Costs","1000/12014","EGM Network Operatio","NO",66.150000000000006,2.11,null,68.260000000000005,null,null,0]
["9999","INTERNAL COST CAPTURE","HX-0014297-4","Feb24 Storm Costs SR&CA PC 12006","4012895","0110","1000/810120","Corp Ops Lead NT","Labour Costs","1000/12014","EGM Network Operatio","NO",null,5472.94,null,5472.94,null,null,0]
["9999","INTERNAL COST CAPTURE","HX-0014297-4","Feb24 Storm Costs SR&CA PC 12006","4012895","0110","1000/810122","Corp Prof Exp NT","Labour Costs","1000/12014","EGM Network Operatio","NO",null,8730.48,null,8730.48,null,null,0]
["9999","INTERNAL COST CAPTURE","HX-0014297-4","Feb24 Storm Costs SR&CA PC 12006","4012895","0110","1000/810136","Corp Semi Prof NT","Labour Costs","1000/12014","EGM Network Operatio","NO",759.44,9018.5499999999993,null,9777.99,null,null,0]
["9999","INTERNAL COST CAPTURE","HX-0014297-4","Feb24 Storm Costs SR&CA PC 12006","4012895","0110","1000/810143","Corp Support NT","Labour Costs","1000/12014","EGM Network Operatio","NO",null,5711.14,null,5711.14,null,null,0]
["9999","INTERNAL COST CAPTURE","HX-0014297-4","Feb24 Storm Costs SR&CA PC 12006","4012895","0110","1000/810160","Corp Manager NT","Labour Costs","1000/12014","EGM Network Operatio","NO",9098.74,0,null,9098.74,null,null,0]
["9999","INTERNAL COST CAPTURE","HX-0014297-4","Feb24 Storm Costs SR&CA PC 12006","4012895","0110","1000/810220","Corp Ops Lead OT","Labour Costs","1000/12014","EGM Network Operatio","NO",156.08000000000001,5993.38,null,6149.46,null,null,0]
["9999","INTERNAL COST CAPTURE","HX-0014297-4","Feb24 Storm Costs SR&CA PC 12006","4012895","0110","1000/810222","Corp Prof Exp OT","Labour Costs","1000/12014","EGM Network Operatio","NO",null,8301.92,null,8301.92,null,null,0]
["9999","INTERNAL COST CAPTURE","HX-0014297-4","Feb24 Storm Costs SR&CA PC 12006","4012895","0110","1000/810223","Corp Prof OT","Labour Costs","1000/12014","EGM Network Operatio","NO",null,3873.63,null,3873.63,null,null,0]
["9999","INTERNAL COST CAPTURE","HX-0014297-4","Feb24 Storm Costs SR&CA PC 12006","4012895","0110","1000/810236","Corp Semi Prof OT","Labour Costs","1000/12014","EGM Network Operatio","NO",null,3674.94,null,3674.94,null,null,0]
["9999","INTERNAL COST CAPTURE","HX-0014297-4","Feb24 Storm Costs SR&CA PC 12006","4012895","0110","1000/810237","Access Coor OT","Labour Costs","1000/12014","EGM Network Operatio","NO",2976.5,null,null,2976.5,null,null,0]
["9999","INTERNAL COST CAPTURE","HX-0014297-4","Feb24 Storm Costs SR&CA PC 12006","4012895","0110","1000/810243","Corp Support OT","Labour Costs","1000/12014","EGM Network Operatio","NO",null,5507.59,null,5507.59,null,null,0]
["9999","INTERNAL COST CAPTURE","HX-0014297-4","Feb24 Storm Costs SR&CA PC 12006","4012895","0110","1000/810260","Corp Manager OT","Labour Costs","1000/12014","EGM Network Operatio","NO",16762.560000000001,0,null,16762.560000000001,null,null,0]
["9999","INTERNAL COST CAPTURE","HX-0014297-4","Feb24 Storm Costs SR&CA PC 12006","4012895","0120","1000/810260","Corp Manager OT","Labour Costs","1000/12014","EGM Network Operatio","NO",330.84,0,null,330.84,null,null,0]
["9999","INTERNAL COST CAPTURE","HX-0014297-4","Feb24 Storm Costs SR&CA PC 12006","4012895","0120","1000/521506","Transportation","Other Costs","1000/12014","EGM Network Operatio","NO",null,129.93,null,129.93,null,null,0]
["9999","INTERNAL COST CAPTURE","HX-0014297-4","Feb24 Storm Costs SR&CA PC 12006","4012895","0120","1000/521508","Accommodation","Other Costs","1000/12014","EGM Network Operatio","NO",null,122.48,null,122.48,null,null,0]
["9999","INTERNAL COST CAPTURE","HX-0014297-5","Feb24 Storm Costs People PC 12306","4012895","0130","1000/810120","Corp Ops Lead NT","Labour Costs","1000/12014","EGM Network Operatio","NO",null,2242.4899999999998,null,2242.4899999999998,null,null,0]
["9999","INTERNAL COST CAPTURE","HX-0014297-5","Feb24 Storm Costs People PC 12306","4012895","0130","1000/810123","Corp Prof NT","Labour Costs","1000/12014","EGM Network Operatio","NO",null,2252.9699999999998,null,2252.9699999999998,null,null,0]
["9999","INTERNAL COST CAPTURE","HX-0014297-5","Feb24 Storm Costs People PC 12306","4012895","0130","1000/810136","Corp Semi Prof NT","Labour Costs","1000/12014","EGM Network Operatio","NO",null,712,null,712,null,null,0]
["9999","INTERNAL COST CAPTURE","HX-0014297-5","Feb24 Storm Costs People PC 12306","4012895","0130","1000/810143","Corp Support NT","Labour Costs","1000/12014","EGM Network Operatio","NO",1676.49,null,null,1676.49,null,null,0]
["9999","INTERNAL COST CAPTURE","HX-0014297-5","Feb24 Storm Costs People PC 12306","4012895","0130","1000/810220","Corp Ops Lead OT","Labour Costs","1000/12014","EGM Network Operatio","NO",null,2055.5700000000002,null,2055.5700000000002,null,null,0]
["9999","INTERNAL COST CAPTURE","HX-0014297-5","Feb24 Storm Costs People PC 12306","4012895","0130","1000/810236","Corp Semi Prof OT","Labour Costs","1000/12014","EGM Network Operatio","NO",null,410.76,null,410.76,null,null,0]
["9999","INTERNAL COST CAPTURE","HX-0014297-5","Feb24 Storm Costs People PC 12306","4012895","0130","1000/810243","Corp Support OT","Labour Costs","1000/12014","EGM Network Operatio","NO",4271.55,null,null,4271.55,null,null,0]
["9999","INTERNAL COST CAPTURE","HX-0014297-5","Feb24 Storm Costs People PC 12306","4012895","0140","1000/521100","Materials","Material Costs","1000/12014","EGM Network Operatio","NO",null,416,null,416,null,null,0]
["9999","INTERNAL COST CAPTURE","HX-0014297-5","Feb24 Storm Costs People PC 12306","4012895","0140","1000/516401","Office Expenses","Other Costs","1000/12014","EGM Network Operatio","NO",null,1362.27,null,1362.27,null,null,0]
["9999","INTERNAL COST CAPTURE","HX-0014297-6","Feb24 Storm Costs DFN PC 12388","4012895","0150","1000/810136","Corp Semi Prof NT","Labour Costs","1000/12014","EGM Network Operatio","NO",2684.18,null,null,2684.18,null,null,0]
["9999","INTERNAL COST CAPTURE","HX-0014297-6","Feb24 Storm Costs DFN PC 12388","4012895","0150","1000/810141","Corp Snr Mngr NT","Labour Costs","1000/12014","EGM Network Operatio","NO",537.33000000000004,null,null,537.33000000000004,null,null,0]
["9999","INTERNAL COST CAPTURE","HX-0014297-6","Feb24 Storm Costs DFN PC 12388","4012895","0150","1000/810160","Corp Manager NT","Labour Costs","1000/12014","EGM Network Operatio","NO",null,3528.15,null,3528.15,null,null,0]
["9999","INTERNAL COST CAPTURE","HX-0014297-6","Feb24 Storm Costs DFN PC 12388","4012895","0150","1000/810224","Corp Prof Spec OT","Labour Costs","1000/12014","EGM Network Operatio","NO",10085.58,null,null,10085.58,null,null,0]
["9999","INTERNAL COST CAPTURE","HX-0014297-6","Feb24 Storm Costs DFN PC 12388","4012895","0150","1000/810236","Corp Semi Prof OT","Labour Costs","1000/12014","EGM Network Operatio","NO",2193.85,1369.2,0,3563.05,null,null,0]
["9999","INTERNAL COST CAPTURE","HX-0014297-6","Feb24 Storm Costs DFN PC 12388","4012895","0150","1000/810241","Corp Snr Mngr OT","Labour Costs","1000/12014","EGM Network Operatio","NO",2841.64,null,null,2841.64,null,null,0]
["9999","INTERNAL COST CAPTURE","HX-0014297-6","Feb24 Storm Costs DFN PC 12388","4012895","0150","1000/810260","Corp Manager OT","Labour Costs","1000/12014","EGM Network Operatio","NO",null,3787.05,null,3787.05,null,null,0]
["9999","INTERNAL COST CAPTURE","HX-0014297-6","Feb24 Storm Costs DFN PC 12388","4012895","0160","1000/521505","Vehicle Parking","Other Costs","1000/12014","EGM Network Operatio","NO",null,68.180000000000007,null,68.180000000000007,null,null,0]
["9999","INTERNAL COST CAPTURE","HX-0014297-6","Feb24 Storm Costs DFN PC 12388","4012895","0160","1000/521508","Accommodation","Other Costs","1000/12014","EGM Network Operatio","NO",null,897.58,null,897.58,null,null,0]
["Overall Result",null,null,null,null,null,null,null,null,null,null,null,754674.06,971565.51,299109.95,2025349.52]

{"sheet":"TS to NW 4012895","index":3,"n_rows":917,"n_cols":39,"rows_kept":917,"cut":false,"hidden":true,"merged":[]}
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Labour Costs per Project",null,{"$f":"SUMIF('HX-0014297 - 4012895'!I:I,\"Labour Costs\",'HX-0014297 - 4012895'!P:P)","v":897733.48999999941}]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,{"$f":"SUBTOTAL(9,AB7:AB916)","v":5473.14},224.24,10.5,738354.87000000011,26033.249999999996,1353.46,null,null,"Labour - Non-Payroll Costs per Project",null,{"$f":"SUMIF('HX-0014297 - 4012895'!I:I,\"Labour - Non-Payroll Costs\",'HX-0014297 - 4012895'!P:P)","v":205690.64}]
["Employee","Employee Name","Cost Center","Cost Center Desc","Work Date","Posting Date","Network Order Number","Nework Order Desc","Network Activity Number","Net Act Desc","NETWORK Number","NOW","Activity Number","Activity Type","Activity Type Desc","Project Number","Project Desc","WBS Element","WBS Element Desc","WC","WC Desc","Project CC","CC Desc","Att/Absence Type","NT/OT","Allowance Type","All Type Desc","Feb-24 Hours","Mar-24 Hours","Apr-24 Hours","Feb-24 Amount","Mar-24 Amount","Apr-24 Amount",null,null,"S&W Proj - NT Adj",null,{"$f":"SUMIF('HX-0014297 - 4012895'!H:H,$AJ$3,'HX-0014297 - 4012895'!P:P)","v":127757.00000000001}]
["","","","","","","","","","","","","","","","","","","","","","","","","","","","ACTUAL QUANTITY","ACTUAL QUANTITY","ACTUAL QUANTITY","ACTUAL AMOUNTS","ACTUAL AMOUNTS","ACTUAL AMOUNTS",null,null,"S&W - Adj",null,{"$f":"SUMIF('HX-0014297 - 4012895'!H:H,$AJ$4,'HX-0014297 - 4012895'!P:P)","v":7616.34}]
["","","","","","","","","","","","","","","","","","","","","","","","","","","Fiscal year/period","2 2025","3 2025","4 2025","2 2025","3 2025","4 2025",null,null,"Labour Costs Excluding Adjustment",null,{"$f":"AL1-AL3-AL4","v":762360.14999999944}]
["Employee",null,"Employee Cost Center",null,"Work Date","Posting Date","Network Order Number",null,"Network Activity Number",null,"Work Order Number",null,"Oper Number for PM","Activity Type",null,"Project Number",null,"WBS Element",null,"Project Work Code",null,"Project Cost Center",null,"Att/Absence Type",null,"Allowance Type","","H","H","H","AUD","AUD","AUD",null,null,"Per TS Report",null,{"$f":"SUM(AE917:AG917)","v":765741.58}]
["10000173","Fiona Pober","1000/16001","Inspection & Assessm","14.02.2024","19.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CSTRAN","1000/CSTRAN","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",6.91,null,null,1577.97,null,null,null,null,"Variance",null,{"$f":"AL5-AL6","v":-3381.4300000005169},{"$f":"AL7-'HX-0014297 - 4012895'!O1","v":{"$error":"#REF!"}}]
["10000174","Julie Warke","1000/13104","Distribution Control","13.02.2024","28.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CSENMO","Corp Snr Mngr OT","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",2.75,null,null,780.75]
["10000174","Julie Warke","1000/13104","Distribution Control","14.02.2024","28.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CSENMO","Corp Snr Mngr OT","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",8.5,null,null,2413.2399999999998,null,null,null,null,"Feb24 Storm Costs NetOps PC 12014",{"$f":"SUMIF(S:S,AJ9,AC:AC)","v":131.07}]
["10000174","Julie Warke","1000/13104","Distribution Control","15.02.2024","28.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CSENMO","Corp Snr Mngr OT","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",8.5,null,null,2413.2399999999998]
["10000174","Julie Warke","1000/13104","Distribution Control","16.02.2024","28.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CSENMO","Corp Snr Mngr OT","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",6,null,null,1703.46]
["10000174","Julie Warke","1000/13104","Distribution Control","17.02.2024","28.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CSENMO","Corp Snr Mngr OT","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",10.25,null,null,2910.08]
["10000174","Julie Warke","1000/13104","Distribution Control","18.02.2024","28.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CSENMO","Corp Snr Mngr OT","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",14,null,null,3974.74]
["10000174","Julie Warke","1000/13104","Distribution Control","22.02.2024","28.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CSENMO","Corp Snr Mngr OT","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",7,null,null,1987.37]
["10000223","Liz Colvin","1000/12018","Mark Data & Mter Ser","23.03.2024","09.04.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CPSRAO","1000/CPSRAO","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",null,5.5,null,null,897.05]
["10000368","Gareth Downes","1000/13723","Cust Prog Cent East","14.02.2024","01.03.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CSENAN","1000/CSENAN","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",8.5,null,null,1343.43]
["10000368","Gareth Downes","1000/13723","Cust Prog Cent East","14.02.2024","01.03.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CSENAO","1000/CSENAO","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",4.5,null,null,1162.49]
["10000368","Gareth Downes","1000/13723","Cust Prog Cent East","15.02.2024","01.03.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CSENAN","1000/CSENAN","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",9.5,null,null,1343.4]
["10000368","Gareth Downes","1000/13723","Cust Prog Cent East","15.02.2024","01.03.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CSENAO","1000/CSENAO","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",4.5,null,null,1162.49]
["10000368","Gareth Downes","1000/13723","Cust Prog Cent East","16.02.2024","01.03.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CSENAN","1000/CSENAN","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",9.5,null,null,1343.4]
["10000368","Gareth Downes","1000/13723","Cust Prog Cent East","16.02.2024","01.03.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CSENAO","1000/CSENAO","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",4.5,null,null,1162.49]
["10000368","Gareth Downes","1000/13723","Cust Prog Cent East","17.02.2024","01.03.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CSENAO","1000/CSENAO","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",13,null,null,3358.29]
["10000368","Gareth Downes","1000/13723","Cust Prog Cent East","18.02.2024","01.03.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CSENAO","1000/CSENAO","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",11.5,null,null,2970.8]
["10000368","Gareth Downes","1000/13723","Cust Prog Cent East","19.02.2024","01.03.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CSENAN","1000/CSENAN","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",9.5,null,null,1343.4]
["10000368","Gareth Downes","1000/13723","Cust Prog Cent East","19.02.2024","01.03.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CSENAO","1000/CSENAO","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",2.5,null,null,645.83000000000004]
["10000368","Gareth Downes","1000/13723","Cust Prog Cent East","20.02.2024","01.03.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CSENAN","1000/CSENAN","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",7.5,null,null,1343.33]
["10000368","Gareth Downes","1000/13723","Cust Prog Cent East","21.02.2024","01.03.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CSENAN","1000/CSENAN","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",4,null,null,716.44]
["10000368","Gareth Downes","1000/13723","Cust Prog Cent East","22.02.2024","01.03.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CSENAN","1000/CSENAN","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",10,null,null,1343.3]
["10000368","Gareth Downes","1000/13723","Cust Prog Cent East","23.02.2024","01.03.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CSENAN","1000/CSENAN","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",4.5,null,null,806]
["10000368","Gareth Downes","1000/13723","Cust Prog Cent East","26.02.2024","01.03.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CSENAN","1000/CSENAN","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",9,null,null,1343.25]
["10000434","Stuart Hanley","1000/11517","Contract Manag Dist","13.02.2024","19.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CMNGAO","1000/CMNGAO","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",1,null,null,220.56]
["10000434","Stuart Hanley","1000/11517","Contract Manag Dist","14.02.2024","19.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CMNGAN","1000/CMNGAN","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",12,null,null,1146.96]
["10000434","Stuart Hanley","1000/11517","Contract Manag Dist","15.02.2024","19.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CMNGAN","1000/CMNGAN","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",11.5,null,null,1146.9000000000001]
["10000434","Stuart Hanley","1000/11517","Contract Manag Dist","16.02.2024","19.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CMNGAN","1000/CMNGAN","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",14,null,null,1146.8800000000001]
["10000434","Stuart Hanley","1000/11517","Contract Manag Dist","18.02.2024","19.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CMNGAO","1000/CMNGAO","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",8,null,null,1764.48]
["10000440","Phil Gay","1000/13263","Transmission Control","14.02.2024","19.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0020","Feb24 Storm Timesheet Tx 12014","4012895","4012895","0020","1000/TCONTO","Txn Controller OT","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",12,null,null,2628.6]
["10000440","Phil Gay","1000/13263","Transmission Control","15.02.2024","19.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0020","Feb24 Storm Timesheet Tx 12014","4012895","4012895","0020","1000/TCONTO","Txn Controller OT","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",12,null,null,2628.6]
["10000449","Katherine O'Brien","1000/13263","Transmission Control","13.02.2024","19.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0020","Feb24 Storm Timesheet Tx 12014","4012895","4012895","0020","1000/TCONTO","Txn Controller OT","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",12,null,null,2628.6]
["10000478","Derek Walton","1000/11517","Contract Manag Dist","13.02.2024","21.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CLEADN","Corp Ops Lead NT","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",4.33,null,null,468.55]
["10000478","Derek Walton","1000/11517","Contract Manag Dist","13.02.2024","21.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CLEADO","Corp Ops Lead OT","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",2.83,null,null,441.71]
["10000478","Derek Walton","1000/11517","Contract Manag Dist","14.02.2024","21.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CLEADN","Corp Ops Lead NT","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",9.5,null,null,901.36]
["10000478","Derek Walton","1000/11517","Contract Manag Dist","14.02.2024","21.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CLEADO","Corp Ops Lead OT","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",2.92,null,null,455.75]
["10000478","Derek Walton","1000/11517","Contract Manag Dist","15.02.2024","21.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CLEADN","Corp Ops Lead NT","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",9.83,null,null,901.41]
["10000478","Derek Walton","1000/11517","Contract Manag Dist","15.02.2024","21.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CLEADO","Corp Ops Lead OT","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",3.5,null,null,546.28]
["10000478","Derek Walton","1000/11517","Contract Manag Dist","16.02.2024","21.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CLEADO","Corp Ops Lead OT","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",10.5,null,null,1638.84]
["10000478","Derek Walton","1000/11517","Contract Manag Dist","17.02.2024","21.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CLEADO","Corp Ops Lead OT","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",6,null,null,936.48]
["10000478","Derek Walton","1000/11517","Contract Manag Dist","18.02.2024","21.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CLEADO","Corp Ops Lead OT","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",3.17,null,null,494.77]
["10000478","Derek Walton","1000/11517","Contract Manag Dist","19.02.2024","23.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CLEADN","Corp Ops Lead NT","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",10.75,null,null,901.39]
["10000478","Derek Walton","1000/11517","Contract Manag Dist","20.02.2024","23.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CLEADN","Corp Ops Lead NT","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",9.75,null,null,901.39]
["10000478","Derek Walton","1000/11517","Contract Manag Dist","21.02.2024","23.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CLEADN","Corp Ops Lead NT","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",10.17,null,null,901.37]
["10000478","Derek Walton","1000/11517","Contract Manag Dist","22.02.2024","23.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CLEADN","Corp Ops Lead NT","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",8.5,null,null,901.43]
["10000478","Derek Walton","1000/11517","Contract Manag Dist","23.02.2024","23.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CLEADN","Corp Ops Lead NT","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",7.42,null,null,802.92]
["10000478","Derek Walton","1000/11517","Contract Manag Dist","26.02.2024","01.03.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CLEADN","Corp Ops Lead NT","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",8.92,null,null,901.46]
["10000478","Derek Walton","1000/11517","Contract Manag Dist","27.02.2024","01.03.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CLEADN","Corp Ops Lead NT","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",4.67,null,null,505.34]
["10000480","Francis Lirios","1000/13489","Asset Management","15.02.2024","16.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0070","Feb24 Storm Timesheet PC 12001","4012895","4012895","0070","1000/CPSVSN","Corp Prof Spec NT","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-2","Feb24 Storm Costs dNet PC 12001","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",9,null,null,1081.3499999999999]
["10000480","Francis Lirios","1000/13489","Asset Management","16.02.2024","16.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0070","Feb24 Storm Timesheet PC 12001","4012895","4012895","0070","1000/CPSVSN","Corp Prof Spec NT","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-2","Feb24 Storm Costs dNet PC 12001","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",8.5,null,null,1081.3699999999999]
["10000480","Francis Lirios","1000/13489","Asset Management","04.03.2024","08.03.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0070","Feb24 Storm Timesheet PC 12001","4012895","4012895","0070","1000/CMNGAN","1000/CMNGAN","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-2","Feb24 Storm Costs dNet PC 12001","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",null,9,null,null,1146.8699999999999]
["10000480","Francis Lirios","1000/13489","Asset Management","05.03.2024","08.03.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0070","Feb24 Storm Timesheet PC 12001","4012895","4012895","0070","1000/CMNGAN","1000/CMNGAN","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-2","Feb24 Storm Costs dNet PC 12001","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",null,9.5,null,null,1146.94]
["10000480","Francis Lirios","1000/13489","Asset Management","06.03.2024","08.03.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0070","Feb24 Storm Timesheet PC 12001","4012895","4012895","0070","1000/CMNGAN","1000/CMNGAN","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-2","Feb24 Storm Costs dNet PC 12001","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",null,8.5,null,null,1146.99]
["10000480","Francis Lirios","1000/13489","Asset Management","07.03.2024","08.03.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0070","Feb24 Storm Timesheet PC 12001","4012895","4012895","0070","1000/CMNGAN","1000/CMNGAN","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-2","Feb24 Storm Costs dNet PC 12001","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",null,9,null,null,1146.8699999999999]
["10000480","Francis Lirios","1000/13489","Asset Management","08.03.2024","08.03.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0070","Feb24 Storm Timesheet PC 12001","4012895","4012895","0070","1000/CMNGAN","1000/CMNGAN","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-2","Feb24 Storm Costs dNet PC 12001","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",null,8,null,null,1146.8800000000001]
["10000481","Sing Wai Mak","1000/13435","Engineering & Projec","13.02.2024","20.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0020","Feb24 Storm Timesheet Tx 12014","4012895","4012895","0020","1000/CSENAN","1000/CSENAN","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",7,null,null,1253.77]
["10000481","Sing Wai Mak","1000/13435","Engineering & Projec","15.02.2024","20.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0020","Feb24 Storm Timesheet Tx 12014","4012895","4012895","0020","1000/CSENAN","1000/CSENAN","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",7.5,null,null,1343.33]
["10000481","Sing Wai Mak","1000/13435","Engineering & Projec","16.02.2024","20.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0020","Feb24 Storm Timesheet Tx 12014","4012895","4012895","0020","1000/CSENAN","1000/CSENAN","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",7.5,null,null,1343.33]
["10000481","Sing Wai Mak","1000/13435","Engineering & Projec","20.02.2024","08.03.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0020","Feb24 Storm Timesheet Tx 12014","4012895","4012895","0020","1000/CSENAN","1000/CSENAN","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",7.5,null,null,1343.33]
["10000493","Terry Jong","1000/12412","Infrastructure Engin","13.02.2024","20.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0150","Feb24 Storm Timesheet PC 12388","4012895","4012895","0150","1000/CSENAN","1000/CSENAN","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-6","Feb24 Storm Costs DFN PC 12388","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",1,null,null,179.11]
["10000493","Terry Jong","1000/12412","Infrastructure Engin","13.02.2024","20.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0150","Feb24 Storm Timesheet PC 12388","4012895","4012895","0150","1000/CSENAO","1000/CSENAO","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-6","Feb24 Storm Costs DFN PC 12388","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",5.5,null,null,1420.82]
["10000493","Terry Jong","1000/12412","Infrastructure Engin","14.02.2024","20.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0150","Feb24 Storm Timesheet PC 12388","4012895","4012895","0150","1000/CSENAN","1000/CSENAN","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-6","Feb24 Storm Costs DFN PC 12388","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",2,null,null,358.22]
["10000493","Terry Jong","1000/12412","Infrastructure Engin","14.02.2024","20.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0150","Feb24 Storm Timesheet PC 12388","4012895","4012895","0150","1000/CSENAO","1000/CSENAO","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-6","Feb24 Storm Costs DFN PC 12388","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",5.5,null,null,1420.82]
["10000510","Gary Hocking","1000/13187","Customer Engagement","20.02.2024","26.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CPSRVN","Corp Prof NT","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",8.8800000000000008,null,null,980.62]
["10000510","Gary Hocking","1000/13187","Customer Engagement","20.02.2024","26.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CPSRVO","Corp Prof OT","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",0.67,null,null,113.76]
["10000510","Gary Hocking","1000/13187","Customer Engagement","21.02.2024","26.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CPSRVN","Corp Prof NT","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",8.08,null,null,951.18]
["10000510","Gary Hocking","1000/13187","Customer Engagement","21.02.2024","26.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CPSRVO","Corp Prof OT","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",2.0499999999999998,null,null,348.07]
["10000510","Gary Hocking","1000/13187","Customer Engagement","22.02.2024","26.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CPSRVN","Corp Prof NT","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",8.08,null,null,951.18]
["10000510","Gary Hocking","1000/13187","Customer Engagement","22.02.2024","26.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CPSRVO","Corp Prof OT","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",1.05,null,null,178.28]
["10000510","Gary Hocking","1000/13187","Customer Engagement","23.02.2024","26.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CPSRVN","Corp Prof NT","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",7.95,null,null,935.88]
["10000510","Gary Hocking","1000/13187","Customer Engagement","23.02.2024","26.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CPSRVO","Corp Prof OT","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",0.82,null,null,139.22999999999999]
["10000510","Gary Hocking","1000/13187","Customer Engagement","24.02.2024","26.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CPSRVO","Corp Prof OT","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",7.44,null,null,1263.24]
["10000510","Gary Hocking","1000/13187","Customer Engagement","26.02.2024","01.03.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CPSRVN","Corp Prof NT","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",8.9499999999999993,null,null,980.56]
["10000510","Gary Hocking","1000/13187","Customer Engagement","21.03.2024","23.03.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CPSPAN","1000/CPSPAN","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",null,3.57,null,null,440.32]
["10000540","Michael Delapena","1000/13104","Distribution Control","15.02.2024","21.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CMNGRN","Corp Manager NT","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",12,null,null,1230.72]
["10000554","Adam Duffield","1000/12182","Health, Safety E & Q","13.02.2024","19.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CMNGAN","1000/CMNGAN","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",2,null,null,305.83999999999997]
["10000554","Adam Duffield","1000/12182","Health, Safety E & Q","13.02.2024","19.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CMNGAO","1000/CMNGAO","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",3.25,null,null,716.82]
["10000554","Adam Duffield","1000/12182","Health, Safety E & Q","14.02.2024","19.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CMNGAN","1000/CMNGAN","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",11,null,null,1146.8599999999999]
["10000554","Adam Duffield","1000/12182","Health, Safety E & Q","15.02.2024","19.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CMNGAN","1000/CMNGAN","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",12.5,null,null,1146.8800000000001]
["10000554","Adam Duffield","1000/12182","Health, Safety E & Q","16.02.2024","19.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CMNGAN","1000/CMNGAN","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",14.25,null,null,1146.8399999999999]
["10000594","Gavan Doherty","1000/16004","Aerial Operations","14.02.2024","23.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CMNGAN","1000/CMNGAN","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",7.5,null,null,1146.9000000000001]
["10000594","Gavan Doherty","1000/16004","Aerial Operations","14.02.2024","23.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CMNGAO","1000/CMNGAO","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",6,null,null,1323.36]
["10000594","Gavan Doherty","1000/16004","Aerial Operations","15.02.2024","23.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CMNGAN","1000/CMNGAN","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",7.5,null,null,1146.9000000000001]
["10000594","Gavan Doherty","1000/16004","Aerial Operations","15.02.2024","23.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CMNGAO","1000/CMNGAO","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",5,null,null,1102.8]
["10000594","Gavan Doherty","1000/16004","Aerial Operations","16.02.2024","23.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CMNGAN","1000/CMNGAN","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",7.5,null,null,1146.9000000000001]
["10000594","Gavan Doherty","1000/16004","Aerial Operations","16.02.2024","23.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CMNGAO","1000/CMNGAO","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",4.5,null,null,992.52]
["10000594","Gavan Doherty","1000/16004","Aerial Operations","17.02.2024","23.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CMNGAO","1000/CMNGAO","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",12,null,null,2646.72]
["10000594","Gavan Doherty","1000/16004","Aerial Operations","18.02.2024","23.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CMNGAO","1000/CMNGAO","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",12.5,null,null,2757]
["10000594","Gavan Doherty","1000/16004","Aerial Operations","19.02.2024","06.03.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CMNGAN","1000/CMNGAN","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",7.5,null,null,1146.9000000000001]
["10000594","Gavan Doherty","1000/16004","Aerial Operations","19.02.2024","06.03.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CMNGAO","1000/CMNGAO","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",2,null,null,441.12]
["10000594","Gavan Doherty","1000/16004","Aerial Operations","20.02.2024","06.03.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CMNGAN","1000/CMNGAN","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",7.5,null,null,1146.9000000000001]
["10000594","Gavan Doherty","1000/16004","Aerial Operations","20.02.2024","06.03.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CMNGAO","1000/CMNGAO","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",3,null,null,661.68]
["10000594","Gavan Doherty","1000/16004","Aerial Operations","21.02.2024","06.03.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CMNGAN","1000/CMNGAN","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",7.5,null,null,1146.9000000000001]
["10000594","Gavan Doherty","1000/16004","Aerial Operations","21.02.2024","06.03.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CMNGAO","1000/CMNGAO","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",3.5,null,null,771.96]
["10000637","David Hunter","1000/16001","Inspection & Assessm","13.02.2024","20.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CLEAAN","1000/CLEAAN","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",8,null,null,810.8]
["10000637","David Hunter","1000/16001","Inspection & Assessm","14.02.2024","20.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CLEAAN","1000/CLEAAN","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",8,null,null,810.8]
["10000637","David Hunter","1000/16001","Inspection & Assessm","14.02.2024","20.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CLEAAO","1000/CLEAAO","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",5,null,null,730.9]
["10000637","David Hunter","1000/16001","Inspection & Assessm","15.02.2024","20.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CLEAAN","1000/CLEAAN","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",8,null,null,810.8]
["10000637","David Hunter","1000/16001","Inspection & Assessm","15.02.2024","20.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CLEAAO","1000/CLEAAO","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",3,null,null,438.54]
["10000637","David Hunter","1000/16001","Inspection & Assessm","16.02.2024","20.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CLEAAN","1000/CLEAAN","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",8,null,null,810.8]
["10000637","David Hunter","1000/16001","Inspection & Assessm","20.02.2024","26.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CLEAAN","1000/CLEAAN","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",8,null,null,810.8]
["10000637","David Hunter","1000/16001","Inspection & Assessm","20.02.2024","26.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CLEAAO","1000/CLEAAO","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",3,null,null,438.54]
["10000637","David Hunter","1000/16001","Inspection & Assessm","22.02.2024","26.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CLEAAN","1000/CLEAAN","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",8,null,null,810.8]
["10000637","David Hunter","1000/16001","Inspection & Assessm","22.02.2024","26.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CLEAAO","1000/CLEAAO","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",1.5,null,null,219.27]
["10000638","Scott Graham","1000/16001","Inspection & Assessm","15.02.2024","20.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0030","Feb24 Storm Timesheet Net unknown 12014","4012895","4012895","0030","1000/CPSEAN","1000/CPSEAN","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",4,null,null,357.88]
["10000677","David Cairns","1000/16004","Aerial Operations","21.02.2024","25.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CLEAAN","1000/CLEAAN","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",8,null,null,760.16]
["10000677","David Cairns","1000/16004","Aerial Operations","21.02.2024","25.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CLEAAO","1000/CLEAAO","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",4,null,null,584.72]
["10000677","David Cairns","1000/16004","Aerial Operations","22.02.2024","25.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CLEAAN","1000/CLEAAN","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",7.5,null,null,760.13]
["10000677","David Cairns","1000/16004","Aerial Operations","22.02.2024","25.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CLEAAO","1000/CLEAAO","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",3.5,null,null,511.63]
["10000677","David Cairns","1000/16004","Aerial Operations","24.02.2024","25.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CLEAAO","1000/CLEAAO","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",8.5,null,null,1242.53]
["10000706","Darren Toogood","1000/16001","Inspection & Assessm","14.02.2024","19.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CPSEAO","1000/CPSEAO","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",1,null,null,129.05000000000001]
["10000706","Darren Toogood","1000/16001","Inspection & Assessm","15.02.2024","19.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CPSEAO","1000/CPSEAO","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",2.5,null,null,322.63]
["10000706","Darren Toogood","1000/16001","Inspection & Assessm","16.02.2024","19.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CPSEAO","1000/CPSEAO","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",2,null,null,258.10000000000002]
["10000709","Steven Oldman","1000/16001","Inspection & Assessm","15.02.2024","20.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0040","Feb24 Storm Purchases Orders Dx 12014","4012895","4012895","0040","1000/AINSPN","Asset Inspector NT","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",4,null,null,285.24]
["10000709","Steven Oldman","1000/16001","Inspection & Assessm","16.02.2024","20.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0040","Feb24 Storm Purchases Orders Dx 12014","4012895","4012895","0040","1000/AINSPN","Asset Inspector NT","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",4,null,null,285.24]
["10000724","Jason Moses","1000/16001","Inspection & Assessm","15.02.2024","21.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/AINSPN","Asset Inspector NT","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",8,null,null,570.48]
["10000724","Jason Moses","1000/16001","Inspection & Assessm","15.02.2024","21.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/AINSPO","Asset Inspector OT","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",1,null,null,102.86]
["10000726","Rod Watson","1000/16001","Inspection & Assessm","15.02.2024","19.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/AINSPN","Asset Inspector NT","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",8,null,null,570.48]
["10000726","Rod Watson","1000/16001","Inspection & Assessm","15.02.2024","19.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/AINSPO","Asset Inspector OT","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",2.5,null,null,257.14999999999998]
["10000726","Rod Watson","1000/16001","Inspection & Assessm","16.02.2024","19.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/AINSPN","Asset Inspector NT","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",8,null,null,570.48]
["10000726","Rod Watson","1000/16001","Inspection & Assessm","16.02.2024","19.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/AINSPO","Asset Inspector OT","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",2,null,null,205.72]
["10000726","Rod Watson","1000/16001","Inspection & Assessm","17.02.2024","19.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/AINSPO","Asset Inspector OT","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",6,null,null,617.16]
["10000744","Lachlan McCoy","1000/13263","Transmission Control","14.02.2024","20.03.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0020","Feb24 Storm Timesheet Tx 12014","4012895","4012895","0020","1000/CMNGAO","1000/CMNGAO","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",12,null,null,2646.72]
["10000744","Lachlan McCoy","1000/13263","Transmission Control","15.02.2024","20.03.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0020","Feb24 Storm Timesheet Tx 12014","4012895","4012895","0020","1000/CMNGAO","1000/CMNGAO","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",12,null,null,2646.72]
["10000747","Matt Lord","1000/16001","Inspection & Assessm","15.02.2024","23.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0040","Feb24 Storm Purchases Orders Dx 12014","4012895","4012895","0040","1000/AINSPN","Asset Inspector NT","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",8,null,null,570.48]
["10000847","Brendan West","1000/16001","Inspection & Assessm","15.02.2024","21.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/AINSPN","Asset Inspector NT","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",8,null,null,570.48]
["10000847","Brendan West","1000/16001","Inspection & Assessm","15.02.2024","21.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/AINSPO","Asset Inspector OT","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",4,null,null,411.44]
["10000847","Brendan West","1000/16001","Inspection & Assessm","16.02.2024","21.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/AINSPN","Asset Inspector NT","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",8,null,null,570.48]
["10000847","Brendan West","1000/16001","Inspection & Assessm","16.02.2024","21.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/AINSPO","Asset Inspector OT","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",3,null,null,308.58]
["10000868","Peter Quinn","1000/13332","Customer Central","13.02.2024","08.03.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CMNGAN","1000/CMNGAN","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",1,null,null,152.91999999999999]
["10000868","Peter Quinn","1000/13332","Customer Central","13.02.2024","08.03.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CMNGAO","1000/CMNGAO","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",9,null,null,1985.04]
["10000868","Peter Quinn","1000/13332","Customer Central","14.02.2024","08.03.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CMNGAN","1000/CMNGAN","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",7.5,null,null,1146.9000000000001]
["10000868","Peter Quinn","1000/13332","Customer Central","14.02.2024","08.03.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CMNGAO","1000/CMNGAO","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",6,null,null,1323.36]
["10000868","Peter Quinn","1000/13332","Customer Central","15.02.2024","08.03.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CMNGAN","1000/CMNGAN","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",7.5,null,null,1146.9000000000001]
["10000868","Peter Quinn","1000/13332","Customer Central","16.02.2024","08.03.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CMNGAN","1000/CMNGAN","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",7.5,null,null,1146.9000000000001]
["10000868","Peter Quinn","1000/13332","Customer Central","16.02.2024","08.03.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CMNGAO","1000/CMNGAO","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",7,null,null,1543.92]
["10000868","Peter Quinn","1000/13332","Customer Central","17.02.2024","08.03.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CMNGAO","1000/CMNGAO","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",7,null,null,1543.92]
["10000886","Luke Hubben","1000/16002","Programs Planning &","15.02.2024","23.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CPSPAN","1000/CPSPAN","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",9,null,null,925.02]
["10000886","Luke Hubben","1000/16002","Programs Planning &","16.02.2024","23.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CPSPAN","1000/CPSPAN","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",9,null,null,925.02]
["10000911","Shane Davidson","1000/16001","Inspection & Assessm","15.02.2024","21.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0040","Feb24 Storm Purchases Orders Dx 12014","4012895","4012895","0040","1000/AINSPN","Asset Inspector NT","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",8,null,null,570.48]
["10000911","Shane Davidson","1000/16001","Inspection & Assessm","15.02.2024","21.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0040","Feb24 Storm Purchases Orders Dx 12014","4012895","4012895","0040","1000/AINSPO","Asset Inspector OT","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",1,null,null,102.86]
["10000921","Gavin Bickery","1000/16001","Inspection & Assessm","16.02.2024","19.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/AINSPN","Asset Inspector NT","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",8,null,null,570.48]
["10000921","Gavin Bickery","1000/16001","Inspection & Assessm","16.02.2024","19.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/AINSPO","Asset Inspector OT","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",2.5,null,null,257.14999999999998]
["10000922","Jason Brickley","1000/16001","Inspection & Assessm","15.02.2024","19.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/AINSPN","Asset Inspector NT","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",8,null,null,570.48]
["10000922","Jason Brickley","1000/16001","Inspection & Assessm","15.02.2024","19.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/AINSPO","Asset Inspector OT","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",2.5,null,null,257.14999999999998]
["10000922","Jason Brickley","1000/16001","Inspection & Assessm","16.02.2024","19.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/AINSPN","Asset Inspector NT","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",8,null,null,570.48]
["10000922","Jason Brickley","1000/16001","Inspection & Assessm","16.02.2024","19.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/AINSPO","Asset Inspector OT","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",3.5,null,null,360.01]
["10000922","Jason Brickley","1000/16001","Inspection & Assessm","17.02.2024","19.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/AINSPO","Asset Inspector OT","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",8,null,null,822.88]
["10000926","Jarrod Phillips","1000/16001","Inspection & Assessm","15.02.2024","20.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/AINSPN","Asset Inspector NT","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",8,null,null,570.48]
["10000926","Jarrod Phillips","1000/16001","Inspection & Assessm","15.02.2024","20.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/AINSPO","Asset Inspector OT","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",1,null,null,102.86]
["10000926","Jarrod Phillips","1000/16001","Inspection & Assessm","16.02.2024","20.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/AINSPN","Asset Inspector NT","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",5,null,null,356.55]
["10000949","Jade Marshall","1000/16001","Inspection & Assessm","15.02.2024","20.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0040","Feb24 Storm Purchases Orders Dx 12014","4012895","4012895","0040","1000/AINSPO","Asset Inspector OT","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",2,null,null,205.72]
["10000949","Jade Marshall","1000/16001","Inspection & Assessm","16.02.2024","20.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0040","Feb24 Storm Purchases Orders Dx 12014","4012895","4012895","0040","1000/AINSPN","Asset Inspector NT","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",4.5,null,null,320.89999999999998]
["10001132","Paul Clarke","1000/16001","Inspection & Assessm","15.02.2024","20.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0040","Feb24 Storm Purchases Orders Dx 12014","4012895","4012895","0040","1000/CSUPHN","1000/CSUPHN","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",5,null,null,372.55]
["10001155","Alanna Pollock","1000/13031","Operations Optimisat","13.02.2024","26.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CPSVAO","1000/CPSVAO","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",4.5,null,null,883.4]
["10001155","Alanna Pollock","1000/13031","Operations Optimisat","14.02.2024","26.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CPSVAN","1000/CPSVAN","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",8,null,null,1020.72]
["10001155","Alanna Pollock","1000/13031","Operations Optimisat","14.02.2024","26.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CPSVAO","1000/CPSVAO","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",6,null,null,1177.8599999999999]
["10001155","Alanna Pollock","1000/13031","Operations Optimisat","15.02.2024","26.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CPSVAN","1000/CPSVAN","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",8,null,null,1020.72]
["10001155","Alanna Pollock","1000/13031","Operations Optimisat","15.02.2024","26.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CPSVAO","1000/CPSVAO","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",5,null,null,981.55]
["10001155","Alanna Pollock","1000/13031","Operations Optimisat","16.02.2024","26.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CPSVAN","1000/CPSVAN","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",8,null,null,1020.72]
["10001155","Alanna Pollock","1000/13031","Operations Optimisat","16.02.2024","26.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CPSVAO","1000/CPSVAO","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",5,null,null,981.55]
["10001155","Alanna Pollock","1000/13031","Operations Optimisat","17.02.2024","26.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CPSVAO","1000/CPSVAO","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",8,null,null,1570.48]
["10001155","Alanna Pollock","1000/13031","Operations Optimisat","18.02.2024","26.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CPSVAO","1000/CPSVAO","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",8,null,null,1570.48]
["10001155","Alanna Pollock","1000/13031","Operations Optimisat","19.02.2024","26.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CPSVAN","1000/CPSVAN","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",9,null,null,1020.69]
["10001155","Alanna Pollock","1000/13031","Operations Optimisat","20.02.2024","26.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CPSVAN","1000/CPSVAN","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",11.5,null,null,1020.74]
["10001155","Alanna Pollock","1000/13031","Operations Optimisat","22.02.2024","26.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CPSVAN","1000/CPSVAN","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",8,null,null,1020.72]
["10001155","Alanna Pollock","1000/13031","Operations Optimisat","22.02.2024","26.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CPSVAO","1000/CPSVAO","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",3,null,null,588.92999999999995]
["10001155","Alanna Pollock","1000/13031","Operations Optimisat","23.02.2024","26.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CPSVAN","1000/CPSVAN","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",8,null,null,1020.72]
["10001155","Alanna Pollock","1000/13031","Operations Optimisat","23.02.2024","26.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CPSVAO","1000/CPSVAO","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",2,null,null,392.62]
["10001170","Mark Snell","1000/12182","Health, Safety E & Q","14.02.2024","19.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0020","Feb24 Storm Timesheet Tx 12014","4012895","4012895","0020","1000/PMNGRN","Project Manager NT","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",3,null,null,402.6]
["10001170","Mark Snell","1000/12182","Health, Safety E & Q","15.02.2024","19.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0020","Feb24 Storm Timesheet Tx 12014","4012895","4012895","0020","1000/PMNGRN","Project Manager NT","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",2.5,null,null,335.5]
["10001174","Patrick Hide","1000/16001","Inspection & Assessm","15.02.2024","19.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/AINSPN","Asset Inspector NT","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",4,null,null,285.24]
["10001176","Lucas Roberts","1000/16001","Inspection & Assessm","15.02.2024","19.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/AINSPN","Asset Inspector NT","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",8,null,null,570.48]
["10001176","Lucas Roberts","1000/16001","Inspection & Assessm","15.02.2024","19.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/AINSPO","Asset Inspector OT","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",3,null,null,308.58]
["10001176","Lucas Roberts","1000/16001","Inspection & Assessm","16.02.2024","19.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/AINSPN","Asset Inspector NT","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",8,null,null,570.48]
["10001176","Lucas Roberts","1000/16001","Inspection & Assessm","16.02.2024","19.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/AINSPO","Asset Inspector OT","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",4,null,null,411.44]
["10001200","Mathew Durack","1000/11517","Contract Manag Dist","14.02.2024","23.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CPSPAN","1000/CPSPAN","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",8,null,null,925.04]
["10001200","Mathew Durack","1000/11517","Contract Manag Dist","14.02.2024","23.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CPSPAO","1000/CPSPAO","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",4,null,null,711.6]
["10001200","Mathew Durack","1000/11517","Contract Manag Dist","15.02.2024","23.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CPSPAN","1000/CPSPAN","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",8,null,null,925.04]
["10001200","Mathew Durack","1000/11517","Contract Manag Dist","15.02.2024","23.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CPSPAO","1000/CPSPAO","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",4.5,null,null,800.55]
["10001200","Mathew Durack","1000/11517","Contract Manag Dist","16.02.2024","23.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CPSPAN","1000/CPSPAN","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",8,null,null,925.04]
["10001200","Mathew Durack","1000/11517","Contract Manag Dist","16.02.2024","23.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CPSPAO","1000/CPSPAO","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",8,null,null,1423.2]
["10001200","Mathew Durack","1000/11517","Contract Manag Dist","17.02.2024","23.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CPSPAO","1000/CPSPAO","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",9.5,null,null,1690.05]
["10001200","Mathew Durack","1000/11517","Contract Manag Dist","18.02.2024","23.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CPSPAO","1000/CPSPAO","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",13.5,null,null,2401.65]
["10001200","Mathew Durack","1000/11517","Contract Manag Dist","19.02.2024","06.03.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CPSPAN","1000/CPSPAN","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",8,null,null,925.04]
["10001200","Mathew Durack","1000/11517","Contract Manag Dist","19.02.2024","06.03.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CPSPAO","1000/CPSPAO","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",2.5,null,null,444.75]
["10001200","Mathew Durack","1000/11517","Contract Manag Dist","20.02.2024","06.03.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CPSPAN","1000/CPSPAN","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",8,null,null,925.04]
["10001200","Mathew Durack","1000/11517","Contract Manag Dist","21.02.2024","06.03.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CPSPAN","1000/CPSPAN","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",8,null,null,925.04]
["10001200","Mathew Durack","1000/11517","Contract Manag Dist","21.02.2024","06.03.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CPSPAO","1000/CPSPAO","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",6.25,null,null,1111.8800000000001]
["10001211","Brian Brann","1000/11903","Eng Serv & Comp (D)","13.02.2024","19.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CPSPEN","Corp Prof Exp NT","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",5.75,null,null,743.71]
["10001211","Brian Brann","1000/11903","Eng Serv & Comp (D)","13.02.2024","19.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CPSPEO","Corp Prof Exp OT","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",5,null,null,932.8]
["10001211","Brian Brann","1000/11903","Eng Serv & Comp (D)","14.02.2024","19.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CPSPEN","Corp Prof Exp NT","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",7.75,null,null,969.99]
["10001211","Brian Brann","1000/11903","Eng Serv & Comp (D)","14.02.2024","19.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CPSPEO","Corp Prof Exp OT","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",1.17,null,null,218.28]
["10001247","Paul Tanner","1000/13121","Cust Prog central","19.02.2024","23.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CPSVAN","1000/CPSVAN","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",8.5,null,null,1020.77]
["10001247","Paul Tanner","1000/13121","Cust Prog central","20.02.2024","23.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CPSVAN","1000/CPSVAN","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",8.5,null,null,1020.77]
["10001248","Ron Tucker","1000/13187","Customer Engagement","19.02.2024","05.03.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CPSPAN","1000/CPSPAN","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",8.33,null,null,1027.42]
["10001248","Ron Tucker","1000/13187","Customer Engagement","20.02.2024","05.03.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CPSPAN","1000/CPSPAN","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",8.33,null,null,1027.42]
["10001248","Ron Tucker","1000/13187","Customer Engagement","20.02.2024","05.03.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CPSPAO","1000/CPSPAO","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",2.92,null,null,519.47]
["10001248","Ron Tucker","1000/13187","Customer Engagement","21.02.2024","05.03.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CPSPAN","1000/CPSPAN","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",8.33,null,null,1027.42]
["10001248","Ron Tucker","1000/13187","Customer Engagement","21.02.2024","05.03.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CPSPAO","1000/CPSPAO","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",4.67,null,null,830.79]
["10001248","Ron Tucker","1000/13187","Customer Engagement","22.02.2024","05.03.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CPSPAN","1000/CPSPAN","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",8.33,null,null,1027.42]
["10001248","Ron Tucker","1000/13187","Customer Engagement","22.02.2024","05.03.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CPSPAO","1000/CPSPAO","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",5.67,null,null,1008.69]
["10001248","Ron Tucker","1000/13187","Customer Engagement","23.02.2024","05.03.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CPSPAO","1000/CPSPAO","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",4.67,null,null,830.79]
["10001248","Ron Tucker","1000/13187","Customer Engagement","24.02.2024","05.03.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CPSPAO","1000/CPSPAO","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",2,null,null,355.8]
["10001248","Ron Tucker","1000/13187","Customer Engagement","25.02.2024","05.03.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CPSPAO","1000/CPSPAO","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",4.25,null,null,756.08]
["10001248","Ron Tucker","1000/13187","Customer Engagement","26.02.2024","05.03.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CPSPAN","1000/CPSPAN","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",4.5,null,null,555.03]
["10001248","Ron Tucker","1000/13187","Customer Engagement","29.02.2024","05.03.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CPSPAN","1000/CPSPAN","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",8.33,null,null,1027.42]
["10001248","Ron Tucker","1000/13187","Customer Engagement","01.03.2024","05.03.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CPSPAN","1000/CPSPAN","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",null,4.5,null,null,555.03]
["10001248","Ron Tucker","1000/13187","Customer Engagement","02.03.2024","05.03.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CPSPAO","1000/CPSPAO","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",null,6.5,null,null,1156.3499999999999]
["10001250","Chris Websdale","1000/13031","Operations Optimisat","15.02.2024","23.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CMNGAN","1000/CMNGAN","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",11.75,null,null,1146.92]
["10001250","Chris Websdale","1000/13031","Operations Optimisat","16.02.2024","23.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CMNGAN","1000/CMNGAN","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",10,null,null,1146.9000000000001]
["10001250","Chris Websdale","1000/13031","Operations Optimisat","17.02.2024","23.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CMNGAN","1000/CMNGAN","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",3.5,null,null,535.22]
["10001258","Matteo DiCarlo","1000/13104","Distribution Control","15.02.2024","21.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CSENAO","1000/CSENAO","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",12.5,null,null,3229.13]
["10001258","Matteo DiCarlo","1000/13104","Distribution Control","22.02.2024","27.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CSENAO","1000/CSENAO","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",12.5,null,null,3229.13]
["10001318","Tom Minogue","1000/13723","Cust Prog Cent East","14.02.2024","26.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CPSPAN","1000/CPSPAN","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",8,null,null,925.04]
["10001318","Tom Minogue","1000/13723","Cust Prog Cent East","14.02.2024","26.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CPSPAO","1000/CPSPAO","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",2,null,null,355.8]
["10001318","Tom Minogue","1000/13723","Cust Prog Cent East","15.02.2024","26.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CPSPAN","1000/CPSPAN","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",8,null,null,925.04]
["10001318","Tom Minogue","1000/13723","Cust Prog Cent East","15.02.2024","26.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CPSPAO","1000/CPSPAO","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",2,null,null,355.8]
["10001318","Tom Minogue","1000/13723","Cust Prog Cent East","16.02.2024","26.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CPSPAN","1000/CPSPAN","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",8,null,null,925.04]
["10001318","Tom Minogue","1000/13723","Cust Prog Cent East","16.02.2024","26.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CPSPAO","1000/CPSPAO","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",6,null,null,1067.4000000000001]
["10001318","Tom Minogue","1000/13723","Cust Prog Cent East","17.02.2024","26.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CPSPAO","1000/CPSPAO","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",3,null,null,533.70000000000005]
["10001318","Tom Minogue","1000/13723","Cust Prog Cent East","18.02.2024","26.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CPSPAO","1000/CPSPAO","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",2,null,null,355.8]
["10001326","Kyle Hickman","1000/13030","Access and Outage Pl","18.02.2024","20.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CPSVAO","1000/CPSVAO","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",10,null,null,1963.1]
["10001326","Kyle Hickman","1000/13030","Access and Outage Pl","19.02.2024","23.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CPSVAO","1000/CPSVAO","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",2,null,null,392.62]
["10001326","Kyle Hickman","1000/13030","Access and Outage Pl","20.02.2024","23.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CPSVAO","1000/CPSVAO","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",2,null,null,392.62]
["10001326","Kyle Hickman","1000/13030","Access and Outage Pl","21.02.2024","23.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CPSVAO","1000/CPSVAO","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",2,null,null,392.62]
["10001334","Andrew Webber","1000/12357","Customer Programs Op","24.02.2024","04.03.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CPSPAO","1000/CPSPAO","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",2,null,null,355.8]
["10001400","Peter Anderson","1000/13030","Access and Outage Pl","14.02.2024","16.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/ACCOOO","Access Coor OT","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",3.25,null,null,456.95]
["10001400","Peter Anderson","1000/13030","Access and Outage Pl","19.02.2024","06.03.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/ACCOON","Access Coor NT","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",8.33,null,null,812.01]
["10001401","Peter Casey","1000/13030","Access and Outage Pl","14.02.2024","19.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/ACCOON","Access Coor NT","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",8.83,null,null,812.01]
["10001401","Peter Casey","1000/13030","Access and Outage Pl","14.02.2024","19.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/ACCOOO","Access Coor OT","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",6,null,null,843.6]
["10001401","Peter Casey","1000/13030","Access and Outage Pl","15.02.2024","19.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/ACCOON","Access Coor NT","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",8.83,null,null,812.01]
["10001401","Peter Casey","1000/13030","Access and Outage Pl","16.02.2024","19.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/ACCOON","Access Coor NT","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",4,null,null,389.92]
["10001403","Anthony Decorrado","1000/13030","Access and Outage Pl","14.02.2024","21.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0110","Feb24 Storm Timesheet PC 12006","4012895","4012895","0110","1000/ACCOOO","Access Coor OT","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-4","Feb24 Storm Costs SR&CA PC 12006","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",7.17,null,null,1008.1]
["10001403","Anthony Decorrado","1000/13030","Access and Outage Pl","18.02.2024","21.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0110","Feb24 Storm Timesheet PC 12006","4012895","4012895","0110","1000/ACCOOO","Access Coor OT","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-4","Feb24 Storm Costs SR&CA PC 12006","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",14,null,null,1968.4]
["10001420","Peter Scotto","1000/11101","Vegetation Managemen","14.02.2024","23.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CLEADO","Corp Ops Lead OT","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",1,null,null,156.08000000000001]
["10001420","Peter Scotto","1000/11101","Vegetation Managemen","15.02.2024","23.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CLEADO","Corp Ops Lead OT","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",1,null,null,156.08000000000001]
["10001420","Peter Scotto","1000/11101","Vegetation Managemen","16.02.2024","23.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CLEADO","Corp Ops Lead OT","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",4,null,null,624.32000000000005]
["10001420","Peter Scotto","1000/11101","Vegetation Managemen","17.02.2024","23.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CLEADO","Corp Ops Lead OT","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",11,null,null,1716.88]
["10001420","Peter Scotto","1000/11101","Vegetation Managemen","18.02.2024","23.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CLEADO","Corp Ops Lead OT","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",12.5,null,null,1951]
["10001420","Peter Scotto","1000/11101","Vegetation Managemen","19.02.2024","27.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CLEADO","Corp Ops Lead OT","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",6,null,null,936.48]
["10001420","Peter Scotto","1000/11101","Vegetation Managemen","20.02.2024","27.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CLEADO","Corp Ops Lead OT","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",4,null,null,624.32000000000005]
["10001420","Peter Scotto","1000/11101","Vegetation Managemen","21.02.2024","27.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CLEADO","Corp Ops Lead OT","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",1,null,null,156.08000000000001]
["10001421","Darren Walker","1000/11101","Vegetation Managemen","18.02.2024","20.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CSUPHO","1000/CSUPHO","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",8,null,null,859.68]
["10001424","Graham Stokes","1000/11101","Vegetation Managemen","14.02.2024","23.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CLEAAO","1000/CLEAAO","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",4,null,null,584.72]
["10001424","Graham Stokes","1000/11101","Vegetation Managemen","15.02.2024","23.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CLEAAO","1000/CLEAAO","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",4.5,null,null,657.81]
["10001424","Graham Stokes","1000/11101","Vegetation Managemen","16.02.2024","23.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CLEAAO","1000/CLEAAO","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",5.33,null,null,779.14]
["10001424","Graham Stokes","1000/11101","Vegetation Managemen","17.02.2024","23.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CLEAAO","1000/CLEAAO","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",11,null,null,1607.98]
["10001424","Graham Stokes","1000/11101","Vegetation Managemen","18.02.2024","23.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CLEAAO","1000/CLEAAO","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",14,null,null,2046.52]
["10001424","Graham Stokes","1000/11101","Vegetation Managemen","19.02.2024","26.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CLEAAO","1000/CLEAAO","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",4.5,null,null,657.81]
["10001424","Graham Stokes","1000/11101","Vegetation Managemen","20.02.2024","26.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CLEAAO","1000/CLEAAO","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",5.33,null,null,779.14]
["10001424","Graham Stokes","1000/11101","Vegetation Managemen","21.02.2024","26.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CLEAAO","1000/CLEAAO","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",2.17,null,null,317.20999999999998]
["10001424","Graham Stokes","1000/11101","Vegetation Managemen","22.02.2024","26.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CLEAAO","1000/CLEAAO","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",4.5,null,null,657.81]
["10001424","Graham Stokes","1000/11101","Vegetation Managemen","25.02.2024","26.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CLEAAO","1000/CLEAAO","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",10,null,null,1461.8]
["10001465","Trevor Biffin","1000/11101","Vegetation Managemen","17.02.2024","20.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0100","Feb24 Storm Purchases Orders PC 12516","4012895","4012895","0100","1000/CPSEAO","1000/CPSEAO","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-3","Feb24 Storm Costs F&G PC 12516","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",12.5,null,null,1613.13]
["10001465","Trevor Biffin","1000/11101","Vegetation Managemen","18.02.2024","20.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CPSEAO","1000/CPSEAO","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",11,null,null,1419.55]
["10001525","Danny Mynard","1000/13723","Cust Prog Cent East","14.02.2024","19.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CPSEAN","1000/CPSEAN","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",8.33,null,null,745.29]
["10001525","Danny Mynard","1000/13723","Cust Prog Cent East","14.02.2024","19.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0050","Feb24 Storm Purchases Orders Tx 12014","4012895","4012895","0050","1000/CPSEAO","1000/CPSEAO","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",4.67,null,null,602.66]
["10001525","Danny Mynard","1000/13723","Cust Prog Cent East","15.02.2024","19.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0050","Feb24 Storm Purchases Orders Tx 12014","4012895","4012895","0050","1000/CPSEAN","1000/CPSEAN","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",8.33,null,null,745.29]
["10001525","Danny Mynard","1000/13723","Cust Prog Cent East","15.02.2024","19.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0050","Feb24 Storm Purchases Orders Tx 12014","4012895","4012895","0050","1000/CPSEAO","1000/CPSEAO","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",4.67,null,null,602.66]
["10001525","Danny Mynard","1000/13723","Cust Prog Cent East","16.02.2024","19.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0050","Feb24 Storm Purchases Orders Tx 12014","4012895","4012895","0050","1000/CPSEAN","1000/CPSEAN","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",8.33,null,null,745.29]
["10001525","Danny Mynard","1000/13723","Cust Prog Cent East","16.02.2024","19.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0050","Feb24 Storm Purchases Orders Tx 12014","4012895","4012895","0050","1000/CPSEAO","1000/CPSEAO","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",4.67,null,null,602.66]
["10001525","Danny Mynard","1000/13723","Cust Prog Cent East","17.02.2024","19.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0050","Feb24 Storm Purchases Orders Tx 12014","4012895","4012895","0050","1000/CPSEAO","1000/CPSEAO","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",13,null,null,1677.65]
["10001525","Danny Mynard","1000/13723","Cust Prog Cent East","18.02.2024","19.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0050","Feb24 Storm Purchases Orders Tx 12014","4012895","4012895","0050","1000/CPSEAO","1000/CPSEAO","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",13,null,null,1677.65]
["10001525","Danny Mynard","1000/13723","Cust Prog Cent East","19.02.2024","23.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0050","Feb24 Storm Purchases Orders Tx 12014","4012895","4012895","0050","1000/CPSEAN","1000/CPSEAN","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",8.33,null,null,745.29]
["10001525","Danny Mynard","1000/13723","Cust Prog Cent East","19.02.2024","23.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0050","Feb24 Storm Purchases Orders Tx 12014","4012895","4012895","0050","1000/CPSEAO","1000/CPSEAO","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",3.5,null,null,451.68]
["10001585","Stephen Lambert","1000/13378","Major Projects Distr","14.02.2024","08.03.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/PMNGRN","Project Manager NT","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",8,null,null,1006.48]
["10001585","Stephen Lambert","1000/13378","Major Projects Distr","15.02.2024","08.03.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/PMNGRN","Project Manager NT","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",8,null,null,1006.48]
["10001585","Stephen Lambert","1000/13378","Major Projects Distr","16.02.2024","08.03.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/PMNGRN","Project Manager NT","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",8,null,null,1006.48]
["10001725","Steven Ray","1000/13030","Access and Outage Pl","14.02.2024","19.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CPSVAO","1000/CPSVAO","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",6,null,null,1177.8599999999999]
["10001725","Steven Ray","1000/13030","Access and Outage Pl","15.02.2024","19.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CPSVAN","1000/CPSVAN","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",8.5,null,null,1020.77]
["10001767","Sharon Jackson","1000/16004","Aerial Operations","23.02.2024","26.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CPSEMO","Corp Semi Prof OT","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",7.5,null,null,1026.9000000000001]
["10001883","Rajesh Siddi","1000/16002","Programs Planning &","15.02.2024","20.03.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CSUPPN","Corp Support NT","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",9,null,null,620.19000000000005]
["10001883","Rajesh Siddi","1000/16002","Programs Planning &","16.02.2024","20.03.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CSUPPN","Corp Support NT","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",4.5,null,null,372.15]
["10001963","Tom Dudley","1000/13723","Cust Prog Cent East","13.02.2024","01.03.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CPSEAO","1000/CPSEAO","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",4,null,null,516.20000000000005]
["10001963","Tom Dudley","1000/13723","Cust Prog Cent East","14.02.2024","01.03.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CPSEAN","1000/CPSEAN","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",8,null,null,671.04]
["10001963","Tom Dudley","1000/13723","Cust Prog Cent East","14.02.2024","01.03.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CPSEAO","1000/CPSEAO","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",9.5,null,null,1225.98]
["10001963","Tom Dudley","1000/13723","Cust Prog Cent East","15.02.2024","01.03.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CPSEAN","1000/CPSEAN","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",8,null,null,671.04]
["10001963","Tom Dudley","1000/13723","Cust Prog Cent East","15.02.2024","01.03.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CPSEAO","1000/CPSEAO","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",3.5,null,null,451.68]
["10002123","James Buchanan","1000/13104","Distribution Control","14.02.2024","23.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CLEAAO","1000/CLEAAO","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",1,null,null,146.18]
["10002123","James Buchanan","1000/13104","Distribution Control","16.02.2024","23.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CLEAAO","1000/CLEAAO","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",12,null,null,1754.16]
["10002201","Paul Monk","1000/13723","Cust Prog Cent East","14.02.2024","16.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CLEADN","Corp Ops Lead NT","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",8,null,null,811.6]
["10002201","Paul Monk","1000/13723","Cust Prog Cent East","14.02.2024","16.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CLEADO","Corp Ops Lead OT","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",4,null,null,624.32000000000005]
["10002201","Paul Monk","1000/13723","Cust Prog Cent East","15.02.2024","16.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CLEADN","Corp Ops Lead NT","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",8,null,null,811.6]
["10002201","Paul Monk","1000/13723","Cust Prog Cent East","15.02.2024","16.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CLEADO","Corp Ops Lead OT","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",4,null,null,624.32000000000005]
["10002201","Paul Monk","1000/13723","Cust Prog Cent East","16.02.2024","16.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CLEADN","Corp Ops Lead NT","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",8,null,null,811.6]
["10002213","Isak Nel","1000/13104","Distribution Control","22.02.2024","09.03.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/DCONTO","Dxn Controller OT","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",12,null,null,2550.2399999999998]
["10002365","Chris Stephens","1000/13723","Cust Prog Cent East","16.02.2024","23.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CLEADN","Corp Ops Lead NT","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",6.5,null,null,703.37]
["10002365","Chris Stephens","1000/13723","Cust Prog Cent East","16.02.2024","23.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CLEADO","Corp Ops Lead OT","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",1,null,null,156.08000000000001]
["10002528","Daniel Potts","1000/13104","Distribution Control","15.02.2024","28.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/DCONTN","Dxn Controller NT","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",12,null,null,1105.08]
["10002528","Daniel Potts","1000/13104","Distribution Control","15.02.2024","28.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/DCONTO","Dxn Controller OT","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",1.5,null,null,318.77999999999997]
["10002580","Rodney Jones","1000/11101","Vegetation Managemen","19.02.2024","26.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CSUPGN","1000/CSUPGN","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",8.83,null,null,575.98]
["10002580","Rodney Jones","1000/11101","Vegetation Managemen","19.02.2024","26.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CSUPGO","1000/CSUPGO","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",1.17,null,null,116.67]
["10002580","Rodney Jones","1000/11101","Vegetation Managemen","20.02.2024","26.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CSUPGN","1000/CSUPGN","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",8.83,null,null,575.98]
["10002580","Rodney Jones","1000/11101","Vegetation Managemen","20.02.2024","26.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CSUPGO","1000/CSUPGO","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",2.17,null,null,216.39]
["10002584","Martyn Williams","1000/13263","Transmission Control","13.02.2024","19.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0020","Feb24 Storm Timesheet Tx 12014","4012895","4012895","0020","1000/TCONTO","Txn Controller OT","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",1.5,null,null,328.58]
["10002584","Martyn Williams","1000/13263","Transmission Control","18.02.2024","19.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0020","Feb24 Storm Timesheet Tx 12014","4012895","4012895","0020","1000/TCONTO","Txn Controller OT","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",12,null,null,2628.6]
["10002588","Scott Dunstan","1000/11101","Vegetation Managemen","17.02.2024","19.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CSUPHO","1000/CSUPHO","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",12.5,null,null,1343.25]
["10002588","Scott Dunstan","1000/11101","Vegetation Managemen","19.02.2024","23.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CSUPHN","1000/CSUPHN","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",8.83,null,null,620.66]
["10002588","Scott Dunstan","1000/11101","Vegetation Managemen","19.02.2024","23.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CSUPHO","1000/CSUPHO","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",3.17,null,null,340.65]
["10002588","Scott Dunstan","1000/11101","Vegetation Managemen","20.02.2024","23.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CSUPHN","1000/CSUPHN","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",8.83,null,null,620.66]
["10002588","Scott Dunstan","1000/11101","Vegetation Managemen","20.02.2024","23.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CSUPHO","1000/CSUPHO","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",3.67,null,null,394.38]
["10002595","Doug Youlten","1000/16001","Inspection & Assessm","15.02.2024","19.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/ASSESN","Asset Assesor NT","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",8.33,null,null,774.69]
["10002603","Andrew Bower","1000/16001","Inspection & Assessm","15.02.2024","20.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CSUPPN","Corp Support NT","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",8,null,null,661.6]
["10002603","Andrew Bower","1000/16001","Inspection & Assessm","15.02.2024","20.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CSUPPO","Corp Support OT","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",1,null,null,119.28]
["10002609","Ashley Winton","1000/16001","Inspection & Assessm","14.02.2024","20.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/ASSESN","Asset Assesor NT","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",8,null,null,744]
["10002609","Ashley Winton","1000/16001","Inspection & Assessm","15.02.2024","20.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/ASSESN","Asset Assesor NT","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",8,null,null,744]
["10002609","Ashley Winton","1000/16001","Inspection & Assessm","15.02.2024","20.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/ASSESO","Asset Assesor OT","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",2.5,null,null,335.33]
["10002609","Ashley Winton","1000/16001","Inspection & Assessm","16.02.2024","20.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/ASSESO","Asset Assesor OT","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",2,null,null,268.26]
["10002609","Ashley Winton","1000/16001","Inspection & Assessm","17.02.2024","20.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/ASSESO","Asset Assesor OT","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",11.5,null,null,1542.5]
["10002609","Ashley Winton","1000/16001","Inspection & Assessm","19.02.2024","26.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/ASSESN","Asset Assesor NT","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",8,null,null,744]
["10002609","Ashley Winton","1000/16001","Inspection & Assessm","21.02.2024","26.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/ASSESN","Asset Assesor NT","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",8,null,null,744]
["10002609","Ashley Winton","1000/16001","Inspection & Assessm","21.02.2024","26.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/ASSESO","Asset Assesor OT","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",2,null,null,268.26]
["10002610","Harley Duffield","1000/16001","Inspection & Assessm","14.02.2024","21.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CLEAAO","1000/CLEAAO","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",2.5,null,null,365.45]
["10002610","Harley Duffield","1000/16001","Inspection & Assessm","15.02.2024","21.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CLEAAN","1000/CLEAAN","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",4,null,null,405.4]
["10002610","Harley Duffield","1000/16001","Inspection & Assessm","15.02.2024","21.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CLEAAO","1000/CLEAAO","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",2.5,null,null,365.45]
["10002610","Harley Duffield","1000/16001","Inspection & Assessm","17.02.2024","21.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CLEAAO","1000/CLEAAO","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",2,null,null,292.36]
["10002610","Harley Duffield","1000/16001","Inspection & Assessm","18.02.2024","21.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CLEAAO","1000/CLEAAO","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",1,null,null,146.18]
["10002635","Nathaniel Taylor","1000/13104","Distribution Control","14.02.2024","21.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CSENAN","1000/CSENAN","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",12,null,null,1343.28]
["10002642","Matt Rogers","1000/13104","Distribution Control","13.02.2024","06.04.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CMNGAO","1000/CMNGAO","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",2.5,null,null,551.4]
["10002642","Matt Rogers","1000/13104","Distribution Control","17.02.2024","06.04.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CMNGAO","1000/CMNGAO","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",11,null,null,2426.16]
["10002699","Leon Hughan","1000/16001","Inspection & Assessm","14.02.2024","20.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CLEADO","Corp Ops Lead OT","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",3.5,null,null,546.28]
["10002699","Leon Hughan","1000/16001","Inspection & Assessm","15.02.2024","20.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CLEADN","Corp Ops Lead NT","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",8,null,null,865.68]
["10002699","Leon Hughan","1000/16001","Inspection & Assessm","15.02.2024","20.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CLEADO","Corp Ops Lead OT","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",3,null,null,468.24]
["10002699","Leon Hughan","1000/16001","Inspection & Assessm","16.02.2024","20.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CLEADN","Corp Ops Lead NT","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",8,null,null,865.68]
["10002699","Leon Hughan","1000/16001","Inspection & Assessm","16.02.2024","20.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CLEADO","Corp Ops Lead OT","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",1,null,null,156.08000000000001]
["10002699","Leon Hughan","1000/16001","Inspection & Assessm","16.02.2024","20.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0110","Feb24 Storm Timesheet PC 12006","4012895","4012895","0110","1000/CLEADO","Corp Ops Lead OT","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-4","Feb24 Storm Costs SR&CA PC 12006","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",1,null,null,156.08000000000001]
["10002699","Leon Hughan","1000/16001","Inspection & Assessm","17.02.2024","20.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CLEADO","Corp Ops Lead OT","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",4,null,null,624.32000000000005]
["10002704","Gary Lamont","1000/16001","Inspection & Assessm","15.02.2024","21.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0020","Feb24 Storm Timesheet Tx 12014","4012895","4012895","0020","1000/ASSESN","Asset Assesor NT","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",8,null,null,744]
["10002704","Gary Lamont","1000/16001","Inspection & Assessm","16.02.2024","21.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0020","Feb24 Storm Timesheet Tx 12014","4012895","4012895","0020","1000/ASSESN","Asset Assesor NT","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",8,null,null,744]
["10002704","Gary Lamont","1000/16001","Inspection & Assessm","05.03.2024","06.03.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0020","Feb24 Storm Timesheet Tx 12014","4012895","4012895","0020","1000/ASSESN","Asset Assesor NT","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",null,4,null,null,372]
["10004685","Joe Hales","1000/11101","Vegetation Managemen","14.02.2024","20.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CPSEAO","1000/CPSEAO","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",1.67,null,null,215.51]
["10004685","Joe Hales","1000/11101","Vegetation Managemen","15.02.2024","20.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CPSEAO","1000/CPSEAO","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",2.17,null,null,280.04000000000002]
["10004685","Joe Hales","1000/11101","Vegetation Managemen","16.02.2024","20.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CPSEAO","1000/CPSEAO","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",3.67,null,null,473.61]
["10004685","Joe Hales","1000/11101","Vegetation Managemen","17.02.2024","20.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CPSEAO","1000/CPSEAO","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",12,null,null,1548.6]
["10004685","Joe Hales","1000/11101","Vegetation Managemen","18.02.2024","20.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CPSEAO","1000/CPSEAO","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",10.5,null,null,1355.03]
["10004685","Joe Hales","1000/11101","Vegetation Managemen","19.02.2024","26.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CPSEAO","1000/CPSEAO","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",9.5,null,null,1225.98]
["10004685","Joe Hales","1000/11101","Vegetation Managemen","20.02.2024","26.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CPSEAO","1000/CPSEAO","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",1.67,null,null,215.51]
["10004685","Joe Hales","1000/11101","Vegetation Managemen","25.02.2024","26.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CPSEAO","1000/CPSEAO","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",10,null,null,1290.5]
["10004694","Lance Kibble","1000/11101","Vegetation Managemen","15.02.2024","20.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CPSEAO","1000/CPSEAO","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",3.5,null,null,451.68]
["10004694","Lance Kibble","1000/11101","Vegetation Managemen","16.02.2024","20.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CPSEAO","1000/CPSEAO","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",3.5,null,null,451.68]
["10004694","Lance Kibble","1000/11101","Vegetation Managemen","17.02.2024","20.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CPSEAO","1000/CPSEAO","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",12,null,null,1548.6]
["10004694","Lance Kibble","1000/11101","Vegetation Managemen","18.02.2024","20.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CPSEAO","1000/CPSEAO","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",10.5,null,null,1355.03]
["10004694","Lance Kibble","1000/11101","Vegetation Managemen","20.02.2024","01.03.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CPSEAO","1000/CPSEAO","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",3,null,null,387.15]
["10004694","Lance Kibble","1000/11101","Vegetation Managemen","22.02.2024","01.03.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CPSEAO","1000/CPSEAO","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",3,null,null,387.15]
["10004694","Lance Kibble","1000/11101","Vegetation Managemen","23.02.2024","01.03.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CPSEAO","1000/CPSEAO","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",10,null,null,1290.5]
["10004694","Lance Kibble","1000/11101","Vegetation Managemen","24.02.2024","01.03.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CPSEAO","1000/CPSEAO","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",10.5,null,null,1355.03]
["10004728","Murray O'Grady","1000/13936","Customer Connections","19.02.2024","28.03.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CPSEAN","1000/CPSEAN","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",1.5,null,null,134.21]
["10004728","Murray O'Grady","1000/13936","Customer Connections","20.02.2024","28.03.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CPSEAN","1000/CPSEAN","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",0.5,null,null,44.74]
["10004728","Murray O'Grady","1000/13936","Customer Connections","21.02.2024","28.03.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CPSEAN","1000/CPSEAN","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",0.5,null,null,44.74]
["10004728","Murray O'Grady","1000/13936","Customer Connections","22.02.2024","28.03.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CPSEAN","1000/CPSEAN","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",14.25,null,null,671.03]
["10004728","Murray O'Grady","1000/13936","Customer Connections","23.02.2024","28.03.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CPSEAN","1000/CPSEAN","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",9,null,null,671.04]
["10004728","Murray O'Grady","1000/13936","Customer Connections","26.02.2024","28.03.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CPSEAN","1000/CPSEAN","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",10,null,null,671]
["10004728","Murray O'Grady","1000/13936","Customer Connections","27.02.2024","28.03.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CPSEAN","1000/CPSEAN","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",10,null,null,671]
["10004728","Murray O'Grady","1000/13936","Customer Connections","28.02.2024","28.03.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CPSEAN","1000/CPSEAN","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",10.5,null,null,671.06]
["10004728","Murray O'Grady","1000/13936","Customer Connections","29.02.2024","28.03.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CPSEAN","1000/CPSEAN","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",10,null,null,671]
["10004728","Murray O'Grady","1000/13936","Customer Connections","01.03.2024","28.03.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CPSEAN","1000/CPSEAN","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",null,10,null,null,671]
["10004728","Murray O'Grady","1000/13936","Customer Connections","04.03.2024","28.03.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CPSEAN","1000/CPSEAN","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",null,10,null,null,671]
["10004728","Murray O'Grady","1000/13936","Customer Connections","06.03.2024","28.03.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CPSEAN","1000/CPSEAN","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",null,12.5,null,null,671]
["10004866","Paul Hoult","1000/13936","Customer Connections","14.02.2024","01.03.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CPSEAN","1000/CPSEAN","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",0.5,null,null,44.74]
["10004880","James Slater","1000/11101","Vegetation Managemen","15.02.2024","20.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CSUPGO","1000/CSUPGO","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",3,null,null,299.16000000000003]
["10004880","James Slater","1000/11101","Vegetation Managemen","16.02.2024","20.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CSUPGO","1000/CSUPGO","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",4,null,null,398.88]
["10004880","James Slater","1000/11101","Vegetation Managemen","18.02.2024","20.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CSUPGO","1000/CSUPGO","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",9.5,null,null,947.34]
["10004880","James Slater","1000/11101","Vegetation Managemen","19.02.2024","27.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CSUPGO","1000/CSUPGO","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",3,null,null,299.16000000000003]
["10004880","James Slater","1000/11101","Vegetation Managemen","20.02.2024","27.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CSUPGO","1000/CSUPGO","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",3,null,null,299.16000000000003]
["10004880","James Slater","1000/11101","Vegetation Managemen","24.02.2024","27.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CSUPGO","1000/CSUPGO","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",11,null,null,1096.92]
["10004967","Jess Sandle","1000/13104","Distribution Control","13.02.2024","20.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CPSEMO","Corp Semi Prof OT","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",1,null,null,136.91999999999999]
["10004967","Jess Sandle","1000/13104","Distribution Control","20.02.2024","20.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0100","Feb24 Storm Purchases Orders PC 12516","4012895","4012895","0100","1000/CPSEMN","Corp Semi Prof NT","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-3","Feb24 Storm Costs F&G PC 12516","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",12,null,null,711.96]
["10004968","Harpreet Singh","1000/13031","Operations Optimisat","13.02.2024","23.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CPSEAO","1000/CPSEAO","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",2,null,null,258.10000000000002]
["10004968","Harpreet Singh","1000/13031","Operations Optimisat","14.02.2024","23.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CPSEAN","1000/CPSEAN","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",8,null,null,671.04]
["10004968","Harpreet Singh","1000/13031","Operations Optimisat","14.02.2024","23.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CPSEAO","1000/CPSEAO","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",5.5,null,null,709.78]
["10004968","Harpreet Singh","1000/13031","Operations Optimisat","15.02.2024","23.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CPSEAN","1000/CPSEAN","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",7.5,null,null,671.03]
["10004968","Harpreet Singh","1000/13031","Operations Optimisat","16.02.2024","23.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CPSEAN","1000/CPSEAN","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",7.5,null,null,671.03]
["10004968","Harpreet Singh","1000/13031","Operations Optimisat","18.02.2024","23.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CPSEAO","1000/CPSEAO","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",12,null,null,1548.6]
["10004968","Harpreet Singh","1000/13031","Operations Optimisat","19.02.2024","28.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CPSEAN","1000/CPSEAN","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",7.5,null,null,671.03]
["10004968","Harpreet Singh","1000/13031","Operations Optimisat","19.02.2024","28.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CPSEAO","1000/CPSEAO","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",3,null,null,387.15]
["10004968","Harpreet Singh","1000/13031","Operations Optimisat","20.02.2024","28.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CPSEAN","1000/CPSEAN","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",7.5,null,null,671.03]
["10004968","Harpreet Singh","1000/13031","Operations Optimisat","20.02.2024","28.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CPSEAO","1000/CPSEAO","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",3,null,null,387.15]
["10004968","Harpreet Singh","1000/13031","Operations Optimisat","21.02.2024","28.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CPSEAN","1000/CPSEAN","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",7.5,null,null,671.03]
["10004968","Harpreet Singh","1000/13031","Operations Optimisat","21.02.2024","28.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CPSEAO","1000/CPSEAO","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",3,null,null,387.15]
["10004968","Harpreet Singh","1000/13031","Operations Optimisat","22.02.2024","28.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CPSEAN","1000/CPSEAN","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",7.5,null,null,671.03]
["10004968","Harpreet Singh","1000/13031","Operations Optimisat","22.02.2024","28.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CPSEAO","1000/CPSEAO","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",2,null,null,258.10000000000002]
["10004968","Harpreet Singh","1000/13031","Operations Optimisat","23.02.2024","28.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CPSEAN","1000/CPSEAN","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",4,null,null,357.88]
["10005157","Richard Kelaart","1000/11101","Vegetation Managemen","14.02.2024","21.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CSUPGO","1000/CSUPGO","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",2.5,null,null,249.3]
["10005157","Richard Kelaart","1000/11101","Vegetation Managemen","15.02.2024","21.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CSUPGO","1000/CSUPGO","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",1.5,null,null,149.58000000000001]
["10005157","Richard Kelaart","1000/11101","Vegetation Managemen","16.02.2024","21.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CSUPGO","1000/CSUPGO","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",3,null,null,299.16000000000003]
["10005157","Richard Kelaart","1000/11101","Vegetation Managemen","17.02.2024","21.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CSUPGN","1000/CSUPGN","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",11,null,null,575.96]
["10005157","Richard Kelaart","1000/11101","Vegetation Managemen","19.02.2024","27.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CSUPGO","1000/CSUPGO","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",2.25,null,null,224.37]
["10005157","Richard Kelaart","1000/11101","Vegetation Managemen","20.02.2024","27.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CSUPGO","1000/CSUPGO","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",2,null,null,199.44]
["10005157","Richard Kelaart","1000/11101","Vegetation Managemen","21.02.2024","27.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CSUPGO","1000/CSUPGO","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",2,null,null,199.44]
["10005529","Anthony Williams","1000/13030","Access and Outage Pl","14.02.2024","19.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0040","Feb24 Storm Purchases Orders Dx 12014","4012895","4012895","0040","1000/ACCOOO","Access Coor OT","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",8.5,null,null,1195.0999999999999]
["10005529","Anthony Williams","1000/13030","Access and Outage Pl","15.02.2024","19.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0040","Feb24 Storm Purchases Orders Dx 12014","4012895","4012895","0040","1000/ACCOOO","Access Coor OT","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",4,null,null,562.4]
["10005529","Anthony Williams","1000/13030","Access and Outage Pl","16.02.2024","19.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0040","Feb24 Storm Purchases Orders Dx 12014","4012895","4012895","0040","1000/ACCOOO","Access Coor OT","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",2,null,null,281.2]
["10005529","Anthony Williams","1000/13030","Access and Outage Pl","18.02.2024","19.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0040","Feb24 Storm Purchases Orders Dx 12014","4012895","4012895","0040","1000/ACCOOO","Access Coor OT","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",13.5,null,null,1898.1]
["10005529","Anthony Williams","1000/13030","Access and Outage Pl","20.02.2024","26.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0040","Feb24 Storm Purchases Orders Dx 12014","4012895","4012895","0040","1000/ACCOOO","Access Coor OT","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",1,null,null,140.6]
["10005529","Anthony Williams","1000/13030","Access and Outage Pl","21.02.2024","26.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0040","Feb24 Storm Purchases Orders Dx 12014","4012895","4012895","0040","1000/ACCOOO","Access Coor OT","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",1,null,null,140.6]
["10005529","Anthony Williams","1000/13030","Access and Outage Pl","22.02.2024","26.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0040","Feb24 Storm Purchases Orders Dx 12014","4012895","4012895","0040","1000/ACCOOO","Access Coor OT","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",2,null,null,281.2]
["10005569","Chris Buley","1000/16002","Programs Planning &","15.02.2024","16.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CSUPDN","1000/CSUPDN","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",8.5,null,null,455.09]
["10005655","Graham Reed","1000/13104","Distribution Control","20.02.2024","20.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/DCONTN","Dxn Controller NT","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",12,null,null,1105.08]
["10005774","Nathan Martinz","1000/13981","Security & Emergency","13.02.2024","19.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CPSPAN","1000/CPSPAN","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",8,null,null,925.04]
["10005774","Nathan Martinz","1000/13981","Security & Emergency","13.02.2024","19.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CPSPAO","1000/CPSPAO","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",4,null,null,711.6]
["10005774","Nathan Martinz","1000/13981","Security & Emergency","14.02.2024","19.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CPSPAN","1000/CPSPAN","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",8,null,null,925.04]
["10005774","Nathan Martinz","1000/13981","Security & Emergency","14.02.2024","19.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CPSPAO","1000/CPSPAO","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",7,null,null,1245.3]
["10005774","Nathan Martinz","1000/13981","Security & Emergency","15.02.2024","19.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CPSPAN","1000/CPSPAN","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",8,null,null,925.04]
["10005774","Nathan Martinz","1000/13981","Security & Emergency","15.02.2024","19.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CPSPAO","1000/CPSPAO","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",5,null,null,889.5]
["10005774","Nathan Martinz","1000/13981","Security & Emergency","16.02.2024","19.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CPSPAN","1000/CPSPAN","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",8,null,null,925.04]
["10005774","Nathan Martinz","1000/13981","Security & Emergency","16.02.2024","19.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CPSPAO","1000/CPSPAO","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",6,null,null,1067.4000000000001]
["10005774","Nathan Martinz","1000/13981","Security & Emergency","17.02.2024","19.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CPSPAO","1000/CPSPAO","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",11,null,null,1956.9]
["10005774","Nathan Martinz","1000/13981","Security & Emergency","18.02.2024","19.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CPSPAO","1000/CPSPAO","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",11,null,null,1956.9]
["10005774","Nathan Martinz","1000/13981","Security & Emergency","19.02.2024","23.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CPSPAN","1000/CPSPAN","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",8,null,null,925.04]
["10005774","Nathan Martinz","1000/13981","Security & Emergency","19.02.2024","23.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CPSPAO","1000/CPSPAO","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",3,null,null,533.70000000000005]
["10005774","Nathan Martinz","1000/13981","Security & Emergency","20.02.2024","23.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CPSPAN","1000/CPSPAN","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",8,null,null,925.04]
["10005774","Nathan Martinz","1000/13981","Security & Emergency","20.02.2024","23.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CPSPAO","1000/CPSPAO","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",3,null,null,533.70000000000005]
["10005774","Nathan Martinz","1000/13981","Security & Emergency","21.02.2024","23.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CPSPAN","1000/CPSPAN","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",8,null,null,925.04]
["10005774","Nathan Martinz","1000/13981","Security & Emergency","21.02.2024","23.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CPSPAO","1000/CPSPAO","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",6,null,null,1067.4000000000001]
["10005774","Nathan Martinz","1000/13981","Security & Emergency","22.02.2024","23.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CPSPAN","1000/CPSPAN","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",8,null,null,925.04]
["10005774","Nathan Martinz","1000/13981","Security & Emergency","22.02.2024","23.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CPSPAO","1000/CPSPAO","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",3,null,null,533.70000000000005]
["10005774","Nathan Martinz","1000/13981","Security & Emergency","23.02.2024","23.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CPSPAN","1000/CPSPAN","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",8,null,null,925.04]
["10005774","Nathan Martinz","1000/13981","Security & Emergency","23.02.2024","23.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CPSPAO","1000/CPSPAO","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",2,null,null,355.8]
["10006297","Troy Hampton","1000/16001","Inspection & Assessm","13.02.2024","01.03.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CPSEMN","Corp Semi Prof NT","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",4,null,null,379.72]
["10006297","Troy Hampton","1000/16001","Inspection & Assessm","14.02.2024","01.03.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CPSEMN","Corp Semi Prof NT","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",8,null,null,759.44]
["10006297","Troy Hampton","1000/16001","Inspection & Assessm","14.02.2024","01.03.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CPSEMO","Corp Semi Prof OT","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",5.5,null,null,753.06]
["10006297","Troy Hampton","1000/16001","Inspection & Assessm","15.02.2024","01.03.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CPSEMN","Corp Semi Prof NT","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",8,null,null,759.44]
["10006297","Troy Hampton","1000/16001","Inspection & Assessm","15.02.2024","01.03.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CPSEMO","Corp Semi Prof OT","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",3,null,null,410.76]
["10006297","Troy Hampton","1000/16001","Inspection & Assessm","16.02.2024","01.03.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CPSEMN","Corp Semi Prof NT","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",8,null,null,759.44]
["10006297","Troy Hampton","1000/16001","Inspection & Assessm","16.02.2024","01.03.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CPSEMO","Corp Semi Prof OT","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",2,null,null,273.83999999999997]
["10006297","Troy Hampton","1000/16001","Inspection & Assessm","17.02.2024","01.03.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CPSEMO","Corp Semi Prof OT","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",11.5,null,null,1574.58]
["10006297","Troy Hampton","1000/16001","Inspection & Assessm","18.02.2024","01.03.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CPSEMO","Corp Semi Prof OT","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",11,null,null,1506.12]
["10006297","Troy Hampton","1000/16001","Inspection & Assessm","19.02.2024","23.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CPSEMN","Corp Semi Prof NT","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",8,null,null,759.44]
["10006297","Troy Hampton","1000/16001","Inspection & Assessm","20.02.2024","23.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CPSEMO","Corp Semi Prof OT","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",2.5,null,null,342.3]
["10006297","Troy Hampton","1000/16001","Inspection & Assessm","20.02.2024","23.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0110","Feb24 Storm Timesheet PC 12006","4012895","4012895","0110","1000/CPSEMN","Corp Semi Prof NT","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-4","Feb24 Storm Costs SR&CA PC 12006","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",8,null,null,759.44]
["10006297","Troy Hampton","1000/16001","Inspection & Assessm","21.02.2024","23.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CPSEMN","Corp Semi Prof NT","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",6,null,null,569.58000000000004]
["10006297","Troy Hampton","1000/16001","Inspection & Assessm","21.02.2024","23.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CPSEMO","Corp Semi Prof OT","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",2,null,null,273.83999999999997]
["10006297","Troy Hampton","1000/16001","Inspection & Assessm","05.03.2024","12.03.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CLEAAN","1000/CLEAAN","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",null,3,null,null,304.05]
["10006313","Leigh Hehir","1000/13104","Distribution Control","14.02.2024","21.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CSENAN","1000/CSENAN","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",12,null,null,1343.28]
["10006313","Leigh Hehir","1000/13104","Distribution Control","15.02.2024","21.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CSENAN","1000/CSENAN","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",12,null,null,1343.28]
["10006816","Andrew Cole","1000/11903","Eng Serv & Comp (D)","14.02.2024","21.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CSENAN","1000/CSENAN","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",11.5,null,null,1343.43]
["10006816","Andrew Cole","1000/11903","Eng Serv & Comp (D)","15.02.2024","21.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CSENAN","1000/CSENAN","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",10,null,null,1343.3]
["10006816","Andrew Cole","1000/11903","Eng Serv & Comp (D)","16.02.2024","21.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CSENAN","1000/CSENAN","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",8.5,null,null,1343.43]
["10006898","Michael Walton","1000/11517","Contract Manag Dist","13.02.2024","08.03.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CPSVAN","1000/CPSVAN","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",3.5,null,null,357.28]
["10006898","Michael Walton","1000/11517","Contract Manag Dist","14.02.2024","08.03.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CPSVAN","1000/CPSVAN","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",7.5,null,null,1020.75]
["10006898","Michael Walton","1000/11517","Contract Manag Dist","14.02.2024","08.03.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CPSVAO","1000/CPSVAO","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",4.5,null,null,883.4]
["10006898","Michael Walton","1000/11517","Contract Manag Dist","15.02.2024","08.03.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CPSVAN","1000/CPSVAN","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",8,null,null,1020.72]
["10006898","Michael Walton","1000/11517","Contract Manag Dist","15.02.2024","08.03.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CPSVAO","1000/CPSVAO","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",2.5,null,null,490.78]
["10006898","Michael Walton","1000/11517","Contract Manag Dist","16.02.2024","08.03.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CPSVAN","1000/CPSVAN","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",8,null,null,1020.72]
["10006898","Michael Walton","1000/11517","Contract Manag Dist","16.02.2024","08.03.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CPSVAO","1000/CPSVAO","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",5.5,null,null,1079.71]
["10006898","Michael Walton","1000/11517","Contract Manag Dist","17.02.2024","08.03.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CPSVAO","1000/CPSVAO","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",10,null,null,1963.1]
["10006898","Michael Walton","1000/11517","Contract Manag Dist","19.02.2024","08.03.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CPSVAN","1000/CPSVAN","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",8,null,null,1020.72]
["10006898","Michael Walton","1000/11517","Contract Manag Dist","20.02.2024","08.03.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CPSVAN","1000/CPSVAN","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",8,null,null,1020.72]
["10006898","Michael Walton","1000/11517","Contract Manag Dist","20.02.2024","08.03.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CPSVAO","1000/CPSVAO","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",2.5,null,null,490.78]
["10006898","Michael Walton","1000/11517","Contract Manag Dist","21.02.2024","08.03.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CPSVAN","1000/CPSVAN","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",8,null,null,1020.72]
["10006898","Michael Walton","1000/11517","Contract Manag Dist","22.02.2024","08.03.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CPSVAN","1000/CPSVAN","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",8.5,null,null,1020.77]
["10006898","Michael Walton","1000/11517","Contract Manag Dist","23.02.2024","08.03.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CPSVAN","1000/CPSVAN","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",4,null,null,544.4]
["10006936","Pindurai Lishandi","1000/13030","Access and Outage Pl","19.02.2024","06.03.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/WPLANO","Work Planner OT","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",2,null,null,308.82]
["10007022","James Radalj","1000/13981","Security & Emergency","13.02.2024","26.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CMNGRN","Corp Manager NT","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",7.5,null,null,1230.75]
["10007022","James Radalj","1000/13981","Security & Emergency","13.02.2024","26.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CMNGRO","Corp Manager OT","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",7.25,null,null,1716]
["10007022","James Radalj","1000/13981","Security & Emergency","14.02.2024","26.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CMNGRN","Corp Manager NT","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",7.5,null,null,1230.75]
["10007022","James Radalj","1000/13981","Security & Emergency","14.02.2024","26.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CMNGRO","Corp Manager OT","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",8.5,null,null,2011.87]
["10007022","James Radalj","1000/13981","Security & Emergency","15.02.2024","26.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CMNGRN","Corp Manager NT","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",7.5,null,null,1230.75]
["10007022","James Radalj","1000/13981","Security & Emergency","15.02.2024","26.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CMNGRO","Corp Manager OT","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",6.5,null,null,1538.49]
["10007022","James Radalj","1000/13981","Security & Emergency","16.02.2024","26.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CMNGRN","Corp Manager NT","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",7.5,null,null,1230.75]
["10007022","James Radalj","1000/13981","Security & Emergency","16.02.2024","26.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CMNGRO","Corp Manager OT","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",5,null,null,1183.45]
["10007022","James Radalj","1000/13981","Security & Emergency","17.02.2024","26.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CMNGRO","Corp Manager OT","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",11.5,null,null,2721.94]
["10007022","James Radalj","1000/13981","Security & Emergency","18.02.2024","26.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CMNGRO","Corp Manager OT","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",12.25,null,null,2899.45]
["10007022","James Radalj","1000/13981","Security & Emergency","19.02.2024","26.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CMNGRN","Corp Manager NT","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",7.5,null,null,1230.75]
["10007022","James Radalj","1000/13981","Security & Emergency","19.02.2024","26.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CMNGRO","Corp Manager OT","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",4.5,null,null,1065.1099999999999]
["10007022","James Radalj","1000/13981","Security & Emergency","21.02.2024","26.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CMNGRO","Corp Manager OT","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",4,null,null,946.76]
["10007022","James Radalj","1000/13981","Security & Emergency","22.02.2024","26.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CMNGRN","Corp Manager NT","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",7.5,null,null,1230.75]
["10007022","James Radalj","1000/13981","Security & Emergency","22.02.2024","26.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CMNGRO","Corp Manager OT","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",4.5,null,null,1065.1099999999999]
["10007022","James Radalj","1000/13981","Security & Emergency","23.02.2024","26.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CMNGRN","Corp Manager NT","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",7.5,null,null,1230.75]
["10007022","James Radalj","1000/13981","Security & Emergency","23.02.2024","26.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CMNGRO","Corp Manager OT","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",3.75,null,null,887.59]
["10007585","Kevin Gibb","1000/13030","Access and Outage Pl","15.02.2024","21.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CPSRAO","1000/CPSRAO","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",0.25,null,null,40.78]
["10007585","Kevin Gibb","1000/13030","Access and Outage Pl","19.02.2024","06.03.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CPSRAO","1000/CPSRAO","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",0.5,null,null,81.55]
["10007585","Kevin Gibb","1000/13030","Access and Outage Pl","20.02.2024","06.03.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CPSRAO","1000/CPSRAO","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",0.5,null,null,81.55]
["10007754","Grant Peters","1000/13104","Distribution Control","15.02.2024","09.03.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CMNGAO","1000/CMNGAO","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",1.5,null,null,330.84]
["10007758","Casey Websdale","1000/13723","Cust Prog Cent East","14.02.2024","19.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CSUPHN","1000/CSUPHN","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",8,null,null,558.79999999999995]
["10007758","Casey Websdale","1000/13723","Cust Prog Cent East","14.02.2024","19.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CSUPHO","1000/CSUPHO","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",1,null,null,107.46]
["10007758","Casey Websdale","1000/13723","Cust Prog Cent East","15.02.2024","19.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CSUPHN","1000/CSUPHN","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",8,null,null,558.79999999999995]
["10007758","Casey Websdale","1000/13723","Cust Prog Cent East","15.02.2024","19.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CSUPHO","1000/CSUPHO","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",2,null,null,214.92]
["10007758","Casey Websdale","1000/13723","Cust Prog Cent East","16.02.2024","19.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CSUPHN","1000/CSUPHN","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",8,null,null,558.79999999999995]
["10007758","Casey Websdale","1000/13723","Cust Prog Cent East","16.02.2024","19.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CSUPHO","1000/CSUPHO","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",2.5,null,null,268.64999999999998]
["10007797","Blake Sokaluk","1000/12182","Health, Safety E & Q","27.02.2024","04.03.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0020","Feb24 Storm Timesheet Tx 12014","4012895","4012895","0020","1000/CLEAAN","1000/CLEAAN","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",4.83,null,null,305.93]
["10007797","Blake Sokaluk","1000/12182","Health, Safety E & Q","29.02.2024","04.03.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0020","Feb24 Storm Timesheet Tx 12014","4012895","4012895","0020","1000/CLEAAN","1000/CLEAAN","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",9.5,null,null,760.19]
["10007798","Rebecca Fitzgerald","1000/12182","Health, Safety E & Q","15.02.2024","23.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CPSPAN","1000/CPSPAN","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",7.5,null,null,925.05]
["10007798","Rebecca Fitzgerald","1000/12182","Health, Safety E & Q","15.02.2024","23.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CPSPAO","1000/CPSPAO","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",4.4800000000000004,null,null,796.99]
["10007798","Rebecca Fitzgerald","1000/12182","Health, Safety E & Q","16.02.2024","23.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CPSPAN","1000/CPSPAN","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",7.5,null,null,925.05]
["10007798","Rebecca Fitzgerald","1000/12182","Health, Safety E & Q","16.02.2024","23.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CPSPAO","1000/CPSPAO","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",3.5,null,null,622.65]
["10007798","Rebecca Fitzgerald","1000/12182","Health, Safety E & Q","17.02.2024","23.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CPSPAO","1000/CPSPAO","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",11,null,null,1956.9]
["10007798","Rebecca Fitzgerald","1000/12182","Health, Safety E & Q","18.02.2024","23.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CPSPAO","1000/CPSPAO","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",11,null,null,1956.9]
["10007798","Rebecca Fitzgerald","1000/12182","Health, Safety E & Q","19.02.2024","08.03.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CPSPAN","1000/CPSPAN","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",7.5,null,null,925.05]
["10007798","Rebecca Fitzgerald","1000/12182","Health, Safety E & Q","19.02.2024","08.03.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CPSPAO","1000/CPSPAO","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",3.5,null,null,622.65]
["10007798","Rebecca Fitzgerald","1000/12182","Health, Safety E & Q","20.02.2024","08.03.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CPSPAN","1000/CPSPAN","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",8,null,null,925.04]
["10007798","Rebecca Fitzgerald","1000/12182","Health, Safety E & Q","20.02.2024","08.03.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CPSPAO","1000/CPSPAO","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",3.25,null,null,578.17999999999995]
["10007798","Rebecca Fitzgerald","1000/12182","Health, Safety E & Q","23.02.2024","08.03.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CPSPAN","1000/CPSPAN","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",7.5,null,null,925.05]
["10007920","Michael Sargent","1000/13104","Distribution Control","15.02.2024","20.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/DCONTN","Dxn Controller NT","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",12,null,null,1105.08]
["10008034","Senthil Selvapathy","1000/13031","Operations Optimisat","13.02.2024","23.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CLEAAO","1000/CLEAAO","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",3.5,null,null,511.63]
["10008034","Senthil Selvapathy","1000/13031","Operations Optimisat","14.02.2024","23.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CLEAAN","1000/CLEAAN","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",8,null,null,760.16]
["10008034","Senthil Selvapathy","1000/13031","Operations Optimisat","15.02.2024","23.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CLEAAN","1000/CLEAAN","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",7.5,null,null,760.13]
["10008034","Senthil Selvapathy","1000/13031","Operations Optimisat","15.02.2024","23.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CLEAAO","1000/CLEAAO","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",1.5,null,null,219.27]
["10008034","Senthil Selvapathy","1000/13031","Operations Optimisat","16.02.2024","23.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CLEAAN","1000/CLEAAN","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",7.5,null,null,760.13]
["10008034","Senthil Selvapathy","1000/13031","Operations Optimisat","16.02.2024","23.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CLEAAO","1000/CLEAAO","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",3,null,null,438.54]
["10008034","Senthil Selvapathy","1000/13031","Operations Optimisat","17.02.2024","23.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CLEAAO","1000/CLEAAO","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",11.5,null,null,1681.07]
["10008034","Senthil Selvapathy","1000/13031","Operations Optimisat","18.02.2024","23.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CLEAAO","1000/CLEAAO","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",4,null,null,584.72]
["10008034","Senthil Selvapathy","1000/13031","Operations Optimisat","19.02.2024","23.03.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CLEAAN","1000/CLEAAN","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",8,null,null,760.16]
["10008034","Senthil Selvapathy","1000/13031","Operations Optimisat","20.02.2024","23.03.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CLEAAN","1000/CLEAAN","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",7.5,null,null,760.13]
["10008034","Senthil Selvapathy","1000/13031","Operations Optimisat","20.02.2024","23.03.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CLEAAO","1000/CLEAAO","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",3,null,null,438.54]
["10008695","Nadia Joss","1000/16001","Inspection & Assessm","15.02.2024","19.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/AINSPN","Asset Inspector NT","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",8,null,null,570.48]
["10008695","Nadia Joss","1000/16001","Inspection & Assessm","15.02.2024","19.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/AINSPO","Asset Inspector OT","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",3.5,null,null,360.01]
["10008695","Nadia Joss","1000/16001","Inspection & Assessm","16.02.2024","19.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/AINSPN","Asset Inspector NT","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",8,null,null,570.48]
["10008695","Nadia Joss","1000/16001","Inspection & Assessm","16.02.2024","19.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/AINSPO","Asset Inspector OT","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",2.5,null,null,257.14999999999998]
["10008696","Braydon Sargent","1000/16001","Inspection & Assessm","15.02.2024","19.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/AINSPN","Asset Inspector NT","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",8,null,null,570.48]
["10008696","Braydon Sargent","1000/16001","Inspection & Assessm","16.02.2024","19.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/AINSPN","Asset Inspector NT","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",8,null,null,570.48]
["10008696","Braydon Sargent","1000/16001","Inspection & Assessm","16.02.2024","19.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/AINSPO","Asset Inspector OT","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",4,null,null,411.44]
["10008760","Renee Meson","1000/11517","Contract Manag Dist","14.02.2024","05.03.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CPSRVN","Corp Prof NT","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",7.5,null,null,882.9]
["10008760","Renee Meson","1000/11517","Contract Manag Dist","14.02.2024","05.03.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CPSRVO","Corp Prof OT","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",3.5,null,null,594.27]
["10008768","Jordan Greenway","1000/13936","Customer Connections","14.02.2024","19.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CSUPDN","1000/CSUPDN","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",0.5,null,null,30.34]
["10008892","James Wilks","1000/13260","Major Projects Trans","19.02.2024","23.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/PMNGRN","Project Manager NT","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",3,null,null,402.6]
["10008892","James Wilks","1000/13260","Major Projects Trans","19.02.2024","23.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/PMNGRO","Project Manager OT","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",5.5,null,null,1064.58]
["10008892","James Wilks","1000/13260","Major Projects Trans","20.02.2024","23.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/PMNGRN","Project Manager NT","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",4,null,null,473.68]
["10008892","James Wilks","1000/13260","Major Projects Trans","20.02.2024","23.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/PMNGRO","Project Manager OT","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",5,null,null,967.8]
["10008908","Sarah Hu","1000/12109","Customer Communicati","14.02.2024","01.03.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0110","Feb24 Storm Timesheet PC 12006","4012895","4012895","0110","1000/CPSEMN","Corp Semi Prof NT","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-4","Feb24 Storm Costs SR&CA PC 12006","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",12.5,null,null,712]
["10008908","Sarah Hu","1000/12109","Customer Communicati","15.02.2024","01.03.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0110","Feb24 Storm Timesheet PC 12006","4012895","4012895","0110","1000/CPSEMN","Corp Semi Prof NT","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-4","Feb24 Storm Costs SR&CA PC 12006","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",12.5,null,null,712]
["10008908","Sarah Hu","1000/12109","Customer Communicati","17.02.2024","01.03.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0110","Feb24 Storm Timesheet PC 12006","4012895","4012895","0110","1000/CPSEMN","Corp Semi Prof NT","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-4","Feb24 Storm Costs SR&CA PC 12006","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",9,null,null,711.99]
["10008908","Sarah Hu","1000/12109","Customer Communicati","18.02.2024","01.03.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0110","Feb24 Storm Timesheet PC 12006","4012895","4012895","0110","1000/CPSEMN","Corp Semi Prof NT","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-4","Feb24 Storm Costs SR&CA PC 12006","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",9,null,null,711.99]
["10008994","Yossaphol Thakranonthachai","1000/13936","Customer Connections","14.02.2024","16.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CSUPEN","1000/CSUPEN","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",1,null,null,62.69]
["10009496","Paulina Erceg","1000/12010","Engineering Solution","17.02.2024","21.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/PRENSO","Project Snr Eng OT","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",10.029999999999999,null,null,1469.9]
["10009496","Paulina Erceg","1000/12010","Engineering Solution","19.02.2024","26.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/PRENSN","Project Snr Eng NT","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",7.77,null,null,762.08]
["10009496","Paulina Erceg","1000/12010","Engineering Solution","20.02.2024","26.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/PRENSN","Project Snr Eng NT","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",7.37,null,null,748.87]
["10009496","Paulina Erceg","1000/12010","Engineering Solution","21.02.2024","26.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/PRENSN","Project Snr Eng NT","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",7.5,null,null,762.08]
["10009496","Paulina Erceg","1000/12010","Engineering Solution","21.02.2024","26.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/PRENSO","Project Snr Eng OT","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",2.35,null,null,344.39]
["10009559","James Missen","1000/16001","Inspection & Assessm","15.02.2024","19.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0100","Feb24 Storm Purchases Orders PC 12516","4012895","4012895","0100","1000/AINSPN","Asset Inspector NT","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-3","Feb24 Storm Costs F&G PC 12516","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",8,null,null,570.48]
["10009559","James Missen","1000/16001","Inspection & Assessm","15.02.2024","19.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0100","Feb24 Storm Purchases Orders PC 12516","4012895","4012895","0100","1000/AINSPO","Asset Inspector OT","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-3","Feb24 Storm Costs F&G PC 12516","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",3,null,null,308.58]
["10009559","James Missen","1000/16001","Inspection & Assessm","16.02.2024","19.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0100","Feb24 Storm Purchases Orders PC 12516","4012895","4012895","0100","1000/AINSPN","Asset Inspector NT","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-3","Feb24 Storm Costs F&G PC 12516","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",8,null,null,570.48]
["10009559","James Missen","1000/16001","Inspection & Assessm","16.02.2024","19.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0100","Feb24 Storm Purchases Orders PC 12516","4012895","4012895","0100","1000/AINSPO","Asset Inspector OT","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-3","Feb24 Storm Costs F&G PC 12516","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",2.5,null,null,257.14999999999998]
["10009559","James Missen","1000/16001","Inspection & Assessm","17.02.2024","19.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0100","Feb24 Storm Purchases Orders PC 12516","4012895","4012895","0100","1000/AINSPO","Asset Inspector OT","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-3","Feb24 Storm Costs F&G PC 12516","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",6.5,null,null,668.59]
["10009572","Matt Wernert","1000/16001","Inspection & Assessm","15.02.2024","20.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/AINSPN","Asset Inspector NT","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",8,null,null,570.48]
["10009572","Matt Wernert","1000/16001","Inspection & Assessm","15.02.2024","20.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/AINSPO","Asset Inspector OT","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",1,null,null,102.86]
["10009746","Jennifer Turner","1000/13187","Customer Engagement","14.02.2024","05.03.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CPSRAO","1000/CPSRAO","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",7,null,null,1141.7]
["10009746","Jennifer Turner","1000/13187","Customer Engagement","15.02.2024","05.03.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CPSRAO","1000/CPSRAO","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",3.5,null,null,570.85]
["10009746","Jennifer Turner","1000/13187","Customer Engagement","16.02.2024","05.03.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CPSRAO","1000/CPSRAO","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",2,null,null,326.2]
["10009746","Jennifer Turner","1000/13187","Customer Engagement","17.02.2024","05.03.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CPSRAO","1000/CPSRAO","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",3.5,null,null,570.85]
["10009746","Jennifer Turner","1000/13187","Customer Engagement","18.02.2024","05.03.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CPSRAO","1000/CPSRAO","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",10.5,null,null,1712.55]
["10009746","Jennifer Turner","1000/13187","Customer Engagement","19.02.2024","05.03.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CPSRAO","1000/CPSRAO","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",1.5,null,null,244.65]
["10009746","Jennifer Turner","1000/13187","Customer Engagement","20.02.2024","05.03.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CPSRAO","1000/CPSRAO","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",5,null,null,815.5]
["10009746","Jennifer Turner","1000/13187","Customer Engagement","21.02.2024","05.03.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CPSRAO","1000/CPSRAO","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",7,null,null,1141.7]
["10009746","Jennifer Turner","1000/13187","Customer Engagement","22.02.2024","05.03.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CPSRAO","1000/CPSRAO","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",3,null,null,489.3]
["10009746","Jennifer Turner","1000/13187","Customer Engagement","23.02.2024","05.03.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CPSRAO","1000/CPSRAO","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",1.5,null,null,244.65]
["10009746","Jennifer Turner","1000/13187","Customer Engagement","26.02.2024","13.03.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CPSRAN","1000/CPSRAN","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",8,null,null,904.64]
["10009746","Jennifer Turner","1000/13187","Customer Engagement","26.02.2024","13.03.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CPSRAO","1000/CPSRAO","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",2,null,null,326.2]
["10009806","Geoff Wigglesworth","1000/11517","Contract Manag Dist","14.02.2024","23.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CMNGRN","Corp Manager NT","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",14.5,null,null,1230.6199999999999]
["10009806","Geoff Wigglesworth","1000/11517","Contract Manag Dist","15.02.2024","23.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CMNGRN","Corp Manager NT","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",14.25,null,null,1230.77]
["10009806","Geoff Wigglesworth","1000/11517","Contract Manag Dist","16.02.2024","23.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CMNGRO","Corp Manager OT","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",4.5,null,null,1065.1099999999999]
["10009806","Geoff Wigglesworth","1000/11517","Contract Manag Dist","18.02.2024","23.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CMNGRO","Corp Manager OT","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",7.5,null,null,1775.18]
["10009806","Geoff Wigglesworth","1000/11517","Contract Manag Dist","19.02.2024","08.03.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CMNGRN","Corp Manager NT","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",15.5,null,null,1230.8599999999999]
["10009806","Geoff Wigglesworth","1000/11517","Contract Manag Dist","20.02.2024","08.03.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CMNGRN","Corp Manager NT","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",12,null,null,1230.72]
["10009806","Geoff Wigglesworth","1000/11517","Contract Manag Dist","21.02.2024","08.03.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0100","Feb24 Storm Purchases Orders PC 12516","4012895","4012895","0100","1000/CMNGRO","Corp Manager OT","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-3","Feb24 Storm Costs F&G PC 12516","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",4,null,null,946.76]
["10009806","Geoff Wigglesworth","1000/11517","Contract Manag Dist","22.02.2024","08.03.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CMNGRO","Corp Manager OT","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",6,null,null,1420.14]
["10009806","Geoff Wigglesworth","1000/11517","Contract Manag Dist","23.02.2024","08.03.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CMNGRO","Corp Manager OT","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",6,null,null,1420.14]
["10009806","Geoff Wigglesworth","1000/11517","Contract Manag Dist","24.02.2024","08.03.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CMNGRO","Corp Manager OT","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",10,null,null,2366.9]
["10009892","Christina Telya","1000/12047","Regulation&Policy-D","16.02.2024","04.03.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0110","Feb24 Storm Timesheet PC 12006","4012895","4012895","0110","1000/CPSRAO","1000/CPSRAO","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-4","Feb24 Storm Costs SR&CA PC 12006","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",8.5,null,null,1386.35]
["10009892","Christina Telya","1000/12047","Regulation&Policy-D","18.02.2024","04.03.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0110","Feb24 Storm Timesheet PC 12006","4012895","4012895","0110","1000/CPSRAO","1000/CPSRAO","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-4","Feb24 Storm Costs SR&CA PC 12006","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",7,null,null,1141.7]
["10009892","Christina Telya","1000/12047","Regulation&Policy-D","21.02.2024","26.03.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0110","Feb24 Storm Timesheet PC 12006","4012895","4012895","0110","1000/CPSRAO","1000/CPSRAO","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-4","Feb24 Storm Costs SR&CA PC 12006","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",8.25,null,null,1345.58]
["10009916","Hossein Sadafi","1000/13030","Access and Outage Pl","13.02.2024","19.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CPSVAO","1000/CPSVAO","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",7,null,null,1374.17]
["10009916","Hossein Sadafi","1000/13030","Access and Outage Pl","14.02.2024","19.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CPSVAO","1000/CPSVAO","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",4,null,null,785.24]
["10009916","Hossein Sadafi","1000/13030","Access and Outage Pl","15.02.2024","19.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CPSVAO","1000/CPSVAO","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",1.25,null,null,245.39]
["10009916","Hossein Sadafi","1000/13030","Access and Outage Pl","16.02.2024","19.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CPSVAO","1000/CPSVAO","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",2,null,null,392.62]
["10009916","Hossein Sadafi","1000/13030","Access and Outage Pl","17.02.2024","19.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CPSVAO","1000/CPSVAO","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",5.75,null,null,1128.78]
["10009916","Hossein Sadafi","1000/13030","Access and Outage Pl","18.02.2024","19.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CPSVAO","1000/CPSVAO","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",2,null,null,392.62]
["10009916","Hossein Sadafi","1000/13030","Access and Outage Pl","22.02.2024","26.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CPSVAO","1000/CPSVAO","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",6,null,null,1177.8599999999999]
["10009916","Hossein Sadafi","1000/13030","Access and Outage Pl","24.02.2024","26.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CPSVAO","1000/CPSVAO","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",1.5,null,null,294.47000000000003]
["10009940","James He","1000/13104","Distribution Control","13.02.2024","01.03.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CPSEMN","Corp Semi Prof NT","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",7.5,null,null,711.98]
["10009940","James He","1000/13104","Distribution Control","13.02.2024","01.03.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CPSEMO","Corp Semi Prof OT","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",3,null,null,410.76]
["10009940","James He","1000/13104","Distribution Control","14.02.2024","01.03.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CPSEMN","Corp Semi Prof NT","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",7.5,null,null,711.98]
["10009940","James He","1000/13104","Distribution Control","14.02.2024","01.03.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CPSEMO","Corp Semi Prof OT","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",2.5,null,null,342.3]
["10009940","James He","1000/13104","Distribution Control","15.02.2024","01.03.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CPSEMN","Corp Semi Prof NT","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",7.5,null,null,711.98]
["10009940","James He","1000/13104","Distribution Control","16.02.2024","01.03.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CPSEMN","Corp Semi Prof NT","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",7.5,null,null,711.98]
["10009940","James He","1000/13104","Distribution Control","19.02.2024","01.03.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CPSEMN","Corp Semi Prof NT","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",7.5,null,null,711.98]
["10009940","James He","1000/13104","Distribution Control","19.02.2024","01.03.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CPSEMO","Corp Semi Prof OT","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",1,null,null,136.91999999999999]
["10009940","James He","1000/13104","Distribution Control","21.02.2024","01.03.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CPSEMN","Corp Semi Prof NT","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",7.5,null,null,711.98]
["10009940","James He","1000/13104","Distribution Control","21.02.2024","01.03.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CPSEMO","Corp Semi Prof OT","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",2,null,null,273.83999999999997]
["10009940","James He","1000/13104","Distribution Control","23.02.2024","01.03.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CPSEMN","Corp Semi Prof NT","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",7.5,null,null,711.98]
["10009940","James He","1000/13104","Distribution Control","23.02.2024","01.03.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CPSEMO","Corp Semi Prof OT","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",1.5,null,null,205.38]
["10009951","Finlay Crantock","1000/12015","Future Networks Prog","14.02.2024","21.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/PRENSN","Project Snr Eng NT","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",7.5,null,null,762.08]
["10009958","Shelley Preen","1000/12029","Future Technology Pl","15.02.2024","19.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0030","Feb24 Storm Timesheet Net unknown 12014","4012895","4012895","0030","1000/CPSVAN","1000/CPSVAN","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",6.5,null,null,491.53]
["10009958","Shelley Preen","1000/12029","Future Technology Pl","16.02.2024","19.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0030","Feb24 Storm Timesheet Net unknown 12014","4012895","4012895","0030","1000/CPSVAN","1000/CPSVAN","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",7,null,null,529.34,null,null,null,null,"Immaterial"]
["10009958","Shelley Preen","1000/12029","Future Technology Pl","17.02.2024","19.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0030","Feb24 Storm Timesheet Net unknown 12014","4012895","4012895","0030","1000/CPSVAN","1000/CPSVAN","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",9.75,null,null,1020.73]
["10009958","Shelley Preen","1000/12029","Future Technology Pl","19.02.2024","26.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0030","Feb24 Storm Timesheet Net unknown 12014","4012895","4012895","0030","1000/CPSVAN","1000/CPSVAN","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",7,null,null,560.35]
["10009958","Shelley Preen","1000/12029","Future Technology Pl","23.02.2024","26.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0030","Feb24 Storm Timesheet Net unknown 12014","4012895","4012895","0030","1000/CPSVAN","1000/CPSVAN","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",7.5,null,null,1020.75]
["10009958","Shelley Preen","1000/12029","Future Technology Pl","02.04.2024","06.04.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0030","Feb24 Storm Timesheet Net unknown 12014","4012895","4012895","0030","1000/CPSVSN","Corp Prof Spec NT","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",null,null,8,null,null,1081.3599999999999]
["10010000","Olivia Harrington","1000/12120","Brand & Marketing","15.02.2024","12.03.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0110","Feb24 Storm Timesheet PC 12006","4012895","4012895","0110","1000/CSUPPN","Corp Support NT","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-4","Feb24 Storm Costs SR&CA PC 12006","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",7.5,null,null,620.25]
["10010000","Olivia Harrington","1000/12120","Brand & Marketing","15.02.2024","12.03.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0110","Feb24 Storm Timesheet PC 12006","4012895","4012895","0110","1000/CSUPPO","Corp Support OT","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-4","Feb24 Storm Costs SR&CA PC 12006","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",5.92,null,null,706.14]
["10010000","Olivia Harrington","1000/12120","Brand & Marketing","16.02.2024","12.03.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0110","Feb24 Storm Timesheet PC 12006","4012895","4012895","0110","1000/CSUPPN","Corp Support NT","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-4","Feb24 Storm Costs SR&CA PC 12006","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",7.5,null,null,620.25]
["10010000","Olivia Harrington","1000/12120","Brand & Marketing","16.02.2024","12.03.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0110","Feb24 Storm Timesheet PC 12006","4012895","4012895","0110","1000/CSUPPO","Corp Support OT","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-4","Feb24 Storm Costs SR&CA PC 12006","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",5.57,null,null,664.39]
["10010000","Olivia Harrington","1000/12120","Brand & Marketing","17.02.2024","12.03.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0110","Feb24 Storm Timesheet PC 12006","4012895","4012895","0110","1000/CSUPPO","Corp Support OT","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-4","Feb24 Storm Costs SR&CA PC 12006","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",9.23,null,null,1100.95]
["10010000","Olivia Harrington","1000/12120","Brand & Marketing","18.02.2024","12.03.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0110","Feb24 Storm Timesheet PC 12006","4012895","4012895","0110","1000/CSUPPO","Corp Support OT","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-4","Feb24 Storm Costs SR&CA PC 12006","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",2.0299999999999998,null,null,242.14]
["10010049","Justin Justin","1000/12028","Western Renewables L","19.02.2024","18.03.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0150","Feb24 Storm Timesheet PC 12388","4012895","4012895","0150","1000/CMNGRN","Corp Manager NT","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-6","Feb24 Storm Costs DFN PC 12388","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",3.5,null,null,574.35]
["10010049","Justin Justin","1000/12028","Western Renewables L","19.02.2024","18.03.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0150","Feb24 Storm Timesheet PC 12388","4012895","4012895","0150","1000/CMNGRO","Corp Manager OT","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-6","Feb24 Storm Costs DFN PC 12388","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",4.5,null,null,1065.1099999999999]
["10010049","Justin Justin","1000/12028","Western Renewables L","20.02.2024","18.03.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0150","Feb24 Storm Timesheet PC 12388","4012895","4012895","0150","1000/CMNGRN","Corp Manager NT","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-6","Feb24 Storm Costs DFN PC 12388","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",7.5,null,null,1230.75]
["10010049","Justin Justin","1000/12028","Western Renewables L","20.02.2024","18.03.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0150","Feb24 Storm Timesheet PC 12388","4012895","4012895","0150","1000/CMNGRO","Corp Manager OT","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-6","Feb24 Storm Costs DFN PC 12388","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",5,null,null,1183.45]
["10010049","Justin Justin","1000/12028","Western Renewables L","21.02.2024","18.03.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0150","Feb24 Storm Timesheet PC 12388","4012895","4012895","0150","1000/CMNGRN","Corp Manager NT","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-6","Feb24 Storm Costs DFN PC 12388","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",7.5,null,null,1230.75]
["10010049","Justin Justin","1000/12028","Western Renewables L","21.02.2024","18.03.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0150","Feb24 Storm Timesheet PC 12388","4012895","4012895","0150","1000/CMNGRO","Corp Manager OT","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-6","Feb24 Storm Costs DFN PC 12388","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",2,null,null,473.38]
["10010049","Justin Justin","1000/12028","Western Renewables L","22.02.2024","18.03.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0150","Feb24 Storm Timesheet PC 12388","4012895","4012895","0150","1000/CMNGRN","Corp Manager NT","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-6","Feb24 Storm Costs DFN PC 12388","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",3,null,null,492.3]
["10010049","Justin Justin","1000/12028","Western Renewables L","22.02.2024","18.03.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0150","Feb24 Storm Timesheet PC 12388","4012895","4012895","0150","1000/CMNGRO","Corp Manager OT","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-6","Feb24 Storm Costs DFN PC 12388","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",4.5,null,null,1065.1099999999999]
["10010081","Murtaza Latif","1000/13417","Network Planning","17.02.2024","06.03.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0070","Feb24 Storm Timesheet PC 12001","4012895","4012895","0070","1000/CPSPEO","Corp Prof Exp OT","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-2","Feb24 Storm Costs dNet PC 12001","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",11,null,null,2052.16]
["10010226","Jennifer Wilson","1000/12026","Partnering & Employe","17.02.2024","19.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0130","Feb24 Storm Timesheet PC 12306","4012895","4012895","0130","1000/CSUPHO","1000/CSUPHO","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-5","Feb24 Storm Costs People PC 12306","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",9.5,null,null,1020.87]
["10010226","Jennifer Wilson","1000/12026","Partnering & Employe","18.02.2024","19.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0130","Feb24 Storm Timesheet PC 12306","4012895","4012895","0130","1000/CSUPHO","1000/CSUPHO","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-5","Feb24 Storm Costs People PC 12306","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",9.25,null,null,994.01]
["10010226","Jennifer Wilson","1000/12026","Partnering & Employe","19.02.2024","28.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0130","Feb24 Storm Timesheet PC 12306","4012895","4012895","0130","1000/CSUPHO","1000/CSUPHO","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-5","Feb24 Storm Costs People PC 12306","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",5.75,null,null,617.9]
["10010226","Jennifer Wilson","1000/12026","Partnering & Employe","20.02.2024","28.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0130","Feb24 Storm Timesheet PC 12306","4012895","4012895","0130","1000/CSUPHN","1000/CSUPHN","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-5","Feb24 Storm Costs People PC 12306","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",7.5,null,null,558.83000000000004]
["10010226","Jennifer Wilson","1000/12026","Partnering & Employe","20.02.2024","28.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0130","Feb24 Storm Timesheet PC 12306","4012895","4012895","0130","1000/CSUPHO","1000/CSUPHO","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-5","Feb24 Storm Costs People PC 12306","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",5.5,null,null,591.03]
["10010226","Jennifer Wilson","1000/12026","Partnering & Employe","22.02.2024","28.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0130","Feb24 Storm Timesheet PC 12306","4012895","4012895","0130","1000/CSUPHN","1000/CSUPHN","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-5","Feb24 Storm Costs People PC 12306","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",7.5,null,null,558.83000000000004]
["10010226","Jennifer Wilson","1000/12026","Partnering & Employe","22.02.2024","28.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0130","Feb24 Storm Timesheet PC 12306","4012895","4012895","0130","1000/CSUPHO","1000/CSUPHO","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-5","Feb24 Storm Costs People PC 12306","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",6.25,null,null,671.63]
["10010226","Jennifer Wilson","1000/12026","Partnering & Employe","23.02.2024","28.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0130","Feb24 Storm Timesheet PC 12306","4012895","4012895","0130","1000/CSUPHN","1000/CSUPHN","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-5","Feb24 Storm Costs People PC 12306","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",7.5,null,null,558.83000000000004]
["10010226","Jennifer Wilson","1000/12026","Partnering & Employe","23.02.2024","28.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0130","Feb24 Storm Timesheet PC 12306","4012895","4012895","0130","1000/CSUPHO","1000/CSUPHO","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-5","Feb24 Storm Costs People PC 12306","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",3.5,null,null,376.11]
["10010247","Simon Jones","1000/13104","Distribution Control","15.02.2024","23.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/DCONTN","Dxn Controller NT","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",12.5,null,null,1105.1300000000001]
["10010247","Simon Jones","1000/13104","Distribution Control","16.02.2024","23.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/DCONTO","Dxn Controller OT","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",12.5,null,null,2656.5]
["10010250","Stephanie Astbury","1000/12412","Infrastructure Engin","15.02.2024","21.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0150","Feb24 Storm Timesheet PC 12388","4012895","4012895","0150","1000/CPSEAN","1000/CPSEAN","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-6","Feb24 Storm Costs DFN PC 12388","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",7.5,null,null,671.03]
["10010250","Stephanie Astbury","1000/12412","Infrastructure Engin","16.02.2024","21.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0150","Feb24 Storm Timesheet PC 12388","4012895","4012895","0150","1000/CPSEAN","1000/CPSEAN","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-6","Feb24 Storm Costs DFN PC 12388","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",8,null,null,671.04]
["10010250","Stephanie Astbury","1000/12412","Infrastructure Engin","17.02.2024","21.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0150","Feb24 Storm Timesheet PC 12388","4012895","4012895","0150","1000/CPSEAO","1000/CPSEAO","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-6","Feb24 Storm Costs DFN PC 12388","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",9,null,null,1161.45]
["10010250","Stephanie Astbury","1000/12412","Infrastructure Engin","18.02.2024","21.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0150","Feb24 Storm Timesheet PC 12388","4012895","4012895","0150","1000/CPSEAO","1000/CPSEAO","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-6","Feb24 Storm Costs DFN PC 12388","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",8,null,null,1032.4000000000001]
["10010250","Stephanie Astbury","1000/12412","Infrastructure Engin","20.02.2024","27.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0150","Feb24 Storm Timesheet PC 12388","4012895","4012895","0150","1000/CPSEAN","1000/CPSEAN","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-6","Feb24 Storm Costs DFN PC 12388","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",7.5,null,null,671.03]
["10010250","Stephanie Astbury","1000/12412","Infrastructure Engin","22.02.2024","27.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0150","Feb24 Storm Timesheet PC 12388","4012895","4012895","0150","1000/CPSEAN","1000/CPSEAN","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-6","Feb24 Storm Costs DFN PC 12388","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",8.5,null,null,671.08]
["10010269","Evelyn Vettivelu","1000/12109","Customer Communicati","13.02.2024","14.03.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0110","Feb24 Storm Timesheet PC 12006","4012895","4012895","0110","1000/CPSPEN","Corp Prof Exp NT","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-4","Feb24 Storm Costs SR&CA PC 12006","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",7.5,null,null,970.05]
["10010269","Evelyn Vettivelu","1000/12109","Customer Communicati","13.02.2024","14.03.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0110","Feb24 Storm Timesheet PC 12006","4012895","4012895","0110","1000/CPSPEO","Corp Prof Exp OT","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-4","Feb24 Storm Costs SR&CA PC 12006","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",7,null,null,1305.92]
["10010269","Evelyn Vettivelu","1000/12109","Customer Communicati","14.02.2024","14.03.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0110","Feb24 Storm Timesheet PC 12006","4012895","4012895","0110","1000/CPSPEN","Corp Prof Exp NT","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-4","Feb24 Storm Costs SR&CA PC 12006","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",7.5,null,null,970.05]
["10010269","Evelyn Vettivelu","1000/12109","Customer Communicati","14.02.2024","14.03.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0110","Feb24 Storm Timesheet PC 12006","4012895","4012895","0110","1000/CPSPEO","Corp Prof Exp OT","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-4","Feb24 Storm Costs SR&CA PC 12006","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",7,null,null,1305.92]
["10010269","Evelyn Vettivelu","1000/12109","Customer Communicati","15.02.2024","14.03.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0110","Feb24 Storm Timesheet PC 12006","4012895","4012895","0110","1000/CPSPEN","Corp Prof Exp NT","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-4","Feb24 Storm Costs SR&CA PC 12006","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",7.5,null,null,970.05]
["10010269","Evelyn Vettivelu","1000/12109","Customer Communicati","15.02.2024","14.03.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0110","Feb24 Storm Timesheet PC 12006","4012895","4012895","0110","1000/CPSPEO","Corp Prof Exp OT","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-4","Feb24 Storm Costs SR&CA PC 12006","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",5.5,null,null,1026.08]
["10010269","Evelyn Vettivelu","1000/12109","Customer Communicati","17.02.2024","14.03.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0110","Feb24 Storm Timesheet PC 12006","4012895","4012895","0110","1000/CPSPEO","Corp Prof Exp OT","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-4","Feb24 Storm Costs SR&CA PC 12006","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",9,null,null,1679.04]
["10010269","Evelyn Vettivelu","1000/12109","Customer Communicati","20.02.2024","14.03.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0110","Feb24 Storm Timesheet PC 12006","4012895","4012895","0110","1000/CPSPEN","Corp Prof Exp NT","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-4","Feb24 Storm Costs SR&CA PC 12006","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",7.5,null,null,970.05]
["10010269","Evelyn Vettivelu","1000/12109","Customer Communicati","20.02.2024","14.03.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0110","Feb24 Storm Timesheet PC 12006","4012895","4012895","0110","1000/CPSPEO","Corp Prof Exp OT","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-4","Feb24 Storm Costs SR&CA PC 12006","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",4.5,null,null,839.52]
["10010269","Evelyn Vettivelu","1000/12109","Customer Communicati","22.02.2024","14.03.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0110","Feb24 Storm Timesheet PC 12006","4012895","4012895","0110","1000/CPSPEN","Corp Prof Exp NT","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-4","Feb24 Storm Costs SR&CA PC 12006","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",8,null,null,970.08]
["10010269","Evelyn Vettivelu","1000/12109","Customer Communicati","23.02.2024","14.03.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0110","Feb24 Storm Timesheet PC 12006","4012895","4012895","0110","1000/CPSPEN","Corp Prof Exp NT","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-4","Feb24 Storm Costs SR&CA PC 12006","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",7.5,null,null,970.05]
["10010269","Evelyn Vettivelu","1000/12109","Customer Communicati","23.02.2024","14.03.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0110","Feb24 Storm Timesheet PC 12006","4012895","4012895","0110","1000/CPSPEO","Corp Prof Exp OT","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-4","Feb24 Storm Costs SR&CA PC 12006","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",2.5,null,null,466.4]
["10010269","Evelyn Vettivelu","1000/12109","Customer Communicati","26.02.2024","14.03.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0110","Feb24 Storm Timesheet PC 12006","4012895","4012895","0110","1000/CPSPEN","Corp Prof Exp NT","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-4","Feb24 Storm Costs SR&CA PC 12006","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",7.5,null,null,970.05]
["10010269","Evelyn Vettivelu","1000/12109","Customer Communicati","26.02.2024","14.03.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0110","Feb24 Storm Timesheet PC 12006","4012895","4012895","0110","1000/CPSPEO","Corp Prof Exp OT","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-4","Feb24 Storm Costs SR&CA PC 12006","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",3.5,null,null,652.96]
["10010269","Evelyn Vettivelu","1000/12109","Customer Communicati","27.02.2024","14.03.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0110","Feb24 Storm Timesheet PC 12006","4012895","4012895","0110","1000/CPSPEN","Corp Prof Exp NT","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-4","Feb24 Storm Costs SR&CA PC 12006","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",7.5,null,null,970.05]
["10010269","Evelyn Vettivelu","1000/12109","Customer Communicati","27.02.2024","14.03.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0110","Feb24 Storm Timesheet PC 12006","4012895","4012895","0110","1000/CPSPEO","Corp Prof Exp OT","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-4","Feb24 Storm Costs SR&CA PC 12006","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",3,null,null,559.67999999999995]
["10010269","Evelyn Vettivelu","1000/12109","Customer Communicati","29.02.2024","14.03.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0110","Feb24 Storm Timesheet PC 12006","4012895","4012895","0110","1000/CPSPEN","Corp Prof Exp NT","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-4","Feb24 Storm Costs SR&CA PC 12006","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",7.5,null,null,970.05]
["10010269","Evelyn Vettivelu","1000/12109","Customer Communicati","29.02.2024","14.03.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0110","Feb24 Storm Timesheet PC 12006","4012895","4012895","0110","1000/CPSPEO","Corp Prof Exp OT","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-4","Feb24 Storm Costs SR&CA PC 12006","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",2.5,null,null,466.4]
["10010359","Tajammul Hussain Bangash","1000/13104","Distribution Control","15.02.2024","20.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/DCONTN","Dxn Controller NT","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",12,null,null,1105.08]
["10010359","Tajammul Hussain Bangash","1000/13104","Distribution Control","16.02.2024","20.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/DCONTO","Dxn Controller OT","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",12,null,null,2550.2399999999998]
["10010382","John Dour","1000/13619","Networks Connections","13.02.2024","26.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0070","Feb24 Storm Timesheet PC 12001","4012895","4012895","0070","1000/CPSVSN","Corp Prof Spec NT","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-2","Feb24 Storm Costs dNet PC 12001","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",8.5,null,null,875.42]
["10010382","John Dour","1000/13619","Networks Connections","14.02.2024","26.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0070","Feb24 Storm Timesheet PC 12001","4012895","4012895","0070","1000/CPSVSN","Corp Prof Spec NT","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-2","Feb24 Storm Costs dNet PC 12001","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",14,null,null,1081.3599999999999]
["10010382","John Dour","1000/13619","Networks Connections","15.02.2024","26.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0070","Feb24 Storm Timesheet PC 12001","4012895","4012895","0070","1000/CPSVSN","Corp Prof Spec NT","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-2","Feb24 Storm Costs dNet PC 12001","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",4,null,null,576.72]
["10010390","John Coggan","1000/13175","Customer Serv & Reso","13.02.2024","23.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0150","Feb24 Storm Timesheet PC 12388","4012895","4012895","0150","1000/CPSVSO","Corp Prof Spec OT","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-6","Feb24 Storm Costs DFN PC 12388","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",6,null,null,1247.7]
["10010390","John Coggan","1000/13175","Customer Serv & Reso","14.02.2024","23.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0150","Feb24 Storm Timesheet PC 12388","4012895","4012895","0150","1000/CPSVSO","Corp Prof Spec OT","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-6","Feb24 Storm Costs DFN PC 12388","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",5,null,null,1039.75]
["10010390","John Coggan","1000/13175","Customer Serv & Reso","15.02.2024","23.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0150","Feb24 Storm Timesheet PC 12388","4012895","4012895","0150","1000/CPSVSO","Corp Prof Spec OT","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-6","Feb24 Storm Costs DFN PC 12388","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",5.5,null,null,1143.73]
["10010390","John Coggan","1000/13175","Customer Serv & Reso","17.02.2024","23.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0150","Feb24 Storm Timesheet PC 12388","4012895","4012895","0150","1000/CPSVSO","Corp Prof Spec OT","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-6","Feb24 Storm Costs DFN PC 12388","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",14,null,null,2911.3]
["10010390","John Coggan","1000/13175","Customer Serv & Reso","18.02.2024","23.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0150","Feb24 Storm Timesheet PC 12388","4012895","4012895","0150","1000/CPSVSO","Corp Prof Spec OT","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-6","Feb24 Storm Costs DFN PC 12388","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",12,null,null,2495.4]
["10010390","John Coggan","1000/13175","Customer Serv & Reso","19.02.2024","23.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0150","Feb24 Storm Timesheet PC 12388","4012895","4012895","0150","1000/CPSVSO","Corp Prof Spec OT","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-6","Feb24 Storm Costs DFN PC 12388","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",3,null,null,623.85]
["10010390","John Coggan","1000/13175","Customer Serv & Reso","20.02.2024","23.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0150","Feb24 Storm Timesheet PC 12388","4012895","4012895","0150","1000/CPSVSO","Corp Prof Spec OT","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-6","Feb24 Storm Costs DFN PC 12388","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",3,null,null,623.85]
["10010477","Rachael Anthony","1000/13187","Customer Engagement","13.02.2024","01.03.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CMNGRO","Corp Manager OT","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",3.5,null,null,828.42]
["10010477","Rachael Anthony","1000/13187","Customer Engagement","14.02.2024","01.03.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CMNGRO","Corp Manager OT","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",5.5,null,null,1301.8]
["10010477","Rachael Anthony","1000/13187","Customer Engagement","15.02.2024","01.03.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CMNGRO","Corp Manager OT","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",5,null,null,1183.45]
["10010477","Rachael Anthony","1000/13187","Customer Engagement","16.02.2024","01.03.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CMNGRO","Corp Manager OT","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",11,null,null,2603.59]
["10010477","Rachael Anthony","1000/13187","Customer Engagement","17.02.2024","01.03.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CMNGRO","Corp Manager OT","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",7.5,null,null,1775.18]
["10010477","Rachael Anthony","1000/13187","Customer Engagement","18.02.2024","01.03.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CMNGRO","Corp Manager OT","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",8,null,null,1893.52]
["10010477","Rachael Anthony","1000/13187","Customer Engagement","19.02.2024","08.03.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CMNGRN","Corp Manager NT","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",12.25,null,null,1558.94]
["10010477","Rachael Anthony","1000/13187","Customer Engagement","20.02.2024","08.03.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CMNGRN","Corp Manager NT","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",12.75,null,null,1558.95]
["10010477","Rachael Anthony","1000/13187","Customer Engagement","21.02.2024","08.03.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CMNGRN","Corp Manager NT","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",13.25,null,null,1559]
["10010477","Rachael Anthony","1000/13187","Customer Engagement","22.02.2024","08.03.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CMNGRN","Corp Manager NT","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",11.75,null,null,1558.88]
["10010477","Rachael Anthony","1000/13187","Customer Engagement","23.02.2024","08.03.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CMNGRN","Corp Manager NT","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",9,null,null,1476.9]
["10010477","Rachael Anthony","1000/13187","Customer Engagement","24.02.2024","08.03.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CMNGRN","Corp Manager NT","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",5,null,null,820.5]
["10010477","Rachael Anthony","1000/13187","Customer Engagement","25.02.2024","08.03.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CMNGRN","Corp Manager NT","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",5.5,null,null,902.55]
["10010477","Rachael Anthony","1000/13187","Customer Engagement","26.02.2024","08.03.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CMNGRN","Corp Manager NT","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",10,null,null,1559]
["10010477","Rachael Anthony","1000/13187","Customer Engagement","27.02.2024","08.03.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CMNGRN","Corp Manager NT","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",10,null,null,1559]
["10010509","Amanda Williams","1000/12273","Risk & Internal Audi","15.02.2024","01.03.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0070","Feb24 Storm Timesheet PC 12001","4012895","4012895","0070","1000/CSENAN","1000/CSENAN","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-2","Feb24 Storm Costs dNet PC 12001","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",8,null,null,1343.36]
["10010509","Amanda Williams","1000/12273","Risk & Internal Audi","16.02.2024","01.03.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0070","Feb24 Storm Timesheet PC 12001","4012895","4012895","0070","1000/CSENAN","1000/CSENAN","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-2","Feb24 Storm Costs dNet PC 12001","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",8,null,null,1343.36]
["10010509","Amanda Williams","1000/12273","Risk & Internal Audi","17.02.2024","01.03.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0070","Feb24 Storm Timesheet PC 12001","4012895","4012895","0070","1000/CSENAN","1000/CSENAN","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-2","Feb24 Storm Costs dNet PC 12001","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",8,null,null,1343.36]
["10010509","Amanda Williams","1000/12273","Risk & Internal Audi","18.02.2024","01.03.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0070","Feb24 Storm Timesheet PC 12001","4012895","4012895","0070","1000/CSENAN","1000/CSENAN","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-2","Feb24 Storm Costs dNet PC 12001","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",8,null,null,1343.36]
["10010512","Nicci de Ryk","1000/12030","Corporate Communicat","13.02.2024","23.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0110","Feb24 Storm Timesheet PC 12006","4012895","4012895","0110","1000/CMNGAN","1000/CMNGAN","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-4","Feb24 Storm Costs SR&CA PC 12006","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",7,null,null,1070.44]
["10010512","Nicci de Ryk","1000/12030","Corporate Communicat","13.02.2024","23.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0110","Feb24 Storm Timesheet PC 12006","4012895","4012895","0110","1000/CMNGAO","1000/CMNGAO","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-4","Feb24 Storm Costs SR&CA PC 12006","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",7,null,null,1543.92]
["10010512","Nicci de Ryk","1000/12030","Corporate Communicat","14.02.2024","23.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0110","Feb24 Storm Timesheet PC 12006","4012895","4012895","0110","1000/CMNGAN","1000/CMNGAN","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-4","Feb24 Storm Costs SR&CA PC 12006","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",7.5,null,null,1146.9000000000001]
["10010512","Nicci de Ryk","1000/12030","Corporate Communicat","14.02.2024","23.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0110","Feb24 Storm Timesheet PC 12006","4012895","4012895","0110","1000/CMNGAO","1000/CMNGAO","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-4","Feb24 Storm Costs SR&CA PC 12006","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",9,null,null,1985.04]
["10010512","Nicci de Ryk","1000/12030","Corporate Communicat","15.02.2024","23.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0110","Feb24 Storm Timesheet PC 12006","4012895","4012895","0110","1000/CMNGAN","1000/CMNGAN","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-4","Feb24 Storm Costs SR&CA PC 12006","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",7.5,null,null,1146.9000000000001]
["10010512","Nicci de Ryk","1000/12030","Corporate Communicat","15.02.2024","23.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0110","Feb24 Storm Timesheet PC 12006","4012895","4012895","0110","1000/CMNGAO","1000/CMNGAO","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-4","Feb24 Storm Costs SR&CA PC 12006","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",8.5,null,null,1874.76]
["10010512","Nicci de Ryk","1000/12030","Corporate Communicat","16.02.2024","23.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0110","Feb24 Storm Timesheet PC 12006","4012895","4012895","0110","1000/CMNGAN","1000/CMNGAN","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-4","Feb24 Storm Costs SR&CA PC 12006","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",7.5,null,null,1146.9000000000001]
["10010512","Nicci de Ryk","1000/12030","Corporate Communicat","16.02.2024","23.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0110","Feb24 Storm Timesheet PC 12006","4012895","4012895","0110","1000/CMNGAO","1000/CMNGAO","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-4","Feb24 Storm Costs SR&CA PC 12006","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",8.5,null,null,1874.76]
["10010512","Nicci de Ryk","1000/12030","Corporate Communicat","17.02.2024","23.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0110","Feb24 Storm Timesheet PC 12006","4012895","4012895","0110","1000/CMNGAO","1000/CMNGAO","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-4","Feb24 Storm Costs SR&CA PC 12006","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",11,null,null,2426.16]
["10010512","Nicci de Ryk","1000/12030","Corporate Communicat","18.02.2024","23.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0110","Feb24 Storm Timesheet PC 12006","4012895","4012895","0110","1000/CMNGAO","1000/CMNGAO","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-4","Feb24 Storm Costs SR&CA PC 12006","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",10,null,null,2205.6]
["10010512","Nicci de Ryk","1000/12030","Corporate Communicat","19.02.2024","06.03.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0110","Feb24 Storm Timesheet PC 12006","4012895","4012895","0110","1000/CMNGAN","1000/CMNGAN","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-4","Feb24 Storm Costs SR&CA PC 12006","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",7.5,null,null,1146.9000000000001]
["10010512","Nicci de Ryk","1000/12030","Corporate Communicat","19.02.2024","06.03.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0110","Feb24 Storm Timesheet PC 12006","4012895","4012895","0110","1000/CMNGAO","1000/CMNGAO","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-4","Feb24 Storm Costs SR&CA PC 12006","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",6.5,null,null,1433.64]
["10010512","Nicci de Ryk","1000/12030","Corporate Communicat","20.02.2024","06.03.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0110","Feb24 Storm Timesheet PC 12006","4012895","4012895","0110","1000/CMNGAN","1000/CMNGAN","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-4","Feb24 Storm Costs SR&CA PC 12006","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",7.5,null,null,1146.9000000000001]
["10010512","Nicci de Ryk","1000/12030","Corporate Communicat","20.02.2024","06.03.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0110","Feb24 Storm Timesheet PC 12006","4012895","4012895","0110","1000/CMNGAO","1000/CMNGAO","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-4","Feb24 Storm Costs SR&CA PC 12006","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",6,null,null,1323.36]
["10010512","Nicci de Ryk","1000/12030","Corporate Communicat","22.02.2024","06.03.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0110","Feb24 Storm Timesheet PC 12006","4012895","4012895","0110","1000/CMNGAN","1000/CMNGAN","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-4","Feb24 Storm Costs SR&CA PC 12006","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",7.5,null,null,1146.9000000000001]
["10010512","Nicci de Ryk","1000/12030","Corporate Communicat","22.02.2024","06.03.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0110","Feb24 Storm Timesheet PC 12006","4012895","4012895","0110","1000/CMNGAO","1000/CMNGAO","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-4","Feb24 Storm Costs SR&CA PC 12006","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",5,null,null,1102.8]
["10010512","Nicci de Ryk","1000/12030","Corporate Communicat","23.02.2024","06.03.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0110","Feb24 Storm Timesheet PC 12006","4012895","4012895","0110","1000/CMNGAN","1000/CMNGAN","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-4","Feb24 Storm Costs SR&CA PC 12006","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",7.5,null,null,1146.9000000000001]
["10010512","Nicci de Ryk","1000/12030","Corporate Communicat","23.02.2024","06.03.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0110","Feb24 Storm Timesheet PC 12006","4012895","4012895","0110","1000/CMNGAO","1000/CMNGAO","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-4","Feb24 Storm Costs SR&CA PC 12006","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",4.5,null,null,992.52]
["10010512","Nicci de Ryk","1000/12030","Corporate Communicat","24.02.2024","06.03.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CMNGAO","1000/CMNGAO","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",4,null,null,882.24]
["10010512","Nicci de Ryk","1000/12030","Corporate Communicat","25.02.2024","06.03.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0120","Feb24 Storm Purchases Orders PC 12006","4012895","4012895","0120","1000/CMNGAO","1000/CMNGAO","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-4","Feb24 Storm Costs SR&CA PC 12006","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",1.5,null,null,330.84]
["10010527","Camille Beloria","1000/13378","Major Projects Distr","13.02.2024","27.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0030","Feb24 Storm Timesheet Net unknown 12014","4012895","4012895","0030","1000/CSUPCN","1000/CSUPCN","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",5,null,null,292.05]
["10010527","Camille Beloria","1000/13378","Major Projects Distr","14.02.2024","27.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0030","Feb24 Storm Timesheet Net unknown 12014","4012895","4012895","0030","1000/CSUPCN","1000/CSUPCN","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",7.5,null,null,438.08]
["10010527","Camille Beloria","1000/13378","Major Projects Distr","15.02.2024","27.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0030","Feb24 Storm Timesheet Net unknown 12014","4012895","4012895","0030","1000/CSUPCN","1000/CSUPCN","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",8,null,null,438.08]
["10010527","Camille Beloria","1000/13378","Major Projects Distr","18.02.2024","27.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0030","Feb24 Storm Timesheet Net unknown 12014","4012895","4012895","0030","1000/CSUPCO","1000/CSUPCO","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",7.5,null,null,631.79999999999995]
["10010527","Camille Beloria","1000/13378","Major Projects Distr","22.02.2024","26.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0030","Feb24 Storm Timesheet Net unknown 12014","4012895","4012895","0030","1000/CSUPCN","1000/CSUPCN","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",7.5,null,null,438.08]
["10010527","Camille Beloria","1000/13378","Major Projects Distr","23.02.2024","26.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0030","Feb24 Storm Timesheet Net unknown 12014","4012895","4012895","0030","1000/CSUPCN","1000/CSUPCN","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",7,null,null,408.87]
["10010560","Ryan Kaal","1000/13104","Distribution Control","20.02.2024","20.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CLEADN","Corp Ops Lead NT","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",12,null,null,811.56]
["10010575","Monica Daniel","1000/12109","Customer Communicati","13.02.2024","04.03.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0110","Feb24 Storm Timesheet PC 12006","4012895","4012895","0110","1000/CLEAAO","1000/CLEAAO","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-4","Feb24 Storm Costs SR&CA PC 12006","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",4,null,null,584.72]
["10010575","Monica Daniel","1000/12109","Customer Communicati","14.02.2024","04.03.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0110","Feb24 Storm Timesheet PC 12006","4012895","4012895","0110","1000/CLEAAN","1000/CLEAAN","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-4","Feb24 Storm Costs SR&CA PC 12006","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",7.5,null,null,760.13]
["10010575","Monica Daniel","1000/12109","Customer Communicati","14.02.2024","04.03.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0110","Feb24 Storm Timesheet PC 12006","4012895","4012895","0110","1000/CLEAAO","1000/CLEAAO","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-4","Feb24 Storm Costs SR&CA PC 12006","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",5,null,null,730.9]
["10010575","Monica Daniel","1000/12109","Customer Communicati","15.02.2024","04.03.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0110","Feb24 Storm Timesheet PC 12006","4012895","4012895","0110","1000/CLEAAN","1000/CLEAAN","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-4","Feb24 Storm Costs SR&CA PC 12006","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",7.5,null,null,760.13]
["10010575","Monica Daniel","1000/12109","Customer Communicati","15.02.2024","04.03.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0110","Feb24 Storm Timesheet PC 12006","4012895","4012895","0110","1000/CLEAAO","1000/CLEAAO","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-4","Feb24 Storm Costs SR&CA PC 12006","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",2,null,null,292.36]
["10010575","Monica Daniel","1000/12109","Customer Communicati","16.02.2024","04.03.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0110","Feb24 Storm Timesheet PC 12006","4012895","4012895","0110","1000/CLEAAN","1000/CLEAAN","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-4","Feb24 Storm Costs SR&CA PC 12006","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",7.5,null,null,760.13]
["10010575","Monica Daniel","1000/12109","Customer Communicati","16.02.2024","04.03.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0110","Feb24 Storm Timesheet PC 12006","4012895","4012895","0110","1000/CLEAAO","1000/CLEAAO","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-4","Feb24 Storm Costs SR&CA PC 12006","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",5.5,null,null,803.99]
["10010575","Monica Daniel","1000/12109","Customer Communicati","17.02.2024","04.03.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0110","Feb24 Storm Timesheet PC 12006","4012895","4012895","0110","1000/CLEAAO","1000/CLEAAO","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-4","Feb24 Storm Costs SR&CA PC 12006","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",4,null,null,584.72]
["10010575","Monica Daniel","1000/12109","Customer Communicati","18.02.2024","04.03.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0110","Feb24 Storm Timesheet PC 12006","4012895","4012895","0110","1000/CLEAAO","1000/CLEAAO","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-4","Feb24 Storm Costs SR&CA PC 12006","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",7,null,null,1023.26]
["10010575","Monica Daniel","1000/12109","Customer Communicati","19.02.2024","04.03.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0110","Feb24 Storm Timesheet PC 12006","4012895","4012895","0110","1000/CLEAAN","1000/CLEAAN","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-4","Feb24 Storm Costs SR&CA PC 12006","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",7.5,null,null,760.13]
["10010575","Monica Daniel","1000/12109","Customer Communicati","19.02.2024","04.03.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0110","Feb24 Storm Timesheet PC 12006","4012895","4012895","0110","1000/CLEAAO","1000/CLEAAO","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-4","Feb24 Storm Costs SR&CA PC 12006","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",2.5,null,null,365.45]
["10010575","Monica Daniel","1000/12109","Customer Communicati","20.02.2024","04.03.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0110","Feb24 Storm Timesheet PC 12006","4012895","4012895","0110","1000/CLEAAN","1000/CLEAAN","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-4","Feb24 Storm Costs SR&CA PC 12006","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",7.5,null,null,760.13]
["10010575","Monica Daniel","1000/12109","Customer Communicati","20.02.2024","04.03.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0110","Feb24 Storm Timesheet PC 12006","4012895","4012895","0110","1000/CLEAAO","1000/CLEAAO","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-4","Feb24 Storm Costs SR&CA PC 12006","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",4.5,null,null,657.81]
["10010575","Monica Daniel","1000/12109","Customer Communicati","21.02.2024","04.03.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0110","Feb24 Storm Timesheet PC 12006","4012895","4012895","0110","1000/CLEAAN","1000/CLEAAN","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-4","Feb24 Storm Costs SR&CA PC 12006","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",7.5,null,null,760.13]
["10010575","Monica Daniel","1000/12109","Customer Communicati","21.02.2024","04.03.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0110","Feb24 Storm Timesheet PC 12006","4012895","4012895","0110","1000/CLEAAO","1000/CLEAAO","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-4","Feb24 Storm Costs SR&CA PC 12006","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",6.5,null,null,950.17]
["10010575","Monica Daniel","1000/12109","Customer Communicati","22.02.2024","04.03.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0110","Feb24 Storm Timesheet PC 12006","4012895","4012895","0110","1000/CLEAAN","1000/CLEAAN","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-4","Feb24 Storm Costs SR&CA PC 12006","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",4.25,null,null,430.74]
["10010575","Monica Daniel","1000/12109","Customer Communicati","23.02.2024","04.03.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0110","Feb24 Storm Timesheet PC 12006","4012895","4012895","0110","1000/CLEAAN","1000/CLEAAN","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-4","Feb24 Storm Costs SR&CA PC 12006","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",4.75,null,null,481.42]
["10010589","Monica Hope","1000/12109","Customer Communicati","14.02.2024","08.03.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0110","Feb24 Storm Timesheet PC 12006","4012895","4012895","0110","1000/CSUPHN","1000/CSUPHN","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-4","Feb24 Storm Costs SR&CA PC 12006","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",7.5,null,null,558.83000000000004]
["10010589","Monica Hope","1000/12109","Customer Communicati","14.02.2024","08.03.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0110","Feb24 Storm Timesheet PC 12006","4012895","4012895","0110","1000/CSUPHO","1000/CSUPHO","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-4","Feb24 Storm Costs SR&CA PC 12006","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",2,null,null,214.92]
["10010589","Monica Hope","1000/12109","Customer Communicati","15.02.2024","08.03.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0110","Feb24 Storm Timesheet PC 12006","4012895","4012895","0110","1000/CSUPHN","1000/CSUPHN","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-4","Feb24 Storm Costs SR&CA PC 12006","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",7.5,null,null,558.83000000000004]
["10010589","Monica Hope","1000/12109","Customer Communicati","15.02.2024","08.03.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0110","Feb24 Storm Timesheet PC 12006","4012895","4012895","0110","1000/CSUPHO","1000/CSUPHO","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-4","Feb24 Storm Costs SR&CA PC 12006","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",6,null,null,644.76]
["10010589","Monica Hope","1000/12109","Customer Communicati","16.02.2024","08.03.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0110","Feb24 Storm Timesheet PC 12006","4012895","4012895","0110","1000/CSUPHN","1000/CSUPHN","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-4","Feb24 Storm Costs SR&CA PC 12006","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",7.5,null,null,558.83000000000004]
["10010589","Monica Hope","1000/12109","Customer Communicati","16.02.2024","08.03.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0110","Feb24 Storm Timesheet PC 12006","4012895","4012895","0110","1000/CSUPHO","1000/CSUPHO","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-4","Feb24 Storm Costs SR&CA PC 12006","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",2.5,null,null,268.64999999999998]
["10010589","Monica Hope","1000/12109","Customer Communicati","17.02.2024","08.03.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0110","Feb24 Storm Timesheet PC 12006","4012895","4012895","0110","1000/CSUPHO","1000/CSUPHO","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-4","Feb24 Storm Costs SR&CA PC 12006","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",2,null,null,214.92]
["10010589","Monica Hope","1000/12109","Customer Communicati","18.02.2024","08.03.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0110","Feb24 Storm Timesheet PC 12006","4012895","4012895","0110","1000/CSUPHO","1000/CSUPHO","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-4","Feb24 Storm Costs SR&CA PC 12006","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",3.75,null,null,402.98]
["10010589","Monica Hope","1000/12109","Customer Communicati","19.02.2024","04.03.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0110","Feb24 Storm Timesheet PC 12006","4012895","4012895","0110","1000/CSUPHN","1000/CSUPHN","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-4","Feb24 Storm Costs SR&CA PC 12006","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",7.5,null,null,558.83000000000004]
["10010589","Monica Hope","1000/12109","Customer Communicati","19.02.2024","04.03.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0110","Feb24 Storm Timesheet PC 12006","4012895","4012895","0110","1000/CSUPHO","1000/CSUPHO","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-4","Feb24 Storm Costs SR&CA PC 12006","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",2.5,null,null,268.64999999999998]
["10010589","Monica Hope","1000/12109","Customer Communicati","20.02.2024","04.03.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0110","Feb24 Storm Timesheet PC 12006","4012895","4012895","0110","1000/CSUPHN","1000/CSUPHN","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-4","Feb24 Storm Costs SR&CA PC 12006","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",7.5,null,null,558.83000000000004]
["10010589","Monica Hope","1000/12109","Customer Communicati","20.02.2024","04.03.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0110","Feb24 Storm Timesheet PC 12006","4012895","4012895","0110","1000/CSUPHO","1000/CSUPHO","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-4","Feb24 Storm Costs SR&CA PC 12006","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",1.5,null,null,161.19]
["10010589","Monica Hope","1000/12109","Customer Communicati","21.02.2024","04.03.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0110","Feb24 Storm Timesheet PC 12006","4012895","4012895","0110","1000/CSUPHN","1000/CSUPHN","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-4","Feb24 Storm Costs SR&CA PC 12006","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",7.5,null,null,558.83000000000004]
["10010589","Monica Hope","1000/12109","Customer Communicati","21.02.2024","04.03.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0110","Feb24 Storm Timesheet PC 12006","4012895","4012895","0110","1000/CSUPHO","1000/CSUPHO","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-4","Feb24 Storm Costs SR&CA PC 12006","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",2.25,null,null,241.79]
["10010589","Monica Hope","1000/12109","Customer Communicati","22.02.2024","04.03.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0110","Feb24 Storm Timesheet PC 12006","4012895","4012895","0110","1000/CSUPHN","1000/CSUPHN","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-4","Feb24 Storm Costs SR&CA PC 12006","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",7.5,null,null,558.83000000000004]
["10010589","Monica Hope","1000/12109","Customer Communicati","22.02.2024","04.03.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0110","Feb24 Storm Timesheet PC 12006","4012895","4012895","0110","1000/CSUPHO","1000/CSUPHO","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-4","Feb24 Storm Costs SR&CA PC 12006","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",2.5,null,null,268.64999999999998]
["10010589","Monica Hope","1000/12109","Customer Communicati","23.02.2024","04.03.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0110","Feb24 Storm Timesheet PC 12006","4012895","4012895","0110","1000/CSUPHN","1000/CSUPHN","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-4","Feb24 Storm Costs SR&CA PC 12006","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",7.5,null,null,558.83000000000004]
["10010589","Monica Hope","1000/12109","Customer Communicati","23.02.2024","04.03.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0110","Feb24 Storm Timesheet PC 12006","4012895","4012895","0110","1000/CSUPHO","1000/CSUPHO","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-4","Feb24 Storm Costs SR&CA PC 12006","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",1,null,null,107.46]
["10010603","John Guihot","1000/13104","Distribution Control","13.02.2024","20.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/DCONTO","Dxn Controller OT","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",1,null,null,212.52]
["10010603","John Guihot","1000/13104","Distribution Control","14.02.2024","20.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/DCONTO","Dxn Controller OT","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",2,null,null,425.04]
["10010614","Annika Forstmanis","1000/12109","Customer Communicati","13.02.2024","08.03.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0110","Feb24 Storm Timesheet PC 12006","4012895","4012895","0110","1000/CPSEMN","Corp Semi Prof NT","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-4","Feb24 Storm Costs SR&CA PC 12006","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",7.5,null,null,711.98]
["10010614","Annika Forstmanis","1000/12109","Customer Communicati","13.02.2024","08.03.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0110","Feb24 Storm Timesheet PC 12006","4012895","4012895","0110","1000/CPSEMO","Corp Semi Prof OT","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-4","Feb24 Storm Costs SR&CA PC 12006","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",3.5,null,null,479.22]
["10010614","Annika Forstmanis","1000/12109","Customer Communicati","14.02.2024","08.03.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0110","Feb24 Storm Timesheet PC 12006","4012895","4012895","0110","1000/CPSEMN","Corp Semi Prof NT","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-4","Feb24 Storm Costs SR&CA PC 12006","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",9.25,null,null,711.97]
["10010614","Annika Forstmanis","1000/12109","Customer Communicati","15.02.2024","08.03.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0110","Feb24 Storm Timesheet PC 12006","4012895","4012895","0110","1000/CPSEMN","Corp Semi Prof NT","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-4","Feb24 Storm Costs SR&CA PC 12006","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",7.5,null,null,711.98]
["10010614","Annika Forstmanis","1000/12109","Customer Communicati","15.02.2024","08.03.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0110","Feb24 Storm Timesheet PC 12006","4012895","4012895","0110","1000/CPSEMO","Corp Semi Prof OT","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-4","Feb24 Storm Costs SR&CA PC 12006","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",6,null,null,821.52]
["10010614","Annika Forstmanis","1000/12109","Customer Communicati","16.02.2024","08.03.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0110","Feb24 Storm Timesheet PC 12006","4012895","4012895","0110","1000/CPSEMN","Corp Semi Prof NT","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-4","Feb24 Storm Costs SR&CA PC 12006","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",8.5,null,null,712.05]
["10010614","Annika Forstmanis","1000/12109","Customer Communicati","18.02.2024","08.03.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0110","Feb24 Storm Timesheet PC 12006","4012895","4012895","0110","1000/CPSEMO","Corp Semi Prof OT","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-4","Feb24 Storm Costs SR&CA PC 12006","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",2.75,null,null,376.53]
["10010614","Annika Forstmanis","1000/12109","Customer Communicati","19.02.2024","08.03.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0110","Feb24 Storm Timesheet PC 12006","4012895","4012895","0110","1000/CPSEMN","Corp Semi Prof NT","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-4","Feb24 Storm Costs SR&CA PC 12006","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",7.5,null,null,711.98]
["10010614","Annika Forstmanis","1000/12109","Customer Communicati","19.02.2024","08.03.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0110","Feb24 Storm Timesheet PC 12006","4012895","4012895","0110","1000/CPSEMO","Corp Semi Prof OT","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-4","Feb24 Storm Costs SR&CA PC 12006","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",5.42,null,null,742.11]
["10010614","Annika Forstmanis","1000/12109","Customer Communicati","20.02.2024","08.03.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0110","Feb24 Storm Timesheet PC 12006","4012895","4012895","0110","1000/CPSEMN","Corp Semi Prof NT","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-4","Feb24 Storm Costs SR&CA PC 12006","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",7.5,null,null,711.98]
["10010614","Annika Forstmanis","1000/12109","Customer Communicati","20.02.2024","08.03.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0110","Feb24 Storm Timesheet PC 12006","4012895","4012895","0110","1000/CPSEMO","Corp Semi Prof OT","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-4","Feb24 Storm Costs SR&CA PC 12006","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",1.67,null,null,228.66]
["10010614","Annika Forstmanis","1000/12109","Customer Communicati","21.02.2024","08.03.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0110","Feb24 Storm Timesheet PC 12006","4012895","4012895","0110","1000/CPSEMN","Corp Semi Prof NT","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-4","Feb24 Storm Costs SR&CA PC 12006","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",7.5,null,null,711.98]
["10010614","Annika Forstmanis","1000/12109","Customer Communicati","21.02.2024","08.03.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0110","Feb24 Storm Timesheet PC 12006","4012895","4012895","0110","1000/CPSEMO","Corp Semi Prof OT","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-4","Feb24 Storm Costs SR&CA PC 12006","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",7.5,null,null,1026.9000000000001]
["10010614","Annika Forstmanis","1000/12109","Customer Communicati","22.02.2024","08.03.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0110","Feb24 Storm Timesheet PC 12006","4012895","4012895","0110","1000/CPSEMN","Corp Semi Prof NT","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-4","Feb24 Storm Costs SR&CA PC 12006","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",5,null,null,474.65]
["10010614","Annika Forstmanis","1000/12109","Customer Communicati","23.02.2024","08.03.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0110","Feb24 Storm Timesheet PC 12006","4012895","4012895","0110","1000/CPSEMN","Corp Semi Prof NT","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-4","Feb24 Storm Costs SR&CA PC 12006","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",8,null,null,712]
["10010637","Alan Davies","1000/13030","Access and Outage Pl","20.02.2024","21.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/ACCOOO","Access Coor OT","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",0.5,null,null,70.3]
["10010642","Matt Keown","1000/13030","Access and Outage Pl","15.02.2024","19.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/ACCOON","Access Coor NT","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",8.83,null,null,812.01]
["10011015","Sam Carey","1000/15006","Cus Serv Desg & Rese","13.02.2024","26.03.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CMNGRO","Corp Manager OT","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",1,null,null,236.69]
["10011015","Sam Carey","1000/15006","Cus Serv Desg & Rese","14.02.2024","26.03.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CMNGRO","Corp Manager OT","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",0.5,null,null,118.35]
["10011015","Sam Carey","1000/15006","Cus Serv Desg & Rese","16.02.2024","26.03.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CMNGRO","Corp Manager OT","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",2,null,null,473.38]
["10011015","Sam Carey","1000/15006","Cus Serv Desg & Rese","19.02.2024","26.03.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CMNGRO","Corp Manager OT","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",1.5,null,null,355.04]
["10011015","Sam Carey","1000/15006","Cus Serv Desg & Rese","21.02.2024","26.03.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CMNGRO","Corp Manager OT","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",3,null,null,710.07]
["10011015","Sam Carey","1000/15006","Cus Serv Desg & Rese","22.02.2024","26.03.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CMNGRO","Corp Manager OT","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",2,null,null,473.38]
["10011015","Sam Carey","1000/15006","Cus Serv Desg & Rese","23.02.2024","26.03.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CMNGRO","Corp Manager OT","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",2,null,null,473.38]
["10011015","Sam Carey","1000/15006","Cus Serv Desg & Rese","26.02.2024","26.03.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CMNGRO","Corp Manager OT","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",2,null,null,473.38]
["10011015","Sam Carey","1000/15006","Cus Serv Desg & Rese","27.02.2024","26.03.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CMNGRO","Corp Manager OT","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",1,null,null,236.69]
["10011015","Sam Carey","1000/15006","Cus Serv Desg & Rese","29.02.2024","26.03.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CMNGRO","Corp Manager OT","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",0.5,null,null,118.35]
["10011015","Sam Carey","1000/15006","Cus Serv Desg & Rese","04.03.2024","02.04.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CLEADO","Corp Ops Lead OT","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",null,0.5,null,null,78.040000000000006]
["10011015","Sam Carey","1000/15006","Cus Serv Desg & Rese","06.03.2024","02.04.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CLEADO","Corp Ops Lead OT","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",null,0.5,null,null,78.040000000000006]
["10011021","Ryan Opferkuch","1000/13030","Access and Outage Pl","14.02.2024","20.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/WPLANO","Work Planner OT","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",1.25,null,null,193.01]
["10011021","Ryan Opferkuch","1000/13030","Access and Outage Pl","15.02.2024","20.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/WPLANO","Work Planner OT","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",1,null,null,154.41]
["10011021","Ryan Opferkuch","1000/13030","Access and Outage Pl","16.02.2024","20.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/WPLANO","Work Planner OT","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",1,null,null,154.41]
["10011021","Ryan Opferkuch","1000/13030","Access and Outage Pl","18.02.2024","20.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/WPLANO","Work Planner OT","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",2.25,null,null,347.42]
["10011077","Dave Pollard","1000/11903","Eng Serv & Comp (D)","17.02.2024","20.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CLEAAO","1000/CLEAAO","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",3,null,null,438.54]
["10011077","Dave Pollard","1000/11903","Eng Serv & Comp (D)","18.02.2024","20.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CLEAAO","1000/CLEAAO","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",3,null,null,438.54]
["10011077","Dave Pollard","1000/11903","Eng Serv & Comp (D)","19.02.2024","26.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CLEAAN","1000/CLEAAN","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",8,null,null,760.16]
["10011077","Dave Pollard","1000/11903","Eng Serv & Comp (D)","19.02.2024","26.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CLEAAO","1000/CLEAAO","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",6,null,null,877.08]
["10011077","Dave Pollard","1000/11903","Eng Serv & Comp (D)","21.02.2024","26.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CLEAAN","1000/CLEAAN","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",8,null,null,760.16]
["10011077","Dave Pollard","1000/11903","Eng Serv & Comp (D)","21.02.2024","26.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CLEAAO","1000/CLEAAO","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",7,null,null,1023.26]
["10011101","Jade Christie","1000/11101","Vegetation Managemen","16.02.2024","20.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CSUPHO","1000/CSUPHO","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",3.17,null,null,340.65]
["10011101","Jade Christie","1000/11101","Vegetation Managemen","17.02.2024","20.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CSUPHO","1000/CSUPHO","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",12,null,null,1289.52]
["10011101","Jade Christie","1000/11101","Vegetation Managemen","18.02.2024","20.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CSUPHO","1000/CSUPHO","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",11.5,null,null,1235.79]
["10011101","Jade Christie","1000/11101","Vegetation Managemen","24.02.2024","26.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CSUPHO","1000/CSUPHO","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",10.5,null,null,1128.33]
["10011113","Shannon Carrigg","1000/13936","Customer Connections","14.02.2024","19.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CSUPDN","1000/CSUPDN","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",7.5,null,null,455.03]
["10011116","Emre Guclu","1000/13936","Customer Connections","14.02.2024","19.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CSUPDN","1000/CSUPDN","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",0.75,null,null,45.5]
["10011128","Danielle Jones","1000/13175","Customer Serv & Reso","12.02.2024","01.03.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CLEAAO","1000/CLEAAO","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",6,null,null,877.08]
["10011128","Danielle Jones","1000/13175","Customer Serv & Reso","13.02.2024","01.03.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CLEAAO","1000/CLEAAO","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",3.25,null,null,475.09]
["10011128","Danielle Jones","1000/13175","Customer Serv & Reso","14.02.2024","01.03.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CLEAAO","1000/CLEAAO","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",4,null,null,584.72]
["10011128","Danielle Jones","1000/13175","Customer Serv & Reso","15.02.2024","01.03.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CLEAAO","1000/CLEAAO","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",3,null,null,438.54]
["10011128","Danielle Jones","1000/13175","Customer Serv & Reso","16.02.2024","01.03.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CLEAAO","1000/CLEAAO","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",1.75,null,null,255.82]
["10011128","Danielle Jones","1000/13175","Customer Serv & Reso","18.02.2024","01.03.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CLEAAO","1000/CLEAAO","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",4.75,null,null,694.36]
["10011128","Danielle Jones","1000/13175","Customer Serv & Reso","19.02.2024","01.03.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CLEAAO","1000/CLEAAO","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",2.25,null,null,328.91]
["10011128","Danielle Jones","1000/13175","Customer Serv & Reso","20.02.2024","01.03.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CLEAAO","1000/CLEAAO","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",3.25,null,null,475.09]
["10011128","Danielle Jones","1000/13175","Customer Serv & Reso","21.02.2024","01.03.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CLEAAO","1000/CLEAAO","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",1.25,null,null,182.73]
["10011128","Danielle Jones","1000/13175","Customer Serv & Reso","22.02.2024","01.03.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CLEAAO","1000/CLEAAO","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",2,null,null,292.36]
["10011133","Navaneeth Varadarajan","1000/14620","Regulated Meter Data","14.02.2024","16.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CSUPPN","Corp Support NT","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",0.5,null,null,41.35]
["10011142","Rafi Muneer","1000/11517","Contract Manag Dist","15.02.2024","05.03.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CLEADN","Corp Ops Lead NT","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",8,null,null,811.6]
["10011142","Rafi Muneer","1000/11517","Contract Manag Dist","15.02.2024","05.03.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CLEADO","Corp Ops Lead OT","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",2,null,null,312.16000000000003]
["10011142","Rafi Muneer","1000/11517","Contract Manag Dist","16.02.2024","05.03.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CLEADN","Corp Ops Lead NT","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",8,null,null,811.6]
["10011145","Ana Burgess","1000/13031","Operations Optimisat","14.02.2024","23.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CLEADN","Corp Ops Lead NT","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",8,null,null,811.6]
["10011145","Ana Burgess","1000/13031","Operations Optimisat","14.02.2024","23.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CLEADO","Corp Ops Lead OT","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",4,null,null,624.32000000000005]
["10011145","Ana Burgess","1000/13031","Operations Optimisat","15.02.2024","23.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CLEADN","Corp Ops Lead NT","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",8,null,null,811.6]
["10011145","Ana Burgess","1000/13031","Operations Optimisat","15.02.2024","23.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CLEADO","Corp Ops Lead OT","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",0.5,null,null,78.040000000000006]
["10011145","Ana Burgess","1000/13031","Operations Optimisat","19.02.2024","26.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CLEADN","Corp Ops Lead NT","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",8,null,null,811.6]
["10011145","Ana Burgess","1000/13031","Operations Optimisat","19.02.2024","26.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CLEADO","Corp Ops Lead OT","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",1.75,null,null,273.14]
["10011145","Ana Burgess","1000/13031","Operations Optimisat","22.02.2024","26.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CLEADO","Corp Ops Lead OT","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",1,null,null,156.08000000000001]
["10011145","Ana Burgess","1000/13031","Operations Optimisat","23.02.2024","26.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CLEADN","Corp Ops Lead NT","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",8,null,null,811.6]
["10011145","Ana Burgess","1000/13031","Operations Optimisat","23.02.2024","26.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CLEADO","Corp Ops Lead OT","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",2.17,null,null,338.69]
["10011183","Wayne Burnett","1000/16001","Inspection & Assessm","15.02.2024","19.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CSUPBN","1000/CSUPBN","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",8,null,null,442.08]
["10011184","Craig Tannock","1000/16001","Inspection & Assessm","15.02.2024","21.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0020","Feb24 Storm Timesheet Tx 12014","4012895","4012895","0020","1000/ASSESN","Asset Assesor NT","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",8.5,null,null,774.69]
["10011184","Craig Tannock","1000/16001","Inspection & Assessm","16.02.2024","21.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0020","Feb24 Storm Timesheet Tx 12014","4012895","4012895","0020","1000/ASSESN","Asset Assesor NT","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",8.5,null,null,774.69]
["10011184","Craig Tannock","1000/16001","Inspection & Assessm","17.02.2024","21.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/ASSESO","Asset Assesor OT","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",13,null,null,1743.69]
["10011184","Craig Tannock","1000/16001","Inspection & Assessm","18.02.2024","21.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/ASSESO","Asset Assesor OT","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",11.5,null,null,1542.5]
["10011184","Craig Tannock","1000/16001","Inspection & Assessm","19.02.2024","24.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0020","Feb24 Storm Timesheet Tx 12014","4012895","4012895","0020","1000/ASSESN","Asset Assesor NT","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",8.5,null,null,774.69]
["10011184","Craig Tannock","1000/16001","Inspection & Assessm","23.02.2024","24.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0020","Feb24 Storm Timesheet Tx 12014","4012895","4012895","0020","1000/ASSESN","Asset Assesor NT","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",8.5,null,null,774.69]
["10011185","Jake Hubben","1000/16001","Inspection & Assessm","15.02.2024","21.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CSUPBN","1000/CSUPBN","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",8,null,null,442.08]
["10011185","Jake Hubben","1000/16001","Inspection & Assessm","16.02.2024","21.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CSUPBN","1000/CSUPBN","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",5,null,null,276.3]
["10011192","Aaron Lipman","1000/16001","Inspection & Assessm","15.02.2024","19.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CSUPBN","1000/CSUPBN","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",8,null,null,442.08]
["10011192","Aaron Lipman","1000/16001","Inspection & Assessm","15.02.2024","19.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CSUPBO","1000/CSUPBO","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",2.5,null,null,199.25]
["10011192","Aaron Lipman","1000/16001","Inspection & Assessm","16.02.2024","19.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CSUPBN","1000/CSUPBN","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",8,null,null,442.08]
["10011192","Aaron Lipman","1000/16001","Inspection & Assessm","16.02.2024","19.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CSUPBO","1000/CSUPBO","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",2,null,null,159.4]
["10011192","Aaron Lipman","1000/16001","Inspection & Assessm","17.02.2024","19.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CSUPBO","1000/CSUPBO","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",6,null,null,478.2]
["10011196","Jack Bower","1000/16001","Inspection & Assessm","15.02.2024","20.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CSUPBN","1000/CSUPBN","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",8,null,null,442.08]
["10011196","Jack Bower","1000/16001","Inspection & Assessm","15.02.2024","20.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CSUPBO","1000/CSUPBO","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",1,null,null,79.7]
["10011217","Elissa Muller","1000/13187","Customer Engagement","14.02.2024","20.03.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0130","Feb24 Storm Timesheet PC 12306","4012895","4012895","0130","1000/CLEADN","Corp Ops Lead NT","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-5","Feb24 Storm Costs People PC 12306","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",6,null,null,467.34]
["10011217","Elissa Muller","1000/13187","Customer Engagement","15.02.2024","20.03.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0130","Feb24 Storm Timesheet PC 12306","4012895","4012895","0130","1000/CLEADN","Corp Ops Lead NT","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-5","Feb24 Storm Costs People PC 12306","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",5.25,null,null,378.74]
["10011217","Elissa Muller","1000/13187","Customer Engagement","16.02.2024","20.03.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0130","Feb24 Storm Timesheet PC 12306","4012895","4012895","0130","1000/CLEADN","Corp Ops Lead NT","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-5","Feb24 Storm Costs People PC 12306","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",2.75,null,null,270.52]
["10011217","Elissa Muller","1000/13187","Customer Engagement","21.02.2024","23.03.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0030","Feb24 Storm Timesheet Net unknown 12014","4012895","4012895","0030","1000/CLEADN","Corp Ops Lead NT","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",2.33,null,null,206.44]
["10011217","Elissa Muller","1000/13187","Customer Engagement","22.02.2024","23.03.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0130","Feb24 Storm Timesheet PC 12306","4012895","4012895","0130","1000/CLEADN","Corp Ops Lead NT","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-5","Feb24 Storm Costs People PC 12306","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",4.5,null,null,442.67]
["10011217","Elissa Muller","1000/13187","Customer Engagement","24.02.2024","23.03.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0130","Feb24 Storm Timesheet PC 12306","4012895","4012895","0130","1000/CLEADO","Corp Ops Lead OT","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-5","Feb24 Storm Costs People PC 12306","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",7.25,null,null,1131.58]
["10011217","Elissa Muller","1000/13187","Customer Engagement","25.02.2024","23.03.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0130","Feb24 Storm Timesheet PC 12306","4012895","4012895","0130","1000/CLEADO","Corp Ops Lead OT","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-5","Feb24 Storm Costs People PC 12306","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",5.92,null,null,923.99]
["10011217","Elissa Muller","1000/13187","Customer Engagement","26.02.2024","20.03.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0130","Feb24 Storm Timesheet PC 12306","4012895","4012895","0130","1000/CLEADN","Corp Ops Lead NT","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-5","Feb24 Storm Costs People PC 12306","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",2,null,null,216.42]
["10011217","Elissa Muller","1000/13187","Customer Engagement","27.02.2024","20.03.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0130","Feb24 Storm Timesheet PC 12306","4012895","4012895","0130","1000/CLEADN","Corp Ops Lead NT","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-5","Feb24 Storm Costs People PC 12306","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",0.5,null,null,52.36]
["10011217","Elissa Muller","1000/13187","Customer Engagement","28.02.2024","20.03.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0130","Feb24 Storm Timesheet PC 12306","4012895","4012895","0130","1000/CLEADN","Corp Ops Lead NT","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-5","Feb24 Storm Costs People PC 12306","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",3.83,null,null,414.44]
["10011217","Elissa Muller","1000/13187","Customer Engagement","01.03.2024","20.03.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0130","Feb24 Storm Timesheet PC 12306","4012895","4012895","0130","1000/CPSRAN","1000/CPSRAN","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-5","Feb24 Storm Costs People PC 12306","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",null,8.5,null,null,848.13]
["10011217","Elissa Muller","1000/13187","Customer Engagement","04.03.2024","20.03.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0130","Feb24 Storm Timesheet PC 12306","4012895","4012895","0130","1000/CPSRAN","1000/CPSRAN","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-5","Feb24 Storm Costs People PC 12306","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",null,2.5,null,null,282.7]
["10011217","Elissa Muller","1000/13187","Customer Engagement","13.03.2024","20.03.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0130","Feb24 Storm Timesheet PC 12306","4012895","4012895","0130","1000/CPSRAN","1000/CPSRAN","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-5","Feb24 Storm Costs People PC 12306","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",null,7.5,null,null,605.78]
["10011217","Elissa Muller","1000/13187","Customer Engagement","15.03.2024","20.03.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0130","Feb24 Storm Timesheet PC 12306","4012895","4012895","0130","1000/CPSRAN","1000/CPSRAN","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-5","Feb24 Storm Costs People PC 12306","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",null,4.67,null,null,516.36]
["10011219","10011219","1000/12182","Health, Safety E & Q","15.02.2024","16.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0040","Feb24 Storm Purchases Orders Dx 12014","4012895","4012895","0040","1000/CPSRVN","Corp Prof NT","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",8,null,null,882.88]
["10011219","10011219","1000/12182","Health, Safety E & Q","16.02.2024","16.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0040","Feb24 Storm Purchases Orders Dx 12014","4012895","4012895","0040","1000/CPSRVN","Corp Prof NT","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",8,null,null,882.88]
["10011251","Daniel White","1000/11517","Contract Manag Dist","14.02.2024","27.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CLEADN","Corp Ops Lead NT","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",8,null,null,811.6]
["10011251","Daniel White","1000/11517","Contract Manag Dist","14.02.2024","27.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CLEADO","Corp Ops Lead OT","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",3,null,null,468.24]
["10011251","Daniel White","1000/11517","Contract Manag Dist","15.02.2024","27.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CLEADN","Corp Ops Lead NT","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",8,null,null,811.6]
["10011251","Daniel White","1000/11517","Contract Manag Dist","15.02.2024","27.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CLEADO","Corp Ops Lead OT","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",7,null,null,1092.56]
["10011251","Daniel White","1000/11517","Contract Manag Dist","16.02.2024","27.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CLEADN","Corp Ops Lead NT","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",8,null,null,811.6]
["10011251","Daniel White","1000/11517","Contract Manag Dist","16.02.2024","27.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CLEADO","Corp Ops Lead OT","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",8,null,null,1248.6400000000001]
["10011251","Daniel White","1000/11517","Contract Manag Dist","17.02.2024","27.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CLEADO","Corp Ops Lead OT","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",9.5,null,null,1482.76]
["10011251","Daniel White","1000/11517","Contract Manag Dist","18.02.2024","27.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CLEADO","Corp Ops Lead OT","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",11,null,null,1716.88]
["10011251","Daniel White","1000/11517","Contract Manag Dist","19.02.2024","27.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CLEADN","Corp Ops Lead NT","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",8,null,null,811.6]
["10011251","Daniel White","1000/11517","Contract Manag Dist","19.02.2024","27.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CLEADO","Corp Ops Lead OT","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",2.5,null,null,390.2]
["10011251","Daniel White","1000/11517","Contract Manag Dist","20.02.2024","27.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CLEADN","Corp Ops Lead NT","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",8,null,null,811.6]
["10011251","Daniel White","1000/11517","Contract Manag Dist","20.02.2024","27.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CLEADO","Corp Ops Lead OT","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",1.5,null,null,234.12]
["10011251","Daniel White","1000/11517","Contract Manag Dist","21.02.2024","27.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CLEADN","Corp Ops Lead NT","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",8,null,null,811.6]
["10011262","Aaron Lee","1000/13981","Security & Emergency","16.02.2024","19.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CPSVSN","Corp Prof Spec NT","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",7.5,null,null,1081.3499999999999]
["10011262","Aaron Lee","1000/13981","Security & Emergency","16.02.2024","19.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CPSVSO","Corp Prof Spec OT","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",3,null,null,623.85]
["10011262","Aaron Lee","1000/13981","Security & Emergency","17.02.2024","19.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CPSVSO","Corp Prof Spec OT","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",11.5,null,null,2391.4299999999998]
["10011262","Aaron Lee","1000/13981","Security & Emergency","20.02.2024","26.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CPSVSO","Corp Prof Spec OT","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",2.5,null,null,519.88]
["10011262","Aaron Lee","1000/13981","Security & Emergency","21.02.2024","26.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CPSVSO","Corp Prof Spec OT","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",2,null,null,415.9]
["10011267","Tara McDonald","1000/13187","Customer Engagement","22.02.2024","23.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CPSVAN","1000/CPSVAN","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",7.5,null,null,1020.75]
["10011267","Tara McDonald","1000/13187","Customer Engagement","26.02.2024","04.03.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CPSVAN","1000/CPSVAN","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",7.5,null,null,1020.75]
["10011267","Tara McDonald","1000/13187","Customer Engagement","27.02.2024","04.03.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CPSVAN","1000/CPSVAN","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",7.5,null,null,1020.75]
["10011267","Tara McDonald","1000/13187","Customer Engagement","01.03.2024","04.03.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CPSVAN","1000/CPSVAN","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",null,7.5,null,null,1020.75]
["10011267","Tara McDonald","1000/13187","Customer Engagement","06.03.2024","08.03.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CPSVAN","1000/CPSVAN","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",null,7.5,null,null,1020.75]
["10011269","Aravindh Etikala","1000/13031","Operations Optimisat","16.02.2024","23.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CPSRVN","Corp Prof NT","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",8,null,null,882.88]
["10011269","Aravindh Etikala","1000/13031","Operations Optimisat","19.02.2024","28.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CPSRVN","Corp Prof NT","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",1,null,null,117.72]
["10011269","Aravindh Etikala","1000/13031","Operations Optimisat","19.02.2024","28.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CPSRVO","Corp Prof OT","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",6,null,null,1018.74]
["10011269","Aravindh Etikala","1000/13031","Operations Optimisat","20.02.2024","28.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CPSRVN","Corp Prof NT","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",8,null,null,882.88]
["10011269","Aravindh Etikala","1000/13031","Operations Optimisat","20.02.2024","28.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CPSRVO","Corp Prof OT","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",3,null,null,509.37]
["10011293","Sarah Wood","1000/12182","Health, Safety E & Q","14.02.2024","23.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CMNGAN","1000/CMNGAN","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",8,null,null,1146.8800000000001]
["10011293","Sarah Wood","1000/12182","Health, Safety E & Q","14.02.2024","23.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CMNGAO","1000/CMNGAO","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",6,null,null,1323.36]
["10011293","Sarah Wood","1000/12182","Health, Safety E & Q","15.02.2024","23.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CMNGAN","1000/CMNGAN","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",8.5,null,null,1146.99]
["10011293","Sarah Wood","1000/12182","Health, Safety E & Q","16.02.2024","23.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CMNGAN","1000/CMNGAN","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",8.5,null,null,1146.99]
["10011293","Sarah Wood","1000/12182","Health, Safety E & Q","16.02.2024","23.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CMNGAO","1000/CMNGAO","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",1,null,null,220.56]
["10011300","Scott Hardy","1000/13187","Customer Engagement","13.02.2024","01.03.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CMNGRN","Corp Manager NT","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",8.5,null,null,1230.8]
["10011300","Scott Hardy","1000/13187","Customer Engagement","14.02.2024","01.03.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CMNGRN","Corp Manager NT","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",7.5,null,null,1230.75]
["10011300","Scott Hardy","1000/13187","Customer Engagement","14.02.2024","01.03.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CMNGRO","Corp Manager OT","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",1.5,null,null,355.04]
["10011300","Scott Hardy","1000/13187","Customer Engagement","15.02.2024","01.03.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CMNGRN","Corp Manager NT","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",7.5,null,null,1230.75]
["10011300","Scott Hardy","1000/13187","Customer Engagement","15.02.2024","01.03.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CMNGRO","Corp Manager OT","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",2,null,null,473.38]
["10011300","Scott Hardy","1000/13187","Customer Engagement","16.02.2024","01.03.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CMNGRN","Corp Manager NT","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",7.5,null,null,1230.75]
["10011300","Scott Hardy","1000/13187","Customer Engagement","16.02.2024","01.03.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CMNGRO","Corp Manager OT","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",3,null,null,710.07]
["10011300","Scott Hardy","1000/13187","Customer Engagement","17.02.2024","01.03.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CMNGRO","Corp Manager OT","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",11.5,null,null,2721.94]
["10011300","Scott Hardy","1000/13187","Customer Engagement","19.02.2024","05.03.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CMNGRN","Corp Manager NT","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",8.5,null,null,1230.8]
["10011300","Scott Hardy","1000/13187","Customer Engagement","20.02.2024","05.03.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CMNGRN","Corp Manager NT","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",7.5,null,null,1230.75]
["10011300","Scott Hardy","1000/13187","Customer Engagement","21.02.2024","05.03.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CMNGRN","Corp Manager NT","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",8.5,null,null,1230.8]
["10011300","Scott Hardy","1000/13187","Customer Engagement","21.02.2024","05.03.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CMNGRO","Corp Manager OT","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",2.5,null,null,591.73]
["10011300","Scott Hardy","1000/13187","Customer Engagement","22.02.2024","05.03.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CMNGRN","Corp Manager NT","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",8,null,null,1230.72]
["10011300","Scott Hardy","1000/13187","Customer Engagement","22.02.2024","05.03.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CMNGRO","Corp Manager OT","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",1.5,null,null,355.04]
["10011300","Scott Hardy","1000/13187","Customer Engagement","23.02.2024","05.03.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CMNGRN","Corp Manager NT","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",8,null,null,1230.72]
["10011300","Scott Hardy","1000/13187","Customer Engagement","23.02.2024","05.03.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CMNGRO","Corp Manager OT","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",3,null,null,710.07]
["10011300","Scott Hardy","1000/13187","Customer Engagement","26.02.2024","26.03.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CMNGRN","Corp Manager NT","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",6.5,null,null,1066.6500000000001]
["10011300","Scott Hardy","1000/13187","Customer Engagement","26.02.2024","26.03.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CMNGRO","Corp Manager OT","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",3.5,null,null,828.42]
["10011300","Scott Hardy","1000/13187","Customer Engagement","27.02.2024","26.03.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CMNGRN","Corp Manager NT","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",8.5,null,null,1230.8]
["10011300","Scott Hardy","1000/13187","Customer Engagement","28.02.2024","26.03.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CMNGRN","Corp Manager NT","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",7.5,null,null,1230.75]
["10011300","Scott Hardy","1000/13187","Customer Engagement","29.02.2024","26.03.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CMNGRN","Corp Manager NT","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",8.5,null,null,1230.8]
["10011300","Scott Hardy","1000/13187","Customer Engagement","01.03.2024","26.03.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CPSRAN","1000/CPSRAN","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",null,8.5,null,null,848.13]
["10011300","Scott Hardy","1000/13187","Customer Engagement","07.03.2024","08.03.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CPSRAN","1000/CPSRAN","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",null,9.5,null,null,848.16]
["10011300","Scott Hardy","1000/13187","Customer Engagement","08.03.2024","08.03.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CPSRAN","1000/CPSRAN","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",null,7.5,null,null,848.1]
["10011300","Scott Hardy","1000/13187","Customer Engagement","13.03.2024","18.03.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CPSRAO","1000/CPSRAO","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",null,4.5,null,null,733.95]
["10011300","Scott Hardy","1000/13187","Customer Engagement","21.03.2024","26.03.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CPSRAO","1000/CPSRAO","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",null,6,null,null,978.6]
["10011300","Scott Hardy","1000/13187","Customer Engagement","23.03.2024","26.03.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CPSRAO","1000/CPSRAO","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",null,9.5,null,null,1549.45]
["10011309","Tanya Gutteridge","1000/13187","Customer Engagement","21.02.2024","27.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CPSVAN","1000/CPSVAN","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",8.5,null,null,1020.77]
["10011309","Tanya Gutteridge","1000/13187","Customer Engagement","22.02.2024","27.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CPSVAN","1000/CPSVAN","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",8.5,null,null,1020.77]
["10011309","Tanya Gutteridge","1000/13187","Customer Engagement","23.02.2024","27.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CPSVAN","1000/CPSVAN","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",9,null,null,1020.69]
["10011309","Tanya Gutteridge","1000/13187","Customer Engagement","24.02.2024","27.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CPSVAN","1000/CPSVAN","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",5,null,null,680.5]
["10011309","Tanya Gutteridge","1000/13187","Customer Engagement","29.02.2024","06.04.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CPSVAN","1000/CPSVAN","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",8.5,null,null,1020.77]
["10011309","Tanya Gutteridge","1000/13187","Customer Engagement","04.03.2024","13.03.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CPSEMN","Corp Semi Prof NT","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",null,5,null,null,418.85]
["10011309","Tanya Gutteridge","1000/13187","Customer Engagement","06.03.2024","13.03.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0130","Feb24 Storm Timesheet PC 12306","4012895","4012895","0130","1000/CPSEMN","Corp Semi Prof NT","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-5","Feb24 Storm Costs People PC 12306","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",null,8,null,null,712]
["10011309","Tanya Gutteridge","1000/13187","Customer Engagement","13.03.2024","15.03.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0130","Feb24 Storm Timesheet PC 12306","4012895","4012895","0130","1000/CPSEMO","Corp Semi Prof OT","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-5","Feb24 Storm Costs People PC 12306","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",null,3,null,null,410.76]
["10011309","Tanya Gutteridge","1000/13187","Customer Engagement","24.03.2024","03.04.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0150","Feb24 Storm Timesheet PC 12388","4012895","4012895","0150","1000/CPSEMO","Corp Semi Prof OT","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-6","Feb24 Storm Costs DFN PC 12388","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",null,10,null,null,1369.2]
["10011310","Nidhin Kurian","1000/13489","Asset Management","18.03.2024","26.03.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0070","Feb24 Storm Timesheet PC 12001","4012895","4012895","0070","1000/CPSPAN","1000/CPSPAN","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-2","Feb24 Storm Costs dNet PC 12001","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",null,2.5,null,null,272.10000000000002]
["10011310","Nidhin Kurian","1000/13489","Asset Management","25.03.2024","05.04.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0070","Feb24 Storm Timesheet PC 12001","4012895","4012895","0070","1000/CPSPAN","1000/CPSPAN","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-2","Feb24 Storm Costs dNet PC 12001","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",null,2.5,null,null,272.10000000000002]
["10011310","Nidhin Kurian","1000/13489","Asset Management","08.04.2024","15.04.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0070","Feb24 Storm Timesheet PC 12001","4012895","4012895","0070","1000/CPSPAN","1000/CPSPAN","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-2","Feb24 Storm Costs dNet PC 12001","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",null,null,2.5,null,null,272.10000000000002]
["10011323","Jessica Crowe","1000/13187","Customer Engagement","20.02.2024","04.03.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CSENAO","1000/CSENAO","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",2,null,null,516.66]
["10011323","Jessica Crowe","1000/13187","Customer Engagement","21.02.2024","04.03.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CSENAO","1000/CSENAO","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",2,null,null,516.66]
["10011323","Jessica Crowe","1000/13187","Customer Engagement","02.03.2024","26.03.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CPSRVO","Corp Prof OT","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","850","Overtime","1000/#","1000/Not assigned",null,5,null,null,848.95]
["10011330","Evelyn Khong","1000/12018","Mark Data & Mter Ser","14.02.2024","16.02.2024","4012895","Feb24 Storm Costs NetOps PC 12014","4012895/0010","Feb24 Storm Timesheet Dx 12014","4012895","4012895","0010","1000/CPSEAN","1000/CPSEAN","HX-0014297","Storm Emergency_Feb24 OPEX","HX-0014297-1","Feb24 Storm Costs NetOps PC 12014","9999","INTERNAL COST CAPTURE","1000/11000","Sweep Profit Centre","800","Normal Time","1000/#","1000/Not assigned",1,null,null,89.47]
["Overall Result",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,5473.14,224.24,10.5,738354.87,26033.25,1353.46]

{"sheet":"June21 Storm sheet","index":4,"n_rows":1694,"n_cols":34,"rows_kept":1694,"cut":false,"hidden":true,"merged":[]}
["Original bus. trans","Business Transaction","Document Date","Posting Date","Period","Fiscal Year","Company Code","Document Number","Project definition","WBS element","Object type","Object","CO object name","Cost Element","Cost element name","Val/COArea Crcy","CO area currency","Name","Reference procedure","User Name","Personnel Number","Material Description","Document type","Timesheet Normally","Include / Exclude","Category"]
["RFBU","COIN","2021-09-29","2021-09-29","6","2022","1100","108503669","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","516204","Professional Fees",89800.92,"AUD","GL Account Corr. to Temp Labour PO 4500122226","BKPFF","WF-BATCH",0,"","AB",null,"Include","Internal"]
["RFBU","COIN","2021-09-29","2021-09-29","6","2022","1100","108503669","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","506500","Cont Lab Non-Payroll",-89800.92,"AUD","GL Account Corr. to Temp Labour PO 4500122226","BKPFF","WF-BATCH",0,"","AB",null,"Exclude"]
["RFBU","COIN","2021-09-29","2021-09-29","6","2022","1100","108504132","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","521100","Materials",149.72,"AUD","PCARD Nicholas Hewes Charger","BKPFF","WF-BATCH",0,"","SA",null,"Include","Internal"]
["RFBU","COIN","2021-09-29","2021-09-29","6","2022","1100","108504132","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","521100","Materials",593.17999999999995,"AUD","PCARD Mathew Durack Storms- New POA","BKPFF","WF-BATCH",0,"","SA",null,"Include","Internal"]
["RFBU","COIN","2021-09-29","2021-09-29","6","2022","1100","108504132","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","521508","Accommodation",-52.23,"AUD","PCARD Mathew Durack reversed charge","BKPFF","WF-BATCH",0,"","SA",null,"Include","Internal"]
["RFBU","COIN","2021-09-29","2021-09-29","6","2022","1100","108504132","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","521508","Accommodation",260,"AUD","PCARD Sergio Inacio Generator Team Stay - Warragul","BKPFF","WF-BATCH",0,"","SA",null,"Include","Internal"]
["RFBU","COIN","2021-09-29","2021-09-29","6","2022","1100","108504132","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","521508","Accommodation",130,"AUD","PCARD Sergio Inacio Gen Team Night Stay Warragal","BKPFF","WF-BATCH",0,"","SA",null,"Include","Internal"]
["RFBU","COIN","2021-09-29","2021-09-29","6","2022","1100","108504132","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","521508","Accommodation",157.26,"AUD","PCARD Dannie Ploegmakers Accom storms","BKPFF","WF-BATCH",0,"","SA",null,"Include","Internal"]
["RFBU","COIN","2021-09-29","2021-09-29","6","2022","1100","108504132","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","521508","Accommodation",262.82,"AUD","PCARD Dannie Ploegmakers Dinner storm response","BKPFF","WF-BATCH",0,"","SA",null,"Include","Internal"]
["RFBU","COIN","2021-09-29","2021-09-29","6","2022","1100","108504132","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","521508","Accommodation",85.73,"AUD","PCARD Dannie Ploegmakers Bfast storm response","BKPFF","WF-BATCH",0,"","SA",null,"Include","Internal"]
["RFBU","COIN","2021-09-29","2021-09-29","6","2022","1100","108504132","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","521508","Accommodation",1743.35,"AUD","PCARD Dannie Ploegmakers Accom storm response","BKPFF","WF-BATCH",0,"","SA",null,"Include","Internal"]
["RFBU","COIN","2021-09-29","2021-09-29","6","2022","1100","108504132","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","521508","Accommodation",36.049999999999997,"AUD","PCARD Nicholas Hewes Meals x 1 Tech","BKPFF","WF-BATCH",0,"","SA",null,"Include","Internal"]
["RFBU","COIN","2021-09-29","2021-09-29","6","2022","1100","108504132","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","521508","Accommodation",117.86,"AUD","PCARD Nicholas Hewes Meals x 2 Techs","BKPFF","WF-BATCH",0,"","SA",null,"Include","Internal"]
["RFBU","COIN","2021-09-29","2021-09-29","6","2022","1100","108504132","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","521508","Accommodation",29.36,"AUD","PCARD Dannie Ploegmakers dinner storm response","BKPFF","WF-BATCH",0,"","SA",null,"Include","Internal"]
["RFBU","COIN","2021-09-29","2021-09-29","6","2022","1100","108504132","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","521508","Accommodation",36.729999999999997,"AUD","PCARD Dannie Ploegmakers Lunch storm response","BKPFF","WF-BATCH",0,"","SA",null,"Include","Internal"]
["RFBU","COIN","2021-09-29","2021-09-29","6","2022","1100","108504132","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","521508","Accommodation",18.18,"AUD","PCARD Dannie Ploegmakers Bfast groceries storm res","BKPFF","WF-BATCH",0,"","SA",null,"Include","Internal"]
["RFBU","COIN","2021-09-29","2021-09-29","6","2022","1100","108504137","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","521508","Accommodation",63.66,"AUD","PCARD Mathew Durack Storms event- meals","BKPFF","WF-BATCH",0,"","SA",null,"Include","Internal"]
["RFBU","COIN","2021-09-29","2021-09-29","6","2022","1100","108504137","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","521508","Accommodation",91.05,"AUD","PCARD Mathew Durack Storms event- meal","BKPFF","WF-BATCH",0,"","SA",null,"Include","Internal"]
["RFBU","COIN","2021-09-29","2021-09-29","6","2022","1100","108504137","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","521508","Accommodation",52.23,"AUD","PCARD Mathew Durack this charge was reversed","BKPFF","WF-BATCH",0,"","SA",null,"Include","Internal"]
["RFBU","COIN","2021-09-29","2021-09-29","6","2022","1100","108504137","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","521508","Accommodation",45.45,"AUD","PCARD Mathew Durack Storms- meal for NH & MD","BKPFF","WF-BATCH",0,"","SA",null,"Include","Internal"]
["RFBU","COIN","2021-09-29","2021-09-29","6","2022","1100","108504137","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","521508","Accommodation",20.45,"AUD","PCARD Mathew Durack Storms event- meals x 2","BKPFF","WF-BATCH",0,"","SA",null,"Include","Internal"]
["RFBU","COIN","2021-09-29","2021-09-29","6","2022","1100","108504137","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","521508","Accommodation",110,"AUD","PCARD Brian Brann BB","BKPFF","WF-BATCH",0,"","SA",null,"Include","Internal"]
["RFBU","COIN","2021-09-29","2021-09-29","6","2022","1100","108504137","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","521508","Accommodation",10.77,"AUD","PCARD Brian Brann B Brann breakfast LDL storms","BKPFF","WF-BATCH",0,"","SA",null,"Include","Internal"]
["RFBU","COIN","2021-09-29","2021-09-29","6","2022","1100","108504137","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","521508","Accommodation",24.09,"AUD","PCARD Brian Brann BB & DP breakfast LDL storms","BKPFF","WF-BATCH",0,"","SA",null,"Include","Internal"]
["RFBU","COIN","2021-09-29","2021-09-29","6","2022","1100","108504137","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","521508","Accommodation",15.45,"AUD","PCARD Brian Brann B Brann lunch LDL storms","BKPFF","WF-BATCH",0,"","SA",null,"Include","Internal"]
["RFBU","COIN","2021-09-29","2021-09-29","6","2022","1100","108504137","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","521508","Accommodation",438.51,"AUD","PCARD Brian Brann B Brann accom Lilydale storms","BKPFF","WF-BATCH",0,"","SA",null,"Include","Internal"]
["RFBU","COIN","2021-09-29","2021-09-29","6","2022","1100","108504137","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","521508","Accommodation",23.18,"AUD","PCARD Brian Brann B Brann evening meal LDL storm","BKPFF","WF-BATCH",0,"","SA",null,"Include","Internal"]
["RFBU","COIN","2021-09-29","2021-09-29","6","2022","1100","108504147","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","521100","Materials",-164.69,"AUD","PCARD Nicholas Hewes Charger","BKPFF","WF-BATCH",0,"","SA",null,"Include","Internal"]
["RFBU","COIN","2021-09-29","2021-09-29","6","2022","1100","108504147","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","521100","Materials",-652.5,"AUD","PCARD Mathew Durack Storms- New POA","BKPFF","WF-BATCH",0,"","SA",null,"Include","Internal"]
["RFBU","COIN","2021-09-29","2021-09-29","6","2022","1100","108504147","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","521508","Accommodation",57.45,"AUD","PCARD Mathew Durack reversed charge","BKPFF","WF-BATCH",0,"","SA",null,"Include","Internal"]
["RFBU","COIN","2021-09-29","2021-09-29","6","2022","1100","108504147","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","521508","Accommodation",-286,"AUD","PCARD Sergio Inacio Generator Team Stay - Warragul","BKPFF","WF-BATCH",0,"","SA",null,"Include","Internal"]
["RFBU","COIN","2021-09-29","2021-09-29","6","2022","1100","108504147","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","521508","Accommodation",-143,"AUD","PCARD Sergio Inacio Gen Team Night Stay Warragal","BKPFF","WF-BATCH",0,"","SA",null,"Include","Internal"]
["RFBU","COIN","2021-09-29","2021-09-29","6","2022","1100","108504147","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","521508","Accommodation",-172.99,"AUD","PCARD Dannie Ploegmakers Accom storms","BKPFF","WF-BATCH",0,"","SA",null,"Include","Internal"]
["RFBU","COIN","2021-09-29","2021-09-29","6","2022","1100","108504147","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","521508","Accommodation",-289.10000000000002,"AUD","PCARD Dannie Ploegmakers Dinner storm response","BKPFF","WF-BATCH",0,"","SA",null,"Include","Internal"]
["RFBU","COIN","2021-09-29","2021-09-29","6","2022","1100","108504147","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","521508","Accommodation",-94.3,"AUD","PCARD Dannie Ploegmakers Bfast storm response","BKPFF","WF-BATCH",0,"","SA",null,"Include","Internal"]
["RFBU","COIN","2021-09-29","2021-09-29","6","2022","1100","108504147","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","521508","Accommodation",-1917.69,"AUD","PCARD Dannie Ploegmakers Accom storm response","BKPFF","WF-BATCH",0,"","SA",null,"Include","Internal"]
["RFBU","COIN","2021-09-29","2021-09-29","6","2022","1100","108504147","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","521508","Accommodation",-39.65,"AUD","PCARD Nicholas Hewes Meals x 1 Tech","BKPFF","WF-BATCH",0,"","SA",null,"Include","Internal"]
["RFBU","COIN","2021-09-29","2021-09-29","6","2022","1100","108504147","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","521508","Accommodation",-129.65,"AUD","PCARD Nicholas Hewes Meals x 2 Techs","BKPFF","WF-BATCH",0,"","SA",null,"Include","Internal"]
["RFBU","COIN","2021-09-29","2021-09-29","6","2022","1100","108504147","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","521508","Accommodation",-32.299999999999997,"AUD","PCARD Dannie Ploegmakers dinner storm response","BKPFF","WF-BATCH",0,"","SA",null,"Include","Internal"]
["RFBU","COIN","2021-09-29","2021-09-29","6","2022","1100","108504147","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","521508","Accommodation",-40.4,"AUD","PCARD Dannie Ploegmakers Lunch storm response","BKPFF","WF-BATCH",0,"","SA",null,"Include","Internal"]
["RFBU","COIN","2021-09-29","2021-09-29","6","2022","1100","108504147","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","521508","Accommodation",-20,"AUD","PCARD Dannie Ploegmakers Bfast groceries storm res","BKPFF","WF-BATCH",0,"","SA",null,"Include","Internal"]
["RFBU","COIN","2021-09-29","2021-09-29","6","2022","1100","108504147","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","521508","Accommodation",-70.03,"AUD","PCARD Mathew Durack Storms event- meals","BKPFF","WF-BATCH",0,"","SA",null,"Include","Internal"]
["RFBU","COIN","2021-09-29","2021-09-29","6","2022","1100","108504147","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","521508","Accommodation",-100.15,"AUD","PCARD Mathew Durack Storms event- meal","BKPFF","WF-BATCH",0,"","SA",null,"Include","Internal"]
["RFBU","COIN","2021-09-29","2021-09-29","6","2022","1100","108504147","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","521508","Accommodation",-57.45,"AUD","PCARD Mathew Durack this charge was reversed","BKPFF","WF-BATCH",0,"","SA",null,"Include","Internal"]
["RFBU","COIN","2021-09-29","2021-09-29","6","2022","1100","108504147","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","521508","Accommodation",-50,"AUD","PCARD Mathew Durack Storms- meal for NH & MD","BKPFF","WF-BATCH",0,"","SA",null,"Include","Internal"]
["RFBU","COIN","2021-09-29","2021-09-29","6","2022","1100","108504147","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","521508","Accommodation",-22.5,"AUD","PCARD Mathew Durack Storms event- meals x 2","BKPFF","WF-BATCH",0,"","SA",null,"Include","Internal"]
["RFBU","COIN","2021-09-29","2021-09-29","6","2022","1100","108504147","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","521508","Accommodation",-121,"AUD","PCARD Brian Brann BB","BKPFF","WF-BATCH",0,"","SA",null,"Include","Internal"]
["RFBU","COIN","2021-09-29","2021-09-29","6","2022","1100","108504147","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","521508","Accommodation",-11.85,"AUD","PCARD Brian Brann B Brann breakfast LDL storms","BKPFF","WF-BATCH",0,"","SA",null,"Include","Internal"]
["RFBU","COIN","2021-09-29","2021-09-29","6","2022","1100","108504147","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","521508","Accommodation",-26.5,"AUD","PCARD Brian Brann BB & DP breakfast LDL storms","BKPFF","WF-BATCH",0,"","SA",null,"Include","Internal"]
["RFBU","COIN","2021-09-29","2021-09-29","6","2022","1100","108504147","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","521508","Accommodation",-17,"AUD","PCARD Brian Brann B Brann lunch LDL storms","BKPFF","WF-BATCH",0,"","SA",null,"Include","Internal"]
["RFBU","COIN","2021-09-29","2021-09-29","6","2022","1100","108504147","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","521508","Accommodation",-482.36,"AUD","PCARD Brian Brann B Brann accom Lilydale storms","BKPFF","WF-BATCH",0,"","SA",null,"Include","Internal"]
["RFBU","COIN","2021-09-29","2021-09-29","6","2022","1100","108504147","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","521508","Accommodation",-25.5,"AUD","PCARD Brian Brann B Brann evening meal LDL storm","BKPFF","WF-BATCH",0,"","SA",null,"Include","Internal"]
["RFBU","COIN","2021-06-29","2021-06-29","3","2022","1100","108174747","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","506401","S&W Proj - NT Adj",9662.69,"AUD","Storm Timesheet - JT","BKPFF","WF-BATCH",0,"","AB",null,"Exclude"]
["RFBU","COIN","2021-06-29","2021-06-29","3","2022","1100","108174747","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","506401","S&W Proj - NT Adj",3844.84,"AUD","Storm Timesheet - TD","BKPFF","WF-BATCH",0,"","AB",null,"Exclude"]
["RFBU","COIN","2021-06-29","2021-06-29","3","2022","1100","108174747","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","506401","S&W Proj - NT Adj",8195.58,"AUD","Storm Timesheet - RQ","BKPFF","WF-BATCH",0,"","AB",null,"Exclude"]
["RFBU","COIN","2021-06-29","2021-06-29","3","2022","1100","108174747","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","506401","S&W Proj - NT Adj",12242.78,"AUD","Storm Timesheet - LW","BKPFF","WF-BATCH",0,"","AB",null,"Exclude"]
["RFBU","COIN","2021-06-29","2021-06-29","3","2022","1100","108174747","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","506401","S&W Proj - NT Adj",8397.94,"AUD","Storm Timesheet - SJ","BKPFF","WF-BATCH",0,"","AB",null,"Exclude"]
["RFBU","COIN","2021-06-29","2021-06-29","3","2022","1100","108174747","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","506401","S&W Proj - NT Adj",7487.32,"AUD","Storm Timesheet - LH","BKPFF","WF-BATCH",0,"","AB",null,"Exclude"]
["RFBU","COIN","2021-06-29","2021-06-29","3","2022","1100","108174747","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","506401","S&W Proj - NT Adj",3237.76,"AUD","Storm Timesheet - LW","BKPFF","WF-BATCH",0,"","AB",null,"Exclude"]
["RFBU","COIN","2021-06-29","2021-06-29","3","2022","1100","108174980","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","506401","S&W Proj - NT Adj",133381.17000000001,"AUD","June-21 Storm Costs Timesheet Reallocation - NOCP","BKPFF","WF-BATCH",0,"","AB",null,"Exclude"]
["RFBU","COIN","2021-06-29","2021-06-29","3","2022","1100","108174980","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","506401","S&W Proj - NT Adj",31964.46,"AUD","June-21 Storm Costs Timesheet Reallocation - NOES","BKPFF","WF-BATCH",0,"","AB",null,"Exclude"]
["RFBU","COIN","2021-06-29","2021-06-29","3","2022","1100","108174980","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","506401","S&W Proj - NT Adj",11019.62,"AUD","June-21 Storm Costs Timesheet Reallocation - NOMP","BKPFF","WF-BATCH",0,"","AB",null,"Exclude"]
["RFBU","COIN","2021-06-29","2021-06-29","3","2022","1100","108175027","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","506401","S&W Proj - NT Adj",8467.5,"AUD","Compliance Storm Inspection - AC","BKPFF","WF-BATCH",0,"","AB",null,"Exclude"]
["RFBU","COIN","2021-06-29","2021-06-29","3","2022","1100","108175027","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","506401","S&W Proj - NT Adj",8467.5,"AUD","Compliance Storm Inspection - BB","BKPFF","WF-BATCH",0,"","AB",null,"Exclude"]
["RFBU","COIN","2021-06-29","2021-06-29","3","2022","1100","108175027","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","506401","S&W Proj - NT Adj",8467.5,"AUD","Compliance Storm Inspection - DP","BKPFF","WF-BATCH",0,"","AB",null,"Exclude"]
["RFBU","COIN","2021-06-29","2021-06-29","3","2022","1100","108175027","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","506401","S&W Proj - NT Adj",8467.5,"AUD","Compliance Storm Inspection - RB","BKPFF","WF-BATCH",0,"","AB",null,"Exclude"]
["RFBU","COIN","2021-06-29","2021-06-29","3","2022","1100","108175027","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","506401","S&W Proj - NT Adj",8467.5,"AUD","Compliance Storm Inspection - BP","BKPFF","WF-BATCH",0,"","AB",null,"Exclude"]
["RFBU","COIN","2021-06-29","2021-06-29","3","2022","1100","108175027","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","506401","S&W Proj - NT Adj",8467.5,"AUD","Compliance Storm Inspection - MP","BKPFF","WF-BATCH",0,"","AB",null,"Exclude"]
["RFBU","COIN","2021-06-29","2021-06-29","3","2022","1100","108175027","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","506401","S&W Proj - NT Adj",8467.5,"AUD","Compliance Storm Inspection - DH","BKPFF","WF-BATCH",0,"","AB",null,"Exclude"]
["RFBU","COIN","2021-06-29","2021-07-02","4","2022","1100","108243036","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","506401","S&W Proj - NT Adj",-133381.17000000001,"AUD","June-21 Storm Costs Timesheet Reallocation - NOCP","BKPFF","PRAVEENK",0,"","AB",null,"Exclude"]
["RFBU","COIN","2021-06-29","2021-07-02","4","2022","1100","108243036","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","506401","S&W Proj - NT Adj",-31964.46,"AUD","June-21 Storm Costs Timesheet Reallocation - NOES","BKPFF","PRAVEENK",0,"","AB",null,"Exclude"]
["RFBU","COIN","2021-06-29","2021-07-02","4","2022","1100","108243036","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","506401","S&W Proj - NT Adj",-11019.62,"AUD","June-21 Storm Costs Timesheet Reallocation - NOMP","BKPFF","PRAVEENK",0,"","AB",null,"Exclude"]
["RFBU","COIN","2021-07-24","2021-07-24","4","2022","1100","108276188","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","516413","Light Meals on Site",72.790000000000006,"AUD","PCARD Keang Ung Ceot dinner 13/06 4 storm even","BKPFF","SYS_BCBATCH",0,"","SA",null,"Include","Internal"]
["RFBU","COIN","2021-07-24","2021-07-24","4","2022","1100","108276188","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","516413","Light Meals on Site",50.5,"AUD","PCARD Keang Ung CEOT beverage for storm event","BKPFF","SYS_BCBATCH",0,"","SA",null,"Include","Internal"]
["RFBU","COIN","2021-07-24","2021-07-24","4","2022","1100","108276188","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","516413","Light Meals on Site",430.85,"AUD","PCARD Keang Ung CEOT Lunch for Storm Event","BKPFF","SYS_BCBATCH",0,"","SA",null,"Include","Internal"]
["RFBU","COIN","2021-07-24","2021-07-24","4","2022","1100","108276188","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","516413","Light Meals on Site",23.5,"AUD","PCARD Keang Ung Ceot beverage for storm event","BKPFF","SYS_BCBATCH",0,"","SA",null,"Include","Internal"]
["RFBU","COIN","2021-07-24","2021-07-24","4","2022","1100","108276188","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","516413","Light Meals on Site",300.49,"AUD","PCARD Keang Ung CEOT Lunch for Storm Event","BKPFF","SYS_BCBATCH",0,"","SA",null,"Include","Internal"]
["RFBU","COIN","2021-07-24","2021-07-24","4","2022","1100","108276188","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","516413","Light Meals on Site",33.44,"AUD","PCARD Keang Ung 21/06 dinner for storm event","BKPFF","SYS_BCBATCH",0,"","SA",null,"Include","Internal"]
["RFBU","COIN","2021-07-24","2021-07-24","4","2022","1100","108276188","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","516413","Light Meals on Site",97.69,"AUD","PCARD Keang Ung CEOT meal storm event","BKPFF","SYS_BCBATCH",0,"","SA",null,"Include","Internal"]
["RFBU","COIN","2021-07-24","2021-07-24","4","2022","1100","108276188","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","521508","Accommodation",22,"AUD","PCARD Nicholas Hewes Meals x 1 Tech","BKPFF","SYS_BCBATCH",0,"","SA",null,"Include","Internal"]
["RFBU","COIN","2021-07-24","2021-07-24","4","2022","1100","108276188","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","521100","Materials",146.94999999999999,"AUD","PCARD Nicholas Hewes Straps","BKPFF","SYS_BCBATCH",0,"","SA",null,"Include","Internal"]
["RFBU","COIN","2021-07-24","2021-07-24","4","2022","1100","108276188","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","521508","Accommodation",47.15,"AUD","PCARD Nicholas Hewes Meals x 2 Techs","BKPFF","SYS_BCBATCH",0,"","SA",null,"Include","Internal"]
["RFBU","COIN","2021-07-24","2021-07-24","4","2022","1100","108276188","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","521508","Accommodation",17.649999999999999,"AUD","PCARD Nicholas Hewes Meals x 1 Tech","BKPFF","SYS_BCBATCH",0,"","SA",null,"Include","Internal"]
["RFBU","COIN","2021-07-24","2021-07-24","4","2022","1100","108276188","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","521100","Materials",660,"AUD","PCARD Nicholas Hewes Gen Tags & Defib Sticker","BKPFF","SYS_BCBATCH",0,"","SA",null,"Include","Internal"]
["RFBU","COIN","2021-07-24","2021-07-24","4","2022","1100","108276188","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","521508","Accommodation",82.5,"AUD","PCARD Nicholas Hewes Meals x 2 Techs","BKPFF","SYS_BCBATCH",0,"","SA",null,"Include","Internal"]
["RFBU","COIN","2021-07-24","2021-07-24","4","2022","1100","108277707","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","521100","Materials",164.69,"AUD","PCARD Nicholas Hewes Charger","BKPFF","SYS_BCBATCH",0,"","SA",null,"Include","Internal"]
["RMWE","COIN","2021-07-26","2021-07-26","4","2022","1100","108278461","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","516204","Professional Fees",125000,"AUD","SMS","MKPF","KLANCAST",0,"","WE",null,"Include","Internal"]
["RFBU","COIN","2021-07-26","2021-07-26","4","2022","1100","108278574","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","506401","S&W Proj - NT Adj",41806.54,"AUD","Timesheet Transfers - 13187","BKPFF","WF-BATCH",0,"","AB",null,"Exclude"]
["RFBU","COIN","2021-07-26","2021-07-26","4","2022","1100","108278574","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","506401","S&W Proj - NT Adj",31820.44,"AUD","Timesheet Transfers - 15006","BKPFF","WF-BATCH",0,"","AB",null,"Exclude"]
["RFBU","COIN","2021-07-26","2021-07-26","4","2022","1100","108278574","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","506401","S&W Proj - NT Adj",136761.71,"AUD","Timesheet Transfers - 13175","BKPFF","WF-BATCH",0,"","AB",null,"Exclude"]
["RFBU","COIN","2021-07-26","2021-07-26","4","2022","1100","108278574","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","506401","S&W Proj - NT Adj",18461.490000000002,"AUD","Timesheet Transfers - 12018","BKPFF","WF-BATCH",0,"","AB",null,"Exclude"]
["RFBU","COIN","2021-07-26","2021-07-26","4","2022","1100","108278574","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","506401","S&W Proj - NT Adj",6127.03,"AUD","Timesheet Transfers - 14620","BKPFF","WF-BATCH",0,"","AB",null,"Exclude"]
["RFBU","COIN","2021-07-27","2021-07-27","4","2022","1100","108282081","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","506500","Cont Lab Non-Payroll",8292.77,"AUD","Mary's work for Storm Response","BKPFF","WF-BATCH",0,"","AB",null,"Exclude"]
["RMWE","COIN","2021-07-28","2021-07-28","4","2022","1100","108282960","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","506500","Cont Lab Non-Payroll",4909.17,"AUD","Siobhan Contractor w/c June 13","MKPF","CSAID",0,"","WE",null,"Exclude"]
["RMWE","COIN","2021-07-28","2021-07-28","4","2022","1100","108282961","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","506500","Cont Lab Non-Payroll",4178.3599999999997,"AUD","Siobhan contractor w/e June 20","MKPF","CSAID",0,"","WE",null,"Exclude"]
["RFBU","COIN","2021-07-28","2021-07-28","4","2022","1100","108284892","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","516204","Professional Fees",-125000,"AUD","GL Account Corr. to Temp Labour PO 4500122226","BKPFF","WF-BATCH",0,"","AB",null,"Include","Internal"]
["RFBU","COIN","2021-07-28","2021-07-28","4","2022","1100","108284892","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","506500","Cont Lab Non-Payroll",125000,"AUD","GL Account Corr. to Temp Labour PO 4500122226","BKPFF","WF-BATCH",0,"","AB",null,"Exclude"]
["RFBU","COIN","2021-07-29","2021-07-29","4","2022","1100","108284989","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","506401","S&W Proj - NT Adj",-6810.47,"AUD","Downer Storm Transfers","BKPFF","WF-BATCH",0,"","AB",null,"Exclude"]
["RFBU","COIN","2021-07-29","2021-07-29","4","2022","1100","108284989","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","506401","S&W Proj - NT Adj",136824.84,"AUD","Downer Storm Transfers","BKPFF","WF-BATCH",0,"","AB",null,"Exclude"]
["RFBU","COIN","2021-07-29","2021-07-29","4","2022","1100","108284989","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","506401","S&W Proj - NT Adj",35972.699999999997,"AUD","Downer Storm Transfers","BKPFF","WF-BATCH",0,"","AB",null,"Exclude"]
["RFBU","COIN","2021-08-17","2021-08-17","5","2022","1100","108367054","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","516204","Professional Fees",125000,"AUD","GL Account Corr. to Temp Labour PO 4500122226","BKPFF","WF-BATCH",0,"","AB",null,"Include","Internal"]
["RFBU","COIN","2021-08-17","2021-08-17","5","2022","1100","108367054","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","506500","Cont Lab Non-Payroll",-125000,"AUD","GL Account Corr. to Temp Labour PO 4500122226","BKPFF","WF-BATCH",0,"","AB",null,"Exclude"]
["RFBU","COIN","2021-08-31","2021-08-31","5","2022","1100","108372009","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","506401","S&W Proj - NT Adj",8653.31,"AUD","CEOT Julie OT storms time","BKPFF","WF-BATCH",0,"","AB",null,"Exclude"]
["RMWE","COIN","2021-07-26","2021-09-02","6","2022","1100","108461552","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","516204","Professional Fees",-125000,"AUD","SMS","MKPF","SHALI",0,"","WE",null,"Include","Internal"]
["RMWE","COIN","2021-09-06","2021-09-06","6","2022","1100","108464854","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","516204","Professional Fees",5818.03,"AUD","Customer & Engagement Specialist","MKPF","STUFFEN",0,"","WE",null,"Include","Internal"]
["RMWE","COIN","2021-09-06","2021-09-06","6","2022","1100","108464855","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","516204","Professional Fees",5818.03,"AUD","Consultant","MKPF","STUFFEN",0,"","WE",null,"Include","Internal"]
["RMWE","COIN","2021-09-06","2021-09-06","6","2022","1100","108464859","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","516204","Professional Fees",5818.03,"AUD","Contractor","MKPF","STUFFEN",0,"","WE",null,"Include","Internal"]
["RMWE","COIN","2021-09-06","2021-09-06","6","2022","1100","108464862","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","516204","Professional Fees",6787.7,"AUD","Contractor","MKPF","STUFFEN",0,"","WE",null,"Include","Internal"]
["RMWE","COIN","2021-09-21","2021-09-21","6","2022","1100","108488730","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","516204","Professional Fees",5139.26,"AUD","Customer Engagement Specialist","MKPF","STUFFEN",0,"","WE",null,"Include","Internal"]
["RMWE","COIN","2021-09-21","2021-09-21","6","2022","1100","108488732","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","516204","Professional Fees",5818.03,"AUD","Customer Engagement Speci","MKPF","STUFFEN",0,"","WE",null,"Include","Internal"]
["RMRU","RKL","2021-06-16","2021-06-16","3","2022","1100","309350084","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810143","Corp Support NT",117.54,"AUD","Storm","AFRU","SYS_BCBATCH",10009884,"","",{"$f":"VLOOKUP(U112,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["RMRU","RKL","2021-06-16","2021-06-16","3","2022","1100","309350085","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810143","Corp Support NT",235.08,"AUD","Storm","AFRU","SYS_BCBATCH",10009884,"","",{"$f":"VLOOKUP(U113,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["RMRU","RKL","2021-06-16","2021-06-16","3","2022","1100","309350086","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810143","Corp Support NT",313.44,"AUD","Storm","AFRU","SYS_BCBATCH",10009884,"","",{"$f":"VLOOKUP(U114,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["RMRU","RKL","2021-06-16","2021-06-16","3","2022","1100","309350087","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810243","Corp Support OT",289.68,"AUD","storm","AFRU","SYS_BCBATCH",10006935,"","",{"$f":"VLOOKUP(U115,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["RMRU","RKL","2021-06-16","2021-06-16","3","2022","1100","309350088","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810243","Corp Support OT",217.26,"AUD","Storm -2021- Time Sheet - 12014","AFRU","SYS_BCBATCH",10006935,"","",{"$f":"VLOOKUP(U116,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["RMRU","RKL","2021-06-16","2021-06-16","3","2022","1100","309350089","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810243","Corp Support OT",362.1,"AUD","Storm -2021- Time Sheet - 12014","AFRU","SYS_BCBATCH",10006935,"","",{"$f":"VLOOKUP(U117,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["RMRU","RKL","2021-06-16","2021-06-16","3","2022","1100","309350090","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810243","Corp Support OT",525.04999999999995,"AUD","Storm -2021- Time Sheet - 12014","AFRU","SYS_BCBATCH",10006935,"","",{"$f":"VLOOKUP(U118,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["RMRU","RKL","2021-06-16","2021-06-16","3","2022","1100","309350091","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810223","Corp Prof OT",1161.99,"AUD","","AFRU","SYS_BCBATCH",10000557,"","",{"$f":"VLOOKUP(U119,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["RMRU","RKL","2021-06-16","2021-06-16","3","2022","1100","309350092","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810223","Corp Prof OT",1161.99,"AUD","","AFRU","SYS_BCBATCH",10000557,"","",{"$f":"VLOOKUP(U120,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["RMRU","RKL","2021-06-16","2021-06-16","3","2022","1100","309350093","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810223","Corp Prof OT",1032.8800000000001,"AUD","","AFRU","SYS_BCBATCH",10000557,"","",{"$f":"VLOOKUP(U121,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["RMRU","RKL","2021-06-16","2021-06-16","3","2022","1100","309350095","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810160","Corp Manager NT",896.85,"AUD","","AFRU","SYS_BCBATCH",10001211,"","",{"$f":"VLOOKUP(U122,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["RMRU","RKL","2021-06-16","2021-06-16","3","2022","1100","309350096","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810160","Corp Manager NT",896.85,"AUD","","AFRU","SYS_BCBATCH",10001211,"","",{"$f":"VLOOKUP(U123,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["RMRU","RKL","2021-06-16","2021-06-16","3","2022","1100","309350097","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810160","Corp Manager NT",896.85,"AUD","","AFRU","SYS_BCBATCH",10001211,"","",{"$f":"VLOOKUP(U124,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["RMRU","RKL","2021-06-16","2021-06-16","3","2022","1100","309350098","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810160","Corp Manager NT",239.16,"AUD","","AFRU","SYS_BCBATCH",10001211,"","",{"$f":"VLOOKUP(U125,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["","RKL","2021-06-11","2021-06-16","3","2022","1100","309350258","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810300","Allowance Expenses",538.11,"AUD","Fri 11/6/21 Storm response 7am - 6pm. 3","CATS","SYS_BCBATCH",10001211,"","",{"$f":"VLOOKUP(U126,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["","RKL","2021-06-11","2021-06-16","3","2022","1100","309350258","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810300","Allowance Expenses",1883.39,"AUD","Sat 12/6/21 Storm response 8:30am to 7pm","CATS","SYS_BCBATCH",10001211,"","",{"$f":"VLOOKUP(U127,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["","RKL","2021-06-11","2021-06-16","3","2022","1100","309350258","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810300","Allowance Expenses",1704.02,"AUD","Sun 13/6/21 Storm response 7:30am to 5pm","CATS","SYS_BCBATCH",10001211,"","",{"$f":"VLOOKUP(U128,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["","RKL","2021-06-06","2021-06-17","3","2022","1100","309350490","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810300","Allowance Expenses",387.33,"AUD","","CATS","SYS_BCBATCH",10001415,"","",{"$f":"VLOOKUP(U129,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["","RKL","2021-06-06","2021-06-17","3","2022","1100","309350490","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810300","Allowance Expenses",322.77999999999997,"AUD","","CATS","SYS_BCBATCH",10001415,"","",{"$f":"VLOOKUP(U130,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["","RKL","2021-06-06","2021-06-17","3","2022","1100","309350490","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810300","Allowance Expenses",1613.88,"AUD","","CATS","SYS_BCBATCH",10001415,"","",{"$f":"VLOOKUP(U131,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["","RKL","2021-06-06","2021-06-17","3","2022","1100","309350490","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810300","Allowance Expenses",60.36,"AUD","","CATS","SYS_BCBATCH",10001415,"","",{"$f":"VLOOKUP(U132,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["","RKL","2021-06-06","2021-06-17","3","2022","1100","309350490","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810300","Allowance Expenses",1549.32,"AUD","","CATS","SYS_BCBATCH",10001415,"","",{"$f":"VLOOKUP(U133,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["","RKL","2021-06-06","2021-06-17","3","2022","1100","309350490","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810300","Allowance Expenses",40.24,"AUD","","CATS","SYS_BCBATCH",10001415,"","",{"$f":"VLOOKUP(U134,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["","RKL","2021-06-06","2021-06-17","3","2022","1100","309350490","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810300","Allowance Expenses",1291.0999999999999,"AUD","","CATS","SYS_BCBATCH",10001415,"","",{"$f":"VLOOKUP(U135,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["","RKL","2021-06-06","2021-06-17","3","2022","1100","309350490","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810300","Allowance Expenses",40.24,"AUD","","CATS","SYS_BCBATCH",10001415,"","",{"$f":"VLOOKUP(U136,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["","RKL","2021-06-06","2021-06-17","3","2022","1100","309350490","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810300","Allowance Expenses",322.77999999999997,"AUD","","CATS","SYS_BCBATCH",10001415,"","",{"$f":"VLOOKUP(U137,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["","RKL","2021-06-06","2021-06-17","3","2022","1100","309350490","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810300","Allowance Expenses",20.12,"AUD","","CATS","SYS_BCBATCH",10001415,"","",{"$f":"VLOOKUP(U138,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-06-16","2021-06-16","3","2022","1100","309351391","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810220","Corp Ops Lead OT",1166.5999999999999,"AUD","","AFRU","SYS_BCBATCH",10001704,"","",{"$f":"VLOOKUP(U139,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["RMRU","RKL","2021-06-16","2021-06-16","3","2022","1100","309351393","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810123","Corp Prof NT",387.32,"AUD","EMT- Recovery Hubs Strike Team","AFRU","SYS_BCBATCH",10001155,"","",{"$f":"VLOOKUP(U140,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["RMRU","RKL","2021-06-16","2021-06-16","3","2022","1100","309351394","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810122","Corp Prof Exp NT",758.85,"AUD","EMT - Recovery Hub Strike Team","AFRU","SYS_BCBATCH",10009892,"","",{"$f":"VLOOKUP(U141,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["RMRU","RKL","2021-06-16","2021-06-16","3","2022","1100","309351395","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810136","Corp Semi Prof NT",235.66,"AUD","","AFRU","SYS_BCBATCH",10002370,"","",{"$f":"VLOOKUP(U142,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-06-17","2021-06-17","3","2022","1100","309353567","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810118","Project Manager NT",854.03,"AUD","","AFRU","SYS_BCBATCH",10000641,"","",{"$f":"VLOOKUP(U143,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-06-17","2021-06-17","3","2022","1100","309353568","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810122","Corp Prof Exp NT",758.85,"AUD","EMT - recovery hub strike team","AFRU","SYS_BCBATCH",10009892,"","",{"$f":"VLOOKUP(U144,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["RMRU","RKL","2021-06-17","2021-06-17","3","2022","1100","309353570","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810122","Corp Prof Exp NT",716.1,"AUD","Storm Response","AFRU","SYS_BCBATCH",10001451,"","",{"$f":"VLOOKUP(U145,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["RMRU","RKL","2021-06-17","2021-06-17","3","2022","1100","309353571","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810122","Corp Prof Exp NT",716.1,"AUD","Storm Response","AFRU","SYS_BCBATCH",10001451,"","",{"$f":"VLOOKUP(U146,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["RMRU","RKL","2021-06-17","2021-06-17","3","2022","1100","309353572","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810122","Corp Prof Exp NT",716.1,"AUD","Storm Response","AFRU","SYS_BCBATCH",10001451,"","",{"$f":"VLOOKUP(U147,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["RMRU","RKL","2021-06-17","2021-06-17","3","2022","1100","309353573","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810122","Corp Prof Exp NT",716.1,"AUD","Storm Response","AFRU","SYS_BCBATCH",10001451,"","",{"$f":"VLOOKUP(U148,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["RMRU","RKL","2021-06-17","2021-06-17","3","2022","1100","309353575","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810136","Corp Semi Prof NT",545.25,"AUD","","AFRU","SYS_BCBATCH",10002617,"","",{"$f":"VLOOKUP(U149,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-06-17","2021-06-17","3","2022","1100","309353576","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810136","Corp Semi Prof NT",545.25,"AUD","","AFRU","SYS_BCBATCH",10002617,"","",{"$f":"VLOOKUP(U150,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-06-17","2021-06-17","3","2022","1100","309353577","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810136","Corp Semi Prof NT",72.7,"AUD","","AFRU","SYS_BCBATCH",10002617,"","",{"$f":"VLOOKUP(U151,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-06-17","2021-06-17","3","2022","1100","309353578","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810136","Corp Semi Prof NT",399.85,"AUD","","AFRU","SYS_BCBATCH",10002617,"","",{"$f":"VLOOKUP(U152,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-06-17","2021-06-17","3","2022","1100","309353579","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810123","Corp Prof NT",645.53,"AUD","","AFRU","SYS_BCBATCH",10001415,"","",{"$f":"VLOOKUP(U153,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-06-17","2021-06-17","3","2022","1100","309353580","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810123","Corp Prof NT",645.53,"AUD","","AFRU","SYS_BCBATCH",10001415,"","",{"$f":"VLOOKUP(U154,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-06-17","2021-06-17","3","2022","1100","309353586","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810123","Corp Prof NT",645.53,"AUD","","AFRU","SYS_BCBATCH",10001415,"","",{"$f":"VLOOKUP(U155,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-06-17","2021-06-17","3","2022","1100","309353587","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810123","Corp Prof NT",645.53,"AUD","","AFRU","SYS_BCBATCH",10001415,"","",{"$f":"VLOOKUP(U156,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-06-17","2021-06-17","3","2022","1100","309353589","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810120","Corp Ops Lead NT",570.78,"AUD","","AFRU","SYS_BCBATCH",10002532,"","",{"$f":"VLOOKUP(U157,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["","RKL","2021-06-12","2021-06-18","3","2022","1100","309358258","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810300","Allowance Expenses",60.36,"AUD","","CATS","SYS_BCBATCH",10002617,"","",{"$f":"VLOOKUP(U158,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["","RKL","2021-06-12","2021-06-18","3","2022","1100","309358258","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810300","Allowance Expenses",60.36,"AUD","","CATS","SYS_BCBATCH",10002617,"","",{"$f":"VLOOKUP(U159,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["","RKL","2021-06-12","2021-06-18","3","2022","1100","309358258","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810300","Allowance Expenses",40.24,"AUD","","CATS","SYS_BCBATCH",10002617,"","",{"$f":"VLOOKUP(U160,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-06-18","2021-06-18","3","2022","1100","309359094","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810160","Corp Manager NT",958.73,"AUD","","AFRU","SYS_BCBATCH",10009915,"","",{"$f":"VLOOKUP(U161,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-06-18","2021-06-18","3","2022","1100","309359095","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810160","Corp Manager NT",958.73,"AUD","","AFRU","SYS_BCBATCH",10009915,"","",{"$f":"VLOOKUP(U162,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-06-18","2021-06-18","3","2022","1100","309359096","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810160","Corp Manager NT",958.73,"AUD","","AFRU","SYS_BCBATCH",10009915,"","",{"$f":"VLOOKUP(U163,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-06-18","2021-06-18","3","2022","1100","309359107","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810236","Corp Semi Prof OT",163.58000000000001,"AUD","","AFRU","SYS_BCBATCH",10002617,"","",{"$f":"VLOOKUP(U164,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-06-18","2021-06-18","3","2022","1100","309359108","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810236","Corp Semi Prof OT",1363.13,"AUD","","AFRU","SYS_BCBATCH",10002617,"","",{"$f":"VLOOKUP(U165,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-06-18","2021-06-18","3","2022","1100","309359109","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810236","Corp Semi Prof OT",1308.5999999999999,"AUD","","AFRU","SYS_BCBATCH",10002617,"","",{"$f":"VLOOKUP(U166,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-06-18","2021-06-18","3","2022","1100","309359110","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810236","Corp Semi Prof OT",981.45,"AUD","","AFRU","SYS_BCBATCH",10002617,"","",{"$f":"VLOOKUP(U167,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-06-18","2021-06-18","3","2022","1100","309359111","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810236","Corp Semi Prof OT",54.53,"AUD","","AFRU","SYS_BCBATCH",10002617,"","",{"$f":"VLOOKUP(U168,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-06-18","2021-06-18","3","2022","1100","309359112","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810236","Corp Semi Prof OT",218.1,"AUD","","AFRU","SYS_BCBATCH",10002617,"","",{"$f":"VLOOKUP(U169,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-06-18","2021-06-18","3","2022","1100","309359125","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810141","Corp Snr Mngr NT",1213.3499999999999,"AUD","","AFRU","SYS_BCBATCH",10001047,"","",{"$f":"VLOOKUP(U170,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-06-18","2021-06-18","3","2022","1100","309359126","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810141","Corp Snr Mngr NT",1213.3499999999999,"AUD","","AFRU","SYS_BCBATCH",10001047,"","",{"$f":"VLOOKUP(U171,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-06-18","2021-06-18","3","2022","1100","309359127","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810141","Corp Snr Mngr NT",1213.3499999999999,"AUD","","AFRU","SYS_BCBATCH",10001047,"","",{"$f":"VLOOKUP(U172,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-06-18","2021-06-18","3","2022","1100","309359128","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810141","Corp Snr Mngr NT",1213.3499999999999,"AUD","","AFRU","SYS_BCBATCH",10001047,"","",{"$f":"VLOOKUP(U173,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["","RKL","2021-06-17","2021-06-24","3","2022","1100","309359172","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810300","Allowance Expenses",716.1,"AUD","","CATS","SYS_BCBATCH",10001318,"","",{"$f":"VLOOKUP(U174,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["","RKL","2021-06-17","2021-06-24","3","2022","1100","309359172","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810300","Allowance Expenses",20.12,"AUD","","CATS","SYS_BCBATCH",10001318,"","",{"$f":"VLOOKUP(U175,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-06-25","2021-06-25","3","2022","1100","309359199","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810122","Corp Prof Exp NT",-1315.34,"AUD","Customer Communications","AFRU","SYS_BCBATCH",10009135,"","",{"$f":"VLOOKUP(U176,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["RMRU","RKL","2021-06-20","2021-06-20","3","2022","1100","309360453","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810123","Corp Prof NT",676.05,"AUD","","AFRU","SYS_BCBATCH",10002256,"","",{"$f":"VLOOKUP(U177,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-06-20","2021-06-20","3","2022","1100","309360454","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810123","Corp Prof NT",676.05,"AUD","","AFRU","SYS_BCBATCH",10002256,"","",{"$f":"VLOOKUP(U178,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-06-20","2021-06-20","3","2022","1100","309360455","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810123","Corp Prof NT",676.05,"AUD","","AFRU","SYS_BCBATCH",10002256,"","",{"$f":"VLOOKUP(U179,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-06-20","2021-06-20","3","2022","1100","309360456","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810123","Corp Prof NT",676.05,"AUD","","AFRU","SYS_BCBATCH",10002256,"","",{"$f":"VLOOKUP(U180,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-06-20","2021-06-20","3","2022","1100","309360457","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810123","Corp Prof NT",676.05,"AUD","","AFRU","SYS_BCBATCH",10002256,"","",{"$f":"VLOOKUP(U181,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-06-20","2021-06-20","3","2022","1100","309360458","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810123","Corp Prof NT",676.05,"AUD","","AFRU","SYS_BCBATCH",10002256,"","",{"$f":"VLOOKUP(U182,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-06-21","2021-06-21","3","2022","1100","309360610","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810118","Project Manager NT",854.03,"AUD","","AFRU","SYS_BCBATCH",10000641,"","",{"$f":"VLOOKUP(U183,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-06-21","2021-06-21","3","2022","1100","309360611","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810122","Corp Prof Exp NT",758.85,"AUD","EMT Recovery Hub Strike Team","AFRU","SYS_BCBATCH",10009892,"","",{"$f":"VLOOKUP(U184,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["RMRU","RKL","2021-06-21","2021-06-21","3","2022","1100","309360614","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810122","Corp Prof Exp NT",607.08000000000004,"AUD","EMT - Customer contact centre training,","AFRU","SYS_BCBATCH",10009892,"","",{"$f":"VLOOKUP(U185,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["RMRU","RKL","2021-06-21","2021-06-21","3","2022","1100","309361099","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810236","Corp Semi Prof OT",404,"AUD","Storm Response Customer Comms","AFRU","SYS_BCBATCH",10008965,"","",{"$f":"VLOOKUP(U186,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["RMRU","RKL","2021-06-21","2021-06-21","3","2022","1100","309361100","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810236","Corp Semi Prof OT",303,"AUD","Storm Response Customer Comms","AFRU","SYS_BCBATCH",10008965,"","",{"$f":"VLOOKUP(U187,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["RMRU","RKL","2021-06-21","2021-06-21","3","2022","1100","309361101","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810236","Corp Semi Prof OT",303,"AUD","Storm Response Customer Comms","AFRU","SYS_BCBATCH",10008965,"","",{"$f":"VLOOKUP(U188,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["RMRU","RKL","2021-06-21","2021-06-21","3","2022","1100","309361102","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810236","Corp Semi Prof OT",1060.5,"AUD","Storm Response Customer Comms","AFRU","SYS_BCBATCH",10008965,"","",{"$f":"VLOOKUP(U189,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["RMRU","RKL","2021-06-21","2021-06-21","3","2022","1100","309361103","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810122","Corp Prof Exp NT",716.1,"AUD","","AFRU","SYS_BCBATCH",10001318,"","",{"$f":"VLOOKUP(U190,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-06-21","2021-06-21","3","2022","1100","309361104","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810122","Corp Prof Exp NT",716.1,"AUD","","AFRU","SYS_BCBATCH",10001318,"","",{"$f":"VLOOKUP(U191,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-06-21","2021-06-21","3","2022","1100","309361105","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810236","Corp Semi Prof OT",1212,"AUD","Storm Response Customer Comms","AFRU","SYS_BCBATCH",10008965,"","",{"$f":"VLOOKUP(U192,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["RMRU","RKL","2021-06-21","2021-06-21","3","2022","1100","309361106","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810236","Corp Semi Prof OT",303,"AUD","Storm Response Customer Comms","AFRU","SYS_BCBATCH",10008965,"","",{"$f":"VLOOKUP(U193,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["RMRU","RKL","2021-06-21","2021-06-21","3","2022","1100","309361107","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810236","Corp Semi Prof OT",252.5,"AUD","Storm Response Customer Comms","AFRU","SYS_BCBATCH",10008965,"","",{"$f":"VLOOKUP(U194,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["RMRU","RKL","2021-06-21","2021-06-21","3","2022","1100","309361108","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810122","Corp Prof Exp NT",1315.34,"AUD","Customer Communications","AFRU","SYS_BCBATCH",10009135,"","",{"$f":"VLOOKUP(U195,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["RMRU","RKL","2021-06-21","2021-06-21","3","2022","1100","309361109","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810124","Corp Prof Spec NT",618.26,"AUD","","AFRU","SYS_BCBATCH",10000868,"","",{"$f":"VLOOKUP(U196,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["RMRU","RKL","2021-06-21","2021-06-21","3","2022","1100","309361110","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810220","Corp Ops Lead OT",291.64999999999998,"AUD","","AFRU","SYS_BCBATCH",10001233,"","",{"$f":"VLOOKUP(U197,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["RMRU","RKL","2021-06-21","2021-06-21","3","2022","1100","309361111","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810120","Corp Ops Lead NT",647.82000000000005,"AUD","","AFRU","SYS_BCBATCH",10001233,"","",{"$f":"VLOOKUP(U198,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["RMRU","RKL","2021-06-21","2021-06-21","3","2022","1100","309361112","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810220","Corp Ops Lead OT",174.99,"AUD","","AFRU","SYS_BCBATCH",10001233,"","",{"$f":"VLOOKUP(U199,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["RMRU","RKL","2021-06-21","2021-06-21","3","2022","1100","309361113","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810120","Corp Ops Lead NT",647.82000000000005,"AUD","","AFRU","SYS_BCBATCH",10001233,"","",{"$f":"VLOOKUP(U200,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["RMRU","RKL","2021-06-21","2021-06-21","3","2022","1100","309361114","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810223","Corp Prof OT",1014.08,"AUD","","AFRU","SYS_BCBATCH",10002256,"","",{"$f":"VLOOKUP(U201,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-06-21","2021-06-21","3","2022","1100","309361115","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810223","Corp Prof OT",1149.29,"AUD","","AFRU","SYS_BCBATCH",10002256,"","",{"$f":"VLOOKUP(U202,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-06-21","2021-06-21","3","2022","1100","309361116","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810222","Corp Prof Exp OT",143.22,"AUD","Storm Response","AFRU","SYS_BCBATCH",10001451,"","",{"$f":"VLOOKUP(U203,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["RMRU","RKL","2021-06-21","2021-06-21","3","2022","1100","309361117","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810222","Corp Prof Exp OT",143.22,"AUD","Storm Response","AFRU","SYS_BCBATCH",10001451,"","",{"$f":"VLOOKUP(U204,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["RMRU","RKL","2021-06-21","2021-06-21","3","2022","1100","309361118","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810222","Corp Prof Exp OT",1288.98,"AUD","Storm Response","AFRU","SYS_BCBATCH",10001451,"","",{"$f":"VLOOKUP(U205,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["RMRU","RKL","2021-06-21","2021-06-21","3","2022","1100","309361119","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810222","Corp Prof Exp OT",143.22,"AUD","Storm Response","AFRU","SYS_BCBATCH",10001451,"","",{"$f":"VLOOKUP(U206,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["RMRU","RKL","2021-06-21","2021-06-21","3","2022","1100","309361120","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810222","Corp Prof Exp OT",143.22,"AUD","Storm Response.","AFRU","SYS_BCBATCH",10001451,"","",{"$f":"VLOOKUP(U207,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["RMRU","RKL","2021-06-22","2021-06-22","3","2022","1100","309361141","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810160","Corp Manager NT",-958.73,"AUD","","AFRU","SYS_BCBATCH",10009915,"","",{"$f":"VLOOKUP(U208,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-06-22","2021-06-22","3","2022","1100","309361143","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810160","Corp Manager NT",-958.73,"AUD","","AFRU","SYS_BCBATCH",10009915,"","",{"$f":"VLOOKUP(U209,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-06-22","2021-06-22","3","2022","1100","309361147","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810124","Corp Prof Spec NT",-618.26,"AUD","","AFRU","SYS_BCBATCH",10000868,"","",{"$f":"VLOOKUP(U210,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["RMRU","RKL","2021-06-22","2021-06-22","3","2022","1100","309361148","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810160","Corp Manager NT",-958.73,"AUD","","AFRU","SYS_BCBATCH",10009915,"","",{"$f":"VLOOKUP(U211,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-06-22","2021-06-22","3","2022","1100","309361766","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810141","Corp Snr Mngr NT",647.12,"AUD","","AFRU","SYS_BCBATCH",10009397,"","",{"$f":"VLOOKUP(U212,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["RMRU","RKL","2021-06-22","2021-06-22","3","2022","1100","309361767","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810141","Corp Snr Mngr NT",2184.0300000000002,"AUD","","AFRU","SYS_BCBATCH",10009397,"","",{"$f":"VLOOKUP(U213,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["RMRU","RKL","2021-06-22","2021-06-22","3","2022","1100","309361768","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810141","Corp Snr Mngr NT",2184.0300000000002,"AUD","","AFRU","SYS_BCBATCH",10009397,"","",{"$f":"VLOOKUP(U214,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["RMRU","RKL","2021-06-22","2021-06-22","3","2022","1100","309361769","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810141","Corp Snr Mngr NT",2143.59,"AUD","","AFRU","SYS_BCBATCH",10009397,"","",{"$f":"VLOOKUP(U215,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["RMRU","RKL","2021-06-22","2021-06-22","3","2022","1100","309361770","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810141","Corp Snr Mngr NT",2143.59,"AUD","","AFRU","SYS_BCBATCH",10009397,"","",{"$f":"VLOOKUP(U216,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["RMRU","RKL","2021-06-22","2021-06-22","3","2022","1100","309361771","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810124","Corp Prof Spec NT",961.02,"AUD","","AFRU","SYS_BCBATCH",10006974,"","",{"$f":"VLOOKUP(U217,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["RMRU","RKL","2021-06-22","2021-06-22","3","2022","1100","309361772","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810124","Corp Prof Spec NT",907.63,"AUD","","AFRU","SYS_BCBATCH",10006974,"","",{"$f":"VLOOKUP(U218,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["RMRU","RKL","2021-06-22","2021-06-22","3","2022","1100","309361773","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810124","Corp Prof Spec NT",907.63,"AUD","","AFRU","SYS_BCBATCH",10006974,"","",{"$f":"VLOOKUP(U219,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["RMRU","RKL","2021-06-22","2021-06-22","3","2022","1100","309361774","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810124","Corp Prof Spec NT",907.63,"AUD","","AFRU","SYS_BCBATCH",10006974,"","",{"$f":"VLOOKUP(U220,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["RMRU","RKL","2021-06-22","2021-06-22","3","2022","1100","309361775","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810124","Corp Prof Spec NT",907.63,"AUD","","AFRU","SYS_BCBATCH",10006974,"","",{"$f":"VLOOKUP(U221,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["RMRU","RKL","2021-06-22","2021-06-22","3","2022","1100","309361776","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810124","Corp Prof Spec NT",907.63,"AUD","","AFRU","SYS_BCBATCH",10006974,"","",{"$f":"VLOOKUP(U222,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["RMRU","RKL","2021-06-22","2021-06-22","3","2022","1100","309361777","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810141","Corp Snr Mngr NT",2184.0300000000002,"AUD","","AFRU","SYS_BCBATCH",10009397,"","",{"$f":"VLOOKUP(U223,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["RMRU","RKL","2021-06-22","2021-06-22","3","2022","1100","309361778","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810141","Corp Snr Mngr NT",2022.25,"AUD","","AFRU","SYS_BCBATCH",10009397,"","",{"$f":"VLOOKUP(U224,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["RMRU","RKL","2021-06-22","2021-06-22","3","2022","1100","309361779","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810141","Corp Snr Mngr NT",2184.0300000000002,"AUD","","AFRU","SYS_BCBATCH",10009397,"","",{"$f":"VLOOKUP(U225,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["RMRU","RKL","2021-06-22","2021-06-22","3","2022","1100","309361780","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810141","Corp Snr Mngr NT",1132.46,"AUD","","AFRU","SYS_BCBATCH",10009397,"","",{"$f":"VLOOKUP(U226,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["RMRU","RKL","2021-06-22","2021-06-22","3","2022","1100","309361781","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810141","Corp Snr Mngr NT",1294.24,"AUD","","AFRU","SYS_BCBATCH",10009397,"","",{"$f":"VLOOKUP(U227,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["RMRU","RKL","2021-06-22","2021-06-22","3","2022","1100","309361782","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810124","Corp Prof Spec NT",480.51,"AUD","Storm -2021- Time Sheet - 12014","AFRU","SYS_BCBATCH",10006974,"","",{"$f":"VLOOKUP(U228,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["RMRU","RKL","2021-06-22","2021-06-22","3","2022","1100","309361783","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810141","Corp Snr Mngr NT",1420.5,"AUD","","AFRU","SYS_BCBATCH",10010076,"","",{"$f":"VLOOKUP(U229,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["RMRU","RKL","2021-06-22","2021-06-22","3","2022","1100","309361784","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810141","Corp Snr Mngr NT",1420.5,"AUD","","AFRU","SYS_BCBATCH",10010076,"","",{"$f":"VLOOKUP(U230,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["RMRU","RKL","2021-06-22","2021-06-22","3","2022","1100","309361786","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810142","Corp Strat Mngr NT",2760.75,"AUD","","AFRU","SYS_BCBATCH",10009799,"","",{"$f":"VLOOKUP(U231,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["RMRU","RKL","2021-06-22","2021-06-22","3","2022","1100","309361787","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810142","Corp Strat Mngr NT",2760.75,"AUD","","AFRU","SYS_BCBATCH",10009799,"","",{"$f":"VLOOKUP(U232,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["RMRU","RKL","2021-06-22","2021-06-22","3","2022","1100","309361788","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810142","Corp Strat Mngr NT",2944.8,"AUD","","AFRU","SYS_BCBATCH",10009799,"","",{"$f":"VLOOKUP(U233,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["RMRU","RKL","2021-06-22","2021-06-22","3","2022","1100","309361789","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810142","Corp Strat Mngr NT",2944.8,"AUD","","AFRU","SYS_BCBATCH",10009799,"","",{"$f":"VLOOKUP(U234,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["RMRU","RKL","2021-06-22","2021-06-22","3","2022","1100","309361790","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810142","Corp Strat Mngr NT",2760.75,"AUD","","AFRU","SYS_BCBATCH",10009799,"","",{"$f":"VLOOKUP(U235,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["RMRU","RKL","2021-06-22","2021-06-22","3","2022","1100","309361791","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810142","Corp Strat Mngr NT",2760.75,"AUD","","AFRU","SYS_BCBATCH",10009799,"","",{"$f":"VLOOKUP(U236,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["RMRU","RKL","2021-06-22","2021-06-22","3","2022","1100","309361792","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810142","Corp Strat Mngr NT",2760.75,"AUD","","AFRU","SYS_BCBATCH",10009799,"","",{"$f":"VLOOKUP(U237,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["RMRU","RKL","2021-06-22","2021-06-22","3","2022","1100","309361793","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810142","Corp Strat Mngr NT",2760.75,"AUD","","AFRU","SYS_BCBATCH",10009799,"","",{"$f":"VLOOKUP(U238,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["RMRU","RKL","2021-06-22","2021-06-22","3","2022","1100","309361794","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810142","Corp Strat Mngr NT",2760.75,"AUD","","AFRU","SYS_BCBATCH",10009799,"","",{"$f":"VLOOKUP(U239,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["RMRU","RKL","2021-06-22","2021-06-22","3","2022","1100","309361795","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810142","Corp Strat Mngr NT",1656.45,"AUD","","AFRU","SYS_BCBATCH",10009799,"","",{"$f":"VLOOKUP(U240,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["RMRU","RKL","2021-06-22","2021-06-22","3","2022","1100","309361796","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810142","Corp Strat Mngr NT",1656.45,"AUD","","AFRU","SYS_BCBATCH",10009799,"","",{"$f":"VLOOKUP(U241,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["RMRU","RKL","2021-06-22","2021-06-22","3","2022","1100","309361799","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810141","Corp Snr Mngr NT",1213.3499999999999,"AUD","","AFRU","SYS_BCBATCH",10000189,"","",{"$f":"VLOOKUP(U242,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-06-22","2021-06-22","3","2022","1100","309361800","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810141","Corp Snr Mngr NT",1213.3499999999999,"AUD","","AFRU","SYS_BCBATCH",10000189,"","",{"$f":"VLOOKUP(U243,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-06-22","2021-06-22","3","2022","1100","309361801","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810141","Corp Snr Mngr NT",1213.3499999999999,"AUD","","AFRU","SYS_BCBATCH",10000189,"","",{"$f":"VLOOKUP(U244,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-06-22","2021-06-22","3","2022","1100","309361802","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810141","Corp Snr Mngr NT",1213.3499999999999,"AUD","","AFRU","SYS_BCBATCH",10000189,"","",{"$f":"VLOOKUP(U245,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-06-22","2021-06-22","3","2022","1100","309361803","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810243","Corp Support OT",506.94,"AUD","OT for Storm Relief SWAT - no breaks tak","AFRU","SYS_BCBATCH",10007996,"","",{"$f":"VLOOKUP(U246,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["RMRU","RKL","2021-06-22","2021-06-22","3","2022","1100","309361804","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810160","Corp Manager NT",896.85,"AUD","","AFRU","SYS_BCBATCH",10001990,"","",{"$f":"VLOOKUP(U247,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["RMRU","RKL","2021-06-22","2021-06-22","3","2022","1100","309361805","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810160","Corp Manager NT",896.85,"AUD","","AFRU","SYS_BCBATCH",10001990,"","",{"$f":"VLOOKUP(U248,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["RMRU","RKL","2021-06-22","2021-06-22","3","2022","1100","309361806","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810160","Corp Manager NT",958.73,"AUD","","AFRU","SYS_BCBATCH",10000371,"","",{"$f":"VLOOKUP(U249,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["RMRU","RKL","2021-06-22","2021-06-22","3","2022","1100","309361807","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810160","Corp Manager NT",958.73,"AUD","","AFRU","SYS_BCBATCH",10000371,"","",{"$f":"VLOOKUP(U250,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["RMRU","RKL","2021-06-22","2021-06-22","3","2022","1100","309361808","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810160","Corp Manager NT",958.73,"AUD","","AFRU","SYS_BCBATCH",10000371,"","",{"$f":"VLOOKUP(U251,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["RMRU","RKL","2021-06-22","2021-06-22","3","2022","1100","309361809","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810160","Corp Manager NT",958.73,"AUD","","AFRU","SYS_BCBATCH",10000371,"","",{"$f":"VLOOKUP(U252,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["RMRU","RKL","2021-06-22","2021-06-22","3","2022","1100","309361824","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810243","Corp Support OT",289.68,"AUD","OT for Storm Relief SWAT - no breaks","AFRU","SYS_BCBATCH",10007996,"","",{"$f":"VLOOKUP(U253,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["RMRU","RKL","2021-06-22","2021-06-22","3","2022","1100","309361825","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810160","Corp Manager NT",896.85,"AUD","","AFRU","SYS_BCBATCH",10001990,"","",{"$f":"VLOOKUP(U254,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["RMRU","RKL","2021-06-22","2021-06-22","3","2022","1100","309361826","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810160","Corp Manager NT",896.85,"AUD","","AFRU","SYS_BCBATCH",10001990,"","",{"$f":"VLOOKUP(U255,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["RMRU","RKL","2021-06-22","2021-06-22","3","2022","1100","309361827","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810160","Corp Manager NT",896.85,"AUD","","AFRU","SYS_BCBATCH",10001990,"","",{"$f":"VLOOKUP(U256,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["RMRU","RKL","2021-06-22","2021-06-22","3","2022","1100","309361836","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810124","Corp Prof Spec NT",786.87,"AUD","","AFRU","SYS_BCBATCH",10000868,"","",{"$f":"VLOOKUP(U257,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["RMRU","RKL","2021-06-23","2021-06-23","3","2022","1100","309362452","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810118","Project Manager NT",854.03,"AUD","","AFRU","SYS_BCBATCH",10000641,"","",{"$f":"VLOOKUP(U258,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-06-23","2021-06-23","3","2022","1100","309362455","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810123","Corp Prof NT",172.14,"AUD","EMT Recovery Hub Assistance","AFRU","SYS_BCBATCH",10001155,"","",{"$f":"VLOOKUP(U259,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["RMRU","RKL","2021-06-23","2021-06-23","3","2022","1100","309362456","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810123","Corp Prof NT",645.53,"AUD","EMT Recovery Hub - Lilydale","AFRU","SYS_BCBATCH",10001155,"","",{"$f":"VLOOKUP(U260,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["RMRU","RKL","2021-06-23","2021-06-23","3","2022","1100","309362457","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810123","Corp Prof NT",645.53,"AUD","EMT Recovery Hub- Lilydale","AFRU","SYS_BCBATCH",10001155,"","",{"$f":"VLOOKUP(U261,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["RMRU","RKL","2021-06-23","2021-06-23","3","2022","1100","309362458","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810123","Corp Prof NT",645.53,"AUD","EMT Mutual Aid job Management- Lilydale","AFRU","SYS_BCBATCH",10001155,"","",{"$f":"VLOOKUP(U262,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["RMRU","RKL","2021-06-23","2021-06-23","3","2022","1100","309362459","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810123","Corp Prof NT",258.20999999999998,"AUD","EMT Mutual Aid job Management","AFRU","SYS_BCBATCH",10001155,"","",{"$f":"VLOOKUP(U263,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["RMRU","RKL","2021-06-23","2021-06-23","3","2022","1100","309362460","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810122","Corp Prof Exp NT",758.85,"AUD","EMT - SWAT team in Kalorama","AFRU","SYS_BCBATCH",10009892,"","",{"$f":"VLOOKUP(U264,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["RMRU","RKL","2021-06-23","2021-06-23","3","2022","1100","309362461","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810141","Corp Snr Mngr NT",1213.3499999999999,"AUD","","AFRU","SYS_BCBATCH",10000189,"","",{"$f":"VLOOKUP(U265,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-06-23","2021-06-23","3","2022","1100","309362462","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810141","Corp Snr Mngr NT",1213.3499999999999,"AUD","","AFRU","SYS_BCBATCH",10000189,"","",{"$f":"VLOOKUP(U266,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-06-23","2021-06-23","3","2022","1100","309362463","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810141","Corp Snr Mngr NT",1213.3499999999999,"AUD","","AFRU","SYS_BCBATCH",10000189,"","",{"$f":"VLOOKUP(U267,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-06-23","2021-06-23","3","2022","1100","309362464","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810141","Corp Snr Mngr NT",1213.3499999999999,"AUD","","AFRU","SYS_BCBATCH",10000189,"","",{"$f":"VLOOKUP(U268,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-06-23","2021-06-23","3","2022","1100","309362465","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810141","Corp Snr Mngr NT",1213.3499999999999,"AUD","","AFRU","SYS_BCBATCH",10000189,"","",{"$f":"VLOOKUP(U269,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-06-23","2021-06-23","3","2022","1100","309362466","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810136","Corp Semi Prof NT",545.25,"AUD","","AFRU","SYS_BCBATCH",10001596,"","",{"$f":"VLOOKUP(U270,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-06-23","2021-06-23","3","2022","1100","309362467","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810136","Corp Semi Prof NT",545.25,"AUD","","AFRU","SYS_BCBATCH",10001596,"","",{"$f":"VLOOKUP(U271,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["","RKL","2021-06-14","2021-06-24","3","2022","1100","309362553","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810300","Allowance Expenses",447.18,"AUD","","CATS","SYS_BCBATCH",10004968,"","",{"$f":"VLOOKUP(U272,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["","RKL","2021-06-12","2021-06-24","3","2022","1100","309362557","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810300","Allowance Expenses",1149.29,"AUD","","CATS","SYS_BCBATCH",10002256,"","",{"$f":"VLOOKUP(U273,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-06-23","2021-06-23","3","2022","1100","309363008","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810160","Corp Manager NT",1533.96,"AUD","","AFRU","SYS_BCBATCH",10002560,"","",{"$f":"VLOOKUP(U274,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["RMRU","RKL","2021-06-23","2021-06-23","3","2022","1100","309363009","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810124","Corp Prof Spec NT",1348.92,"AUD","","AFRU","SYS_BCBATCH",10008723,"","",{"$f":"VLOOKUP(U275,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["RMRU","RKL","2021-06-23","2021-06-23","3","2022","1100","309363010","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810124","Corp Prof Spec NT",1348.92,"AUD","","AFRU","SYS_BCBATCH",10008723,"","",{"$f":"VLOOKUP(U276,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["RMRU","RKL","2021-06-23","2021-06-23","3","2022","1100","309363011","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810122","Corp Prof Exp NT",809.44,"AUD","","AFRU","SYS_BCBATCH",10000478,"","",{"$f":"VLOOKUP(U277,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-06-23","2021-06-23","3","2022","1100","309363012","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810122","Corp Prof Exp NT",809.44,"AUD","","AFRU","SYS_BCBATCH",10000478,"","",{"$f":"VLOOKUP(U278,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-06-23","2021-06-23","3","2022","1100","309363015","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810122","Corp Prof Exp NT",758.85,"AUD","","AFRU","SYS_BCBATCH",10000478,"","",{"$f":"VLOOKUP(U279,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-06-23","2021-06-23","3","2022","1100","309363016","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810122","Corp Prof Exp NT",758.85,"AUD","","AFRU","SYS_BCBATCH",10000478,"","",{"$f":"VLOOKUP(U280,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-06-23","2021-06-23","3","2022","1100","309363017","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810120","Corp Ops Lead NT",647.82000000000005,"AUD","","AFRU","SYS_BCBATCH",10001233,"","",{"$f":"VLOOKUP(U281,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["RMRU","RKL","2021-06-23","2021-06-23","3","2022","1100","309363018","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810120","Corp Ops Lead NT",647.82000000000005,"AUD","","AFRU","SYS_BCBATCH",10001233,"","",{"$f":"VLOOKUP(U282,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["RMRU","RKL","2021-06-23","2021-06-23","3","2022","1100","309363027","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810124","Corp Prof Spec NT",213.56,"AUD","","AFRU","SYS_BCBATCH",10000507,"","",{"$f":"VLOOKUP(U283,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-06-23","2021-06-23","3","2022","1100","309363030","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810141","Corp Snr Mngr NT",1065.3800000000001,"AUD","Storm event","AFRU","SYS_BCBATCH",10000368,"","",{"$f":"VLOOKUP(U284,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-06-23","2021-06-23","3","2022","1100","309363032","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810141","Corp Snr Mngr NT",1065.3800000000001,"AUD","Storm number","AFRU","SYS_BCBATCH",10000368,"","",{"$f":"VLOOKUP(U285,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-06-23","2021-06-23","3","2022","1100","309363033","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810141","Corp Snr Mngr NT",1065.3800000000001,"AUD","Storm number","AFRU","SYS_BCBATCH",10000368,"","",{"$f":"VLOOKUP(U286,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-06-23","2021-06-23","3","2022","1100","309363034","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810141","Corp Snr Mngr NT",1065.3800000000001,"AUD","Storm number","AFRU","SYS_BCBATCH",10000368,"","",{"$f":"VLOOKUP(U287,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-06-23","2021-06-23","3","2022","1100","309363035","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810141","Corp Snr Mngr NT",1065.3800000000001,"AUD","Storm number","AFRU","SYS_BCBATCH",10000368,"","",{"$f":"VLOOKUP(U288,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-06-23","2021-06-23","3","2022","1100","309363036","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810120","Corp Ops Lead NT",647.82000000000005,"AUD","","AFRU","SYS_BCBATCH",10001233,"","",{"$f":"VLOOKUP(U289,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["RMRU","RKL","2021-06-23","2021-06-23","3","2022","1100","309363037","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810120","Corp Ops Lead NT",647.82000000000005,"AUD","","AFRU","SYS_BCBATCH",10001233,"","",{"$f":"VLOOKUP(U290,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["RMRU","RKL","2021-06-24","2021-06-24","3","2022","1100","309363994","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810136","Corp Semi Prof NT",545.25,"AUD","","AFRU","SYS_BCBATCH",10002617,"","",{"$f":"VLOOKUP(U291,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-06-24","2021-06-24","3","2022","1100","309363995","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810118","Project Manager NT",854.03,"AUD","","AFRU","SYS_BCBATCH",10000641,"","",{"$f":"VLOOKUP(U292,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-06-24","2021-06-24","3","2022","1100","309363996","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810136","Corp Semi Prof NT",145.4,"AUD","","AFRU","SYS_BCBATCH",10002617,"","",{"$f":"VLOOKUP(U293,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-06-24","2021-06-24","3","2022","1100","309363997","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810143","Corp Support NT",135.15,"AUD","","AFRU","SYS_BCBATCH",10008903,"","",{"$f":"VLOOKUP(U294,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-06-24","2021-06-24","3","2022","1100","309363999","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810224","Corp Prof Spec OT",2023.44,"AUD","","AFRU","SYS_BCBATCH",10002460,"","",{"$f":"VLOOKUP(U295,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-06-24","2021-06-24","3","2022","1100","309364000","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810236","Corp Semi Prof OT",490.73,"AUD","","AFRU","SYS_BCBATCH",10001596,"","",{"$f":"VLOOKUP(U296,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-06-24","2021-06-24","3","2022","1100","309364001","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810236","Corp Semi Prof OT",1417.65,"AUD","","AFRU","SYS_BCBATCH",10001596,"","",{"$f":"VLOOKUP(U297,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-06-24","2021-06-24","3","2022","1100","309364002","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810236","Corp Semi Prof OT",1199.55,"AUD","","AFRU","SYS_BCBATCH",10001596,"","",{"$f":"VLOOKUP(U298,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-06-24","2021-06-24","3","2022","1100","309364003","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810123","Corp Prof NT",301.25,"AUD","","AFRU","SYS_BCBATCH",10001415,"","",{"$f":"VLOOKUP(U299,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-06-24","2021-06-24","3","2022","1100","309364004","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810141","Corp Snr Mngr NT",1065.3800000000001,"AUD","Storm Response","AFRU","SYS_BCBATCH",10007022,"","",{"$f":"VLOOKUP(U300,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["RMRU","RKL","2021-06-24","2021-06-24","3","2022","1100","309364005","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810141","Corp Snr Mngr NT",1065.3800000000001,"AUD","Storm Response","AFRU","SYS_BCBATCH",10007022,"","",{"$f":"VLOOKUP(U301,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["RMRU","RKL","2021-06-24","2021-06-24","3","2022","1100","309364006","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810141","Corp Snr Mngr NT",1065.3800000000001,"AUD","Storm Response","AFRU","SYS_BCBATCH",10007022,"","",{"$f":"VLOOKUP(U302,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["RMRU","RKL","2021-06-24","2021-06-24","3","2022","1100","309364007","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810141","Corp Snr Mngr NT",1065.3800000000001,"AUD","Storm Response","AFRU","SYS_BCBATCH",10007022,"","",{"$f":"VLOOKUP(U303,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["RMRU","RKL","2021-06-24","2021-06-24","3","2022","1100","309364008","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810141","Corp Snr Mngr NT",1065.3800000000001,"AUD","Storm Response","AFRU","SYS_BCBATCH",10007022,"","",{"$f":"VLOOKUP(U304,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["RMRU","RKL","2021-06-24","2021-06-24","3","2022","1100","309364009","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810141","Corp Snr Mngr NT",1065.3800000000001,"AUD","Storm Response","AFRU","SYS_BCBATCH",10007022,"","",{"$f":"VLOOKUP(U305,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["RMRU","RKL","2021-06-24","2021-06-24","3","2022","1100","309364010","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810141","Corp Snr Mngr NT",1065.3800000000001,"AUD","Storm Response","AFRU","SYS_BCBATCH",10007022,"","",{"$f":"VLOOKUP(U306,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["RMRU","RKL","2021-06-24","2021-06-24","3","2022","1100","309364011","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810141","Corp Snr Mngr NT",1065.3800000000001,"AUD","Storm Response","AFRU","SYS_BCBATCH",10007022,"","",{"$f":"VLOOKUP(U307,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["RMRU","RKL","2021-06-24","2021-06-24","3","2022","1100","309364012","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810141","Corp Snr Mngr NT",1065.3800000000001,"AUD","Storm Response","AFRU","SYS_BCBATCH",10007022,"","",{"$f":"VLOOKUP(U308,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["RMRU","RKL","2021-06-24","2021-06-24","3","2022","1100","309364415","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810241","Corp Snr Mngr OT",2556.96,"AUD","Storm -2021- Time Sheet - 12014","AFRU","SYS_BCBATCH",10007022,"","",{"$f":"VLOOKUP(U309,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["RMRU","RKL","2021-06-24","2021-06-24","3","2022","1100","309364416","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810241","Corp Snr Mngr OT",2556.96,"AUD","Storm -2021- Time Sheet - 12014","AFRU","SYS_BCBATCH",10007022,"","",{"$f":"VLOOKUP(U310,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["RMRU","RKL","2021-06-24","2021-06-24","3","2022","1100","309364417","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810241","Corp Snr Mngr OT",2450.42,"AUD","Storm -2021- Time Sheet - 12014","AFRU","SYS_BCBATCH",10007022,"","",{"$f":"VLOOKUP(U311,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["RMRU","RKL","2021-06-24","2021-06-24","3","2022","1100","309364418","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810241","Corp Snr Mngr OT",2556.96,"AUD","Storm -2021- Time Sheet - 12014","AFRU","SYS_BCBATCH",10007022,"","",{"$f":"VLOOKUP(U312,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["RMRU","RKL","2021-06-24","2021-06-24","3","2022","1100","309364419","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810241","Corp Snr Mngr OT",639.24,"AUD","Storm -2021- Time Sheet - 12014","AFRU","SYS_BCBATCH",10007022,"","",{"$f":"VLOOKUP(U313,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["RMRU","RKL","2021-06-24","2021-06-24","3","2022","1100","309364420","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810241","Corp Snr Mngr OT",639.24,"AUD","Storm -2021- Time Sheet - 12014","AFRU","SYS_BCBATCH",10007022,"","",{"$f":"VLOOKUP(U314,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["RMRU","RKL","2021-06-24","2021-06-24","3","2022","1100","309364421","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810241","Corp Snr Mngr OT",639.24,"AUD","Storm -2021- Time Sheet - 12014","AFRU","SYS_BCBATCH",10007022,"","",{"$f":"VLOOKUP(U315,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["RMRU","RKL","2021-06-24","2021-06-24","3","2022","1100","309364422","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810241","Corp Snr Mngr OT",639.24,"AUD","Storm -2021- Time Sheet - 12014","AFRU","SYS_BCBATCH",10007022,"","",{"$f":"VLOOKUP(U316,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["RMRU","RKL","2021-06-24","2021-06-24","3","2022","1100","309364423","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810241","Corp Snr Mngr OT",639.24,"AUD","Storm -2021- Time Sheet - 12014","AFRU","SYS_BCBATCH",10007022,"","",{"$f":"VLOOKUP(U317,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["RMRU","RKL","2021-06-24","2021-06-24","3","2022","1100","309364424","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810241","Corp Snr Mngr OT",639.24,"AUD","Storm -2021- Time Sheet - 12014","AFRU","SYS_BCBATCH",10007022,"","",{"$f":"VLOOKUP(U318,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["RMRU","RKL","2021-06-24","2021-06-24","3","2022","1100","309364425","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810241","Corp Snr Mngr OT",639.24,"AUD","Storm -2021- Time Sheet - 12014","AFRU","SYS_BCBATCH",10007022,"","",{"$f":"VLOOKUP(U319,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["RMRU","RKL","2021-06-24","2021-06-24","3","2022","1100","309364426","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810241","Corp Snr Mngr OT",639.24,"AUD","Storm -2021- Time Sheet - 12014","AFRU","SYS_BCBATCH",10007022,"","",{"$f":"VLOOKUP(U320,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["RMRU","RKL","2021-06-24","2021-06-24","3","2022","1100","309364427","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810223","Corp Prof OT",645.54999999999995,"AUD","EMT Mutual Aid job Management","AFRU","SYS_BCBATCH",10001155,"","",{"$f":"VLOOKUP(U321,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["RMRU","RKL","2021-06-24","2021-06-24","3","2022","1100","309364428","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810223","Corp Prof OT",258.22000000000003,"AUD","EMT Mutual Aid job Management- Lilydale","AFRU","SYS_BCBATCH",10001155,"","",{"$f":"VLOOKUP(U322,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["RMRU","RKL","2021-06-24","2021-06-24","3","2022","1100","309364429","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810223","Corp Prof OT",258.22000000000003,"AUD","EMT Recovery Hub Strike team- Lilydale","AFRU","SYS_BCBATCH",10001155,"","",{"$f":"VLOOKUP(U323,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["RMRU","RKL","2021-06-24","2021-06-24","3","2022","1100","309364430","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810222","Corp Prof Exp OT",75.89,"AUD","EMT - recovery hub strike team","AFRU","SYS_BCBATCH",10009892,"","",{"$f":"VLOOKUP(U324,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["RMRU","RKL","2021-06-24","2021-06-24","3","2022","1100","309364431","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810223","Corp Prof OT",1161.99,"AUD","EMT- Recovery Hubs Strike Team","AFRU","SYS_BCBATCH",10001155,"","",{"$f":"VLOOKUP(U325,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["RMRU","RKL","2021-06-24","2021-06-24","3","2022","1100","309364432","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810223","Corp Prof OT",1291.0999999999999,"AUD","EMT- Recovery Hubs Strike Team","AFRU","SYS_BCBATCH",10001155,"","",{"$f":"VLOOKUP(U326,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["RMRU","RKL","2021-06-24","2021-06-24","3","2022","1100","309364433","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810223","Corp Prof OT",1355.66,"AUD","EMT- Recovery Hubs Strike Team","AFRU","SYS_BCBATCH",10001155,"","",{"$f":"VLOOKUP(U327,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["RMRU","RKL","2021-06-24","2021-06-24","3","2022","1100","309364434","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810223","Corp Prof OT",774.66,"AUD","EMT- Recovery Hubs Strike Team","AFRU","SYS_BCBATCH",10001155,"","",{"$f":"VLOOKUP(U328,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["RMRU","RKL","2021-06-24","2021-06-24","3","2022","1100","309364435","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810222","Corp Prof Exp OT",303.54000000000002,"AUD","EMT - Recovery Hub Strike Team","AFRU","SYS_BCBATCH",10009892,"","",{"$f":"VLOOKUP(U329,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["RMRU","RKL","2021-06-25","2021-06-25","3","2022","1100","309365366","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810141","Corp Snr Mngr NT",1213.3499999999999,"AUD","","AFRU","SYS_BCBATCH",10000189,"","",{"$f":"VLOOKUP(U330,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-06-25","2021-06-25","3","2022","1100","309365367","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810141","Corp Snr Mngr NT",1213.3499999999999,"AUD","","AFRU","SYS_BCBATCH",10000189,"","",{"$f":"VLOOKUP(U331,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-06-25","2021-06-25","3","2022","1100","309365368","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810143","Corp Support NT",405.45,"AUD","","AFRU","SYS_BCBATCH",10008903,"","",{"$f":"VLOOKUP(U332,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-06-25","2021-06-25","3","2022","1100","309365369","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810143","Corp Support NT",270.3,"AUD","","AFRU","SYS_BCBATCH",10008903,"","",{"$f":"VLOOKUP(U333,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-06-25","2021-06-25","3","2022","1100","309365370","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810143","Corp Support NT",405.45,"AUD","","AFRU","SYS_BCBATCH",10008903,"","",{"$f":"VLOOKUP(U334,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-06-26","2021-06-26","3","2022","1100","309376076","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810100","Dxn Controller NT",1199.52,"AUD","","AFRU","SYS_BCBATCH",10002213,"","",{"$f":"VLOOKUP(U335,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["RMRU","RKL","2021-06-26","2021-06-26","3","2022","1100","309376077","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810100","Dxn Controller NT",1199.52,"AUD","","AFRU","SYS_BCBATCH",10002213,"","",{"$f":"VLOOKUP(U336,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["RMRU","RKL","2021-06-26","2021-06-26","3","2022","1100","309376078","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810100","Dxn Controller NT",1199.52,"AUD","","AFRU","SYS_BCBATCH",10002213,"","",{"$f":"VLOOKUP(U337,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["RMRU","RKL","2021-06-27","2021-06-27","3","2022","1100","309379108","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810100","Dxn Controller NT",1199.52,"AUD","","AFRU","SYS_BCBATCH",10002213,"","",{"$f":"VLOOKUP(U338,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["RMRU","RKL","2021-06-25","2021-06-25","3","2022","1100","309379847","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810124","Corp Prof Spec NT",843.08,"AUD","","AFRU","SYS_BCBATCH",10008780,"","",{"$f":"VLOOKUP(U339,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["RMRU","RKL","2021-06-25","2021-06-25","3","2022","1100","309379848","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810124","Corp Prof Spec NT",843.08,"AUD","","AFRU","SYS_BCBATCH",10008780,"","",{"$f":"VLOOKUP(U340,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["RMRU","RKL","2021-06-25","2021-06-25","3","2022","1100","309379849","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810124","Corp Prof Spec NT",843.08,"AUD","","AFRU","SYS_BCBATCH",10008780,"","",{"$f":"VLOOKUP(U341,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["RMRU","RKL","2021-06-25","2021-06-25","3","2022","1100","309379850","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810124","Corp Prof Spec NT",843.08,"AUD","","AFRU","SYS_BCBATCH",10008780,"","",{"$f":"VLOOKUP(U342,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["RMRU","RKL","2021-06-25","2021-06-25","3","2022","1100","309379851","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810124","Corp Prof Spec NT",1405.13,"AUD","","AFRU","SYS_BCBATCH",10008780,"","",{"$f":"VLOOKUP(U343,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["RMRU","RKL","2021-06-25","2021-06-25","3","2022","1100","309379853","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810123","Corp Prof NT",645.53,"AUD","SCC Shifts","AFRU","SYS_BCBATCH",10009860,"","",{"$f":"VLOOKUP(U344,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-06-25","2021-06-25","3","2022","1100","309379854","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810123","Corp Prof NT",645.53,"AUD","SCC Shifts","AFRU","SYS_BCBATCH",10009860,"","",{"$f":"VLOOKUP(U345,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-06-25","2021-06-25","3","2022","1100","309379855","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810123","Corp Prof NT",645.53,"AUD","SCC Shifts","AFRU","SYS_BCBATCH",10009860,"","",{"$f":"VLOOKUP(U346,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-06-25","2021-06-25","3","2022","1100","309379856","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810123","Corp Prof NT",645.53,"AUD","SCC Shifts","AFRU","SYS_BCBATCH",10009860,"","",{"$f":"VLOOKUP(U347,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-06-25","2021-06-25","3","2022","1100","309379857","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810123","Corp Prof NT",645.53,"AUD","SCC Shifts","AFRU","SYS_BCBATCH",10009860,"","",{"$f":"VLOOKUP(U348,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-06-25","2021-06-25","3","2022","1100","309379858","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810123","Corp Prof NT",645.53,"AUD","SCC Shifts","AFRU","SYS_BCBATCH",10009860,"","",{"$f":"VLOOKUP(U349,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-06-25","2021-06-25","3","2022","1100","309379859","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810123","Corp Prof NT",645.53,"AUD","SCC Shifts","AFRU","SYS_BCBATCH",10009860,"","",{"$f":"VLOOKUP(U350,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-06-25","2021-06-25","3","2022","1100","309379860","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810123","Corp Prof NT",645.53,"AUD","SCC Shifts","AFRU","SYS_BCBATCH",10009860,"","",{"$f":"VLOOKUP(U351,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-06-25","2021-06-25","3","2022","1100","309379863","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810160","Corp Manager NT",1533.96,"AUD","Storm normal time","AFRU","SYS_BCBATCH",10000460,"","",{"$f":"VLOOKUP(U352,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["RMRU","RKL","2021-06-25","2021-06-25","3","2022","1100","309379864","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810160","Corp Manager NT",1533.96,"AUD","Storm normal time","AFRU","SYS_BCBATCH",10000460,"","",{"$f":"VLOOKUP(U353,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["RMRU","RKL","2021-06-25","2021-06-25","3","2022","1100","309379865","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810160","Corp Manager NT",1533.96,"AUD","Storm normal time","AFRU","SYS_BCBATCH",10000460,"","",{"$f":"VLOOKUP(U354,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["RMRU","RKL","2021-06-25","2021-06-25","3","2022","1100","309379866","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810120","Corp Ops Lead NT",611.54999999999995,"AUD","","AFRU","SYS_BCBATCH",10002532,"","",{"$f":"VLOOKUP(U355,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-06-27","2021-06-27","3","2022","1100","309380485","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810200","Dxn Controller OT",1874.25,"AUD","Covered N2","AFRU","SYS_BCBATCH",10002213,"","",{"$f":"VLOOKUP(U356,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["RMRU","RKL","2021-06-27","2021-06-27","3","2022","1100","309380486","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810160","Corp Manager NT",896.85,"AUD","","AFRU","SYS_BCBATCH",10001990,"","",{"$f":"VLOOKUP(U357,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["RMRU","RKL","2021-06-27","2021-06-27","3","2022","1100","309380487","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810160","Corp Manager NT",896.85,"AUD","","AFRU","SYS_BCBATCH",10001990,"","",{"$f":"VLOOKUP(U358,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["RMRU","RKL","2021-06-27","2021-06-27","3","2022","1100","309380488","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810160","Corp Manager NT",896.85,"AUD","","AFRU","SYS_BCBATCH",10001990,"","",{"$f":"VLOOKUP(U359,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["RMRU","RKL","2021-06-27","2021-06-27","3","2022","1100","309380489","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810160","Corp Manager NT",896.85,"AUD","","AFRU","SYS_BCBATCH",10001990,"","",{"$f":"VLOOKUP(U360,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["","RKL","2021-06-20","2021-06-28","3","2022","1100","309380945","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810300","Allowance Expenses",607.08000000000004,"AUD","storm related customer activities","CATS","SYS_BCBATCH",10000478,"","",{"$f":"VLOOKUP(U361,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["","RKL","2021-06-20","2021-06-28","3","2022","1100","309380945","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810300","Allowance Expenses",758.85,"AUD","storm response customer activities inclu","CATS","SYS_BCBATCH",10000478,"","",{"$f":"VLOOKUP(U362,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["","RKL","2021-06-20","2021-06-28","3","2022","1100","309380945","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810300","Allowance Expenses",303.54000000000002,"AUD","17;00 to 19:00","CATS","SYS_BCBATCH",10000478,"","",{"$f":"VLOOKUP(U363,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["","RKL","2021-06-20","2021-06-28","3","2022","1100","309380945","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810300","Allowance Expenses",227.66,"AUD","17:00 to 18:30","CATS","SYS_BCBATCH",10000478,"","",{"$f":"VLOOKUP(U364,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-06-28","2021-06-28","3","2022","1100","309381252","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810143","Corp Support NT",195.9,"AUD","Storm","AFRU","SYS_BCBATCH",10009884,"","",{"$f":"VLOOKUP(U365,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["RMRU","RKL","2021-06-28","2021-06-28","3","2022","1100","309381253","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810143","Corp Support NT",117.54,"AUD","Storm","AFRU","SYS_BCBATCH",10009884,"","",{"$f":"VLOOKUP(U366,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["RMRU","RKL","2021-06-28","2021-06-28","3","2022","1100","309381254","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810143","Corp Support NT",352.62,"AUD","Storm","AFRU","SYS_BCBATCH",10009884,"","",{"$f":"VLOOKUP(U367,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["RMRU","RKL","2021-06-28","2021-06-28","3","2022","1100","309381255","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810243","Corp Support OT",253.47,"AUD","OB calls","AFRU","SYS_BCBATCH",10006935,"","",{"$f":"VLOOKUP(U368,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["RMRU","RKL","2021-06-28","2021-06-28","3","2022","1100","309381256","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810243","Corp Support OT",108.63,"AUD","PPOP OB calls","AFRU","SYS_BCBATCH",10006935,"","",{"$f":"VLOOKUP(U369,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["RMRU","RKL","2021-06-28","2021-06-28","3","2022","1100","309381257","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810243","Corp Support OT",289.68,"AUD","faults and emergencies","AFRU","SYS_BCBATCH",10006935,"","",{"$f":"VLOOKUP(U370,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["","RKL","2021-06-25","2021-06-29","3","2022","1100","309381286","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810300","Allowance Expenses",224.21,"AUD","Lilydale storm response 07:15 to 16:30","CATS","SYS_BCBATCH",10001211,"","",{"$f":"VLOOKUP(U371,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["","RKL","2021-06-25","2021-06-29","3","2022","1100","309381286","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810300","Allowance Expenses",1928.23,"AUD","Lilydale storm response 07:30 to 18:15","CATS","SYS_BCBATCH",10001211,"","",{"$f":"VLOOKUP(U372,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["","RKL","2021-06-25","2021-06-29","3","2022","1100","309381286","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810300","Allowance Expenses",358.74,"AUD","Lilydale storm response 07:00 to 17:00","CATS","SYS_BCBATCH",10001211,"","",{"$f":"VLOOKUP(U373,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["RMRU","RKL","2021-06-29","2021-06-29","3","2022","1100","309381657","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810118","Project Manager NT",-854.03,"AUD","","AFRU","SYS_BCBATCH",10000641,"","",{"$f":"VLOOKUP(U374,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-06-28","2021-06-28","3","2022","1100","309381993","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810160","Corp Manager NT",896.85,"AUD","Central Region storm response","AFRU","SYS_BCBATCH",10001211,"","",{"$f":"VLOOKUP(U375,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["RMRU","RKL","2021-06-28","2021-06-28","3","2022","1100","309381994","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810160","Corp Manager NT",239.16,"AUD","Central Region storm response","AFRU","SYS_BCBATCH",10001211,"","",{"$f":"VLOOKUP(U376,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["RMRU","RKL","2021-06-28","2021-06-28","3","2022","1100","309381995","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810141","Corp Snr Mngr NT",1213.3499999999999,"AUD","","AFRU","SYS_BCBATCH",10000113,"","",{"$f":"VLOOKUP(U377,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-06-28","2021-06-28","3","2022","1100","309381996","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810220","Corp Ops Lead OT",291.64999999999998,"AUD","Storm Support - Storm Relief Inbox suppo","AFRU","SYS_BCBATCH",10001682,"","",{"$f":"VLOOKUP(U378,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["RMRU","RKL","2021-06-28","2021-06-28","3","2022","1100","309381997","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810220","Corp Ops Lead OT",291.64999999999998,"AUD","Storm Support - Storm Relief Inbox assis","AFRU","SYS_BCBATCH",10001682,"","",{"$f":"VLOOKUP(U379,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["RMRU","RKL","2021-06-28","2021-06-28","3","2022","1100","309381998","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810220","Corp Ops Lead OT",816.62,"AUD","Storm Support - Prepartion of customers","AFRU","SYS_BCBATCH",10001682,"","",{"$f":"VLOOKUP(U380,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["","RKL","2021-06-24","2021-06-30","3","2022","1100","309382036","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810300","Allowance Expenses",122.31,"AUD","","CATS","SYS_BCBATCH",10002562,"","",{"$f":"VLOOKUP(U381,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["","RKL","2021-06-24","2021-06-30","3","2022","1100","309382036","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810300","Allowance Expenses",20.12,"AUD","","CATS","SYS_BCBATCH",10002562,"","",{"$f":"VLOOKUP(U382,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["","RKL","2021-06-24","2021-06-30","3","2022","1100","309382036","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810300","Allowance Expenses",244.62,"AUD","","CATS","SYS_BCBATCH",10002562,"","",{"$f":"VLOOKUP(U383,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["","RKL","2021-06-24","2021-06-30","3","2022","1100","309382036","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810300","Allowance Expenses",40.24,"AUD","","CATS","SYS_BCBATCH",10002562,"","",{"$f":"VLOOKUP(U384,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["","RKL","2021-06-21","2021-06-30","3","2022","1100","309382042","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810300","Allowance Expenses",54.72,"AUD","KM for on the ground support in Monbulk","CATS","SYS_BCBATCH",10006898,"","",{"$f":"VLOOKUP(U385,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["","RKL","2021-06-21","2021-06-30","3","2022","1100","309382042","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810300","Allowance Expenses",37.44,"AUD","KM for support in Kalorma relief hub","CATS","SYS_BCBATCH",10006898,"","",{"$f":"VLOOKUP(U386,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["RMRU","RKL","2021-06-29","2021-06-29","3","2022","1100","309382737","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810120","Corp Ops Lead NT",40.770000000000003,"AUD","","AFRU","SYS_BCBATCH",10002532,"","",{"$f":"VLOOKUP(U387,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-06-29","2021-06-29","3","2022","1100","309382738","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810122","Corp Prof Exp NT",708.26,"AUD","","AFRU","SYS_BCBATCH",10000478,"","",{"$f":"VLOOKUP(U388,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-06-29","2021-06-29","3","2022","1100","309382739","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810122","Corp Prof Exp NT",708.26,"AUD","Yarra Ranges Community meetings","AFRU","SYS_BCBATCH",10000478,"","",{"$f":"VLOOKUP(U389,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-06-29","2021-06-29","3","2022","1100","309382740","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810122","Corp Prof Exp NT",758.85,"AUD","","AFRU","SYS_BCBATCH",10000478,"","",{"$f":"VLOOKUP(U390,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-06-29","2021-06-29","3","2022","1100","309382741","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810122","Corp Prof Exp NT",809.44,"AUD","","AFRU","SYS_BCBATCH",10000478,"","",{"$f":"VLOOKUP(U391,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-06-29","2021-06-29","3","2022","1100","309382742","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810120","Corp Ops Lead NT",203.85,"AUD","","AFRU","SYS_BCBATCH",10002562,"","",{"$f":"VLOOKUP(U392,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-06-29","2021-06-29","3","2022","1100","309382743","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810120","Corp Ops Lead NT",203.85,"AUD","","AFRU","SYS_BCBATCH",10002562,"","",{"$f":"VLOOKUP(U393,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-06-29","2021-06-29","3","2022","1100","309382744","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810123","Corp Prof NT",645.53,"AUD","","AFRU","SYS_BCBATCH",10009019,"","",{"$f":"VLOOKUP(U394,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-06-29","2021-06-29","3","2022","1100","309382745","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810123","Corp Prof NT",559.46,"AUD","","AFRU","SYS_BCBATCH",10009019,"","",{"$f":"VLOOKUP(U395,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-06-29","2021-06-29","3","2022","1100","309382750","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810120","Corp Ops Lead NT",203.85,"AUD","","AFRU","SYS_BCBATCH",10002532,"","",{"$f":"VLOOKUP(U396,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-06-29","2021-06-29","3","2022","1100","309382752","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810118","Project Manager NT",854.03,"AUD","","AFRU","SYS_BCBATCH",10000641,"","",{"$f":"VLOOKUP(U397,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-06-29","2021-06-29","3","2022","1100","309382753","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810118","Project Manager NT",854.03,"AUD","","AFRU","SYS_BCBATCH",10000641,"","",{"$f":"VLOOKUP(U398,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-06-29","2021-06-29","3","2022","1100","309382754","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810243","Corp Support OT",217.26,"AUD","","AFRU","SYS_BCBATCH",10002057,"","",{"$f":"VLOOKUP(U399,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["RMRU","RKL","2021-06-29","2021-06-29","3","2022","1100","309382755","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810143","Corp Support NT",156.72,"AUD","","AFRU","SYS_BCBATCH",10009633,"","",{"$f":"VLOOKUP(U400,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["RMRU","RKL","2021-06-29","2021-06-29","3","2022","1100","309382756","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810143","Corp Support NT",117.54,"AUD","storm","AFRU","SYS_BCBATCH",10009633,"","",{"$f":"VLOOKUP(U401,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["RMRU","RKL","2021-06-29","2021-06-29","3","2022","1100","309382757","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810243","Corp Support OT",324.36,"AUD","Storm","AFRU","SYS_BCBATCH",10001684,"","",{"$f":"VLOOKUP(U402,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["RMRU","RKL","2021-06-29","2021-06-29","3","2022","1100","309382758","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810120","Corp Ops Lead NT",647.82000000000005,"AUD","","AFRU","SYS_BCBATCH",10001233,"","",{"$f":"VLOOKUP(U403,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["RMRU","RKL","2021-06-29","2021-06-29","3","2022","1100","309382759","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810120","Corp Ops Lead NT",647.82000000000005,"AUD","","AFRU","SYS_BCBATCH",10001233,"","",{"$f":"VLOOKUP(U404,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["RMRU","RKL","2021-06-29","2021-06-29","3","2022","1100","309382760","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810223","Corp Prof OT",258.22000000000003,"AUD","EMT Admin- Resourcing and Sit rep","AFRU","SYS_BCBATCH",10001155,"","",{"$f":"VLOOKUP(U405,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["RMRU","RKL","2021-06-29","2021-06-29","3","2022","1100","309382761","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810223","Corp Prof OT",258.22000000000003,"AUD","EMT Admin- Resourcing and Sit Reps","AFRU","SYS_BCBATCH",10001155,"","",{"$f":"VLOOKUP(U406,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["RMRU","RKL","2021-06-29","2021-06-29","3","2022","1100","309382762","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810120","Corp Ops Lead NT",611.54999999999995,"AUD","","AFRU","SYS_BCBATCH",10002562,"","",{"$f":"VLOOKUP(U407,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-06-29","2021-06-29","3","2022","1100","309382763","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810120","Corp Ops Lead NT",611.54999999999995,"AUD","","AFRU","SYS_BCBATCH",10002562,"","",{"$f":"VLOOKUP(U408,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-06-29","2021-06-29","3","2022","1100","309382764","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810224","Corp Prof Spec OT",843.1,"AUD","","AFRU","SYS_BCBATCH",10008780,"","",{"$f":"VLOOKUP(U409,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["RMRU","RKL","2021-06-29","2021-06-29","3","2022","1100","309382765","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810224","Corp Prof Spec OT",843.1,"AUD","","AFRU","SYS_BCBATCH",10008780,"","",{"$f":"VLOOKUP(U410,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["RMRU","RKL","2021-06-29","2021-06-29","3","2022","1100","309382766","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810224","Corp Prof Spec OT",843.1,"AUD","","AFRU","SYS_BCBATCH",10008780,"","",{"$f":"VLOOKUP(U411,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["RMRU","RKL","2021-06-29","2021-06-29","3","2022","1100","309382767","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810224","Corp Prof Spec OT",843.1,"AUD","","AFRU","SYS_BCBATCH",10008780,"","",{"$f":"VLOOKUP(U412,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["RMRU","RKL","2021-06-29","2021-06-29","3","2022","1100","309382770","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810118","Project Manager NT",854.03,"AUD","","AFRU","SYS_BCBATCH",10000641,"","",{"$f":"VLOOKUP(U413,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-06-29","2021-06-29","3","2022","1100","309382771","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810118","Project Manager NT",854.03,"AUD","","AFRU","SYS_BCBATCH",10000641,"","",{"$f":"VLOOKUP(U414,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-06-29","2021-06-29","3","2022","1100","309383433","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810122","Corp Prof Exp NT",716.1,"AUD","","AFRU","SYS_BCBATCH",10001395,"","",{"$f":"VLOOKUP(U415,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-06-29","2021-06-29","3","2022","1100","309383437","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810160","Corp Manager NT",896.85,"AUD","Lilydale storm response","AFRU","SYS_BCBATCH",10001211,"","",{"$f":"VLOOKUP(U416,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["RMRU","RKL","2021-06-29","2021-06-29","3","2022","1100","309383438","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810160","Corp Manager NT",896.85,"AUD","Lilydale storm response","AFRU","SYS_BCBATCH",10001211,"","",{"$f":"VLOOKUP(U417,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["RMRU","RKL","2021-06-29","2021-06-29","3","2022","1100","309383439","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810260","Corp Manager OT",1793.7,"AUD","","AFRU","SYS_BCBATCH",10001990,"","",{"$f":"VLOOKUP(U418,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["RMRU","RKL","2021-06-29","2021-06-29","3","2022","1100","309383440","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810260","Corp Manager OT",269.06,"AUD","","AFRU","SYS_BCBATCH",10001990,"","",{"$f":"VLOOKUP(U419,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["RMRU","RKL","2021-06-29","2021-06-29","3","2022","1100","309383441","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810260","Corp Manager OT",358.74,"AUD","","AFRU","SYS_BCBATCH",10001990,"","",{"$f":"VLOOKUP(U420,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["RMRU","RKL","2021-06-29","2021-06-29","3","2022","1100","309383442","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810260","Corp Manager OT",358.74,"AUD","","AFRU","SYS_BCBATCH",10001990,"","",{"$f":"VLOOKUP(U421,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["RMRU","RKL","2021-06-29","2021-06-29","3","2022","1100","309383443","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810220","Corp Ops Lead OT",1399.92,"AUD","Assisting with storm, public holiday","AFRU","SYS_BCBATCH",10002123,"","",{"$f":"VLOOKUP(U422,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["RMRU","RKL","2021-06-29","2021-06-29","3","2022","1100","309383444","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810220","Corp Ops Lead OT",58.33,"AUD","","AFRU","SYS_BCBATCH",10001233,"","",{"$f":"VLOOKUP(U423,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["RMRU","RKL","2021-06-29","2021-06-29","3","2022","1100","309383445","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810220","Corp Ops Lead OT",1166.5999999999999,"AUD","","AFRU","SYS_BCBATCH",10001704,"","",{"$f":"VLOOKUP(U424,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["RMRU","RKL","2021-06-29","2021-06-29","3","2022","1100","309383446","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810260","Corp Manager OT",1704.02,"AUD","","AFRU","SYS_BCBATCH",10001990,"","",{"$f":"VLOOKUP(U425,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["RMRU","RKL","2021-06-29","2021-06-29","3","2022","1100","309383447","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810260","Corp Manager OT",1748.86,"AUD","","AFRU","SYS_BCBATCH",10001990,"","",{"$f":"VLOOKUP(U426,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["RMRU","RKL","2021-06-29","2021-06-29","3","2022","1100","309383448","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810260","Corp Manager OT",582.95000000000005,"AUD","","AFRU","SYS_BCBATCH",10001990,"","",{"$f":"VLOOKUP(U427,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["RMRU","RKL","2021-06-29","2021-06-29","3","2022","1100","309383449","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810260","Corp Manager OT",134.53,"AUD","","AFRU","SYS_BCBATCH",10001990,"","",{"$f":"VLOOKUP(U428,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["RMRU","RKL","2021-06-29","2021-06-29","3","2022","1100","309383450","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810260","Corp Manager OT",538.11,"AUD","","AFRU","SYS_BCBATCH",10001990,"","",{"$f":"VLOOKUP(U429,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["RMRU","RKL","2021-06-29","2021-06-29","3","2022","1100","309383451","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810260","Corp Manager OT",134.53,"AUD","","AFRU","SYS_BCBATCH",10001990,"","",{"$f":"VLOOKUP(U430,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["RMRU","RKL","2021-06-29","2021-06-29","3","2022","1100","309383452","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810260","Corp Manager OT",538.11,"AUD","","AFRU","SYS_BCBATCH",10001990,"","",{"$f":"VLOOKUP(U431,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["RMRU","RKL","2021-06-29","2021-06-29","3","2022","1100","309383453","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810260","Corp Manager OT",2017.91,"AUD","","AFRU","SYS_BCBATCH",10001990,"","",{"$f":"VLOOKUP(U432,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["RMRU","RKL","2021-06-29","2021-06-29","3","2022","1100","309383454","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810260","Corp Manager OT",2376.65,"AUD","","AFRU","SYS_BCBATCH",10001990,"","",{"$f":"VLOOKUP(U433,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["RMRU","RKL","2021-06-29","2021-06-29","3","2022","1100","309383455","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810260","Corp Manager OT",2376.65,"AUD","","AFRU","SYS_BCBATCH",10001990,"","",{"$f":"VLOOKUP(U434,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["RMRU","RKL","2021-06-29","2021-06-29","3","2022","1100","309383456","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810260","Corp Manager OT",807.17,"AUD","","AFRU","SYS_BCBATCH",10001990,"","",{"$f":"VLOOKUP(U435,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["RMRU","RKL","2021-06-29","2021-06-29","3","2022","1100","309383457","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810260","Corp Manager OT",134.53,"AUD","","AFRU","SYS_BCBATCH",10001990,"","",{"$f":"VLOOKUP(U436,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["RMRU","RKL","2021-06-29","2021-06-29","3","2022","1100","309383458","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810260","Corp Manager OT",807.17,"AUD","","AFRU","SYS_BCBATCH",10001990,"","",{"$f":"VLOOKUP(U437,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["RMRU","RKL","2021-06-29","2021-06-29","3","2022","1100","309383459","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810220","Corp Ops Lead OT",116.66,"AUD","","AFRU","SYS_BCBATCH",10001233,"","",{"$f":"VLOOKUP(U438,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["RMRU","RKL","2021-06-29","2021-06-29","3","2022","1100","309383460","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810220","Corp Ops Lead OT",58.33,"AUD","","AFRU","SYS_BCBATCH",10001233,"","",{"$f":"VLOOKUP(U439,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["RMRU","RKL","2021-06-29","2021-06-29","3","2022","1100","309383461","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810220","Corp Ops Lead OT",583.29999999999995,"AUD","","AFRU","SYS_BCBATCH",10001233,"","",{"$f":"VLOOKUP(U440,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["RMRU","RKL","2021-06-30","2021-06-30","3","2022","1100","309384304","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810220","Corp Ops Lead OT",305.77999999999997,"AUD","","AFRU","SYS_BCBATCH",10002562,"","",{"$f":"VLOOKUP(U441,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-06-30","2021-06-30","3","2022","1100","309384305","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810220","Corp Ops Lead OT",611.54999999999995,"AUD","","AFRU","SYS_BCBATCH",10002562,"","",{"$f":"VLOOKUP(U442,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-06-30","2021-06-30","3","2022","1100","309384306","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810220","Corp Ops Lead OT",1406.57,"AUD","","AFRU","SYS_BCBATCH",10006898,"","",{"$f":"VLOOKUP(U443,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["RMRU","RKL","2021-06-30","2021-06-30","3","2022","1100","309384307","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810220","Corp Ops Lead OT",1100.79,"AUD","","AFRU","SYS_BCBATCH",10006898,"","",{"$f":"VLOOKUP(U444,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["RMRU","RKL","2021-06-30","2021-06-30","3","2022","1100","309384308","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810220","Corp Ops Lead OT",366.93,"AUD","","AFRU","SYS_BCBATCH",10006898,"","",{"$f":"VLOOKUP(U445,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["RMRU","RKL","2021-06-30","2021-06-30","3","2022","1100","309384309","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810220","Corp Ops Lead OT",1223.0999999999999,"AUD","","AFRU","SYS_BCBATCH",10006898,"","",{"$f":"VLOOKUP(U446,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["RMRU","RKL","2021-06-30","2021-06-30","3","2022","1100","309384310","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810220","Corp Ops Lead OT",244.62,"AUD","","AFRU","SYS_BCBATCH",10006898,"","",{"$f":"VLOOKUP(U447,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["RMRU","RKL","2021-06-30","2021-06-30","3","2022","1100","309384311","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810223","Corp Prof OT",903.77,"AUD","","AFRU","SYS_BCBATCH",10000557,"","",{"$f":"VLOOKUP(U448,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["RMRU","RKL","2021-06-30","2021-06-30","3","2022","1100","309384312","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810220","Corp Ops Lead OT",366.93,"AUD","","AFRU","SYS_BCBATCH",10006898,"","",{"$f":"VLOOKUP(U449,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["RMRU","RKL","2021-06-30","2021-06-30","3","2022","1100","309384313","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810118","Project Manager NT",854.03,"AUD","","AFRU","SYS_BCBATCH",10000641,"","",{"$f":"VLOOKUP(U450,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-06-30","2021-06-30","3","2022","1100","309384315","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810141","Corp Snr Mngr NT",1213.3499999999999,"AUD","","AFRU","SYS_BCBATCH",10000174,"","",{"$f":"VLOOKUP(U451,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["RMRU","RKL","2021-06-30","2021-06-30","3","2022","1100","309384316","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810141","Corp Snr Mngr NT",1213.3499999999999,"AUD","","AFRU","SYS_BCBATCH",10000174,"","",{"$f":"VLOOKUP(U452,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["RMRU","RKL","2021-06-30","2021-06-30","3","2022","1100","309384317","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810220","Corp Ops Lead OT",183.47,"AUD","","AFRU","SYS_BCBATCH",10006898,"","",{"$f":"VLOOKUP(U453,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["RMRU","RKL","2021-06-30","2021-06-30","3","2022","1100","309384319","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810122","Corp Prof Exp NT",716.1,"AUD","","AFRU","SYS_BCBATCH",10002224,"","",{"$f":"VLOOKUP(U454,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["","RKL","2021-06-19","2021-07-03","4","2022","1100","309465860","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810300","Allowance Expenses",387.33,"AUD","","CATS","SYS_BCBATCH",10008908,"","",{"$f":"VLOOKUP(U455,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["","RKL","2021-06-19","2021-07-03","4","2022","1100","309465860","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810300","Allowance Expenses",516.44000000000005,"AUD","","CATS","SYS_BCBATCH",10008908,"","",{"$f":"VLOOKUP(U456,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["","RKL","2021-06-27","2021-07-03","4","2022","1100","309465881","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810300","Allowance Expenses",910.62,"AUD","Olinda Community Meeting","CATS","SYS_BCBATCH",10000478,"","",{"$f":"VLOOKUP(U457,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["","RKL","2021-06-27","2021-07-03","4","2022","1100","309465881","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810300","Allowance Expenses",569.14,"AUD","Yarra Ranges Community Meetings","CATS","SYS_BCBATCH",10000478,"","",{"$f":"VLOOKUP(U458,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["","RKL","2021-06-12","2021-07-03","4","2022","1100","309465954","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810300","Allowance Expenses",480.51,"AUD","","CATS","SYS_BCBATCH",10009956,"","",{"$f":"VLOOKUP(U459,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["","RKL","2021-06-12","2021-07-03","4","2022","1100","309465954","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810300","Allowance Expenses",1281.3599999999999,"AUD","","CATS","SYS_BCBATCH",10009956,"","",{"$f":"VLOOKUP(U460,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["","RKL","2021-06-12","2021-07-03","4","2022","1100","309465954","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810300","Allowance Expenses",1281.3599999999999,"AUD","","CATS","SYS_BCBATCH",10009956,"","",{"$f":"VLOOKUP(U461,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["RMRU","RKL","2021-07-04","2021-07-04","4","2022","1100","309465999","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810222","Corp Prof Exp OT",1821.24,"AUD","","AFRU","SYS_BCBATCH",10009755,"","",{"$f":"VLOOKUP(U462,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["RMRU","RKL","2021-07-03","2021-07-03","4","2022","1100","309467493","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810223","Corp Prof OT",1149.29,"AUD","Storm response LV gens","AFRU","SYS_BCBATCH",10001121,"","",{"$f":"VLOOKUP(U463,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-07-03","2021-07-03","4","2022","1100","309467494","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810223","Corp Prof OT",676.05,"AUD","Storm response LV gens","AFRU","SYS_BCBATCH",10001121,"","",{"$f":"VLOOKUP(U464,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-07-03","2021-07-03","4","2022","1100","309467495","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810123","Corp Prof NT",676.05,"AUD","","AFRU","SYS_BCBATCH",10001121,"","",{"$f":"VLOOKUP(U465,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-07-03","2021-07-03","4","2022","1100","309467496","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810123","Corp Prof NT",676.05,"AUD","","AFRU","SYS_BCBATCH",10001121,"","",{"$f":"VLOOKUP(U466,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-07-03","2021-07-03","4","2022","1100","309467497","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810243","Corp Support OT",162.18,"AUD","","AFRU","SYS_BCBATCH",10001526,"","",{"$f":"VLOOKUP(U467,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["RMRU","RKL","2021-07-03","2021-07-03","4","2022","1100","309467498","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810243","Corp Support OT",567.63,"AUD","","AFRU","SYS_BCBATCH",10001526,"","",{"$f":"VLOOKUP(U468,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["RMRU","RKL","2021-07-03","2021-07-03","4","2022","1100","309467499","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810141","Corp Snr Mngr NT",1065.3800000000001,"AUD","","AFRU","SYS_BCBATCH",10000368,"","",{"$f":"VLOOKUP(U469,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-07-03","2021-07-03","4","2022","1100","309467500","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810141","Corp Snr Mngr NT",1065.3800000000001,"AUD","","AFRU","SYS_BCBATCH",10000368,"","",{"$f":"VLOOKUP(U470,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-07-03","2021-07-03","4","2022","1100","309467501","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810243","Corp Support OT",133.55000000000001,"AUD","","AFRU","SYS_BCBATCH",10009940,"","",{"$f":"VLOOKUP(U471,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["RMRU","RKL","2021-07-03","2021-07-03","4","2022","1100","309467502","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810243","Corp Support OT",44.52,"AUD","","AFRU","SYS_BCBATCH",10009940,"","",{"$f":"VLOOKUP(U472,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["RMRU","RKL","2021-07-03","2021-07-03","4","2022","1100","309467503","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810243","Corp Support OT",133.55000000000001,"AUD","","AFRU","SYS_BCBATCH",10009940,"","",{"$f":"VLOOKUP(U473,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["RMRU","RKL","2021-07-03","2021-07-03","4","2022","1100","309467504","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810243","Corp Support OT",111.29,"AUD","","AFRU","SYS_BCBATCH",10009940,"","",{"$f":"VLOOKUP(U474,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["RMRU","RKL","2021-07-03","2021-07-03","4","2022","1100","309467505","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810143","Corp Support NT",445.13,"AUD","","AFRU","SYS_BCBATCH",10009940,"","",{"$f":"VLOOKUP(U475,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["RMRU","RKL","2021-07-03","2021-07-03","4","2022","1100","309467506","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810143","Corp Support NT",445.13,"AUD","","AFRU","SYS_BCBATCH",10009940,"","",{"$f":"VLOOKUP(U476,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["RMRU","RKL","2021-07-03","2021-07-03","4","2022","1100","309467507","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810143","Corp Support NT",445.13,"AUD","","AFRU","SYS_BCBATCH",10009940,"","",{"$f":"VLOOKUP(U477,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["RMRU","RKL","2021-07-03","2021-07-03","4","2022","1100","309467508","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810143","Corp Support NT",445.13,"AUD","","AFRU","SYS_BCBATCH",10009940,"","",{"$f":"VLOOKUP(U478,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["RMRU","RKL","2021-07-03","2021-07-03","4","2022","1100","309467509","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810243","Corp Support OT",121.64,"AUD","","AFRU","SYS_BCBATCH",10001684,"","",{"$f":"VLOOKUP(U479,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["RMRU","RKL","2021-07-03","2021-07-03","4","2022","1100","309467510","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810243","Corp Support OT",81.09,"AUD","","AFRU","SYS_BCBATCH",10001684,"","",{"$f":"VLOOKUP(U480,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["RMRU","RKL","2021-07-03","2021-07-03","4","2022","1100","309467511","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810243","Corp Support OT",543.15,"AUD","","AFRU","SYS_BCBATCH",10002057,"","",{"$f":"VLOOKUP(U481,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["RMRU","RKL","2021-07-03","2021-07-03","4","2022","1100","309467512","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810243","Corp Support OT",181.05,"AUD","","AFRU","SYS_BCBATCH",10002057,"","",{"$f":"VLOOKUP(U482,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["RMRU","RKL","2021-07-03","2021-07-03","4","2022","1100","309467513","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810243","Corp Support OT",81.09,"AUD","","AFRU","SYS_BCBATCH",10001684,"","",{"$f":"VLOOKUP(U483,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["RMRU","RKL","2021-07-03","2021-07-03","4","2022","1100","309467514","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810243","Corp Support OT",144.84,"AUD","","AFRU","SYS_BCBATCH",10002057,"","",{"$f":"VLOOKUP(U484,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["RMRU","RKL","2021-07-03","2021-07-03","4","2022","1100","309467516","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810123","Corp Prof NT",90.14,"AUD","","AFRU","SYS_BCBATCH",10002256,"","",{"$f":"VLOOKUP(U485,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-07-03","2021-07-03","4","2022","1100","309467517","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810123","Corp Prof NT",90.14,"AUD","","AFRU","SYS_BCBATCH",10002256,"","",{"$f":"VLOOKUP(U486,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-07-03","2021-07-03","4","2022","1100","309467518","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810123","Corp Prof NT",90.14,"AUD","","AFRU","SYS_BCBATCH",10002256,"","",{"$f":"VLOOKUP(U487,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-07-03","2021-07-03","4","2022","1100","309467519","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810123","Corp Prof NT",90.14,"AUD","","AFRU","SYS_BCBATCH",10002256,"","",{"$f":"VLOOKUP(U488,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-07-03","2021-07-03","4","2022","1100","309467520","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810123","Corp Prof NT",90.14,"AUD","","AFRU","SYS_BCBATCH",10002256,"","",{"$f":"VLOOKUP(U489,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-07-03","2021-07-03","4","2022","1100","309467521","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810123","Corp Prof NT",90.14,"AUD","","AFRU","SYS_BCBATCH",10002256,"","",{"$f":"VLOOKUP(U490,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-07-03","2021-07-03","4","2022","1100","309467522","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810222","Corp Prof Exp OT",1074.1500000000001,"AUD","","AFRU","SYS_BCBATCH",10001200,"","",{"$f":"VLOOKUP(U491,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-07-03","2021-07-03","4","2022","1100","309467523","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810241","Corp Snr Mngr OT",606.67999999999995,"AUD","Stayed back after shift change","AFRU","SYS_BCBATCH",10009790,"","",{"$f":"VLOOKUP(U492,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["RMRU","RKL","2021-07-03","2021-07-03","4","2022","1100","309467524","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810241","Corp Snr Mngr OT",1456.02,"AUD","Change of shift","AFRU","SYS_BCBATCH",10009790,"","",{"$f":"VLOOKUP(U493,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["RMRU","RKL","2021-07-03","2021-07-03","4","2022","1100","309467525","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810222","Corp Prof Exp OT",358.05,"AUD","Worked to 3:30 but then another 2hr comp","AFRU","SYS_BCBATCH",10001200,"","",{"$f":"VLOOKUP(U494,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-07-03","2021-07-03","4","2022","1100","309467526","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810122","Corp Prof Exp NT",716.1,"AUD","","AFRU","SYS_BCBATCH",10001200,"","",{"$f":"VLOOKUP(U495,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-07-03","2021-07-03","4","2022","1100","309467527","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810222","Corp Prof Exp OT",429.66,"AUD","Worked to 17:00 then another 1.5hr compu","AFRU","SYS_BCBATCH",10001200,"","",{"$f":"VLOOKUP(U496,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-07-03","2021-07-03","4","2022","1100","309467528","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810122","Corp Prof Exp NT",716.1,"AUD","","AFRU","SYS_BCBATCH",10001200,"","",{"$f":"VLOOKUP(U497,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-07-03","2021-07-03","4","2022","1100","309467529","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810222","Corp Prof Exp OT",286.44,"AUD","Worked to 16:30 but then another 1hr sun","AFRU","SYS_BCBATCH",10001200,"","",{"$f":"VLOOKUP(U498,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-07-03","2021-07-03","4","2022","1100","309467530","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810122","Corp Prof Exp NT",716.1,"AUD","","AFRU","SYS_BCBATCH",10001200,"","",{"$f":"VLOOKUP(U499,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-07-03","2021-07-03","4","2022","1100","309467531","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810122","Corp Prof Exp NT",716.1,"AUD","","AFRU","SYS_BCBATCH",10001200,"","",{"$f":"VLOOKUP(U500,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-07-03","2021-07-03","4","2022","1100","309467532","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810122","Corp Prof Exp NT",716.1,"AUD","","AFRU","SYS_BCBATCH",10001200,"","",{"$f":"VLOOKUP(U501,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-07-03","2021-07-03","4","2022","1100","309467533","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810222","Corp Prof Exp OT",537.08000000000004,"AUD","","AFRU","SYS_BCBATCH",10001200,"","",{"$f":"VLOOKUP(U502,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-07-03","2021-07-03","4","2022","1100","309467534","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810122","Corp Prof Exp NT",716.1,"AUD","","AFRU","SYS_BCBATCH",10001200,"","",{"$f":"VLOOKUP(U503,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-07-03","2021-07-03","4","2022","1100","309467536","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810119","Corp Exec Mngr NT",1902.3,"AUD","","AFRU","SYS_BCBATCH",10000097,"","",{"$f":"VLOOKUP(U504,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["RMRU","RKL","2021-07-03","2021-07-03","4","2022","1100","309467537","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810119","Corp Exec Mngr NT",1902.3,"AUD","","AFRU","SYS_BCBATCH",10000097,"","",{"$f":"VLOOKUP(U505,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["RMRU","RKL","2021-07-03","2021-07-03","4","2022","1100","309467538","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810119","Corp Exec Mngr NT",1902.3,"AUD","","AFRU","SYS_BCBATCH",10000097,"","",{"$f":"VLOOKUP(U506,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["RMRU","RKL","2021-07-03","2021-07-03","4","2022","1100","309467539","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810119","Corp Exec Mngr NT",1902.3,"AUD","","AFRU","SYS_BCBATCH",10000097,"","",{"$f":"VLOOKUP(U507,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["RMRU","RKL","2021-07-03","2021-07-03","4","2022","1100","309467540","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810119","Corp Exec Mngr NT",1902.3,"AUD","","AFRU","SYS_BCBATCH",10000097,"","",{"$f":"VLOOKUP(U508,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["RMRU","RKL","2021-07-03","2021-07-03","4","2022","1100","309467541","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810119","Corp Exec Mngr NT",1902.3,"AUD","","AFRU","SYS_BCBATCH",10000097,"","",{"$f":"VLOOKUP(U509,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["RMRU","RKL","2021-07-03","2021-07-03","4","2022","1100","309467542","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810119","Corp Exec Mngr NT",1902.3,"AUD","","AFRU","SYS_BCBATCH",10000097,"","",{"$f":"VLOOKUP(U510,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["RMRU","RKL","2021-07-03","2021-07-03","4","2022","1100","309467543","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810119","Corp Exec Mngr NT",1902.3,"AUD","","AFRU","SYS_BCBATCH",10000097,"","",{"$f":"VLOOKUP(U511,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["RMRU","RKL","2021-07-03","2021-07-03","4","2022","1100","309467544","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810119","Corp Exec Mngr NT",1902.3,"AUD","","AFRU","SYS_BCBATCH",10000097,"","",{"$f":"VLOOKUP(U512,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["RMRU","RKL","2021-07-03","2021-07-03","4","2022","1100","309467545","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810119","Corp Exec Mngr NT",1902.3,"AUD","","AFRU","SYS_BCBATCH",10000097,"","",{"$f":"VLOOKUP(U513,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["RMRU","RKL","2021-07-03","2021-07-03","4","2022","1100","309467546","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810119","Corp Exec Mngr NT",1902.3,"AUD","","AFRU","SYS_BCBATCH",10000097,"","",{"$f":"VLOOKUP(U514,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["RMRU","RKL","2021-07-03","2021-07-03","4","2022","1100","309467547","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810119","Corp Exec Mngr NT",1902.3,"AUD","","AFRU","SYS_BCBATCH",10000097,"","",{"$f":"VLOOKUP(U515,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["RMRU","RKL","2021-07-03","2021-07-03","4","2022","1100","309467548","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810119","Corp Exec Mngr NT",1902.3,"AUD","Storm","AFRU","SYS_BCBATCH",10000097,"","",{"$f":"VLOOKUP(U516,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["RMRU","RKL","2021-07-03","2021-07-03","4","2022","1100","309467549","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810119","Corp Exec Mngr NT",1902.3,"AUD","Storm Event","AFRU","SYS_BCBATCH",10000097,"","",{"$f":"VLOOKUP(U517,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["RMRU","RKL","2021-07-03","2021-07-03","4","2022","1100","309467563","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810243","Corp Support OT",144.84,"AUD","Overtime for Storm Relief Outbound Custo","AFRU","SYS_BCBATCH",10008666,"","",{"$f":"VLOOKUP(U518,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-07-03","2021-07-03","4","2022","1100","309467564","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810141","Corp Snr Mngr NT",647.12,"AUD","","AFRU","SYS_BCBATCH",10001047,"","",{"$f":"VLOOKUP(U519,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-07-03","2021-07-03","4","2022","1100","309467565","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810141","Corp Snr Mngr NT",566.23,"AUD","","AFRU","SYS_BCBATCH",10001047,"","",{"$f":"VLOOKUP(U520,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-07-03","2021-07-03","4","2022","1100","309467566","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810141","Corp Snr Mngr NT",1213.3499999999999,"AUD","","AFRU","SYS_BCBATCH",10001047,"","",{"$f":"VLOOKUP(U521,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-07-03","2021-07-03","4","2022","1100","309467567","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810141","Corp Snr Mngr NT",1213.3499999999999,"AUD","","AFRU","SYS_BCBATCH",10001047,"","",{"$f":"VLOOKUP(U522,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-07-03","2021-07-03","4","2022","1100","309467568","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810141","Corp Snr Mngr NT",1213.3499999999999,"AUD","","AFRU","SYS_BCBATCH",10001047,"","",{"$f":"VLOOKUP(U523,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-07-03","2021-07-03","4","2022","1100","309467569","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810122","Corp Prof Exp NT",716.1,"AUD","","AFRU","SYS_BCBATCH",10001451,"","",{"$f":"VLOOKUP(U524,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["RMRU","RKL","2021-07-03","2021-07-03","4","2022","1100","309467570","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810122","Corp Prof Exp NT",716.1,"AUD","","AFRU","SYS_BCBATCH",10001451,"","",{"$f":"VLOOKUP(U525,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["RMRU","RKL","2021-07-03","2021-07-03","4","2022","1100","309467573","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810223","Corp Prof OT",608.45000000000005,"AUD","Storm response LV gens","AFRU","SYS_BCBATCH",10001121,"","",{"$f":"VLOOKUP(U526,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-07-03","2021-07-03","4","2022","1100","309467574","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810123","Corp Prof NT",676.05,"AUD","","AFRU","SYS_BCBATCH",10001121,"","",{"$f":"VLOOKUP(U527,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-07-03","2021-07-03","4","2022","1100","309467575","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810223","Corp Prof OT",371.83,"AUD","Storm response LV gens","AFRU","SYS_BCBATCH",10001121,"","",{"$f":"VLOOKUP(U528,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-07-03","2021-07-03","4","2022","1100","309467576","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810123","Corp Prof NT",676.05,"AUD","","AFRU","SYS_BCBATCH",10001121,"","",{"$f":"VLOOKUP(U529,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-07-03","2021-07-03","4","2022","1100","309467583","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810223","Corp Prof OT",1420.21,"AUD","SCC Shifts","AFRU","SYS_BCBATCH",10009860,"","",{"$f":"VLOOKUP(U530,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-07-03","2021-07-03","4","2022","1100","309467584","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810223","Corp Prof OT",1549.32,"AUD","SCC Shifts","AFRU","SYS_BCBATCH",10009860,"","",{"$f":"VLOOKUP(U531,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-07-03","2021-07-03","4","2022","1100","309467585","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810223","Corp Prof OT",1549.32,"AUD","SCC Shifts","AFRU","SYS_BCBATCH",10009860,"","",{"$f":"VLOOKUP(U532,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-07-03","2021-07-03","4","2022","1100","309467586","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810223","Corp Prof OT",1549.32,"AUD","SCC Shifts","AFRU","SYS_BCBATCH",10009860,"","",{"$f":"VLOOKUP(U533,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-07-03","2021-07-03","4","2022","1100","309467587","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810223","Corp Prof OT",1549.32,"AUD","SCC Shifts","AFRU","SYS_BCBATCH",10009860,"","",{"$f":"VLOOKUP(U534,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-07-03","2021-07-03","4","2022","1100","309467588","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810223","Corp Prof OT",451.89,"AUD","SCC Shifts","AFRU","SYS_BCBATCH",10009860,"","",{"$f":"VLOOKUP(U535,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-07-03","2021-07-03","4","2022","1100","309467589","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810223","Corp Prof OT",451.89,"AUD","SCC Shifts","AFRU","SYS_BCBATCH",10009860,"","",{"$f":"VLOOKUP(U536,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-07-03","2021-07-03","4","2022","1100","309467590","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810223","Corp Prof OT",451.89,"AUD","SCC Shifts","AFRU","SYS_BCBATCH",10009860,"","",{"$f":"VLOOKUP(U537,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-07-03","2021-07-03","4","2022","1100","309467591","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810223","Corp Prof OT",451.89,"AUD","SCC Shifts","AFRU","SYS_BCBATCH",10009860,"","",{"$f":"VLOOKUP(U538,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-07-03","2021-07-03","4","2022","1100","309467592","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810223","Corp Prof OT",451.89,"AUD","SCC Shifts","AFRU","SYS_BCBATCH",10009860,"","",{"$f":"VLOOKUP(U539,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-07-03","2021-07-03","4","2022","1100","309467593","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810223","Corp Prof OT",451.89,"AUD","SCC Shifts","AFRU","SYS_BCBATCH",10009860,"","",{"$f":"VLOOKUP(U540,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-07-03","2021-07-03","4","2022","1100","309467594","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810223","Corp Prof OT",451.89,"AUD","SCC Shifts","AFRU","SYS_BCBATCH",10009860,"","",{"$f":"VLOOKUP(U541,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-07-03","2021-07-03","4","2022","1100","309467595","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810223","Corp Prof OT",451.89,"AUD","SCC Shifts","AFRU","SYS_BCBATCH",10009860,"","",{"$f":"VLOOKUP(U542,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-07-03","2021-07-03","4","2022","1100","309467596","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810241","Corp Snr Mngr OT",2912.04,"AUD","Storm Restoration Assistance","AFRU","SYS_BCBATCH",10000528,"","",{"$f":"VLOOKUP(U543,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["RMRU","RKL","2021-07-03","2021-07-03","4","2022","1100","309467597","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810241","Corp Snr Mngr OT",485.34,"AUD","Operational Manager storm response","AFRU","SYS_BCBATCH",10010010,"","",{"$f":"VLOOKUP(U544,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-07-03","2021-07-03","4","2022","1100","309467598","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810241","Corp Snr Mngr OT",728.01,"AUD","Operational manager storm response","AFRU","SYS_BCBATCH",10010010,"","",{"$f":"VLOOKUP(U545,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-07-03","2021-07-03","4","2022","1100","309467599","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810241","Corp Snr Mngr OT",606.67999999999995,"AUD","Operational manager storm response","AFRU","SYS_BCBATCH",10010010,"","",{"$f":"VLOOKUP(U546,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-07-03","2021-07-03","4","2022","1100","309467600","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810241","Corp Snr Mngr OT",728.01,"AUD","Operational manager","AFRU","SYS_BCBATCH",10010010,"","",{"$f":"VLOOKUP(U547,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-07-03","2021-07-03","4","2022","1100","309467601","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810241","Corp Snr Mngr OT",728.01,"AUD","Operational manager","AFRU","SYS_BCBATCH",10010010,"","",{"$f":"VLOOKUP(U548,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-07-03","2021-07-03","4","2022","1100","309467602","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810241","Corp Snr Mngr OT",728.01,"AUD","Operational manager","AFRU","SYS_BCBATCH",10010010,"","",{"$f":"VLOOKUP(U549,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-07-03","2021-07-03","4","2022","1100","309467603","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810241","Corp Snr Mngr OT",728.01,"AUD","Operational manager","AFRU","SYS_BCBATCH",10010010,"","",{"$f":"VLOOKUP(U550,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-07-03","2021-07-03","4","2022","1100","309467604","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810241","Corp Snr Mngr OT",3033.38,"AUD","Storm response Operational Manager","AFRU","SYS_BCBATCH",10010010,"","",{"$f":"VLOOKUP(U551,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-07-03","2021-07-03","4","2022","1100","309467605","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810241","Corp Snr Mngr OT",1577.36,"AUD","Storm response","AFRU","SYS_BCBATCH",10010010,"","",{"$f":"VLOOKUP(U552,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-07-03","2021-07-03","4","2022","1100","309467606","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810241","Corp Snr Mngr OT",2912.04,"AUD","Assisting with Storm recovery","AFRU","SYS_BCBATCH",10000528,"","",{"$f":"VLOOKUP(U553,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["RMRU","RKL","2021-07-03","2021-07-03","4","2022","1100","309467607","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810241","Corp Snr Mngr OT",2912.04,"AUD","Storm Response","AFRU","SYS_BCBATCH",10006816,"","",{"$f":"VLOOKUP(U554,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["RMRU","RKL","2021-07-03","2021-07-03","4","2022","1100","309467608","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810241","Corp Snr Mngr OT",970.68,"AUD","Storm Response","AFRU","SYS_BCBATCH",10006816,"","",{"$f":"VLOOKUP(U555,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["RMRU","RKL","2021-07-03","2021-07-03","4","2022","1100","309467609","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810241","Corp Snr Mngr OT",849.35,"AUD","Storm Response","AFRU","SYS_BCBATCH",10006816,"","",{"$f":"VLOOKUP(U556,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["RMRU","RKL","2021-07-03","2021-07-03","4","2022","1100","309467610","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810241","Corp Snr Mngr OT",970.68,"AUD","Storm Response","AFRU","SYS_BCBATCH",10006816,"","",{"$f":"VLOOKUP(U557,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["RMRU","RKL","2021-07-03","2021-07-03","4","2022","1100","309467611","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810241","Corp Snr Mngr OT",970.68,"AUD","Storm Response","AFRU","SYS_BCBATCH",10006816,"","",{"$f":"VLOOKUP(U558,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["RMRU","RKL","2021-07-03","2021-07-03","4","2022","1100","309467612","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810241","Corp Snr Mngr OT",3154.71,"AUD","Storm Response","AFRU","SYS_BCBATCH",10006816,"","",{"$f":"VLOOKUP(U559,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["RMRU","RKL","2021-07-03","2021-07-03","4","2022","1100","309467613","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810241","Corp Snr Mngr OT",3154.71,"AUD","Storm Response","AFRU","SYS_BCBATCH",10006816,"","",{"$f":"VLOOKUP(U560,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["RMRU","RKL","2021-07-03","2021-07-03","4","2022","1100","309467614","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810241","Corp Snr Mngr OT",1092.02,"AUD","Storm Response","AFRU","SYS_BCBATCH",10006816,"","",{"$f":"VLOOKUP(U561,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["RMRU","RKL","2021-07-03","2021-07-03","4","2022","1100","309467615","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810241","Corp Snr Mngr OT",1092.02,"AUD","Storm Assistance","AFRU","SYS_BCBATCH",10006816,"","",{"$f":"VLOOKUP(U562,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["RMRU","RKL","2021-07-03","2021-07-03","4","2022","1100","309467616","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810122","Corp Prof Exp NT",716.1,"AUD","","AFRU","SYS_BCBATCH",10001451,"","",{"$f":"VLOOKUP(U563,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["RMRU","RKL","2021-07-03","2021-07-03","4","2022","1100","309467617","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810122","Corp Prof Exp NT",716.1,"AUD","","AFRU","SYS_BCBATCH",10001451,"","",{"$f":"VLOOKUP(U564,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["RMRU","RKL","2021-07-03","2021-07-03","4","2022","1100","309467618","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810122","Corp Prof Exp NT",716.1,"AUD","","AFRU","SYS_BCBATCH",10001451,"","",{"$f":"VLOOKUP(U565,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["RMRU","RKL","2021-07-03","2021-07-03","4","2022","1100","309467619","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810122","Corp Prof Exp NT",716.1,"AUD","","AFRU","SYS_BCBATCH",10001200,"","",{"$f":"VLOOKUP(U566,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-07-03","2021-07-03","4","2022","1100","309467620","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810222","Corp Prof Exp OT",250.64,"AUD","","AFRU","SYS_BCBATCH",10001200,"","",{"$f":"VLOOKUP(U567,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-07-03","2021-07-03","4","2022","1100","309467621","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810122","Corp Prof Exp NT",716.1,"AUD","","AFRU","SYS_BCBATCH",10001200,"","",{"$f":"VLOOKUP(U568,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-07-03","2021-07-03","4","2022","1100","309467622","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810222","Corp Prof Exp OT",1074.1500000000001,"AUD","","AFRU","SYS_BCBATCH",10001200,"","",{"$f":"VLOOKUP(U569,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-07-03","2021-07-03","4","2022","1100","309467623","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810222","Corp Prof Exp OT",1503.81,"AUD","","AFRU","SYS_BCBATCH",10001200,"","",{"$f":"VLOOKUP(U570,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-07-03","2021-07-03","4","2022","1100","309467624","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810122","Corp Prof Exp NT",716.1,"AUD","Fatgue Management day off","AFRU","SYS_BCBATCH",10001200,"","",{"$f":"VLOOKUP(U571,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-07-03","2021-07-03","4","2022","1100","309467625","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810222","Corp Prof Exp OT",787.71,"AUD","","AFRU","SYS_BCBATCH",10001200,"","",{"$f":"VLOOKUP(U572,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-07-03","2021-07-03","4","2022","1100","309467626","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810122","Corp Prof Exp NT",716.1,"AUD","","AFRU","SYS_BCBATCH",10001200,"","",{"$f":"VLOOKUP(U573,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-07-03","2021-07-03","4","2022","1100","309467627","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810222","Corp Prof Exp OT",859.32,"AUD","","AFRU","SYS_BCBATCH",10001200,"","",{"$f":"VLOOKUP(U574,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-07-03","2021-07-03","4","2022","1100","309467628","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810122","Corp Prof Exp NT",716.1,"AUD","","AFRU","SYS_BCBATCH",10001200,"","",{"$f":"VLOOKUP(U575,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-07-03","2021-07-03","4","2022","1100","309467629","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810222","Corp Prof Exp OT",859.32,"AUD","","AFRU","SYS_BCBATCH",10001200,"","",{"$f":"VLOOKUP(U576,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-07-03","2021-07-03","4","2022","1100","309467630","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810122","Corp Prof Exp NT",620.62,"AUD","","AFRU","SYS_BCBATCH",10001200,"","",{"$f":"VLOOKUP(U577,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-07-03","2021-07-03","4","2022","1100","309467631","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810122","Corp Prof Exp NT",95.48,"AUD","ten hr break","AFRU","SYS_BCBATCH",10001200,"","",{"$f":"VLOOKUP(U578,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-07-03","2021-07-03","4","2022","1100","309467632","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810222","Corp Prof Exp OT",1002.54,"AUD","","AFRU","SYS_BCBATCH",10001200,"","",{"$f":"VLOOKUP(U579,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-07-03","2021-07-03","4","2022","1100","309467633","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810222","Corp Prof Exp OT",2148.3000000000002,"AUD","","AFRU","SYS_BCBATCH",10001200,"","",{"$f":"VLOOKUP(U580,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-07-03","2021-07-03","4","2022","1100","309467634","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810222","Corp Prof Exp OT",2219.91,"AUD","","AFRU","SYS_BCBATCH",10001200,"","",{"$f":"VLOOKUP(U581,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-07-03","2021-07-03","4","2022","1100","309467635","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810222","Corp Prof Exp OT",1002.54,"AUD","","AFRU","SYS_BCBATCH",10001200,"","",{"$f":"VLOOKUP(U582,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-07-03","2021-07-03","4","2022","1100","309467636","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810122","Corp Prof Exp NT",429.66,"AUD","","AFRU","SYS_BCBATCH",10001200,"","",{"$f":"VLOOKUP(U583,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-07-03","2021-07-03","4","2022","1100","309467637","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810122","Corp Prof Exp NT",286.44,"AUD","Ten hr break","AFRU","SYS_BCBATCH",10001200,"","",{"$f":"VLOOKUP(U584,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-07-03","2021-07-03","4","2022","1100","309467638","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810222","Corp Prof Exp OT",1217.3699999999999,"AUD","","AFRU","SYS_BCBATCH",10001200,"","",{"$f":"VLOOKUP(U585,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-07-03","2021-07-03","4","2022","1100","309467639","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810122","Corp Prof Exp NT",716.1,"AUD","","AFRU","SYS_BCBATCH",10001200,"","",{"$f":"VLOOKUP(U586,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-07-03","2021-07-03","4","2022","1100","309467640","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810141","Corp Snr Mngr NT",1213.3499999999999,"AUD","","AFRU","SYS_BCBATCH",10000189,"","",{"$f":"VLOOKUP(U587,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-07-03","2021-07-03","4","2022","1100","309467641","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810141","Corp Snr Mngr NT",1213.3499999999999,"AUD","","AFRU","SYS_BCBATCH",10000189,"","",{"$f":"VLOOKUP(U588,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-07-03","2021-07-03","4","2022","1100","309467642","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810141","Corp Snr Mngr NT",1213.3499999999999,"AUD","","AFRU","SYS_BCBATCH",10000189,"","",{"$f":"VLOOKUP(U589,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-07-03","2021-07-03","4","2022","1100","309467643","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810243","Corp Support OT",286.74,"AUD","","AFRU","SYS_BCBATCH",10007914,"","",{"$f":"VLOOKUP(U590,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["RMRU","RKL","2021-07-03","2021-07-03","4","2022","1100","309467644","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810243","Corp Support OT",286.74,"AUD","","AFRU","SYS_BCBATCH",10007914,"","",{"$f":"VLOOKUP(U591,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["RMRU","RKL","2021-07-03","2021-07-03","4","2022","1100","309467645","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810243","Corp Support OT",286.74,"AUD","","AFRU","SYS_BCBATCH",10007914,"","",{"$f":"VLOOKUP(U592,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["RMRU","RKL","2021-07-03","2021-07-03","4","2022","1100","309467646","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810243","Corp Support OT",430.11,"AUD","","AFRU","SYS_BCBATCH",10007914,"","",{"$f":"VLOOKUP(U593,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["RMRU","RKL","2021-07-03","2021-07-03","4","2022","1100","309467647","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810243","Corp Support OT",286.74,"AUD","","AFRU","SYS_BCBATCH",10007914,"","",{"$f":"VLOOKUP(U594,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["RMRU","RKL","2021-07-03","2021-07-03","4","2022","1100","309467648","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810243","Corp Support OT",430.11,"AUD","","AFRU","SYS_BCBATCH",10007914,"","",{"$f":"VLOOKUP(U595,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["RMRU","RKL","2021-07-03","2021-07-03","4","2022","1100","309467649","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810243","Corp Support OT",812.43,"AUD","","AFRU","SYS_BCBATCH",10007914,"","",{"$f":"VLOOKUP(U596,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["RMRU","RKL","2021-07-03","2021-07-03","4","2022","1100","309467650","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810243","Corp Support OT",1146.96,"AUD","","AFRU","SYS_BCBATCH",10007914,"","",{"$f":"VLOOKUP(U597,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["RMRU","RKL","2021-07-03","2021-07-03","4","2022","1100","309467651","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810243","Corp Support OT",525.69000000000005,"AUD","","AFRU","SYS_BCBATCH",10007914,"","",{"$f":"VLOOKUP(U598,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["RMRU","RKL","2021-07-03","2021-07-03","4","2022","1100","309467653","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810243","Corp Support OT",621.27,"AUD","","AFRU","SYS_BCBATCH",10007914,"","",{"$f":"VLOOKUP(U599,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["RMRU","RKL","2021-07-03","2021-07-03","4","2022","1100","309467654","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810243","Corp Support OT",430.11,"AUD","","AFRU","SYS_BCBATCH",10007914,"","",{"$f":"VLOOKUP(U600,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["RMRU","RKL","2021-07-03","2021-07-03","4","2022","1100","309467659","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810160","Corp Manager NT",958.73,"AUD","","AFRU","SYS_BCBATCH",10000371,"","",{"$f":"VLOOKUP(U601,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["RMRU","RKL","2021-07-03","2021-07-03","4","2022","1100","309467660","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810243","Corp Support OT",217.26,"AUD","","AFRU","SYS_BCBATCH",10008994,"","",{"$f":"VLOOKUP(U602,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["RMRU","RKL","2021-07-04","2021-07-04","4","2022","1100","309469500","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810222","Corp Prof Exp OT",1821.24,"AUD","","AFRU","SYS_BCBATCH",10009755,"","",{"$f":"VLOOKUP(U603,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["RMRU","RKL","2021-07-04","2021-07-04","4","2022","1100","309469501","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810222","Corp Prof Exp OT",1745.36,"AUD","","AFRU","SYS_BCBATCH",10009755,"","",{"$f":"VLOOKUP(U604,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["RMRU","RKL","2021-07-06","2021-07-06","4","2022","1100","309470222","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810222","Corp Prof Exp OT",1145.76,"AUD","DOMS Fusion Storm fault cleanup work. Wo","AFRU","SYS_BCBATCH",10001395,"","",{"$f":"VLOOKUP(U605,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-07-06","2021-07-06","4","2022","1100","309470318","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810222","Corp Prof Exp OT",143.22,"AUD","","AFRU","SYS_BCBATCH",10001451,"","",{"$f":"VLOOKUP(U606,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["RMRU","RKL","2021-07-06","2021-07-06","4","2022","1100","309470319","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810222","Corp Prof Exp OT",143.22,"AUD","","AFRU","SYS_BCBATCH",10001451,"","",{"$f":"VLOOKUP(U607,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["RMRU","RKL","2021-07-06","2021-07-06","4","2022","1100","309470320","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810222","Corp Prof Exp OT",1288.98,"AUD","","AFRU","SYS_BCBATCH",10001451,"","",{"$f":"VLOOKUP(U608,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["RMRU","RKL","2021-07-06","2021-07-06","4","2022","1100","309470321","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810222","Corp Prof Exp OT",1288.98,"AUD","","AFRU","SYS_BCBATCH",10001451,"","",{"$f":"VLOOKUP(U609,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["RMRU","RKL","2021-07-06","2021-07-06","4","2022","1100","309470322","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810222","Corp Prof Exp OT",143.22,"AUD","","AFRU","SYS_BCBATCH",10001451,"","",{"$f":"VLOOKUP(U610,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["RMRU","RKL","2021-07-06","2021-07-06","4","2022","1100","309470323","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810222","Corp Prof Exp OT",1217.3699999999999,"AUD","","AFRU","SYS_BCBATCH",10001451,"","",{"$f":"VLOOKUP(U611,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["RMRU","RKL","2021-07-06","2021-07-06","4","2022","1100","309470324","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810160","Corp Manager NT",896.85,"AUD","","AFRU","SYS_BCBATCH",10001990,"","",{"$f":"VLOOKUP(U612,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["RMRU","RKL","2021-07-06","2021-07-06","4","2022","1100","309470325","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810160","Corp Manager NT",896.85,"AUD","","AFRU","SYS_BCBATCH",10001990,"","",{"$f":"VLOOKUP(U613,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["RMRU","RKL","2021-07-06","2021-07-06","4","2022","1100","309470326","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810160","Corp Manager NT",896.85,"AUD","","AFRU","SYS_BCBATCH",10001990,"","",{"$f":"VLOOKUP(U614,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["RMRU","RKL","2021-07-06","2021-07-06","4","2022","1100","309470327","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810160","Corp Manager NT",896.85,"AUD","","AFRU","SYS_BCBATCH",10001990,"","",{"$f":"VLOOKUP(U615,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["RMRU","RKL","2021-07-06","2021-07-06","4","2022","1100","309470328","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810160","Corp Manager NT",896.85,"AUD","","AFRU","SYS_BCBATCH",10001990,"","",{"$f":"VLOOKUP(U616,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["RMRU","RKL","2021-07-06","2021-07-06","4","2022","1100","309470329","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810260","Corp Manager OT",1434.96,"AUD","","AFRU","SYS_BCBATCH",10001990,"","",{"$f":"VLOOKUP(U617,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["RMRU","RKL","2021-07-09","2021-07-09","4","2022","1100","309473765","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810243","Corp Support OT",243,"AUD","Overtime for Storm Support","AFRU","SYS_BCBATCH",10009925,"","",{"$f":"VLOOKUP(U618,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["RMRU","RKL","2021-07-13","2021-07-13","4","2022","1100","309474577","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810141","Corp Snr Mngr NT",1065.3800000000001,"AUD","Storm Response","AFRU","SYS_BCBATCH",10007022,"","",{"$f":"VLOOKUP(U619,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["RMRU","RKL","2021-07-13","2021-07-13","4","2022","1100","309474578","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810141","Corp Snr Mngr NT",1065.3800000000001,"AUD","Storm Response","AFRU","SYS_BCBATCH",10007022,"","",{"$f":"VLOOKUP(U620,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["RMRU","RKL","2021-07-13","2021-07-13","4","2022","1100","309474579","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810141","Corp Snr Mngr NT",1136.4000000000001,"AUD","Storm Response","AFRU","SYS_BCBATCH",10007022,"","",{"$f":"VLOOKUP(U621,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["RMRU","RKL","2021-07-13","2021-07-13","4","2022","1100","309474580","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810141","Corp Snr Mngr NT",1136.4000000000001,"AUD","Storm Response","AFRU","SYS_BCBATCH",10007022,"","",{"$f":"VLOOKUP(U622,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["RMRU","RKL","2021-07-13","2021-07-13","4","2022","1100","309474581","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810141","Corp Snr Mngr NT",1065.3800000000001,"AUD","Storm Response","AFRU","SYS_BCBATCH",10007022,"","",{"$f":"VLOOKUP(U623,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["RMRU","RKL","2021-07-13","2021-07-13","4","2022","1100","309474582","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810141","Corp Snr Mngr NT",1065.3800000000001,"AUD","Storm Response","AFRU","SYS_BCBATCH",10007022,"","",{"$f":"VLOOKUP(U624,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["RMRU","RKL","2021-07-13","2021-07-13","4","2022","1100","309474583","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810141","Corp Snr Mngr NT",1065.3800000000001,"AUD","Storm Response","AFRU","SYS_BCBATCH",10007022,"","",{"$f":"VLOOKUP(U625,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["RMRU","RKL","2021-07-13","2021-07-13","4","2022","1100","309474584","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810141","Corp Snr Mngr NT",1065.3800000000001,"AUD","Storm Response","AFRU","SYS_BCBATCH",10007022,"","",{"$f":"VLOOKUP(U626,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["","RKL","2021-06-17","2021-07-13","4","2022","1100","309475012","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810300","Allowance Expenses",64.349999999999994,"AUD","","CATS","SYS_BCBATCH",10006974,"","",{"$f":"VLOOKUP(U627,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["","RKL","2021-06-17","2021-07-13","4","2022","1100","309475012","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810300","Allowance Expenses",64.349999999999994,"AUD","","CATS","SYS_BCBATCH",10006974,"","",{"$f":"VLOOKUP(U628,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["","RKL","2021-06-17","2021-07-13","4","2022","1100","309475012","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810300","Allowance Expenses",64.349999999999994,"AUD","","CATS","SYS_BCBATCH",10006974,"","",{"$f":"VLOOKUP(U629,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["","RKL","2021-06-17","2021-07-13","4","2022","1100","309475012","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810300","Allowance Expenses",64.349999999999994,"AUD","","CATS","SYS_BCBATCH",10006974,"","",{"$f":"VLOOKUP(U630,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["RMRU","RKL","2021-07-14","2021-07-14","4","2022","1100","309478274","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810120","Corp Ops Lead NT",583.28,"AUD","","AFRU","SYS_BCBATCH",10004968,"","",{"$f":"VLOOKUP(U631,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["RMRU","RKL","2021-07-14","2021-07-14","4","2022","1100","309478275","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810120","Corp Ops Lead NT",583.28,"AUD","","AFRU","SYS_BCBATCH",10004968,"","",{"$f":"VLOOKUP(U632,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["RMRU","RKL","2021-07-14","2021-07-14","4","2022","1100","309478276","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810120","Corp Ops Lead NT",583.28,"AUD","","AFRU","SYS_BCBATCH",10004968,"","",{"$f":"VLOOKUP(U633,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["RMRU","RKL","2021-07-14","2021-07-14","4","2022","1100","309478277","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810120","Corp Ops Lead NT",583.28,"AUD","","AFRU","SYS_BCBATCH",10004968,"","",{"$f":"VLOOKUP(U634,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["RMRU","RKL","2021-07-14","2021-07-14","4","2022","1100","309478278","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810122","Corp Prof Exp NT",716.1,"AUD","","AFRU","SYS_BCBATCH",10001200,"","",{"$f":"VLOOKUP(U635,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-07-14","2021-07-14","4","2022","1100","309478279","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810122","Corp Prof Exp NT",716.1,"AUD","","AFRU","SYS_BCBATCH",10001200,"","",{"$f":"VLOOKUP(U636,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-07-14","2021-07-14","4","2022","1100","309478280","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810122","Corp Prof Exp NT",716.1,"AUD","","AFRU","SYS_BCBATCH",10001200,"","",{"$f":"VLOOKUP(U637,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-07-14","2021-07-14","4","2022","1100","309478281","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810122","Corp Prof Exp NT",716.1,"AUD","","AFRU","SYS_BCBATCH",10001200,"","",{"$f":"VLOOKUP(U638,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-07-14","2021-07-14","4","2022","1100","309478282","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810122","Corp Prof Exp NT",716.1,"AUD","","AFRU","SYS_BCBATCH",10001200,"","",{"$f":"VLOOKUP(U639,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-07-14","2021-07-14","4","2022","1100","309478283","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810122","Corp Prof Exp NT",334.18,"AUD","","AFRU","SYS_BCBATCH",10001200,"","",{"$f":"VLOOKUP(U640,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-07-14","2021-07-14","4","2022","1100","309478284","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810122","Corp Prof Exp NT",716.1,"AUD","","AFRU","SYS_BCBATCH",10001200,"","",{"$f":"VLOOKUP(U641,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-07-15","2021-07-15","4","2022","1100","309479964","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810143","Corp Support NT",477.9,"AUD","accumulated time for returnign REFCLs to","AFRU","SYS_BCBATCH",10007768,"","",{"$f":"VLOOKUP(U642,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-07-15","2021-07-15","4","2022","1100","309479965","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810143","Corp Support NT",477.9,"AUD","accumulated time for returnign REFCLs to","AFRU","SYS_BCBATCH",10007768,"","",{"$f":"VLOOKUP(U643,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-07-15","2021-07-15","4","2022","1100","309479966","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810143","Corp Support NT",477.9,"AUD","accumulated time for returnign REFCLs to","AFRU","SYS_BCBATCH",10007768,"","",{"$f":"VLOOKUP(U644,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-07-15","2021-07-15","4","2022","1100","309479967","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810143","Corp Support NT",477.9,"AUD","accumulated time for returnign REFCLs to","AFRU","SYS_BCBATCH",10007768,"","",{"$f":"VLOOKUP(U645,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-07-15","2021-07-15","4","2022","1100","309479968","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810143","Corp Support NT",477.9,"AUD","accumulated time for returnign REFCLs to","AFRU","SYS_BCBATCH",10007768,"","",{"$f":"VLOOKUP(U646,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-07-15","2021-07-15","4","2022","1100","309479969","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810123","Corp Prof NT",676.05,"AUD","","AFRU","SYS_BCBATCH",10001121,"","",{"$f":"VLOOKUP(U647,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-07-15","2021-07-15","4","2022","1100","309479970","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810123","Corp Prof NT",676.05,"AUD","","AFRU","SYS_BCBATCH",10001121,"","",{"$f":"VLOOKUP(U648,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-07-15","2021-07-15","4","2022","1100","309479971","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810123","Corp Prof NT",495.77,"AUD","","AFRU","SYS_BCBATCH",10001121,"","",{"$f":"VLOOKUP(U649,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-07-15","2021-07-15","4","2022","1100","309479972","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810123","Corp Prof NT",225.35,"AUD","","AFRU","SYS_BCBATCH",10001121,"","",{"$f":"VLOOKUP(U650,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-07-15","2021-07-15","4","2022","1100","309479973","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810123","Corp Prof NT",270.42,"AUD","","AFRU","SYS_BCBATCH",10001121,"","",{"$f":"VLOOKUP(U651,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-07-15","2021-07-15","4","2022","1100","309479974","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810223","Corp Prof OT",540.84,"AUD","","AFRU","SYS_BCBATCH",10001121,"","",{"$f":"VLOOKUP(U652,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-07-15","2021-07-15","4","2022","1100","309479975","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810123","Corp Prof NT",405.63,"AUD","","AFRU","SYS_BCBATCH",10001121,"","",{"$f":"VLOOKUP(U653,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-07-15","2021-07-15","4","2022","1100","309479976","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810223","Corp Prof OT",338.03,"AUD","","AFRU","SYS_BCBATCH",10001121,"","",{"$f":"VLOOKUP(U654,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-07-15","2021-07-15","4","2022","1100","309479977","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810123","Corp Prof NT",360.56,"AUD","","AFRU","SYS_BCBATCH",10001121,"","",{"$f":"VLOOKUP(U655,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-07-15","2021-07-15","4","2022","1100","309479978","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810223","Corp Prof OT",1047.8800000000001,"AUD","","AFRU","SYS_BCBATCH",10001121,"","",{"$f":"VLOOKUP(U656,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-07-15","2021-07-15","4","2022","1100","309479979","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810123","Corp Prof NT",676.05,"AUD","","AFRU","SYS_BCBATCH",10001121,"","",{"$f":"VLOOKUP(U657,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-07-15","2021-07-15","4","2022","1100","309479980","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810223","Corp Prof OT",270.42,"AUD","","AFRU","SYS_BCBATCH",10001121,"","",{"$f":"VLOOKUP(U658,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-07-15","2021-07-15","4","2022","1100","309479981","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810123","Corp Prof NT",315.49,"AUD","","AFRU","SYS_BCBATCH",10001121,"","",{"$f":"VLOOKUP(U659,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-07-15","2021-07-15","4","2022","1100","309479983","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810222","Corp Prof Exp OT",286.44,"AUD","Generation storm response- discon and de","AFRU","SYS_BCBATCH",10001200,"","",{"$f":"VLOOKUP(U660,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-07-15","2021-07-15","4","2022","1100","309479984","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810222","Corp Prof Exp OT",286.44,"AUD","Generation storm response- discon and de","AFRU","SYS_BCBATCH",10001200,"","",{"$f":"VLOOKUP(U661,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-07-15","2021-07-15","4","2022","1100","309479985","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810222","Corp Prof Exp OT",1288.98,"AUD","Generation storm response- discon and de","AFRU","SYS_BCBATCH",10001200,"","",{"$f":"VLOOKUP(U662,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-07-15","2021-07-15","4","2022","1100","309479986","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810222","Corp Prof Exp OT",572.88,"AUD","Generation storm response- refueling","AFRU","SYS_BCBATCH",10001200,"","",{"$f":"VLOOKUP(U663,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-07-15","2021-07-15","4","2022","1100","309479987","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810222","Corp Prof Exp OT",608.69000000000005,"AUD","Generation storm response","AFRU","SYS_BCBATCH",10001200,"","",{"$f":"VLOOKUP(U664,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-07-21","2021-07-21","4","2022","1100","309488947","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810123","Corp Prof NT",645.53,"AUD","","AFRU","SYS_BCBATCH",10002501,"","",{"$f":"VLOOKUP(U665,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-07-21","2021-07-21","4","2022","1100","309488948","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810123","Corp Prof NT",645.53,"AUD","","AFRU","SYS_BCBATCH",10002501,"","",{"$f":"VLOOKUP(U666,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-07-21","2021-07-21","4","2022","1100","309488949","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810123","Corp Prof NT",645.53,"AUD","","AFRU","SYS_BCBATCH",10002501,"","",{"$f":"VLOOKUP(U667,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-07-21","2021-07-21","4","2022","1100","309488950","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810123","Corp Prof NT",645.53,"AUD","","AFRU","SYS_BCBATCH",10002501,"","",{"$f":"VLOOKUP(U668,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-07-21","2021-07-21","4","2022","1100","309488951","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810123","Corp Prof NT",645.53,"AUD","","AFRU","SYS_BCBATCH",10002501,"","",{"$f":"VLOOKUP(U669,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-07-21","2021-07-21","4","2022","1100","309488952","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810123","Corp Prof NT",645.53,"AUD","","AFRU","SYS_BCBATCH",10002501,"","",{"$f":"VLOOKUP(U670,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-07-21","2021-07-21","4","2022","1100","309488953","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810123","Corp Prof NT",645.53,"AUD","","AFRU","SYS_BCBATCH",10002501,"","",{"$f":"VLOOKUP(U671,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-07-21","2021-07-21","4","2022","1100","309488954","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810123","Corp Prof NT",645.53,"AUD","","AFRU","SYS_BCBATCH",10002501,"","",{"$f":"VLOOKUP(U672,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-07-21","2021-07-21","4","2022","1100","309488955","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810123","Corp Prof NT",645.53,"AUD","","AFRU","SYS_BCBATCH",10002501,"","",{"$f":"VLOOKUP(U673,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-07-21","2021-07-21","4","2022","1100","309488956","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810123","Corp Prof NT",645.53,"AUD","","AFRU","SYS_BCBATCH",10002501,"","",{"$f":"VLOOKUP(U674,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-07-21","2021-07-21","4","2022","1100","309488957","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810123","Corp Prof NT",645.53,"AUD","","AFRU","SYS_BCBATCH",10002501,"","",{"$f":"VLOOKUP(U675,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-07-21","2021-07-21","4","2022","1100","309488958","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810123","Corp Prof NT",645.53,"AUD","","AFRU","SYS_BCBATCH",10002501,"","",{"$f":"VLOOKUP(U676,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-07-23","2021-07-23","4","2022","1100","309499376","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810243","Corp Support OT",405.45,"AUD","Worked Sat- Storm Claims from 8.00am to","AFRU","SYS_BCBATCH",10004950,"","",{"$f":"VLOOKUP(U677,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["RMRU","RKL","2021-07-23","2021-07-23","4","2022","1100","309499377","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810243","Corp Support OT",486.54,"AUD","Worked Sat- Storm Event from 7.30am to 1","AFRU","SYS_BCBATCH",10004950,"","",{"$f":"VLOOKUP(U678,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["RMRU","RKL","2021-07-23","2021-07-23","4","2022","1100","309499378","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810243","Corp Support OT",243.27,"AUD","","AFRU","SYS_BCBATCH",10007951,"","",{"$f":"VLOOKUP(U679,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["RMRU","RKL","2021-07-23","2021-07-23","4","2022","1100","309499379","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810243","Corp Support OT",729.81,"AUD","","AFRU","SYS_BCBATCH",10007951,"","",{"$f":"VLOOKUP(U680,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["RMRU","RKL","2021-07-23","2021-07-23","4","2022","1100","309499380","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810243","Corp Support OT",729.81,"AUD","","AFRU","SYS_BCBATCH",10007951,"","",{"$f":"VLOOKUP(U681,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["RMRU","RKL","2021-07-23","2021-07-23","4","2022","1100","309499381","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810243","Corp Support OT",446,"AUD","","AFRU","SYS_BCBATCH",10007951,"","",{"$f":"VLOOKUP(U682,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["RMRU","RKL","2021-07-23","2021-07-23","4","2022","1100","309499382","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810243","Corp Support OT",445.15,"AUD","OT for storm related claims","AFRU","SYS_BCBATCH",10000829,"","",{"$f":"VLOOKUP(U683,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["RMRU","RKL","2021-07-23","2021-07-23","4","2022","1100","309499383","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810243","Corp Support OT",445.15,"AUD","OT for storm claims","AFRU","SYS_BCBATCH",10000829,"","",{"$f":"VLOOKUP(U684,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["RMRU","RKL","2021-07-23","2021-07-23","4","2022","1100","309499384","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810243","Corp Support OT",445.15,"AUD","OT for storm claims","AFRU","SYS_BCBATCH",10000829,"","",{"$f":"VLOOKUP(U685,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["RMRU","RKL","2021-07-23","2021-07-23","4","2022","1100","309499385","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810243","Corp Support OT",445.15,"AUD","OT for storm claims","AFRU","SYS_BCBATCH",10000829,"","",{"$f":"VLOOKUP(U686,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["RMRU","RKL","2021-07-23","2021-07-23","4","2022","1100","309499386","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810243","Corp Support OT",445.15,"AUD","OT for storm claims","AFRU","SYS_BCBATCH",10000829,"","",{"$f":"VLOOKUP(U687,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["RMRU","RKL","2021-07-23","2021-07-23","4","2022","1100","309499387","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810243","Corp Support OT",527.09,"AUD","Worked on Saturday 17.7.21, from 7.30am","AFRU","SYS_BCBATCH",10004950,"","",{"$f":"VLOOKUP(U688,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["RMRU","RKL","2021-07-23","2021-07-23","4","2022","1100","309499388","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810243","Corp Support OT",356.12,"AUD","OT due to storm event","AFRU","SYS_BCBATCH",10000829,"","",{"$f":"VLOOKUP(U689,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["RMRU","RKL","2021-07-23","2021-07-23","4","2022","1100","309499389","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810243","Corp Support OT",445.15,"AUD","OT due to storms","AFRU","SYS_BCBATCH",10000829,"","",{"$f":"VLOOKUP(U690,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["RMRU","RKL","2021-07-23","2021-07-23","4","2022","1100","309499390","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810243","Corp Support OT",567.63,"AUD","","AFRU","SYS_BCBATCH",10007951,"","",{"$f":"VLOOKUP(U691,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["RMRU","RKL","2021-07-26","2021-07-26","4","2022","1100","309501019","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810243","Corp Support OT",405.45,"AUD","Worked Saturday from 8.00am to 1.00pm- 5","AFRU","SYS_BCBATCH",10004950,"","",{"$f":"VLOOKUP(U692,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["RMRU","RKL","2021-07-26","2021-07-26","4","2022","1100","309501020","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810243","Corp Support OT",405.45,"AUD","Worked Sunday from 8.00am to 1.00pm- 5 h","AFRU","SYS_BCBATCH",10004950,"","",{"$f":"VLOOKUP(U693,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["RMRU","RKL","2021-07-26","2021-07-26","4","2022","1100","309501624","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810243","Corp Support OT",289.68,"AUD","faults OT","AFRU","SYS_BCBATCH",10006935,"","",{"$f":"VLOOKUP(U694,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["RMRU","RKL","2021-07-28","2021-07-28","4","2022","1100","309504213","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810243","Corp Support OT",364.91,"AUD","","AFRU","SYS_BCBATCH",10007951,"","",{"$f":"VLOOKUP(U695,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["RMRU","RKL","2021-07-28","2021-07-28","4","2022","1100","309504214","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810123","Corp Prof NT",676.05,"AUD","","AFRU","SYS_BCBATCH",10001121,"","",{"$f":"VLOOKUP(U696,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-07-29","2021-07-29","4","2022","1100","309506220","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810122","Corp Prof Exp NT",716.1,"AUD","","AFRU","SYS_BCBATCH",10001200,"","",{"$f":"VLOOKUP(U697,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-08-02","2021-08-02","5","2022","1100","309574242","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810141","Corp Snr Mngr NT",1420.5,"AUD","","AFRU","SYS_BCBATCH",10010076,"","",{"$f":"VLOOKUP(U698,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["RMRU","RKL","2021-08-02","2021-08-02","5","2022","1100","309574243","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810141","Corp Snr Mngr NT",1420.5,"AUD","","AFRU","SYS_BCBATCH",10010076,"","",{"$f":"VLOOKUP(U699,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["RMRU","RKL","2021-08-02","2021-08-02","5","2022","1100","309574246","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810243","Corp Support OT",534.17999999999995,"AUD","Storm related claims","AFRU","SYS_BCBATCH",10000829,"","",{"$f":"VLOOKUP(U700,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["RMRU","RKL","2021-08-02","2021-08-02","5","2022","1100","309574247","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810243","Corp Support OT",486.54,"AUD","Worked Saturday- from 7.00am to 1.00pm-","AFRU","SYS_BCBATCH",10004950,"","",{"$f":"VLOOKUP(U701,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["RMRU","RKL","2021-08-02","2021-08-02","5","2022","1100","309574248","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810243","Corp Support OT",446,"AUD","Worked Sunday- 8.00am to 1.30pm - (5.5ho","AFRU","SYS_BCBATCH",10004950,"","",{"$f":"VLOOKUP(U702,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["RMRU","RKL","2021-08-02","2021-08-02","5","2022","1100","309574249","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810243","Corp Support OT",729.81,"AUD","","AFRU","SYS_BCBATCH",10007951,"","",{"$f":"VLOOKUP(U703,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["RMRU","RKL","2021-08-20","2021-08-20","5","2022","1100","309598130","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810241","Corp Snr Mngr OT",213.08,"AUD","Storm -2021- Time Sheet - 12014","AFRU","SYS_BCBATCH",10007022,"","",{"$f":"VLOOKUP(U704,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["RMRU","RKL","2021-08-20","2021-08-20","5","2022","1100","309598131","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810241","Corp Snr Mngr OT",1278.48,"AUD","","AFRU","SYS_BCBATCH",10000711,"","",{"$f":"VLOOKUP(U705,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"YES"},"Include","Internal"]
["RMRU","RKL","2021-08-20","2021-08-20","5","2022","1100","309598132","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810241","Corp Snr Mngr OT",1278.48,"AUD","","AFRU","SYS_BCBATCH",10000711,"","",{"$f":"VLOOKUP(U706,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"YES"},"Include","Internal"]
["RMRU","RKL","2021-08-20","2021-08-20","5","2022","1100","309598133","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810241","Corp Snr Mngr OT",1065.4000000000001,"AUD","","AFRU","SYS_BCBATCH",10000711,"","",{"$f":"VLOOKUP(U707,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"YES"},"Include","Internal"]
["RMRU","RKL","2021-08-20","2021-08-20","5","2022","1100","309598134","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810241","Corp Snr Mngr OT",1278.48,"AUD","","AFRU","SYS_BCBATCH",10000711,"","",{"$f":"VLOOKUP(U708,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"YES"},"Include","Internal"]
["RMRU","RKL","2021-08-20","2021-08-20","5","2022","1100","309603157","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810143","Corp Support NT",178.05,"AUD","","AFRU","SYS_BCBATCH",10001773,"","",{"$f":"VLOOKUP(U709,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["RMRU","RKL","2021-08-20","2021-08-20","5","2022","1100","309603158","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810143","Corp Support NT",89.03,"AUD","","AFRU","SYS_BCBATCH",10001773,"","",{"$f":"VLOOKUP(U710,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["RMRU","RKL","2021-08-20","2021-08-20","5","2022","1100","309603159","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810143","Corp Support NT",89.03,"AUD","","AFRU","SYS_BCBATCH",10001773,"","",{"$f":"VLOOKUP(U711,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["RMRU","RKL","2021-08-20","2021-08-20","5","2022","1100","309603160","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810143","Corp Support NT",89.03,"AUD","","AFRU","SYS_BCBATCH",10001773,"","",{"$f":"VLOOKUP(U712,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["RMRU","RKL","2021-08-20","2021-08-20","5","2022","1100","309603161","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810143","Corp Support NT",59.35,"AUD","","AFRU","SYS_BCBATCH",10001773,"","",{"$f":"VLOOKUP(U713,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["RMRU","RKL","2021-08-20","2021-08-20","5","2022","1100","309603162","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810143","Corp Support NT",59.35,"AUD","","AFRU","SYS_BCBATCH",10001773,"","",{"$f":"VLOOKUP(U714,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["RMRU","RKL","2021-08-20","2021-08-20","5","2022","1100","309603163","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810143","Corp Support NT",59.35,"AUD","","AFRU","SYS_BCBATCH",10001773,"","",{"$f":"VLOOKUP(U715,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["RMRU","RKL","2021-08-20","2021-08-20","5","2022","1100","309603164","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810143","Corp Support NT",29.68,"AUD","","AFRU","SYS_BCBATCH",10001773,"","",{"$f":"VLOOKUP(U716,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["RMRU","RKL","2021-08-20","2021-08-20","5","2022","1100","309603165","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810143","Corp Support NT",59.35,"AUD","","AFRU","SYS_BCBATCH",10001773,"","",{"$f":"VLOOKUP(U717,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["RMRU","RKL","2021-08-20","2021-08-20","5","2022","1100","309603166","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810143","Corp Support NT",29.68,"AUD","","AFRU","SYS_BCBATCH",10001773,"","",{"$f":"VLOOKUP(U718,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["RMRU","RKL","2021-08-20","2021-08-20","5","2022","1100","309603167","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810143","Corp Support NT",118.7,"AUD","","AFRU","SYS_BCBATCH",10001773,"","",{"$f":"VLOOKUP(U719,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["RMRU","RKL","2021-08-20","2021-08-20","5","2022","1100","309603168","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810143","Corp Support NT",118.7,"AUD","","AFRU","SYS_BCBATCH",10001773,"","",{"$f":"VLOOKUP(U720,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["RMRU","RKL","2021-08-20","2021-08-20","5","2022","1100","309603169","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810143","Corp Support NT",29.68,"AUD","","AFRU","SYS_BCBATCH",10001773,"","",{"$f":"VLOOKUP(U721,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["RMRU","RKL","2021-08-24","2021-08-24","5","2022","1100","309606003","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810243","Corp Support OT",178.06,"AUD","","AFRU","SYS_BCBATCH",10001773,"","",{"$f":"VLOOKUP(U722,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["RMRU","RKL","2021-08-24","2021-08-24","5","2022","1100","309606004","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810243","Corp Support OT",178.06,"AUD","","AFRU","SYS_BCBATCH",10001773,"","",{"$f":"VLOOKUP(U723,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["RMRU","RKL","2021-08-24","2021-08-24","5","2022","1100","309606005","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810243","Corp Support OT",178.06,"AUD","","AFRU","SYS_BCBATCH",10001773,"","",{"$f":"VLOOKUP(U724,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["RMRU","RKL","2021-08-24","2021-08-24","5","2022","1100","309606006","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810243","Corp Support OT",178.06,"AUD","","AFRU","SYS_BCBATCH",10001773,"","",{"$f":"VLOOKUP(U725,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["RMRU","RKL","2021-08-24","2021-08-24","5","2022","1100","309606007","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810243","Corp Support OT",178.06,"AUD","","AFRU","SYS_BCBATCH",10001773,"","",{"$f":"VLOOKUP(U726,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["RMRU","RKL","2021-08-24","2021-08-24","5","2022","1100","309606008","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810243","Corp Support OT",178.06,"AUD","","AFRU","SYS_BCBATCH",10001773,"","",{"$f":"VLOOKUP(U727,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["RMRU","RKL","2021-08-24","2021-08-24","5","2022","1100","309606009","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810243","Corp Support OT",178.06,"AUD","","AFRU","SYS_BCBATCH",10001773,"","",{"$f":"VLOOKUP(U728,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["RMRU","RKL","2021-08-24","2021-08-24","5","2022","1100","309606010","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810243","Corp Support OT",89.03,"AUD","","AFRU","SYS_BCBATCH",10001773,"","",{"$f":"VLOOKUP(U729,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["RMRU","RKL","2021-08-24","2021-08-24","5","2022","1100","309606011","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810243","Corp Support OT",89.03,"AUD","","AFRU","SYS_BCBATCH",10001773,"","",{"$f":"VLOOKUP(U730,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["RMRU","RKL","2021-08-24","2021-08-24","5","2022","1100","309606012","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810243","Corp Support OT",89.03,"AUD","","AFRU","SYS_BCBATCH",10001773,"","",{"$f":"VLOOKUP(U731,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["RMRU","RKL","2021-08-24","2021-08-24","5","2022","1100","309606013","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810243","Corp Support OT",89.03,"AUD","","AFRU","SYS_BCBATCH",10001773,"","",{"$f":"VLOOKUP(U732,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["RMRU","RKL","2021-08-24","2021-08-24","5","2022","1100","309606014","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810243","Corp Support OT",89.03,"AUD","","AFRU","SYS_BCBATCH",10001773,"","",{"$f":"VLOOKUP(U733,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["RMRU","RKL","2021-08-24","2021-08-24","5","2022","1100","309606015","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810243","Corp Support OT",178.06,"AUD","","AFRU","SYS_BCBATCH",10001773,"","",{"$f":"VLOOKUP(U734,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["RMRU","RKL","2021-08-24","2021-08-24","5","2022","1100","309606016","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810243","Corp Support OT",89.03,"AUD","","AFRU","SYS_BCBATCH",10001773,"","",{"$f":"VLOOKUP(U735,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["RMRU","RKL","2021-08-24","2021-08-24","5","2022","1100","309606017","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810243","Corp Support OT",89.03,"AUD","","AFRU","SYS_BCBATCH",10001773,"","",{"$f":"VLOOKUP(U736,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["RMRU","RKL","2021-08-24","2021-08-24","5","2022","1100","309606018","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810243","Corp Support OT",89.03,"AUD","","AFRU","SYS_BCBATCH",10001773,"","",{"$f":"VLOOKUP(U737,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["RMRU","RKL","2021-08-24","2021-08-24","5","2022","1100","309606019","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810243","Corp Support OT",89.03,"AUD","","AFRU","SYS_BCBATCH",10001773,"","",{"$f":"VLOOKUP(U738,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["RMRU","RKL","2021-08-24","2021-08-24","5","2022","1100","309606020","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810243","Corp Support OT",178.06,"AUD","","AFRU","SYS_BCBATCH",10001773,"","",{"$f":"VLOOKUP(U739,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["RMRU","RKL","2021-08-24","2021-08-24","5","2022","1100","309606021","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810243","Corp Support OT",89.03,"AUD","","AFRU","SYS_BCBATCH",10001773,"","",{"$f":"VLOOKUP(U740,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["RMRU","RKL","2021-08-24","2021-08-24","5","2022","1100","309606022","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810243","Corp Support OT",178.06,"AUD","","AFRU","SYS_BCBATCH",10001773,"","",{"$f":"VLOOKUP(U741,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["RMRU","RKL","2021-08-24","2021-08-24","5","2022","1100","309606023","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810243","Corp Support OT",178.06,"AUD","","AFRU","SYS_BCBATCH",10001773,"","",{"$f":"VLOOKUP(U742,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["RMRU","RKL","2021-08-24","2021-08-24","5","2022","1100","309606024","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810243","Corp Support OT",178.06,"AUD","","AFRU","SYS_BCBATCH",10001773,"","",{"$f":"VLOOKUP(U743,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["","RKL","2021-06-10","2021-09-08","6","2022","1100","309718095","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810300","Allowance Expenses",76.23,"AUD","","CATS","SYS_BCBATCH",10001047,"","",{"$f":"VLOOKUP(U744,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["","RKL","2021-06-10","2021-09-08","6","2022","1100","309718095","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810300","Allowance Expenses",12.32,"AUD","","CATS","SYS_BCBATCH",10001047,"","",{"$f":"VLOOKUP(U745,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-09-08","2021-09-08","6","2022","1100","309719916","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810241","Corp Snr Mngr OT",1092.02,"AUD","","AFRU","SYS_BCBATCH",10001047,"","",{"$f":"VLOOKUP(U746,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-09-08","2021-09-08","6","2022","1100","309719917","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810241","Corp Snr Mngr OT",1092.02,"AUD","","AFRU","SYS_BCBATCH",10001047,"","",{"$f":"VLOOKUP(U747,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-09-08","2021-09-08","6","2022","1100","309719918","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810241","Corp Snr Mngr OT",3154.71,"AUD","","AFRU","SYS_BCBATCH",10001047,"","",{"$f":"VLOOKUP(U748,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-09-08","2021-09-08","6","2022","1100","309719919","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810241","Corp Snr Mngr OT",3154.71,"AUD","","AFRU","SYS_BCBATCH",10001047,"","",{"$f":"VLOOKUP(U749,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-09-08","2021-09-08","6","2022","1100","309719920","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810241","Corp Snr Mngr OT",728.01,"AUD","","AFRU","SYS_BCBATCH",10001047,"","",{"$f":"VLOOKUP(U750,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-09-08","2021-09-08","6","2022","1100","309719921","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810241","Corp Snr Mngr OT",485.34,"AUD","","AFRU","SYS_BCBATCH",10001047,"","",{"$f":"VLOOKUP(U751,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-09-08","2021-09-08","6","2022","1100","309719922","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810241","Corp Snr Mngr OT",606.67999999999995,"AUD","","AFRU","SYS_BCBATCH",10001047,"","",{"$f":"VLOOKUP(U752,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-09-08","2021-09-08","6","2022","1100","309719923","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810241","Corp Snr Mngr OT",606.67999999999995,"AUD","","AFRU","SYS_BCBATCH",10001047,"","",{"$f":"VLOOKUP(U753,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-09-08","2021-09-08","6","2022","1100","309719924","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810241","Corp Snr Mngr OT",849.35,"AUD","","AFRU","SYS_BCBATCH",10001047,"","",{"$f":"VLOOKUP(U754,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-09-08","2021-09-08","6","2022","1100","309719925","","","NWA","4010246 0010","Storm -2021- Time Sheet - 12014","810241","Corp Snr Mngr OT",970.68,"AUD","","AFRU","SYS_BCBATCH",10001047,"","",{"$f":"VLOOKUP(U755,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["","",null,null,"","","","","","","","4010246 0010","","","",1078478.56,"AUD","","","",null,"",""]
["RFBU","COIN","2021-09-29","2021-09-29","6","2022","1100","108504132","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","516413","Light Meals on Site",18.18,"AUD","EEXP Julie Warke Operator 25","BKPFF","WF-BATCH",0,"","SA",null,"Include","Internal"]
["RFBU","COIN","2021-09-29","2021-09-29","6","2022","1100","108504132","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","516413","Light Meals on Site",60.9,"AUD","EEXP Julie Warke Crust Pizza Richmond","BKPFF","WF-BATCH",0,"","SA",null,"Include","Internal"]
["RFBU","COIN","2021-09-29","2021-09-29","6","2022","1100","108504132","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","516413","Light Meals on Site",163.55000000000001,"AUD","EEXP Julie Warke +39 Pizzeria","BKPFF","WF-BATCH",0,"","SA",null,"Include","Internal"]
["RFBU","COIN","2021-09-29","2021-09-29","6","2022","1100","108504132","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","516413","Light Meals on Site",69.400000000000006,"AUD","EEXP Julie Warke The Eatery - Sir Schnitzel","BKPFF","WF-BATCH",0,"","SA",null,"Include","Internal"]
["RFBU","COIN","2021-09-29","2021-09-29","6","2022","1100","108504132","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","516413","Light Meals on Site",3203.46,"AUD","EEXP James Weghorn Balance of COSTCO payment of st","BKPFF","WF-BATCH",0,"","SA",null,"Include","Internal"]
["RFBU","COIN","2021-09-29","2021-09-29","6","2022","1100","108504132","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","516413","Light Meals on Site",48.91,"AUD","EEXP Julie Warke Laurent Bakery","BKPFF","WF-BATCH",0,"","SA",null,"Include","Internal"]
["RFBU","COIN","2021-09-29","2021-09-29","6","2022","1100","108504132","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","516413","Light Meals on Site",74.08,"AUD","EEXP Julie Warke McDonalds","BKPFF","WF-BATCH",0,"","SA",null,"Include","Internal"]
["RFBU","COIN","2021-09-29","2021-09-29","6","2022","1100","108504132","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","516413","Light Meals on Site",150.91,"AUD","EEXP Julie Warke Crust Pizza Melbourne","BKPFF","WF-BATCH",0,"","SA",null,"Include","Internal"]
["RFBU","COIN","2021-09-29","2021-09-29","6","2022","1100","108504132","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","516413","Light Meals on Site",79.73,"AUD","EEXP Julie Warke Grill'd Richmond","BKPFF","WF-BATCH",0,"","SA",null,"Include","Internal"]
["RFBU","COIN","2021-09-29","2021-09-29","6","2022","1100","108504132","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","516413","Light Meals on Site",232.55,"AUD","EEXP Julie Warke +39 Pizzeria","BKPFF","WF-BATCH",0,"","SA",null,"Include","Internal"]
["RFBU","COIN","2021-09-29","2021-09-29","6","2022","1100","108504132","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","521402","MV - Maintenance",13.18,"AUD","EEXP Paul Kempton Carwash","BKPFF","WF-BATCH",0,"","SA",null,"Include","Internal"]
["RFBU","COIN","2021-09-29","2021-09-29","6","2022","1100","108504132","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","521505","Vehicle Parking",29.09,"AUD","EEXP Peter Galey Parking for escalation","BKPFF","WF-BATCH",0,"","SA",null,"Include","Internal"]
["RFBU","COIN","2021-09-29","2021-09-29","6","2022","1100","108504132","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","521505","Vehicle Parking",104.55,"AUD","EEXP Peter Galey Parking 452 Flinders","BKPFF","WF-BATCH",0,"","SA",null,"Include","Internal"]
["RFBU","COIN","2021-09-29","2021-09-29","6","2022","1100","108504132","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","521505","Vehicle Parking",77.27,"AUD","EEXP David Rofe Car Parking EMT Admin","BKPFF","WF-BATCH",0,"","SA",null,"Include","Internal"]
["RFBU","COIN","2021-09-29","2021-09-29","6","2022","1100","108504132","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","506701","Reward & Recognition",-383.27,"AUD","PCARD Johnny Mangala Refund for EMTLunch-Was close","BKPFF","WF-BATCH",0,"","SA",null,"Include","Internal"]
["RFBU","COIN","2021-09-29","2021-09-29","6","2022","1100","108504132","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","506701","Reward & Recognition",383.27,"AUD","PCARD Johnny Mangala EMT Lunch but will be refunde","BKPFF","WF-BATCH",0,"","SA",null,"Include","Internal"]
["RFBU","COIN","2021-09-29","2021-09-29","6","2022","1100","108504132","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","506701","Reward & Recognition",24.72,"AUD","PCARD Johnny Mangala Food for EMT (Jo P)","BKPFF","WF-BATCH",0,"","SA",null,"Include","Internal"]
["RFBU","COIN","2021-09-29","2021-09-29","6","2022","1100","108504132","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","511104","Svc Prov - Labour",360,"AUD","PCARD David Green Connect Generator LGA Depot","BKPFF","WF-BATCH",0,"","SA",null,"Include","Internal"]
["RFBU","COIN","2021-09-29","2021-09-29","6","2022","1100","108504132","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","516102","IT Hardware",72.64,"AUD","PCARD Dannie Ploegmakers Earpods & HDMI cables","BKPFF","WF-BATCH",0,"","SA",null,"Include","Internal"]
["RFBU","COIN","2021-09-29","2021-09-29","6","2022","1100","108504132","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","516103","Comms Charges",164,"AUD","PCARD Gareth Downes New charger for sat phone","BKPFF","WF-BATCH",0,"","SA",null,"Include","Internal"]
["RFBU","COIN","2021-09-29","2021-09-29","6","2022","1100","108504132","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","516105","Phones & Pagers",176.36,"AUD","PCARD Dannie Ploegmakers Earpods & HDMI cables","BKPFF","WF-BATCH",0,"","SA",null,"Include","Internal"]
["RFBU","COIN","2021-09-29","2021-09-29","6","2022","1100","108504132","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","516105","Phones & Pagers",53,"AUD","PCARD Gareth Downes New charger for sat phone","BKPFF","WF-BATCH",0,"","SA",null,"Include","Internal"]
["RFBU","COIN","2021-09-29","2021-09-29","6","2022","1100","108504132","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","521100","Materials",133.59,"AUD","PCARD Nicholas Hewes Straps","BKPFF","WF-BATCH",0,"","SA",null,"Include","Internal"]
["RFBU","COIN","2021-09-29","2021-09-29","6","2022","1100","108504132","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","521100","Materials",600,"AUD","PCARD Nicholas Hewes Gen Tags & Defib Sticker","BKPFF","WF-BATCH",0,"","SA",null,"Include","Internal"]
["RFBU","COIN","2021-09-29","2021-09-29","6","2022","1100","108504132","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","521100","Materials",54.55,"AUD","PCARD Alanna Pollock Supplies for Recovery Hubs","BKPFF","WF-BATCH",0,"","SA",null,"Include","Internal"]
["RFBU","COIN","2021-09-29","2021-09-29","6","2022","1100","108504132","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","521400","MV & Plant - Fuel",34.6,"AUD","PCARD Alanna Pollock Fuel to attend recovery hubs","BKPFF","WF-BATCH",0,"","SA",null,"Include","Internal"]
["RFBU","COIN","2021-09-29","2021-09-29","6","2022","1100","108504132","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","521402","MV - Maintenance",256.36,"AUD","PCARD Scott Harvey battery Rep during storm event","BKPFF","WF-BATCH",0,"","SA",null,"Include","Internal"]
["RFBU","COIN","2021-09-29","2021-09-29","6","2022","1100","108504132","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","521506","Transportation",45.12,"AUD","PCARD Dannie Ploegmakers Parking accommodation","BKPFF","WF-BATCH",0,"","SA",null,"Include","Internal"]
["RFBU","COIN","2021-09-29","2021-09-29","6","2022","1100","108504132","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","521507","Travel",13.88,"AUD","PCARD Dannie Ploegmakers Laundry detergent - Storm","BKPFF","WF-BATCH",0,"","SA",null,"Include","Internal"]
["RFBU","COIN","2021-09-29","2021-09-29","6","2022","1100","108504132","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","521508","Accommodation",16.36,"AUD","PCARD Brian Brann B Brann evening meal LDL storm","BKPFF","WF-BATCH",0,"","SA",null,"Include","Internal"]
["RFBU","COIN","2021-09-29","2021-09-29","6","2022","1100","108504132","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","521508","Accommodation",13.64,"AUD","PCARD Brian Brann B Brann lunch LDL storms","BKPFF","WF-BATCH",0,"","SA",null,"Include","Internal"]
["RFBU","COIN","2021-09-29","2021-09-29","6","2022","1100","108504137","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","521508","Accommodation",-304.69,"AUD","PCARD Dannie Ploegmakers Accom expenses - Cancelle","BKPFF","WF-BATCH",0,"","SA",null,"Include","Internal"]
["RFBU","COIN","2021-09-29","2021-09-29","6","2022","1100","108504137","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","521508","Accommodation",96.59,"AUD","PCARD Dannie Ploegmakers Dinner storm response","BKPFF","WF-BATCH",0,"","SA",null,"Include","Internal"]
["RFBU","COIN","2021-09-29","2021-09-29","6","2022","1100","108504137","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","521508","Accommodation",28.18,"AUD","PCARD Dannie Ploegmakers Bfast storm response","BKPFF","WF-BATCH",0,"","SA",null,"Include","Internal"]
["RFBU","COIN","2021-09-29","2021-09-29","6","2022","1100","108504137","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","516405","Public relations",21.82,"AUD","EEXP Mark Lambert Storm Supplies","BKPFF","WF-BATCH",0,"","SA",null,"Include","Internal"]
["RFBU","COIN","2021-09-29","2021-09-29","6","2022","1100","108504137","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","516405","Public relations",90.45,"AUD","EEXP Mark Lambert Storm Supplies for Relief Centre","BKPFF","WF-BATCH",0,"","SA",null,"Include","Internal"]
["RFBU","COIN","2021-09-29","2021-09-29","6","2022","1100","108504137","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","516405","Public relations",36.450000000000003,"AUD","EEXP Mark Lambert Storm Supplies to relief centre","BKPFF","WF-BATCH",0,"","SA",null,"Include","Internal"]
["RFBU","COIN","2021-09-29","2021-09-29","6","2022","1100","108504137","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","516405","Public relations",129.80000000000001,"AUD","EEXP Mark Lambert Supplies for Storm Relief Centre","BKPFF","WF-BATCH",0,"","SA",null,"Include","Internal"]
["RFBU","COIN","2021-09-29","2021-09-29","6","2022","1100","108504137","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","521400","MV & Plant - Fuel",68.319999999999993,"AUD","EEXP Mark Lambert Fuel for Storm Support","BKPFF","WF-BATCH",0,"","SA",null,"Include","Internal"]
["RFBU","COIN","2021-09-29","2021-09-29","6","2022","1100","108504137","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","521400","MV & Plant - Fuel",85.17,"AUD","EEXP Mark Lambert Fuel for Storm Relief","BKPFF","WF-BATCH",0,"","SA",null,"Include","Internal"]
["RFBU","COIN","2021-09-29","2021-09-29","6","2022","1100","108504137","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","516413","Light Meals on Site",623.54999999999995,"AUD","PCARD James Radalj Meals / Food at SCC during sto","BKPFF","WF-BATCH",0,"","SA",null,"Include","Internal"]
["RFBU","COIN","2021-09-29","2021-09-29","6","2022","1100","108504137","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","516413","Light Meals on Site",955.64,"AUD","PCARD James Radalj Meals / Food for EMT during st","BKPFF","WF-BATCH",0,"","SA",null,"Include","Internal"]
["RFBU","COIN","2021-09-29","2021-09-29","6","2022","1100","108504137","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","521100","Materials",204,"AUD","PCARD Gareth Downes Replacement signs damaged duri","BKPFF","WF-BATCH",0,"","SA",null,"Include","Internal"]
["RFBU","COIN","2021-09-29","2021-09-29","6","2022","1100","108504137","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","521505","Vehicle Parking",245.45,"AUD","PCARD James Radalj Parking at SCC for EMLO","BKPFF","WF-BATCH",0,"","SA",null,"Include","Internal"]
["RFBU","COIN","2021-09-29","2021-09-29","6","2022","1100","108504137","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","521505","Vehicle Parking",18.18,"AUD","PCARD James Radalj James.L.Hunter@police.vic.gov.","BKPFF","WF-BATCH",0,"","SA",null,"Include","Internal"]
["RFBU","COIN","2021-09-29","2021-09-29","6","2022","1100","108504137","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","521505","Vehicle Parking",18.18,"AUD","PCARD James Radalj Parking at SCC for EMLO","BKPFF","WF-BATCH",0,"","SA",null,"Include","Internal"]
["RFBU","COIN","2021-09-29","2021-09-29","6","2022","1100","108504143","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","521508","Accommodation",1033.6400000000001,"AUD","PCARD Dannie Ploegmakers Accom storm response","BKPFF","WF-BATCH",0,"","SA",null,"Include","Internal"]
["RFBU","COIN","2021-09-29","2021-09-29","6","2022","1100","108504143","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","516413","Light Meals on Site",-20,"AUD","EEXP Julie Warke Operator 25","BKPFF","WF-BATCH",0,"","SA",null,"Include","Internal"]
["RFBU","COIN","2021-09-29","2021-09-29","6","2022","1100","108504143","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","516413","Light Meals on Site",-66.989999999999995,"AUD","EEXP Julie Warke Crust Pizza Richmond","BKPFF","WF-BATCH",0,"","SA",null,"Include","Internal"]
["RFBU","COIN","2021-09-29","2021-09-29","6","2022","1100","108504143","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","516413","Light Meals on Site",-179.9,"AUD","EEXP Julie Warke +39 Pizzeria","BKPFF","WF-BATCH",0,"","SA",null,"Include","Internal"]
["RFBU","COIN","2021-09-29","2021-09-29","6","2022","1100","108504143","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","516413","Light Meals on Site",-76.34,"AUD","EEXP Julie Warke The Eatery - Sir Schnitzel","BKPFF","WF-BATCH",0,"","SA",null,"Include","Internal"]
["RFBU","COIN","2021-09-29","2021-09-29","6","2022","1100","108504143","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","516413","Light Meals on Site",-3523.81,"AUD","EEXP James Weghorn Balance of COSTCO payment of st","BKPFF","WF-BATCH",0,"","SA",null,"Include","Internal"]
["RFBU","COIN","2021-09-29","2021-09-29","6","2022","1100","108504143","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","516413","Light Meals on Site",-53.8,"AUD","EEXP Julie Warke Laurent Bakery","BKPFF","WF-BATCH",0,"","SA",null,"Include","Internal"]
["RFBU","COIN","2021-09-29","2021-09-29","6","2022","1100","108504143","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","516413","Light Meals on Site",-81.489999999999995,"AUD","EEXP Julie Warke McDonalds","BKPFF","WF-BATCH",0,"","SA",null,"Include","Internal"]
["RFBU","COIN","2021-09-29","2021-09-29","6","2022","1100","108504147","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","516413","Light Meals on Site",-166,"AUD","EEXP Julie Warke Crust Pizza Melbourne","BKPFF","WF-BATCH",0,"","SA",null,"Include","Internal"]
["RFBU","COIN","2021-09-29","2021-09-29","6","2022","1100","108504147","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","516413","Light Meals on Site",-87.7,"AUD","EEXP Julie Warke Grill'd Richmond","BKPFF","WF-BATCH",0,"","SA",null,"Include","Internal"]
["RFBU","COIN","2021-09-29","2021-09-29","6","2022","1100","108504147","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","516413","Light Meals on Site",-255.8,"AUD","EEXP Julie Warke +39 Pizzeria","BKPFF","WF-BATCH",0,"","SA",null,"Include","Internal"]
["RFBU","COIN","2021-09-29","2021-09-29","6","2022","1100","108504147","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","521402","MV - Maintenance",-14.5,"AUD","EEXP Paul Kempton Carwash","BKPFF","WF-BATCH",0,"","SA",null,"Include","Internal"]
["RFBU","COIN","2021-09-29","2021-09-29","6","2022","1100","108504147","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","521505","Vehicle Parking",-32,"AUD","EEXP Peter Galey Parking for escalation","BKPFF","WF-BATCH",0,"","SA",null,"Include","Internal"]
["RFBU","COIN","2021-09-29","2021-09-29","6","2022","1100","108504147","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","521505","Vehicle Parking",-115,"AUD","EEXP Peter Galey Parking 452 Flinders","BKPFF","WF-BATCH",0,"","SA",null,"Include","Internal"]
["RFBU","COIN","2021-09-29","2021-09-29","6","2022","1100","108504147","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","521505","Vehicle Parking",-85,"AUD","EEXP David Rofe Car Parking EMT Admin","BKPFF","WF-BATCH",0,"","SA",null,"Include","Internal"]
["RFBU","COIN","2021-09-29","2021-09-29","6","2022","1100","108504147","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","506701","Reward & Recognition",421.6,"AUD","PCARD Johnny Mangala Refund for EMTLunch-Was close","BKPFF","WF-BATCH",0,"","SA",null,"Include","Internal"]
["RFBU","COIN","2021-09-29","2021-09-29","6","2022","1100","108504147","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","506701","Reward & Recognition",-421.6,"AUD","PCARD Johnny Mangala EMT Lunch but will be refunde","BKPFF","WF-BATCH",0,"","SA",null,"Include","Internal"]
["RFBU","COIN","2021-09-29","2021-09-29","6","2022","1100","108504147","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","506701","Reward & Recognition",-27.19,"AUD","PCARD Johnny Mangala Food for EMT (Jo P)","BKPFF","WF-BATCH",0,"","SA",null,"Include","Internal"]
["RFBU","COIN","2021-09-29","2021-09-29","6","2022","1100","108504147","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","511104","Svc Prov - Labour",-396,"AUD","PCARD David Green Connect Generator LGA Depot","BKPFF","WF-BATCH",0,"","SA",null,"Include","Internal"]
["RFBU","COIN","2021-09-29","2021-09-29","6","2022","1100","108504147","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","516102","IT Hardware",-79.900000000000006,"AUD","PCARD Dannie Ploegmakers Earpods & HDMI cables","BKPFF","WF-BATCH",0,"","SA",null,"Include","Internal"]
["RFBU","COIN","2021-09-29","2021-09-29","6","2022","1100","108504147","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","516103","Comms Charges",-180.4,"AUD","PCARD Gareth Downes New charger for sat phone","BKPFF","WF-BATCH",0,"","SA",null,"Include","Internal"]
["RFBU","COIN","2021-09-29","2021-09-29","6","2022","1100","108504147","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","516105","Phones & Pagers",-194,"AUD","PCARD Dannie Ploegmakers Earpods & HDMI cables","BKPFF","WF-BATCH",0,"","SA",null,"Include","Internal"]
["RFBU","COIN","2021-09-29","2021-09-29","6","2022","1100","108504147","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","516105","Phones & Pagers",-58.3,"AUD","PCARD Gareth Downes New charger for sat phone","BKPFF","WF-BATCH",0,"","SA",null,"Include","Internal"]
["RFBU","COIN","2021-09-29","2021-09-29","6","2022","1100","108504147","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","521100","Materials",-146.94999999999999,"AUD","PCARD Nicholas Hewes Straps","BKPFF","WF-BATCH",0,"","SA",null,"Include","Internal"]
["RFBU","COIN","2021-09-29","2021-09-29","6","2022","1100","108504147","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","521100","Materials",-660,"AUD","PCARD Nicholas Hewes Gen Tags & Defib Sticker","BKPFF","WF-BATCH",0,"","SA",null,"Include","Internal"]
["RFBU","COIN","2021-09-29","2021-09-29","6","2022","1100","108504147","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","521100","Materials",-60,"AUD","PCARD Alanna Pollock Supplies for Recovery Hubs","BKPFF","WF-BATCH",0,"","SA",null,"Include","Internal"]
["RFBU","COIN","2021-09-29","2021-09-29","6","2022","1100","108504147","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","521400","MV & Plant - Fuel",-38.06,"AUD","PCARD Alanna Pollock Fuel to attend recovery hubs","BKPFF","WF-BATCH",0,"","SA",null,"Include","Internal"]
["RFBU","COIN","2021-09-29","2021-09-29","6","2022","1100","108504147","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","521402","MV - Maintenance",-282,"AUD","PCARD Scott Harvey battery Rep during storm event","BKPFF","WF-BATCH",0,"","SA",null,"Include","Internal"]
["RFBU","COIN","2021-09-29","2021-09-29","6","2022","1100","108504147","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","521506","Transportation",-49.63,"AUD","PCARD Dannie Ploegmakers Parking accommodation","BKPFF","WF-BATCH",0,"","SA",null,"Include","Internal"]
["RFBU","COIN","2021-09-29","2021-09-29","6","2022","1100","108504147","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","521507","Travel",-15.27,"AUD","PCARD Dannie Ploegmakers Laundry detergent - Storm","BKPFF","WF-BATCH",0,"","SA",null,"Include","Internal"]
["RFBU","COIN","2021-09-29","2021-09-29","6","2022","1100","108504147","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","521508","Accommodation",-18,"AUD","PCARD Brian Brann B Brann evening meal LDL storm","BKPFF","WF-BATCH",0,"","SA",null,"Include","Internal"]
["RFBU","COIN","2021-09-29","2021-09-29","6","2022","1100","108504147","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","521508","Accommodation",-15,"AUD","PCARD Brian Brann B Brann lunch LDL storms","BKPFF","WF-BATCH",0,"","SA",null,"Include","Internal"]
["RFBU","COIN","2021-09-29","2021-09-29","6","2022","1100","108504147","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","521508","Accommodation",335.16,"AUD","PCARD Dannie Ploegmakers Accom expenses - Cancelle","BKPFF","WF-BATCH",0,"","SA",null,"Include","Internal"]
["RFBU","COIN","2021-09-29","2021-09-29","6","2022","1100","108504147","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","521508","Accommodation",-106.25,"AUD","PCARD Dannie Ploegmakers Dinner storm response","BKPFF","WF-BATCH",0,"","SA",null,"Include","Internal"]
["RFBU","COIN","2021-09-29","2021-09-29","6","2022","1100","108504147","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","521508","Accommodation",-31,"AUD","PCARD Dannie Ploegmakers Bfast storm response","BKPFF","WF-BATCH",0,"","SA",null,"Include","Internal"]
["RFBU","COIN","2021-09-29","2021-09-29","6","2022","1100","108504153","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","516405","Public relations",-24,"AUD","EEXP Mark Lambert Storm Supplies","BKPFF","WF-BATCH",0,"","SA",null,"Include","Internal"]
["RFBU","COIN","2021-09-29","2021-09-29","6","2022","1100","108504153","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","516405","Public relations",-99.5,"AUD","EEXP Mark Lambert Storm Supplies for Relief Centre","BKPFF","WF-BATCH",0,"","SA",null,"Include","Internal"]
["RFBU","COIN","2021-09-29","2021-09-29","6","2022","1100","108504153","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","516405","Public relations",-40.090000000000003,"AUD","EEXP Mark Lambert Storm Supplies to relief centre","BKPFF","WF-BATCH",0,"","SA",null,"Include","Internal"]
["RFBU","COIN","2021-09-29","2021-09-29","6","2022","1100","108504153","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","516405","Public relations",-142.78,"AUD","EEXP Mark Lambert Supplies for Storm Relief Centre","BKPFF","WF-BATCH",0,"","SA",null,"Include","Internal"]
["RFBU","COIN","2021-09-29","2021-09-29","6","2022","1100","108504153","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","521400","MV & Plant - Fuel",-75.150000000000006,"AUD","EEXP Mark Lambert Fuel for Storm Support","BKPFF","WF-BATCH",0,"","SA",null,"Include","Internal"]
["RFBU","COIN","2021-09-29","2021-09-29","6","2022","1100","108504153","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","521400","MV & Plant - Fuel",-93.69,"AUD","EEXP Mark Lambert Fuel for Storm Relief","BKPFF","WF-BATCH",0,"","SA",null,"Include","Internal"]
["RFBU","COIN","2021-09-29","2021-09-29","6","2022","1100","108504153","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","516413","Light Meals on Site",-685.9,"AUD","PCARD James Radalj Meals / Food at SCC during sto","BKPFF","WF-BATCH",0,"","SA",null,"Include","Internal"]
["RFBU","COIN","2021-09-29","2021-09-29","6","2022","1100","108504153","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","516413","Light Meals on Site",-1051.2,"AUD","PCARD James Radalj Meals / Food for EMT during st","BKPFF","WF-BATCH",0,"","SA",null,"Include","Internal"]
["RFBU","COIN","2021-09-29","2021-09-29","6","2022","1100","108504153","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","521100","Materials",-224.4,"AUD","PCARD Gareth Downes Replacement signs damaged duri","BKPFF","WF-BATCH",0,"","SA",null,"Include","Internal"]
["RFBU","COIN","2021-09-29","2021-09-29","6","2022","1100","108504153","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","521505","Vehicle Parking",-270,"AUD","PCARD James Radalj Parking at SCC for EMLO","BKPFF","WF-BATCH",0,"","SA",null,"Include","Internal"]
["RFBU","COIN","2021-09-29","2021-09-29","6","2022","1100","108504153","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","521505","Vehicle Parking",-20,"AUD","PCARD James Radalj James.L.Hunter@police.vic.gov.","BKPFF","WF-BATCH",0,"","SA",null,"Include","Internal"]
["RFBU","COIN","2021-09-29","2021-09-29","6","2022","1100","108504153","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","521505","Vehicle Parking",-20,"AUD","PCARD James Radalj Parking at SCC for EMLO","BKPFF","WF-BATCH",0,"","SA",null,"Include","Internal"]
["RFBU","COIN","2021-09-29","2021-09-29","6","2022","1100","108504157","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","521508","Accommodation",-1137,"AUD","PCARD Dannie Ploegmakers Accom storm response","BKPFF","WF-BATCH",0,"","SA",null,"Include","Internal"]
["RFBU","COIN","2021-09-29","2021-09-29","6","2022","1100","108504311","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","511100","Svc Prov - Contracts",7320.91,"AUD","Endeavour Energy Storm Assistance Costs","BKPFF","WF-BATCH",0,"","AC",null,"Include","Internal"]
["RFBU","COIN","2021-09-29","2021-09-29","6","2022","1100","108501696","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","521517","Ombudsman Levy",136320.29999999999,"AUD","Ombudsman Storm Transfers","BKPFF","WF-BATCH",0,"","AB",null,"Include","Internal"]
["RFBU","COIN","2021-09-30","2021-09-30","6","2022","1100","108505597","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","511100","Svc Prov - Contracts",142284.49,"AUD","Downer OMSA Storm Reallocation - CEN","BKPFF","WF-BATCH",0,"","AB",null,"Include","External"]
["RFBU","COIN","2021-09-30","2021-09-30","6","2022","1100","108505597","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","511100","Svc Prov - Contracts",37556.870000000003,"AUD","Downer OMSA Storm Reallocation - EAS","BKPFF","WF-BATCH",0,"","AB",null,"Include","External"]
["RFBU","COIN","2021-09-30","2021-09-30","6","2022","1100","108505597","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","511100","Svc Prov - Contracts",5151.58,"AUD","Downer OMSA Storm Reallocation - NOR","BKPFF","WF-BATCH",0,"","AB",null,"Include","External"]
["RFBU","COIN","2021-09-30","2021-09-30","6","2022","1100","108505597","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","511100","Svc Prov - Contracts",113696.5,"AUD","Zinfra Storm Reallocation","BKPFF","WF-BATCH",0,"","AB",null,"Include","Internal"]
["RFBU","COIN","2021-09-30","2021-09-30","6","2022","1100","108505599","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","511201","Maintenance - Vegeta",23381.72,"AUD","VEG Storms - reallocation to EGM","BKPFF","WF-BATCH",0,"","AB",null,"Include","External"]
["RMWE","COIN","2021-06-17","2021-06-24","3","2022","1100","108166077","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","511202","Maintenance - Asset",415.82,"AUD","","MKPF","SJACKSON",0,"","WE",null,"Include","Internal"]
["RFBU","COIN","2021-06-25","2021-06-25","3","2022","1100","108169815","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","521601","Claims & Settlements",285129.13,"AUD","Claims (June Storm) Provision True Up - Jun 21","BKPFF","WF-BATCH",0,"","AB",null,"Include","Internal"]
["RFBU","COIN","2021-06-25","2021-06-25","3","2022","1100","108169815","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","521601","Claims & Settlements",187367.2,"AUD","Claims (June Storm) Provision True Up - Jun 21","BKPFF","WF-BATCH",0,"","AB",null,"Include","Internal"]
["RFBU","COIN","2021-06-25","2021-06-25","3","2022","1100","108169815","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","521602","Domestic Surge Claim",10273.14,"AUD","Claims (June Storm) Provision True Up - Jun 21","BKPFF","WF-BATCH",0,"","AB",null,"Include","Internal"]
["RFBU","COIN","2021-06-25","2021-06-25","3","2022","1100","108169815","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","521603","Comrcl Surge Claims",12056.8,"AUD","Claims (June Storm) Provision True Up - Jun 21","BKPFF","WF-BATCH",0,"","AB",null,"Include","Internal"]
["RFBU","COIN","2021-06-25","2021-06-25","3","2022","1100","108169815","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","521601","Claims & Settlements",34139.769999999997,"AUD","Claims (June Storm) Provision True Up - Jun 21","BKPFF","WF-BATCH",0,"","AB",null,"Include","Internal"]
["RFBU","COIN","2021-06-25","2021-06-25","3","2022","1100","108169815","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","521603","Comrcl Surge Claims",817050.41,"AUD","Claims (June Storm) Provision True Up - Jun 21","BKPFF","WF-BATCH",0,"","AB",null,"Include","Internal"]
["RFBU","COIN","2021-06-24","2021-06-24","3","2022","1100","108170905","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","516413","Light Meals on Site",112,"AUD","PCARD Christopher Braconi OBO-CPA-Storm event - CC","BKPFF","SYS_BCBATCH",0,"","SA",null,"Include","Internal"]
["RFBU","COIN","2021-06-24","2021-06-24","3","2022","1100","108170905","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","516413","Light Meals on Site",37,"AUD","PCARD Christopher Braconi OBO-GW-Storm event - CC","BKPFF","SYS_BCBATCH",0,"","SA",null,"Include","Internal"]
["RFBU","COIN","2021-06-24","2021-06-24","3","2022","1100","108170905","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","516413","Light Meals on Site",341.5,"AUD","PCARD Christopher Braconi OBO-GW-Storm event - CC","BKPFF","SYS_BCBATCH",0,"","SA",null,"Include","Internal"]
["RFBU","COIN","2021-06-24","2021-06-24","3","2022","1100","108170905","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","516408","Freight & Couriers",4.99,"AUD","PCARD Christopher Braconi OBO-GW-Storm event - CC","BKPFF","SYS_BCBATCH",0,"","SA",null,"Include","Internal"]
["RFBU","COIN","2021-06-24","2021-06-24","3","2022","1100","108170905","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","516413","Light Meals on Site",140.9,"AUD","PCARD Gareth Downes Meals for strike team TGN","BKPFF","SYS_BCBATCH",0,"","SA",null,"Include","Internal"]
["RFBU","COIN","2021-06-24","2021-06-24","3","2022","1100","108170905","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","516413","Light Meals on Site",106.95,"AUD","PCARD Gareth Downes Meals for strike team TGN","BKPFF","SYS_BCBATCH",0,"","SA",null,"Include","Internal"]
["RFBU","COIN","2021-06-24","2021-06-24","3","2022","1100","108170905","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","516413","Light Meals on Site",38.700000000000003,"AUD","PCARD Gareth Downes Meals for strike team TGN","BKPFF","SYS_BCBATCH",0,"","SA",null,"Include","Internal"]
["RFBU","COIN","2021-06-24","2021-06-24","3","2022","1100","108170905","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","516413","Light Meals on Site",27.5,"AUD","PCARD Gareth Downes Lunch for strike team","BKPFF","SYS_BCBATCH",0,"","SA",null,"Include","Internal"]
["RFBU","COIN","2021-06-29","2021-06-29","3","2022","1100","108174747","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","506500","Cont Lab Non-Payroll",8313.76,"AUD","Hays Transfers","BKPFF","WF-BATCH",0,"","AB",null,"Exclude"]
["RFBU","COIN","2021-06-29","2021-06-29","3","2022","1100","108174747","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","506500","Cont Lab Non-Payroll",15715.63,"AUD","Hays Transfers","BKPFF","WF-BATCH",0,"","AB",null,"Exclude"]
["RFBU","COIN","2021-06-30","2021-06-30","3","2022","1100","108175044","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","521601","Claims & Settlements",110231.7,"AUD","Customer Claims Storm Transfer","BKPFF","WF-BATCH",0,"","AB",null,"Include","Internal"]
["RFBU","COIN","2021-06-30","2021-06-30","3","2022","1100","108175044","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","521602","Domestic Surge Claim",1764,"AUD","Customer Claims Storm Transfer","BKPFF","WF-BATCH",0,"","AB",null,"Include","Internal"]
["RFBU","COIN","2021-06-30","2021-06-30","3","2022","1100","108175044","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","521605","Cust Comp - Non-GSL",5840,"AUD","Customer Claims Storm Transfer","BKPFF","WF-BATCH",0,"","AB",null,"Include","Internal"]
["RFBU","COIN","2021-06-29","2021-06-29","3","2022","1100","108175150","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","516400","General Expenses",15063.64,"AUD","One Time Vendor Storm Transfer","BKPFF","WF-BATCH",0,"","AB",null,"Include","Internal"]
["RMWE","COIN","2021-07-01","2021-07-01","4","2022","1100","108242203","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","516405","Public relations",13200,"AUD","Storm Damage Video","MKPF","RASSELMA",0,"","WE",null,"Include","Internal"]
["RMWE","COIN","2021-07-13","2021-07-13","4","2022","1100","108254081","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","521100","Materials",1243.4000000000001,"AUD","","MKPF","NHEWES",0,"","WE",null,"Include","Internal"]
["RMWE","COIN","2021-07-15","2021-07-15","4","2022","1100","108261126","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","516204","Professional Fees",36294.300000000003,"AUD","","MKPF","MDURACK",0,"","WE",null,"Include","Internal"]
["RMWE","COIN","2021-07-15","2021-07-15","4","2022","1100","108261127","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","516204","Professional Fees",13573.3,"AUD","","MKPF","MDURACK",0,"","WE",null,"Include","Internal"]
["RMWE","COIN","2021-07-15","2021-07-15","4","2022","1100","108261128","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","516204","Professional Fees",2815.4,"AUD","","MKPF","MDURACK",0,"","WE",null,"Include","Internal"]
["RFBU","COIN","2021-07-13","2021-07-13","4","2022","1100","108261577","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","521505","Vehicle Parking",16,"AUD","EEXP Peter Galey Parking for escalation","BKPFF","BSANKARA",0,"","SA",null,"Include","Internal"]
["RFBU","COIN","2021-07-13","2021-07-13","4","2022","1100","108261577","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","521505","Vehicle Parking",115,"AUD","EEXP Peter Galey Parking 452 Flinders","BKPFF","BSANKARA",0,"","SA",null,"Include","Internal"]
["RFBU","COIN","2021-07-13","2021-07-13","4","2022","1100","108261577","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","521505","Vehicle Parking",16,"AUD","EEXP Peter Galey Parking for escalation","BKPFF","BSANKARA",0,"","SA",null,"Include","Internal"]
["RFBU","COIN","2021-07-13","2021-07-13","4","2022","1100","108261577","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","516413","Light Meals on Site",46.8,"AUD","EEXP Julie Warke Grill'd Richmond","BKPFF","BSANKARA",0,"","SA",null,"Include","Internal"]
["RFBU","COIN","2021-07-13","2021-07-13","4","2022","1100","108261577","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","516413","Light Meals on Site",255.8,"AUD","EEXP Julie Warke +39 Pizzeria","BKPFF","BSANKARA",0,"","SA",null,"Include","Internal"]
["RFBU","COIN","2021-07-13","2021-07-13","4","2022","1100","108261577","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","516413","Light Meals on Site",40.9,"AUD","EEXP Julie Warke Grill'd Richmond","BKPFF","BSANKARA",0,"","SA",null,"Include","Internal"]
["RFBU","COIN","2021-07-13","2021-07-13","4","2022","1100","108261577","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","516413","Light Meals on Site",166,"AUD","EEXP Julie Warke Crust Pizza Melbourne","BKPFF","BSANKARA",0,"","SA",null,"Include","Internal"]
["RFBU","COIN","2021-07-13","2021-07-13","4","2022","1100","108261577","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","521402","MV - Maintenance",14.5,"AUD","EEXP Paul Kempton Carwash","BKPFF","BSANKARA",0,"","SA",null,"Include","Internal"]
["RFBU","COIN","2021-07-13","2021-07-13","4","2022","1100","108261577","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","521505","Vehicle Parking",85,"AUD","EEXP David Rofe Car Parking EMT Admin","BKPFF","BSANKARA",0,"","SA",null,"Include","Internal"]
["RFBU","COIN","2021-07-06","2021-07-06","4","2022","1100","108263863","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","521508","Accommodation",400,"AUD","EEXP Dean Kemp Mutual Aid Reward","BKPFF","BSANKARA",0,"","SA",null,"Include","Internal"]
["RFBU","COIN","2021-07-06","2021-07-06","4","2022","1100","108263863","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","521508","Accommodation",200,"AUD","EEXP Dean Kemp Lunch  - Mutual Aid 20-6-21","BKPFF","BSANKARA",0,"","SA",null,"Include","Internal"]
["RFBU","COIN","2021-07-06","2021-07-06","4","2022","1100","108263863","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","516413","Light Meals on Site",20,"AUD","EEXP Julie Warke Operator 25","BKPFF","BSANKARA",0,"","SA",null,"Include","Internal"]
["RFBU","COIN","2021-07-06","2021-07-06","4","2022","1100","108263863","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","516413","Light Meals on Site",218.99,"AUD","EEXP Julie Warke Crust Pizza Richmond","BKPFF","BSANKARA",0,"","SA",null,"Include","Internal"]
["RFBU","COIN","2021-07-06","2021-07-06","4","2022","1100","108263863","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","516413","Light Meals on Site",53.8,"AUD","EEXP Julie Warke Laurent Bakery","BKPFF","BSANKARA",0,"","SA",null,"Include","Internal"]
["RFBU","COIN","2021-07-06","2021-07-06","4","2022","1100","108263863","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","516413","Light Meals on Site",132.24,"AUD","EEXP Julie Warke McDonalds (Richmond)","BKPFF","BSANKARA",0,"","SA",null,"Include","Internal"]
["RFBU","COIN","2021-07-06","2021-07-06","4","2022","1100","108263863","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","516413","Light Meals on Site",81.489999999999995,"AUD","EEXP Julie Warke McDonalds","BKPFF","BSANKARA",0,"","SA",null,"Include","Internal"]
["RFBU","COIN","2021-07-06","2021-07-06","4","2022","1100","108263863","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","516413","Light Meals on Site",187.29,"AUD","EEXP Julie Warke Grill'd Southern Cross","BKPFF","BSANKARA",0,"","SA",null,"Include","Internal"]
["RFBU","COIN","2021-07-06","2021-07-06","4","2022","1100","108263863","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","516413","Light Meals on Site",132.59,"AUD","EEXP Julie Warke McDonalds","BKPFF","BSANKARA",0,"","SA",null,"Include","Internal"]
["RFBU","COIN","2021-07-06","2021-07-06","4","2022","1100","108263863","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","516413","Light Meals on Site",76.34,"AUD","EEXP Julie Warke The Eatery - Sir Schnitzel","BKPFF","BSANKARA",0,"","SA",null,"Include","Internal"]
["RFBU","COIN","2021-07-06","2021-07-06","4","2022","1100","108263863","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","516413","Light Meals on Site",66.989999999999995,"AUD","EEXP Julie Warke Crust Pizza Richmond","BKPFF","BSANKARA",0,"","SA",null,"Include","Internal"]
["RFBU","COIN","2021-07-06","2021-07-06","4","2022","1100","108263863","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","516413","Light Meals on Site",179.9,"AUD","EEXP Julie Warke +39 Pizzeria","BKPFF","BSANKARA",0,"","SA",null,"Include","Internal"]
["RFBU","COIN","2021-07-21","2021-07-21","4","2022","1100","108270475","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","516402","Protective Clothing",1050,"AUD","MASK FR REUSABLE 3PLY NAVY EA","BKPFF","WF-BATCH",0,"","AB",null,"Include","Internal"]
["RFBU","COIN","2021-07-21","2021-07-21","4","2022","1100","108270475","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","516402","Protective Clothing",350,"AUD","TUFFA MASK FR REUSABLE 3PLY NAVY EA","BKPFF","WF-BATCH",0,"","AB",null,"Include","Internal"]
["RFBU","COIN","2021-07-21","2021-07-21","4","2022","1100","108270475","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","516402","Protective Clothing",2100,"AUD","MASK FR REUSABLE 3PLY NAVY EA","BKPFF","WF-BATCH",0,"","AB",null,"Include","Internal"]
["RMWE","COIN","2021-07-23","2021-07-23","4","2022","1100","108272495","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","521521","Maint - security cos",127356.43,"AUD","Adhoc Guarding Services","MKPF","TJIFKINS",0,"","WE",null,"Include","Internal"]
["RMWE","COIN","2021-07-23","2021-07-23","4","2022","1100","108272496","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","521521","Maint - security cos",24260.69,"AUD","Adhoc Guarding Services","MKPF","TJIFKINS",0,"","WE",null,"Include","Internal"]
["RFBU","COIN","2021-07-24","2021-07-24","4","2022","1100","108276188","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","506701","Reward & Recognition",-421.6,"AUD","PCARD Johnny Mangala Refund for EMTLunch-Was close","BKPFF","SYS_BCBATCH",0,"","SA",null,"Include","Internal"]
["RFBU","COIN","2021-07-24","2021-07-24","4","2022","1100","108276188","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","521508","Accommodation",-57.45,"AUD","PCARD Mathew Durack reversed charge","BKPFF","SYS_BCBATCH",0,"","SA",null,"Include","Internal"]
["RFBU","COIN","2021-07-24","2021-07-24","4","2022","1100","108276188","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","521508","Accommodation",33.39,"AUD","PCARD Dannie Ploegmakers Dinner storm response","BKPFF","SYS_BCBATCH",0,"","SA",null,"Include","Internal"]
["RFBU","COIN","2021-07-24","2021-07-24","4","2022","1100","108276188","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","521508","Accommodation",160.19999999999999,"AUD","PCARD Dannie Ploegmakers Accom storm response","BKPFF","SYS_BCBATCH",0,"","SA",null,"Include","Internal"]
["RFBU","COIN","2021-07-24","2021-07-24","4","2022","1100","108276188","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","521508","Accommodation",32.299999999999997,"AUD","PCARD Dannie Ploegmakers dinner storm response","BKPFF","SYS_BCBATCH",0,"","SA",null,"Include","Internal"]
["RFBU","COIN","2021-07-24","2021-07-24","4","2022","1100","108276188","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","521506","Transportation",40.520000000000003,"AUD","PCARD Dannie Ploegmakers Parking accommodation","BKPFF","SYS_BCBATCH",0,"","SA",null,"Include","Internal"]
["RFBU","COIN","2021-07-24","2021-07-24","4","2022","1100","108276188","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","521508","Accommodation",23,"AUD","PCARD Dannie Ploegmakers Dinner storm response","BKPFF","SYS_BCBATCH",0,"","SA",null,"Include","Internal"]
["RFBU","COIN","2021-07-24","2021-07-24","4","2022","1100","108276188","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","521508","Accommodation",14.45,"AUD","PCARD Dannie Ploegmakers Lunch storm response","BKPFF","SYS_BCBATCH",0,"","SA",null,"Include","Internal"]
["RFBU","COIN","2021-07-24","2021-07-24","4","2022","1100","108276188","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","521508","Accommodation",759.96,"AUD","PCARD Dannie Ploegmakers Accom storm response","BKPFF","SYS_BCBATCH",0,"","SA",null,"Include","Internal"]
["RFBU","COIN","2021-07-24","2021-07-24","4","2022","1100","108276188","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","521508","Accommodation",13,"AUD","PCARD Dannie Ploegmakers Bfast storm response","BKPFF","SYS_BCBATCH",0,"","SA",null,"Include","Internal"]
["RFBU","COIN","2021-07-24","2021-07-24","4","2022","1100","108276188","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","521508","Accommodation",13.5,"AUD","PCARD Dannie Ploegmakers Bfast storm response","BKPFF","SYS_BCBATCH",0,"","SA",null,"Include","Internal"]
["RFBU","COIN","2021-07-24","2021-07-24","4","2022","1100","108276188","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","521508","Accommodation",10.3,"AUD","PCARD Dannie Ploegmakers Bfast storm response","BKPFF","SYS_BCBATCH",0,"","SA",null,"Include","Internal"]
["RFBU","COIN","2021-07-24","2021-07-24","4","2022","1100","108276188","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","521508","Accommodation",30.69,"AUD","PCARD Dannie Ploegmakers Dinner storm response","BKPFF","SYS_BCBATCH",0,"","SA",null,"Include","Internal"]
["RFBU","COIN","2021-07-24","2021-07-24","4","2022","1100","108276188","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","521508","Accommodation",28.49,"AUD","PCARD Dannie Ploegmakers Dinner storm response","BKPFF","SYS_BCBATCH",0,"","SA",null,"Include","Internal"]
["RFBU","COIN","2021-07-24","2021-07-24","4","2022","1100","108276188","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","521508","Accommodation",300,"AUD","PCARD Dannie Ploegmakers Accom storm response","BKPFF","SYS_BCBATCH",0,"","SA",null,"Include","Internal"]
["RFBU","COIN","2021-07-24","2021-07-24","4","2022","1100","108276188","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","521508","Accommodation",23,"AUD","PCARD Dannie Ploegmakers Dinner storm response","BKPFF","SYS_BCBATCH",0,"","SA",null,"Include","Internal"]
["RFBU","COIN","2021-07-24","2021-07-24","4","2022","1100","108276188","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","521508","Accommodation",14,"AUD","PCARD Dannie Ploegmakers Bfast storm response","BKPFF","SYS_BCBATCH",0,"","SA",null,"Include","Internal"]
["RFBU","COIN","2021-07-24","2021-07-24","4","2022","1100","108276188","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","521508","Accommodation",10.95,"AUD","PCARD Dannie Ploegmakers Lunch storm response","BKPFF","SYS_BCBATCH",0,"","SA",null,"Include","Internal"]
["RFBU","COIN","2021-07-24","2021-07-24","4","2022","1100","108276188","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","521508","Accommodation",15,"AUD","PCARD Dannie Ploegmakers Lunch storm response","BKPFF","SYS_BCBATCH",0,"","SA",null,"Include","Internal"]
["RFBU","COIN","2021-07-24","2021-07-24","4","2022","1100","108276188","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","521508","Accommodation",20,"AUD","PCARD Dannie Ploegmakers Bfast groceries storm res","BKPFF","SYS_BCBATCH",0,"","SA",null,"Include","Internal"]
["RFBU","COIN","2021-07-24","2021-07-24","4","2022","1100","108276188","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","521508","Accommodation",35.51,"AUD","PCARD Dannie Ploegmakers Dinner storm response","BKPFF","SYS_BCBATCH",0,"","SA",null,"Include","Internal"]
["RFBU","COIN","2021-07-24","2021-07-24","4","2022","1100","108276188","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","511104","Svc Prov - Labour",396,"AUD","PCARD David Green Connect Generator LGA Depot","BKPFF","SYS_BCBATCH",0,"","SA",null,"Include","Internal"]
["RFBU","COIN","2021-07-24","2021-07-24","4","2022","1100","108276188","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","506701","Reward & Recognition",421.6,"AUD","PCARD Johnny Mangala EMT Lunch but will be refunde","BKPFF","SYS_BCBATCH",0,"","SA",null,"Include","Internal"]
["RFBU","COIN","2021-07-24","2021-07-24","4","2022","1100","108276188","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","506701","Reward & Recognition",221.99,"AUD","PCARD Johnny Mangala Food for EMT (Jo P)","BKPFF","SYS_BCBATCH",0,"","SA",null,"Include","Internal"]
["RFBU","COIN","2021-07-24","2021-07-24","4","2022","1100","108276188","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","506701","Reward & Recognition",27.19,"AUD","PCARD Johnny Mangala Food for EMT (Jo P)","BKPFF","SYS_BCBATCH",0,"","SA",null,"Include","Internal"]
["RFBU","COIN","2021-07-24","2021-07-24","4","2022","1100","108276188","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","516413","Light Meals on Site",161.29,"AUD","PCARD Christopher Braconi Storm Contact Centre mea","BKPFF","SYS_BCBATCH",0,"","SA",null,"Include","Internal"]
["RFBU","COIN","2021-07-24","2021-07-24","4","2022","1100","108276188","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","516413","Light Meals on Site",27.85,"AUD","PCARD Scott Harvey meals for storm","BKPFF","SYS_BCBATCH",0,"","SA",null,"Include","Internal"]
["RFBU","COIN","2021-07-24","2021-07-24","4","2022","1100","108276188","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","516413","Light Meals on Site",275.39999999999998,"AUD","PCARD Scott Harvey Lunch for Storm Response Teams","BKPFF","SYS_BCBATCH",0,"","SA",null,"Include","Internal"]
["RFBU","COIN","2021-07-24","2021-07-24","4","2022","1100","108276188","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","516413","Light Meals on Site",28.4,"AUD","PCARD Scott Harvey Dinner for Storm Event","BKPFF","SYS_BCBATCH",0,"","SA",null,"Include","Internal"]
["RFBU","COIN","2021-07-24","2021-07-24","4","2022","1100","108276188","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","516413","Light Meals on Site",19.149999999999999,"AUD","PCARD Scott Harvey Dinner for Storms Event","BKPFF","SYS_BCBATCH",0,"","SA",null,"Include","Internal"]
["RFBU","COIN","2021-07-24","2021-07-24","4","2022","1100","108276188","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","521402","MV - Maintenance",282,"AUD","PCARD Scott Harvey battery Rep during storm event","BKPFF","SYS_BCBATCH",0,"","SA",null,"Include","Internal"]
["RFBU","COIN","2021-07-24","2021-07-24","4","2022","1100","108276188","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","506701","Reward & Recognition",144.59,"AUD","PCARD Hossein Sadafi Food for CEOT/Storms Recovery","BKPFF","SYS_BCBATCH",0,"","SA",null,"Include","Internal"]
["RFBU","COIN","2021-07-24","2021-07-24","4","2022","1100","108276188","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","506701","Reward & Recognition",250.9,"AUD","PCARD Hossein Sadafi Food for CEOT/Storms Recovery","BKPFF","SYS_BCBATCH",0,"","SA",null,"Include","Internal"]
["RFBU","COIN","2021-07-24","2021-07-24","4","2022","1100","108276188","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","516413","Light Meals on Site",69.989999999999995,"AUD","PCARD Sergio Inacio Storm Night Meals FLD Team","BKPFF","SYS_BCBATCH",0,"","SA",null,"Include","Internal"]
["RFBU","COIN","2021-07-24","2021-07-24","4","2022","1100","108276188","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","521508","Accommodation",286,"AUD","PCARD Sergio Inacio Generator Team Stay - Warragul","BKPFF","SYS_BCBATCH",0,"","SA",null,"Include","Internal"]
["RFBU","COIN","2021-07-24","2021-07-24","4","2022","1100","108276188","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","516413","Light Meals on Site",147.44,"AUD","PCARD Sergio Inacio MorningTea - EMT team - Storm","BKPFF","SYS_BCBATCH",0,"","SA",null,"Include","Internal"]
["RFBU","COIN","2021-07-24","2021-07-24","4","2022","1100","108276188","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","521508","Accommodation",143,"AUD","PCARD Sergio Inacio Gen Team Night Stay Warragal","BKPFF","SYS_BCBATCH",0,"","SA",null,"Include","Internal"]
["RFBU","COIN","2021-07-24","2021-07-24","4","2022","1100","108276188","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","521508","Accommodation",172.99,"AUD","PCARD Dannie Ploegmakers Accom storms","BKPFF","SYS_BCBATCH",0,"","SA",null,"Include","Internal"]
["RFBU","COIN","2021-07-24","2021-07-24","4","2022","1100","108276188","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","521508","Accommodation",23.94,"AUD","PCARD Dannie Ploegmakers Dinner storm response","BKPFF","SYS_BCBATCH",0,"","SA",null,"Include","Internal"]
["RFBU","COIN","2021-07-24","2021-07-24","4","2022","1100","108276188","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","521508","Accommodation",12.8,"AUD","PCARD Dannie Ploegmakers Bfast storm response","BKPFF","SYS_BCBATCH",0,"","SA",null,"Include","Internal"]
["RFBU","COIN","2021-07-24","2021-07-24","4","2022","1100","108276188","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","521508","Accommodation",10.6,"AUD","PCARD Dannie Ploegmakers Bfast storm response","BKPFF","SYS_BCBATCH",0,"","SA",null,"Include","Internal"]
["RFBU","COIN","2021-07-24","2021-07-24","4","2022","1100","108276188","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","516105","Phones & Pagers",194,"AUD","PCARD Dannie Ploegmakers Earpods & HDMI cables","BKPFF","SYS_BCBATCH",0,"","SA",null,"Include","Internal"]
["RFBU","COIN","2021-07-24","2021-07-24","4","2022","1100","108276188","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","516102","IT Hardware",79.900000000000006,"AUD","PCARD Dannie Ploegmakers Earpods & HDMI cables","BKPFF","SYS_BCBATCH",0,"","SA",null,"Include","Internal"]
["RFBU","COIN","2021-07-24","2021-07-24","4","2022","1100","108276188","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","521508","Accommodation",30.49,"AUD","PCARD Dannie Ploegmakers Dinner storm response","BKPFF","SYS_BCBATCH",0,"","SA",null,"Include","Internal"]
["RFBU","COIN","2021-07-24","2021-07-24","4","2022","1100","108276188","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","521508","Accommodation",25.09,"AUD","PCARD Dannie Ploegmakers Dinner storm response","BKPFF","SYS_BCBATCH",0,"","SA",null,"Include","Internal"]
["RFBU","COIN","2021-07-24","2021-07-24","4","2022","1100","108276188","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","521507","Travel",15.27,"AUD","PCARD Dannie Ploegmakers Laundry detergent - Storm","BKPFF","SYS_BCBATCH",0,"","SA",null,"Include","Internal"]
["RFBU","COIN","2021-07-24","2021-07-24","4","2022","1100","108276188","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","521506","Transportation",9.11,"AUD","PCARD Dannie Ploegmakers Parking accommodation","BKPFF","SYS_BCBATCH",0,"","SA",null,"Include","Internal"]
["RFBU","COIN","2021-07-24","2021-07-24","4","2022","1100","108276188","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","521508","Accommodation",35.5,"AUD","PCARD Dannie Ploegmakers Dinner storm response","BKPFF","SYS_BCBATCH",0,"","SA",null,"Include","Internal"]
["RFBU","COIN","2021-07-24","2021-07-24","4","2022","1100","108276188","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","521508","Accommodation",336.62,"AUD","PCARD Dannie Ploegmakers Accom storm response","BKPFF","SYS_BCBATCH",0,"","SA",null,"Include","Internal"]
["RFBU","COIN","2021-07-24","2021-07-24","4","2022","1100","108276188","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","521508","Accommodation",360.91,"AUD","PCARD Dannie Ploegmakers Accom storm response","BKPFF","SYS_BCBATCH",0,"","SA",null,"Include","Internal"]
["RFBU","COIN","2021-07-24","2021-07-24","4","2022","1100","108276188","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","521508","Accommodation",20.100000000000001,"AUD","PCARD Dannie Ploegmakers Bfast storm response","BKPFF","SYS_BCBATCH",0,"","SA",null,"Include","Internal"]
["RFBU","COIN","2021-07-24","2021-07-24","4","2022","1100","108276188","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","521400","MV & Plant - Fuel",49.59,"AUD","PCARD Alanna Pollock for travel to recovery hubs","BKPFF","SYS_BCBATCH",0,"","SA",null,"Include","Internal"]
["RFBU","COIN","2021-07-24","2021-07-24","4","2022","1100","108276188","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","521400","MV & Plant - Fuel",182.38,"AUD","PCARD Alanna Pollock Fuel for visiting recoveryhub","BKPFF","SYS_BCBATCH",0,"","SA",null,"Include","Internal"]
["RFBU","COIN","2021-07-24","2021-07-24","4","2022","1100","108276188","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","516401","Office Expenses",122,"AUD","PCARD Alanna Pollock Required by Recovery Hub LST","BKPFF","SYS_BCBATCH",0,"","SA",null,"Include","Internal"]
["RFBU","COIN","2021-07-24","2021-07-24","4","2022","1100","108276188","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","516413","Light Meals on Site",117.35,"AUD","PCARD Alanna Pollock Hot Drinks- Recovery Hubs LST","BKPFF","SYS_BCBATCH",0,"","SA",null,"Include","Internal"]
["RFBU","COIN","2021-07-24","2021-07-24","4","2022","1100","108276188","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","521100","Materials",60,"AUD","PCARD Alanna Pollock Supplies for Recovery Hubs","BKPFF","SYS_BCBATCH",0,"","SA",null,"Include","Internal"]
["RFBU","COIN","2021-07-24","2021-07-24","4","2022","1100","108276188","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","521400","MV & Plant - Fuel",38.06,"AUD","PCARD Alanna Pollock Fuel to attend recovery hubs","BKPFF","SYS_BCBATCH",0,"","SA",null,"Include","Internal"]
["RFBU","COIN","2021-07-24","2021-07-24","4","2022","1100","108276188","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","521508","Accommodation",20.13,"AUD","PCARD Mathew Durack Storms event- meals","BKPFF","SYS_BCBATCH",0,"","SA",null,"Include","Internal"]
["RFBU","COIN","2021-07-24","2021-07-24","4","2022","1100","108276188","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","521508","Accommodation",15.89,"AUD","PCARD Mathew Durack Storms event- meals","BKPFF","SYS_BCBATCH",0,"","SA",null,"Include","Internal"]
["RFBU","COIN","2021-07-24","2021-07-24","4","2022","1100","108276188","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","521508","Accommodation",28,"AUD","PCARD Mathew Durack Storms event- meals","BKPFF","SYS_BCBATCH",0,"","SA",null,"Include","Internal"]
["RFBU","COIN","2021-07-24","2021-07-24","4","2022","1100","108276188","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","521508","Accommodation",20,"AUD","PCARD Mathew Durack Storms event- meal","BKPFF","SYS_BCBATCH",0,"","SA",null,"Include","Internal"]
["RFBU","COIN","2021-07-24","2021-07-24","4","2022","1100","108276188","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","521508","Accommodation",57.45,"AUD","PCARD Mathew Durack this charge was reversed","BKPFF","SYS_BCBATCH",0,"","SA",null,"Include","Internal"]
["RFBU","COIN","2021-07-24","2021-07-24","4","2022","1100","108276188","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","521508","Accommodation",49.45,"AUD","PCARD Mathew Durack Storms event- meal","BKPFF","SYS_BCBATCH",0,"","SA",null,"Include","Internal"]
["RFBU","COIN","2021-07-24","2021-07-24","4","2022","1100","108276188","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","521508","Accommodation",50,"AUD","PCARD Mathew Durack Storms- meal for NH & MD","BKPFF","SYS_BCBATCH",0,"","SA",null,"Include","Internal"]
["RFBU","COIN","2021-07-24","2021-07-24","4","2022","1100","108276188","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","521508","Accommodation",8.8000000000000007,"AUD","PCARD Mathew Durack Storms event- coffees","BKPFF","SYS_BCBATCH",0,"","SA",null,"Include","Internal"]
["RFBU","COIN","2021-07-24","2021-07-24","4","2022","1100","108276188","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","521508","Accommodation",7.7,"AUD","PCARD Mathew Durack Storms event- meal","BKPFF","SYS_BCBATCH",0,"","SA",null,"Include","Internal"]
["RFBU","COIN","2021-07-24","2021-07-24","4","2022","1100","108276188","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","521508","Accommodation",21.9,"AUD","PCARD Mathew Durack Storms event- meals","BKPFF","SYS_BCBATCH",0,"","SA",null,"Include","Internal"]
["RFBU","COIN","2021-07-24","2021-07-24","4","2022","1100","108276188","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","521508","Accommodation",23,"AUD","PCARD Mathew Durack Storms event- meal","BKPFF","SYS_BCBATCH",0,"","SA",null,"Include","Internal"]
["RFBU","COIN","2021-07-24","2021-07-24","4","2022","1100","108276188","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","521508","Accommodation",22.5,"AUD","PCARD Mathew Durack Storms event- meals x 2","BKPFF","SYS_BCBATCH",0,"","SA",null,"Include","Internal"]
["RFBU","COIN","2021-07-24","2021-07-24","4","2022","1100","108276188","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","521508","Accommodation",121,"AUD","PCARD Brian Brann BB","BKPFF","SYS_BCBATCH",0,"","SA",null,"Include","Internal"]
["RFBU","COIN","2021-07-24","2021-07-24","4","2022","1100","108276188","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","521508","Accommodation",11.85,"AUD","PCARD Brian Brann B Brann breakfast LDL storms","BKPFF","SYS_BCBATCH",0,"","SA",null,"Include","Internal"]
["RFBU","COIN","2021-07-24","2021-07-24","4","2022","1100","108276188","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","521508","Accommodation",26.5,"AUD","PCARD Brian Brann BB & DP breakfast LDL storms","BKPFF","SYS_BCBATCH",0,"","SA",null,"Include","Internal"]
["RFBU","COIN","2021-07-24","2021-07-24","4","2022","1100","108276188","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","521508","Accommodation",17,"AUD","PCARD Brian Brann B Brann lunch LDL storms","BKPFF","SYS_BCBATCH",0,"","SA",null,"Include","Internal"]
["RFBU","COIN","2021-07-24","2021-07-24","4","2022","1100","108276188","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","521508","Accommodation",482.36,"AUD","PCARD Brian Brann B Brann accom Lilydale storms","BKPFF","SYS_BCBATCH",0,"","SA",null,"Include","Internal"]
["RFBU","COIN","2021-07-24","2021-07-24","4","2022","1100","108276188","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","521508","Accommodation",25.5,"AUD","PCARD Brian Brann B Brann evening meal LDL storm","BKPFF","SYS_BCBATCH",0,"","SA",null,"Include","Internal"]
["RFBU","COIN","2021-07-24","2021-07-24","4","2022","1100","108277707","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","521508","Accommodation",-335.16,"AUD","PCARD Dannie Ploegmakers Accom expenses - Cancelle","BKPFF","SYS_BCBATCH",0,"","SA",null,"Include","Internal"]
["RFBU","COIN","2021-07-24","2021-07-24","4","2022","1100","108277707","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","521508","Accommodation",19,"AUD","PCARD Dannie Ploegmakers Dinner storm response","BKPFF","SYS_BCBATCH",0,"","SA",null,"Include","Internal"]
["RFBU","COIN","2021-07-24","2021-07-24","4","2022","1100","108277707","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","521508","Accommodation",58.84,"AUD","PCARD Dannie Ploegmakers Dinner storm response","BKPFF","SYS_BCBATCH",0,"","SA",null,"Include","Internal"]
["RFBU","COIN","2021-07-24","2021-07-24","4","2022","1100","108277707","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","521508","Accommodation",28.41,"AUD","PCARD Dannie Ploegmakers Dinner storm response","BKPFF","SYS_BCBATCH",0,"","SA",null,"Include","Internal"]
["RFBU","COIN","2021-07-24","2021-07-24","4","2022","1100","108277707","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","521508","Accommodation",31,"AUD","PCARD Dannie Ploegmakers Bfast storm response","BKPFF","SYS_BCBATCH",0,"","SA",null,"Include","Internal"]
["RFBU","COIN","2021-07-24","2021-07-24","4","2022","1100","108277707","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","516105","Phones & Pagers",58.3,"AUD","PCARD Gareth Downes New charger for sat phone","BKPFF","SYS_BCBATCH",0,"","SA",null,"Include","Internal"]
["RFBU","COIN","2021-07-24","2021-07-24","4","2022","1100","108277707","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","516103","Comms Charges",180.4,"AUD","PCARD Gareth Downes New charger for sat phone","BKPFF","SYS_BCBATCH",0,"","SA",null,"Include","Internal"]
["RFBU","COIN","2021-07-24","2021-07-24","4","2022","1100","108277707","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","521508","Accommodation",18,"AUD","PCARD Brian Brann B Brann evening meal LDL storm","BKPFF","SYS_BCBATCH",0,"","SA",null,"Include","Internal"]
["RFBU","COIN","2021-07-24","2021-07-24","4","2022","1100","108277707","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","521508","Accommodation",10.7,"AUD","PCARD Brian Brann B Brann lunch LDL storms","BKPFF","SYS_BCBATCH",0,"","SA",null,"Include","Internal"]
["RFBU","COIN","2021-07-24","2021-07-24","4","2022","1100","108277707","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","521508","Accommodation",4.3,"AUD","PCARD Brian Brann B Brann lunch LDL storms","BKPFF","SYS_BCBATCH",0,"","SA",null,"Include","Internal"]
["RFBU","COIN","2021-07-24","2021-07-24","4","2022","1100","108277707","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","521100","Materials",652.5,"AUD","PCARD Mathew Durack Storms- New POA","BKPFF","SYS_BCBATCH",0,"","SA",null,"Include","Internal"]
["RFBU","COIN","2021-07-26","2021-07-26","4","2022","1100","108278574","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","506500","Cont Lab Non-Payroll",4861.6099999999997,"AUD","Hays Personnel Transfers","BKPFF","WF-BATCH",0,"","AB",null,"Exclude"]
["RFBU","COIN","2021-07-26","2021-07-26","4","2022","1100","108278574","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","506401","S&W Proj - NT Adj",11283.25,"AUD","Storm Internal Labour Transfers","BKPFF","WF-BATCH",0,"","AB",null,"Exclude"]
["RFBU","COIN","2021-07-26","2021-07-26","4","2022","1100","108278574","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","506500","Cont Lab Non-Payroll",43818.79,"AUD","Agency Storm Transfers","BKPFF","WF-BATCH",0,"","AB",null,"Exclude"]
["RFBU","COIN","2021-07-26","2021-07-26","4","2022","1100","108278574","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","506500","Cont Lab Non-Payroll",51100.14,"AUD","Chandler Storm Transfers","BKPFF","WF-BATCH",0,"","AB",null,"Exclude"]
["RFBU","COIN","2021-07-26","2021-07-26","4","2022","1100","108278574","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","516103","Comms Charges",48047.16,"AUD","Whispir Transfers (SMS)","BKPFF","WF-BATCH",0,"","AB",null,"Include","Internal"]
["RFBU","COIN","2021-07-27","2021-07-27","4","2022","1100","108281149","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","511100","Svc Prov - Contracts",200000,"AUD","Downer LDL REFCL Testing After Storm","BKPFF","WF-BATCH",0,"","AB",null,"Include","External"]
["RFBU","COIN","2021-07-27","2021-07-27","4","2022","1100","108281834","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","521601","Claims & Settlements",-225294.06,"AUD","Claims (Jule Storm) Provision True Up - Jul 21","BKPFF","WF-BATCH",0,"","AB",null,"Include","Internal"]
["RFBU","COIN","2021-07-27","2021-07-27","4","2022","1100","108281834","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","521601","Claims & Settlements",404871.61,"AUD","Claims (Jule Storm) Provision True Up - Jul 21","BKPFF","WF-BATCH",0,"","AB",null,"Include","Internal"]
["RFBU","COIN","2021-07-27","2021-07-27","4","2022","1100","108281834","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","521602","Domestic Surge Claim",8269.2900000000009,"AUD","Claims (Jule Storm) Provision True Up - Jul 21","BKPFF","WF-BATCH",0,"","AB",null,"Include","Internal"]
["RFBU","COIN","2021-07-27","2021-07-27","4","2022","1100","108281834","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","521603","Comrcl Surge Claims",3418.2,"AUD","Claims (Jule Storm) Provision True Up - Jul 21","BKPFF","WF-BATCH",0,"","AB",null,"Include","Internal"]
["RFBU","COIN","2021-07-27","2021-07-27","4","2022","1100","108281834","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","521601","Claims & Settlements",9672.07,"AUD","Claims (Jule Storm) Provision True Up - Jul 21","BKPFF","WF-BATCH",0,"","AB",null,"Include","Internal"]
["RFBU","COIN","2021-07-27","2021-07-27","4","2022","1100","108281834","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","521603","Comrcl Surge Claims",-773374.63,"AUD","Claims (Jule Storm) Provision True Up - Jul 21","BKPFF","WF-BATCH",0,"","AB",null,"Include","Internal"]
["RFBU","COIN","2021-07-29","2021-07-29","4","2022","1100","108284989","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","506701","Reward & Recognition",300,"AUD","Downer Storm Transfers","BKPFF","WF-BATCH",0,"","AB",null,"Include","External"]
["RFBU","COIN","2021-07-29","2021-07-29","4","2022","1100","108284989","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","511202","Maintenance - Asset",199583.4,"AUD","Downer Storm Transfers","BKPFF","WF-BATCH",0,"","AB",null,"Include","External"]
["RFBU","COIN","2021-07-29","2021-07-29","4","2022","1100","108284989","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","516102","IT Hardware",34.950000000000003,"AUD","Downer Storm Transfers","BKPFF","WF-BATCH",0,"","AB",null,"Include","External"]
["RFBU","COIN","2021-07-29","2021-07-29","4","2022","1100","108284989","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","516300","Lease - MV & Mobil",12.97,"AUD","Downer Storm Transfers","BKPFF","WF-BATCH",0,"","AB",null,"Include","External"]
["RFBU","COIN","2021-07-29","2021-07-29","4","2022","1100","108284989","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","516402","Protective Clothing",368.98,"AUD","Downer Storm Transfers","BKPFF","WF-BATCH",0,"","AB",null,"Include","External"]
["RFBU","COIN","2021-07-29","2021-07-29","4","2022","1100","108284989","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","516407","Vehicle Tolls",26.55,"AUD","Downer Storm Transfers","BKPFF","WF-BATCH",0,"","AB",null,"Include","External"]
["RFBU","COIN","2021-07-29","2021-07-29","4","2022","1100","108284989","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","516413","Light Meals on Site",182.17,"AUD","Downer Storm Transfers","BKPFF","WF-BATCH",0,"","AB",null,"Include","External"]
["RFBU","COIN","2021-07-29","2021-07-29","4","2022","1100","108284989","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","516416","Entertmnt - Meals",24.5,"AUD","Downer Storm Transfers","BKPFF","WF-BATCH",0,"","AB",null,"Include","External"]
["RFBU","COIN","2021-07-29","2021-07-29","4","2022","1100","108284989","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","521400","MV & Plant - Fuel",645.54999999999995,"AUD","Downer Storm Transfers","BKPFF","WF-BATCH",0,"","AB",null,"Include","External"]
["RFBU","COIN","2021-07-29","2021-07-29","4","2022","1100","108284989","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","521402","MV - Maintenance",23.85,"AUD","Downer Storm Transfers","BKPFF","WF-BATCH",0,"","AB",null,"Include","External"]
["RFBU","COIN","2021-07-29","2021-07-29","4","2022","1100","108284989","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","521507","Travel",4328.6000000000004,"AUD","Downer Storm Transfers","BKPFF","WF-BATCH",0,"","AB",null,"Include","External"]
["RFBU","COIN","2021-07-29","2021-07-29","4","2022","1100","108284989","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","521508","Accommodation",1280.32,"AUD","Downer Storm Transfers","BKPFF","WF-BATCH",0,"","AB",null,"Include","External"]
["RFBU","COIN","2021-07-29","2021-07-29","4","2022","1100","108285979","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","521517","Ombudsman Levy",7105,"AUD","Customer EWOV June Storm Transfers","BKPFF","WF-BATCH",0,"","AB",null,"Include","Internal"]
["RFBU","COIN","2021-07-29","2021-07-29","4","2022","1100","108287172","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","521601","Claims & Settlements",548748,"AUD","Customer Claims Storm Transfer","BKPFF","WF-BATCH",0,"","AB",null,"Include","Internal"]
["RFBU","COIN","2021-07-29","2021-07-29","4","2022","1100","108287172","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","521602","Domestic Surge Claim",9910.0300000000007,"AUD","Customer Claims Storm Transfer","BKPFF","WF-BATCH",0,"","AB",null,"Include","Internal"]
["RFBU","COIN","2021-07-29","2021-07-29","4","2022","1100","108287172","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","521605","Cust Comp - Non-GSL",4639.6499999999996,"AUD","Customer Claims Storm Transfer","BKPFF","WF-BATCH",0,"","AB",null,"Include","Internal"]
["RFBU","COIN","2021-07-30","2021-07-30","4","2022","1100","108287258","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","516103","Comms Charges",-48047.16,"AUD","Whispir Transfers (SMS)","BKPFF","WF-BATCH",0,"","AB",null,"Include","Internal"]
["RFBU","COIN","2021-07-30","2021-07-30","4","2022","1100","108287370","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","511100","Svc Prov - Contracts",72015.73,"AUD","Zinfra Storm Reallocation","BKPFF","WF-BATCH",0,"","AB",null,"Include","Internal"]
["RFBU","COIN","2021-07-30","2021-07-30","4","2022","1100","108287370","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","511100","Svc Prov - Contracts",138268.62,"AUD","Downer OMSA Storm Reallocation - CEN","BKPFF","WF-BATCH",0,"","AB",null,"Include","External"]
["RFBU","COIN","2021-07-30","2021-07-30","4","2022","1100","108287370","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","511100","Svc Prov - Contracts",36367.43,"AUD","Downer OMSA Storm Reallocation - EAS","BKPFF","WF-BATCH",0,"","AB",null,"Include","External"]
["RFBU","COIN","2021-07-30","2021-07-30","4","2022","1100","108287370","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","511100","Svc Prov - Contracts",18255.849999999999,"AUD","Downer OMSA Storm Reallocation - NOR","BKPFF","WF-BATCH",0,"","AB",null,"Include","External"]
["RFBU","COIN","2021-07-29","2021-07-29","4","2022","1100","108287427","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","516103","Comms Charges",285000,"AUD","Whispir Transfers","BKPFF","WF-BATCH",0,"","AB",null,"Include","Internal"]
["RFBU","COIN","2021-07-29","2021-07-29","4","2022","1100","108287427","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","506500","Cont Lab Non-Payroll",28576.95,"AUD","Hays Transfers","BKPFF","WF-BATCH",0,"","AB",null,"Exclude"]
["RFBU","COIN","2021-07-29","2021-07-29","4","2022","1100","108287427","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","506401","S&W Proj - NT Adj",5032.45,"AUD","Overtime Transfers","BKPFF","WF-BATCH",0,"","AB",null,"Exclude"]
["RFBU","COIN","2021-07-29","2021-07-29","4","2022","1100","108287435","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","511201","Maintenance - Vegeta",4814871.66,"AUD","VEG Storms - reallocation to EGM","BKPFF","WF-BATCH",0,"","AB",null,"Include","External"]
["RFBU","COIN","2021-07-30","2021-08-03","5","2022","1100","108343489","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","511100","Svc Prov - Contracts",-72015.73,"AUD","Zinfra Storm Reallocation","BKPFF","PRAVEENK",0,"","AB",null,"Include","Internal"]
["RFBU","COIN","2021-07-30","2021-08-03","5","2022","1100","108343489","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","511100","Svc Prov - Contracts",-138268.62,"AUD","Downer OMSA Storm Reallocation - CEN","BKPFF","PRAVEENK",0,"","AB",null,"Include","External"]
["RFBU","COIN","2021-07-30","2021-08-03","5","2022","1100","108343489","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","511100","Svc Prov - Contracts",-36367.43,"AUD","Downer OMSA Storm Reallocation - EAS","BKPFF","PRAVEENK",0,"","AB",null,"Include","External"]
["RFBU","COIN","2021-07-30","2021-08-03","5","2022","1100","108343489","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","511100","Svc Prov - Contracts",-18255.849999999999,"AUD","Downer OMSA Storm Reallocation - NOR","BKPFF","PRAVEENK",0,"","AB",null,"Include","External"]
["RFBU","COIN","2021-08-03","2021-08-03","5","2022","1100","108348518","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","516405","Public relations",142.78,"AUD","EEXP Mark Lambert Supplies for Storm Relief Centre","BKPFF","SYS_BCBATCH",0,"","SA",null,"Include","Internal"]
["RFBU","COIN","2021-08-03","2021-08-03","5","2022","1100","108348518","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","516405","Public relations",12,"AUD","EEXP Mark Lambert Storm Supplies for Relief Centre","BKPFF","SYS_BCBATCH",0,"","SA",null,"Include","Internal"]
["RFBU","COIN","2021-08-03","2021-08-03","5","2022","1100","108348518","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","516405","Public relations",40.090000000000003,"AUD","EEXP Mark Lambert Storm Supplies to relief centre","BKPFF","SYS_BCBATCH",0,"","SA",null,"Include","Internal"]
["RFBU","COIN","2021-08-03","2021-08-03","5","2022","1100","108348518","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","521400","MV & Plant - Fuel",93.69,"AUD","EEXP Mark Lambert Fuel for Storm Relief","BKPFF","SYS_BCBATCH",0,"","SA",null,"Include","Internal"]
["RFBU","COIN","2021-08-03","2021-08-03","5","2022","1100","108348518","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","516405","Public relations",57.41,"AUD","EEXP Mark Lambert Storm Supplies for Relief Centre","BKPFF","SYS_BCBATCH",0,"","SA",null,"Include","Internal"]
["RFBU","COIN","2021-08-03","2021-08-03","5","2022","1100","108348518","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","521400","MV & Plant - Fuel",75.150000000000006,"AUD","EEXP Mark Lambert Fuel for Storm Support","BKPFF","SYS_BCBATCH",0,"","SA",null,"Include","Internal"]
["RFBU","COIN","2021-08-03","2021-08-03","5","2022","1100","108348518","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","516405","Public relations",30.09,"AUD","EEXP Mark Lambert Storm Supplies for Relief Centre","BKPFF","SYS_BCBATCH",0,"","SA",null,"Include","Internal"]
["RFBU","COIN","2021-08-03","2021-08-03","5","2022","1100","108348518","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","516405","Public relations",24,"AUD","EEXP Mark Lambert Storm Supplies","BKPFF","SYS_BCBATCH",0,"","SA",null,"Include","Internal"]
["RFBU","COIN","2021-08-05","2021-08-05","5","2022","1100","108352056","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","506500","Cont Lab Non-Payroll",73009.81,"AUD","Agency Storm Transfers","BKPFF","WF-BATCH",0,"","AB",null,"Exclude"]
["RFBU","COIN","2021-08-06","2021-08-06","5","2022","1100","108352068","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","521400","MV & Plant - Fuel",1195.93,"AUD","29/6 Storm Response","BKPFF","WF-BATCH",0,"","AB",null,"Include","Internal"]
["RFBU","COIN","2021-08-06","2021-08-06","5","2022","1100","108352068","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","521400","MV & Plant - Fuel",1110.9000000000001,"AUD","14/06 Storm Response","BKPFF","WF-BATCH",0,"","AB",null,"Include","Internal"]
["RFBU","COIN","2021-08-06","2021-08-06","5","2022","1100","108352068","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","521400","MV & Plant - Fuel",1148.3499999999999,"AUD","14/06 Storm Response","BKPFF","WF-BATCH",0,"","AB",null,"Include","Internal"]
["RFBU","COIN","2021-08-06","2021-08-06","5","2022","1100","108352068","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","521400","MV & Plant - Fuel",1134.1099999999999,"AUD","14/06 Storm Response","BKPFF","WF-BATCH",0,"","AB",null,"Include","Internal"]
["RFBU","COIN","2021-08-06","2021-08-06","5","2022","1100","108356143","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","521400","MV & Plant - Fuel",1155.56,"AUD","June 2021 Storm","BKPFF","WF-BATCH",0,"","AB",null,"Include","Internal"]
["RFBU","COIN","2021-08-06","2021-08-06","5","2022","1100","108356143","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","521400","MV & Plant - Fuel",1117.78,"AUD","June 2021 Storm","BKPFF","WF-BATCH",0,"","AB",null,"Include","Internal"]
["RFBU","COIN","2021-08-06","2021-08-06","5","2022","1100","108356143","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","521400","MV & Plant - Fuel",1094.82,"AUD","June 2021 Storm","BKPFF","WF-BATCH",0,"","AB",null,"Include","Internal"]
["RFBU","COIN","2021-08-06","2021-08-06","5","2022","1100","108356143","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","521400","MV & Plant - Fuel",839.49,"AUD","June 2021 Storm","BKPFF","WF-BATCH",0,"","AB",null,"Include","Internal"]
["RFBU","COIN","2021-08-06","2021-08-06","5","2022","1100","108356143","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","521400","MV & Plant - Fuel",988.47,"AUD","June 2021 Storm","BKPFF","WF-BATCH",0,"","AB",null,"Include","Internal"]
["RFBU","COIN","2021-08-06","2021-08-06","5","2022","1100","108356143","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","521400","MV & Plant - Fuel",1067.54,"AUD","June 2021 Storm","BKPFF","WF-BATCH",0,"","AB",null,"Include","Internal"]
["RFBU","COIN","2021-08-06","2021-08-06","5","2022","1100","108356143","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","521400","MV & Plant - Fuel",1145.5899999999999,"AUD","June 2021 Storm","BKPFF","WF-BATCH",0,"","AB",null,"Include","Internal"]
["RFBU","COIN","2021-08-06","2021-08-06","5","2022","1100","108356143","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","521400","MV & Plant - Fuel",1129.72,"AUD","June 2021 Storm","BKPFF","WF-BATCH",0,"","AB",null,"Include","Internal"]
["RFBU","COIN","2021-08-06","2021-08-06","5","2022","1100","108356143","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","521400","MV & Plant - Fuel",889.38,"AUD","June 2021 Storm","BKPFF","WF-BATCH",0,"","AB",null,"Include","Internal"]
["RFBU","COIN","2021-08-06","2021-08-06","5","2022","1100","108356143","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","521400","MV & Plant - Fuel",1112.3599999999999,"AUD","June 2021 Storm","BKPFF","WF-BATCH",0,"","AB",null,"Include","Internal"]
["RFBU","COIN","2021-08-06","2021-08-06","5","2022","1100","108356143","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","521400","MV & Plant - Fuel",287.43,"AUD","June 2021 Storm","BKPFF","WF-BATCH",0,"","AB",null,"Include","Internal"]
["RFBU","COIN","2021-08-06","2021-08-06","5","2022","1100","108356143","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","521400","MV & Plant - Fuel",889.38,"AUD","June 2021 Storm","BKPFF","WF-BATCH",0,"","AB",null,"Include","Internal"]
["RFBU","COIN","2021-08-06","2021-08-06","5","2022","1100","108356143","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","521400","MV & Plant - Fuel",432.47,"AUD","June 2021 Storm","BKPFF","WF-BATCH",0,"","AB",null,"Include","Internal"]
["RFBU","COIN","2021-08-06","2021-08-06","5","2022","1100","108356143","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","521400","MV & Plant - Fuel",583.79,"AUD","June 2021 Storm","BKPFF","WF-BATCH",0,"","AB",null,"Include","Internal"]
["RFBU","COIN","2021-08-06","2021-08-06","5","2022","1100","108356143","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","521400","MV & Plant - Fuel",567.98,"AUD","June 2021 Storm","BKPFF","WF-BATCH",0,"","AB",null,"Include","Internal"]
["RFBU","COIN","2021-08-06","2021-08-06","5","2022","1100","108356143","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","521400","MV & Plant - Fuel",538.88,"AUD","June 2021 Storm","BKPFF","WF-BATCH",0,"","AB",null,"Include","Internal"]
["RFBU","COIN","2021-08-06","2021-08-06","5","2022","1100","108356143","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","521400","MV & Plant - Fuel",538.88,"AUD","June 2021 Storm","BKPFF","WF-BATCH",0,"","AB",null,"Include","Internal"]
["RFBU","COIN","2021-08-06","2021-08-06","5","2022","1100","108356143","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","521400","MV & Plant - Fuel",521.49,"AUD","June 2021 Storm","BKPFF","WF-BATCH",0,"","AB",null,"Include","Internal"]
["RFBU","COIN","2021-08-06","2021-08-06","5","2022","1100","108356143","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","521400","MV & Plant - Fuel",318.62,"AUD","June 2021 Storm","BKPFF","WF-BATCH",0,"","AB",null,"Include","Internal"]
["RFBU","COIN","2021-08-06","2021-08-06","5","2022","1100","108356143","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","521400","MV & Plant - Fuel",782.21,"AUD","June 2021 Storm","BKPFF","WF-BATCH",0,"","AB",null,"Include","Internal"]
["RFBU","COIN","2021-08-06","2021-08-06","5","2022","1100","108356143","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","521400","MV & Plant - Fuel",560.02,"AUD","June 2021 Storm","BKPFF","WF-BATCH",0,"","AB",null,"Include","Internal"]
["RFBU","COIN","2021-08-06","2021-08-06","5","2022","1100","108356143","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","521400","MV & Plant - Fuel",538.88,"AUD","June 2021 Storm","BKPFF","WF-BATCH",0,"","AB",null,"Include","Internal"]
["RFBU","COIN","2021-08-06","2021-08-06","5","2022","1100","108356143","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","521400","MV & Plant - Fuel",1106.73,"AUD","June 2021 Storm","BKPFF","WF-BATCH",0,"","AB",null,"Include","Internal"]
["RMWE","COIN","2021-08-10","2021-08-10","5","2022","1100","108360065","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","521406","Hire - Plant & Equip",13434.11,"AUD","","MKPF","MDURACK",0,"","WE",null,"Include","Internal"]
["RMWE","COIN","2021-08-10","2021-08-10","5","2022","1100","108360068","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","521406","Hire - Plant & Equip",7190.23,"AUD","","MKPF","MDURACK",0,"","WE",null,"Include","Internal"]
["RMWE","COIN","2021-08-10","2021-08-10","5","2022","1100","108360069","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","521406","Hire - Plant & Equip",4119.29,"AUD","","MKPF","MDURACK",0,"","WE",null,"Include","Internal"]
["RMWE","COIN","2021-08-10","2021-08-10","5","2022","1100","108360070","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","521406","Hire - Plant & Equip",3838.72,"AUD","","MKPF","MDURACK",0,"","WE",null,"Include","Internal"]
["RMWE","COIN","2021-08-10","2021-08-10","5","2022","1100","108360071","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","521406","Hire - Plant & Equip",5561.32,"AUD","","MKPF","MDURACK",0,"","WE",null,"Include","Internal"]
["RMWE","COIN","2021-08-10","2021-08-10","5","2022","1100","108360072","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","521406","Hire - Plant & Equip",2656.45,"AUD","","MKPF","MDURACK",0,"","WE",null,"Include","Internal"]
["RMWE","COIN","2021-08-10","2021-08-10","5","2022","1100","108360073","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","521406","Hire - Plant & Equip",5065.3,"AUD","","MKPF","MDURACK",0,"","WE",null,"Include","Internal"]
["RMWE","COIN","2021-08-10","2021-08-10","5","2022","1100","108360074","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","521406","Hire - Plant & Equip",3702.75,"AUD","","MKPF","MDURACK",0,"","WE",null,"Include","Internal"]
["RMWE","COIN","2021-08-10","2021-08-10","5","2022","1100","108360075","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","521406","Hire - Plant & Equip",2707.25,"AUD","","MKPF","MDURACK",0,"","WE",null,"Include","Internal"]
["RMWE","COIN","2021-08-10","2021-08-10","5","2022","1100","108360077","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","521406","Hire - Plant & Equip",8468.5,"AUD","","MKPF","MDURACK",0,"","WE",null,"Include","Internal"]
["RMWE","COIN","2021-08-10","2021-08-10","5","2022","1100","108360079","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","521406","Hire - Plant & Equip",4756.4399999999996,"AUD","","MKPF","MDURACK",0,"","WE",null,"Include","Internal"]
["RMWE","COIN","2021-08-10","2021-08-10","5","2022","1100","108360082","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","521406","Hire - Plant & Equip",5709.6,"AUD","","MKPF","MDURACK",0,"","WE",null,"Include","Internal"]
["RMWE","COIN","2021-08-10","2021-08-10","5","2022","1100","108360083","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","521406","Hire - Plant & Equip",5593.93,"AUD","","MKPF","MDURACK",0,"","WE",null,"Include","Internal"]
["RMWE","COIN","2021-08-10","2021-08-10","5","2022","1100","108360084","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","521406","Hire - Plant & Equip",5109,"AUD","","MKPF","MDURACK",0,"","WE",null,"Include","Internal"]
["RMWE","COIN","2021-08-10","2021-08-10","5","2022","1100","108360085","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","521406","Hire - Plant & Equip",7463.31,"AUD","","MKPF","MDURACK",0,"","WE",null,"Include","Internal"]
["RMWE","COIN","2021-08-10","2021-08-10","5","2022","1100","108360086","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","521406","Hire - Plant & Equip",8123.31,"AUD","","MKPF","MDURACK",0,"","WE",null,"Include","Internal"]
["RMWE","COIN","2021-08-10","2021-08-10","5","2022","1100","108360087","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","521406","Hire - Plant & Equip",5867.58,"AUD","","MKPF","MDURACK",0,"","WE",null,"Include","Internal"]
["RMWE","COIN","2021-08-10","2021-08-10","5","2022","1100","108360088","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","521406","Hire - Plant & Equip",9551.9599999999991,"AUD","","MKPF","MDURACK",0,"","WE",null,"Include","Internal"]
["RMWE","COIN","2021-08-10","2021-08-10","5","2022","1100","108360089","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","521406","Hire - Plant & Equip",7277,"AUD","","MKPF","MDURACK",0,"","WE",null,"Include","Internal"]
["RMWE","COIN","2021-08-10","2021-08-10","5","2022","1100","108360090","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","521406","Hire - Plant & Equip",4684.59,"AUD","","MKPF","MDURACK",0,"","WE",null,"Include","Internal"]
["RMWE","COIN","2021-08-10","2021-08-10","5","2022","1100","108360091","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","521406","Hire - Plant & Equip",5672.45,"AUD","","MKPF","MDURACK",0,"","WE",null,"Include","Internal"]
["RMWE","COIN","2021-08-11","2021-08-11","5","2022","1100","108360299","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","521406","Hire - Plant & Equip",5011.25,"AUD","","MKPF","MDURACK",0,"","WE",null,"Include","Internal"]
["RMWE","COIN","2021-08-11","2021-08-11","5","2022","1100","108360300","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","521406","Hire - Plant & Equip",5434.8,"AUD","","MKPF","MDURACK",0,"","WE",null,"Include","Internal"]
["RMWE","COIN","2021-08-11","2021-08-11","5","2022","1100","108361702","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","521406","Hire - Plant & Equip",2647.14,"AUD","","MKPF","MDURACK",0,"","WE",null,"Include","Internal"]
["RMWE","COIN","2021-08-11","2021-08-11","5","2022","1100","108361703","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","521406","Hire - Plant & Equip",2540.31,"AUD","","MKPF","MDURACK",0,"","WE",null,"Include","Internal"]
["RMWE","COIN","2021-08-11","2021-08-11","5","2022","1100","108361704","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","521406","Hire - Plant & Equip",3434.5,"AUD","","MKPF","MDURACK",0,"","WE",null,"Include","Internal"]
["RMWE","COIN","2021-08-11","2021-08-11","5","2022","1100","108361705","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","521406","Hire - Plant & Equip",4652.21,"AUD","","MKPF","MDURACK",0,"","WE",null,"Include","Internal"]
["RMWE","COIN","2021-08-11","2021-08-11","5","2022","1100","108361707","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","521406","Hire - Plant & Equip",2412.63,"AUD","","MKPF","MDURACK",0,"","WE",null,"Include","Internal"]
["RFBU","COIN","2021-08-17","2021-08-17","5","2022","1100","108372003","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","516103","Comms Charges",-285000,"AUD","Whispir Transfers","BKPFF","WF-BATCH",0,"","AB",null,"Include","Internal"]
["RFBU","COIN","2021-08-23","2021-08-23","5","2022","1100","108376537","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","506500","Cont Lab Non-Payroll",-73009.81,"AUD","Agency Storm Transfers","BKPFF","WF-BATCH",0,"","AB",null,"Exclude"]
["RFBU","COIN","2021-08-23","2021-08-23","5","2022","1100","108377810","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","521601","Claims & Settlements",-548748,"AUD","Customer Claims Storm Transfer","BKPFF","WF-BATCH",0,"","AB",null,"Include","Internal"]
["RFBU","COIN","2021-08-23","2021-08-23","5","2022","1100","108377810","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","521602","Domestic Surge Claim",-9910.0300000000007,"AUD","Customer Claims Storm Transfer","BKPFF","WF-BATCH",0,"","AB",null,"Include","Internal"]
["RFBU","COIN","2021-08-23","2021-08-23","5","2022","1100","108377810","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","521605","Cust Comp - Non-GSL",-4639.6499999999996,"AUD","Customer Claims Storm Transfer","BKPFF","WF-BATCH",0,"","AB",null,"Include","Internal"]
["RFBU","COIN","2021-08-23","2021-08-23","5","2022","1100","108377810","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","521601","Claims & Settlements",548748,"AUD","Customer Claims Storm Transfer","BKPFF","WF-BATCH",0,"","AB",null,"Include","Internal"]
["RFBU","COIN","2021-08-23","2021-08-23","5","2022","1100","108377810","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","521602","Domestic Surge Claim",9910.0300000000007,"AUD","Customer Claims Storm Transfer","BKPFF","WF-BATCH",0,"","AB",null,"Include","Internal"]
["RFBU","COIN","2021-08-23","2021-08-23","5","2022","1100","108377810","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","521605","Cust Comp - Non-GSL",4639.6499999999996,"AUD","Customer Claims Storm Transfer","BKPFF","WF-BATCH",0,"","AB",null,"Include","Internal"]
["RMWE","COIN","2021-08-24","2021-08-24","5","2022","1100","108378389","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","521406","Hire - Plant & Equip",5138.32,"AUD","","MKPF","MDURACK",0,"","WE",null,"Include","Internal"]
["RMWE","COIN","2021-08-24","2021-08-24","5","2022","1100","108378391","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","521406","Hire - Plant & Equip",4082.5,"AUD","","MKPF","MDURACK",0,"","WE",null,"Include","Internal"]
["RMWE","COIN","2021-08-24","2021-08-24","5","2022","1100","108378392","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","521406","Hire - Plant & Equip",10129.43,"AUD","","MKPF","MDURACK",0,"","WE",null,"Include","Internal"]
["RMWE","COIN","2021-08-24","2021-08-24","5","2022","1100","108378393","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","521406","Hire - Plant & Equip",2369.81,"AUD","","MKPF","MDURACK",0,"","WE",null,"Include","Internal"]
["RFBU","COIN","2021-08-25","2021-08-25","5","2022","1100","108383382","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","506500","Cont Lab Non-Payroll",65430.53,"AUD","Customer Conrtactors - Chandler Macleod","BKPFF","WF-BATCH",0,"","AB",null,"Exclude"]
["RFBU","COIN","2021-08-24","2021-08-24","5","2022","1100","108384837","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","516413","Light Meals on Site",85,"AUD","PCARD James Radalj Meals / Food for EMT during st","BKPFF","SYS_BCBATCH",0,"","SA",null,"Include","Internal"]
["RFBU","COIN","2021-08-24","2021-08-24","5","2022","1100","108384837","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","516413","Light Meals on Site",70.5,"AUD","PCARD James Radalj Meals / Food for EMT during st","BKPFF","SYS_BCBATCH",0,"","SA",null,"Include","Internal"]
["RFBU","COIN","2021-08-24","2021-08-24","5","2022","1100","108384837","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","521505","Vehicle Parking",20,"AUD","PCARD James Radalj Parking at SCC for EMLO","BKPFF","SYS_BCBATCH",0,"","SA",null,"Include","Internal"]
["RFBU","COIN","2021-08-24","2021-08-24","5","2022","1100","108384837","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","521505","Vehicle Parking",20,"AUD","PCARD James Radalj Parking at SCC for EMLO","BKPFF","SYS_BCBATCH",0,"","SA",null,"Include","Internal"]
["RFBU","COIN","2021-08-24","2021-08-24","5","2022","1100","108384837","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","521505","Vehicle Parking",20,"AUD","PCARD James Radalj Parking at SCC for EMLO","BKPFF","SYS_BCBATCH",0,"","SA",null,"Include","Internal"]
["RFBU","COIN","2021-08-24","2021-08-24","5","2022","1100","108384837","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","516413","Light Meals on Site",92.79,"AUD","PCARD James Radalj Meals for EMT during Storm","BKPFF","SYS_BCBATCH",0,"","SA",null,"Include","Internal"]
["RFBU","COIN","2021-08-24","2021-08-24","5","2022","1100","108384837","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","521505","Vehicle Parking",10,"AUD","PCARD James Radalj Parking at SCC for EMLO","BKPFF","SYS_BCBATCH",0,"","SA",null,"Include","Internal"]
["RFBU","COIN","2021-08-24","2021-08-24","5","2022","1100","108384837","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","516413","Light Meals on Site",98,"AUD","PCARD James Radalj Meals / Food at SCC during sto","BKPFF","SYS_BCBATCH",0,"","SA",null,"Include","Internal"]
["RFBU","COIN","2021-08-24","2021-08-24","5","2022","1100","108384837","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","521505","Vehicle Parking",10,"AUD","PCARD James Radalj Parking at SCC for EMLO","BKPFF","SYS_BCBATCH",0,"","SA",null,"Include","Internal"]
["RFBU","COIN","2021-08-24","2021-08-24","5","2022","1100","108384837","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","521505","Vehicle Parking",20,"AUD","PCARD James Radalj Parking at SCC for EMLO","BKPFF","SYS_BCBATCH",0,"","SA",null,"Include","Internal"]
["RFBU","COIN","2021-08-24","2021-08-24","5","2022","1100","108384837","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","516413","Light Meals on Site",93,"AUD","PCARD James Radalj Meals / Food for EMT during st","BKPFF","SYS_BCBATCH",0,"","SA",null,"Include","Internal"]
["RFBU","COIN","2021-08-24","2021-08-24","5","2022","1100","108384837","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","516413","Light Meals on Site",113.79,"AUD","PCARD James Radalj Meals for EMT during Storm","BKPFF","SYS_BCBATCH",0,"","SA",null,"Include","Internal"]
["RFBU","COIN","2021-08-24","2021-08-24","5","2022","1100","108384837","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","516413","Light Meals on Site",24,"AUD","PCARD James Radalj Meals / Food at SCC during sto","BKPFF","SYS_BCBATCH",0,"","SA",null,"Include","Internal"]
["RFBU","COIN","2021-08-24","2021-08-24","5","2022","1100","108384837","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","516413","Light Meals on Site",80.5,"AUD","PCARD James Radalj Meals / Food at SCC during sto","BKPFF","SYS_BCBATCH",0,"","SA",null,"Include","Internal"]
["RFBU","COIN","2021-08-24","2021-08-24","5","2022","1100","108384837","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","516413","Light Meals on Site",24,"AUD","PCARD James Radalj Meals / Food at SCC during sto","BKPFF","SYS_BCBATCH",0,"","SA",null,"Include","Internal"]
["RFBU","COIN","2021-08-24","2021-08-24","5","2022","1100","108384837","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","521505","Vehicle Parking",20,"AUD","PCARD James Radalj Parking at SCC for EMLO","BKPFF","SYS_BCBATCH",0,"","SA",null,"Include","Internal"]
["RFBU","COIN","2021-08-24","2021-08-24","5","2022","1100","108384837","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","521505","Vehicle Parking",20,"AUD","PCARD James Radalj Parking at SCC for EMLO","BKPFF","SYS_BCBATCH",0,"","SA",null,"Include","Internal"]
["RFBU","COIN","2021-08-24","2021-08-24","5","2022","1100","108384837","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","516413","Light Meals on Site",24,"AUD","PCARD James Radalj Meals / Food at SCC during sto","BKPFF","SYS_BCBATCH",0,"","SA",null,"Include","Internal"]
["RFBU","COIN","2021-08-24","2021-08-24","5","2022","1100","108384837","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","516413","Light Meals on Site",68.5,"AUD","PCARD James Radalj Meals / Food at SCC during sto","BKPFF","SYS_BCBATCH",0,"","SA",null,"Include","Internal"]
["RFBU","COIN","2021-08-24","2021-08-24","5","2022","1100","108384837","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","516413","Light Meals on Site",81.99,"AUD","PCARD James Radalj Meals for EMT during Storm","BKPFF","SYS_BCBATCH",0,"","SA",null,"Include","Internal"]
["RFBU","COIN","2021-08-24","2021-08-24","5","2022","1100","108384837","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","516413","Light Meals on Site",68.59,"AUD","PCARD James Radalj Meals for EMT during Storm","BKPFF","SYS_BCBATCH",0,"","SA",null,"Include","Internal"]
["RFBU","COIN","2021-08-24","2021-08-24","5","2022","1100","108384837","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","521505","Vehicle Parking",20,"AUD","PCARD James Radalj James.L.Hunter@police.vic.gov.","BKPFF","SYS_BCBATCH",0,"","SA",null,"Include","Internal"]
["RFBU","COIN","2021-08-24","2021-08-24","5","2022","1100","108384837","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","521505","Vehicle Parking",20,"AUD","PCARD James Radalj Parking at SCC for EMLO","BKPFF","SYS_BCBATCH",0,"","SA",null,"Include","Internal"]
["RFBU","COIN","2021-08-24","2021-08-24","5","2022","1100","108384837","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","516413","Light Meals on Site",44.92,"AUD","PCARD James Radalj Meals / Food for EMT during st","BKPFF","SYS_BCBATCH",0,"","SA",null,"Include","Internal"]
["RFBU","COIN","2021-08-24","2021-08-24","5","2022","1100","108384837","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","516413","Light Meals on Site",83.3,"AUD","PCARD James Radalj Meals / Food for EMT during st","BKPFF","SYS_BCBATCH",0,"","SA",null,"Include","Internal"]
["RFBU","COIN","2021-08-24","2021-08-24","5","2022","1100","108384837","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","516413","Light Meals on Site",54,"AUD","PCARD James Radalj Meals / Food for EMT during st","BKPFF","SYS_BCBATCH",0,"","SA",null,"Include","Internal"]
["RFBU","COIN","2021-08-24","2021-08-24","5","2022","1100","108384837","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","516413","Light Meals on Site",236.84,"AUD","PCARD James Radalj Meals for EMT during Storm","BKPFF","SYS_BCBATCH",0,"","SA",null,"Include","Internal"]
["RFBU","COIN","2021-08-24","2021-08-24","5","2022","1100","108384837","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","516413","Light Meals on Site",76,"AUD","PCARD James Radalj Meals / Food for EMT during st","BKPFF","SYS_BCBATCH",0,"","SA",null,"Include","Internal"]
["RFBU","COIN","2021-08-24","2021-08-24","5","2022","1100","108384837","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","516413","Light Meals on Site",211.19,"AUD","PCARD James Radalj Meals for EMT during Storm","BKPFF","SYS_BCBATCH",0,"","SA",null,"Include","Internal"]
["RFBU","COIN","2021-08-24","2021-08-24","5","2022","1100","108384837","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","516413","Light Meals on Site",61,"AUD","PCARD James Radalj Meals / Food for EMT during st","BKPFF","SYS_BCBATCH",0,"","SA",null,"Include","Internal"]
["RFBU","COIN","2021-08-24","2021-08-24","5","2022","1100","108384837","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","516413","Light Meals on Site",68,"AUD","PCARD James Radalj Meals / Food for EMT during st","BKPFF","SYS_BCBATCH",0,"","SA",null,"Include","Internal"]
["RFBU","COIN","2021-08-24","2021-08-24","5","2022","1100","108384837","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","521505","Vehicle Parking",20,"AUD","PCARD James Radalj Parking at SCC for EMLO","BKPFF","SYS_BCBATCH",0,"","SA",null,"Include","Internal"]
["RFBU","COIN","2021-08-24","2021-08-24","5","2022","1100","108384837","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","516413","Light Meals on Site",61,"AUD","PCARD James Radalj Meals / Food for EMT during st","BKPFF","SYS_BCBATCH",0,"","SA",null,"Include","Internal"]
["RFBU","COIN","2021-08-24","2021-08-24","5","2022","1100","108384837","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","516413","Light Meals on Site",78.5,"AUD","PCARD James Radalj Meals / Food at SCC during sto","BKPFF","SYS_BCBATCH",0,"","SA",null,"Include","Internal"]
["RFBU","COIN","2021-08-24","2021-08-24","5","2022","1100","108384837","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","516413","Light Meals on Site",183.79,"AUD","PCARD James Radalj Meals for EMT during Storm","BKPFF","SYS_BCBATCH",0,"","SA",null,"Include","Internal"]
["RFBU","COIN","2021-08-24","2021-08-24","5","2022","1100","108384837","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","521505","Vehicle Parking",10,"AUD","PCARD James Radalj Parking at SCC for EMLO","BKPFF","SYS_BCBATCH",0,"","SA",null,"Include","Internal"]
["RFBU","COIN","2021-08-24","2021-08-24","5","2022","1100","108384837","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","516413","Light Meals on Site",108,"AUD","PCARD James Radalj Meals / Food for EMT during st","BKPFF","SYS_BCBATCH",0,"","SA",null,"Include","Internal"]
["RFBU","COIN","2021-08-24","2021-08-24","5","2022","1100","108384837","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","516413","Light Meals on Site",270.89999999999998,"AUD","PCARD James Radalj Meals for EMT during storm","BKPFF","SYS_BCBATCH",0,"","SA",null,"Include","Internal"]
["RFBU","COIN","2021-08-24","2021-08-24","5","2022","1100","108384837","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","521505","Vehicle Parking",10,"AUD","PCARD James Radalj Parking at SCC for EMLO","BKPFF","SYS_BCBATCH",0,"","SA",null,"Include","Internal"]
["RFBU","COIN","2021-08-24","2021-08-24","5","2022","1100","108384837","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","521505","Vehicle Parking",20,"AUD","PCARD James Radalj Parking at SCC for EMLO","BKPFF","SYS_BCBATCH",0,"","SA",null,"Include","Internal"]
["RFBU","COIN","2021-08-24","2021-08-24","5","2022","1100","108384837","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","516413","Light Meals on Site",88.98,"AUD","PCARD James Radalj Meals / Food for EMT during st","BKPFF","SYS_BCBATCH",0,"","SA",null,"Include","Internal"]
["RFBU","COIN","2021-08-24","2021-08-24","5","2022","1100","108384837","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","516413","Light Meals on Site",231.04,"AUD","PCARD James Radalj Meals for EMT during Storm","BKPFF","SYS_BCBATCH",0,"","SA",null,"Include","Internal"]
["RFBU","COIN","2021-08-24","2021-08-24","5","2022","1100","108384837","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","516413","Light Meals on Site",46.5,"AUD","PCARD James Radalj Meals / Food at SCC during sto","BKPFF","SYS_BCBATCH",0,"","SA",null,"Include","Internal"]
["RFBU","COIN","2021-08-24","2021-08-24","5","2022","1100","108384837","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","516413","Light Meals on Site",24,"AUD","PCARD James Radalj Meals / Food at SCC during sto","BKPFF","SYS_BCBATCH",0,"","SA",null,"Include","Internal"]
["RFBU","COIN","2021-08-24","2021-08-24","5","2022","1100","108384837","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","516413","Light Meals on Site",63,"AUD","PCARD James Radalj Meals / Food at SCC during sto","BKPFF","SYS_BCBATCH",0,"","SA",null,"Include","Internal"]
["RFBU","COIN","2021-08-24","2021-08-24","5","2022","1100","108384837","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","521505","Vehicle Parking",10,"AUD","PCARD James Radalj Parking at SCC for EMLO","BKPFF","SYS_BCBATCH",0,"","SA",null,"Include","Internal"]
["RFBU","COIN","2021-08-24","2021-08-24","5","2022","1100","108384837","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","516413","Light Meals on Site",19.899999999999999,"AUD","PCARD James Radalj Meals / Food at SCC during sto","BKPFF","SYS_BCBATCH",0,"","SA",null,"Include","Internal"]
["RFBU","COIN","2021-08-24","2021-08-24","5","2022","1100","108384837","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","516413","Light Meals on Site",72.5,"AUD","PCARD James Radalj Meals / Food for EMT during st","BKPFF","SYS_BCBATCH",0,"","SA",null,"Include","Internal"]
["RFBU","COIN","2021-08-24","2021-08-24","5","2022","1100","108384837","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","521505","Vehicle Parking",20,"AUD","PCARD James Radalj Parking at SCC for EMLO","BKPFF","SYS_BCBATCH",0,"","SA",null,"Include","Internal"]
["RFBU","COIN","2021-08-24","2021-08-24","5","2022","1100","108384837","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","516413","Light Meals on Site",24,"AUD","PCARD James Radalj Meals / Food at SCC during sto","BKPFF","SYS_BCBATCH",0,"","SA",null,"Include","Internal"]
["RFBU","COIN","2021-08-24","2021-08-24","5","2022","1100","108384837","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","516413","Light Meals on Site",51,"AUD","PCARD James Radalj Meals / Food at SCC during sto","BKPFF","SYS_BCBATCH",0,"","SA",null,"Include","Internal"]
["RFBU","COIN","2021-08-24","2021-08-24","5","2022","1100","108384837","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","521505","Vehicle Parking",20,"AUD","PCARD James Radalj Parking at SCC for EMLO","BKPFF","SYS_BCBATCH",0,"","SA",null,"Include","Internal"]
["RFBU","COIN","2021-08-24","2021-08-24","5","2022","1100","108384837","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","516413","Light Meals on Site",233.79,"AUD","PCARD James Radalj Meals for EMT during Storm","BKPFF","SYS_BCBATCH",0,"","SA",null,"Include","Internal"]
["RFBU","COIN","2021-08-24","2021-08-24","5","2022","1100","108384837","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","516413","Light Meals on Site",85,"AUD","PCARD James Radalj Meals / Food for EMT during st","BKPFF","SYS_BCBATCH",0,"","SA",null,"Include","Internal"]
["RFBU","COIN","2021-08-24","2021-08-24","5","2022","1100","108384837","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","516413","Light Meals on Site",60,"AUD","PCARD James Radalj Meals / Food at SCC during sto","BKPFF","SYS_BCBATCH",0,"","SA",null,"Include","Internal"]
["RFBU","COIN","2021-08-24","2021-08-24","5","2022","1100","108389031","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","521505","Vehicle Parking",20,"AUD","PCARD James Radalj Parking at SCC for EMLO","BKPFF","BSANKARA",0,"","SA",null,"Include","Internal"]
["RFBU","COIN","2021-08-24","2021-08-24","5","2022","1100","108389031","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","521100","Materials",224.4,"AUD","PCARD Gareth Downes Replacement signs damaged duri","BKPFF","BSANKARA",0,"","SA",null,"Include","Internal"]
["RFBU","COIN","2021-08-27","2021-08-27","5","2022","1100","108390286","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","521601","Claims & Settlements",212913.53,"AUD","Customer Claims Storm Transfer","BKPFF","WF-BATCH",0,"","AB",null,"Include","Internal"]
["RFBU","COIN","2021-08-27","2021-08-27","5","2022","1100","108390286","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","521602","Domestic Surge Claim",28914.85,"AUD","Customer Claims Storm Transfer","BKPFF","WF-BATCH",0,"","AB",null,"Include","Internal"]
["RFBU","COIN","2021-08-27","2021-08-27","5","2022","1100","108390286","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","521605","Cust Comp - Non-GSL",26868.38,"AUD","Customer Claims Storm Transfer","BKPFF","WF-BATCH",0,"","AB",null,"Include","Internal"]
["RFBU","COIN","2021-08-27","2021-08-27","5","2022","1100","108391031","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","521601","Claims & Settlements",-52109.64,"AUD","Claims (Jule Storm) Provision True Up - Aug 21","BKPFF","WF-BATCH",0,"","AB",null,"Include","Internal"]
["RFBU","COIN","2021-08-27","2021-08-27","5","2022","1100","108391031","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","521601","Claims & Settlements",-85123.18,"AUD","Claims (Jule Storm) Provision True Up - Aug 21","BKPFF","WF-BATCH",0,"","AB",null,"Include","Internal"]
["RFBU","COIN","2021-08-27","2021-08-27","5","2022","1100","108391031","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","521602","Domestic Surge Claim",5708.35,"AUD","Claims (Jule Storm) Provision True Up - Aug 21","BKPFF","WF-BATCH",0,"","AB",null,"Include","Internal"]
["RFBU","COIN","2021-08-27","2021-08-27","5","2022","1100","108391031","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","521603","Comrcl Surge Claims",-1679.96,"AUD","Claims (Jule Storm) Provision True Up - Aug 21","BKPFF","WF-BATCH",0,"","AB",null,"Include","Internal"]
["RFBU","COIN","2021-08-27","2021-08-27","5","2022","1100","108391031","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","521601","Claims & Settlements",-32492.97,"AUD","Claims (Jule Storm) Provision True Up - Aug 21","BKPFF","WF-BATCH",0,"","AB",null,"Include","Internal"]
["RFBU","COIN","2021-08-27","2021-08-27","5","2022","1100","108391031","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","521603","Comrcl Surge Claims",1663.39,"AUD","Claims (Jule Storm) Provision True Up - Aug 21","BKPFF","WF-BATCH",0,"","AB",null,"Include","Internal"]
["RFBU","COIN","2021-08-31","2021-08-31","5","2022","1100","108393956","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","511201","Maintenance - Vegeta",-1974097.38,"AUD","VEG Storms - reallocation to CAPEX","BKPFF","WF-BATCH",0,"","AB",null,"Include","External"]
["RFBU","COIN","2021-08-31","2021-08-31","5","2022","1100","108394566","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","516103","Comms Charges",215592.13,"AUD","Comms Response","BKPFF","WF-BATCH",0,"","AB",null,"Include","Internal"]
["RFBU","COIN","2021-08-31","2021-08-31","5","2022","1100","108394566","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","516103","Comms Charges",61663.18,"AUD","Comms Response","BKPFF","WF-BATCH",0,"","AB",null,"Include","Internal"]
["RFBU","COIN","2021-08-31","2021-08-31","5","2022","1100","108394566","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","516103","Comms Charges",7744.69,"AUD","Comms Response","BKPFF","WF-BATCH",0,"","AB",null,"Include","Internal"]
["RFBU","COIN","2021-08-31","2021-08-31","5","2022","1100","108395716","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","511100","Svc Prov - Contracts",136787.64000000001,"AUD","Downer OMSA Storm Reallocation - CEN","BKPFF","WF-BATCH",0,"","AB",null,"Include","External"]
["RFBU","COIN","2021-08-31","2021-08-31","5","2022","1100","108395716","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","511100","Svc Prov - Contracts",37293.31,"AUD","Downer OMSA Storm Reallocation - EAS","BKPFF","WF-BATCH",0,"","AB",null,"Include","External"]
["RFBU","COIN","2021-08-31","2021-08-31","5","2022","1100","108395716","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","511100","Svc Prov - Contracts",5151.57,"AUD","Downer OMSA Storm Reallocation - NOR","BKPFF","WF-BATCH",0,"","AB",null,"Include","External"]
["RFBU","COIN","2021-08-31","2021-08-31","5","2022","1100","108395716","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","511100","Svc Prov - Contracts",105923.01,"AUD","Zinfra Storm Reallocation","BKPFF","WF-BATCH",0,"","AB",null,"Include","Internal"]
["RFBU","COIN","2021-08-31","2021-08-31","5","2022","1100","108395822","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","511100","Svc Prov - Contracts",2334.15,"AUD","Endeavour Energy Storm Assistance Costs","BKPFF","WF-BATCH",0,"","AC",null,"Include","Internal"]
["RFBU","COIN","2021-08-31","2021-09-01","6","2022","1100","108462533","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","511100","Svc Prov - Contracts",-2334.15,"AUD","Endeavour Energy Storm Assistance Costs","BKPFF","SYS_BCBATCH",0,"","AR",null,"Include","Internal"]
["RFBU","COIN","2021-08-31","2021-09-08","6","2022","1100","108467863","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","511100","Svc Prov - Contracts",-136787.64000000001,"AUD","Downer OMSA Storm Reallocation - CEN","BKPFF","PRAVEENK",0,"","AB",null,"Include","External"]
["RFBU","COIN","2021-08-31","2021-09-08","6","2022","1100","108467863","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","511100","Svc Prov - Contracts",-37293.31,"AUD","Downer OMSA Storm Reallocation - EAS","BKPFF","PRAVEENK",0,"","AB",null,"Include","External"]
["RFBU","COIN","2021-08-31","2021-09-08","6","2022","1100","108467863","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","511100","Svc Prov - Contracts",-5151.57,"AUD","Downer OMSA Storm Reallocation - NOR","BKPFF","PRAVEENK",0,"","AB",null,"Include","External"]
["RFBU","COIN","2021-08-31","2021-09-08","6","2022","1100","108467863","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","511100","Svc Prov - Contracts",-105923.01,"AUD","Zinfra Storm Reallocation","BKPFF","PRAVEENK",0,"","AB",null,"Include","Internal"]
["RFBU","COIN","2021-09-24","2021-09-24","6","2022","1100","108495104","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","521508","Accommodation",571.20000000000005,"AUD","PCARD Dannie Ploegmakers Accom storm response","BKPFF","SYS_BCBATCH",0,"","SA",null,"Include","Internal"]
["RFBU","COIN","2021-09-24","2021-09-24","6","2022","1100","108495104","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","521508","Accommodation",565.79999999999995,"AUD","PCARD Dannie Ploegmakers Accom storm response","BKPFF","SYS_BCBATCH",0,"","SA",null,"Include","Internal"]
["RFBU","COIN","2021-09-28","2021-09-28","6","2022","1100","108497771","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","521601","Claims & Settlements",-5879.54,"AUD","Claims (June Storm) Provision True Up - Sep 21","BKPFF","WF-BATCH",0,"","AB",null,"Include","Internal"]
["RFBU","COIN","2021-09-28","2021-09-28","6","2022","1100","108497771","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","521601","Claims & Settlements",-464798.03,"AUD","Claims (June Storm) Provision True Up - Sep 21","BKPFF","WF-BATCH",0,"","AB",null,"Include","Internal"]
["RFBU","COIN","2021-09-28","2021-09-28","6","2022","1100","108497771","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","521602","Domestic Surge Claim",-234.02,"AUD","Claims (June Storm) Provision True Up - Sep 21","BKPFF","WF-BATCH",0,"","AB",null,"Include","Internal"]
["RFBU","COIN","2021-09-28","2021-09-28","6","2022","1100","108497771","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","521603","Comrcl Surge Claims",-10877.21,"AUD","Claims (June Storm) Provision True Up - Sep 21","BKPFF","WF-BATCH",0,"","AB",null,"Include","Internal"]
["RFBU","COIN","2021-09-28","2021-09-28","6","2022","1100","108497771","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","521603","Comrcl Surge Claims",128.11000000000001,"AUD","Claims (June Storm) Provision True Up - Sep 21","BKPFF","WF-BATCH",0,"","AB",null,"Include","Internal"]
["RFBU","COIN","2021-09-28","2021-09-28","6","2022","1100","108497771","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","521601","Claims & Settlements",-8203.26,"AUD","Claims (June Storm) Provision True Up - Sep 21","BKPFF","WF-BATCH",0,"","AB",null,"Include","Internal"]
["RFBU","COIN","2021-09-28","2021-09-28","6","2022","1100","108497771","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","521603","Comrcl Surge Claims",-15406.25,"AUD","Claims (June Storm) Provision True Up - Sep 21","BKPFF","WF-BATCH",0,"","AB",null,"Include","Internal"]
["RFBU","COIN","2021-09-27","2021-09-27","6","2022","1100","108497849","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","521601","Claims & Settlements",23042.28,"AUD","Customer Claims Storm Transfer","BKPFF","WF-BATCH",0,"","AB",null,"Include","Internal"]
["RFBU","COIN","2021-09-27","2021-09-27","6","2022","1100","108497849","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","521602","Domestic Surge Claim",8248.74,"AUD","Customer Claims Storm Transfer","BKPFF","WF-BATCH",0,"","AB",null,"Include","Internal"]
["RFBU","COIN","2021-09-27","2021-09-27","6","2022","1100","108497849","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","521605","Cust Comp - Non-GSL",5564.99,"AUD","Customer Claims Storm Transfer","BKPFF","WF-BATCH",0,"","AB",null,"Include","Internal"]
["RMWE","COIN","2021-09-28","2021-09-28","6","2022","1100","108501108","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","516204","Professional Fees",7950,"AUD","Benestar Additional Services","MKPF","SIRUSSO",0,"","WE",null,"Include","Internal"]
["RFBU","COIN","2021-09-28","2021-09-28","6","2022","1100","108501549","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","506500","Cont Lab Non-Payroll",14523.05,"AUD","POPM Storm Transfers","BKPFF","WF-BATCH",0,"","AB",null,"Exclude"]
["","RKL","2021-06-10","2021-09-08","6","2022","1100","309718095","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","810300","Allowance Expenses",76.23,"AUD","","CATS","SYS_BCBATCH",10001047,"","",{"$f":"VLOOKUP(U1208,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["","RKL","2021-06-10","2021-09-08","6","2022","1100","309718095","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","810300","Allowance Expenses",76.23,"AUD","","CATS","SYS_BCBATCH",10001047,"","",{"$f":"VLOOKUP(U1209,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["","RKL","2021-06-10","2021-09-08","6","2022","1100","309718095","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","810300","Allowance Expenses",12.32,"AUD","","CATS","SYS_BCBATCH",10001047,"","",{"$f":"VLOOKUP(U1210,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["","RKL","2021-06-10","2021-09-08","6","2022","1100","309718095","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","810300","Allowance Expenses",76.23,"AUD","","CATS","SYS_BCBATCH",10001047,"","",{"$f":"VLOOKUP(U1211,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["","RKL","2021-06-10","2021-09-08","6","2022","1100","309718095","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","810300","Allowance Expenses",12.32,"AUD","","CATS","SYS_BCBATCH",10001047,"","",{"$f":"VLOOKUP(U1212,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["","RKL","2021-06-10","2021-09-08","6","2022","1100","309718095","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","810300","Allowance Expenses",76.23,"AUD","","CATS","SYS_BCBATCH",10001047,"","",{"$f":"VLOOKUP(U1213,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["","RKL","2021-06-10","2021-09-08","6","2022","1100","309718095","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","810300","Allowance Expenses",12.32,"AUD","","CATS","SYS_BCBATCH",10001047,"","",{"$f":"VLOOKUP(U1214,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["","RKL","2021-06-10","2021-09-08","6","2022","1100","309718095","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","810300","Allowance Expenses",76.23,"AUD","","CATS","SYS_BCBATCH",10001047,"","",{"$f":"VLOOKUP(U1215,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["","RKL","2021-06-10","2021-09-08","6","2022","1100","309718095","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","810300","Allowance Expenses",12.32,"AUD","","CATS","SYS_BCBATCH",10001047,"","",{"$f":"VLOOKUP(U1216,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["","RKL","2021-06-10","2021-09-08","6","2022","1100","309718095","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","810300","Allowance Expenses",76.23,"AUD","","CATS","SYS_BCBATCH",10001047,"","",{"$f":"VLOOKUP(U1217,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["","RKL","2021-06-10","2021-09-08","6","2022","1100","309718095","","","NWA","4010246 0020","Storm- 2021-Purchase Orders - 12014","810300","Allowance Expenses",12.32,"AUD","","CATS","SYS_BCBATCH",10001047,"","",{"$f":"VLOOKUP(U1218,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["","",null,null,"","","","","","","","4010246 0020","","","",5804003.3200000003,"AUD","","","",null,"",""]
["RMWE","COIN","2021-08-31","2021-09-21","6","2022","1100","108488717","","","NWA","4010246 0040","Storm-2021-Purchase Orders - 12047","516203","Legal Expenses",20408.3,"AUD","GSL advice","MKPF","LDONOGHU",0,"","WE",null,"Include","Internal"]
["","",null,null,"","","","","","","","4010246 0040","","","",20408.3,"AUD","","","",null,"",""]
["RMRU","RKL","2021-07-03","2021-07-03","4","2022","1100","309467535","","","NWA","4010246 0070","Storm-2021-Time Sheet - 12002","810141","Corp Snr Mngr NT",1213.3499999999999,"AUD","Attendance on site at Lilydale and relie","AFRU","SYS_BCBATCH",10007809,"","",{"$f":"VLOOKUP(U1222,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-09-10","2021-09-10","6","2022","1100","309725142","","","NWA","4010246 0070","Storm-2021-Time Sheet - 12002","810142","Corp Strat Mngr NT",1472.4,"AUD","","AFRU","SYS_BCBATCH",10000088,"","",{"$f":"VLOOKUP(U1223,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["RMRU","RKL","2021-09-10","2021-09-10","6","2022","1100","309725143","","","NWA","4010246 0070","Storm-2021-Time Sheet - 12002","810142","Corp Strat Mngr NT",1472.4,"AUD","","AFRU","SYS_BCBATCH",10000088,"","",{"$f":"VLOOKUP(U1224,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["","",null,null,"","","","","","","","4010246 0070","","","",4158.1499999999996,"AUD","","","",null,"",""]
["RFBU","COIN","2021-09-29","2021-09-29","6","2022","1100","108504132","","","NWA","4010246 0080","Storm-2021-Purchase Orders - 12002","516100","General IT Support",690,"AUD","PCARD Rodney Berry replacement iPad","BKPFF","WF-BATCH",0,"","SA",null,"Include","Internal"]
["RFBU","COIN","2021-09-29","2021-09-29","6","2022","1100","108504132","","","NWA","4010246 0080","Storm-2021-Purchase Orders - 12002","516404","Minor Equip Purchase",200.87,"AUD","PCARD Rodney Berry Protective case for iPad","BKPFF","WF-BATCH",0,"","SA",null,"Include","Internal"]
["RFBU","COIN","2021-09-29","2021-09-29","6","2022","1100","108504147","","","NWA","4010246 0080","Storm-2021-Purchase Orders - 12002","516100","General IT Support",-759,"AUD","PCARD Rodney Berry replacement iPad","BKPFF","WF-BATCH",0,"","SA",null,"Include","Internal"]
["RFBU","COIN","2021-09-29","2021-09-29","6","2022","1100","108504147","","","NWA","4010246 0080","Storm-2021-Purchase Orders - 12002","516404","Minor Equip Purchase",-220.96,"AUD","PCARD Rodney Berry Protective case for iPad","BKPFF","WF-BATCH",0,"","SA",null,"Include","Internal"]
["RFBU","COIN","2021-07-24","2021-07-24","4","2022","1100","108276188","","","NWA","4010246 0080","Storm-2021-Purchase Orders - 12002","516100","General IT Support",759,"AUD","PCARD Rodney Berry replacement iPad","BKPFF","SYS_BCBATCH",0,"","SA",null,"Include","Internal"]
["RFBU","COIN","2021-07-24","2021-07-24","4","2022","1100","108277707","","","NWA","4010246 0080","Storm-2021-Purchase Orders - 12002","516404","Minor Equip Purchase",220.96,"AUD","PCARD Rodney Berry Protective case for iPad","BKPFF","SYS_BCBATCH",0,"","SA",null,"Include","Internal"]
["RMWE","COIN","2021-07-22","2021-08-01","5","2022","1100","108288931","","","NWA","4010246 0080","Storm-2021-Purchase Orders - 12002","516203","Legal Expenses",3136,"AUD","Dandenong customers supply","MKPF","LDONOGHU",0,"","WE",null,"Include","Internal"]
["","",null,null,"","","","","","","","4010246 0080","","","",4026.87,"AUD","","","",null,"",""]
["RMRU","RKL","2021-06-16","2021-06-16","3","2022","1100","309350094","","","NWA","4010246 0090","Storm-2021-Time Sheet - 12388","810160","Corp Manager NT",896.85,"AUD","Volunteered to support the storm recover","AFRU","SYS_BCBATCH",10006526,"","",{"$f":"VLOOKUP(U1234,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-06-28","2021-06-28","3","2022","1100","309381999","","","NWA","4010246 0090","Storm-2021-Time Sheet - 12388","810143","Corp Support NT",477.9,"AUD","","AFRU","SYS_BCBATCH",10008923,"","",{"$f":"VLOOKUP(U1235,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-06-28","2021-06-28","3","2022","1100","309382000","","","NWA","4010246 0090","Storm-2021-Time Sheet - 12388","810143","Corp Support NT",477.9,"AUD","","AFRU","SYS_BCBATCH",10008923,"","",{"$f":"VLOOKUP(U1236,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-06-28","2021-06-28","3","2022","1100","309382001","","","NWA","4010246 0090","Storm-2021-Time Sheet - 12388","810143","Corp Support NT",477.9,"AUD","","AFRU","SYS_BCBATCH",10008923,"","",{"$f":"VLOOKUP(U1237,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-06-28","2021-06-28","3","2022","1100","309382002","","","NWA","4010246 0090","Storm-2021-Time Sheet - 12388","810143","Corp Support NT",477.9,"AUD","","AFRU","SYS_BCBATCH",10008923,"","",{"$f":"VLOOKUP(U1238,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-06-28","2021-06-28","3","2022","1100","309382003","","","NWA","4010246 0090","Storm-2021-Time Sheet - 12388","810143","Corp Support NT",477.9,"AUD","","AFRU","SYS_BCBATCH",10008923,"","",{"$f":"VLOOKUP(U1239,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["","RKL","2021-06-19","2021-07-03","4","2022","1100","309465861","","","NWA","4010246 0090","Storm-2021-Time Sheet - 12388","810300","Allowance Expenses",1264.6500000000001,"AUD","","CATS","SYS_BCBATCH",10008959,"","",{"$f":"VLOOKUP(U1240,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["","RKL","2021-06-10","2021-07-20","4","2022","1100","309487418","","","NWA","4010246 0090","Storm-2021-Time Sheet - 12388","810300","Allowance Expenses",449.64,"AUD","Storm response","CATS","SYS_BCBATCH",10007036,"","",{"$f":"VLOOKUP(U1241,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["","RKL","2021-06-10","2021-07-20","4","2022","1100","309487418","","","NWA","4010246 0090","Storm-2021-Time Sheet - 12388","810300","Allowance Expenses",2192.06,"AUD","","CATS","SYS_BCBATCH",10007036,"","",{"$f":"VLOOKUP(U1242,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["","RKL","2021-06-10","2021-07-20","4","2022","1100","309487418","","","NWA","4010246 0090","Storm-2021-Time Sheet - 12388","810300","Allowance Expenses",2192.06,"AUD","","CATS","SYS_BCBATCH",10007036,"","",{"$f":"VLOOKUP(U1243,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["","RKL","2021-06-10","2021-07-20","4","2022","1100","309487418","","","NWA","4010246 0090","Storm-2021-Time Sheet - 12388","810300","Allowance Expenses",562.04999999999995,"AUD","","CATS","SYS_BCBATCH",10007036,"","",{"$f":"VLOOKUP(U1244,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["","RKL","2021-06-10","2021-07-20","4","2022","1100","309487418","","","NWA","4010246 0090","Storm-2021-Time Sheet - 12388","810300","Allowance Expenses",224.82,"AUD","","CATS","SYS_BCBATCH",10007036,"","",{"$f":"VLOOKUP(U1245,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["","RKL","2021-06-10","2021-07-20","4","2022","1100","309487418","","","NWA","4010246 0090","Storm-2021-Time Sheet - 12388","810300","Allowance Expenses",562.04999999999995,"AUD","","CATS","SYS_BCBATCH",10007036,"","",{"$f":"VLOOKUP(U1246,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["","RKL","2021-06-10","2021-07-20","4","2022","1100","309487418","","","NWA","4010246 0090","Storm-2021-Time Sheet - 12388","810300","Allowance Expenses",562.04999999999995,"AUD","","CATS","SYS_BCBATCH",10007036,"","",{"$f":"VLOOKUP(U1247,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["","RKL","2021-06-13","2021-07-26","4","2022","1100","309499694","","","NWA","4010246 0090","Storm-2021-Time Sheet - 12388","810300","Allowance Expenses",320.33999999999997,"AUD","","CATS","SYS_BCBATCH",10007034,"","",{"$f":"VLOOKUP(U1248,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["","RKL","2021-06-13","2021-07-26","4","2022","1100","309499694","","","NWA","4010246 0090","Storm-2021-Time Sheet - 12388","810300","Allowance Expenses",640.67999999999995,"AUD","","CATS","SYS_BCBATCH",10007034,"","",{"$f":"VLOOKUP(U1249,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["","RKL","2021-06-13","2021-07-26","4","2022","1100","309501306","","","NWA","4010246 0090","Storm-2021-Time Sheet - 12388","810300","Allowance Expenses",810.9,"AUD","Storm response social media from 11:30 a","CATS","SYS_BCBATCH",10010000,"","",{"$f":"VLOOKUP(U1250,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["","RKL","2021-06-13","2021-07-26","4","2022","1100","309501306","","","NWA","4010246 0090","Storm-2021-Time Sheet - 12388","810300","Allowance Expenses",608.17999999999995,"AUD","Storm response assistance working 9:00am","CATS","SYS_BCBATCH",10010000,"","",{"$f":"VLOOKUP(U1251,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["RMRU","RKL","2021-07-26","2021-07-26","4","2022","1100","309501625","","","NWA","4010246 0090","Storm-2021-Time Sheet - 12388","810143","Corp Support NT",54.06,"AUD","Storm response","AFRU","SYS_BCBATCH",10010000,"","",{"$f":"VLOOKUP(U1252,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["RMRU","RKL","2021-07-26","2021-07-26","4","2022","1100","309501626","","","NWA","4010246 0090","Storm-2021-Time Sheet - 12388","810243","Corp Support OT",324.36,"AUD","Storm response","AFRU","SYS_BCBATCH",10010000,"","",{"$f":"VLOOKUP(U1253,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["RMRU","RKL","2021-07-26","2021-07-26","4","2022","1100","309501627","","","NWA","4010246 0090","Storm-2021-Time Sheet - 12388","810143","Corp Support NT",54.06,"AUD","Storm response","AFRU","SYS_BCBATCH",10010000,"","",{"$f":"VLOOKUP(U1254,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["RMRU","RKL","2021-07-26","2021-07-26","4","2022","1100","309501628","","","NWA","4010246 0090","Storm-2021-Time Sheet - 12388","810143","Corp Support NT",54.06,"AUD","Storm response","AFRU","SYS_BCBATCH",10010000,"","",{"$f":"VLOOKUP(U1255,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["RMRU","RKL","2021-07-26","2021-07-26","4","2022","1100","309501629","","","NWA","4010246 0090","Storm-2021-Time Sheet - 12388","810143","Corp Support NT",175.7,"AUD","Storm response","AFRU","SYS_BCBATCH",10010000,"","",{"$f":"VLOOKUP(U1256,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["RMRU","RKL","2021-07-26","2021-07-26","4","2022","1100","309501630","","","NWA","4010246 0090","Storm-2021-Time Sheet - 12388","810143","Corp Support NT",175.7,"AUD","Storm response","AFRU","SYS_BCBATCH",10010000,"","",{"$f":"VLOOKUP(U1257,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["RMRU","RKL","2021-07-26","2021-07-26","4","2022","1100","309501631","","","NWA","4010246 0090","Storm-2021-Time Sheet - 12388","810143","Corp Support NT",54.06,"AUD","Storm response","AFRU","SYS_BCBATCH",10010000,"","",{"$f":"VLOOKUP(U1258,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["RMRU","RKL","2021-07-26","2021-07-26","4","2022","1100","309501632","","","NWA","4010246 0090","Storm-2021-Time Sheet - 12388","810143","Corp Support NT",135.15,"AUD","Storm response","AFRU","SYS_BCBATCH",10010000,"","",{"$f":"VLOOKUP(U1259,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["","",null,null,"","","","","","","","4010246 0090","","","",14702.98,"AUD","","","",null,"",""]
["RFBU","COIN","2021-07-24","2021-07-24","4","2022","1100","108276188","","","NWA","4010246 0100","Storm-2021-Purchase Orders - 12388","516413","Light Meals on Site",50.25,"AUD","PCARD Nathan Martinz Faults CSC Night Shift Dinner","BKPFF","SYS_BCBATCH",0,"","SA",null,"Include","Internal"]
["","RKL","2021-06-14","2021-06-21","3","2022","1100","309359144","","","NWA","4010246 0100","Storm-2021-Purchase Orders - 12388","810300","Allowance Expenses",76.23,"AUD","Volunteered to support the storm recover","CATS","SYS_BCBATCH",10006526,"","",{"$f":"VLOOKUP(U1262,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["","RKL","2021-06-14","2021-06-21","3","2022","1100","309359144","","","NWA","4010246 0100","Storm-2021-Purchase Orders - 12388","810300","Allowance Expenses",59.29,"AUD","Volunteered to support the storm recover","CATS","SYS_BCBATCH",10006526,"","",{"$f":"VLOOKUP(U1263,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-06-29","2021-06-29","3","2022","1100","309382768","","","NWA","4010246 0100","Storm-2021-Purchase Orders - 12388","810118","Project Manager NT",854.03,"AUD","","AFRU","SYS_BCBATCH",10000641,"","",{"$f":"VLOOKUP(U1264,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-06-29","2021-06-29","3","2022","1100","309382769","","","NWA","4010246 0100","Storm-2021-Purchase Orders - 12388","810118","Project Manager NT",854.03,"AUD","","AFRU","SYS_BCBATCH",10000641,"","",{"$f":"VLOOKUP(U1265,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["","RKL","2021-06-19","2021-07-03","4","2022","1100","309465861","","","NWA","4010246 0100","Storm-2021-Purchase Orders - 12388","810300","Allowance Expenses",67.099999999999994,"AUD","","CATS","SYS_BCBATCH",10008959,"","",{"$f":"VLOOKUP(U1266,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["","RKL","2021-06-19","2021-07-03","4","2022","1100","309465861","","","NWA","4010246 0100","Storm-2021-Purchase Orders - 12388","810300","Allowance Expenses",67.099999999999994,"AUD","","CATS","SYS_BCBATCH",10008959,"","",{"$f":"VLOOKUP(U1267,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["","RKL","2021-06-24","2021-07-03","4","2022","1100","309465876","","","NWA","4010246 0100","Storm-2021-Purchase Orders - 12388","810300","Allowance Expenses",70.56,"AUD","Worked in Olinda at the Community Hub fo","CATS","SYS_BCBATCH",10008923,"","",{"$f":"VLOOKUP(U1268,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["","",null,null,"","","","","","","","4010246 0100","","","",2098.59,"AUD","","","",null,"",""]
["RMRU","RKL","2021-06-17","2021-06-17","3","2022","1100","309353569","","","NWA","4010246 0110","Storm-2021-Time Sheet - 12627","810122","Corp Prof Exp NT",716.1,"AUD","Storm Recovery - Support Hubs","AFRU","SYS_BCBATCH",10009794,"","",{"$f":"VLOOKUP(U1270,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-06-18","2021-06-18","3","2022","1100","309359105","","","NWA","4010246 0110","Storm-2021-Time Sheet - 12627","810122","Corp Prof Exp NT",50.59,"AUD","","AFRU","SYS_BCBATCH",10009875,"","",{"$f":"VLOOKUP(U1271,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-06-18","2021-06-18","3","2022","1100","309359106","","","NWA","4010246 0110","Storm-2021-Time Sheet - 12627","810122","Corp Prof Exp NT",505.9,"AUD","","AFRU","SYS_BCBATCH",10009875,"","",{"$f":"VLOOKUP(U1272,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-06-18","2021-06-18","3","2022","1100","309359129","","","NWA","4010246 0110","Storm-2021-Time Sheet - 12627","810122","Corp Prof Exp NT",151.77000000000001,"AUD","","AFRU","SYS_BCBATCH",10009875,"","",{"$f":"VLOOKUP(U1273,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-06-18","2021-06-18","3","2022","1100","309359130","","","NWA","4010246 0110","Storm-2021-Time Sheet - 12627","810122","Corp Prof Exp NT",50.59,"AUD","","AFRU","SYS_BCBATCH",10009875,"","",{"$f":"VLOOKUP(U1274,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-06-22","2021-06-22","3","2022","1100","309361797","","","NWA","4010246 0110","Storm-2021-Time Sheet - 12627","810160","Corp Manager NT",298.95,"AUD","investigating payment options","AFRU","SYS_BCBATCH",10005266,"","",{"$f":"VLOOKUP(U1275,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-06-22","2021-06-22","3","2022","1100","309361798","","","NWA","4010246 0110","Storm-2021-Time Sheet - 12627","810160","Corp Manager NT",777.27,"AUD","Olinda Hub - Including travel time","AFRU","SYS_BCBATCH",10005266,"","",{"$f":"VLOOKUP(U1276,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-06-22","2021-06-22","3","2022","1100","309361810","","","NWA","4010246 0110","Storm-2021-Time Sheet - 12627","810141","Corp Snr Mngr NT",1213.3499999999999,"AUD","","AFRU","SYS_BCBATCH",10000333,"","",{"$f":"VLOOKUP(U1277,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-06-22","2021-06-22","3","2022","1100","309361811","","","NWA","4010246 0110","Storm-2021-Time Sheet - 12627","810141","Corp Snr Mngr NT",1213.3499999999999,"AUD","","AFRU","SYS_BCBATCH",10000333,"","",{"$f":"VLOOKUP(U1278,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-06-22","2021-06-22","3","2022","1100","309361812","","","NWA","4010246 0110","Storm-2021-Time Sheet - 12627","810141","Corp Snr Mngr NT",1375.13,"AUD","","AFRU","SYS_BCBATCH",10000333,"","",{"$f":"VLOOKUP(U1279,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-06-22","2021-06-22","3","2022","1100","309361813","","","NWA","4010246 0110","Storm-2021-Time Sheet - 12627","810141","Corp Snr Mngr NT",1375.13,"AUD","","AFRU","SYS_BCBATCH",10000333,"","",{"$f":"VLOOKUP(U1280,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-06-22","2021-06-22","3","2022","1100","309361814","","","NWA","4010246 0110","Storm-2021-Time Sheet - 12627","810141","Corp Snr Mngr NT",1213.3499999999999,"AUD","","AFRU","SYS_BCBATCH",10000333,"","",{"$f":"VLOOKUP(U1281,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-06-22","2021-06-22","3","2022","1100","309361815","","","NWA","4010246 0110","Storm-2021-Time Sheet - 12627","810141","Corp Snr Mngr NT",1213.3499999999999,"AUD","","AFRU","SYS_BCBATCH",10000333,"","",{"$f":"VLOOKUP(U1282,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-06-22","2021-06-22","3","2022","1100","309361816","","","NWA","4010246 0110","Storm-2021-Time Sheet - 12627","810141","Corp Snr Mngr NT",1213.3499999999999,"AUD","","AFRU","SYS_BCBATCH",10000333,"","",{"$f":"VLOOKUP(U1283,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-06-22","2021-06-22","3","2022","1100","309361817","","","NWA","4010246 0110","Storm-2021-Time Sheet - 12627","810141","Corp Snr Mngr NT",1213.3499999999999,"AUD","","AFRU","SYS_BCBATCH",10000333,"","",{"$f":"VLOOKUP(U1284,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-06-22","2021-06-22","3","2022","1100","309361818","","","NWA","4010246 0110","Storm-2021-Time Sheet - 12627","810141","Corp Snr Mngr NT",1213.3499999999999,"AUD","","AFRU","SYS_BCBATCH",10000333,"","",{"$f":"VLOOKUP(U1285,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-06-22","2021-06-22","3","2022","1100","309361819","","","NWA","4010246 0110","Storm-2021-Time Sheet - 12627","810141","Corp Snr Mngr NT",1375.13,"AUD","","AFRU","SYS_BCBATCH",10000333,"","",{"$f":"VLOOKUP(U1286,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-06-22","2021-06-22","3","2022","1100","309361820","","","NWA","4010246 0110","Storm-2021-Time Sheet - 12627","810141","Corp Snr Mngr NT",1375.13,"AUD","","AFRU","SYS_BCBATCH",10000333,"","",{"$f":"VLOOKUP(U1287,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-06-22","2021-06-22","3","2022","1100","309361821","","","NWA","4010246 0110","Storm-2021-Time Sheet - 12627","810141","Corp Snr Mngr NT",1213.3499999999999,"AUD","","AFRU","SYS_BCBATCH",10000333,"","",{"$f":"VLOOKUP(U1288,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-06-22","2021-06-22","3","2022","1100","309361822","","","NWA","4010246 0110","Storm-2021-Time Sheet - 12627","810141","Corp Snr Mngr NT",1213.3499999999999,"AUD","","AFRU","SYS_BCBATCH",10000333,"","",{"$f":"VLOOKUP(U1289,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-06-22","2021-06-22","3","2022","1100","309361823","","","NWA","4010246 0110","Storm-2021-Time Sheet - 12627","810141","Corp Snr Mngr NT",1213.3499999999999,"AUD","","AFRU","SYS_BCBATCH",10000333,"","",{"$f":"VLOOKUP(U1290,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-06-22","2021-06-22","3","2022","1100","309361833","","","NWA","4010246 0110","Storm-2021-Time Sheet - 12627","810160","Corp Manager NT",958.73,"AUD","","AFRU","SYS_BCBATCH",10009915,"","",{"$f":"VLOOKUP(U1291,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-06-22","2021-06-22","3","2022","1100","309361834","","","NWA","4010246 0110","Storm-2021-Time Sheet - 12627","810160","Corp Manager NT",958.73,"AUD","","AFRU","SYS_BCBATCH",10009915,"","",{"$f":"VLOOKUP(U1292,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-06-22","2021-06-22","3","2022","1100","309361835","","","NWA","4010246 0110","Storm-2021-Time Sheet - 12627","810160","Corp Manager NT",958.73,"AUD","","AFRU","SYS_BCBATCH",10009915,"","",{"$f":"VLOOKUP(U1293,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-06-23","2021-06-23","3","2022","1100","309362450","","","NWA","4010246 0110","Storm-2021-Time Sheet - 12627","810222","Corp Prof Exp OT",1074.1500000000001,"AUD","","AFRU","SYS_BCBATCH",10009794,"","",{"$f":"VLOOKUP(U1294,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-06-23","2021-06-23","3","2022","1100","309362451","","","NWA","4010246 0110","Storm-2021-Time Sheet - 12627","810222","Corp Prof Exp OT",1217.3699999999999,"AUD","Storm Recovery - Weekend Work","AFRU","SYS_BCBATCH",10009794,"","",{"$f":"VLOOKUP(U1295,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-06-23","2021-06-23","3","2022","1100","309362453","","","NWA","4010246 0110","Storm-2021-Time Sheet - 12627","810141","Corp Snr Mngr NT",1213.3499999999999,"AUD","","AFRU","SYS_BCBATCH",10000333,"","",{"$f":"VLOOKUP(U1296,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-06-23","2021-06-23","3","2022","1100","309363022","","","NWA","4010246 0110","Storm-2021-Time Sheet - 12627","810120","Corp Ops Lead NT",611.54999999999995,"AUD","","AFRU","SYS_BCBATCH",10001974,"","",{"$f":"VLOOKUP(U1297,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-06-25","2021-06-25","3","2022","1100","309379852","","","NWA","4010246 0110","Storm-2021-Time Sheet - 12627","810160","Corp Manager NT",958.73,"AUD","","AFRU","SYS_BCBATCH",10009915,"","",{"$f":"VLOOKUP(U1298,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-06-29","2021-06-29","3","2022","1100","309382746","","","NWA","4010246 0110","Storm-2021-Time Sheet - 12627","810141","Corp Snr Mngr NT",1213.3499999999999,"AUD","","AFRU","SYS_BCBATCH",10000333,"","",{"$f":"VLOOKUP(U1299,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-06-29","2021-06-29","3","2022","1100","309382747","","","NWA","4010246 0110","Storm-2021-Time Sheet - 12627","810141","Corp Snr Mngr NT",1213.3499999999999,"AUD","","AFRU","SYS_BCBATCH",10000333,"","",{"$f":"VLOOKUP(U1300,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-06-29","2021-06-29","3","2022","1100","309382748","","","NWA","4010246 0110","Storm-2021-Time Sheet - 12627","810141","Corp Snr Mngr NT",1213.3499999999999,"AUD","","AFRU","SYS_BCBATCH",10000333,"","",{"$f":"VLOOKUP(U1301,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-06-29","2021-06-29","3","2022","1100","309382749","","","NWA","4010246 0110","Storm-2021-Time Sheet - 12627","810141","Corp Snr Mngr NT",1213.3499999999999,"AUD","","AFRU","SYS_BCBATCH",10000333,"","",{"$f":"VLOOKUP(U1302,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-06-29","2021-06-29","3","2022","1100","309382751","","","NWA","4010246 0110","Storm-2021-Time Sheet - 12627","810141","Corp Snr Mngr NT",647.12,"AUD","Storm assistance at Monbulk","AFRU","SYS_BCBATCH",10008019,"","",{"$f":"VLOOKUP(U1303,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-06-29","2021-06-29","3","2022","1100","309383432","","","NWA","4010246 0110","Storm-2021-Time Sheet - 12627","810124","Corp Prof Spec NT",786.87,"AUD","","AFRU","SYS_BCBATCH",10001625,"","",{"$f":"VLOOKUP(U1304,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-06-29","2021-06-29","3","2022","1100","309383434","","","NWA","4010246 0110","Storm-2021-Time Sheet - 12627","810160","Corp Manager NT",958.73,"AUD","","AFRU","SYS_BCBATCH",10009831,"","",{"$f":"VLOOKUP(U1305,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-06-29","2021-06-29","3","2022","1100","309383435","","","NWA","4010246 0110","Storm-2021-Time Sheet - 12627","810160","Corp Manager NT",958.73,"AUD","","AFRU","SYS_BCBATCH",10009831,"","",{"$f":"VLOOKUP(U1306,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-06-29","2021-06-29","3","2022","1100","309383436","","","NWA","4010246 0110","Storm-2021-Time Sheet - 12627","810160","Corp Manager NT",657.69,"AUD","Support Olinda Hub","AFRU","SYS_BCBATCH",10005266,"","",{"$f":"VLOOKUP(U1307,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-06-30","2021-06-30","3","2022","1100","309384314","","","NWA","4010246 0110","Storm-2021-Time Sheet - 12627","810141","Corp Snr Mngr NT",1213.3499999999999,"AUD","","AFRU","SYS_BCBATCH",10000333,"","",{"$f":"VLOOKUP(U1308,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-07-03","2021-07-03","4","2022","1100","309467515","","","NWA","4010246 0110","Storm-2021-Time Sheet - 12627","810142","Corp Strat Mngr NT",1380.38,"AUD","","AFRU","SYS_BCBATCH",10006840,"","",{"$f":"VLOOKUP(U1309,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-07-03","2021-07-03","4","2022","1100","309467550","","","NWA","4010246 0110","Storm-2021-Time Sheet - 12627","810124","Corp Prof Spec NT",1124.0999999999999,"AUD","","AFRU","SYS_BCBATCH",10006445,"","",{"$f":"VLOOKUP(U1310,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-07-03","2021-07-03","4","2022","1100","309467551","","","NWA","4010246 0110","Storm-2021-Time Sheet - 12627","810124","Corp Prof Spec NT",1124.0999999999999,"AUD","","AFRU","SYS_BCBATCH",10006445,"","",{"$f":"VLOOKUP(U1311,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-07-03","2021-07-03","4","2022","1100","309467552","","","NWA","4010246 0110","Storm-2021-Time Sheet - 12627","810124","Corp Prof Spec NT",1742.36,"AUD","","AFRU","SYS_BCBATCH",10006445,"","",{"$f":"VLOOKUP(U1312,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-07-03","2021-07-03","4","2022","1100","309467553","","","NWA","4010246 0110","Storm-2021-Time Sheet - 12627","810124","Corp Prof Spec NT",1742.36,"AUD","","AFRU","SYS_BCBATCH",10006445,"","",{"$f":"VLOOKUP(U1313,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-07-03","2021-07-03","4","2022","1100","309467554","","","NWA","4010246 0110","Storm-2021-Time Sheet - 12627","810124","Corp Prof Spec NT",1573.74,"AUD","","AFRU","SYS_BCBATCH",10006445,"","",{"$f":"VLOOKUP(U1314,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-07-03","2021-07-03","4","2022","1100","309467555","","","NWA","4010246 0110","Storm-2021-Time Sheet - 12627","810124","Corp Prof Spec NT",955.49,"AUD","","AFRU","SYS_BCBATCH",10006445,"","",{"$f":"VLOOKUP(U1315,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-07-03","2021-07-03","4","2022","1100","309467556","","","NWA","4010246 0110","Storm-2021-Time Sheet - 12627","810124","Corp Prof Spec NT",618.26,"AUD","","AFRU","SYS_BCBATCH",10006445,"","",{"$f":"VLOOKUP(U1316,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-07-03","2021-07-03","4","2022","1100","309467557","","","NWA","4010246 0110","Storm-2021-Time Sheet - 12627","810124","Corp Prof Spec NT",337.23,"AUD","","AFRU","SYS_BCBATCH",10006445,"","",{"$f":"VLOOKUP(U1317,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-07-03","2021-07-03","4","2022","1100","309467558","","","NWA","4010246 0110","Storm-2021-Time Sheet - 12627","810124","Corp Prof Spec NT",1461.33,"AUD","","AFRU","SYS_BCBATCH",10006445,"","",{"$f":"VLOOKUP(U1318,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-07-03","2021-07-03","4","2022","1100","309467559","","","NWA","4010246 0110","Storm-2021-Time Sheet - 12627","810124","Corp Prof Spec NT",1180.31,"AUD","","AFRU","SYS_BCBATCH",10006445,"","",{"$f":"VLOOKUP(U1319,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-07-03","2021-07-03","4","2022","1100","309467560","","","NWA","4010246 0110","Storm-2021-Time Sheet - 12627","810124","Corp Prof Spec NT",1124.0999999999999,"AUD","","AFRU","SYS_BCBATCH",10006445,"","",{"$f":"VLOOKUP(U1320,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-07-03","2021-07-03","4","2022","1100","309467561","","","NWA","4010246 0110","Storm-2021-Time Sheet - 12627","810124","Corp Prof Spec NT",1067.9000000000001,"AUD","","AFRU","SYS_BCBATCH",10006445,"","",{"$f":"VLOOKUP(U1321,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-07-03","2021-07-03","4","2022","1100","309467562","","","NWA","4010246 0110","Storm-2021-Time Sheet - 12627","810124","Corp Prof Spec NT",1180.31,"AUD","","AFRU","SYS_BCBATCH",10006445,"","",{"$f":"VLOOKUP(U1322,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-07-03","2021-07-03","4","2022","1100","309467577","","","NWA","4010246 0110","Storm-2021-Time Sheet - 12627","810122","Corp Prof Exp NT",716.1,"AUD","June storm costs - call centre assistanc","AFRU","SYS_BCBATCH",10004595,"","",{"$f":"VLOOKUP(U1323,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-07-03","2021-07-03","4","2022","1100","309467578","","","NWA","4010246 0110","Storm-2021-Time Sheet - 12627","810122","Corp Prof Exp NT",716.1,"AUD","June storm costs - call centre assistanc","AFRU","SYS_BCBATCH",10004595,"","",{"$f":"VLOOKUP(U1324,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-07-03","2021-07-03","4","2022","1100","309467579","","","NWA","4010246 0110","Storm-2021-Time Sheet - 12627","810122","Corp Prof Exp NT",716.1,"AUD","June storm costs - call centre assistanc","AFRU","SYS_BCBATCH",10004595,"","",{"$f":"VLOOKUP(U1325,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-07-03","2021-07-03","4","2022","1100","309467580","","","NWA","4010246 0110","Storm-2021-Time Sheet - 12627","810222","Corp Prof Exp OT",859.32,"AUD","June storm costs - call centre assistanc","AFRU","SYS_BCBATCH",10004595,"","",{"$f":"VLOOKUP(U1326,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-07-09","2021-07-09","4","2022","1100","309473918","","","NWA","4010246 0110","Storm-2021-Time Sheet - 12627","810124","Corp Prof Spec NT",843.08,"AUD","","AFRU","SYS_BCBATCH",10006445,"","",{"$f":"VLOOKUP(U1327,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-07-09","2021-07-09","4","2022","1100","309473919","","","NWA","4010246 0110","Storm-2021-Time Sheet - 12627","810124","Corp Prof Spec NT",843.08,"AUD","","AFRU","SYS_BCBATCH",10006445,"","",{"$f":"VLOOKUP(U1328,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-07-09","2021-07-09","4","2022","1100","309473920","","","NWA","4010246 0110","Storm-2021-Time Sheet - 12627","810124","Corp Prof Spec NT",843.08,"AUD","","AFRU","SYS_BCBATCH",10006445,"","",{"$f":"VLOOKUP(U1329,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-07-09","2021-07-09","4","2022","1100","309473921","","","NWA","4010246 0110","Storm-2021-Time Sheet - 12627","810124","Corp Prof Spec NT",843.08,"AUD","","AFRU","SYS_BCBATCH",10006445,"","",{"$f":"VLOOKUP(U1330,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-07-09","2021-07-09","4","2022","1100","309473922","","","NWA","4010246 0110","Storm-2021-Time Sheet - 12627","810124","Corp Prof Spec NT",843.08,"AUD","","AFRU","SYS_BCBATCH",10006445,"","",{"$f":"VLOOKUP(U1331,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-07-12","2021-07-12","4","2022","1100","309474783","","","NWA","4010246 0110","Storm-2021-Time Sheet - 12627","810141","Corp Snr Mngr NT",1213.3499999999999,"AUD","","AFRU","SYS_BCBATCH",10000333,"","",{"$f":"VLOOKUP(U1332,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-07-12","2021-07-12","4","2022","1100","309474784","","","NWA","4010246 0110","Storm-2021-Time Sheet - 12627","810141","Corp Snr Mngr NT",1213.3499999999999,"AUD","","AFRU","SYS_BCBATCH",10000333,"","",{"$f":"VLOOKUP(U1333,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-07-12","2021-07-12","4","2022","1100","309474785","","","NWA","4010246 0110","Storm-2021-Time Sheet - 12627","810141","Corp Snr Mngr NT",1213.3499999999999,"AUD","","AFRU","SYS_BCBATCH",10000333,"","",{"$f":"VLOOKUP(U1334,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-07-12","2021-07-12","4","2022","1100","309474786","","","NWA","4010246 0110","Storm-2021-Time Sheet - 12627","810141","Corp Snr Mngr NT",1213.3499999999999,"AUD","","AFRU","SYS_BCBATCH",10000333,"","",{"$f":"VLOOKUP(U1335,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-07-12","2021-07-12","4","2022","1100","309474787","","","NWA","4010246 0110","Storm-2021-Time Sheet - 12627","810141","Corp Snr Mngr NT",1213.3499999999999,"AUD","","AFRU","SYS_BCBATCH",10000333,"","",{"$f":"VLOOKUP(U1336,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["","",null,null,"","","","","","","","4010246 0110","","","",68114.16,"AUD","","","",null,"",""]
["RFBU","COIN","2021-09-29","2021-09-29","6","2022","1100","108504137","","","NWA","4010246 0120","Storm-2021Purchase Orders - 12627","521100","Materials",226.18,"AUD","EEXP Luciana Bitelman Power banks for Storm relief","BKPFF","WF-BATCH",0,"","SA",null,"Include","Internal"]
["RFBU","COIN","2021-09-29","2021-09-29","6","2022","1100","108504153","","","NWA","4010246 0120","Storm-2021Purchase Orders - 12627","521100","Materials",-248.8,"AUD","EEXP Luciana Bitelman Power banks for Storm relief","BKPFF","WF-BATCH",0,"","SA",null,"Include","Internal"]
["RFBU","COIN","2021-06-12","2021-06-18","3","2022","1100","108157856","","","NWA","4010246 0120","Storm-2021Purchase Orders - 12627","516400","General Expenses",14220,"AUD","Order by Charlie","BKPFF","WF-BATCH",0,"","KR",null,"Include","Internal"]
["RFBU","COIN","2021-07-29","2021-07-29","4","2022","1100","108285165","","","NWA","4010246 0120","Storm-2021Purchase Orders - 12627","516101","IT Software",13525,"AUD","Reallocate Storm costs to projcts","BKPFF","WF-BATCH",0,"","AB",null,"Include","Internal"]
["RFBU","COIN","2021-08-02","2021-08-24","5","2022","1100","108378972","","","NWA","4010246 0120","Storm-2021Purchase Orders - 12627","516400","General Expenses",22985,"AUD","","BKPFF","WF-BATCH",0,"","KR",null,"Include","Internal"]
["RFBU","COIN","2021-08-24","2021-08-24","5","2022","1100","108384819","","","NWA","4010246 0120","Storm-2021Purchase Orders - 12627","521100","Materials",248.8,"AUD","EEXP Luciana Bitelman Power banks for Storm relief","BKPFF","SYS_BCBATCH",0,"","SA",null,"Include","Internal"]
["","",null,null,"","","","","","","","4010246 0120","","","",50956.18,"AUD","","","",null,"",""]
["","RKL","2021-06-12","2021-06-16","3","2022","1100","309350235","","","NWA","4010246 0130","Storm-2021-Time Sheet - 12006","810300","Allowance Expenses",20.12,"AUD","Storm response","CATS","SYS_BCBATCH",10004696,"","",{"$f":"VLOOKUP(U1345,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["","RKL","2021-06-12","2021-06-16","3","2022","1100","309350235","","","NWA","4010246 0130","Storm-2021-Time Sheet - 12006","810300","Allowance Expenses",20.12,"AUD","Storm response","CATS","SYS_BCBATCH",10004696,"","",{"$f":"VLOOKUP(U1346,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["","RKL","2021-06-12","2021-06-16","3","2022","1100","309350235","","","NWA","4010246 0130","Storm-2021-Time Sheet - 12006","810300","Allowance Expenses",20.12,"AUD","Storm response","CATS","SYS_BCBATCH",10004696,"","",{"$f":"VLOOKUP(U1347,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["","RKL","2021-06-12","2021-06-16","3","2022","1100","309350235","","","NWA","4010246 0130","Storm-2021-Time Sheet - 12006","810300","Allowance Expenses",20.12,"AUD","Storm response","CATS","SYS_BCBATCH",10004696,"","",{"$f":"VLOOKUP(U1348,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-06-16","2021-06-16","3","2022","1100","309351387","","","NWA","4010246 0130","Storm-2021-Time Sheet - 12006","810223","Corp Prof OT",1032.8800000000001,"AUD","Storm response","AFRU","SYS_BCBATCH",10004696,"","",{"$f":"VLOOKUP(U1349,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-06-16","2021-06-16","3","2022","1100","309351388","","","NWA","4010246 0130","Storm-2021-Time Sheet - 12006","810223","Corp Prof OT",1032.8800000000001,"AUD","Storm response","AFRU","SYS_BCBATCH",10004696,"","",{"$f":"VLOOKUP(U1350,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-06-16","2021-06-16","3","2022","1100","309351389","","","NWA","4010246 0130","Storm-2021-Time Sheet - 12006","810223","Corp Prof OT",1420.21,"AUD","Storm response","AFRU","SYS_BCBATCH",10004696,"","",{"$f":"VLOOKUP(U1351,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-06-16","2021-06-16","3","2022","1100","309351390","","","NWA","4010246 0130","Storm-2021-Time Sheet - 12006","810223","Corp Prof OT",645.54999999999995,"AUD","Storm response","AFRU","SYS_BCBATCH",10004696,"","",{"$f":"VLOOKUP(U1352,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-06-18","2021-06-18","3","2022","1100","309359083","","","NWA","4010246 0130","Storm-2021-Time Sheet - 12006","810142","Corp Strat Mngr NT",1541.55,"AUD","Recovery & Distribution Hub Lead","AFRU","SYS_BCBATCH",10004602,"","",{"$f":"VLOOKUP(U1353,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-06-18","2021-06-18","3","2022","1100","309359084","","","NWA","4010246 0130","Storm-2021-Time Sheet - 12006","810142","Corp Strat Mngr NT",1541.55,"AUD","Recovery & Distribution Hub Lead","AFRU","SYS_BCBATCH",10004602,"","",{"$f":"VLOOKUP(U1354,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-06-18","2021-06-18","3","2022","1100","309359085","","","NWA","4010246 0130","Storm-2021-Time Sheet - 12006","810142","Corp Strat Mngr NT",1541.55,"AUD","Recovery & Distribution Hub Lead","AFRU","SYS_BCBATCH",10004602,"","",{"$f":"VLOOKUP(U1355,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-06-18","2021-06-18","3","2022","1100","309359086","","","NWA","4010246 0130","Storm-2021-Time Sheet - 12006","810142","Corp Strat Mngr NT",1541.55,"AUD","Recovery & Distribution Hub Lead","AFRU","SYS_BCBATCH",10004602,"","",{"$f":"VLOOKUP(U1356,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-06-18","2021-06-18","3","2022","1100","309359087","","","NWA","4010246 0130","Storm-2021-Time Sheet - 12006","810142","Corp Strat Mngr NT",1541.55,"AUD","Recovery & Distribution Hub Lead","AFRU","SYS_BCBATCH",10004602,"","",{"$f":"VLOOKUP(U1357,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-06-18","2021-06-18","3","2022","1100","309359088","","","NWA","4010246 0130","Storm-2021-Time Sheet - 12006","810142","Corp Strat Mngr NT",1541.55,"AUD","Recovery & Distribution Hub Lead","AFRU","SYS_BCBATCH",10004602,"","",{"$f":"VLOOKUP(U1358,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-06-22","2021-06-22","3","2022","1100","309361139","","","NWA","4010246 0130","Storm-2021-Time Sheet - 12006","810142","Corp Strat Mngr NT",-1541.55,"AUD","Recovery & Distribution Hub Lead","AFRU","SYS_BCBATCH",10004602,"","",{"$f":"VLOOKUP(U1359,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-06-22","2021-06-22","3","2022","1100","309361140","","","NWA","4010246 0130","Storm-2021-Time Sheet - 12006","810142","Corp Strat Mngr NT",-1541.55,"AUD","","AFRU","SYS_BCBATCH",10004602,"","",{"$f":"VLOOKUP(U1360,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-06-22","2021-06-22","3","2022","1100","309361142","","","NWA","4010246 0130","Storm-2021-Time Sheet - 12006","810142","Corp Strat Mngr NT",-1541.55,"AUD","Recovery & Distribution Hub Lead","AFRU","SYS_BCBATCH",10004602,"","",{"$f":"VLOOKUP(U1361,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-06-22","2021-06-22","3","2022","1100","309361144","","","NWA","4010246 0130","Storm-2021-Time Sheet - 12006","810142","Corp Strat Mngr NT",-1541.55,"AUD","Recovery & Distribution Hub Lead","AFRU","SYS_BCBATCH",10004602,"","",{"$f":"VLOOKUP(U1362,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-06-22","2021-06-22","3","2022","1100","309361145","","","NWA","4010246 0130","Storm-2021-Time Sheet - 12006","810142","Corp Strat Mngr NT",-1541.55,"AUD","","AFRU","SYS_BCBATCH",10004602,"","",{"$f":"VLOOKUP(U1363,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-06-22","2021-06-22","3","2022","1100","309361146","","","NWA","4010246 0130","Storm-2021-Time Sheet - 12006","810142","Corp Strat Mngr NT",-1541.55,"AUD","","AFRU","SYS_BCBATCH",10004602,"","",{"$f":"VLOOKUP(U1364,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-06-22","2021-06-22","3","2022","1100","309361149","","","NWA","4010246 0130","Storm-2021-Time Sheet - 12006","810142","Corp Strat Mngr NT",-1541.55,"AUD","Recovery & Distribution Hub Lead","AFRU","SYS_BCBATCH",10004602,"","",{"$f":"VLOOKUP(U1365,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-06-22","2021-06-22","3","2022","1100","309361150","","","NWA","4010246 0130","Storm-2021-Time Sheet - 12006","810142","Corp Strat Mngr NT",-1541.55,"AUD","Recovery & Distribution Hub Lead","AFRU","SYS_BCBATCH",10004602,"","",{"$f":"VLOOKUP(U1366,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-06-22","2021-06-22","3","2022","1100","309361151","","","NWA","4010246 0130","Storm-2021-Time Sheet - 12006","810142","Corp Strat Mngr NT",-1541.55,"AUD","Recovery & Distribution Hub Lead","AFRU","SYS_BCBATCH",10004602,"","",{"$f":"VLOOKUP(U1367,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-06-22","2021-06-22","3","2022","1100","309361560","","","NWA","4010246 0130","Storm-2021-Time Sheet - 12006","810142","Corp Strat Mngr NT",1541.55,"AUD","","AFRU","SYS_BCBATCH",10004602,"","",{"$f":"VLOOKUP(U1368,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-06-22","2021-06-22","3","2022","1100","309361561","","","NWA","4010246 0130","Storm-2021-Time Sheet - 12006","810142","Corp Strat Mngr NT",1541.55,"AUD","","AFRU","SYS_BCBATCH",10004602,"","",{"$f":"VLOOKUP(U1369,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-06-22","2021-06-22","3","2022","1100","309361562","","","NWA","4010246 0130","Storm-2021-Time Sheet - 12006","810142","Corp Strat Mngr NT",1541.55,"AUD","","AFRU","SYS_BCBATCH",10004602,"","",{"$f":"VLOOKUP(U1370,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-06-22","2021-06-22","3","2022","1100","309361763","","","NWA","4010246 0130","Storm-2021-Time Sheet - 12006","810142","Corp Strat Mngr NT",1541.55,"AUD","EMT - Recovery Hub Strike Team Lead","AFRU","SYS_BCBATCH",10004602,"","",{"$f":"VLOOKUP(U1371,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-06-22","2021-06-22","3","2022","1100","309361764","","","NWA","4010246 0130","Storm-2021-Time Sheet - 12006","810142","Corp Strat Mngr NT",1541.55,"AUD","EMT - Recovery Hub Strike Team Lead","AFRU","SYS_BCBATCH",10004602,"","",{"$f":"VLOOKUP(U1372,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-06-22","2021-06-22","3","2022","1100","309361765","","","NWA","4010246 0130","Storm-2021-Time Sheet - 12006","810142","Corp Strat Mngr NT",1541.55,"AUD","EMT - Recovery Hub Strike Team Lead","AFRU","SYS_BCBATCH",10004602,"","",{"$f":"VLOOKUP(U1373,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-06-22","2021-06-22","3","2022","1100","309361837","","","NWA","4010246 0130","Storm-2021-Time Sheet - 12006","810142","Corp Strat Mngr NT",1541.55,"AUD","EMT - Recovery Hub Strike Team Lead","AFRU","SYS_BCBATCH",10004602,"","",{"$f":"VLOOKUP(U1374,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-06-22","2021-06-22","3","2022","1100","309361838","","","NWA","4010246 0130","Storm-2021-Time Sheet - 12006","810142","Corp Strat Mngr NT",1541.55,"AUD","EMT - Recovery Hub Strike Team Lead","AFRU","SYS_BCBATCH",10004602,"","",{"$f":"VLOOKUP(U1375,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-06-22","2021-06-22","3","2022","1100","309361839","","","NWA","4010246 0130","Storm-2021-Time Sheet - 12006","810142","Corp Strat Mngr NT",1541.55,"AUD","EMT - Recovery Hub Strike Team Lead","AFRU","SYS_BCBATCH",10004602,"","",{"$f":"VLOOKUP(U1376,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-06-22","2021-06-22","3","2022","1100","309361840","","","NWA","4010246 0130","Storm-2021-Time Sheet - 12006","810142","Corp Strat Mngr NT",1541.55,"AUD","EMT - Recovery Hub Strike Team Lead","AFRU","SYS_BCBATCH",10004602,"","",{"$f":"VLOOKUP(U1377,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-06-22","2021-06-22","3","2022","1100","309361841","","","NWA","4010246 0130","Storm-2021-Time Sheet - 12006","810142","Corp Strat Mngr NT",1541.55,"AUD","EMT - Recovery Hub Strike Team Lead","AFRU","SYS_BCBATCH",10004602,"","",{"$f":"VLOOKUP(U1378,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-06-22","2021-06-22","3","2022","1100","309361842","","","NWA","4010246 0130","Storm-2021-Time Sheet - 12006","810142","Corp Strat Mngr NT",1541.55,"AUD","EMT - Recovery Hub Strike Team Lead","AFRU","SYS_BCBATCH",10004602,"","",{"$f":"VLOOKUP(U1379,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-06-24","2021-06-24","3","2022","1100","309362143","","","NWA","4010246 0130","Storm-2021-Time Sheet - 12006","810223","Corp Prof OT",-1032.8800000000001,"AUD","Storm response","AFRU","SYS_BCBATCH",10004696,"","",{"$f":"VLOOKUP(U1380,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-06-24","2021-06-24","3","2022","1100","309362144","","","NWA","4010246 0130","Storm-2021-Time Sheet - 12006","810223","Corp Prof OT",-645.54999999999995,"AUD","Storm response","AFRU","SYS_BCBATCH",10004696,"","",{"$f":"VLOOKUP(U1381,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-06-24","2021-06-24","3","2022","1100","309362145","","","NWA","4010246 0130","Storm-2021-Time Sheet - 12006","810223","Corp Prof OT",-1032.8800000000001,"AUD","Storm response","AFRU","SYS_BCBATCH",10004696,"","",{"$f":"VLOOKUP(U1382,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-06-24","2021-06-24","3","2022","1100","309362146","","","NWA","4010246 0130","Storm-2021-Time Sheet - 12006","810223","Corp Prof OT",-1420.21,"AUD","Storm response","AFRU","SYS_BCBATCH",10004696,"","",{"$f":"VLOOKUP(U1383,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-06-23","2021-06-23","3","2022","1100","309362454","","","NWA","4010246 0130","Storm-2021-Time Sheet - 12006","810142","Corp Strat Mngr NT",1541.55,"AUD","EMT - Recovery Hub Strike Team Lead","AFRU","SYS_BCBATCH",10004602,"","",{"$f":"VLOOKUP(U1384,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["","RKL","2021-06-10","2021-06-24","3","2022","1100","309362556","","","NWA","4010246 0130","Storm-2021-Time Sheet - 12006","810300","Allowance Expenses",1032.8800000000001,"AUD","Storm Response - SWAT Strike Team","CATS","SYS_BCBATCH",10004696,"","",{"$f":"VLOOKUP(U1385,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["","RKL","2021-06-10","2021-06-24","3","2022","1100","309362556","","","NWA","4010246 0130","Storm-2021-Time Sheet - 12006","810300","Allowance Expenses",1032.8800000000001,"AUD","Storm Response - SWAT Strike Team","CATS","SYS_BCBATCH",10004696,"","",{"$f":"VLOOKUP(U1386,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["","RKL","2021-06-10","2021-06-24","3","2022","1100","309362556","","","NWA","4010246 0130","Storm-2021-Time Sheet - 12006","810300","Allowance Expenses",1420.21,"AUD","Storm Response - SWAT Strike Team","CATS","SYS_BCBATCH",10004696,"","",{"$f":"VLOOKUP(U1387,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["","RKL","2021-06-10","2021-06-24","3","2022","1100","309362556","","","NWA","4010246 0130","Storm-2021-Time Sheet - 12006","810300","Allowance Expenses",645.54999999999995,"AUD","Storm Response - SWAT Strike Team","CATS","SYS_BCBATCH",10004696,"","",{"$f":"VLOOKUP(U1388,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-06-23","2021-06-23","3","2022","1100","309363019","","","NWA","4010246 0130","Storm-2021-Time Sheet - 12006","810123","Corp Prof NT",645.53,"AUD","Storm Response - SWAT Strike Team","AFRU","SYS_BCBATCH",10004696,"","",{"$f":"VLOOKUP(U1389,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-06-23","2021-06-23","3","2022","1100","309363020","","","NWA","4010246 0130","Storm-2021-Time Sheet - 12006","810123","Corp Prof NT",645.53,"AUD","EMT - Recovery Hub Strike Team","AFRU","SYS_BCBATCH",10004696,"","",{"$f":"VLOOKUP(U1390,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-06-23","2021-06-23","3","2022","1100","309363021","","","NWA","4010246 0130","Storm-2021-Time Sheet - 12006","810123","Corp Prof NT",645.53,"AUD","EMT - Recovery Hub Strike Team","AFRU","SYS_BCBATCH",10004696,"","",{"$f":"VLOOKUP(U1391,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-06-23","2021-06-23","3","2022","1100","309363023","","","NWA","4010246 0130","Storm-2021-Time Sheet - 12006","810123","Corp Prof NT",645.53,"AUD","EMT - Recovery Hub Strike Team","AFRU","SYS_BCBATCH",10004696,"","",{"$f":"VLOOKUP(U1392,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-06-23","2021-06-23","3","2022","1100","309363024","","","NWA","4010246 0130","Storm-2021-Time Sheet - 12006","810123","Corp Prof NT",645.53,"AUD","EMT - Recovery Hub Strike Team","AFRU","SYS_BCBATCH",10004696,"","",{"$f":"VLOOKUP(U1393,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-06-23","2021-06-23","3","2022","1100","309363025","","","NWA","4010246 0130","Storm-2021-Time Sheet - 12006","810123","Corp Prof NT",645.53,"AUD","EMT - Recovery Hub Strike Team","AFRU","SYS_BCBATCH",10004696,"","",{"$f":"VLOOKUP(U1394,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-06-23","2021-06-23","3","2022","1100","309363026","","","NWA","4010246 0130","Storm-2021-Time Sheet - 12006","810123","Corp Prof NT",645.53,"AUD","Storm Response - SWAT Strike Team","AFRU","SYS_BCBATCH",10004696,"","",{"$f":"VLOOKUP(U1395,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-06-24","2021-06-24","3","2022","1100","309363998","","","NWA","4010246 0130","Storm-2021-Time Sheet - 12006","810142","Corp Strat Mngr NT",1541.55,"AUD","EMT - Recovery Hub Strike Team Lead","AFRU","SYS_BCBATCH",10004602,"","",{"$f":"VLOOKUP(U1396,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-06-24","2021-06-24","3","2022","1100","309364410","","","NWA","4010246 0130","Storm-2021-Time Sheet - 12006","810124","Corp Prof Spec NT",800.85,"AUD","Storm Relief Payment","AFRU","SYS_BCBATCH",10005652,"","",{"$f":"VLOOKUP(U1397,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["RMRU","RKL","2021-06-24","2021-06-24","3","2022","1100","309364411","","","NWA","4010246 0130","Storm-2021-Time Sheet - 12006","810124","Corp Prof Spec NT",800.85,"AUD","Storm Relief Payment","AFRU","SYS_BCBATCH",10005652,"","",{"$f":"VLOOKUP(U1398,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["RMRU","RKL","2021-06-24","2021-06-24","3","2022","1100","309364412","","","NWA","4010246 0130","Storm-2021-Time Sheet - 12006","810124","Corp Prof Spec NT",800.85,"AUD","Storm Relief Payment","AFRU","SYS_BCBATCH",10005652,"","",{"$f":"VLOOKUP(U1399,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["RMRU","RKL","2021-06-24","2021-06-24","3","2022","1100","309364413","","","NWA","4010246 0130","Storm-2021-Time Sheet - 12006","810124","Corp Prof Spec NT",800.85,"AUD","Storm Relief Payments","AFRU","SYS_BCBATCH",10005652,"","",{"$f":"VLOOKUP(U1400,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["RMRU","RKL","2021-06-24","2021-06-24","3","2022","1100","309364414","","","NWA","4010246 0130","Storm-2021-Time Sheet - 12006","810124","Corp Prof Spec NT",800.85,"AUD","Storm Relief Payments","AFRU","SYS_BCBATCH",10005652,"","",{"$f":"VLOOKUP(U1401,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["RMRU","RKL","2021-06-25","2021-06-25","3","2022","1100","309365365","","","NWA","4010246 0130","Storm-2021-Time Sheet - 12006","810142","Corp Strat Mngr NT",1541.55,"AUD","EMT - Recovery Hub Strike Team Lead","AFRU","SYS_BCBATCH",10004602,"","",{"$f":"VLOOKUP(U1402,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-06-29","2021-06-29","3","2022","1100","309382971","","","NWA","4010246 0130","Storm-2021-Time Sheet - 12006","810142","Corp Strat Mngr NT",-1541.55,"AUD","EMT - Recovery Hub Strike Team Lead","AFRU","SYS_BCBATCH",10004602,"","",{"$f":"VLOOKUP(U1403,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-06-29","2021-06-29","3","2022","1100","309382972","","","NWA","4010246 0130","Storm-2021-Time Sheet - 12006","810142","Corp Strat Mngr NT",-1541.55,"AUD","EMT - Recovery Hub Strike Team Lead","AFRU","SYS_BCBATCH",10004602,"","",{"$f":"VLOOKUP(U1404,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-06-29","2021-06-29","3","2022","1100","309382974","","","NWA","4010246 0130","Storm-2021-Time Sheet - 12006","810142","Corp Strat Mngr NT",-1541.55,"AUD","EMT - Recovery Hub Strike Team Lead","AFRU","SYS_BCBATCH",10004602,"","",{"$f":"VLOOKUP(U1405,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-06-29","2021-06-29","3","2022","1100","309382975","","","NWA","4010246 0130","Storm-2021-Time Sheet - 12006","810142","Corp Strat Mngr NT",-1541.55,"AUD","EMT - Recovery Hub Strike Team Lead","AFRU","SYS_BCBATCH",10004602,"","",{"$f":"VLOOKUP(U1406,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-06-29","2021-06-29","3","2022","1100","309382976","","","NWA","4010246 0130","Storm-2021-Time Sheet - 12006","810142","Corp Strat Mngr NT",-1541.55,"AUD","EMT - Recovery Hub Strike Team Lead","AFRU","SYS_BCBATCH",10004602,"","",{"$f":"VLOOKUP(U1407,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-06-29","2021-06-29","3","2022","1100","309382978","","","NWA","4010246 0130","Storm-2021-Time Sheet - 12006","810142","Corp Strat Mngr NT",-1541.55,"AUD","EMT - Recovery Hub Strike Team Lead","AFRU","SYS_BCBATCH",10004602,"","",{"$f":"VLOOKUP(U1408,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-06-29","2021-06-29","3","2022","1100","309382979","","","NWA","4010246 0130","Storm-2021-Time Sheet - 12006","810142","Corp Strat Mngr NT",-1541.55,"AUD","EMT - Recovery Hub Strike Team Lead","AFRU","SYS_BCBATCH",10004602,"","",{"$f":"VLOOKUP(U1409,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-06-29","2021-06-29","3","2022","1100","309382980","","","NWA","4010246 0130","Storm-2021-Time Sheet - 12006","810142","Corp Strat Mngr NT",-1541.55,"AUD","EMT - Recovery Hub Strike Team Lead","AFRU","SYS_BCBATCH",10004602,"","",{"$f":"VLOOKUP(U1410,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-06-29","2021-06-29","3","2022","1100","309382981","","","NWA","4010246 0130","Storm-2021-Time Sheet - 12006","810142","Corp Strat Mngr NT",-1541.55,"AUD","EMT - Recovery Hub Strike Team Lead","AFRU","SYS_BCBATCH",10004602,"","",{"$f":"VLOOKUP(U1411,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-06-29","2021-06-29","3","2022","1100","309382982","","","NWA","4010246 0130","Storm-2021-Time Sheet - 12006","810142","Corp Strat Mngr NT",-1541.55,"AUD","EMT - Recovery Hub Strike Team Lead","AFRU","SYS_BCBATCH",10004602,"","",{"$f":"VLOOKUP(U1412,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-06-29","2021-06-29","3","2022","1100","309382983","","","NWA","4010246 0130","Storm-2021-Time Sheet - 12006","810142","Corp Strat Mngr NT",-1541.55,"AUD","EMT - Recovery Hub Strike Team Lead","AFRU","SYS_BCBATCH",10004602,"","",{"$f":"VLOOKUP(U1413,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-06-29","2021-06-29","3","2022","1100","309382984","","","NWA","4010246 0130","Storm-2021-Time Sheet - 12006","810142","Corp Strat Mngr NT",-1541.55,"AUD","EMT - Recovery Hub Strike Team Lead","AFRU","SYS_BCBATCH",10004602,"","",{"$f":"VLOOKUP(U1414,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-06-29","2021-06-29","3","2022","1100","309383428","","","NWA","4010246 0130","Storm-2021-Time Sheet - 12006","810124","Corp Prof Spec NT",587.29,"AUD","Storm Payments","AFRU","SYS_BCBATCH",10005652,"","",{"$f":"VLOOKUP(U1415,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["RMRU","RKL","2021-06-29","2021-06-29","3","2022","1100","309383429","","","NWA","4010246 0130","Storm-2021-Time Sheet - 12006","810124","Corp Prof Spec NT",800.85,"AUD","Storm Payments","AFRU","SYS_BCBATCH",10005652,"","",{"$f":"VLOOKUP(U1416,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["RMRU","RKL","2021-06-29","2021-06-29","3","2022","1100","309383430","","","NWA","4010246 0130","Storm-2021-Time Sheet - 12006","810124","Corp Prof Spec NT",800.85,"AUD","Storm Payments","AFRU","SYS_BCBATCH",10005652,"","",{"$f":"VLOOKUP(U1417,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["RMRU","RKL","2021-06-29","2021-06-29","3","2022","1100","309383431","","","NWA","4010246 0130","Storm-2021-Time Sheet - 12006","810124","Corp Prof Spec NT",480.51,"AUD","Storm Payments","AFRU","SYS_BCBATCH",10005652,"","",{"$f":"VLOOKUP(U1418,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["RMRU","RKL","2021-06-30","2021-06-30","3","2022","1100","309384318","","","NWA","4010246 0130","Storm-2021-Time Sheet - 12006","810124","Corp Prof Spec NT",587.29,"AUD","Storm Payments","AFRU","SYS_BCBATCH",10005652,"","",{"$f":"VLOOKUP(U1419,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["RMRU","RKL","2021-07-03","2021-07-03","4","2022","1100","309467581","","","NWA","4010246 0130","Storm-2021-Time Sheet - 12006","810142","Corp Strat Mngr NT",1541.55,"AUD","EMT - Recovery Hub Strike Team Lead - 10","AFRU","SYS_BCBATCH",10004602,"","",{"$f":"VLOOKUP(U1420,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-07-03","2021-07-03","4","2022","1100","309467582","","","NWA","4010246 0130","Storm-2021-Time Sheet - 12006","810142","Corp Strat Mngr NT",1541.55,"AUD","EMT - Recovery Hub Strike Team Lead - 9/","AFRU","SYS_BCBATCH",10004602,"","",{"$f":"VLOOKUP(U1421,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-07-05","2021-07-05","4","2022","1100","309469781","","","NWA","4010246 0130","Storm-2021-Time Sheet - 12006","810142","Corp Strat Mngr NT",1541.55,"AUD","EMT - Recovery Hub Strike Team Lead - 11","AFRU","SYS_BCBATCH",10004602,"","",{"$f":"VLOOKUP(U1422,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-07-06","2021-07-06","4","2022","1100","309470223","","","NWA","4010246 0130","Storm-2021-Time Sheet - 12006","810142","Corp Strat Mngr NT",1541.55,"AUD","EMT - Recovery Hub Strike Team Lead - 15","AFRU","SYS_BCBATCH",10004602,"","",{"$f":"VLOOKUP(U1423,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-07-07","2021-07-07","4","2022","1100","309470972","","","NWA","4010246 0130","Storm-2021-Time Sheet - 12006","810142","Corp Strat Mngr NT",1541.55,"AUD","EMT - Recovery Hub Strike Team Lead - 16","AFRU","SYS_BCBATCH",10004602,"","",{"$f":"VLOOKUP(U1424,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["","RKL","2021-06-09","2021-07-08","4","2022","1100","309472243","","","NWA","4010246 0130","Storm-2021-Time Sheet - 12006","810300","Allowance Expenses",64.349999999999994,"AUD","EMT - Recovery Hub Strike Team Lead","CATS","SYS_BCBATCH",10004602,"","",{"$f":"VLOOKUP(U1425,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["","RKL","2021-06-09","2021-07-08","4","2022","1100","309472243","","","NWA","4010246 0130","Storm-2021-Time Sheet - 12006","810300","Allowance Expenses",64.349999999999994,"AUD","EMT - Recovery Hub Strike Team Lead","CATS","SYS_BCBATCH",10004602,"","",{"$f":"VLOOKUP(U1426,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["","RKL","2021-06-09","2021-07-08","4","2022","1100","309472243","","","NWA","4010246 0130","Storm-2021-Time Sheet - 12006","810300","Allowance Expenses",64.349999999999994,"AUD","EMT - Recovery Hub Strike Team Lead","CATS","SYS_BCBATCH",10004602,"","",{"$f":"VLOOKUP(U1427,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["","RKL","2021-06-09","2021-07-08","4","2022","1100","309472243","","","NWA","4010246 0130","Storm-2021-Time Sheet - 12006","810300","Allowance Expenses",64.349999999999994,"AUD","EMT - Recovery Hub Strike Team Lead","CATS","SYS_BCBATCH",10004602,"","",{"$f":"VLOOKUP(U1428,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["","RKL","2021-06-09","2021-07-08","4","2022","1100","309472243","","","NWA","4010246 0130","Storm-2021-Time Sheet - 12006","810300","Allowance Expenses",64.349999999999994,"AUD","EMT - Recovery Hub Strike Team Lead","CATS","SYS_BCBATCH",10004602,"","",{"$f":"VLOOKUP(U1429,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["","RKL","2021-06-09","2021-07-08","4","2022","1100","309472243","","","NWA","4010246 0130","Storm-2021-Time Sheet - 12006","810300","Allowance Expenses",64.349999999999994,"AUD","EMT - Recovery Hub Strike Team Lead","CATS","SYS_BCBATCH",10004602,"","",{"$f":"VLOOKUP(U1430,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["","RKL","2021-06-09","2021-07-08","4","2022","1100","309472243","","","NWA","4010246 0130","Storm-2021-Time Sheet - 12006","810300","Allowance Expenses",64.349999999999994,"AUD","EMT - Recovery Hub Strike Team Lead","CATS","SYS_BCBATCH",10004602,"","",{"$f":"VLOOKUP(U1431,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["","RKL","2021-06-09","2021-07-08","4","2022","1100","309472243","","","NWA","4010246 0130","Storm-2021-Time Sheet - 12006","810300","Allowance Expenses",64.349999999999994,"AUD","EMT - Recovery Hub Strike Team Lead","CATS","SYS_BCBATCH",10004602,"","",{"$f":"VLOOKUP(U1432,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["","RKL","2021-06-09","2021-07-08","4","2022","1100","309472243","","","NWA","4010246 0130","Storm-2021-Time Sheet - 12006","810300","Allowance Expenses",64.349999999999994,"AUD","EMT - Recovery Hub Strike Team Lead","CATS","SYS_BCBATCH",10004602,"","",{"$f":"VLOOKUP(U1433,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["","RKL","2021-06-09","2021-07-08","4","2022","1100","309472243","","","NWA","4010246 0130","Storm-2021-Time Sheet - 12006","810300","Allowance Expenses",64.349999999999994,"AUD","EMT - Recovery Hub Strike Team Lead","CATS","SYS_BCBATCH",10004602,"","",{"$f":"VLOOKUP(U1434,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["","RKL","2021-06-09","2021-07-08","4","2022","1100","309472243","","","NWA","4010246 0130","Storm-2021-Time Sheet - 12006","810300","Allowance Expenses",64.349999999999994,"AUD","EMT - Recovery Hub Strike Team Lead","CATS","SYS_BCBATCH",10004602,"","",{"$f":"VLOOKUP(U1435,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-07-13","2021-07-13","4","2022","1100","309475239","","","NWA","4010246 0130","Storm-2021-Time Sheet - 12006","810124","Corp Prof Spec NT",373.73,"AUD","Storm Payments","AFRU","SYS_BCBATCH",10005652,"","",{"$f":"VLOOKUP(U1436,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["RMRU","RKL","2021-07-13","2021-07-13","4","2022","1100","309475240","","","NWA","4010246 0130","Storm-2021-Time Sheet - 12006","810124","Corp Prof Spec NT",533.9,"AUD","Storm Payments","AFRU","SYS_BCBATCH",10005652,"","",{"$f":"VLOOKUP(U1437,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["","",null,null,"","","","","","","","4010246 0130","","","",25314.98,"AUD","","","",null,"",""]
["RFBU","COIN","2021-06-17","2021-06-18","3","2022","1100","108152965","","","NWA","4010246 0140","Storm-2021-Purchase Orders - 12006","516400","General Expenses",9090.9,"AUD","","BKPFF","WF-BATCH",0,"","KR",null,"Include","Internal"]
["RFBU","COIN","2021-06-16","2021-06-17","3","2022","1100","108156904","","","NWA","4010246 0140","Storm-2021-Purchase Orders - 12006","516400","General Expenses",4586.16,"AUD","","BKPFF","WF-BATCH",0,"","KR",null,"Include","Internal"]
["RFBU","COIN","2021-06-14","2021-06-18","3","2022","1100","108157710","","","NWA","4010246 0140","Storm-2021-Purchase Orders - 12006","516413","Light Meals on Site",6362.5,"AUD","","BKPFF","WF-BATCH",0,"","KR",null,"Include","Internal"]
["RFBU","COIN","2021-06-24","2021-06-24","3","2022","1100","108170905","","","NWA","4010246 0140","Storm-2021-Purchase Orders - 12006","521508","Accommodation",450,"AUD","PCARD Christopher Braconi Storm event -3 nights Li","BKPFF","SYS_BCBATCH",0,"","SA",null,"Include","Internal"]
["RFBU","COIN","2021-06-24","2021-06-24","3","2022","1100","108170905","","","NWA","4010246 0140","Storm-2021-Purchase Orders - 12006","516413","Light Meals on Site",1000,"AUD","PCARD Christopher Braconi Storm event - field cate","BKPFF","SYS_BCBATCH",0,"","SA",null,"Include","Internal"]
["RFBU","COIN","2021-06-29","2021-06-29","3","2022","1100","108175118","","","NWA","4010246 0140","Storm-2021-Purchase Orders - 12006","516413","Light Meals on Site",25,"AUD","PCARD Gareth Downes Lunch for strike team","BKPFF","WF-BATCH",0,"","SA",null,"Include","Internal"]
["RFBU","COIN","2021-06-29","2021-06-29","3","2022","1100","108175118","","","NWA","4010246 0140","Storm-2021-Purchase Orders - 12006","516413","Light Meals on Site",260.5,"AUD","PCARD Gareth Downes Meals for strike team TGN","BKPFF","WF-BATCH",0,"","SA",null,"Include","Internal"]
["RFBU","COIN","2021-06-29","2021-06-29","3","2022","1100","108175118","","","NWA","4010246 0140","Storm-2021-Purchase Orders - 12006","516413","Light Meals on Site",33.64,"AUD","PCARD Christopher Braconi OBO-GW-Storm event - CC","BKPFF","WF-BATCH",0,"","SA",null,"Include","Internal"]
["RFBU","COIN","2021-06-29","2021-06-29","3","2022","1100","108175118","","","NWA","4010246 0140","Storm-2021-Purchase Orders - 12006","516413","Light Meals on Site",101.82,"AUD","PCARD Christopher Braconi OBO-CPA-Storm event - CC","BKPFF","WF-BATCH",0,"","SA",null,"Include","Internal"]
["RFBU","COIN","2021-06-29","2021-06-29","3","2022","1100","108175122","","","NWA","4010246 0140","Storm-2021-Purchase Orders - 12006","521508","Accommodation",409.09,"AUD","PCARD Christopher Braconi Storm event -3 nights Li","BKPFF","WF-BATCH",0,"","SA",null,"Include","Internal"]
["RFBU","COIN","2021-06-29","2021-06-29","3","2022","1100","108175137","","","NWA","4010246 0140","Storm-2021-Purchase Orders - 12006","516413","Light Meals on Site",-27.5,"AUD","PCARD Gareth Downes Lunch for strike team","BKPFF","WF-BATCH",0,"","SA",null,"Include","Internal"]
["RFBU","COIN","2021-06-29","2021-06-29","3","2022","1100","108175137","","","NWA","4010246 0140","Storm-2021-Purchase Orders - 12006","516413","Light Meals on Site",-286.55,"AUD","PCARD Gareth Downes Meals for strike team TGN","BKPFF","WF-BATCH",0,"","SA",null,"Include","Internal"]
["RFBU","COIN","2021-06-29","2021-06-29","3","2022","1100","108175137","","","NWA","4010246 0140","Storm-2021-Purchase Orders - 12006","516413","Light Meals on Site",-37,"AUD","PCARD Christopher Braconi OBO-GW-Storm event - CC","BKPFF","WF-BATCH",0,"","SA",null,"Include","Internal"]
["RFBU","COIN","2021-06-29","2021-06-29","3","2022","1100","108175137","","","NWA","4010246 0140","Storm-2021-Purchase Orders - 12006","516413","Light Meals on Site",-112,"AUD","PCARD Christopher Braconi OBO-CPA-Storm event - CC","BKPFF","WF-BATCH",0,"","SA",null,"Include","Internal"]
["RFBU","COIN","2021-06-29","2021-06-29","3","2022","1100","108175137","","","NWA","4010246 0140","Storm-2021-Purchase Orders - 12006","521508","Accommodation",-450,"AUD","PCARD Christopher Braconi Storm event -3 nights Li","BKPFF","WF-BATCH",0,"","SA",null,"Include","Internal"]
["RFBU","COIN","2021-07-21","2021-07-21","4","2022","1100","108270473","","","NWA","4010246 0140","Storm-2021-Purchase Orders - 12006","516402","Protective Clothing",1082.4000000000001,"AUD","CAN JERRY PLASTIC RED 20LT FUEL 0950","BKPFF","WF-BATCH",0,"","AB",null,"Include","Internal"]
["RFBU","COIN","2021-07-21","2021-07-21","4","2022","1100","108270473","","","NWA","4010246 0140","Storm-2021-Purchase Orders - 12006","516402","Protective Clothing",108.24,"AUD","CAN JERRY PLASTIC DIESEL YELLOW 20L","BKPFF","WF-BATCH",0,"","AB",null,"Include","Internal"]
["RFBU","COIN","2021-07-21","2021-07-21","4","2022","1100","108270473","","","NWA","4010246 0140","Storm-2021-Purchase Orders - 12006","516402","Protective Clothing",1923.98,"AUD","TORCH EVEREADY BRILLIAN BEAM 2XD VAL2D","BKPFF","WF-BATCH",0,"","AB",null,"Include","Internal"]
["RFBU","COIN","2021-07-21","2021-07-21","4","2022","1100","108270473","","","NWA","4010246 0140","Storm-2021-Purchase Orders - 12006","516402","Protective Clothing",681,"AUD","STROM INDUSTRIAL AA BATTERY 4 PACK","BKPFF","WF-BATCH",0,"","AB",null,"Include","Internal"]
["RFBU","COIN","2021-07-21","2021-07-21","4","2022","1100","108270473","","","NWA","4010246 0140","Storm-2021-Purchase Orders - 12006","516402","Protective Clothing",181.6,"AUD","BATTERY INDUSTRIAL AAA STROM 4 PACK","BKPFF","WF-BATCH",0,"","AB",null,"Include","Internal"]
["RFBU","COIN","2021-07-21","2021-07-21","4","2022","1100","108270473","","","NWA","4010246 0140","Storm-2021-Purchase Orders - 12006","516402","Protective Clothing",350.88,"AUD","STROM INDUSTRIAL C BATTERY 12 PACK","BKPFF","WF-BATCH",0,"","AB",null,"Include","Internal"]
["RFBU","COIN","2021-07-21","2021-07-21","4","2022","1100","108270473","","","NWA","4010246 0140","Storm-2021-Purchase Orders - 12006","516402","Protective Clothing",306.77,"AUD","STROM INDUSTRIAL D BATTERY 12 PACK","BKPFF","WF-BATCH",0,"","AB",null,"Include","Internal"]
["RFBU","COIN","2021-07-21","2021-07-21","4","2022","1100","108270473","","","NWA","4010246 0140","Storm-2021-Purchase Orders - 12006","516402","Protective Clothing",1147.5999999999999,"AUD","PAPER TOILET SCOTT 5741 2PLY 400SH","BKPFF","WF-BATCH",0,"","AB",null,"Include","Internal"]
["RFBU","COIN","2021-07-21","2021-07-21","4","2022","1100","108270477","","","NWA","4010246 0140","Storm-2021-Purchase Orders - 12006","516402","Protective Clothing",249,"AUD","WATER BOTTLED 600ML (24)","BKPFF","WF-BATCH",0,"","AB",null,"Include","Internal"]
["RFBU","COIN","2021-07-21","2021-07-21","4","2022","1100","108270477","","","NWA","4010246 0140","Storm-2021-Purchase Orders - 12006","516402","Protective Clothing",520.79999999999995,"AUD","UHT MILK SKIM 1L","BKPFF","WF-BATCH",0,"","AB",null,"Include","Internal"]
["RFBU","COIN","2021-08-27","2021-08-27","5","2022","1100","108390275","","","NWA","4010246 0140","Storm-2021-Purchase Orders - 12006","516413","Light Meals on Site",3937.5,"AUD","Coffee Events Pty Ltd INV-0113","BKPF","HKAFEERO",0,"","AB",null,"Include","Internal"]
["RFBU","COIN","2021-08-26","2021-08-26","5","2022","1100","108390280","","","NWA","4010246 0140","Storm-2021-Purchase Orders - 12006","516413","Light Meals on Site",4331.25,"AUD","Storm payment invoice payments","BKPFF","WF-BATCH",0,"","AB",null,"Include","Internal"]
["RFBU","COIN","2021-08-26","2021-08-26","5","2022","1100","108390280","","","NWA","4010246 0140","Storm-2021-Purchase Orders - 12006","516413","Light Meals on Site",9418.75,"AUD","Storm payment invoice payments","BKPFF","WF-BATCH",0,"","AB",null,"Include","Internal"]
["RFBU","COIN","2021-08-26","2021-08-26","5","2022","1100","108390280","","","NWA","4010246 0140","Storm-2021-Purchase Orders - 12006","516400","General Expenses",3696.62,"AUD","Storm payment invoice payments","BKPFF","WF-BATCH",0,"","AB",null,"Include","Internal"]
["RFBU","COIN","2021-08-27","2021-08-27","5","2022","1100","108391024","","","NWA","4010246 0140","Storm-2021-Purchase Orders - 12006","516413","Light Meals on Site",8562.5,"AUD","Coffee Events Pty Ltd INV-0111 and Inv-0112","BKPF","HKAFEERO",0,"","AB",null,"Include","Internal"]
["RFBU","COIN","2021-08-27","2021-08-27","5","2022","1100","108391025","","","NWA","4010246 0140","Storm-2021-Purchase Orders - 12006","516400","General Expenses",3360.56,"AUD","HB Battery Specialist INV/0621/70016157","BKPF","HKAFEERO",0,"","AB",null,"Include","Internal"]
["RFBU","COIN","2021-08-26","2021-08-26","5","2022","1100","108391215","","","NWA","4010246 0140","Storm-2021-Purchase Orders - 12006","516413","Light Meals on Site",-4331.25,"AUD","Storm payment invoice payments","BKPFF","PRAVEENK",0,"","AB",null,"Include","Internal"]
["RFBU","COIN","2021-08-26","2021-08-26","5","2022","1100","108391215","","","NWA","4010246 0140","Storm-2021-Purchase Orders - 12006","516413","Light Meals on Site",-9418.75,"AUD","Storm payment invoice payments","BKPFF","PRAVEENK",0,"","AB",null,"Include","Internal"]
["RFBU","COIN","2021-08-26","2021-08-26","5","2022","1100","108391215","","","NWA","4010246 0140","Storm-2021-Purchase Orders - 12006","516400","General Expenses",-3696.62,"AUD","Storm payment invoice payments","BKPFF","PRAVEENK",0,"","AB",null,"Include","Internal"]
["","",null,null,"","","","","","","","4010246 0140","","","",43819.39,"AUD","","","",null,"",""]
["RFBU","COIN","2021-06-25","2021-06-25","3","2022","1100","108171320","","","NWA","4010246 0150","Storm-2021-Time Sheet - 12306","506500","Cont Lab Non-Payroll",5374.86,"AUD","[Jacqui Penry] PO4500116862 {we 20-Jun}","BKPFF","WF-BATCH",0,"","AB",null,"Exclude"]
["RFBU","COIN","2021-06-25","2021-06-25","3","2022","1100","108171320","","","NWA","4010246 0150","Storm-2021-Time Sheet - 12306","506500","Cont Lab Non-Payroll",1849.37,"AUD","[Jo Fuller] PO4500096394 {we 20-Jun}","BKPFF","WF-BATCH",0,"","AB",null,"Exclude"]
["RFBU","COIN","2021-07-30","2021-07-30","4","2022","1100","108287265","","","NWA","4010246 0150","Storm-2021-Time Sheet - 12306","506500","Cont Lab Non-Payroll",651.5,"AUD","[Jacqui Penry] PO4500116862 {Apr-Jul 21}","BKPFF","WF-BATCH",0,"","AB",null,"Exclude"]
["RFBU","COIN","2021-07-30","2021-07-30","4","2022","1100","108287265","","","NWA","4010246 0150","Storm-2021-Time Sheet - 12306","506500","Cont Lab Non-Payroll",489.9,"AUD","[Jo Fuller] PO4500096394 {Apr-Jul 21}","BKPFF","WF-BATCH",0,"","AB",null,"Exclude"]
["RMRU","RKL","2021-06-17","2021-06-17","3","2022","1100","309353574","","","NWA","4010246 0150","Storm-2021-Time Sheet - 12306","810160","Corp Manager NT",358.74,"AUD","Storm Relief - replying to customer DMs","AFRU","SYS_BCBATCH",10009958,"","",{"$f":"VLOOKUP(U1478,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-06-17","2021-06-17","3","2022","1100","309353581","","","NWA","4010246 0150","Storm-2021-Time Sheet - 12306","810141","Corp Snr Mngr NT",532.69000000000005,"AUD","","AFRU","SYS_BCBATCH",10004697,"","",{"$f":"VLOOKUP(U1479,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-06-17","2021-06-17","3","2022","1100","309353582","","","NWA","4010246 0150","Storm-2021-Time Sheet - 12306","810141","Corp Snr Mngr NT",1065.3800000000001,"AUD","","AFRU","SYS_BCBATCH",10004697,"","",{"$f":"VLOOKUP(U1480,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-06-17","2021-06-17","3","2022","1100","309353583","","","NWA","4010246 0150","Storm-2021-Time Sheet - 12306","810141","Corp Snr Mngr NT",1065.3800000000001,"AUD","","AFRU","SYS_BCBATCH",10004697,"","",{"$f":"VLOOKUP(U1481,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-06-17","2021-06-17","3","2022","1100","309353584","","","NWA","4010246 0150","Storm-2021-Time Sheet - 12306","810141","Corp Snr Mngr NT",1207.43,"AUD","","AFRU","SYS_BCBATCH",10004697,"","",{"$f":"VLOOKUP(U1482,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-06-17","2021-06-17","3","2022","1100","309353585","","","NWA","4010246 0150","Storm-2021-Time Sheet - 12306","810141","Corp Snr Mngr NT",1207.43,"AUD","","AFRU","SYS_BCBATCH",10004697,"","",{"$f":"VLOOKUP(U1483,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-06-17","2021-06-17","3","2022","1100","309353588","","","NWA","4010246 0150","Storm-2021-Time Sheet - 12306","810141","Corp Snr Mngr NT",1065.3800000000001,"AUD","","AFRU","SYS_BCBATCH",10004697,"","",{"$f":"VLOOKUP(U1484,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-06-17","2021-06-17","3","2022","1100","309353590","","","NWA","4010246 0150","Storm-2021-Time Sheet - 12306","810160","Corp Manager NT",358.74,"AUD","","AFRU","SYS_BCBATCH",10009958,"","",{"$f":"VLOOKUP(U1485,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-06-17","2021-06-17","3","2022","1100","309353591","","","NWA","4010246 0150","Storm-2021-Time Sheet - 12306","810160","Corp Manager NT",1255.5899999999999,"AUD","Storm Recovery Costs - Recovery and dist","AFRU","SYS_BCBATCH",10009958,"","",{"$f":"VLOOKUP(U1486,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-06-17","2021-06-17","3","2022","1100","309353592","","","NWA","4010246 0150","Storm-2021-Time Sheet - 12306","810160","Corp Manager NT",1375.17,"AUD","Storm Recovery Costs - Recovery and dist","AFRU","SYS_BCBATCH",10009958,"","",{"$f":"VLOOKUP(U1487,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-06-17","2021-06-17","3","2022","1100","309353593","","","NWA","4010246 0150","Storm-2021-Time Sheet - 12306","810160","Corp Manager NT",777.27,"AUD","Storm Recovery Costs - Recovery and dist","AFRU","SYS_BCBATCH",10009958,"","",{"$f":"VLOOKUP(U1488,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-06-17","2021-06-17","3","2022","1100","309353594","","","NWA","4010246 0150","Storm-2021-Time Sheet - 12306","810160","Corp Manager NT",358.74,"AUD","Storm Recovery Costs - Responding to cus","AFRU","SYS_BCBATCH",10009958,"","",{"$f":"VLOOKUP(U1489,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-06-18","2021-06-18","3","2022","1100","309359089","","","NWA","4010246 0150","Storm-2021-Time Sheet - 12306","810160","Corp Manager NT",59.79,"AUD","Storm Relief - Distribution Hub and resp","AFRU","SYS_BCBATCH",10009958,"","",{"$f":"VLOOKUP(U1490,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-06-18","2021-06-18","3","2022","1100","309359090","","","NWA","4010246 0150","Storm-2021-Time Sheet - 12306","810160","Corp Manager NT",896.85,"AUD","Storm Relief Distribution Hub and respon","AFRU","SYS_BCBATCH",10009958,"","",{"$f":"VLOOKUP(U1491,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-06-20","2021-06-20","3","2022","1100","309360459","","","NWA","4010246 0150","Storm-2021-Time Sheet - 12306","810141","Corp Snr Mngr NT",1065.3800000000001,"AUD","EMT Storm Response","AFRU","SYS_BCBATCH",10007538,"","",{"$f":"VLOOKUP(U1492,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["RMRU","RKL","2021-06-20","2021-06-20","3","2022","1100","309360460","","","NWA","4010246 0150","Storm-2021-Time Sheet - 12306","810141","Corp Snr Mngr NT",1065.3800000000001,"AUD","EMT Storm Response","AFRU","SYS_BCBATCH",10007538,"","",{"$f":"VLOOKUP(U1493,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["RMRU","RKL","2021-06-20","2021-06-20","3","2022","1100","309360461","","","NWA","4010246 0150","Storm-2021-Time Sheet - 12306","810141","Corp Snr Mngr NT",1065.3800000000001,"AUD","EMT Storm Response","AFRU","SYS_BCBATCH",10007538,"","",{"$f":"VLOOKUP(U1494,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["RMRU","RKL","2021-06-20","2021-06-20","3","2022","1100","309360462","","","NWA","4010246 0150","Storm-2021-Time Sheet - 12306","810141","Corp Snr Mngr NT",1065.3800000000001,"AUD","EMT Storm Response","AFRU","SYS_BCBATCH",10007538,"","",{"$f":"VLOOKUP(U1495,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["RMRU","RKL","2021-06-20","2021-06-20","3","2022","1100","309360463","","","NWA","4010246 0150","Storm-2021-Time Sheet - 12306","810141","Corp Snr Mngr NT",1065.3800000000001,"AUD","","AFRU","SYS_BCBATCH",10007538,"","",{"$f":"VLOOKUP(U1496,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["RMRU","RKL","2021-06-22","2021-06-22","3","2022","1100","309361563","","","NWA","4010246 0150","Storm-2021-Time Sheet - 12306","810160","Corp Manager NT",1342.22,"AUD","Storms Support","AFRU","SYS_BCBATCH",10000554,"","",{"$f":"VLOOKUP(U1497,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-06-22","2021-06-22","3","2022","1100","309361564","","","NWA","4010246 0150","Storm-2021-Time Sheet - 12306","810160","Corp Manager NT",1342.22,"AUD","Storms support","AFRU","SYS_BCBATCH",10000554,"","",{"$f":"VLOOKUP(U1498,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-06-22","2021-06-22","3","2022","1100","309361565","","","NWA","4010246 0150","Storm-2021-Time Sheet - 12306","810160","Corp Manager NT",1342.22,"AUD","Queens B'day Storms assist","AFRU","SYS_BCBATCH",10000554,"","",{"$f":"VLOOKUP(U1499,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-06-22","2021-06-22","3","2022","1100","309361566","","","NWA","4010246 0150","Storm-2021-Time Sheet - 12306","810160","Corp Manager NT",1278.3,"AUD","Storms support","AFRU","SYS_BCBATCH",10000554,"","",{"$f":"VLOOKUP(U1500,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-06-22","2021-06-22","3","2022","1100","309361567","","","NWA","4010246 0150","Storm-2021-Time Sheet - 12306","810160","Corp Manager NT",1214.3900000000001,"AUD","storms support","AFRU","SYS_BCBATCH",10000554,"","",{"$f":"VLOOKUP(U1501,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-06-22","2021-06-22","3","2022","1100","309361568","","","NWA","4010246 0150","Storm-2021-Time Sheet - 12306","810160","Corp Manager NT",1086.56,"AUD","storms support","AFRU","SYS_BCBATCH",10000554,"","",{"$f":"VLOOKUP(U1502,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-06-22","2021-06-22","3","2022","1100","309361569","","","NWA","4010246 0150","Storm-2021-Time Sheet - 12306","810160","Corp Manager NT",1214.3900000000001,"AUD","Storms support","AFRU","SYS_BCBATCH",10000554,"","",{"$f":"VLOOKUP(U1503,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-06-22","2021-06-22","3","2022","1100","309361570","","","NWA","4010246 0150","Storm-2021-Time Sheet - 12306","810160","Corp Manager NT",766.98,"AUD","Storms support","AFRU","SYS_BCBATCH",10000554,"","",{"$f":"VLOOKUP(U1504,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-06-22","2021-06-22","3","2022","1100","309361571","","","NWA","4010246 0150","Storm-2021-Time Sheet - 12306","810160","Corp Manager NT",1214.3900000000001,"AUD","Storms support","AFRU","SYS_BCBATCH",10000554,"","",{"$f":"VLOOKUP(U1505,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-07-03","2021-07-03","4","2022","1100","309465376","","","NWA","4010246 0150","Storm-2021-Time Sheet - 12306","810160","Corp Manager NT",-59.79,"AUD","Storm Relief - Distribution Hub and resp","AFRU","SYS_BCBATCH",10009958,"","",{"$f":"VLOOKUP(U1506,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-07-21","2021-07-21","4","2022","1100","309488946","","","NWA","4010246 0150","Storm-2021-Time Sheet - 12306","810241","Corp Snr Mngr OT",1917.72,"AUD","EMT Deputy Manager - Storm Response","AFRU","SYS_BCBATCH",10000407,"","",{"$f":"VLOOKUP(U1507,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["","",null,null,"","","","","","","","4010246 0150","","","",37936.71,"AUD","","","",null,"",""]
["RFBU","COIN","2021-06-16","2021-06-17","3","2022","1100","108156722","","","NWA","4010246 0160","Storm-2021-Purchase Orders - 12306","516400","General Expenses",285,"AUD","","BKPFF","WF-BATCH",0,"","KR",null,"Include","Internal"]
["RFBU","COIN","2021-06-16","2021-06-18","3","2022","1100","108157671","","","NWA","4010246 0160","Storm-2021-Purchase Orders - 12306","516400","General Expenses",7672.65,"AUD","","BKPFF","WF-BATCH",0,"","KR",null,"Include","Internal"]
["RMWE","COIN","2021-06-18","2021-06-18","3","2022","1100","108157927","","","NWA","4010246 0160","Storm-2021-Purchase Orders - 12306","516400","General Expenses",7480,"AUD","","MKPF","CBRACONI",0,"","WE",null,"Include","Internal"]
["RMWE","COIN","2021-06-18","2021-06-18","3","2022","1100","108157927","","","NWA","4010246 0160","Storm-2021-Purchase Orders - 12306","516400","General Expenses",4840,"AUD","","MKPF","CBRACONI",0,"","WE",null,"Include","Internal"]
["RMWE","COIN","2021-06-18","2021-06-18","3","2022","1100","108157927","","","NWA","4010246 0160","Storm-2021-Purchase Orders - 12306","516104","Postal Charges",192.65,"AUD","","MKPF","CBRACONI",0,"","WE",null,"Include","Internal"]
["RFBU","COIN","2021-07-13","2021-07-13","4","2022","1100","108261577","","","NWA","4010246 0160","Storm-2021-Purchase Orders - 12306","516102","IT Hardware",761.2,"AUD","EEXP James Weghorn USB Charging stations","BKPFF","BSANKARA",0,"","SA",null,"Include","Internal"]
["RFBU","COIN","2021-07-06","2021-07-06","4","2022","1100","108263863","","","NWA","4010246 0160","Storm-2021-Purchase Orders - 12306","521505","Vehicle Parking",85,"AUD","EEXP Jessica Naylor Flinders Street Parking","BKPFF","BSANKARA",0,"","SA",null,"Include","Internal"]
["RFBU","COIN","2021-07-06","2021-07-06","4","2022","1100","108263863","","","NWA","4010246 0160","Storm-2021-Purchase Orders - 12306","521508","Accommodation",372,"AUD","EEXP Jessica Naylor Urgent Customer Accom - Storm","BKPFF","BSANKARA",0,"","SA",null,"Include","Internal"]
["RFBU","COIN","2021-07-06","2021-07-06","4","2022","1100","108263863","","","NWA","4010246 0160","Storm-2021-Purchase Orders - 12306","521508","Accommodation",196.8,"AUD","EEXP Jessica Naylor GYG for controllers & customer","BKPFF","BSANKARA",0,"","SA",null,"Include","Internal"]
["RFBU","COIN","2021-07-06","2021-07-06","4","2022","1100","108263863","","","NWA","4010246 0160","Storm-2021-Purchase Orders - 12306","516413","Light Meals on Site",3523.81,"AUD","EEXP James Weghorn Balance of COSTCO payment of st","BKPFF","BSANKARA",0,"","SA",null,"Include","Internal"]
["RFBU","COIN","2021-07-24","2021-07-24","4","2022","1100","108276188","","","NWA","4010246 0160","Storm-2021-Purchase Orders - 12306","516401","Office Expenses",39.369999999999997,"AUD","PCARD James Weghorn Powerbanks - test purchase","BKPFF","SYS_BCBATCH",0,"","SA",null,"Include","Internal"]
["RFBU","COIN","2021-07-24","2021-07-24","4","2022","1100","108276188","","","NWA","4010246 0160","Storm-2021-Purchase Orders - 12306","516401","Office Expenses",5000,"AUD","PCARD James Weghorn Storm supplies for customers","BKPFF","SYS_BCBATCH",0,"","SA",null,"Include","Internal"]
["RFBU","COIN","2021-07-24","2021-07-24","4","2022","1100","108276188","","","NWA","4010246 0160","Storm-2021-Purchase Orders - 12306","516413","Light Meals on Site",436,"AUD","PCARD James Weghorn Lilydale Lunch for storm 12/12","BKPFF","SYS_BCBATCH",0,"","SA",null,"Include","Internal"]
["RFBU","COIN","2021-07-24","2021-07-24","4","2022","1100","108276188","","","NWA","4010246 0160","Storm-2021-Purchase Orders - 12306","516401","Office Expenses",11293.82,"AUD","PCARD Vanessa Cripps Care package stock for custom","BKPFF","SYS_BCBATCH",0,"","SA",null,"Include","Internal"]
["RFBU","COIN","2021-07-24","2021-07-24","4","2022","1100","108276188","","","NWA","4010246 0160","Storm-2021-Purchase Orders - 12306","516401","Office Expenses",798.41,"AUD","PCARD Vanessa Cripps Care package stock for custom","BKPFF","SYS_BCBATCH",0,"","SA",null,"Include","Internal"]
["RFBU","COIN","2021-07-24","2021-07-24","4","2022","1100","108276188","","","NWA","4010246 0160","Storm-2021-Purchase Orders - 12306","516401","Office Expenses",10316.08,"AUD","PCARD Vanessa Cripps Care package stock for custom","BKPFF","SYS_BCBATCH",0,"","SA",null,"Include","Internal"]
["RFBU","COIN","2021-07-24","2021-07-24","4","2022","1100","108276188","","","NWA","4010246 0160","Storm-2021-Purchase Orders - 12306","516401","Office Expenses",11324.85,"AUD","PCARD Vanessa Cripps Care package stock for custom","BKPFF","SYS_BCBATCH",0,"","SA",null,"Include","Internal"]
["RFBU","COIN","2021-07-24","2021-07-24","4","2022","1100","108276188","","","NWA","4010246 0160","Storm-2021-Purchase Orders - 12306","516401","Office Expenses",7258.21,"AUD","PCARD Vanessa Cripps Storm care package supplies","BKPFF","SYS_BCBATCH",0,"","SA",null,"Include","Internal"]
["RFBU","COIN","2021-07-24","2021-07-24","4","2022","1100","108276188","","","NWA","4010246 0160","Storm-2021-Purchase Orders - 12306","516401","Office Expenses",1408.77,"AUD","PCARD Vanessa Cripps Storm care package supplies","BKPFF","SYS_BCBATCH",0,"","SA",null,"Include","Internal"]
["RFBU","COIN","2021-07-24","2021-07-24","4","2022","1100","108276188","","","NWA","4010246 0160","Storm-2021-Purchase Orders - 12306","516401","Office Expenses",2000,"AUD","PCARD Vanessa Cripps Care package stock for custom","BKPFF","SYS_BCBATCH",0,"","SA",null,"Include","Internal"]
["","",null,null,"","","","","","","","4010246 0160","","","",75284.62,"AUD","","","",null,"",""]
["RMRU","RKL","2021-06-16","2021-06-16","3","2022","1100","309351392","","","NWA","4010246 0170","Storm-2021-Time Sheet - 12001","810141","Corp Snr Mngr NT",1213.3499999999999,"AUD","","AFRU","SYS_BCBATCH",10001030,"","",{"$f":"VLOOKUP(U1530,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-06-18","2021-06-18","3","2022","1100","309359091","","","NWA","4010246 0170","Storm-2021-Time Sheet - 12001","810141","Corp Snr Mngr NT",1213.3499999999999,"AUD","","AFRU","SYS_BCBATCH",10007804,"","",{"$f":"VLOOKUP(U1531,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-06-18","2021-06-18","3","2022","1100","309359092","","","NWA","4010246 0170","Storm-2021-Time Sheet - 12001","810141","Corp Snr Mngr NT",323.56,"AUD","","AFRU","SYS_BCBATCH",10000134,"","",{"$f":"VLOOKUP(U1532,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-06-18","2021-06-18","3","2022","1100","309359093","","","NWA","4010246 0170","Storm-2021-Time Sheet - 12001","810141","Corp Snr Mngr NT",1617.8,"AUD","","AFRU","SYS_BCBATCH",10000134,"","",{"$f":"VLOOKUP(U1533,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-06-18","2021-06-18","3","2022","1100","309359097","","","NWA","4010246 0170","Storm-2021-Time Sheet - 12001","810122","Corp Prof Exp NT",758.85,"AUD","Storm response - Generator support","AFRU","SYS_BCBATCH",10000568,"","",{"$f":"VLOOKUP(U1534,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-06-18","2021-06-18","3","2022","1100","309359098","","","NWA","4010246 0170","Storm-2021-Time Sheet - 12001","810122","Corp Prof Exp NT",758.85,"AUD","Storm response - Generator support","AFRU","SYS_BCBATCH",10000568,"","",{"$f":"VLOOKUP(U1535,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-06-18","2021-06-18","3","2022","1100","309359099","","","NWA","4010246 0170","Storm-2021-Time Sheet - 12001","810122","Corp Prof Exp NT",758.85,"AUD","Storm response - Generator support","AFRU","SYS_BCBATCH",10000568,"","",{"$f":"VLOOKUP(U1536,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-06-18","2021-06-18","3","2022","1100","309359100","","","NWA","4010246 0170","Storm-2021-Time Sheet - 12001","810122","Corp Prof Exp NT",758.85,"AUD","Storm response - Generator support","AFRU","SYS_BCBATCH",10000568,"","",{"$f":"VLOOKUP(U1537,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-06-18","2021-06-18","3","2022","1100","309359101","","","NWA","4010246 0170","Storm-2021-Time Sheet - 12001","810122","Corp Prof Exp NT",758.85,"AUD","Storm response - Generator support","AFRU","SYS_BCBATCH",10000568,"","",{"$f":"VLOOKUP(U1538,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-06-18","2021-06-18","3","2022","1100","309359102","","","NWA","4010246 0170","Storm-2021-Time Sheet - 12001","810122","Corp Prof Exp NT",758.85,"AUD","Storm response - Generator support","AFRU","SYS_BCBATCH",10000568,"","",{"$f":"VLOOKUP(U1539,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-06-18","2021-06-18","3","2022","1100","309359103","","","NWA","4010246 0170","Storm-2021-Time Sheet - 12001","810141","Corp Snr Mngr NT",1213.3499999999999,"AUD","","AFRU","SYS_BCBATCH",10006320,"","",{"$f":"VLOOKUP(U1540,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-06-18","2021-06-18","3","2022","1100","309359104","","","NWA","4010246 0170","Storm-2021-Time Sheet - 12001","810141","Corp Snr Mngr NT",1213.3499999999999,"AUD","","AFRU","SYS_BCBATCH",10006320,"","",{"$f":"VLOOKUP(U1541,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-06-18","2021-06-18","3","2022","1100","309359113","","","NWA","4010246 0170","Storm-2021-Time Sheet - 12001","810160","Corp Manager NT",956.64,"AUD","","AFRU","SYS_BCBATCH",10000682,"","",{"$f":"VLOOKUP(U1542,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-06-18","2021-06-18","3","2022","1100","309359114","","","NWA","4010246 0170","Storm-2021-Time Sheet - 12001","810160","Corp Manager NT",1016.43,"AUD","","AFRU","SYS_BCBATCH",10000682,"","",{"$f":"VLOOKUP(U1543,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-06-18","2021-06-18","3","2022","1100","309359115","","","NWA","4010246 0170","Storm-2021-Time Sheet - 12001","810160","Corp Manager NT",1255.5899999999999,"AUD","","AFRU","SYS_BCBATCH",10000682,"","",{"$f":"VLOOKUP(U1544,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-06-18","2021-06-18","3","2022","1100","309359116","","","NWA","4010246 0170","Storm-2021-Time Sheet - 12001","810160","Corp Manager NT",896.85,"AUD","","AFRU","SYS_BCBATCH",10000682,"","",{"$f":"VLOOKUP(U1545,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-06-18","2021-06-18","3","2022","1100","309359117","","","NWA","4010246 0170","Storm-2021-Time Sheet - 12001","810160","Corp Manager NT",538.11,"AUD","","AFRU","SYS_BCBATCH",10000682,"","",{"$f":"VLOOKUP(U1546,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-06-18","2021-06-18","3","2022","1100","309359118","","","NWA","4010246 0170","Storm-2021-Time Sheet - 12001","810160","Corp Manager NT",418.53,"AUD","","AFRU","SYS_BCBATCH",10000682,"","",{"$f":"VLOOKUP(U1547,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-06-18","2021-06-18","3","2022","1100","309359119","","","NWA","4010246 0170","Storm-2021-Time Sheet - 12001","810141","Corp Snr Mngr NT",1456.02,"AUD","","AFRU","SYS_BCBATCH",10000454,"","",{"$f":"VLOOKUP(U1548,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-06-18","2021-06-18","3","2022","1100","309359120","","","NWA","4010246 0170","Storm-2021-Time Sheet - 12001","810141","Corp Snr Mngr NT",1779.58,"AUD","","AFRU","SYS_BCBATCH",10000454,"","",{"$f":"VLOOKUP(U1549,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-06-18","2021-06-18","3","2022","1100","309359121","","","NWA","4010246 0170","Storm-2021-Time Sheet - 12001","810141","Corp Snr Mngr NT",1779.58,"AUD","","AFRU","SYS_BCBATCH",10000454,"","",{"$f":"VLOOKUP(U1550,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-06-18","2021-06-18","3","2022","1100","309359122","","","NWA","4010246 0170","Storm-2021-Time Sheet - 12001","810141","Corp Snr Mngr NT",1779.58,"AUD","","AFRU","SYS_BCBATCH",10000454,"","",{"$f":"VLOOKUP(U1551,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-06-18","2021-06-18","3","2022","1100","309359123","","","NWA","4010246 0170","Storm-2021-Time Sheet - 12001","810141","Corp Snr Mngr NT",1698.69,"AUD","","AFRU","SYS_BCBATCH",10000454,"","",{"$f":"VLOOKUP(U1552,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-06-18","2021-06-18","3","2022","1100","309359124","","","NWA","4010246 0170","Storm-2021-Time Sheet - 12001","810141","Corp Snr Mngr NT",1860.47,"AUD","","AFRU","SYS_BCBATCH",10000454,"","",{"$f":"VLOOKUP(U1553,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-06-21","2021-06-21","3","2022","1100","309361097","","","NWA","4010246 0170","Storm-2021-Time Sheet - 12001","810141","Corp Snr Mngr NT",1507.79,"AUD","","AFRU","SYS_BCBATCH",10000134,"","",{"$f":"VLOOKUP(U1554,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-06-21","2021-06-21","3","2022","1100","309361098","","","NWA","4010246 0170","Storm-2021-Time Sheet - 12001","810119","Corp Exec Mngr NT",910.84,"AUD","","AFRU","SYS_BCBATCH",10000213,"","",{"$f":"VLOOKUP(U1555,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["RMRU","RKL","2021-06-22","2021-06-22","3","2022","1100","309361785","","","NWA","4010246 0170","Storm-2021-Time Sheet - 12001","810142","Corp Strat Mngr NT",1541.55,"AUD","","AFRU","SYS_BCBATCH",10006950,"","",{"$f":"VLOOKUP(U1556,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["RMRU","RKL","2021-06-22","2021-06-22","3","2022","1100","309361828","","","NWA","4010246 0170","Storm-2021-Time Sheet - 12001","810160","Corp Manager NT",896.85,"AUD","","AFRU","SYS_BCBATCH",10007152,"","",{"$f":"VLOOKUP(U1557,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"No"},"Exclude"]
["RMRU","RKL","2021-06-22","2021-06-22","3","2022","1100","309361829","","","NWA","4010246 0170","Storm-2021-Time Sheet - 12001","810160","Corp Manager NT",896.85,"AUD","","AFRU","SYS_BCBATCH",10007152,"","",{"$f":"VLOOKUP(U1558,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"No"},"Exclude"]
["RMRU","RKL","2021-06-22","2021-06-22","3","2022","1100","309361830","","","NWA","4010246 0170","Storm-2021-Time Sheet - 12001","810160","Corp Manager NT",896.85,"AUD","","AFRU","SYS_BCBATCH",10007152,"","",{"$f":"VLOOKUP(U1559,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"No"},"Exclude"]
["RMRU","RKL","2021-06-22","2021-06-22","3","2022","1100","309361831","","","NWA","4010246 0170","Storm-2021-Time Sheet - 12001","810160","Corp Manager NT",896.85,"AUD","","AFRU","SYS_BCBATCH",10007152,"","",{"$f":"VLOOKUP(U1560,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"No"},"Exclude"]
["RMRU","RKL","2021-06-22","2021-06-22","3","2022","1100","309361832","","","NWA","4010246 0170","Storm-2021-Time Sheet - 12001","810160","Corp Manager NT",896.85,"AUD","","AFRU","SYS_BCBATCH",10007152,"","",{"$f":"VLOOKUP(U1561,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"No"},"Exclude"]
["RMRU","RKL","2021-06-23","2021-06-23","3","2022","1100","309363028","","","NWA","4010246 0170","Storm-2021-Time Sheet - 12001","810141","Corp Snr Mngr NT",242.67,"AUD","","AFRU","SYS_BCBATCH",10000454,"","",{"$f":"VLOOKUP(U1562,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-06-23","2021-06-23","3","2022","1100","309363029","","","NWA","4010246 0170","Storm-2021-Time Sheet - 12001","810141","Corp Snr Mngr NT",242.67,"AUD","","AFRU","SYS_BCBATCH",10000454,"","",{"$f":"VLOOKUP(U1563,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-06-23","2021-06-23","3","2022","1100","309363031","","","NWA","4010246 0170","Storm-2021-Time Sheet - 12001","810141","Corp Snr Mngr NT",1617.8,"AUD","","AFRU","SYS_BCBATCH",10000454,"","",{"$f":"VLOOKUP(U1564,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-06-24","2021-06-24","3","2022","1100","309364404","","","NWA","4010246 0170","Storm-2021-Time Sheet - 12001","810122","Corp Prof Exp NT",758.85,"AUD","","AFRU","SYS_BCBATCH",10000404,"","",{"$f":"VLOOKUP(U1565,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["RMRU","RKL","2021-06-24","2021-06-24","3","2022","1100","309364405","","","NWA","4010246 0170","Storm-2021-Time Sheet - 12001","810122","Corp Prof Exp NT",758.85,"AUD","","AFRU","SYS_BCBATCH",10000404,"","",{"$f":"VLOOKUP(U1566,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["RMRU","RKL","2021-06-24","2021-06-24","3","2022","1100","309364406","","","NWA","4010246 0170","Storm-2021-Time Sheet - 12001","810122","Corp Prof Exp NT",758.85,"AUD","","AFRU","SYS_BCBATCH",10000404,"","",{"$f":"VLOOKUP(U1567,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["RMRU","RKL","2021-06-24","2021-06-24","3","2022","1100","309364407","","","NWA","4010246 0170","Storm-2021-Time Sheet - 12001","810122","Corp Prof Exp NT",758.85,"AUD","","AFRU","SYS_BCBATCH",10000404,"","",{"$f":"VLOOKUP(U1568,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["RMRU","RKL","2021-06-24","2021-06-24","3","2022","1100","309364408","","","NWA","4010246 0170","Storm-2021-Time Sheet - 12001","810122","Corp Prof Exp NT",758.85,"AUD","","AFRU","SYS_BCBATCH",10000404,"","",{"$f":"VLOOKUP(U1569,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"NO"},"Exclude"]
["RMRU","RKL","2021-06-24","2021-06-24","3","2022","1100","309364409","","","NWA","4010246 0170","Storm-2021-Time Sheet - 12001","810141","Corp Snr Mngr NT",323.56,"AUD","","AFRU","SYS_BCBATCH",10000454,"","",{"$f":"VLOOKUP(U1570,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-06-27","2021-06-27","3","2022","1100","309379109","","","NWA","4010246 0170","Storm-2021-Time Sheet - 12001","810141","Corp Snr Mngr NT",323.56,"AUD","","AFRU","SYS_BCBATCH",10000454,"","",{"$f":"VLOOKUP(U1571,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-06-27","2021-06-27","3","2022","1100","309379110","","","NWA","4010246 0170","Storm-2021-Time Sheet - 12001","810141","Corp Snr Mngr NT",485.34,"AUD","","AFRU","SYS_BCBATCH",10000454,"","",{"$f":"VLOOKUP(U1572,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-06-27","2021-06-27","3","2022","1100","309379111","","","NWA","4010246 0170","Storm-2021-Time Sheet - 12001","810141","Corp Snr Mngr NT",242.67,"AUD","","AFRU","SYS_BCBATCH",10000454,"","",{"$f":"VLOOKUP(U1573,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-06-25","2021-06-25","3","2022","1100","309379861","","","NWA","4010246 0170","Storm-2021-Time Sheet - 12001","810120","Corp Ops Lead NT",583.28,"AUD","","AFRU","SYS_BCBATCH",10008984,"","",{"$f":"VLOOKUP(U1574,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-06-25","2021-06-25","3","2022","1100","309379862","","","NWA","4010246 0170","Storm-2021-Time Sheet - 12001","810120","Corp Ops Lead NT",699.93,"AUD","","AFRU","SYS_BCBATCH",10008984,"","",{"$f":"VLOOKUP(U1575,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-06-28","2021-06-28","3","2022","1100","309382004","","","NWA","4010246 0170","Storm-2021-Time Sheet - 12001","810142","Corp Strat Mngr NT",1952.63,"AUD","EMLO role at SCC","AFRU","SYS_BCBATCH",10001031,"","",{"$f":"VLOOKUP(U1576,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-06-28","2021-06-28","3","2022","1100","309382005","","","NWA","4010246 0170","Storm-2021-Time Sheet - 12001","810142","Corp Strat Mngr NT",2055.4,"AUD","EMLO at SCC","AFRU","SYS_BCBATCH",10001031,"","",{"$f":"VLOOKUP(U1577,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-06-28","2021-06-28","3","2022","1100","309382006","","","NWA","4010246 0170","Storm-2021-Time Sheet - 12001","810142","Corp Strat Mngr NT",2466.48,"AUD","EMLO at SCC","AFRU","SYS_BCBATCH",10001031,"","",{"$f":"VLOOKUP(U1578,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-06-28","2021-06-28","3","2022","1100","309382007","","","NWA","4010246 0170","Storm-2021-Time Sheet - 12001","810142","Corp Strat Mngr NT",2020.46,"AUD","EMLO at SCC","AFRU","SYS_BCBATCH",10001031,"","",{"$f":"VLOOKUP(U1579,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-06-28","2021-06-28","3","2022","1100","309382008","","","NWA","4010246 0170","Storm-2021-Time Sheet - 12001","810142","Corp Strat Mngr NT",2363.71,"AUD","EMLO at SCC","AFRU","SYS_BCBATCH",10001031,"","",{"$f":"VLOOKUP(U1580,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-06-28","2021-06-28","3","2022","1100","309382009","","","NWA","4010246 0170","Storm-2021-Time Sheet - 12001","810142","Corp Strat Mngr NT",2363.71,"AUD","EMLO at SCC","AFRU","SYS_BCBATCH",10001031,"","",{"$f":"VLOOKUP(U1581,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-06-28","2021-06-28","3","2022","1100","309382010","","","NWA","4010246 0170","Storm-2021-Time Sheet - 12001","810142","Corp Strat Mngr NT",2466.48,"AUD","","AFRU","SYS_BCBATCH",10001031,"","",{"$f":"VLOOKUP(U1582,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-06-28","2021-06-28","3","2022","1100","309382011","","","NWA","4010246 0170","Storm-2021-Time Sheet - 12001","810142","Corp Strat Mngr NT",2363.71,"AUD","","AFRU","SYS_BCBATCH",10001031,"","",{"$f":"VLOOKUP(U1583,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-06-28","2021-06-28","3","2022","1100","309382012","","","NWA","4010246 0170","Storm-2021-Time Sheet - 12001","810141","Corp Snr Mngr NT",1213.3499999999999,"AUD","","AFRU","SYS_BCBATCH",10007804,"","",{"$f":"VLOOKUP(U1584,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-07-03","2021-07-03","4","2022","1100","309467571","","","NWA","4010246 0170","Storm-2021-Time Sheet - 12001","810160","Corp Manager NT",1278.3,"AUD","","AFRU","SYS_BCBATCH",10000734,"","",{"$f":"VLOOKUP(U1585,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-07-03","2021-07-03","4","2022","1100","309467572","","","NWA","4010246 0170","Storm-2021-Time Sheet - 12001","810160","Corp Manager NT",1278.3,"AUD","","AFRU","SYS_BCBATCH",10000734,"","",{"$f":"VLOOKUP(U1586,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-07-03","2021-07-03","4","2022","1100","309467652","","","NWA","4010246 0170","Storm-2021-Time Sheet - 12001","810141","Corp Snr Mngr NT",1213.3499999999999,"AUD","","AFRU","SYS_BCBATCH",10001030,"","",{"$f":"VLOOKUP(U1587,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-07-03","2021-07-03","4","2022","1100","309467658","","","NWA","4010246 0170","Storm-2021-Time Sheet - 12001","810141","Corp Snr Mngr NT",566.23,"AUD","","AFRU","SYS_BCBATCH",10007804,"","",{"$f":"VLOOKUP(U1588,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-07-15","2021-07-15","4","2022","1100","309479982","","","NWA","4010246 0170","Storm-2021-Time Sheet - 12001","810224","Corp Prof Spec OT",2023.44,"AUD","Volunteering in response to Storm at Lil","AFRU","SYS_BCBATCH",10009738,"","",{"$f":"VLOOKUP(U1589,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["","",null,null,"","","","","","","","4010246 0170","","","",69409.64,"AUD","","","",null,"",""]
["RFBU","COIN","2021-07-06","2021-07-06","4","2022","1100","108263863","","","NWA","4010246 0180","Storm-2021-Purchase Orders - 12001","521505","Vehicle Parking",20,"AUD","EEXP Joanne Soysa EMLO parking 11th","BKPFF","BSANKARA",0,"","SA",null,"Include","Internal"]
["RFBU","COIN","2021-07-06","2021-07-06","4","2022","1100","108263863","","","NWA","4010246 0180","Storm-2021-Purchase Orders - 12001","521505","Vehicle Parking",10,"AUD","EEXP Joanne Soysa parking 12th June","BKPFF","BSANKARA",0,"","SA",null,"Include","Internal"]
["RFBU","COIN","2021-07-06","2021-07-06","4","2022","1100","108263863","","","NWA","4010246 0180","Storm-2021-Purchase Orders - 12001","521508","Accommodation",18.25,"AUD","EEXP Joanne Soysa Meal and Parking 15th","BKPFF","BSANKARA",0,"","SA",null,"Include","Internal"]
["RFBU","COIN","2021-07-06","2021-07-06","4","2022","1100","108263863","","","NWA","4010246 0180","Storm-2021-Purchase Orders - 12001","521506","Transportation",20,"AUD","EEXP Joanne Soysa Meal and Parking 15th","BKPFF","BSANKARA",0,"","SA",null,"Include","Internal"]
["RFBU","COIN","2021-07-06","2021-07-06","4","2022","1100","108263863","","","NWA","4010246 0180","Storm-2021-Purchase Orders - 12001","521505","Vehicle Parking",73,"AUD","EEXP Joanne Soysa Parking EMLO","BKPFF","BSANKARA",0,"","SA",null,"Include","Internal"]
["RFBU","COIN","2021-07-06","2021-07-06","4","2022","1100","108263863","","","NWA","4010246 0180","Storm-2021-Purchase Orders - 12001","521505","Vehicle Parking",10,"AUD","EEXP Joanne Soysa Parking 19th","BKPFF","BSANKARA",0,"","SA",null,"Include","Internal"]
["RFBU","COIN","2021-07-06","2021-07-06","4","2022","1100","108263863","","","NWA","4010246 0180","Storm-2021-Purchase Orders - 12001","521505","Vehicle Parking",20,"AUD","EEXP Joanne Soysa parking 25th","BKPFF","BSANKARA",0,"","SA",null,"Include","Internal"]
["RFBU","COIN","2021-07-06","2021-07-06","4","2022","1100","108263863","","","NWA","4010246 0180","Storm-2021-Purchase Orders - 12001","521505","Vehicle Parking",20,"AUD","EEXP Joanne Soysa parking 18th","BKPFF","BSANKARA",0,"","SA",null,"Include","Internal"]
["RFBU","COIN","2021-07-06","2021-07-06","4","2022","1100","108263863","","","NWA","4010246 0180","Storm-2021-Purchase Orders - 12001","521505","Vehicle Parking",10,"AUD","EEXP Joanne Soysa parking 14th June","BKPFF","BSANKARA",0,"","SA",null,"Include","Internal"]
["RFBU","COIN","2021-07-24","2021-07-24","4","2022","1100","108276188","","","NWA","4010246 0180","Storm-2021-Purchase Orders - 12001","516413","Light Meals on Site",62.91,"AUD","PCARD Andrew Kennan Meals","BKPFF","SYS_BCBATCH",0,"","SA",null,"Include","Internal"]
["RFBU","COIN","2021-07-24","2021-07-24","4","2022","1100","108276188","","","NWA","4010246 0180","Storm-2021-Purchase Orders - 12001","516413","Light Meals on Site",6,"AUD","PCARD Andrew Kennan Meals","BKPFF","SYS_BCBATCH",0,"","SA",null,"Include","Internal"]
["RFBU","COIN","2021-07-24","2021-07-24","4","2022","1100","108276188","","","NWA","4010246 0180","Storm-2021-Purchase Orders - 12001","516413","Light Meals on Site",4.3,"AUD","PCARD Andrew Kennan Meals","BKPFF","SYS_BCBATCH",0,"","SA",null,"Include","Internal"]
["RFBU","COIN","2021-07-24","2021-07-24","4","2022","1100","108276188","","","NWA","4010246 0180","Storm-2021-Purchase Orders - 12001","516413","Light Meals on Site",10,"AUD","PCARD Andrew Kennan Meals","BKPFF","SYS_BCBATCH",0,"","SA",null,"Include","Internal"]
["RFBU","COIN","2021-07-24","2021-07-24","4","2022","1100","108276188","","","NWA","4010246 0180","Storm-2021-Purchase Orders - 12001","516413","Light Meals on Site",26,"AUD","PCARD Andrew Kennan Meals","BKPFF","SYS_BCBATCH",0,"","SA",null,"Include","Internal"]
["RFBU","COIN","2021-07-24","2021-07-24","4","2022","1100","108276188","","","NWA","4010246 0180","Storm-2021-Purchase Orders - 12001","516413","Light Meals on Site",19.46,"AUD","PCARD Andrew Kennan Meals","BKPFF","SYS_BCBATCH",0,"","SA",null,"Include","Internal"]
["RMRU","RKL","2021-07-03","2021-07-03","4","2022","1100","309467655","","","NWA","4010246 0180","Storm-2021-Purchase Orders - 12001","810124","Corp Prof Spec NT",843.08,"AUD","Work in SCC","AFRU","SYS_BCBATCH",10010015,"","",{"$f":"VLOOKUP(U1606,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-07-03","2021-07-03","4","2022","1100","309467656","","","NWA","4010246 0180","Storm-2021-Purchase Orders - 12001","810124","Corp Prof Spec NT",899.28,"AUD","Work in SCC","AFRU","SYS_BCBATCH",10010015,"","",{"$f":"VLOOKUP(U1607,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-07-03","2021-07-03","4","2022","1100","309467657","","","NWA","4010246 0180","Storm-2021-Purchase Orders - 12001","810124","Corp Prof Spec NT",786.87,"AUD","Work in SCC","AFRU","SYS_BCBATCH",10010015,"","",{"$f":"VLOOKUP(U1608,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["","",null,null,"","","","","","","","4010246 0180","","","",2859.15,"AUD","","","",null,"",""]
["RFBU","COIN","2021-09-29","2021-09-29","6","2022","1100","108504252","","","NWA","4010246 0190","Storm -2021- REFCL - 12014","511100","Svc Prov - Contracts",158173.5,"AUD","LDL REFCL Testing After Storm - Additional Work","BKPFF","PRAVEENK",0,"","AC",null,"Include","Internal"]
["RMRU","RKL","2021-06-23","2021-06-23","3","2022","1100","309363013","","","NWA","4010246 0190","Storm -2021- REFCL - 12014","810160","Corp Manager NT",958.73,"AUD","","AFRU","SYS_BCBATCH",10001668,"","",{"$f":"VLOOKUP(U1611,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-06-23","2021-06-23","3","2022","1100","309363014","","","NWA","4010246 0190","Storm -2021- REFCL - 12014","810160","Corp Manager NT",958.73,"AUD","","AFRU","SYS_BCBATCH",10001668,"","",{"$f":"VLOOKUP(U1612,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-07-06","2021-07-06","4","2022","1100","309470330","","","NWA","4010246 0190","Storm -2021- REFCL - 12014","810160","Corp Manager NT",958.73,"AUD","","AFRU","SYS_BCBATCH",10000441,"","",{"$f":"VLOOKUP(U1613,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-07-06","2021-07-06","4","2022","1100","309470331","","","NWA","4010246 0190","Storm -2021- REFCL - 12014","810160","Corp Manager NT",958.73,"AUD","","AFRU","SYS_BCBATCH",10000441,"","",{"$f":"VLOOKUP(U1614,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["","",null,null,"","","","","","","","4010246 0190","","","",162008.42000000001,"AUD","","","",null,"",""]
["RFBU","COIN","2021-07-20","2021-07-20","4","2022","1100","108267402","","","NWA","4010246 0200","Storm -2021- REFCL - 12001","506401","S&W Proj - NT Adj",9398.02,"AUD","Storm damage costs","BKPFF","WF-BATCH",0,"","AB",null,"Exclude"]
["RMRU","RKL","2021-06-21","2021-06-21","3","2022","1100","309360612","","","NWA","4010246 0200","Storm -2021- REFCL - 12001","810143","Corp Support NT",445.13,"AUD","LDL11 transfer analysis","AFRU","SYS_BCBATCH",10009393,"","",{"$f":"VLOOKUP(U1617,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-06-21","2021-06-21","3","2022","1100","309360613","","","NWA","4010246 0200","Storm -2021- REFCL - 12001","810143","Corp Support NT",445.13,"AUD","LDL11 transfer analysis","AFRU","SYS_BCBATCH",10009393,"","",{"$f":"VLOOKUP(U1618,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-07-06","2021-07-06","4","2022","1100","309470332","","","NWA","4010246 0200","Storm -2021- REFCL - 12001","810160","Corp Manager NT",958.73,"AUD","","AFRU","SYS_BCBATCH",10000441,"","",{"$f":"VLOOKUP(U1619,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-07-06","2021-07-06","4","2022","1100","309470333","","","NWA","4010246 0200","Storm -2021- REFCL - 12001","810160","Corp Manager NT",958.73,"AUD","","AFRU","SYS_BCBATCH",10000441,"","",{"$f":"VLOOKUP(U1620,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-07-16","2021-07-16","4","2022","1100","309485274","","","NWA","4010246 0200","Storm -2021- REFCL - 12001","810143","Corp Support NT",445.13,"AUD","LDL unbalance analysis to check network","AFRU","SYS_BCBATCH",10009393,"","",{"$f":"VLOOKUP(U1621,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-07-26","2021-07-26","4","2022","1100","309501633","","","NWA","4010246 0200","Storm -2021- REFCL - 12001","810143","Corp Support NT",445.13,"AUD","LDL PB testing","AFRU","SYS_BCBATCH",10009393,"","",{"$f":"VLOOKUP(U1622,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["","RKL","2021-07-19","2021-08-02","5","2022","1100","309572303","","","NWA","4010246 0200","Storm -2021- REFCL - 12001","810300","Allowance Expenses",50.4,"AUD","LDL ZSS to Home","CATS","SYS_BCBATCH",10009393,"","",{"$f":"VLOOKUP(U1623,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["","RKL","2021-07-19","2021-08-02","5","2022","1100","309572303","","","NWA","4010246 0200","Storm -2021- REFCL - 12001","810300","Allowance Expenses",50.4,"AUD","Home to LDL ZSS","CATS","SYS_BCBATCH",10009393,"","",{"$f":"VLOOKUP(U1624,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-08-02","2021-08-02","5","2022","1100","309574244","","","NWA","4010246 0200","Storm -2021- REFCL - 12001","810243","Corp Support OT",267.08999999999997,"AUD","LDL PB testing","AFRU","SYS_BCBATCH",10009393,"","",{"$f":"VLOOKUP(U1625,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["RMRU","RKL","2021-08-02","2021-08-02","5","2022","1100","309574245","","","NWA","4010246 0200","Storm -2021- REFCL - 12001","810243","Corp Support OT",267.08999999999997,"AUD","LDL PB testing","AFRU","SYS_BCBATCH",10009393,"","",{"$f":"VLOOKUP(U1626,'[1]3. Labour - TS'!$R:$Y,8,0)","v":"Yes"},"Include","Internal"]
["","",null,null,"","","","","","","","4010246 0200","","","",13730.98,"AUD","","","",null,"",""]
["","",null,null,"","","","","","","","","","","",7477311,"AUD","","","",null,"",""]
[]
[]
[]
[]
[]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Include / Exclude","(Multiple Items)"]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Include / Exclude","Include",null,"Include / Exclude","(Multiple Items)",null,null,null,null,null,null,null,null,"Object","(Multiple Items)"]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Opex by AST Division"]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Row Labels","Sum of Val/COArea Crcy",null,"Row Labels","Sum of Val/COArea Crcy",null,"Net Ops",{"$f":"T1638+T1639+T1652","v":7044490.3000000082},null,null,null,null,null,"Row Labels","Cost element name","Sum of Val/COArea Crcy"]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Accommodation",7504.8199999999979,null,"4010246 0010",1078478.5600000012,1078478.5600000012,"REA",{"$f":"T1654","v":20408.3},null,null,null,null,null,"506401","S&W Proj - NT Adj",538274.70000000007]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Allowance Expenses",18731.910000000007,null,"4010246 0020",5804003.3200000068,5804003.3200000068,"Finance",0,null,null,null,null,null,"506500","Cont Lab Non-Payroll",159919.84]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Claims & Settlements",942214.6100000001,null,"4010246 0070",4158.1499999999996,4158.1499999999996,"Gov",{"$f":"T1640+T1641","v":8185.0199999999995},null,null,null,null,null,"506701","Reward & Recognition",942.2]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Comms Charges",285164,null,"4010246 0080",4026.87,4026.87,"GFN",{"$f":"T1642+T1643","v":16801.569999999996},null,null,null,null,null,"511100","Svc Prov - Contracts",664183.85]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Comrcl Surge Claims",32978.859999999986,null,"4010246 0090",14702.979999999998,14702.979999999998,"Digital",{"$f":"T1644+T1645","v":119070.34000000003},null,null,null,null,null,"511104","Svc Prov - Labour",360]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Corp Manager NT",37957.040000000008,null,"4010246 0100",2098.5899999999997,2098.5899999999997,"Strategy",{"$f":"T1646+T1647","v":69134.369999999966},null,null,null,null,null,"511201","Maintenance - Vegeta",2864156]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Corp Ops Lead NT",4952.51,null,"4010246 0110",68114.160000000018,68114.160000000018,"PSC",{"$f":"T1648+T1649","v":113221.33000000002},null,null,null,null,null,"511202","Maintenance - Asset",199999.22]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Corp Ops Lead OT",917.32999999999993,null,"4010246 0120",50956.18,50956.18,"NM",{"$f":"T1650+T1651+T1653","v":85999.769999999975},null,null,null,null,null,"516102","IT Hardware",107.59]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Corp Prof Exp NT",32534.419999999976,null,"4010246 0130",25314.97999999997,25314.97999999997,null,{"$f":"SUM(V1637:V1645)","v":7477311.0000000075},null,null,null,null,null,"516103","Comms Charges",285164]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Corp Prof Exp OT",22951.019999999993,null,"4010246 0140",43819.39,43819.39,null,null,null,null,null,null,null,"516105","Phones & Pagers",229.36]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Corp Prof NT",33596.429999999993,null,"4010246 0150",37936.710000000006,37936.710000000006,null,null,null,null,null,null,null,"516204","Professional Fees",185632.99999999997]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Corp Prof OT",18398.769999999993,null,"4010246 0160",75284.62000000001,75284.62000000001,null,null,null,null,null,null,null,"516300","Lease - MV & Mobil",12.97]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Corp Prof Spec NT",22976.649999999998,null,"4010246 0170",69409.639999999985,69409.639999999985,null,null,null,null,null,null,null,"516400","General Expenses",15063.64]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Corp Prof Spec OT",4046.88,null,"4010246 0180",2859.1499999999996,2859.1499999999996,null,null,null,null,null,null,null,"516401","Office Expenses",122]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Corp Semi Prof NT",3579.86,null,"4010246 0190",162008.42000000001,162008.42000000001,null,null,null,null,null,null,null,"516402","Protective Clothing",3868.98]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Corp Semi Prof OT",7197.3200000000006,null,"4010246 0200",13730.98,13730.98,null,null,null,null,null,null,null,"516405","Public relations",13478.52]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Corp Snr Mngr NT",99477.410000000091,null,"4010246 0040",20408.3,20408.3,null,null,null,null,null,null,null,"516407","Vehicle Tolls",26.55]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Corp Snr Mngr OT",28901.569999999996,null,"Grand Total",7477311.0000000084,7477311.0000000084,null,null,null,null,null,null,null,"516408","Freight & Couriers",4.99]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Corp Strat Mngr NT",27140.709999999995,null,null,null,null,null,null,null,null,null,null,null,"516413","Light Meals on Site",7395.7199999999993]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Corp Support NT",7775.8699999999972,null,null,null,null,null,null,null,null,null,null,null,"516416","Entertmnt - Meals",24.5]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Corp Support OT",679.02,null,null,null,null,null,null,null,null,null,null,null,"521100","Materials",2978.44]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Cust Comp - Non-GSL",42913.020000000004,null,null,null,null,null,null,null,null,null,null,null,"521400","MV & Plant - Fuel",23862.370000000003,null,null,"Labour",{"$f":"SUM(AD1672:AD1693,AD1638:AD1640)","v":1205726.93}]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Domestic Surge Claim",72854.38,null,null,null,null,null,null,null,null,null,null,null,"521402","MV - Maintenance",293.39000000000004,null,null,"Maintenance",{"$f":"SUM(AD1641:AD1644,AD1667)","v":3880316.1900000004}]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Entertmnt - Meals",24.5,null,null,null,null,null,null,null,null,null,null,null,"521406","Hire - Plant & Equip",174405.99000000002,null,null,"IT & Communications",{"$f":"SUM(AD1645:AD1647)","v":285500.95}]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Freight & Couriers",4.99,null,null,null,null,null,null,null,null,null,null,null,"521505","Vehicle Parking",492.71999999999997,null,null,"External Consulting & Legal",{"$f":"SUM(GETPIVOTDATA(\"Val/COArea Crcy\",$AB$1637,\"Cost Element\",\"516204\",\"Cost element name\",\"Professional Fees\"))","v":185632.99999999997}]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"General Expenses",89583.91,null,null,null,null,null,null,null,null,null,null,null,"521506","Transportation",45.12,null,null,"Operating Leases",{"$f":"SUM(GETPIVOTDATA(\"Val/COArea Crcy\",$AB$1637,\"Cost Element\",\"516300\",\"Cost element name\",\"Lease - MV & Mobil\"))","v":12.97}]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"General IT Support",690,null,null,null,null,null,null,null,null,null,null,null,"521507","Travel",4342.4800000000005,null,null,"Materials",{"$f":"SUM(GETPIVOTDATA(\"Val/COArea Crcy\",$AB$1637,\"Cost Element\",\"521100\",\"Cost element name\",\"Materials\"))","v":2978.44}]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"IT Hardware",868.79000000000008,null,null,null,null,null,null,null,null,null,null,null,"521508","Accommodation",6508.6799999999985,null,null,"Motor Vehicle & Mobile Plant",{"$f":"SUM(AD1659:AD1661,AD1654)","v":198588.30000000002}]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"IT Software",13525,null,null,null,null,null,null,null,null,null,null,null,"521517","Ombudsman Levy",143425.29999999999,null,null,"Other Costs",{"$f":"SUM(AD1650:AD1653,AD1655,AD1656,AD1657,AD1662,AD1663,AD1664,AD1665,AD1666)","v":194772.65}]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Lease - MV & Mobil",12.97,null,null,null,null,null,null,null,null,null,null,null,"521521","Maint - security cos",151617.12,null,null,"Claims",{"$f":"SUM(AD1668:AD1671)","v":1090960.8700000001}]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Light Meals on Site",31354.860000000008,null,null,null,null,null,null,null,null,null,null,null,"521601","Claims & Settlements",942214.6100000001,null,null,null,{"$f":"SUM(AH1659:AH1667)","v":7044490.3000000007}]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Maint - security cos",151617.12,null,null,null,null,null,null,null,null,null,null,null,"521602","Domestic Surge Claim",72854.38]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Maintenance - Asset",199999.22,null,null,null,null,null,null,null,null,null,null,null,"521603","Comrcl Surge Claims",32978.86000000003]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Maintenance - Vegeta",2864156,null,null,null,null,null,null,null,null,null,null,null,"521605","Cust Comp - Non-GSL",42913.02]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Materials",3204.6200000000008,null,null,null,null,null,null,null,null,null,null,null,"810100","Dxn Controller NT",4798.08]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Minor Equip Purchase",200.87,null,null,null,null,null,null,null,null,null,null,null,"810118","Project Manager NT",6832.2399999999989]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"MV - Maintenance",293.39000000000004,null,null,null,null,null,null,null,null,null,null,null,"810119","Corp Exec Mngr NT",26632.199999999993]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"MV & Plant - Fuel",23862.370000000003,null,null,null,null,null,null,null,null,null,null,null,"810120","Corp Ops Lead NT",10573.430000000004]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Office Expenses",49561.510000000009,null,null,null,null,null,null,null,null,null,null,null,"810122","Corp Prof Exp NT",34445.449999999968]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Ombudsman Levy",143425.29999999999,null,null,null,null,null,null,null,null,null,null,null,"810123","Corp Prof NT",31831.979999999985]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Phones & Pagers",229.36,null,null,null,null,null,null,null,null,null,null,null,"810124","Corp Prof Spec NT",14455.399999999998]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Postal Charges",192.65,null,null,null,null,null,null,null,null,null,null,null,"810136","Corp Semi Prof NT",3579.86]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Professional Fees",185632.99999999997,null,null,null,null,null,null,null,null,null,null,null,"810141","Corp Snr Mngr NT",79846.27999999997]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Project Manager NT",8540.2999999999993,null,null,null,null,null,null,null,null,null,null,null,"810142","Corp Strat Mngr NT",28527.75]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Protective Clothing",10421.25,null,null,null,null,null,null,null,null,null,null,null,"810143","Corp Support NT",8001.73]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Public relations",13478.52,null,null,null,null,null,null,null,null,null,null,null,"810160","Corp Manager NT",33179.729999999981]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Reward & Recognition",942.2,null,null,null,null,null,null,null,null,null,null,null,"810200","Dxn Controller OT",1874.25]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Svc Prov - Contracts",664183.85000000009,null,null,null,null,null,null,null,null,null,null,null,"810220","Corp Ops Lead OT",12226.040000000003]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Svc Prov - Labour",360,null,null,null,null,null,null,null,null,null,null,null,"810222","Corp Prof Exp OT",31654.3]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Transportation",65.12,null,null,null,null,null,null,null,null,null,null,null,"810223","Corp Prof OT",28921.239999999994]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Travel",4342.4800000000005,null,null,null,null,null,null,null,null,null,null,null,"810224","Corp Prof Spec OT",5395.84]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Vehicle Parking",740.7199999999998,null,null,null,null,null,null,null,null,null,null,null,"810236","Corp Semi Prof OT",11035.32]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Vehicle Tolls",26.55,null,null,null,null,null,null,null,null,null,null,null,"810241","Corp Snr Mngr OT",65485.819999999985]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Hire - Plant & Equip",174405.99000000002,null,null,null,null,null,null,null,null,null,null,null,"810243","Corp Support OT",25690.090000000011]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Legal Expenses",23544.3,null,null,null,null,null,null,null,null,null,null,null,"810260","Corp Manager OT",18116.389999999996]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Grand Total",6414936.120000001,null,null,null,null,null,null,null,null,null,null,null,"810300","Allowance Expenses",23486.769999999993]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Grand Total",null,7044490.3000000017]

{"sheet":"Positions TS & cons.June21 Stor","index":5,"n_rows":31,"n_cols":22,"rows_kept":31,"cut":false,"hidden":true,"merged":[]}
["Division","Org Unit","Org Unit Description","Cost Center","Cost Center Desc","Employee No.","Employee Name","Position","Position - Description","Manager's Emp No.","Manager's Name","Manager's Position","Manager's Position Desc","Location ID","Location","Employment Status","Type","Company Code","Company Code Desc","Hours per week","Headcount","FTE"]
["Network Operations & Safety","10000053","CEOT","13104","Distribution Control","10010010","Peter Galey","30022480","Network Control Support Manager","10000174","Julie Warke","30019834","Manager, CEOT","3005","Flinders St","Permanent Full Time","IEA","1200","AusNet Electricity Srvs","37.50",1,1]
["Network Operations & Safety","10000199","Transmission Performance","13263","Transmission Control","10000711","Martin Cavanagh","30000172","Manager, Operational and Access Planning","10000087","Tim Lloyd","30018660","GM Network Control & Operations","3005","Flinders St","Permanent Full Time","IEA","2100","AusNet Transmission Grp","37.50",1,1]
["Network Operations & Safety","10000209","Customer & Support - East","13187","Community Engagement","10000478","Derek Walton","30020895","Community Engagement Manager","10009850","Kate Lancaster","30021390","Customer Comms & Engagement Manager","3022","Traralgon","Permanent Full Time","IEA","1200","AusNet Electricity Srvs","37.50",1,1]
["Network Operations & Safety","10000263","Commissioning & Construction","13513","Commissioning & Cons","10001121","Nick Hewes","30001063","Lines Connect Engineer","10007676","Matthew Yob","30021190","Group Leader Commissioning & Constructn","3011","Malvern","Permanent Full Time","IEA","1200","AusNet Electricity Srvs","37.50",1,1]
["Network Operations & Safety","10000263","Commissioning & Construction","13513","Commissioning & Cons","10001200","Mathew Durack","30001128","Lines Connect Engineer","10007676","Matthew Yob","30021190","Group Leader Commissioning & Constructn","3011","Malvern","Permanent Full Time","IEA","1200","AusNet Electricity Srvs","37.50",1,1]
["Network Operations & Safety","10000290","Lines Engineering Design","12012","Engineering Solution","10009019","Rafi Muneer","30002212","Design Engineer","10010038","Gope Gunaratnam","30022598","Team Leader Engineering Design","3010","Lilydale","Permanent Full Time","IEA","1200","AusNet Electricity Srvs","37.50",1,1]
["Network Operations & Safety","10000290","Lines Engineering Design","12012","Engineering Solution","10002617","Stephanie Phillips","30010826","Design Officer","10010038","Gope Gunaratnam","30022598","Team Leader Engineering Design","3010","Lilydale","Permanent Full Time","ASU/APESMA","1200","AusNet Electricity Srvs","37.50",1,1]
["Network Operations & Safety","10000328","Local Network Service Provider (LNSP)","12018","Mark Data & Mter Ser","10008666","Khyati Shah","30001672","LNSP Analyst","10001682","Prachi Mehta","30010802","LNSP Team Leader","3007","Freshwater Pl","Permanent Full Time","IEA","1200","AusNet Electricity Srvs","37.50",1,1]
["Network Operations & Safety","10000343","Customer Programs - North","13121","Cust Prog central","10002224","Matt Parker","30022670","Energy Project Coordinator - Complex","10001247","Paul Tanner","30020888","Customer Program Manager - North","3026","Wodonga","Permanent Full Time","IEA","1200","AusNet Electricity Srvs","37.50",1,1]
["Network Operations & Safety","10000343","Customer Programs - North","13121","Cust Prog central","10001415","Paul Kempton","30021197","Energy Project Coordinator - Complex","10001247","Paul Tanner","30020888","Customer Program Manager - North","3010","Lilydale","Permanent Full Time","ASU/APESMA","1200","AusNet Electricity Srvs","37.50",1,1]
["Network Operations & Safety","10000407","Network Control 3","13104","Distribution Control","10002460","Matt McEwan","30007469","Network Controller (D)","10000593","Sergio Inacio","30008519","Shift Manager","3005","Flinders St","Permanent Full Time","IEA Shift 12","1200","AusNet Electricity Srvs","37.50",1,1]
["Network Operations & Safety","10002231","Customer Programs - East","13723","Cust Prog Cent East","10000368","Gareth Downes","30020736","Customer Program Manager - East","10009397","Scott Harvey","30018448","Customer Projects Manager","3001","Beaconsfield","Permanent Full Time","IEA","1200","AusNet Electricity Srvs","37.50",1,1]
["Network Operations & Safety","10002317","Distribution Network Access Planning","13031","Operations Optimisat","10002256","Dulan Gamage","30021138","Network Reliability Perf Engineer Lead","10004457","Johnny Mangala","30020613","Distribution Network Access Manager","3005","Flinders St","Permanent Full Time","IEA","1200","AusNet Electricity Srvs","37.50",1,1]
["Network Operations & Safety","10002317","Distribution Network Access Planning","13031","Operations Optimisat","10002501","Lin Wu","30021137","Network Reliability Analyst","10004457","Johnny Mangala","30020613","Distribution Network Access Manager","3005","Flinders St","Permanent Full Time","IEA","2100","AusNet Transmission Grp","37.50",1,1]
["Network Operations & Safety","10004392","Metering Field Data Collection - LDL","16008","Business Enablement","10002370","Willem VanEkeris","30002458","Field Service Representative Lilydale","10000402","Terry Poulton","30000441","Fld Data Collectn Manager Central","3010","Lilydale","Permanent Full Time","ASU/APESMA","1200","AusNet Electricity Srvs","37.50",1,1]
["Network Management & Digital","10004485","Human Centred Design","12213","Digital Futures&Inno","10000507","Lance Robson","30018351","Business Analyst","10007159","Rebecca Monaghan","30014005","Head of Human Centred Design","3007","Freshwater Pl","Permanent Full Time","IEA","2100","AusNet Transmission Grp","37.50",1,1]
["Network Operations & Safety","10004529","Security & Emergency Services","13981","Security & Emergency","10009860","Tony Jifkins","30014712","Project Security Advisor","10007022","James Radalj","30000338","Security & Emergency Serv Manager","3007","Freshwater Pl","Permanent Full Time","IEA","1200","AusNet Electricity Srvs","37.50",1,1]
["Network Operations & Safety","10005903","TX Contract Management","14605","Contract Mang Trans","10000113","Geoff Thorn","30021437","Transmission Contract Manager","10000097","Dean Kemp","30018661","GM Field Operations","3007","Freshwater Pl","Permanent Full Time","IEA","2100","AusNet Transmission Grp","37.50",1,1]
["Network Management & Digital","10006354","5MS","12029","Future Technology Pl","10009915","Amy Miller","30021340","Project Manager (Enterprise)","10009538","Suresh Maguluri","30019857","Program Director - 5MS","3007","Freshwater Pl","Permanent Full Time","IEA","1200","AusNet Electricity Srvs","37.50",1,1]
["Network Operations & Safety","10007210","3D CAD/BIM Lines Central/North","12012","Engineering Solution","10002532","Dean Wright","30002622","Line Designer","10010021","Travis Saunders","30022286","Team Leader 3D CAD BIM Lines","3010","Lilydale","Permanent Full Time","ASU/APESMA","1200","AusNet Electricity Srvs","37.50",1,1]
["Network Operations & Safety","10007210","3D CAD/BIM Lines Central/North","12012","Engineering Solution","10002562","Daniel Calgaro","30002649","Line Designer","10010021","Travis Saunders","30022286","Team Leader 3D CAD BIM Lines","3010","Lilydale","Permanent Full Time","ASU/APESMA","1200","AusNet Electricity Srvs","37.50",1,1]
["Network Operations & Safety","10007210","3D CAD/BIM Lines Central/North","12012","Engineering Solution","10008903","Tobias Binkert","30002229","Drafter","10010021","Travis Saunders","30022286","Team Leader 3D CAD BIM Lines","3010","Lilydale","Permanent Full Time","ASU/APESMA","1200","AusNet Electricity Srvs","37.50",1,1]
["Network Operations & Safety","10007366","Energy Projects - North 2","13121","Cust Prog central","10001395","Paul Hoffman","30021198","Lead Energy Project Coordinator","10001247","Paul Tanner","30020888","Customer Program Manager - North","3026","Wodonga","Permanent Full Time","IEA","1200","AusNet Electricity Srvs","37.50",1,1]
["Network Operations & Safety","10007367","Energy Projects - East 2","13723","Cust Prog Cent East","10001318","Tom Minogue","30021196","Lead Energy Project Coordinator","10000368","Gareth Downes","30020736","Customer Program Manager - East","3001","Beaconsfield","Permanent Full Time","IEA","1200","AusNet Electricity Srvs","37.50",1,1]
["Network Operations & Safety","10007367","Energy Projects - East 2","13723","Cust Prog Cent East","10001596","Will Joshua","30013633","Electricity Network Representative","10001318","Tom Minogue","30021196","Lead Energy Project Coordinator","3001","Beaconsfield","Permanent Full Time","ASU/APESMA","1200","AusNet Electricity Srvs","37.50",1,1]
["Network Operations & Safety","10007433","Major Projects Distribution","13260","Major Projects Trans","10000641","Ross Gibb","30000667","Project Manager","10000189","Ross Stewart","30022262","Group Leader Major Projects Distribution","3011","Malvern","Permanent Part Time","IEA","1200","AusNet Electricity Srvs","30.00",1,0.8]
["Network Operations & Safety","10007433","Major Projects Distribution","13378","Major Projects Distr","10000189","Ross Stewart","30022262","Group Leader Major Projects Distribution","10009799","Andrew Linnie","30000116","Manager Major Projects Delivery","3011","Malvern","Permanent Full Time","IEA","2100","AusNet Transmission Grp","37.50",1,1]
["Network Management & Digital","10007800","Primary Asset Performance Stk Engagement","12017","NIU_Primary Asset Pe","10001047","David Platt","30000991","Principal Engineer Switchgear","10008984","Shadman Khan","30023284","Primary Asset Perf Stk Engagement,TL","3007","Freshwater Pl","Permanent Full Time","IEA","2100","AusNet Transmission Grp","37.50",1,1]
["Network Management & Digital","10007801","Secondary Asset Performance Optimisation","15012","NIU_Secondary Asset","10007768","Michael Wiener","30017744","REFCL Engineer","10009780","Danielle Roche","30021262","GM Asset Management","3007","Freshwater Pl","Permanent Full Time","IEA","1200","AusNet Electricity Srvs","37.50",1,1]
["","","","","","","","","","","","","","","","","","","","",29,28.8]