## Cover
CitiPower
Regulatory proposal 2026-31
#NAME?
Model number: | #NAME?
2025-01-31

## Summary
CitiPower
Head office
All dollar values are in $m June 2026 unless otherwise stated
Cost summary: Total Citipower, Powercor & United Energy
| Preferred option: | Option 2
| PV of Costs | -37.9413
| Capex | -28.9794
| Loss of efficiency during redevelopment | -8.9618
| PV of benefits | 186.7578
| Not fit for purpose | 82.1595
| Aged facilities | 55.9676
| Reduced employee wellbeing and satisfaction | 48.6307
| NPV | 148.8165
| Option 2 capex | 2026/27 | 2027/28 | 2028/29 | 2029/30 | 2030/31
| Labour | 0 | 0 | 0 | 0 | 0
| Material | 0 | 0 | 5.5223 | 14.8162 | 0
| Contracts | 0 | 0 | 4.3178 | 8.2539 | 0
| Total Property Costs ($ 2025/26) | 0 | 0 | 9.8401 | 23.07 | 0
Cost summary: CitiPower
| Preferred option: | Option 2
| PV of Costs | -7.9677
| Capex | -6.0857
| Loss of efficiency during redevelopment | -1.882
| PV of benefits | 39.2191
| Not fit for purpose | 17.2535
| Aged facilities | 11.7532
| Reduced employee wellbeing and satisfaction | 10.2124
| NPV | 31.2515
| Option 2 capex | 2026/27 | 2027/28 | 2028/29 | 2029/30 | 2030/31
| Labour | 0 | 0 | 0 | 0 | 0
| Material | 0 | 0 | 1.1597 | 3.1114 | 0
| Contracts | 0 | 0 | 0.90674 | 1.7333 | 0
| Total Property Costs ($ 2025/26) | 0 | 0 | 2.0664 | 4.8447 | 0

## Options Analysis
CitiPower | [28 empty] | Input
Head office | [28 empty] | Formula do not edit
All dollar values are in $m June 2026 unless otherwise stated
Options summary
| Option |  | Preferred Option | PV Costs | PV Benefits | NPV
| Option 1 |  |  | 0 | 0 | 0
| Option 2 |  | * | -37.9413 | 186.7578 | 148.8165
| Option 3 |  |  | -77.1211 | 186.7578 | 109.6367
Options Analysis
| Option 1 | Do nothing |  | 2026/27 | 2027/28 | 2028/29 | 2029/30 | 2030/31 | 2031/32 | 2032/33 | 2033/34 | 2034/35 | 2035/36 | 2036/37 | 2037/38 | 2038/39 | 2039/40 | 2040/41 | 2041/42 | 2042/43 | 2043/44 | 2044/45 | 2045/46 | 2046/47 | 2047/48 | 2048/49 | 2049/50 | 2050/51
| Costs |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Benefits/Risks avoided |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Total cost of Do nothing |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| PV costs | 0
| PV benefits | 0
| NPV | 0
| Option 2 | Upgrade existing site |  | 2026/27 | 2027/28 | 2028/29 | 2029/30 | 2030/31 | 2031/32 | 2032/33 | 2033/34 | 2034/35 | 2035/36 | 2036/37 | 2037/38 | 2038/39 | 2039/40 | 2040/41 | 2041/42 | 2042/43 | 2043/44 | 2044/45 | 2045/46 | 2046/47 | 2047/48 | 2048/49 | 2049/50 | 2050/51
| Capex |  |  | 0 | 0 | -9.8401 | -23.07 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Additional costs
| - | Loss of efficiency during redevelopment |  | 0 | 0 | -5.0535 | -5.0535 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Total costs |  |  | 0 | 0 | -14.8937 | -28.1235 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Benefits/Risks avoided
| - | Not fit for purpose |  | 0 | 0 | 0 | 0 | 5.6086 | 5.6927 | 5.7781 | 5.8648 | 5.9528 | 6.0421 | 6.1327 | 6.2247 | 6.3181 | 6.4128 | 6.509 | 6.6067 | 6.7058 | 6.8064 | 6.9084 | 7.0121 | 7.1173 | 7.224 | 7.3324 | 7.4424 | 7.554
| - | Aged facilities |  | 0 | 0 | 0 | 0 | 3.8117 | 3.8697 | 3.9286 | 3.9884 | 4.0492 | 4.1109 | 4.1736 | 4.2373 | 4.3019 | 4.3676 | 4.4343 | 4.502 | 4.5709 | 4.6408 | 4.7118 | 4.7839 | 4.8572 | 4.9317 | 5.0073 | 5.0841 | 5.1622
| - | Reduced employee wellbeing and satisfaction |  | 0 | 0 | 0 | 0 | 3.5504 | 3.5772 | 3.6042 | 3.6314 | 3.6589 | 3.6865 | 3.7145 | 3.7426 | 3.771 | 3.7997 | 3.8285 | 3.8576 | 3.887 | 3.9166 | 3.9465 | 3.9766 | 4.007 | 4.0376 | 4.0685 | 4.0996 | 4.131
| Total benefits |  |  | 0 | 0 | 0 | 0 | 12.9707 | 13.1396 | 13.3109 | 13.4846 | 13.6608 | 13.8395 | 14.0208 | 14.2046 | 14.391 | 14.5801 | 14.7718 | 14.9664 | 15.1636 | 15.3637 | 15.5667 | 15.7726 | 15.9814 | 16.1932 | 16.4081 | 16.6261 | 16.8472
| Total cost of Upgrade existing site |  |  | 0 | 0 | -14.8937 | -28.1235 | 12.9707 | 13.1396 | 13.3109 | 13.4846 | 13.6608 | 13.8395 | 14.0208 | 14.2046 | 14.391 | 14.5801 | 14.7718 | 14.9664 | 15.1636 | 15.3637 | 15.5667 | 15.7726 | 15.9814 | 16.1932 | 16.4081 | 16.6261 | 16.8472
| PV costs | -37.9413
| PV benefits | 186.7578
| NPV | 148.8165
| Option 3 | New lease for head office |  | 2026/27 | 2027/28 | 2028/29 | 2029/30 | 2030/31 | 2031/32 | 2032/33 | 2033/34 | 2034/35 | 2035/36 | 2036/37 | 2037/38 | 2038/39 | 2039/40 | 2040/41 | 2041/42 | 2042/43 | 2043/44 | 2044/45 | 2045/46 | 2046/47 | 2047/48 | 2048/49 | 2049/50 | 2050/51
| Capex |  |  | 0 | 0 | -11.5985 | -26.9761 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Additional costs
| - | Suboptimal site location |  | 0 | 0 | 0 | 0 | -3.369 | -3.369 | -3.369 | -3.369 | -3.369 | -3.369 | -3.369 | -3.369 | -3.369 | -3.369 | -3.369 | -3.369 | -3.369 | -3.369 | -3.369 | -3.369 | -3.369 | -3.369 | -3.369 | -3.369 | -3.369
| Total costs |  |  | 0 | 0 | -11.5985 | -26.9761 | -3.369 | -3.369 | -3.369 | -3.369 | -3.369 | -3.369 | -3.369 | -3.369 | -3.369 | -3.369 | -3.369 | -3.369 | -3.369 | -3.369 | -3.369 | -3.369 | -3.369 | -3.369 | -3.369 | -3.369 | -3.369
Risks avoided
| - | Not fit for purpose |  | 0 | 0 | 0 | 0 | 5.6086 | 5.6927 | 5.7781 | 5.8648 | 5.9528 | 6.0421 | 6.1327 | 6.2247 | 6.3181 | 6.4128 | 6.509 | 6.6067 | 6.7058 | 6.8064 | 6.9084 | 7.0121 | 7.1173 | 7.224 | 7.3324 | 7.4424 | 7.554
| - | Aged facilities |  | 0 | 0 | 0 | 0 | 3.8117 | 3.8697 | 3.9286 | 3.9884 | 4.0492 | 4.1109 | 4.1736 | 4.2373 | 4.3019 | 4.3676 | 4.4343 | 4.502 | 4.5709 | 4.6408 | 4.7118 | 4.7839 | 4.8572 | 4.9317 | 5.0073 | 5.0841 | 5.1622
| - | Reduced employee wellbeing and satisfaction |  | 0 | 0 | 0 | 0 | 3.5504 | 3.5772 | 3.6042 | 3.6314 | 3.6589 | 3.6865 | 3.7145 | 3.7426 | 3.771 | 3.7997 | 3.8285 | 3.8576 | 3.887 | 3.9166 | 3.9465 | 3.9766 | 4.007 | 4.0376 | 4.0685 | 4.0996 | 4.131
| Total benefits |  |  | 0 | 0 | 0 | 0 | 12.9707 | 13.1396 | 13.3109 | 13.4846 | 13.6608 | 13.8395 | 14.0208 | 14.2046 | 14.391 | 14.5801 | 14.7718 | 14.9664 | 15.1636 | 15.3637 | 15.5667 | 15.7726 | 15.9814 | 16.1932 | 16.4081 | 16.6261 | 16.8472
| Total cost of New lease for head office |  |  | 0 | 0 | -11.5985 | -26.9761 | 9.6017 | 9.7706 | 9.9419 | 10.1156 | 10.2918 | 10.4705 | 10.6518 | 10.8356 | 11.022 | 11.2111 | 11.4028 | 11.5973 | 11.7946 | 11.9947 | 12.1977 | 12.4036 | 12.6124 | 12.8242 | 13.0391 | 13.2571 | 13.4782
| PV costs | -77.1211
| PV benefits | 186.7578
| NPV | 109.6367

## Costs
CitiPower | [10 empty] | Input
Head office | [10 empty] | Formula do not edit
All dollar values are in $ June 2024 unless otherwise stated
Cost summary
| Option |  |  | NPV | Total | 2026/27 | 2027/28 | 2028/29 | 2029/30 | 2030/31
| Option 1 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Option 2 |  |  | 26039271.1882 | 29571200 | 0 | 0 | 8841788.8 | 20729411.2 | 0
| Option 3 |  |  | 30522893.7363 | 34660960 | 0 | 0 | 10421788.8 | 24239171.2 | 0
Cost inputs
| Option 1 |  | Labour | Materials | Contracts | 2026/27 | 2027/28 | 2028/29 | 2029/30 | 2030/31 | Total
| New Depot Design | Option 2 New Depot Design | 0% | 0% | 100% | 0 |  | 0 | 0 | 0 | 0
| Staff Relocation / Alternative Accom | Option 2 Staff Relocation / Alternative Accom | 0% | 10% | 90% | 0 | 0 | 0 | 0 | 0 | 0
| Land acquisition | Option 2 Land acquisition |  | 100% |  | 0 | 0 | 0 | 0 | 0 | 0
| Civil Works/Demolition works | Option 2 Civil Works/Demolition works | 0% | 50% | 50% | 0 | 0 | 0 | 0 | 0 | 0
| Building works | Option 2 Building works | 0% | 70% | 30% | 0 | 0 | 0 | 0 | 0 | 0
| Services | Option 2 Services | 0% | 20% | 80% | 0 | 0 | 0 | 0 | 0 | 0
| Fixtures, Furniture & equipment | Option 2 Fixtures, Furniture & equipment | 0% | 100% | 0% | 0 | 0 | 0 | 0 | 0 | 0
| Other | Option 2 Other | 0% | 100% | 0% | 0 | 0 | 0 | 0 | 0 | 0
| Project Management | Option 2 Project Management | 50% | 0% | 50% | 0 | 0 | 0 | 0 | 0 | 0
| Total Property Cost |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
| Labour |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
| Material |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
| Contracts |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
| Option 2 |  | Labour | Materials | Contracts | 2026/27 | 2027/28 | 2028/29 | 2029/30 | 2030/31 | Total
| New Depot Design | Option 2 New Depot Design | 0% | 0% | 100% |  |  | 1330704 |  |  | 1330704
| Staff Relocation / Alternative Accom | Option 2 Staff Relocation / Alternative Accom | 0% | 10% | 90% |  |  |  | 887136 |  | 887136
| Land acquisition | Option 2 Land acquisition |  | 100% |  | 0 | 0 |  | 0 | 0 | 0
| Civil Works/Demolition works | Option 2 Civil Works/Demolition works | 0% | 50% | 50% |  |  | 1478560 |  |  | 1478560
| Building works | Option 2 Building works | 0% | 70% | 30% |  |  | 6032524.8 | 9048787.2 |  | 15081312
| Services | Option 2 Services | 0% | 20% | 80% |  |  |  | 4879248 |  | 4879248
| Fixtures, Furniture & equipment | Option 2 Fixtures, Furniture & equipment | 0% | 100% | 0% |  |  |  | 5914240 |  | 5914240
| Other | Option 2 Other | 0% | 100% | 0% | [5 empty] | 0
| Project Management | Option 2 Project Management | 50% | 0% | 50% | [5 empty] | 0
| Total Property Cost |  |  |  |  | 0 | 0 | 8841788.8 | 20729411.2 | 0 | 29571200
| Labour |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
| Material |  |  |  |  | 0 | 0 | 4962047.36 | 13312954.24 | 0 | 18275001.6
| Contracts |  |  |  |  | 0 | 0 | 3879741.44 | 7416456.96 | 0 | 11296198.4
| Option 3 |  | Labour | Materials | Contracts | 2026/27 | 2027/28 | 2028/29 | 2029/30 | 2030/31 | Total
| New Depot Design | Option 3 New Depot Design | 0% | 0% | 100% |  |  | 1330704 |  |  | 1330704
| Staff Relocation / Alternative Accom | Option 3 Staff Relocation / Alternative Accom | 0% | 10% | 90% |  |  |  | 1477136 |  | 1477136
| Land acquisition | Option 3 Land acquisition |  | 100% | [6 empty] | 0
| Civil Works/Demolition works | Option 3 Civil Works/Demolition works | 0% | 50% | 50% |  |  | 1478560 |  |  | 1478560
| Building works | Option 3 Building works | 0% | 70% | 30% |  |  | 7612524.8 | 11418787.2 |  | 19031312
| Services | Option 3 Services | 0% | 20% | 80% |  |  |  | 4879248 |  | 4879248
| Fixtures, Furniture & equipment | Option 3 Fixtures, Furniture & equipment | 0% | 100% | 0% |  |  |  | 6464000 |  | 6464000
| Other | Option 3 Other | 0% | 100% | 0% | [5 empty] | 0
| Project Management | Option 3 Project Management | 50% | 0% | 50% | [5 empty] | 0
| Total Property Cost |  |  |  |  | 0 | 0 | 10421788.8 | 24239171.2 | 0 | 34660960
| Labour |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
| Material |  |  |  |  | 0 | 0 | 6068047.36 | 15580714.24 | 0 | 21648761.6
| Contracts |  |  |  |  | 0 | 0 | 4353741.44 | 8658456.96 | 0 | 13012198.4

## Risks
CitiPower | [31 empty] | Input
Head office | [31 empty] | Formula do not edit
All dollar values are in $ June 2024 unless otherwise stated
Risk summary
| Risk category |  |  | NPV | Total |  | 2026/27 | 2027/28 | 2028/29 | 2029/30 | 2030/31 | 2031/32 | 2032/33 | 2033/34 | 2034/35 | 2035/36 | 2036/37 | 2037/38 | 2038/39 | 2039/40 | 2040/41 | 2041/42 | 2042/43 | 2043/44 | 2044/45 | 2045/46 | 2046/47 | 2047/48 | 2048/49 | 2049/50 | 2050/51
| Not fit for purpose |  |  | 73823810.0514 | 123321246.3255 |  | 0 | 0 | 0 | 0 | 5039583.7805 | 5115177.5372 | 5191905.2003 | 5269783.7783 | 5348830.5349 | 5429062.993 | 5510498.9379 | 5593156.4219 | 5677053.7683 | 5762209.5748 | 5848642.7184 | 5936372.3592 | 6025417.9446 | 6115799.2137 | 6207536.2019 | 6300649.245 | 6395158.9837 | 6491086.3684 | 6588452.6639 | 6687279.4539 | 6787588.6457
| Aged facilities |  |  | 50289300.5613 | 84036296.1088 |  | 0 | 0 | 0 | 0 | 3424971.0414 | 3477093.9797 | 3530028.5041 | 3583788.122 | 3638386.6069 | 3693838.0058 | 3750156.6461 | 3807357.144 | 3865454.4116 | 3924463.6657 | 3984400.4362 | 4045280.5747 | 4107120.2641 | 4169936.0279 | 4233744.7404 | 4298563.6367 | 4364410.3235 | 4431302.7905 | 4499259.4217 | 4568299.0077 | 4638440.7582
| Reduced employee wellbeing and satisfaction |  |  | 43696793.5469 | 72326171.3061 |  | 0 | 0 | 0 | 0 | 3190161.3642 | 3214226.0913 | 3238492.2813 | 3262961.7529 | 3287636.3419 | 3312517.9016 | 3337608.303 | 3362909.4344 | 3388423.2025 | 3414151.5315 | 3440096.3644 | 3466259.6621 | 3492643.4045 | 3519249.5901 | 3546080.2363 | 3573137.3797 | 3600423.0762 | 3627939.4013 | 3655688.4501 | 3683672.3377 | 3711893.1992
| Loss of efficiency during redevelopment |  |  | 8052586.3054 | 9081600 |  | 0 | 0 | 4540800 | 4540800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Suboptimal site location |  |  | 38773695.5935 | 63571200 |  | 0 | 0 | 0 | 0 | 3027200 | 3027200 | 3027200 | 3027200 | 3027200 | 3027200 | 3027200 | 3027200 | 3027200 | 3027200 | 3027200 | 3027200 | 3027200 | 3027200 | 3027200 | 3027200 | 3027200 | 3027200 | 3027200 | 3027200 | 3027200
Risk calculations
Not fit for purpose
Reduced productivity due to insufficient meeting rooms, collaboration spaces, hot desking capability
| Total office personnel (FTE) | # | 946
| Average cost per FTE p.a. | $ June 2024 | 160000
| Productivity loss as at 2024 | % | 3%
| Deterioration in productivity p.a. | % | 1.5%
[6 empty] | 2025/26 | 2026/27 | 2027/28 | 2028/29 | 2029/30 | 2030/31 | 2031/32 | 2032/33 | 2033/34 | 2034/35 | 2035/36 | 2036/37 | 2037/38 | 2038/39 | 2039/40 | 2040/41 | 2041/42 | 2042/43 | 2043/44 | 2044/45 | 2045/46 | 2046/47 | 2047/48 | 2048/49 | 2049/50 | 2050/51
| Reduced productivity due to insufficient meeting rooms, collaboration spaces, hot desking capability |  |  |  |  | 4678045.68 | 4748216.3652 | 4819439.6107 | 4891731.2048 | 4965107.1729 | 5039583.7805 | 5115177.5372 | 5191905.2003 | 5269783.7783 | 5348830.5349 | 5429062.993 | 5510498.9379 | 5593156.4219 | 5677053.7683 | 5762209.5748 | 5848642.7184 | 5936372.3592 | 6025417.9446 | 6115799.2137 | 6207536.2019 | 6300649.245 | 6395158.9837 | 6491086.3684 | 6588452.6639 | 6687279.4539 | 6787588.6457
[7 empty] | 2026/27 | 2027/28 | 2028/29 | 2029/30 | 2030/31 | 2031/32 | 2032/33 | 2033/34 | 2034/35 | 2035/36 | 2036/37 | 2037/38 | 2038/39 | 2039/40 | 2040/41 | 2041/42 | 2042/43 | 2043/44 | 2044/45 | 2045/46 | 2046/47 | 2047/48 | 2048/49 | 2049/50 | 2050/51
| Total risk due to Not fit for purpose | [5 empty] | 4748216.3652 | 4819439.6107 | 4891731.2048 | 4965107.1729 | 5039583.7805 | 5115177.5372 | 5191905.2003 | 5269783.7783 | 5348830.5349 | 5429062.993 | 5510498.9379 | 5593156.4219 | 5677053.7683 | 5762209.5748 | 5848642.7184 | 5936372.3592 | 6025417.9446 | 6115799.2137 | 6207536.2019 | 6300649.245 | 6395158.9837 | 6491086.3684 | 6588452.6639 | 6687279.4539 | 6787588.6457
Aged facilities
Reduced office productivity due to aged facilities (slow lifts, out of order etc.)
| Total office personnel (FTE) | # | 946
| Average cost per FTE p.a. | $ June 2024 | 160000
| Productivity loss as at 2024 | % | 2%
| Deterioration in productivity p.a. | % | 1.5%
[6 empty] | 2025/26 | 2026/27 | 2027/28 | 2028/29 | 2029/30 | 2030/31 | 2031/32 | 2032/33 | 2033/34 | 2034/35 | 2035/36 | 2036/37 | 2037/38 | 2038/39 | 2039/40 | 2040/41 | 2041/42 | 2042/43 | 2043/44 | 2044/45 | 2045/46 | 2046/47 | 2047/48 | 2048/49 | 2049/50 | 2050/51
| Reduced office productivity due to aged facilities (slow lifts, out of order etc.) |  |  |  |  | 3118697.12 | 3165477.5768 | 3212959.7405 | 3261154.1366 | 3310071.4486 | 3359722.5203 | 3410118.3581 | 3461270.1335 | 3513189.1855 | 3565887.0233 | 3619375.3286 | 3673665.9586 | 3728770.948 | 3784702.5122 | 3841473.0499 | 3899095.1456 | 3957581.5728 | 4016945.2964 | 4077199.4758 | 4138357.468 | 4200432.83 | 4263439.3224 | 4327390.9123 | 4392301.776 | 4458186.3026 | 4525059.0971
Increased maintenance costs
| Annual office maintenance costs in 2024 | $ June 2024 | 400000
| Maintenance costs attributable to aged facilities | % | 50%
| Annual increase in maintenance costs | % | 5%
[6 empty] | 2025/26 | 2026/27 | 2027/28 | 2028/29 | 2029/30 | 2030/31 | 2031/32 | 2032/33 | 2033/34 | 2034/35 | 2035/36 | 2036/37 | 2037/38 | 2038/39 | 2039/40 | 2040/41 | 2041/42 | 2042/43 | 2043/44 | 2044/45 | 2045/46 | 2046/47 | 2047/48 | 2048/49 | 2049/50 | 2050/51
| Increased maintenance costs |  |  |  |  | 11025 | 11576.25 | 12155.0625 | 12762.8156 | 13400.9564 | 14071.0042 | 14774.5544 | 15513.2822 | 16288.9463 | 17103.3936 | 17958.5633 | 18856.4914 | 19799.316 | 20789.2818 | 21828.7459 | 22920.1832 | 24066.1923 | 25269.502 | 26532.9771 | 27859.6259 | 29252.6072 | 30715.2376 | 32250.9994 | 33863.5494 | 35556.7269 | 37334.5632
Death or serious injury caused by structural failure
| Value of statistical life ($ 000) | #VALUE! | 5940414.4211
| Disproportionality factor |  | 3
| Annual major failure probability | % | 0.25%
| Increase in risk with age per annum | % | 2%
[6 empty] | 2025/26 | 2026/27 | 2027/28 | 2028/29 | 2029/30 | 2030/31 | 2031/32 | 2032/33 | 2033/34 | 2034/35 | 2035/36 | 2036/37 | 2037/38 | 2038/39 | 2039/40 | 2040/41 | 2041/42 | 2042/43 | 2043/44 | 2044/45 | 2045/46 | 2046/47 | 2047/48 | 2048/49 | 2049/50 | 2050/51
| Death or serious injury caused by structural failure |  |  |  |  | 46353.0537 | 47280.1148 | 48225.7171 | 49190.2314 | 50174.0361 | 51177.5168 | 52201.0671 | 53245.0885 | 54309.9902 | 55396.19 | 56504.1138 | 57634.1961 | 58786.88 | 59962.6176 | 61161.87 | 62385.1074 | 63632.8095 | 64905.4657 | 66203.5751 | 67527.6466 | 68878.1995 | 70255.7635 | 71660.8787 | 73094.0963 | 74555.9782 | 76047.0978
[7 empty] | 2026/27 | 2027/28 | 2028/29 | 2029/30 | 2030/31 | 2031/32 | 2032/33 | 2033/34 | 2034/35 | 2035/36 | 2036/37 | 2037/38 | 2038/39 | 2039/40 | 2040/41 | 2041/42 | 2042/43 | 2043/44 | 2044/45 | 2045/46 | 2046/47 | 2047/48 | 2048/49 | 2049/50 | 2050/51
| Total risk due to Aged facilities | [5 empty] | 3224333.9416 | 3273340.5201 | 3323107.1836 | 3373646.4411 | 3424971.0414 | 3477093.9797 | 3530028.5041 | 3583788.122 | 3638386.6069 | 3693838.0058 | 3750156.6461 | 3807357.144 | 3865454.4116 | 3924463.6657 | 3984400.4362 | 4045280.5747 | 4107120.2641 | 4169936.0279 | 4233744.7404 | 4298563.6367 | 4364410.3235 | 4431302.7905 | 4499259.4217 | 4568299.0077 | 4638440.7582
Reduced employee wellbeing and satisfaction
Reduced productivity due to reduced employee wellbeing and satisfaction
| Total office personnel (FTE) | # | 946
| Average cost per FTE p.a. | $ June 2024 | 160000
| Productivity loss as at 2024 | % | 1%
| Deterioration in productivity p.a. | % | 1%
[6 empty] | 2025/26 | 2026/27 | 2027/28 | 2028/29 | 2029/30 | 2030/31 | 2031/32 | 2032/33 | 2033/34 | 2034/35 | 2035/36 | 2036/37 | 2037/38 | 2038/39 | 2039/40 | 2040/41 | 2041/42 | 2042/43 | 2043/44 | 2044/45 | 2045/46 | 2046/47 | 2047/48 | 2048/49 | 2049/50 | 2050/51
| Reduced productivity due to reduced employee wellbeing and satisfaction |  |  |  |  | 1544023.36 | 1559463.5936 | 1575058.2295 | 1590808.8118 | 1606716.8999 | 1622784.0689 | 1639011.9096 | 1655402.0287 | 1671956.049 | 1688675.6095 | 1705562.3656 | 1722617.9893 | 1739844.1692 | 1757242.6108 | 1774815.037 | 1792563.1873 | 1810488.8192 | 1828593.7074 | 1846879.6445 | 1865348.4409 | 1884001.9253 | 1902841.9446 | 1921870.364 | 1941089.0677 | 1960499.9583 | 1980104.9579
Reduced productivity due to reduced staff retention/increased turnover
| Total office personnel (FTE) | # | 946
| Average cost per FTE p.a. | $ June 2024 | 160000
| Productivity loss as at 2024 | % | 1%
| Deterioration in productivity p.a. | % | 0.5%
[6 empty] | 2025/26 | 2026/27 | 2027/28 | 2028/29 | 2029/30 | 2030/31 | 2031/32 | 2032/33 | 2033/34 | 2034/35 | 2035/36 | 2036/37 | 2037/38 | 2038/39 | 2039/40 | 2040/41 | 2041/42 | 2042/43 | 2043/44 | 2044/45 | 2045/46 | 2046/47 | 2047/48 | 2048/49 | 2049/50 | 2050/51
| Reduced productivity due to reduced staff retention/increased turnover |  |  |  |  | 1528773.84 | 1536417.7092 | 1544099.7977 | 1551820.2967 | 1559579.3982 | 1567377.2952 | 1575214.1817 | 1583090.2526 | 1591005.7039 | 1598960.7324 | 1606955.536 | 1614990.3137 | 1623065.2653 | 1631180.5916 | 1639336.4946 | 1647533.177 | 1655770.8429 | 1664049.6971 | 1672369.9456 | 1680731.7954 | 1689135.4543 | 1697581.1316 | 1706069.0373 | 1714599.3825 | 1723172.3794 | 1731788.2413
[7 empty] | 2026/27 | 2027/28 | 2028/29 | 2029/30 | 2030/31 | 2031/32 | 2032/33 | 2033/34 | 2034/35 | 2035/36 | 2036/37 | 2037/38 | 2038/39 | 2039/40 | 2040/41 | 2041/42 | 2042/43 | 2043/44 | 2044/45 | 2045/46 | 2046/47 | 2047/48 | 2048/49 | 2049/50 | 2050/51
| Total risk due to Reduced employee wellbeing and satisfaction | [5 empty] | 3095881.3028 | 3119158.0273 | 3142629.1086 | 3166296.2982 | 3190161.3642 | 3214226.0913 | 3238492.2813 | 3262961.7529 | 3287636.3419 | 3312517.9016 | 3337608.303 | 3362909.4344 | 3388423.2025 | 3414151.5315 | 3440096.3644 | 3466259.6621 | 3492643.4045 | 3519249.5901 | 3546080.2363 | 3573137.3797 | 3600423.0762 | 3627939.4013 | 3655688.4501 | 3683672.3377 | 3711893.1992
Loss of efficiency during redevelopment
Reduced office productivity during disruption
| Total office personnel (FTE) | # | 946
| Average cost per FTE p.a. | $ June 2024 | 160000
| Productivity reduction | % | 3%
[6 empty] | 2025/26 | 2026/27 | 2027/28 | 2028/29 | 2029/30 | 2030/31 | 2031/32 | 2032/33 | 2033/34 | 2034/35 | 2035/36 | 2036/37 | 2037/38 | 2038/39 | 2039/40 | 2040/41 | 2041/42 | 2042/43 | 2043/44 | 2044/45 | 2045/46 | 2046/47 | 2047/48 | 2048/49 | 2049/50 | 2050/51
| Reduced office productivity during disruption | [5 empty] | 0 | 0 | 4540800 | 4540800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | 2026/27 | 2027/28 | 2028/29 | 2029/30 | 2030/31 | 2031/32 | 2032/33 | 2033/34 | 2034/35 | 2035/36 | 2036/37 | 2037/38 | 2038/39 | 2039/40 | 2040/41 | 2041/42 | 2042/43 | 2043/44 | 2044/45 | 2045/46 | 2046/47 | 2047/48 | 2048/49 | 2049/50 | 2050/51
| Total risk due to Loss of efficiency during redevelopment | [5 empty] | 0 | 0 | 4540800 | 4540800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Suboptimal site location
Reduced office productivity during disruption
| Total office personnel (FTE) | # | 946
| Average cost per FTE p.a. | $ June 2024 | 160000
| Productivity reduction | % | 2%
[6 empty] | 2025/26 | 2026/27 | 2027/28 | 2028/29 | 2029/30 | 2030/31 | 2031/32 | 2032/33 | 2033/34 | 2034/35 | 2035/36 | 2036/37 | 2037/38 | 2038/39 | 2039/40 | 2040/41 | 2041/42 | 2042/43 | 2043/44 | 2044/45 | 2045/46 | 2046/47 | 2047/48 | 2048/49 | 2049/50 | 2050/51
| Reduced office productivity during disruption | [5 empty] | 0 | 0 | 0 | 0 | 3027200 | 3027200 | 3027200 | 3027200 | 3027200 | 3027200 | 3027200 | 3027200 | 3027200 | 3027200 | 3027200 | 3027200 | 3027200 | 3027200 | 3027200 | 3027200 | 3027200 | 3027200 | 3027200 | 3027200 | 3027200
[7 empty] | 2026/27 | 2027/28 | 2028/29 | 2029/30 | 2030/31 | 2031/32 | 2032/33 | 2033/34 | 2034/35 | 2035/36 | 2036/37 | 2037/38 | 2038/39 | 2039/40 | 2040/41 | 2041/42 | 2042/43 | 2043/44 | 2044/45 | 2045/46 | 2046/47 | 2047/48 | 2048/49 | 2049/50 | 2050/51
| Total risk due to Suboptimal site location | [5 empty] | 0 | 0 | 0 | 0 | 3027200 | 3027200 | 3027200 | 3027200 | 3027200 | 3027200 | 3027200 | 3027200 | 3027200 | 3027200 | 3027200 | 3027200 | 3027200 | 3027200 | 3027200 | 3027200 | 3027200 | 3027200 | 3027200 | 3027200 | 3027200

## Risk Assumptions
CitiPower | [6 empty] | Input
Head office | [6 empty] | Formula do not edit
All dollar values are in $ June 2024 unless otherwise stated
| Input name | Unit | Value | Conversion required | Unit used for risk calculations | Value used for risk calculations
Productivity loss
| Deterioration in productivity p.a. | % | 1.5% | FALSE | % | 1.5%
| Productivity lost as at 2024 in field due to office not fit for purpose | % | 3% | FALSE | % | 3%
| Productivity lost as at 2024 in office due to outdated facilities | % | 2% | FALSE | % | 2%
| Productivity lost as at 2024 due to reduced employee wellbeing and satisfaction | % | 1% | FALSE | % | 1%
| Deterioration in productivity p.a. due to reduced employee wellbeing and satisfaction | % | 1% | FALSE | % | 1%
| Productivity lost as at 2024 due to reduced staff retention/increased turnover | % | 1% | FALSE | % | 1%
| Deterioration in productivity p.a. due to reduced staff retention/increased turnover | % | 0.5% | FALSE | % | 0.5%
| Productivity loss during depot redevelopment | % | 3% | FALSE | % | 3%
| Productivity loss due to suboptimal site location | % | 2% | FALSE | % | 2%
Maintenance
| Annual maintenance costs | $ 2024 | 400000 | FALSE | $ June 2024 | 400000
| Portion of maintenance costs attributable to aged facilities | % | 50% | FALSE | % | 50%
| Annual increase in maintenance costs of aged facilities | % | 5% | FALSE | % | 5%
Staff
| Office staff (FTE) | # | 946 | FALSE | # | 946
| Average cost per FTE | $ 2024 | 160000 | FALSE | $ June 2024 | 160000
Safety
| Value of statistical life | $ 2022 | 5300000 | TRUE | $ June 2024 | 5940414.4211
| Disproportionality factor |  | 3 | FALSE |  | 3
| Probability of major structural failure p.a. | % | 0.25% | FALSE | % | 0.25%
| Increase in likelihood of major structural failure p.a. | % | 2% | FALSE | % | 2%

## Reg Assumptions
CitiPower | [6 empty] | Key: | Input
Regulatory assumptions | [7 empty] | Regulation only input
Assumption Types | Assumptions | Parameters | Area Applied |  |  |  |  | Formula do not edit
Business: | CitiPower
Model name | Head office
Cost inputs from SME: | 2024-06-30
Output for business case: | 2026-06-30
Options | Option 1 | Do nothing
| Option 2 | Upgrade existing site
| Option 3 | New lease for head office
Real Discount rate: | 3.5%
Escalation: for Regulation use |  |  |  | 2019/20 | 2020/21 | 2021/22 | 2022/23 | 2023/24 | 2024/25 | 2025/26
CPI Lagged conversion to June 24 |  |  |  | 1.1394 | 1.1256 | 1.1208 | 1.097 | 1.0384 | 0.98034 | 0.94696
CPI Lagged conversion to June 26 |  |  |  | 1.2211 | 1.2064 | 1.2012 | 1.1757 | 1.1129 | 1.0507 | 1.0149
Multiply by (2024 to 2026): |  | 1.1129
Cost allocation
Cost & benefit allocation | Citipower | 21%
| Powercor | 49%
| United Energy | 30%
Cost allocation for this business | CitiPower | 21%