## Summary_old (hidden)
Summary
Direct Non-Labour Expenditure
Expenditure Item |  |  | Dollar basis |  | Value | Asset Class | As Incurred Spend Profile
Category | Source | Units |  |  |  |  | 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | Total
Pre-Construction Development Costs ¦ Substation | Project Team Input | $Millions | #REF! |  | #REF! | #REF! | [7 empty] | 0%
Pre-Construction Development Costs ¦ Transmission Lines | Project Team Input | $Millions | #REF! |  | #REF! | #REF! | [7 empty] | 0%
Long Lead Equipment ¦ Transformers | Project Team Input | $Millions | #REF! |  | #REF! | #REF! | [7 empty] | 0%
Long Lead Equipment ¦ Reactors | Project Team Input | $Millions | #REF! |  | #REF! | #REF! | [7 empty] | 0%
Long Lead Equipment ¦ Conductor and Steel | Project Team Input | $Millions | #REF! |  | #REF! | #REF! | [7 empty] | 0%
Biodiversity Offsets | Project Team Input | $Millions | #REF! |  | #REF! | #REF! | [7 empty] | 0%
Land and Easement Acquisition | Project Team Input | $Millions | #REF! |  | #REF! | #REF! | [7 empty] | 0%
|  |  |  | Total | #REF!
Asset Classes

## variance (hidden)
Direct Non-Labour Expenditure |  |  |  |  | Latest version | Version 10th Feb
Expenditure Item |  |  | Dollar basis |  | Value | Value
Category | Source | Units
Construction Costs ¦ D&C Contract - Transmission Line | Project Team Input | $Millions | $ Nominal |  | [C-i-C] | 99476591.1505 | #VALUE!
Construction Costs ¦ D&C Contract - Substations | Project Team Input | $Millions | $ Nominal |  | [C-i-C] | 37404091.1744 | #VALUE!
Construction Costs ¦ D&C Contract - Secondary System | Project Team Input | $Millions | $ Nominal |  | [C-i-C] | 4433925.4224 | #VALUE!
Construction Costs ¦ Transposition | Project Team Input | $Millions | $ Nominal |  | [C-i-C] | 82000000 | #VALUE!
Equipment Costs ¦ Transformers (CT) | Project Team Input | $Millions | $30 June 2026 |  | 0 | 857572.9125 | -857572.9125
Equipment Costs ¦ Circuit Breakers (CB) | Project Team Input | $Millions | $30 June 2026 |  | 0 | 570782.0476 | -570782.0476
Equipment Costs ¦ Voltage Transformers (VT) | Project Team Input | $Millions | $30 June 2026 |  | 0 | 292792.7234 | -292792.7234
Equipment Costs ¦ Line Trap (LT) | Project Team Input | $Millions | $30 June 2026 |  | 0 | 239042.0561 | -239042.0561
Equipment Costs ¦ Earth Switch | Project Team Input | $Millions | $30 June 2026 |  | 0 | 323288.8933 | -323288.8933
Equipment Costs ¦ Surge Arrestor | Project Team Input | $Millions | $30 June 2026 |  | 0 | 73055.7012 | -73055.7012
Equipment Costs ¦ Disconnector | Project Team Input | $Millions | $30 June 2026 |  | 0 | 758115.0618 | -758115.0618
Equipment Costs ¦ Insulator (16KN) | Project Team Input | $Millions | $30 June 2026 |  | 0 | 13960.4205 | -13960.4205
Equipment Costs ¦ Insulator (6KN) | Project Team Input | $Millions | $30 June 2026 |  | 0 | 12155.7658 | -12155.7658
Equipment Costs ¦ Insulator (6KN) (UH) | Project Team Input | $Millions | $30 June 2026 |  | 0 | 4882.3005 | -4882.3005
Property Costs ¦ Easements | Project Team Input | $Millions | $30 June 2026 |  | [C-i-C] | 4298734.34 | #VALUE!
Insurance ¦ Insurance - Transmission Lines | Project Team Input | $Millions | $ Nominal |  | #NAME? | 994765.9115 | #NAME?
Insurance ¦ Insurance - Substation | Project Team Input | $Millions | $ Nominal |  | #NAME? | 374040.9117 | #NAME?
Insurance ¦ Insurance - Secondary System | Project Team Input | $Millions | $ Nominal |  | #NAME? | 44339.2542 | #NAME?
Environment ¦ Biodiversity Offsets | Project Team Input | $Millions | $30 June 2026 |  | [C-i-C] | 24849041.1668 | #VALUE!
Barigan Creek ¦ Barigan Creek | Project Team Input | $Millions | $ Nominal |  | 0 | 202050000 | -202050000
|  |  |  | Total | #NAME? | 459071177.2141 | #NAME? | Increase in cost

## Summary
Summary
Direct Non-Labour Expenditure
Expenditure Item |  |  | Dollar basis |  | Value | Asset Class | RIN Asset Category | As Incurred Spend Profile (%) | [9 empty] | As Incurred Spend Profile ($, Various) | [7 empty] | As Incurred Spend Profile ($, Nominal) | [7 empty] | As commissioned Spend Profile (%) | [7 empty] | As Commissioned Spend Profile ($, Various) | [7 empty] | 2026-27 - IPF - TET split |  | Source of IPF TET Split: Delivery Team
Category | Source | Units | [5 empty] | 2024-25 | 2025-26 | 2026-27 | 2027-28 | 2028-29 | 2029-30 | 2030-31 | Total |  |  | 2024-25 | 2025-26 | 2026-27 | 2027-28 | 2028-29 | 2029-30 | 2030-31 | Total | 2024-25 | 2025-26 | 2026-27 | 2027-28 | 2028-29 | 2029-30 | 2030-31 | Total | 2024-25 | 2025-26 | 2026-27 | 2027-28 | 2028-29 | 2029-30 | 2030-31 | Total | 2024-25 | 2025-26 | 2026-27 | 2027-28 | 2028-29 | 2029-30 | 2030-31 | Total | IPF portion | Non IPF portion
Construction Costs ¦ D&C Contract - Transmission Line | Project Team Input | $Millions | $ Nominal mid FY |  | [C-i-C] | Transmission Lines |  | As Incurred Spend Profile (%) 2024-25: 4%; As Incurred Spend Profile (%) 2025-26: 11%; As Incurred Spend Profile (%) 2026-27: 52%; As Incurred Spend Profile (%) 2027-28: 33% | 100% |  |  | [C-i-C] | [C-i-C] | [C-i-C] | [C-i-C] | [C-i-C] | [C-i-C] | [C-i-C] | [C-i-C] | [C-i-C] | [C-i-C] | [C-i-C] | [C-i-C] | [C-i-C] | [C-i-C] | [C-i-C] | [C-i-C] |  |  | 49.73% | 50.27% |  |  |  | 100% | [C-i-C] | [C-i-C] | [C-i-C] | [C-i-C] | [C-i-C] | [C-i-C] | [C-i-C] | [C-i-C] | 18.23% | 81.77%
| Project Team Input | $Millions | $ Nominal mid FY |  | [C-i-C] | Transmission Lines | Transmission towers | As Incurred Spend Profile (%) 2024-25: 4%; As Incurred Spend Profile (%) 2025-26: 11%; As Incurred Spend Profile (%) 2026-27: 52%; As Incurred Spend Profile (%) 2027-28: 33% | 100% |  |  | [C-i-C] | [C-i-C] | [C-i-C] | [C-i-C] | [C-i-C] | [C-i-C] | [C-i-C] | [C-i-C] | [C-i-C] | [C-i-C] | [C-i-C] | [C-i-C] | [C-i-C] | [C-i-C] | [C-i-C] | [C-i-C] |  |  | 86.54% | 13.46% |  |  |  | 100% | [C-i-C] | [C-i-C] | [C-i-C] | [C-i-C] | [C-i-C] | [C-i-C] | [C-i-C] | [C-i-C]
| Project Team Input | $Millions | $ Nominal mid FY |  | [C-i-C] | Transmission Lines | Transmission tower support structures | As Incurred Spend Profile (%) 2024-25: 4%; As Incurred Spend Profile (%) 2025-26: 11%; As Incurred Spend Profile (%) 2026-27: 52%; As Incurred Spend Profile (%) 2027-28: 33% | 100% |  |  | [C-i-C] | [C-i-C] | [C-i-C] | [C-i-C] | [C-i-C] | [C-i-C] | [C-i-C] | [C-i-C] | [C-i-C] | [C-i-C] | [C-i-C] | [C-i-C] | [C-i-C] | [C-i-C] | [C-i-C] | [C-i-C] |  |  | 86.54% | 13.46% |  |  |  | 100% | [C-i-C] | [C-i-C] | [C-i-C] | [C-i-C] | [C-i-C] | [C-i-C] | [C-i-C] | [C-i-C]
| Project Team Input | $Millions | $ Nominal mid FY |  | [C-i-C] | Transmission Lines | Conductors | As Incurred Spend Profile (%) 2024-25: 4%; As Incurred Spend Profile (%) 2025-26: 11%; As Incurred Spend Profile (%) 2026-27: 52%; As Incurred Spend Profile (%) 2027-28: 33% | 100% |  |  | [C-i-C] | [C-i-C] | [C-i-C] | [C-i-C] | [C-i-C] | [C-i-C] | [C-i-C] | [C-i-C] | [C-i-C] | [C-i-C] | [C-i-C] | [C-i-C] | [C-i-C] | [C-i-C] | [C-i-C] | [C-i-C] |  |  |  | 100% |  |  |  | 100% | [C-i-C] | [C-i-C] | [C-i-C] | [C-i-C] | [C-i-C] | [C-i-C] | [C-i-C] | [C-i-C]
Construction Costs ¦ D&C Contract - Substations | Project Team Input | $Millions | $ Nominal mid FY |  | [C-i-C] | Substations |  | As Incurred Spend Profile (%) 2024-25: 4%; As Incurred Spend Profile (%) 2025-26: 11%; As Incurred Spend Profile (%) 2026-27: 52%; As Incurred Spend Profile (%) 2027-28: 33% | 100% |  |  | [C-i-C] | [C-i-C] | [C-i-C] | [C-i-C] | [C-i-C] | [C-i-C] | [C-i-C] | [C-i-C] | [C-i-C] | [C-i-C] | [C-i-C] | [C-i-C] | [C-i-C] | [C-i-C] | [C-i-C] | [C-i-C] |  |  |  | 100% |  |  |  | 100% | [C-i-C] | [C-i-C] | [C-i-C] | [C-i-C] | [C-i-C] | [C-i-C] | [C-i-C] | [C-i-C] | 28.77% | 71.23%
| Project Team Input | $Millions | $ Nominal mid FY |  | [C-i-C] | Substations | Substation switchbays | As Incurred Spend Profile (%) 2024-25: 4%; As Incurred Spend Profile (%) 2025-26: 11%; As Incurred Spend Profile (%) 2026-27: 52%; As Incurred Spend Profile (%) 2027-28: 33% | 100% |  |  | [C-i-C] | [C-i-C] | [C-i-C] | [C-i-C] | [C-i-C] | [C-i-C] | [C-i-C] | [C-i-C] | [C-i-C] | [C-i-C] | [C-i-C] | [C-i-C] | [C-i-C] | [C-i-C] | [C-i-C] | [C-i-C] |  |  |  | 100% |  |  |  | 100% | [C-i-C] | [C-i-C] | [C-i-C] | [C-i-C] | [C-i-C] | [C-i-C] | [C-i-C] | [C-i-C]
| Project Team Input | $Millions | $ Nominal mid FY |  | [C-i-C] | Substations | Substation power transformers | As Incurred Spend Profile (%) 2024-25: 4%; As Incurred Spend Profile (%) 2025-26: 11%; As Incurred Spend Profile (%) 2026-27: 52%; As Incurred Spend Profile (%) 2027-28: 33% | 100% |  |  | [C-i-C] | [C-i-C] | [C-i-C] | [C-i-C] | [C-i-C] | [C-i-C] | [C-i-C] | [C-i-C] | [C-i-C] | [C-i-C] | [C-i-C] | [C-i-C] | [C-i-C] | [C-i-C] | [C-i-C] | [C-i-C] |  |  |  | 100% |  |  |  | 100% | [C-i-C] | [C-i-C] | [C-i-C] | [C-i-C] | [C-i-C] | [C-i-C] | [C-i-C] | [C-i-C]
| Project Team Input | $Millions | $ Nominal mid FY |  | [C-i-C] | Substations | Substation reactive plant | As Incurred Spend Profile (%) 2024-25: 4%; As Incurred Spend Profile (%) 2025-26: 11%; As Incurred Spend Profile (%) 2026-27: 52%; As Incurred Spend Profile (%) 2027-28: 33% | 100% |  |  | [C-i-C] | [C-i-C] | [C-i-C] | [C-i-C] | [C-i-C] | [C-i-C] | [C-i-C] | [C-i-C] | [C-i-C] | [C-i-C] | [C-i-C] | [C-i-C] | [C-i-C] | [C-i-C] | [C-i-C] | [C-i-C] |  |  |  | 100% |  |  |  | 100% | [C-i-C] | [C-i-C] | [C-i-C] | [C-i-C] | [C-i-C] | [C-i-C] | [C-i-C] | [C-i-C]
Construction Costs ¦ D&C Contract - Secondary System | Project Team Input | $Millions | $ Nominal mid FY |  | [C-i-C] | Secondary System | SCADA, network control and protection systems | As Incurred Spend Profile (%) 2024-25: 4%; As Incurred Spend Profile (%) 2025-26: 11%; As Incurred Spend Profile (%) 2026-27: 52%; As Incurred Spend Profile (%) 2027-28: 33% | 100% |  |  | [C-i-C] | [C-i-C] | [C-i-C] | [C-i-C] | [C-i-C] | [C-i-C] | [C-i-C] | [C-i-C] | [C-i-C] | [C-i-C] | [C-i-C] | [C-i-C] | [C-i-C] | [C-i-C] | [C-i-C] | [C-i-C] |  |  |  | 100% |  |  |  | 100% | [C-i-C] | [C-i-C] | [C-i-C] | [C-i-C] | [C-i-C] | [C-i-C] | [C-i-C] | [C-i-C] | 28.77% | 71.23%
Construction Costs ¦ Transposition | Project Team Input | $Millions | $ Nominal mid FY |  | [C-i-C] | Transmission Lines |  | 0% | 16.58% | 27.18% | 40.77% | 15.47% |  |  | 100% |  |  | [C-i-C] | [C-i-C] | [C-i-C] | [C-i-C] | [C-i-C] | [C-i-C] | [C-i-C] | [C-i-C] | [C-i-C] | [C-i-C] | [C-i-C] | [C-i-C] | [C-i-C] | [C-i-C] | [C-i-C] | [C-i-C] |  |  |  | 84.53% | 15.47% |  |  | 100% | [C-i-C] | [C-i-C] | [C-i-C] | [C-i-C] | [C-i-C] | [C-i-C] | [C-i-C] | [C-i-C] | 22.02% | 77.98%
| Project Team Input | $Millions | $ Nominal mid FY |  | [C-i-C] | Transmission Lines | Transmission towers | 0% | 16.58% | 27.18% | 40.77% | 15.47% |  |  | 100% |  |  | [C-i-C] | [C-i-C] | [C-i-C] | [C-i-C] | [C-i-C] | [C-i-C] | [C-i-C] | [C-i-C] | [C-i-C] | [C-i-C] | [C-i-C] | [C-i-C] | [C-i-C] | [C-i-C] | [C-i-C] | [C-i-C] |  |  |  | 84.53% | 15.47% |  |  | 100% | [C-i-C] | [C-i-C] | [C-i-C] | [C-i-C] | [C-i-C] | [C-i-C] | [C-i-C] | [C-i-C]
| Project Team Input | $Millions | $ Nominal mid FY |  | [C-i-C] | Transmission Lines | Transmission tower support structures | 0% | 16.58% | 27.18% | 40.77% | 15.47% |  |  | 100% |  |  | [C-i-C] | [C-i-C] | [C-i-C] | [C-i-C] | [C-i-C] | [C-i-C] | [C-i-C] | [C-i-C] | [C-i-C] | [C-i-C] | [C-i-C] | [C-i-C] | [C-i-C] | [C-i-C] | [C-i-C] | [C-i-C] |  |  |  | 84.53% | 15.47% |  |  | 100% | [C-i-C] | [C-i-C] | [C-i-C] | [C-i-C] | [C-i-C] | [C-i-C] | [C-i-C] | [C-i-C]
| Project Team Input | $Millions | $ Nominal mid FY |  | [C-i-C] | Transmission Lines | Conductors | 0% | 16.58% | 27.18% | 40.77% | 15.47% |  |  | 100% |  |  | [C-i-C] | [C-i-C] | [C-i-C] | [C-i-C] | [C-i-C] | [C-i-C] | [C-i-C] | [C-i-C] | [C-i-C] | [C-i-C] | [C-i-C] | [C-i-C] | [C-i-C] | [C-i-C] | [C-i-C] | [C-i-C] |  |  |  | 84.53% | 15.47% |  |  | 100% | [C-i-C] | [C-i-C] | [C-i-C] | [C-i-C] | [C-i-C] | [C-i-C] | [C-i-C] | [C-i-C]
Secondary System ¦ Protection Relays | Project Team Input | $Millions | $30 June 2026 |  | 0.4105 | Secondary System | SCADA, network control and protection systems | As Incurred Spend Profile (%) 2025-26: 100% | 100% |  |  | 0 | 0.4105 | 0 | 0 | 0 | 0 | 0 | 0.4105 | 0 | 0.40409 | 0 | 0 | 0 | 0 | 0 | 0.40409 |  | 100% | [5 empty] | 100% | 0 | 0.4105 | 0 | 0 | 0 | 0 | 0 | 0.4105 | 100% | 0%
Secondary System ¦ IED SEL Terminals | Project Team Input | $Millions | $30 June 2026 |  | 0.10424 | Secondary System | SCADA, network control and protection systems | As Incurred Spend Profile (%) 2025-26: 100% | 100% |  |  | 0 | 0.10424 | 0 | 0 | 0 | 0 | 0 | 0.10424 | 0 | 0.10261 | 0 | 0 | 0 | 0 | 0 | 0.10261 |  | 100% | [5 empty] | 100% | 0 | 0.10424 | 0 | 0 | 0 | 0 | 0 | 0.10424 | 100% | 0%
Secondary System ¦ QOS Meter | Project Team Input | $Millions | $30 June 2026 |  | 0.16169 | Secondary System | SCADA, network control and protection systems | As Incurred Spend Profile (%) 2025-26: 100% | 100% |  |  | 0 | 0.16169 | 0 | 0 | 0 | 0 | 0 | 0.16169 | 0 | 0.15916 | 0 | 0 | 0 | 0 | 0 | 0.15916 |  | 100% | [5 empty] | 100% | 0 | 0.16169 | 0 | 0 | 0 | 0 | 0 | 0.16169 | 100% | 0%
Secondary System ¦ Disturbance Recorder | Project Team Input | $Millions | $30 June 2026 |  | 0.074118 | Secondary System | SCADA, network control and protection systems | As Incurred Spend Profile (%) 2025-26: 100% | 100% |  |  | 0 | 0.074118 | 0 | 0 | 0 | 0 | 0 | 0.074118 | 0 | 0.07296 | 0 | 0 | 0 | 0 | 0 | 0.07296 |  | 100% | [5 empty] | 100% | 0 | 0.074118 | 0 | 0 | 0 | 0 | 0 | 0.074118 | 100% | 0%
Secondary System ¦ Metering Panel | Project Team Input | $Millions | $30 June 2026 |  | 0.063068 | Secondary System | SCADA, network control and protection systems | As Incurred Spend Profile (%) 2025-26: 100% | 100% |  |  | 0 | 0.063068 | 0 | 0 | 0 | 0 | 0 | 0.063068 | 0 | 0.062082 | 0 | 0 | 0 | 0 | 0 | 0.062082 |  | 100% | [5 empty] | 100% | 0 | 0.063068 | 0 | 0 | 0 | 0 | 0 | 0.063068 | 100% | 0%
Secondary System ¦ TWFL | Project Team Input | $Millions | $30 June 2026 |  | 0.067906 | Secondary System | SCADA, network control and protection systems | As Incurred Spend Profile (%) 2025-26: 100% | 100% |  |  | 0 | 0.067906 | 0 | 0 | 0 | 0 | 0 | 0.067906 | 0 | 0.066845 | 0 | 0 | 0 | 0 | 0 | 0.066845 |  | 100% | [5 empty] | 100% | 0 | 0.067906 | 0 | 0 | 0 | 0 | 0 | 0.067906 | 100% | 0%
Secondary System ¦ Comms - XTRAN | Project Team Input | $Millions | $30 June 2026 |  | 0.27582 | Secondary System | SCADA, network control and protection systems | As Incurred Spend Profile (%) 2025-26: 100% | 100% |  |  | 0 | 0.27582 | 0 | 0 | 0 | 0 | 0 | 0.27582 | 0 | 0.27151 | 0 | 0 | 0 | 0 | 0 | 0.27151 |  | 100% | [5 empty] | 100% | 0 | 0.27582 | 0 | 0 | 0 | 0 | 0 | 0.27582 | 100% | 0%
Secondary System ¦ Comms - RAD | Project Team Input | $Millions | $30 June 2026 |  | 0.10233 | Secondary System | SCADA, network control and protection systems | As Incurred Spend Profile (%) 2025-26: 100% | 100% |  |  | 0 | 0.10233 | 0 | 0 | 0 | 0 | 0 | 0.10233 | 0 | 0.10073 | 0 | 0 | 0 | 0 | 0 | 0.10073 |  | 100% | [5 empty] | 100% | 0 | 0.10233 | 0 | 0 | 0 | 0 | 0 | 0.10233 | 100% | 0%
Equipment Costs ¦ Transformers (CT) | Project Team Input | $Millions | $30 June 2026 |  |  | Substations |  | As Incurred Spend Profile (%) 2025-26: 100% | 100% |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 100% | [5 empty] | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0%
| Project Team Input | $Millions | $30 June 2026 |  | 0 | Substations | Substation switchbays | As Incurred Spend Profile (%) 2025-26: 100% | 100% |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 100% | [5 empty] | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0%
| Project Team Input | $Millions | $30 June 2026 |  | 0.85757 | Substations | Substation power transformers | As Incurred Spend Profile (%) 2025-26: 100% | 100% |  |  | 0 | 0.85757 | 0 | 0 | 0 | 0 | 0 | 0.85757 | 0 | 0.84417 | 0 | 0 | 0 | 0 | 0 | 0.84417 |  | 100% | [5 empty] | 100% | 0 | 0.85757 | 0 | 0 | 0 | 0 | 0 | 0.85757 | 100% | 0%
| Project Team Input | $Millions | $30 June 2026 |  | 0 | Substations | Substation reactive plant | As Incurred Spend Profile (%) 2025-26: 100% | 100% |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 100% | [5 empty] | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0%
Equipment Costs ¦ Circuit Breakers (CB) | Project Team Input | $Millions | $30 June 2026 |  |  | Substations |  | As Incurred Spend Profile (%) 2025-26: 100% | 100% |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 100% | [5 empty] | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0%
| Project Team Input | $Millions | $30 June 2026 |  | 0.57376 | Substations | Substation switchbays | As Incurred Spend Profile (%) 2025-26: 100% | 100% |  |  | 0 | 0.57376 | 0 | 0 | 0 | 0 | 0 | 0.57376 | 0 | 0.56479 | 0 | 0 | 0 | 0 | 0 | 0.56479 |  | 100% | [5 empty] | 100% | 0 | 0.57376 | 0 | 0 | 0 | 0 | 0 | 0.57376 | 100% | 0%
| Project Team Input | $Millions | $30 June 2026 |  | 0 | Substations | Substation power transformers | As Incurred Spend Profile (%) 2025-26: 100% | 100% |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 100% | [5 empty] | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0%
| Project Team Input | $Millions | $30 June 2026 |  | 0 | Substations | Substation reactive plant | As Incurred Spend Profile (%) 2025-26: 100% | 100% |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 100% | [5 empty] | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0%
Equipment Costs ¦ Voltage Transformers (VT) | Project Team Input | $Millions | $30 June 2026 |  |  | Substations |  | As Incurred Spend Profile (%) 2025-26: 100% | 100% |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 100% | [5 empty] | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0%
| Project Team Input | $Millions | $30 June 2026 |  | 0 | Substations | Substation switchbays | As Incurred Spend Profile (%) 2025-26: 100% | 100% |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 100% | [5 empty] | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0%
| Project Team Input | $Millions | $30 June 2026 |  | 0.29279 | Substations | Substation power transformers | As Incurred Spend Profile (%) 2025-26: 100% | 100% |  |  | 0 | 0.29279 | 0 | 0 | 0 | 0 | 0 | 0.29279 | 0 | 0.28822 | 0 | 0 | 0 | 0 | 0 | 0.28822 |  | 100% | [5 empty] | 100% | 0 | 0.29279 | 0 | 0 | 0 | 0 | 0 | 0.29279 | 100% | 0%
| Project Team Input | $Millions | $30 June 2026 |  | 0 | Substations | Substation reactive plant | As Incurred Spend Profile (%) 2025-26: 100% | 100% |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 100% | [5 empty] | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0%
Equipment Costs ¦ Line Trap (LT) | Project Team Input | $Millions | $30 June 2026 |  |  | Substations |  | As Incurred Spend Profile (%) 2025-26: 100% | 100% |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 100% | [5 empty] | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0%
| Project Team Input | $Millions | $30 June 2026 |  | 0.61909 | Substations | Substation switchbays | As Incurred Spend Profile (%) 2025-26: 100% | 100% |  |  | 0 | 0.61909 | 0 | 0 | 0 | 0 | 0 | 0.61909 | 0 | 0.60941 | 0 | 0 | 0 | 0 | 0 | 0.60941 |  | 100% | [5 empty] | 100% | 0 | 0.61909 | 0 | 0 | 0 | 0 | 0 | 0.61909 | 100% | 0%
| Project Team Input | $Millions | $30 June 2026 |  | 0 | Substations | Substation power transformers | As Incurred Spend Profile (%) 2025-26: 100% | 100% |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 100% | [5 empty] | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0%
| Project Team Input | $Millions | $30 June 2026 |  | 0 | Substations | Substation reactive plant | As Incurred Spend Profile (%) 2025-26: 100% | 100% |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 100% | [5 empty] | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0%
Equipment Costs ¦ Earth Switch | Project Team Input | $Millions | $30 June 2026 |  |  | Substations |  | As Incurred Spend Profile (%) 2025-26: 100% | 100% |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 100% | [5 empty] | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0%
| Project Team Input | $Millions | $30 June 2026 |  | 0.32257 | Substations | Substation switchbays | As Incurred Spend Profile (%) 2025-26: 100% | 100% |  |  | 0 | 0.32257 | 0 | 0 | 0 | 0 | 0 | 0.32257 | 0 | 0.31753 | 0 | 0 | 0 | 0 | 0 | 0.31753 |  | 100% | [5 empty] | 100% | 0 | 0.32257 | 0 | 0 | 0 | 0 | 0 | 0.32257 | 100% | 0%
| Project Team Input | $Millions | $30 June 2026 |  | 0 | Substations | Substation power transformers | As Incurred Spend Profile (%) 2025-26: 100% | 100% |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 100% | [5 empty] | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0%
| Project Team Input | $Millions | $30 June 2026 |  | 0 | Substations | Substation reactive plant | As Incurred Spend Profile (%) 2025-26: 100% | 100% |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 100% | [5 empty] | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0%
Equipment Costs ¦ Surge Arrestor | Project Team Input | $Millions | $30 June 2026 |  |  | Substations |  | As Incurred Spend Profile (%) 2025-26: 100% | 100% |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 100% | [5 empty] | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0%
| Project Team Input | $Millions | $30 June 2026 |  | 0 | Substations | Substation switchbays | As Incurred Spend Profile (%) 2025-26: 100% | 100% |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 100% | [5 empty] | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0%
| Project Team Input | $Millions | $30 June 2026 |  | 0 | Substations | Substation power transformers | As Incurred Spend Profile (%) 2025-26: 100% | 100% |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 100% | [5 empty] | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0%
| Project Team Input | $Millions | $30 June 2026 |  | 0.078188 | Substations | Substation reactive plant | As Incurred Spend Profile (%) 2025-26: 100% | 100% |  |  | 0 | 0.078188 | 0 | 0 | 0 | 0 | 0 | 0.078188 | 0 | 0.076966 | 0 | 0 | 0 | 0 | 0 | 0.076966 |  | 100% | [5 empty] | 100% | 0 | 0.078188 | 0 | 0 | 0 | 0 | 0 | 0.078188 | 100% | 0%
Equipment Costs ¦ Disconnector | Project Team Input | $Millions | $30 June 2026 |  |  | Substations |  | As Incurred Spend Profile (%) 2025-26: 100% | 100% |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 100% | [5 empty] | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0%
| Project Team Input | $Millions | $30 June 2026 |  | 0 | Substations | Substation switchbays | As Incurred Spend Profile (%) 2025-26: 100% | 100% |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 100% | [5 empty] | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0%
| Project Team Input | $Millions | $30 June 2026 |  | 0 | Substations | Substation power transformers | As Incurred Spend Profile (%) 2025-26: 100% | 100% |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 100% | [5 empty] | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0%
| Project Team Input | $Millions | $30 June 2026 |  | 0.78843 | Substations | Substation reactive plant | As Incurred Spend Profile (%) 2025-26: 100% | 100% |  |  | 0 | 0.78843 | 0 | 0 | 0 | 0 | 0 | 0.78843 | 0 | 0.77611 | 0 | 0 | 0 | 0 | 0 | 0.77611 |  | 100% | [5 empty] | 100% | 0 | 0.78843 | 0 | 0 | 0 | 0 | 0 | 0.78843 | 100% | 0%
Equipment Costs ¦ Insulator (16KN) | Project Team Input | $Millions | $30 June 2026 |  |  | Substations |  | As Incurred Spend Profile (%) 2025-26: 100% | 100% |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 100% | [5 empty] | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0%
| Project Team Input | $Millions | $30 June 2026 |  | 0 | Substations | Substation switchbays | As Incurred Spend Profile (%) 2025-26: 100% | 100% |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 100% | [5 empty] | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0%
| Project Team Input | $Millions | $30 June 2026 |  | 0 | Substations | Substation power transformers | As Incurred Spend Profile (%) 2025-26: 100% | 100% |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 100% | [5 empty] | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0%
| Project Team Input | $Millions | $30 June 2026 |  | 0.01396 | Substations | Substation reactive plant | As Incurred Spend Profile (%) 2025-26: 100% | 100% |  |  | 0 | 0.01396 | 0 | 0 | 0 | 0 | 0 | 0.01396 | 0 | 0.013742 | 0 | 0 | 0 | 0 | 0 | 0.013742 |  | 100% | [5 empty] | 100% | 0 | 0.01396 | 0 | 0 | 0 | 0 | 0 | 0.01396 | 100% | 0%
Equipment Costs ¦ Insulator (6KN) | Project Team Input | $Millions | $30 June 2026 |  |  | Substations |  | As Incurred Spend Profile (%) 2025-26: 100% | 100% |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 100% | [5 empty] | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0%
| Project Team Input | $Millions | $30 June 2026 |  | 0 | Substations | Substation switchbays | As Incurred Spend Profile (%) 2025-26: 100% | 100% |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 100% | [5 empty] | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0%
| Project Team Input | $Millions | $30 June 2026 |  | 0 | Substations | Substation power transformers | As Incurred Spend Profile (%) 2025-26: 100% | 100% |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 100% | [5 empty] | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0%
| Project Team Input | $Millions | $30 June 2026 |  | 0.012156 | Substations | Substation reactive plant | As Incurred Spend Profile (%) 2025-26: 100% | 100% |  |  | 0 | 0.012156 | 0 | 0 | 0 | 0 | 0 | 0.012156 | 0 | 0.011966 | 0 | 0 | 0 | 0 | 0 | 0.011966 |  | 100% | [5 empty] | 100% | 0 | 0.012156 | 0 | 0 | 0 | 0 | 0 | 0.012156 | 100% | 0%
Equipment Costs ¦ Insulator (6KN) (UH) | Project Team Input | $Millions | $30 June 2026 |  |  | Substations |  | As Incurred Spend Profile (%) 2025-26: 100% | 100% |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 100% | [5 empty] | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0%
| Project Team Input | $Millions | $30 June 2026 |  | 0 | Substations | Substation switchbays | As Incurred Spend Profile (%) 2025-26: 100% | 100% |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 100% | [5 empty] | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0%
| Project Team Input | $Millions | $30 June 2026 |  | 0 | Substations | Substation power transformers | As Incurred Spend Profile (%) 2025-26: 100% | 100% |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 100% | [5 empty] | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0%
| Project Team Input | $Millions | $30 June 2026 |  | 0.0042752 | Substations | Substation reactive plant | As Incurred Spend Profile (%) 2025-26: 100% | 100% |  |  | 0 | 0.0042752 | 0 | 0 | 0 | 0 | 0 | 0.0042752 | 0 | 0.0042084 | 0 | 0 | 0 | 0 | 0 | 0.0042084 |  | 100% | [5 empty] | 100% | 0 | 0.0042752 | 0 | 0 | 0 | 0 | 0 | 0.0042752 | 100% | 0%
Property Costs ¦ Easements - Augmentation | Project Team Input | $Millions | $30 June 2026 |  | [C-i-C] | Land & Easements | Other | As Incurred Spend Profile (%) 2024-25: 20%; As Incurred Spend Profile (%) 2025-26: 80% | 100% |  |  | [C-i-C] | [C-i-C] | [C-i-C] | [C-i-C] | [C-i-C] | [C-i-C] | [C-i-C] | [C-i-C] | [C-i-C] | [C-i-C] | [C-i-C] | [C-i-C] | [C-i-C] | [C-i-C] | [C-i-C] | [C-i-C] |  | 100% | [5 empty] | 100% | [C-i-C] | [C-i-C] | [C-i-C] | [C-i-C] | [C-i-C] | [C-i-C] | [C-i-C] | [C-i-C] | 10% | 90%
Property Costs ¦ Easements - Transposition | Project Team Input | $Millions | $30 June 2026 |  | [C-i-C] | Land & Easements | Other | As Incurred Spend Profile (%) 2024-25: 11.75%; As Incurred Spend Profile (%) 2025-26: 63.25%; As Incurred Spend Profile (%) 2026-27: 25% | 100% |  |  | [C-i-C] | [C-i-C] | [C-i-C] | [C-i-C] | [C-i-C] | [C-i-C] | [C-i-C] | [C-i-C] | [C-i-C] | [C-i-C] | [C-i-C] | [C-i-C] | [C-i-C] | [C-i-C] | [C-i-C] | [C-i-C] |  |  | 100% |  |  |  |  | 100% | [C-i-C] | [C-i-C] | [C-i-C] | [C-i-C] | [C-i-C] | [C-i-C] | [C-i-C] | [C-i-C] | 10% | 90%
Environment ¦ Biodiversity Offsets | Project Team Input | $Millions | $30 June 2026 |  | [C-i-C] | Biodiversity offsets - Stewardship sites | Biodiversity Offsets | As Incurred Spend Profile (%) 2024-25: 0%; As Incurred Spend Profile (%) 2025-26: 43%; As Incurred Spend Profile (%) 2026-27: 22%; As Incurred Spend Profile (%) 2027-28: 35% | 100% |  |  | [C-i-C] | [C-i-C] | [C-i-C] | [C-i-C] | [C-i-C] | [C-i-C] | [C-i-C] | [C-i-C] | [C-i-C] | [C-i-C] | [C-i-C] | [C-i-C] | [C-i-C] | [C-i-C] | [C-i-C] | [C-i-C] | 0% | 43% | 22% | 35% | 0% | 0% | 0% | 100% | [C-i-C] | [C-i-C] | [C-i-C] | [C-i-C] | [C-i-C] | [C-i-C] | [C-i-C] | [C-i-C] | 10% | 90%
| Project Team Input | $Millions | $30 June 2026 |  | [C-i-C] | Biodiversity offsets - Direct payments & Other costs | Biodiversity Offsets | As Incurred Spend Profile (%) 2024-25: 0%; As Incurred Spend Profile (%) 2025-26: 43%; As Incurred Spend Profile (%) 2026-27: 22%; As Incurred Spend Profile (%) 2027-28: 35% | 100% |  |  | [C-i-C] | [C-i-C] | [C-i-C] | [C-i-C] | [C-i-C] | [C-i-C] | [C-i-C] | [C-i-C] | [C-i-C] | [C-i-C] | [C-i-C] | [C-i-C] | [C-i-C] | [C-i-C] | [C-i-C] | [C-i-C] | 0% | 43% | 22% | 35% | 0% | 0% | 0% | 100% | [C-i-C] | [C-i-C] | [C-i-C] | [C-i-C] | [C-i-C] | [C-i-C] | [C-i-C] | [C-i-C] | 10% | 90%
Infrastructure Planner Fee - Other | Commercial Team Input | $Millions | $ Nominal mid FY |  | 3.2717 | Transmission Lines | Transmission towers | As Incurred Spend Profile (%) 2026-27: 100% | 100% |  |  | 0 | 0 | 3.2717 | 0 | 0 | 0 | 0 | 3.2717 | 0 | 0 | 3.2717 | 0 | 0 | 0 | 0 | 3.2717 |  |  | 100% |  |  |  |  | 100% | 0 | 0 | 3.2717 | 0 | 0 | 0 | 0 | 3.2717 | 100% | 0%
Infrastructure Planner Fee - Other | Commercial Team Input | $Millions | $ Nominal mid FY |  | 0.74462 | Substations | Substation switchbays | As Incurred Spend Profile (%) 2026-27: 100% | 100% |  |  | 0 | 0 | 0.74462 | 0 | 0 | 0 | 0 | 0.74462 | 0 | 0 | 0.74462 | 0 | 0 | 0 | 0 | 0.74462 |  |  | 100% |  |  |  |  | 100% | 0 | 0 | 0.74462 | 0 | 0 | 0 | 0 | 0.74462 | 100% | 0%
Infrastructure Planner Fee - Other | Commercial Team Input | $Millions | $ Nominal mid FY |  | 0.16323 | Biodiversity offsets - Stewardship sites | Biodiversity Offsets | As Incurred Spend Profile (%) 2026-27: 100% | 100% |  |  | 0 | 0 | 0.16323 | 0 | 0 | 0 | 0 | 0.16323 | 0 | 0 | 0.16323 | 0 | 0 | 0 | 0 | 0.16323 |  |  | 100% |  |  |  |  | 100% | 0 | 0 | 0.16323 | 0 | 0 | 0 | 0 | 0.16323 | 100% | 0%
Infrastructure Planner Fee - Other | Commercial Team Input | $Millions | $ Nominal mid FY |  | 0.39107 | Biodiversity offsets - Direct payments & Other costs | Biodiversity Offsets | As Incurred Spend Profile (%) 2026-27: 100% | 100% |  |  | 0 | 0 | 0.39107 | 0 | 0 | 0 | 0 | 0.39107 | 0 | 0 | 0.39107 | 0 | 0 | 0 | 0 | 0.39107 |  |  | 100% |  |  |  |  | 100% | 0 | 0 | 0.39107 | 0 | 0 | 0 | 0 | 0.39107 | 100% | 0%
Infrastructure Planner Fee - Other | Commercial Team Input | $Millions | $ Nominal mid FY |  | 0.3294 | Secondary System | SCADA, network control and protection systems | As Incurred Spend Profile (%) 2026-27: 100% | 100% |  |  | 0 | 0 | 0.3294 | 0 | 0 | 0 | 0 | 0.3294 | 0 | 0 | 0.3294 | 0 | 0 | 0 | 0 | 0.3294 |  |  | 100% |  |  |  |  | 100% | 0 | 0 | 0.3294 | 0 | 0 | 0 | 0 | 0.3294 | 100% | 0%
|  |  | Subtotal |  | 245.5853 | [12 empty] | 8.0357 | 46.5557 | 107.5179 | 78.2763 | 5.1998 | 0 | 0 | 245.5853 | 7.9774 | 46.2016 | 107.6127 | 78.6797 | 5.1998 | 0 | 0 | 245.6712 | [8 empty] | 0 | 21.5381 | 94.9344 | 123.9128 | 5.2 | 0 | 0 | 245.5853
Risk ¦ Other Construction Cost | Project Team Input | $Millions | $ Nominal mid FY |  |  | Transmission Lines |  | As Incurred Spend Profile (%) 2025-26: 4.56%; As Incurred Spend Profile (%) 2026-27: 38.21%; As Incurred Spend Profile (%) 2027-28: 40.95%; As Incurred Spend Profile (%) 2028-29: 16.28% | 100% |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 100% |  |  | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 100%
| Project Team Input | $Millions | $ Nominal mid FY |  | 3.7914 | Transmission Lines | Transmission towers | As Incurred Spend Profile (%) 2025-26: 4.56%; As Incurred Spend Profile (%) 2026-27: 38.21%; As Incurred Spend Profile (%) 2027-28: 40.95%; As Incurred Spend Profile (%) 2028-29: 16.28% | 100% |  |  | 0 | 0.17289 | 1.4487 | 1.5526 | 0.61723 | 0 | 0 | 3.7914 | 0 | 0.17289 | 1.4487 | 1.5526 | 0.61723 | 0 | 0 | 3.7914 |  |  |  |  | 100% |  |  | 100% | 0 | 0 | 0 | 0 | 3.7914 | 0 | 0 | 3.7914 | 0% | 100%
| Project Team Input | $Millions | $ Nominal mid FY |  | 4.023 | Transmission Lines | Transmission tower support structures | As Incurred Spend Profile (%) 2025-26: 4.56%; As Incurred Spend Profile (%) 2026-27: 38.21%; As Incurred Spend Profile (%) 2027-28: 40.95%; As Incurred Spend Profile (%) 2028-29: 16.28% | 100% |  |  | 0 | 0.18345 | 1.5372 | 1.6474 | 0.65494 | 0 | 0 | 4.023 | 0 | 0.18345 | 1.5372 | 1.6474 | 0.65494 | 0 | 0 | 4.023 |  |  |  |  | 100% |  |  | 100% | 0 | 0 | 0 | 0 | 4.023 | 0 | 0 | 4.023 | 0% | 100%
| Project Team Input | $Millions | $ Nominal mid FY |  | 2.0379 | Transmission Lines | Conductors | As Incurred Spend Profile (%) 2025-26: 4.56%; As Incurred Spend Profile (%) 2026-27: 38.21%; As Incurred Spend Profile (%) 2027-28: 40.95%; As Incurred Spend Profile (%) 2028-29: 16.28% | 100% |  |  | 0 | 0.092928 | 0.77868 | 0.83451 | 0.33177 | 0 | 0 | 2.0379 | 0 | 0.092928 | 0.77868 | 0.83451 | 0.33177 | 0 | 0 | 2.0379 |  |  |  |  | 100% |  |  | 100% | 0 | 0 | 0 | 0 | 2.0379 | 0 | 0 | 2.0379 | 0% | 100%
| Project Team Input | $Millions | $ Nominal mid FY |  | 1.6371 | Transmission Lines | Substation switchbays | As Incurred Spend Profile (%) 2025-26: 4.56%; As Incurred Spend Profile (%) 2026-27: 38.21%; As Incurred Spend Profile (%) 2027-28: 40.95%; As Incurred Spend Profile (%) 2028-29: 16.28% | 100% |  |  | 0 | 0.07465 | 0.62552 | 0.67038 | 0.26651 | 0 | 0 | 1.6371 | 0 | 0.07465 | 0.62552 | 0.67038 | 0.26651 | 0 | 0 | 1.6371 |  |  |  |  | 100% |  |  | 100% | 0 | 0 | 0 | 0 | 1.6371 | 0 | 0 | 1.6371 | 0% | 100%
| Project Team Input | $Millions | $ Nominal mid FY |  | 1.1946 | Transmission Lines | Substation power transformers | As Incurred Spend Profile (%) 2025-26: 4.56%; As Incurred Spend Profile (%) 2026-27: 38.21%; As Incurred Spend Profile (%) 2027-28: 40.95%; As Incurred Spend Profile (%) 2028-29: 16.28% | 100% |  |  | 0 | 0.054472 | 0.45644 | 0.48917 | 0.19447 | 0 | 0 | 1.1946 | 0 | 0.054472 | 0.45644 | 0.48917 | 0.19447 | 0 | 0 | 1.1946 |  |  |  |  | 100% |  |  | 100% | 0 | 0 | 0 | 0 | 1.1946 | 0 | 0 | 1.1946 | 0% | 100%
|  |  |  | Total | 258.2691 | [12 empty] | 8.0357 | 47.1341 | 112.3643 | 83.4703 | 7.2647 | 0 | 0 | 258.2691 | 7.9774 | 46.78 | 112.4592 | 83.8737 | 7.2647 | 0 | 0 | 258.355 | [8 empty] | 0 | 21.5381 | 94.9344 | 123.9128 | 17.8838 | 0 | 0 | 258.2691
Asset Classes
Asset Classes | Total - Excl BCSS ($Nominal)
RAB asset classes
Transmission Lines | 167.0937
Substations | 38.0299
Land & Easements | [C-i-C]
Biodiversity offsets - Stewardship sites | [C-i-C]
Biodiversity offsets - Direct payments & Other costs | [C-i-C]
Secondary System | 16.8232
Underground Cables | 0
Communications (short life) | 0
Business IT | 0
Minor Plant, Motor Vehicles & Mobile Plant | 0
Transmission Line Life Extension | 0
NSCAS Assets | 0
Synchronous Condensers (2018-23) | 0
Leasehold Land and Property | 0
Buildings - capital works | 0
In-house software | 0
0
Asset Classes (RAB asset classes) | RIN Asset Categories
Transmission Lines | Transmission towers
Transmission tower support structures
Conductors
Substations | Substation switchbays
Substation power transformers
Substation reactive plant
Land & Easements | Other
Biodiversity offsets - Stewardship sites | Biodiversity Offsets
Biodiversity offsets - Direct payments & Other costs | Biodiversity Offsets
Secondary System | SCADA, network control and protection systems
Underground Cables | Transmission cables
Communications (short life) | SCADA, network control and protection systems
Business IT | IT & Communications
Minor Plant, Motor Vehicles & Mobile Plant | Other non-network
Transmission Line Life Extension | Transmission cables
NSCAS Assets | Other non-network
Synchronous Condensers (2018-23) | Other network
Leasehold Land and Property | Buildings and property
Buildings - capital works | Buildings and property
In-house software | IT & Communications
CPI
Convert From | Convert To | Factor
2022 | to 2026 | 1.1632
2023 | to 2026 | 1.0971
2024 | to 2026 | 1.0568
2025 | to 2026 | 1.032
2026 | to 2026 | 1
$ Nominal | to 2026
Indexation | [7 empty] | As Incurred Spend Profile (%) 2024-25: Indexation
Item | Source | Units | [5 empty] | 2020 | 2021 | 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | 2031
Real 2026 End Period to Nominal Mid Period | Calculated | Factor | [5 empty] | 0.78129 | 0.79479 | 0.83444 | 0.88523 | 0.92873 | 0.95757 | 0.98437 | 1.0138 | 1.042 | 1.071 | 1.1007 | 1.1313
Rates | [7 empty] | Indexation 2020: Rates
Item | Source | Units | [5 empty] | 2020 | 2021 | 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 |  | 2030 | 2031
Real labour escalation | AER Final Determination / Transgrid proposal | Percent | [7 empty] | -2.177% | -3.47% | 0.3905% | 1.308% | 1.155% | 0.433% | 0.3009%
Inflation | ABS June to June / RBA Forecast | Factor | [7 empty] | 6.145% | 6.027% | 3.815% | 2.4% | 3.2% | 2.78% | 2.78%
Dollar Basis
Real / Nominal
$ Nominal mid FY
$30 June 2021
$30 June 2022
$30 June 2023
$30 June 2024
$30 June 2025
$30 June 2026
RIN Asset Categories
Transmission towers
Transmission tower support structures
Conductors
Transmission cables
Substation switchbays
Substation power transformers
Substation reactive plant
SCADA, network control and protection systems
Biodiversity offsets
Other

## D&C Contract - Transmission Lin
CONFIDENTIAL
D&C Contractor Costs - Transmission Lines
Calculation & Supporting Evidence
Confidential information has been removed from this worksheet
End

## D&C Contract - Substations
CONFIDENTIAL
D&C Contractor Costs - Substations
Calculation & Supporting Evidence
Confidential information has been removed from this worksheet
End

## D&C Contract - Secondary System
CONFIDENTIAL
D&C Contractor Costs - Secondary Systems
Calculation & Supporting Evidence
Confidential information has been removed from this worksheet
End

## Transposition
CONFIDENTIAL
Transposition
Calculation & Supporting Evidence
Confidential information has been removed from this worksheet

## version comparison (hidden)
|  |  |  | After update | Before update | Variance
Construction Costs ¦ D&C Contract - Transmission Line | Project Team Input | $Millions | $ Nominal mid FY | 117872243.9681 | 117872243.9681 | 0
Construction Costs ¦ D&C Contract - Substations | Project Team Input | $Millions | $ Nominal mid FY | 33436324.4509 | 34129776.1066 | -693451.6558
Construction Costs ¦ D&C Contract - Secondary System | Project Team Input | $Millions | $ Nominal mid FY | 15253771.9646 | 15253771.9646 | 0
Construction Costs ¦ Transposition | Project Team Input | $Millions | $ Nominal mid FY | 44993130.06 | 44993131 | -0.94
Secondary System ¦ Protection Relays | Project Team Input | $Millions | $30 June 2026 | 410346.1647 | 410346.1647 | 0
Secondary System ¦ IED SEL Terminals | Project Team Input | $Millions | $30 June 2026 | 104237.3129 | 104237.3129 | 0
Secondary System ¦ QOS Meter | Project Team Input | $Millions | $30 June 2026 | 161530.855 | 161530.855 | 0
Secondary System ¦ Disturbance Recorder | Project Team Input | $Millions | $30 June 2026 | 74045.9295 | 81450.5225 | -7404.593
Secondary System ¦ Metering Panel | Project Team Input | $Millions | $30 June 2026 | 63067.9142 | 63067.9142 | 0
Secondary System ¦ TWFL | Project Team Input | $Millions | $30 June 2026 | 67906.3965 | 67906.3965 | 0
Secondary System ¦ Comms - XTRAN | Project Team Input | $Millions | $30 June 2026 | 275550.0187 | 275550.0187 | 0
Secondary System ¦ Comms - RAD | Project Team Input | $Millions | $30 June 2026 | 102330.0157 | 102330.0157 | 0
Equipment Costs ¦ Transformers (CT) | Project Team Input | $Millions | $30 June 2026 | 857567.232 | 857567.232 | 0
Equipment Costs ¦ Circuit Breakers (CB) | Project Team Input | $Millions | $30 June 2026 | 573758.4476 | 573758.3208 | 0.12681
Equipment Costs ¦ Voltage Transformers (VT) | Project Team Input | $Millions | $30 June 2026 | 292790.784 | 292790.784 | 0
Equipment Costs ¦ Line Trap (LT) | Project Team Input | $Millions | $30 June 2026 | 618483.9778 | 618483.9778 | 0
Equipment Costs ¦ Earth Switch | Project Team Input | $Millions | $30 June 2026 | 322568.1496 | 323286.7519 | -718.6022
Equipment Costs ¦ Surge Arrestor | Project Team Input | $Millions | $30 June 2026 | 78111.4037 | 78111.4037 | 0
Equipment Costs ¦ Disconnector | Project Team Input | $Millions | $30 June 2026 | 788434.4205 | 788434.4205 | 0
Equipment Costs ¦ Insulator (16KN) | Project Team Input | $Millions | $30 June 2026 | 13960.328 | 13960.328 | 0
Equipment Costs ¦ Insulator (6KN) | Project Team Input | $Millions | $30 June 2026 | 12155.6853 | 12155.6853 | 0
Equipment Costs ¦ Insulator (6KN) (UH) | Project Team Input | $Millions | $30 June 2026 | 4275.1549 | 4275.1549 | 0
Property Costs ¦ Easements | Project Team Input | $Millions | $30 June 2026 | 4907963.7666 | 4905587.8879 | 2375.8787
Property Costs ¦ Transposition_1 | Project Team Input | $Millions | $30 June 2026 | 3261998.4015 | 3205766.8086 | 56231.5929
Environment ¦ Biodiversity Offsets | Project Team Input | $Millions | $30 June 2026 | 28541801.2838 | 28541801.2838 | 0
|  |  | Subtotal | 253088354.0863
Barigan Creek ¦ Barigan Creek | Project Team Input | $Millions | $ Nominal mid FY | 202557409 | 202557409 | 0
P50 Risk ¦ Risk | Project Team Input | $Millions | $ Nominal mid FY | 12885630 | 0 | 12885630
|  |  | Total | 468531393.0863 | 456288731.2788 | 12242661.8074
.

## Easements - Augmentation
CONFIDENTIAL
Easements - Augmentation
Calculation & Supporting Evidence
Confidential information has been removed from this worksheet
End
End

## Easement - Transposition
CONFIDENTIAL
Easements - Transposition
Calculation & Supporting Evidence
Confidential information has been removed from this worksheet
End
End

## Biodiversity Offsets
CONFIDENTIAL
Biodiversity Offsets
Calculation & Supporting Evidence
Confidential information has been removed from this worksheet
End

## OCC
CONFIDENTIAL
Other Construction Costs
Calculation & Supporting Evidence
Confidential information has been removed from this worksheet
End