## Summary
Optimal timing of enabling works for Cable 2 - decision analysis
Background
CASE 1 - STANDARD DISCOUNT RATE AND NET BENEFIT FROM CABLE 2 OF $443M
Note:
| Expected net benefit of undertaking the enabling works for Cable 2 |  |  |  |  | The discount rate is 7%, which is AEMO's current approach. It is expected that this discount rate will be reduced to 3%, as per the draft IASR.
The expected benefit from Cable 2 reflects the RIT-T update published in July 2025.
Expected costs $m (PV, 2023 prices)
|  |  | Scenario 1 | Scenario 2 | Average
| Combined works |  | 384.0357 | 384.0357
| Separate works |  | 510.3518 | 610.7973
| Net benefit |  | 126.3161 | 226.7616 | 176.5389
CASE 2 - WITH CONCESSIONAL FINANCE AND NET BENEFIT FROM CABLE 2 OF $443M
Note:
| Expected net benefit of undertaking the enabling works for Cable 2 |  |  |  |  | The discount rate is 2.0%, which reflects an estimate of the concessional finance on a real pre-tax basis.
Expected costs $m (PV, 2023 prices)
|  |  | Scenario 1 | Scenario 2 | Average
| Combined works |  | 426.4867 | 426.4867
| Separate works |  | 647.1742 | 842.5116
| Net benefit |  | 220.6875 | 416.0249 | 318.3562
Description of scenarios
| Scenario 1: | Social license impacts cause a project delay of 2 years, if Cable 2 is required in either 2034 or 2038, in effect meaning that it is delivered in 2036 or 2040 instead and deferring the project benefits.
| Scenario 2: | Social license impacts result in Cable 2 being unable to be completed, causing a loss of project benefits in either 2034 or 2038 depending on when Cable 2 would be required.
Discussion of results and key assumptions
The 2024 ISP defines Stages 1 and 2 of Marinus Link as a single actionable ISP project. However, there is some uncertainty as to the optimal timing of Cable 2, and a possibility that it may not be required at all. The purpose of this spreadsheet is to assess whether the enabling works for Cable 2 should be included in MLPL's construction costs for Stage 1 of the project. This is an update to the analysis previously provided to the AER as an appendix to Attachment 3 of the revised Revenue Proposal. In response to AER Information Request #007, MLPL has concluded that the scope of the repeated costs for Stage 2 works is lower than indicated in the spreadsheet that was submitted as part of our revised Revenue Proposal. This spreadsheet complements MLPL's written response to the AER on Information Request #007, which was submitted on 8 September 2025,
The works include:
(a) Balance of works (BoW), principally the land cable civil works
(b) Landfall Horizontal Direct Drilling (LHDD) works
Undertaking the BoW and LHDD works for both cables together results in lower total project costs, because there are fixed set up and mobilisation costs that can be avoided by completing the works together. However. there is also a risk that Cable 2 may not be required, in which case the enabling works could have been avoided. As the BoW and LHDD works also involve disruption to landusers, additional disruption costs may be avoided if the works are undertaken together. In fact, MLPL's view is that landusers may react very negatively to a second period of disruption, leading to project delay or cancellation.
The analysis assesses the net benefit of undertaking the enabling works, assuming the following probabilities: (a) a 20% that Cable will not proceed; (b) a 40% probability that it will be required in 2034; and (c) a 40% probability that it will be required in 2038. We examined two cases, one using the standard discount rate assumptions and the other using concessional finance. We have also considered two scenarios for each case, as explained below. All data is shown in 2023 prices.
1. We have reported the net benefit for undertaking the enabling works for Cable 2. The average net benefit of bringing forward the expenditure is $176.5m in Case 1 and $318.4m in Case 2. On that basis, it is appropriate to bring forward the enabling expenditure (consistent with MLPL's Revenue Proposal). The probability of Cable 2 not being required would need to be 72.2% or higher in Case 1 (averaged across the two scenarios) and 80.4% in Case 2 in order to justify undertaking the works separately. As Cable 2 is expected to provide a net market benefit of $443m, it is appropriate that the enabling works should proceed. These net benefits are obtained from enabling works totalling $107.8m in 2023 prices, which means that there is a compelling case for proceeding with the enabling works.
2. The assumptions in the analysis presented are 'conservative' in the sense that they are likely to understate the benefits of undertaking the enabling works for Cable 2, including:
(a) We have not assumed any cost increase in real terms if the works for Cable 2 are undertaken later. In practice, however, it is likely that the Cable 2 works would be substantially higher both in relation to ordinary cost escalation (above CPI), but also to address the safety risks associated with civil works being conducted close to a live cable. It is highly likely that increased easement sizes and safety-related costs would arise if the work were undertaken separately.
(b) We have adopted relatively modest assumptions regarding disruption/stakeholder management costs.
(c) The analysis allows for project delays without any consequential impact on the total project costs.
(d) No allowance has been made in relation to the impact of separating the Cable 2 works on MLPL's environmental approvals. This cost impact could be highly significant.
(e) We have not increased the net benefits from Cable 2 that would result from adopting a discount rate consistent with concessional finance. Concessional finance has only been applied in relation to the cost benefit analysis, but adopting the same net benefits from Cable 2 as $443 million.
These conservative assumptions suggest that the case for undertaking the enabling works for Cable 2 will be substantially higher than indicated here.
4. We have apportioned the delay and project cancellation costs between the LCC and LHDD works on a 50/50 basis. However, this approach is only appropriate if both works are either undertaken or not undertaken. To consider whether only one element should be brought forward, the analysis would need to be updated to attribute the total delay or cancellation costs to each case. This is because the delay or project cancellation costs could be caused if either category of enabling work is not undertaken.

## CASE 1_BoW
Balance of Works (BoW)
SCENARIOS 1 AND 2 RESULTS - BoW COSTS
Results Summary - Scenario 1 - BoW Costs | [6 empty] | Calculation of social license (delay) costs |  |  |  |  | $m
Social license issues cause a 2 year project delay | [6 empty] | Assumed net benefit of Cable 2, if it proceeds (PV 2025) |  |  |  |  | 443
| Cable installation option |  | Probability of
| A. Together | B. Separate | this outcome |  | Break even probability |  | Economic life of cable 2 (years) |  |  |  |  | 40
BoW costs if Cable 2 is not required | 265.6643 | 217.9272 | 20% |  | 72.22% |  | Discount rate |  |  |  |  | 7%
BoW costs if Cable 2 is required in 2034 | 265.6643 | 397.398 | 40% |  |  |  | Annuity of Cable 2 net benefit |  |  |  |  | 33.229
BoW costs if Cable 2 is required in 2038 | 265.6643 | 354.8446 | 40%
Expected cost | 265.6643 | 344.4825 |  |  |  |  | Deferral period (years) |  |  |  |  | 2
PV cost saving if Cable 1 and 2 BoW works are undertaken together | 78.8182
Results Summary - Scenario 2- BoW Costs | [6 empty] | Costs of enabling works |  |  | 56.3
Social license issues result in Cable 2 not proceeding | [6 empty] | Notes:
| Cable installation option |  | Probability of |  |  |  | The net benefit from Cable 2 is $443m, which reflects the latest delphi weighted average
| A. Together | B. Separate | this outcome
BoW costs if Cable 2 is not required | 265.6643 | 217.9272 | 20% |  |  |  | The analysis also recognises that cable 2 may not proceed, in which case the net benefit would be zero or negative.
BoW costs if Cable 2 is required in 2034 | 265.6643 | 505.253 | 40%
BoW costs if Cable 2 is required in 2038 | 265.6643 | 437.1267 | 40% |  |  |  | Probability that Cable 2 does not proceed |  |  |  | 20%
Expected cost | 265.6643 | 420.5373
PV cost saving if Cable 1 and 2 BoW works are undertaken together | 154.8731
Cash flow details: Cable 2 decision in 2034
Social license issues cause a 2 year project delay
Discount rate = | 7% | real, pre-tax
Option a (Both cables together) |  | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | 2031 | 2032 | 2033 | 2034 | 2035 | 2036 | 2037 | 2038 | 2039 | 2040
| t= | 0 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
PV
BoW costs if Cable 2 is not justified* | 265.6643 | real, pre-tax 2025 0: 0; real, pre-tax 2026 1: 14.1792; real, pre-tax 2027 2: 144.2227; real, pre-tax 2028 3: 154.8982
PV
BoW costs if cable 2 is required in 2034 | 265.6643 | real, pre-tax 2025 0: 0; real, pre-tax 2026 1: 14.1792; real, pre-tax 2027 2: 144.2227; real, pre-tax 2028 3: 154.8982
Notes:
* Data from capex model
Option b (Separate cable works) |  | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | 2031 | 2032 | 2033 | 2034 | 2035 | 2036 | 2037 | 2038 | 2039 | 2040
| t= | 0 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
PV
BoW costs if Cable 2 is not justified* | 217.9272 | 2025 0: 0; 2026 1: 11.6457; 2027 2: 118.3247; 2028 3: 127.0297
PV
BoW costs if Cable 2 is required in 2034, but is delayed 2 years** |  | 2025 0: 0; 2026 1: 11.6457; 2027 2: 118.3247; 2028 3: 127.0297; 2031 6: 11.6457; 2032 7: 118.3247; 2033 8: 127.0297
Disruption/stakeholder management costs*** |  | 2025 0: 0; 2026 1: 0; 2027 2: 0; 2028 3: 0; 2029 4: 0; 2030 5: 3; 2031 6: 3; 2032 7: 3; 2033 8: 3
Delay costs (2 years) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16.6145 | 16.6145
BoW total costs if cable 2 is required in 2034 | 397.398 | 0 | 11.6457 | 118.3247 | 127.0297 | 0 | 3 | 14.6457 | 121.3247 | 130.0297 | 0 | 16.6145 | 16.6145
Notes:
* Data derived from capex model
**For cable 2, the completion of the land cable civil works leads to a delay in project completion
*** We have included some disruption/stakeholder management costs, but otherwise assumed that the costs are unchanged from cable 1 works. These costs include working with landusers and the affected communities.
Cash flow details: Cable 2 decision in 2034
Social license costs result in Cable 2 not proceeding
Discount rate = | 7% | 2025 0: real, pre-tax
Option a (Both cables together) |  | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | 2031 | 2032 | 2033 | 2034 | 2035 | 2036 | 2037 | 2038 | 2039 | 2040
| t= | 0 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
PV
BoW costs if Cable 2 is not justified* | 265.6643 | real, pre-tax 2025 0: 0; real, pre-tax 2026 1: 14.1792; real, pre-tax 2027 2: 144.2227; real, pre-tax 2028 3: 154.8982
PV
BoW costs if cable 2 is required in 2034* | 265.6643 | real, pre-tax 2025 0: 0; real, pre-tax 2026 1: 14.1792; real, pre-tax 2027 2: 144.2227; real, pre-tax 2028 3: 154.8982
Notes:
* Data from capex model, Total Cost Sum', row 171.
Option b (Separate cable works) |  | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | 2031 | 2032 | 2033 | 2034 | 2035 | 2036 | 2037 | 2038 | 2039 | 2040
| t= | 0 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
PV
BoW costs if Cable 2 is not justified* | 217.9272 | 2025 0: 0; 2026 1: 11.6457; 2027 2: 118.3247; 2028 3: 127.0297
PV
BoW costs if cable 2 is required in 2034, but cannot proceed** |  | 0 | 11.6457 | 118.3247 | 127.0297 | 0 | 0 | 11.6457 | 118.3247 | 127.0297 | 0
Disruption/stakeholder management costs |  | 0 | 0 | 0 | 0 | 0 | 5 | 5 | 5 | 2.5 | 0
Loss of project benefits, as project does not proceed |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 221.5
BoW costs if cable 2 is required in 2034 | 505.253 | 0 | 11.6457 | 118.3247 | 127.0297 | 0 | 5 | 16.6457 | 123.3247 | 129.5297 | 221.5
Notes:
* Data derived from capex model
**For cable 2, we have included some costs of works in 2031, 2032 and 2033, but assume that it then becomes apparent that the project cannot proceed as a result of loss of social license (which is shared 50/50 with LHDD)
*** We have included some disruption/stakeholder management costs, but not beyond 2033. These costs include working with landusers and the affected communities.
Cash flow details: Cable 2 decision in 2038
Social license issues result in a 2 year project delay
Discount rate = | 7% | 2025 0: real, pre-tax
Option a (Both cables together) |  | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | 2031 | 2032 | 2033 | 2034 | 2035 | 2036 | 2037 | 2038 | 2039 | 2040
| t= | 0 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
PV
BoW costs if Cable 2 is not justified* | 265.6643 | real, pre-tax 2025 0: 0; real, pre-tax 2026 1: 14.1792; real, pre-tax 2027 2: 144.2227; real, pre-tax 2028 3: 154.8982
PV
BoW costs if cable 2 is required in 2038 | 265.6643 | real, pre-tax 2025 0: 0; real, pre-tax 2026 1: 14.1792; real, pre-tax 2027 2: 144.2227; real, pre-tax 2028 3: 154.8982
Notes:
* Data from capex model, Total Cost Sum', row 171.
Option b (Separate cable works) |  | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | 2031 | 2032 | 2033 | 2034 | 2035 | 2036 | 2037 | 2038 | 2039 | 2040 | 2041
| t= | 0 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16
PV
BoW costs if Cable 2 is not justified* | 217.9272 | 2025 0: 0; 2026 1: 11.6457; 2027 2: 118.3247; 2028 3: 127.0297
PV
BoW costs if Cable 2 is required in 2038, but is delayed 2 years** |  | 2025 0: 0; 2026 1: 11.6457; 2027 2: 118.3247; 2028 3: 127.0297; 2032 7: 0; 2033 8: 0; 2034 9: 0; 2035 10: 11.6457; 2036 11: 118.3247; 2037 12: 127.0297
Disruption/stakeholder management costs*** |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 3 | 3
Delay costs (2 years) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16.6145 | 16.6145
BoW total costs if cable 2 is required in 2038 | 354.8446 | 0 | 11.6457 | 118.3247 | 127.0297 | 0 | 0 | 0 | 0 | 0 | 3 | 14.6457 | 121.3247 | 130.0297 | 0 | 16.6145 | 16.6145
Notes:
* Data derived from capex model
**For cable 2, we have included social license costs in 2039 and 2040, as the project is expected to be delayed as a result of the negative impact on social license. The delay impact has been attributed 50/50 to the BoW and LHDD analysis.
The timing of the capex is also assumed to be delayed - it should have started 2 years earlier than shown in order to meet the 2038 timeframe.
*** We have included some disruption/stakeholder management costs, but otherwise assumed that the costs are unchanged from cable 1 works. These costs include working with landusers and the affected communities.
Cash flow details: Cable 2 decision in 2038
Social license issues result in Cable 2 not proceeding
Discount rate = | 7% | 2025 0: real, pre-tax
Option a (Both cables together) |  | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | 2031 | 2032 | 2033 | 2034 | 2035 | 2036 | 2037 | 2038 | 2039 | 2040
| t= | 0 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
PV
BoW costs if Cable 2 is not justified* | 265.6643 | real, pre-tax 2025 0: 0; real, pre-tax 2026 1: 14.1792; real, pre-tax 2027 2: 144.2227; real, pre-tax 2028 3: 154.8982
PV
BoW costs if cable 2 is required in 2038* | 265.6643 | real, pre-tax 2025 0: 0; real, pre-tax 2026 1: 14.1792; real, pre-tax 2027 2: 144.2227; real, pre-tax 2028 3: 154.8982
Notes:
* Data from capex model
Option b (Separate cable works) |  | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | 2031 | 2032 | 2033 | 2034 | 2035 | 2036 | 2037 | 2038 | 2039 | 2040
| t= | 0 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
PV
BoW costs if Cable 2 is not justified* | 217.9272 | 2025 0: 0; 2026 1: 11.6457; 2027 2: 118.3247; 2028 3: 127.0297
PV
BoW costs if cable 2 is required in 2038, but cannot proceed** |  | 0 | 11.6457 | 118.3247 | 127.0297 | 0 | 0 | 0 | 0 | 0 | 0 | 11.6457 | 118.3247 | 127.0297 | 0
Disruption/stakeholder management costs*** |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 5 | 5 | 2.5 | 0
Loss of project benefits, as project does not proceed |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 221.5
BoW costs if cable 2 is required in 2038 | 437.1267 | 0 | 11.6457 | 118.3247 | 127.0297 | 0 | 0 | 0 | 0 | 0 | 5 | 16.6457 | 123.3247 | 129.5297 | 221.5
Notes:
* Data derived from capex model
**For cable 2, we have included costs of works in 2035, 2036 and 2037, but assume that it then becomes apparent that the project cannot proceed as a result of loss of social license (shared 50/50 with LHDD).
*** We have included higher disruption/stakeholder management costs, but not beyond 2037. These costs include working with landusers and the affected communities.

## CASE 1_LHDD
Landfall Horizontal Direct Drilling (LHDD) works
SCENARIOS 1 AND 2 RESULTS LHDD COSTS
Results Summary - Scenario 1 - LHDD Costs | [6 empty] | Calculation of social license (delay) costs |  |  |  |  | $m
Social license cause a 2 year project delay | [6 empty] | Assumed net benefit of Cable 2, if it proceeds (PV 2025) |  |  |  |  | 443
| Cable installation option |  | Probability of
| A. Together | B. Separate | this outcome |  |  |  | Economic life of cable 2 (years) |  |  |  |  | 40
LHDD costs if Cable 2 is not required | 118.3714 | 72.2066 | 20% |  |  |  | Discount rate |  |  |  |  | 7%
LHDD costs if Cable 2 is required in 2034 | 118.3714 | 139.0753 | 40% |  |  |  | Annuity of Cable 2 net benefit |  |  |  |  | 33.229
LHDD costs if Cable 2 is required in 2038 | 118.3714 | 239.4948 | 40%
Expected cost | 118.3714 | 165.8694 |  |  |  |  | Deferral period (years) |  |  |  |  | 2
PV cost saving if Cable 1 and 2 LHDD works are undertaken together | 47.4979
Results Summary - Scenario 2 - LHDD Costs
Social license issues result in Cable 2 not proceeding
| Cable installation option |  | Probability of |  |  |  | Notes:
| A. Together | B. Separate | this outcome |  |  |  | The net benefit of cable 2 of $443m in present value terms is the assumed net benefit if the project proceeds. We have apportioned these costs on a 50/50 basis between the BoW analysis and the LHDD analysis
LHDD costs if Cable 2 is not required | 118.3714 | 72.2066 | 20%
LHDD costs if Cable 2 is required in 2034 | 118.3714 | 239.4948 | 40% |  |  |  | It is important to note that this is the assumed net benefit if Cable 2 proceeds, we also consider the possibilty that the net benefit is negative and the project does not proceed.
LHDD costs if Cable 2 is required in 2038 | 118.3714 | 200.052 | 40%
Expected cost | 118.3714 | 190.26
PV cost saving if Cable 1 and 2 LHDD works are undertaken together | 71.8886
Cash flow details: Cable 2 decision in 2034
Social license issues cause a 2 year project delay
Discount rate = | 7% | real, pre-tax
Option a (Both cables together) |  | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | 2031 | 2032 | 2033 | 2034 | 2035 | 2036 | 2037 | 2038 | 2039 | 2040
| t= | 0 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
PV
LHDD costs if Cable 2 is not justified* | 118.3714 | real, pre-tax 2025 0: 19.0086; real, pre-tax 2026 1: 15.3064; real, pre-tax 2027 2: 89.2495; real, pre-tax 2028 3: 8.7025
PV
LHDD costs if Cable 2 is required in 2034 | 118.3714 | real, pre-tax 2025 0: 19.0086; real, pre-tax 2026 1: 15.3064; real, pre-tax 2027 2: 89.2495; real, pre-tax 2028 3: 8.7025
Notes:
* Data from capex model.
Option b (Separate cable works) |  | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | 2031 | 2032 | 2033 | 2034 | 2035 | 2036 | 2037 | 2038 | 2039 | 2040
| t= | 0 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
PV
LHDD costs if Cable 2 is not justified* | 72.2066 | 2025 0: 11.5952; 2026 1: 9.3369; 2027 2: 54.4422; 2028 3: 5.3085
PV
LHDD costs if cable 2 is required in 2034, but is delayed 2 years** |  | 11.5952 | 9.3369 | 54.4422 | 5.3085 | 0 | 0 | 11.5952 | 9.3369 | 54.4422 | 5.3085 | 0 | 0
Disruption/stakeholder management costs*** |  | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0
Delay costs (2 years) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16.6145 | 16.6145
LHDD total costs if cable 2 is required in 2034 | 139.0753 | 11.5952 | 9.3369 | 54.4422 | 5.3085 | 0 | 0 | 12.5952 | 10.3369 | 55.4422 | 6.3085 | 16.6145 | 16.6145
Notes:
* Data from capex model.
**For Cable 2, we have included social license costs in 2035 and 2036, as the project is expected to be delayed as a result of the negative impact on social license (total delay costs are attributed 50/50 to the BoW and LHDD analysis).
The timing of the capex is also assumed to be delayed - it should have started 2 years earlier than shown in order to meet the 2034 timeframe.
*** We have included some disruption/stakeholder management costs, but otherwise assumed that the costs are unchanged from cable 1 works. These costs include working with landusers and the affected communities.
Cash flow details: Cable 2 decision in 2034
Social license costs result in Cable 2 not proceeding
Discount rate = | 7% | 2025 0: real, pre-tax
Option a (Both cables together) |  | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | 2031 | 2032 | 2033 | 2034 | 2035 | 2036 | 2037 | 2038 | 2039 | 2040
| t= | 0 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
PV
LHDD costs if Cable 2 is not justified | 118.3714 | real, pre-tax 2025 0: 19.0086; real, pre-tax 2026 1: 15.3064; real, pre-tax 2027 2: 89.2495; real, pre-tax 2028 3: 8.7025
PV
LHDD costs if Cable 2 is required in 2034 | 118.3714 | real, pre-tax 2025 0: 19.0086; real, pre-tax 2026 1: 15.3064; real, pre-tax 2027 2: 89.2495; real, pre-tax 2028 3: 8.7025
Notes:
* Data from capex model, 'Total cost sum' tab, row 204.
Option b (Separate cable works) |  | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | 2031 | 2032 | 2033 | 2034 | 2035 | 2036 | 2037 | 2038 | 2039 | 2040
| t= | 0 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
PV
LHDD costs if Cable 2 is not justified* | 72.2066 | 2025 0: 11.5952; 2026 1: 9.3369; 2027 2: 54.4422; 2028 3: 5.3085
PV
LHDD costs if Cable 2 is required in 2034, but cannot proceed** |  | 11.5952 | 9.3369 | 54.4422 | 5.3085 | 0 | 0 | 11.5952 | 9.3369 | 54.4422 | 0
Disruption/stakeholder management costs |  | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0.5 | 0
Loss of project benefits, as project does not proceed |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 221.5
LHDD costs if Cable 2 is required in 2034 | 239.4948 | 11.5952 | 9.3369 | 54.4422 | 5.3085 | 0 | 0 | 12.5952 | 10.3369 | 54.9422 | 221.5
Notes:
* Data from capex model.
**For cable 2, we have included costs of works to 2033, but in 2034 it becomes apparent that the project cannot proceed as a result of loss of social license.
*** We have included some disruption/stakeholder management costs, but otherwise assumed that the costs are unchanged from cable 1 works. These costs include working with landusers and the affected communities.
Cash flow details: Cable 2 decision in 2038
Social license results in a 2 year project delay
Discount rate = | 7% | 2025 0: real, pre-tax
Option a (Both cables together) |  | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | 2031 | 2032 | 2033 | 2034 | 2035 | 2036 | 2037 | 2038 | 2039 | 2040
| t= | 0 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
PV
LHDD costs if Cable 2 is not justified* | 118.3714 | real, pre-tax 2025 0: 19.0086; real, pre-tax 2026 1: 15.3064; real, pre-tax 2027 2: 89.2495; real, pre-tax 2028 3: 8.7025
PV
LHDD costs if Cable 2 is required by 2038 | 118.3714 | real, pre-tax 2025 0: 19.0086; real, pre-tax 2026 1: 15.3064; real, pre-tax 2027 2: 89.2495; real, pre-tax 2028 3: 8.7025
Notes:
* Data from capex model.
Option b (Separate cable works) |  | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | 2031 | 2032 | 2033 | 2034 | 2035 | 2036 | 2037 | 2038 | 2039 | 2040
| t= | 0 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
PV
LHDD costs if Cable 2 is not justified* | 72.2066 | 2025 0: 11.5952; 2026 1: 9.3369; 2027 2: 54.4422; 2028 3: 5.3085
PV
LHDD costs if cable 2 is required in 2038, but is delayed by 2 years** |  | 11.5952 | 9.3369 | 54.4422 | 5.3085 | 0 | 0 | 0 | 0 | 0 | 0 | 11.5952 | 9.3369 | 54.4422 | 5.3085 | 0 | 0
Disruption/stakeholder management costs*** |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0
Delay costs (2 years) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16.6145 | 16.6145
LHDD total costs if cable 2 is required in 2038 | 123.2204 | 11.5952 | 9.3369 | 54.4422 | 5.3085 | 0 | 0 | 0 | 0 | 0 | 0 | 12.5952 | 10.3369 | 55.4422 | 6.3085 | 16.6145 | 16.6145
Notes:
* Data from capex model, 'Dashboard' tab, cell H63.
**For Cable 2, we have included social license costs in 2039 and 2040, as the project is expected to be delayed as a result of the negative impact on social license (total delay costs are attributed 50/50 to the BoW and LHDD analysis).
The timing of the capex is also assumed to be delayed - it should have started 2 years earlier than shown in order to meet the 2038 timeframe.
*** We have included some disruption/stakeholder management costs, but otherwise assumed that the costs are unchanged from cable 1 works. These costs include working with landusers and the affected communities.
Cash flow details: Cable 2 decision in 2038
Social license costs result in Cable 2 not proceeding
Discount rate = | 7% | 2025 0: real, pre-tax
Option a (Both cables together) |  | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | 2031 | 2032 | 2033 | 2034 | 2035 | 2036 | 2037 | 2038 | 2039 | 2040
| t= | 0 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
PV
LHDD costs if Cable 2 is not justified | 118.3714 | real, pre-tax 2025 0: 19.0086; real, pre-tax 2026 1: 15.3064; real, pre-tax 2027 2: 89.2495; real, pre-tax 2028 3: 8.7025
PV
LHDD costs if Cable 2 is required by 2038 | 118.3714 | real, pre-tax 2025 0: 19.0086; real, pre-tax 2026 1: 15.3064; real, pre-tax 2027 2: 89.2495; real, pre-tax 2028 3: 8.7025
Notes:
* Data from capex model.
Option b (Separate cable works) |  | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | 2031 | 2032 | 2033 | 2034 | 2035 | 2036 | 2037 | 2038 | 2039 | 2040
| t= | 0 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
PV
LHDD costs if Cable 2 is not justified* | 72.2066 | 2025 0: 11.5952; 2026 1: 9.3369; 2027 2: 54.4422; 2028 3: 5.3085
PV
LHDD costs if Cable 2 is required in 2038, but cannot proceed** |  | 11.5952 | 9.3369 | 54.4422 | 5.3085 | 0 | 0 | 0 | 0 | 0 | 0 | 11.5952 | 9.3369 | 54.4422 | 0
Disruption/stakeholder management costs |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0
Loss of project benefits, as project does not proceed |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 221.5
LHDD costs if Cable 2 is required in 2038 | 200.052 | 11.5952 | 9.3369 | 54.4422 | 5.3085 | 0 | 0 | 0 | 0 | 0 | 0 | 12.5952 | 10.3369 | 55.4422 | 221.5
Notes:
* Data from capex model.
**For cable 2, we have included costs of works in 2037 and 2038, but in 2039 it becomes apparent that the project cannot proceed as a result of loss of social license.
*** We have included some disruption/stakeholder management costs, but otherwise assumed that the costs are unchanged from cable 1 works. These costs include working with landusers and the affected communities.

## CASE 2_BoW
Balance of Works (BoW)
SCENARIOS 1 AND 2 RESULTS - BoW COSTS
Results Summary - Scenario 1 - BoW Costs | [6 empty] | Calculation of social license (delay) costs |  |  |  |  | $m
Social license issues cause a 2 year project delay | [6 empty] | Assumed net benefit of Cable 2, if it proceeds (PV 2025) |  |  |  |  | 443
| Cable installation option |  | Probability of
| A. Together | B. Separate | this outcome |  | Break even probability |  | Economic life of cable 2 (years) |  |  |  |  | 40
BoW costs if Cable 2 is not required | 298.4875 | 244.8502 | 20% |  | 80.36% |  | Discount rate |  |  |  |  | 2%
BoW costs if Cable 2 is required in 2034 | 298.4875 | 490.3264 | 40% |  |  |  | Annuity of Cable 2 net benefit |  |  |  |  | 16.1942
BoW costs if Cable 2 is required in 2038 | 298.4875 | 471.6323 | 40%
Expected cost | 298.4875 | 433.7535 |  |  |  |  | Deferral period (years) |  |  |  |  | 2
PV cost saving if Cable 1 and 2 BoW works are undertaken together | 135.2661
Results Summary - Scenario 2- BoW Costs | [6 empty] | Costs of enabling works |  |  | 56.3
Social license issues result in Cable 2 not proceeding | [6 empty] | Notes:
| Cable installation option |  | Probability of |  |  |  | The net benefit from Cable 2 is $443m, which reflects the latest delphi weighted average
| A. Together | B. Separate | this outcome
BoW costs if Cable 2 is not required | 298.4875 | 244.8502 | 20% |  |  |  | The analysis also recognises that cable 2 may not proceed, in which case the net benefit would be zero or negative.
BoW costs if Cable 2 is required in 2034 | 298.4875 | 667.4149 | 40%
BoW costs if Cable 2 is required in 2038 | 298.4875 | 635.2346 | 40% |  |  |  | Probability that Cable 2 does not proceed |  |  |  | 20%
Expected cost | 298.4875 | 570.0298
PV cost saving if Cable 1 and 2 BoW works are undertaken together | 271.5424
Cash flow details: Cable 2 decision in 2034
Social license issues cause a 2 year project delay
Discount rate = | 2% | real, pre-tax
Option a (Both cables together) |  | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | 2031 | 2032 | 2033 | 2034 | 2035 | 2036 | 2037 | 2038 | 2039 | 2040
| t= | 0 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
PV
BoW costs if Cable 2 is not justified* | 298.4875 | real, pre-tax 2025 0: 0; real, pre-tax 2026 1: 14.1792; real, pre-tax 2027 2: 144.2227; real, pre-tax 2028 3: 154.8982
PV
BoW costs if cable 2 is required in 2034 | 298.4875 | real, pre-tax 2025 0: 0; real, pre-tax 2026 1: 14.1792; real, pre-tax 2027 2: 144.2227; real, pre-tax 2028 3: 154.8982
Notes:
* Data from capex model
Option b (Separate cable works) |  | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | 2031 | 2032 | 2033 | 2034 | 2035 | 2036 | 2037 | 2038 | 2039 | 2040
| t= | 0 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
PV
BoW costs if Cable 2 is not justified* | 244.8502 | 2025 0: 0; 2026 1: 11.6457; 2027 2: 118.3247; 2028 3: 127.0297
PV
BoW costs if Cable 2 is required in 2034, but is delayed 2 years** |  | 2025 0: 0; 2026 1: 11.6457; 2027 2: 118.3247; 2028 3: 127.0297; 2031 6: 11.6457; 2032 7: 118.3247; 2033 8: 127.0297
Disruption/stakeholder management costs*** |  | 2025 0: 0; 2026 1: 0; 2027 2: 0; 2028 3: 0; 2029 4: 0; 2030 5: 3; 2031 6: 3; 2032 7: 3; 2033 8: 3
Delay costs (2 years) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.0971 | 8.0971
BoW total costs if cable 2 is required in 2034 | 490.3264 | 0 | 11.6457 | 118.3247 | 127.0297 | 0 | 3 | 14.6457 | 121.3247 | 130.0297 | 0 | 8.0971 | 8.0971
Notes:
* Data derived from capex model
**For cable 2, the completion of the land cable civil works leads to a delay in project completion
*** We have included some disruption/stakeholder management costs, but otherwise assumed that the costs are unchanged from cable 1 works. These costs include working with landusers and the affected communities.
Cash flow details: Cable 2 decision in 2034
Social license costs result in Cable 2 not proceeding
Discount rate = | 2% | 2025 0: real, pre-tax
Option a (Both cables together) |  | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | 2031 | 2032 | 2033 | 2034 | 2035 | 2036 | 2037 | 2038 | 2039 | 2040
| t= | 0 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
PV
BoW costs if Cable 2 is not justified* | 298.4875 | real, pre-tax 2025 0: 0; real, pre-tax 2026 1: 14.1792; real, pre-tax 2027 2: 144.2227; real, pre-tax 2028 3: 154.8982
PV
BoW costs if cable 2 is required in 2034* | 298.4875 | real, pre-tax 2025 0: 0; real, pre-tax 2026 1: 14.1792; real, pre-tax 2027 2: 144.2227; real, pre-tax 2028 3: 154.8982
Notes:
* Data from capex model, Total Cost Sum', row 171.
Option b (Separate cable works) |  | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | 2031 | 2032 | 2033 | 2034 | 2035 | 2036 | 2037 | 2038 | 2039 | 2040
| t= | 0 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
PV
BoW costs if Cable 2 is not justified* | 244.8502 | 2025 0: 0; 2026 1: 11.6457; 2027 2: 118.3247; 2028 3: 127.0297
PV
BoW costs if cable 2 is required in 2034, but cannot proceed** |  | 0 | 11.6457 | 118.3247 | 127.0297 | 0 | 0 | 11.6457 | 118.3247 | 127.0297 | 0
Disruption/stakeholder management costs |  | 0 | 0 | 0 | 0 | 0 | 5 | 5 | 5 | 2.5 | 0
Loss of project benefits, as project does not proceed |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 221.5
BoW costs if cable 2 is required in 2034 | 667.4149 | 0 | 11.6457 | 118.3247 | 127.0297 | 0 | 5 | 16.6457 | 123.3247 | 129.5297 | 221.5
Notes:
* Data derived from capex model
**For cable 2, we have included some costs of works in 2031, 2032 and 2033, but assume that it then becomes apparent that the project cannot proceed as a result of loss of social license (which is shared 50/50 with LHDD)
*** We have included some disruption/stakeholder management costs, but not beyond 2033. These costs include working with landusers and the affected communities.
Cash flow details: Cable 2 decision in 2038
Social license issues result in a 2 year project delay
Discount rate = | 2% | 2025 0: real, pre-tax
Option a (Both cables together) |  | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | 2031 | 2032 | 2033 | 2034 | 2035 | 2036 | 2037 | 2038 | 2039 | 2040
| t= | 0 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
PV
BoW costs if Cable 2 is not justified* | 298.4875 | real, pre-tax 2025 0: 0; real, pre-tax 2026 1: 14.1792; real, pre-tax 2027 2: 144.2227; real, pre-tax 2028 3: 154.8982
PV
BoW costs if cable 2 is required in 2038 | 298.4875 | real, pre-tax 2025 0: 0; real, pre-tax 2026 1: 14.1792; real, pre-tax 2027 2: 144.2227; real, pre-tax 2028 3: 154.8982
Notes:
* Data from capex model, Total Cost Sum', row 171.
Option b (Separate cable works) |  | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | 2031 | 2032 | 2033 | 2034 | 2035 | 2036 | 2037 | 2038 | 2039 | 2040 | 2041
| t= | 0 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16
PV
BoW costs if Cable 2 is not justified* | 244.8502 | 2025 0: 0; 2026 1: 11.6457; 2027 2: 118.3247; 2028 3: 127.0297
PV
BoW costs if Cable 2 is required in 2038, but is delayed 2 years** |  | 2025 0: 0; 2026 1: 11.6457; 2027 2: 118.3247; 2028 3: 127.0297; 2032 7: 0; 2033 8: 0; 2034 9: 0; 2035 10: 11.6457; 2036 11: 118.3247; 2037 12: 127.0297
Disruption/stakeholder management costs*** |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 3 | 3
Delay costs (2 years) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.0971 | 8.0971
BoW total costs if cable 2 is required in 2038 | 471.6323 | 0 | 11.6457 | 118.3247 | 127.0297 | 0 | 0 | 0 | 0 | 0 | 3 | 14.6457 | 121.3247 | 130.0297 | 0 | 8.0971 | 8.0971
Notes:
* Data derived from capex model
**For cable 2, we have included social license costs in 2039 and 2040, as the project is expected to be delayed as a result of the negative impact on social license. The delay impact has been attributed 50/50 to the BoW and LHDD analysis.
The timing of the capex is also assumed to be delayed - it should have started 2 years earlier than shown in order to meet the 2038 timeframe.
*** We have included some disruption/stakeholder management costs, but otherwise assumed that the costs are unchanged from cable 1 works. These costs include working with landusers and the affected communities.
Cash flow details: Cable 2 decision in 2038
Social license issues result in Cable 2 not proceeding
Discount rate = | 2% | 2025 0: real, pre-tax
Option a (Both cables together) |  | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | 2031 | 2032 | 2033 | 2034 | 2035 | 2036 | 2037 | 2038 | 2039 | 2040
| t= | 0 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
PV
BoW costs if Cable 2 is not justified* | 298.4875 | real, pre-tax 2025 0: 0; real, pre-tax 2026 1: 14.1792; real, pre-tax 2027 2: 144.2227; real, pre-tax 2028 3: 154.8982
PV
BoW costs if cable 2 is required in 2038* | 298.4875 | real, pre-tax 2025 0: 0; real, pre-tax 2026 1: 14.1792; real, pre-tax 2027 2: 144.2227; real, pre-tax 2028 3: 154.8982
Notes:
* Data from capex model
Option b (Separate cable works) |  | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | 2031 | 2032 | 2033 | 2034 | 2035 | 2036 | 2037 | 2038 | 2039 | 2040
| t= | 0 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
PV
BoW costs if Cable 2 is not justified* | 244.8502 | 2025 0: 0; 2026 1: 11.6457; 2027 2: 118.3247; 2028 3: 127.0297
PV
BoW costs if cable 2 is required in 2038, but cannot proceed** |  | 0 | 11.6457 | 118.3247 | 127.0297 | 0 | 0 | 0 | 0 | 0 | 0 | 11.6457 | 118.3247 | 127.0297 | 0
Disruption/stakeholder management costs*** |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 5 | 5 | 2.5 | 0
Loss of project benefits, as project does not proceed |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 221.5
BoW costs if cable 2 is required in 2038 | 635.2346 | 0 | 11.6457 | 118.3247 | 127.0297 | 0 | 0 | 0 | 0 | 0 | 5 | 16.6457 | 123.3247 | 129.5297 | 221.5
Notes:
* Data derived from capex model
**For cable 2, we have included costs of works in 2035, 2036 and 2037, but assume that it then becomes apparent that the project cannot proceed as a result of loss of social license (shared 50/50 with LHDD).
*** We have included higher disruption/stakeholder management costs, but not beyond 2037. These costs include working with landusers and the affected communities.

## CASE 2_LHDD
Landfall Horizontal Direct Drilling (LHDD) works
SCENARIOS 1 AND 2 RESULTS LHDD COSTS
Results Summary - Scenario 1 - LHDD Costs | [6 empty] | Calculation of social license (delay) costs |  |  |  |  | $m
Social license cause a 2 year project delay | [6 empty] | Assumed net benefit of Cable 2, if it proceeds (PV in 2025) |  |  |  |  | 443
| Cable installation option |  | Probability of
| A. Together | B. Separate | this outcome |  |  |  | Economic life of cable 2 (years) |  |  |  |  | 40
LHDD costs if Cable 2 is not required | 127.9993 | 78.0796 | 20% |  |  |  | Discount rate |  |  |  |  | 2%
LHDD costs if Cable 2 is required in 2034 | 127.9993 | 164.0154 | 40% |  |  |  | Annuity of Cable 2 net benefit |  |  |  |  | 16.1942
LHDD costs if Cable 2 is required in 2038 | 127.9993 | 330.4966 | 40%
Expected cost | 127.9993 | 213.4207 |  |  |  |  | Deferral period (years) |  |  |  |  | 2
PV cost saving if Cable 1 and 2 LHDD works are undertaken together | 85.4214
Results Summary - Scenario 2 - LHDD Costs
Social license issues result in Cable 2 not proceeding | [6 empty] | Notes:
| Cable installation option |  | Probability of |  |  |  | The net benefit from Cable 2 is $443m, which reflects the latest delphi weighted average.
| A. Together | B. Separate | this outcome
LHDD costs if Cable 2 is not required | 127.9993 | 78.0796 | 20%
LHDD costs if Cable 2 is required in 2034 | 127.9993 | 330.4966 | 40% |  |  |  | The discount rate is reduced to 2.0%, which is an estimate of the concessional finance on a real pre-tax basis.
LHDD costs if Cable 2 is required in 2038 | 127.9993 | 311.6681 | 40%
Expected cost | 127.9993 | 272.4818
PV cost saving if Cable 1 and 2 LHDD works are undertaken together | 144.4825
Cash flow details: Cable 2 decision in 2034
Social license issues cause a 2 year project delay
Discount rate = | 2% | real, pre-tax
Option a (Both cables together) |  | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | 2031 | 2032 | 2033 | 2034 | 2035 | 2036 | 2037 | 2038 | 2039 | 2040
| t= | 0 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
PV
LHDD costs if Cable 2 is not justified* | 127.9993 | real, pre-tax 2025 0: 19.0086; real, pre-tax 2026 1: 15.3064; real, pre-tax 2027 2: 89.2495; real, pre-tax 2028 3: 8.7025
PV
LHDD costs if Cable 2 is required in 2034 | 127.9993 | real, pre-tax 2025 0: 19.0086; real, pre-tax 2026 1: 15.3064; real, pre-tax 2027 2: 89.2495; real, pre-tax 2028 3: 8.7025
Notes:
* Data from capex model
Option b (Separate cable works) |  | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | 2031 | 2032 | 2033 | 2034 | 2035 | 2036 | 2037 | 2038 | 2039 | 2040
| t= | 0 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
PV
LHDD costs if Cable 2 is not justified* | 78.0796 | 2025 0: 11.5952; 2026 1: 9.3369; 2027 2: 54.4422; 2028 3: 5.3085
PV
LHDD costs if cable 2 is required in 2034, but is delayed 2 years** |  | 11.5952 | 9.3369 | 54.4422 | 5.3085 | 0 | 0 | 11.5952 | 9.3369 | 54.4422 | 5.3085 | 0 | 0
Disruption/stakeholder management costs*** |  | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0
Delay costs (2 years) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.0971 | 8.0971
LHDD total costs if cable 2 is required in 2034 | 164.0154 | 11.5952 | 9.3369 | 54.4422 | 5.3085 | 0 | 0 | 12.5952 | 10.3369 | 55.4422 | 6.3085 | 8.0971 | 8.0971
Notes:
* Data from capex model.
**For Cable 2, we have included social license costs in 2035 and 2036, as the project is expected to be delayed as a result of the negative impact on social license (total delay costs are attributed 50/50 to the BoW and LHDD analysis).
The timing of the capex is also assumed to be delayed - it should have started 2 years earlier than shown in order to meet the 2034 timeframe.
*** We have included some disruption/stakeholder management costs, but otherwise assumed that the costs are unchanged from cable 1 works. These costs include working with landusers and the affected communities.
Cash flow details: Cable 2 decision in 2034
Social license costs result in Cable 2 not proceeding
Discount rate = | 2% | 2025 0: real, pre-tax
Option a (Both cables together) |  | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | 2031 | 2032 | 2033 | 2034 | 2035 | 2036 | 2037 | 2038 | 2039 | 2040
| t= | 0 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
PV
LHDD costs if Cable 2 is not justified | 127.9993 | real, pre-tax 2025 0: 19.0086; real, pre-tax 2026 1: 15.3064; real, pre-tax 2027 2: 89.2495; real, pre-tax 2028 3: 8.7025
PV
LHDD costs if Cable 2 is required in 2034 | 127.9993 | real, pre-tax 2025 0: 19.0086; real, pre-tax 2026 1: 15.3064; real, pre-tax 2027 2: 89.2495; real, pre-tax 2028 3: 8.7025
Notes:
* Data from capex model.
Option b (Separate cable works) |  | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | 2031 | 2032 | 2033 | 2034 | 2035 | 2036 | 2037 | 2038 | 2039 | 2040
| t= | 0 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
PV
LHDD costs if Cable 2 is not justified* | 78.0796 | 2025 0: 11.5952; 2026 1: 9.3369; 2027 2: 54.4422; 2028 3: 5.3085
PV
LHDD costs if Cable 2 is required in 2034, but cannot proceed** |  | 11.5952 | 9.3369 | 54.4422 | 5.3085 | 0 | 0 | 11.5952 | 9.3369 | 54.4422 | 0
Disruption/stakeholder management costs |  | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0.5 | 0
Loss of project benefits, as project does not proceed |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 221.5
LHDD costs if Cable 2 is required in 2034 | 330.4966 | 11.5952 | 9.3369 | 54.4422 | 5.3085 | 0 | 0 | 12.5952 | 10.3369 | 54.9422 | 221.5
Notes:
* Data from capex model.
**For cable 2, we have included costs of works to 2033, but in 2034 it becomes apparent that the project cannot proceed as a result of loss of social license.
*** We have included some disruption/stakeholder management costs, but otherwise assumed that the costs are unchanged from cable 1 works. These costs include working with landusers and the affected communities.
Cash flow details: Cable 2 decision in 2038
Social license results in a 2 year project delay
Discount rate = | 2% | 2025 0: real, pre-tax
Option a (Both cables together) |  | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | 2031 | 2032 | 2033 | 2034 | 2035 | 2036 | 2037 | 2038 | 2039 | 2040
| t= | 0 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
PV
LHDD costs if Cable 2 is not justified* | 127.9993 | real, pre-tax 2025 0: 19.0086; real, pre-tax 2026 1: 15.3064; real, pre-tax 2027 2: 89.2495; real, pre-tax 2028 3: 8.7025
PV
LHDD costs if Cable 2 is required by 2038 | 127.9993 | real, pre-tax 2025 0: 19.0086; real, pre-tax 2026 1: 15.3064; real, pre-tax 2027 2: 89.2495; real, pre-tax 2028 3: 8.7025
Notes:
* Data from capex model, 'Total cost sum' tab, row 204.
Option b (Separate cable works) |  | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | 2031 | 2032 | 2033 | 2034 | 2035 | 2036 | 2037 | 2038 | 2039 | 2040
| t= | 0 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
PV
LHDD costs if Cable 2 is not justified* | 78.0796 | 2025 0: 11.5952; 2026 1: 9.3369; 2027 2: 54.4422; 2028 3: 5.3085
PV
LHDD costs if cable 2 is required in 2038, but is delayed by 2 years** |  | 11.5952 | 9.3369 | 54.4422 | 5.3085 | 0 | 0 | 0 | 0 | 0 | 0 | 11.5952 | 9.3369 | 54.4422 | 5.3085 | 0 | 0
Disruption/stakeholder management costs*** |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0
Delay costs (2 years) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.0971 | 8.0971
LHDD total costs if cable 2 is required in 2038 | 157.471 | 11.5952 | 9.3369 | 54.4422 | 5.3085 | 0 | 0 | 0 | 0 | 0 | 0 | 12.5952 | 10.3369 | 55.4422 | 6.3085 | 8.0971 | 8.0971
Notes:
* Data from capex model.
**For Cable 2, we have included social license costs in 2039 and 2040, as the project is expected to be delayed as a result of the negative impact on social license (total delay costs are attributed 50/50 to the BoW and LHDD analysis).
The timing of the capex is also assumed to be delayed - it should have started 2 years earlier than shown in order to meet the 2038 timeframe.
*** We have included some disruption/stakeholder management costs, but otherwise assumed that the costs are unchanged from cable 1 works. These costs include working with landusers and the affected communities.
Cash flow details: Cable 2 decision in 2038
Social license costs result in Cable 2 not proceeding
Discount rate = | 2% | 2025 0: real, pre-tax
Option a (Both cables together) |  | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | 2031 | 2032 | 2033 | 2034 | 2035 | 2036 | 2037 | 2038 | 2039 | 2040
| t= | 0 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
PV
LHDD costs if Cable 2 is not justified | 127.9993 | real, pre-tax 2025 0: 19.0086; real, pre-tax 2026 1: 15.3064; real, pre-tax 2027 2: 89.2495; real, pre-tax 2028 3: 8.7025
PV
LHDD costs if Cable 2 is required by 2038 | 127.9993 | real, pre-tax 2025 0: 19.0086; real, pre-tax 2026 1: 15.3064; real, pre-tax 2027 2: 89.2495; real, pre-tax 2028 3: 8.7025
Notes:
* Data from capex model.
Option b (Separate cable works) |  | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | 2031 | 2032 | 2033 | 2034 | 2035 | 2036 | 2037 | 2038 | 2039 | 2040
| t= | 0 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
PV
LHDD costs if Cable 2 is not justified* | 78.0796 | 2025 0: 11.5952; 2026 1: 9.3369; 2027 2: 54.4422; 2028 3: 5.3085
PV
LHDD costs if Cable 2 is required in 2038, but cannot proceed** |  | 11.5952 | 9.3369 | 54.4422 | 5.3085 | 0 | 0 | 0 | 0 | 0 | 0 | 11.5952 | 9.3369 | 54.4422 | 0
Disruption/stakeholder management costs |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0
Loss of project benefits, as project does not proceed |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 221.5
LHDD costs if Cable 2 is required in 2038 | 311.6681 | 11.5952 | 9.3369 | 54.4422 | 5.3085 | 0 | 0 | 0 | 0 | 0 | 0 | 12.5952 | 10.3369 | 55.4422 | 221.5
Notes:
* Data from capex model.
**For cable 2, we have included costs of works in 2037 and 2038, but in 2039 it becomes apparent that the project cannot proceed as a result of loss of social license.
*** We have included some disruption/stakeholder management costs, but otherwise assumed that the costs are unchanged from cable 1 works. These costs include working with landusers and the affected communities.