## Risk Register
Project TD-0014579 Risk Register
| Project Name: |  | HYTS-APD Stage 2 | [15 empty] | P(50) | P(90) | Total
| Project Sponsor: |  | AusNet | [15 empty] | 12504395.5861 | 23225870.3574 | 35730265.9435
| Date: |  | 2026-07-06
Risk Identification | [8 empty] | Initial Qualitative Assessment |  |  |  |  | Residual Risk Assessment |  |  |  |  | Monte Carlo
Risk row from Library | Risk ID # | Status | Risk Category | Risk Theme | Risk Title & Description | Consequence | Risk Owner | Consulted SME/Specialist (By Name) | Existing Controls | Control Effectiveness | Consequence Rating | Likelihood | Risk Rating | Planned Mitigations | Consequence Rating2 | Likelihood | Mitigated Risk Rating | Risk Owner Company (Post Mitigation/allocation) | MIN ($) | ML ($) | MAX ($) | LIKELIHOOD | PERT ($)
| 1 | Open | Project General | Schedule | Inclement Weather There is risk of excessive adverse weather conditions (e.g. heavy rain, high winds, flooding). This impacts site access, productivity, and safe execution of construction activities, causing delays. | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C]
| 2 | Open | Project General | Schedule | Outage Delays and Issues There is a risk of cancelled or delayed outages due to AEMO directives, unplanned outages, or other system security risks. Because the soul customer and the 500KV line that serves them is critical to network stability. Because of this, the line is specifically subject to limited and tight outage constraints. Additionally, there is major work going at HYTS there for apply constrains on outages and ability to conduct live line procedures | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C]
| 3 | Open | Project General | Scope | Construction Methodology Definition There is risk of bypass and sequencing changes in the replacement of towers. This is because project is still in project development. | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C]
| 4 | Open | Commercial Procurement | Schedule and Budget | Additional Material Costs - AusNet Free Issue Material There is a risk of additional material costs due to the supplier installation or incorrect, damaged, or non-compliant free issue materials (FIM) being supplied to site. (Free issue material is material/equipment that AusNet will procure through exciting "preferred supplier" contracts. This equipment will then be provided to the CDP at no cost to implement or install.) | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C]
| 5 | Open | Technical General | Delivery | Scope Changes There is a risk of scope change requests during delivery phase. Because we are still in development phase and detailed design has not yet occurred. | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C]
| 6 | Open | Environmental & Access | Site Access | Physical/geological site access issues. There is a risk of project disruptions because of natural obstacles, fences and gates etc blocking access to the site. This because of the various gates, various tracks, lack of tracks, this is farmland, national parks etc | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C]
| 7 | Open | Project General | Delivery | Staging interdependencies There is a risk that the commencement date of stage 2 is delayed because of various stage 1 schedule impacts and blow impacts | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C]
| 11 | Open | Project General | Safety | Safety Incident There is a risk of a major safety incident occurring during construction due to the nature of the works involved. | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C]
| 13 | Open | Technical General | Schedule | CDP Plant and Equipment Availability There is a risk of availability to procure plant and equipment. This is because plant and equipment is in high demand and are not available as required with the number or project within Victoria. High risk dependant on design. | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C]
| 14 | Open | Technical General | Schedule | Delays of Design Inputs There is a risk of Ausnet causing delay during the design maturity phase of the project. Such as late responses to RFIs , artifact supply and decision making. Included for completeness, but not costed for TRR purposes | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C]
| 15 | Open | Technical General | Asset | Existing Assets Unexpected Repairs There is a risk of existing AusNet assets within the AusNet work zone being found to be in poorer condition than expected, leading to failures or requiring unplanned repair or replacement during construction. | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C]
| 16 | Open | Technical Civil | Land/Soil/Geology | Geotechnical Conditions There is a risk of geotechnical conditions encountered onsite differing from those assumed during design (including presence of rock, poor bearing capacity, or unexpected groundwater conditions). This is because the relevant Geo tech studies and assessment have not been actioned and information is limited. | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C]
| 17 | Open | Technical General | Project Compliance | Defects / Poor Workmanship There is a risk of work delivered from the CDP suffering from defects or not meeting specification or a satisfactory standard. | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C]
| 18 | Open | Technical Civil | Land/Soil/Geology | Contaminated Land There is risk of contaminated soil are encountered during site investigations, excavation, or disposal that were not identified during preliminary assessments. Because historically AusNet have seen public users of near by road dump waste such as oils under the easement. | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C]
| 19 | Open | Technical Civil | Asset | Unidentified Services There is a risk of the discovery of UG cables/services on site or in nearby areas or unidentified or misidentified services located during construction. Because there is most likely a gas supply line and other infrastructure to support that line | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C]
| 20 | Open | Environmental & Access | Project Compliance | Delay of External Approvals There is a risk of required approvals which are needed to commence/ continue works taking longer than expected resulting in works on site stopping or being delayed. Approval examples are: Heritage Victoria, EPA, Vic Roads, Vic Planning, Environmental Vic etc) | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C]
| 21 | Open | Commercial General | Budget | General Inflation - Rates above 4.5% There is a risk of general inflation on aspects of the project other than labour wage. Included for completeness, not costed as capex forecasting is done in real dollars for TRR purposes | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C]
| 22 | Open | Technical General | Resources | Design Review There is a risk of necessary design approval resources being unavailable to deliver on time. Included for completeness, but not costed for TRR purposes | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C]
| 23 | Open | Project General | Resources | Internal Labour Shortages There is a risk of internal labour shortages within AusNet requiring re allocation and prioritisation of resources from other projects or conduct specific hiring activities. Included for completeness, but not costed for TRR purposes | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C]
| 26 | Open | Stakeholder & Community | Project Compliance | Community Concerns There is a risk of local community stakeholder concerns arising during the project (e.g. complaints about noise, dust, traffic, visual impact) resulting in a change of community attitude towards the project. This because this project runs through various properties and historical complaints with rural communities | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C]
| 27 | Open | Commercial General | Schedule | Contract Commitment Delays There is a risk of delays in contract execution or delivery of project resulting in additional costs and delayed revenue recognition. | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C]
| 28 | Open | Commercial General | Schedule | Scheduling Milestones Risks There is a risk of key milestones not being met due to ineffective scheduling / constraints not being identified. Included for completeness, but not costed for TRR purposes | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C]
| 29 | Open | Commercial General | Resources | Subcontractor/Vendor Shortages/availability There is a risk that there will be limited subcontractor/vendor that be available This is due to a significant number of large infrastructure projects in flight within Victoria. | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C]
| 30 | Open | Commercial General | Budget | External Labour Wage Escalation There is a risk of labour wage cost escalation because the project may go beyond project timeframes and current EBA contracts. | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C]
| 32 | Open | Commercial General | Contracts | Free Issue Material Supply and availability There is risk that free issue materials will not be available, have excessive lead times or excessive costs. Example: Ausnet have a panel arrangement with a particular supplier and that supplier can't supply that material forcing Ausnet to procure material from another supplier. | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C]
| 33 | Open | Commercial General | Contracts | Damaged/Faulty Equipment (Excluding Free issue Material) There is a risk of damaged/faulty equipment being supplied from AusNet suppliers. | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C]
| 35 | Open | Commercial Procurement | Contracts | Contractor Procurement There is a risk of difficulties arising in negotiating Terms & Conditions with the Contractor causing delays to the procurement. | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C]
| 36 | Open | Commercial Procurement | Budget | CDP Commissioning Resources There is a risk that commissioning resources will demand premium rates. This is due to current market conditions and the availability of specialist commissioning resources. | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C]
| 39 | Open | Legal | Resources | Industrial Action There is a risk of industrial action being undertaken which stops work on AusNet project. | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C]
| 41 | Open | Security | Property | Theft from Site There is a risk of physical theft from site resulting in damage or loss of project materials/plant and equipment. | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C]
| 43 | Open | Commercial General | Contracts | Extraordinary Events or Circumstances During project delivery, AusNet projects may be significantly delayed due to epidemics like COVID-type scenario, global conflicts, Environmental disasters and other unforeseen events. These event cause supply chain constraints and material resource cost spikes/increases | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C]
| 44 | Open | Commercial General | Contracts | ForEx Volatility Exposure Risk that FX exposure exceeds forecast levels, requiring financial adjustments to manage the impact. | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C]
| 45 | Open | Commercial Procurement | Schedule and budget | DDP and CDP Tender - Higher Market Response There is a risk that market testing and tender responses may result in costs significantly higher than anticipated. This may occur where DDPs and CDPs submit higher-priced bids due to limited capacity, resource constraints, or perceived delivery risks. | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C]
| 46 | Open | Commercial General | Contracts | Commodity Exposure Risk that commodity exposure exceeds forecast levels, requiring financial adjustments to manage the impact.. | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C]
| 47 | Open | Project General | Schedule and Budget | The recall time risk There is a risk of work stoppages during planned outages due to AusNet's contractual obligation to provide a three-hour recall capability for the Alcoa aluminium smelter. | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C] | [C-I-C]
Note on B10: - Identification number. - Provide ID number when creating or importing a new risk
Note on C10: - Drop down menu - Open when creating risk, close when certain circumstances of completely removed the risk from the project. - PM's have the authority to close risks can open and close a risk.
Note on D10: - Drop down entry - A high-level classification used to group risks based on their primary source or domain of impact, providing a structured way to organise and report risks across an organisation or project.
Note on E10: - Drop down menu entry A more specific descriptor used to identify the key underlying driver or characteristic of a risk within a category, enabling consistent identification of common issues or patterns
Note on F10: Title (in bold and first line). Think scenario based in just a few words Description: Think scenario in few sentences. Phrasing recommendation: There is risk that... (event) will occur, because of…(reason).
Note on G10: - Describe in plan text the outcome/consequence of the risk occurring. Provide specific and measurable impacts and rational.
Note on H10: - Drop down menu entry - The owner is overall accountable for the risk assessment to be completed - Default is PM of Development, if no PM then Default is PE. - Complete this cell when creating or tailoring risk lines. If unknown seek consultation at appropriate meetings such a project progress meetings - Owners are teams lead, PM, PE, lead estimator etc. Use the risk category as guidance
Note on I10: - Name of individual who will complete the risk assessment or provide consultation with risk owner regarding the risk assessment - Risk Owners delegate this section - Use the risk theme as guidance for the identifying the right individual
Note on J10: - Provide list of controls for this risk - Controls are embedded AusNet protocols or procedures that can be implemented to manage risks and issues in the first instance. - If guidance is needed, see the Control Reference tab to seek appropriate controls, and rating for generic risks.
Note on K10: - Drop down menu section - Refer to the effectiveness rating in the control reference tab for rational of effectiveness
Note on O10: - Provide the plan to derisk. What will be implemented to decrease or transfer risk. - Enter content in plan text - Consider, specific and measurable actions and plans. Provide assumptions and rational

## Risk Toolkit
| Consequence Criteria | [6 empty] | A | B | C | D | E
[8 empty] | Highly Unlikely | Unlikely | Possible | Likely | Highly Likely
| Health & Safety | Environment & Community | Financial | Customer & Business Disruption | Legal & Regulatory | Reputation |  | Once in | Once in | Once in | Once in | At least once
[8 empty] | 100+ years | 10 - 100 years | 3 - 10 years | 1 - 3 years | a year
[8 empty] | <1% | 1 - 10% | >10 - 33% | >33 - 80% | >80%
5 - Critical | • One or more fatalities (employees, contractors, public) | • Destruction of more than 1% of a threatened species extant population or habitat, and/or permanent impact to environmental attributes locally and offsite | >$100m | • Loss of electricity supply for more than 4.7m customer hours, for example: | • Major litigation (including potential or threatened) with exposure to damages/ third party legal costs (≥$10m or ≥10% annual turnover) | • Complete loss of stakeholder confidence or severe reduction in brand. Multiple stakeholder groups including government representatives intervening or taking action detrimental to AusNet | 5 - Critical | Medium* | High | High | Very High | Very High
| • Multiple persons with total permanent disabilities or irreversible occupational illnesses (e.g. amputation, long term disability or disorder where the person is unable to return to their previous role, activities or level of mobility) | • Permanent damage to areas or items of cultural or historical significance |  | • a system black event | • Non-compliance, other incident or circumstance with exposure to: | • Sustained lead story and adverse national or international coverage. Uncontrolled negative social media
|  | • Extensive permanent loss of community livelihood. Long-term/ prolonged social unrest and outrage |  | • >30% of Victorian customers | • severe fines/ penalties (≥$10m or ≥10% annual turnover), whether imposed directly from a regulator or through litigation,
|  |  |  | for 5 hours | • criminal conviction against any director/executive(s) (inc. imprisonment or disqualification), and/or
|  |  |  | • >100k Dx customers for 48 hours | • removal, suspension or severe restriction of operating licence or business operation
• CBD for >12 hours
• Loss of supply to >500 gas customers or curtailment (load shed)
or generation
• Loss of a Critical Business Function for
7 + days
4 - Major | • Single instance of total permanent disability or irreversible occupational illness (employees, contractors or public) (e.g. amputation, long-term disability or disorder where the person is unable to return to their previous role, activities or level of mobility) | • Destruction of more than 0.1% of a threatened species extant population or habitat, or reversible impact to environmental attributes locally or offsite with long-term recovery (>10 years) | $30m - 100m | • Loss of electricity supply for 1.5m to 1.5m ≥ 4.7m customer hours, for example.: | • Litigation (including potential or threatened) with exposure to damages/ third party legal costs ($100k - <$10m) | • Significant Reduction in stakeholder confidence or brand. Multiple stakeholder groups and/or government representatives expressing heightened concern | 4 - Major | Medium | Medium | High | High | Very High
|  | • Damage to areas or items of cultural or historical significance |  | • >10% Victorian customers | • Non-compliance, other incident or circumstance with exposure to: | • Recurring negative publicity or coverage in multiple state or national media channels and/or social media
|  | • Extensive reversible loss of community livelihood, business viability or social wellbeing. Prolonged community tension or outrage |  | for 5 hours e.g. multiple terminal station outages | • significant fines/ penalties ($100k - <$10m), whether imposed directly from a regulator or through litigation,
|  |  |  | • >35k Dx customers for 48 hours | • criminal conviction against AusNet or any employee or contractor in the course of their employment/engagement with AusNet, and/or
|  |  |  | • CBD for <12 hours | • regulator imposed variation of conditions of licence that leads to significant operational changes; enforceable undertaking
• Significant reduction in supply to critical gas supply point, event resulting in both gas Slam Shuts operating
• Loss of a Critical Business Function for
1 - 6 days
3 - Serious | • Serious injury or illness (e.g. requiring hospital or outpatient treatment, >10 days lost time) | • Reversible impacts to environmental attributes, medium-term recovery (5-10 years) | $2m - 30m | • Loss of electricity or gas supply for more than 800k <1.5m customer hours, for example: | • Litigation (including potential or threatened) with exposure to damages/ third party legal costs ($10k - <100k) | • Serious reduction in stakeholder confidence. More than one stakeholder group offering a negative opinion or view in public forums | 3 - Serious | Low | Low | Medium | High | High
|  | • Interference with area/s or items of cultural or historical significance |  | • >5% Victorian customers for 5 hours e.g. a terminal station outage | • Non-compliance, other incident or circumstance with exposure to: | • Multiple instances of negative publicity or coverage through state media channels
|  | • Significant impacts to community cost of living, business viability or social wellbeing. High levels of community tension |  | • >35K Dx customers for 12 hours or >15k Dx customers for 48 hours | • statutory fines/ penalties ($10k - <100k), whether imposed directly from a regulator or through litigation, and/or
|  |  |  | • Significant event that will require active management for an extended period (e.g. weeks) | • regulator direction or improvement notice (other than a rectification notice for a non-compliant electric line or asset)
2 - Moderate | • Moderate injury or illness (e.g. requiring medical treatment but not hospitalisation, | • Reversible impacts to environmental attributes, short-term recovery (<5 years) | $500k -2m | • Loss of electricity or gas supply for more than 150k <800m customer hours, for example: | • Non-compliance, other incident or circumstance with exposure to: | • Single stakeholder group drawing negative attention to incident, event or approach | 2 - Moderate | Low | Low | Low | Medium | Medium
| < 10 days lost time) | • Small scale impacts to community cost of living, business viability or social wellbeing. Isolated examples of community tension |  | • >1% Victorian customers for 5 hours e.g. Partial loss of a Terminal station or feeder | • statutory fines/ penalties (<$10k), whether imposed directly from a regulator or through litigation, and/or | • Recurring adverse publicity or coverage through local media channels with potential reach and influence
|  |  |  | • > 15k Dx customers for 12 hours e.g. Full or partial loss of a terminal station or feeder | • regulator reporting, monitoring, request for information, investigation, warning or a rectification notice for a non-compliant electric line or asset)
• Will require some local management attention over several days
1- Minor | • Minor injury or illness resulting in first aid or no treatment | • Minor and confined environmental or community impact (excluding any cultural heritage impacts) readily dealt with or naturally dissipating with no action required | <$500k | • Loss of electricity or gas supply for less than 150k customer hours, e.g.: | • Contractual or other dispute (including potential or threatened) that is unlikely to progress to litigation | • A person or organisation within stakeholder group signaling concern in an incident, event or approach | 1 - Minor | Low | Low | Low | Low | Medium
|  |  |  | • <1% Victorian customers for 5 hours | • Non-compliance that is not reportable to a regulator; non-compliance, other incident or circumstance that is reportable to a regulator but with no formal action from the regulator; or non-compliance, other incident or circumstance that is identified and notified to AusNet by a regulator but with no formal action from the regulator | • Small volume of negative publicity or coverage in local media channels with limited reach or influence
• <15k Dx customers for 12 hours
• Impact of event absorbed through normal activity