## Risk allowances summary
AusNet Transmission Revenue Resert 2027-32 Revised Proposal
Risk allowance summary
All costs are provided in real 2024-25 dollars, before labour cost escalation, excluding overheads (i.e. Input dollars for capex model)
96.87% | Conversion from real 2025-26 to real 2024-25
|  | Initial Proposal (consistent with IR#022 response) |  |  |  | Draft Decision | Revised Proposal analysis | [5 empty] | Revised Proposal outcomes
Category | Project name | Total risk allowance | Total project cost including risk allowances | RY28-32 risk allowance | RY28-32 project cost including risk allowances | RY28-32 project cost excluding risk allowances | Total risk allowance - Initial Proposal | Total risk allowance - detailed risk register | Total risk allowance - Project Change Request documentation | RY28-32 risk allowance - Initial Proposal | RY28-32 risk allowance - detailed risk register | RY28-32 risk allowance - Project Change Request documentation | Selected risk allowance | RY28-32 project cost including selected risk allowances | RY28-32 selected risk allowances | Notes
ACCEPT DRAFT DECISION ON RISK ALLOWANCES
Major station projects | MLTS CB Replacement | 1688.9858 | 57988.5323 | 332.9699 | 11431.9706 | 10323.308 | 1688.9858 |  |  | 332.9699 |  |  | Zero - no risk allowance included | 10323.308 |  | We accept the Draft Decision to remove risk allowances for these projects. We have adopted the Draft Decision capex inputs for the capex model.
Major station projects | SYTS 500kV GIS Replacement | 4913.1636 | 105414.052 | 1480.3068 | 31760.624 | 29739.1898 | 4913.1636 |  |  | 1480.3068 |  |  | Zero - no risk allowance included | 29739.1898
Major station projects | TTS Circuit Breaker Replacement ​ | 2463.6147 | 37498.617 | 1885.1646 | 28694.0428 | 0 | 2463.6147 | 4160.9539 |  | 1885.1646 | 3183.9731 |  | Zero - no risk allowance included | 24205.7977 |  | We accept the Draft Decision to remove risk allowances for these projects. However, we have updated the capex forecast to more accurately reflect the Initial Proposal cost less contractor incentives and risk allowances. We have provided updated cost estimates to support this. No change has been made to the other cost components.
Major station projects | MWTS 66kV Circuit Breaker Replacement​ | 1550.4769 | 26302.6486 | 1174.9311 | 19931.8031 | 17770.6762 | 1550.4769 | 2935.674 |  | 1174.9311 | 2224.6154 |  | Zero - no risk allowance included | 18271.2781
Major station projects | LYPS and HWTS 500kV Circuit Breaker Replacement Stage 2​ | 4357.5173 | 60792.7925 | 4308.1085 | 60103.4781 | 19568.9852 | 4357.5173 | 3275.745 |  | 4308.1085 | 3238.6021 |  | Zero - no risk allowance included | 25143.8877 |  | We accept the Draft Decision to remove risk allowances for these projects. However, we have updated the capex forecast to incorporate changes to scope, namely the removal of the HWTS scope from the LYPS/HWTS project, and the addition of the 500kV reactor to the MLTS Reactor project
Major station projects | MLTS Reactor Replacement​ | 1016.5031 | 17049.6755 | 1016.5031 | 17049.6755 | 10883.9363 | 1016.5031 |  |  | 1016.5031 |  |  | Zero - no risk allowance included | 38099.066
Major station projects | SMTS 500kV GIS and F2 Transformer Replacement | 18707.8384 | 271056.2899 | 16771.6049 | 243002.3669 | 219698.2722 | 18707.8384 |  |  | 16771.6049 |  |  | Zero - no risk allowance included | 222410.8709 |  | We accept the capex amount approved in the Draft Decision for the 2027-32 period. However, we have changes to the profile of the project to support deliverability. This is discussed in Chapter 3 of the Revised Proposal.
RETAIN INITIAL PROPOSAL RISK ALLOWANCES
Major station projects | NPSD 220kV GIS | 12075.9373 | 139302.5385 | 12075.9373 | 139302.5379 | 55683.9921 | 12075.9373 | 18302.3086 |  | 12075.9373 | 18302.3086 |  | Initial Proposal | 134167.7939 | 12075.9373 | For these projects, we developed detailed risk registers and produced an updated estimate of the risk allowance. This additional work revealed that risk allowance amounts are material. However, we have chosen to retain the Initial Proposal risk amounts, to limit the number of issues under consideration
Major station projects | ROTS 500 kV GIL Replacement | 3543.5239 | 56702.5115 | 3516.4842 | 56269.8303 | 50929.5535 | 3543.5239 | 7213.84 |  | 3516.4842 | 7158.7932 |  | Initial Proposal | 54382.5959 | 3516.4842
Major station projects | BATS B2 Transformer Replacement | 2356.6018 | 41262.3829 | 2356.6017 | 41262.382 | 36780.7743 | 2356.6018 | 3780.869 |  | 2356.6017 | 3780.8689 |  | Initial Proposal | 40071.9083 | 2356.6017
Major station projects | TTS B4 Transformer Replacement | 1846.9437 | 20770.8013 | 1787.6198 | 20103.6426 | 17861.6023 | 1846.9437 | 3359.0814 |  | 1787.6198 | 3251.1876 |  | Initial Proposal | 20316.3808 | 1787.6198
UPDATE RISK ALLOWANCES FOR WHOLE PROJECT
Major station projects | KTS 500/220kV Transformer Replacement | 13644.192 | 248297.7536 | 11499.3044 | 209264.9718 | 191475.2007 | 13644.192 | 22766.6418 |  | 11499.3044 | 19789.9646 |  | Detailed risk register | 281792.5381 | 19789.9646 | For the KTS project, we have updated our capex forecasts to reflect updated scope, market-tested costs, and the detailed risk register
Asset replacement programs | Portland tower replacement - Stage 2 |  |  | 11511.6279 | 165000 | 153488.3721 |  |  |  | 11511.6279 | 12504.3956 |  | Detailed risk register | 165992.7677 | 12504.3956 | For the Portland Stage 2 project, we have updated our capex forecasts to reflect the detailed risk register
UPDATE RISK ALLOWANCES FOR NEXT PERIOD
Major station projects | SHTS Transformer and CB Replacement |  |  |  | 17138.7591 | 0 |  |  |  |  | 5116.1731 | 4886.9046 | Detailed risk register | 56766.9614 | 5116.1731 | For these projects, we have updated our capex forecasts excluding risk allowances (i.e. "base" capex) to reflect the Project Change Request documentation, and risk allowances to reflect the detailed risk register. For these in flight projects, the risk register was developed considering only future risks, and not those that have already eventuated. Therefore, updated risk amounts are applied only to the next regulatory period
Major station projects | RCTS Transformer & SwitchgearReplacement |  |  |  | 32685.4976 | 20220.0889 |  |  |  |  | 4748.6025 | 5321.4922 | Detailed risk register | 31667.8308 | 4748.6025
Major station projects | SMTS 330/220kV Transformer Replacement | 9028.647 | 132700.0932 | 6461.6346 | 94970.987 | 88547.8656 |  |  |  | 6461.6346 | 8733.8373 |  | Detailed risk register | 92944.1279 | 8733.8373 | For this project, we have updated risk allowances to reflect the detailed risk register. For this in flight project, the risk register was developed considering only future risks, and not those that have already eventuated. Therefore, updated risk amounts are applied only to the next regulatory period

## Graphs
AusNet Transmission Revenue Resert 2027-32 Revised Proposal
Risk allowance summary
| Initial Proposal | Detailed risk register
NPSD 220kV GIS | 12.0759 | 18.3023
ROTS 500 kV GIL Replacement | 3.5165 | 7.1588
BATS B2 Transformer Replacement | 2.3566 | 3.7809
TTS B4 Transformer Replacement | 1.7876 | 3.2512
KTS 500/220kV Transformer Replacement | 11.4993 | 19.79
Portland tower replacement - Stage 2 | 11.5116 | 12.5044
SMTS 330/220kV Transformer Replacement | 6.4616 | 8.7338

## Revised Proposal
AusNet Transmission 2027-28
|  | AER Capex Forecast Model | Sheet Validation | 0 |  |  |  | Key: | Input | Input - optional | Formula - do not edit
Input¦ Projects As Inc
[8 empty] | Total annual direct costs, unescalated | [13 empty] | 0 | 0
[8 empty] | 0 | 236285.5385 | 526921.4907 | 531984.8807 | 485667.5171 | 386139.4247 | 268922.3622 | [7 empty] | NOTE: fill in table only if you select 'DNSP defined' overhead allocation in table 32 | [12 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50
|  | 12. Project Details |  |  | 13. Level 3 Mapping | 14. Driver mapping categories |  | 15. Unescalated direct costs ($'000s 2024-25 March) | [7 empty] | 16. Cost components as % of direct costs |  |  |  | 17. Capitalised overheads allocation |  | 18. Allocation of capitalised overheads - DNSP defined |  | 19. Driver categories as % of direct costs (i.e. total costs reported in table 15, excluding capitalised overheads) | [10 empty] | 1: 20. PTRM asset classes as % of direct costs (i.e. total costs reported in table 15, excluding capitalised overheads)
[19 empty] | 0 |  |  | % of total capitalised overheads allocated to project: | [11 empty] | 0 | [50 empty] | 0
|  | Project/Program Inputs | Unique ID |  |  | Driver categories |  | 2025-26 | 2026-27 | 2027-28 | 2028-29 | 2029-30 | 2030-31 | 2031-32 | Total | Internal labour | Contract labour | Non-labour |  | Network Overheads Applies | Corporate Overheads Applies | % of total network overheads | % of total corporate overheads | Replacement - Major Stations | Replacement - Other | Compliance | Resillience | ICT capex | Property capex | Fleet capex | Other non-network capex | Capitalised network overheads | Capitalised corporate overheads |  | Secondary | Switchgear | Transformers | Reactive | Towers and Conductor | Establishment | Communications | Inventory | IT | Vehicles | Other (Non-Network) | Premises | Land | Easements | Polymeric Insulators | Leases L&B - Short Lives | Head Office Leases | Buildings - Capital Works | In-House Software
| 1 | KTS 500/220kV Transformer Replacement | TD-0003454 |  | Major Station | Replacement - Major Stations | Replacement | 0 | 27884.3106 | 60572.0791 | 55900.3929 | 71266.0789 | 74224.0216 | 19829.9656 | 281792.5381 | 10% | 50% | 40% |  | Yes | No |  |  | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  | 4.747% | 11.18% | 73.8% | 0% | 1.541% | 8.5% | 0.2322% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 2 | MLTS CB Replacement | TD-0006168 |  | Major Station | Replacement - Major Stations | Replacement | 0 | 18024.4202 | 9967.947 | 355.361 | 0 | 0 | 0 | 10323.308 | 10% | 50% | 40% |  | Yes | No |  |  | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  | 2.583% | 77.2% | 0% | 0% | 3.024% | 16.9% | 0.2935% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 3 | TSTS - Tx and Switchgear Replacement | TD-0007772 |  | Major Station | Replacement - Major Stations | Replacement | 0 | 8034.2161 | 0 | 0 | 0 | 0 | 0 | 0 | 10% | 50% | 40% |  | Yes | No |  |  | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  | 14.29% | 39.21% | 38.01% | 0% | 0% | 8.483% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 4 | SHTS Transformer and CB Replacement | TD-0007996 |  | Major Station | Replacement - Major Stations | Replacement | 0 | 9252.4156 | 29124.2557 | 15498.8518 | 12143.8539 | 0 | 0 | 56766.9614 | 10% | 50% | 40% |  | Yes | No |  |  | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  | 14.29% | 39.21% | 38.01% | 0% | 0% | 8.483% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 5 | RCTS Transformer & SwitchgearReplacement | TD-0008004 |  | Major Station | Replacement - Major Stations | Replacement | 0 | 22263.5387 | 31667.8308 | 0 | 0 | 0 | 0 | 31667.8308 | 10% | 50% | 40% |  | Yes | No |  |  | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  | 4.484% | 8.371% | 66.3% | 0% | 5.064% | 15% | 0.7852% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 6 | SYTS 500kV GIS Replacement | TD-0008033 |  | Major Station | Replacement - Major Stations | Replacement | 0 | 14861.5619 | 25472.6127 | 4266.5771 | 0 | 0 | 0 | 29739.1898 | 10% | 50% | 40% |  | Yes | No |  |  | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  | 9.142% | 33.07% | 0% | 0% | 27.36% | 23.04% | 7.382% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 7 | SMTS H Transformer | TD-0014633 |  | Major Station | Replacement - Major Stations | Replacement | 0 | 27550.23 | 49432.217 | 43511.9109 | 0 | 0 | 0 | 92944.1279 | 10% | 50% | 40% |  | Yes | No |  |  | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  | 2.243% | 6.402% | 86.86% | 0% | 1.442% | 2.902% | 0.1529% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 8 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% |  | No | No |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 9 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% |  | No | No |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 10 | SMTS 500kV GIS and F2 Transformer Replacement | TD-0008025 |  | Major Station | Replacement - Major Stations | Replacement | 0 | 9977.4524 | 6120.2131 | 44526.063 | 61049.6133 | 62722.8574 | 47992.1242 | 222410.8709 | 10% | 50% | 40% |  | Yes | No |  |  | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  | 10.69% | 33.83% | 21.88% | 0% | 10.11% | 22.55% | 0.9383% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 11 | NPSD 220kV GIS | TD-0013613 |  | Major Station | Replacement - Major Stations | Replacement | 0 | 232.4061 | 2518.6615 | 16700.8018 | 41799.393 | 41799.393 | 31349.5447 | 134167.7939 | 10% | 50% | 40% |  | Yes | No |  |  | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  | 9.015% | 48.11% | 0% | 0% | 5.484% | 36.4% | 0.9985% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
[8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% |  | No | No |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
[8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% |  | No | No |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | ROTS 500 kV GIL Replacement | TD-0013738 |  | Power Cables (Major Projects) | Replacement - Major Stations | Replacement | 0 | 432.6812 | 6971.5967 | 22042.9156 | 17642.0986 | 7725.9851 | 0 | 54382.5959 | 10% | 50% | 40% |  | Yes | No |  |  | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | TTS Circuit Breaker Replacement ​ | TD-0003597 |  | Circuit Breakers (Major Projects) | Replacement - Major Stations | Replacement | 0 | 7988.9398 | 14344.1338 | 9861.6639 | 0 | 0 | 0 | 24205.7977 | 10% | 50% | 40% |  | Yes | No |  |  | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  | 34% | 33% | 0% | 0% | 0% | 33% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | LYPS Circuit Breaker Replacement Stage 2​ | TD-0008023 |  | Circuit Breakers (Major Projects) | Replacement - Major Stations | Replacement | 0 | 644.8826 | 1925.0551 | 4166.6984 | 11437.7542 | 7570.5649 | 43.8151 | 25143.8877 | 10% | 50% | 40% |  | Yes | No |  |  | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  | 16% | 68% | 0% | 0% | 0% | 16% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | MLTS Reactor Replacement​ | TD-0015755​ |  | Power Transformers and Oil Filled Reactors (Major Projects) | Replacement - Major Stations | Replacement | 0 | 800.8762 | 7453.1692 | 17854.9732 | 9280.2705 | 3510.653 | 0 | 38099.066 | 10% | 50% | 40% |  | Yes | No |  |  | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  | 29% | 19% | 35% | 0% | 0% | 17% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | BATS B2 Transformer Replacement | TD-0015756​ |  | Power Transformers and Oil Filled Reactors (Major Projects) | Replacement - Major Stations | Replacement | 0 | 0 | 0 | 4427.6927 | 17109.076 | 13242.2804 | 5292.8592 | 40071.9083 | 10% | 50% | 40% |  | Yes | No |  |  | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | MWTS 66kV Circuit Breaker Replacement​ | TD-0008003​ |  | Circuit Breakers (Major Projects) | Replacement - Major Stations | Replacement | 0 | 0 | 87.2559 | 1841.6179 | 5714.7181 | 4414.5165 | 6213.1697 | 18271.2781 | 10% | 50% | 40% |  | Yes | No |  |  | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  | 35% | 42% | 0% | 0% | 0% | 23% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | TTS B4 Transformer Replacement | TD-0016676 |  | Power Transformers and Oil Filled Reactors (Major Projects) | Replacement - Major Stations | Replacement | 0 | 0 | 340.4562 | 2854.7759 | 7548.8815 | 7002.5503 | 2569.7169 | 20316.3808 | 10% | 50% | 40% |  | Yes | No |  |  | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
[8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% |  | No | No |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
[8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% |  | No | No |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | MPLS-TP Metro East Pilot Comms Replace | TD-0010115 |  | Communication Systems | Replacement - Other | Replacement | 0 | 110.645 | 8 | 0 | 0 | 0 | 0 | 8 | 10% | 50% | 40% |  | Yes | No |  |  | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | North East Network Comms Replacement | TD-0009897 |  | Communication Systems | Replacement - Other | Replacement | 0 | 5553.0179 | 4637.6703 | 0 | 0 | 0 | 0 | 4637.6703 | 10% | 50% | 40% |  | Yes | No |  |  | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | North West SDH Comms Replacement | TD-0013861 |  | Communication Systems | Replacement - Other | Replacement | 0 | 2562.3882 | 0 | 0 | 0 | 0 | 0 | 0 | 10% | 50% | 40% |  | Yes | No |  |  | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Phasor Measurement Units Project 2024 | TD-0014486 |  | PMU Installation | Replacement - Other | Replacement | 0 | 4923.9249 | 0 | 0 | 0 | 0 | 0 | 0 | 10% | 50% | 40% |  | Yes | No |  |  | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | South West Network Comms Replacement | TD-0010117 |  | Communication Systems | Replacement - Other | Replacement | 0 | 6365.147 | 11310.4409 | 1036.1447 | 0 | 0 | 0 | 12346.5857 | 10% | 50% | 40% |  | Yes | No |  |  | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Transmission Insulator Replacement | TD-0014597 |  | Transmission Line Insulators | Replacement - Other | Replacement | 0 | 18612.5407 | 20 | 0 | 0 | 0 | 0 | 20 | 10% | 50% | 40% |  | Yes | No |  |  | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0%
|  | T624 to T628B HYTS-APD tower replacement | TD-0012063 |  | Transmission Line Structures | Replacement - Other | Replacement | 0 | 29410.699 | 405.693 | 0 | 0 | 0 | 0 | 405.693 | 10% | 50% | 40% |  | Yes | No |  |  | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Portland tower replacement - Stage 2 | TD-0014579 |  | Transmission Line Structures | Replacement - Other | Replacement | 0 | 0 | 15593.26 | 85511.4258 | 64888.0819 | 0 | 0 | 165992.7677 | 10% | 50% | 40% |  | Yes | No |  |  | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | VNSC & Comms Sites Battery Replacement | TD-0013827 |  | Communication Systems | Replacement - Other | Replacement | 0 | 9810.4535 | 5190.3504 | 0 | 0 | 0 | 0 | 5190.3504 | 10% | 50% | 40% |  | Yes | No |  |  | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Tranche1 Rectification Low Spans, TL | TD-0014572 |  | Management of Transmission Line Ground Clearances | Compliance | Replacement | 0 | 10988.7908 | 8574.158 | 15058.72 | 0 | 0 | 0 | 23632.878 | 10% | 50% | 40% |  | Yes | No |  |  | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
[8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% |  | No | No |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
[8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% |  | No | No |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Auxiliary Power Supplies | Program |  | Auxiliary Power Supplies | Replacement - Other | Replacement | 0 | 0 | 3214.8837 | 3214.8837 | 3214.8837 | 3214.8837 | 3214.8837 | 16074.4186 | 10% | 50% | 40% |  | Yes | No |  |  | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Circuit Breakers | Program |  | Circuit Breakers | Replacement - Other | Replacement | 0 | 0 | 3188 | 3188 | 3188 | 3188 | 3188 | 15940 | 10% | 50% | 40% |  | Yes | No |  |  | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Civil Infrastructure | Program |  | Civil Infrastructure | Replacement - Other | Replacement | 0 | 0 | 1748.8372 | 1748.8372 | 1748.8372 | 1748.8372 | 1748.8372 | 8744.186 | 10% | 50% | 40% |  | Yes | No |  |  | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Communication Systems | Program |  | Communication Systems | Replacement - Other | Replacement | 0 | 0 | 3545.5042 | 16841.145 | 16841.145 | 16841.145 | 16841.145 | 70910.084 | 10% | 50% | 40% |  | Yes | No |  |  | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Disconnectors and Earth Switches | Program |  | Disconnectors and Earth Switches | Replacement - Other | Replacement | 0 | 0 | 1371.1628 | 1371.1628 | 1371.1628 | 1371.1628 | 1371.1628 | 6855.814 | 10% | 50% | 40% |  | Yes | No |  |  | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Fire Detection and Suppression | Program |  | Fire Detection and Suppression | Compliance | Replacement | 0 | 0 | 560 | 560 | 560 | 560 | 560 | 2800 | 10% | 50% | 40% |  | Yes | No |  |  | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Instrument Transformers | Program |  | Instrument Transformers | Replacement - Other | Replacement | 0 | 0 | 483.7209 | 483.7209 | 483.7209 | 483.7209 | 483.7209 | 2418.6047 | 10% | 50% | 40% |  | Yes | No |  |  | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Power Transformers and Oil Filled Reactors | Program |  | Power Transformers and Oil Filled Reactors | Replacement - Other | Replacement | 0 | 0 | 4005 | 4005 | 4005 | 4005 | 4005 | 20025 | 10% | 50% | 40% |  | Yes | No |  |  | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Secondary Systems | Program |  | Secondary Systems | Replacement - Other | Replacement | 0 | 0 | 5685.0542 | 5685.0542 | 5685.0542 | 5685.0542 | 5685.0542 | 28425.2712 | 10% | 50% | 40% |  | Yes | No |  |  | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Surge Diverters | Program |  | Surge Diverters | Replacement - Other | Replacement | 0 | 0 | 366.5116 | 366.5116 | 366.5116 | 366.5116 | 366.5116 | 1832.5581 | 10% | 50% | 40% |  | Yes | No |  |  | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Transmission Line Insulators | Program |  | Transmission Line Insulators | Replacement - Other | Replacement | 0 | 0 | 27626 | 27626 | 27626 | 27626 | 27626 | 138130 | 10% | 50% | 40% |  | Yes | No |  |  | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0%
|  | Transmission Lines Conductors - Low Span (Tranche 2) | Program |  | Management of Transmission Line Ground Clearances | Compliance | Replacement | 0 | 0 | 0 | 0 | 7600 | 7600 | 0 | 15200 | 10% | 50% | 40% |  | Yes | No |  |  | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Transmission Line Structures | Program |  | Transmission Line Structures | Replacement - Other | Replacement | 0 | 0 | 2069.3566 | 2069.3566 | 2069.3566 | 2069.3566 | 2069.3566 | 10346.7828 | 10% | 50% | 40% |  | Yes | No |  |  | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Transmission Line Fall Arrest Towers | Program |  | Transmission Line Structures (Compliance) | Compliance | Replacement | 0 | 0 | 1040 | 1040 | 1040 | 1040 | 1040 | 5200 | 10% | 50% | 40% |  | Yes | No |  |  | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Transmission Lines Fall Arrest System (FAS) Racks | Program |  | Transmission Line Structures (Compliance) | Compliance | Replacement | 0 | 0 | 300 | 300 | 300 | 300 | 300 | 1500 | 10% | 50% | 40% |  | Yes | No |  |  | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Transmission Tower Resilience Program | Program |  | Transmission Line Structures (Resilience) | Resillience | Replacement | 0 | 0 | 6496 | 6496 | 6496 | 6496 | 6496 | 32480 | 10% | 50% | 40% |  | Yes | No |  |  | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% |  | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Transmission Lines Conductors (GW & Ph Cond) | Program |  | Transmission Lines Conductors (GW & Ph Cond) | Replacement - Other | Replacement | 0 | 0 | 3720 | 3720 | 3720 | 3720 | 3720 | 18600 | 10% | 50% | 40% |  | Yes | No |  |  | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Transmission Lines Conductors (GW & Ph Cond) | Program |  | Transmission Lines Conductors (Compliance) | Compliance | Replacement | 0 | 0 | 16938 | 16938 | 16938 | 16938 | 16938 | 84690 | 10% | 50% | 40% |  | Yes | No |  |  | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
[8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% |  | No | No |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
[8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% |  | No | No |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Environmental | Program |  | Environmental | Compliance | Replacement | 0 | 0 | 1024.5359 | 1024.5359 | 1024.5359 | 1024.5359 | 1024.5359 | 5122.6795 | 10% | 50% | 40% |  | Yes | No |  |  | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Rework | Program |  | Environmental | Compliance | Replacement | 0 | 0 | 2053.8165 | 2053.8165 | 2053.8165 | 2053.8165 | 2053.8165 | 10269.0825 | 10% | 50% | 40% |  | Yes | No |  |  | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Consultant | Program |  | Environmental | Compliance | Replacement | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10% | 50% | 40% |  | Yes | No |  |  | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
[8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% |  | No | No |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
[8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% |  | No | No |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Metering | Program |  | Metering | Replacement - Other | Replacement | 0 | 0 | 2095.5479 | 2095.5479 | 2095.5479 | 2095.5479 | 2095.5479 | 10477.7394 | 10% | 50% | 40% |  | Yes | No |  |  | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
[8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% |  | No | No |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
[8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% |  | No | No |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Testing Equipment | Program |  | Other (Non-Network) | Other non-network capex | Non-network capex | 0 | 0 | 3654.107 | 4542.9346 | 4613.9791 | 1809.9288 | 1515.945 | 16136.8945 | 10% | 0% | 90% |  | No | No |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% |  | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Vehicles - Replacement - Car | Program |  | Vehicles | Fleet capex | Non-network capex | 0 | 0 | 174.938 | 0 | 0 | 427.6263 | 476.2202 | 1078.7845 | 10% | 0% | 90% |  | No | No |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Vehicles - Replacement - LCV | Program |  | Vehicles | Fleet capex | Non-network capex | 0 | 0 | 620.832 | 235.1636 | 1382.7622 | 545.5796 | 235.1636 | 3019.501 | 10% | 0% | 90% |  | No | No |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Vehicles - Replacement - HCV | Program |  | Vehicles | Fleet capex | Non-network capex | 0 | 0 | 0 | 364.9578 | 0 | 0 | 0 | 364.9578 | 10% | 0% | 90% |  | No | No |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Vehicles - Replacement - Other (trailer and plant) | Program |  | Vehicles | Fleet capex | Non-network capex | 0 | 0 | 91.2395 | 91.2395 | 91.2395 | 91.2395 | 91.2395 | 456.1973 | 10% | 0% | 90% |  | No | No |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Vehicles - TOMSA - LCV | Program |  | Vehicles | Fleet capex | Non-network capex | 0 | 0 | 0 | 1642.3101 | 1642.3101 | 1642.3101 | 0 | 4926.9304 | 10% | 0% | 90% |  | No | No |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Vehicles - Growth - Car | Program |  | Vehicles | Fleet capex | Non-network capex | 0 | 0 | 118.6113 | 118.6113 | 118.6113 | 118.6113 | 118.6113 | 593.0564 | 10% | 0% | 90% |  | No | No |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Vehicles - Growth - LCV | Program |  | Vehicles | Fleet capex | Non-network capex | 0 | 0 | 182.4789 | 182.4789 | 182.4789 | 182.4789 | 182.4789 | 912.3945 | 10% | 0% | 90% |  | No | No |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
[8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% |  | No | No |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
[8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% |  | No | No |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Building Services | Program |  | Premises | Property capex | Non-network capex | 0 | 0 | 490 | 595 | 325 | 300 | 300 | 2010 | 10% | 50% | 40% |  | No | No |  |  | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0%
|  | Fitout Capex | Program |  | Premises | Property capex | Non-network capex | 0 | 0 | 11064.742 | 0 | 0 | 0 | 0 | 11064.742 | 10% | 50% | 40% |  | No | No |  |  | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 38.57% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 61.43% | 0%
|  | South Morang Training Centre | Program |  | Premises | Property capex | Non-network capex | 0 | 0 | 6130 | 6130 | 0 | 0 | 0 | 12260 | 10% | 50% | 40% |  | No | No |  |  | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0%
|  | Head Office Leases | Program |  | Capitalised Leases | Property capex | Non-network capex | 0 | 0 | 43417.3233 | 0 | 0 | 0 | 0 | 43417.3233 | 0% | 0% | 100% |  | No | No |  |  | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0%
|  | Leases L&B - Short Lives | Program |  | Capitalised Leases | Property capex | Non-network capex | 0 | 0 | 230.9953 | 109.9729 | 313.5745 | 141.5829 | 245.9953 | 1042.1209 | 0% | 0% | 100% |  | No | No |  |  | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0%
[8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% |  | No | No |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
[8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% |  | No | No |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Advanced Energy Management System - Connection asset demand management | Advanced Energy Management System - Non-recurrent |  | IT | ICT capex | Non-network capex | 0 | 0 | 0 | 0 | 0 | 0 | 10000 | 10000 | 0% | 95% | 5% |  | No | Yes |  |  | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 10% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 90%
|  | Advanced Energy Management System - Demand Management Phase 2 | Advanced Energy Management System - Non-recurrent |  | IT | ICT capex | Non-network capex | 0 | 0 | 0 | 0 | 5000 | 0 | 0 | 5000 | 0% | 95% | 5% |  | No | Yes |  |  | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 10% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 90%
|  | Advanced Energy Management System - Distributed Photovolataics (DPV) forecasts for modelling | Advanced Energy Management System - Non-recurrent |  | IT | ICT capex | Non-network capex | 0 | 0 | 0 | 0 | 3000 | 0 | 0 | 3000 | 0% | 75% | 25% |  | No | Yes |  |  | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 10% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 90%
|  | Advanced Energy Management System - Dynamic control room displays | Advanced Energy Management System - Non-recurrent |  | IT | ICT capex | Non-network capex | 0 | 0 | 0 | 0 | 0 | 0 | 1500 | 1500 | 0% | 95% | 5% |  | No | Yes |  |  | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 10% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 90%
|  | Advanced Energy Management System - Dynamic Ratings (SOCS & OSSCA) upgrade | Advanced Energy Management System - Non-recurrent |  | IT | ICT capex | Non-network capex | 0 | 0 | 0 | 0 | 0 | 3000 | 0 | 3000 | 0% | 70% | 30% |  | No | Yes |  |  | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 20% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 80%
|  | Advanced Energy Management System - Geospatial threat monitoring and forecast | Advanced Energy Management System - Non-recurrent |  | IT | ICT capex | Non-network capex | 0 | 0 | 0 | 10000 | 0 | 0 | 0 | 10000 | 0% | 75% | 25% |  | No | Yes |  |  | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 10% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 90%
|  | Advanced Energy Management System - HMI upgrades for TOC | Advanced Energy Management System - Non-recurrent |  | IT | ICT capex | Non-network capex | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 5000 | 0% | 100% | 0% |  | No | Yes |  |  | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100%
|  | Advanced Energy Management System - Load forecasting by feeder | Advanced Energy Management System - Non-recurrent |  | IT | ICT capex | Non-network capex | 0 | 0 | 0 | 0 | 1500 | 0 | 0 | 1500 | 0% | 70% | 30% |  | No | Yes |  |  | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 20% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 80%
|  | Advanced Energy Management System - Network operations scenario simulator uplift | Advanced Energy Management System - Non-recurrent |  | IT | ICT capex | Non-network capex | 0 | 0 | 0 | 0 | 2000 | 0 | 0 | 2000 | 0% | 75% | 25% |  | No | Yes |  |  | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 10% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 90%
|  | Advanced Energy Management System - Passive knowledge management | Advanced Energy Management System - Non-recurrent |  | IT | ICT capex | Non-network capex | 0 | 0 | 500 | 0 | 0 | 0 | 0 | 500 | 0% | 75% | 25% |  | No | Yes |  |  | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 10% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 90%
|  | Advanced Energy Management System - Ratings management Phase 1 | Advanced Energy Management System - Non-recurrent |  | IT | ICT capex | Non-network capex | 0 | 0 | 500 | 0 | 0 | 0 | 0 | 500 | 0% | 70% | 30% |  | No | Yes |  |  | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 20% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 80%
|  | Advanced Energy Management System - Ratings management Phase 2 | Advanced Energy Management System - Non-recurrent |  | IT | ICT capex | Non-network capex | 0 | 0 | 0 | 0 | 2750 | 0 | 0 | 2750 | 0% | 70% | 30% |  | No | Yes |  |  | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 20% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 80%
|  | Advanced Energy Management System - Security cameras for network purposes | Advanced Energy Management System - Non-recurrent |  | IT | ICT capex | Non-network capex | 0 | 0 | 2000 | 0 | 0 | 0 | 0 | 2000 | 0% | 75% | 25% |  | No | Yes |  |  | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 10% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 90%
|  | Advanced Energy Management System - System restart uplift | Advanced Energy Management System - Non-recurrent |  | IT | ICT capex | Non-network capex | 0 | 0 | 0 | 0 | 0 | 3000 | 0 | 3000 | 0% | 95% | 5% |  | No | Yes |  |  | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 10% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 90%
|  | Advanced Energy Management System - TASM opex (TBC opex baseline year) | Advanced Energy Management System - Opex |  | IT | ICT capex | Non-network capex | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% |  | No | Yes |  |  | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Advanced Energy Management System - TASM Phase 2: SAP automation, automated conditions & constraints analysis | Advanced Energy Management System - Non-recurrent |  | IT | ICT capex | Non-network capex | 0 | 0 | 0 | 5000 | 0 | 0 | 0 | 5000 | 0% | 95% | 5% |  | No | Yes |  |  | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 10% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 90%
|  | Advanced Energy Management System - Transmission alarm management | Advanced Energy Management System - Non-recurrent |  | IT | ICT capex | Non-network capex | 0 | 0 | 0 | 0 | 0 | 3000 | 0 | 3000 | 0% | 95% | 5% |  | No | Yes |  |  | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 10% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 90%
|  | Advanced Energy Management System - VicTNSP capability | Advanced Energy Management System - Non-recurrent |  | IT | ICT capex | Non-network capex | 0 | 0 | 2520 | 0 | 0 | 0 | 0 | 2520 | 0% | 70% | 30% |  | No | Yes |  |  | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 20% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 80%
|  | Advanced Energy Management System - Wide Area Monitoring System (Oscillation detection & Monitoring) | Advanced Energy Management System - Non-recurrent |  | IT | ICT capex | Non-network capex | 0 | 0 | 0 | 0 | 0 | 5000 | 5000 | 10000 | 0% | 95% | 5% |  | No | Yes |  |  | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 10% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 90%
|  | Advanced Energy Management System - Net New - TNSP ICCP links | Advanced Energy Management System - Non-recurrent |  | IT | ICT capex | Non-network capex | 0 | 0 | 0 | 3600 | 0 | 0 | 0 | 3600 | 0% | 95% | 5% |  | No | Yes |  |  | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 10% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 90%
|  | Asset Management & Field Enablement - Centralised data storage (e.g. videos, photos, others) | Asset Management & Field Enablement - Non-recurrent |  | IT | ICT capex | Non-network capex | 0 | 0 | 1625 | 1625 | 0 | 0 | 0 | 3250 | 0% | 95% | 5% |  | No | Yes |  |  | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 10% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 90%
|  | Asset Management & Field Enablement - Knowledge management for various documents | Asset Management & Field Enablement - Non-recurrent |  | IT | ICT capex | Non-network capex | 0 | 0 | 1125 | 1125 | 0 | 0 | 0 | 2250 | 0% | 95% | 5% |  | No | Yes |  |  | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 10% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 90%
|  | Asset Management & Field Enablement - Asset condition desktop monitoring & more frequent ARM for network capex planning | Asset Management & Field Enablement - Non-recurrent |  | IT | ICT capex | Non-network capex | 0 | 0 | 0 | 2565 | 2565 | 0 | 0 | 5130 | 0% | 75% | 25% |  | No | Yes |  |  | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 10% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 90%
|  | Asset Management & Field Enablement - Asset Performance Management (APM) System for maintenance opex optimisation | Asset Management & Field Enablement - Non-recurrent |  | IT | ICT capex | Non-network capex | 0 | 0 | 0 | 0 | 0 | 3825 | 3825 | 7650 | 0% | 75% | 25% |  | No | Yes |  |  | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 10% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 90%
|  | Asset Management & Field Enablement - Asset performance analytics using SCADA data | Asset Management & Field Enablement - Non-recurrent |  | IT | ICT capex | Non-network capex | 0 | 0 | 1000 | 0 | 0 | 0 | 0 | 1000 | 0% | 95% | 5% |  | No | Yes |  |  | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 10% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 90%
|  | Asset Management & Field Enablement - Automating transformer rating calculations​ | Asset Management & Field Enablement - Non-recurrent |  | IT | ICT capex | Non-network capex | 0 | 0 | 0 | 1000 | 0 | 0 | 0 | 1000 | 0% | 95% | 5% |  | No | Yes |  |  | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 10% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 90%
|  | Asset Management & Field Enablement - Consolidate Geospatial Capability | Asset Management & Field Enablement - Non-recurrent |  | IT | ICT capex | Non-network capex | 0 | 0 | 0 | 0 | 1050 | 350 | 0 | 1400 | 0% | 75% | 25% |  | No | Yes |  |  | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 10% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 90%
|  | Asset Management & Field Enablement - Tx field mobility | Asset Management & Field Enablement - Non-recurrent |  | IT | ICT capex | Non-network capex | 0 | 0 | 0 | 1000 | 0 | 0 | 0 | 1000 | 0% | 55% | 45% |  | No | Yes |  |  | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100%
|  | Asset Management & Field Enablement - Tx Asset Data Enhancement Program | Asset Management & Field Enablement - Non-recurrent |  | IT | ICT capex | Non-network capex | 0 | 0 | 4275 | 0 | 0 | 0 | 0 | 4275 | 0% | 95% | 5% |  | No | Yes |  |  | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 10% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 90%
|  | Customer Engagement - Transmission landholder access | Customer Engagement - Non-recurrent |  | IT | ICT capex | Non-network capex | 0 | 0 | 3600 | 0 | 0 | 0 | 0 | 3600 | 0% | 55% | 45% |  | No | Yes |  |  | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100%
|  | Metering Systems - EziView upgrade | Metering Systems - Non-recurrent |  | IT | ICT capex | Non-network capex | 0 | 0 | 2000 | 0 | 0 | 0 | 0 | 2000 | 0% | 55% | 45% |  | No | Yes |  |  | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100%
|  | Metering Systems - Meter data storage & analytics | Metering Systems - Non-recurrent |  | IT | ICT capex | Non-network capex | 0 | 0 | 0 | 5125 | 0 | 0 | 0 | 5125 | 0% | 100% | 0% |  | No | Yes |  |  | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 10% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 90%
|  | Metering Systems - Meter asset register | Metering Systems - Non-recurrent |  | IT | ICT capex | Non-network capex | 0 | 0 | 480 | 0 | 0 | 0 | 0 | 480 | 0% | 75% | 25% |  | No | Yes |  |  | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 10% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 90%
|  | Digital resilience – applications - Data and Analytics Tx Systems (cloud) | Digital resilience – applications - Recurrent |  | IT | ICT capex | Non-network capex | 0 | 0 | 55.1755 | 55.1755 | 55.1755 | 55.1755 | 55.1755 | 275.8776 | 0% | 100% | 0% |  | No | Yes |  |  | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100%
|  | Digital resilience – applications - Enterprise Resource Planning (ERP) | Digital resilience – applications - Recurrent |  | IT | ICT capex | Non-network capex | 0 | 0 | 300 | 2495.9184 | 265.3061 | 0 | 0 | 3061.2245 | 0% | 100% | 0% |  | No | Yes |  |  | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100%
|  | Digital resilience – applications - eTerra Upgrade | Digital resilience – applications - Recurrent |  | IT | ICT capex | Non-network capex | 0 | 0 | 1000 | 1500 | 0 | 2500 | 7500 | 12500 | 0% | 100% | 0% |  | No | Yes |  |  | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100%
|  | Digital resilience – applications - Geospatial Systems | Digital resilience – applications - Recurrent |  | IT | ICT capex | Non-network capex | 0 | 0 | 0 | 1520 | 0 | 0 | 0 | 1520 | 0% | 100% | 0% |  | No | Yes |  |  | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100%
|  | Digital resilience – applications - HSEQ | Digital resilience – applications - Recurrent |  | IT | ICT capex | Non-network capex | 0 | 0 | 91.8367 | 30.6122 | 0 | 0 | 0 | 122.449 | 0% | 100% | 0% |  | No | Yes |  |  | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100%
|  | Digital resilience – applications - Identity Management | Digital resilience – applications - Recurrent |  | IT | ICT capex | Non-network capex | 0 | 0 | 0 | 609.1837 | 3.0612 | 0 | 0 | 612.2449 | 0% | 100% | 0% |  | No | Yes |  |  | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100%
|  | Digital resilience – applications - OPEX - SaaS/PaaS cloud service growth | Digital resilience – applications - Opex |  | IT | ICT capex | Non-network capex | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 100% | 0% |  | No | Yes |  |  | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100%
|  | Digital resilience – applications - Other Business Systems | Digital resilience – applications - Recurrent |  | IT | ICT capex | Non-network capex | 0 | 0 | 235.102 | 235.102 | 235.102 | 235.102 | 235.102 | 1175.5102 | 0% | 100% | 0% |  | No | Yes |  |  | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100%
|  | Digital resilience – applications - Protection and Control Settings | Digital resilience – applications - Recurrent |  | IT | ICT capex | Non-network capex | 0 | 0 | 0 | 0 | 0 | 45.9677 | 61.2903 | 107.2581 | 0% | 100% | 0% |  | No | Yes |  |  | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100%
|  | Digital resilience – applications - Other TX applications | Digital resilience – applications - Recurrent |  | IT | ICT capex | Non-network capex | 0 | 0 | 700 | 700 | 700 | 700 | 700 | 3500 | 0% | 100% | 0% |  | No | Yes |  |  | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100%
|  | Digital resilience – applications - System Integration Platforms | Digital resilience – applications - Recurrent |  | IT | ICT capex | Non-network capex | 0 | 0 | 918.3673 | 306.1224 | 0 | 0 | 0 | 1224.4898 | 0% | 100% | 0% |  | No | Yes |  |  | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100%
|  | Digital resilience – applications - Telecommunications Systems (SDMT, CNMS) | Digital resilience – applications - Recurrent |  | IT | ICT capex | Non-network capex | 0 | 0 | 2000 | 1000 | 3000 | 2000 | 0 | 8000 | 0% | 100% | 0% |  | No | Yes |  |  | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100%
|  | Digital resilience – applications - Weather and Solar Services | Digital resilience – applications - Recurrent |  | IT | ICT capex | Non-network capex | 0 | 0 | 0 | 0 | 0 | 137.9032 | 183.871 | 321.7742 | 0% | 100% | 0% |  | No | Yes |  |  | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100%
|  | Digital resilience – applications - SCADA Data Historian | Digital resilience – applications - Recurrent |  | IT | ICT capex | Non-network capex | 0 | 0 | 0 | 0 | 1140 | 0 | 0 | 1140 | 0% | 100% | 0% |  | No | Yes |  |  | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100%
|  | Digital resilience – infrastructure - Data centre facilities | Digital resilience – infrastructure - Recurrent |  | IT | ICT capex | Non-network capex | 0 | 0 | 844.4727 | 844.4727 | 844.4727 | 844.4727 | 844.4727 | 4222.3634 | 0% | 30% | 70% |  | No | Yes |  |  | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Digital resilience – infrastructure - High security network | Digital resilience – infrastructure - Recurrent |  | IT | ICT capex | Non-network capex | 0 | 0 | 1400 | 1400 | 1400 | 1400 | 1400 | 7000 | 0% | 30% | 70% |  | No | Yes |  |  | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Digital resilience – infrastructure - Physical security digital infrastructure | Digital resilience – infrastructure - Recurrent |  | IT | ICT capex | Non-network capex | 0 | 0 | 230 | 230 | 220 | 220 | 100 | 1000 | 0% | 30% | 70% |  | No | Yes |  |  | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Digital resilience – infrastructure - Shared Data Centre Infrastructure | Digital resilience – infrastructure - Recurrent |  | IT | ICT capex | Non-network capex | 0 | 0 | 1002.6721 | 1002.6721 | 1002.6721 | 1002.6721 | 1002.6721 | 5013.3606 | 0% | 30% | 70% |  | No | Yes |  |  | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Digital resilience – infrastructure - Mission + Business – Other infrastructure upgrades | Digital resilience – infrastructure - Recurrent |  | IT | ICT capex | Non-network capex | 0 | 0 | 1000 | 1000 | 1000 | 1500 | 1000 | 5500 | 0% | 30% | 70% |  | No | Yes |  |  | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Digital resilience – infrastructure - System Integration Platforms - HW | Digital resilience – infrastructure - Recurrent |  | IT | ICT capex | Non-network capex | 0 | 0 | 183.8235 | -3.8776 | 0 | 0 | 0 | 179.946 | 0% | 30% | 70% |  | No | Yes |  |  | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Digital resilience – infrastructure - Telecommunications Systems (HW) | Digital resilience – infrastructure - Recurrent |  | IT | ICT capex | Non-network capex | 0 | 0 | 0 | 0 | 2000 | 1000 | 0 | 3000 | 0% | 30% | 70% |  | No | Yes |  |  | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Digital resilience – infrastructure - SCADA Data Historian - Infra | Digital resilience – infrastructure - Recurrent |  | IT | ICT capex | Non-network capex | 0 | 0 | 0 | 0 | 0 | 1900 | 0 | 1900 | 0% | 30% | 70% |  | No | Yes |  |  | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Digital Resilience – infrastructure - OT Communication equipment firmware | Digital Resilience – infrastructure - Recurrent |  | IT | ICT capex | Non-network capex | 0 | 0 | 0 | 0 | 600 | 0 | 0 | 600 | 0% | 30% | 70% |  | No | Yes |  |  | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Digital Resilience – infrastructure - End user devices (laptops, mobile, peripherals) | Digital Resilience – infrastructure - Recurrent |  | IT | ICT capex | Non-network capex | 0 | 0 | 48.9796 | 48.9796 | 48.9796 | 48.9796 | 48.9796 | 244.898 | 0% | 30% | 70% |  | No | Yes |  |  | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Cyber security - Cyber Security Systems Refresh | Cyber security - Recurrent |  | IT | ICT capex | Non-network capex | 0 | 0 | 4082.4 | 4082.4 | 4082.4 | 4082.4 | 4082.4 | 20412 | 0% | 75% | 25% |  | No | Yes |  |  | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 10% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 90%
|  | Cyber security - Cyber New Threat/Capability uplift (PWC Cyber Security Program) | Cyber security - Non-recurrent |  | IT | ICT capex | Non-network capex | 0 | 0 | 6930 | 6791.4 | 6930 | 6930 | 6930 | 34511.4 | 0% | 100% | 0% |  | No | Yes |  |  | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100%
|  | CI Fortify - OT Critical Application Hosting Domain | CI Fortify - Non-recurrent |  | IT | ICT capex | Non-network capex | 0 | 0 | 7038.2683 | 4432.7182 | 0 | 0 | 0 | 11470.9866 | 0% | 30% | 70% |  | No | Yes |  |  | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | CI Fortify - IT Border Firewall | CI Fortify - Non-recurrent |  | IT | ICT capex | Non-network capex | 0 | 0 | 1464.75 | 0 | 0 | 0 | 0 | 1464.75 | 0% | 30% | 70% |  | No | Yes |  |  | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | CI Fortify - OT Network Fabric | CI Fortify - Non-recurrent |  | IT | ICT capex | Non-network capex | 0 | 0 | 2145.7058 | 0 | 0 | 0 | 0 | 2145.7058 | 0% | 30% | 70% |  | No | Yes |  |  | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | CI Fortify - Migration of PMU data onto OT | CI Fortify - Non-recurrent |  | IT | ICT capex | Non-network capex | 0 | 0 | 0 | 314.91 | 0 | 0 | 0 | 314.91 | 0% | 30% | 70% |  | No | Yes |  |  | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | CI Fortify - Business continuity plans development | CI Fortify - Non-recurrent |  | IT | ICT capex | Non-network capex | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 100% | 0% |  | No | Yes |  |  | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100%
|  | CI Fortify - Critical operational support workforce | CI Fortify - Non-recurrent |  | IT | ICT capex | Non-network capex | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% |  | No | Yes |  |  | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Sovereignty - FOCI and Supply Chain – Privileged operational support | Sovereignty - Non-recurrent |  | IT | ICT capex | Non-network capex | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% |  | No | Yes |  |  | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Sovereignty - FOCI and Supply Chain – Integrated supplier platform | Sovereignty - Non-recurrent |  | IT | ICT capex | Non-network capex | 0 | 0 | 1569.25 | 1569.25 | 0 | 0 | 0 | 3138.5 | 0% | 75% | 25% |  | No | Yes |  |  | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 10% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 90%
|  | AI Defence - Build local AI compute | AI Defence - Non-recurrent |  | IT | ICT capex | Non-network capex | 0 | 0 | 1270.732 | 1050 | 0 | 0 | 0 | 2320.732 | 0% | 30% | 70% |  | No | Yes |  |  | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | AI Defence - OT defence | AI Defence - Non-recurrent |  | IT | ICT capex | Non-network capex | 0 | 0 | 0 | 300 | 150 | 150 | 150 | 750 | 0% | 70% | 30% |  | No | Yes |  |  | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 20% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 80%
|  | AI Defence - AI Governance | AI Defence - Non-recurrent |  | IT | ICT capex | Non-network capex | 0 | 0 | 638.425 | 0 | 0 | 0 | 0 | 638.425 | 0% | 75% | 25% |  | No | Yes |  |  | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 10% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 90%
|  | AI Defence - Agentic AI SOC | AI Defence - Non-recurrent |  | IT | ICT capex | Non-network capex | 0 | 0 | 750 | 0 | 0 | 0 | 0 | 750 | 0% | 75% | 25% |  | No | Yes |  |  | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 10% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 90%
|  | AI Defence - AI-driven security testing | AI Defence - Non-recurrent |  | IT | ICT capex | Non-network capex | 0 | 0 | 300 | 0 | 0 | 0 | 0 | 300 | 0% | 75% | 25% |  | No | Yes |  |  | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 10% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 90%
|  | AI Defence - Continuous exposure analysis and management | AI Defence - Non-recurrent |  | IT | ICT capex | Non-network capex | 0 | 0 | 400 | 0 | 0 | 0 | 0 | 400 | 0% | 75% | 25% |  | No | Yes |  |  | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 10% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 90%
|  | Patching - IT vulnerability scanning | Patching - Non-recurrent |  | IT | ICT capex | Non-network capex | 0 | 0 | 850 | 0 | 0 | 0 | 0 | 850 | 0% | 75% | 25% |  | No | Yes |  |  | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 10% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 90%
|  | Patching - IT & OT prioritisation tooling | Patching - Non-recurrent |  | IT | ICT capex | Non-network capex | 0 | 0 | 500 | 0 | 0 | 0 | 0 | 500 | 0% | 75% | 25% |  | No | Yes |  |  | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 10% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 90%
|  | Patching - Dual cell integration platform to manage downtime | Patching - Non-recurrent |  | IT | ICT capex | Non-network capex | 0 | 0 | 830 | 0 | 0 | 0 | 0 | 830 | 0% | 100% | 0% |  | No | Yes |  |  | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100%
|  | Patching - Automated OT/SCADA testing capabilities | Patching - Non-recurrent |  | IT | ICT capex | Non-network capex | 0 | 0 | 674 | 0 | 0 | 0 | 0 | 674 | 0% | 70% | 30% |  | No | Yes |  |  | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 20% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 80%
|  | - | - |  | IT | ICT capex | Non-network capex | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% |  | No | Yes |  |  | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
[8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% |  | No | No |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
[8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% |  | No | No |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | SOCI - CCTV (Building and Poles) | Program |  | SOCI | Compliance | Replacement | 0 | 0 | 1688.1403 | 2209 | 2372.25 | 2862 | 2146.5 | 11277.8903 | 10% | 50% | 40% |  | Yes | No |  |  | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | SOCI - Lighting | Program |  | SOCI | Compliance | Replacement | 0 | 0 | 269.49 | 200.97 | 0 | 0 | 0 | 470.46 | 10% | 50% | 40% |  | Yes | No |  |  | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | SOCI - Sub-component Protection | Program |  | SOCI | Compliance | Replacement | 0 | 0 | 417.9688 | 200.625 | 0 | 0 | 0 | 618.5938 | 10% | 50% | 40% |  | Yes | No |  |  | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | SOCI - Signage | Program |  | SOCI | Compliance | Replacement | 0 | 0 | 120.125 | 164.6875 | 126.25 | 126.25 | 94.6875 | 632 | 10% | 50% | 40% |  | Yes | No |  |  | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | SOCI - Window Protection | Program |  | SOCI | Compliance | Replacement | 0 | 0 | 84.3 | 34.65 | 0 | 0 | 0 | 118.95 | 10% | 50% | 40% |  | Yes | No |  |  | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | SOCI - Security Fencing | Program |  | SOCI | Compliance | Replacement | 0 | 0 | 12134.627 | 4800 | 4584.5 | 3938 | 2953.5 | 28410.627 | 10% | 50% | 40% |  | Yes | No |  |  | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | SOCI - Gate Installation and Paving Works (exclusive of Gate Motors) | Program |  | SOCI | Compliance | Replacement | 0 | 0 | 1130.63 | 460.5 | 0 | 0 | 0 | 1591.13 | 10% | 50% | 40% |  | Yes | No |  |  | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | SOCI - Access Control | Program |  | SOCI | Compliance | Replacement | 0 | 0 | 75 | 225 | 0 | 0 | 0 | 300 | 10% | 50% | 40% |  | Yes | No |  |  | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Non-SOCI Security - Fault Finding - Replacement of Broken Assets | Program |  | Non-SOCI Security | Compliance | Replacement | 0 | 0 | 100 | 92.5 | 65 | 50 | 50 | 357.5 | 10% | 50% | 40% |  | Yes | No |  |  | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Non-SOCI Security - Replacement Gate Motors | Program |  | Non-SOCI Security | Compliance | Replacement | 0 | 0 | 140.4 | 421.2 | 0 | 0 | 0 | 561.6 | 10% | 50% | 40% |  | Yes | No |  |  | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Non-SOCI Security - Padlock Protection | Program |  | Non-SOCI Security | Compliance | Replacement | 0 | 0 | 75.0938 | 225.2812 | 0 | 0 | 0 | 300.375 | 10% | 50% | 40% |  | Yes | No |  |  | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Non-SOCI Security - CCTV End of Life replacement (Tier 1 and Tier 2) | Program |  | Non-SOCI Security | Compliance | Replacement | 0 | 0 | 0 | 0 | 0 | 0 | 767.04 | 767.04 | 10% | 50% | 40% |  | Yes | No |  |  | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Non-SOCI Security - Trailer technology replacement | Program |  | Non-SOCI Security | Compliance | Replacement | 0 | 0 | 0 | 0 | 0 | 80 | 240 | 320 | 10% | 50% | 40% |  | Yes | No |  |  | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Non-SOCI Security - CCTV Server Replacement | Program |  | Non-SOCI Security | Compliance | Replacement | 0 | 0 | 0 | 0 | 0 | 255.75 | 767.25 | 1023 | 10% | 50% | 40% |  | Yes | No |  |  | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Non-SOCI Security - Rapid Deployment camera | Program |  | Non-SOCI Security | Compliance | Replacement | 0 | 0 | 225 | 0 | 0 | 0 | 0 | 225 | 10% | 50% | 40% |  | Yes | No |  |  | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Non-SOCI Security - Security Control Room Upgrade | Program |  | Non-SOCI Security | Compliance | Replacement | 0 | 0 | 937.5 | 0 | 0 | 0 | 0 | 937.5 | 10% | 50% | 40% |  | Yes | No |  |  | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Non-SOCI Security - Future Technology | Program |  | Non-SOCI Security | Compliance | Replacement | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10% | 50% | 40% |  | Yes | No |  |  | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
[8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | [5 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
[8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | [5 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
[8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | [5 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
[8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | [5 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
[8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | [5 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
[8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | [5 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
[8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | [5 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
[8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | [5 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
[8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | [5 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
[8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | [5 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
[8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | [5 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
[8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | [5 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
[8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | [5 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
[8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | [5 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
[8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | [5 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
[8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | [5 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
[8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | [5 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
[8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | [5 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
[8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | [5 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
[8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | [5 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
[8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | [5 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
[16 empty] | 0% | 0% | 0% | [5 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%

## Draft Decision
AusNet Transmission 2027-28
|  | AER Capex Forecast Model | Sheet Validation | 0 |  |  |  | Key: | Input | Input - optional | Formula - do not edit | AER alternative
Input¦ Projects As Inc
[8 empty] | Total annual direct costs, unescalated | [13 empty] | 0 | 0
[8 empty] | 163405.5739 | 280501.1144 | 422974.0522 | 389199.1361 | 262403.0035 | 244885.1956 | 224453.7763 | [7 empty] | NOTE: fill in table only if you select 'DNSP defined' overhead allocation in table 32 | [12 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50
|  | 12. Project Details |  |  | 13. Level 3 Mapping | 14. Driver mapping categories |  | 15. Unescalated direct costs ($'000s 2024-25 March) | [7 empty] | 16. Cost components as % of direct costs |  |  |  | 17. Capitalised overheads allocation |  | 18. Allocation of capitalised overheads - DNSP defined |  | 19. Driver categories as % of direct costs (i.e. total costs reported in table 15, excluding capitalised overheads) | [10 empty] | 1: 20. PTRM asset classes as % of direct costs (i.e. total costs reported in table 15, excluding capitalised overheads)
[19 empty] | 0 |  |  | % of total capitalised overheads allocated to project: | [11 empty] | 0 | [50 empty] | 0
|  | Project/Program Inputs | Unique ID |  |  | Driver categories |  | 2025-26 | 2026-27 | 2027-28 | 2028-29 | 2029-30 | 2030-31 | 2031-32 | Total | Internal labour | Contract labour | Non-labour |  | Network Overheads Applies | Corporate Overheads Applies | % of total network overheads | % of total corporate overheads | Replacement - Major Stations | Replacement - Other | Compliance | Resillience | ICT capex | Property capex | Fleet capex | Other non-network capex | Capitalised network overheads | Capitalised corporate overheads |  | Secondary | Switchgear | Transformers | Reactive | Towers and Conductor | Establishment | Communications | Inventory | IT | Vehicles | Other (Non-Network) | Premises | Land | Easements | Polymeric Insulators | Leases L&B - Short Lives | Head Office Leases | Buildings - Capital Works | In-House Software
| 1 | MLTS CB Replacement | TD-0006168 |  | Major Station | Replacement - Major Stations | Replacement | 15858.9386 | 18024.4202 | 9967.947 | 355.361 | 0 | 0 | 0 | 10323.308 | 10% | 50% | 40% |  | Yes | No |  |  | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  | 2.583% | 77.2% | 0% | 0% | 3.024% | 16.9% | 0.2935% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 2 | TSTS - Tx and Switchgear Replacement | TD-0007772 |  | Major Station | Replacement - Major Stations | Replacement | 13386.9566 | 8266.6924 | 0 | 0 | 0 | 0 | 0 | 0 | 10% | 50% | 40% |  | Yes | No |  |  | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  | 14.29% | 39.21% | 38.01% | 0% | 0% | 8.483% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 3 | SHTS Transformer and CB Replacement | TD-0007996 |  | Major Station | Replacement - Major Stations | Replacement | 12911.9795 | 9520.1414 | 0 | 0 | 0 | 0 | 0 | 0 | 10% | 50% | 40% |  | Yes | No |  |  | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  | 14.29% | 39.21% | 38.01% | 0% | 0% | 8.483% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 4 | RCTS Transformer & SwitchgearReplacement | TD-0008004 |  | Major Station | Replacement - Major Stations | Replacement | 6449.2634 | 22907.7514 | 16785.9097 | 3434.1792 | 0 | 0 | 0 | 20220.0889 | 10% | 50% | 40% |  | Yes | No |  |  | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  | 4.484% | 8.371% | 66.3% | 0% | 5.064% | 15% | 0.7852% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 5 | SYTS 500kV GIS Replacement | TD-0008033 |  | Major Station | Replacement - Major Stations | Replacement | 30909.3175 | 14861.5619 | 25472.6127 | 4266.5771 | 0 | 0 | 0 | 29739.1898 | 10% | 50% | 40% |  | Yes | No |  |  | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  | 9.142% | 33.07% | 0% | 0% | 27.36% | 23.04% | 7.382% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 6 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% |  | No | No |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 7 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% |  | No | No |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 8 | KTS 500/220kV Transformer Replacement | TD-0003454 |  | Major Station | Replacement - Major Stations | Replacement | 12569.0291 | 26000.2693 | 58955.7881 | 58955.7881 | 48467.4466 | 16187.1902 | 8908.9877 | 191475.2007 | 10% | 50% | 40% |  | Yes | No |  |  | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  | 4.747% | 11.18% | 73.8% | 0% | 1.541% | 8.5% | 0.2322% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 9 | SMTS 500kV GIS and F2 Transformer Replacement | TD-0008025 |  | Major Station | Replacement - Major Stations | Replacement | 3465.3417 | 20963.614 | 20290.1202 | 56125.2572 | 57219.3023 | 50586.979 | 35476.6135 | 219698.2722 | 10% | 50% | 40% |  | Yes | No |  |  | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  | 10.69% | 33.83% | 21.88% | 0% | 10.11% | 22.55% | 0.9383% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 10 | SMTS 330/220kV Transformer Replacement | TD-0014633 |  | Major Station | Replacement - Major Stations | Replacement | 10178.8762 | 27550.23 | 47092.7256 | 41455.1401 | 0 | 0 | 0 | 88547.8656 | 10% | 50% | 40% |  | Yes | No |  |  | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  | 2.243% | 6.402% | 86.86% | 0% | 1.442% | 2.902% | 0.1529% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 11 | NPSD 220kV GIS | TD-0013613 |  | Major Station | Replacement - Major Stations | Replacement | 0 | 0 | 0 | 0 | 2464.4954 | 15089.674 | 38129.8226 | 55683.9921 | 10% | 50% | 40% |  | Yes | No |  |  | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  | 9.015% | 48.11% | 0% | 0% | 5.484% | 36.4% | 0.9985% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 12 | DDTS H3 330/220kV Transformer and Circuit Breaker Replacement | TD-0008026 |  | Major Station | Replacement - Major Stations | Replacement | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10% | 50% | 40% |  | Yes | No |  |  | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  | 15.2% | 22.79% | 58.24% | 0% | 0% | 3.182% | 0.5823% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 13 | WOTS Spare 330/66/22kV Transformer Procurement | TD-0016808 |  | Major Station | Replacement - Major Stations | Replacement | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10% | 50% | 40% |  | Yes | No |  |  | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 14 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% |  | No | No |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 15 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% |  | No | No |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 16 | ROTS 500 kV GIL Replacement | TD-0013738 |  | Power Cables (Major Projects) | Replacement - Major Stations | Replacement | 0 | 432.6812 | 6416.7167 | 20484.7268 | 16715.0842 | 7313.0258 | 0 | 50929.5535 | 10% | 50% | 40% |  | Yes | No |  |  | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 17 | TTS Circuit Breaker Replacement ​ | TD-0003597 |  | Circuit Breakers (Major Projects) | Replacement - Major Stations | Replacement | 475.3326 | 8329.2416 | 0 | 0 | 0 | 0 | 0 | 0 | 10% | 50% | 40% |  | Yes | No |  |  | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  | 34% | 33% | 0% | 0% | 0% | 33% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 18 | LYPS and HWTS 500kV Circuit Breaker Replacement Stage 2​ | TD-0008023 |  | Circuit Breakers (Major Projects) | Replacement - Major Stations | Replacement | 0 | 689.3143 | 0 | 0 | 3526.165 | 6928.1804 | 9114.6398 | 19568.9852 | 10% | 50% | 40% |  | Yes | No |  |  | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  | 16% | 68% | 0% | 0% | 0% | 16% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 19 | MLTS Reactor Replacement​ | TD-0015755​ |  | Power Transformers and Oil Filled Reactors (Major Projects) | Replacement - Major Stations | Replacement | 0 | 0 | 0 | 0 | 51.9737 | 3309.8824 | 7522.0802 | 10883.9363 | 10% | 50% | 40% |  | Yes | No |  |  | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  | 29% | 19% | 35% | 0% | 0% | 17% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 20 | BATS B2 Transformer Replacement | TD-0015756​ |  | Power Transformers and Oil Filled Reactors (Major Projects) | Replacement - Major Stations | Replacement | 0 | 0 | 0 | 4037.5186 | 15612.4616 | 12157.4861 | 4973.3079 | 36780.7743 | 10% | 50% | 40% |  | Yes | No |  |  | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 21 | MWTS 66kV Circuit Breaker Replacement​ | TD-0008003​ |  | Circuit Breakers (Major Projects) | Replacement - Major Stations | Replacement | 0 | 0 | 0 | 916.605 | 2817.4123 | 4548.7244 | 9487.9345 | 17770.6762 | 10% | 50% | 40% |  | Yes | No |  |  | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  | 35% | 42% | 0% | 0% | 0% | 23% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 22 | TTS B4 Transformer Replacement | TD-0016676 |  | Power Transformers and Oil Filled Reactors (Major Projects) | Replacement - Major Stations | Replacement | 0 | 0 | 0 | 1171.0849 | 6306.4671 | 7307.396 | 3076.6542 | 17861.6023 | 10% | 50% | 40% |  | Yes | No |  |  | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 23 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% |  | No | No |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 24 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% |  | No | No |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 25 | MPLS-TP Metro East Pilot Comms Replace | TD-0010115 |  | Communication Systems | Replacement - Other | Replacement | 865.9651 | 110.645 | 8 | 0 | 0 | 0 | 0 | 8 | 10% | 50% | 40% |  | Yes | No |  |  | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 26 | North East Network Comms Replacement | TD-0009897 |  | Communication Systems | Replacement - Other | Replacement | 3075.5545 | 5553.0179 | 4637.6703 | 0 | 0 | 0 | 0 | 4637.6703 | 10% | 50% | 40% |  | Yes | No |  |  | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 27 | North West SDH Comms Replacement | TD-0013861 |  | Communication Systems | Replacement - Other | Replacement | 865.3762 | 2562.3882 | 0 | 0 | 0 | 0 | 0 | 0 | 10% | 50% | 40% |  | Yes | No |  |  | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 28 | Phasor Measurement Units Project 2024 | TD-0014486 |  | PMU Installation | Replacement - Other | Replacement | 2421.7836 | 4923.9249 | 0 | 0 | 0 | 0 | 0 | 0 | 10% | 50% | 40% |  | Yes | No |  |  | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 29 | South West Network Comms Replacement | TD-0010117 |  | Communication Systems | Replacement - Other | Replacement | 2878.8141 | 6365.147 | 11310.4409 | 1036.1447 | 0 | 0 | 0 | 12346.5857 | 10% | 50% | 40% |  | Yes | No |  |  | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 30 | Transmission Insulator Replacement | TD-0014597 |  | Transmission Line Insulators | Replacement - Other | Replacement | 11577.9451 | 18612.5407 | 20 | 0 | 0 | 0 | 0 | 20 | 10% | 50% | 40% |  | Yes | No |  |  | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0%
| 31 | T624 to T628B HYTS-APD tower replacement | TD-0012063 |  | Transmission Line Structures | Replacement - Other | Replacement | 24954.5725 | 29410.699 | 405.693 | 0 | 0 | 0 | 0 | 405.693 | 10% | 50% | 40% |  | Yes | No |  |  | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 32 | Portland tower replacement - Stage 2 | TD-0014579 |  | Transmission Line Structures | Replacement - Other | Replacement | 1728.2088 | 18032.648 | 74418.6047 | 79069.7674 | 0 | 0 | 0 | 153488.3721 | 10% | 50% | 40% |  | Yes | No |  |  | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 33 | VNSC & Comms Sites Battery Replacement | TD-0013827 |  | Communication Systems | Replacement - Other | Replacement | 1389.4641 | 9810.4535 | 5190.3504 | 0 | 0 | 0 | 0 | 5190.3504 | 10% | 50% | 40% |  | Yes | No |  |  | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 34 | Tranche1 Rectification Low Spans, TL | TD-0014572 |  | Management of Transmission Line Ground Clearances | Replacement - Other | Replacement | 4262.3597 | 10988.7908 | 6919.6908 | 5189.2649 | 612.7834 | 0 | 0 | 12721.739 | 10% | 50% | 40% |  | Yes | No |  |  | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 35 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% |  | No | No |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 36 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% |  | No | No |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 37 | Auxiliary Power Supplies | Program |  | Auxiliary Power Supplies | Replacement - Other | Replacement | 0 | 0 | 3214.8837 | 3214.8837 | 3214.8837 | 3214.8837 | 3214.8837 | 16074.4186 | 10% | 50% | 40% |  | Yes | No |  |  | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 38 | Circuit Breakers | Program |  | Circuit Breakers | Replacement - Other | Replacement | 0 | 0 | 2084.9068 | 2084.9068 | 2084.9068 | 2084.9068 | 2084.9068 | 10424.534 | 10% | 50% | 40% |  | Yes | No |  |  | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 39 | Civil Infrastructure | Program |  | Civil Infrastructure | Replacement - Other | Replacement | 0 | 0 | 1748.8372 | 1748.8372 | 1748.8372 | 1748.8372 | 1748.8372 | 8744.186 | 10% | 50% | 40% |  | Yes | No |  |  | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 40 | Communication Systems | Program |  | Communication Systems | Replacement - Other | Replacement | 0 | 0 | 10717.2808 | 10717.2808 | 10717.2808 | 10717.2808 | 10717.2808 | 53586.4038 | 10% | 50% | 40% |  | Yes | No |  |  | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 41 | Disconnectors and Earth Switches | Program |  | Disconnectors and Earth Switches | Replacement - Other | Replacement | 0 | 0 | 1371.1628 | 1371.1628 | 1371.1628 | 1371.1628 | 1371.1628 | 6855.814 | 10% | 50% | 40% |  | Yes | No |  |  | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 42 | Fire Detection and Suppression | Program |  | Fire Detection and Suppression | Compliance | Replacement | 0 | 0 | 560 | 560 | 560 | 560 | 560 | 2800 | 10% | 50% | 40% |  | Yes | No |  |  | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 43 | Instrument Transformers | Program |  | Instrument Transformers | Replacement - Other | Replacement | 0 | 0 | 483.7209 | 483.7209 | 483.7209 | 483.7209 | 483.7209 | 2418.6047 | 10% | 50% | 40% |  | Yes | No |  |  | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 44 | Power Transformers and Oil Filled Reactors | Program |  | Power Transformers and Oil Filled Reactors | Replacement - Other | Replacement | 0 | 0 | 2428.4831 | 2428.4831 | 2428.4831 | 2428.4831 | 2428.4831 | 12142.4156 | 10% | 50% | 40% |  | Yes | No |  |  | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 45 | Secondary Systems | Program |  | Secondary Systems | Replacement - Other | Replacement | 0 | 0 | 5685.0542 | 5685.0542 | 5685.0542 | 5685.0542 | 5685.0542 | 28425.2712 | 10% | 50% | 40% |  | Yes | No |  |  | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 46 | Surge Diverters | Program |  | Surge Diverters | Replacement - Other | Replacement | 0 | 0 | 366.5116 | 366.5116 | 366.5116 | 366.5116 | 366.5116 | 1832.5581 | 10% | 50% | 40% |  | Yes | No |  |  | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 47 | Transmission Line Insulators | Program |  | Transmission Line Insulators | Replacement - Other | Replacement | 0 | 0 | 14657.8558 | 14657.8558 | 14657.8558 | 14657.8558 | 14657.8558 | 73289.2791 | 10% | 50% | 40% |  | Yes | No |  |  | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0%
| 48 | Management of Transmission Line Ground Clearances | Program |  | Management of Transmission Line Ground Clearances | Compliance | Replacement | 0 | 0 | 1825.7561 | 1825.7561 | 1825.7561 | 1825.7561 | 1825.7561 | 9128.7805 | 10% | 50% | 40% |  | Yes | No |  |  | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 49 | Transmission Line Structures | Program |  | Transmission Line Structures | Replacement - Other | Replacement | 0 | 0 | 2069.3566 | 2069.3566 | 2069.3566 | 2069.3566 | 2069.3566 | 10346.7828 | 10% | 50% | 40% |  | Yes | No |  |  | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 50 | Transmission Line Fall Arrest Towers | Program |  | Transmission Line Structures (Compliance) | Compliance | Replacement | 0 | 0 | 1040 | 1040 | 1040 | 1040 | 1040 | 5200 | 10% | 50% | 40% |  | Yes | No |  |  | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 51 | Transmission Lines Fall Arrest System (FAS) Racks | Program |  | Transmission Line Structures (Compliance) | Compliance | Replacement | 0 | 0 | 300 | 300 | 300 | 300 | 300 | 1500 | 10% | 50% | 40% |  | Yes | No |  |  | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 52 | Transmission Tower Resilience Program | Program |  | Transmission Line Structures (Resilience) | Resillience | Replacement | 0 | 0 | 2432.7676 | 2432.7676 | 2432.7676 | 2432.7676 | 2432.7676 | 12163.8379 | 10% | 50% | 40% |  | Yes | No |  |  | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% |  | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 53 | Transmission Lines Conductors (GW & Ph Cond) | Program |  | Transmission Lines Conductors (GW & Ph Cond) | Replacement - Other | Replacement | 0 | 0 | 1742.9451 | 1742.9451 | 1742.9451 | 1742.9451 | 1742.9451 | 8714.7255 | 10% | 50% | 40% |  | Yes | No |  |  | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 54 | Transmission Lines Conductors (GW & Ph Cond) | Program |  | Transmission Lines Conductors (Compliance) | Compliance | Replacement | 0 | 0 | 2489.3117 | 2489.3117 | 2489.3117 | 2489.3117 | 2489.3117 | 12446.5584 | 10% | 50% | 40% |  | Yes | No |  |  | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 55 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% |  | No | No |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 56 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% |  | No | No |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 57 | Environmental | Program |  | Environmental | Compliance | Replacement | 0 | 0 | 1024.5359 | 1024.5359 | 1024.5359 | 1024.5359 | 1024.5359 | 5122.6795 | 10% | 50% | 40% |  | Yes | No |  |  | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 58 | Rework | Program |  | Environmental | Compliance | Replacement | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10% | 50% | 40% |  | Yes | No |  |  | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 59 | Consultant | Program |  | Environmental | Compliance | Replacement | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10% | 50% | 40% |  | Yes | No |  |  | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 60 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% |  | No | No |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 61 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% |  | No | No |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 62 | Metering | Program |  | Metering | Replacement - Other | Replacement | 0 | 0 | 2095.5479 | 2095.5479 | 2095.5479 | 2095.5479 | 2095.5479 | 10477.7394 | 10% | 50% | 40% |  | Yes | No |  |  | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 63 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% |  | No | No |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 64 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% |  | No | No |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 65 | Testing Equipment | Program |  | Other (Non-Network) | Other non-network capex | Non-network capex | 0 | 0 | 3654.107 | 4542.9346 | 4613.9792 | 1304.6137 | 0 | 14115.6345 | 10% | 0% | 90% |  | No | No |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% |  | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 66 | Vehicles - Replacement - Car | Program |  | Vehicles | Fleet capex | Non-network capex | 0 | 0 | 174.938 | 0 | 0 | 427.6263 | 476.2202 | 1078.7845 | 10% | 0% | 90% |  | No | No |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 67 | Vehicles - Replacement - LCV | Program |  | Vehicles | Fleet capex | Non-network capex | 0 | 0 | 624.9794 | 236.7346 | 1391.9997 | 549.2244 | 236.7346 | 3039.6727 | 10% | 0% | 90% |  | No | No |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 68 | Vehicles - Replacement - HCV | Program |  | Vehicles | Fleet capex | Non-network capex | 0 | 0 | 0 | 367.3959 | 0 | 0 | 0 | 367.3959 | 10% | 0% | 90% |  | No | No |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 69 | Vehicles - Replacement - Other (trailer and plant) | Program |  | Vehicles | Fleet capex | Non-network capex | 0 | 0 | 91.849 | 91.849 | 91.849 | 91.849 | 91.849 | 459.2449 | 10% | 0% | 90% |  | No | No |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 70 | Vehicles - TOMSA - LCV | Program |  | Vehicles | Fleet capex | Non-network capex | 0 | 0 | 0 | 1653.2815 | 1653.2815 | 1653.2815 | 0 | 4959.8446 | 10% | 0% | 90% |  | No | No |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 71 | Vehicles - Growth - Car | Program |  | Vehicles | Fleet capex | Non-network capex | 0 | 0 | 119.4037 | 119.4037 | 119.4037 | 119.4037 | 119.4037 | 597.0183 | 10% | 0% | 90% |  | No | No |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 72 | Vehicles - Growth - LCV | Program |  | Vehicles | Fleet capex | Non-network capex | 0 | 0 | 183.6979 | 183.6979 | 183.6979 | 183.6979 | 183.6979 | 918.4897 | 10% | 0% | 90% |  | No | No |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 73 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% |  | No | No |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 74 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% |  | No | No |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 75 | Building Services | Program |  | Premises | Property capex | Non-network capex | 0 | 0 | 490 | 595 | 325 | 300 | 300 | 2010 | 10% | 50% | 40% |  | No | No |  |  | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0%
| 76 | Fitout Capex | Program |  | Premises | Property capex | Non-network capex | 0 | 0 | 4402.6506 | 0 | 0 | 2150.93 | 0 | 6553.5805 | 10% | 50% | 40% |  | No | No |  |  | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0%
| 77 | South Morang Training Centre | Program |  | Premises | Property capex | Non-network capex | 0 | 0 | 6130 | 6130 | 0 | 0 | 0 | 12260 | 10% | 50% | 40% |  | No | No |  |  | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0%
| 78 | Head Office Leases | Program |  | Capitalised Leases | Property capex | Non-network capex | 0 | 0 | 8596.7335 | 0 | 0 | 10214.2297 | 0 | 18810.9632 | 0% | 0% | 100% |  | No | No |  |  | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0%
| 79 | Leases L&B - Short Lives | Program |  | Capitalised Leases | Property capex | Non-network capex | 0 | 0 | 230.9953 | 109.9729 | 313.5745 | 141.5836 | 245.9953 | 1042.1216 | 0% | 0% | 100% |  | No | No |  |  | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0%
| 80 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% |  | No | No |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 81 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% |  | No | No |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 82 | Advanced Energy Management System - Connection asset demand management | Advanced Energy Management System - Non-recurrent |  | IT | ICT capex | Non-network capex | 0 | 0 | 0 | 0 | 0 | 0 | 10000 | 10000 | 0% | 95% | 5% |  | No | Yes |  |  | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 10% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 90%
| 83 | Advanced Energy Management System - Demand Management Phase 2 | Advanced Energy Management System - Non-recurrent |  | IT | ICT capex | Non-network capex | 0 | 0 | 0 | 0 | 5000 | 0 | 0 | 5000 | 0% | 95% | 5% |  | No | Yes |  |  | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 10% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 90%
| 84 | Advanced Energy Management System - Distributed Photovolataics (DPV) forecasts for modelling | Advanced Energy Management System - Non-recurrent |  | IT | ICT capex | Non-network capex | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 75% | 25% |  | No | Yes |  |  | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 10% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 90%
| 85 | Advanced Energy Management System - Dynamic control room displays | Advanced Energy Management System - Non-recurrent |  | IT | ICT capex | Non-network capex | 0 | 0 | 0 | 0 | 0 | 0 | 1500 | 1500 | 0% | 95% | 5% |  | No | Yes |  |  | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 10% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 90%
| 86 | Advanced Energy Management System - Dynamic Ratings (SOCS & OSSCA) upgrade | Advanced Energy Management System - Non-recurrent |  | IT | ICT capex | Non-network capex | 0 | 0 | 0 | 0 | 0 | 3000 | 0 | 3000 | 0% | 70% | 30% |  | No | Yes |  |  | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 20% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 80%
| 87 | Advanced Energy Management System - Geospatial threat monitoring and forecast | Advanced Energy Management System - Non-recurrent |  | IT | ICT capex | Non-network capex | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 75% | 25% |  | No | Yes |  |  | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 10% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 90%
| 88 | Advanced Energy Management System - HMI upgrades for TOC | Advanced Energy Management System - Non-recurrent |  | IT | ICT capex | Non-network capex | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 5000 | 0% | 100% | 0% |  | No | Yes |  |  | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100%
| 89 | Advanced Energy Management System - Load forecasting by feeder | Advanced Energy Management System - Non-recurrent |  | IT | ICT capex | Non-network capex | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 70% | 30% |  | No | Yes |  |  | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 20% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 80%
| 90 | Advanced Energy Management System - Network operations scenario simulator uplift | Advanced Energy Management System - Non-recurrent |  | IT | ICT capex | Non-network capex | 0 | 0 | 0 | 0 | 2000 | 0 | 0 | 2000 | 0% | 75% | 25% |  | No | Yes |  |  | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 10% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 90%
| 91 | Advanced Energy Management System - Passive knowledge management | Advanced Energy Management System - Non-recurrent |  | IT | ICT capex | Non-network capex | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 75% | 25% |  | No | Yes |  |  | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 10% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 90%
| 92 | Advanced Energy Management System - Ratings management Phase 1 | Advanced Energy Management System - Non-recurrent |  | IT | ICT capex | Non-network capex | 0 | 0 | 500 | 0 | 0 | 0 | 0 | 500 | 0% | 70% | 30% |  | No | Yes |  |  | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 20% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 80%
| 93 | Advanced Energy Management System - Ratings management Phase 2 | Advanced Energy Management System - Non-recurrent |  | IT | ICT capex | Non-network capex | 0 | 0 | 0 | 0 | 2750 | 0 | 0 | 2750 | 0% | 70% | 30% |  | No | Yes |  |  | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 20% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 80%
| 94 | Advanced Energy Management System - Security cameras for network purposes | Advanced Energy Management System - Non-recurrent |  | IT | ICT capex | Non-network capex | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 75% | 25% |  | No | Yes |  |  | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 10% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 90%
| 95 | Advanced Energy Management System - System restart uplift | Advanced Energy Management System - Non-recurrent |  | IT | ICT capex | Non-network capex | 0 | 0 | 0 | 0 | 0 | 3000 | 0 | 3000 | 0% | 95% | 5% |  | No | Yes |  |  | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 10% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 90%
| 96 | Advanced Energy Management System - TASM opex (TBC opex baseline year) | Advanced Energy Management System - Opex |  | IT | ICT capex | Non-network capex | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% |  | No | Yes |  |  | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 97 | Advanced Energy Management System - TASM Phase 2: SAP automation, automated conditions & constraints analysis | Advanced Energy Management System - Non-recurrent |  | IT | ICT capex | Non-network capex | 0 | 0 | 0 | 5000 | 0 | 0 | 0 | 5000 | 0% | 95% | 5% |  | No | Yes |  |  | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 10% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 90%
| 98 | Advanced Energy Management System - TASM Phase 3: Integrating new adjacent capabilities | Advanced Energy Management System - Non-recurrent |  | IT | ICT capex | Non-network capex | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 95% | 5% |  | No | Yes |  |  | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 10% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 90%
| 99 | Advanced Energy Management System - Tx alarm management Phase 2 | Advanced Energy Management System - Non-recurrent |  | IT | ICT capex | Non-network capex | 0 | 0 | 0 | 0 | 0 | 3000 | 0 | 3000 | 0% | 95% | 5% |  | No | Yes |  |  | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 10% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 90%
| 100 | Advanced Energy Management System - VicTNSP capability | Advanced Energy Management System - Non-recurrent |  | IT | ICT capex | Non-network capex | 0 | 0 | 2520 | 0 | 0 | 0 | 0 | 2520 | 0% | 70% | 30% |  | No | Yes |  |  | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 20% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 80%
| 101 | Advanced Energy Management System - Wide Area Monitoring System (Oscillation detection & Monitoring) | Advanced Energy Management System - Non-recurrent |  | IT | ICT capex | Non-network capex | 0 | 0 | 0 | 0 | 0 | 5000 | 5000 | 10000 | 0% | 95% | 5% |  | No | Yes |  |  | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 10% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 90%
| 102 | Advanced Energy Management System - PMU data for incident response and investigation | Advanced Energy Management System - Non-recurrent |  | IT | ICT capex | Non-network capex | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 95% | 5% |  | No | Yes |  |  | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 10% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 90%
| 103 | Advanced Energy Management System - UAV/Drone Inspection | Advanced Energy Management System - Non-recurrent |  | IT | ICT capex | Non-network capex | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 95% | 5% |  | No | Yes |  |  | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 10% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 90%
| 104 | Asset Management & Field Enablement - Centralised data storage (e.g. videos, photos, others) | Asset Management & Field Enablement - Non-recurrent |  | IT | ICT capex | Non-network capex | 0 | 0 | 1625 | 1625 | 0 | 0 | 0 | 3250 | 0% | 95% | 5% |  | No | Yes |  |  | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 10% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 90%
| 105 | Asset Management & Field Enablement - Knowledge management for various documents | Asset Management & Field Enablement - Non-recurrent |  | IT | ICT capex | Non-network capex | 0 | 0 | 1125 | 1125 | 0 | 0 | 0 | 2250 | 0% | 95% | 5% |  | No | Yes |  |  | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 10% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 90%
| 106 | Asset Management & Field Enablement - Asset condition desktop monitoring & more frequent ARM for network capex planning | Asset Management & Field Enablement - Non-recurrent |  | IT | ICT capex | Non-network capex | 0 | 0 | 0 | 2565 | 2565 | 0 | 0 | 5130 | 0% | 75% | 25% |  | No | Yes |  |  | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 10% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 90%
| 107 | Asset Management & Field Enablement - Asset Performance Management (APM) System for maintenance opex optimisation | Asset Management & Field Enablement - Non-recurrent |  | IT | ICT capex | Non-network capex | 0 | 0 | 0 | 0 | 0 | 3825 | 3825 | 7650 | 0% | 75% | 25% |  | No | Yes |  |  | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 10% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 90%
| 108 | Asset Management & Field Enablement - Asset performance analytics using SCADA data | Asset Management & Field Enablement - Non-recurrent |  | IT | ICT capex | Non-network capex | 0 | 0 | 1000 | 0 | 0 | 0 | 0 | 1000 | 0% | 95% | 5% |  | No | Yes |  |  | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 10% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 90%
| 109 | Asset Management & Field Enablement - Automating transformer rating calculations​ | Asset Management & Field Enablement - Non-recurrent |  | IT | ICT capex | Non-network capex | 0 | 0 | 0 | 1000 | 0 | 0 | 0 | 1000 | 0% | 95% | 5% |  | No | Yes |  |  | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 10% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 90%
| 110 | Asset Management & Field Enablement - Consolidate Geospatial Capability | Asset Management & Field Enablement - Non-recurrent |  | IT | ICT capex | Non-network capex | 0 | 0 | 0 | 0 | 1050 | 350 | 0 | 1400 | 0% | 75% | 25% |  | No | Yes |  |  | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 10% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 90%
| 111 | Asset Management & Field Enablement - Tx field mobility | Asset Management & Field Enablement - Non-recurrent |  | IT | ICT capex | Non-network capex | 0 | 0 | 0 | 1000 | 0 | 0 | 0 | 1000 | 0% | 55% | 45% |  | No | Yes |  |  | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100%
| 112 | Asset Management & Field Enablement - Tx Asset Data Enhancement Program | Asset Management & Field Enablement - Non-recurrent |  | IT | ICT capex | Non-network capex | 0 | 0 | 4275 | 0 | 0 | 0 | 0 | 4275 | 0% | 95% | 5% |  | No | Yes |  |  | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 10% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 90%
| 113 | Customer Engagement - Transmission landholder access | Customer Engagement - Non-recurrent |  | IT | ICT capex | Non-network capex | 0 | 0 | 3600 | 0 | 0 | 0 | 0 | 3600 | 0% | 55% | 45% |  | No | Yes |  |  | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100%
| 114 | Metering Systems - Capability for latest meter technology (e.g. meter reading software & meter management solution) | Metering Systems - Non-recurrent |  | IT | ICT capex | Non-network capex | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 70% | 30% |  | No | Yes |  |  | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 20% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 80%
| 115 | Metering Systems - Enhance meter data integrity & analytics | Metering Systems - Non-recurrent |  | IT | ICT capex | Non-network capex | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 100% | 0% |  | No | Yes |  |  | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 10% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 90%
| 116 | Metering Systems - Meter data storage system | Metering Systems - Non-recurrent |  | IT | ICT capex | Non-network capex | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 75% | 25% |  | No | Yes |  |  | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 10% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 90%
| 117 | Metering Systems - Metering asset register | Metering Systems - Non-recurrent |  | IT | ICT capex | Non-network capex | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 95% | 5% |  | No | Yes |  |  | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 10% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 90%
| 118 | Metering Systems - Stream meter data vs polling | Metering Systems - Non-recurrent |  | IT | ICT capex | Non-network capex | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 95% | 5% |  | No | Yes |  |  | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 10% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 90%
| 119 | Digital resilience – applications - Data and Analytics Tx Systems (cloud) | Digital resilience – applications - Recurrent |  | IT | ICT capex | Non-network capex | 0 | 0 | 55.1755 | 55.1755 | 55.1755 | 55.1755 | 55.1755 | 275.8776 | 0% | 100% | 0% |  | No | Yes |  |  | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100%
| 120 | Digital resilience – applications - Enterprise Resource Planning (ERP) | Digital resilience – applications - Recurrent |  | IT | ICT capex | Non-network capex | 0 | 0 | 300 | 2495.9184 | 265.3061 | 0 | 0 | 3061.2245 | 0% | 100% | 0% |  | No | Yes |  |  | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100%
| 121 | Digital resilience – applications - eTerra Upgrade | Digital resilience – applications - Recurrent |  | IT | ICT capex | Non-network capex | 0 | 0 | 1000 | 1500 | 0 | 2500 | 7500 | 12500 | 0% | 100% | 0% |  | No | Yes |  |  | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100%
| 122 | Digital resilience – applications - Geospatial Systems | Digital resilience – applications - Recurrent |  | IT | ICT capex | Non-network capex | 0 | 0 | 0 | 1520 | 0 | 0 | 0 | 1520 | 0% | 100% | 0% |  | No | Yes |  |  | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100%
| 123 | Digital resilience – applications - HSEQ | Digital resilience – applications - Recurrent |  | IT | ICT capex | Non-network capex | 0 | 0 | 91.8367 | 30.6122 | 0 | 0 | 0 | 122.449 | 0% | 100% | 0% |  | No | Yes |  |  | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100%
| 124 | Digital resilience – applications - Identity Management | Digital resilience – applications - Recurrent |  | IT | ICT capex | Non-network capex | 0 | 0 | 0 | 609.1837 | 3.0612 | 0 | 0 | 612.2449 | 0% | 100% | 0% |  | No | Yes |  |  | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100%
| 125 | Digital resilience – applications - OPEX - SaaS/PaaS cloud service growth | Digital resilience – applications - Opex |  | IT | ICT capex | Non-network capex | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 100% | 0% |  | No | Yes |  |  | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100%
| 126 | Digital resilience – applications - Other Business Systems | Digital resilience – applications - Recurrent |  | IT | ICT capex | Non-network capex | 0 | 0 | 235.102 | 235.102 | 235.102 | 235.102 | 235.102 | 1175.5102 | 0% | 100% | 0% |  | No | Yes |  |  | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100%
| 127 | Digital resilience – applications - Protection and Control Settings | Digital resilience – applications - Recurrent |  | IT | ICT capex | Non-network capex | 0 | 0 | 0 | 0 | 0 | 45.9677 | 61.2903 | 107.2581 | 0% | 100% | 0% |  | No | Yes |  |  | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100%
| 128 | Digital resilience – applications - Other TX applications | Digital resilience – applications - Recurrent |  | IT | ICT capex | Non-network capex | 0 | 0 | 700 | 700 | 700 | 700 | 700 | 3500 | 0% | 100% | 0% |  | No | Yes |  |  | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100%
| 129 | Digital resilience – applications - System Integration Platforms | Digital resilience – applications - Recurrent |  | IT | ICT capex | Non-network capex | 0 | 0 | 918.3673 | 306.1224 | 0 | 0 | 0 | 1224.4898 | 0% | 100% | 0% |  | No | Yes |  |  | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100%
| 130 | Digital resilience – applications - Telecommunications Systems (SDMT, CNMS) | Digital resilience – applications - Recurrent |  | IT | ICT capex | Non-network capex | 0 | 0 | 2000 | 1000 | 3000 | 2000 | 0 | 8000 | 0% | 100% | 0% |  | No | Yes |  |  | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100%
| 131 | Digital resilience – applications - Weather and Solar Services | Digital resilience – applications - Recurrent |  | IT | ICT capex | Non-network capex | 0 | 0 | 0 | 0 | 0 | 137.9032 | 183.871 | 321.7742 | 0% | 100% | 0% |  | No | Yes |  |  | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100%
| 132 | Digital resilience – applications - SCADA Data Historian | Digital resilience – applications - Recurrent |  | IT | ICT capex | Non-network capex | 0 | 0 | 0 | 0 | 1140 | 0 | 0 | 1140 | 0% | 100% | 0% |  | No | Yes |  |  | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100%
| 133 | Digital resilience – infrastructure - Data Centre Facilities | Digital resilience – infrastructure - Recurrent |  | IT | ICT capex | Non-network capex | 0 | 0 | 228.5714 | 228.5714 | 228.5714 | 228.5714 | 228.5714 | 1142.8571 | 0% | 30% | 70% |  | No | Yes |  |  | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 134 | Digital resilience – infrastructure - Fire Supression (DC) | Digital resilience – infrastructure - Recurrent |  | IT | ICT capex | Non-network capex | 0 | 0 | 240 | 240 | 240 | 240 | 240 | 1200 | 0% | 30% | 70% |  | No | Yes |  |  | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 135 | Digital resilience – infrastructure - HiSec Network | Digital resilience – infrastructure - Recurrent |  | IT | ICT capex | Non-network capex | 0 | 0 | 1400 | 1400 | 1400 | 1400 | 1400 | 7000 | 0% | 30% | 70% |  | No | Yes |  |  | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 136 | Digital resilience – infrastructure - Physical security digital infrastructure (servers, storage, network bandwidth) | Digital resilience – infrastructure - Recurrent |  | IT | ICT capex | Non-network capex | 0 | 0 | 230 | 230 | 220 | 220 | 100 | 1000 | 0% | 30% | 70% |  | No | Yes |  |  | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 137 | Digital resilience – infrastructure - Shared Data Centre Infrastructure | Digital resilience – infrastructure - Recurrent |  | IT | ICT capex | Non-network capex | 0 | 0 | 582.6 | 582.6 | 582.6 | 582.6 | 582.6 | 2913 | 0% | 30% | 70% |  | No | Yes |  |  | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 138 | Digital resilience – infrastructure - Other infrastructure upgrades (e.g. Zetron, RADAR, Pegasus, Pacsis - does the settings of the ratings) | Digital resilience – infrastructure - Recurrent |  | IT | ICT capex | Non-network capex | 0 | 0 | 1000 | 1000 | 1000 | 1500 | 1000 | 5500 | 0% | 30% | 70% |  | No | Yes |  |  | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 139 | Digital resilience – infrastructure - System Integration Platforms - HW | Digital resilience – infrastructure - Recurrent |  | IT | ICT capex | Non-network capex | 0 | 0 | 582.9 | 0 | 0 | 0 | 0 | 582.9 | 0% | 30% | 70% |  | No | Yes |  |  | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 140 | Digital resilience – infrastructure - Telecommunications Systems (HW) | Digital resilience – infrastructure - Recurrent |  | IT | ICT capex | Non-network capex | 0 | 0 | 0 | 0 | 2000 | 1000 | 0 | 3000 | 0% | 30% | 70% |  | No | Yes |  |  | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 141 | Digital resilience – infrastructure - User Devices (laptops, mobile, peripherals) | Digital resilience – infrastructure - Recurrent |  | IT | ICT capex | Non-network capex | 0 | 0 | 48.9796 | 48.9796 | 48.9796 | 48.9796 | 48.9796 | 244.898 | 0% | 30% | 70% |  | No | Yes |  |  | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 142 | Digital Resilience – infrastructure - SCADA Data Historian - Infra | Digital Resilience – infrastructure - Recurrent |  | IT | ICT capex | Non-network capex | 0 | 0 | 0 | 0 | 0 | 1900 | 0 | 1900 | 0% | 30% | 70% |  | No | Yes |  |  | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 143 | Digital Resilience – infrastructure - OT Comms Equipment firmware updates | Digital Resilience – infrastructure - Recurrent |  | IT | ICT capex | Non-network capex | 0 | 0 | 0 | 0 | 600 | 0 | 0 | 600 | 0% | 30% | 70% |  | No | Yes |  |  | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 144 | Cyber security - Cyber Security Systems Refresh | Cyber security - Recurrent |  | IT | ICT capex | Non-network capex | 0 | 0 | 4080 | 4080 | 4080 | 4080 | 4080 | 20400 | 0% | 75% | 25% |  | No | Yes |  |  | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 10% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 90%
| 145 | Cyber security - Cyber New Threat/Capability uplift (PWC Cyber Security Program) | Cyber security - Non-recurrent |  | IT | ICT capex | Non-network capex | 0 | 0 | 5401.4 | 5401.4 | 5401.4 | 5401.4 | 5401.4 | 27006.9999 | 0% | 100% | 0% |  | No | Yes |  |  | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100%
| 146 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% |  | No | No |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 147 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% |  | No | No |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 148 | SOCI - CCTV (Building and Poles) | Program |  | SOCI | Compliance | Replacement | 767.75 | 3374.3277 | 1690.2911 | 1107.2369 | 331.7628 | 306.6 | 229.95 | 3665.8407 | 10% | 50% | 40% |  | Yes | No |  |  | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 149 | SOCI - Lighting | Program |  | SOCI | Compliance | Replacement | 24.92 | 142.26 | 269.49 | 200.97 | 0 | 0 | 0 | 470.46 | 10% | 50% | 40% |  | Yes | No |  |  | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 150 | SOCI - Sub-component Protection | Program |  | SOCI | Compliance | Replacement | 66.875 | 317.6562 | 417.9688 | 200.625 | 0 | 0 | 0 | 618.5938 | 10% | 50% | 40% |  | Yes | No |  |  | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 151 | SOCI - Signage | Program |  | SOCI | Compliance | Replacement | 25.25 | 101 | 120.125 | 164.6875 | 126.25 | 126.25 | 94.6875 | 632 | 10% | 50% | 40% |  | Yes | No |  |  | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 152 | SOCI - Window Protection | Program |  | SOCI | Compliance | Replacement | 15.2 | 69.85 | 84.3 | 34.65 | 0 | 0 | 0 | 118.95 | 10% | 50% | 40% |  | Yes | No |  |  | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 153 | SOCI - Security Fencing | Program |  | SOCI | Compliance | Replacement | 2109.25 | 11327.8875 | 8040.7786 | 3374.2171 | 6417.5 | 4640 | 3480 | 25952.4958 | 10% | 50% | 40% |  | Yes | No |  |  | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 154 | SOCI - Gate Installation and Paving Works (exclusive of Gate Motors) | Program |  | SOCI | Compliance | Replacement | 146.25 | 764.46 | 1130.63 | 460.5 | 0 | 0 | 0 | 1591.13 | 10% | 50% | 40% |  | Yes | No |  |  | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 155 | SOCI - Access Control | Program |  | SOCI | Compliance | Replacement | 0 | 0 | 72 | 72 | 72 | 72 | 0 | 288 | 10% | 50% | 40% |  | Yes | No |  |  | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 156 | Non-SOCI Security - Fault Finding - Replacement of Broken Assets | Program |  | Non-SOCI Security | Compliance | Replacement | 25 | 100 | 100 | 92.5 | 65 | 50 | 50 | 357.5 | 10% | 50% | 40% |  | Yes | No |  |  | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 157 | Non-SOCI Security - Replacement Gate Motors | Program |  | Non-SOCI Security | Compliance | Replacement | 0 | 0 | 140.4 | 421.2 | 0 | 0 | 0 | 561.6 | 10% | 50% | 40% |  | Yes | No |  |  | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 158 | Non-SOCI Security - Padlock Protection | Program |  | Non-SOCI Security | Compliance | Replacement | 0 | 0 | 75.0938 | 225.2812 | 0 | 0 | 0 | 300.375 | 10% | 50% | 40% |  | Yes | No |  |  | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 159 | Non-SOCI Security - CCTV End of Life replacement (Tier 1 and Tier 2) | Program |  | Non-SOCI Security | Compliance | Replacement | 0 | 0 | 0 | 0 | 0 | 0 | 767.04 | 767.04 | 10% | 50% | 40% |  | Yes | No |  |  | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 160 | Non-SOCI Security - Trailer technology replacement | Program |  | Non-SOCI Security | Compliance | Replacement | 0 | 0 | 0 | 0 | 0 | 80 | 240 | 320 | 10% | 50% | 40% |  | Yes | No |  |  | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 161 | Non-SOCI Security - CCTV Server Replacement | Program |  | Non-SOCI Security | Compliance | Replacement | 0 | 0 | 0 | 0 | 0 | 255.75 | 767.25 | 1023 | 10% | 50% | 40% |  | Yes | No |  |  | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 162 | Non-SOCI Security - Rapid Deployment camera | Program |  | Non-SOCI Security | Compliance | Replacement | 0 | 75 | 225 | 0 | 0 | 0 | 0 | 225 | 10% | 50% | 40% |  | Yes | No |  |  | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 163 | Non-SOCI Security - Security Control Room Upgrade | Program |  | Non-SOCI Security | Compliance | Replacement | 0 | 312.5 | 937.5 | 0 | 0 | 0 | 0 | 937.5 | 10% | 50% | 40% |  | Yes | No |  |  | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 164 | Non-SOCI Security - Future Technology | Program |  | Non-SOCI Security | Compliance | Replacement | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10% | 50% | 40% |  | Yes | No |  |  | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 165 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | [5 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 166 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | [5 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 167 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | [5 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 168 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | [5 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 169 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | [5 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 170 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0%
| 171 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0%
| 172 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0%
| 173 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0%
| 174 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0%
| 175 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0%
| 176 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0%
| 177 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0%
178
179
180
181
182
183
184
185
186
187
188
189
190
191
192
193
194
195
196
197
198
199
200