## Overview
Overview of this model
This model: - is a supporting document to the 'Labour and Indirect Costs forecast for HumeLink Project' document, dated April 2022; - substantiates the ‘Corporate and Network Overhead’ capital expenditure (Capex) for the HumeLink Project through to the FID (Financial Investment Decision), which is linked to when the AER accepts TransGrid's Final CPA and currently expected around 30 June 2024; - relates partly to the current regulatory period 2018-19 to 2022-23 (2018-23) and partly to the subsequent regulatory period 2023-24 to 2027-28 (2023-28); and - reflects actuals up to end December 2021 and forecasts after that date.
Model structure / Navigation instructions
Below outlines the key components of this model which map to the respective section of the written report (for example, section 7 of the report relates to 'Key Assumptions' and this is reflected in the worksheet titled 'A. Key Assumptions').
Reference to HumeLink Labour and Indirect Costs report | Header worksheets | Description of worksheet
Section 7 | A. Key assumptions | The Key assumptions worksheet outlines the key assumptions and rates which apply across the below listed categories.
Section 3 | B. HumeLink Summary Historical and Forecast | Consolidates details from the Historical and Forecast worksheets to provide a summarised overview of the total forecast corporate and network overhead costs for HumeLink through to 30 June 2024.
Section 2 | C. Historical Labour and Indirect Capex | Provides a summarised view of the Labour and Indirect Capex incurred to date (i.e. the 'Actuals') to progress the HumeLink Project. The Actuals have been incurred since FY18 through to 31 December 2021 (after which the HumeLink forecast costs commence, i.e. from 1 January 2022).
| C.1 Historical Indirect-sub-cat | Provides a more detailed view of the Indirect Capex incurred to date (i.e. the 'Actuals') to progress the HumeLink Project. The Actuals have been incurred since FY18 through to 31 December 2021 (after which the HumeLink forecast costs commence, i.e. from 1 January 2022).
Sections 5-6 | D. Forecast Labour and Indirect Capex | Provides a summarised view of the forecast Labour and Indirect Capex through to 30 June 2024. This is supported by worksheets relating to Labour, Labour Related and Non-Labour costs.
| - Labour | Forecasts Labour costs by applying a schedule of hourly rates to monthly FTE forecasts for each relevant type of labour resource. The bottom-up build is undertaken for five categories - Project management, Transaction Procurement Support, Community and Stakeholder Engagement, Land and Environment, Other support and Corporate Roles. Some outsourced labour resources have also been included (and separately identified) in this spreadsheet because they will effectively function as part of the internal project team. The associated costs have been forecast at the contracted amounts.
| - Labour Related | Forecasts Labour Related costs in the categories of Training, Recruitment, and IT Hardware. For the first of these (i.e. Training), the costs are related to the forecasts FTEs on the Labour spreadsheet. For the other categories, the costs reflect bottom up estimates prepared outside this spreadsheet based on what is required to meet the project schedule for HumeLink.
| - Indirect | Forecasts Indirect costs, which relate to a wide range of professional and consulting services, together with tender payments and associated facilities costs and early equipment procurement and design.

## A. Key assumptions
Key Assumptions
The following rates have been applied across the categories of cost estimates.
Any changes made in the black cells link to the corresponding calculations in the worksheets
Escalation and Labour Rate restatement
Costs have been collected in current year rates.
TransGrid's standard labour rates as at 1 July 2021 (and applying through 2021-22) have been used in labour costing forecasts
In order to restate these figures to Real $ June 2018, discount factors have been applied as follows:
| Labour real cost escalation per year (from ACCC Final Decision) | 0.81%
|  | 2017-18 | 2018-19 | 2019-20 | 2020-21 | 2021-22 | 2022-23 | 2023-24
| Labour real cost de-escalation | 1 | 0.99197 | 0.98399 | 0.97609 | 0.96825 | 0.96047 | 0.95275
| June quarter CPI - actual to 2020-21 then forecast (from ACCC Final Decision) |  | 1.593% | -0.3484% | 3.846% | 2.75% | 2.25% | 2.35%
| CPI discount | 1 | 0.98432 | 0.98776 | 0.95118 | 0.92572 | 0.90535 | 0.88456
Salary assumptions
| Oncosts - contract | 30.3%
| Oncosts - Enterprise Agreement | 35.3%
| Support costs | 90%
| Indexation - 2022-23 and 2023-24 - contract | 3%
| Indexation - 2022-23 and 2023-24 - Enterprise Agreement | 2%
| Number of FTE hours per month | 150
| Forecast months in 2021-22 | 6
Training cost assumptions
| Training cost per annum per employee - Real $ June 2018 | 1500 | (Applied to Project Management, and Land and Environment teams)

## B. HumeLink Summary
HumeLink Summary - Historical + Forecast
Labour and Indirect Capex - $ Real 30 June 2018, with Labour and Labour Related Costs restated to remove real labour price growth
| Cost category | 2017-18 | 2018-19 | 2019-20 | 2020-21 | 2021-22 | 2022-23 | 2023-24 | Total
Labour (see Note)
| Project Management | 0 | 233447.7237 | 2661967.3212 | 3357542.2052 | 7348579.7332 | 11871964.9782 | 11751036.6893 | 37224538.6508
| Transaction procurement support | 0 | 0 | 0 | 407979.2308 | 1286812.8796 | 3475311.2777 | 1631885.772 | 6801989.1601
| Community and Stakeholder Engagement | 0 | 4859.0438 | 311097.7461 | 1021876.141 | 1130076.7436 | 1061005.5574 | 939269.8166 | 4468185.0485
| Land and Environment | 0 | 73171.2081 | 1205013.1224 | 2066372.184 | 3032361.8697 | 3991517.1063 | 3544976.9178 | 13913412.4082
| Other Support and Corporate Roles | 0 | 40079.2814 | 1471249.555 | 2056167.3539 | 1991890.08 | 1582074.8482 | 1717327.2498 | 8858788.3683
| Sub-total | 0 | 351557.257 | 5649327.7446 | 8909937.1148 | 14789721.3062 | 21981873.7679 | 19584496.4454 | 71266913.6359
Labour Related
| Project Management | 0 | 0 | 0 | 0 | 72157.2486 | 244068.3969 | 134627.4008 | 450853.0463
| Transaction procurement support | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Community and Stakeholder Engagement | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Land and Environment | 0 | 0 | 0 | 0 | 9245.1562 | 19282.5 | 17132.5 | 45660.1562
| Other Support and Corporate Roles | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Sub-total | 0 | 0 | 0 | 0 | 81402.4049 | 263350.8969 | 151759.9008 | 496513.2026
Indirect
| Procurement | 0 | 0 | 0 | 0 | 1644756.9305 | 24788867.7989 | 1120703.2543 | 27554327.9838
| Project Development | 0 | 0 | 49597.9521 | 1652001.6167 | 7057054.3091 | 14897390.6312 | 9201168.0124 | 32857212.5215
| Land and Environment | 0 | 124785.5606 | 1483625.7381 | 2421758.6467 | 11251215.8115 | 10211085.8176 | 3353555.9517 | 28846027.5262
| Community and Stakeholder Engagement | 0 | 0 | 157743.8861 | 1355513.163 | 4307838.4384 | 4006636.0298 | 8731142.7664 | 18558874.2837
| Regulatory Approvals and Other Support Costs | 376333.63 | 159228.976 | 1196392.6048 | 980506.1223 | 3083441.1839 | 1841625.857 | 4260853.0866 | 11898381.4605
| Sub-total | 376333.63 | 284014.5366 | 2887360.1811 | 6409779.5486 | 27344306.6734 | 55745606.1346 | 26667423.0715 | 119714823.7757
| Total | 376333.63 | 635571.7935 | 8536687.9257 | 15319716.6635 | 42215430.3844 | 77990830.7993 | 46403679.4177 | 191478250.6142
TRUE
Note - For Historical costs, the Labour category above includes both Labour and Labour-Related Costs.

## C. Historical Lab & Indirect
Historical Labour and Indirect Capex
Incurred between 1 July 2017 and 31 December 2021
|  | Labour and Indirect Capex - Nominal | [7 empty] | Labour and Indirect Capex - $ Real 30 June 2018, with Labour and Labour Related Costs restated to remove real labour price growth
| Cost category | 2017-18 | 2018-19 | 2019-20 | 2020-21 | 2021-22 | 2022-23 | 2023-24 | Total | 2017-18 | 2018-19 | 2019-20 | 2020-21 | 2021-22 | 2022-23 | 2023-24 | Total
Labour and Labour Related
| Project Management | 0 | 239087.4075 | 2738782.4114 | 3616348.8838 | 2782314.66 |  |  | 9376533.3627 | 0 | 233447.7237 | 2661967.3212 | 3357542.2052 | 2493859.3564 | 0 | 0 | 8746816.6064
| Transaction procurement support | 0 | 0 | 0 | 439427.16 | 229110.22 |  |  | 668537.38 | 0 | 0 | 0 | 407979.2308 | 205357.3142 | 0 | 0 | 613336.545
| Community and Stakeholder Engagement | 0 | 4976.4297 | 320074.9417 | 1100644.5834 | 630844.98 |  |  | 2056540.9349 | 0 | 4859.0438 | 311097.7461 | 1021876.141 | 565442.3917 | 0 | 0 | 1903275.3226
| Land and Environment | 0 | 74938.895 | 1239785.5973 | 2225652.6602 | 1242126.11 |  |  | 4782503.2625 | 0 | 73171.2081 | 1205013.1224 | 2066372.184 | 1113349.2073 | 0 | 0 | 4457905.7218
| Other Support and Corporate Roles | 0 | 41047.5259 | 1513704.6845 | 2214661.2196 | 922251.76 |  |  | 4691665.19 | 0 | 40079.2814 | 1471249.555 | 2056167.3539 | 826637.6962 | 0 | 0 | 4394133.8865
| Sub-total | 0 | 360050.2581 | 5812347.6349 | 9596734.507 | 5806647.73 | 0 | 0 | 21575780.13 | 0 | 351557.257 | 5649327.7446 | 8909937.1148 | 5204645.9657 | 0 | 0 | 20115468.0822
Indirect
| Procurement | 0 | 0 | 0 | 0 | 246958 | 0 | 0 | 246958 | 0 | 0 | 0 | 0 | 228614.2364 | 0 | 0 | 228614.2364
| Project Development | 0 | 0 | 50212.44 | 1736794.62 | 1514735.15 | 0 | 0 | 3301742.21 | 0 | 0 | 49597.9521 | 1652001.6167 | 1402222.3201 | 0 | 0 | 3103821.8889
| Land and Environment | 0 | 126773.2952 | 1502006.9419 | 2546061.3029 | 3689930.95 | 0 | 0 | 7864772.49 | 0 | 124785.5606 | 1483625.7381 | 2421758.6467 | 3415847.0131 | 0 | 0 | 7446016.9585
| Community and Stakeholder Engagement | 0 | 0 | 159698.2351 | 1425088.1749 | 1708961.05 | 0 | 0 | 3293747.46 | 0 | 0 | 157743.8861 | 1355513.163 | 1582021.3379 | 0 | 0 | 3095278.3869
| Regulatory Approvals and Other Support Costs | 376333.63 | 161765.3667 | 1211215.168 | 1030832.9852 | 1407064.51 | 0 | 0 | 4187211.66 | 376333.63 | 159228.976 | 1196392.6048 | 980506.1223 | 1302549.3346 | 0 | 0 | 4015010.6677
| Sub-total | 376333.63 | 288538.6619 | 2923132.7851 | 6738777.083 | 8567649.66 | 0 | 0 | 18894431.82 | 376333.63 | 284014.5366 | 2887360.1811 | 6409779.5486 | 7931254.2422 | 0 | 0 | 17888742.1384
| Total | 376333.63 | 648588.92 | 8735480.42 | 16335511.59 | 14374297.39 | 0 | 0 | 40470211.95 | 376333.63 | 635571.7935 | 8536687.9257 | 15319716.6635 | 13135900.2079 | 0 | 0 | 38004210.2206
|  | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE

## C.1 Historical Indirect-sub-cat
Historical Indirect Capex - by sub-category
Incurred between 1 July 2017 and 31 December 2021
|  | Indirect Capex - Nominal | [7 empty] | Indirect Capex - $ Real 30 June 2018
| Cost category | 2017-18 | 2018-19 | 2019-20 | 2020-21 | 2021-22 | 2022-23 | 2023-24 | Total | 2017-18 | 2018-19 | 2019-20 | 2020-21 | 2021-22 | 2022-23 | 2023-24 | Total
Procurement
| Bidder Payments | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Data Room Services | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Transaction management expenses | 0 | 0 | 0 | 0 | 246958 |  |  | 246958 | 0 | 0 | 0 | 0 | 228614.2364 | 0 | 0 | 228614.2364
| Sub-total | 0 | 0 | 0 | 0 | 246958 | 0 | 0 | 246958 | 0 | 0 | 0 | 0 | 228614.2364 | 0 | 0 | 228614.2364
Project Development
| External Legal Expenses | 0 | 0 | 0 | 137613.98 | 437521 |  |  | 575134.98 | 0 | 0 | 0 | 130895.4524 | 405022.4303 | 0 | 0 | 535917.8827
| Project Management / Concept Engineering | 0 | 0 | 50212.44 | 1150293.27 | 828903.8 |  |  | 2029409.51 | 0 | 0 | 49597.9521 | 1094134.171 | 767333.7544 | 0 | 0 | 1911065.8775
| Geotech and Surveys | 0 | 0 | 0 | 53395 | 0 |  |  | 53395 | 0 | 0 | 0 | 50788.1734 | 0 | 0 | 0 | 50788.1734
| Owners Engineer |  |  |  |  | 24102.5 |  |  | 24102.5 | 0 | 0 | 0 | 0 | 22312.1933 | 0 | 0 | 22312.1933
| Specialist Studies | 0 | 0 | 0 | 171922.29 | 78918.75 |  |  | 250841.04 | 0 | 0 | 0 | 163528.7775 | 73056.7537 | 0 | 0 | 236585.5312
| Travel/accomodation/PPWA and minor expenses | 0 | 0 | 0 | 67352.26 | 28581.52 |  |  | 95933.78 | 0 | 0 | 0 | 64064.0184 | 26458.5167 | 0 | 0 | 90522.5351
| Other (PACR Validation and Project Implementation Plan) | 0 | 0 | 0 | 153501.57 | 87145.08 |  |  | 240646.65 | 0 | 0 | 0 | 146007.3856 | 80672.0411 | 0 | 0 | 226679.4267
| Probity Advisor | 0 | 0 | 0 | 2716.25 | 5842.5 |  |  | 8558.75 | 0 | 0 | 0 | 2583.6385 | 5408.5256 | 0 | 0 | 7992.1641
| Risk analysis, reporting and cost control support |  |  |  |  | 23720 |  |  | 23720 | 0 | 0 | 0 | 0 | 21958.105 | 0 | 0 | 21958.105
| Sub-total | 0 | 0 | 50212.44 | 1736794.62 | 1514735.15 | 0 | 0 | 3301742.21 | 0 | 0 | 49597.9521 | 1652001.6167 | 1402222.3201 | 0 | 0 | 3103821.8889
Land and Environment
| EIS Application Fee | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| EIS Development | 0 | 34100.8166 | 1314470.6542 | 2462071.5192 | 3548506.18 |  |  | 7359149.17 | 0 | 33566.1348 | 1298384.4749 | 2341869.3744 | 3284927.1166 | 0 | 0 | 6958747.1006
| Land Agents | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Specialist services and expenses | 0 | 0 | 0 | 16065.95 | 30716.84 |  |  | 46782.79 | 0 | 0 | 0 | 15281.5854 | 28435.2275 | 0 | 0 | 43716.813
| Travel/accomodation/PPWA and minor expenses | 0 | 92672.4786 | 187536.2878 | 67923.8336 | 110707.93 |  |  | 458840.53 | 0 | 91219.4258 | 185241.2633 | 64607.6869 | 102484.669 | 0 | 0 | 443553.0449
| Sub-total | 0 | 126773.2952 | 1502006.9419 | 2546061.3029 | 3689930.95 | 0 | 0 | 7864772.49 | 0 | 124785.5606 | 1483625.7381 | 2421758.6467 | 3415847.0131 | 0 | 0 | 7446016.9585
Community and Stakeholder Engagement
| Community engagement services | 0 | 0 | 75609.8 | 1110105.51 | 1411052.12 |  |  | 2596767.43 | 0 | 0 | 74684.5052 | 1055908.4396 | 1306240.7494 | 0 | 0 | 2436833.6943
| Community grants |  |  |  |  | 6041.39 |  |  | 6041.39 | 0 | 0 | 0 | 0 | 5592.6423 | 0 | 0 | 5592.6423
| Media and events | 0 | 0 | 0 | 91400.05 | 41592.74 |  |  | 132992.79 | 0 | 0 | 0 | 86937.758 | 38503.2779 | 0 | 0 | 125441.0359
| Community strategy development | 0 | 0 | 0 | 0 | 220213.75 |  |  | 220213.75 | 0 | 0 | 0 | 0 | 203856.5194 | 0 | 0 | 203856.5194
| Travel/accomodation/PPWA and minor expenses | 0 | 0 | 84088.4351 | 223582.6149 | 30061.05 |  |  | 337732.1 | 0 | 0 | 83059.3809 | 212666.9653 | 27828.1489 | 0 | 0 | 323554.4951
| Social legacy initiatives | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Sub-total | 0 | 0 | 159698.2351 | 1425088.1749 | 1708961.05 | 0 | 0 | 3293747.46 | 0 | 0 | 157743.8861 | 1355513.163 | 1582021.3379 | 0 | 0 | 3095278.3869
Regulatory Approvals and Other Support Costs
| Stage 2 CPA submission | 0 | 0 | 0 | 0 | 80.68 |  |  | 80.68 | 0 | 0 | 0 | 0 | 74.6872 | 0 | 0 | 74.6872
| Stage 1 CPA submission | 0 | 0 | 0 | 0 | 94447.65 |  |  | 94447.65 | 0 | 0 | 0 | 0 | 87432.1844 | 0 | 0 | 87432.1844
| Independent external validation PACR | 0 | 0 | 0 | 161064 | 526040.99 |  |  | 687104.99 | 0 | 0 | 0 | 153200.6061 | 486967.2546 | 0 | 0 | 640167.8607
| RIT-T documentation | 0 | 0 | 642972.57 | 825315.09 | 701209 |  |  | 2169496.66 | 0 | 0 | 635104.0246 | 785021.929 | 649123.9811 | 0 | 0 | 2069249.9347
| Market benefits modelling for Stage 2 CPA | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Related expenditure - Snowy II and HumeLink Board Meetings | 376333.63 | 161765.3667 | 344449.678 | -64868.3348 | 659.81 |  |  | 818340.15 | 376333.63 | 159228.976 | 340234.3848 | -61701.3622 | 610.8001 | 0 | 0 | 814706.4286
| Corporate support and systems | 0 | 0 | 223792.92 | 109322.23 | 84626.38 |  |  | 417741.53 | 0 | 0 | 221054.1955 | 103984.9494 | 78340.4273 | 0 | 0 | 403379.5722
| Sub-total | 376333.63 | 161765.3667 | 1211215.168 | 1030832.9852 | 1407064.51 | 0 | 0 | 4187211.66 | 376333.63 | 159228.976 | 1196392.6048 | 980506.1223 | 1302549.3346 | 0 | 0 | 4015010.6677
| Total | 376333.63 | 288538.6619 | 2923132.7851 | 6738777.083 | 8567649.66 | 0 | 0 | 18894431.82 | 376333.63 | 284014.5366 | 2887360.1811 | 6409779.5486 | 7931254.2422 | 0 | 0 | 17888742.1384
|  | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE
Indirect
| Procurement | 0 | 0 | 0 | 0 | 246958 | 0 | 0 | 246958 | 0 | 0 | 0 | 0 | 228614.2364 | 0 | 0 | 228614.2364
| Project Development | 0 | 0 | 50212.44 | 1736794.62 | 1514735.15 | 0 | 0 | 3301742.21 | 0 | 0 | 49597.9521 | 1652001.6167 | 1402222.3201 | 0 | 0 | 3103821.8889
| Land and Environment | 0 | 126773.2952 | 1502006.9419 | 2546061.3029 | 3689930.95 | 0 | 0 | 7864772.49 | 0 | 124785.5606 | 1483625.7381 | 2421758.6467 | 3415847.0131 | 0 | 0 | 7446016.9585
| Community and Stakeholder Engagement | 0 | 0 | 159698.2351 | 1425088.1749 | 1708961.05 | 0 | 0 | 3293747.46 | 0 | 0 | 157743.8861 | 1355513.163 | 1582021.3379 | 0 | 0 | 3095278.3869
| Regulatory Approvals and Other Support Costs | 376333.63 | 161765.3667 | 1211215.168 | 1030832.9852 | 1407064.51 | 0 | 0 | 4187211.66 | 376333.63 | 159228.976 | 1196392.6048 | 980506.1223 | 1302549.3346 | 0 | 0 | 4015010.6677
| Sub-total | 376333.63 | 288538.6619 | 2923132.7851 | 6738777.083 | 8567649.66 | 0 | 0 | 18894431.82 | 376333.63 | 284014.5366 | 2887360.1811 | 6409779.5486 | 7931254.2422 | 0 | 0 | 17888742.1384
|  | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE

## D. Forecast Lab & Indirect
Forecast Labour and Indirect Capex
Forecast Cost - $ Real 30 June 2018, and restated to remove real labour price growth
| Cost category | 2017-18 | 2018-19 | 2019-20 | 2020-21 | 2021-22 (from Jan 22) | 2022-23 | 2023-24 | Total
Labour - Internal and Outsourced
| Project Management |  |  |  |  | 4854720.3769 | 11871964.9782 | 11751036.6893 | 28477722.0444
| Transaction procurement support |  |  |  |  | 1081455.5654 | 3475311.2777 | 1631885.772 | 6188652.6151
| Community and Stakeholder Engagement |  |  |  |  | 564634.352 | 1061005.5574 | 939269.8166 | 2564909.7259
| Land and Environment |  |  |  |  | 1919012.6624 | 3991517.1063 | 3544976.9178 | 9455506.6865
| Other Support and Corporate Roles |  |  |  |  | 1165252.3839 | 1582074.8482 | 1717327.2498 | 4464654.4818
| Sub-total |  |  |  |  | 9585075.3404 | 21981873.7679 | 19584496.4454 | 51151445.5537
Labour Related
| Project Management |  |  |  |  | 72157.2486 | 244068.3969 | 134627.4008 | 450853.0463
| Transaction procurement support |  |  |  |  | 0 | 0 | 0 | 0
| Community and Stakeholder Engagement |  |  |  |  | 0 | 0 | 0 | 0
| Land and Environment |  |  |  |  | 9245.1562 | 19282.5 | 17132.5 | 45660.1562
| Other Support and Corporate Roles |  |  |  |  | 0 | 0 | 0 | 0
| Sub-total |  |  |  |  | 81402.4049 | 263350.8969 | 151759.9008 | 496513.2026
Indirect
| Procurement |  |  |  |  | 1416142.6941 | 24788867.7989 | 1120703.2543 | 27325713.7474
| Project Development |  |  |  |  | 5654831.989 | 14897390.6312 | 9201168.0124 | 29753390.6326
| Land and Environment |  |  |  |  | 7835368.7984 | 10211085.8176 | 3353555.9517 | 21400010.5677
| Community and Stakeholder Engagement |  |  |  |  | 2725817.1005 | 4006636.0298 | 8731142.7664 | 15463595.8968
| Regulatory Approvals and Other Support Costs |  |  |  |  | 1780891.8492 | 1841625.857 | 4260853.0866 | 7883370.7928
| Sub-total |  |  |  |  | 19413052.4312 | 55745606.1346 | 26667423.0715 | 101826081.6373
| Total |  |  |  |  | 29079530.1765 | 77990830.7993 | 46403679.4177 | 153474040.3936
TRUE

## D.1 Forecast Labour
[CONFIDENTIAL INFORMATION REMOVED]

## D.2 Forecast Lab Related
Forecast Labour Related
[6 empty] | CPI discount year | 2021-22 | CPI discount | 0.92572
Training |  | Training Cost based on FTEs (see Forecast Labour) and Annual Training Cost per FTE (see Key Assumptions) - Real $ June 2022 |  |  |  | Training Cost - Real $ June 2018
| Cost category | 2021-22 (from Jan 2022) | 2022-23 | 2023-24 | Total | 2021-22 (from Jan 2022) | 2022-23 | 2023-24 | Total
| Project Management | 22185.0696 | 55092.1858 | 55429.7605 | 132707.016 | 20537.1875 | 51000 | 51312.5 | 122849.6875
| Transaction Procurement Support |  |  |  | 0 | 0 | 0 | 0 | 0
| Community and Stakeholder Engagement |  |  |  | 0 | 0 | 0 | 0 | 0
| Land and Environment | 9986.9778 | 20829.7073 | 18507.1936 | 49323.8787 | 9245.1562 | 19282.5 | 17132.5 | 45660.1562
| Other Support and Corporate Roles |  |  |  | 0 | 0 | 0 | 0 | 0
| Total | 32172.0474 | 75921.8932 | 73936.9541 | 182030.8947 | 29782.3437 | 70282.5 | 68445 | 168509.8438
Recruitment |  | Recruitment Cost - Real $ June 2022 |  |  |  | Recruitment Cost - Real $ June 2018
| Cost category | 2021-22 (from Jan 2022) | 2022-23 | 2023-24 | Total | 2021-22 (from Jan 2022) | 2022-23 | 2023-24 | Total
| Project Management | 0 | 120000 | 90000 | 210000 | 0 | 111086.5344 | 83314.9008 | 194401.4353
| Transaction Procurement Support |  |  |  | 0 | 0 | 0 | 0 | 0
| Community and Stakeholder Engagement |  |  |  | 0 | 0 | 0 | 0 | 0
| Land and Environment |  |  |  | 0 | 0 | 0 | 0 | 0
| Other Support and Corporate Roles |  |  |  | 0 | 0 | 0 | 0 | 0
| Total | 0 | 120000 | 90000 | 210000 | 0 | 111086.5344 | 83314.9008 | 194401.4353
IT Hardware |  | IT Hardware Cost for new staff - Real $ June 2022 |  |  |  | IT Hardware Cost - Real $ June 2018
| Cost category | 2021-22 (from Jan 2022) | 2022-23 | 2023-24 | Total | 2021-22 (from Jan 2022) | 2022-23 | 2023-24 | Total
| Project Management | 55762 | 88560 | 0 | 144322 | 51620.0611 | 81981.8624 | 0 | 133601.9235
| Transaction procurement support |  |  |  | 0 | 0 | 0 | 0 | 0
| Community and Stakeholder Engagement |  |  |  | 0 | 0 | 0 | 0 | 0
| Land and Environment |  |  |  | 0 | 0 | 0 | 0 | 0
| Other Support and Corporate Roles |  |  |  | 0 | 0 | 0 | 0 | 0
| Total | 55762 | 88560 | 0 | 144322 | 51620.0611 | 81981.8624 | 0 | 133601.9235
Summary |  | Labour Related Cost - $ Real June 2022 |  |  |  | Labour Related Cost - Real $ June 2018
| Cost category | 2021-22 (from Jan 2022) | 2022-23 | 2023-24 | Total | 2021-22 (from Jan 2022) | 2022-23 | 2023-24 | Total
| Project Management | 77947.0696 | 263652.1858 | 145429.7605 | 487029.016 | 72157.2486 | 244068.3969 | 134627.4008 | 450853.0463
| Transaction procurement support | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Community and Stakeholder Engagement | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Land and Environment | 9986.9778 | 20829.7073 | 18507.1936 | 49323.8787 | 9245.1562 | 19282.5 | 17132.5 | 45660.1562
| Other Support and Corporate Roles | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Total | 87934.0474 | 284481.8932 | 163936.9541 | 536352.8947 | 81402.4049 | 263350.8969 | 151759.9008 | 496513.2026
[5 empty] | TRUE |  |  |  | TRUE

## D.3 Forecast Indirect
[CONFIDENTIAL INFORMATION REMOVED]

## Tables - Labour and Indirect
Table 2‑1: Historical Labour and indirect capex by category, from 1 July 2017 to 31 August 2021 ($M, Real June 2018)
Capex category | 2017-18 | 2018-19 | 2019-20 | 2020-21 | 2021-22 | Total capex
Labour and Labour-Related | 0 | 0.35156 | 5.6493 | 8.9099 | 5.2046 | 20.1155
Project Management | 0 | 0.23345 | 2.662 | 3.3575 | 2.4939 | 8.7468
Transaction Procurement Support | 0 | 0 | 0 | 0.40798 | 0.20536 | 0.61334
Community and Stakeholder Engagement | 0 | 0.004859 | 0.3111 | 1.0219 | 0.56544 | 1.9033
Land and Environment | 0 | 0.073171 | 1.205 | 2.0664 | 1.1133 | 4.4579
Other Support and Corporate Roles | 0 | 0.040079 | 1.4712 | 2.0562 | 0.82664 | 4.3941
Indirect | 0.37633 | 0.28401 | 2.8874 | 6.4098 | 7.9313 | 17.8887
Procurement | 0 | 0 | 0 | 0 | 0.22861 | 0.22861
Project Development | 0 | 0 | 0.049598 | 1.652 | 1.4022 | 3.1038
Land and Environment | 0 | 0.12479 | 1.4836 | 2.4218 | 3.4158 | 7.446
Community and Stakeholder Engagement | 0 | 0 | 0.15774 | 1.3555 | 1.582 | 3.0953
Regulatory Approvals and Other Support Costs | 0.37633 | 0.15923 | 1.1964 | 0.98051 | 1.3025 | 4.015
Total | 0.37633 | 0.63557 | 8.5367 | 15.3197 | 13.1359 | 38.0042
Figure 2-1: Historical labour and indirect capex from 1 July 2017 to 31 August 2021 ($M, Real June 2018)
Labour and Labour-related | 20.1155
Non-Labour | 17.8887
Table 3‑1: Summary total capex – historical and forecast ($M, Real June 2018)
Capex category | 2017-18 | 2018-19 | 2019-20 | 2020-21 | 2021-22 | 2022-23 | 2023-24 | Total capex | % of total capex
Historical | 0.37633 | 0.63557 | 8.5367 | 15.3197 | 13.1359 |  |  | 38.0042 | 19.85%
Forecast |  |  |  |  | 29.0795 | 77.9908 | 46.4037 | 153.474 | 80.15%
Total | 0.37633 | 0.63557 | 8.5367 | 15.3197 | 42.2154 | 77.9908 | 46.4037 | 191.4783 | 100%
Table 3-2: Forecast Labour and indirect capex by category, from 1 January 2022 to 30 June 2024 ($M, Real June 2018)
Capex category | 2021-22 | 2022-23 | 2023-24 | Total capex | % of total capex
Labour and Labour-Related | 9.6665 | 22.2452 | 19.7363 | 51.648 | 33.65%
Project Management | 4.9269 | 12.116 | 11.8857 | 28.9286 | 18.85%
Transaction Procurement Support | 1.0815 | 3.4753 | 1.6319 | 6.1887 | 4.032%
Community and Stakeholder Engagement | 0.56463 | 1.061 | 0.93927 | 2.5649 | 1.671%
Land and Environment | 1.9283 | 4.0108 | 3.5621 | 9.5012 | 6.191%
Other Support and Corporate Roles | 1.1653 | 1.5821 | 1.7173 | 4.4647 | 2.909%
Indirect | 19.4131 | 55.7456 | 26.6674 | 101.8261 | 66.35%
Procurement | 1.4161 | 24.7889 | 1.1207 | 27.3257 | 17.8%
Project Development | 5.6548 | 14.8974 | 9.2012 | 29.7534 | 19.39%
Land and Environment | 7.8354 | 10.2111 | 3.3536 | 21.4 | 13.94%
Community and Stakeholder Engagement | 2.7258 | 4.0066 | 8.7311 | 15.4636 | 10.08%
Regulatory Approvals and Other Support Costs | 1.7809 | 1.8416 | 4.2609 | 7.8834 | 5.137%
Total | 29.0795 | 77.9908 | 46.4037 | 153.474 | 100%
| TRUE | TRUE | TRUE | TRUE | TRUE
Figure 3-1 - Forecast labour and indirect capex by nature, from 1 January 2022 to 30 June 2024 ($M, Real June 2018)
Labour | 51.1514
Labour-related | 0.49651
Tender Payments & Facillities Fees | 22.7727
Legal Expense | 16.0943
EIS | 14.4065
Other costs | 48.5525
TRUE
Figure 3-2: Forecast monthly FTEs (Internal Labour)
Table 5-1 Summary of labour and labour-related costs for Project management ($M, Real June 2018)
Category | Total capex
Labour | 28.4777 | TRUE
Internal | 27.2156
Outsourced | 1.2621
Labour-related costs | 0.45085 | TRUE
Training | 0.12285
Recruitment | 0.1944
IT Hardware expenses | 0.1336
Total | 28.9286 | TRUE
Table 5-2 Summary of labour-related costs for Project Management ($M, Real June 2018)
Category | Total capex
Training | 0.12285
Recruitment | 0.1944
IT Hardware expenses | 0.1336
Table 5-3 Summary of labour and labour-related costs for Transaction Procurement Support ($M, Real June 2018)
Category | Total capex
Labour | 6.1887 | TRUE
Internal | 5.7431
Outsourced | 0.44559
Labour-related costs | 0 | TRUE
Training | 0
Recruitment | 0
IT Hardware expenses | 0
Total | 6.1887 | TRUE
Table 5-4 Summary of labour and labour-related costs for Community and Stakeholder Engagement ($M, Real June 2018)
Category | Total capex
Labour | 2.5649 | TRUE
Internal | 2.5649
Outsourced | 0
Labour-related costs | 0 | TRUE
Training | 0
Recruitment | 0
IT Hardware expenses | 0
Total | 2.5649 | TRUE
Table 5-5 Summary of labour and labour-related costs for Land and Envrironment ($M, Real June 2018)
Category | Total capex
Labour | 9.4555 | TRUE
Internal | 9.4555
Outsourced | 0
Labour-related costs | 0.04566 | TRUE
Training | 0.04566
Recruitment | 0
IT Hardware expenses | 0
Total | 9.5012 | TRUE
Table 5-6 Summary of labour and labour-related costs for Other Support and Corporate Roles ($M, Real June 2018)
Category | Total capex
Labour | 4.4647 | TRUE
Internal | 4.4647
Outsourced | 0
Labour-related costs | 0 | TRUE
Training | 0
Recruitment | 0
IT Hardware expenses | 0
Total | 4.4647 | TRUE

## Tables - Capex Forecasting Meth
Labour and Indirects Model Output Template
Table 2.2: Historical and Forecast capex for the Initial CPA by capex category ($M, Real 2017-18, including overheads)
|  |  | Dollar basis | Units | 2018 | 2019 | 2020 | 2021 | 2022 | 2023 | 2024 | Total
| Labour and related costs |  |  |  | 0 | 0.35156 | 5.6493 | 8.9099 | 14.8711 | 22.2452 | 19.7363 | 71.7634
| Project team resources | Labour and corporate support for project management, procurement, land and environmental activities | Real $2018 | $Million | 0 | 0.35156 | 5.6493 | 8.9099 | 14.8711 | 22.2452 | 19.7363 | 71.7634 | TRUE
| Indirect Costs |  |  |  | 0.37633 | 0.28401 | 2.8874 | 6.4098 | 27.3443 | 55.7456 | 26.6674 | 119.7148
| Procurement | Bidder payments | Real $2018 | $Million | 0 | 0 | 0 | 0 | 0 | 22.2173 | 0 | 22.2173 | TRUE
|  | Data room services and market road show | Real $2018 | $Million | 0 | 0 | 0 | 0 | 0.55543 | 0 | 0 | 0.55543
|  | Other | Real $2018 | $Million | 0 | 0 | 0 | 0 | 1.0893 | 2.5716 | 1.1207 | 4.7816
| Project development | Development, engineering, legal and economic support | Real $2018 | $Million | 0 | 0 | 0.049598 | 1.652 | 7.0571 | 14.8974 | 9.2012 | 32.8572 | TRUE
| Land and Environment | Fees, labour and indirect costs | Real $2018 | $Million | 0 | 0.12479 | 1.4836 | 2.4218 | 11.2512 | 10.2111 | 3.3536 | 28.846 | TRUE
| Community and stakeholder engagement | Indirect costs for management, media, events and grants | Real $2018 | $Million | 0 | 0 | 0.15774 | 1.3555 | 4.3078 | 4.0066 | 8.7311 | 18.5589 | TRUE
| Regulatory approvals and other support costs | External corporate support and indirect costs for regulatory RIT-T and CPA activities | Real $2018 | $Million | 0.37633 | 0.15923 | 1.1964 | 0.98051 | 3.0834 | 1.8416 | 4.2609 | 11.8984 | TRUE
| Labour and Indirect Costs - Total |  | Real $2018 | $Million | 0.37633 | 0.63557 | 8.5367 | 15.3197 | 42.2154 | 77.9908 | 46.4037 | 191.4783 | TRUE
[5 empty] | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE
Table 5 2: Actual Labour and indirect capex by category to 31 December 2021 ($M, Real 2017-18) (before labour escalation applied)
|  |  | Dollar basis | Units | 2018 | 2019 | 2020 | 2021 | 2022 | 2023 | 2024 | Total
| Labour and related costs |  |  |  | 0 | 0.35156 | 5.6493 | 8.9099 | 5.2046 | 0 | 0 | 20.1155
| Project Management |  | Real $2018 | $Million | 0 | 0.23345 | 2.662 | 3.3575 | 2.4939 | 0 | 0 | 8.7468
| Transaction procurement support |  | Real $2018 | $Million | 0 | 0 | 0 | 0.40798 | 0.20536 | 0 | 0 | 0.61334
| Community and Stakeholder Engagement |  | Real $2018 | $Million | 0 | 0.004859 | 0.3111 | 1.0219 | 0.56544 | 0 | 0 | 1.9033
| Land and Environment |  | Real $2018 | $Million | 0 | 0.073171 | 1.205 | 2.0664 | 1.1133 | 0 | 0 | 4.4579
| Other Support and Corporate Roles |  | Real $2018 | $Million | 0 | 0.040079 | 1.4712 | 2.0562 | 0.82664 | 0 | 0 | 4.3941
| Indirect Costs |  |  |  | 0.37633 | 0.28401 | 2.8874 | 6.4098 | 7.9313 | 0 | 0 | 17.8887
| Procurement |  | Real $2018 | $Million | 0 | 0 | 0 | 0 | 0.22861 | 0 | 0 | 0.22861
| Project development |  | Real $2018 | $Million | 0 | 0 | 0.049598 | 1.652 | 1.4022 | 0 | 0 | 3.1038
| Land and Environment |  | Real $2018 | $Million | 0 | 0.12479 | 1.4836 | 2.4218 | 3.4158 | 0 | 0 | 7.446
| Community and stakeholder engagement |  | Real $2018 | $Million | 0 | 0 | 0.15774 | 1.3555 | 1.582 | 0 | 0 | 3.0953
| Regulatory approvals and other support costs |  | Real $2018 | $Million | 0.37633 | 0.15923 | 1.1964 | 0.98051 | 1.3025 | 0 | 0 | 4.015
| Labour and Indirect Costs - Total |  | Real $2018 | $Million | 0.37633 | 0.63557 | 8.5367 | 15.3197 | 13.1359 | 0 | 0 | 38.0042 | TRUE
Table 5 3: Summary of forecast capex for project team resources ($M, Real 2017-18)
|  |  | Dollar basis | Units | Historical Capex | Forecast to FID | Total Capex
| Project Management |  | Real $2018 | $Million | 8.7468 | 28.9286 | 37.6754
| Transaction procurement support |  | Real $2018 | $Million | 0.61334 | 6.1887 | 6.802
| Community and Stakeholder Engagement |  | Real $2018 | $Million | 1.9033 | 2.5649 | 4.4682
| Land and Environment |  | Real $2018 | $Million | 4.4579 | 9.5012 | 13.9591
| Other Support and Corporate Roles |  | Real $2018 | $Million | 4.3941 | 4.4647 | 8.8588
| Total |  | Real $2018 | $Million | 20.1155 | 51.648 | 71.7634 | TRUE
Table 5 4: Procurement indirect costs and basis of estimates ($M Real $2017-18)
|  |  | Dollar basis | Units | Historical Capex | Forecast to FID | Total Capex
| Bidder Payments |  | Real $2018 | $Million | 0 | 22.2173 | 22.2173
| Data Room Services |  | Real $2018 | $Million | 0 | 0.55543 | 0.55543
| Transaction management expenses |  | Real $2018 | $Million | 0.22861 | 4.553 | 4.7816
| Total |  | Real $2018 | $Million | 0.22861 | 27.3257 | 27.5543 | TRUE
Table 5 5: Summary of forecast capex for project development resources ($M, Real 2017-18 )
|  |  | Dollar basis | Units | Historical Capex | Forecast to FID | Total Capex
Project Development
| External Legal Expenses |  | Real $2018 | $Million | 0.53592 | 16.0943 | 16.6302
| Project Management / Concept Engineering |  | Real $2018 | $Million | 1.9111 | 2.9461 | 4.8572
| Geotech and Surveys |  | Real $2018 | $Million | 0.050788 | 5.4774 | 5.5282
| Owners Engineer |  | Real $2018 | $Million | 0.022312 | 2.6049 | 2.6272
| Specialist Studies |  | Real $2018 | $Million | 0.23659 | 0.11757 | 0.35415
| Travel/accomodation/PPWA and minor expenses |  | Real $2018 | $Million | 0.090523 | 1.032 | 1.1225
| Other (PACR Validation and Project Implementation Plan) |  | Real $2018 | $Million | 0.22668 | 0.024069 | 0.25075
| Probity Advisor |  | Real $2018 | $Million | 0.0079922 |  | 0.0079922
| Risk analysis, reporting and cost control support |  | Real $2018 | $Million | 0.021958 | 1.4571 | 1.479
| Total |  | Real $2018 | $Million | 3.1038 | 29.7534 | 32.8572 | TRUE
Table 5 6: Summary of forecast capex for land and environment ($M, Real 2017-18 )
|  |  | Dollar basis | Units | Historical Capex | Forecast to FID | Total Capex
Land and Environment
| EIS Application Fee |  | Real $2018 | $Million | 0 | 2.5799 | 2.5799
| EIS Development |  | Real $2018 | $Million | 6.9587 | 11.8266 | 18.7854
| Land Agents |  | Real $2018 | $Million | 0 | 6.6356 | 6.6356
| Specialist services and expenses |  | Real $2018 | $Million | 0.043717 | 0.053594 | 0.097311
| Travel/accomodation/PPWA and minor expenses |  | Real $2018 | $Million | 0.44355 | 0.30434 | 0.74789
| Total |  | Real $2018 | $Million | 7.446 | 21.4 | 28.846 | TRUE
Table 5 7: Summary of forecast capex for community and stakeholder engagement ($M, Real 2017-18 )
|  |  | Dollar basis | Units | Historical Capex | Forecast to FID | Total Capex
Community and Stakeholder Engagement
| Community engagement services |  | Real $2018 | $Million | 2.4368 | 6.1292 | 8.5661
| Community grants |  | Real $2018 | $Million | 0.0055926 | 0.55543 | 0.56103
| Media and events |  | Real $2018 | $Million | 0.12544 | 0.4512 | 0.57664
| Community strategy development |  | Real $2018 | $Million | 0.20386 | 0.3147 | 0.51855
| Travel/accomodation/PPWA and minor expenses |  | Real $2018 | $Million | 0.32355 | 0.436 | 0.75956
| Social legacy initiatives |  | Real $2018 | $Million | 0 | 7.577 | 7.577
| Total |  | Real $2018 | $Million | 3.0953 | 15.4636 | 18.5589 | TRUE
Table 5 8: Summary of forecast capex for regulatory approvals and other support ($M, Real 2017-18 )
|  |  | Dollar basis | Units | Historical Capex | Forecast to FID | Total Capex
Regulatory approvals and other support costs
| Stage 2 CPA submission |  | Real $2018 | $Million | 7.4687e-05 | 3.4994 | 3.4994 | -
| Stage 1 CPA submission |  | Real $2018 | $Million | 0.087432 | 0.24779 | 0.33522 | -
| Independent external validation PACR |  | Real $2018 | $Million | 0.64017 |  | 0.64017 | -
| RIT-T documentation |  | Real $2018 | $Million | 2.0692 | 0.081094 | 2.1503 | -
| Market benefits modelling for Stage 2 CPA |  | Real $2018 | $Million | 0 | 1.1109 | 1.1109 | -
| Related expenditure - Snowy II and HumeLink Board Meetings |  | Real $2018 | $Million | 0.81471 | 0.020533 | 0.83524 | -
| Corporate support and systems |  | Real $2018 | $Million | 0.40338 | 2.9237 | 3.3271 | -
| Total |  | Real $2018 | $Million | 4.015 | 7.8834 | 11.8984 | TRUE