## Index
AER Capex Model - from APA proposal
Index
Model Index
Summary Chart
Draft Decision - Output│Tables
1.0 Output│PTRM
1.1 Output│RFM
1.2 Output│RIN
1.3 Output│Tables
1.4 Output│Graphs
1.5 Output│2017 Corp Capex
2.0 Input│Historic Capex
3.0 Input│AMP
3.1 Input│B&T
3.2 Input│Other
3.3 Input│RIN
4.0 Calc│AER Forecast ($nom)
4.1 Calc│Hist Act ($nom)
4.2 Calc│Hist Com ($nom)
5.0 Calc│Forecast Projects
5.1 Calc│$ million
5.2 Calc│VTS
5.3 Calc│Forecast $2017
5.4 Calc│Escalators
5.5 Calc│Escalated capex
5.6 Calc│As Commissioned
End

## Summary Chart
APA VTS 2018-22 Access Arrangement - AER Draft Decision
Figures reported below are net
|  | 2013 | 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 | 2022
| APA actual capex | 2013: 15.5962; 2014: 124.1752; 2015: 94.5272; 2016: 105.0136
| APA estimated capex | 2017: 68.9868
| Approved capex forecast | 2013: 19.7; 2014: 95.4; 2015: 25.2; 2016: 14.1; 2017: 9.3
| APA forecast capex | 2018: 77.7098; 2019: 71.9244; 2020: 73.7286; 2021: 17.7904; 2022: 14.9199
| AER draft decision | 2018: 61.1348; 2019: 56.9351; 2020: 72.341; 2021: 13.7257; 2022: 10.8724
APA revised proposal
AER final decision
| Underspend | 2013: 4.1038; 2014: -28.7752; 2015: -69.3272; 2016: -90.9136; 2017: -59.6868

## Draft Decision - Output│Tables
APA VTS - Actual Capex - Output¦Tables | [8 empty] | Draft Decision - Output│Tables
| Historic Capex ($nominal m) | [8 empty] | Historic Capex ($nominal m)
|  | 2013 | 2014 | 2015 | 2016 (e) | 2017 (f) | Total |  |  |  | 2013 | 2014 | 2015 | 2016 (e) | 2017 (f) | Total
| Capital expenditure | 15.5962 | 124.1752 | 94.5272 | 105.0136 | 68.9868 | 408.2989 |  |  | Capital expenditure | 15.5962 | 124.1752 | 94.5272 | 105.0136 | 62.9868 | 402.2989
| Capex by Asset Class ($ nominal m) | [8 empty] | Capex by Asset Class ($ nominal m)
| Asset Class | 2013 | 2014 | 2015 | 2016 (e) | 2017 (f) | Total |  |  | Asset Class | 2013 | 2014 | 2015 | 2016 (e) | 2017 (f) | Total
| Pipelines | 4.1116 | 85.8261 | 72.0774 | 93.2526 | 52.541 | 307.8086 |  |  | Pipelines | 4.1116 | 85.8261 | 72.0774 | 93.2526 | 52.541 | 307.8086
| Compressors | 8.4012 | 27.7984 | 7.7657 | 6.317 | 0.965 | 51.2474 |  |  | Compressors | 8.4012 | 27.7984 | 7.7657 | 6.317 | 0.965 | 51.2474
| City Gates & Field Regs | 1.1037 | 5.1064 | 8.3758 | 1.503 | 3.46 | 19.5489 |  |  | City Gates & Field Regs | 1.1037 | 5.1064 | 8.3758 | 1.503 | 0.46 | 16.5489
| Odourant Plants | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Odourant Plants | 0 | 0 | 0 | 0 | 0 | 0
| Gas Quality | 0 | 0.09101 | 0.28585 | 0.35095 | 0.05 | 0.77781 |  |  | Gas Quality | 0 | 0.09101 | 0.28585 | 0.35095 | 0.05 | 0.77781
| Other | 1.9333 | 5.126 | 5.0021 | 3.5331 | 11.9238 | 27.5183 |  |  | Other | 1.9333 | 5.126 | 5.0021 | 3.5331 | 8.9238 | 24.5183
| Buildings | 0.046302 | 0.22734 | 1.0204 | 0.056882 | 0.04705 | 1.398 |  |  | Buildings | 0.046302 | 0.22734 | 1.0204 | 0.056882 | 0.04705 | 1.398
| General Land | 0 | 0 | 0 | 0 | 0 | 0 |  |  | General Land | 0 | 0 | 0 | 0 | 0 | 0
| Total | 15.5962 | 124.1752 | 94.5272 | 105.0136 | 68.9868 | 408.2989 | 0 |  | Total | 15.5962 | 124.1752 | 94.5272 | 105.0136 | 62.9868 | 402.2989 | 0
| Capex by Asset Category ($nominal m) | [8 empty] | Capex by Asset Category ($nominal m)
| Asset Category | 2013 | 2014 | 2015 | 2016 (e) | 2017 (f) | Total |  |  | Asset Category | 2013 | 2014 | 2015 | 2016 (e) | 2017 (f) | Total
| Augmentation | 12.3099 | 112.4157 | 74.5887 | 92.1364 | 52.331 | 343.7817 |  |  | Augmentation | 12.3099 | 112.4157 | 74.5887 | 92.1364 | 52.331 | 343.7817
| Replacement | 1.5504 | 7.5217 | 14.2083 | 10.5241 | 8.105 | 41.9095 |  |  | Replacement | 1.5504 | 7.5217 | 14.2083 | 10.5241 | 2.105 | 35.9095
| Non-System | 1.7358 | 4.2378 | 5.7301 | 2.3531 | 8.5508 | 22.6077 |  |  | Non-System | 1.7358 | 4.2378 | 5.7301 | 2.3531 | 8.5508 | 22.6077
| Total | 15.5962 | 124.1752 | 94.5272 | 105.0136 | 68.9868 | 408.2989 | 0 |  | Total | 15.5962 | 124.1752 | 94.5272 | 105.0136 | 62.9868 | 402.2989 | 0
APA VTS - Proposed Capex - Output¦Tables | [8 empty] | Draft Decision - Output│Tables
| Forecast Capex (nominal $m) | [8 empty] | Forecast Capex (nominal $m)
|  | 2018 | 2019 | 2020 | 2021 | 2022 | Total |  |  |  | 2018 | 2019 | 2020 | 2021 | 2022 | Total
| Capital expenditure | 77.7098 | 71.9244 | 73.7286 | 17.7904 | 14.9199 | 256.0731 |  |  | Capital expenditure | 61.1348 | 56.9351 | 72.341 | 13.7257 | 10.8724 | 215.0091
| Capex by Asset Class (real 2017 $m) | [8 empty] | Capex by Asset Class (real 2017 $m)
|  | 2018 | 2019 | 2020 | 2021 | 2022 | Total |  |  |  | 2018 | 2019 | 2020 | 2021 | 2022 | Total
| Pipelines | 50.6752 | 48.7949 | 53.1625 | 3.197 | 0.50398 | 156.3336 |  |  | Pipelines | 35.9329 | 33.8056 | 51.7749 | 0.17029 | 0.17029 | 121.854
| Compressors | 14.4254 | 13.4972 | 12.9727 | 4.4042 | 6.5459 | 51.8452 |  |  | Compressors | 14.4254 | 13.4972 | 12.9727 | 3.3662 | 2.8321 | 47.0934
| City Gates & Field Regs | 0 | 2.3361 | 2.378 | 0.68322 | 0.24695 | 5.6443 |  |  | City Gates & Field Regs | 0 | 2.3361 | 2.378 | 0.68322 | 0.24695 | 5.6443
| Odourant Plants | 0.07808 | 0 | 0 | 0 | 0 | 0.07808 |  |  | Odourant Plants | 0.07808 | 0 | 0 | 0 | 0 | 0.07808
| Gas Quality | 1.0063 | 0 | 0 | 0 | 0 | 1.0063 |  |  | Gas Quality | 1.0063 | 0 | 0 | 0 | 0 | 1.0063
| Other | 10.865 | 6.3257 | 4.2449 | 8.5355 | 7.2736 | 37.2446 |  |  | Other | 9.0323 | 6.3257 | 4.2449 | 8.5355 | 7.2736 | 35.412
| Buildings | 0.65985 | 0.97052 | 0.97052 | 0.97052 | 0.34957 | 3.921 |  |  | Buildings | 0.65985 | 0.97052 | 0.97052 | 0.97052 | 0.34957 | 3.921
| General Land | 0 | 0 | 0 | 0 | 0 | 0 |  |  | General Land | 0 | 0 | 0 | 0 | 0 | 0
| Total | 77.7098 | 71.9244 | 73.7286 | 17.7904 | 14.9199 | 256.0731 |  |  | Total | 61.1348 | 56.9351 | 72.341 | 13.7257 | 10.8724 | 215.0091
| Capex by Driver (real 2017 $m) | [8 empty] | Capex by Driver (real 2017 $m)
| Asset Category | 2018 | 2019 | 2020 | 2021 | 2022 | Total |  |  | Asset Category | 2018 | 2019 | 2020 | 2021 | 2022 | Total
| Augmentation | 44.3874 | 49.7329 | 60.9452 | 0 | 0 | 155.0654 |  |  | Augmentation | 44.3874 | 46.8372 | 59.7724 | 0 | 0 | 150.9969
| Replacement | 29.0849 | 18.639 | 9.5309 | 14.2229 | 12.627 | 84.1047 |  |  | Replacement | 12.51 | 6.5454 | 9.3162 | 10.1582 | 8.5795 | 47.1092
| Non-System | 4.2375 | 3.5526 | 3.2525 | 3.5675 | 2.293 | 16.903 |  |  | Non-System | 4.2375 | 3.5526 | 3.2525 | 3.5675 | 2.293 | 16.903
| Total | 77.7098 | 71.9244 | 73.7286 | 17.7904 | 14.9199 | 256.0731 |  |  | Total | 61.1348 | 56.9351 | 72.341 | 13.7257 | 10.8724 | 215.0091

## 1.0 Output│PTRM
1.0 Output│PTRM |  |  | Check | TRUE
Forecast Capex as incurred ($2017 m)
| c | 2018 | 2019 | 2020 | 2021 | 2022 | Total
| Pipelines | 35.9329 | 33.8056 | 51.7749 | 0.17029 | 0.17029 | 121.854
| Compressors | 14.4254 | 13.4972 | 12.9727 | 3.3662 | 2.8321 | 47.0934
| City Gates & Field Regs | 0 | 2.3361 | 2.378 | 0.68322 | 0.24695 | 5.6443
| Odourant Plants | 0.07808 | 0 | 0 | 0 | 0 | 0.07808
| Gas Quality | 1.0063 | 0 | 0 | 0 | 0 | 1.0063
| Other | 9.0323 | 6.3257 | 4.2449 | 8.5355 | 7.2736 | 35.412
| Buildings | 0.65985 | 0.97052 | 0.97052 | 0.97052 | 0.34957 | 3.921
| General Land | 0 | 0 | 0 | 0 | 0 | 0
| Total | 61.1348 | 56.9351 | 72.341 | 13.7257 | 10.8724 | 215.0091
Forecast Capex as commissioned ($2017 m)
| Asset Class Name | 2018 | 2019 | 2020 | 2021 | 2022 | Total
| Pipelines | 28.6614 | 2.1473 | 100.8616 | 0.17029 | 0.17029 | 132.0108
| Compressors | 12.1929 | 1.0562 | 30.0293 | 3.3866 | 0.45838 | 47.1234
| City Gates & Field Regs | 0.029347 | 0.63983 | 4.0743 | 0.68322 | 0.24695 | 5.6736
| Odourant Plants | 0.07808 | 0 | 0 | 0 | 0 | 0.07808
| Gas Quality | 1.0663 | 0 | 0 | 0 | 0 | 1.0663
| Other | 8.8234 | 7.8007 | 3.5935 | 8.1117 | 7.2736 | 35.6028
| Buildings | 0.65985 | 0.34957 | 0.34957 | 2.2124 | 0.34957 | 3.921
| General Land | 0 | 0 | 0 | 0 | 0 | 0
| Total | 51.5114 | 11.9935 | 138.9082 | 14.5642 | 8.4987 | 225.4761
0
[7 empty] | 215.0091 | -10466950.5027

## 1.1 Output│RFM
1.1 Output│RFM |  | Check | TRUE
Capex as incurred (nominal $m)
| Asset Class Name | 2013 | 2014 | 2015 | 2016 | 2017 | Total
| Pipelines | 4.1116 | 85.8261 | 72.0774 | 93.2526 | 52.541 | 307.8086 | 307.8086 | 0
| Compressors | 8.4012 | 27.7984 | 7.7657 | 6.317 | 0.965 | 51.2474 | 51.2474 | 0
| City Gates & Field Regs | 1.1037 | 5.1064 | 8.3758 | 1.503 | 0.46 | 16.5489 | 16.5489 | 0
| Odourant Plants | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Gas Quality | 0 | 0.09101 | 0.28585 | 0.35095 | 0.05 | 0.77781 | 0.77781 | 0
| Other | 1.9333 | 5.126 | 5.0021 | 3.5331 | 8.9238 | 24.5183 | 24.5183 | 0
| Buildings | 0.046302 | 0.22734 | 1.0204 | 0.056882 | 0.04705 | 1.398 | 1.398 | 0
| General Land | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Total | 15.5962 | 124.1752 | 94.5272 | 105.0136 | 62.9868 | 402.2989 | 402.2989 | 0
Capex as commissioned (nominal $m)
| Asset Class Name | 2013 | 2014 | 2015 | 2016 | 2017 | Total
| Pipelines | 0.07044 | 32.4916 | 123.6759 | 0.23889 | 141.1749 | 297.6518 | 297.6518 | 0
| Compressors | 0.23527 | 0.25427 | 37.3216 | 11.2055 | 2.2007 | 51.2174 | 51.2174 | 0
| City Gates & Field Regs | 0.16393 | 2.9485 | 11.3765 | 1.1835 | 0.84714 | 16.5196 | 16.5196 | 0
| Odourant Plants | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Gas Quality | 0 | 0.09101 | 0.28585 | 0.34095 | 0 | 0.71781 | 0.71781 | 0
| Other | 0.85818 | 3.4061 | 7.2063 | 2.931 | 9.9259 | 24.3274 | 24.3274 | 0
| Buildings | 0 | 0.18051 | 1.1135 | 0.054026 | 0.0028568 | 1.3509 | 1.3509 | 0
| General Land | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Total | 1.3278 | 39.3721 | 180.9798 | 15.9538 | 154.1515 | 391.7849 | 391.7849 | 0
0
391.7849
10.514

## 1.2 Output│RIN
4.1 - CAPEX
4.1.1 - EXPANSION (by Project)
| EXPENDITURE Actual ($0's) |  |  | EXPENDITURE Forecast ($0's real, December 2017)
| 1 July to 31 December 2013 | 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 | 2022
Wollert to Clonbinane Looping | 4006990.75 | 85648927.66 | 65640112.89 | 643437.5283 | 0 | 0 | 0 | 0 | 0 | 0
VNIE Looping 6 to 8 | 0 | 0 | 6392032.4513 | 92414222.7837 | 43063099.4902 | 0 | 0 | 0 | 0 | 0
WORM (50km x 20" Pipeline) | 0 | 0 | 0 | 0 | 0 | 16439771.1413 | 29960486.7805 | 50436222.8004 | 0 | 0
Stonehaven CS - now Winchelsea | 8134553.96 | 26606375.39 | 2492547.98 | 888.642 | 0 | 0 | 0 | 0 | 0 | 0
Anglesea Pipeline Extension | 0 | 0 | 0 | 0 | 9267887.2827 | 17176915.8237 | 0 | 0 | 0 | 0
WORM (C50 at Wollert) | 0 | 0 | 0 | 0 | 0 | 7277668.4555 | 12494032.3453 | 6381927.8453 | 0 | 0
Warragul Looping 6" (Southern Route) | 0 | 0 | 0 | 0 | 0 | 0 | 2600000 | 900000 | 0 | 0
WORM (PRS at Wollert) | 0 | 0 | 0 | 0 | 0 | 0 | 1696263.7392 | 2024314.7222 | 0 | 0
BCS Reconfiguration (2B) | 0 | 0 | 0 | 0 | 0 | 2025261.4569 | 0 | 0 | 0 | 0
Winchelsea Bi-Directional Flow | 0 | 0 | 0 | 0 | 0 | 1467750.2937 | 0 | 0 | 0 | 0
VTS - EUROA CS NEW (PPOM) | 116664.37 | 121805.28 | 59020.54 | -2979.3672 | 0 | 0 | 0 | 0 | 0 | 0
VTS - SUNBURY PIPE LOOP (NEW) | 51715.09 | 38571.05 | 5019.95 | 4081.3088 | 0 | 0 | 0 | 0 | 0 | 0
Total | 12309924.17 | 112415679.38 | 74588733.8113 | 93059650.8956 | 52330986.7729 | 44387367.171 | 46750782.865 | 59742465.3678 | 0 | 0
Check | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE
4.1.2 - REPLACEMENT (by Project)
| EXPENDITURE Actual ($0's) | EXPENDITURE Forecast ($0's real, December 2017) 2016: EXPENDITURE Forecast ($0's real, December 2017)
| 1 July to 31 December 2013 | 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 | 2022
Regulator upgrade - Dandenong City Gate (exclude filters) | 479498.96 | 2616566.96 | 7811136.25 | 760192.0344 | 0 | 0 | 0 | 0 | 0 | 0
BLP Safety Measures for High Consequence areas-(urban growth, fracture control) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
BCS Unit 10 & 11 Cooler Upgrade | 27089.84 | 889622.65 | 5007242.54 | 3314651.9393 | 0 | 0 | 0 | 0 | 0 | 0
WOP Safety Measures for High Consequence areas-(urban growth, fracture control) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Brooklyn Compressor Station | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2373685.7636 | 2373685.7636 | 2373685.7636
BCP Safety Measures for High Consequence areas-(urban growth, fracture control) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Turbine Overhauls | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Pig Trap Installation Trugannina to Plumpton | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Pigging Program (T1 Dandenong - Morwell) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Pigging Program T60 Longford -Dandenong | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2460022.429
Pig Trap Installation James Street to Laverton Pipeline (253) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Actuate MLV's in T1 areas | 0 | 0 | 0 | 0 | 0 | 988494.4455 | 988494.4455 | 0 | 0 | 0
Pig Trap - Keon Park Install | 325106.72 | 1640823.98 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Pig Trap - Dandenong to Princes Highway Pipeline Install (129) | 0 | 0 | 31113.5 | 355269.8955 | 0 | 0 | 0 | 0 | 0 | 0
Coogee decommissioning, Step Change | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
BCS Station Isolation and Loading Valves | 2244.6 | 16577.75 | 183683.64 | 1631331.8054 | 0 | 0 | 0 | 0 | 0 | 0
Iona CS aftercooler augmentation | 0 | 0 | 0 | 0 | 0 | 1711368.7421 | 0 | 0 | 0 | 0
Pig Trap - Somerton to Somerton Pipeline Install (238) | 0 | 1590 | 24041.28 | 3764.2919 | 0 | 0 | 0 | 0 | 0 | 0
CP - Cathodic Protection Replacement | 18725 | 98704 | 20000 | 90964.0741 | 50000 | 240187.3674 | 240187.3674 | 240187.3674 | 240187.3674 | 240187.3674
Pigging Program T24 Brooklyn - Corio | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1426531.7343 | 0
Pigging Program T16 Dandenong – West Melbourne | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1423541.5066 | 0
Hazardous Area Rectification | 10313.6 | 32182.3 | 134741.2 | 165095.9047 | 100000 | 183913.5556 | 183913.5556 | 183913.5556 | 183913.5556 | 183913.5556
Emergency- Response Equipment | 0 | 0 | 0 | 0 | 0 | 266373.6154 | 266373.6154 | 266373.6154 | 266373.6154 | 266373.6154
Iona CS Automation replacement | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1212394.8789 | 0 | 0
Pigging Program T1 Morwell - Dandenong Repair Program | 0 | 0 | 0 | 0 | 0 | 956271.2614 | 179900.2311 | 0 | 0 | 0
Compressor Type B Compliance | 0 | 0 | 0 | 0 | 0 | 223918.4115 | 223918.4115 | 223918.4115 | 223918.4115 | 223918.4115
WCS A Process Safety | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1080239.7847 | 0 | 0
Pigging Program T33 South Melbourne – Brooklyn | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1057669.0866 | 0
Compressor Station Vent Stack Upgrade (BCS, WCS, GCS, SCS) | 0 | 0 | 0 | 0 | 0 | 0 | 341374.2665 | 341374.2665 | 341374.2665 | 0
Culcairn Injection Gas Quality equipment | 0 | 0 | 0 | 0 | 0 | 1006317.5288 | 0 | 0 | 0 | 0
GCS unit discharge and station manifold check valves replacement | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 931918.2343 | 0 | 0
Pig Trap - A Branch Valve on Pipeline 108 to Newport Install(124) | 0 | 0 | 20098.4 | 880081.4888 | 0 | 0 | 0 | 0 | 0 | 0
GCS Anti-Surge & Fast-Stop Valves Upgrade | 0 | 0 | 10038.5 | 503749.0544 | 365000 | 0 | 0 | 0 | 0 | 0
Pipe Support replacement | 0 | 0 | 0 | 0 | 0 | 170286.4298 | 170286.4298 | 170286.4298 | 170286.4298 | 170286.4298
Remote CP/critical drainage bond monitoring | 0 | 0 | 0 | 0 | 0 | 592091.8977 | 62465.0567 | 62465.0567 | 62465.0567 | 62465.0567
Regulator Upgrade - Lara pneumatic control system upgrade | 0 | 0 | 5301 | 0 | 160000 | 0 | 639830.9202 | 0 | 0 | 0
Other Replacement (details in forecast capex model) | 682099.47 | 1608781.65 | 856454.93 | 2420271.4755 | 1330000 | 3826036.1725 | 1546235.4118 | 1776348.6046 | 1303819.3171 | 1529096.7054
Pigging Program T65 Dandenong to Princes Highway Pipeline (129)
Total | 1545078.19 | 6904849.29 | 14103851.24 | 10125371.964 | 2005000 | 10165259.4277 | 4842979.7115 | 8863105.969 | 9073766.111 | 7509949.3344
Check | 1550442 | 7521688.32 | 14208332.65 | 10660501.5676 | 2105000 | 12509982.34 | 6545390.0621 | 9316168.1584 | 10158218.663 | 8579472.2385
| -5363.81 | -616839.03 | -104481.41 | -535129.6036 | -100000 | -2344722.9123 | -1702410.3507 | -453062.1894 | -1084452.552 | -1069522.9042
4.1.3 - NON SYSTEM CAPEX
| EXPENDITURE Actual ($0's) | EXPENDITURE Forecast ($0's real, December 2017) 2016: EXPENDITURE Forecast ($0's real, December 2017)
| 1 July to 31 December 2013 | 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 | 2022
Enterprise Asset Management | 806330.3274 | 1986550.9701 | 2564771.5454 | 1794.8446 | 0 | 0 | 0 | 0 | 0 | 0
Dandenong Relocation | 0 | 0 | 0 | 0 | 5057812 | 0 | 0 | 0 | 0 | 0
WAN Upgrade (Satellite project) | 0 | 0 | 0 | 0 | 0 | 978453.096 | 978453.096 | 978453.096 | 978453.096 | 978453.096
Applications Renewal | 0 | 0 | 0 | 0 | 0 | 744925.7116 | 930617.3383 | 744925.7116 | 930617.3383 | 744925.7116
Storage shed-Dandenong, Wollert & Springhurst | 0 | 0 | 0 | 0 | 0 | 0 | 620944.1189 | 620944.1189 | 620944.1189 | 0
Security - Physical | 0 | 0 | 0 | 0 | 0 | 349572.9355 | 349572.9355 | 349572.9355 | 349572.9355 | 349572.9355
Corporate IT | 211241.5961 | 302736.8717 | 276048.921 | 379176.6999 | 209022 | 0 | 0 | 0 | 0 | 0
Dandenong site fire mains replacement | 4961.3378 | 88164.1814 | 1020411.517 | 30567.2059 | 47050 | 0 | 0 | 0 | 0 | 0
SCADA - Comms upgrade to IP network-VTS only | 0 | 0 | 0 | 56649.9537 | 1000000 | 0 | 0 | 0 | 0 | 0
Data Centre | 65362.0189 | 895833.2344 | 79250.1745 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Equipment - Victorian low value pool purchases | 52890.5047 | 215346.1091 | 550230.7606 | 165502.2312 | 28230 | 0 | 0 | 0 | 0 | 0
Enterprise Content Management | 0 | 0 | 104729.0841 | 330175.7976 | 512309 | 0 | 0 | 0 | 0 | 0
Corporate other | 242365.2632 | 340342.973 | 308327.8805 | 17750.0006 | 0 | 0 | 0 | 0 | 0 | 0
eForm Digitisation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 173557.2996 | 447753.928 | 0
Other Non System (details in forecast capex model) | 352672.2813 | 408852.6704 | 826326.5371 | 1401996.1538 | 1696397 | 2164519.0875 | 672978.5051 | 385040.8181 | 240175.7606 | 220004.7641
Total | 1735823.3294 | 4237827.0102 | 5730096.4203 | 2383612.8873 | 8550820 | 4237470.8307 | 3552565.9939 | 3252493.9798 | 3567517.1773 | 2292956.5073
Check | 1735823.3294 | 4237827.0102 | 5730096.4203 | 2383612.8873 | 8550820 | 4237470.8307 | 3552565.9939 | 3252493.9798 | 3567517.1773 | 2292956.5073
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.3 - FORECAST CAPEX
EXPENDITURE Forecast ($0's real, December 2017)
|  |  |  | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 | 2022
Direct labour expenditure |  |  |  | 13817969.6734 | 10296658.2303 | 19218127.486 | 12391044.4472 | 12580548.0023 | 3766249.0834 | 3032759.641
Direct materials expenditure |  |  |  | 31586618.8868 | 19259904.5917 | 21099732.9899 | 22315914.5573 | 26421522.276 | 2567079.8252 | 2237825.3279
Direct contractor expenditure |  |  |  | 56365220.7514 | 35202122.6987 | 7640174.5335 | 4950231.5977 | 4847960.7208 | 7235027.4749 | 5513345.8016
Other direct expenditure |  |  |  | 4605064.9818 | 4228121.2522 | 13176785.3324 | 17277926.0967 | 28490996.5069 | 157379.4569 | 88497.9754
Overheads |  | EXPENDITURE Forecast ($0's real, December 2017) 2016: 0; EXPENDITURE Forecast ($0's real, December 2017) 2017: 0
Total |  |  |  | 106374874.2934 | 68986806.7729 | 61134820.3417 | 56935116.6988 | 72341027.5061 | 13725735.8403 | 10872428.7458
Check |  | EXPENDITURE Forecast ($0's real, December 2017) 2018: 58790097.4295; EXPENDITURE Forecast ($0's real, December 2017) 2019: 55146328.5704; EXPENDITURE Forecast ($0's real, December 2017) 2020: 71858065.3167; EXPENDITURE Forecast ($0's real, December 2017) 2021: 12641283.2883; EXPENDITURE Forecast ($0's real, December 2017) 2022: 9802905.8416
3.1 - INFLATION OR EXTRAPOLATION RATES
| Actual % | EXPENDITURE Forecast ($0's real, December 2017) 2021: Forecast %
| 2008 | 2009 | 2010 | 2011 | 2012 | 2013 | 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 | 2022 | 2023 | 2024 | 2025 | 2026 | 2027
Inflation or extrapolation rate (eg CPI) | 1.977% | 4.447% | 2.074% | 2.46% | 3.549% | 1.562% | 2.308% | 1.504% | 1.296% | 2% | 2% | 1% | 1% | 1% | 1%
| 2007-06-01 | 2014: 2008-06-01; 2015: 2009-06-01; EXPENDITURE Forecast ($0's real, December 2017) 2016: 2010-06-01; EXPENDITURE Forecast ($0's real, December 2017) 2017: 2011-06-01
7.1 - CAPITAL EXPENDITURE - AS INCURRED (by driver)
| EXPENDITURE Actual ($0's) | EXPENDITURE Forecast ($0's real, December 2017) 2016: EXPENDITURE Forecast ($0's real, December 2017)
| 1 July to 31 December 2013 | 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 | 2022
Pipelines
Replacement
Conforming capital expenditure | 52902.3 | 138555.75 | 40185.4 | 1125263.7452 | 210000 | 2316189.8374 | 1158780.8753 | 408816.112 | 170286.4298 | 170286.4298
Non-conforming capital expenditure - recovered by a surcharge
Non-conforming capital expenditure - added to the speculative capital expenditure account
Non-conforming capital expenditure - other
Capital contributions rolled into the capital base
Speculative capital expenditure account rolled into the capital base
Re-use of redundant assets rolled into the capital base
Redundant assets rolled out of the capital base
Disposals
Augmentation
Conforming capital expenditure | 4058705.84 | 85687498.71 | 72037165.2913 | 93059847.5986 | 52330986.7729 | 33616686.965 | 32646864.5582 | 51366122.8004 | 0 | 0
Non-conforming capital expenditure - recovered by a surcharge
Non-conforming capital expenditure - added to the speculative capital expenditure account
Non-conforming capital expenditure - other
Capital contributions rolled into the capital base
Speculative capital expenditure account rolled into the capital base
Re-use of redundant assets rolled into the capital base
Redundant assets rolled out of the capital base
Disposals
Non-system
Conforming capital expenditure |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Non-conforming capital expenditure - recovered by a surcharge
Non-conforming capital expenditure - added to the speculative capital expenditure account
Non-conforming capital expenditure - other
Capital contributions rolled into the capital base
Speculative capital expenditure account rolled into the capital base
Re-use of redundant assets rolled into the capital base
Redundant assets rolled out of the capital base
Disposals
Check |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | Check Pipelines
COMPRESSORS |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Replacement
Conforming capital expenditure | 150026.93 | 1070306.11 | 5214100.68 | 6351963.0937 | 965000 | 3654674.7167 | 1003126.5288 | 6590745.6848 | 3366192.7868 | 2747337.448
Non-conforming capital expenditure - recovered by a surcharge
Non-conforming capital expenditure - added to the speculative capital expenditure account
Non-conforming capital expenditure - other
Capital contributions rolled into the capital base
Speculative capital expenditure account rolled into the capital base
Re-use of redundant assets rolled into the capital base
Redundant assets rolled out of the capital base
Disposals
Augmentation
Conforming capital expenditure | 8251218.33 | 26728180.67 | 2551568.52 | 886.0427 | 0 | 10770680.2061 | 12494032.3453 | 6381927.8453 | 0 | 0
Non-conforming capital expenditure - recovered by a surcharge
Non-conforming capital expenditure - added to the speculative capital expenditure account
Non-conforming capital expenditure - other
Capital contributions rolled into the capital base
Speculative capital expenditure account rolled into the capital base
Re-use of redundant assets rolled into the capital base
Redundant assets rolled out of the capital base
Disposals
Non-system
Conforming capital expenditure | 15596189.4994 | 124175194.7102 | 94527162.8816 | 106063722.8128 | 0 | 0 | 0 | 0 | 0 | 84727.045
Non-conforming capital expenditure - recovered by a surcharge
Non-conforming capital expenditure - added to the speculative capital expenditure account
Non-conforming capital expenditure - other
Capital contributions rolled into the capital base
Speculative capital expenditure account rolled into the capital base
Re-use of redundant assets rolled into the capital base
Redundant assets rolled out of the capital base
Disposals
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  | Check COMPRESSORS
City Gates & Field Regs |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Replacement
Conforming capital expenditure | 1103730.39 | 5106391.56 | 8375791.26 | 1518056.6438 | 460000 | 0 | 639830.9202 | 353719.7429 | 683220.5812 | 246948.9266
Non-conforming capital expenditure - recovered by a surcharge
Non-conforming capital expenditure - added to the speculative capital expenditure account
Non-conforming capital expenditure - other
Capital contributions rolled into the capital base
Speculative capital expenditure account rolled into the capital base
Re-use of redundant assets rolled into the capital base
Redundant assets rolled out of the capital base
Disposals
Augmentation
Conforming capital expenditure |  |  |  |  | 0 | 0 | 1696263.7392 | 2024314.7222 | 0 | 0
Non-conforming capital expenditure - recovered by a surcharge
Non-conforming capital expenditure - added to the speculative capital expenditure account
Non-conforming capital expenditure - other
Capital contributions rolled into the capital base
Speculative capital expenditure account rolled into the capital base
Re-use of redundant assets rolled into the capital base
Redundant assets rolled out of the capital base
Disposals
Non-system
Conforming capital expenditure |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Non-conforming capital expenditure - recovered by a surcharge
Non-conforming capital expenditure - added to the speculative capital expenditure account
Non-conforming capital expenditure - other
Capital contributions rolled into the capital base
Speculative capital expenditure account rolled into the capital base
Re-use of redundant assets rolled into the capital base
Redundant assets rolled out of the capital base
Disposals
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  | Check City Gates & Field Regs
ODOURANT PLANTS
Replacement
Conforming capital expenditure |  |  |  |  | 0 | 78079.7768 | 0 | 0 | 0 | 0
Non-conforming capital expenditure - recovered by a surcharge
Non-conforming capital expenditure - added to the speculative capital expenditure account
Non-conforming capital expenditure - other
Capital contributions rolled into the capital base
Speculative capital expenditure account rolled into the capital base
Re-use of redundant assets rolled into the capital base
Redundant assets rolled out of the capital base
Disposals
Augmentation
Conforming capital expenditure |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Non-conforming capital expenditure - recovered by a surcharge
Non-conforming capital expenditure - added to the speculative capital expenditure account
Non-conforming capital expenditure - other
Capital contributions rolled into the capital base
Speculative capital expenditure account rolled into the capital base
Re-use of redundant assets rolled into the capital base
Redundant assets rolled out of the capital base
Disposals
Non-system
Conforming capital expenditure |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Non-conforming capital expenditure - recovered by a surcharge
Non-conforming capital expenditure - added to the speculative capital expenditure account
Non-conforming capital expenditure - other
Capital contributions rolled into the capital base
Speculative capital expenditure account rolled into the capital base
Re-use of redundant assets rolled into the capital base
Redundant assets rolled out of the capital base
Disposals
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  | Check ODOURANT PLANTS
GAS QUALITY | bar: EXPENDITURE Forecast ($0's real, December 2017) 2017
Replacement
Conforming capital expenditure | 0 | 91009.78 | 285847.41 | 354457.985 | 50000 | 1006317.5288 | 0 | 0 | 0 | 0
Non-conforming capital expenditure - recovered by a surcharge
Non-conforming capital expenditure - added to the speculative capital expenditure account
Non-conforming capital expenditure - other
Capital contributions rolled into the capital base
Speculative capital expenditure account rolled into the capital base
Re-use of redundant assets rolled into the capital base
Redundant assets rolled out of the capital base
Disposals
Augmentation
Conforming capital expenditure |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Non-conforming capital expenditure - recovered by a surcharge
Non-conforming capital expenditure - added to the speculative capital expenditure account
Non-conforming capital expenditure - other
Capital contributions rolled into the capital base
Speculative capital expenditure account rolled into the capital base
Re-use of redundant assets rolled into the capital base
Redundant assets rolled out of the capital base
Disposals
Non-system
Conforming capital expenditure |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Non-conforming capital expenditure - recovered by a surcharge
Non-conforming capital expenditure - added to the speculative capital expenditure account
Non-conforming capital expenditure - other
Capital contributions rolled into the capital base
Speculative capital expenditure account rolled into the capital base
Re-use of redundant assets rolled into the capital base
Redundant assets rolled out of the capital base
Disposals
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  | Check GAS QUALITY
BUILDINGS
Replacement
Conforming capital expenditure |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Non-conforming capital expenditure - recovered by a surcharge
Non-conforming capital expenditure - added to the speculative capital expenditure account
Non-conforming capital expenditure - other
Capital contributions rolled into the capital base
Speculative capital expenditure account rolled into the capital base
Re-use of redundant assets rolled into the capital base
Redundant assets rolled out of the capital base
Disposals
Augmentation
Conforming capital expenditure |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Non-conforming capital expenditure - recovered by a surcharge
Non-conforming capital expenditure - added to the speculative capital expenditure account
Non-conforming capital expenditure - other
Capital contributions rolled into the capital base
Speculative capital expenditure account rolled into the capital base
Re-use of redundant assets rolled into the capital base
Redundant assets rolled out of the capital base
Disposals
Non-system
Conforming capital expenditure | 0 | 0 | 0 | 0 | 47050 | 659848.6909 | 970517.0545 | 970517.0545 | 970517.0545 | 349572.9355
Non-conforming capital expenditure - recovered by a surcharge
Non-conforming capital expenditure - added to the speculative capital expenditure account
Non-conforming capital expenditure - other
Capital contributions rolled into the capital base
Speculative capital expenditure account rolled into the capital base
Re-use of redundant assets rolled into the capital base
Redundant assets rolled out of the capital base
Disposals
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  | Check BUILDINGS
General Land
Replacement
Conforming capital expenditure |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Non-conforming capital expenditure - recovered by a surcharge
Non-conforming capital expenditure - added to the speculative capital expenditure account
Non-conforming capital expenditure - other
Capital contributions rolled into the capital base
Speculative capital expenditure account rolled into the capital base
Re-use of redundant assets rolled into the capital base
Redundant assets rolled out of the capital base
Disposals
Augmentation
Conforming capital expenditure |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Non-conforming capital expenditure - recovered by a surcharge
Non-conforming capital expenditure - added to the speculative capital expenditure account
Non-conforming capital expenditure - other
Capital contributions rolled into the capital base
Speculative capital expenditure account rolled into the capital base
Re-use of redundant assets rolled into the capital base
Redundant assets rolled out of the capital base
Disposals
Non-system
Conforming capital expenditure |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Non-conforming capital expenditure - recovered by a surcharge
Non-conforming capital expenditure - added to the speculative capital expenditure account
Non-conforming capital expenditure - other
Capital contributions rolled into the capital base
Speculative capital expenditure account rolled into the capital base
Re-use of redundant assets rolled into the capital base
Redundant assets rolled out of the capital base
Disposals
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  | Check General Land
OTHER
Replacement
Conforming capital expenditure | 243782.38 | 1115425.12 | 292407.9 | 1279577.6456 | 420000 | 5454720.4803 | 3743651.7378 | 1962886.6187 | 5938518.8651 | 5414899.4341
Non-conforming capital expenditure - recovered by a surcharge
Non-conforming capital expenditure - added to the speculative capital expenditure account
Non-conforming capital expenditure - other
Capital contributions rolled into the capital base
Speculative capital expenditure account rolled into the capital base
Re-use of redundant assets rolled into the capital base
Redundant assets rolled out of the capital base
Disposals
Augmentation
Conforming capital expenditure |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Non-conforming capital expenditure - recovered by a surcharge
Non-conforming capital expenditure - added to the speculative capital expenditure account
Non-conforming capital expenditure - other
Capital contributions rolled into the capital base
Speculative capital expenditure account rolled into the capital base
Re-use of redundant assets rolled into the capital base
Redundant assets rolled out of the capital base
Disposals
Non-system
Conforming capital expenditure | 0 | 0 | 0 | 0 | 8503770 | 3577622.1398 | 2582048.9394 | 2281976.9253 | 2597000.1229 | 1858656.5268
Non-conforming capital expenditure - recovered by a surcharge
Non-conforming capital expenditure - added to the speculative capital expenditure account
Non-conforming capital expenditure - other
Capital contributions rolled into the capital base
Speculative capital expenditure account rolled into the capital base
Re-use of redundant assets rolled into the capital base
Redundant assets rolled out of the capital base
Disposals
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Check OTHER
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Check Total
7.2 - CAPITAL EXPENDITURE - AS COMMISSIONED (by driver)
| EXPENDITURE Actual ($0's) | EXPENDITURE Forecast ($0's real, December 2017) 2016: EXPENDITURE Forecast ($0's real, December 2017)
| 1 July to 31 December 2013 | 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 | 2022
Pipelines
Replacement
Conforming capital expenditure |  | EXPENDITURE Forecast ($0's real, December 2017) 2018: 2216612.8119; EXPENDITURE Forecast ($0's real, December 2017) 2019: 2147275.3208; EXPENDITURE Forecast ($0's real, December 2017) 2020: 408816.112; EXPENDITURE Forecast ($0's real, December 2017) 2021: 170286.4298; EXPENDITURE Forecast ($0's real, December 2017) 2022: 170286.4298
Non-conforming capital expenditure - recovered by a surcharge
Non-conforming capital expenditure - added to the speculative capital expenditure account
Non-conforming capital expenditure - other
Capital contributions rolled into the capital base
Speculative capital expenditure account rolled into the capital base
Re-use of redundant assets rolled into the capital base
Redundant assets rolled out of the capital base
Disposals
Augmentation
Conforming capital expenditure |  | EXPENDITURE Forecast ($0's real, December 2017) 2018: 26444803.1064; EXPENDITURE Forecast ($0's real, December 2017) 2019: 0; EXPENDITURE Forecast ($0's real, December 2017) 2020: 100452758.4999; EXPENDITURE Forecast ($0's real, December 2017) 2021: 0; EXPENDITURE Forecast ($0's real, December 2017) 2022: 0
Non-conforming capital expenditure - recovered by a surcharge
Non-conforming capital expenditure - added to the speculative capital expenditure account
Non-conforming capital expenditure - other
Capital contributions rolled into the capital base
Speculative capital expenditure account rolled into the capital base
Re-use of redundant assets rolled into the capital base
Redundant assets rolled out of the capital base
Disposals
Non-system
Conforming capital expenditure |  | EXPENDITURE Forecast ($0's real, December 2017) 2018: 0; EXPENDITURE Forecast ($0's real, December 2017) 2019: 0; EXPENDITURE Forecast ($0's real, December 2017) 2020: 0; EXPENDITURE Forecast ($0's real, December 2017) 2021: 0; EXPENDITURE Forecast ($0's real, December 2017) 2022: 0
Non-conforming capital expenditure - recovered by a surcharge
Non-conforming capital expenditure - added to the speculative capital expenditure account
Non-conforming capital expenditure - other
Capital contributions rolled into the capital base
Speculative capital expenditure account rolled into the capital base
Re-use of redundant assets rolled into the capital base
Redundant assets rolled out of the capital base
Disposals
|  | EXPENDITURE Forecast ($0's real, December 2017) 2018: 0; EXPENDITURE Forecast ($0's real, December 2017) 2019: 0; EXPENDITURE Forecast ($0's real, December 2017) 2020: 0; EXPENDITURE Forecast ($0's real, December 2017) 2021: 0; EXPENDITURE Forecast ($0's real, December 2017) 2022: 0 |  | Check Pipelines
COMPRESSORS
Replacement
Conforming capital expenditure |  | EXPENDITURE Forecast ($0's real, December 2017) 2018: 8699898.8232; EXPENDITURE Forecast ($0's real, December 2017) 2019: 1056164.7047; EXPENDITURE Forecast ($0's real, December 2017) 2020: 3875685.6547; EXPENDITURE Forecast ($0's real, December 2017) 2021: 3386624.2982; EXPENDITURE Forecast ($0's real, December 2017) 2022: 373651.6844
Non-conforming capital expenditure - recovered by a surcharge
Non-conforming capital expenditure - added to the speculative capital expenditure account
Non-conforming capital expenditure - other
Capital contributions rolled into the capital base
Speculative capital expenditure account rolled into the capital base
Re-use of redundant assets rolled into the capital base
Redundant assets rolled out of the capital base
Disposals
Augmentation
Conforming capital expenditure |  | EXPENDITURE Forecast ($0's real, December 2017) 2018: 3493011.7505; EXPENDITURE Forecast ($0's real, December 2017) 2019: 0; EXPENDITURE Forecast ($0's real, December 2017) 2020: 26153628.6461; EXPENDITURE Forecast ($0's real, December 2017) 2021: 0; EXPENDITURE Forecast ($0's real, December 2017) 2022: 0
Non-conforming capital expenditure - recovered by a surcharge
Non-conforming capital expenditure - added to the speculative capital expenditure account
Non-conforming capital expenditure - other
Capital contributions rolled into the capital base
Speculative capital expenditure account rolled into the capital base
Re-use of redundant assets rolled into the capital base
Redundant assets rolled out of the capital base
Disposals
Non-system
Conforming capital expenditure |  | EXPENDITURE Forecast ($0's real, December 2017) 2018: 0; EXPENDITURE Forecast ($0's real, December 2017) 2019: 0; EXPENDITURE Forecast ($0's real, December 2017) 2020: 0; EXPENDITURE Forecast ($0's real, December 2017) 2021: 0; EXPENDITURE Forecast ($0's real, December 2017) 2022: 84727.045
Non-conforming capital expenditure - recovered by a surcharge
Non-conforming capital expenditure - added to the speculative capital expenditure account
Non-conforming capital expenditure - other
Capital contributions rolled into the capital base
Speculative capital expenditure account rolled into the capital base
Re-use of redundant assets rolled into the capital base
Redundant assets rolled out of the capital base
Disposals
|  | EXPENDITURE Forecast ($0's real, December 2017) 2018: 0; EXPENDITURE Forecast ($0's real, December 2017) 2019: 0; EXPENDITURE Forecast ($0's real, December 2017) 2020: 0; EXPENDITURE Forecast ($0's real, December 2017) 2021: 0; EXPENDITURE Forecast ($0's real, December 2017) 2022: 0 |  | Check COMPRESSORS
City Gates & Field Regs
Replacement
Conforming capital expenditure |  | EXPENDITURE Forecast ($0's real, December 2017) 2018: 29347.4; EXPENDITURE Forecast ($0's real, December 2017) 2019: 639830.9202; EXPENDITURE Forecast ($0's real, December 2017) 2020: 353719.7429; EXPENDITURE Forecast ($0's real, December 2017) 2021: 683220.5812; EXPENDITURE Forecast ($0's real, December 2017) 2022: 246948.9266
Non-conforming capital expenditure - recovered by a surcharge
Non-conforming capital expenditure - added to the speculative capital expenditure account
Non-conforming capital expenditure - other
Capital contributions rolled into the capital base
Speculative capital expenditure account rolled into the capital base
Re-use of redundant assets rolled into the capital base
Redundant assets rolled out of the capital base
Disposals
Augmentation
Conforming capital expenditure |  | EXPENDITURE Forecast ($0's real, December 2017) 2018: 0; EXPENDITURE Forecast ($0's real, December 2017) 2019: 0; EXPENDITURE Forecast ($0's real, December 2017) 2020: 3720578.4614; EXPENDITURE Forecast ($0's real, December 2017) 2021: 0; EXPENDITURE Forecast ($0's real, December 2017) 2022: 0
Non-conforming capital expenditure - recovered by a surcharge
Non-conforming capital expenditure - added to the speculative capital expenditure account
Non-conforming capital expenditure - other
Capital contributions rolled into the capital base
Speculative capital expenditure account rolled into the capital base
Re-use of redundant assets rolled into the capital base
Redundant assets rolled out of the capital base
Disposals
Non-system
Conforming capital expenditure |  | EXPENDITURE Forecast ($0's real, December 2017) 2018: 0; EXPENDITURE Forecast ($0's real, December 2017) 2019: 0; EXPENDITURE Forecast ($0's real, December 2017) 2020: 0; EXPENDITURE Forecast ($0's real, December 2017) 2021: 0; EXPENDITURE Forecast ($0's real, December 2017) 2022: 0
Non-conforming capital expenditure - recovered by a surcharge
Non-conforming capital expenditure - added to the speculative capital expenditure account
Non-conforming capital expenditure - other
Capital contributions rolled into the capital base
Speculative capital expenditure account rolled into the capital base
Re-use of redundant assets rolled into the capital base
Redundant assets rolled out of the capital base
Disposals
|  | EXPENDITURE Forecast ($0's real, December 2017) 2018: 0; EXPENDITURE Forecast ($0's real, December 2017) 2019: 0; EXPENDITURE Forecast ($0's real, December 2017) 2020: 0; EXPENDITURE Forecast ($0's real, December 2017) 2021: 0; EXPENDITURE Forecast ($0's real, December 2017) 2022: 0 |  | Check City Gates & Field Regs
ODOURANT PLANTS
Replacement
Conforming capital expenditure |  | EXPENDITURE Forecast ($0's real, December 2017) 2018: 78079.7768; EXPENDITURE Forecast ($0's real, December 2017) 2019: 0; EXPENDITURE Forecast ($0's real, December 2017) 2020: 0; EXPENDITURE Forecast ($0's real, December 2017) 2021: 0; EXPENDITURE Forecast ($0's real, December 2017) 2022: 0
Non-conforming capital expenditure - recovered by a surcharge
Non-conforming capital expenditure - added to the speculative capital expenditure account
Non-conforming capital expenditure - other
Capital contributions rolled into the capital base
Speculative capital expenditure account rolled into the capital base
Re-use of redundant assets rolled into the capital base
Redundant assets rolled out of the capital base
Disposals
Augmentation
Conforming capital expenditure |  | EXPENDITURE Forecast ($0's real, December 2017) 2018: 0; EXPENDITURE Forecast ($0's real, December 2017) 2019: 0; EXPENDITURE Forecast ($0's real, December 2017) 2020: 0; EXPENDITURE Forecast ($0's real, December 2017) 2021: 0; EXPENDITURE Forecast ($0's real, December 2017) 2022: 0
Non-conforming capital expenditure - recovered by a surcharge
Non-conforming capital expenditure - added to the speculative capital expenditure account
Non-conforming capital expenditure - other
Capital contributions rolled into the capital base
Speculative capital expenditure account rolled into the capital base
Re-use of redundant assets rolled into the capital base
Redundant assets rolled out of the capital base
Disposals
Non-system
Conforming capital expenditure |  | EXPENDITURE Forecast ($0's real, December 2017) 2018: 0; EXPENDITURE Forecast ($0's real, December 2017) 2019: 0; EXPENDITURE Forecast ($0's real, December 2017) 2020: 0; EXPENDITURE Forecast ($0's real, December 2017) 2021: 0; EXPENDITURE Forecast ($0's real, December 2017) 2022: 0
Non-conforming capital expenditure - recovered by a surcharge
Non-conforming capital expenditure - added to the speculative capital expenditure account
Non-conforming capital expenditure - other
Capital contributions rolled into the capital base
Speculative capital expenditure account rolled into the capital base
Re-use of redundant assets rolled into the capital base
Redundant assets rolled out of the capital base
Disposals
|  | EXPENDITURE Forecast ($0's real, December 2017) 2018: 0; EXPENDITURE Forecast ($0's real, December 2017) 2019: 0; EXPENDITURE Forecast ($0's real, December 2017) 2020: 0; EXPENDITURE Forecast ($0's real, December 2017) 2021: 0; EXPENDITURE Forecast ($0's real, December 2017) 2022: 0 |  | Check ODOURANT PLANTS
Gas Quality
Replacement |  | EXPENDITURE Forecast ($0's real, December 2017) 2018: 1066317.5288; EXPENDITURE Forecast ($0's real, December 2017) 2019: 0; EXPENDITURE Forecast ($0's real, December 2017) 2020: 0; EXPENDITURE Forecast ($0's real, December 2017) 2021: 0; EXPENDITURE Forecast ($0's real, December 2017) 2022: 0
Conforming capital expenditure
Non-conforming capital expenditure - recovered by a surcharge
Non-conforming capital expenditure - added to the speculative capital expenditure account
Non-conforming capital expenditure - other
Capital contributions rolled into the capital base
Speculative capital expenditure account rolled into the capital base
Re-use of redundant assets rolled into the capital base
Redundant assets rolled out of the capital base
Disposals
Augmentation |  | EXPENDITURE Forecast ($0's real, December 2017) 2018: 0; EXPENDITURE Forecast ($0's real, December 2017) 2019: 0; EXPENDITURE Forecast ($0's real, December 2017) 2020: 0; EXPENDITURE Forecast ($0's real, December 2017) 2021: 0; EXPENDITURE Forecast ($0's real, December 2017) 2022: 0
Conforming capital expenditure
Non-conforming capital expenditure - recovered by a surcharge
Non-conforming capital expenditure - added to the speculative capital expenditure account
Non-conforming capital expenditure - other
Capital contributions rolled into the capital base
Speculative capital expenditure account rolled into the capital base
Re-use of redundant assets rolled into the capital base
Redundant assets rolled out of the capital base
Disposals
Non-system |  | EXPENDITURE Forecast ($0's real, December 2017) 2018: 0; EXPENDITURE Forecast ($0's real, December 2017) 2019: 0; EXPENDITURE Forecast ($0's real, December 2017) 2020: 0; EXPENDITURE Forecast ($0's real, December 2017) 2021: 0; EXPENDITURE Forecast ($0's real, December 2017) 2022: 0
Conforming capital expenditure
Non-conforming capital expenditure - recovered by a surcharge
Non-conforming capital expenditure - added to the speculative capital expenditure account
Non-conforming capital expenditure - other
Capital contributions rolled into the capital base
Speculative capital expenditure account rolled into the capital base
Re-use of redundant assets rolled into the capital base
Redundant assets rolled out of the capital base
Disposals |  | EXPENDITURE Forecast ($0's real, December 2017) 2018: 0; EXPENDITURE Forecast ($0's real, December 2017) 2019: 0; EXPENDITURE Forecast ($0's real, December 2017) 2020: 0; EXPENDITURE Forecast ($0's real, December 2017) 2021: 0; EXPENDITURE Forecast ($0's real, December 2017) 2022: 0 |  | Check Gas Quality
BUILDINGS
Replacement
Conforming capital expenditure |  | EXPENDITURE Forecast ($0's real, December 2017) 2018: 0; EXPENDITURE Forecast ($0's real, December 2017) 2019: 0; EXPENDITURE Forecast ($0's real, December 2017) 2020: 0; EXPENDITURE Forecast ($0's real, December 2017) 2021: 0; EXPENDITURE Forecast ($0's real, December 2017) 2022: 0
Non-conforming capital expenditure - recovered by a surcharge
Non-conforming capital expenditure - added to the speculative capital expenditure account
Non-conforming capital expenditure - other
Capital contributions rolled into the capital base
Speculative capital expenditure account rolled into the capital base
Re-use of redundant assets rolled into the capital base
Redundant assets rolled out of the capital base
Disposals
Augmentation
Conforming capital expenditure |  | EXPENDITURE Forecast ($0's real, December 2017) 2018: 0; EXPENDITURE Forecast ($0's real, December 2017) 2019: 0; EXPENDITURE Forecast ($0's real, December 2017) 2020: 0; EXPENDITURE Forecast ($0's real, December 2017) 2021: 0; EXPENDITURE Forecast ($0's real, December 2017) 2022: 0
Non-conforming capital expenditure - recovered by a surcharge
Non-conforming capital expenditure - added to the speculative capital expenditure account
Non-conforming capital expenditure - other
Capital contributions rolled into the capital base
Speculative capital expenditure account rolled into the capital base
Re-use of redundant assets rolled into the capital base
Redundant assets rolled out of the capital base
Disposals
Non-system
Conforming capital expenditure |  | EXPENDITURE Forecast ($0's real, December 2017) 2018: 659848.6909; EXPENDITURE Forecast ($0's real, December 2017) 2019: 349572.9355; EXPENDITURE Forecast ($0's real, December 2017) 2020: 349572.9355; EXPENDITURE Forecast ($0's real, December 2017) 2021: 2212405.2923; EXPENDITURE Forecast ($0's real, December 2017) 2022: 349572.9355
Non-conforming capital expenditure - recovered by a surcharge
Non-conforming capital expenditure - added to the speculative capital expenditure account
Non-conforming capital expenditure - other
Capital contributions rolled into the capital base
Speculative capital expenditure account rolled into the capital base
Re-use of redundant assets rolled into the capital base
Redundant assets rolled out of the capital base
Disposals
|  | EXPENDITURE Forecast ($0's real, December 2017) 2018: 0; EXPENDITURE Forecast ($0's real, December 2017) 2019: 0; EXPENDITURE Forecast ($0's real, December 2017) 2020: 0; EXPENDITURE Forecast ($0's real, December 2017) 2021: 0; EXPENDITURE Forecast ($0's real, December 2017) 2022: 0 |  | Check BUILDINGS
General Land
Replacement
Conforming capital expenditure |  | EXPENDITURE Forecast ($0's real, December 2017) 2018: 0; EXPENDITURE Forecast ($0's real, December 2017) 2019: 0; EXPENDITURE Forecast ($0's real, December 2017) 2020: 0; EXPENDITURE Forecast ($0's real, December 2017) 2021: 0; EXPENDITURE Forecast ($0's real, December 2017) 2022: 0
Non-conforming capital expenditure - recovered by a surcharge
Non-conforming capital expenditure - added to the speculative capital expenditure account
Non-conforming capital expenditure - other
Capital contributions rolled into the capital base
Speculative capital expenditure account rolled into the capital base
Re-use of redundant assets rolled into the capital base
Redundant assets rolled out of the capital base
Disposals
Augmentation
Conforming capital expenditure |  | EXPENDITURE Forecast ($0's real, December 2017) 2018: 0; EXPENDITURE Forecast ($0's real, December 2017) 2019: 0; EXPENDITURE Forecast ($0's real, December 2017) 2020: 0; EXPENDITURE Forecast ($0's real, December 2017) 2021: 0; EXPENDITURE Forecast ($0's real, December 2017) 2022: 0
Non-conforming capital expenditure - recovered by a surcharge
Non-conforming capital expenditure - added to the speculative capital expenditure account
Non-conforming capital expenditure - other
Capital contributions rolled into the capital base
Speculative capital expenditure account rolled into the capital base
Re-use of redundant assets rolled into the capital base
Redundant assets rolled out of the capital base
Disposals
Non-system
Conforming capital expenditure |  | EXPENDITURE Forecast ($0's real, December 2017) 2018: 0; EXPENDITURE Forecast ($0's real, December 2017) 2019: 0; EXPENDITURE Forecast ($0's real, December 2017) 2020: 0; EXPENDITURE Forecast ($0's real, December 2017) 2021: 0; EXPENDITURE Forecast ($0's real, December 2017) 2022: 0
Non-conforming capital expenditure - recovered by a surcharge
Non-conforming capital expenditure - added to the speculative capital expenditure account
Non-conforming capital expenditure - other
Capital contributions rolled into the capital base
Speculative capital expenditure account rolled into the capital base
Re-use of redundant assets rolled into the capital base
Redundant assets rolled out of the capital base
Disposals
|  | EXPENDITURE Forecast ($0's real, December 2017) 2018: 0; EXPENDITURE Forecast ($0's real, December 2017) 2019: 0; EXPENDITURE Forecast ($0's real, December 2017) 2020: 0; EXPENDITURE Forecast ($0's real, December 2017) 2021: 0; EXPENDITURE Forecast ($0's real, December 2017) 2022: 0 |  | Check General Land
OTHER
Replacement
Conforming capital expenditure |  | EXPENDITURE Forecast ($0's real, December 2017) 2018: 4521436.007; EXPENDITURE Forecast ($0's real, December 2017) 2019: 5442233.0387; EXPENDITURE Forecast ($0's real, December 2017) 2020: 1388440.1911; EXPENDITURE Forecast ($0's real, December 2017) 2021: 5938518.8651; EXPENDITURE Forecast ($0's real, December 2017) 2022: 5414899.4341
Non-conforming capital expenditure - recovered by a surcharge
Non-conforming capital expenditure - added to the speculative capital expenditure account
Non-conforming capital expenditure - other
Capital contributions rolled into the capital base
Speculative capital expenditure account rolled into the capital base
Re-use of redundant assets rolled into the capital base
Redundant assets rolled out of the capital base
Disposals
Augmentation
Conforming capital expenditure |  | EXPENDITURE Forecast ($0's real, December 2017) 2018: 0; EXPENDITURE Forecast ($0's real, December 2017) 2019: 0; EXPENDITURE Forecast ($0's real, December 2017) 2020: 0; EXPENDITURE Forecast ($0's real, December 2017) 2021: 0; EXPENDITURE Forecast ($0's real, December 2017) 2022: 0
Non-conforming capital expenditure - recovered by a surcharge
Non-conforming capital expenditure - added to the speculative capital expenditure account
Non-conforming capital expenditure - other
Capital contributions rolled into the capital base
Speculative capital expenditure account rolled into the capital base
Re-use of redundant assets rolled into the capital base
Redundant assets rolled out of the capital base
Disposals
Non-system
Conforming capital expenditure |  | EXPENDITURE Forecast ($0's real, December 2017) 2018: 4302012.5025; EXPENDITURE Forecast ($0's real, December 2017) 2019: 2358423.021; EXPENDITURE Forecast ($0's real, December 2017) 2020: 2205038.5537; EXPENDITURE Forecast ($0's real, December 2017) 2021: 2173174.0503; EXPENDITURE Forecast ($0's real, December 2017) 2022: 1858656.5268
Non-conforming capital expenditure - recovered by a surcharge
Non-conforming capital expenditure - added to the speculative capital expenditure account
Non-conforming capital expenditure - other
Capital contributions rolled into the capital base
Speculative capital expenditure account rolled into the capital base
Re-use of redundant assets rolled into the capital base
Redundant assets rolled out of the capital base
Disposals
|  | EXPENDITURE Forecast ($0's real, December 2017) 2018: 0; EXPENDITURE Forecast ($0's real, December 2017) 2019: 0; EXPENDITURE Forecast ($0's real, December 2017) 2020: 0; EXPENDITURE Forecast ($0's real, December 2017) 2021: 0; EXPENDITURE Forecast ($0's real, December 2017) 2022: 0 |  | Check OTHER
|  | EXPENDITURE Forecast ($0's real, December 2017) 2018: 0; EXPENDITURE Forecast ($0's real, December 2017) 2019: 0; EXPENDITURE Forecast ($0's real, December 2017) 2020: 0; EXPENDITURE Forecast ($0's real, December 2017) 2021: 0; EXPENDITURE Forecast ($0's real, December 2017) 2022: 0 |  | Check Total
Note: Regarding 7.2 - CAPITAL EXPENDITURE - AS COMMISSIONED (by driver)
As per S5.2.2 of the submission :
APA VTS has recorded all capital expenditure on an “as Incurred” basis. The distinction between capital expenditure “as Incurred” vs “as Commissioned” is that the Service Provider is allowed to earn a return on capital invested “as Incurred”, but does not record depreciation on the investment until a depreciable asset has been created (that is, it has been Commissioned).
Since APA VTS has applied the forecast depreciation from the earlier PTRM, the distinction between capex “as Incurred” and “as Commissioned” is not required to drive the calculation of depreciation in the Roll Forward Model.

## 1.3 Output│Tables
1.3 Output│Tables
| Historic Capex ($nominal m) | [8 empty] | Forecast Capex (nominal $m) | [7 empty] | Pipelines identified for pigging
|  | 2013 | 2014 | 2015 | 2016 (e) | 2017 (f) | Total |  |  |  | 2018 | 2019 | 2020 | 2021 | 2022 | Total |  | Pipeline | Length (km) | Diameter (mm) | Cost ($m) | Year of ILI | Current usage pattern | 2015-12-01 | 2018-01-01 | 2020-01-01 | 2021-01-01 | 2022-01-01
| Capital expenditure | 15.5962 | 124.1752 | 94.5272 | 105.0136 | 62.9868 | 402.2989 |  |  | Capital expenditure | 61.1348 | 56.9351 | 72.341 | 13.7257 | 10.8724 | 215.0091 |  | T57 Ballan – Ballarat | 22 | 150 | 0.6 | 2018/19 | WCS 4 | 14760 | 20538 | 26315 | 29204 | 32093
[18 empty] | T61 Pakenham – Wollert | 93 | 750 | 0.7 | 2019/20 | WCS 5 | 14375 | 20002 | 25629 | 28442 | 31256
| Capex by Asset Class ($ nominal m) | [8 empty] | Capex by Asset Class (real 2017 $m) | [7 empty] | T62 Derrimut – Sunbury | 24 | 150 | 0.4 | 2017/18 | Increased Rate of 10%
[18 empty] | T66-70 Mt Franklin -Kyneton - Bendigo | 91 | 300 | 0.6 | 2019/20 | WCS 4 | 14760 | 21115 | 27471 | 30648 | 33826
| Asset Class | 2013 | 2014 | 2015 | 2016 (e) | 2017 (f) | Total |  |  |  | 2018 | 2019 | 2020 | 2021 | 2022 | Total |  | T75 Wandong - Kyneton | 84 | 300 | 0.6 | 2019/2020 | WCS 5 | 14375 | 20565 | 26754 | 29849 | 32944
| Pipelines | 4.1116 | 85.8261 | 72.0774 | 93.2526 | 52.541 | 307.8086 |  |  | Pipelines | 35.9329 | 33.8056 | 51.7749 | 0.17029 | 0.17029 | 121.854 |  | T108 Newport | 1 | 450 | 0.5 | 2018
| Compressors | 8.4012 | 27.7984 | 7.7657 | 6.317 | 0.965 | 51.2474 |  |  | Compressors | 14.4254 | 13.4972 | 12.9727 | 3.3662 | 2.8321 | 47.0934 |  | T65 Dandenong - Princes Highway | 6 | 750 | 0.6 | 2018
| City Gates & Field Regs | 1.1037 | 5.1064 | 8.3758 | 1.503 | 0.46 | 16.5489 |  |  | City Gates & Field Regs | 0 | 2.3361 | 2.378 | 0.68322 | 0.24695 | 5.6443 |  | T24 Brooklyn - Corio | 51 | 350 | 0.2 | 2021
| Odourant Plants | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Odourant Plants | 0.07808 | 0 | 0 | 0 | 0 | 0.07808 |  | T16 Dandenong – West Melbourne | 36 | 750 | 0.2 | 2021
| Gas Quality | 0 | 0.09101 | 0.28585 | 0.35095 | 0.05 | 0.77781 |  |  | Gas Quality | 1.0063 | 0 | 0 | 0 | 0 | 1.0063 |  | T60 Longford -Dandenong | 109 | 750 | 0.3 | 2022
| Other | 1.9333 | 5.126 | 5.0021 | 3.5331 | 8.9238 | 24.5183 |  |  | Other | 9.0323 | 6.3257 | 4.2449 | 8.5355 | 7.2736 | 35.412 |  | T70 Ballan – Bendigo | 91 | 150 | 0.6 | 2020
| Buildings | 0.046302 | 0.22734 | 1.0204 | 0.056882 | 0.04705 | 1.398 |  |  | Buildings | 0.65985 | 0.97052 | 0.97052 | 0.97052 | 0.34957 | 3.921 |  | T33 South Melbourne – Brooklyn | 13 | 750 | 0.1 | 2021
| General Land | 0 | 0 | 0 | 0 | 0 | 0 |  |  | General Land | 0 | 0 | 0 | 0 | 0 | 0 |  | T60 Longford – Tyers | 65 | 750 | 0.9 | 2022
| Total | 15.5962 | 124.1752 | 94.5272 | 105.0136 | 62.9868 | 402.2989 |  | 0 | Total | 61.1348 | 56.9351 | 72.341 | 13.7257 | 10.8724 | 215.0091 | 0 | T63 Tyers - Morwell | 16 | 500 | 0.7 | 2021
[18 empty] | T96 & T98 Chiltern- Rutherglen – Koonoomoo | 104 | 200 | 0.6 | 2022
| Capex by Asset Category ($nominal m) | [8 empty] | Capex by Driver (real 2017 $m) | [7 empty] | James Street - Laverton Pipeline (253) | 2 | 350 | 0.5 | Immediately after trap installation
[18 empty] | T37 Tyres - Maryvale | 5 | 150 | 0.4 | Immediately after trap installation
| Asset Category | 2013 | 2014 | 2015 | 2016 (e) | 2017 (f) | Total |  |  | Asset Category | 2018 | 2019 | 2020 | 2021 | 2022 | Total |  | T118 Trugannina-Plumpton | 8 | 500 | 0.6 | 2022
| Augmentation | 12.3099 | 112.4157 | 74.5887 | 92.1364 | 52.331 | 343.7817 |  |  | Augmentation | 44.3874 | 46.8372 | 59.7724 | 0 | 0 | 150.9969 |  | T01 Morwell – Dandenong (post inspection program) | 127 | 450 | 0.1 | 2018
| Replacement | 1.5504 | 7.5217 | 14.2083 | 10.5241 | 2.105 | 35.9095 |  |  | Replacement | 12.51 | 6.5454 | 9.3162 | 10.1582 | 8.5795 | 47.1092
| Non-System | 1.7358 | 4.2378 | 5.7301 | 2.3531 | 8.5508 | 22.6077 |  |  | Non-System | 4.2375 | 3.5526 | 3.2525 | 3.5675 | 2.293 | 16.903
| Total | 15.5962 | 124.1752 | 94.5272 | 105.0136 | 62.9868 | 402.2989 |  | 0 | Total | 61.1348 | 56.9351 | 72.341 | 13.7257 | 10.8724 | 215.0091 | 0
| Non Augmentation Capex($nominal m) | [8 empty] | Warragul lateral expansion (real 2017 $m)
| Asset Category | 2013 | 2014 | 2015 | 2016 (e) | 2017 (f) | Total |  |  |  | 2018 | 2019 | 2020 | 2021 | 2022 | Total
| Non Augmentation capex | 3.2863 | 11.7595 | 19.9384 | 12.8772 | 10.6558 | 58.5172 |  | 0 | Warragul lateral expansion | 0 | 2.6864 | 0.9299 | 0 | 0 | 3.6163
| Historic Actual vs AER Forecast ($nominal m) | [8 empty] | Westbound expansion of the South West Pipeline (real 2017 $m)
| Asset Category | 2013 | 2014 | 2015 | 2016 (e) | 2017 (f) | Total |  |  |  | 2018 | 2019 | 2020 | 2021 | 2022 | Total
| AER Forecast | [8 empty] | Brooklyn reconfiguration | 2.0253 | 0 | 0 | 0 | 0 | 2.0253
| Augmentation | 6.1205 | 78.0233 | 12.1831 | 0 | 0 | 96.3269 |  |  | Winchelsea bi-directional works | 1.4678 | 0 | 0 | 0 | 0 | 1.4678
| Replacement | 8.8816 | 15.4969 | 11.6568 | 12.1844 | 6.4082 | 54.6279 |  |  | Total | 3.493 | 0 | 0 | 0 | 0 | 3.493
| Non-System | 2.8696 | 6.0232 | 1.0482 | 1.7652 | 2.8436 | 14.5499
| Total | 17.8717 | 99.5434 | 24.8881 | 13.9496 | 9.2518 | 165.5046 |  | 0 | WORM (real 2017 $m)
Actuals
| Augmentation | 12.3099 | 112.4157 | 74.5887 | 92.1364 | 52.331 | 343.7817 |  | 0 |  | 2018 | 2019 | 2020 | 2021 | 2022 | 0
| Replacement | 1.5504 | 7.5217 | 14.2083 | 10.5241 | 2.105 | 35.9095 |  | 0 | WORM | 23.7174 | 44.1508 | 58.8425 | 0 | 0 | 126.7107
| Non-System | 1.7358 | 4.2378 | 5.7301 | 2.3531 | 8.5508 | 22.6077 |  | 0
| Total | 15.5962 | 124.1752 | 94.5272 | 105.0136 | 62.9868 | 402.2989 |  | 0 | Inline inspection (real 2017 $m)
Difference
| Augmentation | 6.1894 | 34.3924 | 62.4056 | 92.1364 | 52.331 | 247.4548 |  |  |  | 2018 | 2019 | 2020 | 2021 | 2022 | Total
| Replacement | -7.3312 | -7.9752 | 2.5516 | -1.6603 | -4.3032 | -18.7183 |  |  | Inline inspection | 3.6142 | 2.616 | 0.73488 | 4.6959 | 4.2901 | 15.9512
| Non-System | -1.1338 | -1.7854 | 4.6819 | 0.58787 | 5.7072 | 8.0578
| Total | -2.2756 | 24.6318 | 69.6391 | 91.064 | 53.735 | 236.7943 |  |  | Safety management - High consequence areas (real 2017 $m)
| Gas to Culcairn (nominal $m) | [9 empty] | 2018 | 2019 | 2020 | 2021 | 2022 | Total
|  | H1 | H2 | 2014 | 2015 | E2016 | F2017 | Total |  | Safety management - High consequence areas | 0 | 0 | 0 | 0 | 0 | 0
|  | 2013 | 2013
| Winchelsea compressor | 3.0965 | 8.1346 | 26.6064 | 2.4925 | 0.00087727 | 0 | 40.3309 |  | Brooklyn Compressor Station Upgrade (real 2017 $m)
| Wollert to Barnawartha looping (62TJ) | 2.0128 | 4.007 | 85.6489 | 72.0321 | 92.1344 | 43.0631 | 298.8984
| Total | 5.1093 | 12.1415 | 112.2553 | 74.5247 | 92.1353 | 43.0631 | 339.2292 |  |  | 2018 | 2019 | 2020 | 2021 | 2022 | Total
[10 empty] | Brooklyn Compressor Station Upgrade | 0 | 0 | 2.3737 | 2.3737 | 2.3737 | 7.1211
| $’m ($###) | H2 | 2014 | 2015 | E2016 | F2017 | Total
|  | 2013 | [7 empty] | VTS Turbine Overhauls (real 2017 $m)
| Wollert to Barnawartha looping | 4.007 | 85.6489 | 72.0321 | 92.1344 | 43.0631 | 298.8984
[11 empty] | 2018 | 2019 | 2020 | 2021 | 2022 | Total
[10 empty] | VTS Turbine Overhauls | 0 | 0 | 0 | 0 | 0 | 0
Anglesea Pipeline (nominal $m)
Actuate mainline valves in HCA areas (real 2017 $m)
|  | 2013 | 2014 | 2015 | 2016 (e) | 2017 (f) | 2018 (f) | Total
| AER Forecast | 0 | 1.3403 | 12.1831 | 0 | 0 | 0 | 13.5235 |  |  | 2018 | 2019 | 2020 | 2021 | 2022 | Total
| Actuals | 0 | 0 | 0 | 0 | 9.2679 | 17.5205 | 26.7883 |  | Actuate mainline valves in HCA areas | 0.98849 | 0.98849 | 0 | 0 | 0 | 1.977
| Difference | 0 | -1.3403 | -12.1831 | 0 | 9.2679 | 17.5205 | 13.2649
Coogee decommissioning (real 2017 $m)
Refurbishment and Upgrade capex compared to AER forecast (nominal $m)
[11 empty] | 2018 | 2019 | 2020 | 2021 | 2022 | Total
|  | 2013 | 2014 | 2015 | 2016 (e) | 2017 (f) | Total |  |  | Coogee decommissioning | 0 | 0 | 0 | 0 | 0 | 0
| AER Forecast | 8.8816 | 15.4969 | 11.6568 | 12.1844 | 6.4082 | 54.6279
| Actuals | 1.5504 | 7.5217 | 14.2083 | 10.5241 | 2.105 | 35.9095 |  |  | Iona CS aftercooler upgrade (real 2017 $m)
| Difference | -7.3312 | -7.9752 | 2.5516 | -1.6603 | -4.3032 | -18.7183
[11 empty] | 2018 | 2019 | 2020 | 2021 | 2022 | Total
| Regulator upgrade - Dandenong City Gate (nominal $m) | [8 empty] | Iona CS aftercooler upgrade | 1.7114 | 0 | 0 | 0 | 0 | 1.7114
|  | 2013 | 2014 | 2015 | 2016 (e) | 2017 (f) | Total |  |  | Emergency Equipment (real 2017 $m)
| AER Forecast | 3.7985 | 1.542 | 0 | 0 | 0 | 5.3405
| Actuals | 0.4795 | 2.6166 | 7.8111 | 0.75046 | 0 | 11.6577 |  |  |  | 2018 | 2019 | 2020 | 2021 | 2022 | Total
| Difference | -3.319 | 1.0746 | 7.8111 | 0.75046 | 0 | 6.3172 |  |  | Emergency Equipment | 0.26824 | 0.26824 | 0.37149 | 0.38606 | 0.26824 | 1.5623
| Inline inspection (nominal $m) | [8 empty] | B&T projects (real 2017 $m)
|  | 2013 | 2014 | 2015 | 2016 (e) | 2017 (f) | Total |  |  |  | 2018 | 2019 | 2020 | 2021 | 2022 | Total
| AER Forecast | 0.3458 | 0.21429 | 1.6125 | 6.8102 | 3.9168 | 12.8997 |  |  | B&T projects | 2.4639 | 1.4683 | 1.1443 | 1.4593 | 0.74493 | 7.2808
| Actuals | 0.33064 | 2.3225 | 0.60559 | 2.1761 | 0.15 | 5.5849
| Difference | -0.01516 | 2.1082 | -1.0069 | -4.6341 | -3.7668 | -7.3148 |  |  | Storage shed-Dandenong, Wollert & Springhurst (real 2017 $m)
| Brooklyn Compressor station cooler upgrades (nominal $m) | [9 empty] | 2018 | 2019 | 2020 | 2021 | 2022 | Total
[10 empty] | Storage shed-Dandenong, Wollert & Springhurst | 0 | 0.62094 | 0.62094 | 0.62094 | 0 | 1.8628
|  | 2013 | 2014 | 2015 | 2016 (e) | 2017 (f) | Total
| AER Forecast | -0.0071171 | 4.4113 | 0 | 0 | 0 | 4.4041 |  |  | Security - Physical (real 2017 $m)
| Actuals | 0.02709 | 0.88962 | 5.0072 | 3.2722 | 0 | 9.1962
| Difference | 0.034207 | -3.5216 | 5.0072 | 3.2722 | 0 | 4.792 |  |  |  | 2018 | 2019 | 2020 | 2021 | 2022 | Total
[10 empty] | Security - Physical | 0.34957 | 0.34957 | 0.34957 | 0.34957 | 0.34957 | 1.7479
Brooklyn Compressor Station Brooklyn Compressor Station Isolation and Loading Valves upgrades (nominal $m)
|  | 2013 | 2014 | 2015 | 2016 (e) | 2017 (f) | Total
| AER Forecast | 0 | 0.94971 | 0 | 0 | 0 | 0.94971
| Actuals | 0.0022446 | 0.016578 | 0.18368 | 1.6105 | 0 | 1.813
| Difference | 0.0022446 | -0.93313 | 0.18368 | 1.6105 | 0 | 0.86325
Non-system capital expenditure (nominal $m)
|  | 2013 | 2014 | 2015 | 2016 (e) | 2017 (f) | Total
| AER Forecast | 2.8696 | 6.0232 | 1.0482 | 1.7652 | 2.8436 | 14.5499 |  | 0
| Actuals | 1.7358 | 4.2378 | 5.7301 | 2.3531 | 8.5508 | 22.6077 |  | 0
| Difference | -1.1338 | -1.7854 | 4.6819 | 0.58787 | 5.7072 | 8.0578
Corporate IT, business and technology projects
|  | 2013 | 2014 | 2015 | 2016 (e) | 2017 (f) | Total
| AER Forecast | -1.5422 | 0 | 0 | 0 | 0 | -1.5422
| Actuals | 1.5213 | 3.6419 | 4.0075 | 1.8744 | 7.0055 | 18.0506
| Difference | 3.0634 | 3.6419 | 4.0075 | 1.8744 | 7.0055 | 19.5928
Dandenong redevelopment (nominal $m)
|  | 2013 | 2014 | 2015 | 2016 (e) | 2017 (f) | Total
| AER Forecast | 3.908 | 5.5786 | 0 | 0 | 0 | 9.4866
| Actuals | 0 | 0 | 0 | 0 | 5.0578 | 5.0578
| Difference | -3.908 | -5.5786 | 0 | 0 | 5.0578 | -4.4288

## 1.4 Output│Graphs
1.4 Output│Graphs
Capital expenditure acroos current and forecast AA
|  | 2013 | 2014 | 2015 | 2016 (e) | 2017 (f) | 2018 | 2019 | 2020 | 2021 | 2022
| APA VTS Actuals/Forecast | 15.5962 | 124.1752 | 94.5272 | 105.0136 | 62.9868 | 61.1348 | 56.9351 | 72.341 | 13.7257 | 10.8724
| AER Forecast | 17.8717 | 99.5434 | 24.8881 | 13.9496 | 9.2518 | 0 | 0 | 0 | 0 | 0
| APA Forecast | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## 1.5 Output│2017 Corp Capex
1.5 Output│2017 Corp Capex
| Historic Capex # | Project | Unit | 2017
| 89 | Enterprise Content Management | real $2017 | 0
| 90 | Victoria CRE | real $2017 | 0
| 90 | APA Grid Energy Components Upgrade | real $2017 | 0
| 91 | APA Grid Extend Program | real $2017 | 0
| 92 | APA Grid Services Initiatives Program | real $2017 | 0
| 93 | Hyperion Upgrade to 11.1.2.4 | real $2017 | 0
| 94 | BI - Transmission Dashboard and Enterprise Pilot | real $2017 | 0
| 95 | HR Systems Refresh | real $2017 | 0
| 96 | Transmission EAM Data Management Tool | real $2017 | 0
| 97 | SharePoint Upgrade | real $2017 | 0
| 98 | eForm Digitisation | real $2017 | 0
| 99 | Historian Upgrade - version 2012 to 2015 | real $2017 | 0
| 100 | Hazardous Area Platform | real $2017 | 0
| 101 | PPM Refresh | real $2017 | 0
| 102 | BizTalk Upgrade FY2018 | real $2017 | 0
| 103 | Automated Testing Tool | real $2017 | 0
| 104 | Code Management Software | real $2017 | 0
| 105 | CRM Upgrade | real $2017 | 0
| 106 | X-Info Aware Version 2 | real $2017 | 0
| 106 | Supplier Qualification and Compliance | real $2017 | 0
| 107 | Oracle eBS Upgrade to 12.2 | real $2017 | 0
| 108 | BizTalk System Upgrade 2020 | real $2017 | 0
| 109 | Applications Renewal | real $2017 | 0
| 110 | Infrastructure Renewal | real $2017 | 0
| 111 | Dandenong Relocation | real $2017 | 0
| 112 | 0 | real $2017 | 0
| 0 | 0 | real $2017 | 0
| 0 | 0 | real $2017 | 0
| 0 | 0 | real $2017 | 0
| 0 | 0 | real $2017 | 0
Table for inclusion in Historic Capex
|  | Hyperion Upgrade to 11.1.2.4 | real $2017 | 0
|  | SharePoint Upgrade | real $2017 | 0
|  | APA Grid Extend Program | real $2017 | 0
|  | Enterprise Content Management | real $2017 | 0
|  | Victoria CRE | real $2017 | 0
|  | Dandenong Relocation | real $2017 | 0
|  | B&T Projects | real $2017 | 0
|  | Total B&T Projects | real $2017 | 0

## 2.0 Input│Historic Capex
2.0 Input│Historic Capex |  |  |  |  | Actual Capex | [6 empty] | AER Forecast
Capex # | Project Name | Class | Category | Included in forecast? | 2012 | 2013 | 2014 | 2015 | 2016 (e) | 2017 (f) | Total | 2013 | 2014 | 2015 | 2016 | 2017 | Total
1 | Stonehaven CS - now Winchelsea | Compressors | Augmentation | Yes | 0 | 8134553.96 | 26606375.39 | 2492547.98 | 877.27 | 0 | 37234354.6 | 4309004.3764 | 29602016.1411 | 0 | 0 | 0 | 33911020.5175
2 | Warragul Looping | Pipelines | Augmentation | Yes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2517235.2838 | 0 | 0 | 0 | 2517235.2838
3 | Anglesea Pipeline Extension | Pipelines | Augmentation | Yes | 0 | 0 | 0 | 0 | 0 | 9267887.2827 | 9267887.2827 | 0 | 1289952.7622 | 11551411.6212 | 0 | 0 | 12841364.3835
4 | Wollert CS A Unit reinstrumentation | Compressors | Replacement | Yes | 0 | 0 | 0 | 0 | 100000 | 200000 | 300000 | 0 | 0 | 252120.4319 | 252708.1907 | 0 | 504828.6226
5 | BCS Filter | City Gates & Field Regs | Replacement | Yes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 402388.9808 | 0 | 0 | 0 | 402388.9808
6 | Iona CS - Inlet Pressure Reduction | Compressors | Replacement | Yes | 0 | 104428.1 | 9056 | 0 | 0 | 0 | 113484.1 | 90049.12 | 0 | 0 | 0 | 0 | 90049.12
7 | Iona CS Control system replacement | Compressors | Replacement | Yes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 663922.5128 | 0 | 0 | 0 | 663922.5128
8 | SCS Cooler Upgrade | Compressors | Replacement | Yes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 909192.0344 | 0 | 0 | 909192.0344
9 | BCS Emergency Lighting | Other | Replacement | Yes | 0 | 61810.95 | 0 | 0 | 0 | 0 | 61810.95 | 12688.7 | 0 | 0 | 0 | 0 | 12688.7
10 | GCS Emergency Lighting Upgrade | Other | Replacement | Yes | 0 | 879.8 | 0 | 0 | 0 | 0 | 879.8 | -6200.92 | 0 | 0 | 0 | 0 | -6200.92
11 | Wollert CS Emergency Lighting | Other | Replacement | Yes | 0 | 0 | 111330.8 | 0 | 0 | 0 | 111330.8 | 50134.75 | 0 | 0 | 0 | 0 | 50134.75
12 | Emergency - fully equipped caravan | Other | Replacement | Yes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 141829.4511 | 0 | 0 | 0 | 141829.4511
13 | Emergency - Gas blowdown and flaring sytem | Other | Replacement | Yes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 202382.2122 | 202382.2122
14 | Emergency - refurbish and re-testing of pipes | Other | Replacement | Yes | 0 | 0 | 40300 | 0 | 0 | 0 | 40300 | 0 | 0 | 0 | 12120.2505 | 202382.2122 | 214502.4626
15 | Emergency - SMR radio upgrade | Other | Replacement | Yes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 66661.3776 | 0 | 66661.3776
16 | Emergency BA escape sets | Other | Replacement | Yes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10029.2 | 0 | 0 | 0 | 0 | 10029.2
17 | Emergency diesel fuel storage | Other | Replacement | Yes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50294.1316 | 84667.0825 | 0 | 0 | 134961.2141
18 | Emergency Plidco fittings - Sleeve vent | Pipelines | Replacement | Yes | 0 | 0 | 0 | 0 | 0 | 70000 | 70000 | 0 | 0 | 40207.1685 | 191241.7169 | 0 | 231448.8853
19 | Emergency Response Equipment | Other | Replacement | Yes | 0 | 0 | 14416.72 | 38911 | 30323.6 | 0 | 83651.32 | 90262.8 | 90529.4369 | 90714.7312 | 90901.8786 | 91071.9955 | 453480.8422
20 | Emergency Spark Proof tools | Other | Replacement | Yes | 0 | 0 | 0 | 0 | 0 | 20000 | 20000 | 20058.4 | 20117.6526 | 20158.8292 | 0 | 0 | 60334.8818
21 | Purchase and replacement of emergency fittings and Equipment | Other | Replacement | Yes | 0 | 59521.63 | 173679.9 | 0 | 0 | 0 | 233201.53 | 500705.2547 | 778243.1205 | 0 | 0 | 0 | 1278948.3753
22 | Facilities Communication Systems Upgrade | Other | Replacement | Yes | 0 | 0 | 16081.25 | 0 | 0 | 0 | 16081.25 | 10026.95 | 10061.0718 | 10092.9213 | 10120.506 | 10155.2999 | 50456.749
23 | GCS Station Valve Upgrade | Compressors | Replacement | Yes | 0 | 922.2 | 94508.09 | 0 | 0 | 0 | 95430.29 | 0 | 183832.6928 | 0 | 0 | 0 | 183832.6928
24 | GCS Unit 3 Turbine Overhaul | Compressors | Replacement | Yes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 353063.1517 | 0 | 0 | 353063.1517
25 | SMS - Compressor station vents-Various | Compressors | Replacement | Yes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100610.7182 | 0 | 0 | 0 | 100610.7182
26 | AS 2885 Design Life reviews of Facilities&Pipelines | City Gates & Field Regs | Replacement | Yes | 0 | 890.75 | 142234.07 | 54126.05 | 63973.92 | 50000 | 311224.79 | 210095.6911 | 213898.8643 | 215318.6246 | 216698.6838 | 325703.4189 | 1181715.2827
27 | BCG Un-regulated Bypass Upgrade | City Gates & Field Regs | Replacement | Yes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 126354.0954 | 0 | 126354.0954
28 | Dandenong CG gas heater | City Gates & Field Regs | Replacement | Yes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2928953.3117 | 0 | 0 | 2928953.3117
29 | Hazardous Area Rectification | City Gates & Field Regs | Replacement | Yes | 0 | 10313.6 | 32182.3 | 134741.2 | 162983.16 | 100000 | 440220.26 | 185256.1857 | 213753.5702 | 225328.8143 | 163270.8299 | 111172.1288 | 898781.5289
30 | Hazardous Areas Review | City Gates & Field Regs | Replacement | Yes | 0 | 34062.33 | 0 | 0 | 0 | 0 | 34062.33 | 422529.6954 | 406329.1105 | 277205.7189 | 50746.6663 | 50919.0449 | 1207730.2359
31 | Heater upgrade - Laverton North CG | City Gates & Field Regs | Replacement | Yes | 0 | 5671 | 0 | 0 | 0 | 0 | 5671 | 0 | 0 | 0 | 723528.0377 | 0 | 723528.0377
32 | Odorant Dandenong Pump Upgrade 700 & 2800 kPa | Gas Quality | Replacement | Yes | 0 | 0 | 0 | 285847.41 | 6015.5 | 0 | 291862.91 | 0 | 251504.3405 | 0 | 0 | 0 | 251504.3405
33 | Regulator upgrade - Dandenong City Gate (exclude filters) | City Gates & Field Regs | Replacement | Yes | 0 | 479498.96 | 2616566.96 | 7811136.25 | 750463.8 | 0 | 11657665.97 | 3740075.5782 | 1483992.4241 | 0 | 0 | 0 | 5224068.0022
34 | Valve - Pipeline LNG plant Isolation Valve Actuator Replacement | City Gates & Field Regs | Replacement | Yes | 0 | 67874.3 | 307062.84 | 0 | -0.02 | 0 | 374937.12 | 0 | 0 | 93612.1728 | 0 | 0 | 93612.1728
35 | Valve - Pipeline to LNG plant UV325 valve replacement and loading valve | City Gates & Field Regs | Replacement | Yes | 0 | 67319.22 | 210131.45 | 0 | 0 | 0 | 277450.67 | 41114.185 | 241444.1669 | 0 | 0 | 0 | 282558.3519
36 | Valve - Corio CG Un-regulated Bypass Upgrade | City Gates & Field Regs | Replacement | Yes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 126354.0954 | 0 | 126354.0954
37 | Valve - Tyers Branch Valve Actuator Replacement | Pipelines | Replacement | Yes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 201203.4724 | 0 | 0 | 0 | 201203.4724
38 | Valve - UniBolt Phase 3 Replacement | City Gates & Field Regs | Replacement | Yes | 0 | 1130.5 | 92576.04 | 30257.33 | 53832.91 | 100000 | 277796.78 | -110012.58 | 0 | 126093.9827 | 126404.8385 | 0 | 142486.2412
39 | Pig Trap - Enclosure upgrade | City Gates & Field Regs | Replacement | Yes | 0 | 0 | 0 | 17709 | 84557.63 | 25000 | 127266.63 | 46128.11 | 90541.5626 | 90787.6676 | 91011.4837 | 91267.4178 | 409736.2417
40 | Pig Trap - Pipe Support Upgrade | City Gates & Field Regs | Replacement | Yes | 0 | 174 | 63266.31 | 250206.75 | 24895.18 | 25000 | 363542.24 | 95264.575 | 95571.6494 | 95831.4269 | 96067.6772 | 20281.6484 | 403016.9769
41 | BCS Administration Building Distribution Board Upgrade | Compressors | Replacement | Yes | 0 | 0 | -52 | 0 | 30000 | 0 | 29948 | 30028.85 | 0 | 0 | 0 | 0 | 30028.85
42 | Equipment - Field Equipment | Other | Non-System | Yes | 0 | 78414.37 | 33433 | 0 | 0 | 10000 | 121847.37 | 47656 | 50294.1316 | 50397.0729 | 50501.0436 | 50595.553 | 249443.8012
43 | Equipment - Gas Detectors | Other | Non-System | Yes | 0 | 0 | 0 | 0 | 0 | 10000 | 10000 | 0 | 0 | 0 | 0 | 101191.1061 | 101191.1061
44 | Equipment - IT Purchases | Other | Non-System | Yes | 0 | 28090.5164 | 85086.328 | 94876.5278 | 59503.3603 | 0 | 267556.7325 | 23593.693 | 23663.3889 | 23711.8228 | 23760.741 | 23805.2077 | 118534.8535
45 | Equipment - Test | Other | Non-System | Yes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50146 | 50294.1316 | 50397.0729 | 50501.0436 | 50595.553 | 251933.8012
46 | Equipment - Victorian low value pool purchases | Other | Non-System | Yes | 0 | 52890.5047 | 215346.1091 | 550230.7606 | 163384.2868 | 28230 | 1010081.6612 | -126715.05 | 10058.8263 | 10079.4146 | 10100.2087 | 10119.1106 | -86357.4898
47 | Dandenong 180 Greens Road Office Redevelopment | Buildings | Non-System | Yes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3847881.4201 | 5368873.9617 | 0 | 0 | 0 | 9216755.3818
48 | Dandenong Asphalt Resurfacing | Other | Non-System | Yes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 252187.9655 | 0 | 0 | 252187.9655
49 | Dandenong Complex asbestos removal | Buildings | Non-System | Yes | 0 | 0 | 60923.51 | 0 | 0 | 0 | 60923.51 | 75208.875 | 75451.3022 | 30262.5559 | 30337.1612 | 30422.4726 | 241682.3669
50 | Dandenong external surface repainting | Buildings | Non-System | Yes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100610.7182 | 0 | 0 | 0 | 100610.7182
51 | Dandenong Office Purchases | Other | Non-System | Yes | 0 | 8861.6981 | 34769.95 | 31686.2177 | 0 | 0 | 75317.8658 | -18289.614 | 47326.7778 | 47423.6456 | 47521.4821 | 47610.4154 | 171592.7069
52 | Dandenong Site - Storage shed | Buildings | Non-System | Yes | 0 | 11857.7292 | 66978.2157 | 0 | 0 | 0 | 78835.9449 | 442388 | 0 | 0 | 0 | 0 | 442388
53 | Pigging - Tracking and locating tools | Other | Non-System | Yes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20122.1436 | 0 | 0 | 0 | 20122.1436
54 | Pigging - Two portable liquid collectors for pigging | Other | Non-System | Yes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 235807.7893 | 0 | 235807.7893
55 | Pigging -Two portable dust collectors for pigging | Other | Non-System | Yes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 234850.3598 | 0 | 0 | 234850.3598
56 | Control Room - Additonal OE monitor | Other | Non-System | Yes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10026.95 | 0 | 0 | 0 | 0 | 10026.95
57 | SCADA - Comms upgrade to IP network-VTS only | Other | Non-System | Yes | 0 | 0 | 0 | 0 | 55925 | 1000000 | 1055925 | 0 | 0 | 0 | 0 | 1813494.5561 | 1813494.5561
58 | SCADA - IT security | Other | Non-System | Yes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 94353.5995 | 0 | 0 | 0 | 0 | 94353.5995
59 | SCADA - Remote maintenance and engineering workstations [Control Room, Gooding, Brooklyn CS&CG, Wollert CS&CG, Springhurst, Iona] | Other | Non-System | Yes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10026.95 | 10061.0718 | 10092.9213 | 10120.506 | 10155.2999 | 50456.749
60 | SCADA - RTU/ PLC/HMI Development and Test bench [PC, iFix, Control Logix, Bristol Designer Tools] | Other | Non-System | Yes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23435.1125 | 0 | 0 | 0 | 0 | 23435.1125
61 | SCADA System Upgrade | Other | Non-System | Yes | 0 | 0 | 0 | 25383.25 | 113039.53 | 450000 | 588422.78 | 0 | 0 | 103816.4325 | 1042838.6837 | 471456.2441 | 1618111.3603
62 | Dandenong Building exterior coatings | Buildings | Non-System | Yes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150599.6738 | 150805.5024 | 0 | 301405.1762
63 | Dandenong site fire mains replacement | Buildings | Non-System | Yes | 0 | 4961.3378 | 88164.1814 | 1020411.517 | 30176.035 | 47050 | 1190763.0712 | 260525.5 | 0 | 0 | 0 | 0 | 260525.5
64 | Brooklyn guttering | Buildings | Non-System | Yes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40008.982 | 0 | 0 | 0 | 40008.982
65 | Wollert Control Room guttering | Buildings | Non-System | Yes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30040.5202 | 0 | 0 | 30040.5202
66 | Corporate IT | Other | Non-System | Yes | 0 | 211241.5961 | 302736.8717 | 276048.921 | 374324.3473 | 209022 | 1373373.7361 | -1518438.1342 | 0 | 0 | 0 | 0 | -1518438.1342
67 | Liquid management - Brooklyn | City Gates & Field Regs | Replacement | Yes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 329938.0122 | 0 | 0 | 329938.0122
68 | Liquid management - Gooding | City Gates & Field Regs | Replacement | Yes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 179323.053 | 0 | 0 | 0 | 179323.053
69 | Liquid management - Longford | City Gates & Field Regs | Replacement | Yes | 0 | -4131.05 | 0 | 0 | 0 | 0 | -4131.05 | -26613.3 | 0 | 0 | 0 | 0 | -26613.3
70 | Liquid Management - Pakenham | City Gates & Field Regs | Replacement | Yes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 144640.99 | 0 | 0 | 0 | 0 | 144640.99
71 | CP - Cathodic Protection Replacement | Pipelines | Replacement | Yes | 0 | 18725 | 98704 | 20000 | 89800 | 50000 | 277229 | 111615 | 200600.2392 | 200866.1817 | 201110.3393 | 201384.1158 | 915575.876
72 | CP - Corrosion Protection Testing Equipment | Other | Replacement | Yes | 0 | 0 | 0 | 0 | 47690 | 0 | 47690 | 10028.3 | 10059.7245 | 10084.8173 | 10108.3276 | 10133.5863 | 50414.7558
73 | Pig Trap - A Branch Valve on Pipeline 108 to Newport Install(124) | Pipelines | Replacement | Yes | 0 | 0 | 0 | 20098.4 | 868819.02 | 0 | 888917.42 | 0 | 0 | 0 | 2544803.7983 | 0 | 2544803.7983
74 | Pig Trap - Dandenong to Princes Highway Pipeline Install (129) | City Gates & Field Regs | Replacement | Yes | 0 | 0 | 0 | 31113.5 | 350723.48 |  | 381836.98 | 0 | 0 | 0 | 0 | 612316.7644 | 612316.7644
75 | Pig Trap - Laverton North to Laverton North Pipeline Install (162) | City Gates & Field Regs | Replacement | Yes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 927231.0325 | 0 | 927231.0325
76 | Pig Trap - Pakenham to Pakenham Pipeline Install (68) | City Gates & Field Regs | Replacement | Yes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1048301.8019 | 0 | 1048301.8019
77 | Pigging Program (T1 Dandenong - Morwell) | Other | Replacement | Yes | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 544363.3105 | 544363.3105
78 | Pigging Program (T56 Brooklyn - Ballan) | Other | Replacement | Yes | 0 | 0 | 0 | 140780.29 | 307245.02 | 0 | 448025.31 | 0 | 0 | 0 | 437345.3352 | 0 | 437345.3352
79 | Pigging Program (T59 Euro - Kyabram) | Other | Replacement | Yes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 405509.9168 | 0 | 405509.9168
80 | Pigging Program (T67 Guilford - Maryborough) | Other | Replacement | Yes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 222973.8245 | 222973.8245
81 | Pigging Program (T74 Keon Park - Wollert) | Other | Replacement | Yes | 0 | 5363.81 | 616839.03 | 37257.13 | 41434.17 | 0 | 700894.14 | 463932.6 | 0 | 0 | 0 | 0 | 463932.6
82 | Pigging Program (T92 Iona - Brooklyn) | Other | Replacement | Yes | 0 | 0 | 0 | 67224.28 | 486847.34 | 100000 | 654071.62 | 0 | 0 | 0 | 588402.5107 | 0 | 588402.5107
83 | Pig Trap - Princes Highway to Regent Street Pipeline Install(36) | City Gates & Field Regs | Replacement | Yes | 0 | 0 | 0 | 17158.9 | 7880.2 | 0 | 25039.1 | 0 | 0 | 0 | 0 | 1302572.535 | 1302572.535
84 | Pig Trap - Somerton to Somerton Pipeline Install (238) | City Gates & Field Regs | Replacement | Yes | 0 | 0 | 1590 | 24041.28 | 3716.12 |  | 29347.4 | 0 | 0 | 1107453.3093 | 0 | 0 | 1107453.3093
85 | Pig Trap - Tyers to Maryvale Pipeline Install (67) | City Gates & Field Regs | Replacement | Yes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 800555.5831 | 800555.5831
86 | Exposed pipe coating refurbishment | Pipelines | Replacement | Yes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 385280.0457 | 666424.8174 | 451772.5382 | 331747.4951 | 473524.7546 | 2308749.6509
87 | BCS Safety and Process Control System and RTU Upgrade | Compressors | Replacement | Yes | 0 | 23570.02 | 15134.58 | 12066 | 0 | 0 | 50770.6 | -10182.4 | 0 | 0 | 0 | 0 | -10182.4
88 | CS Type B compliance upgrade | Compressors | Replacement | Yes | 0 | 0 | 0 | 1070 | 230475.43 | 100000 | 331545.43 | 857042.8 | 0 | 0 | 0 | 0 | 857042.8
89 | GCS GEA Fuel Gas Upgrade | Compressors | Replacement | Yes | 0 | 0 | 0 | 0 | 61409.78 | 0 | 61409.78 | 50103.83 | 0 | 0 | 0 | 0 | 50103.83
90 | GCS Units 1,2,3&4 Suction/Discharge Actuated Valve Replacement | Compressors | Replacement | Yes | 0 | 0 | 0 | 0 | 218 | 300000 | 300218 | 851826 | 0 | 0 | 0 | 0 | 851826
91 | Mothball WCS station 'A' | Compressors | Replacement | Yes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 417567.5792 | 417567.5792
92 | Regulator Upgrade - Lara pneumatic control system upgrade | City Gates & Field Regs | Replacement | Yes | 0 | 0 | 0 | 5301 | 0 | 160000 | 165301 | 200883.4988 | 225031.278 | 0 | 0 | 0 | 425914.7768
93 | Security - High Risk sites security upgrade | Other | Replacement | Yes | 0 | 17837.72 | 24900 | 0 | 0 | 150000 | 192737.72 | 653450.2343 | 0 | 1013598.5702 | 726387.0907 | 0 | 2393435.8952
94 | Security - Small Site Facilities Fencing Upgrade | Other | Replacement | Yes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 75380.1395 | 75571.3785 | 75739.067 | 75945.4931 | 302636.0782
95 | Zonal Chromatograph Bottle Regulator Panels Upgrades | Gas Quality | Replacement | Yes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29343.24 | 0 | 0 | 0 | 0 | 29343.24
96 | Zonal Chromatograph Insertion Probes | Gas Quality | Replacement | Yes | 0 | 0 | 0 | 0 | 10000 | 50000 | 60000 | 95138.5 | 0 | 0 | 0 | 0 | 95138.5
97 | Zonal Chromatograph Upgrades | Gas Quality | Replacement | Yes | 0 | 0 | 91009.78 | 0 | 334933 | 0 | 425942.78 | 100175 | 100375.1495 | 100541.3636 | 100693.962 | 0 | 401785.4751
98 | RTU & Control System Upgrade - Facilities | Other | Replacement | Yes | 0 | 98368.47 | 100004.42 | 8235.2 | 131637.03 | 150000 | 488245.12 | -177951.8891 | 112280.706 | 112818.8859 | 113323.0898 | 113864.8742 | 274335.6667
99 | GCS Anti-Surge & Fast-Stop Valves Upgrade | Compressors | Replacement | Yes | 0 | 0 | 0 | 10038.5 | 497302.54 | 365000 | 872341.04 | 670537.384 | 0 | 0 | 0 | 0 | 670537.384
100 | GCS Control Room Fire Suppression System | Compressors | Replacement | Yes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45121.275 | 100610.7182 | 0 | 0 | 0 | 145731.9932
101 | GCS Units 1,2,3&4 Fire Suppression System | Compressors | Replacement | Yes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 227711.3845 | 0 | 227711.3845
102 | Iona CS - Unit Fire Suppression System | Compressors | Replacement | Yes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 281684.8614 | 0 | 0 | 0 | 281684.8614
103 | Wollert CG Control Hut Fire Suppression System | Compressors | Replacement | Yes | 0 | 0 | 0 | 0 | 80000 | 0 | 80000 | 0 | 35213.7514 | 35325.2246 | 0 | 0 | 70538.976
104 | Wollert CS A/B Control Room Fire Suppression System | Compressors | Replacement | Yes | 0 | 0 | 0 | 0 | 120000 | 0 | 120000 | 0 | 100610.7182 | 126161.5164 | 0 | 0 | 226772.2346
105 | BCG Control Hut Fire Suppression System | City Gates & Field Regs | Replacement | Yes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 65175.175 | 0 | 0 | 0 | 0 | 65175.175
106 | Valve - Actuate MLV's in T1 areas | Pipelines | Replacement | Yes | 0 | 0 | 0 | 0 | 10534 | 90000 | 100534 | 0 | 1318211.3589 | 1320304.4754 | 1322147.5981 | 0 | 3960663.4324
107 | Valve - Longford to Dandenong LV10 Vent Stack | Pipelines | Replacement | Yes | 0 | 34177.3 | 39851.75 | 0 | 0 | 0 | 74029.05 | 33404.0563 | 0 | 0 | 0 | 0 | 33404.0563
108 | BCS Station Isolation and Loading Valves | Compressors | Replacement | Yes | 0 | 2244.6 | 16577.75 | 183683.64 | 1610455.53 | 0 | 1812961.52 | 0 | 914005.1414 | 0 | 0 | 0 | 914005.1414
109 | Iona CS - Capacity Aftercooler upgrade | Compressors | Replacement | Yes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 709036.4354 | 0 | 0 | 0 | 709036.4354
110 | BCS DEA Upgrade | Compressors | Replacement | Yes | 0 | 1160 | 17428 | 0 | 316977 | 0 | 335565 | 0 | 0 | 354548.5777 | 0 | 0 | 354548.5777
111 | Pig Trap - Keon Park Install | City Gates & Field Regs | Replacement | Yes | 0 | 325106.72 | 1640823.98 | 0 | 0 | 0 | 1965930.7 | -375147.25 | 0 | 0 | 0 | 0 | -375147.25
112 | BCS Replacement of FSV, ASV & Other Valves | Compressors | Replacement | Yes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 894640.3511 | 0 | 0 | 0 | 894640.3511
113 | BCS Unit 10 & 11 Cooler Upgrade | Compressors | Replacement | Yes | 0 | 27089.84 | 889622.65 | 5007242.54 | 3272234.09 | 0 | 9196189.12 | -7007.61 | 3350780.2388 | 0 | 0 | 0 | 3343772.6288
114 | SMS - GIS & Aerial Photography | Pipelines | Replacement | Yes | 0 | 0 | 0 | 87 | 144969.5 | 0 | 145056.5 | 0 | 0 | 0 | 0 | 0 | 0
115 | Wollert to Clonbinane Looping | Pipelines | Augmentation | Yes | 0 | 4006990.75 | 85648927.66 | 65640112.89 | 635203.41 | 0 | 155931234.71 | 1819127.1999 | 34518284.328 | 0 | 0 | 0 | 36337411.5279
116 | MAOP Upgrade - Euroa to Springhurst (pipe) | Pipelines | Augmentation | Yes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 190659.3106 | 1722649.6837 | 0 | 0 | 0 | 1913308.9944
117 | MAOP Upgrade - Euroa to Springhurst (Reg) | City Gates & Field Regs | Augmentation | Yes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 602082.0336 | 5439946.3697 | 0 | 0 | 0 | 6042028.4033
118 | Valve - T60 Longford - Dandenong Upgrade hydraulic hand pump of actuators | Other | Replacement | Yes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 110306.35 | 0 | 0 | 0 | 0 | 110306.35
119 | VTS - BROOKLYN LARA LOOP | Pipelines | Replacement | Yes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -22513.1 | 0 | 0 | 0 | 0 | -22513.1
120 | VTS - WOLLERT 4 & 5 CAPEX | Compressors | Replacement | Yes | 0 | 3203.9 | 5158.96 | 0 | 0 | 0 | 8362.86 | -12958.5 | 0 | 0 | 0 | 0 | -12958.5
121 | VTS - MORWELL TYERS UPGRADE | City Gates & Field Regs | Replacement | Yes | 0 | 6147.52 | 0 | 0 | 0 | 0 | 6147.52 | -224.47 | 0 | 0 | 0 | 0 | -224.47
122 | VTS - MAOP UPGRADE CAPEX | City Gates & Field Regs | Replacement | Yes | 0 | 0 | -42.39 | 0 | 0 | 0 | -42.39 | -15153.32 | 0 | 0 | 0 | 0 | -15153.32
123 | VTS - BBP & BCP CG UPGRADE | City Gates & Field Regs | Replacement | Yes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -96840.03 | 0 | 0 | 0 | 0 | -96840.03
124 | VTS - BRANCH VALVE CASTLEMAINE | Pipelines | Replacement | Yes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -25899.12 | 0 | 0 | 0 | 0 | -25899.12
125 | VTS - EUROA CS NEW (PPOM) | Compressors | Augmentation | Yes | 0 | 116664.37 | 121805.28 | 59020.54 | -2941.24 | 0 | 294548.95 | -411065.65 | 0 | 0 | 0 | 0 | -411065.65
126 | VTS - SUNBURY PIPE LOOP (NEW) | Pipelines | Augmentation | Yes | 0 | 51715.09 | 38571.05 | 5019.95 | 4029.08 | 0 | 99335.17 | -483491.84 | 0 | 0 | 0 | 0 | -483491.84
127 | VTS - BCS 8&9 COOLERS UPG (NEW | Compressors | Replacement | Yes | 0 | -12591.73 | 22820.08 | 0 | 0 | 0 | 10228.35 | -453916.73 | 0 | 0 | 0 | 0 | -453916.73
128 | VTS - BCS 12 FAST STOP VALVE | Compressors | Replacement | Yes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -35578.82 | 0 | 0 | 0 | 0 | -35578.82
129 | VTS - BCS 8 & 9 UNIT VALVES | Compressors | Replacement | Yes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -281229.85 | 0 | 0 | 0 | 0 | -281229.85
130 | PIGGING T91 CURDIEVALE | Other | Replacement | Yes | 0 | 0 | 17873 | 0 | 0 | 0 | 17873 | 0 | 0 | 0 | 0 | 0 | 0
131 | VTS - BROOKLYN FIRE SERVICE | Buildings | Non-System | Yes | 0 | 29482.73 | 11269.5 | 0 | 0 | 0 | 40752.23 | -426344.52 | 0 | 0 | 0 | 0 | -426344.52
132 | VTS - BCS LUBE OIL COOLER 8&9 | City Gates & Field Regs | Replacement | Yes | 0 | 109672.54 | 0 | 0 | 0 | 0 | 109672.54 | 0 | 0 | 0 | 0 | 0 | 0
133 | VNIE Looping 6 to 8 | Pipelines | Augmentation | Yes | 0 | 0 | 0 | 6392032.4513 | 91499230.4789 | 43063099.4902 | 140954362.4203 | 0 | 0 | 0 | 0 | 0 | 0
134 | VTS16.SIB42 WOLL SOFT STARTERS | Other | Replacement | Yes | 0 | 0 | 0 | 0 | 30881 | 0 | 30881 | 0 | 0 | 0 | 0 | 0 | 0
135 | VTS.SIB99 WCS STN-A DISCHRG LQ | Other | Replacement | Yes | 0 | 0 | 0 | 0 | 190850.4 | 0 | 190850.4 | 0 | 0 | 0 | 0 | 0 | 0
136 | VTS17.SIB27 SCS CR EPS REMOVAL | Buildings | Non-System | Yes | 0 | 0 | 0 | 0 | 2856.8 | 0 | 2856.8 | 0 | 0 | 0 | 0 | 0 | 0
137 | VTS17.SIB30 DND EMERG ENTRANCE | Buildings | Non-System | Yes | 0 | 0 | 0 | 0 | 23849.55 | 0 | 23849.55 | 0 | 0 | 0 | 0 | 0 | 0
138 | Corporate other | Other | Non-System | Yes | 0 | 242365.2632 | 340342.973 | 308327.8805 | 17522.8525 | 0 | 908558.9692 | 0 | 0 | 0 | 0 | 0 | 0
139 | Market Services _APA Grid Prog | Other | Non-System | Yes | 0 | 0 | 0 | 153669.9247 | 156678.9204 | 0 | 310348.845 | 0 | 0 | 0 | 0 | 0 | 0
140 | APA Grid Perf & Resil Overhaul | Other | Non-System | Yes | 0 | 0 | 0 | 44725.1667 | 22022.8998 | 0 | 66748.0665 | 0 | 0 | 0 | 0 | 0 | 0
141 | APA Grid & Mrkt Srvs SIB Capex | Other | Non-System | Yes | 0 | 0 | 0 | 0 | 458.3444 | 0 | 458.3444 | 0 | 0 | 0 | 0 | 0 | 0
142 | APA Grid Extend | Other | Non-System | Yes | 0 | 0 | 0 | 0 | 67569.955 | 0 | 67569.955 | 0 | 0 | 0 | 0 | 0 | 0
143 | APA Grid Services Initiatives | Other | Non-System | Yes | 0 | 0 | 0 | 0 | 111589.8195 | 0 | 111589.8195 | 0 | 0 | 0 | 0 | 0 | 0
144 | CORP SIB16 DANDENONG REFURB | Other | Non-System | Yes | 0 | 0 | 0 | 303211.3819 | 3462.88 | 0 | 306674.2619 | 0 | 0 | 0 | 0 | 0 | 0
145 | Data Centre | Other | Non-System | Yes | 0 | 65362.0189 | 895833.2344 | 79250.1745 | 0 | 0 | 1040445.4278 | 0 | 0 | 0 | 0 | 0 | 0
146 | Enterprise Asset Management | Other | Non-System | Yes | 0 | 806330.3274 | 1986550.9701 | 2564771.5454 | 1771.8759 | 0 | 5359424.7188 | 0 | 0 | 0 | 0 | 0 | 0
147 | Enterprise Content Management | Other | Non-System | Yes | 0 | 0 | 0 | 104729.0841 | 325950.5132 | 512309 | 942988.5973 | 0 | 0 | 0 | 0 | 0 | 0
148 | EAM Bus Support & Governance | Other | Non-System | Yes | 0 | 0 | 0 | 0 | 42640.3455 | 0 | 42640.3455 | 0 | 0 | 0 | 0 | 0 | 0
149 | EAM TRANSMISSION ESTAB WORK | Other | Non-System | Yes | 0 | 0 | 0 | 0 | 160167.1738 | 0 | 160167.1738 | 0 | 0 | 0 | 0 | 0 | 0
150 | Oracle Integration with EAM | Other | Non-System | Yes | 0 | 0 | 0 | 0 | 10956.5236 | 0 | 10956.5236 | 0 | 0 | 0 | 0 | 0 | 0
151 | EAM Business Support-Reports | Other | Non-System | Yes | 0 | 0 | 0 | 0 | 3457.1067 | 0 | 3457.1067 | 0 | 0 | 0 | 0 | 0 | 0
152 | EC Upgrade | Other | Non-System | Yes | 0 | 0 | 0 | 0 | 185722.3966 | 0 | 185722.3966 | 0 | 0 | 0 | 0 | 0 | 0
153 | Finance Systems | Other | Non-System | Yes | 0 | 1751.8135 | 0 | 0 | 0 | 0 | 1751.8135 | 0 | 0 | 0 | 0 | 0 | 0
154 | Mobile phone CAPEX purchases | Other | Non-System | Yes | 0 | 0 | 22811.9773 | 27279.5795 | 28375.3809 | 0 | 78466.9376 | 0 | 0 | 0 | 0 | 0 | 0
155 | PPOM Phase 2 | Other | Non-System | Yes | 0 | 5453.1938 | 0 | 0 | 0 | 0 | 5453.1938 | 0 | 0 | 0 | 0 | 0 | 0
156 | Project Server Status Report | Other | Non-System | Yes | 0 | 7605.6406 | 4061.9411 | 0 | 0 | 0 | 11667.5817 | 0 | 0 | 0 | 0 | 0 | 0
157 | BI reporting | Other | Non-System | Yes | 0 | 33318.3814 | 2571.9179 | 0 | 0 | 0 | 35890.2993 | 0 | 0 | 0 | 0 | 0 | 0
158 | PPOM Snapshot Engine | Other | Non-System | Yes | 0 | 9285.9184 | 12608.9365 | 0 | 0 | 0 | 21894.8549 | 0 | 0 | 0 | 0 | 0 | 0
159 | APA Grid Ph.2 | Other | Non-System | Yes | 0 | 135912.9265 | 98899.2122 | 0 | 0 | 0 | 234812.1387 | 0 | 0 | 0 | 0 | 0 | 0
160 | APA Grid Ph. 3 | Other | Non-System | Yes | 0 | 2637.3633 | 0 | 0 | 0 | 0 | 2637.3633 | 0 | 0 | 0 | 0 | 0 | 0
161 | Vehicle Comms & Journey Mgmt | Other | Non-System | Yes | 0 | 0 | 2091.1818 | 85100.7826 | 154249.1835 | 0 | 241441.1479 | 0 | 0 | 0 | 0 | 0 | 0
162 | SCADA Satellite Strategy | Other | Non-System | Yes | 0 | 0 | 0 | 37193.7062 | 61169.9502 | 0 | 98363.6564 | 0 | 0 | 0 | 0 | 0 | 0
163 | SCADA Resilience Project FEED | Other | Non-System | Yes | 0 | 0 | 0 | 0 | 19777.1403 | 0 | 19777.1403 | 0 | 0 | 0 | 0 | 0 | 0
164 | IOC SCADA GAP ANALYSIS | Other | Non-System | Yes | 0 | 0 | 0 | 0 | 4246.8422 | 0 | 4246.8422 | 0 | 0 | 0 | 0 | 0 | 0
165 | SCADA Resilience Phase 1 Recom | Other | Non-System | Yes | 0 | 0 | 0 | 0 | 4887.8165 | 0 | 4887.8165 | 0 | 0 | 0 | 0 | 0 | 0
166 | Melbourne Metro CRE | Other | Non-System | Yes | 0 | 0 | 0 | 0 | 295817.7849 | 0 | 295817.7849 | 0 | 0 | 0 | 0 | 0 | 0
167 | Adjustments required for differences in CWIP and FAR records | Other | Non-System | Yes | 0 | 0 | -26601 | 23200 | -178445 | 0 | -181846 | 0 | 0 | 0 | 0 | 0 | 0
168 | APA Grid | Other | Non-System | Yes | 0 | 0 | 0 | 0 | 0 | 261222 | 261222 | 0 | 0 | 0 | 0 | 0 | 0
169 | B&T projects | Other | Non-System | Yes | 0 | 0 | 0 | 0 | 0 | 598799 | 598799 | 0 | 0 | 0 | 0 | 0 | 0
170 | Dandenong Relocation | Other | Non-System | Yes | 0 | 0 | 0 | 0 | 0 | 5057812 | 5057812 | 0 | 0 | 0 | 0 | 0 | 0
171 | Victoria CRE | Other | Non-System | Yes | 0 | 0 | 0 | 0 | 0 | 366376 | 366376 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0
0
0

## 3.0 Input│AMP
3.0 Input│AMP
Item Ref. | Access Arrangement Description | Business case number | Allocator | Asset Class | Asset Category | 2018 | 2019 | 2020 | 2021 | 2022 | Labour | Material | Plant | Subcontract | Other | Total
1 | All CS buffer Air shutoff system for all compressors | 202 | VTS | Compressors | Replacement | 381730.5067 | 190865.2533 | 0 | 0 | 0 | 23.66% | 74.37% | 0% | 1.964% | 0% | 100% | Correct
2 | WCS A Process Safety | 203 | VTS | Compressors | Replacement | 0 | 0 | 1045505.76 | 0 | 0 | 23.66% | 48.65% | 0% | 27.69% | 0% | 100% | Correct
3 | Brooklyn Compressor Station | 204 | VTS | Compressors | Replacement | 0 | 0 | 2297362.2833 | 2297362.2833 | 2297362.2833 | 25.12% | 46.38% | 0% | 28.49% | 0% | 100% | Correct
4 | Compressor Station Vent Stack Upgrade (BCS, WCS, GCS, SCS) | 205 | VTS | Compressors | Replacement | 0 | 330397.72 | 330397.72 | 330397.72 | 0 | 23.66% | 29.62% | 0% | 26.54% | 20.18% | 100% | Correct
5 | Longford Odorant Pump Power Gas Upgrade | 206 | VTS | Odourant Plants | Replacement | 75569.2 | 0 | 0 | 0 | 0 | 28.57% | 32.83% | 0% | 33.54% | 5.06% | 100% | Correct
6 | GCS compressor unit vent valves & actuators replacement | 207a | VTS | Compressors | Replacement | 139391.86 | 0 | 0 | 0 | 0 | 23.66% | 47.61% | 0% | 28.73% | 0% | 100% | Correct
7 | GCS unit discharge and station manifold check valves replacement | 207b | VTS | Compressors | Replacement | 0 | 0 | 901953.34 | 0 | 0 | 24.64% | 56.58% | 0% | 18.78% | 0% | 100% | Correct
8 | GCS Decomm & removal of turbine oil reservoir & auto fill system | 207c | VTS | Compressors | Replacement | 0 | 87971.74 | 0 | 0 | 0 | 23.66% | 0.74% | 0% | 75.6% | 0% | 100% | Correct
9 | BCS Instrument Air reliability upgrade | 208 | VTS | Compressors | Replacement | 93782.9 | 0 | 0 | 0 | 0 | 23.66% | 27.93% | 0% | 48.4% | 0% | 100% | Correct
10 | Compressor lagging and pipe coating replacement (expand to GCS, Springhurst/BCS12/WCS A/WCS B, Euroa) | 209 | VTS | Compressors | Replacement | 144918.75 | 144918.75 | 144918.75 | 144918.75 | 144918.75 | 23.66% | 0% | 0% | 76.34% | 0% | 100% | Correct
11 | Storage shed-Dandenong, Wollert & Springhurst | 210 | Victoria | Buildings | Non-System | 0 | 648767 | 648767 | 648767 | 0 | 28.57% | 0% | 0% | 71.43% | 0% | 100% | Correct
12 | Iona CS aftercooler augmentation | 211 | VTS | Compressors | Replacement | 1656341.4 | 0 | 0 | 0 | 0 | 28.57% | 34.02% | 0% | 37.41% | 0% | 100% | Correct
13 | Battery replacement | 212 | VTS | Other | Replacement | 70284.2 | 70284.2 | 70284.2 | 70284.2 | 70284.2 | 32.67% | 48.02% | 0% | 14.76% | 4.553% | 100% | Correct
14 | Wollert CG Instrument Air Conversion | 216 | VTS | City Gates & Field Regs | Replacement | 0 | 0 | 0 | 504246.51 | 0 | 23.66% | 19.8% | 0% | 56.54% | 0% | 100% | Correct
15 | Pit installation on LV03 bypass valves on T33 | 220 | VTS | Pipelines | Replacement | 0 | 0 | 230860 | 0 | 0 | 28.57% | 13.37% | 0% | 58.06% | 0% | 100% | Correct
16 | Dandenong water supply & fire main modification | 223 | Victoria | Buildings | Non-System | 324178.4 | 0 | 0 | 0 | 0 | 28.57% | 0% | 0% | 71.43% | 0% | 100% | Correct
17 | Culcairn Injection Gas Quality equipment | 224 | VTS | Gas Quality | Replacement | 973960.4 | 0 | 0 | 0 | 0 | 28.57% | 66.77% | 0% | 4.661% | 0% | 100% | Correct
18 | Positioner Replacement | 225 | VTS | Other | Replacement | 101494.96 | 101494.96 | 101494.96 | 101494.96 | 101494.96 | 35.1% | 31.94% | 0% | 22.08% | 10.88% | 100% | Correct
19 | VTS Safety Management Study aerial photography | 227 | VTS | Other | Replacement | 162466.1262 | 2780.5938 | 0 | 0 | 0 | 21.88% | 0% | 0% | 0% | 78.12% | 100% | Correct
20 | BCP Safety Measures for High Consequence areas-(urban growth, fracture control) | 230a | VTS | Pipelines | Replacement |  |  | 0 | 0 | 0 | 21.88% | 29.7% | 0% | 48.42% | 0% | 100% | Error
21 | BLP Safety Measures for High Consequence areas-(urban growth, fracture control) | 230b | VTS | Pipelines | Replacement |  |  | 0 | 0 | 0 | 21.88% | 29.86% | 0% | 48.26% | 0% | 100% | Error
22 | WOP Safety Measures for High Consequence areas-(urban growth, fracture control) | 230c | VTS | Pipelines | Replacement |  |  | 0 | 0 | 0 | 21.88% | 30.02% | 0% | 48.11% | 0% | 100% | Error
23 | ILP Safety Measures for High Consequence areas-(urban growth, fracture control) | 230e | VTS | Pipelines | Replacement |  |  | 0 | 0 | 0 | 21.88% | 16.84% | 0% | 61.29% | 0% | 100% | Error
24 | Turbine Overhauls | 235 | VTS | Compressors | Replacement | 0 | 0 | 0 |  |  | 23.66% | 0% | 0% | 76.34% | 0% | 100% | Error
25 | Iona CS Automation replacement | 236 | VTS | Compressors | Replacement | 0 | 0 | 1173411.54 | 0 | 0 | 36.55% | 45.54% | 0% | 17.91% | 0% | 100% | Correct
26 | GCS Control Room and Unit Enclosure 1,2,3&4 Fire Suppression System | 237a | VTS | Compressors | Replacement | 268558.9473 | 0 | 0 | 0 | 0 | 23.66% | 0% | 0% | 76.34% | 0% | 100% | Correct
27 | BCS MCC Room Fire Suppression System | 237b | VTS | Compressors | Replacement | 0 | 0 | 268558.9473 | 0 | 0 | 23.66% | 0% | 0% | 76.34% | 0% | 100% | Correct
28 | Iona CS Control Room and Unit Enclosure Fire Suppression System | 237d | VTS | Compressors | Replacement | 0 | 0 | 0 | 268558.9473 | 0 | 23.66% | 0% | 0% | 76.34% | 0% | 100% | Correct
29 | Lara City Gate Control Hut Fire Suppression System | 237e | VTS | City Gates & Field Regs | Replacement | 0 | 0 | 0 | 0 | 82002.732 | 28.57% | 0% | 0% | 71.43% | 0% | 100% | Correct
30 | BCS Control Room Fire Suppression System | 237f | VTS | Compressors | Non-System | 0 | 0 | 0 | 0 | 82002.732 | 28.57% | 0% | 0% | 71.43% | 0% | 100% | Correct
31 | Emergency- BA escape sets | 239a | Victoria | Other | Replacement | 19083.52 | 0 | 0 | 0 | 0 | 21.88% | 78.12% | 0% | 0% | 0% | 100% | Correct
32 | Emergency- Response Equipment | 239b | Victoria | Other | Replacement | 278309.12 | 278309.12 | 278309.12 | 278309.12 | 278309.12 | 21.88% | 77.87% | 0% | 0.258% | 0% | 100% | Correct
33 | Emergency- Spark Proof tools | 239c | Victoria | Other | Replacement | 1945.6 | 1945.6 | 1945.6 | 1945.6 | 1945.6 | 58.88% | 41.12% | 0% | 0% | 0% | 100% | Correct
34 | Emergency - fully equipped caravan | 239d | Victoria | Other | Replacement | 0 | 0 | 107878.4 | 0 | 0 | 21.88% | 73.58% | 0% | 4.542% | 0% | 100% | Correct
35 | Emergency diesel fuel storage | 239e | Victoria | Other | Replacement | 0 | 0 | 0 | 123107.84 | 0 | 21.88% | 41.12% | 0% | 37% | 0% | 100% | Correct
36 | Vent stack for CL600 & 900 pipeline | 240 | VTS | Pipelines | Replacement | 210339.84 | 0 | 0 | 0 | 0 | 21.88% | 78.12% | 0% | 0% | 0% | 100% | Correct
37 | Remote CP/critical drainage bond monitoring | 241 | VTS | Other | Replacement | 573053.7778 | 60456.5556 | 60456.5556 | 60456.5556 | 60456.5556 | 33.41% | 64.43% | 0% | 0% | 2.163% | 100% | Correct
38 | BCG Un-regulated Bypass Upgrade | 242 | VTS | City Gates & Field Regs | Replacement | 0 | 0 | 342346.24 | 0 | 0 | 23.42% | 9.593% | 0% | 66.99% | 0% | 100% | Correct
39 | Security - Physical | 243 | Victoria | Buildings | Non-System | 365236.384 | 365236.384 | 365236.384 | 365236.384 | 365236.384 | 37.33% | 0% | 0% | 62.67% | 0% | 100% | Correct
40 | CP - Cathodic Protection Replacement | 244 | VTS | Other | Replacement | 232464.384 | 232464.384 | 232464.384 | 232464.384 | 232464.384 | 36.12% | 52.09% | 1.084% | 4.938% | 5.766% | 100% | Correct
41 | Equipment - Gas Detectors | 245 | Victoria | Other | Non-System | 0 | 0 | 25000 | 25000 | 0 | 0% | 100% | 0% | 0% | 0% | 100% | Correct
42 | Regulator Upgrade - Lara pneumatic control system upgrade | 247 | VTS | City Gates & Field Regs | Replacement | 0 | 619257.8 | 0 | 0 | 0 | 32.45% | 53.39% | 0% | 14.16% | 0% | 100% | Correct
43 | Hazardous Area Rectification | 249 | VTS | Other | Replacement | 178000 | 178000 | 178000 | 178000 | 178000 | 11.24% | 38.2% | 0% | 50.56% | 0% | 100% | Correct
44 | Actuate MLV's in T1 areas | 250 | VTS | Pipelines | Replacement | 956710.4 | 956710.4 | 0 | 0 | 0 | 21.88% | 62.21% | 0% | 10.89% | 5.017% | 100% | Correct
45 | Asbestos removal and replacement | 251 | VTS | Other | Non-System | 70000 | 70000 | 70000 | 70000 | 70000 | 28.57% | 0% | 0% | 71.43% | 0% | 100% | Correct
46 | T33 non-piggable and encased sections (unknown technical solution) | 257 | VTS | Other | Replacement | 151759.04 | 151759.04 | 151759.04 | 151759.04 | 0 | 25.63% | 5.189% | 0% | 69.18% | 0% | 100% | Correct
47 | Pigging Program T57 Ballan - Ballarat | 258a | VTS | Other | Replacement | 564768 | 0 | 0 | 0 | 0 | 22.3% | 3.564% | 0% | 74.14% | 0% | 100% | Correct
48 | Pigging Program T62 Derrimut - Sunbury | 258b | VTS | Other | Replacement | 425799.68 | 0 | 0 | 0 | 0 | 22.44% | 2.461% | 0% | 75.1% | 0% | 100% | Correct
49 | Pigging Program T61 Packenham - Wollert | 258c | VTS | Other | Replacement | 0 | 649896.96 | 0 | 0 | 0 | 22.24% | 7.276% | 0% | 70.48% | 0% | 100% | Correct
50 | Pigging Program T16 Dandenong – West Melbourne | 258d | VTS | Other | Replacement | 0 | 0 | 0 | 1377768.96 | 0 | 22.05% | 3.432% | 0% | 74.52% | 0% | 100% | Correct
51 | Pigging Program T60 Longford -Dandenong | 258e | VTS | Other | Replacement | 0 | 0 | 0 | 0 | 2380922.88 | 21.98% | 1.986% | 0% | 76.04% | 0% | 100% | Correct
52 | Pigging Program T33 South Melbourne – Brooklyn | 258f | VTS | Other | Replacement | 0 | 0 | 0 | 1023660.8 | 0 | 22.11% | 4.619% | 0% | 73.27% | 0% | 100% | Correct
53 | Pigging Program T65 Dandenong to Princes Highway Pipeline (129) | 258g | VTS | Other | Replacement | 573095.68 | 0 | 0 | 0 | 0 | 22.29% | 8.251% | 0% | 69.46% | 0% | 100% | Correct
54 | Pigging Program T66-70 Mt Franklin -Kyneton - Bendigo | 258i | VTS | Other | Replacement | 0 | 587336.96 | 0 | 0 | 0 | 22.28% | 3.427% | 0% | 74.29% | 0% | 100% | Correct
55 | Pigging Program T75 Wandong - Kyneton | 258k | VTS | Other | Replacement | 0 | 521020.16 | 0 | 0 | 0 | 22.34% | 3.863% | 0% | 73.8% | 0% | 100% | Correct
56 | Pigging Program T24 Brooklyn - Corio | 258l | VTS | Other | Replacement | 0 | 0 | 0 | 1380663.04 | 0 | 22.05% | 1.6% | 0% | 76.35% | 0% | 100% | Correct
57 | Pigging Program T70 Ballan – Bendigo | 258m | VTS | Other | Replacement | 0 | 0 | 555975.68 | 0 | 0 | 22.31% | 1.885% | 0% | 75.81% | 0% | 100% | Correct
58 | Pigging Program T60 Longford – Tyers | 258n | VTS | Other | Replacement | 0 | 0 | 0 | 0 | 748398.08 | 22.2% | 6.318% | 0% | 71.49% | 0% | 100% | Correct
59 | Pigging Program T63 Tyers - Morwell | 258o | VTS | Other | Replacement | 0 | 0 | 0 | 611088.64 | 0 | 22.27% | 5.161% | 0% | 72.57% | 0% | 100% | Correct
60 | Pigging Program T96 & T98 Chiltern- Rutherglen – Koonoomoo | 258p | VTS | Other | Replacement | 0 | 0 | 0 | 0 | 510551.04 | 22.35% | 2.669% | 0% | 74.99% | 0% | 100% | Correct
61 | Pigging Program T118 Trugannina-Plumpton | 258q | VTS | Other | Replacement | 0 | 0 | 0 | 0 | 512325.12 | 22.34% | 6.156% | 0% | 71.5% | 0% | 100% | Correct
62 | Pigging Program James Street to Laverton Pipeline (253) | 258s | VTS | Other | Replacement | 0 | 447777.28 | 0 | 0 | 0 | 22.41% | 4.933% | 0% | 72.66% | 0% | 100% | Correct
63 | Pigging Program Tyres to Maryvale (67) | 258u | VTS | Other | Replacement | 383189.76 | 0 | 0 | 0 | 0 | 22.5% | 2.735% | 0% | 74.76% | 0% | 100% | Correct
64 | Pigging Program T108 Newport | 258v | VTS | Other | Replacement | 473861.12 | 0 | 0 | 0 | 0 | 22.38% | 5.988% | 0% | 71.63% | 0% | 100% | Correct
65 | Pigging Program Inner Ring Main | 258w | VTS | Other | Replacement | 0 | 0 | 3513.6 | 0 | 0 | 22.33% | 5.379% | 0% | 72.29% | 0% | 100% | Correct
66 | Pigging Program T1 Morwell - Dandenong Repair Program | 258x | VTS | Other | Replacement | 925523.32 | 174115.72 | 0 | 0 | 0 | 21.88% | 2.305% | 0% | 75.82% | 0% | 100% | Correct
67 | Pig Trap Installation James Street to Laverton Pipeline (253) | 259a | VTS | Pipelines | Replacement | 0 |  |  | 0 | 0 | 13.54% | 29.08% | 0% | 57.38% | 0% | 100% | Error
68 | Pig Trap Installation Tyers to Maryvale Pipeline (67) | 259d | VTS | Pipelines | Replacement |  |  | 0 | 0 | 0 | 13.55% | 27.44% | 0% | 59.01% | 0% | 100% | Error
69 | Pig Trap Installation Trugannina to Plumpton | 259g | VTS | Pipelines | Replacement | 0 | 0 | 0 |  |  | 14.29% | 31.93% | 0% | 53.79% | 0% | 100% | Error
70 | Liquid Management - Brooklyn | 260a | VTS | City Gates & Field Regs | Replacement | 0 | 0 | 0 | 0 | 157005.8 | 29.27% | 15.68% | 0% | 55.05% | 0% | 100% | Correct
71 | Liquid Management - Pakenham | 260b | VTS | City Gates & Field Regs | Replacement | 0 | 0 | 0 | 157005.8 | 0 | 29.27% | 15.68% | 0% | 55.05% | 0% | 100% | Correct
72 | RTU replacement | 262 | VTS | Other | Replacement | 141816.64 | 141816.64 | 141816.64 | 141816.64 | 141816.64 | 71.47% | 9.837% | 0% | 16.49% | 2.196% | 100% | Correct
73 | Pipe Support replacement | 263 | VTS | Pipelines | Replacement | 164811.0408 | 164811.0408 | 164811.0408 | 164811.0408 | 164811.0408 | 28.57% | 0% | 0% | 71.43% | 0% | 100% | Correct
74 | HMI upgrade to CLEAR SCADA at BCS, SCS and WCS & CG, Longford | 264 | VTS | Other | Non-System | 60928 | 60928 | 60928 | 60928 | 60928 | 58.51% | 35.45% | 0% | 1.313% | 4.727% | 100% | Correct
75 | BCS Unit 12 Inlet Filter Replacement/Augmentation | 267 | VTS | Compressors | Replacement | 635719.42 | 0 | 0 | 0 | 0 | 23.66% | 36.51% | 0% | 39.83% | 0% | 100% | Correct
76 | Coogee decommissioning, Step Change | 268 | VTS | Other | Replacement |  | 0 | 0 | 0 | 0 | 21.88% | 0.006765% | 0% | 78.12% | 0% | 100% | Error
77 | Compressor Type B Compliance | 271 | VTS | Compressors | Replacement | 216718.54 | 216718.54 | 216718.54 | 216718.54 | 216718.54 | 33.45% | 36.05% | 0% | 30.5% | 0% | 100% | Correct
78 | Dandenong LNG Isolation Valve Upgrade | 275 | VTS | Pipelines | Replacement | 649021.8 | 0 | 0 | 0 | 0 | 29.4% | 29.64% | 0% | 40.97% | 0% | 100% | Correct
79 | Morwell-Dandenong Fatigue Crack Detection from High Loads | 276 | VTS | Pipelines | Replacement | 260832 | 0 | 0 | 0 | 0 | 25.56% | 6.653% | 0% | 67.79% | 0% | 100% | Correct
80 | Unibolt Enclosure Replacement | 277 | VTS | Other | Replacement | 44464 | 44464 | 44464 | 44464 | 44464 | 28.57% | 11.25% | 0% | 60.18% | 0% | 100% | Correct
81 | WAN Upgrade (Satellite project) | 278 | VTS | Other | Non-System | 946991.92 | 946991.92 | 946991.92 | 946991.92 | 946991.92 | 46.57% | 29.89% | 0% | 18.2% | 5.355% | 100% | Correct
82 | Warragul Looping 6" (Southern Route) | Warragul 6" (Sth) | VTS | Pipelines | Augmentation | 0 | 2600000 | 900000 | 0 | 0 | 34.54% | 52.68% | 0% | 12.78% | 0% | 100% | Correct
83 | Anglesea Pipeline Extension | Anglesea | VTS | Pipelines | Augmentation | 16624609.3573 | 0 | 0 | 0 | 0 | 49.2% | 30.91% | 0% | 0% | 19.88% | 100% | Correct
84 | BCS Reconfiguration (2B) | BCS Reconfig (2A) | VTS | Compressors | Augmentation | 1960141.21 | 0 | 0 | 0 | 0 | 54.96% | 45.04% | 0% | 0% | 0% | 100% | Correct
85 | Winchelsea Bi-Directional Flow | Winchelsea Bi-Direction | VTS | Compressors | Augmentation | 1420556.258 | 0 | 0 | 0 | 0 | 33.73% | 32.27% | 0% | 25.19% | 8.808% | 100% | Correct
86 | WORM (50km x 20" Pipeline) | WORM (Pipeline) | VTS | Pipelines | Augmentation | 15911166.8213 | 28997137.4367 | 48814496.7419 | 0 | 0 | 10.58% | 33.69% | 0% | 0% | 55.73% | 100% | Correct
87 | WORM (C50 at Wollert) | WORM (C50) | VTS | Compressors | Augmentation | 7043662.34 | 12092299.2911 | 6176723.3689 | 0 | 0 | 37.05% | 60.4% | 0% | 0% | 2.553% | 100% | Correct
88 | WORM (PRS at Wollert) | WORM (PRS) | VTS | City Gates & Field Regs | Augmentation | 0 | 1641722.0833 | 1959224.9167 | 0 | 0 | 42.22% | 54.63% | 0% | 0% | 3.152% | 100% | Correct
0 | 0 | #REF! |  |  |  | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | 0% | Correct
0 | 0 | #REF! |  |  |  | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | 0% | Correct
0 | 0 | #REF! |  |  |  | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | 0% | Correct
0 | 0 | #REF! |  |  |  | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | 0% | Correct
0 | 0 | #REF! |  |  |  | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | 0% | Correct
0 | 0 | #REF! |  |  |  | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | 0% | Correct
0 | 0 | #REF! |  |  |  | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | 0% | Correct
0 | 0 | #REF! |  |  |  | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | 0% | Correct
0 | 0 | #REF! |  |  |  | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | 0% | Correct
0 | 0 | #REF! |  |  |  | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | 0% | Correct
0 | 0 | #REF! |  |  |  | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | 0% | Correct
0 | 0 | #REF! |  |  |  | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | 0% | Correct
0 | 0 | #REF! |  |  |  | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | 0% | Correct
0 | 0 | #REF! |  |  |  | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | 0% | Correct
0 | 0 | #REF! |  |  |  | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | 0% | Correct
0 | 0 | #REF! |  |  |  | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | 0% | Correct
0 | 0 | #REF! |  |  |  | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | 0% | Correct
0 | 0 | #REF! |  |  |  | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | 0% | Correct
0 | 0 | #REF! |  |  |  | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | 0% | Correct
0 | 0 | #REF! |  |  |  | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | 0% | Correct
0 | 0 | #REF! |  |  |  | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | 0% | Correct
0 | 0 | #REF! |  |  |  | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | 0% | Correct
0 | 0 | #REF! |  |  |  | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | 0% | Correct
0 | 0 | #REF! |  |  |  | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | 0% | Correct
0 | 0 | #REF! |  |  |  | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | 0% | Correct
0 | 0 | #REF! |  |  |  | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | 0% | Correct
0 | 0 | #REF! |  |  |  | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | 0% | Correct
0 | 0 | #REF! |  |  |  | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | 0% | Correct
0 | 0 | #REF! |  |  |  | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | 0% | Correct
0 | 0 | #REF! |  |  |  | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | 0% | Correct
0 | 0 | #REF! |  |  |  | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | 0% | Correct
0 | 0 | #REF! |  |  |  | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | 0% | Correct
0 | 0 | #REF! |  |  |  | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | 0% | Correct
0 | 0 | #REF! |  |  |  | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | 0% | Correct
0 | 0 | #REF! |  |  |  | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | 0% | Correct
0 | 0 | #REF! |  |  |  | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | 0% | Correct
0 | 0 | #REF! |  |  |  | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | 0% | Correct
0 | 0 | #REF! |  |  |  | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | 0% | Correct
0 | 0 | #REF! |  |  |  | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | 0% | Correct
0 | 0 | #REF! |  |  |  | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | 0% | Correct
0 | 0 | #REF! |  |  |  | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | 0% | Correct
0 | 0 | #REF! |  |  |  | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | 0% | Correct
0 | 0 | #REF! |  |  |  | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | 0% | Correct
0 | 0 | #REF! |  |  |  | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | 0% | Correct
0 | 0 | #REF! |  |  |  | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | 0% | Correct
0 | 0 | #REF! |  |  |  | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | 0% | Correct
0 | 0 | #REF! |  |  |  | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | 0% | Correct
0 | 0 | #REF! |  |  |  | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | 0% | Correct
0 | 0 | #REF! |  |  |  | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | 0% | Correct
0 | 0 | #REF! |  |  |  | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | 0% | Correct
0 | 0 | #REF! |  |  |  | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | 0% | Correct
0 | 0 | #REF! |  |  |  | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | 0% | Correct
0 | 0 | #REF! |  |  |  | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | 0% | Correct
0

## 3.1 Input│B&T
3.1 Input│B&T
Capex # | Project Name | Allocator | Asset Class | Asset Category | 2017 (f) | 2018 | 2019 | 2020 | 2021 | 2022 | Direct Labour % | Direct Contractor % | Direct Material % | Direct Other % | 2017 Extension of existing project
89 | Enterprise Content Management | APA | Other | Non-System | 4903000 | 0 | 0 | 0 | 0 | 0 | 30% | 65% | 5% | 0%
90 | Victoria CRE | APA | Other | Non-System | 3506365.2941 | 0 | 0 | 0 | 0 | 0 | 30% | 65% | 5% | 0%
91 | APA Grid Energy Components Upgrade | APA | Other | Non-System | 1297041.8584 | 0 | 0 | 0 | 0 | 0 | 30% | 65% | 5% | 0%
92 | APA Grid Extend Program | APA | Other | Non-System | 2500000 | 2500000 | 0 | 0 | 0 | 0 | 30% | 65% | 5% | 0%
93 | APA Grid Services Initiatives Program | APA | Other | Non-System | 210813.4562 | 0 | 0 | 0 | 0 | 0 | 30% | 65% | 5% | 0%
94 | Hyperion Upgrade to 11.1.2.4 | APA | Other | Non-System | 261068.5766 | 0 | 0 | 0 | 0 | 0 | 30% | 65% | 5% | 0%
95 | BI - Transmission Dashboard and Enterprise Pilot | APA | Other | Non-System | 1200000 | 2000000 | 1500000 | 0 | 0 | 0 | 30% | 65% | 5% | 0%
96 | HR Systems Refresh | APA | Other | Non-System | 0 | 0 | 0 | 0 | 0 | 0 | 30% | 65% | 5% | 0%
97 | Transmission EAM Data Management Tool | APA | Other | Non-System | 465223.3 | 0 | 0 | 0 | 0 | 0 | 30% | 65% | 5% | 0%
98 | SharePoint Upgrade | APA | Other | Non-System | 1739351.9 | 243778.5 | 0 | 0 | 0 | 0 | 30% | 65% | 5% | 0%
99 | eForm Digitisation | APA | Other | Non-System | 0 | 0 | 0 | 1607603.75 | 4147396.25 | 0 | 30% | 65% | 5% | 0%
100 | Historian Upgrade - version 2012 to 2015 | APA | Other | Non-System | 270259 | 0 | 0 | 0 | 0 | 0 | 30% | 65% | 5% | 0%
101 | Hazardous Area Platform | APA | Other | Non-System | 1187405.7 | 1552491.3 | 0 | 0 | 0 | 0 | 30% | 65% | 5% | 0%
102 | PPM Refresh | APA | Other | Non-System | 1100000 | 3000000 | 0 | 0 | 0 | 0 | 30% | 65% | 5% | 0%
103 | BizTalk Upgrade FY2018 | APA | Other | Non-System | 0 | 0 | 604848.9048 | 670918.5097 | 0 | 0 | 30% | 65% | 5% | 0%
104 | Automated Testing Tool | APA | Other | Non-System | 0 | 632204.9999 | 0 | 0 | 0 | 0 | 30% | 65% | 5% | 0%
105 | Code Management Software | APA | Other | Non-System | 0 | 905930.625 | 0 | 0 | 0 | 0 | 30% | 65% | 5% | 0%
106 | CRM Upgrade | APA | Other | Non-System | 0 | 1408186.2 | 59047.8 | 0 | 0 | 0 | 30% | 65% | 5% | 0%
107 | X-Info Aware Version 2 | APA | Other | Non-System | 0 | 430081.5 | 0 | 0 | 0 | 0 | 30% | 65% | 5% | 0%
108 | Supplier Qualification and Compliance | APA | Other | Non-System | 0 | 697848.96 | 185555.04 | 0 | 0 | 0 | 30% | 65% | 5% | 0%
109 | Oracle eBS Upgrade to 12.2 | APA | Other | Non-System | 0 | 267113.0161 | 1276243.5381 | 0 | 0 | 0 | 30% | 65% | 5% | 0%
110 | BizTalk System Upgrade 2020 | APA | Other | Non-System | 0 | 0 | 604848.9048 | 670918.5097 | 0 | 0 | 30% | 65% | 5% | 0%
111 | Applications Renewal | APA | Other | Non-System | 0 | 6900000 | 8620000 | 6900000 | 8620000 | 6900000 | 30% | 65% | 5% | 0%
112 | Infrastructure Renewal | APA | Other | Non-System | 0 | 2250000 | 750000 | 750000 | 750000 | 0 | 30% | 65% | 5% | 0%
113 | Dandenong Relocation | APA | Buildings | Non-System | 5460000 | 0 | 0 | 0 | 0 | 0 | 50% | 0% | 50% | 0%
0 |  | APA | Other | Non-System |  | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 50% | 0%
0 |  | APA | Other | Non-System | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 50% | 0%
0 |  | APA | Other | Non-System | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 50% | 0%
0 |  | APA | Other | Non-System | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 50% | 0%

## 3.2 Input│Other
3.2 Input│Other
Years | Start | Finish | check (years)
Previous AA | 2008-01-01 | 2013-06-30 | 5.5
Current AA | 2013-07-01 | 2017-12-31 | 4.5
Forecast AA | 2018-01-01 | 2022-12-31 | 5
Allocators
VTS | 100%
APA | 10.45%
Transmission | 11.57%
Victoria | 92.63%
|  |  |  | 2011-06-01 | 2012-06-01 | 2013-06-01 | 2014-06-01 | 2015-06-01 | 2016-06-01
Inflation |  |  |  | 2012 | 2013 | 2014 | 2015 | 2016 (e) | 2017 (f) | 2018 | 2019 | 2020 | 2021 | 2022
CPI |  |  |  | 3.549% | 1.562% | 2.308% | 1.504% | 1.296% | 2% | 2% | 1% | 1% | 1% | 1%
Base Year to Dec 2017 |  |  |  | 0.91766 | 0.932 | 0.95351 | 0.96785 | 0.98039 | 1 | 1.02 | 1.0302 | 1.0405 | 1.0509 | 1.0614
AER Forecast Inflation |  |  |  |  | 2.5% | 2.5% | 2.5% | 2.5% | 2.5% | 2.5% | 2.5% | 2.5% | 2.5% | 2.5%
AER forecast to base year to Dec 2012 |  |  |  | 1 | 0.97561 | 0.95181 | 0.9286 | 0.90595 | 0.88385 | 0.8623 | 0.84127 | 0.82075 | 0.80073 | 0.7812
Nominal from Dec 2012 |  |  |  | 1 | 1.0156 | 1.0391 | 1.0547 | 1.0684 | 1.0897 | 1.1115 | 1.1226 | 1.1339 | 1.1452 | 1.1567
Inverse of Nominal From 2012 |  |  |  | 1 | 0.98462 | 0.96241 | 0.94815 | 0.93601 | 0.91766 | 0.89967 | 0.89076 | 0.88194 | 0.87321 | 0.86456
Real cost Escalation
Increase
Labour | bar: 2012 to 2022
Contractor | bar: 2012 to 2022
Materials | bar: 2012 to 2022
Other | bar: 2012 to 2022
Index
Labour | bar: 2017 (f) to 2022
Contractor | bar: 2017 (f) to 2022
Materials | bar: 2017 (f) to 2022
Other | bar: 2017 (f) to 2022
Asset Classes
Pipelines
Compressors
City Gates & Field Regs
Odourant Plants
Gas Quality
Other
Buildings
General Land
Asset Category
Augmentation
Replacement
Non-System
Formulas:
Start = [Finish, row above]+1
Finish = DATE(YEAR([Start])+5,MONTH([Start]),DAY([Start])-1)

## 3.3 Input│RIN
4.1 - CAPEX
4.1.1 - EXPANSION (by Project)
| EXPENDITURE Actual ($0's) |  |  | EXPENDITURE Forecast ($0's real, December 2017)
| 1 July to 31 December 2013 | 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 | 2022
Wollert to Clonbinane Looping | 4006990.75 | 85648927.66 | 65640112.89 | 643437.5283 | 0 | 0 | 0 | 0 | 0 | 0
VNIE Looping 6 to 8 | 0 | 0 | 6392032.4513 | 92414222.7837 | 43063099.4902 | 0 | 0 | 0 | 0 | 0 |  |  | Check | #REF!
WORM (50km x 20" Pipeline) | 0 | 0 | 0 | 0 | 0 | 16439771.1413 | 29960486.7805 | 50436222.8004 | 0 | 0
Stonehaven CS - now Winchelsea | 8134553.96 | 26606375.39 | 2492547.98 | 888.642 | 0 | 0 | 0 | 0 | 0 | 0
Anglesea Pipeline Extension | 0 | 0 | 0 | 0 | 9267887.2827 | 17176915.8237 | 0 | 0 | 0 | 0
WORM (C50 at Wollert) | 0 | 0 | 0 | 0 | 0 | 7277668.4555 | 12494032.3453 | 6381927.8453 | 0 | 0
Warragul Looping 6" (Southern Route) | 0 | 0 | 0 | 0 | 0 | 0 | 2600000 | 900000 | 0 | 0
WORM (PRS at Wollert) | 0 | 0 | 0 | 0 | 0 | 0 | 1696263.7392 | 2024314.7222 | 0 | 0
BCS Reconfiguration (2B) | 0 | 0 | 0 | 0 | 0 | 2025261.4569 | 0 | 0 | 0 | 0
Winchelsea Bi-Directional Flow | 0 | 0 | 0 | 0 | 0 | 1467750.2937 | 0 | 0 | 0 | 0
VTS - EUROA CS NEW (PPOM) | 116664.37 | 121805.28 | 59020.54 | -2979.3672 | 0 | 0 | 0 | 0 | 0 | 0
VTS - SUNBURY PIPE LOOP (NEW) | 51715.09 | 38571.05 | 5019.95 | 4081.3088 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total | 12309924.17 | 112415679.38 | 74588733.8113 | 93059650.8956 | 52330986.7729 | 44387367.171 | 46750782.865 | 59742465.3678 | 0 | 0
Check | 12309924.17 | 112415679.38 | 74588733.8113 | 93330759.7266 | 52330986.7729 | 44387367.171 | 46837160.6428 | 59772365.3678 | 0 | 0
| 0 | 0 | 0 | -271108.831 | 0 | 0 | -86377.7778 | -29900 | 0 | 0
4.1.2 - REPLACEMENT (by Project)
| EXPENDITURE Actual ($0's) | EXPENDITURE Forecast ($0's real, December 2017) 2016: EXPENDITURE Forecast ($0's real, December 2017)
| 1 July to 31 December 2013 | 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 | 2022 | Total | Proportion
Regulator upgrade - Dandenong City Gate (exclude filters) | 479498.96 | 2616566.96 | 7811136.25 | 760192.0344 | 0 | 0 | 0 | 0 | 0 | 0 | 11667394.2044 | 13.91% | Check | #REF!
BLP Safety Measures for High Consequence areas-(urban growth, fracture control) | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 13.91%
BCS Unit 10 & 11 Cooler Upgrade | 27089.84 | 889622.65 | 5007242.54 | 3314651.9393 | 0 | 0 | 0 | 0 | 0 | 0 | 9238606.9693 | 24.92%
WOP Safety Measures for High Consequence areas-(urban growth, fracture control) | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 24.92%
Brooklyn Compressor Station | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2373685.7636 | 2373685.7636 | 2373685.7636 | 7121057.2909 | 33.4%
BCP Safety Measures for High Consequence areas-(urban growth, fracture control) | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 33.4%
Turbine Overhauls | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 33.4%
Pig Trap Installation Trugannina to Plumpton | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 33.4%
Pigging Program (T1 Dandenong - Morwell) | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 33.4%
Pigging Program T60 Longford -Dandenong | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2460022.429 | 2460022.429 | 36.34%
Pig Trap Installation James Street to Laverton Pipeline (253) | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 36.34%
Actuate MLV's in T1 areas | 0 | 0 | 0 | 0 | 0 | 988494.4455 | 988494.4455 | 0 | 0 | 0 | 1976988.891 | 38.69%
Pig Trap - Keon Park Install | 325106.72 | 1640823.98 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1965930.7 | 41.04%
Pig Trap - Dandenong to Princes Highway Pipeline Install (129) | 0 | 0 | 31113.5 | 355269.8955 |  | 0 | 0 | 0 | 0 | 0 | 386383.3955 | 41.5%
Coogee decommissioning, Step Change | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 41.5%
BCS Station Isolation and Loading Valves | 2244.6 | 16577.75 | 183683.64 | 1631331.8054 | 0 | 0 | 0 | 0 | 0 | 0 | 1833837.7954 | 43.68%
Iona CS aftercooler augmentation | 0 | 0 | 0 | 0 | 0 | 1711368.7421 | 0 | 0 | 0 | 0 | 1711368.7421 | 45.72%
Pig Trap - Somerton to Somerton Pipeline Install (238) | 0 | 1590 | 24041.28 | 3764.2919 |  | 0 | 0 | 0 | 0 | 0 | 29395.5719 | 45.76%
CP - Cathodic Protection Replacement | 18725 | 98704 | 20000 | 90964.0741 | 50000 | 240187.3674 | 240187.3674 | 240187.3674 | 240187.3674 | 240187.3674 | 1479329.9112 | 47.52%
Pigging Program T24 Brooklyn - Corio | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1426531.7343 | 0 | 1426531.7343 | 49.22%
Pigging Program T16 Dandenong – West Melbourne | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1423541.5066 | 0 | 1423541.5066 | 50.92%
Hazardous Area Rectification | 10313.6 | 32182.3 | 134741.2 | 165095.9047 | 100000 | 183913.5556 | 183913.5556 | 183913.5556 | 183913.5556 | 183913.5556 | 1361900.7824 | 52.54%
Emergency- Response Equipment | 0 | 0 | 0 | 0 | 0 | 266373.6154 | 266373.6154 | 266373.6154 | 266373.6154 | 266373.6154 | 1331868.0768 | 54.13%
Iona CS Automation replacement | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1212394.8789 | 0 | 0 | 1212394.8789 | 55.57%
Pigging Program T1 Morwell - Dandenong Repair Program | 0 | 0 | 0 | 0 | 0 | 956271.2614 | 179900.2311 | 0 | 0 | 0 | 1136171.4926 | 56.93%
Compressor Type B Compliance | 0 | 0 | 0 | 0 | 0 | 223918.4115 | 223918.4115 | 223918.4115 | 223918.4115 | 223918.4115 | 1119592.0575 | 58.26%
WCS A Process Safety | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1080239.7847 | 0 | 0 | 1080239.7847 | 59.55%
Pigging Program T33 South Melbourne – Brooklyn | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1057669.0866 | 0 | 1057669.0866 | 60.81%
Compressor Station Vent Stack Upgrade (BCS, WCS, GCS, SCS) | 0 | 0 | 0 | 0 | 0 | 0 | 341374.2665 | 341374.2665 | 341374.2665 | 0 | 1024122.7994 | 62.03%
Culcairn Injection Gas Quality equipment | 0 | 0 | 0 | 0 | 0 | 1006317.5288 | 0 | 0 | 0 | 0 | 1006317.5288 | 63.23%
GCS unit discharge and station manifold check valves replacement | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 931918.2343 | 0 | 0 | 931918.2343 | 64.34%
Pig Trap - A Branch Valve on Pipeline 108 to Newport Install(124) | 0 | 0 | 20098.4 | 880081.4888 | 0 | 0 | 0 | 0 | 0 | 0 | 900179.8888 | 65.41%
GCS Anti-Surge & Fast-Stop Valves Upgrade | 0 | 0 | 10038.5 | 503749.0544 | 365000 | 0 | 0 | 0 | 0 | 0 | 878787.5544 | 66.46%
Pipe Support replacement | 0 | 0 | 0 | 0 | 0 | 170286.4298 | 170286.4298 | 170286.4298 | 170286.4298 | 170286.4298 | 851432.1491 | 67.47%
Remote CP/critical drainage bond monitoring | 0 | 0 | 0 | 0 | 0 | 592091.8977 | 62465.0567 | 62465.0567 | 62465.0567 | 62465.0567 | 841952.1244 | 68.48%
Regulator Upgrade - Lara pneumatic control system upgrade | 0 | 0 | 5301 | 0 | 160000 | 0 | 639830.9202 | 0 | 0 | 0 | 805131.9202 | 69.44%
Pigging Program T60 Longford – Tyers | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 773261.5273 | 773261.5273 | 70.36%
Compressor lagging and pipe coating replacement (expand to GCS, Springhurst/BCS12/WCS A/WCS B, Euroa) | 0 | 0 | 0 | 0 | 0 | 149733.2729 | 149733.2729 | 149733.2729 | 149733.2729 | 149733.2729 | 748666.3646 | 71.25%
RTU replacement | 0 | 0 | 0 | 0 | 0 | 146528.1039 | 146528.1039 | 146528.1039 | 146528.1039 | 146528.1039 | 732640.5196 | 72.12%
Pigging Program (T74 Keon Park - Wollert) | 5363.81 | 616839.03 | 37257.13 | 41971.2796 | 0 | 0 | 0 | 0 | 0 | 0 | 701431.2496 | 72.96%
Pig Trap Installation Tyers to Maryvale Pipeline (67) | 0 | 0 | 0 | 0 | 0 | 609471.455 | 81107.2821 | 0 | 0 | 0 | 690578.7371 | 73.78%
Pigging Program T61 Packenham - Wollert | 0 | 0 | 0 | 0 | 0 | 0 | 671487.9812 | 0 | 0 | 0 | 671487.9812 | 74.58%
Dandenong LNG Isolation Valve Upgrade | 0 | 0 | 0 | 0 | 0 | 670583.7465 | 0 | 0 | 0 | 0 | 670583.7465 | 75.38%
BCS Unit 12 Inlet Filter Replacement/Augmentation | 0 | 0 | 0 | 0 | 0 | 656839.4318 | 0 | 0 | 0 | 0 | 656839.4318 | 76.17%
Pigging Program (T92 Iona - Brooklyn) | 0 | 0 | 67224.28 | 493158.324 | 100000 | 0 | 0 | 0 | 0 | 0 | 660382.604 | 76.95%
Pigging Program T63 Tyers - Morwell | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 631390.3626 | 0 | 631390.3626 | 77.71%
T33 non-piggable and encased sections (unknown technical solution) | 0 | 0 | 0 | 0 | 0 | 156800.8126 | 156800.8126 | 156800.8126 | 156800.8126 | 0 | 627203.2502 | 78.45%
Pigging Program T66-70 Mt Franklin -Kyneton - Bendigo | 0 | 0 | 0 | 0 | 0 | 0 | 606849.599 | 0 | 0 | 0 | 606849.599 | 79.18%
Pigging Program T65 Dandenong to Princes Highway Pipeline (129) | 0 | 0 | 0 | 0 | 0 | 592135.192 | 0 | 0 | 0 | 0 | 592135.192 | 79.88%
All CS buffer Air shutoff system for all compressors | 0 | 0 | 0 | 0 | 0 | 394412.4424 | 197206.2212 | 0 | 0 | 0 | 591618.6636 | 80.59%
Pigging Program T57 Ballan - Ballarat | 0 | 0 | 0 | 0 | 0 | 583530.848 | 0 | 0 | 0 | 0 | 583530.848 | 81.28%
Pigging Program T70 Ballan – Bendigo | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 574446.4276 | 0 | 0 | 574446.4276 | 81.97%
Pigging Program T75 Wandong - Kyneton | 0 | 0 | 0 | 0 | 0 | 0 | 538329.6075 | 0 | 0 | 0 | 538329.6075 | 82.61%
Pigging Program T118 Trugannina-Plumpton | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 529345.699 | 529345.699 | 83.24%
Pigging Program T96 & T98 Chiltern- Rutherglen – Koonoomoo | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 527512.6801 | 527512.6801 | 83.87%
Positioner Replacement | 0 | 0 | 0 | 0 | 0 | 104866.8481 | 104866.8481 | 104866.8481 | 104866.8481 | 104866.8481 | 524334.2406 | 84.49%
Wollert CG Instrument Air Conversion | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 520998.6996 | 0 | 520998.6996 | 85.11%
Pigging Program T108 Newport | 0 | 0 | 0 | 0 | 0 | 489603.8394 | 0 | 0 | 0 | 0 | 489603.8394 | 85.7%
RTU & Control System Upgrade - Facilities | 98368.47 | 100004.42 | 8235.2 | 133343.4359 | 150000 | 0 | 0 | 0 | 0 | 0 | 489951.5259 | 86.28%
Pigging Program James Street to Laverton Pipeline (253) | 0 | 0 | 0 | 0 | 0 | 0 | 462653.4363 | 0 | 0 | 0 | 462653.4363 | 86.83%
Pigging Program (T56 Brooklyn - Ballan) | 0 | 0 | 140780.29 | 311227.8258 | 0 | 0 | 0 | 0 | 0 | 0 | 452008.1158 | 87.37%
Pigging Program T62 Derrimut - Sunbury | 0 | 0 | 0 | 0 | 0 | 439945.6916 | 0 | 0 | 0 | 0 | 439945.6916 | 87.9%
Zonal Chromatograph Upgrades | 0 | 91009.78 | 0 | 339274.7241 | 0 | 0 | 0 | 0 | 0 | 0 | 430284.5041 | 88.41%
Pigging Program Tyres to Maryvale (67) | 0 | 0 | 0 | 0 | 0 | 395920.1754 | 0 | 0 | 0 | 0 | 395920.1754 | 88.88%
Valve - Pipeline LNG plant Isolation Valve Actuator Replacement | 67874.3 | 307062.84 | 0 | -0.020259 | 0 | 0 | 0 | 0 | 0 | 0 | 374937.1197 | 89.33%
Pig Trap - Pipe Support Upgrade | 174 | 63266.31 | 250206.75 | 25217.8953 | 25000 | 0 | 0 | 0 | 0 | 0 | 363864.9553 | 89.76%
Battery replacement | 0 | 0 | 0 | 0 | 0 | 72619.1973 | 72619.1973 | 72619.1973 | 72619.1973 | 72619.1973 | 363095.9866 | 90.19%
BCG Un-regulated Bypass Upgrade | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 353719.7429 | 0 | 0 | 353719.7429 | 90.62%
BCS DEA Upgrade | 1160 | 17428 | 0 | 321085.9611 | 0 | 0 | 0 | 0 | 0 | 0 | 339673.9611 | 91.02%
CS Type B compliance upgrade | 0 | 0 | 1070 | 233463.0745 | 100000 | 0 | 0 | 0 | 0 | 0 | 334533.0745 | 91.42%
AS 2885 Design Life reviews of Facilities&Pipelines | 890.75 | 142234.07 | 54126.05 | 64803.2116 | 50000 | 0 | 0 | 0 | 0 | 0 | 312054.0816 | 91.79%
GCS Units 1,2,3&4 Suction/Discharge Actuated Valve Replacement | 0 | 0 | 0 | 220.8259 | 300000 | 0 | 0 | 0 | 0 | 0 | 300220.8259 | 92.15%
Wollert CS A Unit reinstrumentation | 0 | 0 | 0 | 101296.2963 | 200000 | 0 | 0 | 0 | 0 | 0 | 301296.2963 | 92.51%
Odorant Dandenong Pump Upgrade 700 & 2800 kPa | 0 | 0 | 285847.41 | 6093.4787 | 0 | 0 | 0 | 0 | 0 | 0 | 291940.8887 | 92.86%
Valve - UniBolt Phase 3 Replacement | 1130.5 | 92576.04 | 30257.33 | 54530.744 | 100000 | 0 | 0 | 0 | 0 | 0 | 278494.614 | 93.19%
GCS Control Room and Unit Enclosure 1,2,3&4 Fire Suppression System | 0 | 0 | 0 | 0 | 0 | 277481.0723 | 0 | 0 | 0 | 0 | 277481.0723 | 93.52%
GCS Control Room and Unit Enclosure 1,2,3&4 Fire Suppression System | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 277481.0723 | 0 | 0 | 277481.0723 | 93.85%
BCS MCC Room Fire Suppression System | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 277481.0723 | 0 | 277481.0723 | 94.18%
Iona CS Control Room and Unit Enclosure Fire Suppression System | 67319.22 | 210131.45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 277450.67 | 94.51%
Morwell-Dandenong Fatigue Crack Detection from High Loads | 0 | 0 | 0 | 0 | 0 | 269497.4187 | 0 | 0 | 0 | 0 | 269497.4187 | 94.83%
Pit installation on LV03 bypass valves on T33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 238529.6822 | 0 | 0 | 238529.6822 | 95.12%
Purchase and replacement of emergency fittings and Equipment | 59521.63 | 173679.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 233201.53 | 95.4%
Unibolt Enclosure Replacement | 0 | 0 | 0 | 0 | 0 | 45941.1929 | 45941.1929 | 45941.1929 | 45941.1929 | 45941.1929 | 229705.9644 | 95.67%
Vent stack for CL600 & 900 pipeline | 0 | 0 | 0 | 0 | 0 | 217327.7969 | 0 | 0 | 0 | 0 | 217327.7969 | 95.93%
Security - High Risk sites security upgrade | 17837.72 | 24900 | 0 | 0 | 150000 | 0 | 0 | 0 | 0 | 0 | 192737.72 | 96.16%
VTS.SIB99 WCS STN-A DISCHRG LQ | 0 | 0 | 0 | 193324.3867 | 0 | 0 | 0 | 0 | 0 | 0 | 193324.3867 | 96.39%
VTS Safety Management Study aerial photography | 0 | 0 | 0 | 0 | 0 | 167863.6119 | 2872.9714 | 0 | 0 | 0 | 170736.5833 | 96.59%
Liquid Management - Brooklyn | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 162221.8816 | 162221.8816 | 96.78%
Liquid Management - Pakenham | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 162221.8816 | 0 | 162221.8816 | 96.98%
SMS - GIS & Aerial Photography | 0 | 0 | 87 | 146848.7343 | 0 | 0 | 0 | 0 | 0 | 0 | 146935.7343 | 97.15%
GCS compressor unit vent valves & actuators replacement | 0 | 0 | 0 | 0 | 0 | 144022.7673 | 0 | 0 | 0 | 0 | 144022.7673 | 97.32%
Pig Trap - Enclosure upgrade | 0 | 0 | 17709 | 85653.7474 | 25000 | 0 | 0 | 0 | 0 | 0 | 128362.7474 | 97.48%
Wollert CS A/B Control Room Fire Suppression System | 0 | 0 | 0 | 121555.5556 | 0 | 0 | 0 | 0 | 0 | 0 | 121555.5556 | 97.62%
Emergency diesel fuel storage | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 117828.2638 | 0 | 117828.2638 | 97.76%
Iona CS - Inlet Pressure Reduction | 104428.1 | 9056 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 113484.1 | 97.9%
Wollert CS Emergency Lighting | 0 | 111330.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 111330.8 | 98.03%
VTS - BCS LUBE OIL COOLER 8&9 | 109672.54 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 109672.54 | 98.16%
Emergency - fully equipped caravan | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 103251.9503 | 0 | 0 | 103251.9503 | 98.28%
Valve - Actuate MLV's in T1 areas | 0 | 0 | 0 | 10670.5519 | 90000 | 0 | 0 | 0 | 0 | 0 | 100670.5519 | 98.4%
BCS Instrument Air reliability upgrade | 0 | 0 | 0 | 0 | 0 | 96898.5763 | 0 | 0 | 0 | 0 | 96898.5763 | 98.52%
GCS Station Valve Upgrade | 922.2 | 94508.09 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 95430.29 | 98.63%
GCS Decomm & removal of turbine oil reservoir & auto fill system | 0 | 0 | 0 | 0 | 0 | 0 | 90894.3567 | 0 | 0 | 0 | 90894.3567 | 98.74%
Lara City Gate Control Hut Fire Suppression System | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 84727.045 | 84727.045 | 98.84%
Emergency Response Equipment | 0 | 14416.72 | 38911 | 30716.6837 | 0 | 0 | 0 | 0 | 0 | 0 | 84044.4037 | 98.94%
Wollert CG Control Hut Fire Suppression System | 0 | 0 | 0 | 81037.037 | 0 | 0 | 0 | 0 | 0 | 0 | 81037.037 | 99.04%
Longford Odorant Pump Power Gas Upgrade | 0 | 0 | 0 | 0 | 0 | 78079.7768 | 0 | 0 | 0 | 0 | 78079.7768 | 99.13%
Valve - Longford to Dandenong LV10 Vent Stack | 34177.3 | 39851.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 74029.05 | 99.22%
Emergency Plidco fittings - Sleeve vent | 0 | 0 | 0 | 0 | 70000 | 0 | 0 | 0 | 0 | 0 | 70000 | 99.3%
BCS Emergency Lighting | 61810.95 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 61810.95 | 99.38%
GCS GEA Fuel Gas Upgrade | 0 | 0 | 0 | 62205.8327 | 0 | 0 | 0 | 0 | 0 | 0 | 62205.8327 | 99.45%
Zonal Chromatograph Insertion Probes | 0 | 0 | 0 | 10129.6296 | 50000 | 0 | 0 | 0 | 0 | 0 | 60129.6296 | 99.52%
ILP Safety Measures for High Consequence areas-(urban growth, fracture control) | 0 | 0 | 0 | 0 | 0 | 27897.6475 | 28989.419 | 0 | 0 | 0 | 56887.0665 | 99.59%
BCS Safety and Process Control System and RTU Upgrade | 23570.02 | 15134.58 | 12066 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50770.6 | 99.65%
CP - Corrosion Protection Testing Equipment | 0 | 0 | 0 | 48308.2037 | 0 | 0 | 0 | 0 | 0 | 0 | 48308.2037 | 99.71%
Emergency - refurbish and re-testing of pipes | 0 | 40300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40300 | 99.76%
Hazardous Areas Review | 34062.33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 34062.33 | 99.8%
VTS16.SIB42 WOLL SOFT STARTERS | 0 | 0 | 0 | 31281.3093 | 0 | 0 | 0 | 0 | 0 | 0 | 31281.3093 | 99.84%
Pig Trap - Princes Highway to Regent Street Pipeline Install(36) | 0 | 0 | 17158.9 | 7982.3507 | 0 | 0 | 0 | 0 | 0 | 0 | 25141.2507 | 99.87%
Emergency Spark Proof tools | 0 | 0 | 0 | 0 | 20000 | 0 | 0 | 0 | 0 | 0 | 20000 | 99.89%
Emergency- BA escape sets | 0 | 0 | 0 | 0 | 0 | 18265.1083 | 0 | 0 | 0 | 0 | 18265.1083 | 99.91%
PIGGING T91 CURDIEVALE | 0 | 17873 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17873 | 99.93%
Facilities Communication Systems Upgrade | 0 | 16081.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16081.25 | 99.95%
VTS - BCS 8&9 COOLERS UPG (NEW | -12591.73 | 22820.08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10228.35 | 99.96%
Emergency- Spark Proof tools | 0 | 0 | 0 | 0 | 0 | 1862.1614 | 1862.1614 | 1862.1614 | 1862.1614 | 1862.1614 | 9310.8071 | 99.98%
VTS - WOLLERT 4 & 5 CAPEX | 3203.9 | 5158.96 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8362.86 | 99.99%
VTS - MORWELL TYERS UPGRADE | 6147.52 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6147.52 | 99.99%
Heater upgrade - Laverton North CG | 5671 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5671 | 100%
Pigging Program Inner Ring Main | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3630.3296 | 0 | 0 | 3630.3296 | 100%
GCS Emergency Lighting Upgrade | 879.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 879.8 | 100%
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100%
VTS - MAOP UPGRADE CAPEX | 0 | -42.39 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -42.39 | 100%
Liquid management - Longford | -4131.05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -4131.05 | 100%
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100%
Total | 1550442 | 7521688.32 | 14208332.65 | 10660501.5676 | 2105000 | 13147351.4425 | 6655486.7632 | 9316168.1584 | 10158218.663 | 8579472.2385
Check | 1550442 | 7521688.32 | 14208332.65 | 10660501.5676 | 2105000 | 12509982.34 | 6545390.0621 | 9316168.1584 | 10158218.663 | 8579472.2385
| 0 | 0 | 0 | 0 | 0 | 637369.1025 | 110096.701 | 0 | 0 | 0
4.1.3 - NON SYSTEM CAPEX
| EXPENDITURE Actual ($0's) | EXPENDITURE Forecast ($0's real, December 2017) 2016: EXPENDITURE Forecast ($0's real, December 2017)
| 1 July to 31 December 2013 | 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 | 2022 | Total | Proportion
Enterprise Asset Management | 806330.3274 | 1986550.9701 | 2564771.5454 | 1794.8446 | 0 | 0 | 0 | 0 | 0 | 0 | 5359447.6876 | 13.55% | Check | #REF!
Dandenong Relocation | 0 | 0 | 0 | 0 | 5057812 | 0 | 0 | 0 | 0 | 0 | 5057812 | 26.35%
WAN Upgrade (Satellite project) | 0 | 0 | 0 | 0 | 0 | 978453.096 | 978453.096 | 978453.096 | 978453.096 | 978453.096 | 4892265.48 | 38.72%
Applications Renewal | 0 | 0 | 0 | 0 | 0 | 744925.7116 | 930617.3383 | 744925.7116 | 930617.3383 | 744925.7116 | 4096011.8116 | 49.08%
Storage shed-Dandenong, Wollert & Springhurst | 0 | 0 | 0 | 0 | 0 | 0 | 620944.1189 | 620944.1189 | 620944.1189 | 0 | 1862832.3568 | 53.79%
Security - Physical | 0 | 0 | 0 | 0 | 0 | 349572.9355 | 349572.9355 | 349572.9355 | 349572.9355 | 349572.9355 | 1747864.6777 | 58.21%
Corporate IT | 211241.5961 | 302736.8717 | 276048.921 | 379176.6999 | 209022 | 0 | 0 | 0 | 0 | 0 | 1378226.0887 | 61.69%
Dandenong site fire mains replacement | 4961.3378 | 88164.1814 | 1020411.517 | 30567.2059 | 47050 | 0 | 0 | 0 | 0 | 0 | 1191154.2421 | 64.71%
SCADA - Comms upgrade to IP network-VTS only | 0 | 0 | 0 | 56649.9537 | 1000000 | 0 | 0 | 0 | 0 | 0 | 1056649.9537 | 67.38%
Data Centre | 65362.0189 | 895833.2344 | 79250.1745 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1040445.4278 | 70.01%
Equipment - Victorian low value pool purchases | 52890.5047 | 215346.1091 | 550230.7606 | 165502.2312 | 28230 | 0 | 0 | 0 | 0 | 0 | 1012199.6057 | 72.57%
Enterprise Content Management | 0 | 0 | 104729.0841 | 330175.7976 | 512309 | 0 | 0 | 0 | 0 | 0 | 947213.8817 | 74.97%
Corporate other | 242365.2632 | 340342.973 | 308327.8805 | 17750.0006 | 0 | 0 | 0 | 0 | 0 | 0 | 908786.1173 | 77.26%
eForm Digitisation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 173557.2996 | 447753.928 | 0 | 621311.2276 | 78.83%
B&T projects | 0 | 0 | 0 | 0 | 598799 | 0 | 0 | 0 | 0 | 0 | 598799 | 80.35%
SCADA System Upgrade | 0 | 0 | 25383.25 | 114504.8572 | 450000 | 0 | 0 | 0 | 0 | 0 | 589888.1072 | 81.84%
Infrastructure Renewal | 0 | 0 | 0 | 0 | 0 | 242910.5581 | 80970.186 | 80970.186 | 80970.186 | 0 | 485821.1163 | 83.07%
BI - Transmission Dashboard and Enterprise Pilot | 0 | 0 | 0 | 0 | 0 | 215920.4961 | 161940.3721 | 0 | 0 | 0 | 377860.8682 | 84.03%
Victoria CRE | 0 | 0 | 0 | 0 | 366376 | 0 | 0 | 0 | 0 | 0 | 366376 | 84.95%
Asbestos removal and replacement | 0 | 0 | 0 | 0 | 0 | 72325.5556 | 72325.5556 | 72325.5556 | 72325.5556 | 72325.5556 | 361627.7778 | 85.87%
PPM Refresh | 0 | 0 | 0 | 0 | 0 | 323880.7442 | 0 | 0 | 0 | 0 | 323880.7442 | 86.69%
HMI upgrade to CLEAR SCADA at BCS, SCS and WCS & CG, Longford | 0 | 0 | 0 | 0 | 0 | 62952.1636 | 62952.1636 | 62952.1636 | 62952.1636 | 62952.1636 | 314760.8178 | 87.48%
Market Services _APA Grid Prog | 0 | 0 | 153669.9247 | 158709.9434 | 0 | 0 | 0 | 0 | 0 | 0 | 312379.8681 | 88.27%
Dandenong water supply & fire main modification | 0 | 0 | 0 | 0 | 0 | 310275.7553 | 0 | 0 | 0 | 0 | 310275.7553 | 89.06%
CORP SIB16 DANDENONG REFURB | 0 | 0 | 303211.3819 | 3507.7692 | 0 | 0 | 0 | 0 | 0 | 0 | 306719.1511 | 89.83%
Melbourne Metro CRE | 0 | 0 | 0 | 299652.4599 | 0 | 0 | 0 | 0 | 0 | 0 | 299652.4599 | 90.59%
APA Grid Extend Program | 0 | 0 | 0 | 0 | 0 | 269900.6202 | 0 | 0 | 0 | 0 | 269900.6202 | 91.27%
Equipment - IT Purchases | 28090.5164 | 85086.328 | 94876.5278 | 60274.7002 | 0 | 0 | 0 | 0 | 0 | 0 | 268328.0724 | 91.95%
APA Grid | 0 | 0 | 0 | 0 | 261222 | 0 | 0 | 0 | 0 | 0 | 261222 | 92.61%
Vehicle Comms & Journey Mgmt | 0 | 2091.1818 | 85100.7826 | 156248.7099 | 0 | 0 | 0 | 0 | 0 | 0 | 243440.6743 | 93.23%
APA Grid Ph.2 | 135912.9265 | 98899.2122 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 234812.1387 | 93.82%
EC Upgrade | 0 | 0 | 0 | 188129.9092 | 0 | 0 | 0 | 0 | 0 | 0 | 188129.9092 | 94.3%
Hazardous Area Platform | 0 | 0 | 0 | 0 | 0 | 167607.3459 | 0 | 0 | 0 | 0 | 167607.3459 | 94.72%
Oracle eBS Upgrade to 12.2 | 0 | 0 | 0 | 0 | 0 | 28837.5875 | 137783.569 | 0 | 0 | 0 | 166621.1564 | 95.14%
EAM TRANSMISSION ESTAB WORK | 0 | 0 | 0 | 162243.4149 | 0 | 0 | 0 | 0 | 0 | 0 | 162243.4149 | 95.55%
CRM Upgrade | 0 | 0 | 0 | 0 | 0 | 152028.1315 | 6374.8151 | 0 | 0 | 0 | 158402.9466 | 95.95%
BizTalk Upgrade FY2018 | 0 | 0 | 0 | 0 | 0 | 0 | 65299.6378 | 72432.5287 | 0 | 0 | 137732.1665 | 96.3%
BizTalk System Upgrade 2020 | 0 | 0 | 0 | 0 | 0 | 0 | 65299.6378 | 72432.5287 | 0 | 0 | 137732.1665 | 96.65%
Equipment - Field Equipment | 78414.37 | 33433 | 0 | 0 | 10000 | 0 | 0 | 0 | 0 | 0 | 121847.37 | 96.96%
APA Grid Services Initiatives | 0 | 0 | 0 | 113036.3542 | 0 | 0 | 0 | 0 | 0 | 0 | 113036.3542 | 97.24%
SCADA Satellite Strategy | 0 | 0 | 37193.7062 | 61962.894 | 0 | 0 | 0 | 0 | 0 | 0 | 99156.6002 | 97.49%
Code Management Software | 0 | 0 | 0 | 0 | 0 | 97804.495 | 0 | 0 | 0 | 0 | 97804.495 | 97.74%
Supplier Qualification and Compliance | 0 | 0 | 0 | 0 | 0 | 75339.9468 | 20032.5681 | 0 | 0 | 0 | 95372.515 | 97.98%
BCS Control Room Fire Suppression System | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 84727.045 | 84727.045 | 98.2%
Dandenong Site - Storage shed | 11857.7292 | 66978.2157 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 78835.9449 | 98.4%
Mobile phone CAPEX purchases | 0 | 22811.9773 | 27279.5795 | 28743.2099 | 0 | 0 | 0 | 0 | 0 | 0 | 78834.7666 | 98.6%
Dandenong Office Purchases | 8861.6981 | 34769.95 | 31686.2177 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 75317.8658 | 98.79%
Automated Testing Tool | 0 | 0 | 0 | 0 | 0 | 71985.595 | 0 | 0 | 0 | 0 | 71985.595 | 98.97%
APA Grid Extend | 0 | 0 | 0 | 68445.8618 | 0 | 0 | 0 | 0 | 0 | 0 | 68445.8618 | 99.14%
APA Grid Perf & Resil Overhaul | 0 | 0 | 44725.1667 | 22308.3818 | 0 | 0 | 0 | 0 | 0 | 0 | 67033.5486 | 99.31%
Dandenong Complex asbestos removal | 0 | 60923.51 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60923.51 | 99.47%
Equipment - Gas Detectors | 0 | 0 | 0 | 0 | 10000 | 0 | 0 | 23927.8554 | 23927.8554 | 0 | 57855.7108 | 99.61%
X-Info Aware Version 2 | 0 | 0 | 0 | 0 | 0 | 46431.7054 | 0 | 0 | 0 | 0 | 46431.7054 | 99.73%
EAM Bus Support & Governance | 0 | 0 | 0 | 43193.0907 | 0 | 0 | 0 | 0 | 0 | 0 | 43193.0907 | 99.84%
VTS - BROOKLYN FIRE SERVICE | 29482.73 | 11269.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40752.23 | 99.94%
BI reporting | 33318.3814 | 2571.9179 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35890.2993 | 100%
BCS Administration Building Distribution Board Upgrade | 0 | -52 | 0 | 30388.8889 | 0 | 0 | 0 | 0 | 0 | 0 | 30336.8889 | 100.1%
SharePoint Upgrade | 0 | 0 | 0 | 0 | 0 | 26318.3873 | 0 | 0 | 0 | 0 | 26318.3873 | 100.2%
VTS17.SIB30 DND EMERG ENTRANCE | 0 | 0 | 0 | 24158.7108 | 0 | 0 | 0 | 0 | 0 | 0 | 24158.7108 | 100.2%
PPOM Snapshot Engine | 9285.9184 | 12608.9365 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21894.8549 | 100.3%
SCADA Resilience Project FEED | 0 | 0 | 0 | 20033.5106 | 0 | 0 | 0 | 0 | 0 | 0 | 20033.5106 | 100.3%
Project Server Status Report | 7605.6406 | 4061.9411 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11667.5817 | 100.4%
Oracle Integration with EAM | 0 | 0 | 0 | 11098.5526 | 0 | 0 | 0 | 0 | 0 | 0 | 11098.5526 | 100.4%
PPOM Phase 2 | 5453.1938 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5453.1938 | 100.4%
SCADA Resilience Phase 1 Recom | 0 | 0 | 0 | 4951.1771 | 0 | 0 | 0 | 0 | 0 | 0 | 4951.1771 | 100.4%
IOC SCADA GAP ANALYSIS | 0 | 0 | 0 | 4301.8938 | 0 | 0 | 0 | 0 | 0 | 0 | 4301.8938 | 100.4%
EAM Business Support-Reports | 0 | 0 | 0 | 3501.9211 | 0 | 0 | 0 | 0 | 0 | 0 | 3501.9211 | 100.4%
VTS17.SIB27 SCS CR EPS REMOVAL | 0 | 0 | 0 | 2893.8326 | 0 | 0 | 0 | 0 | 0 | 0 | 2893.8326 | 100.5%
APA Grid Ph. 3 | 2637.3633 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2637.3633 | 100.5%
Finance Systems | 1751.8135 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1751.8135 | 100.5%
APA Grid & Mrkt Srvs SIB Capex | 0 | 0 | 0 | 464.2859 | 0 | 0 | 0 | 0 | 0 | 0 | 464.2859 | 100.5%
Adjustments required for differences in CWIP and FAR records | 0 | -26601 | 23200 | -180758.1759 | 0 | 0 | 0 | 0 | 0 | 0 | -184159.1759 | 100%
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100%
Total | 1735823.3294 | 4237827.0102 | 5730096.4203 | 2383612.8873 | 8550820 | 4237470.8307 | 3552565.9939 | 3252493.9798 | 3567517.1773 | 2292956.5073
Check | 1735823.3294 | 4237827.0102 | 5730096.4203 | 2383612.8873 | 8550820 | 4237470.8307 | 3552565.9939 | 3252493.9798 | 3567517.1773 | 2292956.5073
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.3 - FORECAST CAPEX
EXPENDITURE Forecast ($0's real, December 2017)
|  |  |  | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 | 2022
Direct labour expenditure |  |  |  | 13817969.6734 | 10296658.2303 | 19218127.486 | 12391044.4472 | 12580548.0023 | 3766249.0834 | 3032759.641
Direct materials expenditure |  |  |  | 31586618.8868 | 19259904.5917 | 21099732.9899 | 22315914.5573 | 26421522.276 | 2567079.8252 | 2237825.3279
Direct contractor expenditure |  |  |  | 56365220.7514 | 35202122.6987 | 7640174.5335 | 4950231.5977 | 4847960.7208 | 7235027.4749 | 5513345.8016
Other direct expenditure |  |  |  | 4605064.9818 | 4228121.2522 | 13176785.3324 | 17277926.0967 | 28490996.5069 | 157379.4569 | 88497.9754
Overheads |  | EXPENDITURE Forecast ($0's real, December 2017) 2016: 0; EXPENDITURE Forecast ($0's real, December 2017) 2017: 0
Total |  |  |  | 106374874.2934 | 68986806.7729 | 61134820.3417 | 56935116.6988 | 72341027.5061 | 13725735.8403 | 10872428.7458
Check |  |  |  | 106103765.3505 | 62986806.7729 | 61772189.4442 | 56958835.6221 | 72311127.5061 | 13725735.8403 | 10872428.7458
|  |  |  | 271108.9429 | 6000000 | -637369.1025 | -23718.9233 | 29900 | 0 | 0
[6 empty] | 61134820.3417 | 56935116.6988 | 72341027.5061 | 13725735.8403 | 10872428.7458

## 4.0 Calc│AER Forecast ($nom)
Check
| 4.0 Calc│AER Forecast ($nom) |  |  |  | 17596792.6476 | 95801187.616 | 23597604.0001 | 13057047.239 | 8489983.318 | 158542614.8208 | 158542614.8208 | 0
Capex # | Project Name | Forecast? |  | Category | Reg 2013 | 2014 | 2015 | 2016 | 2017 | Total
1 | Stonehaven CS - now Winchelsea | Yes | Compressors | Augmentation | 4376332.5698 | 30758344.8966 | 0 | 0 | 0 | 35134677.4664 |  | 15203.1404 | TRUE
2 | Warragul Looping | Yes | Pipelines | Augmentation | 0 | 2615564.7871 | 0 | 0 | 0 | 2615564.7871 |  | 0 | TRUE
3 | Anglesea Pipeline Extension | Yes | Pipelines | Augmentation | 0 | 1340341.542 | 12183129.4443 | 0 | 0 | 13523470.9863 |  | 0 | TRUE
4 | Wollert CS A Unit reinstrumentation | Yes | Compressors | Replacement | 0 | 0 | 265908.268 | 269983.1647 | 0 | 535891.4326 |  | 0 | TRUE
5 | BCS Filter | Yes | City Gates & Field Regs | Replacement | 0 | 418107.3004 | 0 | 0 | 0 | 418107.3004 |  | 0 | TRUE
6 | Iona CS - Inlet Pressure Reduction | Yes | Compressors | Replacement | 91456.1375 | 0 | 0 | 0 | 0 | 91456.1375 |  | 317.7136 | TRUE
7 | Iona CS Control system replacement | Yes | Compressors | Replacement | 0 | 689856.986 | 0 | 0 | 0 | 689856.986 |  | 0 | TRUE
8 | SCS Cooler Upgrade | Yes | Compressors | Replacement | 0 | 0 | 958913.4738 | 0 | 0 | 958913.4738 |  | 0 | TRUE
9 | BCS Emergency Lighting | Yes | Other | Replacement | 12886.9609 | 0 | 0 | 0 | 0 | 12886.9609 |  | 44.7686 | TRUE
10 | GCS Emergency Lighting Upgrade | Yes | Other | Replacement | -6297.8094 | 0 | 0 | 0 | 0 | -6297.8094 |  | -21.8782 | TRUE
11 | Wollert CS Emergency Lighting | Yes | Other | Replacement | 50918.1055 | 0 | 0 | 0 | 0 | 50918.1055 |  | 176.8867 | TRUE
12 | Emergency - fully equipped caravan | Yes | Other | Replacement | 0 | 147369.664 | 0 | 0 | 0 | 147369.664 |  | 0 | TRUE
13 | Emergency - Gas blowdown and flaring sytem | Yes | Other | Replacement | 0 | 0 | 0 | 0 | 220541.2724 | 220541.2724 |  | 0 | TRUE
14 | Emergency - refurbish and re-testing of pipes | Yes | Other | Replacement | 0 | 0 | 0 | 12948.7832 | 220541.2724 | 233490.0556 |  | 0 | TRUE
15 | Emergency - SMR radio upgrade | Yes | Other | Replacement | 0 | 0 | 0 | 71218.3077 | 0 | 71218.3077 |  | 0 | TRUE
16 | Emergency BA escape sets | Yes | Other | Replacement | 10185.9062 | 0 | 0 | 0 | 0 | 10185.9062 |  | 35.3853 | TRUE
17 | Emergency diesel fuel storage | Yes | Other | Replacement | 0 | 52258.7461 | 89297.3136 | 0 | 0 | 141556.0597 |  | 0 | TRUE
18 | Emergency Plidco fittings - Sleeve vent | Yes | Pipelines | Replacement | 0 | 0 | 42405.998 | 204314.8811 | 0 | 246720.8791 |  | 0 | TRUE
19 | Emergency Response Equipment | Yes | Other | Replacement | 91673.1562 | 94065.743 | 95675.6931 | 97115.8742 | 99243.5726 | 477774.0391 |  | 318.4675 | TRUE
20 | Emergency Spark Proof tools | Yes | Other | Replacement | 20371.8125 | 20903.4984 | 21261.2651 | 0 | 0 | 62536.5761 |  | 70.7706 | TRUE
21 | Purchase and replacement of emergency fittings and Equipment | Yes | Other | Replacement | 508528.7744 | 808643.2424 | 0 | 0 | 0 | 1317172.0168 |  | 1766.6012 | TRUE
22 | Facilities Communication Systems Upgrade | Yes | Other | Replacement | 10183.6211 | 10454.0824 | 10644.8779 | 10812.3374 | 11066.5001 | 53161.419 |  | 35.3773 | TRUE
23 | GCS Station Valve Upgrade | Yes | Compressors | Replacement | 0 | 191013.6574 | 0 | 0 | 0 | 191013.6574 |  | 0 | TRUE
24 | GCS Unit 3 Turbine Overhaul | Yes | Compressors | Replacement | 0 | 0 | 372371.2928 | 0 | 0 | 372371.2928 |  | 0 | TRUE
25 | SMS - Compressor station vents-Various | Yes | Compressors | Replacement | 0 | 104540.8244 | 0 | 0 | 0 | 104540.8244 |  | 0 | TRUE
26 | AS 2885 Design Life reviews of Facilities&Pipelines | Yes | City Gates & Field Regs | Replacement | 213378.4362 | 222254.2887 | 227093.8619 | 231512.0703 | 354927.6671 | 1249166.3243 |  | 741.265 | TRUE
27 | BCG Un-regulated Bypass Upgrade | Yes | City Gates & Field Regs | Replacement | 0 | 0 | 0 | 134991.5823 | 0 | 134991.5823 |  | 0 | TRUE
28 | Dandenong CG gas heater | Yes | City Gates & Field Regs | Replacement | 0 | 0 | 3089130.4459 | 0 | 0 | 3089130.4459 |  | 0 | TRUE
29 | Hazardous Area Rectification | Yes | City Gates & Field Regs | Replacement | 188150.8136 | 222103.319 | 237651.4839 | 174431.9218 | 121147.2218 | 943484.76 |  | 653.6257 | TRUE
30 | Hazardous Areas Review | Yes | City Gates & Field Regs | Replacement | 429131.7219 | 422201.3413 | 292365.4066 | 54215.6767 | 55487.8357 | 1253401.9823 |  | 1490.7802 | TRUE
31 | Heater upgrade - Laverton North CG | Yes | City Gates & Field Regs | Replacement | 0 | 0 | 0 | 772987.9621 | 0 | 772987.9621 |  | 0 | TRUE
32 | Odorant Dandenong Pump Upgrade 700 & 2800 kPa | Yes | Gas Quality | Replacement | 0 | 261328.7288 | 0 | 0 | 0 | 261328.7288 |  | 0 | TRUE
33 | Regulator upgrade - Dandenong City Gate (exclude filters) | Yes | City Gates & Field Regs | Replacement | 3798514.2591 | 1541960.8781 | 0 | 0 | 0 | 5340475.1372 |  | 13195.8312 | TRUE
34 | Valve - Pipeline LNG plant Isolation Valve Actuator Replacement | Yes | City Gates & Field Regs | Replacement | 0 | 0 | 98731.5885 | 0 | 0 | 98731.5885 |  | 0 | TRUE
35 | Valve - Pipeline to LNG plant UV325 valve replacement and loading valve | Yes | City Gates & Field Regs | Replacement | 41756.5941 | 250875.5796 | 0 | 0 | 0 | 292632.1738 |  | 145.0601 | TRUE
36 | Valve - Corio CG Un-regulated Bypass Upgrade | Yes | City Gates & Field Regs | Replacement | 0 | 0 | 0 | 134991.5823 | 0 | 134991.5823 |  | 0 | TRUE
37 | Valve - Tyers Branch Valve Actuator Replacement | Yes | Pipelines | Replacement | 0 | 209062.983 | 0 | 0 | 0 | 209062.983 |  | 0 | TRUE
38 | Valve - UniBolt Phase 3 Replacement | Yes | City Gates & Field Regs | Replacement | -111731.5266 | 0 | 132989.7474 | 135045.7942 | 0 | 156304.0151 |  | -388.1492 | TRUE
39 | Pig Trap - Enclosure upgrade | Yes | City Gates & Field Regs | Replacement | 46848.8617 | 94078.3424 | 95752.6181 | 97232.9718 | 99456.5295 | 433369.3236 |  | 162.7504 | TRUE
40 | Pig Trap - Pipe Support Upgrade | Yes | City Gates & Field Regs | Replacement | 96753.084 | 99304.9169 | 101072.208 | 102634.8036 | 22101.451 | 421866.4636 |  | 336.1149 | TRUE
41 | BCS Administration Building Distribution Board Upgrade | Yes | Compressors | Non-System | 30498.0508 | 0 | 0 | 0 | 0 | 30498.0508 |  | 105.9486 | TRUE
42 | Equipment - Field Equipment | Yes | Other | Non-System | 48400.625 | 52258.7461 | 53153.1628 | 53953.2634 | 55135.3181 | 262901.1155 |  | 168.1411 | TRUE
43 | Equipment - Gas Detectors | Yes | Other | Non-System | 0 | 0 | 0 | 0 | 110270.6362 | 110270.6362 |  | 0 | TRUE
44 | Equipment - IT Purchases | Yes | Other | Non-System | 23962.3445 | 24587.74 | 25008.5631 | 25385.0104 | 25941.1672 | 124884.8252 |  | 83.2439 | TRUE
45 | Equipment - Test | Yes | Other | Non-System | 50929.5312 | 52258.7461 | 53153.1628 | 53953.2634 | 55135.3181 | 265430.0217 |  | 176.9264 | TRUE
46 | Equipment - Victorian low value pool purchases | Yes | Other | Non-System | -128694.9727 | 10451.7492 | 10630.6326 | 10790.6527 | 11027.0636 | -85794.8746 |  | -447.0793 | TRUE
47 | Dandenong 180 Greens Road Office Redevelopment | Yes | Buildings | Non-System | 3908004.5673 | 5578595.6008 | 0 | 0 | 0 | 9486600.1681 |  | 13576.1945 | TRUE
48 | Dandenong Asphalt Resurfacing | Yes | Other | Non-System | 0 | 0 | 265979.4949 | 0 | 0 | 265979.4949 |  | 0 | TRUE
49 | Dandenong Complex asbestos removal | Yes | Buildings | Non-System | 76384.0137 | 78398.6186 | 31917.5394 | 32410.9906 | 33152.1765 | 252263.3388 |  | 265.3539 | TRUE
50 | Dandenong external surface repainting | Yes | Buildings | Non-System | 0 | 104540.8244 | 0 | 0 | 0 | 104540.8244 |  | 0 | TRUE
51 | Dandenong Office Purchases | Yes | Other | Non-System | -18575.3892 | 49175.4801 | 50017.1262 | 50770.0209 | 51882.3343 | 183269.5723 |  | -64.5299 | TRUE
52 | Dandenong Site - Storage shed | Yes | Buildings | Non-System | 449300.3125 | 0 | 0 | 0 | 0 | 449300.3125 |  | 1560.8448 | TRUE
53 | Pigging - Tracking and locating tools | Yes | Other | Non-System | 0 | 20908.1649 | 0 | 0 | 0 | 20908.1649 |  | 0 | TRUE
54 | Pigging - Two portable liquid collectors for pigging | Yes | Other | Non-System | 0 | 0 | 0 | 251927.4624 | 0 | 251927.4624 |  | 0 | TRUE
55 | Pigging -Two portable dust collectors for pigging | Yes | Other | Non-System | 0 | 0 | 247693.7388 | 0 | 0 | 247693.7388 |  | 0 | TRUE
56 | Control Room - Additonal OE monitor | Yes | Other | Non-System | 10183.6211 | 0 | 0 | 0 | 0 | 10183.6211 |  | 35.3773 | TRUE
57 | SCADA - Comms upgrade to IP network-VTS only | Yes | Other | Non-System | 0 | 0 | 0 | 0 | 1976213.1887 | 1976213.1887 |  | 0 | TRUE
58 | SCADA - IT security | Yes | Other | Non-System | 95827.8745 | 0 | 0 | 0 | 0 | 95827.8745 |  | 332.9008 | TRUE
59 | SCADA - Remote maintenance and engineering workstations [Control Room, Gooding, Brooklyn CS&CG, Wollert CS&CG, Springhurst, Iona] | Yes | Other | Non-System | 10183.6211 | 10454.0824 | 10644.8779 | 10812.3374 | 11066.5001 | 53161.419 |  | 35.3773 | TRUE
60 | SCADA - RTU/ PLC/HMI Development and Test bench [PC, iFix, Control Logix, Bristol Designer Tools] | Yes | Other | Non-System | 23801.2861 | 0 | 0 | 0 | 0 | 23801.2861 |  | 82.6844 | TRUE
61 | SCADA System Upgrade | Yes | Other | Non-System | 0 | 0 | 109493.8937 | 1114126.4843 | 513758.3923 | 1737378.7702 |  | 0 | TRUE
62 | Dandenong Building exterior coatings | Yes | Buildings | Non-System | 0 | 0 | 158835.5935 | 161114.4722 | 0 | 319950.0657 |  | 0 | TRUE
63 | Dandenong site fire mains replacement | Yes | Buildings | Non-System | 264596.2109 | 0 | 0 | 0 | 0 | 264596.2109 |  | 919.1928 | TRUE
64 | Brooklyn guttering | Yes | Buildings | Non-System | 0 | 41571.8329 | 0 | 0 | 0 | 41571.8329 |  | 0 | TRUE
65 | Wollert Control Room guttering | Yes | Buildings | Non-System | 0 | 0 | 31683.3611 | 0 | 0 | 31683.3611 |  | 0 | TRUE
66 | Corporate IT | Yes | Other | Non-System | -1542163.7301 | 0 | 0 | 0 | 0 | -1542163.7301 |  | -5357.3926 | TRUE
67 | Liquid management - Brooklyn | Yes | City Gates & Field Regs | Replacement | 0 | 0 | 347981.4972 | 0 | 0 | 347981.4972 |  | 0 | TRUE
68 | Liquid management - Gooding | Yes | City Gates & Field Regs | Replacement | 0 | 186327.8597 | 0 | 0 | 0 | 186327.8597 |  | 0 | TRUE
69 | Liquid management - Longford | Yes | City Gates & Field Regs | Replacement | -27029.1328 | 0 | 0 | 0 | 0 | -27029.1328 |  | -93.8977 | TRUE
70 | Liquid Management - Pakenham | Yes | City Gates & Field Regs | Replacement | 146901.0055 | 0 | 0 | 0 | 0 | 146901.0055 |  | 510.3261 | TRUE
71 | CP - Cathodic Protection Replacement | Yes | Pipelines | Replacement | 113358.9844 | 208436.186 | 211851.051 | 214858.1164 | 219453.6203 | 967957.9581 |  | 393.8029 | TRUE
72 | CP - Corrosion Protection Testing Equipment | Yes | Other | Replacement | 10184.9922 | 10452.6825 | 10636.3307 | 10799.3266 | 11042.8382 | 53116.1702 |  | 35.3821 | TRUE
73 | Pig Trap - A Branch Valve on Pipeline 108 to Newport Install(124) | Yes | Pipelines | Replacement | 0 | 0 | 0 | 2718764.9954 | 0 | 2718764.9954 |  | 0 | TRUE
74 | Pig Trap - Dandenong to Princes Highway Pipeline Install (129) | Yes | City Gates & Field Regs | Replacement | 0 | 0 | 0 | 0 | 667257.8429 | 667257.8429 |  | 0 | TRUE
75 | Pig Trap - Laverton North to Laverton North Pipeline Install (162) | Yes | City Gates & Field Regs | Replacement | 0 | 0 | 0 | 990615.9663 | 0 | 990615.9663 |  | 0 | TRUE
76 | Pig Trap - Pakenham to Pakenham Pipeline Install (68) | Yes | City Gates & Field Regs | Replacement | 0 | 0 | 0 | 1119963.0579 | 0 | 1119963.0579 |  | 0 | TRUE
77 | Pigging Program (T1 Dandenong - Morwell) | Yes | Other | Replacement | 0 | 0 | 0 | 0 | 593207.1591 | 593207.1591 |  | 0 | TRUE
78 | Pigging Program (T56 Brooklyn - Ballan) | Yes | Other | Replacement | 0 | 0 | 0 | 467241.989 | 0 | 467241.989 |  | 0 | TRUE
79 | Pigging Program (T59 Euro - Kyabram) | Yes | Other | Replacement | 0 | 0 | 0 | 433230.3213 | 0 | 433230.3213 |  | 0 | TRUE
80 | Pigging Program (T67 Guilford - Maryborough) | Yes | Other | Replacement | 0 | 0 | 0 | 0 | 242980.4994 | 242980.4994 |  | 0 | TRUE
81 | Pigging Program (T74 Keon Park - Wollert) | Yes | Other | Replacement | 471181.5469 | 0 | 0 | 0 | 0 | 471181.5469 |  | 1636.859 | TRUE
82 | Pigging Program (T92 Iona - Brooklyn) | Yes | Other | Replacement | 0 | 0 | 0 | 628625.3386 | 0 | 628625.3386 |  | 0 | TRUE
83 | Pig Trap - Princes Highway to Regent Street Pipeline Install(36) | Yes | City Gates & Field Regs | Replacement | 0 | 0 | 0 | 0 | 1419447.891 | 1419447.891 |  | 0 | TRUE
84 | Pig Trap - Somerton to Somerton Pipeline Install (238) | Yes | City Gates & Field Regs | Replacement | 0 | 0 | 1168017.1622 | 0 | 0 | 1168017.1622 |  | 0 | TRUE
85 | Pig Trap - Tyers to Maryvale Pipeline Install (67) | Yes | City Gates & Field Regs | Replacement | 0 | 0 | 0 | 0 | 872386.6837 | 872386.6837 |  | 0 | TRUE
86 | Exposed pipe coating refurbishment | Yes | Pipelines | Replacement | 391300.0464 | 692457.0369 | 476478.8489 | 354425.5465 | 516012.5031 | 2430673.9817 |  | 1359.355 | TRUE
87 | BCS Safety and Process Control System and RTU Upgrade | Yes | Compressors | Replacement | -10341.5 | 0 | 0 | 0 | 0 | -10341.5 |  | -35.9258 | TRUE
88 | CS Type B compliance upgrade | Yes | Compressors | Replacement | 870434.0938 | 0 | 0 | 0 | 0 | 870434.0938 |  | 3023.8405 | TRUE
89 | GCS GEA Fuel Gas Upgrade | Yes | Compressors | Replacement | 50886.7023 | 0 | 0 | 0 | 0 | 50886.7023 |  | 176.7776 | TRUE
90 | GCS Units 1,2,3&4 Suction/Discharge Actuated Valve Replacement | Yes | Compressors | Replacement | 865135.7812 | 0 | 0 | 0 | 0 | 865135.7812 |  | 3005.4345 | TRUE
91 | Mothball WCS station 'A' | Yes | Compressors | Replacement | 0 | 0 | 0 | 0 | 455034.4827 | 455034.4827 |  | 0 | TRUE
92 | Regulator Upgrade - Lara pneumatic control system upgrade | Yes | City Gates & Field Regs | Replacement | 204022.3035 | 233821.5623 | 0 | 0 | 0 | 437843.8658 |  | 708.7623 | TRUE
93 | Security - High Risk sites security upgrade | Yes | Other | Replacement | 663660.3942 | 0 | 1069029.742 | 776042.4582 | 0 | 2508732.5945 |  | 2305.52 | TRUE
94 | Security - Small Site Facilities Fencing Upgrade | Yes | Other | Replacement | 0 | 78324.6762 | 79704.1883 | 80916.5423 | 82759.8212 | 321705.228 |  | 0 | TRUE
95 | Zonal Chromatograph Bottle Regulator Panels Upgrades | Yes | Gas Quality | Replacement | 29801.7281 | 0 | 0 | 0 | 0 | 29801.7281 |  | 103.5296 | TRUE
96 | Zonal Chromatograph Insertion Probes | Yes | Gas Quality | Replacement | 96625.0391 | 0 | 0 | 0 | 0 | 96625.0391 |  | 335.6701 | TRUE
97 | Zonal Chromatograph Upgrades | Yes | Gas Quality | Replacement | 101740.2344 | 104296.0538 | 106039.7194 | 107577.3384 | 0 | 419653.3459 |  | 353.44 | TRUE
98 | RTU & Control System Upgrade - Facilities | Yes | Other | Replacement | -180732.3874 | 116666.671 | 118988.6687 | 121069.7854 | 124081.5779 | 300074.3156 |  | -627.8544 | TRUE
99 | GCS Anti-Surge & Fast-Stop Valves Upgrade | Yes | Compressors | Replacement | 681014.5306 | 0 | 0 | 0 | 0 | 681014.5306 |  | 2365.8073 | TRUE
100 | GCS Control Room Fire Suppression System | Yes | Compressors | Replacement | 45826.2949 | 104540.8244 | 0 | 0 | 0 | 150367.1193 |  | 159.198 | TRUE
101 | GCS Units 1,2,3&4 Fire Suppression System | Yes | Compressors | Replacement | 0 | 0 | 0 | 243277.5924 | 0 | 243277.5924 |  | 0 | TRUE
102 | Iona CS - Unit Fire Suppression System | Yes | Compressors | Replacement | 0 | 292688.1763 | 0 | 0 | 0 | 292688.1763 |  | 0 | TRUE
103 | Wollert CG Control Hut Fire Suppression System | Yes | Compressors | Replacement | 0 | 36589.2885 | 37257.0728 | 0 | 0 | 73846.3613 |  | 0 | TRUE
104 | Wollert CS A/B Control Room Fire Suppression System | Yes | Compressors | Replacement | 0 | 104540.8244 | 133060.9743 | 0 | 0 | 237601.7987 |  | 0 | TRUE
105 | BCG Control Hut Fire Suppression System | Yes | City Gates & Field Regs | Replacement | 66193.5371 | 0 | 0 | 0 | 0 | 66193.5371 |  | 229.9527 | TRUE
106 | Valve - Actuate MLV's in T1 areas | Yes | Pipelines | Replacement | 0 | 1369703.9901 | 1392508.6264 | 1412528.7815 | 0 | 4174741.398 |  | 0 | TRUE
107 | Valve - Longford to Dandenong LV10 Vent Stack | Yes | Pipelines | Replacement | 33925.9947 | 0 | 0 | 0 | 0 | 33925.9947 |  | 117.8571 | TRUE
108 | BCS Station Isolation and Loading Valves | Yes | Compressors | Replacement | 0 | 949708.4673 | 0 | 0 | 0 | 949708.4673 |  | 0 | TRUE
109 | Iona CS - Capacity Aftercooler upgrade | Yes | Compressors | Replacement | 0 | 736733.1711 | 0 | 0 | 0 | 736733.1711 |  | 0 | TRUE
110 | BCS DEA Upgrade | Yes | Compressors | Replacement | 0 | 0 | 373937.953 | 0 | 0 | 373937.953 |  | 0 | TRUE
111 | Pig Trap - Keon Park Install | Yes | City Gates & Field Regs | Replacement | -381008.9258 | 0 | 0 | 0 | 0 | -381008.9258 |  | -1323.6042 | TRUE
112 | BCS Replacement of FSV, ASV & Other Valves | Yes | Compressors | Replacement | 0 | 929587.2398 | 0 | 0 | 0 | 929587.2398 |  | 0 | TRUE
113 | BCS Unit 10 & 11 Cooler Upgrade | Yes | Compressors | Replacement | -7117.1039 | 3481670.0919 | 0 | 0 | 0 | 3474552.988 |  | -24.7244 | TRUE
114 | SMS - GIS & Aerial Photography | Yes | Pipelines | Replacement | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | TRUE
115 | Wollert to Clonbinane Looping | Yes | Pipelines | Augmentation | 1847551.0624 | 35866654.8096 | 0 | 0 | 0 | 37714205.872 |  | 6418.2915 | TRUE
116 | MAOP Upgrade - Euroa to Springhurst (pipe) | Yes | Pipelines | Augmentation | 193638.3624 | 1789940.687 | 0 | 0 | 0 | 1983579.0494 |  | #N/A | #N/A
117 | MAOP Upgrade - Euroa to Springhurst (Reg) | Yes | City Gates & Field Regs | Augmentation | 611489.5654 | 5652444.2748 | 0 | 0 | 0 | 6263933.8401 |  | #N/A | #N/A
118 | Valve - T60 Longford - Dandenong Upgrade hydraulic hand pump of actuators | Yes | Other | Replacement | 112029.8867 | 0 | 0 | 0 | 0 | 112029.8867 |  | 389.1857 | TRUE
119 | VTS - BROOKLYN LARA LOOP | Yes | Pipelines | Replacement | -22864.8672 | 0 | 0 | 0 | 0 | -22864.8672 |  | #N/A | #N/A
120 | VTS - WOLLERT 4 & 5 CAPEX | Yes | Compressors | Replacement | -13160.9766 | 0 | 0 | 0 | 0 | -13160.9766 |  | #N/A | #N/A
121 | VTS - MORWELL TYERS UPGRADE | Yes | City Gates & Field Regs | Replacement | -227.9773 | 0 | 0 | 0 | 0 | -227.9773 |  | #N/A | #N/A
122 | VTS - MAOP UPGRADE CAPEX | Yes | City Gates & Field Regs | Replacement | -15390.0906 | 0 | 0 | 0 | 0 | -15390.0906 |  | #N/A | #N/A
123 | VTS - BBP & BCP CG UPGRADE | Yes | City Gates & Field Regs | Replacement | -98353.1555 | 0 | 0 | 0 | 0 | -98353.1555 |  | #N/A | #N/A
124 | VTS - BRANCH VALVE CASTLEMAINE | Yes | Pipelines | Replacement | -26303.7937 | 0 | 0 | 0 | 0 | -26303.7937 |  | #N/A | #N/A
125 | VTS - EUROA CS NEW (PPOM) | Yes | Compressors | Augmentation | -417488.5508 | 0 | 0 | 0 | 0 | -417488.5508 |  | #N/A | #N/A
126 | VTS - SUNBURY PIPE LOOP (NEW) | Yes | Pipelines | Augmentation | -491046.4 | 0 | 0 | 0 | 0 | -491046.4 |  | #N/A | #N/A
127 | VTS - BCS 8&9 COOLERS UPG (NEW | Yes | Compressors | Replacement | -461009.1789 | 0 | 0 | 0 | 0 | -461009.1789 |  | #N/A | #N/A
128 | VTS - BCS 12 FAST STOP VALVE | Yes | Compressors | Replacement | -36134.7391 | 0 | 0 | 0 | 0 | -36134.7391 |  | #N/A | #N/A
129 | VTS - BCS 8 & 9 UNIT VALVES | Yes | Compressors | Replacement | -285624.0664 | 0 | 0 | 0 | 0 | -285624.0664 |  | #N/A | #N/A
130 | PIGGING T91 CURDIEVALE | Yes | Other | Replacement | 0 | 0 | 0 | 0 | 0 | 0 |  | #N/A | #N/A
131 | VTS - BROOKLYN FIRE SERVICE | Yes | Buildings | Non-System | -433006.1531 | 0 | 0 | 0 | 0 | -433006.1531 |  | #N/A | #N/A
132 | VTS - BCS LUBE OIL COOLER 8&9 | Yes | City Gates & Field Regs | Replacement | 0 | 0 | 0 | 0 | 0 | 0 |  | #N/A | #N/A
133 | VNIE Looping 6 to 8 | Yes | Pipelines | Augmentation | 0 | 0 | 0 | 0 | 0 | 0 |  | #N/A | #N/A
134 | VTS16.SIB42 WOLL SOFT STARTERS | Yes | Other | Replacement | 0 | 0 | 0 | 0 | 0 | 0 |  | #N/A | #N/A
135 | VTS.SIB99 WCS STN-A DISCHRG LQ | Yes | Other | Replacement | 0 | 0 | 0 | 0 | 0 | 0 |  | #N/A | #N/A
136 | VTS17.SIB27 SCS CR EPS REMOVAL | Yes | Buildings | Non-System | 0 | 0 | 0 | 0 | 0 | 0 |  | #N/A | #N/A
137 | VTS17.SIB30 DND EMERG ENTRANCE | Yes | Buildings | Non-System | 0 | 0 | 0 | 0 | 0 | 0 |  | #N/A | #N/A
138 | Corporate other | Yes | Other | Non-System | 0 | 0 | 0 | 0 | 0 | 0 |  | #N/A | #N/A
139 | Market Services _APA Grid Prog | Yes | Other | Non-System | 0 | 0 | 0 | 0 | 0 | 0 |  | #N/A | #N/A
140 | APA Grid Perf & Resil Overhaul | Yes | Other | Non-System | 0 | 0 | 0 | 0 | 0 | 0 |  | #N/A | #N/A
141 | APA Grid & Mrkt Srvs SIB Capex | Yes | Other | Non-System | 0 | 0 | 0 | 0 | 0 | 0 |  | #N/A | #N/A
142 | APA Grid Extend | Yes | Other | Non-System | 0 | 0 | 0 | 0 | 0 | 0 |  | #N/A | #N/A
143 | APA Grid Services Initiatives | Yes | Other | Non-System | 0 | 0 | 0 | 0 | 0 | 0 |  | #N/A | #N/A
144 | CORP SIB16 DANDENONG REFURB | Yes | Other | Non-System | 0 | 0 | 0 | 0 | 0 | 0 |  | #N/A | #N/A
145 | Data Centre | Yes | Other | Non-System | 0 | 0 | 0 | 0 | 0 | 0 |  | #N/A | #N/A
146 | Enterprise Asset Management | Yes | Other | Non-System | 0 | 0 | 0 | 0 | 0 | 0 |  | #N/A | #N/A
147 | Enterprise Content Management | Yes | Other | Non-System | 0 | 0 | 0 | 0 | 0 | 0 |  | #N/A | #N/A
148 | EAM Bus Support & Governance | Yes | Other | Non-System | 0 | 0 | 0 | 0 | 0 | 0 |  | #N/A | #N/A
149 | EAM TRANSMISSION ESTAB WORK | Yes | Other | Non-System | 0 | 0 | 0 | 0 | 0 | 0 |  | #N/A | #N/A
150 | Oracle Integration with EAM | Yes | Other | Non-System | 0 | 0 | 0 | 0 | 0 | 0 |  | #N/A | #N/A
151 | EAM Business Support-Reports | Yes | Other | Non-System | 0 | 0 | 0 | 0 | 0 | 0 |  | #N/A | #N/A
152 | EC Upgrade | Yes | Other | Non-System | 0 | 0 | 0 | 0 | 0 | 0 |  | #N/A | #N/A
153 | Finance Systems | Yes | Other | Non-System | 0 | 0 | 0 | 0 | 0 | 0 |  | #N/A | #N/A
154 | Mobile phone CAPEX purchases | Yes | Other | Non-System | 0 | 0 | 0 | 0 | 0 | 0 |  | #N/A | #N/A
155 | PPOM Phase 2 | Yes | Other | Non-System | 0 | 0 | 0 | 0 | 0 | 0 |  | #N/A | #N/A
156 | Project Server Status Report | Yes | Other | Non-System | 0 | 0 | 0 | 0 | 0 | 0 |  | #N/A | #N/A
157 | BI reporting | Yes | Other | Non-System | 0 | 0 | 0 | 0 | 0 | 0 |  | #N/A | #N/A
158 | PPOM Snapshot Engine | Yes | Other | Non-System | 0 | 0 | 0 | 0 | 0 | 0 |  | #N/A | #N/A
159 | APA Grid Ph.2 | Yes | Other | Non-System | 0 | 0 | 0 | 0 | 0 | 0 |  | #N/A | #N/A
160 | APA Grid Ph. 3 | Yes | Other | Non-System | 0 | 0 | 0 | 0 | 0 | 0 |  | #N/A | #N/A
161 | Vehicle Comms & Journey Mgmt | Yes | Other | Non-System | 0 | 0 | 0 | 0 | 0 | 0 |  | #N/A | #N/A
162 | SCADA Satellite Strategy | Yes | Other | Non-System | 0 | 0 | 0 | 0 | 0 | 0 |  | #N/A | #N/A
163 | SCADA Resilience Project FEED | Yes | Other | Non-System | 0 | 0 | 0 | 0 | 0 | 0 |  | #N/A | #N/A
164 | IOC SCADA GAP ANALYSIS | Yes | Other | Non-System | 0 | 0 | 0 | 0 | 0 | 0 |  | #N/A | #N/A
165 | SCADA Resilience Phase 1 Recom | Yes | Other | Non-System | 0 | 0 | 0 | 0 | 0 | 0 |  | #N/A | #N/A
166 | Melbourne Metro CRE | Yes | Other | Non-System | 0 | 0 | 0 | 0 | 0 | 0 |  | #N/A | #N/A
167 | Adjustments required for differences in CWIP and FAR records | Yes | Other | Non-System | 0 | 0 | 0 | 0 | 0 | 0 |  | #N/A | #N/A
168 | APA Grid | Yes | Other | Non-System | 0 | 0 | 0 | 0 | 0 | 0 |  | #N/A | #N/A
169 | B&T projects | Yes | Other | Non-System | 0 | 0 | 0 | 0 | 0 | 0 |  | #N/A | #N/A
170 | Dandenong Relocation | Yes | Other | Non-System | 0 | 0 | 0 | 0 | 0 | 0 |  | #N/A | #N/A
171 | Victoria CRE | Yes | Other | Non-System | 0 | 0 | 0 | 0 | 0 | 0 |  | #N/A | #N/A
0 | 0 | 0 |  | Replacement | 0 | 0 | 0 | 0 | 0 | 0 |  | #N/A | #N/A
0 | 0 | 0 |  | Replacement | 0 | 0 | 0 | 0 | 0 | 0 |  | #N/A | #N/A
0 | 0 | 0 |  | Replacement | 0 | 0 | 0 | 0 | 0 | 0 |  | #N/A | #N/A
0 | 0 | 0 |  | Replacement | 0 | 0 | 0 | 0 | 0 | 0 |  | #N/A | #N/A
0 | 0 | 0 |  | Replacement | 0 | 0 | 0 | 0 | 0 | 0 |  | #N/A | #N/A
0 | 0 | 0 |  | Replacement | 0 | 0 | 0 | 0 | 0 | 0 |  | #N/A | #N/A
0 | 0 | 0 |  | Replacement | 0 | 0 | 0 | 0 | 0 | 0 |  | #N/A | #N/A
0 | 0 | 0 |  | Replacement | 0 | 0 | 0 | 0 | 0 | 0 |  | #N/A | #N/A
0 | 0 | 0 |  | Replacement | 0 | 0 | 0 | 0 | 0 | 0 |  | #N/A | #N/A
0 | 0 | 0 |  | Replacement | 0 | 0 | 0 | 0 | 0 | 0 |  | #N/A | #N/A
0 | 0 | 0 |  | Replacement | 0 | 0 | 0 | 0 | 0 | 0 |  | #N/A | #N/A
0 | 0 | 0 |  | Replacement | 0 | 0 | 0 | 0 | 0 | 0 |  | #N/A | #N/A
0 | 0 | 0 |  | Replacement | 0 | 0 | 0 | 0 | 0 | 0 |  | #N/A | #N/A
0 | 0 | 0 |  | Replacement | 0 | 0 | 0 | 0 | 0 | 0 |  | #N/A | #N/A
0 | 0 | 0 |  | Replacement | 0 | 0 | 0 | 0 | 0 | 0 |  | #N/A | #N/A
0 | 0 | 0 |  | Replacement | 0 | 0 | 0 | 0 | 0 | 0 |  | #N/A | #N/A
0 | 0 | 0 |  | Replacement | 0 | 0 | 0 | 0 | 0 | 0 |  | #N/A | #N/A
0 | 0 | 0 |  | Replacement | 0 | 0 | 0 | 0 | 0 | 0 |  | #N/A | #N/A
0 | 0 | 0 | 0 | Replacement | 0 | 0 | 0 | 0 | 0 | 0 |  | #N/A | #N/A
0 | 0 | 0 | 0 | Replacement | 0 | 0 | 0 | 0 | 0 | 0 |  | #N/A | #N/A
0 | 0 | 0 | 0 | Replacement | 0 | 0 | 0 | 0 | 0 | 0 |  | #N/A | #N/A
0 | 0 | 0 | 0 | Replacement | 0 | 0 | 0 | 0 | 0 | 0 |  | #N/A | #N/A
0 | 0 | 0 | 0 | Replacement | 0 | 0 | 0 | 0 | 0 | 0 |  | #N/A | #N/A
0 | 0 | 0 | 0 | Replacement | 0 | 0 | 0 | 0 | 0 | 0 |  | #N/A | #N/A
0 | 0 | 0 | 0 | Replacement | 0 | 0 | 0 | 0 | 0 | 0 |  | #N/A | #N/A
0 | 0 | 0 | 0 | Replacement | 0 | 0 | 0 | 0 | 0 | 0 |  | #N/A | #N/A
0 | 0 | 0 | 0 | Replacement | 0 | 0 | 0 | 0 | 0 | 0 |  | #N/A | #N/A
0 | 0 | 0 | 0 | Replacement | 0 | 0 | 0 | 0 | 0 | 0 |  | #N/A | #N/A
0 | 0 | 0 | 0 | Replacement | 0 | 0 | 0 | 0 | 0 | 0 |  | #N/A | #N/A
0 | 0 | 0 | 0 | Replacement | 0 | 0 | 0 | 0 | 0 | 0 |  | #N/A | #N/A
0 | 0 | 0 | 0 | Replacement | 0 | 0 | 0 | 0 | 0 | 0 |  | #N/A | #N/A
0 | 0 | 0 | 0 | Replacement | 0 | 0 | 0 | 0 | 0 | 0 |  | #N/A | #N/A
0 | 0 | 0 | 0 | Replacement | 0 | 0 | 0 | 0 | 0 | 0 |  | #N/A | #N/A
0 | 0 | 0 | 0 | Replacement | 0 | 0 | 0 | 0 | 0 | 0 |  | #N/A | #N/A
0 | 0 | 0 | 0 | Replacement | 0 | 0 | 0 | 0 | 0 | 0 |  | #N/A | #N/A
0 | 0 | 0 | 0 | Replacement | 0 | 0 | 0 | 0 | 0 | 0 |  | #N/A | #N/A
0 | 0 | 0 | 0 | Replacement | 0 | 0 | 0 | 0 | 0 | 0 |  | #N/A | #N/A
0 | 0 | 0 | 0 | Replacement | 0 | 0 | 0 | 0 | 0 | 0 |  | #N/A | #N/A
0 | 0 | 0 | 0 | Replacement | 0 | 0 | 0 | 0 | 0 | 0 |  | #N/A | #N/A
0 | 0 | 0 | 0 | Replacement | 0 | 0 | 0 | 0 | 0 | 0 |  | #N/A | #N/A
0 | 0 | 0 | 0 | Replacement | 0 | 0 | 0 | 0 | 0 | 0 |  | #N/A | #N/A
0 | 0 | 0 | 0 | Replacement | 0 | 0 | 0 | 0 | 0 | 0 |  | #N/A | #N/A
0 | 0 | 0 | 0 | Replacement | 0 | 0 | 0 | 0 | 0 | 0 |  | #N/A | #N/A
0 | 0 | 0 | 0 | Replacement | 0 | 0 | 0 | 0 | 0 | 0 |  | #N/A | #N/A
0 | 0 | 0 | 0 | Replacement | 0 | 0 | 0 | 0 | 0 | 0 |  | #N/A | #N/A
0 | 0 | 0 | 0 | Replacement | 0 | 0 | 0 | 0 | 0 | 0 |  | #N/A | #N/A
0 | 0 | 0 | 0 | Replacement | 0 | 0 | 0 | 0 | 0 | 0 |  | #N/A | #N/A
0 | 0 | 0 | 0 | Replacement | 0 | 0 | 0 | 0 | 0 | 0 |  | #N/A | #N/A
0 | 0 | 0 | 0 | Replacement | 0 | 0 | 0 | 0 | 0 | 0 |  | #N/A | #N/A
0 | 0 | 0 | 0 | Replacement | 0 | 0 | 0 | 0 | 0 | 0 |  | #N/A | #N/A
0 | 0 | 0 | 0 | Replacement | 0 | 0 | 0 | 0 | 0 | 0 |  | #N/A | #N/A
0 | 0 | 0 | 0 | Replacement | 0 | 0 | 0 | 0 | 0 | 0 |  | #N/A | #N/A
0 | 0 | 0 | 0 | Replacement | 0 | 0 | 0 | 0 | 0 | 0 |  | #N/A | #N/A
[12 empty] | #N/A | #N/A

## 4.1 Calc│Hist Act ($nom)
|  |  |  | TRUE | TRUE | TRUE | TRUE | TRUE | Check
4.1 Calc│Hist Act ($nom)
Capex # | Project Name | Class | Category | 2013 | 2014 | 2015 | 2016 | 2017 | Total
1 | Stonehaven CS - now Winchelsea | Compressors | Augmentation | 8134553.96 | 26606375.39 | 2492547.98 | 877.27 | 0 | 37234354.6
2 | Warragul Looping | Pipelines | Augmentation | 0 | 0 | 0 | 0 | 0 | 0
3 | Anglesea Pipeline Extension | Pipelines | Augmentation | 0 | 0 | 0 | 0 | 9267887.2827 | 9267887.2827
4 | Wollert CS A Unit reinstrumentation | Compressors | Replacement | 0 | 0 | 0 | 100000 | 200000 | 300000
5 | BCS Filter | City Gates & Field Regs | Replacement | 0 | 0 | 0 | 0 | 0 | 0
6 | Iona CS - Inlet Pressure Reduction | Compressors | Replacement | 104428.1 | 9056 | 0 | 0 | 0 | 113484.1
7 | Iona CS Control system replacement | Compressors | Replacement | 0 | 0 | 0 | 0 | 0 | 0
8 | SCS Cooler Upgrade | Compressors | Replacement | 0 | 0 | 0 | 0 | 0 | 0
9 | BCS Emergency Lighting | Other | Replacement | 61810.95 | 0 | 0 | 0 | 0 | 61810.95
10 | GCS Emergency Lighting Upgrade | Other | Replacement | 879.8 | 0 | 0 | 0 | 0 | 879.8
11 | Wollert CS Emergency Lighting | Other | Replacement | 0 | 111330.8 | 0 | 0 | 0 | 111330.8
12 | Emergency - fully equipped caravan | Other | Replacement | 0 | 0 | 0 | 0 | 0 | 0
13 | Emergency - Gas blowdown and flaring sytem | Other | Replacement | 0 | 0 | 0 | 0 | 0 | 0
14 | Emergency - refurbish and re-testing of pipes | Other | Replacement | 0 | 40300 | 0 | 0 | 0 | 40300
15 | Emergency - SMR radio upgrade | Other | Replacement | 0 | 0 | 0 | 0 | 0 | 0
16 | Emergency BA escape sets | Other | Replacement | 0 | 0 | 0 | 0 | 0 | 0
17 | Emergency diesel fuel storage | Other | Replacement | 0 | 0 | 0 | 0 | 0 | 0
18 | Emergency Plidco fittings - Sleeve vent | Pipelines | Replacement | 0 | 0 | 0 | 0 | 70000 | 70000
19 | Emergency Response Equipment | Other | Replacement | 0 | 14416.72 | 38911 | 30323.6 | 0 | 83651.32
20 | Emergency Spark Proof tools | Other | Replacement | 0 | 0 | 0 | 0 | 20000 | 20000
21 | Purchase and replacement of emergency fittings and Equipment | Other | Replacement | 59521.63 | 173679.9 | 0 | 0 | 0 | 233201.53
22 | Facilities Communication Systems Upgrade | Other | Replacement | 0 | 16081.25 | 0 | 0 | 0 | 16081.25
23 | GCS Station Valve Upgrade | Compressors | Replacement | 922.2 | 94508.09 | 0 | 0 | 0 | 95430.29
24 | GCS Unit 3 Turbine Overhaul | Compressors | Replacement | 0 | 0 | 0 | 0 | 0 | 0
25 | SMS - Compressor station vents-Various | Compressors | Replacement | 0 | 0 | 0 | 0 | 0 | 0
26 | AS 2885 Design Life reviews of Facilities&Pipelines | City Gates & Field Regs | Replacement | 890.75 | 142234.07 | 54126.05 | 63973.92 | 50000 | 311224.79
27 | BCG Un-regulated Bypass Upgrade | City Gates & Field Regs | Replacement | 0 | 0 | 0 | 0 | 0 | 0
28 | Dandenong CG gas heater | City Gates & Field Regs | Replacement | 0 | 0 | 0 | 0 | 0 | 0
29 | Hazardous Area Rectification | City Gates & Field Regs | Replacement | 10313.6 | 32182.3 | 134741.2 | 162983.16 | 100000 | 440220.26
30 | Hazardous Areas Review | City Gates & Field Regs | Replacement | 34062.33 | 0 | 0 | 0 | 0 | 34062.33
31 | Heater upgrade - Laverton North CG | City Gates & Field Regs | Replacement | 5671 | 0 | 0 | 0 | 0 | 5671
32 | Odorant Dandenong Pump Upgrade 700 & 2800 kPa | Gas Quality | Replacement | 0 | 0 | 285847.41 | 6015.5 | 0 | 291862.91
33 | Regulator upgrade - Dandenong City Gate (exclude filters) | City Gates & Field Regs | Replacement | 479498.96 | 2616566.96 | 7811136.25 | 750463.8 | 0 | 11657665.97
34 | Valve - Pipeline LNG plant Isolation Valve Actuator Replacement | City Gates & Field Regs | Replacement | 67874.3 | 307062.84 | 0 | -0.02 | 0 | 374937.12
35 | Valve - Pipeline to LNG plant UV325 valve replacement and loading valve | City Gates & Field Regs | Replacement | 67319.22 | 210131.45 | 0 | 0 | 0 | 277450.67
36 | Valve - Corio CG Un-regulated Bypass Upgrade | City Gates & Field Regs | Replacement | 0 | 0 | 0 | 0 | 0 | 0
37 | Valve - Tyers Branch Valve Actuator Replacement | Pipelines | Replacement | 0 | 0 | 0 | 0 | 0 | 0
38 | Valve - UniBolt Phase 3 Replacement | City Gates & Field Regs | Replacement | 1130.5 | 92576.04 | 30257.33 | 53832.91 | 100000 | 277796.78
39 | Pig Trap - Enclosure upgrade | City Gates & Field Regs | Replacement | 0 | 0 | 17709 | 84557.63 | 25000 | 127266.63
40 | Pig Trap - Pipe Support Upgrade | City Gates & Field Regs | Replacement | 174 | 63266.31 | 250206.75 | 24895.18 | 25000 | 363542.24
41 | BCS Administration Building Distribution Board Upgrade | Compressors | Non-System | 0 | -52 | 0 | 30000 | 0 | 29948
42 | Equipment - Field Equipment | Other | Non-System | 78414.37 | 33433 | 0 | 0 | 10000 | 121847.37
43 | Equipment - Gas Detectors | Other | Non-System | 0 | 0 | 0 | 0 | 10000 | 10000
44 | Equipment - IT Purchases | Other | Non-System | 28090.5164 | 85086.328 | 94876.5278 | 59503.3603 | 0 | 267556.7325
45 | Equipment - Test | Other | Non-System | 0 | 0 | 0 | 0 | 0 | 0
46 | Equipment - Victorian low value pool purchases | Other | Non-System | 52890.5047 | 215346.1091 | 550230.7606 | 163384.2868 | 28230 | 1010081.6612
47 | Dandenong 180 Greens Road Office Redevelopment | Buildings | Non-System | 0 | 0 | 0 | 0 | 0 | 0
48 | Dandenong Asphalt Resurfacing | Other | Non-System | 0 | 0 | 0 | 0 | 0 | 0
49 | Dandenong Complex asbestos removal | Buildings | Non-System | 0 | 60923.51 | 0 | 0 | 0 | 60923.51
50 | Dandenong external surface repainting | Buildings | Non-System | 0 | 0 | 0 | 0 | 0 | 0
51 | Dandenong Office Purchases | Other | Non-System | 8861.6981 | 34769.95 | 31686.2177 | 0 | 0 | 75317.8658
52 | Dandenong Site - Storage shed | Buildings | Non-System | 11857.7292 | 66978.2157 | 0 | 0 | 0 | 78835.9449
53 | Pigging - Tracking and locating tools | Other | Non-System | 0 | 0 | 0 | 0 | 0 | 0
54 | Pigging - Two portable liquid collectors for pigging | Other | Non-System | 0 | 0 | 0 | 0 | 0 | 0
55 | Pigging -Two portable dust collectors for pigging | Other | Replacement | 0 | 0 | 0 | 0 | 0 | 0
56 | Control Room - Additonal OE monitor | Other | Replacement | 0 | 0 | 0 | 0 | 0 | 0
57 | SCADA - Comms upgrade to IP network-VTS only | Other | Non-System | 0 | 0 | 0 | 55925 | 1000000 | 1055925
58 | SCADA - IT security | Other | Non-System | 0 | 0 | 0 | 0 | 0 | 0
59 | SCADA - Remote maintenance and engineering workstations [Control Room, Gooding, Brooklyn CS&CG, Wollert CS&CG, Springhurst, Iona] | Other | Replacement | 0 | 0 | 0 | 0 | 0 | 0
60 | SCADA - RTU/ PLC/HMI Development and Test bench [PC, iFix, Control Logix, Bristol Designer Tools] | Other | Replacement | 0 | 0 | 0 | 0 | 0 | 0
61 | SCADA System Upgrade | Other | Non-System | 0 | 0 | 25383.25 | 113039.53 | 450000 | 588422.78
62 | Dandenong Building exterior coatings | Buildings | Replacement | 0 | 0 | 0 | 0 | 0 | 0
63 | Dandenong site fire mains replacement | Buildings | Non-System | 4961.3378 | 88164.1814 | 1020411.517 | 30176.035 | 47050 | 1190763.0712
64 | Brooklyn guttering | Buildings | Non-System | 0 | 0 | 0 | 0 | 0 | 0
65 | Wollert Control Room guttering | Buildings | Non-System | 0 | 0 | 0 | 0 | 0 | 0
66 | Corporate IT | Other | Non-System | 211241.5961 | 302736.8717 | 276048.921 | 374324.3473 | 209022 | 1373373.7361
67 | Liquid management - Brooklyn | City Gates & Field Regs | Replacement | 0 | 0 | 0 | 0 | 0 | 0
68 | Liquid management - Gooding | City Gates & Field Regs | Replacement | 0 | 0 | 0 | 0 | 0 | 0
69 | Liquid management - Longford | City Gates & Field Regs | Replacement | -4131.05 | 0 | 0 | 0 | 0 | -4131.05
70 | Liquid Management - Pakenham | City Gates & Field Regs | Replacement | 0 | 0 | 0 | 0 | 0 | 0
71 | CP - Cathodic Protection Replacement | Pipelines | Replacement | 18725 | 98704 | 20000 | 89800 | 50000 | 277229
72 | CP - Corrosion Protection Testing Equipment | Other | Replacement | 0 | 0 | 0 | 47690 | 0 | 47690
73 | Pig Trap - A Branch Valve on Pipeline 108 to Newport Install(124) | Pipelines | Replacement | 0 | 0 | 20098.4 | 868819.02 | 0 | 888917.42
74 | Pig Trap - Dandenong to Princes Highway Pipeline Install (129) | City Gates & Field Regs | Replacement | 0 | 0 | 31113.5 | 350723.48 | 0 | 381836.98
75 | Pig Trap - Laverton North to Laverton North Pipeline Install (162) | City Gates & Field Regs | Replacement | 0 | 0 | 0 | 0 | 0 | 0
76 | Pig Trap - Pakenham to Pakenham Pipeline Install (68) | City Gates & Field Regs | Replacement | 0 | 0 | 0 | 0 | 0 | 0
77 | Pigging Program (T1 Dandenong - Morwell) | Other | Replacement | 0 | 0 | 0 | 0 | 0 | 0
78 | Pigging Program (T56 Brooklyn - Ballan) | Other | Replacement | 0 | 0 | 140780.29 | 307245.02 | 0 | 448025.31
79 | Pigging Program (T59 Euro - Kyabram) | Other | Replacement | 0 | 0 | 0 | 0 | 0 | 0
80 | Pigging Program (T67 Guilford - Maryborough) | Other | Replacement | 0 | 0 | 0 | 0 | 0 | 0
81 | Pigging Program (T74 Keon Park - Wollert) | Other | Replacement | 5363.81 | 616839.03 | 37257.13 | 41434.17 | 0 | 700894.14
82 | Pigging Program (T92 Iona - Brooklyn) | Other | Replacement | 0 | 0 | 67224.28 | 486847.34 | 100000 | 654071.62
83 | Pig Trap - Princes Highway to Regent Street Pipeline Install(36) | City Gates & Field Regs | Replacement | 0 | 0 | 17158.9 | 7880.2 | 0 | 25039.1
84 | Pig Trap - Somerton to Somerton Pipeline Install (238) | City Gates & Field Regs | Replacement | 0 | 1590 | 24041.28 | 3716.12 | 0 | 29347.4
85 | Pig Trap - Tyers to Maryvale Pipeline Install (67) | City Gates & Field Regs | Replacement | 0 | 0 | 0 | 0 | 0 | 0
86 | Exposed pipe coating refurbishment | Pipelines | Replacement | 0 | 0 | 0 | 0 | 0 | 0
87 | BCS Safety and Process Control System and RTU Upgrade | Compressors | Replacement | 23570.02 | 15134.58 | 12066 | 0 | 0 | 50770.6
88 | CS Type B compliance upgrade | Compressors | Replacement | 0 | 0 | 1070 | 230475.43 | 100000 | 331545.43
89 | GCS GEA Fuel Gas Upgrade | Compressors | Replacement | 0 | 0 | 0 | 61409.78 | 0 | 61409.78
90 | GCS Units 1,2,3&4 Suction/Discharge Actuated Valve Replacement | Compressors | Replacement | 0 | 0 | 0 | 218 | 300000 | 300218
91 | Mothball WCS station 'A' | Compressors | Replacement | 0 | 0 | 0 | 0 | 0 | 0
92 | Regulator Upgrade - Lara pneumatic control system upgrade | City Gates & Field Regs | Replacement | 0 | 0 | 5301 | 0 | 160000 | 165301
93 | Security - High Risk sites security upgrade | Other | Replacement | 17837.72 | 24900 | 0 | 0 | 150000 | 192737.72
94 | Security - Small Site Facilities Fencing Upgrade | Other | Replacement | 0 | 0 | 0 | 0 | 0 | 0
95 | Zonal Chromatograph Bottle Regulator Panels Upgrades | Gas Quality | Replacement | 0 | 0 | 0 | 0 | 0 | 0
96 | Zonal Chromatograph Insertion Probes | Gas Quality | Replacement | 0 | 0 | 0 | 10000 | 50000 | 60000
97 | Zonal Chromatograph Upgrades | Gas Quality | Replacement | 0 | 91009.78 | 0 | 334933 | 0 | 425942.78
98 | RTU & Control System Upgrade - Facilities | Other | Replacement | 98368.47 | 100004.42 | 8235.2 | 131637.03 | 150000 | 488245.12
99 | GCS Anti-Surge & Fast-Stop Valves Upgrade | Compressors | Replacement | 0 | 0 | 10038.5 | 497302.54 | 365000 | 872341.04
100 | GCS Control Room Fire Suppression System | Compressors | Replacement | 0 | 0 | 0 | 0 | 0 | 0
101 | GCS Units 1,2,3&4 Fire Suppression System | Compressors | Replacement | 0 | 0 | 0 | 0 | 0 | 0
102 | Iona CS - Unit Fire Suppression System | Compressors | Replacement | 0 | 0 | 0 | 0 | 0 | 0
103 | Wollert CG Control Hut Fire Suppression System | Compressors | Replacement | 0 | 0 | 0 | 80000 | 0 | 80000
104 | Wollert CS A/B Control Room Fire Suppression System | Compressors | Replacement | 0 | 0 | 0 | 120000 | 0 | 120000
105 | BCG Control Hut Fire Suppression System | City Gates & Field Regs | Replacement | 0 | 0 | 0 | 0 | 0 | 0
106 | Valve - Actuate MLV's in T1 areas | Pipelines | Replacement | 0 | 0 | 0 | 10534 | 90000 | 100534
107 | Valve - Longford to Dandenong LV10 Vent Stack | Pipelines | Replacement | 34177.3 | 39851.75 | 0 | 0 | 0 | 74029.05
108 | BCS Station Isolation and Loading Valves | Compressors | Replacement | 2244.6 | 16577.75 | 183683.64 | 1610455.53 | 0 | 1812961.52
109 | Iona CS - Capacity Aftercooler upgrade | Compressors | Replacement | 0 | 0 | 0 | 0 | 0 | 0
110 | BCS DEA Upgrade | Compressors | Replacement | 1160 | 17428 | 0 | 316977 | 0 | 335565
111 | Pig Trap - Keon Park Install | City Gates & Field Regs | Replacement | 325106.72 | 1640823.98 | 0 | 0 | 0 | 1965930.7
112 | BCS Replacement of FSV, ASV & Other Valves | Compressors | Replacement | 0 | 0 | 0 | 0 | 0 | 0
113 | BCS Unit 10 & 11 Cooler Upgrade | Compressors | Replacement | 27089.84 | 889622.65 | 5007242.54 | 3272234.09 | 0 | 9196189.12
114 | SMS - GIS & Aerial Photography | Pipelines | Replacement | 0 | 0 | 87 | 144969.5 | 0 | 145056.5
115 | Wollert to Clonbinane Looping | Pipelines | Augmentation | 4006990.75 | 85648927.66 | 65640112.89 | 635203.41 | 0 | 155931234.71
116 | MAOP Upgrade - Euroa to Springhurst (pipe) | Pipelines | Augmentation | 0 | 0 | 0 | 0 | 0 | 0
117 | MAOP Upgrade - Euroa to Springhurst (Reg) | City Gates & Field Regs | Augmentation | 0 | 0 | 0 | 0 | 0 | 0
118 | Valve - T60 Longford - Dandenong Upgrade hydraulic hand pump of actuators | Other | Replacement | 0 | 0 | 0 | 0 | 0 | 0
119 | VTS - BROOKLYN LARA LOOP | Pipelines | Replacement | 0 | 0 | 0 | 0 | 0 | 0
120 | VTS - WOLLERT 4 & 5 CAPEX | Compressors | Replacement | 3203.9 | 5158.96 | 0 | 0 | 0 | 8362.86
121 | VTS - MORWELL TYERS UPGRADE | City Gates & Field Regs | Replacement | 6147.52 | 0 | 0 | 0 | 0 | 6147.52
122 | VTS - MAOP UPGRADE CAPEX | City Gates & Field Regs | Replacement | 0 | -42.39 | 0 | 0 | 0 | -42.39
123 | VTS - BBP & BCP CG UPGRADE | City Gates & Field Regs | Replacement | 0 | 0 | 0 | 0 | 0 | 0
124 | VTS - BRANCH VALVE CASTLEMAINE | Pipelines | Replacement | 0 | 0 | 0 | 0 | 0 | 0
125 | VTS - EUROA CS NEW (PPOM) | Compressors | Augmentation | 116664.37 | 121805.28 | 59020.54 | -2941.24 | 0 | 294548.95
126 | VTS - SUNBURY PIPE LOOP (NEW) | Pipelines | Augmentation | 51715.09 | 38571.05 | 5019.95 | 4029.08 | 0 | 99335.17
127 | VTS - BCS 8&9 COOLERS UPG (NEW | Compressors | Replacement | -12591.73 | 22820.08 | 0 | 0 | 0 | 10228.35
128 | VTS - BCS 12 FAST STOP VALVE | Compressors | Replacement | 0 | 0 | 0 | 0 | 0 | 0
129 | VTS - BCS 8 & 9 UNIT VALVES | Compressors | Replacement | 0 | 0 | 0 | 0 | 0 | 0
130 | PIGGING T91 CURDIEVALE | Other | Replacement | 0 | 17873 | 0 | 0 | 0 | 17873
131 | VTS - BROOKLYN FIRE SERVICE | Buildings | Non-System | 29482.73 | 11269.5 | 0 | 0 | 0 | 40752.23
132 | VTS - BCS LUBE OIL COOLER 8&9 | City Gates & Field Regs | Replacement | 109672.54 | 0 | 0 | 0 | 0 | 109672.54
133 | VNIE Looping 6 to 8 | Pipelines | Augmentation | 0 | 0 | 6392032.4513 | 91499230.4789 | 43063099.4902 | 140954362.4203
134 | VTS16.SIB42 WOLL SOFT STARTERS | Other | Replacement | 0 | 0 | 0 | 30881 | 0 | 30881
135 | VTS.SIB99 WCS STN-A DISCHRG LQ | Other | Replacement | 0 | 0 | 0 | 190850.4 | 0 | 190850.4
136 | VTS17.SIB27 SCS CR EPS REMOVAL | Buildings | Non-System | 0 | 0 | 0 | 2856.8 | 0 | 2856.8
137 | VTS17.SIB30 DND EMERG ENTRANCE | Buildings | Non-System | 0 | 0 | 0 | 23849.55 | 0 | 23849.55
138 | Corporate other | Other | Non-System | 242365.2632 | 340342.973 | 308327.8805 | 17522.8525 | 0 | 908558.9692
139 | Market Services _APA Grid Prog | Other | Non-System | 0 | 0 | 153669.9247 | 156678.9204 | 0 | 310348.845
140 | APA Grid Perf & Resil Overhaul | Other | Non-System | 0 | 0 | 44725.1667 | 22022.8998 | 0 | 66748.0665
141 | APA Grid & Mrkt Srvs SIB Capex | Other | Non-System | 0 | 0 | 0 | 458.3444 | 0 | 458.3444
142 | APA Grid Extend | Other | Non-System | 0 | 0 | 0 | 67569.955 | 0 | 67569.955
143 | APA Grid Services Initiatives | Other | Non-System | 0 | 0 | 0 | 111589.8195 | 0 | 111589.8195
144 | CORP SIB16 DANDENONG REFURB | Other | Non-System | 0 | 0 | 303211.3819 | 3462.88 | 0 | 306674.2619
145 | Data Centre | Other | Non-System | 65362.0189 | 895833.2344 | 79250.1745 | 0 | 0 | 1040445.4278
146 | Enterprise Asset Management | Other | Non-System | 806330.3274 | 1986550.9701 | 2564771.5454 | 1771.8759 | 0 | 5359424.7188
147 | Enterprise Content Management | Other | Non-System | 0 | 0 | 104729.0841 | 325950.5132 | 512309 | 942988.5973
148 | EAM Bus Support & Governance | Other | Non-System | 0 | 0 | 0 | 42640.3455 | 0 | 42640.3455
149 | EAM TRANSMISSION ESTAB WORK | Other | Non-System | 0 | 0 | 0 | 160167.1738 | 0 | 160167.1738
150 | Oracle Integration with EAM | Other | Non-System | 0 | 0 | 0 | 10956.5236 | 0 | 10956.5236
151 | EAM Business Support-Reports | Other | Non-System | 0 | 0 | 0 | 3457.1067 | 0 | 3457.1067
152 | EC Upgrade | Other | Non-System | 0 | 0 | 0 | 185722.3966 | 0 | 185722.3966
153 | Finance Systems | Other | Non-System | 1751.8135 | 0 | 0 | 0 | 0 | 1751.8135
154 | Mobile phone CAPEX purchases | Other | Non-System | 0 | 22811.9773 | 27279.5795 | 28375.3809 | 0 | 78466.9376
155 | PPOM Phase 2 | Other | Non-System | 5453.1938 | 0 | 0 | 0 | 0 | 5453.1938
156 | Project Server Status Report | Other | Non-System | 7605.6406 | 4061.9411 | 0 | 0 | 0 | 11667.5817
157 | BI reporting | Other | Non-System | 33318.3814 | 2571.9179 | 0 | 0 | 0 | 35890.2993
158 | PPOM Snapshot Engine | Other | Non-System | 9285.9184 | 12608.9365 | 0 | 0 | 0 | 21894.8549
159 | APA Grid Ph.2 | Other | Non-System | 135912.9265 | 98899.2122 | 0 | 0 | 0 | 234812.1387
160 | APA Grid Ph. 3 | Other | Non-System | 2637.3633 | 0 | 0 | 0 | 0 | 2637.3633
161 | Vehicle Comms & Journey Mgmt | Other | Non-System | 0 | 2091.1818 | 85100.7826 | 154249.1835 | 0 | 241441.1479
162 | SCADA Satellite Strategy | Other | Non-System | 0 | 0 | 37193.7062 | 61169.9502 | 0 | 98363.6564
163 | SCADA Resilience Project FEED | Other | Non-System | 0 | 0 | 0 | 19777.1403 | 0 | 19777.1403
164 | IOC SCADA GAP ANALYSIS | Other | Non-System | 0 | 0 | 0 | 4246.8422 | 0 | 4246.8422
165 | SCADA Resilience Phase 1 Recom | Other | Non-System | 0 | 0 | 0 | 4887.8165 | 0 | 4887.8165
166 | Melbourne Metro CRE | Other | Non-System | 0 | 0 | 0 | 295817.7849 | 0 | 295817.7849
167 | Adjustments required for differences in CWIP and FAR records | Other | Non-System | 0 | -26601 | 23200 | -178445 | 0 | -181846
168 | APA Grid | Other | Non-System | 0 | 0 | 0 | 0 | 261222 | 261222
169 | B&T projects | Other | Non-System | 0 | 0 | 0 | 0 | 598799 | 598799
170 | Dandenong Relocation | Other | Non-System | 0 | 0 | 0 | 0 | 5057812 | 5057812
171 | Victoria CRE | Other | Non-System | 0 | 0 | 0 | 0 | 366376 | 366376
0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## 4.2 Calc│Hist Com ($nom)
[5 empty] | FALSE | FALSE | FALSE | FALSE | FALSE |  | Check
4.2 Calc│Hist Com ($nom)
Capex # | Project Name | Class | Category | Commissioned | 2013 | 2014 | 2015 | 2016 | 2017 | 2018 | Total (13-17)
1 | Stonehaven CS - now Winchelsea | Compressors | Augmentation | 2015 | 0 | 0 | 37234354.6 | 0 | 0 | 0 | 37234354.6
2 | Warragul Looping | Pipelines | Augmentation | Incurred | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | Anglesea Pipeline Extension | Pipelines | Augmentation | 2018 | 0 | 0 | 0 | 0 | 0 | 9267887.2827 | 0
4 | Wollert CS A Unit reinstrumentation | Compressors | Replacement | 2017 | 0 | 0 | 0 | 0 | 300000 | 0 | 300000
5 | BCS Filter | City Gates & Field Regs | Replacement | Incurred | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | Iona CS - Inlet Pressure Reduction | Compressors | Replacement | Incurred | 104428.1 | 9056 | 0 | 0 | 0 | 0 | 113484.1
7 | Iona CS Control system replacement | Compressors | Replacement | Incurred | 0 | 0 | 0 | 0 | 0 | 0 | 0
8 | SCS Cooler Upgrade | Compressors | Replacement | Incurred | 0 | 0 | 0 | 0 | 0 | 0 | 0
9 | BCS Emergency Lighting | Other | Replacement | 2013 | 61810.95 | 0 | 0 | 0 | 0 | 0 | 61810.95
10 | GCS Emergency Lighting Upgrade | Other | Replacement | 2013 | 879.8 | 0 | 0 | 0 | 0 | 0 | 879.8
11 | Wollert CS Emergency Lighting | Other | Replacement | 2014 | 0 | 111330.8 | 0 | 0 | 0 | 0 | 111330.8
12 | Emergency - fully equipped caravan | Other | Replacement | Incurred | 0 | 0 | 0 | 0 | 0 | 0 | 0
13 | Emergency - Gas blowdown and flaring sytem | Other | Replacement | Incurred | 0 | 0 | 0 | 0 | 0 | 0 | 0
14 | Emergency - refurbish and re-testing of pipes | Other | Replacement | Incurred | 0 | 40300 | 0 | 0 | 0 | 0 | 40300
15 | Emergency - SMR radio upgrade | Other | Replacement | Incurred | 0 | 0 | 0 | 0 | 0 | 0 | 0
16 | Emergency BA escape sets | Other | Replacement | Incurred | 0 | 0 | 0 | 0 | 0 | 0 | 0
17 | Emergency diesel fuel storage | Other | Replacement | Incurred | 0 | 0 | 0 | 0 | 0 | 0 | 0
18 | Emergency Plidco fittings - Sleeve vent | Pipelines | Replacement | 2017 | 0 | 0 | 0 | 0 | 70000 | 0 | 70000
19 | Emergency Response Equipment | Other | Replacement | Incurred | 0 | 14416.72 | 38911 | 30323.6 | 0 | 0 | 83651.32
20 | Emergency Spark Proof tools | Other | Replacement | 2017 | 0 | 0 | 0 | 0 | 20000 | 0 | 20000
21 | Purchase and replacement of emergency fittings and Equipment | Other | Replacement | 2014 | 0 | 233201.53 | 0 | 0 | 0 | 0 | 233201.53
22 | Facilities Communication Systems Upgrade | Other | Replacement | 2014 | 0 | 16081.25 | 0 | 0 | 0 | 0 | 16081.25
23 | GCS Station Valve Upgrade | Compressors | Replacement | 2014 | 0 | 95430.29 | 0 | 0 | 0 | 0 | 95430.29
24 | GCS Unit 3 Turbine Overhaul | Compressors | Replacement | Incurred | 0 | 0 | 0 | 0 | 0 | 0 | 0
25 | SMS - Compressor station vents-Various | Compressors | Replacement | Incurred | 0 | 0 | 0 | 0 | 0 | 0 | 0
26 | AS 2885 Design Life reviews of Facilities&Pipelines | City Gates & Field Regs | Replacement | Incurred | 890.75 | 142234.07 | 54126.05 | 63973.92 | 50000 | 0 | 311224.79
27 | BCG Un-regulated Bypass Upgrade | City Gates & Field Regs | Replacement | Incurred | 0 | 0 | 0 | 0 | 0 | 0 | 0
28 | Dandenong CG gas heater | City Gates & Field Regs | Replacement | Incurred | 0 | 0 | 0 | 0 | 0 | 0 | 0
29 | Hazardous Area Rectification | City Gates & Field Regs | Replacement | Incurred | 10313.6 | 32182.3 | 134741.2 | 162983.16 | 100000 | 0 | 440220.26
30 | Hazardous Areas Review | City Gates & Field Regs | Replacement | Incurred | 34062.33 | 0 | 0 | 0 | 0 | 0 | 34062.33
31 | Heater upgrade - Laverton North CG | City Gates & Field Regs | Replacement | 2013 | 5671 | 0 | 0 | 0 | 0 | 0 | 5671
32 | Odorant Dandenong Pump Upgrade 700 & 2800 kPa | Gas Quality | Replacement | Incurred | 0 | 0 | 285847.41 | 6015.5 | 0 | 0 | 291862.91
33 | Regulator upgrade - Dandenong City Gate (exclude filters) | City Gates & Field Regs | Replacement |  | 0 | 0 | 10907202.17 | 750463.8 | 0 | 0 | 11657665.97
34 | Valve - Pipeline LNG plant Isolation Valve Actuator Replacement | City Gates & Field Regs | Replacement | 2014 | 0 | 374937.12 | 0 | 0 | 0 | 0 | 374937.12
35 | Valve - Pipeline to LNG plant UV325 valve replacement and loading valve | City Gates & Field Regs | Replacement | 2014 | 0 | 277450.67 | 0 | 0 | 0 | 0 | 277450.67
36 | Valve - Corio CG Un-regulated Bypass Upgrade | City Gates & Field Regs | Replacement | Incurred | 0 | 0 | 0 | 0 | 0 | 0 | 0
37 | Valve - Tyers Branch Valve Actuator Replacement | Pipelines | Replacement | Incurred | 0 | 0 | 0 | 0 | 0 | 0 | 0
38 | Valve - UniBolt Phase 3 Replacement | City Gates & Field Regs | Replacement | Incurred | 1130.5 | 92576.04 | 30257.33 | 53832.91 | 100000 | 0 | 277796.78
39 | Pig Trap - Enclosure upgrade | City Gates & Field Regs | Replacement |  | 0 | 0 | 0 | 102266.63 | 25000 | 0 | 127266.63
40 | Pig Trap - Pipe Support Upgrade | City Gates & Field Regs | Replacement | Incurred | 174 | 63266.31 | 250206.75 | 24895.18 | 25000 | 0 | 363542.24
41 | BCS Administration Building Distribution Board Upgrade | Compressors | Replacement | 2018 | 0 | 0 | 0 | 0 | 0 | 29948 | 0
42 | Equipment - Field Equipment | Other | Non-System | Incurred | 78414.37 | 33433 | 0 | 0 | 10000 | 0 | 121847.37
43 | Equipment - Gas Detectors | Other | Non-System | Incurred | 0 | 0 | 0 | 0 | 10000 | 0 | 10000
44 | Equipment - IT Purchases | Other | Non-System | Incurred | 28090.5164 | 85086.328 | 94876.5278 | 59503.3603 | 0 | 0 | 267556.7325
45 | Equipment - Test | Other | Non-System | Incurred | 0 | 0 | 0 | 0 | 0 | 0 | 0
46 | Equipment - Victorian low value pool purchases | Other | Non-System | Incurred | 52890.5047 | 215346.1091 | 550230.7606 | 163384.2868 | 28230 | 0 | 1010081.6612
47 | Dandenong 180 Greens Road Office Redevelopment | Buildings | Non-System | Incurred | 0 | 0 | 0 | 0 | 0 | 0 | 0
48 | Dandenong Asphalt Resurfacing | Other | Non-System | Incurred | 0 | 0 | 0 | 0 | 0 | 0 | 0
49 | Dandenong Complex asbestos removal | Buildings | Non-System | 2014 | 0 | 60923.51 | 0 | 0 | 0 | 0 | 60923.51
50 | Dandenong external surface repainting | Buildings | Non-System | Incurred | 0 | 0 | 0 | 0 | 0 | 0 | 0
51 | Dandenong Office Purchases | Other | Non-System | Incurred | 8861.6981 | 34769.95 | 31686.2177 | 0 | 0 | 0 | 75317.8658
52 | Dandenong Site - Storage shed | Buildings | Non-System | 2014 | 0 | 78835.9449 | 0 | 0 | 0 | 0 | 78835.9449
53 | Pigging - Tracking and locating tools | Other | Non-System | Incurred | 0 | 0 | 0 | 0 | 0 | 0 | 0
54 | Pigging - Two portable liquid collectors for pigging | Other | Non-System | Incurred | 0 | 0 | 0 | 0 | 0 | 0 | 0
55 | Pigging -Two portable dust collectors for pigging | Other | Replacement | Incurred | 0 | 0 | 0 | 0 | 0 | 0 | 0
56 | Control Room - Additonal OE monitor | Other | Replacement | Incurred | 0 | 0 | 0 | 0 | 0 | 0 | 0
57 | SCADA - Comms upgrade to IP network-VTS only | Other | Replacement | Incurred | 0 | 0 | 0 | 55925 | 1000000 | 0 | 1055925
58 | SCADA - IT security | Other | Non-System | Incurred | 0 | 0 | 0 | 0 | 0 | 0 | 0
59 | SCADA - Remote maintenance and engineering workstations [Control Room, Gooding, Brooklyn CS&CG, Wollert CS&CG, Springhurst, Iona] | Other | Replacement | Incurred | 0 | 0 | 0 | 0 | 0 | 0 | 0
60 | SCADA - RTU/ PLC/HMI Development and Test bench [PC, iFix, Control Logix, Bristol Designer Tools] | Other | Replacement | Incurred | 0 | 0 | 0 | 0 | 0 | 0 | 0
61 | SCADA System Upgrade | Other | Replacement | Incurred | 0 | 0 | 25383.25 | 113039.53 | 450000 | 0 | 588422.78
62 | Dandenong Building exterior coatings | Buildings | Replacement | Incurred | 0 | 0 | 0 | 0 | 0 | 0 | 0
63 | Dandenong site fire mains replacement | Buildings | Replacement |  | 0 | 0 | 1113537.0362 | 30176.035 | 0 | 0 | 1143713.0712
64 | Brooklyn guttering | Buildings | Non-System | Incurred | 0 | 0 | 0 | 0 | 0 | 0 | 0
65 | Wollert Control Room guttering | Buildings | Non-System | Incurred | 0 | 0 | 0 | 0 | 0 | 0 | 0
66 | Corporate IT | Other | Non-System | Incurred | 211241.5961 | 302736.8717 | 276048.921 | 374324.3473 | 209022 | 0 | 1373373.7361
67 | Liquid management - Brooklyn | City Gates & Field Regs | Replacement | Incurred | 0 | 0 | 0 | 0 | 0 | 0 | 0
68 | Liquid management - Gooding | City Gates & Field Regs | Replacement | Incurred | 0 | 0 | 0 | 0 | 0 | 0 | 0
69 | Liquid management - Longford | City Gates & Field Regs | Replacement | Incurred | -4131.05 | 0 | 0 | 0 | 0 | 0 | -4131.05
70 | Liquid Management - Pakenham | City Gates & Field Regs | Replacement | Incurred | 0 | 0 | 0 | 0 | 0 | 0 | 0
71 | CP - Cathodic Protection Replacement | Pipelines | Replacement | Incurred | 18725 | 98704 | 20000 | 89800 | 50000 | 0 | 277229
72 | CP - Corrosion Protection Testing Equipment | Other | Replacement | Incurred | 0 | 0 | 0 | 47690 | 0 | 0 | 47690
73 | Pig Trap - A Branch Valve on Pipeline 108 to Newport Install(124) | Pipelines | Replacement | 2018 | 0 | 0 | 0 | 0 | 0 | 888917.42 | 0
74 | Pig Trap - Dandenong to Princes Highway Pipeline Install (129) | City Gates & Field Regs | Replacement | 2017 | 0 | 0 | 0 | 0 | 381836.98 | 0 | 381836.98
75 | Pig Trap - Laverton North to Laverton North Pipeline Install (162) | City Gates & Field Regs | Replacement | Incurred | 0 | 0 | 0 | 0 | 0 | 0 | 0
76 | Pig Trap - Pakenham to Pakenham Pipeline Install (68) | City Gates & Field Regs | Replacement | Incurred | 0 | 0 | 0 | 0 | 0 | 0 | 0
77 | Pigging Program (T1 Dandenong - Morwell) | Other | Replacement | Incurred | 0 | 0 | 0 | 0 | 0 | 0 | 0
78 | Pigging Program (T56 Brooklyn - Ballan) | Other | Replacement | 2017 | 0 | 0 | 0 | 0 | 448025.31 | 0 | 448025.31
79 | Pigging Program (T59 Euro - Kyabram) | Other | Replacement | Incurred | 0 | 0 | 0 | 0 | 0 | 0 | 0
80 | Pigging Program (T67 Guilford - Maryborough) | Other | Replacement | Incurred | 0 | 0 | 0 | 0 | 0 | 0 | 0
81 | Pigging Program (T74 Keon Park - Wollert) | Other | Replacement | Incurred | 0 | 622202.84 | 37257.13 | 41434.17 | 0 | 0 | 700894.14
82 | Pigging Program (T92 Iona - Brooklyn) | Other | Replacement | 2017 | 0 | 0 | 0 | 0 | 654071.62 | 0 | 654071.62
83 | Pig Trap - Princes Highway to Regent Street Pipeline Install(36) | City Gates & Field Regs | Replacement | 2016 | 0 | 0 | 0 | 25039.1 | 0 | 0 | 25039.1
84 | Pig Trap - Somerton to Somerton Pipeline Install (238) | City Gates & Field Regs | Replacement | 2018 | 0 | 0 | 0 | 0 | 0 | 29347.4 | 0
85 | Pig Trap - Tyers to Maryvale Pipeline Install (67) | City Gates & Field Regs | Replacement | Incurred | 0 | 0 | 0 | 0 | 0 | 0 | 0
86 | Exposed pipe coating refurbishment | Pipelines | Replacement | Incurred | 0 | 0 | 0 | 0 | 0 | 0 | 0
87 | BCS Safety and Process Control System and RTU Upgrade | Compressors | Replacement |  | 23570.02 | 0 | 27200.58 | 0 | 0 | 0 | 50770.6
88 | CS Type B compliance upgrade | Compressors | Replacement |  | 0 | 0 | 1070 | 137904.72 | 192570.71 | 0 | 331545.43
89 | GCS GEA Fuel Gas Upgrade | Compressors | Replacement | 2016 | 0 | 0 | 0 | 61409.78 | 0 | 0 | 61409.78
90 | GCS Units 1,2,3&4 Suction/Discharge Actuated Valve Replacement | Compressors | Replacement | 2017 | 0 | 0 | 0 | 0 | 300218 | 0 | 300218
91 | Mothball WCS station 'A' | Compressors | Replacement | Incurred | 0 | 0 | 0 | 0 | 0 | 0 | 0
92 | Regulator Upgrade - Lara pneumatic control system upgrade | City Gates & Field Regs | Replacement | 2017 | 0 | 0 | 0 | 0 | 165301 | 0 | 165301
93 | Security - High Risk sites security upgrade | Other | Replacement | Incurred | 17837.72 | 24900 | 0 | 0 | 150000 | 0 | 192737.72
94 | Security - Small Site Facilities Fencing Upgrade | Other | Replacement | Incurred | 0 | 0 | 0 | 0 | 0 | 0 | 0
95 | Zonal Chromatograph Bottle Regulator Panels Upgrades | Gas Quality | Replacement | Incurred | 0 | 0 | 0 | 0 | 0 | 0 | 0
96 | Zonal Chromatograph Insertion Probes | Gas Quality | Replacement | 2018 | 0 | 0 | 0 | 0 | 0 | 60000 | 0
97 | Zonal Chromatograph Upgrades | Gas Quality | Replacement | Incurred | 0 | 91009.78 | 0 | 334933 | 0 | 0 | 425942.78
98 | RTU & Control System Upgrade - Facilities | Other | Replacement | Incurred | 98368.47 | 100004.42 | 8235.2 | 131637.03 | 150000 | 0 | 488245.12
99 | GCS Anti-Surge & Fast-Stop Valves Upgrade | Compressors | Replacement | 2017 | 0 | 0 | 0 | 0 | 872341.04 | 0 | 872341.04
100 | GCS Control Room Fire Suppression System | Compressors | Replacement | Incurred | 0 | 0 | 0 | 0 | 0 | 0 | 0
101 | GCS Units 1,2,3&4 Fire Suppression System | Compressors | Replacement | Incurred | 0 | 0 | 0 | 0 | 0 | 0 | 0
102 | Iona CS - Unit Fire Suppression System | Compressors | Replacement | Incurred | 0 | 0 | 0 | 0 | 0 | 0 | 0
103 | Wollert CG Control Hut Fire Suppression System | Compressors | Replacement | 2017 | 0 | 0 | 0 | 0 | 80000 | 0 | 80000
104 | Wollert CS A/B Control Room Fire Suppression System | Compressors | Replacement | 2017 | 0 | 0 | 0 | 0 | 120000 | 0 | 120000
105 | BCG Control Hut Fire Suppression System | City Gates & Field Regs | Replacement | Incurred | 0 | 0 | 0 | 0 | 0 | 0 | 0
106 | Valve - Actuate MLV's in T1 areas | Pipelines | Replacement | 2017 | 0 | 0 | 0 | 0 | 100534 | 0 | 100534
107 | Valve - Longford to Dandenong LV10 Vent Stack | Pipelines | Replacement | 2014 | 0 | 74029.05 | 0 | 0 | 0 | 0 | 74029.05
108 | BCS Station Isolation and Loading Valves | Compressors | Replacement | 2016 | 0 | 0 | 0 | 1812961.52 | 0 | 0 | 1812961.52
109 | Iona CS - Capacity Aftercooler upgrade | Compressors | Replacement | Incurred | 0 | 0 | 0 | 0 | 0 | 0 | 0
110 | BCS DEA Upgrade | Compressors | Replacement | 2017 | 0 | 0 | 0 | 0 | 335565 | 0 | 335565
111 | Pig Trap - Keon Park Install | City Gates & Field Regs | Replacement | 2014 | 0 | 1965930.7 | 0 | 0 | 0 | 0 | 1965930.7
112 | BCS Replacement of FSV, ASV & Other Valves | Compressors | Replacement | Incurred | 0 | 0 | 0 | 0 | 0 | 0 | 0
113 | BCS Unit 10 & 11 Cooler Upgrade | Compressors | Replacement | 2016 | 0 | 0 | 0 | 9196189.12 | 0 | 0 | 9196189.12
114 | SMS - GIS & Aerial Photography | Pipelines | Replacement | 2016 | 0 | 0 | 0 | 145056.5 | 0 | 0 | 145056.5
115 | Wollert to Clonbinane Looping | Pipelines | Augmentation |  | 0 | 32280328.014 | 123650906.696 | 0 | 0 | 0 | 155931234.71
116 | MAOP Upgrade - Euroa to Springhurst (pipe) | Pipelines | Augmentation | Incurred | 0 | 0 | 0 | 0 | 0 | 0 | 0
117 | MAOP Upgrade - Euroa to Springhurst (Reg) | City Gates & Field Regs | Augmentation | Incurred | 0 | 0 | 0 | 0 | 0 | 0 | 0
118 | Valve - T60 Longford - Dandenong Upgrade hydraulic hand pump of actuators | Other | Replacement | Incurred | 0 | 0 | 0 | 0 | 0 | 0 | 0
119 | VTS - BROOKLYN LARA LOOP | Pipelines | Replacement | Incurred | 0 | 0 | 0 | 0 | 0 | 0 | 0
120 | VTS - WOLLERT 4 & 5 CAPEX | Compressors | Replacement | Incurred | 3203.9 | 5158.96 | 0 | 0 | 0 | 0 | 8362.86
121 | VTS - MORWELL TYERS UPGRADE | City Gates & Field Regs | Replacement | Incurred | 6147.52 | 0 | 0 | 0 | 0 | 0 | 6147.52
122 | VTS - MAOP UPGRADE CAPEX | City Gates & Field Regs | Replacement | Incurred | 0 | -42.39 | 0 | 0 | 0 | 0 | -42.39
123 | VTS - BBP & BCP CG UPGRADE | City Gates & Field Regs | Replacement | Incurred | 0 | 0 | 0 | 0 | 0 | 0 | 0
124 | VTS - BRANCH VALVE CASTLEMAINE | Pipelines | Replacement | Incurred | 0 | 0 | 0 | 0 | 0 | 0 | 0
125 | VTS - EUROA CS NEW (PPOM) | Compressors | Augmentation | Incurred | 116664.37 | 121805.28 | 59020.54 | -2941.24 | 0 | 0 | 294548.95
126 | VTS - SUNBURY PIPE LOOP (NEW) | Pipelines | Augmentation | Incurred | 51715.09 | 38571.05 | 5019.95 | 4029.08 | 0 | 0 | 99335.17
127 | VTS - BCS 8&9 COOLERS UPG (NEW | Compressors | Replacement | Incurred | -12591.73 | 22820.08 | 0 | 0 | 0 | 0 | 10228.35
128 | VTS - BCS 12 FAST STOP VALVE | Compressors | Replacement | Incurred | 0 | 0 | 0 | 0 | 0 | 0 | 0
129 | VTS - BCS 8 & 9 UNIT VALVES | Compressors | Replacement | Incurred | 0 | 0 | 0 | 0 | 0 | 0 | 0
130 | PIGGING T91 CURDIEVALE | Other | Replacement | Incurred | 0 | 17873 | 0 | 0 | 0 | 0 | 17873
131 | VTS - BROOKLYN FIRE SERVICE | Buildings | Non-System | 2014 | 0 | 40752.23 | 0 | 0 | 0 | 0 | 40752.23
132 | VTS - BCS LUBE OIL COOLER 8&9 | City Gates & Field Regs | Replacement | Incurred | 109672.54 | 0 | 0 | 0 | 0 | 0 | 109672.54
133 | VNIE Looping 6 to 8 | Pipelines | Augmentation | 2017 | 0 | 0 | 0 | 0 | 140954362.4203 | 0 | 140954362.4203
134 | VTS16.SIB42 WOLL SOFT STARTERS | Other | Replacement | Incurred | 0 | 0 | 0 | 30881 | 0 | 0 | 30881
135 | VTS.SIB99 WCS STN-A DISCHRG LQ | Other | Replacement | 2018 | 0 | 0 | 0 | 0 | 0 | 190850.4 | 0
136 | VTS17.SIB27 SCS CR EPS REMOVAL | Buildings | Non-System | 2017 | 0 | 0 | 0 | 0 | 2856.8 | 0 | 2856.8
137 | VTS17.SIB30 DND EMERG ENTRANCE | Buildings | Non-System | Incurred | 0 | 0 | 0 | 23849.55 | 0 | 0 | 23849.55
138 | Corporate other | Other | Non-System | Incurred | 242365.2632 | 340342.973 | 308327.8805 | 17522.8525 | 0 | 0 | 908558.9692
139 | Market Services _APA Grid Prog | Other | Non-System | 2016 | 0 | 0 | 0 | 310348.845 | 0 | 0 | 310348.845
140 | APA Grid Perf & Resil Overhaul | Other | Non-System | Incurred | 0 | 0 | 44725.1667 | 22022.8998 | 0 | 0 | 66748.0665
141 | APA Grid & Mrkt Srvs SIB Capex | Other | Non-System | Incurred | 0 | 0 | 0 | 458.3444 | 0 | 0 | 458.3444
142 | APA Grid Extend | Other | Non-System | Incurred | 0 | 0 | 0 | 67569.955 | 0 | 0 | 67569.955
143 | APA Grid Services Initiatives | Other | Non-System | Incurred | 0 | 0 | 0 | 111589.8195 | 0 | 0 | 111589.8195
144 | CORP SIB16 DANDENONG REFURB | Other | Non-System | Incurred | 0 | 0 | 303211.3819 | 3462.88 | 0 | 0 | 306674.2619
145 | Data Centre | Other | Non-System |  | 0 | 961195.2533 | 79250.1745 | 0 | 0 | 0 | 1040445.4278
146 | Enterprise Asset Management | Other | Non-System |  | 0 | 0 | 5357652.8429 | 1771.8759 | 0 | 0 | 5359424.7188
147 | Enterprise Content Management | Other | Non-System |  | 0 | 0 | 0 | 430679.5973 | 512309 | 0 | 942988.5973
148 | EAM Bus Support & Governance | Other | Non-System | Incurred | 0 | 0 | 0 | 42640.3455 | 0 | 0 | 42640.3455
149 | EAM TRANSMISSION ESTAB WORK | Other | Non-System | Incurred | 0 | 0 | 0 | 160167.1738 | 0 | 0 | 160167.1738
150 | Oracle Integration with EAM | Other | Non-System | Incurred | 0 | 0 | 0 | 10956.5236 | 0 | 0 | 10956.5236
151 | EAM Business Support-Reports | Other | Non-System | Incurred | 0 | 0 | 0 | 3457.1067 | 0 | 0 | 3457.1067
152 | EC Upgrade | Other | Non-System | Incurred | 0 | 0 | 0 | 185722.3966 | 0 | 0 | 185722.3966
153 | Finance Systems | Other | Non-System | Incurred | 1751.8135 | 0 | 0 | 0 | 0 | 0 | 1751.8135
154 | Mobile phone CAPEX purchases | Other | Non-System | Incurred | 0 | 22811.9773 | 27279.5795 | 28375.3809 | 0 | 0 | 78466.9376
155 | PPOM Phase 2 | Other | Non-System | Incurred | 5453.1938 | 0 | 0 | 0 | 0 | 0 | 5453.1938
156 | Project Server Status Report | Other | Non-System | Incurred | 7605.6406 | 4061.9411 | 0 | 0 | 0 | 0 | 11667.5817
157 | BI reporting | Other | Non-System | Incurred | 33318.3814 | 2571.9179 | 0 | 0 | 0 | 0 | 35890.2993
158 | PPOM Snapshot Engine | Other | Non-System | Incurred | 9285.9184 | 12608.9365 | 0 | 0 | 0 | 0 | 21894.8549
159 | APA Grid Ph.2 | Other | Non-System | 2014 | 0 | 234812.1387 | 0 | 0 | 0 | 0 | 234812.1387
160 | APA Grid Ph. 3 | Other | Non-System | 2014 | 0 | 2637.3633 | 0 | 0 | 0 | 0 | 2637.3633
161 | Vehicle Comms & Journey Mgmt | Other | Non-System | 2016 | 0 | 0 | 0 | 241441.1479 | 0 | 0 | 241441.1479
162 | SCADA Satellite Strategy | Other | Non-System | 2016 | 0 | 0 | 0 | 98363.6564 | 0 | 0 | 98363.6564
163 | SCADA Resilience Project FEED | Other | Non-System | Incurred | 0 | 0 | 0 | 19777.1403 | 0 | 0 | 19777.1403
164 | IOC SCADA GAP ANALYSIS | Other | Non-System | Incurred | 0 | 0 | 0 | 4246.8422 | 0 | 0 | 4246.8422
165 | SCADA Resilience Phase 1 Recom | Other | Non-System | Incurred | 0 | 0 | 0 | 4887.8165 | 0 | 0 | 4887.8165
166 | Melbourne Metro CRE | Other | Non-System | Incurred | 0 | 0 | 0 | 295817.7849 | 0 | 0 | 295817.7849
167 | Adjustments required for differences in CWIP and FAR records | Other | Non-System | Incurred | 0 | -26601 | 23200 | -178445 | 0 | 0 | -181846
168 | APA Grid | Other | Non-System | Incurred | 0 | 0 | 0 | 0 | 261222 | 0 | 261222
169 | B&T projects | Other | Non-System | Incurred | 0 | 0 | 0 | 0 | 598799 | 0 | 598799
170 | Dandenong Relocation | Other | Non-System | Incurred | 0 | 0 | 0 | 0 | 5057812 | 0 | 5057812
171 | Victoria CRE | Other | Non-System | Incurred | 0 | 0 | 0 | 0 | 366376 | 0 | 366376
0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
1327821.7763

## 5.0 Calc│Forecast Projects
| 5.0 Calc│Forecast Projects |  | Check | 268881140.5732 | 268881140.5732 | TRUE |  |  |  |  | 12 | 15 | 13 | 16
Capex # | Project Name | Business case/ project code | Unit | Allocator | Year | 2018 | 2019 | 2020 | 2021 | 2022 | Labour | Contractor | Materials | Other | Check
1 | All CS buffer Air shutoff system for all compressors | 202 | 1 | VTS | 2016 | 381730.5067 | 190865.2533 | 0 | 0 | 0 | 23.66% | 1.964% | 74.37% | 0% | 100%
2 | WCS A Process Safety | 203 | 1 | VTS | 2016 | 0 | 0 | 1045505.76 | 0 | 0 | 23.66% | 27.69% | 48.65% | 0% | 100%
3 | Brooklyn Compressor Station | 204 | 1 | VTS | 2016 | 0 | 0 | 2297362.2833 | 2297362.2833 | 2297362.2833 | 25.12% | 28.49% | 46.38% | 0% | 100%
4 | Compressor Station Vent Stack Upgrade (BCS, WCS, GCS, SCS) | 205 | 1 | VTS | 2016 | 0 | 330397.72 | 330397.72 | 330397.72 | 0 | 23.66% | 26.54% | 29.62% | 20.18% | 100%
5 | Longford Odorant Pump Power Gas Upgrade | 206 | 1 | VTS | 2016 | 75569.2 | 0 | 0 | 0 | 0 | 28.57% | 33.54% | 32.83% | 5.06% | 100%
6 | GCS compressor unit vent valves & actuators replacement | 207a | 1 | VTS | 2016 | 139391.86 | 0 | 0 | 0 | 0 | 23.66% | 28.73% | 47.61% | 0% | 100%
7 | GCS unit discharge and station manifold check valves replacement | 207b | 1 | VTS | 2016 | 0 | 0 | 901953.34 | 0 | 0 | 24.64% | 18.78% | 56.58% | 0% | 100%
8 | GCS Decomm & removal of turbine oil reservoir & auto fill system | 207c | 1 | VTS | 2016 | 0 | 87971.74 | 0 | 0 | 0 | 23.66% | 75.6% | 0.74% | 0% | 100%
9 | BCS Instrument Air reliability upgrade | 208 | 1 | VTS | 2016 | 93782.9 | 0 | 0 | 0 | 0 | 23.66% | 48.4% | 27.93% | 0% | 100%
10 | Compressor lagging and pipe coating replacement (expand to GCS, Springhurst/BCS12/WCS A/WCS B, Euroa) | 209 | 1 | VTS | 2016 | 144918.75 | 144918.75 | 144918.75 | 144918.75 | 144918.75 | 23.66% | 76.34% | 0% | 0% | 100%
11 | Storage shed-Dandenong, Wollert & Springhurst | 210 | 1 | Victoria | 2016 | 0 | 648767 | 648767 | 648767 | 0 | 28.57% | 71.43% | 0% | 0% | 100%
12 | Iona CS aftercooler augmentation | 211 | 1 | VTS | 2016 | 1656341.4 | 0 | 0 | 0 | 0 | 28.57% | 37.41% | 34.02% | 0% | 100%
13 | Battery replacement | 212 | 1 | VTS | 2016 | 70284.2 | 70284.2 | 70284.2 | 70284.2 | 70284.2 | 32.67% | 14.76% | 48.02% | 4.553% | 100%
14 | Wollert CG Instrument Air Conversion | 216 | 1 | VTS | 2016 | 0 | 0 | 0 | 504246.51 | 0 | 23.66% | 56.54% | 19.8% | 0% | 100%
15 | Pit installation on LV03 bypass valves on T33 | 220 | 1 | VTS | 2016 | 0 | 0 | 230860 | 0 | 0 | 28.57% | 58.06% | 13.37% | 0% | 100%
16 | Dandenong water supply & fire main modification | 223 | 1 | Victoria | 2016 | 324178.4 | 0 | 0 | 0 | 0 | 28.57% | 71.43% | 0% | 0% | 100%
17 | Culcairn Injection Gas Quality equipment | 224 | 1 | VTS | 2016 | 973960.4 | 0 | 0 | 0 | 0 | 28.57% | 4.661% | 66.77% | 0% | 100%
18 | Positioner Replacement | 225 | 1 | VTS | 2016 | 101494.96 | 101494.96 | 101494.96 | 101494.96 | 101494.96 | 35.1% | 22.08% | 31.94% | 10.88% | 100%
19 | VTS Safety Management Study aerial photography | 227 | 1 | VTS | 2016 | 162466.1262 | 2780.5938 | 0 | 0 | 0 | 21.88% | 0% | 0% | 78.12% | 100%
20 | BCP Safety Measures for High Consequence areas-(urban growth, fracture control) | 230a | 1 | VTS | 2016 | 0 | 0 | 0 | 0 | 0 | 21.88% | 48.42% | 29.7% | 0% | 100%
21 | BLP Safety Measures for High Consequence areas-(urban growth, fracture control) | 230b | 1 | VTS | 2016 | 0 | 0 | 0 | 0 | 0 | 21.88% | 48.26% | 29.86% | 0% | 100%
22 | WOP Safety Measures for High Consequence areas-(urban growth, fracture control) | 230c | 1 | VTS | 2016 | 0 | 0 | 0 | 0 | 0 | 21.88% | 48.11% | 30.02% | 0% | 100%
23 | ILP Safety Measures for High Consequence areas-(urban growth, fracture control) | 230e | 1 | VTS | 2016 | 0 | 0 | 0 | 0 | 0 | 21.88% | 61.29% | 16.84% | 0% | 100%
24 | Turbine Overhauls | 235 | 1 | VTS | 2016 | 0 | 0 | 0 | 0 | 0 | 23.66% | 76.34% | 0% | 0% | 100%
25 | Iona CS Automation replacement | 236 | 1 | VTS | 2016 | 0 | 0 | 1173411.54 | 0 | 0 | 36.55% | 17.91% | 45.54% | 0% | 100%
26 | GCS Control Room and Unit Enclosure 1,2,3&4 Fire Suppression System | 237a | 1 | VTS | 2016 | 268558.9473 | 0 | 0 | 0 | 0 | 23.66% | 76.34% | 0% | 0% | 100%
27 | BCS MCC Room Fire Suppression System | 237b | 1 | VTS | 2016 | 0 | 0 | 268558.9473 | 0 | 0 | 23.66% | 76.34% | 0% | 0% | 100%
28 | Iona CS Control Room and Unit Enclosure Fire Suppression System | 237d | 1 | VTS | 2016 | 0 | 0 | 0 | 268558.9473 | 0 | 23.66% | 76.34% | 0% | 0% | 100%
29 | Lara City Gate Control Hut Fire Suppression System | 237e | 1 | VTS | 2016 | 0 | 0 | 0 | 0 | 82002.732 | 28.57% | 71.43% | 0% | 0% | 100%
30 | BCS Control Room Fire Suppression System | 237f | 1 | VTS | 2016 | 0 | 0 | 0 | 0 | 82002.732 | 28.57% | 71.43% | 0% | 0% | 100%
31 | Emergency- BA escape sets | 239a | 1 | Victoria | 2016 | 19083.52 | 0 | 0 | 0 | 0 | 21.88% | 0% | 78.12% | 0% | 100%
32 | Emergency- Response Equipment | 239b | 1 | Victoria | 2016 | 278309.12 | 278309.12 | 278309.12 | 278309.12 | 278309.12 | 21.88% | 0.258% | 77.87% | 0% | 100%
33 | Emergency- Spark Proof tools | 239c | 1 | Victoria | 2016 | 1945.6 | 1945.6 | 1945.6 | 1945.6 | 1945.6 | 58.88% | 0% | 41.12% | 0% | 100%
34 | Emergency - fully equipped caravan | 239d | 1 | Victoria | 2016 | 0 | 0 | 107878.4 | 0 | 0 | 21.88% | 4.542% | 73.58% | 0% | 100%
35 | Emergency diesel fuel storage | 239e | 1 | Victoria | 2016 | 0 | 0 | 0 | 123107.84 | 0 | 21.88% | 37% | 41.12% | 0% | 100%
36 | Vent stack for CL600 & 900 pipeline | 240 | 1 | VTS | 2016 | 210339.84 | 0 | 0 | 0 | 0 | 21.88% | 0% | 78.12% | 0% | 100%
37 | Remote CP/critical drainage bond monitoring | 241 | 1 | VTS | 2016 | 573053.7778 | 60456.5556 | 60456.5556 | 60456.5556 | 60456.5556 | 33.41% | 0% | 64.43% | 2.163% | 100%
38 | BCG Un-regulated Bypass Upgrade | 242 | 1 | VTS | 2016 | 0 | 0 | 342346.24 | 0 | 0 | 23.42% | 66.99% | 9.593% | 0% | 100%
39 | Security - Physical | 243 | 1 | Victoria | 2016 | 365236.384 | 365236.384 | 365236.384 | 365236.384 | 365236.384 | 37.33% | 62.67% | 0% | 0% | 100%
40 | CP - Cathodic Protection Replacement | 244 | 1 | VTS | 2016 | 232464.384 | 232464.384 | 232464.384 | 232464.384 | 232464.384 | 36.12% | 4.938% | 53.17% | 5.766% | 100%
41 | Equipment - Gas Detectors | 245 | 1 | Victoria | 2016 | 0 | 0 | 25000 | 25000 | 0 | 0% | 0% | 100% | 0% | 100%
42 | Regulator Upgrade - Lara pneumatic control system upgrade | 247 | 1 | VTS | 2016 | 0 | 619257.8 | 0 | 0 | 0 | 32.45% | 14.16% | 53.39% | 0% | 100%
43 | Hazardous Area Rectification | 249 | 1 | VTS | 2016 | 178000 | 178000 | 178000 | 178000 | 178000 | 11.24% | 50.56% | 38.2% | 0% | 100%
44 | Actuate MLV's in T1 areas | 250 | 1 | VTS | 2016 | 956710.4 | 956710.4 | 0 | 0 | 0 | 21.88% | 10.89% | 62.21% | 5.017% | 100%
45 | Asbestos removal and replacement | 251 | 1 | VTS | 2016 | 70000 | 70000 | 70000 | 70000 | 70000 | 28.57% | 71.43% | 0% | 0% | 100%
46 | T33 non-piggable and encased sections (unknown technical solution) | 257 | 1 | VTS | 2016 | 151759.04 | 151759.04 | 151759.04 | 151759.04 | 0 | 25.63% | 69.18% | 5.189% | 0% | 100%
47 | Pigging Program T57 Ballan - Ballarat | 258a | 1 | VTS | 2016 | 564768 | 0 | 0 | 0 | 0 | 22.3% | 74.14% | 3.564% | 0% | 100%
48 | Pigging Program T62 Derrimut - Sunbury | 258b | 1 | VTS | 2016 | 425799.68 | 0 | 0 | 0 | 0 | 22.44% | 75.1% | 2.461% | 0% | 100%
49 | Pigging Program T61 Packenham - Wollert | 258c | 1 | VTS | 2016 | 0 | 649896.96 | 0 | 0 | 0 | 22.24% | 70.48% | 7.276% | 0% | 100%
50 | Pigging Program T16 Dandenong – West Melbourne | 258d | 1 | VTS | 2016 | 0 | 0 | 0 | 1377768.96 | 0 | 22.05% | 74.52% | 3.432% | 0% | 100%
51 | Pigging Program T60 Longford -Dandenong | 258e | 1 | VTS | 2016 | 0 | 0 | 0 | 0 | 2380922.88 | 21.98% | 76.04% | 1.986% | 0% | 100%
52 | Pigging Program T33 South Melbourne – Brooklyn | 258f | 1 | VTS | 2016 | 0 | 0 | 0 | 1023660.8 | 0 | 22.11% | 73.27% | 4.619% | 0% | 100%
53 | Pigging Program T65 Dandenong to Princes Highway Pipeline (129) | 258g | 1 | VTS | 2016 | 573095.68 | 0 | 0 | 0 | 0 | 22.29% | 69.46% | 8.251% | 0% | 100%
54 | Pigging Program T66-70 Mt Franklin -Kyneton - Bendigo | 258i | 1 | VTS | 2016 | 0 | 587336.96 | 0 | 0 | 0 | 22.28% | 74.29% | 3.427% | 0% | 100%
55 | Pigging Program T75 Wandong - Kyneton | 258k | 1 | VTS | 2016 | 0 | 521020.16 | 0 | 0 | 0 | 22.34% | 73.8% | 3.863% | 0% | 100%
56 | Pigging Program T24 Brooklyn - Corio | 258l | 1 | VTS | 2016 | 0 | 0 | 0 | 1380663.04 | 0 | 22.05% | 76.35% | 1.6% | 0% | 100%
57 | Pigging Program T70 Ballan – Bendigo | 258m | 1 | VTS | 2016 | 0 | 0 | 555975.68 | 0 | 0 | 22.31% | 75.81% | 1.885% | 0% | 100%
58 | Pigging Program T60 Longford – Tyers | 258n | 1 | VTS | 2016 | 0 | 0 | 0 | 0 | 748398.08 | 22.2% | 71.49% | 6.318% | 0% | 100%
59 | Pigging Program T63 Tyers - Morwell | 258o | 1 | VTS | 2016 | 0 | 0 | 0 | 611088.64 | 0 | 22.27% | 72.57% | 5.161% | 0% | 100%
60 | Pigging Program T96 & T98 Chiltern- Rutherglen – Koonoomoo | 258p | 1 | VTS | 2016 | 0 | 0 | 0 | 0 | 510551.04 | 22.35% | 74.99% | 2.669% | 0% | 100%
61 | Pigging Program T118 Trugannina-Plumpton | 258q | 1 | VTS | 2016 | 0 | 0 | 0 | 0 | 512325.12 | 22.34% | 71.5% | 6.156% | 0% | 100%
62 | Pigging Program James Street to Laverton Pipeline (253) | 258s | 1 | VTS | 2016 | 0 | 447777.28 | 0 | 0 | 0 | 22.41% | 72.66% | 4.933% | 0% | 100%
63 | Pigging Program Tyres to Maryvale (67) | 258u | 1 | VTS | 2016 | 383189.76 | 0 | 0 | 0 | 0 | 22.5% | 74.76% | 2.735% | 0% | 100%
64 | Pigging Program T108 Newport | 258v | 1 | VTS | 2016 | 473861.12 | 0 | 0 | 0 | 0 | 22.38% | 71.63% | 5.988% | 0% | 100%
65 | Pigging Program Inner Ring Main | 258w | 1 | VTS | 2016 | 0 | 0 | 3513.6 | 0 | 0 | 22.33% | 72.29% | 5.379% | 0% | 100%
66 | Pigging Program T1 Morwell - Dandenong Repair Program | 258x | 1 | VTS | 2016 | 925523.32 | 174115.72 | 0 | 0 | 0 | 21.88% | 75.82% | 2.305% | 0% | 100%
67 | Pig Trap Installation James Street to Laverton Pipeline (253) | 259a | 1 | VTS | 2016 | 0 | 0 | 0 | 0 | 0 | 13.54% | 57.38% | 29.08% | 0% | 100%
68 | Pig Trap Installation Tyers to Maryvale Pipeline (67) | 259d | 1 | VTS | 2016 | 0 | 0 | 0 | 0 | 0 | 13.55% | 59.01% | 27.44% | 0% | 100%
69 | Pig Trap Installation Trugannina to Plumpton | 259g | 1 | VTS | 2016 | 0 | 0 | 0 | 0 | 0 | 14.29% | 53.79% | 31.93% | 0% | 100%
70 | Liquid Management - Brooklyn | 260a | 1 | VTS | 2016 | 0 | 0 | 0 | 0 | 157005.8 | 29.27% | 55.05% | 15.68% | 0% | 100%
71 | Liquid Management - Pakenham | 260b | 1 | VTS | 2016 | 0 | 0 | 0 | 157005.8 | 0 | 29.27% | 55.05% | 15.68% | 0% | 100%
72 | RTU replacement | 262 | 1 | VTS | 2016 | 141816.64 | 141816.64 | 141816.64 | 141816.64 | 141816.64 | 71.47% | 16.49% | 9.837% | 2.196% | 100%
73 | Pipe Support replacement | 263 | 1 | VTS | 2016 | 164811.0408 | 164811.0408 | 164811.0408 | 164811.0408 | 164811.0408 | 28.57% | 71.43% | 0% | 0% | 100%
74 | HMI upgrade to CLEAR SCADA at BCS, SCS and WCS & CG, Longford | 264 | 1 | VTS | 2016 | 60928 | 60928 | 60928 | 60928 | 60928 | 58.51% | 1.313% | 35.45% | 4.727% | 100%
75 | BCS Unit 12 Inlet Filter Replacement/Augmentation | 267 | 1 | VTS | 2016 | 635719.42 | 0 | 0 | 0 | 0 | 23.66% | 39.83% | 36.51% | 0% | 100%
76 | Coogee decommissioning, Step Change | 268 | 1 | VTS | 2016 | 0 | 0 | 0 | 0 | 0 | 21.88% | 78.12% | 0.006765% | 0% | 100%
77 | Compressor Type B Compliance | 271 | 1 | VTS | 2016 | 216718.54 | 216718.54 | 216718.54 | 216718.54 | 216718.54 | 33.45% | 30.5% | 36.05% | 0% | 100%
78 | Dandenong LNG Isolation Valve Upgrade | 275 | 1 | VTS | 2016 | 649021.8 | 0 | 0 | 0 | 0 | 29.4% | 40.97% | 29.64% | 0% | 100%
79 | Morwell-Dandenong Fatigue Crack Detection from High Loads | 276 | 1 | VTS | 2016 | 260832 | 0 | 0 | 0 | 0 | 25.56% | 67.79% | 6.653% | 0% | 100%
80 | Unibolt Enclosure Replacement | 277 | 1 | VTS | 2016 | 44464 | 44464 | 44464 | 44464 | 44464 | 28.57% | 60.18% | 11.25% | 0% | 100%
81 | WAN Upgrade (Satellite project) | 278 | 1 | VTS | 2016 | 946991.92 | 946991.92 | 946991.92 | 946991.92 | 946991.92 | 46.57% | 18.2% | 29.89% | 5.355% | 100%
82 | Warragul Looping 6" (Southern Route) | Warragul 6" (Sth) | 1 | VTS | 2016 | 0 | 2600000 | 900000 | 0 | 0 | 34.54% | 12.78% | 52.68% | 0% | 100%
83 | Anglesea Pipeline Extension | Anglesea | 1 | VTS | 2016 | 16624609.3573 | 0 | 0 | 0 | 0 | 49.2% | 0% | 30.91% | 19.88% | 100%
84 | BCS Reconfiguration (2B) | BCS Reconfig (2A) | 1 | VTS | 2016 | 1960141.21 | 0 | 0 | 0 | 0 | 54.96% | 0% | 45.04% | 0% | 100%
85 | Winchelsea Bi-Directional Flow | Winchelsea Bi-Direction | 1 | VTS | 2016 | 1420556.258 | 0 | 0 | 0 | 0 | 33.73% | 25.19% | 32.27% | 8.808% | 100%
86 | WORM (50km x 20" Pipeline) | WORM (Pipeline) | 1 | VTS | 2016 | 15911166.8213 | 28997137.4367 | 48814496.7419 | 0 | 0 | 10.58% | 0% | 33.69% | 55.73% | 100%
87 | WORM (C50 at Wollert) | WORM (C50) | 1 | VTS | 2016 | 7043662.34 | 12092299.2911 | 6176723.3689 | 0 | 0 | 37.05% | 0% | 60.4% | 2.553% | 100%
88 | WORM (PRS at Wollert) | WORM (PRS) | 1 | VTS | 2016 | 0 | 1641722.0833 | 1959224.9167 | 0 | 0 | 42.22% | 0% | 54.63% | 3.152% | 100%
89 | Enterprise Content Management | APA | 1 | APA | 2016 | 0 | 0 | 0 | 0 | 0 | 30% | 65% | 5% | 0% | 100%
90 | Victoria CRE | APA | 1 | APA | 2016 | 0 | 0 | 0 | 0 | 0 | 30% | 65% | 5% | 0% | 100%
91 | APA Grid Energy Components Upgrade | APA | 1 | APA | 2016 | 0 | 0 | 0 | 0 | 0 | 30% | 65% | 5% | 0% | 100%
92 | APA Grid Extend Program | APA | 1 | APA | 2016 | 2500000 | 0 | 0 | 0 | 0 | 30% | 65% | 5% | 0% | 100%
93 | APA Grid Services Initiatives Program | APA | 1 | APA | 2016 | 0 | 0 | 0 | 0 | 0 | 30% | 65% | 5% | 0% | 100%
94 | Hyperion Upgrade to 11.1.2.4 | APA | 1 | APA | 2016 | 0 | 0 | 0 | 0 | 0 | 30% | 65% | 5% | 0% | 100%
95 | BI - Transmission Dashboard and Enterprise Pilot | APA | 1 | APA | 2016 | 2000000 | 1500000 | 0 | 0 | 0 | 30% | 65% | 5% | 0% | 100%
96 | HR Systems Refresh | APA | 1 | APA | 2016 | 0 | 0 | 0 | 0 | 0 | 30% | 65% | 5% | 0% | 100%
97 | Transmission EAM Data Management Tool | APA | 1 | APA | 2016 | 0 | 0 | 0 | 0 | 0 | 30% | 65% | 5% | 0% | 100%
98 | SharePoint Upgrade | APA | 1 | APA | 2016 | 243778.5 | 0 | 0 | 0 | 0 | 30% | 65% | 5% | 0% | 100%
99 | eForm Digitisation | APA | 1 | APA | 2016 | 0 | 0 | 1607603.75 | 4147396.25 | 0 | 30% | 65% | 5% | 0% | 100%
100 | Historian Upgrade - version 2012 to 2015 | APA | 1 | APA | 2016 | 0 | 0 | 0 | 0 | 0 | 30% | 65% | 5% | 0% | 100%
101 | Hazardous Area Platform | APA | 1 | APA | 2016 | 1552491.3 | 0 | 0 | 0 | 0 | 30% | 65% | 5% | 0% | 100%
102 | PPM Refresh | APA | 1 | APA | 2016 | 3000000 | 0 | 0 | 0 | 0 | 30% | 65% | 5% | 0% | 100%
103 | BizTalk Upgrade FY2018 | APA | 1 | APA | 2016 | 0 | 604848.9048 | 670918.5097 | 0 | 0 | 30% | 65% | 5% | 0% | 100%
104 | Automated Testing Tool | APA | 1 | APA | 2012 | 632204.9999 | 0 | 0 | 0 | 0 | 30% | 65% | 5% | 0% | 100%
105 | Code Management Software | APA | 1 | APA | 2016 | 905930.625 | 0 | 0 | 0 | 0 | 30% | 65% | 5% | 0% | 100%
106 | CRM Upgrade | APA | 1 | APA | 2016 | 1408186.2 | 59047.8 | 0 | 0 | 0 | 30% | 65% | 5% | 0% | 100%
107 | X-Info Aware Version 2 | APA | 1 | APA | 2016 | 430081.5 | 0 | 0 | 0 | 0 | 30% | 65% | 5% | 0% | 100%
108 | Supplier Qualification and Compliance | APA | 1 | APA | 2016 | 697848.96 | 185555.04 | 0 | 0 | 0 | 30% | 65% | 5% | 0% | 100%
109 | Oracle eBS Upgrade to 12.2 | APA | 1 | APA | 2016 | 267113.0161 | 1276243.5381 | 0 | 0 | 0 | 30% | 65% | 5% | 0% | 100%
110 | BizTalk System Upgrade 2020 | APA | 1 | APA | 2016 | 0 | 604848.9048 | 670918.5097 | 0 | 0 | 30% | 65% | 5% | 0% | 100%
111 | Applications Renewal | APA | 1 | APA | 2016 | 6900000 | 8620000 | 6900000 | 8620000 | 6900000 | 30% | 65% | 5% | 0% | 100%
112 | Infrastructure Renewal | APA | 1 | APA | 2016 | 2250000 | 750000 | 750000 | 750000 | 0 | 30% | 65% | 5% | 0% | 100%
113 | Dandenong Relocation | APA | 1 | APA | 2016 | 0 | 0 | 0 | 0 | 0 | 50% | 0% | 50% | 0% | 100%
- |  | - | 1 | - | 2016 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0%
- |  | - | 1 | - | 2016 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0%
- |  | - | 1 | - | 2016 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0%
- |  | - | 1 | - | 2016 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0%
- |  | - | 1 | - | 2016 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0%
- |  | - | 1 | - | 2016 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0%
- |  | - |  | - |  | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0%
- |  | - |  | - |  | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0%
- |  | - |  | - |  | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0%
- |  | - |  | - |  | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0%
- |  | - |  | - |  | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0%
- |  | - |  | - |  | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0%
- |  | - |  | - |  | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0%
- |  | - |  | - |  | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0%
- |  | - |  | - |  | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0%
- |  | - |  | - |  | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0%
- |  | - |  | - |  | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0%
- |  | - |  | - |  | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0%
- |  | - |  | - |  | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0%
- |  | - |  | - |  | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0%
- |  | - |  | - |  | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0%
- |  | - |  | - |  | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0%
- |  | - |  | - |  | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0%
- |  | - |  | - |  | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0%
- |  | - |  | - |  | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0%
- |  | - |  | - |  | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0%
- |  | - |  | - |  | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0%
- |  | - |  | - |  | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0%
- |  | - |  | - |  | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0%
- |  | - |  | - |  | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0%
- |  | - |  | - |  | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0%
- |  | - |  | - |  | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0%
- |  | - |  | - |  | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0%
- |  | - |  | - |  | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0%
- |  | - |  | - |  | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0%
- |  | - |  | - |  | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0%
- |  | - |  | - |  | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0%
- |  | - |  | - |  | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0%
- |  | - |  | - |  | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0%
- |  | - |  | - |  | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0%
- |  | - |  | - |  | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0%
- |  | - |  | - |  | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0%
- |  | - |  | - |  | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0%
- |  | - |  | - |  | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0%
- |  | - |  | - |  | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0%
- |  | - |  | - |  | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0%
- |  | - |  | - |  | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0%
- |  | - |  | - |  | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0%
- |  | - |  | - |  | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0%
- |  | - |  | - |  | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0%
- |  | - |  | - |  | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0%
- |  | - |  | - |  | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0%
- |  | - |  | - |  | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0%
- |  | - |  | - |  | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0%
- |  | - |  | - |  | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0%
- |  | - |  | - |  | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0%
- |  | - |  | - |  | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0%
- |  | - |  | - |  | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0%
- |  | - |  | - |  | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0%
- |  | - |  | - |  | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0%
- |  | - |  | - |  | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0%
- |  | - |  | - |  | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0%
- |  | - |  | - |  | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0%
- |  | - |  | - |  | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0%
- |  | - |  | - |  | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0%
- |  | - |  | - |  | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0%
- |  | - |  | - |  | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0%
- |  | - |  | - |  | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0%
- |  | - |  | - |  | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0%
- |  | - |  | - |  | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0%
- |  | - |  | - |  | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0%
- |  | - |  | - |  | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0%
- |  | - |  | - |  | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0%
- |  | - |  | - |  | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0%
- |  | - |  | - |  | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0%

## 5.1 Calc│$ million
| 5.1 Calc│$ million | Check picking up all projects | TRUE |  | Check values | TRUE | TRUE | TRUE | TRUE | TRUE
Capex # | Project Name | Business case/ project code | Unit Input | Converter |  | 2018 | 2019 | 2020 | 2021 | 2022
1 | All CS buffer Air shutoff system for all compressors | 202 | 1 | 1e-06 |  | 0.38173 | 0.19087 | 0 | 0 | 0
2 | WCS A Process Safety | 203 | 1 | 1e-06 |  | 0 | 0 | 1.0455 | 0 | 0
3 | Brooklyn Compressor Station | 204 | 1 | 1e-06 |  | 0 | 0 | 2.2974 | 2.2974 | 2.2974
4 | Compressor Station Vent Stack Upgrade (BCS, WCS, GCS, SCS) | 205 | 1 | 1e-06 |  | 0 | 0.3304 | 0.3304 | 0.3304 | 0
5 | Longford Odorant Pump Power Gas Upgrade | 206 | 1 | 1e-06 |  | 0.075569 | 0 | 0 | 0 | 0
6 | GCS compressor unit vent valves & actuators replacement | 207a | 1 | 1e-06 |  | 0.13939 | 0 | 0 | 0 | 0
7 | GCS unit discharge and station manifold check valves replacement | 207b | 1 | 1e-06 |  | 0 | 0 | 0.90195 | 0 | 0
8 | GCS Decomm & removal of turbine oil reservoir & auto fill system | 207c | 1 | 1e-06 |  | 0 | 0.087972 | 0 | 0 | 0
9 | BCS Instrument Air reliability upgrade | 208 | 1 | 1e-06 |  | 0.093783 | 0 | 0 | 0 | 0
10 | Compressor lagging and pipe coating replacement (expand to GCS, Springhurst/BCS12/WCS A/WCS B, Euroa) | 209 | 1 | 1e-06 |  | 0.14492 | 0.14492 | 0.14492 | 0.14492 | 0.14492
11 | Storage shed-Dandenong, Wollert & Springhurst | 210 | 1 | 1e-06 |  | 0 | 0.64877 | 0.64877 | 0.64877 | 0
12 | Iona CS aftercooler augmentation | 211 | 1 | 1e-06 |  | 1.6563 | 0 | 0 | 0 | 0
13 | Battery replacement | 212 | 1 | 1e-06 |  | 0.070284 | 0.070284 | 0.070284 | 0.070284 | 0.070284
14 | Wollert CG Instrument Air Conversion | 216 | 1 | 1e-06 |  | 0 | 0 | 0 | 0.50425 | 0
15 | Pit installation on LV03 bypass valves on T33 | 220 | 1 | 1e-06 |  | 0 | 0 | 0.23086 | 0 | 0
16 | Dandenong water supply & fire main modification | 223 | 1 | 1e-06 |  | 0.32418 | 0 | 0 | 0 | 0
17 | Culcairn Injection Gas Quality equipment | 224 | 1 | 1e-06 |  | 0.97396 | 0 | 0 | 0 | 0
18 | Positioner Replacement | 225 | 1 | 1e-06 |  | 0.10149 | 0.10149 | 0.10149 | 0.10149 | 0.10149
19 | VTS Safety Management Study aerial photography | 227 | 1 | 1e-06 |  | 0.16247 | 0.0027806 | 0 | 0 | 0
20 | BCP Safety Measures for High Consequence areas-(urban growth, fracture control) | 230a | 1 | 1e-06 |  | 0 | 0 | 0 | 0 | 0
21 | BLP Safety Measures for High Consequence areas-(urban growth, fracture control) | 230b | 1 | 1e-06 |  | 0 | 0 | 0 | 0 | 0
22 | WOP Safety Measures for High Consequence areas-(urban growth, fracture control) | 230c | 1 | 1e-06 |  | 0 | 0 | 0 | 0 | 0
23 | ILP Safety Measures for High Consequence areas-(urban growth, fracture control) | 230e | 1 | 1e-06 |  | 0 | 0 | 0 | 0 | 0
24 | Turbine Overhauls | 235 | 1 | 1e-06 |  | 0 | 0 | 0 | 0 | 0
25 | Iona CS Automation replacement | 236 | 1 | 1e-06 |  | 0 | 0 | 1.1734 | 0 | 0
26 | GCS Control Room and Unit Enclosure 1,2,3&4 Fire Suppression System | 237a | 1 | 1e-06 |  | 0.26856 | 0 | 0 | 0 | 0
27 | BCS MCC Room Fire Suppression System | 237b | 1 | 1e-06 |  | 0 | 0 | 0.26856 | 0 | 0
28 | Iona CS Control Room and Unit Enclosure Fire Suppression System | 237d | 1 | 1e-06 |  | 0 | 0 | 0 | 0.26856 | 0
29 | Lara City Gate Control Hut Fire Suppression System | 237e | 1 | 1e-06 |  | 0 | 0 | 0 | 0 | 0.082003
30 | BCS Control Room Fire Suppression System | 237f | 1 | 1e-06 |  | 0 | 0 | 0 | 0 | 0.082003
31 | Emergency- BA escape sets | 239a | 1 | 1e-06 |  | 0.019084 | 0 | 0 | 0 | 0
32 | Emergency- Response Equipment | 239b | 1 | 1e-06 |  | 0.27831 | 0.27831 | 0.27831 | 0.27831 | 0.27831
33 | Emergency- Spark Proof tools | 239c | 1 | 1e-06 |  | 0.0019456 | 0.0019456 | 0.0019456 | 0.0019456 | 0.0019456
34 | Emergency - fully equipped caravan | 239d | 1 | 1e-06 |  | 0 | 0 | 0.10788 | 0 | 0
35 | Emergency diesel fuel storage | 239e | 1 | 1e-06 |  | 0 | 0 | 0 | 0.12311 | 0
36 | Vent stack for CL600 & 900 pipeline | 240 | 1 | 1e-06 |  | 0.21034 | 0 | 0 | 0 | 0
37 | Remote CP/critical drainage bond monitoring | 241 | 1 | 1e-06 |  | 0.57305 | 0.060457 | 0.060457 | 0.060457 | 0.060457
38 | BCG Un-regulated Bypass Upgrade | 242 | 1 | 1e-06 |  | 0 | 0 | 0.34235 | 0 | 0
39 | Security - Physical | 243 | 1 | 1e-06 |  | 0.36524 | 0.36524 | 0.36524 | 0.36524 | 0.36524
40 | CP - Cathodic Protection Replacement | 244 | 1 | 1e-06 |  | 0.23246 | 0.23246 | 0.23246 | 0.23246 | 0.23246
41 | Equipment - Gas Detectors | 245 | 1 | 1e-06 |  | 0 | 0 | 0.025 | 0.025 | 0
42 | Regulator Upgrade - Lara pneumatic control system upgrade | 247 | 1 | 1e-06 |  | 0 | 0.61926 | 0 | 0 | 0
43 | Hazardous Area Rectification | 249 | 1 | 1e-06 |  | 0.178 | 0.178 | 0.178 | 0.178 | 0.178
44 | Actuate MLV's in T1 areas | 250 | 1 | 1e-06 |  | 0.95671 | 0.95671 | 0 | 0 | 0
45 | Asbestos removal and replacement | 251 | 1 | 1e-06 |  | 0.07 | 0.07 | 0.07 | 0.07 | 0.07
46 | T33 non-piggable and encased sections (unknown technical solution) | 257 | 1 | 1e-06 |  | 0.15176 | 0.15176 | 0.15176 | 0.15176 | 0
47 | Pigging Program T57 Ballan - Ballarat | 258a | 1 | 1e-06 |  | 0.56477 | 0 | 0 | 0 | 0
48 | Pigging Program T62 Derrimut - Sunbury | 258b | 1 | 1e-06 |  | 0.4258 | 0 | 0 | 0 | 0
49 | Pigging Program T61 Packenham - Wollert | 258c | 1 | 1e-06 |  | 0 | 0.6499 | 0 | 0 | 0
50 | Pigging Program T16 Dandenong – West Melbourne | 258d | 1 | 1e-06 |  | 0 | 0 | 0 | 1.3778 | 0
51 | Pigging Program T60 Longford -Dandenong | 258e | 1 | 1e-06 |  | 0 | 0 | 0 | 0 | 2.3809
52 | Pigging Program T33 South Melbourne – Brooklyn | 258f | 1 | 1e-06 |  | 0 | 0 | 0 | 1.0237 | 0
53 | Pigging Program T65 Dandenong to Princes Highway Pipeline (129) | 258g | 1 | 1e-06 |  | 0.5731 | 0 | 0 | 0 | 0
54 | Pigging Program T66-70 Mt Franklin -Kyneton - Bendigo | 258i | 1 | 1e-06 |  | 0 | 0.58734 | 0 | 0 | 0
55 | Pigging Program T75 Wandong - Kyneton | 258k | 1 | 1e-06 |  | 0 | 0.52102 | 0 | 0 | 0
56 | Pigging Program T24 Brooklyn - Corio | 258l | 1 | 1e-06 |  | 0 | 0 | 0 | 1.3807 | 0
57 | Pigging Program T70 Ballan – Bendigo | 258m | 1 | 1e-06 |  | 0 | 0 | 0.55598 | 0 | 0
58 | Pigging Program T60 Longford – Tyers | 258n | 1 | 1e-06 |  | 0 | 0 | 0 | 0 | 0.7484
59 | Pigging Program T63 Tyers - Morwell | 258o | 1 | 1e-06 |  | 0 | 0 | 0 | 0.61109 | 0
60 | Pigging Program T96 & T98 Chiltern- Rutherglen – Koonoomoo | 258p | 1 | 1e-06 |  | 0 | 0 | 0 | 0 | 0.51055
61 | Pigging Program T118 Trugannina-Plumpton | 258q | 1 | 1e-06 |  | 0 | 0 | 0 | 0 | 0.51233
62 | Pigging Program James Street to Laverton Pipeline (253) | 258s | 1 | 1e-06 |  | 0 | 0.44778 | 0 | 0 | 0
63 | Pigging Program Tyres to Maryvale (67) | 258u | 1 | 1e-06 |  | 0.38319 | 0 | 0 | 0 | 0
64 | Pigging Program T108 Newport | 258v | 1 | 1e-06 |  | 0.47386 | 0 | 0 | 0 | 0
65 | Pigging Program Inner Ring Main | 258w | 1 | 1e-06 |  | 0 | 0 | 0.0035136 | 0 | 0
66 | Pigging Program T1 Morwell - Dandenong Repair Program | 258x | 1 | 1e-06 |  | 0.92552 | 0.17412 | 0 | 0 | 0
67 | Pig Trap Installation James Street to Laverton Pipeline (253) | 259a | 1 | 1e-06 |  | 0 | 0 | 0 | 0 | 0
68 | Pig Trap Installation Tyers to Maryvale Pipeline (67) | 259d | 1 | 1e-06 |  | 0 | 0 | 0 | 0 | 0
69 | Pig Trap Installation Trugannina to Plumpton | 259g | 1 | 1e-06 |  | 0 | 0 | 0 | 0 | 0
70 | Liquid Management - Brooklyn | 260a | 1 | 1e-06 |  | 0 | 0 | 0 | 0 | 0.15701
71 | Liquid Management - Pakenham | 260b | 1 | 1e-06 |  | 0 | 0 | 0 | 0.15701 | 0
72 | RTU replacement | 262 | 1 | 1e-06 |  | 0.14182 | 0.14182 | 0.14182 | 0.14182 | 0.14182
73 | Pipe Support replacement | 263 | 1 | 1e-06 |  | 0.16481 | 0.16481 | 0.16481 | 0.16481 | 0.16481
74 | HMI upgrade to CLEAR SCADA at BCS, SCS and WCS & CG, Longford | 264 | 1 | 1e-06 |  | 0.060928 | 0.060928 | 0.060928 | 0.060928 | 0.060928
75 | BCS Unit 12 Inlet Filter Replacement/Augmentation | 267 | 1 | 1e-06 |  | 0.63572 | 0 | 0 | 0 | 0
76 | Coogee decommissioning, Step Change | 268 | 1 | 1e-06 |  | 0 | 0 | 0 | 0 | 0
77 | Compressor Type B Compliance | 271 | 1 | 1e-06 |  | 0.21672 | 0.21672 | 0.21672 | 0.21672 | 0.21672
78 | Dandenong LNG Isolation Valve Upgrade | 275 | 1 | 1e-06 |  | 0.64902 | 0 | 0 | 0 | 0
79 | Morwell-Dandenong Fatigue Crack Detection from High Loads | 276 | 1 | 1e-06 |  | 0.26083 | 0 | 0 | 0 | 0
80 | Unibolt Enclosure Replacement | 277 | 1 | 1e-06 |  | 0.044464 | 0.044464 | 0.044464 | 0.044464 | 0.044464
81 | WAN Upgrade (Satellite project) | 278 | 1 | 1e-06 |  | 0.94699 | 0.94699 | 0.94699 | 0.94699 | 0.94699
82 | Warragul Looping 6" (Southern Route) | Warragul 6" (Sth) | 1 | 1e-06 |  | 0 | 2.6 | 0.9 | 0 | 0
83 | Anglesea Pipeline Extension | Anglesea | 1 | 1e-06 |  | 16.6246 | 0 | 0 | 0 | 0
84 | BCS Reconfiguration (2B) | BCS Reconfig (2A) | 1 | 1e-06 |  | 1.9601 | 0 | 0 | 0 | 0
85 | Winchelsea Bi-Directional Flow | Winchelsea Bi-Direction | 1 | 1e-06 |  | 1.4206 | 0 | 0 | 0 | 0
86 | WORM (50km x 20" Pipeline) | WORM (Pipeline) | 1 | 1e-06 |  | 15.9112 | 28.9971 | 48.8145 | 0 | 0
87 | WORM (C50 at Wollert) | WORM (C50) | 1 | 1e-06 |  | 7.0437 | 12.0923 | 6.1767 | 0 | 0
88 | WORM (PRS at Wollert) | WORM (PRS) | 1 | 1e-06 |  | 0 | 1.6417 | 1.9592 | 0 | 0
89 | Enterprise Content Management | APA | 1 | 1e-06 |  | 0 | 0 | 0 | 0 | 0
90 | Victoria CRE | APA | 1 | 1e-06 |  | 0 | 0 | 0 | 0 | 0
91 | APA Grid Energy Components Upgrade | APA | 1 | 1e-06 |  | 0 | 0 | 0 | 0 | 0
92 | APA Grid Extend Program | APA | 1 | 1e-06 |  | 2.5 | 0 | 0 | 0 | 0
93 | APA Grid Services Initiatives Program | APA | 1 | 1e-06 |  | 0 | 0 | 0 | 0 | 0
94 | Hyperion Upgrade to 11.1.2.4 | APA | 1 | 1e-06 |  | 0 | 0 | 0 | 0 | 0
95 | BI - Transmission Dashboard and Enterprise Pilot | APA | 1 | 1e-06 |  | 2 | 1.5 | 0 | 0 | 0
96 | HR Systems Refresh | APA | 1 | 1e-06 |  | 0 | 0 | 0 | 0 | 0
97 | Transmission EAM Data Management Tool | APA | 1 | 1e-06 |  | 0 | 0 | 0 | 0 | 0
98 | SharePoint Upgrade | APA | 1 | 1e-06 |  | 0.24378 | 0 | 0 | 0 | 0
99 | eForm Digitisation | APA | 1 | 1e-06 |  | 0 | 0 | 1.6076 | 4.1474 | 0
100 | Historian Upgrade - version 2012 to 2015 | APA | 1 | 1e-06 |  | 0 | 0 | 0 | 0 | 0
101 | Hazardous Area Platform | APA | 1 | 1e-06 |  | 1.5525 | 0 | 0 | 0 | 0
102 | PPM Refresh | APA | 1 | 1e-06 |  | 3 | 0 | 0 | 0 | 0
103 | BizTalk Upgrade FY2018 | APA | 1 | 1e-06 |  | 0 | 0.60485 | 0.67092 | 0 | 0
104 | Automated Testing Tool | APA | 1 | 1e-06 |  | 0.6322 | 0 | 0 | 0 | 0
105 | Code Management Software | APA | 1 | 1e-06 |  | 0.90593 | 0 | 0 | 0 | 0
106 | CRM Upgrade | APA | 1 | 1e-06 |  | 1.4082 | 0.059048 | 0 | 0 | 0
107 | X-Info Aware Version 2 | APA | 1 | 1e-06 |  | 0.43008 | 0 | 0 | 0 | 0
108 | Supplier Qualification and Compliance | APA | 1 | 1e-06 |  | 0.69785 | 0.18556 | 0 | 0 | 0
109 | Oracle eBS Upgrade to 12.2 | APA | 1 | 1e-06 |  | 0.26711 | 1.2762 | 0 | 0 | 0
110 | BizTalk System Upgrade 2020 | APA | 1 | 1e-06 |  | 0 | 0.60485 | 0.67092 | 0 | 0
111 | Applications Renewal | APA | 1 | 1e-06 |  | 6.9 | 8.62 | 6.9 | 8.62 | 6.9
112 | Infrastructure Renewal | APA | 1 | 1e-06 |  | 2.25 | 0.75 | 0.75 | 0.75 | 0
113 | Dandenong Relocation | APA | 1 | 1e-06 |  | 0 | 0 | 0 | 0 | 0
- |  | - | 1 | 1e-06 |  | 0 | 0 | 0 | 0 | 0
- |  | - | 1 | 1e-06 |  | 0 | 0 | 0 | 0 | 0
- |  | - | 1 | 1e-06 |  | 0 | 0 | 0 | 0 | 0
- |  | - | 1 | 1e-06 |  | 0 | 0 | 0 | 0 | 0
- |  | - | 1 | 1e-06 |  | 0 | 0 | 0 | 0 | 0
- |  | - | 1 | 1e-06 |  | 0 | 0 | 0 | 0 | 0
- |  | - | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
- |  | - | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
- |  | - | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
- |  | - | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
- |  | - | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
- |  | - | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
- |  | - | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
- |  | - | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
- |  | - | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
- |  | - | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
- |  | - | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
- |  | - | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
- |  | - | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
- |  | - | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
- |  | - | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
- |  | - | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
- |  | - | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
- |  | - | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
- |  | - | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
- |  | - | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
- |  | - | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
- |  | - | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
- |  | - | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
- |  | - | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
- |  | - | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
- |  | - | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
- |  | - | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
- |  | - | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
- |  | - | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
- |  | - | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
- |  | - | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
- |  | - | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
- |  | - | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
- |  | - | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
- |  | - | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
- |  | - | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
- |  | - | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
- |  | - | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
- |  | - | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
- |  | - | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
- |  | - | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
- |  | - | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
- |  | - | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
- |  | - | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
- |  | - | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
- |  | - | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
- |  | - | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
- |  | - | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
- |  | - | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
- |  | - | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
- |  | - | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
- |  | - | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
- |  | - | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
- |  | - | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
- |  | - | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
- |  | - | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
- |  | - | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
- |  | - | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
- |  | - | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
- |  | - | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
- |  | - | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
- |  | - | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
- |  | - | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
- |  | - | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
- |  | - | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
- |  | - | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
- |  | - | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
- |  | - | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
- |  | - | 0 | 0 |  | 0 | 0 | 0 | 0 | 0

## 5.2 Calc│VTS
| 5.2 Calc│VTS | Check picking up all projects | TRUE |  | Check values | TRUE | TRUE | TRUE | TRUE | TRUE
Capex # | Project Name | Business case/ project code | Allocator Class | Allocator |  | 2018 | 2019 | 2020 | 2021 | 2022
1 | All CS buffer Air shutoff system for all compressors | 202 | VTS | 100% |  | 0.38173 | 0.19087 | 0 | 0 | 0
2 | WCS A Process Safety | 203 | VTS | 100% |  | 0 | 0 | 1.0455 | 0 | 0
3 | Brooklyn Compressor Station | 204 | VTS | 100% |  | 0 | 0 | 2.2974 | 2.2974 | 2.2974
4 | Compressor Station Vent Stack Upgrade (BCS, WCS, GCS, SCS) | 205 | VTS | 100% |  | 0 | 0.3304 | 0.3304 | 0.3304 | 0
5 | Longford Odorant Pump Power Gas Upgrade | 206 | VTS | 100% |  | 0.075569 | 0 | 0 | 0 | 0
6 | GCS compressor unit vent valves & actuators replacement | 207a | VTS | 100% |  | 0.13939 | 0 | 0 | 0 | 0
7 | GCS unit discharge and station manifold check valves replacement | 207b | VTS | 100% |  | 0 | 0 | 0.90195 | 0 | 0
8 | GCS Decomm & removal of turbine oil reservoir & auto fill system | 207c | VTS | 100% |  | 0 | 0.087972 | 0 | 0 | 0
9 | BCS Instrument Air reliability upgrade | 208 | VTS | 100% |  | 0.093783 | 0 | 0 | 0 | 0
10 | Compressor lagging and pipe coating replacement (expand to GCS, Springhurst/BCS12/WCS A/WCS B, Euroa) | 209 | VTS | 100% |  | 0.14492 | 0.14492 | 0.14492 | 0.14492 | 0.14492
11 | Storage shed-Dandenong, Wollert & Springhurst | 210 | Victoria | 92.63% |  | 0 | 0.60098 | 0.60098 | 0.60098 | 0
12 | Iona CS aftercooler augmentation | 211 | VTS | 100% |  | 1.6563 | 0 | 0 | 0 | 0
13 | Battery replacement | 212 | VTS | 100% |  | 0.070284 | 0.070284 | 0.070284 | 0.070284 | 0.070284
14 | Wollert CG Instrument Air Conversion | 216 | VTS | 100% |  | 0 | 0 | 0 | 0.50425 | 0
15 | Pit installation on LV03 bypass valves on T33 | 220 | VTS | 100% |  | 0 | 0 | 0.23086 | 0 | 0
16 | Dandenong water supply & fire main modification | 223 | Victoria | 92.63% |  | 0.3003 | 0 | 0 | 0 | 0
17 | Culcairn Injection Gas Quality equipment | 224 | VTS | 100% |  | 0.97396 | 0 | 0 | 0 | 0
18 | Positioner Replacement | 225 | VTS | 100% |  | 0.10149 | 0.10149 | 0.10149 | 0.10149 | 0.10149
19 | VTS Safety Management Study aerial photography | 227 | VTS | 100% |  | 0.16247 | 0.0027806 | 0 | 0 | 0
20 | BCP Safety Measures for High Consequence areas-(urban growth, fracture control) | 230a | VTS | 100% |  | 0 | 0 | 0 | 0 | 0
21 | BLP Safety Measures for High Consequence areas-(urban growth, fracture control) | 230b | VTS | 100% |  | 0 | 0 | 0 | 0 | 0
22 | WOP Safety Measures for High Consequence areas-(urban growth, fracture control) | 230c | VTS | 100% |  | 0 | 0 | 0 | 0 | 0
23 | ILP Safety Measures for High Consequence areas-(urban growth, fracture control) | 230e | VTS | 100% |  | 0 | 0 | 0 | 0 | 0
24 | Turbine Overhauls | 235 | VTS | 100% |  | 0 | 0 | 0 | 0 | 0
25 | Iona CS Automation replacement | 236 | VTS | 100% |  | 0 | 0 | 1.1734 | 0 | 0
26 | GCS Control Room and Unit Enclosure 1,2,3&4 Fire Suppression System | 237a | VTS | 100% |  | 0.26856 | 0 | 0 | 0 | 0
27 | BCS MCC Room Fire Suppression System | 237b | VTS | 100% |  | 0 | 0 | 0.26856 | 0 | 0
28 | Iona CS Control Room and Unit Enclosure Fire Suppression System | 237d | VTS | 100% |  | 0 | 0 | 0 | 0.26856 | 0
29 | Lara City Gate Control Hut Fire Suppression System | 237e | VTS | 100% |  | 0 | 0 | 0 | 0 | 0.082003
30 | BCS Control Room Fire Suppression System | 237f | VTS | 100% |  | 0 | 0 | 0 | 0 | 0.082003
31 | Emergency- BA escape sets | 239a | Victoria | 92.63% |  | 0.017678 | 0 | 0 | 0 | 0
32 | Emergency- Response Equipment | 239b | Victoria | 92.63% |  | 0.25781 | 0.25781 | 0.25781 | 0.25781 | 0.25781
33 | Emergency- Spark Proof tools | 239c | Victoria | 92.63% |  | 0.0018023 | 0.0018023 | 0.0018023 | 0.0018023 | 0.0018023
34 | Emergency - fully equipped caravan | 239d | Victoria | 92.63% |  | 0 | 0 | 0.099932 | 0 | 0
35 | Emergency diesel fuel storage | 239e | Victoria | 92.63% |  | 0 | 0 | 0 | 0.11404 | 0
36 | Vent stack for CL600 & 900 pipeline | 240 | VTS | 100% |  | 0.21034 | 0 | 0 | 0 | 0
37 | Remote CP/critical drainage bond monitoring | 241 | VTS | 100% |  | 0.57305 | 0.060457 | 0.060457 | 0.060457 | 0.060457
38 | BCG Un-regulated Bypass Upgrade | 242 | VTS | 100% |  | 0 | 0 | 0.34235 | 0 | 0
39 | Security - Physical | 243 | Victoria | 92.63% |  | 0.33833 | 0.33833 | 0.33833 | 0.33833 | 0.33833
40 | CP - Cathodic Protection Replacement | 244 | VTS | 100% |  | 0.23246 | 0.23246 | 0.23246 | 0.23246 | 0.23246
41 | Equipment - Gas Detectors | 245 | Victoria | 92.63% |  | 0 | 0 | 0.023158 | 0.023158 | 0
42 | Regulator Upgrade - Lara pneumatic control system upgrade | 247 | VTS | 100% |  | 0 | 0.61926 | 0 | 0 | 0
43 | Hazardous Area Rectification | 249 | VTS | 100% |  | 0.178 | 0.178 | 0.178 | 0.178 | 0.178
44 | Actuate MLV's in T1 areas | 250 | VTS | 100% |  | 0.95671 | 0.95671 | 0 | 0 | 0
45 | Asbestos removal and replacement | 251 | VTS | 100% |  | 0.07 | 0.07 | 0.07 | 0.07 | 0.07
46 | T33 non-piggable and encased sections (unknown technical solution) | 257 | VTS | 100% |  | 0.15176 | 0.15176 | 0.15176 | 0.15176 | 0
47 | Pigging Program T57 Ballan - Ballarat | 258a | VTS | 100% |  | 0.56477 | 0 | 0 | 0 | 0
48 | Pigging Program T62 Derrimut - Sunbury | 258b | VTS | 100% |  | 0.4258 | 0 | 0 | 0 | 0
49 | Pigging Program T61 Packenham - Wollert | 258c | VTS | 100% |  | 0 | 0.6499 | 0 | 0 | 0
50 | Pigging Program T16 Dandenong – West Melbourne | 258d | VTS | 100% |  | 0 | 0 | 0 | 1.3778 | 0
51 | Pigging Program T60 Longford -Dandenong | 258e | VTS | 100% |  | 0 | 0 | 0 | 0 | 2.3809
52 | Pigging Program T33 South Melbourne – Brooklyn | 258f | VTS | 100% |  | 0 | 0 | 0 | 1.0237 | 0
53 | Pigging Program T65 Dandenong to Princes Highway Pipeline (129) | 258g | VTS | 100% |  | 0.5731 | 0 | 0 | 0 | 0
54 | Pigging Program T66-70 Mt Franklin -Kyneton - Bendigo | 258i | VTS | 100% |  | 0 | 0.58734 | 0 | 0 | 0
55 | Pigging Program T75 Wandong - Kyneton | 258k | VTS | 100% |  | 0 | 0.52102 | 0 | 0 | 0
56 | Pigging Program T24 Brooklyn - Corio | 258l | VTS | 100% |  | 0 | 0 | 0 | 1.3807 | 0
57 | Pigging Program T70 Ballan – Bendigo | 258m | VTS | 100% |  | 0 | 0 | 0.55598 | 0 | 0
58 | Pigging Program T60 Longford – Tyers | 258n | VTS | 100% |  | 0 | 0 | 0 | 0 | 0.7484
59 | Pigging Program T63 Tyers - Morwell | 258o | VTS | 100% |  | 0 | 0 | 0 | 0.61109 | 0
60 | Pigging Program T96 & T98 Chiltern- Rutherglen – Koonoomoo | 258p | VTS | 100% |  | 0 | 0 | 0 | 0 | 0.51055
61 | Pigging Program T118 Trugannina-Plumpton | 258q | VTS | 100% |  | 0 | 0 | 0 | 0 | 0.51233
62 | Pigging Program James Street to Laverton Pipeline (253) | 258s | VTS | 100% |  | 0 | 0.44778 | 0 | 0 | 0
63 | Pigging Program Tyres to Maryvale (67) | 258u | VTS | 100% |  | 0.38319 | 0 | 0 | 0 | 0
64 | Pigging Program T108 Newport | 258v | VTS | 100% |  | 0.47386 | 0 | 0 | 0 | 0
65 | Pigging Program Inner Ring Main | 258w | VTS | 100% |  | 0 | 0 | 0.0035136 | 0 | 0
66 | Pigging Program T1 Morwell - Dandenong Repair Program | 258x | VTS | 100% |  | 0.92552 | 0.17412 | 0 | 0 | 0
67 | Pig Trap Installation James Street to Laverton Pipeline (253) | 259a | VTS | 100% |  | 0 | 0 | 0 | 0 | 0
68 | Pig Trap Installation Tyers to Maryvale Pipeline (67) | 259d | VTS | 100% |  | 0 | 0 | 0 | 0 | 0
69 | Pig Trap Installation Trugannina to Plumpton | 259g | VTS | 100% |  | 0 | 0 | 0 | 0 | 0
70 | Liquid Management - Brooklyn | 260a | VTS | 100% |  | 0 | 0 | 0 | 0 | 0.15701
71 | Liquid Management - Pakenham | 260b | VTS | 100% |  | 0 | 0 | 0 | 0.15701 | 0
72 | RTU replacement | 262 | VTS | 100% |  | 0.14182 | 0.14182 | 0.14182 | 0.14182 | 0.14182
73 | Pipe Support replacement | 263 | VTS | 100% |  | 0.16481 | 0.16481 | 0.16481 | 0.16481 | 0.16481
74 | HMI upgrade to CLEAR SCADA at BCS, SCS and WCS & CG, Longford | 264 | VTS | 100% |  | 0.060928 | 0.060928 | 0.060928 | 0.060928 | 0.060928
75 | BCS Unit 12 Inlet Filter Replacement/Augmentation | 267 | VTS | 100% |  | 0.63572 | 0 | 0 | 0 | 0
76 | Coogee decommissioning, Step Change | 268 | VTS | 100% |  | 0 | 0 | 0 | 0 | 0
77 | Compressor Type B Compliance | 271 | VTS | 100% |  | 0.21672 | 0.21672 | 0.21672 | 0.21672 | 0.21672
78 | Dandenong LNG Isolation Valve Upgrade | 275 | VTS | 100% |  | 0.64902 | 0 | 0 | 0 | 0
79 | Morwell-Dandenong Fatigue Crack Detection from High Loads | 276 | VTS | 100% |  | 0.26083 | 0 | 0 | 0 | 0
80 | Unibolt Enclosure Replacement | 277 | VTS | 100% |  | 0.044464 | 0.044464 | 0.044464 | 0.044464 | 0.044464
81 | WAN Upgrade (Satellite project) | 278 | VTS | 100% |  | 0.94699 | 0.94699 | 0.94699 | 0.94699 | 0.94699
82 | Warragul Looping 6" (Southern Route) | Warragul 6" (Sth) | VTS | 100% |  | 0 | 2.6 | 0.9 | 0 | 0
83 | Anglesea Pipeline Extension | Anglesea | VTS | 100% |  | 16.6246 | 0 | 0 | 0 | 0
84 | BCS Reconfiguration (2B) | BCS Reconfig (2A) | VTS | 100% |  | 1.9601 | 0 | 0 | 0 | 0
85 | Winchelsea Bi-Directional Flow | Winchelsea Bi-Direction | VTS | 100% |  | 1.4206 | 0 | 0 | 0 | 0
86 | WORM (50km x 20" Pipeline) | WORM (Pipeline) | VTS | 100% |  | 15.9112 | 28.9971 | 48.8145 | 0 | 0
87 | WORM (C50 at Wollert) | WORM (C50) | VTS | 100% |  | 7.0437 | 12.0923 | 6.1767 | 0 | 0
88 | WORM (PRS at Wollert) | WORM (PRS) | VTS | 100% |  | 0 | 1.6417 | 1.9592 | 0 | 0
89 | Enterprise Content Management | APA | APA | 10.45% |  | 0 | 0 | 0 | 0 | 0
90 | Victoria CRE | APA | APA | 10.45% |  | 0 | 0 | 0 | 0 | 0
91 | APA Grid Energy Components Upgrade | APA | APA | 10.45% |  | 0 | 0 | 0 | 0 | 0
92 | APA Grid Extend Program | APA | APA | 10.45% |  | 0.26122 | 0 | 0 | 0 | 0
93 | APA Grid Services Initiatives Program | APA | APA | 10.45% |  | 0 | 0 | 0 | 0 | 0
94 | Hyperion Upgrade to 11.1.2.4 | APA | APA | 10.45% |  | 0 | 0 | 0 | 0 | 0
95 | BI - Transmission Dashboard and Enterprise Pilot | APA | APA | 10.45% |  | 0.20898 | 0.15673 | 0 | 0 | 0
96 | HR Systems Refresh | APA | APA | 10.45% |  | 0 | 0 | 0 | 0 | 0
97 | Transmission EAM Data Management Tool | APA | APA | 10.45% |  | 0 | 0 | 0 | 0 | 0
98 | SharePoint Upgrade | APA | APA | 10.45% |  | 0.025472 | 0 | 0 | 0 | 0
99 | eForm Digitisation | APA | APA | 10.45% |  | 0 | 0 | 0.16798 | 0.43336 | 0
100 | Historian Upgrade - version 2012 to 2015 | APA | APA | 10.45% |  | 0 | 0 | 0 | 0 | 0
101 | Hazardous Area Platform | APA | APA | 10.45% |  | 0.16222 | 0 | 0 | 0 | 0
102 | PPM Refresh | APA | APA | 10.45% |  | 0.31347 | 0 | 0 | 0 | 0
103 | BizTalk Upgrade FY2018 | APA | APA | 10.45% |  | 0 | 0.0632 | 0.070104 | 0 | 0
104 | Automated Testing Tool | APA | APA | 10.45% |  | 0.066058 | 0 | 0 | 0 | 0
105 | Code Management Software | APA | APA | 10.45% |  | 0.09466 | 0 | 0 | 0 | 0
106 | CRM Upgrade | APA | APA | 10.45% |  | 0.14714 | 0.0061698 | 0 | 0 | 0
107 | X-Info Aware Version 2 | APA | APA | 10.45% |  | 0.044939 | 0 | 0 | 0 | 0
108 | Supplier Qualification and Compliance | APA | APA | 10.45% |  | 0.072917 | 0.019388 | 0 | 0 | 0
109 | Oracle eBS Upgrade to 12.2 | APA | APA | 10.45% |  | 0.02791 | 0.13335 | 0 | 0 | 0
110 | BizTalk System Upgrade 2020 | APA | APA | 10.45% |  | 0 | 0.0632 | 0.070104 | 0 | 0
111 | Applications Renewal | APA | APA | 10.45% |  | 0.72097 | 0.90069 | 0.72097 | 0.90069 | 0.72097
112 | Infrastructure Renewal | APA | APA | 10.45% |  | 0.2351 | 0.078367 | 0.078367 | 0.078367 | 0
113 | Dandenong Relocation | APA | APA | 10.45% |  | 0 | 0 | 0 | 0 | 0
- |  | - | - | 0% |  | 0 | 0 | 0 | 0 | 0
- |  | - | - | 0% |  | 0 | 0 | 0 | 0 | 0
- |  | - | - | 0% |  | 0 | 0 | 0 | 0 | 0
- |  | - | - | 0% |  | 0 | 0 | 0 | 0 | 0
- |  | - | - | 0% |  | 0 | 0 | 0 | 0 | 0
- |  | - | - | 0% |  | 0 | 0 | 0 | 0 | 0
- |  | - | - | 0% |  | 0 | 0 | 0 | 0 | 0
- |  | - | - | 0% |  | 0 | 0 | 0 | 0 | 0
- |  | - | - | 0% |  | 0 | 0 | 0 | 0 | 0
- |  | - | - | 0% |  | 0 | 0 | 0 | 0 | 0
- |  | - | - | 0% |  | 0 | 0 | 0 | 0 | 0
- |  | - | - | 0% |  | 0 | 0 | 0 | 0 | 0
- |  | - | - | 0% |  | 0 | 0 | 0 | 0 | 0
- |  | - | - | 0% |  | 0 | 0 | 0 | 0 | 0
- |  | - | - | 0% |  | 0 | 0 | 0 | 0 | 0
- |  | - | - | 0% |  | 0 | 0 | 0 | 0 | 0
- |  | - | - | 0% |  | 0 | 0 | 0 | 0 | 0
- |  | - | - | 0% |  | 0 | 0 | 0 | 0 | 0
- |  | - | - | 0% |  | 0 | 0 | 0 | 0 | 0
- |  | - | - | 0% |  | 0 | 0 | 0 | 0 | 0
- |  | - | - | 0% |  | 0 | 0 | 0 | 0 | 0
- |  | - | - | 0% |  | 0 | 0 | 0 | 0 | 0
- |  | - | - | 0% |  | 0 | 0 | 0 | 0 | 0
- |  | - | - | 0% |  | 0 | 0 | 0 | 0 | 0
- |  | - | - | 0% |  | 0 | 0 | 0 | 0 | 0
- |  | - | - | 0% |  | 0 | 0 | 0 | 0 | 0
- |  | - | - | 0% |  | 0 | 0 | 0 | 0 | 0
- |  | - | - | 0% |  | 0 | 0 | 0 | 0 | 0
- |  | - | - | 0% |  | 0 | 0 | 0 | 0 | 0
- |  | - | - | 0% |  | 0 | 0 | 0 | 0 | 0
- |  | - | - | 0% |  | 0 | 0 | 0 | 0 | 0
- |  | - | - | 0% |  | 0 | 0 | 0 | 0 | 0
- |  | - | - | 0% |  | 0 | 0 | 0 | 0 | 0
- |  | - | - | 0% |  | 0 | 0 | 0 | 0 | 0
- |  | - | - | 0% |  | 0 | 0 | 0 | 0 | 0
- |  | - | - | 0% |  | 0 | 0 | 0 | 0 | 0
- |  | - | - | 0% |  | 0 | 0 | 0 | 0 | 0
- |  | - | - | 0% |  | 0 | 0 | 0 | 0 | 0
- |  | - | - | 0% |  | 0 | 0 | 0 | 0 | 0
- |  | - | - | 0% |  | 0 | 0 | 0 | 0 | 0
- |  | - | - | 0% |  | 0 | 0 | 0 | 0 | 0
- |  | - | - | 0% |  | 0 | 0 | 0 | 0 | 0
- |  | - | - | 0% |  | 0 | 0 | 0 | 0 | 0
- |  | - | - | 0% |  | 0 | 0 | 0 | 0 | 0
- |  | - | - | 0% |  | 0 | 0 | 0 | 0 | 0
- |  | - | - | 0% |  | 0 | 0 | 0 | 0 | 0
- |  | - | - | 0% |  | 0 | 0 | 0 | 0 | 0
- |  | - | - | 0% |  | 0 | 0 | 0 | 0 | 0
- |  | - | - | 0% |  | 0 | 0 | 0 | 0 | 0
- |  | - | - | 0% |  | 0 | 0 | 0 | 0 | 0
- |  | - | - | 0% |  | 0 | 0 | 0 | 0 | 0
- |  | - | - | 0% |  | 0 | 0 | 0 | 0 | 0
- |  | - | - | 0% |  | 0 | 0 | 0 | 0 | 0
- |  | - | - | 0% |  | 0 | 0 | 0 | 0 | 0
- |  | - | - | 0% |  | 0 | 0 | 0 | 0 | 0
- |  | - | - | 0% |  | 0 | 0 | 0 | 0 | 0
- |  | - | - | 0% |  | 0 | 0 | 0 | 0 | 0
- |  | - | - | 0% |  | 0 | 0 | 0 | 0 | 0
- |  | - | - | 0% |  | 0 | 0 | 0 | 0 | 0
- |  | - | - | 0% |  | 0 | 0 | 0 | 0 | 0
- |  | - | - | 0% |  | 0 | 0 | 0 | 0 | 0
- |  | - | - | 0% |  | 0 | 0 | 0 | 0 | 0
- |  | - | - | 0% |  | 0 | 0 | 0 | 0 | 0
- |  | - | - | 0% |  | 0 | 0 | 0 | 0 | 0
- |  | - | - | 0% |  | 0 | 0 | 0 | 0 | 0
- |  | - | - | 0% |  | 0 | 0 | 0 | 0 | 0
- |  | - | - | 0% |  | 0 | 0 | 0 | 0 | 0
- |  | - | - | 0% |  | 0 | 0 | 0 | 0 | 0
- |  | - | - | 0% |  | 0 | 0 | 0 | 0 | 0
- |  | - | - | 0% |  | 0 | 0 | 0 | 0 | 0
- |  | - | - | 0% |  | 0 | 0 | 0 | 0 | 0
- |  | - | - | 0% |  | 0 | 0 | 0 | 0 | 0
- |  | - | - | 0% |  | 0 | 0 | 0 | 0 | 0
- |  | - | - | 0% |  | 0 | 0 | 0 | 0 | 0
- |  | - | - | 0% |  | 0 | 0 | 0 | 0 | 0

## 5.3 Calc│Forecast $2017
[6 empty] | 0 | 0 | 0 | 0 | 0
| 5.3 Calc│Forecast $2017 | Check picking up projects | TRUE |  | Check values | TRUE | TRUE | TRUE | TRUE | TRUE
Capex # | Project Name | Business case/ project code | Input currency | conversion |  | 2018 | 2019 | 2020 | 2021 | 2022
1 | All CS buffer Air shutoff system for all compressors | 202 | 2016 | 1.0332 | 0 | 0.39441 | 0.19721 | 0 | 0 | 0
2 | WCS A Process Safety | 203 | 2016 | 1.0332 |  | 0 | 0 | 1.0802 | 0 | 0
3 | Brooklyn Compressor Station | 204 | 2016 | 1.0332 |  | 0 | 0 | 2.3737 | 2.3737 | 2.3737
4 | Compressor Station Vent Stack Upgrade (BCS, WCS, GCS, SCS) | 205 | 2016 | 1.0332 |  | 0 | 0.34137 | 0.34137 | 0.34137 | 0
5 | Longford Odorant Pump Power Gas Upgrade | 206 | 2016 | 1.0332 |  | 0.07808 | 0 | 0 | 0 | 0
6 | GCS compressor unit vent valves & actuators replacement | 207a | 2016 | 1.0332 |  | 0.14402 | 0 | 0 | 0 | 0
7 | GCS unit discharge and station manifold check valves replacement | 207b | 2016 | 1.0332 |  | 0 | 0 | 0.93192 | 0 | 0
8 | GCS Decomm & removal of turbine oil reservoir & auto fill system | 207c | 2016 | 1.0332 |  | 0 | 0.090894 | 0 | 0 | 0
9 | BCS Instrument Air reliability upgrade | 208 | 2016 | 1.0332 |  | 0.096899 | 0 | 0 | 0 | 0
10 | Compressor lagging and pipe coating replacement (expand to GCS, Springhurst/BCS12/WCS A/WCS B, Euroa) | 209 | 2016 | 1.0332 |  | 0.14973 | 0.14973 | 0.14973 | 0.14973 | 0.14973
11 | Storage shed-Dandenong, Wollert & Springhurst | 210 | 2016 | 1.0332 |  | 0 | 0.62094 | 0.62094 | 0.62094 | 0
12 | Iona CS aftercooler augmentation | 211 | 2016 | 1.0332 |  | 1.7114 | 0 | 0 | 0 | 0
13 | Battery replacement | 212 | 2016 | 1.0332 |  | 0.072619 | 0.072619 | 0.072619 | 0.072619 | 0.072619
14 | Wollert CG Instrument Air Conversion | 216 | 2016 | 1.0332 |  | 0 | 0 | 0 | 0.521 | 0
15 | Pit installation on LV03 bypass valves on T33 | 220 | 2016 | 1.0332 |  | 0 | 0 | 0.23853 | 0 | 0
16 | Dandenong water supply & fire main modification | 223 | 2016 | 1.0332 |  | 0.31028 | 0 | 0 | 0 | 0
17 | Culcairn Injection Gas Quality equipment | 224 | 2016 | 1.0332 |  | 1.0063 | 0 | 0 | 0 | 0
18 | Positioner Replacement | 225 | 2016 | 1.0332 |  | 0.10487 | 0.10487 | 0.10487 | 0.10487 | 0.10487
19 | VTS Safety Management Study aerial photography | 227 | 2016 | 1.0332 |  | 0.16786 | 0.002873 | 0 | 0 | 0
20 | BCP Safety Measures for High Consequence areas-(urban growth, fracture control) | 230a | 2016 | 1.0332 |  | 0 | 0 | 0 | 0 | 0
21 | BLP Safety Measures for High Consequence areas-(urban growth, fracture control) | 230b | 2016 | 1.0332 |  | 0 | 0 | 0 | 0 | 0
22 | WOP Safety Measures for High Consequence areas-(urban growth, fracture control) | 230c | 2016 | 1.0332 |  | 0 | 0 | 0 | 0 | 0
23 | ILP Safety Measures for High Consequence areas-(urban growth, fracture control) | 230e | 2016 | 1.0332 |  | 0 | 0 | 0 | 0 | 0
24 | Turbine Overhauls | 235 | 2016 | 1.0332 |  | 0 | 0 | 0 | 0 | 0
25 | Iona CS Automation replacement | 236 | 2016 | 1.0332 |  | 0 | 0 | 1.2124 | 0 | 0
26 | GCS Control Room and Unit Enclosure 1,2,3&4 Fire Suppression System | 237a | 2016 | 1.0332 |  | 0.27748 | 0 | 0 | 0 | 0
27 | BCS MCC Room Fire Suppression System | 237b | 2016 | 1.0332 |  | 0 | 0 | 0.27748 | 0 | 0
28 | Iona CS Control Room and Unit Enclosure Fire Suppression System | 237d | 2016 | 1.0332 |  | 0 | 0 | 0 | 0.27748 | 0
29 | Lara City Gate Control Hut Fire Suppression System | 237e | 2016 | 1.0332 |  | 0 | 0 | 0 | 0 | 0.084727
30 | BCS Control Room Fire Suppression System | 237f | 2016 | 1.0332 |  | 0 | 0 | 0 | 0 | 0.084727
31 | Emergency- BA escape sets | 239a | 2016 | 1.0332 |  | 0.018265 | 0 | 0 | 0 | 0
32 | Emergency- Response Equipment | 239b | 2016 | 1.0332 |  | 0.26637 | 0.26637 | 0.26637 | 0.26637 | 0.26637
33 | Emergency- Spark Proof tools | 239c | 2016 | 1.0332 |  | 0.0018622 | 0.0018622 | 0.0018622 | 0.0018622 | 0.0018622
34 | Emergency - fully equipped caravan | 239d | 2016 | 1.0332 |  | 0 | 0 | 0.10325 | 0 | 0
35 | Emergency diesel fuel storage | 239e | 2016 | 1.0332 |  | 0 | 0 | 0 | 0.11783 | 0
36 | Vent stack for CL600 & 900 pipeline | 240 | 2016 | 1.0332 |  | 0.21733 | 0 | 0 | 0 | 0
37 | Remote CP/critical drainage bond monitoring | 241 | 2016 | 1.0332 |  | 0.59209 | 0.062465 | 0.062465 | 0.062465 | 0.062465
38 | BCG Un-regulated Bypass Upgrade | 242 | 2016 | 1.0332 |  | 0 | 0 | 0.35372 | 0 | 0
39 | Security - Physical | 243 | 2016 | 1.0332 |  | 0.34957 | 0.34957 | 0.34957 | 0.34957 | 0.34957
40 | CP - Cathodic Protection Replacement | 244 | 2016 | 1.0332 |  | 0.24019 | 0.24019 | 0.24019 | 0.24019 | 0.24019
41 | Equipment - Gas Detectors | 245 | 2016 | 1.0332 |  | 0 | 0 | 0.023928 | 0.023928 | 0
42 | Regulator Upgrade - Lara pneumatic control system upgrade | 247 | 2016 | 1.0332 |  | 0 | 0.63983 | 0 | 0 | 0
43 | Hazardous Area Rectification | 249 | 2016 | 1.0332 |  | 0.18391 | 0.18391 | 0.18391 | 0.18391 | 0.18391
44 | Actuate MLV's in T1 areas | 250 | 2016 | 1.0332 |  | 0.98849 | 0.98849 | 0 | 0 | 0
45 | Asbestos removal and replacement | 251 | 2016 | 1.0332 |  | 0.072326 | 0.072326 | 0.072326 | 0.072326 | 0.072326
46 | T33 non-piggable and encased sections (unknown technical solution) | 257 | 2016 | 1.0332 |  | 0.1568 | 0.1568 | 0.1568 | 0.1568 | 0
47 | Pigging Program T57 Ballan - Ballarat | 258a | 2016 | 1.0332 |  | 0.58353 | 0 | 0 | 0 | 0
48 | Pigging Program T62 Derrimut - Sunbury | 258b | 2016 | 1.0332 |  | 0.43995 | 0 | 0 | 0 | 0
49 | Pigging Program T61 Packenham - Wollert | 258c | 2016 | 1.0332 |  | 0 | 0.67149 | 0 | 0 | 0
50 | Pigging Program T16 Dandenong – West Melbourne | 258d | 2016 | 1.0332 |  | 0 | 0 | 0 | 1.4235 | 0
51 | Pigging Program T60 Longford -Dandenong | 258e | 2016 | 1.0332 |  | 0 | 0 | 0 | 0 | 2.46
52 | Pigging Program T33 South Melbourne – Brooklyn | 258f | 2016 | 1.0332 |  | 0 | 0 | 0 | 1.0577 | 0
53 | Pigging Program T65 Dandenong to Princes Highway Pipeline (129) | 258g | 2016 | 1.0332 |  | 0.59214 | 0 | 0 | 0 | 0
54 | Pigging Program T66-70 Mt Franklin -Kyneton - Bendigo | 258i | 2016 | 1.0332 |  | 0 | 0.60685 | 0 | 0 | 0
55 | Pigging Program T75 Wandong - Kyneton | 258k | 2016 | 1.0332 |  | 0 | 0.53833 | 0 | 0 | 0
56 | Pigging Program T24 Brooklyn - Corio | 258l | 2016 | 1.0332 |  | 0 | 0 | 0 | 1.4265 | 0
57 | Pigging Program T70 Ballan – Bendigo | 258m | 2016 | 1.0332 |  | 0 | 0 | 0.57445 | 0 | 0
58 | Pigging Program T60 Longford – Tyers | 258n | 2016 | 1.0332 |  | 0 | 0 | 0 | 0 | 0.77326
59 | Pigging Program T63 Tyers - Morwell | 258o | 2016 | 1.0332 |  | 0 | 0 | 0 | 0.63139 | 0
60 | Pigging Program T96 & T98 Chiltern- Rutherglen – Koonoomoo | 258p | 2016 | 1.0332 |  | 0 | 0 | 0 | 0 | 0.52751
61 | Pigging Program T118 Trugannina-Plumpton | 258q | 2016 | 1.0332 |  | 0 | 0 | 0 | 0 | 0.52935
62 | Pigging Program James Street to Laverton Pipeline (253) | 258s | 2016 | 1.0332 |  | 0 | 0.46265 | 0 | 0 | 0
63 | Pigging Program Tyres to Maryvale (67) | 258u | 2016 | 1.0332 |  | 0.39592 | 0 | 0 | 0 | 0
64 | Pigging Program T108 Newport | 258v | 2016 | 1.0332 |  | 0.4896 | 0 | 0 | 0 | 0
65 | Pigging Program Inner Ring Main | 258w | 2016 | 1.0332 |  | 0 | 0 | 0.0036303 | 0 | 0
66 | Pigging Program T1 Morwell - Dandenong Repair Program | 258x | 2016 | 1.0332 |  | 0.95627 | 0.1799 | 0 | 0 | 0
67 | Pig Trap Installation James Street to Laverton Pipeline (253) | 259a | 2016 | 1.0332 |  | 0 | 0 | 0 | 0 | 0
68 | Pig Trap Installation Tyers to Maryvale Pipeline (67) | 259d | 2016 | 1.0332 |  | 0 | 0 | 0 | 0 | 0
69 | Pig Trap Installation Trugannina to Plumpton | 259g | 2016 | 1.0332 |  | 0 | 0 | 0 | 0 | 0
70 | Liquid Management - Brooklyn | 260a | 2016 | 1.0332 |  | 0 | 0 | 0 | 0 | 0.16222
71 | Liquid Management - Pakenham | 260b | 2016 | 1.0332 |  | 0 | 0 | 0 | 0.16222 | 0
72 | RTU replacement | 262 | 2016 | 1.0332 |  | 0.14653 | 0.14653 | 0.14653 | 0.14653 | 0.14653
73 | Pipe Support replacement | 263 | 2016 | 1.0332 |  | 0.17029 | 0.17029 | 0.17029 | 0.17029 | 0.17029
74 | HMI upgrade to CLEAR SCADA at BCS, SCS and WCS & CG, Longford | 264 | 2016 | 1.0332 |  | 0.062952 | 0.062952 | 0.062952 | 0.062952 | 0.062952
75 | BCS Unit 12 Inlet Filter Replacement/Augmentation | 267 | 2016 | 1.0332 |  | 0.65684 | 0 | 0 | 0 | 0
76 | Coogee decommissioning, Step Change | 268 | 2016 | 1.0332 |  | 0 | 0 | 0 | 0 | 0
77 | Compressor Type B Compliance | 271 | 2016 | 1.0332 |  | 0.22392 | 0.22392 | 0.22392 | 0.22392 | 0.22392
78 | Dandenong LNG Isolation Valve Upgrade | 275 | 2016 | 1.0332 |  | 0.67058 | 0 | 0 | 0 | 0
79 | Morwell-Dandenong Fatigue Crack Detection from High Loads | 276 | 2016 | 1.0332 |  | 0.2695 | 0 | 0 | 0 | 0
80 | Unibolt Enclosure Replacement | 277 | 2016 | 1.0332 |  | 0.045941 | 0.045941 | 0.045941 | 0.045941 | 0.045941
81 | WAN Upgrade (Satellite project) | 278 | 2016 | 1.0332 |  | 0.97845 | 0.97845 | 0.97845 | 0.97845 | 0.97845
82 | Warragul Looping 6" (Southern Route) | Warragul 6" (Sth) | 2016 | 1.0332 |  | 0 | 2.6864 | 0.9299 | 0 | 0
83 | Anglesea Pipeline Extension | Anglesea | 2016 | 1.0332 |  | 17.1769 | 0 | 0 | 0 | 0
84 | BCS Reconfiguration (2B) | BCS Reconfig (2A) | 2016 | 1.0332 |  | 2.0253 | 0 | 0 | 0 | 0
85 | Winchelsea Bi-Directional Flow | Winchelsea Bi-Direction | 2016 | 1.0332 |  | 1.4678 | 0 | 0 | 0 | 0
86 | WORM (50km x 20" Pipeline) | WORM (Pipeline) | 2016 | 1.0332 |  | 16.4398 | 29.9605 | 50.4362 | 0 | 0
87 | WORM (C50 at Wollert) | WORM (C50) | 2016 | 1.0332 |  | 7.2777 | 12.494 | 6.3819 | 0 | 0
88 | WORM (PRS at Wollert) | WORM (PRS) | 2016 | 1.0332 |  | 0 | 1.6963 | 2.0243 | 0 | 0
89 | Enterprise Content Management | APA | 2016 | 1.0332 |  | 0 | 0 | 0 | 0 | 0
90 | Victoria CRE | APA | 2016 | 1.0332 |  | 0 | 0 | 0 | 0 | 0
91 | APA Grid Energy Components Upgrade | APA | 2016 | 1.0332 |  | 0 | 0 | 0 | 0 | 0
92 | APA Grid Extend Program | APA | 2016 | 1.0332 |  | 0.2699 | 0 | 0 | 0 | 0
93 | APA Grid Services Initiatives Program | APA | 2016 | 1.0332 |  | 0 | 0 | 0 | 0 | 0
94 | Hyperion Upgrade to 11.1.2.4 | APA | 2016 | 1.0332 |  | 0 | 0 | 0 | 0 | 0
95 | BI - Transmission Dashboard and Enterprise Pilot | APA | 2016 | 1.0332 |  | 0.21592 | 0.16194 | 0 | 0 | 0
96 | HR Systems Refresh | APA | 2016 | 1.0332 |  | 0 | 0 | 0 | 0 | 0
97 | Transmission EAM Data Management Tool | APA | 2016 | 1.0332 |  | 0 | 0 | 0 | 0 | 0
98 | SharePoint Upgrade | APA | 2016 | 1.0332 |  | 0.026318 | 0 | 0 | 0 | 0
99 | eForm Digitisation | APA | 2016 | 1.0332 |  | 0 | 0 | 0.17356 | 0.44775 | 0
100 | Historian Upgrade - version 2012 to 2015 | APA | 2016 | 1.0332 |  | 0 | 0 | 0 | 0 | 0
101 | Hazardous Area Platform | APA | 2016 | 1.0332 |  | 0.16761 | 0 | 0 | 0 | 0
102 | PPM Refresh | APA | 2016 | 1.0332 |  | 0.32388 | 0 | 0 | 0 | 0
103 | BizTalk Upgrade FY2018 | APA | 2016 | 1.0332 |  | 0 | 0.0653 | 0.072433 | 0 | 0
104 | Automated Testing Tool | APA | 2012 | 1.0897 |  | 0.071986 | 0 | 0 | 0 | 0
105 | Code Management Software | APA | 2016 | 1.0332 |  | 0.097804 | 0 | 0 | 0 | 0
106 | CRM Upgrade | APA | 2016 | 1.0332 |  | 0.15203 | 0.0063748 | 0 | 0 | 0
107 | X-Info Aware Version 2 | APA | 2016 | 1.0332 |  | 0.046432 | 0 | 0 | 0 | 0
108 | Supplier Qualification and Compliance | APA | 2016 | 1.0332 |  | 0.07534 | 0.020033 | 0 | 0 | 0
109 | Oracle eBS Upgrade to 12.2 | APA | 2016 | 1.0332 |  | 0.028838 | 0.13778 | 0 | 0 | 0
110 | BizTalk System Upgrade 2020 | APA | 2016 | 1.0332 |  | 0 | 0.0653 | 0.072433 | 0 | 0
111 | Applications Renewal | APA | 2016 | 1.0332 |  | 0.74493 | 0.93062 | 0.74493 | 0.93062 | 0.74493
112 | Infrastructure Renewal | APA | 2016 | 1.0332 |  | 0.24291 | 0.08097 | 0.08097 | 0.08097 | 0
113 | Dandenong Relocation | APA | 2016 | 1.0332 |  | 0 | 0 | 0 | 0 | 0
- |  | - | 2016 | 1.0332 |  | 0 | 0 | 0 | 0 | 0
- |  | - | 2016 | 1.0332 |  | 0 | 0 | 0 | 0 | 0
- |  | - | 2016 | 1.0332 |  | 0 | 0 | 0 | 0 | 0
- |  | - | 2016 | 1.0332 |  | 0 | 0 | 0 | 0 | 0
- |  | - | 2016 | 1.0332 |  | 0 | 0 | 0 | 0 | 0
- |  | - | 2016 | 1.0332 |  | 0 | 0 | 0 | 0 | 0
- |  | - | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
- |  | - | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
- |  | - | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
- |  | - | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
- |  | - | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
- |  | - | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
- |  | - | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
- |  | - | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
- |  | - | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
- |  | - | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
- |  | - | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
- |  | - | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
- |  | - | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
- |  | - | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
- |  | - | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
- |  | - | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
- |  | - | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
- |  | - | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
- |  | - | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
- |  | - | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
- |  | - | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
- |  | - | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
- |  | - | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
- |  | - | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
- |  | - | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
- |  | - | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
- |  | - | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
- |  | - | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
- |  | - | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
- |  | - | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
- |  | - | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
- |  | - | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
- |  | - | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
- |  | - | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
- |  | - | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
- |  | - | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
- |  | - | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
- |  | - | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
- |  | - | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
- |  | - | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
- |  | - | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
- |  | - | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
- |  | - | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
- |  | - | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
- |  | - | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
- |  | - | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
- |  | - | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
- |  | - | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
- |  | - | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
- |  | - | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
- |  | - | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
- |  | - | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
- |  | - | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
- |  | - | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
- |  | - | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
- |  | - | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
- |  | - | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
- |  | - | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
- |  | - | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
- |  | - | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
- |  | - | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
- |  | - | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
- |  | - | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
- |  | - | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
- |  | - | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
- |  | - | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
- |  | - | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
- |  | - | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
- |  | - | 0 | 0 |  | 0 | 0 | 0 | 0 | 0

## 5.4 Calc│Escalators
5.4 Calc│Escalators
Capex # | Project Name | Labour | Contractor | Materials | Other | 2018 | 2019 | 2020 | 2021 | 2022
1 | All CS buffer Air shutoff system for all compressors | 23.66% | 1.964% | 74.37% | 0% | 1 | 1 | 1 | 1 | 1 | 100%
2 | WCS A Process Safety | 23.66% | 27.69% | 48.65% | 0% | 1 | 1 | 1 | 1 | 1 | 100%
3 | Brooklyn Compressor Station | 25.12% | 28.49% | 46.38% | 0% | 1 | 1 | 1 | 1 | 1 | 100%
4 | Compressor Station Vent Stack Upgrade (BCS, WCS, GCS, SCS) | 23.66% | 26.54% | 29.62% | 20.18% | 1 | 1 | 1 | 1 | 1 | 100%
5 | Longford Odorant Pump Power Gas Upgrade | 28.57% | 33.54% | 32.83% | 5.06% | 1 | 1 | 1 | 1 | 1 | 100%
6 | GCS compressor unit vent valves & actuators replacement | 23.66% | 28.73% | 47.61% | 0% | 1 | 1 | 1 | 1 | 1 | 100%
7 | GCS unit discharge and station manifold check valves replacement | 24.64% | 18.78% | 56.58% | 0% | 1 | 1 | 1 | 1 | 1 | 100%
8 | GCS Decomm & removal of turbine oil reservoir & auto fill system | 23.66% | 75.6% | 0.74% | 0% | 1 | 1 | 1 | 1 | 1 | 100%
9 | BCS Instrument Air reliability upgrade | 23.66% | 48.4% | 27.93% | 0% | 1 | 1 | 1 | 1 | 1 | 100%
10 | Compressor lagging and pipe coating replacement (expand to GCS, Springhurst/BCS12/WCS A/WCS B, Euroa) | 23.66% | 76.34% | 0% | 0% | 1 | 1 | 1 | 1 | 1 | 100%
11 | Storage shed-Dandenong, Wollert & Springhurst | 28.57% | 71.43% | 0% | 0% | 1 | 1 | 1 | 1 | 1 | 100%
12 | Iona CS aftercooler augmentation | 28.57% | 37.41% | 34.02% | 0% | 1 | 1 | 1 | 1 | 1 | 100%
13 | Battery replacement | 32.67% | 14.76% | 48.02% | 4.553% | 1 | 1 | 1 | 1 | 1 | 100%
14 | Wollert CG Instrument Air Conversion | 23.66% | 56.54% | 19.8% | 0% | 1 | 1 | 1 | 1 | 1 | 100%
15 | Pit installation on LV03 bypass valves on T33 | 28.57% | 58.06% | 13.37% | 0% | 1 | 1 | 1 | 1 | 1 | 100%
16 | Dandenong water supply & fire main modification | 28.57% | 71.43% | 0% | 0% | 1 | 1 | 1 | 1 | 1 | 100%
17 | Culcairn Injection Gas Quality equipment | 28.57% | 4.661% | 66.77% | 0% | 1 | 1 | 1 | 1 | 1 | 100%
18 | Positioner Replacement | 35.1% | 22.08% | 31.94% | 10.88% | 1 | 1 | 1 | 1 | 1 | 100%
19 | VTS Safety Management Study aerial photography | 21.88% | 0% | 0% | 78.12% | 1 | 1 | 1 | 1 | 1 | 100%
20 | BCP Safety Measures for High Consequence areas-(urban growth, fracture control) | 21.88% | 48.42% | 29.7% | 0% | 1 | 1 | 1 | 1 | 1 | 100%
21 | BLP Safety Measures for High Consequence areas-(urban growth, fracture control) | 21.88% | 48.26% | 29.86% | 0% | 1 | 1 | 1 | 1 | 1 | 100%
22 | WOP Safety Measures for High Consequence areas-(urban growth, fracture control) | 21.88% | 48.11% | 30.02% | 0% | 1 | 1 | 1 | 1 | 1 | 100%
23 | ILP Safety Measures for High Consequence areas-(urban growth, fracture control) | 21.88% | 61.29% | 16.84% | 0% | 1 | 1 | 1 | 1 | 1 | 100%
24 | Turbine Overhauls | 23.66% | 76.34% | 0% | 0% | 1 | 1 | 1 | 1 | 1 | 100%
25 | Iona CS Automation replacement | 36.55% | 17.91% | 45.54% | 0% | 1 | 1 | 1 | 1 | 1 | 100%
26 | GCS Control Room and Unit Enclosure 1,2,3&4 Fire Suppression System | 23.66% | 76.34% | 0% | 0% | 1 | 1 | 1 | 1 | 1 | 100%
27 | BCS MCC Room Fire Suppression System | 23.66% | 76.34% | 0% | 0% | 1 | 1 | 1 | 1 | 1 | 100%
28 | Iona CS Control Room and Unit Enclosure Fire Suppression System | 23.66% | 76.34% | 0% | 0% | 1 | 1 | 1 | 1 | 1 | 100%
29 | Lara City Gate Control Hut Fire Suppression System | 28.57% | 71.43% | 0% | 0% | 1 | 1 | 1 | 1 | 1 | 100%
30 | BCS Control Room Fire Suppression System | 28.57% | 71.43% | 0% | 0% | 1 | 1 | 1 | 1 | 1 | 100%
31 | Emergency- BA escape sets | 21.88% | 0% | 78.12% | 0% | 1 | 1 | 1 | 1 | 1 | 100%
32 | Emergency- Response Equipment | 21.88% | 0.258% | 77.87% | 0% | 1 | 1 | 1 | 1 | 1 | 100%
33 | Emergency- Spark Proof tools | 58.88% | 0% | 41.12% | 0% | 1 | 1 | 1 | 1 | 1 | 100%
34 | Emergency - fully equipped caravan | 21.88% | 4.542% | 73.58% | 0% | 1 | 1 | 1 | 1 | 1 | 100%
35 | Emergency diesel fuel storage | 21.88% | 37% | 41.12% | 0% | 1 | 1 | 1 | 1 | 1 | 100%
36 | Vent stack for CL600 & 900 pipeline | 21.88% | 0% | 78.12% | 0% | 1 | 1 | 1 | 1 | 1 | 100%
37 | Remote CP/critical drainage bond monitoring | 33.41% | 0% | 64.43% | 2.163% | 1 | 1 | 1 | 1 | 1 | 100%
38 | BCG Un-regulated Bypass Upgrade | 23.42% | 66.99% | 9.593% | 0% | 1 | 1 | 1 | 1 | 1 | 100%
39 | Security - Physical | 37.33% | 62.67% | 0% | 0% | 1 | 1 | 1 | 1 | 1 | 100%
40 | CP - Cathodic Protection Replacement | 36.12% | 4.938% | 53.17% | 5.766% | 1 | 1 | 1 | 1 | 1 | 100%
41 | Equipment - Gas Detectors | 0% | 0% | 100% | 0% | 1 | 1 | 1 | 1 | 1 | 100%
42 | Regulator Upgrade - Lara pneumatic control system upgrade | 32.45% | 14.16% | 53.39% | 0% | 1 | 1 | 1 | 1 | 1 | 100%
43 | Hazardous Area Rectification | 11.24% | 50.56% | 38.2% | 0% | 1 | 1 | 1 | 1 | 1 | 100%
44 | Actuate MLV's in T1 areas | 21.88% | 10.89% | 62.21% | 5.017% | 1 | 1 | 1 | 1 | 1 | 100%
45 | Asbestos removal and replacement | 28.57% | 71.43% | 0% | 0% | 1 | 1 | 1 | 1 | 1 | 100%
46 | T33 non-piggable and encased sections (unknown technical solution) | 25.63% | 69.18% | 5.189% | 0% | 1 | 1 | 1 | 1 | 1 | 100%
47 | Pigging Program T57 Ballan - Ballarat | 22.3% | 74.14% | 3.564% | 0% | 1 | 1 | 1 | 1 | 1 | 100%
48 | Pigging Program T62 Derrimut - Sunbury | 22.44% | 75.1% | 2.461% | 0% | 1 | 1 | 1 | 1 | 1 | 100%
49 | Pigging Program T61 Packenham - Wollert | 22.24% | 70.48% | 7.276% | 0% | 1 | 1 | 1 | 1 | 1 | 100%
50 | Pigging Program T16 Dandenong – West Melbourne | 22.05% | 74.52% | 3.432% | 0% | 1 | 1 | 1 | 1 | 1 | 100%
51 | Pigging Program T60 Longford -Dandenong | 21.98% | 76.04% | 1.986% | 0% | 1 | 1 | 1 | 1 | 1 | 100%
52 | Pigging Program T33 South Melbourne – Brooklyn | 22.11% | 73.27% | 4.619% | 0% | 1 | 1 | 1 | 1 | 1 | 100%
53 | Pigging Program T65 Dandenong to Princes Highway Pipeline (129) | 22.29% | 69.46% | 8.251% | 0% | 1 | 1 | 1 | 1 | 1 | 100%
54 | Pigging Program T66-70 Mt Franklin -Kyneton - Bendigo | 22.28% | 74.29% | 3.427% | 0% | 1 | 1 | 1 | 1 | 1 | 100%
55 | Pigging Program T75 Wandong - Kyneton | 22.34% | 73.8% | 3.863% | 0% | 1 | 1 | 1 | 1 | 1 | 100%
56 | Pigging Program T24 Brooklyn - Corio | 22.05% | 76.35% | 1.6% | 0% | 1 | 1 | 1 | 1 | 1 | 100%
57 | Pigging Program T70 Ballan – Bendigo | 22.31% | 75.81% | 1.885% | 0% | 1 | 1 | 1 | 1 | 1 | 100%
58 | Pigging Program T60 Longford – Tyers | 22.2% | 71.49% | 6.318% | 0% | 1 | 1 | 1 | 1 | 1 | 100%
59 | Pigging Program T63 Tyers - Morwell | 22.27% | 72.57% | 5.161% | 0% | 1 | 1 | 1 | 1 | 1 | 100%
60 | Pigging Program T96 & T98 Chiltern- Rutherglen – Koonoomoo | 22.35% | 74.99% | 2.669% | 0% | 1 | 1 | 1 | 1 | 1 | 100%
61 | Pigging Program T118 Trugannina-Plumpton | 22.34% | 71.5% | 6.156% | 0% | 1 | 1 | 1 | 1 | 1 | 100%
62 | Pigging Program James Street to Laverton Pipeline (253) | 22.41% | 72.66% | 4.933% | 0% | 1 | 1 | 1 | 1 | 1 | 100%
63 | Pigging Program Tyres to Maryvale (67) | 22.5% | 74.76% | 2.735% | 0% | 1 | 1 | 1 | 1 | 1 | 100%
64 | Pigging Program T108 Newport | 22.38% | 71.63% | 5.988% | 0% | 1 | 1 | 1 | 1 | 1 | 100%
65 | Pigging Program Inner Ring Main | 22.33% | 72.29% | 5.379% | 0% | 1 | 1 | 1 | 1 | 1 | 100%
66 | Pigging Program T1 Morwell - Dandenong Repair Program | 21.88% | 75.82% | 2.305% | 0% | 1 | 1 | 1 | 1 | 1 | 100%
67 | Pig Trap Installation James Street to Laverton Pipeline (253) | 13.54% | 57.38% | 29.08% | 0% | 1 | 1 | 1 | 1 | 1 | 100%
68 | Pig Trap Installation Tyers to Maryvale Pipeline (67) | 13.55% | 59.01% | 27.44% | 0% | 1 | 1 | 1 | 1 | 1 | 100%
69 | Pig Trap Installation Trugannina to Plumpton | 14.29% | 53.79% | 31.93% | 0% | 1 | 1 | 1 | 1 | 1 | 100%
70 | Liquid Management - Brooklyn | 29.27% | 55.05% | 15.68% | 0% | 1 | 1 | 1 | 1 | 1 | 100%
71 | Liquid Management - Pakenham | 29.27% | 55.05% | 15.68% | 0% | 1 | 1 | 1 | 1 | 1 | 100%
72 | RTU replacement | 71.47% | 16.49% | 9.837% | 2.196% | 1 | 1 | 1 | 1 | 1 | 100%
73 | Pipe Support replacement | 28.57% | 71.43% | 0% | 0% | 1 | 1 | 1 | 1 | 1 | 100%
74 | HMI upgrade to CLEAR SCADA at BCS, SCS and WCS & CG, Longford | 58.51% | 1.313% | 35.45% | 4.727% | 1 | 1 | 1 | 1 | 1 | 100%
75 | BCS Unit 12 Inlet Filter Replacement/Augmentation | 23.66% | 39.83% | 36.51% | 0% | 1 | 1 | 1 | 1 | 1 | 100%
76 | Coogee decommissioning, Step Change | 21.88% | 78.12% | 0.006765% | 0% | 1 | 1 | 1 | 1 | 1 | 100%
77 | Compressor Type B Compliance | 33.45% | 30.5% | 36.05% | 0% | 1 | 1 | 1 | 1 | 1 | 100%
78 | Dandenong LNG Isolation Valve Upgrade | 29.4% | 40.97% | 29.64% | 0% | 1 | 1 | 1 | 1 | 1 | 100%
79 | Morwell-Dandenong Fatigue Crack Detection from High Loads | 25.56% | 67.79% | 6.653% | 0% | 1 | 1 | 1 | 1 | 1 | 100%
80 | Unibolt Enclosure Replacement | 28.57% | 60.18% | 11.25% | 0% | 1 | 1 | 1 | 1 | 1 | 100%
81 | WAN Upgrade (Satellite project) | 46.57% | 18.2% | 29.89% | 5.355% | 1 | 1 | 1 | 1 | 1 | 100%
82 | Warragul Looping 6" (Southern Route) | 34.54% | 12.78% | 52.68% | 0% | 1 | 1 | 1 | 1 | 1 | 100%
83 | Anglesea Pipeline Extension | 49.2% | 0% | 30.91% | 19.88% | 1 | 1 | 1 | 1 | 1 | 100%
84 | BCS Reconfiguration (2B) | 54.96% | 0% | 45.04% | 0% | 1 | 1 | 1 | 1 | 1 | 100%
85 | Winchelsea Bi-Directional Flow | 33.73% | 25.19% | 32.27% | 8.808% | 1 | 1 | 1 | 1 | 1 | 100%
86 | WORM (50km x 20" Pipeline) | 10.58% | 0% | 33.69% | 55.73% | 1 | 1 | 1 | 1 | 1 | 100%
87 | WORM (C50 at Wollert) | 37.05% | 0% | 60.4% | 2.553% | 1 | 1 | 1 | 1 | 1 | 100%
88 | WORM (PRS at Wollert) | 42.22% | 0% | 54.63% | 3.152% | 1 | 1 | 1 | 1 | 1 | 100%
89 | Enterprise Content Management | 30% | 65% | 5% | 0% | 1 | 1 | 1 | 1 | 1 | 100%
90 | Victoria CRE | 30% | 65% | 5% | 0% | 1 | 1 | 1 | 1 | 1 | 100%
91 | APA Grid Energy Components Upgrade | 30% | 65% | 5% | 0% | 1 | 1 | 1 | 1 | 1 | 100%
92 | APA Grid Extend Program | 30% | 65% | 5% | 0% | 1 | 1 | 1 | 1 | 1 | 100%
93 | APA Grid Services Initiatives Program | 30% | 65% | 5% | 0% | 1 | 1 | 1 | 1 | 1 | 100%
94 | Hyperion Upgrade to 11.1.2.4 | 30% | 65% | 5% | 0% | 1 | 1 | 1 | 1 | 1 | 100%
95 | BI - Transmission Dashboard and Enterprise Pilot | 30% | 65% | 5% | 0% | 1 | 1 | 1 | 1 | 1 | 100%
96 | HR Systems Refresh | 30% | 65% | 5% | 0% | 1 | 1 | 1 | 1 | 1 | 100%
97 | Transmission EAM Data Management Tool | 30% | 65% | 5% | 0% | 1 | 1 | 1 | 1 | 1 | 100%
98 | SharePoint Upgrade | 30% | 65% | 5% | 0% | 1 | 1 | 1 | 1 | 1 | 100%
99 | eForm Digitisation | 30% | 65% | 5% | 0% | 1 | 1 | 1 | 1 | 1 | 100%
100 | Historian Upgrade - version 2012 to 2015 | 30% | 65% | 5% | 0% | 1 | 1 | 1 | 1 | 1 | 100%
101 | Hazardous Area Platform | 30% | 65% | 5% | 0% | 1 | 1 | 1 | 1 | 1 | 100%
102 | PPM Refresh | 30% | 65% | 5% | 0% | 1 | 1 | 1 | 1 | 1 | 100%
103 | BizTalk Upgrade FY2018 | 30% | 65% | 5% | 0% | 1 | 1 | 1 | 1 | 1 | 100%
104 | Automated Testing Tool | 30% | 65% | 5% | 0% | 1 | 1 | 1 | 1 | 1 | 100%
105 | Code Management Software | 30% | 65% | 5% | 0% | 1 | 1 | 1 | 1 | 1 | 100%
106 | CRM Upgrade | 30% | 65% | 5% | 0% | 1 | 1 | 1 | 1 | 1 | 100%
107 | X-Info Aware Version 2 | 30% | 65% | 5% | 0% | 1 | 1 | 1 | 1 | 1 | 100%
108 | Supplier Qualification and Compliance | 30% | 65% | 5% | 0% | 1 | 1 | 1 | 1 | 1 | 100%
109 | Oracle eBS Upgrade to 12.2 | 30% | 65% | 5% | 0% | 1 | 1 | 1 | 1 | 1 | 100%
110 | BizTalk System Upgrade 2020 | 30% | 65% | 5% | 0% | 1 | 1 | 1 | 1 | 1 | 100%
111 | Applications Renewal | 30% | 65% | 5% | 0% | 1 | 1 | 1 | 1 | 1 | 100%
112 | Infrastructure Renewal | 30% | 65% | 5% | 0% | 1 | 1 | 1 | 1 | 1 | 100%
113 | Dandenong Relocation | 50% | 0% | 50% | 0% | 1 | 1 | 1 | 1 | 1 | 100%
- |  | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0%
- |  | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0%
- |  | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0%
- |  | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0%
- |  | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0%
- |  | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0%
- |  | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0%
- |  | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0%
- |  | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0%
- |  | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0%
- |  | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0%
- |  | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0%
- |  | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0%
- |  | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0%
- |  | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0%
- |  | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0%
- |  | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0%
- |  | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0%
- |  | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0%
- |  | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0%
- |  | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0%
- |  | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0%
- |  | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0%
- |  | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0%
- |  | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0%
- |  | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0%
- |  | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0%
- |  | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0%
- |  | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0%
- |  | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0%
- |  | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0%
- |  | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0%
- |  | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0%
- |  | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0%
- |  | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0%
- |  | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0%
- |  | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0%
- |  | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0%
- |  | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0%
- |  | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0%
- |  | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0%
- |  | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0%
- |  | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0%
- |  | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0%
- |  | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0%
- |  | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0%
- |  | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0%
- |  | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0%
- |  | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0%
- |  | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0%
- |  | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0%
- |  | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0%
- |  | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0%
- |  | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0%
- |  | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0%
- |  | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0%
- |  | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0%
- |  | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0%
- |  | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0%
- |  | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0%
- |  | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0%
- |  | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0%
- |  | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0%
- |  | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0%
- |  | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0%
- |  | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0%
- |  | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0%
- |  | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0%
- |  | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0%
- |  | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0%
- |  | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0%
- |  | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0%
- |  | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0%
- |  | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0%
- |  | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0%

## 5.5 Calc│Escalated capex
| 5.5 Calc│Escalated capex | Check pickup all projects | TRUE |  | Check values | TRUE | TRUE | TRUE | TRUE | TRUE | 215.0091
Capex # | Project Name | Project number | Asset class | Asset category |  | 2018 | 2019 | 2020 | 2021 | 2022 | Forecast total | Zones
1 | All CS buffer Air shutoff system for all compressors | 202 | Compressors | Replacement |  | 0.39441 | 0.19721 | 0 | 0 | 0 | 0.59162
2 | WCS A Process Safety | 203 | Compressors | Replacement |  | 0 | 0 | 1.0802 | 0 | 0 | 1.0802
3 | Brooklyn Compressor Station | 204 | Compressors | Replacement |  | 0 | 0 | 2.3737 | 2.3737 | 2.3737 | 7.1211
4 | Compressor Station Vent Stack Upgrade (BCS, WCS, GCS, SCS) | 205 | Compressors | Replacement |  | 0 | 0.34137 | 0.34137 | 0.34137 | 0 | 1.0241
5 | Longford Odorant Pump Power Gas Upgrade | 206 | Odourant Plants | Replacement |  | 0.07808 | 0 | 0 | 0 | 0 | 0.07808
6 | GCS compressor unit vent valves & actuators replacement | 207a | Compressors | Replacement |  | 0.14402 | 0 | 0 | 0 | 0 | 0.14402
7 | GCS unit discharge and station manifold check valves replacement | 207b | Compressors | Replacement |  | 0 | 0 | 0.93192 | 0 | 0 | 0.93192
8 | GCS Decomm & removal of turbine oil reservoir & auto fill system | 207c | Compressors | Replacement |  | 0 | 0.090894 | 0 | 0 | 0 | 0.090894
9 | BCS Instrument Air reliability upgrade | 208 | Compressors | Replacement |  | 0.096899 | 0 | 0 | 0 | 0 | 0.096899
10 | Compressor lagging and pipe coating replacement (expand to GCS, Springhurst/BCS12/WCS A/WCS B, Euroa) | 209 | Compressors | Replacement |  | 0.14973 | 0.14973 | 0.14973 | 0.14973 | 0.14973 | 0.74867
11 | Storage shed-Dandenong, Wollert & Springhurst | 210 | Buildings | Non-System |  | 0 | 0.62094 | 0.62094 | 0.62094 | 0 | 1.8628
12 | Iona CS aftercooler augmentation | 211 | Compressors | Replacement |  | 1.7114 | 0 | 0 | 0 | 0 | 1.7114
13 | Battery replacement | 212 | Other | Replacement |  | 0.072619 | 0.072619 | 0.072619 | 0.072619 | 0.072619 | 0.3631
14 | Wollert CG Instrument Air Conversion | 216 | City Gates & Field Regs | Replacement |  | 0 | 0 | 0 | 0.521 | 0 | 0.521
15 | Pit installation on LV03 bypass valves on T33 | 220 | Pipelines | Replacement |  | 0 | 0 | 0.23853 | 0 | 0 | 0.23853
16 | Dandenong water supply & fire main modification | 223 | Buildings | Non-System |  | 0.31028 | 0 | 0 | 0 | 0 | 0.31028
17 | Culcairn Injection Gas Quality equipment | 224 | Gas Quality | Replacement |  | 1.0063 | 0 | 0 | 0 | 0 | 1.0063
18 | Positioner Replacement | 225 | Other | Replacement |  | 0.10487 | 0.10487 | 0.10487 | 0.10487 | 0.10487 | 0.52433
19 | VTS Safety Management Study aerial photography | 227 | Other | Replacement |  | 0.16786 | 0.002873 | 0 | 0 | 0 | 0.17074
20 | BCP Safety Measures for High Consequence areas-(urban growth, fracture control) | 230a |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
21 | BLP Safety Measures for High Consequence areas-(urban growth, fracture control) | 230b |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
22 | WOP Safety Measures for High Consequence areas-(urban growth, fracture control) | 230c |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
23 | ILP Safety Measures for High Consequence areas-(urban growth, fracture control) | 230e |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
24 | Turbine Overhauls | 235 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
25 | Iona CS Automation replacement | 236 | Compressors | Replacement |  | 0 | 0 | 1.2124 | 0 | 0 | 1.2124
26 | GCS Control Room and Unit Enclosure 1,2,3&4 Fire Suppression System | 237a | Compressors | Replacement |  | 0.27748 | 0 | 0 | 0 | 0 | 0.27748
27 | BCS MCC Room Fire Suppression System | 237b | Compressors | Replacement |  | 0 | 0 | 0.27748 | 0 | 0 | 0.27748
28 | Iona CS Control Room and Unit Enclosure Fire Suppression System | 237d | Compressors | Replacement |  | 0 | 0 | 0 | 0.27748 | 0 | 0.27748
29 | Lara City Gate Control Hut Fire Suppression System | 237e | City Gates & Field Regs | Replacement |  | 0 | 0 | 0 | 0 | 0.084727 | 0.084727
30 | BCS Control Room Fire Suppression System | 237f | Compressors | Non-System |  | 0 | 0 | 0 | 0 | 0.084727 | 0.084727
31 | Emergency- BA escape sets | 239a | Other | Replacement |  | 0.018265 | 0 | 0 | 0 | 0 | 0.018265
32 | Emergency- Response Equipment | 239b | Other | Replacement |  | 0.26637 | 0.26637 | 0.26637 | 0.26637 | 0.26637 | 1.3319
33 | Emergency- Spark Proof tools | 239c | Other | Replacement |  | 0.0018622 | 0.0018622 | 0.0018622 | 0.0018622 | 0.0018622 | 0.0093108
34 | Emergency - fully equipped caravan | 239d | Other | Replacement |  | 0 | 0 | 0.10325 | 0 | 0 | 0.10325
35 | Emergency diesel fuel storage | 239e | Other | Replacement |  | 0 | 0 | 0 | 0.11783 | 0 | 0.11783
36 | Vent stack for CL600 & 900 pipeline | 240 | Pipelines | Replacement |  | 0.21733 | 0 | 0 | 0 | 0 | 0.21733
37 | Remote CP/critical drainage bond monitoring | 241 | Other | Replacement |  | 0.59209 | 0.062465 | 0.062465 | 0.062465 | 0.062465 | 0.84195
38 | BCG Un-regulated Bypass Upgrade | 242 | City Gates & Field Regs | Replacement |  | 0 | 0 | 0.35372 | 0 | 0 | 0.35372
39 | Security - Physical | 243 | Buildings | Non-System |  | 0.34957 | 0.34957 | 0.34957 | 0.34957 | 0.34957 | 1.7479
40 | CP - Cathodic Protection Replacement | 244 | Other | Replacement |  | 0.24019 | 0.24019 | 0.24019 | 0.24019 | 0.24019 | 1.2009
41 | Equipment - Gas Detectors | 245 | Other | Non-System |  | 0 | 0 | 0.023928 | 0.023928 | 0 | 0.047856
42 | Regulator Upgrade - Lara pneumatic control system upgrade | 247 | City Gates & Field Regs | Replacement |  | 0 | 0.63983 | 0 | 0 | 0 | 0.63983
43 | Hazardous Area Rectification | 249 | Other | Replacement |  | 0.18391 | 0.18391 | 0.18391 | 0.18391 | 0.18391 | 0.91957
44 | Actuate MLV's in T1 areas | 250 | Pipelines | Replacement |  | 0.98849 | 0.98849 | 0 | 0 | 0 | 1.977
45 | Asbestos removal and replacement | 251 | Other | Non-System |  | 0.072326 | 0.072326 | 0.072326 | 0.072326 | 0.072326 | 0.36163
46 | T33 non-piggable and encased sections (unknown technical solution) | 257 | Other | Replacement |  | 0.1568 | 0.1568 | 0.1568 | 0.1568 | 0 | 0.6272
47 | Pigging Program T57 Ballan - Ballarat | 258a | Other | Replacement |  | 0.58353 | 0 | 0 | 0 | 0 | 0.58353
48 | Pigging Program T62 Derrimut - Sunbury | 258b | Other | Replacement |  | 0.43995 | 0 | 0 | 0 | 0 | 0.43995
49 | Pigging Program T61 Packenham - Wollert | 258c | Other | Replacement |  | 0 | 0.67149 | 0 | 0 | 0 | 0.67149
50 | Pigging Program T16 Dandenong – West Melbourne | 258d | Other | Replacement |  | 0 | 0 | 0 | 1.4235 | 0 | 1.4235
51 | Pigging Program T60 Longford -Dandenong | 258e | Other | Replacement |  | 0 | 0 | 0 | 0 | 2.46 | 2.46
52 | Pigging Program T33 South Melbourne – Brooklyn | 258f | Other | Replacement |  | 0 | 0 | 0 | 1.0577 | 0 | 1.0577
53 | Pigging Program T65 Dandenong to Princes Highway Pipeline (129) | 258g | Other | Replacement |  | 0.59214 | 0 | 0 | 0 | 0 | 0.59214
54 | Pigging Program T66-70 Mt Franklin -Kyneton - Bendigo | 258i | Other | Replacement |  | 0 | 0.60685 | 0 | 0 | 0 | 0.60685
55 | Pigging Program T75 Wandong - Kyneton | 258k | Other | Replacement |  | 0 | 0.53833 | 0 | 0 | 0 | 0.53833
56 | Pigging Program T24 Brooklyn - Corio | 258l | Other | Replacement |  | 0 | 0 | 0 | 1.4265 | 0 | 1.4265
57 | Pigging Program T70 Ballan – Bendigo | 258m | Other | Replacement |  | 0 | 0 | 0.57445 | 0 | 0 | 0.57445
58 | Pigging Program T60 Longford – Tyers | 258n | Other | Replacement |  | 0 | 0 | 0 | 0 | 0.77326 | 0.77326
59 | Pigging Program T63 Tyers - Morwell | 258o | Other | Replacement |  | 0 | 0 | 0 | 0.63139 | 0 | 0.63139
60 | Pigging Program T96 & T98 Chiltern- Rutherglen – Koonoomoo | 258p | Other | Replacement |  | 0 | 0 | 0 | 0 | 0.52751 | 0.52751
61 | Pigging Program T118 Trugannina-Plumpton | 258q | Other | Replacement |  | 0 | 0 | 0 | 0 | 0.52935 | 0.52935
62 | Pigging Program James Street to Laverton Pipeline (253) | 258s | Other | Replacement |  | 0 | 0.46265 | 0 | 0 | 0 | 0.46265
63 | Pigging Program Tyres to Maryvale (67) | 258u | Other | Replacement |  | 0.39592 | 0 | 0 | 0 | 0 | 0.39592
64 | Pigging Program T108 Newport | 258v | Other | Replacement |  | 0.4896 | 0 | 0 | 0 | 0 | 0.4896
65 | Pigging Program Inner Ring Main | 258w | Other | Replacement |  | 0 | 0 | 0.0036303 | 0 | 0 | 0.0036303
66 | Pigging Program T1 Morwell - Dandenong Repair Program | 258x | Other | Replacement |  | 0.95627 | 0.1799 | 0 | 0 | 0 | 1.1362
67 | Pig Trap Installation James Street to Laverton Pipeline (253) | 259a |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
68 | Pig Trap Installation Tyers to Maryvale Pipeline (67) | 259d |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
69 | Pig Trap Installation Trugannina to Plumpton | 259g |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
70 | Liquid Management - Brooklyn | 260a | City Gates & Field Regs | Replacement |  | 0 | 0 | 0 | 0 | 0.16222 | 0.16222
71 | Liquid Management - Pakenham | 260b | City Gates & Field Regs | Replacement |  | 0 | 0 | 0 | 0.16222 | 0 | 0.16222
72 | RTU replacement | 262 | Other | Replacement |  | 0.14653 | 0.14653 | 0.14653 | 0.14653 | 0.14653 | 0.73264
73 | Pipe Support replacement | 263 | Pipelines | Replacement |  | 0.17029 | 0.17029 | 0.17029 | 0.17029 | 0.17029 | 0.85143
74 | HMI upgrade to CLEAR SCADA at BCS, SCS and WCS & CG, Longford | 264 | Other | Non-System |  | 0.062952 | 0.062952 | 0.062952 | 0.062952 | 0.062952 | 0.31476
75 | BCS Unit 12 Inlet Filter Replacement/Augmentation | 267 | Compressors | Replacement |  | 0.65684 | 0 | 0 | 0 | 0 | 0.65684
76 | Coogee decommissioning, Step Change | 268 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
77 | Compressor Type B Compliance | 271 | Compressors | Replacement |  | 0.22392 | 0.22392 | 0.22392 | 0.22392 | 0.22392 | 1.1196
78 | Dandenong LNG Isolation Valve Upgrade | 275 | Pipelines | Replacement |  | 0.67058 | 0 | 0 | 0 | 0 | 0.67058
79 | Morwell-Dandenong Fatigue Crack Detection from High Loads | 276 | Pipelines | Replacement |  | 0.2695 | 0 | 0 | 0 | 0 | 0.2695
80 | Unibolt Enclosure Replacement | 277 | Other | Replacement |  | 0.045941 | 0.045941 | 0.045941 | 0.045941 | 0.045941 | 0.22971
81 | WAN Upgrade (Satellite project) | 278 | Other | Non-System |  | 0.97845 | 0.97845 | 0.97845 | 0.97845 | 0.97845 | 4.8923
82 | Warragul Looping 6" (Southern Route) | Warragul 6" (Sth) | Pipelines | Augmentation |  | 0 | 2.6864 | 0.9299 | 0 | 0 | 3.6163
83 | Anglesea Pipeline Extension | Anglesea | Pipelines | Augmentation |  | 17.1769 | 0 | 0 | 0 | 0 | 17.1769
84 | BCS Reconfiguration (2B) | BCS Reconfig (2A) | Compressors | Augmentation |  | 2.0253 | 0 | 0 | 0 | 0 | 2.0253
85 | Winchelsea Bi-Directional Flow | Winchelsea Bi-Direction | Compressors | Augmentation |  | 1.4678 | 0 | 0 | 0 | 0 | 1.4678
86 | WORM (50km x 20" Pipeline) | WORM (Pipeline) | Pipelines | Augmentation |  | 16.4398 | 29.9605 | 50.4362 | 0 | 0 | 96.8365
87 | WORM (C50 at Wollert) | WORM (C50) | Compressors | Augmentation |  | 7.2777 | 12.494 | 6.3819 | 0 | 0 | 26.1536
88 | WORM (PRS at Wollert) | WORM (PRS) | City Gates & Field Regs | Augmentation |  | 0 | 1.6963 | 2.0243 | 0 | 0 | 3.7206
89 | Enterprise Content Management | APA |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
90 | Victoria CRE | APA |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 1 Longford to Tyers (loop end)
91 | APA Grid Energy Components Upgrade | APA |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 3 Tyers to Morwell & Maryvale lateral
92 | APA Grid Extend Program | APA | Other | Non-System |  | 0.2699 | 0 | 0 | 0 | 0 | 0.2699
93 | APA Grid Services Initiatives Program | APA |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 22 Deer Park to Sunbury
94 | Hyperion Upgrade to 11.1.2.4 | APA |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 21 Wollert to Keon Park
95 | BI - Transmission Dashboard and Enterprise Pilot | APA | Other | Non-System |  | 0.21592 | 0.16194 | 0 | 0 | 0 | 0.37786
96 | HR Systems Refresh | APA |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
97 | Transmission EAM Data Management Tool | APA |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
98 | SharePoint Upgrade | APA | Other | Non-System |  | 0.026318 | 0 | 0 | 0 | 0 | 0.026318
99 | eForm Digitisation | APA | Other | Non-System |  | 0 | 0 | 0.17356 | 0.44775 | 0 | 0.62131
100 | Historian Upgrade - version 2012 to 2015 | APA |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
101 | Hazardous Area Platform | APA | Other | Non-System |  | 0.16761 | 0 | 0 | 0 | 0 | 0.16761
102 | PPM Refresh | APA | Other | Non-System |  | 0.32388 | 0 | 0 | 0 | 0 | 0.32388
103 | BizTalk Upgrade FY2018 | APA | Other | Non-System |  | 0 | 0.0653 | 0.072433 | 0 | 0 | 0.13773
104 | Automated Testing Tool | APA | Other | Non-System |  | 0.071986 | 0 | 0 | 0 | 0 | 0.071986
105 | Code Management Software | APA | Other | Non-System |  | 0.097804 | 0 | 0 | 0 | 0 | 0.097804
106 | CRM Upgrade | APA | Other | Non-System |  | 0.15203 | 0.0063748 | 0 | 0 | 0 | 0.1584
107 | X-Info Aware Version 2 | APA | Other | Non-System |  | 0.046432 | 0 | 0 | 0 | 0 | 0.046432
108 | Supplier Qualification and Compliance | APA | Other | Non-System |  | 0.07534 | 0.020033 | 0 | 0 | 0 | 0.095373
109 | Oracle eBS Upgrade to 12.2 | APA | Other | Non-System |  | 0.028838 | 0.13778 | 0 | 0 | 0 | 0.16662
110 | BizTalk System Upgrade 2020 | APA | Other | Non-System |  | 0 | 0.0653 | 0.072433 | 0 | 0 | 0.13773
111 | Applications Renewal | APA | Other | Non-System |  | 0.74493 | 0.93062 | 0.74493 | 0.93062 | 0.74493 | 4.096
112 | Infrastructure Renewal | APA | Other | Non-System |  | 0.24291 | 0.08097 | 0.08097 | 0.08097 | 0 | 0.48582
113 | Dandenong Relocation | APA |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
- |  | - |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
- |  | - |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
- |  | - |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
- |  | - |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
- |  | - |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
- |  | - |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
- |  | - |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
- |  | - |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
- |  | - |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
- |  | - |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
- |  | - |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
- |  | - |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
- |  | - |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
- |  | - |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
- |  | - |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
- |  | - |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
- |  | - |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
- |  | - |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
- |  | - |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
- |  | - |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
- |  | - |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
- |  | - |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
- |  | - |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
- |  | - |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
- |  | - |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
- |  | - |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
- |  | - |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
- |  | - |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
- |  | - |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
- |  | - |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
- |  | - |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
- |  | - |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
- |  | - |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
- |  | - |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
- |  | - |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
- |  | - |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
- |  | - |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
- |  | - |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
- |  | - |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
- |  | - |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
- |  | - |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
- |  | - |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
- |  | - |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
- |  | - |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
- |  | - |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
- |  | - |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
- |  | - |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
- |  | - |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
- |  | - |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
- |  | - |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
- |  | - |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
- |  | - |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
- |  | - |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
- |  | - |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
- |  | - |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
- |  | - |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
- |  | - |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
- |  | - |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
- |  | - |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
- |  | - |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
- |  | - |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
- |  | - |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
- |  | - |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
- |  | - |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
- |  | - |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
- |  | - |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
- |  | - |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
- |  | - |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
- |  | - |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
- |  | - |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
- |  | - |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
- |  | - |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
- |  | - |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
- |  | - |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
- |  | - |  |  |  | 0 | 0 | 0 | 0 | 0 | 0

## 5.6 Calc│As Commissioned
| 5.6 Calc│As Commissioned | Check pickup all projects | TRUE |  | Check values | [5 empty] | 225.4761
Capex # | Project Name | Project number | Asset class | Asset category | Completion Year | 2018 | 2019 | 2020 | 2021 | 2022 | Forecast total
1 | All CS buffer Air shutoff system for all compressors | 202 | Compressors | Replacement | 2019 | 0 | 0.59162 | 0 | 0 | 0 | 0.59162
2 | WCS A Process Safety | 203 | Compressors | Replacement | 2020 | 0 | 0 | 1.0802 | 0 | 0 | 1.0802
3 | Brooklyn Compressor Station | 204 | Compressors | Replacement | 2018 | 7.1211 | 0 | 0 | 0 | 0 | 7.1211
4 | Compressor Station Vent Stack Upgrade (BCS, WCS, GCS, SCS) | 205 | Compressors | Replacement | 2021 | 0 | 0 | 0 | 1.0241 | 0 | 1.0241
5 | Longford Odorant Pump Power Gas Upgrade | 206 | Odourant Plants | Replacement | 2018 | 0.07808 | 0 | 0 | 0 | 0 | 0.07808
6 | GCS compressor unit vent valves & actuators replacement | 207a | Compressors | Replacement | 2018 | 0.14402 | 0 | 0 | 0 | 0 | 0.14402
7 | GCS unit discharge and station manifold check valves replacement | 207b | Compressors | Replacement | 2020 | 0 | 0 | 0.93192 | 0 | 0 | 0.93192
8 | GCS Decomm & removal of turbine oil reservoir & auto fill system | 207c | Compressors | Replacement | 2019 | 0 | 0.090894 | 0 | 0 | 0 | 0.090894
9 | BCS Instrument Air reliability upgrade | 208 | Compressors | Replacement | 2018 | 0.096899 | 0 | 0 | 0 | 0 | 0.096899
10 | Compressor lagging and pipe coating replacement (expand to GCS, Springhurst/BCS12/WCS A/WCS B, Euroa) | 209 | Compressors | Replacement | incurred | 0.14973 | 0.14973 | 0.14973 | 0.14973 | 0.14973 | 0.74867
11 | Storage shed-Dandenong, Wollert & Springhurst | 210 | Buildings | Non-System | 2021 | 0 | 0 | 0 | 1.8628 | 0 | 1.8628
12 | Iona CS aftercooler augmentation | 211 | Compressors | Replacement | 2021 | 0 | 0 | 0 | 1.7114 | 0 | 1.7114
13 | Battery replacement | 212 | Other | Replacement | incurred | 0.072619 | 0.072619 | 0.072619 | 0.072619 | 0.072619 | 0.3631
14 | Wollert CG Instrument Air Conversion | 216 | City Gates & Field Regs | Replacement | 2021 | 0 | 0 | 0 | 0.521 | 0 | 0.521
15 | Pit installation on LV03 bypass valves on T33 | 220 | Pipelines | Replacement | 2020 | 0 | 0 | 0.23853 | 0 | 0 | 0.23853
16 | Dandenong water supply & fire main modification | 223 | Buildings | Non-System | 2018 | 0.31028 | 0 | 0 | 0 | 0 | 0.31028
17 | Culcairn Injection Gas Quality equipment | 224 | Gas Quality | Replacement | 2018 | 1.0063 | 0 | 0 | 0 | 0 | 1.0063
18 | Positioner Replacement | 225 | Other | Replacement | incurred | 0.10487 | 0.10487 | 0.10487 | 0.10487 | 0.10487 | 0.52433
19 | VTS Safety Management Study aerial photography | 227 | Other | Replacement | 2019 | 0 | 0.17074 | 0 | 0 | 0 | 0.17074
20 | BCP Safety Measures for High Consequence areas-(urban growth, fracture control) | 230a |  |  | 2019 | 0 | 0 | 0 | 0 | 0 | 0
21 | BLP Safety Measures for High Consequence areas-(urban growth, fracture control) | 230b |  |  | 2019 | 0 | 0 | 0 | 0 | 0 | 0
22 | WOP Safety Measures for High Consequence areas-(urban growth, fracture control) | 230c |  |  | 2019 | 0 | 0 | 0 | 0 | 0 | 0
23 | ILP Safety Measures for High Consequence areas-(urban growth, fracture control) | 230e |  |  | 2019 | 0 | 0 | 0 | 0 | 0 | 0
24 | Turbine Overhauls | 235 |  |  | 2022 | 0 | 0 | 0 | 0 | 0 | 0
25 | Iona CS Automation replacement | 236 | Compressors | Replacement | 2020 | 0 | 0 | 1.2124 | 0 | 0 | 1.2124
26 | GCS Control Room and Unit Enclosure 1,2,3&4 Fire Suppression System | 237a | Compressors | Replacement | 2018 | 0.27748 | 0 | 0 | 0 | 0 | 0.27748
27 | BCS MCC Room Fire Suppression System | 237b | Compressors | Replacement | 2020 | 0 | 0 | 0.27748 | 0 | 0 | 0.27748
28 | Iona CS Control Room and Unit Enclosure Fire Suppression System | 237d | Compressors | Replacement | 2021 | 0 | 0 | 0 | 0.27748 | 0 | 0.27748
29 | Lara City Gate Control Hut Fire Suppression System | 237e | City Gates & Field Regs | Replacement | 2022 | 0 | 0 | 0 | 0 | 0.084727 | 0.084727
30 | BCS Control Room Fire Suppression System | 237f | Compressors | Non-System | 2022 | 0 | 0 | 0 | 0 | 0.084727 | 0.084727
31 | Emergency- BA escape sets | 239a | Other | Replacement | 2018 | 0.018265 | 0 | 0 | 0 | 0 | 0.018265
32 | Emergency- Response Equipment | 239b | Other | Replacement | incurred | 0.26637 | 0.26637 | 0.26637 | 0.26637 | 0.26637 | 1.3319
33 | Emergency- Spark Proof tools | 239c | Other | Replacement | incurred | 0.0018622 | 0.0018622 | 0.0018622 | 0.0018622 | 0.0018622 | 0.0093108
34 | Emergency - fully equipped caravan | 239d | Other | Replacement | 2020 | 0 | 0 | 0.10325 | 0 | 0 | 0.10325
35 | Emergency diesel fuel storage | 239e | Other | Replacement | 2021 | 0 | 0 | 0 | 0.11783 | 0 | 0.11783
36 | Vent stack for CL600 & 900 pipeline | 240 | Pipelines | Replacement | 2018 | 0.21733 | 0 | 0 | 0 | 0 | 0.21733
37 | Remote CP/critical drainage bond monitoring | 241 | Other | Replacement | incurred | 0.59209 | 0.062465 | 0.062465 | 0.062465 | 0.062465 | 0.84195
38 | BCG Un-regulated Bypass Upgrade | 242 | City Gates & Field Regs | Replacement | 2020 | 0 | 0 | 0.35372 | 0 | 0 | 0.35372
39 | Security - Physical | 243 | Buildings | Non-System | incurred | 0.34957 | 0.34957 | 0.34957 | 0.34957 | 0.34957 | 1.7479
40 | CP - Cathodic Protection Replacement | 244 | Other | Replacement | incurred | 0.24019 | 0.24019 | 0.24019 | 0.24019 | 0.24019 | 1.2009
41 | Equipment - Gas Detectors | 245 | Other | Non-System | 2021 | 0 | 0 | 0 | 0.047856 | 0 | 0.047856
42 | Regulator Upgrade - Lara pneumatic control system upgrade | 247 | City Gates & Field Regs | Replacement | 2019 | 0 | 0.63983 | 0 | 0 | 0 | 0.63983
43 | Hazardous Area Rectification | 249 | Other | Replacement | incurred | 0.18391 | 0.18391 | 0.18391 | 0.18391 | 0.18391 | 0.91957
44 | Actuate MLV's in T1 areas | 250 | Pipelines | Replacement | 2019 | 0 | 1.977 | 0 | 0 | 0 | 1.977
45 | Asbestos removal and replacement | 251 | Other | Non-System | incurred | 0.072326 | 0.072326 | 0.072326 | 0.072326 | 0.072326 | 0.36163
46 | T33 non-piggable and encased sections (unknown technical solution) | 257 | Other | Replacement | incurred | 0.1568 | 0.1568 | 0.1568 | 0.1568 | 0 | 0.6272
47 | Pigging Program T57 Ballan - Ballarat | 258a | Other | Replacement | 2018 | 0.58353 | 0 | 0 | 0 | 0 | 0.58353
48 | Pigging Program T62 Derrimut - Sunbury | 258b | Other | Replacement | 2018 | 0.43995 | 0 | 0 | 0 | 0 | 0.43995
49 | Pigging Program T61 Packenham - Wollert | 258c | Other | Replacement | 2019 | 0 | 0.67149 | 0 | 0 | 0 | 0.67149
50 | Pigging Program T16 Dandenong – West Melbourne | 258d | Other | Replacement | 2021 | 0 | 0 | 0 | 1.4235 | 0 | 1.4235
51 | Pigging Program T60 Longford -Dandenong | 258e | Other | Replacement | 2022 | 0 | 0 | 0 | 0 | 2.46 | 2.46
52 | Pigging Program T33 South Melbourne – Brooklyn | 258f | Other | Replacement | 2021 | 0 | 0 | 0 | 1.0577 | 0 | 1.0577
53 | Pigging Program T65 Dandenong to Princes Highway Pipeline (129) | 258g | Other | Replacement | 2018 | 0.59214 | 0 | 0 | 0 | 0 | 0.59214
54 | Pigging Program T66-70 Mt Franklin -Kyneton - Bendigo | 258i | Other | Replacement | 2019 | 0 | 0.60685 | 0 | 0 | 0 | 0.60685
55 | Pigging Program T75 Wandong - Kyneton | 258k | Other | Replacement | 2019 | 0 | 0.53833 | 0 | 0 | 0 | 0.53833
56 | Pigging Program T24 Brooklyn - Corio | 258l | Other | Replacement | 2021 | 0 | 0 | 0 | 1.4265 | 0 | 1.4265
57 | Pigging Program T70 Ballan – Bendigo | 258m | Other | Replacement | 2019 | 0 | 0.57445 | 0 | 0 | 0 | 0.57445
58 | Pigging Program T60 Longford – Tyers | 258n | Other | Replacement | 2022 | 0 | 0 | 0 | 0 | 0.77326 | 0.77326
59 | Pigging Program T63 Tyers - Morwell | 258o | Other | Replacement | 2021 | 0 | 0 | 0 | 0.63139 | 0 | 0.63139
60 | Pigging Program T96 & T98 Chiltern- Rutherglen – Koonoomoo | 258p | Other | Replacement | 2022 | 0 | 0 | 0 | 0 | 0.52751 | 0.52751
61 | Pigging Program T118 Trugannina-Plumpton | 258q | Other | Replacement | 2022 | 0 | 0 | 0 | 0 | 0.52935 | 0.52935
62 | Pigging Program James Street to Laverton Pipeline (253) | 258s | Other | Replacement | 2019 | 0 | 0.46265 | 0 | 0 | 0 | 0.46265
63 | Pigging Program Tyres to Maryvale (67) | 258u | Other | Replacement | 2018 | 0.39592 | 0 | 0 | 0 | 0 | 0.39592
64 | Pigging Program T108 Newport | 258v | Other | Replacement | 2018 | 0.4896 | 0 | 0 | 0 | 0 | 0.4896
65 | Pigging Program Inner Ring Main | 258w | Other | Replacement | 2020 | 0 | 0 | 0.0036303 | 0 | 0 | 0.0036303
66 | Pigging Program T1 Morwell - Dandenong Repair Program | 258x | Other | Replacement | 2019 | 0 | 1.1362 | 0 | 0 | 0 | 1.1362
67 | Pig Trap Installation James Street to Laverton Pipeline (253) | 259a |  |  | 2020 | 0 | 0 | 0 | 0 | 0 | 0
68 | Pig Trap Installation Tyers to Maryvale Pipeline (67) | 259d |  |  | 2019 | 0 | 0 | 0 | 0 | 0 | 0
69 | Pig Trap Installation Trugannina to Plumpton | 259g |  |  | 2022 | 0 | 0 | 0 | 0 | 0 | 0
70 | Liquid Management - Brooklyn | 260a | City Gates & Field Regs | Replacement | 2022 | 0 | 0 | 0 | 0 | 0.16222 | 0.16222
71 | Liquid Management - Pakenham | 260b | City Gates & Field Regs | Replacement | 2021 | 0 | 0 | 0 | 0.16222 | 0 | 0.16222
72 | RTU replacement | 262 | Other | Replacement | incurred | 0.14653 | 0.14653 | 0.14653 | 0.14653 | 0.14653 | 0.73264
73 | Pipe Support replacement | 263 | Pipelines | Replacement | incurred | 0.17029 | 0.17029 | 0.17029 | 0.17029 | 0.17029 | 0.85143
74 | HMI upgrade to CLEAR SCADA at BCS, SCS and WCS & CG, Longford | 264 | Other | Non-System | incurred | 0.062952 | 0.062952 | 0.062952 | 0.062952 | 0.062952 | 0.31476
75 | BCS Unit 12 Inlet Filter Replacement/Augmentation | 267 | Compressors | Replacement | 2018 | 0.65684 | 0 | 0 | 0 | 0 | 0.65684
76 | Coogee decommissioning, Step Change | 268 | Other |  | 2018 | 0 | 0 | 0 | 0 | 0 | 0
77 | Compressor Type B Compliance | 271 | Compressors | Replacement | incurred | 0.22392 | 0.22392 | 0.22392 | 0.22392 | 0.22392 | 1.1196
78 | Dandenong LNG Isolation Valve Upgrade | 275 | Pipelines | Replacement | 2018 | 0.67058 | 0 | 0 | 0 | 0 | 0.67058
79 | Morwell-Dandenong Fatigue Crack Detection from High Loads | 276 | Pipelines | Replacement | 2018 | 0.2695 | 0 | 0 | 0 | 0 | 0.2695
80 | Unibolt Enclosure Replacement | 277 | Other | Replacement | incurred | 0.045941 | 0.045941 | 0.045941 | 0.045941 | 0.045941 | 0.22971
81 | WAN Upgrade (Satellite project) | 278 | Other | Non-System | incurred | 0.97845 | 0.97845 | 0.97845 | 0.97845 | 0.97845 | 4.8923
82 | Warragul Looping 6" (Southern Route) | Warragul 6" (Sth) | Pipelines | Augmentation | 2020 | 0 | 0 | 3.6163 | 0 | 0 | 3.6163
83 | Anglesea Pipeline Extension | Anglesea | Pipelines | Augmentation | 2018 | 26.4448 | 0 | 0 | 0 | 0 | 26.4448
84 | BCS Reconfiguration (2B) | BCS Reconfig (2A) | Compressors | Augmentation | 2018 | 2.0253 | 0 | 0 | 0 | 0 | 2.0253
85 | Winchelsea Bi-Directional Flow | Winchelsea Bi-Direction | Compressors | Augmentation | 2018 | 1.4678 | 0 | 0 | 0 | 0 | 1.4678
86 | WORM (50km x 20" Pipeline) | WORM (Pipeline) | Pipelines | Augmentation | 2020 | 0 | 0 | 96.8365 | 0 | 0 | 96.8365
87 | WORM (C50 at Wollert) | WORM (C50) | Compressors | Augmentation | 2020 | 0 | 0 | 26.1536 | 0 | 0 | 26.1536
88 | WORM (PRS at Wollert) | WORM (PRS) | City Gates & Field Regs | Augmentation | 2020 | 0 | 0 | 3.7206 | 0 | 0 | 3.7206
89 | Enterprise Content Management | APA |  |  | incurred | 0 | 0 | 0 | 0 | 0 | 0
90 | Victoria CRE | APA |  |  | 2018 | 0 | 0 | 0 | 0 | 0 | 0
91 | APA Grid Energy Components Upgrade | APA |  |  | 2018 | 0 | 0 | 0 | 0 | 0 | 0
92 | APA Grid Extend Program | APA | Other | Non-System | 2018 | 0.2699 | 0 | 0 | 0 | 0 | 0.2699
93 | APA Grid Services Initiatives Program | APA |  |  | 2021 | 0 | 0 | 0 | 0 | 0 | 0
94 | Hyperion Upgrade to 11.1.2.4 | APA |  |  | 2018 | 0 | 0 | 0 | 0 | 0 | 0
95 | BI - Transmission Dashboard and Enterprise Pilot | APA | Other | Non-System | 2018 | 0.37786 | 0 | 0 | 0 | 0 | 0.37786
96 | HR Systems Refresh | APA |  |  | 2018 | 0 | 0 | 0 | 0 | 0 | 0
97 | Transmission EAM Data Management Tool | APA |  |  | 2019 | 0 | 0 | 0 | 0 | 0 | 0
98 | SharePoint Upgrade | APA | Other | Non-System | 2018 | 0.026318 | 0 | 0 | 0 | 0 | 0.026318
99 | eForm Digitisation | APA | Other | Non-System | 2018 | 0.62131 | 0 | 0 | 0 | 0 | 0.62131
100 | Historian Upgrade - version 2012 to 2015 | APA |  |  | 2018 | 0 | 0 | 0 | 0 | 0 | 0
101 | Hazardous Area Platform | APA | Other | Non-System | 2020 | 0 | 0 | 0.16761 | 0 | 0 | 0.16761
102 | PPM Refresh | APA | Other | Non-System | 2018 | 0.32388 | 0 | 0 | 0 | 0 | 0.32388
103 | BizTalk Upgrade FY2018 | APA | Other | Non-System | 2018 | 0.13773 | 0 | 0 | 0 | 0 | 0.13773
104 | Automated Testing Tool | APA | Other | Non-System | 2018 | 0.071986 | 0 | 0 | 0 | 0 | 0.071986
105 | Code Management Software | APA | Other | Non-System | 2020 | 0 | 0 | 0.097804 | 0 | 0 | 0.097804
106 | CRM Upgrade | APA | Other | Non-System | 2018 | 0.1584 | 0 | 0 | 0 | 0 | 0.1584
107 | X-Info Aware Version 2 | APA | Other | Non-System | 2018 | 0.046432 | 0 | 0 | 0 | 0 | 0.046432
108 | Supplier Qualification and Compliance | APA | Other | Non-System | 2019 | 0 | 0.095373 | 0 | 0 | 0 | 0.095373
109 | Oracle eBS Upgrade to 12.2 | APA | Other | Non-System | 2018 | 0.16662 | 0 | 0 | 0 | 0 | 0.16662
110 | BizTalk System Upgrade 2020 | APA | Other | Non-System | 2019 | 0 | 0.13773 | 0 | 0 | 0 | 0.13773
111 | Applications Renewal | APA | Other | Non-System | incurred | 0.74493 | 0.93062 | 0.74493 | 0.93062 | 0.74493 | 4.096
112 | Infrastructure Renewal | APA | Other | Non-System | incurred | 0.24291 | 0.08097 | 0.08097 | 0.08097 | 0 | 0.48582
113 | Dandenong Relocation | APA |  |  | incurred | 0 | 0 | 0 | 0 | 0 | 0
- | BCS Administration Building Distribution Board Upgrade | VTS | Compressors | Replacement | 2018 | 0.029948 | 0 | 0 | 0 | 0 | 0.029948
- | Pig Trap - A Branch Valve on Pipeline 108 to Newport Install(124) | VTS | Pipelines | Replacement | 2018 | 0.88892 | 0 | 0 | 0 | 0 | 0.88892
- | Pig Trap - Somerton to Somerton Pipeline Install (238) | VTS | City Gates & Field Regs | Replacement | 2018 | 0.029347 | 0 | 0 | 0 | 0 | 0.029347
- | Zonal Chromatograph Insertion Probes | VTS | Gas Quality | Replacement | 2018 | 0.06 | 0 | 0 | 0 | 0 | 0.06
- | VTS.SIB99 WCS STN-A DISCHRG LQ | VTS | Other | Replacement | 2018 | 0.19085 | 0 | 0 | 0 | 0 | 0.19085
- |  | - |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
- |  | - |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
- |  | - |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
- |  | - |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
- |  | - |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
- |  | - |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
- |  | - |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
- |  | - |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
- |  | - |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
- |  | - |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
- |  | - |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
- |  | - |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
- |  | - |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
- |  | - |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
- |  | - |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
- |  | - |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
- |  | - |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
- |  | - |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
- |  | - |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
- |  | - |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
- |  | - |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
- |  | - |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
- |  | - |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
- |  | - |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
- |  | - |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
- |  | - |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
- |  | - |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
- |  | - |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
- |  | - |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
- |  | - |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
- |  | - |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
- |  | - |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
- |  | - |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
- |  | - |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
- |  | - |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
- |  | - |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
- |  | - |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
- |  | - |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
- |  | - |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
- |  | - |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
- |  | - |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
- |  | - |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
- |  | - |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
- |  | - |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
- |  | - |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
- |  | - |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
- |  | - |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
- |  | - |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
- |  | - | [8 empty] | 0
- |  | - | [8 empty] | 0
- |  | - | [8 empty] | 0
- |  | - | [8 empty] | 0
- |  | - | [8 empty] | 0
- |  | - | [8 empty] | 0
- |  | - | [8 empty] | 0
- |  | - | [8 empty] | 0
- |  | - | [8 empty] | 0
- |  | - | [8 empty] | 0
- |  | - | [8 empty] | 0
- |  | - | [8 empty] | 0
- |  | - | [8 empty] | 0
- |  | - | [8 empty] | 0
- |  | - | [8 empty] | 0
- |  | - | [8 empty] | 0
- |  | - | [8 empty] | 0
- |  | - | [8 empty] | 0
- |  | - | [8 empty] | 0
- |  | - | [8 empty] | 0
- |  | - | [8 empty] | 0
- |  | - | [8 empty] | 0