

 FINAL DECISION

Ausgrid distribution determination

 2015−16 to 2018−19

Attachment 12 – Demand management incentive scheme

April 2015

© Commonwealth of Australia 2015

This work is copyright. In addition to any use permitted under the Copyright Act 1968, all material contained within this work is provided under a Creative Commons Attributions 3.0 Australia licence, with the exception of:

* the Commonwealth Coat of Arms
* the ACCC and AER logos
* any illustration, diagram, photograph or graphic over which the Australian Competition and Consumer Commission does not hold copyright, but which may be part of or contained within this publication. The details of the relevant licence conditions are available on the Creative Commons website, as is the full legal code for the CC BY 3.0 AU licence.

Requests and inquiries concerning reproduction and rights should be addressed to the:

Director, Corporate Communications
Australian Competition and Consumer Commission
GPO Box 4141, Canberra ACT 2601

or publishing.unit@accc.gov.au.

Inquiries about this publication should be addressed to:

Australian Energy Regulator
GPO Box 520
Melbourne Vic 3001

Tel: (03) 9290 1444
Fax: (03) 9290 1457

Email: AERInquiry@aer.gov.au

AER reference: 52294

1. Note
2. This attachment forms part of the AER's final decision on Ausgrid’s revenue proposal 2015–19. It should be read with other parts of the final decision.
3. The final decision includes the following documents:
4. Overview

Attachment 1 - Annual revenue requirement

Attachment 2 - Regulatory asset base

Attachment 3 - Rate of return

Attachment 4 - Value of imputation credits

Attachment 5 - Regulatory depreciation

Attachment 6 - Capital expenditure

Attachment 7 - Operating expenditure

Attachment 8 - Corporate income tax

Attachment 9 - Efficiency benefit sharing scheme

Attachment 10 - Capital expenditure sharing scheme

Attachment 11 - Service target performance incentive scheme

Attachment 12 - Demand management incentive scheme

Attachment 13 - Classification of services

Attachment 14 - Control mechanism

Attachment 15 - Pass through events

Attachment 16 - Alternative control services

Attachment 17 - Negotiated services framework and criteria

Attachment 18 - Connection methodology

Attachment 19 - Pricing methodology

Attachment 20 - Analysis of financial viability

1. Contents

[Note 12-2](#_Toc416788951)

[Contents 12-3](#_Toc416788952)

[Shortened forms 12-4](#_Toc416788953)

[12 Demand management incentive scheme 12-6](#_Toc416788954)

[12.1 Final decision 12-7](#_Toc416788955)

[12.2 Ausgrid’s revised proposal 12-7](#_Toc416788956)

[12.3 AER’s assessment approach 12-7](#_Toc416788957)

[12.4 Reasons for final decision 12-8](#_Toc416788958)

1. Shortened forms

| 1. Shortened form
 | 1. Extended form
 |
| --- | --- |
| 1. AEMC
 | 1. Australian Energy Market Commission
 |
| 1. AEMO
 | 1. Australian Energy Market Operator
 |
| 1. AER
 | 1. Australian Energy Regulator
 |
| 1. augex
 | 1. augmentation expenditure
 |
| 1. capex
 | 1. capital expenditure
 |
| 1. CCP
 | 1. Consumer Challenge Panel
 |
| 1. CESS
 | 1. capital expenditure sharing scheme
 |
| 1. CPI
 | 1. consumer price index
 |
| 1. DRP
 | 1. debt risk premium
 |
| 1. DMIA
 | 1. demand management innovation allowance
 |
| 1. DMIS
 | 1. demand management incentive scheme
 |
| 1. distributor
 | 1. distribution network service provider
 |
| 1. DUoS
 | 1. distribution use of system
 |
| 1. EBSS
 | 1. efficiency benefit sharing scheme
 |
| 1. ERP
 | 1. equity risk premium
 |
| 1. Expenditure Assessment Guideline
 | 1. expenditure forecast assessment Guideline for electricity distribution
 |
| 1. F&A
 | 1. framework and approach
 |
| 1. MRP
 | 1. market risk premium
 |
| 1. NEL
 | 1. national electricity law
 |
| 1. NEM
 | 1. national electricity market
 |
| 1. NEO
 | 1. national electricity objective
 |
| 1. NER
 | 1. national electricity rules
 |
| 1. NSP
 | 1. network service provider
 |
| 1. opex
 | 1. operating expenditure
 |
| 1. PPI
 | 1. partial performance indicators
 |
| 1. PTRM
 | 1. post-tax revenue model
 |
| 1. RAB
 | 1. regulatory asset base
 |
| 1. RBA
 | 1. Reserve Bank of Australia
 |
| 1. repex
 | 1. replacement expenditure
 |
| 1. RFM
 | 1. roll forward model
 |
| 1. RIN
 | 1. regulatory information notice
 |
| 1. RPP
 | 1. revenue and pricing principles
 |
| 1. SAIDI
 | 1. system average interruption duration index
 |
| 1. SAIFI
 | 1. system average interruption frequency index
 |
| 1. SLCAPM
 | 1. Sharpe-Lintner capital asset pricing model
 |
| 1. STPIS
 | 1. service target performance incentive scheme
 |
| 1. WACC
 | 1. weighted average cost of capital
 |

#  Demand management incentive scheme

1. The National Electricity Rules (NER) require us to develop and implement mechanisms to incentivise distributors to consider efficient alternatives to building more network.[[1]](#footnote-1) To meet this requirement, and motivated by the need to improve distributors' capability in the demand management area, we implemented a demand management incentive scheme (DMIS) in our NSW/ACT distribution determinations for the 2009–14 regulatory control period.[[2]](#footnote-2)
2. The current DMIS for NSW distributors includes two components—the demand management innovation allowance (DMIA)[[3]](#footnote-3) and the D-factor.[[4]](#footnote-4)
3. The DMIA is a capped allowance for distributors to investigate and conduct broad-based and/or peak demand management projects. It contains two parts:
* Part A provides for an innovation allowance to be incorporated into each distributor's revenue allowance for opex each year of the regulatory control period. Distributors prepare annual reports on their expenditure under the DMIA[[5]](#footnote-5) in the previous year, which we then assess against specific criteria.[[6]](#footnote-6)
* Part B compensates distributors for any foregone revenue demonstrated to have resulted from demand management initiatives approved under Part A. During the 2009–14 regulatory control period, NSW distributors were subject to a weighted average price cap (WAPC) form of control. Under this control mechanism, if a demand management project resulted in a fall in demand for direct control services, the distributor's recoverable revenues would fall as prices were fixed. For this reason, foregone revenue was recoverable under Part B of the DMIA.
1. Under the scheme, we return any underspend against the allowance to customers. Also, once we know the approved DMIA expenditure for each year of the current period, we compensate distributors for approved foregone revenue. We implement this as an adjustment to each distributor's innovation allowance in the following regulatory control period.
2. The D-factor scheme[[7]](#footnote-7) acts as a counter balance to distributors' disincentive to implement demand management under the WAPC form of control. The D-factor offers compensation for both the costs and foregone revenue incurred from demand management projects for which the distributor can demonstrate a resultant reduction in both capex and demand.

## Final decision

1. We have determined to continue Part A of the DMIA but we will not apply either Part B of the DMIA or the D-Factor scheme for Ausgrid in the 2015–19 regulatory control period. This is consistent with our draft decision[[8]](#footnote-8) and our proposed approach in the Stage 2 Framework and Approach (F&A).[[9]](#footnote-9) Also consistent with our draft decision, we have determined that Ausgrid's proposed Demand Management Benefit Sharing Scheme (DMBSS) not be introduced at this time.
2. The current innovation allowance amount of $1 million ($2014–15) per annum will continue in the 2015–19 regulatory control period.

## Ausgrid’s revised proposal

1. Ausgrid accepted our draft decision to continue applying Part A of the DMIA at the same scale as is currently applied, but to discontinue Part B of the scheme as it related to compensation for foregone revenue. However, Ausgrid submitted that no effective consideration was given to the maintenance of positive incentives for demand management formerly available through the D-factor and retained its proposal for the DMBSS.[[10]](#footnote-10)

## AER’s assessment approach

1. The rules require us to have regard to several factors in developing and implementing a DMIS for Ausgrid.[[11]](#footnote-11) These are:
* Benefits to consumers
* the need to ensure that benefits to electricity consumers likely to result from the scheme are sufficient to warrant any reward or penalty under the scheme
* the willingness of customers or end users to pay for increases in costs resulting from implementing DMIS.
* Balanced incentives
* the effect of a particular control mechanism (i.e. price as distinct from revenue regulation) on a distributor's incentives to adopt or implement efficient non-network alternatives
* the effect of classification of services on a distributor's incentive to adopt or implement efficient embedded generator connections
* the extent the distributor is able to offer efficient pricing structures
* the possible interactions between DMIS and other incentive schemes.
1. We had regard to these factors in considering the proposed approach to the DMIS for Ausgrid as set out in our draft decision[[12]](#footnote-12) and the Stage 2 F&A for the NSW distributors[[13]](#footnote-13) and we have again taken these factors into account in making our final decision.

## Reasons for final decision

1. Consistent with our decisions for the transitional regulatory control period and our draft decision, we will not apply the Part B foregone revenue component of the DMIA or the D-factor in the 2015–19 regulatory control period due to the move to a revenue cap.[[14]](#footnote-14) However, as the D-factor operates on a two-year lag, Ausgrid will be able to recover the costs and foregone revenues of applicable demand management projects relevant to the 2009–14 regulatory control period in the 2015–19 regulatory control period.

Considering a significant proportion of Ausgrid's allowance remains for the current regulatory control period[[15]](#footnote-15), we have determined that the current innovation allowance amount of $1 million ($2014–15) per annum will continue in the 2015–19 regulatory control period.

Our Stage 2 F&A and draft decision stated that our intention to develop and implement a new DMIS for the 2015–19 regulatory control period was dependent on the progress of the rule change process arising from the AEMC’s Power of Choice review.[[16]](#footnote-16) On 19 February 2015, the AEMC commenced consultation on the rule change. Submissions closed on 19 March 2015. The AEMC is currently considering the rule amendments.

1. The Total Environment Centre (TEC) accepted the position we adopted in our draft decision to await the outcomes of the AEMC's review before considering reform of the current DMIS, but suggested that we consider introducing measures to promote the effective use of demand management initiatives. Such measures included requiring businesses to report annually, providing businesses with specific metrics or performance indicators and the development of a demand management guideline.[[17]](#footnote-17)
2. The Public Interest Advocacy Centre (PIAC) also agreed that revision of the DMIS would ideally follow the AEMC's review, however, given delays in the rule change process and the importance of demand management to consumers, recommended that we urgently revise the current scheme such that it applies to the current determination. PIAC supported Ausgrid's proposed DMBSS as an interim measure.[[18]](#footnote-18) The Ethnic Communities' Council of NSW Inc. supported these recommendations made by the PIAC.[[19]](#footnote-19)
3. The University of Technology Sydney (UTS) was critical of our decision not to accept Ausgrid's proposed DMBSS without offering an alternative in its place.[[20]](#footnote-20) EnerNOC submitted that our position was 'to prioritise process over outcomes' and that Ausgrid's proposed DMBSS 'is good enough to serve as an interim scheme until it is replaced by an AEMC-consulted one for the next regulatory cycle'.[[21]](#footnote-21) Regarding the innovation allowance amount, the TEC submitted that we should consider providing Ausgrid with a $1 million minimum allowance rather than cap the allowance provided it is accompanied by a robust measurement, verification and reporting mechanism.[[22]](#footnote-22) PIAC also recommended that we consider whether there is a case for increasing Ausgrid's innovation allowance and reviewing the DMIA criteria, particularly to fund proposed pilots and trials.[[23]](#footnote-23) UTS also recommended that Ausgrid's innovation allowance be increased and that performance benchmarks or guidelines for the outcomes, impact and cost effectiveness of demand management projects be introduced.[[24]](#footnote-24)

Regarding forms of price control and the D-factor, TEC and the CCP accepted it is appropriate to remove the D-factor in light of the move to a revenue cap.[[25]](#footnote-25) UTS welcomed the move to a revenue cap but considered the removal of the D-factor without replacement with balanced incentives constituted a significant reduction in the incentives for demand management.[[26]](#footnote-26)

1. In support of the retention of its proposed DMBSS, Ausgrid stated that our decision not to introduce its scheme was based on two incorrect assertions[[27]](#footnote-27). The first assertion was a reference to Ausgrid having proposed the DMBSS in anticipation of a series of rules changes that are currently being considered by the AEMC as part of its Power of Choice review. We did not offer this statement as a reason for not introducing the DMBSS. It was merely a descriptive statement referencing Ausgrid's regulatory proposal which first referred to the AEMC's rule change process.
2. The second assertion was a reference in our draft decision to the change to a revenue cap form of control providing distributors with opportunities to improve and expand their demand management programs. However, Ausgrid's abbreviated quotation from our draft decision may lead to misinterpretation. For clarity, the change to a revenue cap form of control removes any disincentive to reduce the quantity of electricity sold while more robust obligations to consider non-network alternatives in order to satisfy RIT-D requirements provide opportunities to expand demand management programs. We consider these issues are relevant to our decision.
3. In any case, as we stated in our draft decision:

'We do not intend to pre-empt consultation on the AEMC’s review of the current demand management arrangements by commencing a separate consultation process on a new DMIS before the outcomes of the review are finalised. Quite apart from the unnecessary complications and inefficiencies that a parallel policy process would create, the confines of a distribution revenue review make it ill-suited to driving regulatory reform.'[[28]](#footnote-28)

1. This point is reiterated in our reasons for the draft decision[[29]](#footnote-29). We do not consider it appropriate to develop an alternative incentive structure in parallel to the AEMC's review through Ausgrid's regulatory proposal. The AEMC will be able to consider how any changes to the NER can be implemented in the 2015–19 regulatory control period through transitional arrangements.
2. Ausgrid does not respond to this point within its revised regulatory proposal. We consider that this remains valid and is a significant factor in deciding not to introduce Ausgrid's proposed DMBSS. This is also the reason why we are not proceeding with amendments to the current scheme or the introduction of other interim demand management incentive measures proposed by stakeholders in submissions.
3. We will consider the introduction of a revised DMIS as soon as practicable following the AEMC's rule change process.
4. Ausgrid proposed a number of demand management costs as part of its total forecast capital expenditure and operating expenditure building blocks. Our decision on Ausgrid's demand management related capital expenditure or operating expenditure building blocks can be found in attachments 6 and 7 respectively.
1. NER, cl. 6.6.3(a). [↑](#footnote-ref-1)
2. The rules have since changed the name to 'Demand Management and Embedded Generation Connection Incentive Scheme' (DMEGCIS) to explicitly cover innovation with respect to the connection of embedded generation. Our current and proposed DMIS includes embedded generation. We consider embedded generation to be one means of demand management, as it typically reduces demand for power drawn from a distribution network. [↑](#footnote-ref-2)
3. AER, Demand management incentive scheme for the ACT and NSW 2009 distribution determinations—Demand management innovation allowance scheme, 28 November 2008. (AER, DMIA for ACT and NSW distributors, November 2008). [↑](#footnote-ref-3)
4. AER, Demand management incentive scheme for the ACT and NSW 2009 distribution determinations—D-factor scheme, 29 February 2008. [↑](#footnote-ref-4)
5. The DMIA excludes the costs of demand management initiatives approved in our determination for the 2009–14 regulatory control period or under the D-factor scheme. [↑](#footnote-ref-5)
6. AER, DMIA for ACT and NSW distributors, November 2008, pp. 4–5. [↑](#footnote-ref-6)
7. From IPART's NSW distribution determinations for the 2004–09 regulatory control period. [↑](#footnote-ref-7)
8. AER, Draft decision: Ausgrid distribution determination 2015–19, November 2014, Attachment 12, pp. 7 & 8 (AER, Draft Decision, November 2014). [↑](#footnote-ref-8)
9. AER, Stage 2 Framework and Approach paper for Ausgrid, January 2014, p. 32 (AER, Stage 2 Framework and Approach, January 2014). [↑](#footnote-ref-9)
10. Ausgrid, Revised Regulatory Proposal and Preliminary Submission: 1 July 2014 to 30 June 2019, 20 January 2015, pp. 58 & 59 (Ausgrid, Revised Regulatory Proposal, January 2015). [↑](#footnote-ref-10)
11. NER, cl 6.6.3(b). [↑](#footnote-ref-11)
12. AER, Draft Decision, November 2014, Attachment 12, p. 9. [↑](#footnote-ref-12)
13. AER, Stage 2 Framework and Approach, January 2014, pp. 33–35. [↑](#footnote-ref-13)
14. AER, Draft Decision, November 2014, Attachment 12, p. 9. [↑](#footnote-ref-14)
15. AER, Applications by DNSPs for Demand Management Innovation Allowance for 2013 calendar year (Victorian DNSPs) and 2012–13 financial year (all other DNSPs), April 2015, p. 4. [↑](#footnote-ref-15)
16. AER, Stage 2 Framework and Approach, January 2014, p. 32. AER, Draft Decision, November 2015, Attachment 12, p. 9. For information regarding the AEMC's Power of Choice Review, see <http://www.aemc.gov.au/Major-Pages/Power-of-choice>. The AEMC received a proposed rule change from COAG Energy Ministers and the Total Environment Centre. [↑](#footnote-ref-16)
17. Total Environment Centre, Submission to the AER on the Draft Determination on NSW DB's Regulatory Proposals 2014–19, February 2015, pp. 2-3 & 5-6. [↑](#footnote-ref-17)
18. Public Interest Advocacy Centre Inc., Submission to the Australian Energy Regulator's Draft Determination for Ausgrid, Endeavour Energy and Essential Energy, 13 February 2015, pp. 51-52. [↑](#footnote-ref-18)
19. Ethnic Communities' Council of NSW Inc., Submission concerning the NSW Distribution Networks Revised Revenue Proposal 2014–19, 11 February 2015, pp. 5-6. [↑](#footnote-ref-19)
20. University of Technology Sydney, ISF Submission to AER: Draft determination for Ausgrid 2014–19, 13 February 2015, Attachment A, pp. 2-3. [↑](#footnote-ref-20)
21. EnerNOC, Submission on 2015–19 draft decisions and revised proposals for NSW DNSPs, 13 February 2015, p. 3. [↑](#footnote-ref-21)
22. Total Environment Centre, Submission to the AER on the Draft Determination on NSW DB's Regulatory Proposals 2014–19, February 2015, p. 11. [↑](#footnote-ref-22)
23. Public Interest Advocacy Centre Inc., Submission to the Australian Energy Regulator's Draft Determination for Ausgrid, Endeavour Energy and Essential Energy, 13 February 2015, p. 49. [↑](#footnote-ref-23)
24. University of Technology Sydney, ISF Submission to AER: Draft determination for Ausgrid 2014–19, 13 February 2015, Attachment A, pp. 1-2. [↑](#footnote-ref-24)
25. Total Environment Centre, Submission to the AER on the Draft Determination on NSW DB's Regulatory Proposals 2014–19, February 2015, p. 6.

 Consumer Challenge Panel, Submission to the AER: Responding to NSW draft determinations and revised proposals from electricity distribution networks, 16 February 2015, p. 54. [↑](#footnote-ref-25)
26. University of Technology Sydney, ISF Submission to AER: Draft determination for Ausgrid 2014–19, 13 February 2015, Attachment A, p. 1. [↑](#footnote-ref-26)
27. Ausgrid, Revised Regulatory Proposal, January 2015, p. 58. [↑](#footnote-ref-27)
28. AER, Draft Decision, November 2014, Attachment 12, p. 10. [↑](#footnote-ref-28)
29. AER, Draft Decision, November 2014, Attachment 12, p. 10. [↑](#footnote-ref-29)