## Summary Chart
APA VTS 2018-22 Access Arrangement - AER Final Decision
Figures reported below are net
|  | 2013 | 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 | 2022
| APA actual capex | 2013: 15.6; 2014: 124.2; 2015: 94.5; 2016: 105
| APA estimated capex | 2017: 58.5
| Approved capex forecast | 2013: 19.7; 2014: 95.4; 2015: 25.2; 2016: 14.1; 2017: 9.3
| APA forecast capex | 2018: 77.7098; 2019: 71.9244; 2020: 73.7286; 2021: 17.7904; 2022: 14.9199
| AER draft decision | 2018: 62.0904; 2019: 73.6522; 2020: 70.7093; 2021: 16.2642; 2022: 16.306
| APA revised proposal | 2018: 65.7; 2019: 73.8; 2020: 71.8; 2021: 16.5; 2022: 16.5
| AER final decision | 2018: 62.0904; 2019: 73.6522; 2020: 70.7093; 2021: 16.2642; 2022: 16.306
| Underspend | 2013: 4.1; 2014: -28.8; 2015: -69.3; 2016: -90.9; 2017: -49.2

## Final Decision - Output│Tables
APA VTS - Initial Capex Proposal - Output¦Tables | [8 empty] | Final Decision - Output│Tables
| Historic Capex ($nominal m) | [8 empty] | Historic Capex ($nominal m)
|  | 2013 | 2014 | 2015 | 2016 (e) | 2017 (f) | Total |  |  |  | 2013 | 2014 | 2015 | 2016 (e) | 2017 (f) | Total
| Capital expenditure | 15.5962 | 124.1752 | 94.5272 | 105.0136 | 68.9868 | 408.2989 |  |  | Capital expenditure | 15.5962 | 124.1752 | 94.5272 | 91.717 | 62.492 | 388.5075
| Capex by Asset Class ($ nominal m) | [8 empty] | Capex by Asset Class ($ nominal m)
| Asset Class | 2013 | 2014 | 2015 | 2016 (e) | 2017 (f) | Total |  |  | Asset Class | 2013 | 2014 | 2015 | 2016 (e) | 2017 (f) | Total
| Pipelines | 4.1116 | 85.8261 | 72.0774 | 93.2526 | 52.541 | 307.8086 |  |  | Pipelines | 4.1116 | 85.8261 | 72.0774 | 75.7835 | 46.1698 | 283.9683
| Compressors | 8.4012 | 27.7984 | 7.7657 | 6.317 | 0.965 | 51.2474 |  |  | Compressors | 8.4012 | 27.7984 | 7.7657 | 6.0345 | 6.4271 | 56.427
| City Gates & Field Regs | 1.1037 | 5.1064 | 8.3758 | 1.503 | 3.46 | 19.5489 |  |  | City Gates & Field Regs | 1.1037 | 5.1064 | 8.3758 | 1.3431 | 1.8804 | 17.8094
| Odourant Plants | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Odourant Plants | 0 | 0 | 0 | 0 | 0 | 0
| Gas Quality | 0 | 0.09101 | 0.28585 | 0.35095 | 0.05 | 0.77781 |  |  | Gas Quality | 0 | 0.09101 | 0.28585 | 0.34095 | 0.035251 | 0.75306
| Other | 1.9333 | 5.126 | 5.0021 | 3.5331 | 11.9238 | 27.5183 |  |  | Other | 1.9333 | 5.126 | 5.0021 | 8.1569 | 7.647 | 27.8653
| Buildings | 0.046302 | 0.22734 | 1.0204 | 0.056882 | 0.04705 | 1.398 |  |  | Buildings | 0.046302 | 0.22734 | 1.0204 | 0.057962 | 0.33252 | 1.6845
| General Land | 0 | 0 | 0 | 0 | 0 | 0 |  |  | General Land | 0 | 0 | 0 | 0 | 0 | 0
| Total | 15.5962 | 124.1752 | 94.5272 | 105.0136 | 68.9868 | 408.2989 | 0 |  | Total | 15.5962 | 124.1752 | 94.5272 | 91.717 | 62.492 | 388.5075 | 24.013
| Capex by Asset Category ($nominal m) | [8 empty] | Capex by Asset Category ($nominal m)
| Asset Category | 2013 | 2014 | 2015 | 2016 (e) | 2017 (f) | Total |  |  | Asset Category | 2013 | 2014 | 2015 | 2016 (e) | 2017 (f) | Total
| Augmentation | 12.3099 | 112.4157 | 74.5887 | 92.1364 | 52.331 | 343.7817 |  |  | Augmentation | 12.1415 | 112.2553 | 74.5247 | 75.1561 | 48.1056 | 322.1832
| Replacement | 1.5504 | 7.5217 | 14.2083 | 10.5241 | 8.105 | 41.9095 |  |  | Replacement | 1.7188 | 7.6821 | 14.2724 | 9.3196 | 7.2486 | 40.2414
| Non-System | 1.7358 | 4.2378 | 5.7301 | 2.3531 | 8.5508 | 22.6077 |  |  | Non-System | 1.7358 | 4.2378 | 5.7301 | 7.2413 | 7.1378 | 26.0829
| Total | 15.5962 | 124.1752 | 94.5272 | 105.0136 | 68.9868 | 408.2989 | 0 |  | Total | 15.5962 | 124.1752 | 94.5272 | 91.717 | 62.492 | 388.5075 | 0
APA VTS - Proposed Capex - Output¦Tables | [8 empty] | Final Decision - Output│Tables
| Forecast Capex (nominal $m) | [8 empty] | Forecast Capex (nominal $m)
|  | 2018 | 2019 | 2020 | 2021 | 2022 | Total |  |  |  | 2018 | 2019 | 2020 | 2021 | 2022 | Total
| Capital expenditure | 77.7098 | 71.9244 | 73.7286 | 17.7904 | 14.9199 | 256.0731 |  |  | Capital expenditure | 62.0904 | 73.6522 | 70.7093 | 16.2642 | 16.306 | 239.0221
| Capex by Asset Class (real 2017 $m) | [8 empty] | Capex by Asset Class (real 2017 $m)
|  | 2018 | 2019 | 2020 | 2021 | 2022 | Total |  |  |  | 2018 | 2019 | 2020 | 2021 | 2022 | Total
| Pipelines | 50.6752 | 48.7949 | 53.1625 | 3.197 | 0.50398 | 156.3336 |  |  | Pipelines | 41.3032 | 49.8617 | 50.4064 | 0.16811 | 2.0745 | 143.8139
| Compressors | 14.4254 | 13.4972 | 12.9727 | 4.4042 | 6.5459 | 51.8452 |  |  | Compressors | 9.6538 | 13.3244 | 12.8067 | 6.0373 | 6.4621 | 48.2842
| City Gates & Field Regs | 0 | 2.3361 | 2.378 | 0.68322 | 0.24695 | 5.6443 |  |  | City Gates & Field Regs | 0 | 2.3062 | 2.3476 | 0.67448 | 0.24379 | 5.5721
| Odourant Plants | 0.07808 | 0 | 0 | 0 | 0 | 0.07808 |  |  | Odourant Plants | 0.077081 | 0 | 0 | 0 | 0 | 0.077081
| Gas Quality | 1.0063 | 0 | 0 | 0 | 0 | 1.0063 |  |  | Gas Quality | 0.99344 | 0 | 0 | 0 | 0 | 0.99344
| Other | 10.865 | 6.3257 | 4.2449 | 8.5355 | 7.2736 | 37.2446 |  |  | Other | 9.4115 | 7.2018 | 4.1905 | 8.4263 | 7.1805 | 36.4106
| Buildings | 0.65985 | 0.97052 | 0.97052 | 0.97052 | 0.34957 | 3.921 |  |  | Buildings | 0.6514 | 0.9581 | 0.9581 | 0.9581 | 0.3451 | 3.8708
| General Land | 0 | 0 | 0 | 0 | 0 | 0 |  |  | General Land | 0 | 0 | 0 | 0 | 0 | 0
| Total | 77.7098 | 71.9244 | 73.7286 | 17.7904 | 14.9199 | 256.0731 |  |  | Total | 62.0904 | 73.6522 | 70.7093 | 16.2642 | 16.306 | 239.0221 |  | 215
24.0221
| Capex by Driver (real 2017 $m) | [8 empty] | Capex by Driver (real 2017 $m) | [7 empty] | 1.1117
| Asset Category | 2018 | 2019 | 2020 | 2021 | 2022 | Total |  |  | Asset Category | 2018 | 2019 | 2020 | 2021 | 2022 | Total
| Augmentation | 44.3874 | 49.7329 | 60.9452 | 0 | 0 | 155.0654 |  |  | Augmentation | 44.9804 | 58.1432 | 58.0895 | 0 | 0 | 161.2131
| Replacement | 29.0849 | 18.639 | 9.5309 | 14.2229 | 12.627 | 84.1047 |  |  | Replacement | 12.9305 | 12.0019 | 9.409 | 12.7424 | 14.0423 | 61.126
| Non-System | 4.2375 | 3.5526 | 3.2525 | 3.5675 | 2.293 | 16.903 |  |  | Non-System | 4.1796 | 3.5071 | 3.2109 | 3.5219 | 2.2636 | 16.683
| Total | 77.7098 | 71.9244 | 73.7286 | 17.7904 | 14.9199 | 256.0731 |  |  | Total | 62.0904 | 73.6522 | 70.7093 | 16.2642 | 16.306 | 239.0221

## 1.0 Output│PTRM
1.0 Output│PTRM |  |  | Check | 0 |  | Check RFM & PTRM | 0
Forecast Capex as incurred ($2017 m)
| Asset Class Name | 2018 | 2019 | 2020 | 2021 | 2022 | Total
| Pipelines | 41.3032 | 49.8617 | 50.4064 | 0.16811 | 2.0745 | 143.8139
| Compressors | 9.6538 | 13.3244 | 12.8067 | 6.0373 | 6.4621 | 48.2842
| City Gates & Field Regs | 0 | 2.3062 | 2.3476 | 0.67448 | 0.24379 | 5.5721
| Odourant Plants | 0.077081 | 0 | 0 | 0 | 0 | 0.077081
| Gas Quality | 0.99344 | 0 | 0 | 0 | 0 | 0.99344
| Other | 9.4115 | 7.2018 | 4.1905 | 8.4263 | 7.1805 | 36.4106
| Buildings | 0.6514 | 0.9581 | 0.9581 | 0.9581 | 0.3451 | 3.8708
| General Land | 0 | 0 | 0 | 0 | 0 | 0
| Total | 62.0904 | 73.6522 | 70.7093 | 16.2642 | 16.306 | 239.0221 | 627.5296
Forecast Capex as commissioned ($2017 m)
| Asset Class Name | 2018 | 2019 | 2020 | 2021 | 2022 | Total
| Pipelines | 2.9255 | 34.8587 | 105.6936 | 0.16811 | 0.16811 | 143.8139
| Compressors | 10.6869 | 1.0426 | 29.645 | 3.3433 | 5.1435 | 49.8613
| City Gates & Field Regs | 0 | 0.63164 | 4.0222 | 0.67448 | 0.24379 | 5.5721
| Odourant Plants | 0.077081 | 0 | 0 | 0 | 0 | 0.077081
| Gas Quality | 0.99344 | 0 | 0 | 0 | 0 | 0.99344
| Other | 12.2162 | 8.5121 | 2.4702 | 7.0092 | 6.4451 | 36.6528
| Buildings | 0.6514 | 0.3451 | 0.3451 | 2.1841 | 0.3451 | 3.8708
| General Land | 0 | 0 | 0 | 0 | 0 | 0
| Total | 27.5505 | 45.3901 | 142.176 | 13.3792 | 12.3456 | 240.8413 | 627.1207
0.40889

## 1.1 Output│RFM
1.1 Output│RFM |  | Check | 0
Capex as incurred (nominal $m)
| Asset Class Name | 2013 | 2014 | 2015 | 2016 | 2017 | Total
| Pipelines | 4.1116 | 85.8261 | 72.0774 | 75.7835 | 46.1698 | 283.9683
| Compressors | 8.4012 | 27.7984 | 7.7657 | 6.0345 | 6.4271 | 56.427
| City Gates & Field Regs | 1.1037 | 5.1064 | 8.3758 | 1.3431 | 1.8804 | 17.8094
| Odourant Plants | 0 | 0 | 0 | 0 | 0 | 0
| Gas Quality | 0 | 0.09101 | 0.28585 | 0.34095 | 0.035251 | 0.75306
| Other | 1.9333 | 5.126 | 5.0021 | 8.1569 | 7.647 | 27.8653
| Buildings | 0.046302 | 0.22734 | 1.0204 | 0.057962 | 0.33252 | 1.6845
| General Land | 0 | 0 | 0 | 0 | 0 | 0
| Total | 15.5962 | 124.1752 | 94.5272 | 91.717 | 62.492 | 388.5075
Capex as Commissioned (nominal $m)
| Asset Class Name | 2013 | 2014 | 2015 | 2016 | 2017 | Total
| Pipelines | 0.07044 | 32.4916 | 123.6759 | 1.0482 | 126.2732 | 283.5594
| Compressors | 0.23527 | 0.25422 | 37.3208 | 11.214 | 5.8257 | 54.8499
| City Gates & Field Regs | 0.16393 | 2.9485 | 11.3765 | 1.1433 | 2.1771 | 17.8094
| Odourant Plants | 0 | 0 | 0 | 0 | 0 | 0
| Gas Quality | 0 | 0.09101 | 0.28585 | 0.34095 | 0.035251 | 0.75306
| Other | 0.85818 | 3.4061 | 7.2063 | 7.8165 | 8.336 | 27.6231
| Buildings | 0 | 0.18051 | 1.1135 | 0.030176 | 0.36031 | 1.6845
| General Land | 0 | 0 | 0 | 0 | 0 | 0
| Total | 1.3278 | 39.372 | 180.9789 | 21.5931 | 143.0076 | 386.2794
0.40889

## 1.2 Output│Tables
Check
1.2 Output│Tables
| Historic Capex ($nominal m) | [9 empty] | Forecast Capex (nominal $m)
|  | 2013 | 2014 | 2015 | 2016 | 2017 (f) | Total |  |  |  |  | 2018 | 2019 | 2020 | 2021 | 2022 | Total
| Capital expenditure | 15.5962 | 124.1752 | 94.5272 | 91.717 | 62.492 | 388.5075 |  |  | 0 | Capital expenditure | 63.6116 | 77.3052 | 76.0345 | 17.9176 | 18.4036 | 253.2725 |  | 0
| Capex by Asset Class ($ nominal m) | [9 empty] | Capex by Asset Class (real 2017 $m)
| Asset Class | 2013 | 2014 | 2015 | 2016 | 2017 (f) | Total |  |  |  |  | 2018 | 2019 | 2020 | 2021 | 2022 | Total
| Pipelines | 4.1116 | 85.8261 | 72.0774 | 75.7835 | 46.1698 | 283.9683 |  |  |  | Pipelines | 41.3032 | 49.8617 | 50.4064 | 0.16811 | 2.0745 | 143.8139
| Compressors | 8.4012 | 27.7984 | 7.7657 | 6.0345 | 6.4271 | 56.427 |  |  |  | Compressors | 9.6538 | 13.3244 | 12.8067 | 6.0373 | 6.4621 | 48.2842
| City Gates & Field Regs | 1.1037 | 5.1064 | 8.3758 | 1.3431 | 1.8804 | 17.8094 |  |  |  | City Gates & Field Regs | 0 | 2.3062 | 2.3476 | 0.67448 | 0.24379 | 5.5721
| Odourant Plants | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | Odourant Plants | 0.077081 | 0 | 0 | 0 | 0 | 0.077081
| Gas Quality | 0 | 0.09101 | 0.28585 | 0.34095 | 0.035251 | 0.75306 |  |  |  | Gas Quality | 0.99344 | 0 | 0 | 0 | 0 | 0.99344
| Other | 1.9333 | 5.126 | 5.0021 | 8.1569 | 7.647 | 27.8653 |  |  |  | Other | 9.4115 | 7.2018 | 4.1905 | 8.4263 | 7.1805 | 36.4106
| Buildings | 0.046302 | 0.22734 | 1.0204 | 0.057962 | 0.33252 | 1.6845 |  |  |  | Buildings | 0.6514 | 0.9581 | 0.9581 | 0.9581 | 0.3451 | 3.8708
| General Land | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | General Land | 0 | 0 | 0 | 0 | 0 | 0
| Total | 15.5962 | 124.1752 | 94.5272 | 91.717 | 62.492 | 388.5075 |  |  | 0 | Total | 62.0904 | 73.6522 | 70.7093 | 16.2642 | 16.306 | 239.0221 |  | 0
| Capex by Asset Category ($nominal m) | [9 empty] | Capex by Driver (real 2017 $m)
| Asset Category | 2013 | 2014 | 2015 | 2016 | 2017 (f) | Total |  |  |  | Asset Category | 2018 | 2019 | 2020 | 2021 | 2022 | Total
| Augmentation | 12.1415 | 112.2553 | 74.5247 | 75.1561 | 48.1056 | 322.1832 |  |  |  | Augmentation | 44.9804 | 58.1432 | 58.0895 | 0 | 0 | 161.2131
| Replacement | 1.7188 | 7.6821 | 14.2724 | 9.3196 | 7.2486 | 40.2414 |  |  |  | Replacement | 12.9305 | 12.0019 | 9.409 | 12.7424 | 14.0423 | 61.126
| Non-System | 1.7358 | 4.2378 | 5.7301 | 7.2413 | 7.1378 | 26.0829 |  |  |  | Non-System | 4.1796 | 3.5071 | 3.2109 | 3.5219 | 2.2636 | 16.683
| Total | 15.5962 | 124.1752 | 94.5272 | 91.717 | 62.492 | 388.5075 |  |  | 0 | Total | 62.0904 | 73.6522 | 70.7093 | 16.2642 | 16.306 | 239.0221 |  | 0
| Non Augmentation Capex($nominal m) | [9 empty] | Warragul lateral expansion (real 2017 $m)
| Asset Category | 2013 | 2014 | 2015 | 2016 | 2017 (f) | Total |  |  |  |  | 2018 | 2019 | 2020 | 2021 | 2022 | Total
| Non Augmentation capex | 3.4546 | 11.9199 | 20.0025 | 16.5609 | 14.3864 | 66.3243 |  |  | 0 | Warragul lateral expansion | 5.508 | 2.04 | 0 | 0 | 0 | 7.548 |  | Warragul Looping 6" (Southern Route)
| Historic Actual vs AER Draft Decision ($nominal m) | [9 empty] | Westbound expansion of the South West Pipeline (real 2017 $m)
| Asset Category | 2013 | 2014 | 2015 | 2016 | 2017 (f) | Total |  |  |  |  | 2017 (f) | 2018 | 2019 | 2020 | 2021 | 2022 | Total
| AER Draft Decision | [9 empty] | Brooklyn reconfiguration | 3.179 | 0.5508 | 0 | 0 | 0 | 0 | 3.7298 | Wichelsea Bi Direction and Brooklyn Reconfiguration
| Augmentation | 12.3099 | 112.4157 | 74.5887 | 92.1364 | 52.331 | 343.7817
| Replacement | 1.5504 | 7.5217 | 14.2083 | 10.5241 | 8.105 | 41.9095 |  |  |  | WORM (real 2017 $m)
| Non-System | 1.7358 | 4.2378 | 5.7301 | 2.3531 | 8.5508 | 22.6077
| Total | 15.5962 | 124.1752 | 94.5272 | 105.0136 | 68.9868 | 408.2989 |  |  |  |  | 2018 | 2019 | 2020 | 2021 | 2022 | 0
| Actuals | [9 empty] | WORM | 16.2294 | 29.5771 | 49.7908 | 0 | 0 | 95.5973 |  | WORM (50km x 20" Pipeline)
| Augmentation | 12.1415 | 112.2553 | 74.5247 | 75.1561 | 48.1056 | 322.1832 |  |  |  | WORM Compressor | 7.1845 | 12.3341 | 6.3003 | 0 | 0 | 25.8189 |  | WORM (C50 at Wollert)
| Replacement | 1.7188 | 7.6821 | 14.2724 | 9.3196 | 7.2486 | 40.2414 |  |  |  | WORM RTS | 0 | 1.6746 | 1.9984 | 0 | 0 | 3.673 |  | WORM (PRS at Wollert)
| Non-System | 1.7358 | 4.2378 | 5.7301 | 7.2413 | 7.1378 | 26.0829 |  |  |  | Total WORM | 23.4139 | 43.5858 | 58.0895 | 0 | 0 | 125.0892
| Total | 15.5962 | 124.1752 | 94.5272 | 91.717 | 62.492 | 388.5075 |  |  | 0
| Difference | [9 empty] | Inline inspection (real 2017 $m)
| Augmentation | -0.16838 | -0.16038 | -0.06404 | -16.9803 | -4.2254 | -21.5985
| Replacement | 0.16838 | 0.16038 | 0.06404 | -1.2045 | -0.85637 | -1.6681 |  |  |  |  | 2018 | 2019 | 2020 | 2021 | 2022 | Total |  | 257
| Non-System | 0 | 0 | 0 | 4.8882 | -1.413 | 3.4752 |  |  |  | Inline inspection | 4.6681 | 5.5523 | 0.93748 | 4.6358 | 4.2352 | 20.0289 |  | 258
| Total | 0 | -3e-07 | -2e-07 | -13.2966 | -6.4948 | -19.7914 |  |  | 0 | [8 empty] | 259
Safety management - High consequence areas (real 2017 $m)
Gas to Culcairn (nominal $m)
|  | H1 | H2 | 2014 | 2015 | E2016 | F2017 | Total |  |  |  | 2018 | 2019 | 2020 | 2021 | 2022 | Total
|  | H1: 2013; H2: 2013 |  |  |  | Safety management - High consequence areas | 1.1699 | 2.5705 | 0 | 0 | 1.9064 | 5.6468 |  | 230
| Winchelsea compressor | 3.0965 | 8.1346 | 26.6064 | 2.4925 | 0.00087727 | 0.00018903 | 40.3311
| Wollert to Barnawartha looping (62TJ) | 2.0128 | 4.007 | 85.6489 | 72.0321 | 75.1552 | 44.9264 | 283.7824 |  |  | Brooklyn Compressor Station Upgrade (real 2017 $m)
| Total | 5.1093 | 12.1415 | 112.2553 | 74.5247 | 75.1561 | 44.9266 | 324.1135
[12 empty] | 2018 | 2019 | 2020 | 2021 | 2022 | Total
| $’m (nominal) | H2 | 2014 | 2015 | E2016 | F2017 | Total |  |  |  | Brooklyn Compressor Station Upgrade | 0 | 0 | 2.3433 | 2.3433 | 2.3433 | 7.0299 |  | Brooklyn Compressor Station
2013
| Wollert to Barnawartha looping | 4.007 | 85.6489 | 72.0321 | 75.1552 | 44.9264 | 283.7824 |  |  |  | VTS Turbine Overhauls (real 2017 $m)
| Anglesea Pipeline (nominal $m) | [10 empty] | 2018 | 2019 | 2020 | 2021 | 2022 | Total
[11 empty] | VTS Turbine Overhauls | 0 | 0 | 0 | 1.0247 | 3.6663 | 4.691 |  | Turbine Overhauls
|  | 2013 | 2014 | 2015 | 2016 | 2017 (f) | 2018 (f) | 2019 (f) | Total
| AER Forecast | 0 | 1.3481 | 12.2762 | 0 | 0 | 0 | 0 | 13.6243 |  | AER DD vs Revised Proposal (real 2017 $m)
| Actuals | 0 | 0 | 0 | 0 | 0 | 13.8929 | 12.5174 | 26.4103
| Difference | 0 | -1.3481 | -12.2762 | 0 | 0 | 13.8929 | 12.5174 | 12.786 |  | Asset Category | 2018 | 2019 | 2020 | 2021 | 2022 | Total
AER Draft Decision
| Inline inspection (nominal $m) | [9 empty] | Augmentation | 44.3874 | 46.8372 | 59.7724 | 0 | 0 | 150.9969
[11 empty] | Replacement | 12.51 | 6.5454 | 9.3162 | 10.1582 | 8.5795 | 47.1092
|  | 2013 | 2014 | 2015 | 2016 | 2017 (f) | Total |  |  |  | Non-System | 4.2375 | 3.5526 | 3.2525 | 3.5675 | 2.293 | 16.903
| AER Forecast | 0.21337 | 0.21554 | 1.6249 | 6.8744 | 3.9538 | 12.882 |  |  |  | Total | 61.1348 | 56.9351 | 72.341 | 13.7257 | 10.8724 | 215.0091
| Actuals | 0.33064 | 2.3225 | 0.60559 | 1.2191 | 2.2377 | 6.7156 |  |  |  | Forecast
| Difference | 0.11728 | 2.107 | -1.0193 | -5.6554 | -1.716 | -6.1664 |  |  |  | Augmentation | 44.9804 | 58.1432 | 58.0895 | 0 | 0 | 161.2131
[11 empty] | Replacement | 12.9305 | 12.0019 | 9.409 | 12.7424 | 14.0423 | 61.126
[11 empty] | Non-System | 4.1796 | 3.5071 | 3.2109 | 3.5219 | 2.2636 | 16.683
[11 empty] | Total | 62.0904 | 73.6522 | 70.7093 | 16.2642 | 16.306 | 239.0221
Difference
[11 empty] | Augmentation | 0.59301 | 11.3061 | -1.6829 | 0 | 0 | 10.2162
[11 empty] | Replacement | 0.42049 | 5.4565 | 0.092786 | 2.5842 | 5.4629 | 14.0168
[11 empty] | Non-System | -0.057912 | -0.045462 | -0.041622 | -0.045654 | -0.029343 | -0.21999
[11 empty] | Total | 0.95559 | 16.7171 | -1.6317 | 2.5385 | 5.4335 | 24.013

## 1.3 Output│Graphs
1.3 Output│Graphs
Capital expenditure acroos current and forecast AA
|  | 2013 | 2014 | 2015 | 2016 | 2017 (f) | 2018 | 2019 | 2020 | 2021 | 2022
| APA VTS Actuals/Forecast | 15.5962 | 124.1752 | 94.5272 | 91.717 | 62.492 | 63.6116 | 77.3052 | 76.0345 | 17.9176 | 18.4036
| AER Forecast | 15.5962 | 124.1752 | 94.5272 | 105.0136 | 68.9868 | 61.1348 | 56.9351 | 72.341 | 13.7257 | 10.8724
| APA Forecast | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## 2.0 Input│Historic Capex
2.0 Input│Historic Capex
Input column heading
Input column number |  | 2 | 4
Capex # | Project Name | Class | Category |  | 2013 | 2014 | 2015 | 2016 | 2017 (f) | Total | 2013 | 2014 | 2015 | 2016 | 2017 | Total | 2013 | 2014 | 2015 | 2016 | 2017 (f) | Total
1 | Stonehaven CS - now Winchelsea | Compressors | Augmentation | Yes | 8134553.96 | 26606375.39 | 2492547.98 | 877.27 | 189.03 | 37234543.63 | 4309004.3764 | 29602016.1411 | 0 | 0 | 0 | 33911020.5175 |  |  | 37233477.33 | 877.27 | 189.03 | 37234543.63
2 | Warragul Looping | Pipelines | Augmentation | Yes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2517235.2838 | 0 | 0 | 0 | 2517235.2838 |  |  |  |  | 0 | 0
3 | Anglesea Pipeline Extension | Pipelines | Augmentation | Yes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1289952.7622 | 11551411.6212 | 0 | 0 | 12841364.3835 |  |  |  |  | 0 | 0
4 | Wollert CS A Unit reinstrumentation | Compressors | Replacement | Yes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 252120.4319 | 252708.1907 | 0 | 504828.6226 |  |  |  |  | 0 | 0
5 | BCS Filter | City Gates & Field Regs | Replacement | Yes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 402388.9808 | 0 | 0 | 0 | 402388.9808 |  |  |  |  | 0 | 0
6 | Wollert to Barnawartha Looping | Pipelines | Augmentation | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0
7 | Iona CS - Inlet Pressure Reduction | Compressors | Replacement | Yes | 104428.1 | 9056 | 0 | 0 | 0 | 113484.1 | 90049.12 | 0 | 0 | 0 | 0 | 90049.12 | 104428.1 | 9056 | 0 | 0 | 0 | 113484.1
8 | Iona CS Control system replacement | Compressors | Replacement | Yes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 663922.5128 | 0 | 0 | 0 | 663922.5128 |  |  |  |  | 0 | 0
9 | SCS Cooler Upgrade | Compressors | Replacement | Yes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 909192.0344 | 0 | 0 | 909192.0344 |  |  |  |  | 0 | 0
10 | Rockbank PRS | City Gates & Field Regs | Replacement | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0
11 | BCS Emergency Lighting | Other | Replacement | Yes | 61810.95 | 0 | 0 | 0 | 0 | 61810.95 | 12688.7 | 0 | 0 | 0 | 0 | 12688.7 | 61810.95 | 0 | 0 | 0 | 0 | 61810.95
12 | GCS Emergency Lighting Upgrade | Other | Replacement | Yes | 879.8 | 0 | 0 | 0 | 0 | 879.8 | -6200.92 | 0 | 0 | 0 | 0 | -6200.92 | 879.8 | 0 | 0 | 0 | 0 | 879.8
13 | Wollert CS Emergency Lighting | Other | Replacement | Yes | 0 | 111330.8 | 0 | 0 | 0 | 111330.8 | 50134.75 | 0 | 0 | 0 | 0 | 50134.75 |  | 111330.8 | 0 | 0 | 0 | 111330.8
14 | Emergency - fully equipped caravan | Other | Replacement | Yes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 141829.4511 | 0 | 0 | 0 | 141829.4511 |  |  |  |  | 0 | 0
15 | Emergency - Gas blowdown and flaring sytem | Other | Replacement | Yes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 202382.2122 | 202382.2122 |  |  |  |  | 0 | 0
16 | Emergency - refurbish and re-testing of pipes | Other | Replacement | Yes | 0 | 40300 | 0 | 0 | 0 | 40300 | 0 | 0 | 0 | 12120.2505 | 202382.2122 | 214502.4626 |  | 40300 |  |  | 0 | 40300
17 | Emergency - SMR radio upgrade | Other | Replacement | Yes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 66661.3776 | 0 | 66661.3776 |  |  |  |  | 0 | 0
18 | Emergency BA escape sets | Other | Replacement | Yes | 0 | 0 | 0 | 0 | 0 | 0 | 10029.2 | 0 | 0 | 0 | 0 | 10029.2 |  |  |  |  | 0 | 0
19 | Emergency diesel fuel storage | Other | Replacement | Yes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50294.1316 | 84667.0825 | 0 | 0 | 134961.2141 |  |  |  |  | 0 | 0
20 | Emergency Plidco fittings - Sleeve vent | Pipelines | Replacement | Yes | 0 | 0 | 0 | 0 | 135220 | 135220 | 0 | 0 | 40207.1685 | 191241.7169 | 0 | 231448.8853 | 0 | 0 | 0 | 0 | 135220 | 135220
21 | Emergency Response Equipment | Other | Replacement | Yes | 0 | 14416.72 | 38911 | 30371.33 | 401537.7 | 485236.75 | 90262.8 | 90529.4369 | 90714.7312 | 90901.8786 | 91071.9955 | 453480.8422 | 0 | 14416.72 | 38911 | 30371.33 | 401537.7 | 485236.75
22 | Emergency Spark Proof tools | Other | Replacement | Yes | 0 | 0 | 0 | 0 | 0 | 0 | 20058.4 | 20117.6526 | 20158.8292 | 0 | 0 | 60334.8818 | 0 | 0 | 0 | 0 | 0 | 0
23 | Purchase and replacement of emergency fittings and Equipment | Other | Replacement | Yes | 59521.63 | 173679.9 | 0 | 0 | 0 | 233201.53 | 500705.2547 | 778243.1205 | 0 | 0 | 0 | 1278948.3753 |  | 233201.53 | 0 | 0 | 0 | 233201.53
24 | Facilities Communication Systems Upgrade | Other | Replacement | Yes | 0 | 16081.25 | 0 | 0 | 0 | 16081.25 | 10026.95 | 10061.0718 | 10092.9213 | 10120.506 | 10155.2999 | 50456.749 |  | 16081.25 | 0 | 0 | 0 | 16081.25
25 | GCS Station Valve Upgrade | Compressors | Replacement | Yes | 922.2 | 94508.09 | 0 | 0 | 0 | 95430.29 | 0 | 183832.6928 | 0 | 0 | 0 | 183832.6928 |  | 95430.29 | 0 | 0 | 0 | 95430.29
26 | GCS Unit 3 Turbine Overhaul | Compressors | Replacement | Yes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 353063.1517 | 0 | 0 | 353063.1517 |  |  |  |  | 0 | 0
27 | SMS - Compressor station vents-Various | Compressors | Replacement | Yes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100610.7182 | 0 | 0 | 0 | 100610.7182 |  |  |  |  | 0 | 0
28 | AS 2885 Design Life reviews of Facilities&Pipelines | City Gates & Field Regs | Replacement | Yes | 890.75 | 142234.07 | 54126.05 | 67446.92 | 0 | 264697.79 | 210095.6911 | 213898.8643 | 215318.6246 | 216698.6838 | 325703.4189 | 1181715.2827 | 890.75 | 142234.07 | 54126.05 | 67446.92 | 0 | 264697.79
29 | BCG Un-regulated Bypass Upgrade | City Gates & Field Regs | Replacement | Yes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 126354.0954 | 0 | 126354.0954 |  |  |  |  | 0 | 0
30 | Dandenong CG gas heater | City Gates & Field Regs | Replacement | Yes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2928953.3117 | 0 | 0 | 2928953.3117 |  |  |  |  | 0 | 0
31 | Hazardous Area Rectification | City Gates & Field Regs | Replacement | Yes | 10313.6 | 32182 | 134741 | 142983.16 | 25485.2 | 345704.96 | 185256.1857 | 213753.5702 | 225328.8143 | 163270.8299 | 111172.1288 | 898781.5289 | 10313.6 | 32182 | 134741 | 142983.16 | 25485.2 | 345704.96
32 | Hazardous Areas Review | City Gates & Field Regs | Replacement | Yes | 34062.33 | 0 | 0 | 0 | 0 | 34062.33 | 422529.6954 | 406329.1105 | 277205.7189 | 50746.6663 | 50919.0449 | 1207730.2359 | 34062.33 | 0 | 0 | 0 | 0 | 34062.33
33 | Heater upgrade - Laverton North CG | City Gates & Field Regs | Replacement | Yes | 5671 | 0 | 0 | 0 | 0 | 5671 | 0 | 0 | 0 | 723528.0377 | 0 | 723528.0377 | 5671 | 0 | 0 | 0 | 0 | 5671
34 | Odorant Dandenong Pump Upgrade 700 & 2800 kPa | Gas Quality | Replacement | Yes | 0 | 0 | 285847.41 | 6015.5 | 0 | 291862.91 | 0 | 251504.3405 | 0 | 0 | 0 | 251504.3405 | 0 | 0 | 285847.41 | 6015.5 | 0 | 291862.91
35 | Regulator upgrade - Dandenong City Gate (exclude filters) | City Gates & Field Regs | Replacement | Yes | 479498.96 | 2616566.96 | 7811136.25 | 751879.8 | 59691.29 | 11718773.26 | 3740075.5782 | 1483992.4241 | 0 | 0 | 0 | 5224068.0022 |  |  | 10907202.17 | 751879.8 | 59691.29 | 11718773.26
36 | Valve - Pipeline LNG plant Isolation Valve Actuator Replacement | City Gates & Field Regs | Replacement | Yes | 67874.3 | 307062.84 | 0 | -0.02 | 0 | 374937.12 | 0 | 0 | 93612.1728 | 0 | 0 | 93612.1728 |  | 374937.14 | 0 | -0.02 | 0 | 374937.12
37 | Valve - Pipeline to LNG plant UV325 valve replacement and loading valve | City Gates & Field Regs | Replacement | Yes | 67319.22 | 210131.45 | 0 | 0 | 0 | 277450.67 | 41114.185 | 241444.1669 | 0 | 0 | 0 | 282558.3519 |  | 277450.67 | 0 | 0 | 0 | 277450.67
38 | Valve - Corio CG Un-regulated Bypass Upgrade | City Gates & Field Regs | Replacement | Yes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 126354.0954 | 0 | 126354.0954 |  |  |  |  | 0 | 0
39 | Valve - Tyers Branch Valve Actuator Replacement | Pipelines | Replacement | Yes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 201203.4724 | 0 | 0 | 0 | 201203.4724 |  |  |  |  | 0 | 0
40 | Valve - UniBolt Phase 3 Replacement | City Gates & Field Regs | Replacement | Yes | 1130.5 | 92576.04 | 30257.33 | 53832.91 | 210141.93 | 387938.71 | -110012.58 | 0 | 126093.9827 | 126404.8385 | 0 | 142486.2412 | 1130.5 | 92576.04 | 30257.33 | 53832.91 | 210141.93 | 387938.71
41 | Pig Trap - Enclosure upgrade | City Gates & Field Regs | Replacement | Yes | 0 | 0 | 17709 | 84557.63 | 0 | 102266.63 | 46128.11 | 90541.5626 | 90787.6676 | 91011.4837 | 91267.4178 | 409736.2417 |  | 0 |  | 102266.63 | 0 | 102266.63
42 | Pig Trap - Pipe Support Upgrade | City Gates & Field Regs | Replacement | Yes | 174 | 63266.31 | 250206.75 | 24895.18 | 1526.9 | 340069.14 | 95264.575 | 95571.6494 | 95831.4269 | 96067.6772 | 20281.6484 | 403016.9769 | 174 | 63266.31 | 250206.75 | 24895.18 | 1526.9 | 340069.14
43 | BCS Administration Building Distribution Board Upgrade | Compressors | Non-System | Yes | 0 | -52 | 0 | 0 | 56182.04 | 56130.04 | 30028.85 | 0 | 0 | 0 | 0 | 30028.85 | 0 | -52 | 0 | 0 | 56182.04 | 56130.04
44 | Equipment - Field Equipment | Other | Non-System | Yes | 78414.37 | 33433 | 0 | 0 | 56776.67 | 168624.04 | 47656 | 50294.1316 | 50397.0729 | 50501.0436 | 50595.553 | 249443.8012 | 78414.37 | 33433 | 0 | 0 | 56776.67 | 168624.04
45 | Equipment - Gas Detectors | Other | Non-System | Yes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 101191.1061 | 101191.1061 | 0 | 0 | 0 | 0 | 0 | 0
46 | Equipment - IT Purchases | Other | Non-System | Yes | 28090.5164 | 85086.328 | 94876.5278 | 73787.5668 | 79054.297 | 360895.2361 | 23593.693 | 23663.3889 | 23711.8228 | 23760.741 | 23805.2077 | 118534.8535 | 28090.5164 | 85086.328 | 94876.5278 | 73787.5668 | 79054.297 | 360895.2361
47 | Equipment - Test | Other | Non-System | Yes | 0 | 0 | 0 | 0 | 31930 | 31930 | 50146 | 50294.1316 | 50397.0729 | 50501.0436 | 50595.553 | 251933.8012 | 0 | 0 | 0 | 0 | 31930 | 31930
48 | Equipment - Victorian low value pool purchases | Other | Non-System | Yes | 52890.5047 | 215346.1092 | 550230.7606 | 173195.9057 | 336661.5806 | 1328324.8608 | -126715.05 | 10058.8263 | 10079.4146 | 10100.2087 | 10119.1106 | -86357.4898 | 52890.5047 | 215346.1092 | 550230.7606 | 173195.9057 | 336661.5806 | 1328324.8608
49 | Dandenong 180 Greens Road Office Redevelopment | Buildings | Non-System | Yes | 0 | 0 | 0 | 0 | 0 | 0 | 3847881.4201 | 5368873.9617 | 0 | 0 | 0 | 9216755.3818 |  |  |  |  | 0 | 0
50 | Dandenong Asphalt Resurfacing | Other | Non-System | Yes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 252187.9655 | 0 | 0 | 252187.9655 |  |  |  |  | 0 | 0
51 | Dandenong Complex asbestos removal | Buildings | Non-System | Yes | 0 | 60923.51 | 0 | 0 | 0 | 60923.51 | 75208.875 | 75451.3022 | 30262.5559 | 30337.1612 | 30422.4726 | 241682.3669 |  | 60923.51 | 0 | 0 | 0 | 60923.51
52 | Dandenong external surface repainting | Buildings | Non-System | Yes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100610.7182 | 0 | 0 | 0 | 100610.7182 |  |  |  |  | 0 | 0
53 | Dandenong Office Purchases | Other | Non-System | Yes | 8861.6981 | 34769.95 | 31686.2177 | 0 | 0 | 75317.8658 | -18289.614 | 47326.7778 | 47423.6456 | 47521.4821 | 47610.4154 | 171592.7069 | 8861.6981 | 34769.95 | 31686.2177 | 0 | 0 | 75317.8658
54 | Dandenong Site - Storage shed | Buildings | Non-System | Yes | 11857.7292 | 66978.2157 | 0 | 0 | -86152.2199 | -7316.275 | 442388 | 0 | 0 | 0 | 0 | 442388 |  | 78835.9449 | 0 | 0 | -86152.2199 | -7316.275
55 | Pigging - Tracking and locating tools | Other | Non-System | Yes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20122.1436 | 0 | 0 | 0 | 20122.1436 |  |  |  |  | 0 | 0
56 | Pigging - Two portable liquid collectors for pigging | Other | Non-System | Yes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 235807.7893 | 0 | 235807.7893 |  |  |  |  | 0 | 0
57 | Pigging -Two portable dust collectors for pigging | Other | Non-System | Yes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 234850.3598 | 0 | 0 | 234850.3598 |  |  |  |  | 0 | 0
58 | Control Room - Additonal OE monitor | Other | Non-System | Yes | 0 | 0 | 0 | 0 | 0 | 0 | 10026.95 | 0 | 0 | 0 | 0 | 10026.95 |  |  |  |  | 0 | 0
59 | SCADA - Comms upgrade to IP network-VTS only | Other | Non-System | Yes | 0 | 0 | 0 | 11925 | 1372449.18 | 1384374.18 | 0 | 0 | 0 | 0 | 1813494.5561 | 1813494.5561 | 0 | 0 | 0 | 11925 | 1372449.18 | 1384374.18
60 | SCADA - IT security | Other | Non-System | Yes | 0 | 0 | 0 | 0 | 0 | 0 | 94353.5995 | 0 | 0 | 0 | 0 | 94353.5995 |  |  |  |  | 0 | 0
61 | SCADA - Remote maintenance and engineering workstations [Control Room, Gooding, Brooklyn CS&CG, Wollert CS&CG, Springhurst, Iona] | Other | Non-System | Yes | 0 | 0 | 0 | 0 | 0 | 0 | 10026.95 | 10061.0718 | 10092.9213 | 10120.506 | 10155.2999 | 50456.749 |  |  |  |  | 0 | 0
62 | SCADA - RTU/ PLC/HMI Development and Test bench [PC, iFix, Control Logix, Bristol Designer Tools] | Other | Non-System | Yes | 0 | 0 | 0 | 0 | 0 | 0 | 23435.1125 | 0 | 0 | 0 | 0 | 23435.1125 |  |  |  |  | 0 | 0
63 | SCADA System Upgrade | Other | Non-System | Yes | 0 | 0 | 25383.25 | 63489.53 | 650304.01 | 739176.79 | 0 | 0 | 103816.4325 | 1042838.6837 | 471456.2441 | 1618111.3603 | 0 | 0 | 25383.25 | 63489.53 | 650304.01 | 739176.79
64 | Dandenong Building exterior coatings | Buildings | Non-System | Yes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150599.6738 | 150805.5024 | 0 | 301405.1762 |  |  |  |  | 0 | 0
65 | Dandenong site fire mains replacement | Buildings | Non-System | Yes | 4961.3378 | 88164.1814 | 1020411.517 | 30176.035 | 22378.8 | 1166091.8712 | 260525.5 | 0 | 0 | 0 | 0 | 260525.5 |  |  | 1113537.0362 | 30176.035 | 22378.8 | 1166091.8712
66 | Brooklyn guttering | Buildings | Non-System | Yes | 0 | 0 | 0 | 0 | 53670 | 53670 | 0 | 40008.982 | 0 | 0 | 0 | 40008.982 |  |  |  |  | 53670 | 53670
67 | Wollert Control Room guttering | Buildings | Non-System | Yes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30040.5202 | 0 | 0 | 30040.5202 |  |  |  |  | 0 | 0
68 | Corporate IT | Other | Non-System | Yes | 211241.5961 | 302736.8717 | 276048.921 | 531059.9152 | 502162.3028 | 1823249.6069 | -1518438.1342 | 0 | 0 | 0 | 0 | -1518438.1342 | 211241.5961 | 302736.8717 | 276048.921 | 531059.9152 | 502162.3028 | 1823249.6069
69 | Liquid management - Brooklyn | City Gates & Field Regs | Replacement | Yes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 329938.0122 | 0 | 0 | 329938.0122 |  |  |  |  | 0 | 0
70 | Liquid management - Gooding | City Gates & Field Regs | Replacement | Yes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 179323.053 | 0 | 0 | 0 | 179323.053 |  |  |  |  | 0 | 0
71 | Liquid management - Longford | City Gates & Field Regs | Replacement | Yes | -4131.05 | 0 | 0 | 0 | 0 | -4131.05 | -26613.3 | 0 | 0 | 0 | 0 | -26613.3 | -4131.05 | 0 | 0 | 0 | 0 | -4131.05
72 | Liquid Management - Pakenham | City Gates & Field Regs | Replacement | Yes | 0 | 0 | 0 | 0 | 0 | 0 | 144640.99 | 0 | 0 | 0 | 0 | 144640.99 |  |  |  |  | 0 | 0
73 | CP - Cathodic Protection Replacement | Pipelines | Replacement | Yes | 18725 | 98704 | 20000 | 89800 | 33464.4 | 260693.4 | 111615 | 200600.2392 | 200866.1817 | 201110.3393 | 201384.1158 | 915575.876 | 18725 | 98704 | 20000 | 89800 | 33464.4 | 260693.4
74 | CP - Corrosion Protection Testing Equipment | Other | Replacement | Yes | 0 | 0 | 0 | 47690 | 12494 | 60184 | 10028.3 | 10059.7245 | 10084.8173 | 10108.3276 | 10133.5863 | 50414.7558 |  |  |  | 47690 | 12494 | 60184
75 | Pig Trap - A Branch Valve on Pipeline 108 to Newport Install(124) | Pipelines | Replacement | Yes | 0 | 0 | 20098.4 | 388795.23 | 0 | 408893.63 | 0 | 0 | 0 | 2544803.7983 | 0 | 2544803.7983 |  |  |  |  | 0 | 0
76 | Pig Trap - Dandenong to Princes Highway Pipeline Install (129) | City Gates & Field Regs | Replacement | Yes | 0 | 0 | 31113.5 | 260290.51 | 1385616.27 | 1677020.28 | 0 | 0 | 0 | 0 | 612316.7644 | 612316.7644 |  |  |  |  | 1677020.28 | 1677020.28
77 | Pig Trap - Laverton North to Laverton North Pipeline Install (162) | City Gates & Field Regs | Replacement | Yes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 927231.0325 | 0 | 927231.0325 |  |  |  |  | 0 | 0
78 | Pig Trap - Pakenham to Pakenham Pipeline Install (68) | City Gates & Field Regs | Replacement | Yes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1048301.8019 | 0 | 1048301.8019 |  |  |  |  | 0 | 0
79 | Pigging Program (T1 Dandenong - Morwell) | Other | Replacement | Yes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 544363.3105 | 544363.3105 |  |  |  |  | 0 | 0
80 | Pigging Program (T56 Brooklyn - Ballan) | Other | Replacement | Yes | 0 | 0 | 140780.29 | 273457.91 | 13.35 | 414251.55 | 0 | 0 | 0 | 437345.3352 | 0 | 437345.3352 |  |  |  |  | 414251.55 | 414251.55
81 | Pigging Program (T59 Euro - Kyabram) | Other | Replacement | Yes | 0 | 0 | 0 | 0 | 173370.21 | 173370.21 | 0 | 0 | 0 | 405509.9168 | 0 | 405509.9168 |  |  |  |  | 173370.21 | 173370.21
82 | Pigging Program (T67 Guilford - Maryborough) | Other | Replacement | Yes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 222973.8245 | 222973.8245 |  |  |  |  | 0 | 0
83 | Pigging Program (T74 Keon Park - Wollert) | Other | Replacement | Yes | 5363.81 | 616839.03 | 37257.13 | 41434.17 | 0 | 700894.14 | 463932.6 | 0 | 0 | 0 | 0 | 463932.6 |  | 622202.84 | 37257.13 | 41434.17 | 0 | 700894.14
84 | Pigging Program (T92 Iona - Brooklyn) | Other | Replacement | Yes | 0 | 0 | 67224.28 | 188438.41 | 182993.22 | 438655.91 | 0 | 0 | 0 | 588402.5107 | 0 | 588402.5107 |  |  |  |  | 438655.91 | 438655.91
85 | Pig Trap - Princes Highway to Regent Street Pipeline Install(36) | City Gates & Field Regs | Replacement | Yes | 0 | 0 | 17158.9 | -17158.9 | 0 | 0 | 0 | 0 | 0 | 0 | 1302572.535 | 1302572.535 |  |  |  |  | 0 | 0
86 | Pig Trap - Somerton to Somerton Pipeline Install (238) | City Gates & Field Regs | Replacement | Yes | 0 | 1590 | 24041.28 | -25631.28 | 0 | 0 | 0 | 0 | 1107453.3093 | 0 | 0 | 1107453.3093 |  |  |  |  | 0 | 0
87 | Pig Trap - Tyers to Maryvale Pipeline Install (67) | City Gates & Field Regs | Replacement | Yes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 800555.5831 | 800555.5831 |  |  |  |  | 0 | 0
88 | Exposed pipe coating refurbishment | Pipelines | Replacement | Yes | 0 | 0 | 0 | 0 | 66170 | 66170 | 385280.0457 | 666424.8174 | 451772.5382 | 331747.4951 | 473524.7546 | 2308749.6509 | 0 | 0 | 0 | 0 | 66170 | 66170
89 | BCS Safety and Process Control System and RTU Upgrade | Compressors | Replacement | Yes | 23570.02 | 15134.58 | 12066 | 0 | 0 | 50770.6 | -10182.4 | 0 | 0 | 0 | 0 | -10182.4 | 23570.02 |  | 27200.58 | 0 | 0 | 50770.6
90 | CS Type B compliance upgrade | Compressors | Replacement | Yes | 0 | 0 | 1070 | 389055.47 | 1387215.29 | 1777340.76 | 857042.8 | 0 | 0 | 0 | 0 | 857042.8 |  |  | 1070 | 163698.12 | 1612572.64 | 1777340.76
91 | GCS GEA Fuel Gas Upgrade | Compressors | Replacement | Yes | 0 | 0 | 0 | 44673.16 | 4018.05 | 48691.21 | 50103.83 | 0 | 0 | 0 | 0 | 50103.83 |  |  |  | 44673.16 | 4018.05 | 48691.21
92 | GCS Units 1,2,3&4 Suction/Discharge Actuated Valve Replacement | Compressors | Replacement | Yes | 0 | 0 | 0 | 31842.5 | 22711.09 | 54553.59 | 851826 | 0 | 0 | 0 | 0 | 851826 |  |  |  |  | 54553.59 | 54553.59
93 | Mothball BCS Stage 3 incl BCS8,9,10,11 | Compressors | Replacement | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0
94 | Mothball WCS station 'A' | Compressors | Replacement | Yes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 417567.5792 | 417567.5792 |  |  |  |  | 0 | 0
95 | Regulator Upgrade - Lara pneumatic control system upgrade | City Gates & Field Regs | Replacement | Yes | 0 | 0 | 5301 | 0 | 157902 | 163203 | 200883.4988 | 225031.278 | 0 | 0 | 0 | 425914.7768 |  |  |  |  | 163203 | 163203
96 | Security - High Risk sites security upgrade | Other | Replacement | Yes | 17837.72 | 24900 | 0 | 0 | 0 | 42737.72 | 653450.2343 | 0 | 1013598.5702 | 726387.0907 | 0 | 2393435.8952 | 17837.72 | 24900 | 0 | 0 | 0 | 42737.72
97 | Security - Small Site Facilities Fencing Upgrade | Other | Replacement | Yes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 75380.1395 | 75571.3785 | 75739.067 | 75945.4931 | 302636.0782 | 0 | 0 | 0 | 0 | 0 | 0
98 | Zonal Chromatograph Bottle Regulator Panels Upgrades | Gas Quality | Replacement | Yes | 0 | 0 | 0 | 0 | 35251.2 | 35251.2 | 29343.24 | 0 | 0 | 0 | 0 | 29343.24 | 0 | 0 | 0 | 0 | 35251.2 | 35251.2
99 | Zonal Chromatograph Insertion Probes | Gas Quality | Replacement | Yes | 0 | 0 | 0 | 0 | 0 | 0 | 95138.5 | 0 | 0 | 0 | 0 | 95138.5 |  |  |  |  | 0 | 0
100 | Zonal Chromatograph Upgrades | Gas Quality | Replacement | Yes | 0 | 91009.78 | 0 | 334933 | 0 | 425942.78 | 100175 | 100375.1495 | 100541.3636 | 100693.962 | 0 | 401785.4751 | 0 | 91009.78 | 0 | 334933 | 0 | 425942.78
101 | RTU & Control System Upgrade - Facilities | Other | Replacement | Yes | 98368.47 | 100004.42 | 8235.2 | 130842.63 | 70312.21 | 407762.93 | -177951.8891 | 112280.706 | 112818.8859 | 113323.0898 | 113864.8742 | 274335.6667 | 98368.47 | 100004.42 | 8235.2 | 130842.63 | 70312.21 | 407762.93
102 | GCS Anti-Surge & Fast-Stop Valves Upgrade | Compressors | Replacement | Yes | 0 | 0 | 10038.5 | 543860.57 | 1023154.23 | 1577053.3 | 670537.384 | 0 | 0 | 0 | 0 | 670537.384 |  |  |  |  | 0 | 0
103 | GCS Control Room Fire Suppression System | Compressors | Replacement | Yes | 0 | 0 | 0 | 0 | 213359.56 | 213359.56 | 45121.275 | 100610.7182 | 0 | 0 | 0 | 145731.9932 |  |  |  |  | 213359.56 | 213359.56
104 | GCS Units 1,2,3&4 Fire Suppression System | Compressors | Replacement | Yes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 227711.3845 | 0 | 227711.3845 |  |  |  |  | 0 | 0
105 | Iona CS - Unit Fire Suppression System | Compressors | Replacement | Yes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 281684.8614 | 0 | 0 | 0 | 281684.8614 |  |  |  |  | 0 | 0
106 | Wollert CG Control Hut Fire Suppression System | Compressors | Replacement | Yes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35213.7514 | 35325.2246 | 0 | 0 | 70538.976 |  |  |  |  | 0 | 0
107 | Wollert CS A/B Control Room Fire Suppression System | Compressors | Replacement | Yes | 0 | 0 | 0 | 1008 | 76860.99 | 77868.99 | 0 | 100610.7182 | 126161.5164 | 0 | 0 | 226772.2346 |  |  |  |  | 77868.99 | 77868.99
108 | BCG Control Hut Fire Suppression System | City Gates & Field Regs | Replacement | Yes | 0 | 0 | 0 | 0 | 40000 | 40000 | 65175.175 | 0 | 0 | 0 | 0 | 65175.175 |  |  |  |  | 40000 | 40000
109 | Valve - Actuate MLV's in T1 areas | Pipelines | Replacement | Yes | 0 | 0 | 0 | 5359.6 | 85787.9 | 91147.5 | 0 | 1318211.3589 | 1320304.4754 | 1322147.5981 | 0 | 3960663.4324 |  |  |  |  | 91147.5 | 91147.5
110 | Valve - Longford to Dandenong LV10 Vent Stack | Pipelines | Replacement | Yes | 34177.3 | 39851.75 | 0 | 0 | 0 | 74029.05 | 33404.0563 | 0 | 0 | 0 | 0 | 33404.0563 |  | 74029.05 | 0 | 0 | 0 | 74029.05
111 | BCS Station Isolation and Loading Valves | Compressors | Replacement | Yes | 2244.6 | 16577.75 | 183683.64 | 1608978.12 | 38092.44 | 1849576.55 | 0 | 914005.1414 | 0 | 0 | 0 | 914005.1414 |  |  |  | 1811484.11 | 38092.44 | 1849576.55
112 | Iona CS - Capacity Aftercooler upgrade | Compressors | Replacement | Yes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 709036.4354 | 0 | 0 | 0 | 709036.4354 |  |  |  |  | 0 | 0
113 | BCS DEA Upgrade | Compressors | Replacement | Yes | 1160 | 17428 | 0 | 144959 | 426295.17 | 589842.17 | 0 | 0 | 354548.5777 | 0 | 0 | 354548.5777 |  |  |  |  | 589842.17 | 589842.17
114 | BCS GEA Upgrade | Compressors | Replacement | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0
115 | Pig Trap - Keon Park Install | City Gates & Field Regs | Replacement | Yes | 325106.72 | 1640823.98 | 0 | 0 | 0 | 1965930.7 | -375147.25 | 0 | 0 | 0 | 0 | -375147.25 |  | 1965930.7 | 0 | 0 | 0 | 1965930.7
116 | BCS Replacement of FSV, ASV & Other Valves | Compressors | Replacement | Yes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 894640.3511 | 0 | 0 | 0 | 894640.3511 |  |  |  |  | 0 | 0
117 | BCS Unit 10 & 11 Cooler Upgrade | Compressors | Replacement | Yes | 27089.84 | 889622.65 | 5007242.54 | 3272234.09 | 0 | 9196189.12 | -7007.61 | 3350780.2388 | 0 | 0 | 0 | 3343772.6288 |  |  |  | 9196189.12 | 0 | 9196189.12
118 | SMS - GIS & Aerial Photography | Pipelines | Replacement | No | 0 | 0 | 87 | 144969.5 | 0 | 145056.5 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 145056.5 | 0 | 145056.5
119 | SMS - Vehicle Barrier Protection | Pipelines | Replacement | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0
120 | SMS - Site Hazops | Pipelines | Replacement | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0
121 | SMS - Bush Fire Impact Studies | Pipelines | Replacement | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0
122 | Wollert to Clonbinane Looping | Pipelines | Augmentation | Yes | 4006990.75 | 85648927.66 | 65640112.89 | 813975.86 | 366946.99 | 156476954.15 | 1819127.1999 | 34518284.328 | 0 | 0 | 0 | 36337411.5279 |  | 32280328.01 | 123650906.7 | 813975.86 | -268256.01 | 156476954.56
123 | MAOP Upgrade - Euroa to Springhurst | Pipelines | Augmentation | Yes | 0 | 0 | 0 | 0 | 0 | 0 | 190659.3106 | 1722649.6837 | 0 | 0 | 0 | 1913308.9944 |  |  |  |  | 0 | 0
124 | Valve - T60 Longford - Dandenong Upgrade hydraulic hand pump of actuators | Other | Replacement | Yes | 0 | 0 | 0 | 0 | 0 | 0 | 110306.35 | 0 | 0 | 0 | 0 | 110306.35 |  |  |  |  | 0 | 0
125 | VTS - BROOKLYN LARA LOOP | Pipelines | Replacement | Yes | 0 | 0 | 0 | 0 | 0 | 0 | -22513.1 | 0 | 0 | 0 | 0 | -22513.1 | 0 | 0 |  | 0 | 0 | 0
126 | VTS - WOLLERT 4 & 5 CAPEX | Compressors | Replacement | Yes | 3203.9 | 5158.96 | 0 | 0 | 0 | 8362.86 | -12958.5 | 0 | 0 | 0 | 0 | -12958.5 | 3203.9 | 5158.96 |  |  | 0 | 8362.86
127 | VTS - MORWELL TYERS UPGRADE | City Gates & Field Regs | Replacement | Yes | 6147.52 | 0 | 0 | 0 | 0 | 6147.52 | -224.47 | 0 | 0 | 0 | 0 | -224.47 | 6147.52 | 0 | 0 | 0 | 0 | 6147.52
128 | VTS - MAOP UPGRADE CAPEX | City Gates & Field Regs | Replacement | Yes | 0 | -42.39 | 0 | 0 | 0 | -42.39 | -15153.32 | 0 | 0 | 0 | 0 | -15153.32 | 0 | -42.39 | 0 | 0 | 0 | -42.39
129 | VTS - BBP & BCP CG UPGRADE | City Gates & Field Regs | Replacement | Yes | 0 | 0 | 0 | 0 | 0 | 0 | -96840.03 | 0 | 0 | 0 | 0 | -96840.03 |  |  |  |  | 0 | 0
130 | VTS - BRANCH VALVE CASTLEMAINE | Pipelines | Replacement | Yes | 0 | 0 | 0 | 0 | 0 | 0 | -25899.12 | 0 | 0 | 0 | 0 | -25899.12 |  |  |  |  | 0 | 0
131 | VTS - EUROA CS NEW (PPOM) | Compressors | Replacement | Yes | 116664.37 | 121805.28 | 59020.54 | -2941.24 | 0 | 294548.95 | -411065.65 | 0 | 0 | 0 | 0 | -411065.65 | 116664.37 | 121805.28 | 59020.54 | -2941.24 | 0 | 294548.95
132 | VTS - SUNBURY PIPE LOOP (NEW) | Pipelines | Replacement | Yes | 51715.09 | 38571.05 | 5019.95 | -654.99 | 0 | 94651.1 | -483491.84 | 0 | 0 | 0 | 0 | -483491.84 | 51715.09 | 38571.05 | 5019.95 | -654.99 | 0 | 94651.1
133 | VTS - BCS 8&9 COOLERS UPG (NEW | Compressors | Replacement | Yes | -12591.73 | 22820.08 | 0 | 0 | 0 | 10228.35 | -453916.73 | 0 | 0 | 0 | 0 | -453916.73 | -12591.73 | 22820.08 | 0 | 0 | 0 | 10228.35
134 | VTS - BCS 12 FAST STOP VALVE | Compressors | Replacement | Yes | 0 | 0 | 0 | 0 | 0 | 0 | -35578.82 | 0 | 0 | 0 | 0 | -35578.82 |  |  |  |  | 0 | 0
135 | VTS - BCS 8 & 9 UNIT VALVES | Compressors | Replacement | Yes | 0 | 0 | 0 | 0 | 0 | 0 | -281229.85 | 0 | 0 | 0 | 0 | -281229.85 |  |  |  |  | 0 | 0
136 | PIGGING T91 CURDIEVALE | Other | Replacement | No | 0 | 17873 | 0 | 0 | 0 | 17873 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17873 | 0 | 0 | 0 | 17873
137 | VTS - BROOKLYN FIRE SERVICE | Buildings | Non-System | Yes | 29482.73 | 11269.5 | 0 | 0 | 0 | 40752.23 | -426344.52 | 0 | 0 | 0 | 0 | -426344.52 |  | 40752.23 | 0 | 0 | 0 | 40752.23
138 | VTS - BCS LUBE OIL COOLER 8&9 | City Gates & Field Regs | Replacement | No | 109672.54 | 0 | 0 | 0 | 0 | 109672.54 | 0 | 0 | 0 | 0 | 0 | 0 | 109672.54 | 0 | 0 | 0 | 0 | 109672.54
139 | VNIE Looping 6 to 8 | Pipelines | Augmentation | No | 0 | 0 | 6392032.4513 | 74341242.7516 | 44559438.9085 | 125292714.1114 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 125292714.1114 | 125292714.1114
140 | VTS16.SIB42 WOLL SOFT STARTERS | Other | Replacement | No | 0 | 0 | 0 | 30881 | 0 | 30881 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 30881 | 30881
141 | VTS.SIB99 WCS STN-A DISCHRG LQ | Other | Replacement | No | 0 | 0 | 0 | 219226.8 | 5400 | 224626.8 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0
142 | VTS17.SIB27 SCS CR EPS REMOVAL | Buildings | Non-System | No | 0 | 0 | 0 | 2856.8 | 321349.4 | 324206.2 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 324206.2 | 324206.2
143 | VTS17.SIB30 DND EMERG ENTRANCE | Buildings | Non-System | No | 0 | 0 | 0 | 24545.55 | 0 | 24545.55 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 24545.55 | 24545.55
144 | Corporate other | Other | Non-System | No | 242365.2632 | 340342.973 | 308327.8805 | 17522.8525 | 193217.0674 | 1101776.0366 | 0 | 0 | 0 | 0 | 0 | 0 | 242365.2632 | 340342.973 | 308327.8805 | 17522.8525 | 193217.0674 | 1101776.0366
145 | Market Services _APA Grid Prog | Other | Non-System | No | 0 | 0 | 153669.9247 | 156678.9204 | 0 | 310348.845 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 310348.845 | 0 | 310348.845
146 | APA Grid Perf & Resil Overhaul | Other | Non-System | No | 0 | 0 | 44725.1667 | 22022.8998 | 0 | 66748.0665 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 44725.1667 | 22022.8998 | 0 | 66748.0665
147 | APA Grid & Mrkt Srvs SIB Capex | Other | Non-System | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
148 | APA Grid Extend | Other | Non-System | No | 0 | 0 | 0 | 80289.867 | 681495.7221 | 761785.5891 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 80289.867 | 681495.7221 | 761785.5891
149 | APA Grid Services Initiatives | Other | Non-System | No | 0 | 0 | 0 | 188898.9119 | 93837.1179 | 282736.0298 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 188898.9119 | 93837.1179 | 282736.0298
150 | CORP SIB16 DANDENONG REFURB | Other | Non-System | No | 0 | 0 | 303211.3819 | 3462.88 | 0 | 306674.2619 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 303211.3819 | 3462.88 | 0 | 306674.2619
151 | Data Centre | Other | Non-System | No | 65362.0189 | 895833.2344 | 79250.1745 | 0 | 0 | 1040445.4278 | 0 | 0 | 0 | 0 | 0 | 0 |  | 961195.2533 | 79250.1745 | 0 | 0 | 1040445.4278
152 | Enterprise Asset Management | Other | Non-System | No | 806330.3274 | 1986550.9701 | 2564771.5454 | 1771.8759 | -11.219 | 5359413.4998 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 5357652.8429 | 1771.8759 | -11.219 | 5359413.4998
153 | Enterprise Content Management | Other | Non-System | No | 0 | 0 | 104729.0841 | 399680.7896 | 555995.9985 | 1060405.8722 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 504409.8737 | 555995.9985 | 1060405.8722
154 | EAM Bus Support & Governance | Other | Non-System | No | 0 | 0 | 0 | 42640.3455 | 65.1413 | 42705.4868 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42640.3455 | 65.1413 | 42705.4868
155 | EAM TRANSMISSION ESTAB WORK | Other | Non-System | No | 0 | 0 | 0 | 199413.8739 | 247813.8633 | 447227.7372 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 199413.8739 | 247813.8633 | 447227.7372
156 | Oracle Integration with EAM | Other | Non-System | No | 0 | 0 | 0 | 10956.5236 | 0 | 10956.5236 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10956.5236 | 0 | 10956.5236
157 | EAM Business Support-Reports | Other | Non-System | No | 0 | 0 | 0 | 5944.4937 | 3565.8563 | 9510.3501 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5944.4937 | 3565.8563 | 9510.3501
158 | EC Upgrade | Other | Non-System | No | 0 | 0 | 0 | 256499.7136 | 139404.1118 | 395903.8254 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 256499.7136 | 139404.1118 | 395903.8254
159 | Finance Systems | Other | Non-System | No | 1751.8135 | 0 | 0 | 0 | 0 | 1751.8135 | 0 | 0 | 0 | 0 | 0 | 0 | 1751.8135 | 0 | 0 | 0 | 0 | 1751.8135
160 | Mobile phone CAPEX purchases | Other | Non-System | No | 0 | 22811.9773 | 27279.5795 | 34752.7222 | 21127.7494 | 105972.0283 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22811.9773 | 27279.5795 | 34752.7222 | 21127.7494 | 105972.0283
161 | PPOM Phase 2 | Other | Non-System | No | 5453.1938 | 0 | 0 | 0 | 0 | 5453.1938 | 0 | 0 | 0 | 0 | 0 | 0 | 5453.1938 | 0 | 0 | 0 | 0 | 5453.1938
162 | Project Server Status Report | Other | Non-System | No | 7605.6406 | 4061.9411 | 0 | 0 | 0 | 11667.5817 | 0 | 0 | 0 | 0 | 0 | 0 | 7605.6406 | 4061.9411 | 0 | 0 | 0 | 11667.5817
163 | BI reporting | Other | Non-System | No | 33318.3814 | 2571.9179 | 0 | 0 | 0 | 35890.2993 | 0 | 0 | 0 | 0 | 0 | 0 | 33318.3814 | 2571.9179 | 0 | 0 | 0 | 35890.2993
164 | PPOM Snapshot Engine | Other | Non-System | No | 9285.9184 | 12608.9365 | 0 | 0 | 0 | 21894.8549 | 0 | 0 | 0 | 0 | 0 | 0 | 9285.9184 | 12608.9365 | 0 | 0 | 0 | 21894.8549
165 | APA Grid Ph.2 | Other | Non-System | No | 135912.9265 | 98899.2122 | 0 | 0 | 0 | 234812.1387 | 0 | 0 | 0 | 0 | 0 | 0 |  | 234812.1387 |  |  | 0 | 234812.1387
166 | APA Grid Ph. 3 | Other | Non-System | No | 2637.3633 | 0 | 0 | 0 | 0 | 2637.3633 | 0 | 0 | 0 | 0 | 0 | 0 |  | 2637.3633 |  |  | 0 | 2637.3633
167 | Vehicle Comms & Journey Mgmt | Other | Non-System | No | 0 | 2091.1818 | 85100.7826 | 156458.5302 | -8653.3782 | 234997.1164 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 243650.4946 | -8653.3782 | 234997.1164
168 | SCADA Satellite Strategy | Other | Non-System | No | 0 | 0 | 37193.7062 | 94128.7989 | 45922.7906 | 177245.2957 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 131322.5051 | 45922.7906 | 177245.2957
169 | SCADA Resilience Project FEED | Other | Non-System | No | 0 | 0 | 0 | 19777.1403 | 0 | 19777.1403 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19777.1403 | 0 | 19777.1403
170 | IOC SCADA GAP ANALYSIS | Other | Non-System | No | 0 | 0 | 0 | 4246.8422 | 0 | 4246.8422 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4246.8422 | 0 | 4246.8422
171 | SCADA Resilience Phase 1 Recom | Other | Non-System | No | 0 | 0 | 0 | 22462.5329 | 67609.9204 | 90072.4533 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22462.5329 | 67609.9204 | 90072.4533
172 | Melbourne Metro CRE | Other | Non-System | No | 0 | 0 | 0 | 4584380.0134 | 1008115.8558 | 5592495.8692 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4584380.0134 | 1008115.8558 | 5592495.8692
173 | HR Systems Refresh | Other | Non-System | No | 0 | 0 | 0 | 0 | 152663.248 | 152663.248 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 152663.248 | 152663.248
174 | Historian Upgrade - version 2012 to 2015 | Other | Non-System | No | 0 | 0 | 0 | 0 | 41738.0552 | 41738.0552 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 41738.0552 | 41738.0552
175 | EAM System Upgrade 2018 | Other | Non-System | No | 0 | 0 | 0 | 0 | 109617.3011 | 109617.3011 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 109617.3011 | 109617.3011
176 | BizTalk Upgrade FY2018 | Other | Non-System | No | 0 | 0 | 0 | 0 | 101135.0037 | 101135.0037 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 101135.0037 | 101135.0037
177 | Code Management Software | Other | Non-System | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0
178 | X-Info Aware Version 2 | Other | Non-System | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0
179 | Adjustments required for differences in CWIP and FAR records | Other | Non-System | No | 0 | -26601 | 23200 | 0 | 0 | -3401 | 0 | 0 | 0 | 0 | 0 | 0 |  | -26601 | 23200 |  | 0 | -3401
180 | Sharepoint site | Other | Non-System | No | 0 | 0 | 0 | 0 | 65134.503 | 65134.503 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 65134.503 | 65134.503
181 | APA Grid | Other | Non-System | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0
182 | B&T projects | Other | Non-System | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0
183 | Dandenong Relocation | Other | Non-System | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0
184 | Victoria CRE | Other | Non-System | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0
185 | Access Arrangement Costs | Other | Non-System | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0
186 | Trans EAM Data Management Tool | Other | Non-System | No | 0 | 0 | 0 | 2653.6996 | 0 | 2653.6996 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2653.6996 | 0 | 2653.6996
187 | EAM Site Stores/Warehouses | Other | Non-System | No | 0 | 0 | 0 | 25238.5762 | 0 | 25238.5762 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25238.5762 | 0 | 25238.5762
188 | BI - Transmission Dashboard and Enterprise Pilot | Other | Non-System | No | 0 | 0 | 0 | 0 | 47542.4471 | 47542.4471 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 47542.4471 | 47542.4471
189 | APA Grid Future Initiatives Projects | Other | Non-System | No | 0 | 0 | 0 | 0 | 121083.5996 | 121083.5996 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 121083.5996 | 121083.5996
190 | GRC Platform | Other | Non-System | No | 0 | 0 | 0 | 0 | 19591.6678 | 19591.6678 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 19591.6678 | 19591.6678
191 | Direct Link Dispatch Display Application Replacement | Other | Non-System | No | 0 | 0 | 0 | 0 | 11747.9477 | 11747.9477 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 11747.9477 | 11747.9477
192 | T92 & DDN3 RTU Upgrade | Other | Replacement | No | 0 | 0 | 0 | 5215.8 | 40207.33 | 45423.13 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 45423.13 | 45423.13
193 | SCS Vent Modifications | Other | Replacement | No | 0 | 0 | 0 | 6011.3 | 11569.73 | 17581.03 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0
194 | BCS Admin Board Upgrade | Buildings | Non-System | No | 0 | 0 | 0 | 384 | 21276.8 | 21660.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 21660.8 | 21660.8
195 | Pigging Program (T57 & T70) | Pipelines | Replacement | No | 0 | 0 | 0 | 0 | 494213.62 | 494213.62 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 494213.62 | 494213.62
196 | REMOTE CP MONITOR (37863) | Pipelines | Replacement | No | 0 | 0 | 0 | 0 | 254005.25 | 254005.25 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 254005.25 | 254005.25
197 | Maryvale Direct Assessment | Pipelines | Replacement | No | 0 | 0 | 0 | 0 | 91167.02 | 91167.02 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 91167.02 | 91167.02
198 | Wichelsea Bi Direction and Brooklyn Reconfiguration | Compressors | Augmentation | No | 0 | 0 | 0 | 0 | 3179000.24 | 3179000.24 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 3179000.24 | 3179000.24
199 | ILUKA WBH FIRE TUBE | Pipelines | Replacement | No | 0 | 0 | 0 | 0 | 23875 | 23875 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 23875 | 23875
200 | REMOTE CP MONITOR (38260) | Pipelines | Replacement | No | 0 | 0 | 0 | 0 | 59511.13 | 59511.13 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 59511.13 | 59511.13
201 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
202 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
203 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
204 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Note on J165: Allen, Mark: Delete to remove double counting

## 3.0 Input│AMP
3.0 Input│AMP
Item Ref. | Access Arrangement Description | Business case number | Allocator | Asset Class | Asset Category | 2018 | 2019 | 2020 | 2021 | 2022 | Labour | Material | Plant | Subcontract | Other | Total
1 | All CS buffer Air shutoff system for all compressors | 202 | VTS | Compressors | Replacement | 381730.5067 | 190865.2533 | 0 | 0 | 0 | 23.66% | 74.37% | 0% | 1.964% | 0% | 100% | Correct | 572595.76
2 | WCS A Process Safety | 203 | VTS | Compressors | Replacement | 0 | 0 | 1045505.76 | 0 | 0 | 23.66% | 48.65% | 0% | 27.69% | 0% | 100% | Correct | 1045505.76
3 | Brooklyn Compressor Station | 204 | VTS | Compressors | Replacement | 0 | 0 | 2297362.2833 | 2297362.2833 | 2297362.2833 | 25.12% | 46.38% | 0% | 28.49% | 0% | 100% | Correct | 6892086.85
4 | Compressor Station Vent Stack Upgrade (BCS, WCS, GCS, SCS) | 205 | VTS | Compressors | Replacement | 0 | 330397.72 | 330397.72 | 330397.72 | 0 | 23.66% | 29.62% | 0% | 26.54% | 20.18% | 100% | Correct | 991193.16
5 | Longford Odorant Pump Power Gas Upgrade | 206 | VTS | Odourant Plants | Replacement | 75569.2 | 0 | 0 | 0 | 0 | 28.57% | 32.83% | 0% | 33.54% | 5.06% | 100% | Correct | 75569.2
6 | GCS compressor unit vent valves & actuators replacement | 207a | VTS | Compressors | Replacement | 139391.86 | 0 | 0 | 0 | 0 | 23.66% | 47.61% | 0% | 28.73% | 0% | 100% | Correct | 139391.86
7 | GCS unit discharge and station manifold check valves replacement | 207b | VTS | Compressors | Replacement | 0 | 0 | 901953.34 | 0 | 0 | 24.64% | 56.58% | 0% | 18.78% | 0% | 100% | Correct | 901953.34
8 | GCS Decomm & removal of turbine oil reservoir & auto fill system | 207c | VTS | Compressors | Replacement | 0 | 87971.74 | 0 | 0 | 0 | 23.66% | 0.74% | 0% | 75.6% | 0% | 100% | Correct | 87971.74
9 | BCS Instrument Air reliability upgrade | 208 | VTS | Compressors | Replacement | 93782.9 | 0 | 0 | 0 | 0 | 23.66% | 27.93% | 0% | 48.4% | 0% | 100% | Correct | 93782.9
10 | Compressor lagging and pipe coating replacement (expand to GCS, Springhurst/BCS12/WCS A/WCS B, Euroa) | 209 | VTS | Compressors | Replacement | 144918.75 | 144918.75 | 144918.75 | 144918.75 | 144918.75 | 23.66% | 0% | 0% | 76.34% | 0% | 100% | Correct | 724593.75
11 | Storage shed-Dandenong, Wollert & Springhurst | 210 | Victoria | Buildings | Non-System | 0 | 648767 | 648767 | 648767 | 0 | 28.57% | 0% | 0% | 71.43% | 0% | 100% | Correct | 1946301
12 | Iona CS aftercooler augmentation | 211 | VTS | Compressors | Replacement | 0 | 0 | 0 | 1656341.4 | 0 | 28.57% | 34.02% | 0% | 37.41% | 0% | 100% | Correct | 1656341.4
13 | Battery replacement | 212 | VTS | Other | Replacement | 70284.2 | 70284.2 | 70284.2 | 70284.2 | 70284.2 | 32.67% | 48.02% | 0% | 14.76% | 4.553% | 100% | Correct | 351421
14 | Wollert CG Instrument Air Conversion | 216 | VTS | City Gates & Field Regs | Replacement | 0 | 0 | 0 | 504246.51 | 0 | 23.66% | 19.8% | 0% | 56.54% | 0% | 100% | Correct | 504246.51
15 | Pit installation on LV03 bypass valves on T33 | 220 | VTS | Pipelines | Replacement | 0 | 0 | 230860 | 0 | 0 | 28.57% | 13.37% | 0% | 58.06% | 0% | 100% | Correct | 230860
16 | Dandenong water supply & fire main modification | 223 | Victoria | Buildings | Non-System | 324178.4 | 0 | 0 | 0 | 0 | 28.57% | 0% | 0% | 71.43% | 0% | 100% | Correct | 324178.4
17 | Culcairn Injection Gas Quality equipment | 224 | VTS | Gas Quality | Replacement | 973960.4 | 0 | 0 | 0 | 0 | 28.57% | 66.77% | 0% | 4.661% | 0% | 100% | Correct | 973960.4
18 | Positioner Replacement | 225 | VTS | Other | Replacement | 101494.96 | 101494.96 | 101494.96 | 101494.96 | 101494.96 | 35.1% | 31.94% | 0% | 22.08% | 10.88% | 100% | Correct | 507474.8
19 | VTS Safety Management Study aerial photography | 227 | VTS | Other | Replacement | 162466.1262 | 2780.5938 | 0 | 0 | 0 | 21.88% | 0% | 0% | 0% | 78.12% | 100% | Correct | 165246.72
20 | BLP Safety Measures for High Consequence areas-(urban growth, fracture control) | 230b | VTS | Pipelines | Replacement | 0 | 2492000 | 0 | 0 | 1869000 | 21.88% | 29.86% | 0% | 48.26% | 0% | 100% | Correct | 4361000
21 | WOP Safety Measures for High Consequence areas-(urban growth, fracture control) | 230c | VTS | Pipelines | Replacement | 1120000 | 0 | 0 | 0 | 0 | 21.88% | 30.02% | 0% | 48.11% | 0% | 100% | Correct | 1120000
22 | ILP Safety Measures for High Consequence areas-(urban growth, fracture control) | 230e | VTS | Pipelines | Replacement | 27000.6267 | 28057.2933 | 0 | 0 | 0 | 21.88% | 16.84% | 0% | 61.29% | 0% | 100% | Correct | 55057.92
23 | Turbine Overhauls | 235 | VTS | Compressors | Replacement | 0 | 0 | 0 | 1004594.5846 | 3594396.2154 | 23.66% | 0% | 0% | 76.34% | 0% | 100% | Correct | 4598990.8
24 | Iona CS Automation replacement | 236 | VTS | Compressors | Replacement | 0 | 0 | 1173411.54 | 0 | 0 | 36.55% | 45.54% | 0% | 17.91% | 0% | 100% | Correct | 1173411.54
25 | GCS Control Room and Unit Enclosure 1,2,3&4 Fire Suppression System | 237a | VTS | Compressors | Replacement | 268558.9473 | 0 | 0 | 0 | 0 | 23.66% | 0% | 0% | 76.34% | 0% | 100% | Correct | 268558.9473
26 | BCS MCC Room Fire Suppression System | 237b | VTS | Compressors | Replacement | 0 | 0 | 268558.9473 | 0 | 0 | 23.66% | 0% | 0% | 76.34% | 0% | 100% | Correct | 268558.9473
27 | Iona CS Control Room and Unit Enclosure Fire Suppression System | 237d | VTS | Compressors | Replacement | 0 | 0 | 0 | 268558.9473 | 0 | 23.66% | 0% | 0% | 76.34% | 0% | 100% | Correct | 268558.9473
28 | Lara City Gate Control Hut Fire Suppression System | 237e | VTS | City Gates & Field Regs | Replacement | 0 | 0 | 0 | 0 | 82002.732 | 28.57% | 0% | 0% | 71.43% | 0% | 100% | Correct | 82002.732
29 | BCS Control Room Fire Suppression System | 237f | VTS | Compressors | Non-System | 0 | 0 | 0 | 0 | 82002.732 | 28.57% | 0% | 0% | 71.43% | 0% | 100% | Correct | 82002.732
30 | Emergency- BA escape sets | 239a | Victoria | Other | Replacement | 19083.52 | 0 | 0 | 0 | 0 | 21.88% | 78.12% | 0% | 0% | 0% | 100% | Correct | 19083.52
31 | Emergency- Response Equipment | 239b | Victoria | Other | Replacement | 278309.12 | 278309.12 | 278309.12 | 278309.12 | 278309.12 | 21.88% | 77.87% | 0% | 0.258% | 0% | 100% | Correct | 1391545.6
32 | Emergency- Spark Proof tools | 239c | Victoria | Other | Replacement | 1945.6 | 1945.6 | 1945.6 | 1945.6 | 1945.6 | 58.88% | 41.12% | 0% | 0% | 0% | 100% | Correct | 9728
33 | Emergency - fully equipped caravan | 239d | Victoria | Other | Replacement | 0 | 0 | 107878.4 | 0 | 0 | 21.88% | 73.58% | 0% | 4.542% | 0% | 100% | Correct | 107878.4
34 | Emergency diesel fuel storage | 239e | Victoria | Other | Replacement | 0 | 0 | 0 | 123107.84 | 0 | 21.88% | 41.12% | 0% | 37% | 0% | 100% | Correct | 123107.84
35 | Vent stack for CL600 & 900 pipeline | 240 | VTS | Pipelines | Replacement | 210339.84 | 0 | 0 | 0 | 0 | 21.88% | 78.12% | 0% | 0% | 0% | 100% | Correct | 210339.84
36 | Remote CP/critical drainage bond monitoring | 241 | VTS | Other | Replacement | 573053.7778 | 60456.5556 | 60456.5556 | 60456.5556 | 60456.5556 | 33.41% | 64.43% | 0% | 0% | 2.163% | 100% | Correct | 814880
37 | BCG Un-regulated Bypass Upgrade | 242 | VTS | City Gates & Field Regs | Replacement | 0 | 0 | 342346.24 | 0 | 0 | 23.42% | 9.593% | 0% | 66.99% | 0% | 100% | Correct | 342346.24
38 | Security - Physical | 243 | Victoria | Buildings | Non-System | 365236.384 | 365236.384 | 365236.384 | 365236.384 | 365236.384 | 37.33% | 0% | 0% | 62.67% | 0% | 100% | Correct | 1826181.92
39 | CP - Cathodic Protection Replacement | 244 | VTS | Other | Replacement | 232464.384 | 232464.384 | 232464.384 | 232464.384 | 232464.384 | 36.12% | 52.09% | 1.084% | 4.938% | 5.766% | 100% | Correct | 1162321.92
40 | Equipment - Gas Detectors | 245 | Victoria | Other | Non-System | 0 | 0 | 25000 | 25000 | 0 | 0% | 100% | 0% | 0% | 0% | 100% | Correct | 50000
41 | Regulator Upgrade - Lara pneumatic control system upgrade | 247 | VTS | City Gates & Field Regs | Replacement | 0 | 619257.8 | 0 | 0 | 0 | 32.45% | 53.39% | 0% | 14.16% | 0% | 100% | Correct | 619257.8
42 | Hazardous Area Rectification | 249 | VTS | Other | Replacement | 178000 | 178000 | 178000 | 178000 | 178000 | 11.24% | 38.2% | 0% | 50.56% | 0% | 100% | Correct | 890000
43 | Actuate MLV's in T1 areas | 250 | VTS | Pipelines | Replacement | 956710.4 | 956710.4 | 0 | 0 | 0 | 21.88% | 62.21% | 0% | 10.89% | 5.017% | 100% | Correct | 1913420.8
44 | Asbestos removal and replacement | 251 | VTS | Other | Non-System | 70000 | 70000 | 70000 | 70000 | 70000 | 28.57% | 0% | 0% | 71.43% | 0% | 100% | Correct | 350000
45 | T33 non-piggable and encased sections (unknown technical solution) | 257 | VTS | Other | Replacement | 151759.04 | 151759.04 | 151759.04 | 151759.04 | 0 | 25.63% | 5.189% | 0% | 69.18% | 0% | 100% | Correct | 607036.16
46 | Pigging Program T57 Ballan - Ballarat | 258a | VTS | Other | Replacement | 564768 | 0 | 0 | 0 | 0 | 22.3% | 3.564% | 0% | 74.14% | 0% | 100% | Correct | 564768
47 | Pigging Program T62 Derrimut - Sunbury | 258b | VTS | Other | Replacement | 425799.68 | 0 | 0 | 0 | 0 | 22.44% | 2.461% | 0% | 75.1% | 0% | 100% | Correct | 425799.68
48 | Pigging Program T61 Packenham - Wollert | 258c | VTS | Other | Replacement | 0 | 649896.96 | 0 | 0 | 0 | 22.24% | 7.276% | 0% | 70.48% | 0% | 100% | Correct | 649896.96
49 | Pigging Program T16 Dandenong – West Melbourne | 258d | VTS | Other | Replacement | 0 | 0 | 0 | 1377768.96 | 0 | 22.05% | 3.432% | 0% | 74.52% | 0% | 100% | Correct | 1377768.96
50 | Pigging Program T60 Longford -Dandenong | 258e | VTS | Other | Replacement | 0 | 0 | 0 | 0 | 2380922.88 | 21.98% | 1.986% | 0% | 76.04% | 0% | 100% | Correct | 2380922.88
51 | Pigging Program T33 South Melbourne – Brooklyn | 258f | VTS | Other | Replacement | 0 | 0 | 0 | 1023660.8 | 0 | 22.11% | 4.619% | 0% | 73.27% | 0% | 100% | Correct | 1023660.8
52 | Pigging Program T66-70 Mt Franklin -Kyneton - Bendigo | 258i | VTS | Other | Replacement | 0 | 587336.96 | 0 | 0 | 0 | 22.28% | 3.427% | 0% | 74.29% | 0% | 100% | Correct | 587336.96
53 | Pigging Program T75 Wandong - Kyneton | 258k | VTS | Other | Replacement | 0 | 521020.16 | 0 | 0 | 0 | 22.34% | 3.863% | 0% | 73.8% | 0% | 100% | Correct | 521020.16
54 | Pigging Program T24 Brooklyn - Corio | 258l | VTS | Other | Replacement | 0 | 0 | 0 | 1380663.04 | 0 | 22.05% | 1.6% | 0% | 76.35% | 0% | 100% | Correct | 1380663.04
55 | Pigging Program T70 Ballan – Bendigo | 258m | VTS | Other | Replacement | 0 | 0 | 555975.68 | 0 | 0 | 22.31% | 1.885% | 0% | 75.81% | 0% | 100% | Correct | 555975.68
56 | Pigging Program T60 Longford – Tyers | 258n | VTS | Other | Replacement | 0 | 0 | 0 | 0 | 748398.08 | 22.2% | 6.318% | 0% | 71.49% | 0% | 100% | Correct | 748398.08
57 | Pigging Program T63 Tyers - Morwell | 258o | VTS | Other | Replacement | 0 | 0 | 0 | 611088.64 | 0 | 22.27% | 5.161% | 0% | 72.57% | 0% | 100% | Correct | 611088.64
58 | Pigging Program T96 & T98 Chiltern- Rutherglen – Koonoomoo | 258p | VTS | Other | Replacement | 0 | 0 | 0 | 0 | 510551.04 | 22.35% | 2.669% | 0% | 74.99% | 0% | 100% | Correct | 510551.04
59 | Pigging Program T118 Trugannina-Plumpton | 258q | VTS | Other | Replacement | 0 | 0 | 0 | 0 | 512325.12 | 22.34% | 6.156% | 0% | 71.5% | 0% | 100% | Correct | 512325.12
60 | Pigging Program James Street to Laverton Pipeline (253) | 258s | VTS | Other | Replacement | 0 | 447777.28 | 0 | 0 | 0 | 22.41% | 4.933% | 0% | 72.66% | 0% | 100% | Correct | 447777.28
61 | Pigging Program Tyres to Maryvale (67) | 258u | VTS | Other | Replacement | 383189.76 | 0 | 0 | 0 | 0 | 22.5% | 2.735% | 0% | 74.76% | 0% | 100% | Correct | 383189.76
62 | Pigging Program T108 Newport | 258v | VTS | Other | Replacement | 473861.12 | 0 | 0 | 0 | 0 | 22.38% | 5.988% | 0% | 71.63% | 0% | 100% | Correct | 473861.12
63 | Pigging Program Inner Ring Main | 258w | VTS | Other | Replacement | 0 | 0 | 3513.6 | 0 | 0 | 22.33% | 5.379% | 0% | 72.29% | 0% | 100% | Correct | 3513.6
64 | Pigging Program T1 Morwell - Dandenong Pigging and Repair Program | 258x | VTS | Other | Replacement | 1987281.2739 | 1112357.7261 | 0 | 0 | 0 | 21.88% | 2.305% | 0% | 75.82% | 0% | 100% | Correct | 3099639
65 | Pig Trap Installation James Street to Laverton Pipeline (253) | 259a | VTS | Pipelines | Replacement | 0 | 1894808.9075 | 207849.08 | 0 | 0 | 13.54% | 29.08% | 0% | 57.38% | 0% | 100% | Correct | 2102657.9875
66 | Pig Trap Installation Tyers to Maryvale Pipeline (67) | 259d | VTS | Pipelines | Replacement | 589874.5129 | 78499.3589 | 0 | 0 | 0 | 13.55% | 27.44% | 0% | 59.01% | 0% | 100% | Correct | 668373.8718
67 | Liquid Management - Brooklyn | 260a | VTS | City Gates & Field Regs | Replacement | 0 | 0 | 0 | 0 | 157005.8 | 29.27% | 15.68% | 0% | 55.05% | 0% | 100% | Correct | 157005.8
68 | Liquid Management - Pakenham | 260b | VTS | City Gates & Field Regs | Replacement | 0 | 0 | 0 | 157005.8 | 0 | 29.27% | 15.68% | 0% | 55.05% | 0% | 100% | Correct | 157005.8
69 | RTU replacement | 262 | VTS | Other | Replacement | 141816.64 | 141816.64 | 141816.64 | 141816.64 | 141816.64 | 71.47% | 9.837% | 0% | 16.49% | 2.196% | 100% | Correct | 709083.2
70 | Pipe Support replacement | 263 | VTS | Pipelines | Replacement | 164811.0408 | 164811.0408 | 164811.0408 | 164811.0408 | 164811.0408 | 28.57% | 0% | 0% | 71.43% | 0% | 100% | Correct | 824055.204
71 | HMI upgrade to CLEAR SCADA at BCS, SCS and WCS & CG, Longford | 264 | VTS | Other | Non-System | 60928 | 60928 | 60928 | 60928 | 60928 | 58.51% | 35.45% | 0% | 1.313% | 4.727% | 100% | Correct | 304640
72 | BCS Unit 12 Inlet Filter Replacement/Augmentation | 267 | VTS | Compressors | Replacement | 635719.42 | 0 | 0 | 0 | 0 | 23.66% | 36.51% | 0% | 39.83% | 0% | 100% | Correct | 635719.42
73 | Coogee decommissioning | 268 | VTS | Other | Replacement | [5 empty] | 0% | 0% | 0% | 0% | 0% | 0% | Correct | 0
74 | Compressor Type B Compliance | 271 | VTS | Compressors | Replacement | 216718.54 | 216718.54 | 216718.54 | 216718.54 | 216718.54 | 33.45% | 36.05% | 0% | 30.5% | 0% | 100% | Correct | 1083592.7
75 | Dandenong LNG Isolation Valve Upgrade | 275 | VTS | Pipelines | Replacement | 649021.8 | 0 | 0 | 0 | 0 | 29.4% | 29.64% | 0% | 40.97% | 0% | 100% | Correct | 649021.8
76 | Morwell-Dandenong Fatigue Crack Detection from High Loads | 276 | VTS | Pipelines | Replacement | 260832 | 0 | 0 | 0 | 0 | 25.56% | 6.653% | 0% | 67.79% | 0% | 100% | Correct | 260832
77 | Unibolt Enclosure Replacement | 277 | VTS | Other | Replacement | 44464 | 44464 | 44464 | 44464 | 44464 | 28.57% | 11.25% | 0% | 60.18% | 0% | 100% | Correct | 222320
78 | WAN Upgrade (Satellite project) | 278 | VTS | Other | Non-System | 946991.92 | 946991.92 | 946991.92 | 946991.92 | 946991.92 | 46.57% | 29.89% | 0% | 18.2% | 5.355% | 100% | Correct | 4734959.6
79 | Warragul Looping 6" (Southern Route) | Warragul 6" (Sth) | VTS | Pipelines | Augmentation | 5400000 | 2000000 | 0 | 0 | 0 | 34.54% | 52.68% | 0% | 12.78% | 0% | 100% | Correct | 7400000
80 | Angelsea Pipeline (Western Route) | Anglesea | VTS | Pipelines | Augmentation | 13620487.6931 | 12272008.9469 | 0 | 0 | 0 | 49.2% | 30.91% | 0% | 0% | 19.88% | 100% | Correct | 25892496.64
81 | VNIE | VNIE | VTS | Pipelines | Augmentation | 1583090.777 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 100% | 0% | 100% | Correct | 1583090.777
82 | Wichelsea Bi Direction and Brooklyn Reconfiguration | WCS Bi-Dir and BCS reconfig | VTS | Compressors | Augmentation | 540000 | 0 | 0 | 0 | 0 | 55.56% | 33.33% | 0% | 11.11% | 0% | 100% | Correct | 540000
83 | WORM (50km x 20" Pipeline) | WORM (Pipeline) | VTS | Pipelines | Augmentation | 15911166.8213 | 28997137.4367 | 48814496.7419 | 0 | 0 | 10.58% | 33.69% | 0% | 0% | 55.73% | 100% | Correct | 93722801
84 | WORM (C50 at Wollert) | WORM (C50) | VTS | Compressors | Augmentation | 7043662.34 | 12092299.2911 | 6176723.3689 | 0 | 0 | 37.05% | 60.4% | 0% | 0% | 2.553% | 100% | Correct | 25312685
85 | WORM (PRS at Wollert) | WORM (PRS) | VTS | City Gates & Field Regs | Augmentation | 0 | 1641722.0833 | 1959224.9167 | 0 | 0 | 42.22% | 54.63% | 0% | 0% | 3.152% | 100% | Correct | 3600947
0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | 0% | Correct | 0
0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | 0% | Correct | 0
0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | 0% | Correct | 0
0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | 0% | Correct | 0
0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | 0% | Correct | 0
0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | 0% | Correct | 0
0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | 0% | Correct | 0
0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | 0% | Correct | 0
0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | 0% | Correct | 0
0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | 0% | Correct | 0
0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | 0% | Correct | 0
0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | 0% | Correct | 0
0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | 0% | Correct | 0
0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | 0% | Correct | 0
0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | 0% | Correct | 0
0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | 0% | Correct | 0
0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | 0% | Correct | 0
0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | 0% | Correct | 0
0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | 0% | Correct | 0
0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | 0% | Correct | 0
0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | 0% | Correct | 0
0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | 0% | Correct | 0
0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | 0% | Correct | 0
0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | 0% | Correct | 0
0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | 0% | Correct | 0
0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | 0% | Correct | 0
0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | 0% | Correct | 0
0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | 0% | Correct | 0
0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | 0% | Correct | 0
0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | 0% | Correct | 0
0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | 0% | Correct | 0
0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | 0% | Correct | 0
0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | 0% | Correct | 0
0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | 0% | Correct | 0
0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | 0% | Correct | 0
0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | 0% | Correct | 0
0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | 0% | Correct | 0
0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | 0% | Correct | 0
0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | 0% | Correct | 0
0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | 0% | Correct | 0
0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | 0% | Correct | 0
0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | 0% | Correct | 0
0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | 0% | Correct | 0
0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | 0% | Correct | 0
0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | 0% | Correct | 0
0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | 0% | Correct | 0
0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | 0% | Correct | 0
0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | 0% | Correct | 0
0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | 0% | Correct | 0
0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | 0% | Correct | 0
0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | 0% | Correct | 0
0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | 0% | Correct | 0
0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | 0% | Correct | 0
0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | 0% | Correct | 0
0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | 0% | Correct | 0
0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | 0% | Correct | 0
0 | [17 empty] | 227719389.7161
201476124.2652
26243265.451

## 3.1 Input│B&T
3.1 Input│B&T
Capex # | Project Name | Allocator | Asset Class | Asset Category | 2017 (f) | 2018 | 2019 | 2020 | 2021 | 2022 | Direct Labour % | Direct Contractor % | Direct Material % | Direct Other % | 2017 Extension of existing project
86 | Enterprise Content Management | APA | Other | Non-System | 4903000 | 0 | 0 | 0 | 0 | 0 | 30% | 65% | 5% | 0%
87 | Victoria CRE | APA | Other | Non-System | 3506365.2941 | 0 | 0 | 0 | 0 | 0 | 30% | 65% | 5% | 0%
88 | APA Grid Energy Components Upgrade | APA | Other | Non-System | 1297041.8584 | 0 | 0 | 0 | 0 | 0 | 30% | 65% | 5% | 0%
89 | APA Grid Extend Program | APA | Other | Non-System | 2500000 | 2500000 | 0 | 0 | 0 | 0 | 30% | 65% | 5% | 0%
90 | APA Grid Services Initiatives Program | APA | Other | Non-System | 210813.4562 | 0 | 0 | 0 | 0 | 0 | 30% | 65% | 5% | 0%
91 | Hyperion Upgrade to 11.1.2.4 | APA | Other | Non-System | 261068.5766 | 0 | 0 | 0 | 0 | 0 | 30% | 65% | 5% | 0%
92 | BI - Transmission Dashboard and Enterprise Pilot | APA | Other | Non-System | 1200000 | 2000000 | 1500000 | 0 | 0 | 0 | 30% | 65% | 5% | 0%
93 | HR Systems Refresh | APA | Other | Non-System | 0 | 0 | 0 | 0 | 0 | 0 | 30% | 65% | 5% | 0%
94 | Transmission EAM Data Management Tool | APA | Other | Non-System | 465223.3 | 0 | 0 | 0 | 0 | 0 | 30% | 65% | 5% | 0%
95 | SharePoint Upgrade | APA | Other | Non-System | 1739351.9 | 243778.5 | 0 | 0 | 0 | 0 | 30% | 65% | 5% | 0%
96 | eForm Digitisation | APA | Other | Non-System | 0 | 0 | 0 | 1607603.75 | 4147396.25 | 0 | 30% | 65% | 5% | 0%
97 | Historian Upgrade - version 2012 to 2015 | APA | Other | Non-System | 270259 | 0 | 0 | 0 | 0 | 0 | 30% | 65% | 5% | 0%
98 | Hazardous Area Platform | APA | Other | Non-System | 1187405.7 | 1552491.3 | 0 | 0 | 0 | 0 | 30% | 65% | 5% | 0%
99 | PPM Refresh | APA | Other | Non-System | 1100000 | 3000000 | 0 | 0 | 0 | 0 | 30% | 65% | 5% | 0%
100 | BizTalk Upgrade FY2018 | APA | Other | Non-System | 0 | 0 | 604848.9048 | 670918.5097 | 0 | 0 | 30% | 65% | 5% | 0%
101 | Automated Testing Tool | APA | Other | Non-System | 0 | 632204.9999 | 0 | 0 | 0 | 0 | 30% | 65% | 5% | 0%
102 | Code Management Software | APA | Other | Non-System | 0 | 905930.625 | 0 | 0 | 0 | 0 | 30% | 65% | 5% | 0%
103 | CRM Upgrade | APA | Other | Non-System | 0 | 1408186.2 | 59047.8 | 0 | 0 | 0 | 30% | 65% | 5% | 0%
104 | X-Info Aware Version 2 | APA | Other | Non-System | 0 | 430081.5 | 0 | 0 | 0 | 0 | 30% | 65% | 5% | 0%
105 | Supplier Qualification and Compliance | APA | Other | Non-System | 0 | 697848.96 | 185555.04 | 0 | 0 | 0 | 30% | 65% | 5% | 0%
106 | Oracle eBS Upgrade to 12.2 | APA | Other | Non-System | 0 | 267113.0161 | 1276243.5381 | 0 | 0 | 0 | 30% | 65% | 5% | 0%
107 | BizTalk System Upgrade 2020 | APA | Other | Non-System | 0 | 0 | 604848.9048 | 670918.5097 | 0 | 0 | 30% | 65% | 5% | 0%
108 | Applications Renewal | APA | Other | Non-System | 0 | 6900000 | 8620000 | 6900000 | 8620000 | 6900000 | 30% | 65% | 5% | 0%
109 | Infrastructure Renewal | APA | Other | Non-System | 0 | 2250000 | 750000 | 750000 | 750000 | 0 | 30% | 65% | 5% | 0%
110 | Dandenong Relocation | APA | Buildings | Non-System | 5460000 | 0 | 0 | 0 | 0 | 0 | 50% | 0% | 50% | 0%
0 |  | APA | Other | Non-System |  | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 50% | 0%
0 |  | APA | Other | Non-System | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 50% | 0%
0 |  | APA | Other | Non-System | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 50% | 0%
0 |  | APA | Other | Non-System | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 50% | 0%

## 3.2 Input│Other
3.2 Input│Other
Years | Start | Finish | check (years)
Previous AA | 2008-01-01 | 2013-06-30 | 5.5
Current AA | 2013-07-01 | 2017-12-31 | 4.5
Forecast AA | 2018-01-01 | 2022-12-31 | 5
Allocators
VTS | 100%
APA | 10.45%
Transmission | 11.57%
Victoria | 92.63%
|  |  |  | 2011-12-01 | 2012-12-01 | 2013-12-01 | 2014-12-01 | 2015-12-01 | 2016-12-01
Inflation |  |  |  | 2012 | 2013 | 2014 | 2015 | 2016 | 2017 (f) | 2018 | 2019 | 2020 | 2021 | 2022
CPI |  |  |  | 2.204% | 2.745% | 1.718% | 1.689% | 1.476% | 2% | 2.45% | 2.45% | 2.45% | 2.45% | 2.45%
Base Year to Dec 2017 |  |  |  | 0.90909 | 0.93405 | 0.95009 | 0.96613 | 0.98039 | 1 | 1.0245 | 1.0496 | 1.0753 | 1.1017 | 1.1286
AER Forecast Inflation |  |  |  |  | 2.5% | 2.5% | 2.5% | 2.5% | 2.5% | 2.5% | 2.5% | 2.5% | 2.5% | 2.5%
AER forecast to base year to Dec 2012 |  |  |  | 1 | 0.97561 | 0.95181 | 0.9286 | 0.90595 | 0.88385 | 0.8623 | 0.84127 | 0.82075 | 0.80073 | 0.7812
Nominal from Dec 2012 |  |  |  | 1 | 1.0275 | 1.0451 | 1.0627 | 1.0784 | 1.1 | 1.1269 | 1.1546 | 1.1828 | 1.2118 | 1.2415
Inverse of Nominal From 2012 |  |  |  | 1 | 0.97328 | 0.95685 | 0.94096 | 0.92727 | 0.90909 | 0.88735 | 0.86613 | 0.84542 | 0.8252 | 0.80547
Real cost Escalation
Increase
Labour | [9 empty] | 0% | 0% | 0% | 0% | 0% | bar: 2011-12-01 to 2016-12-01
Contractor | [9 empty] | 0% | 0% | 0% | 0% | 0% | bar: 2011-12-01 to 2016-12-01
Materials | [9 empty] | 0% | 0% | 0% | 0% | 0% | bar: 2011-12-01 to 2016-12-01
Other | [9 empty] | 0% | 0% | 0% | 0% | 0% | bar: 2011-12-01 to 2016-12-01
Index
Labour | [9 empty] | 0% | 0% | 0% | 0% | 0% | bar: 2016-12-01
Contractor | [9 empty] | 0% | 0% | 0% | 0% | 0% | bar: 2016-12-01
Materials | [9 empty] | 0% | 0% | 0% | 0% | 0% | bar: 2016-12-01
Other | [9 empty] | 0% | 0% | 0% | 0% | 0% | bar: 2016-12-01
Asset Classes
Pipelines
Compressors
City Gates & Field Regs
Odourant Plants
Gas Quality
Other
Buildings
General Land
Asset Category
Augmentation
Replacement
Non-System
Formulas:
Start = [Finish, row above]+1
Finish = DATE(YEAR([Start])+5,MONTH([Start]),DAY([Start])-1)

## 4.0 Calc│AER Forecast ($nom)
| 4.0 Calc│AER Forecast ($nom) |  |  |  | Check | 16994710.614 | 90361241.2463 | 23597604.0001 | 13057047.239 | 8489983.318 | 152500586.4175 | 152500586.4175 | 0
Capex # | Project Name | Forecast? |  | Category |  | Reg 2013 | 2014 | 2015 | 2016 | 2017 | Total
1 | Stonehaven CS - now Winchelsea | Yes | Compressors | Augmentation |  | 4427290.771 | 30937009.0259 | 0 | 0 | 0 | 35364299.7969
2 | Warragul Looping | Yes | Pipelines | Augmentation |  | 0 | 2630757.6594 | 0 | 0 | 0 | 2630757.6594
3 | Anglesea Pipeline Extension | Yes | Pipelines | Augmentation |  | 0 | 1348127.1025 | 12276206.0759 | 0 | 0 | 13624333.1784
4 | Wollert CS A Unit reinstrumentation | Yes | Compressors | Replacement |  | 0 | 0 | 267939.7531 | 272528.441 | 0 | 540468.194
5 | BCS Filter | Yes | City Gates & Field Regs | Replacement |  | 0 | 420535.9348 | 0 | 0 | 0 | 420535.9348
6 | Wollert to Barnawartha Looping | No | Pipelines | Augmentation |  | 0 | 0 | 0 | 0 | 0 | 0
7 | Iona CS - Inlet Pressure Reduction | Yes | Compressors | Replacement |  | 92521.0566 | 0 | 0 | 0 | 0 | 92521.0566
8 | Iona CS Control system replacement | Yes | Compressors | Replacement |  | 0 | 693864.1163 | 0 | 0 | 0 | 693864.1163
9 | SCS Cooler Upgrade | Yes | Compressors | Replacement |  | 0 | 0 | 966239.3778 | 0 | 0 | 966239.3778
10 | Rockbank PRS | No | City Gates & Field Regs | Replacement |  | 0 | 0 | 0 | 0 | 0 | 0
11 | BCS Emergency Lighting | Yes | Other | Replacement |  | 13037.0173 | 0 | 0 | 0 | 0 | 13037.0173
12 | GCS Emergency Lighting Upgrade | Yes | Other | Replacement |  | -6371.1413 | 0 | 0 | 0 | 0 | -6371.1413
13 | Wollert CS Emergency Lighting | Yes | Other | Replacement |  | 51510.998 | 0 | 0 | 0 | 0 | 51510.998
14 | Emergency - fully equipped caravan | Yes | Other | Replacement |  | 0 | 148225.6813 | 0 | 0 | 0 | 148225.6813
15 | Emergency - Gas blowdown and flaring sytem | Yes | Other | Replacement |  | 0 | 0 | 0 | 0 | 222620.4334 | 222620.4334
16 | Emergency - refurbish and re-testing of pipes | Yes | Other | Replacement |  | 0 | 0 | 0 | 13070.8584 | 222620.4334 | 235691.2917
17 | Emergency - SMR radio upgrade | Yes | Other | Replacement |  | 0 | 0 | 0 | 71889.721 | 0 | 71889.721
18 | Emergency BA escape sets | Yes | Other | Replacement |  | 10304.5114 | 0 | 0 | 0 | 0 | 10304.5114
19 | Emergency diesel fuel storage | Yes | Other | Replacement |  | 0 | 52562.2983 | 89979.5269 | 0 | 0 | 142541.8252
20 | Emergency Plidco fittings - Sleeve vent | Yes | Pipelines | Replacement |  | 0 | 0 | 42729.9712 | 206241.0672 | 0 | 248971.0384
21 | Emergency Response Equipment | Yes | Other | Replacement |  | 92740.6024 | 94612.137 | 96406.636 | 98031.4377 | 100179.195 | 481970.008
22 | Emergency Spark Proof tools | Yes | Other | Replacement |  | 20609.0227 | 21024.9193 | 21423.6969 | 0 | 0 | 63057.639
23 | Purchase and replacement of emergency fittings and Equipment | Yes | Other | Replacement |  | 514450.1049 | 813340.3593 | 0 | 0 | 0 | 1327790.4642
24 | Facilities Communication Systems Upgrade | Yes | Other | Replacement |  | 10302.1996 | 10514.8064 | 10726.2026 | 10914.2712 | 11170.8299 | 53628.3098
25 | GCS Station Valve Upgrade | Yes | Compressors | Replacement |  | 0 | 192123.1868 | 0 | 0 | 0 | 192123.1868
26 | GCS Unit 3 Turbine Overhaul | Yes | Compressors | Replacement |  | 0 | 0 | 375216.1338 | 0 | 0 | 375216.1338
27 | SMS - Compressor station vents-Various | Yes | Compressors | Replacement |  | 0 | 105148.0643 | 0 | 0 | 0 | 105148.0643
28 | AS 2885 Design Life reviews of Facilities&Pipelines | Yes | City Gates & Field Regs | Replacement |  | 215863.0238 | 223545.2837 | 228828.8128 | 233694.6589 | 358273.7608 | 1260205.54
29 | BCG Un-regulated Bypass Upgrade | Yes | City Gates & Field Regs | Replacement |  | 0 | 0 | 0 | 136264.2205 | 0 | 136264.2205
30 | Dandenong CG gas heater | Yes | City Gates & Field Regs | Replacement |  | 0 | 0 | 3112730.7744 | 0 | 0 | 3112730.7744
31 | Hazardous Area Rectification | Yes | City Gates & Field Regs | Replacement |  | 190341.6496 | 223393.4371 | 239467.0929 | 176076.3852 | 122289.3417 | 951567.9064
32 | Hazardous Areas Review | Yes | City Gates & Field Regs | Replacement |  | 434128.5498 | 424653.7566 | 294599.0189 | 54726.797 | 56010.9494 | 1264119.0716
33 | Heater upgrade - Laverton North CG | Yes | City Gates & Field Regs | Replacement |  | 0 | 0 | 0 | 780275.3348 | 0 | 780275.3348
34 | Odorant Dandenong Pump Upgrade 700 & 2800 kPa | Yes | Gas Quality | Replacement |  | 0 | 262846.6931 | 0 | 0 | 0 | 262846.6931
35 | Regulator upgrade - Dandenong City Gate (exclude filters) | Yes | City Gates & Field Regs | Replacement |  | 3842744.3195 | 1550917.5726 | 0 | 0 | 0 | 5393661.8921
36 | Valve - Pipeline LNG plant Isolation Valve Actuator Replacement | Yes | City Gates & Field Regs | Replacement |  | 0 | 0 | 99485.8778 | 0 | 0 | 99485.8778
37 | Valve - Pipeline to LNG plant UV325 valve replacement and loading valve | Yes | City Gates & Field Regs | Replacement |  | 42242.8097 | 252332.8254 | 0 | 0 | 0 | 294575.6351
38 | Valve - Corio CG Un-regulated Bypass Upgrade | Yes | City Gates & Field Regs | Replacement |  | 0 | 0 | 0 | 136264.2205 | 0 | 136264.2205
39 | Valve - Tyers Branch Valve Actuator Replacement | Yes | Pipelines | Replacement |  | 0 | 210277.3545 | 0 | 0 | 0 | 210277.3545
40 | Valve - UniBolt Phase 3 Replacement | Yes | City Gates & Field Regs | Replacement |  | -113032.5332 | 0 | 134005.7621 | 136318.9434 | 0 | 157292.1723
41 | Pig Trap - Enclosure upgrade | Yes | City Gates & Field Regs | Replacement |  | 47394.3718 | 94624.8095 | 96484.1487 | 98149.6393 | 100394.1596 | 437047.129
42 | Pig Trap - Pipe Support Upgrade | Yes | City Gates & Field Regs | Replacement |  | 97879.681 | 99881.7434 | 101844.3792 | 103602.397 | 22309.8133 | 425518.0138
43 | BCS Administration Building Distribution Board Upgrade | Yes | Compressors | Non-System |  | 30853.1714 | 0 | 0 | 0 | 0 | 30853.1714
44 | Equipment - Field Equipment | Yes | Other | Non-System |  | 48964.2039 | 52562.2983 | 53559.2422 | 54461.9098 | 55655.1083 | 265202.7626
45 | Equipment - Gas Detectors | Yes | Other | Non-System |  | 0 | 0 | 0 | 0 | 111310.2167 | 111310.2167
46 | Equipment - IT Purchases | Yes | Other | Non-System |  | 24241.363 | 24730.5614 | 25199.6235 | 25624.3286 | 26185.7285 | 125981.6049
47 | Equipment - Test | Yes | Other | Non-System |  | 51522.5569 | 52562.2983 | 53559.2422 | 54461.9098 | 55655.1083 | 267761.1155
48 | Equipment - Victorian low value pool purchases | Yes | Other | Non-System |  | -130193.5024 | 10512.4597 | 10711.8484 | 10892.382 | 11131.0217 | -86945.7906
49 | Dandenong 180 Greens Road Office Redevelopment | Yes | Buildings | Non-System |  | 3953509.5376 | 5610999.6501 | 0 | 0 | 0 | 9564509.1877
50 | Dandenong Asphalt Resurfacing | Yes | Other | Non-System |  | 0 | 0 | 268011.5241 | 0 | 0 | 268011.5241
51 | Dandenong Complex asbestos removal | Yes | Buildings | Non-System |  | 77273.4324 | 78854.0079 | 32161.3829 | 32716.5464 | 33464.7199 | 254470.0895
52 | Dandenong external surface repainting | Yes | Buildings | Non-System |  | 0 | 105148.0643 | 0 | 0 | 0 | 105148.0643
53 | Dandenong Office Purchases | Yes | Other | Non-System |  | -18791.6818 | 49461.1227 | 50399.2469 | 51248.6571 | 52371.4569 | 184688.8019
54 | Dandenong Site - Storage shed | Yes | Buildings | Non-System |  | 454531.9843 | 0 | 0 | 0 | 0 | 454531.9843
55 | Pigging - Tracking and locating tools | Yes | Other | Non-System |  | 0 | 21029.6129 | 0 | 0 | 0 | 21029.6129
56 | Pigging - Two portable liquid collectors for pigging | Yes | Other | Non-System |  | 0 | 0 | 0 | 254302.5178 | 0 | 254302.5178
57 | Pigging -Two portable dust collectors for pigging | Yes | Other | Non-System |  | 0 | 0 | 249586.0686 | 0 | 0 | 249586.0686
58 | Control Room - Additonal OE monitor | Yes | Other | Non-System |  | 10302.1996 | 0 | 0 | 0 | 0 | 10302.1996
59 | SCADA - Comms upgrade to IP network-VTS only | Yes | Other | Non-System |  | 0 | 0 | 0 | 0 | 1994844.0117 | 1994844.0117
60 | SCADA - IT security | Yes | Other | Non-System |  | 96943.6983 | 0 | 0 | 0 | 0 | 96943.6983
61 | SCADA - Remote maintenance and engineering workstations [Control Room, Gooding, Brooklyn CS&CG, Wollert CS&CG, Springhurst, Iona] | Yes | Other | Non-System |  | 10302.1996 | 10514.8064 | 10726.2026 | 10914.2712 | 11170.8299 | 53628.3098
62 | SCADA - RTU/ PLC/HMI Development and Test bench [PC, iFix, Control Logix, Bristol Designer Tools] | Yes | Other | Non-System |  | 24078.4293 | 0 | 0 | 0 | 0 | 24078.4293
63 | SCADA System Upgrade | Yes | Other | Non-System |  | 0 | 0 | 110330.4047 | 1124629.953 | 518601.8685 | 1753562.2262
64 | Dandenong Building exterior coatings | Yes | Buildings | Non-System |  | 0 | 0 | 160049.0651 | 162633.3849 | 0 | 322682.45
65 | Dandenong site fire mains replacement | Yes | Buildings | Non-System |  | 267677.1804 | 0 | 0 | 0 | 0 | 267677.1804
66 | Brooklyn guttering | Yes | Buildings | Non-System |  | 0 | 41813.3086 | 0 | 0 | 0 | 41813.3086
67 | Wollert Control Room guttering | Yes | Buildings | Non-System |  | 0 | 0 | 31925.4156 | 0 | 0 | 31925.4156
68 | Corporate IT | Yes | Other | Non-System |  | -1560120.7497 | 0 | 0 | 0 | 0 | -1560120.7497
69 | Liquid management - Brooklyn | Yes | City Gates & Field Regs | Replacement |  | 0 | 0 | 350640.0051 | 0 | 0 | 350640.0051
70 | Liquid management - Gooding | Yes | City Gates & Field Regs | Replacement |  | 0 | 187410.171 | 0 | 0 | 0 | 187410.171
71 | Liquid management - Longford | Yes | City Gates & Field Regs | Replacement |  | -27343.8612 | 0 | 0 | 0 | 0 | -27343.8612
72 | Liquid Management - Pakenham | Yes | City Gates & Field Regs | Replacement |  | 148611.527 | 0 | 0 | 0 | 0 | 148611.527
73 | CP - Cathodic Protection Replacement | Yes | Pipelines | Replacement |  | 114678.9412 | 209646.9167 | 213469.55 | 216883.6992 | 221522.5274 | 976201.6344
74 | CP - Corrosion Protection Testing Equipment | Yes | Other | Replacement |  | 10303.5867 | 10513.3984 | 10717.5901 | 10901.1376 | 11146.945 | 53582.6578
75 | Pig Trap - A Branch Valve on Pipeline 108 to Newport Install(124) | Yes | Pipelines | Replacement |  | 0 | 0 | 0 | 2744396.253 | 0 | 2744396.253
76 | Pig Trap - Dandenong to Princes Highway Pipeline Install (129) | Yes | City Gates & Field Regs | Replacement |  | 0 | 0 | 0 | 0 | 673548.4409 | 673548.4409
77 | Pig Trap - Laverton North to Laverton North Pipeline Install (162) | Yes | City Gates & Field Regs | Replacement |  | 0 | 0 | 0 | 999955.035 | 0 | 999955.035
78 | Pig Trap - Pakenham to Pakenham Pipeline Install (68) | Yes | City Gates & Field Regs | Replacement |  | 0 | 0 | 0 | 1130521.5511 | 0 | 1130521.5511
79 | Pigging Program (T1 Dandenong - Morwell) | Yes | Other | Replacement |  | 0 | 0 | 0 | 0 | 598799.6415 | 598799.6415
80 | Pigging Program (T56 Brooklyn - Ballan) | Yes | Other | Replacement |  | 0 | 0 | 0 | 471646.9301 | 0 | 471646.9301
81 | Pigging Program (T59 Euro - Kyabram) | Yes | Other | Replacement |  | 0 | 0 | 0 | 437314.6161 | 0 | 437314.6161
82 | Pigging Program (T67 Guilford - Maryborough) | Yes | Other | Replacement |  | 0 | 0 | 0 | 0 | 245271.207 | 245271.207
83 | Pigging Program (T74 Keon Park - Wollert) | Yes | Other | Replacement |  | 476668.0047 | 0 | 0 | 0 | 0 | 476668.0047
84 | Pigging Program (T92 Iona - Brooklyn) | Yes | Other | Replacement |  | 0 | 0 | 0 | 634551.7272 | 0 | 634551.7272
85 | Pig Trap - Princes Highway to Regent Street Pipeline Install(36) | Yes | City Gates & Field Regs | Replacement |  | 0 | 0 | 0 | 0 | 1432829.7885 | 1432829.7885
86 | Pig Trap - Somerton to Somerton Pipeline Install (238) | Yes | City Gates & Field Regs | Replacement |  | 0 | 0 | 1176940.5758 | 0 | 0 | 1176940.5758
87 | Pig Trap - Tyers to Maryvale Pipeline Install (67) | Yes | City Gates & Field Regs | Replacement |  | 0 | 0 | 0 | 0 | 880611.1414 | 880611.1414
88 | Exposed pipe coating refurbishment | Yes | Pipelines | Replacement |  | 395856.3606 | 696479.27 | 480119.0504 | 357766.9065 | 520877.23 | 2451098.8175
89 | BCS Safety and Process Control System and RTU Upgrade | Yes | Compressors | Replacement |  | -10461.9169 | 0 | 0 | 0 | 0 | -10461.9169
90 | CS Type B compliance upgrade | Yes | Compressors | Replacement |  | 880569.4651 | 0 | 0 | 0 | 0 | 880569.4651
91 | GCS GEA Fuel Gas Upgrade | Yes | Compressors | Replacement |  | 51479.2293 | 0 | 0 | 0 | 0 | 51479.2293
92 | GCS Units 1,2,3&4 Suction/Discharge Actuated Valve Replacement | Yes | Compressors | Replacement |  | 875209.4588 | 0 | 0 | 0 | 0 | 875209.4588
93 | Mothball BCS Stage 3 incl BCS8,9,10,11 | No | Compressors | Replacement |  | 0 | 0 | 0 | 0 | 0 | 0
94 | Mothball WCS station 'A' | Yes | Compressors | Replacement |  | 0 | 0 | 0 | 0 | 459324.3371 | 459324.3371
95 | Regulator Upgrade - Lara pneumatic control system upgrade | Yes | City Gates & Field Regs | Replacement |  | 206397.9478 | 235179.7474 | 0 | 0 | 0 | 441577.6952
96 | Security - High Risk sites security upgrade | Yes | Other | Replacement |  | 671388.0839 | 0 | 1077196.9119 | 783358.6272 | 0 | 2531943.623
97 | Security - Small Site Facilities Fencing Upgrade | Yes | Other | Replacement |  | 0 | 78779.636 | 80313.1121 | 81679.386 | 83540.0424 | 324312.1765
98 | Zonal Chromatograph Bottle Regulator Panels Upgrades | Yes | Gas Quality | Replacement |  | 30148.7407 | 0 | 0 | 0 | 0 | 30148.7407
99 | Zonal Chromatograph Insertion Probes | Yes | Gas Quality | Replacement |  | 97750.1451 | 0 | 0 | 0 | 0 | 97750.1451
100 | Zonal Chromatograph Upgrades | Yes | Gas Quality | Replacement |  | 102924.902 | 104901.8719 | 106849.8413 | 108591.5277 | 0 | 423268.1429
101 | RTU & Control System Upgrade - Facilities | Yes | Other | Replacement |  | -182836.843 | 117344.3456 | 119897.7179 | 122211.1753 | 125251.3616 | 301867.7575
102 | GCS Anti-Surge & Fast-Stop Valves Upgrade | Yes | Compressors | Replacement |  | 688944.2926 | 0 | 0 | 0 | 0 | 688944.2926
103 | GCS Control Room Fire Suppression System | Yes | Compressors | Replacement |  | 46359.8982 | 105148.0643 | 0 | 0 | 0 | 151507.9626
104 | GCS Units 1,2,3&4 Fire Suppression System | Yes | Compressors | Replacement |  | 0 | 0 | 0 | 245571.1009 | 0 | 245571.1009
105 | Iona CS - Unit Fire Suppression System | Yes | Compressors | Replacement |  | 0 | 294388.2963 | 0 | 0 | 0 | 294388.2963
106 | Wollert CG Control Hut Fire Suppression System | Yes | Compressors | Replacement |  | 0 | 36801.8225 | 37541.7093 | 0 | 0 | 74343.5318
107 | Wollert CS A/B Control Room Fire Suppression System | Yes | Compressors | Replacement |  | 0 | 105148.0643 | 134077.5331 | 0 | 0 | 239225.5974
108 | BCG Control Hut Fire Suppression System | Yes | City Gates & Field Regs | Replacement |  | 66964.2975 | 0 | 0 | 0 | 0 | 66964.2975
109 | Valve - Actuate MLV's in T1 areas | Yes | Pipelines | Replacement |  | 0 | 1377660.1064 | 1403147.1092 | 1425845.4489 | 0 | 4206652.6645
110 | Valve - Longford to Dandenong LV10 Vent Stack | Yes | Pipelines | Replacement |  | 34321.0304 | 0 | 0 | 0 | 0 | 34321.0304
111 | BCS Station Isolation and Loading Valves | Yes | Compressors | Replacement |  | 0 | 955224.9811 | 0 | 0 | 0 | 955224.9811
112 | Iona CS - Capacity Aftercooler upgrade | Yes | Compressors | Replacement |  | 0 | 741012.5883 | 0 | 0 | 0 | 741012.5883
113 | BCS DEA Upgrade | Yes | Compressors | Replacement |  | 0 | 0 | 376794.763 | 0 | 0 | 376794.763
114 | BCS GEA Upgrade | No | Compressors | Replacement |  | 0 | 0 | 0 | 0 | 0 | 0
115 | Pig Trap - Keon Park Install | Yes | City Gates & Field Regs | Replacement |  | -385445.4098 | 0 | 0 | 0 | 0 | -385445.4098
116 | BCS Replacement of FSV, ASV & Other Valves | Yes | Compressors | Replacement |  | 0 | 934986.8767 | 0 | 0 | 0 | 934986.8767
117 | BCS Unit 10 & 11 Cooler Upgrade | Yes | Compressors | Replacement |  | -7199.9758 | 3501893.8574 | 0 | 0 | 0 | 3494693.8816
118 | SMS - GIS & Aerial Photography | No | Pipelines | Replacement |  | 0 | 0 | 0 | 0 | 0 | 0
119 | SMS - Vehicle Barrier Protection | No | Pipelines | Replacement |  | 0 | 0 | 0 | 0 | 0 | 0
120 | SMS - Site Hazops | No | Pipelines | Replacement |  | 0 | 0 | 0 | 0 | 0 | 0
121 | SMS - Bush Fire Impact Studies | No | Pipelines | Replacement |  | 0 | 0 | 0 | 0 | 0 | 0
122 | Wollert to Clonbinane Looping | Yes | Pipelines | Augmentation |  | 1869064.025 | 36074991.2683 | 0 | 0 | 0 | 37944055.2933
123 | MAOP Upgrade - Euroa to Springhurst | Yes | Pipelines | Augmentation |  | 195893.0956 | 1800337.8067 | 0 | 0 | 0 | 1996230.9024
124 | Valve - T60 Longford - Dandenong Upgrade hydraulic hand pump of actuators | Yes | Other | Replacement |  | 113334.3675 | 0 | 0 | 0 | 0 | 113334.3675
125 | VTS - BROOKLYN LARA LOOP | Yes | Pipelines | Replacement |  | -23131.1067 | 0 | 0 | 0 | 0 | -23131.1067
126 | VTS - WOLLERT 4 & 5 CAPEX | Yes | Compressors | Replacement |  | -13314.2235 | 0 | 0 | 0 | 0 | -13314.2235
127 | VTS - MORWELL TYERS UPGRADE | Yes | City Gates & Field Regs | Replacement |  | -230.6319 | 0 | 0 | 0 | 0 | -230.6319
128 | VTS - MAOP UPGRADE CAPEX | Yes | City Gates & Field Regs | Replacement |  | -15569.2935 | 0 | 0 | 0 | 0 | -15569.2935
129 | VTS - BBP & BCP CG UPGRADE | Yes | City Gates & Field Regs | Replacement |  | -99498.3838 | 0 | 0 | 0 | 0 | -99498.3838
130 | VTS - BRANCH VALVE CASTLEMAINE | Yes | Pipelines | Replacement |  | -26610.0762 | 0 | 0 | 0 | 0 | -26610.0762
131 | VTS - EUROA CS NEW (PPOM) | Yes | Compressors | Replacement |  | -422349.8051 | 0 | 0 | 0 | 0 | -422349.8051
132 | VTS - SUNBURY PIPE LOOP (NEW) | Yes | Pipelines | Replacement |  | -496764.165 | 0 | 0 | 0 | 0 | -496764.165
133 | VTS - BCS 8&9 COOLERS UPG (NEW | Yes | Compressors | Replacement |  | -466377.1893 | 0 | 0 | 0 | 0 | -466377.1893
134 | VTS - BCS 12 FAST STOP VALVE | Yes | Compressors | Replacement |  | -36555.4935 | 0 | 0 | 0 | 0 | -36555.4935
135 | VTS - BCS 8 & 9 UNIT VALVES | Yes | Compressors | Replacement |  | -288949.8851 | 0 | 0 | 0 | 0 | -288949.8851
136 | PIGGING T91 CURDIEVALE | No | Other | Replacement |  | 0 | 0 | 0 | 0 | 0 | 0
137 | VTS - BROOKLYN FIRE SERVICE | Yes | Buildings | Non-System |  | -438048.0951 | 0 | 0 | 0 | 0 | -438048.0951
138 | VTS - BCS LUBE OIL COOLER 8&9 | No | City Gates & Field Regs | Replacement |  | 0 | 0 | 0 | 0 | 0 | 0
139 | VNIE Looping 6 to 8 | No | Pipelines | Augmentation |  | 0 | 0 | 0 | 0 | 0 | 0
140 | VTS16.SIB42 WOLL SOFT STARTERS | No | Other | Replacement |  | 0 | 0 | 0 | 0 | 0 | 0
141 | VTS.SIB99 WCS STN-A DISCHRG LQ | No | Other | Replacement |  | 0 | 0 | 0 | 0 | 0 | 0
142 | VTS17.SIB27 SCS CR EPS REMOVAL | No | Buildings | Non-System |  | 0 | 0 | 0 | 0 | 0 | 0
143 | VTS17.SIB30 DND EMERG ENTRANCE | No | Buildings | Non-System |  | 0 | 0 | 0 | 0 | 0 | 0
144 | Corporate other | No | Other | Non-System |  | 0 | 0 | 0 | 0 | 0 | 0
145 | Market Services _APA Grid Prog | No | Other | Non-System |  | 0 | 0 | 0 | 0 | 0 | 0
146 | APA Grid Perf & Resil Overhaul | No | Other | Non-System |  | 0 | 0 | 0 | 0 | 0 | 0
147 | APA Grid & Mrkt Srvs SIB Capex | No | Other | Non-System |  | 0 | 0 | 0 | 0 | 0 | 0
148 | APA Grid Extend | No | Other | Non-System |  | 0 | 0 | 0 | 0 | 0 | 0
149 | APA Grid Services Initiatives | No | Other | Non-System |  | 0 | 0 | 0 | 0 | 0 | 0
150 | CORP SIB16 DANDENONG REFURB | No | Other | Non-System |  | 0 | 0 | 0 | 0 | 0 | 0
151 | Data Centre | No | Other | Non-System |  | 0 | 0 | 0 | 0 | 0 | 0
152 | Enterprise Asset Management | No | Other | Non-System |  | 0 | 0 | 0 | 0 | 0 | 0
153 | Enterprise Content Management | No | Other | Non-System |  | 0 | 0 | 0 | 0 | 0 | 0
154 | EAM Bus Support & Governance | No | Other | Non-System |  | 0 | 0 | 0 | 0 | 0 | 0
155 | EAM TRANSMISSION ESTAB WORK | No | Other | Non-System |  | 0 | 0 | 0 | 0 | 0 | 0
156 | Oracle Integration with EAM | No | Other | Non-System |  | 0 | 0 | 0 | 0 | 0 | 0
157 | EAM Business Support-Reports | No | Other | Non-System |  | 0 | 0 | 0 | 0 | 0 | 0
158 | EC Upgrade | No | Other | Non-System |  | 0 | 0 | 0 | 0 | 0 | 0
159 | Finance Systems | No | Other | Non-System |  | 0 | 0 | 0 | 0 | 0 | 0
160 | Mobile phone CAPEX purchases | No | Other | Non-System |  | 0 | 0 | 0 | 0 | 0 | 0
161 | PPOM Phase 2 | No | Other | Non-System |  | 0 | 0 | 0 | 0 | 0 | 0
162 | Project Server Status Report | No | Other | Non-System |  | 0 | 0 | 0 | 0 | 0 | 0
163 | BI reporting | No | Other | Non-System |  | 0 | 0 | 0 | 0 | 0 | 0
164 | PPOM Snapshot Engine | No | Other | Non-System |  | 0 | 0 | 0 | 0 | 0 | 0
165 | APA Grid Ph.2 | No | Other | Non-System |  | 0 | 0 | 0 | 0 | 0 | 0
166 | APA Grid Ph. 3 | No | Other | Non-System |  | 0 | 0 | 0 | 0 | 0 | 0
167 | Vehicle Comms & Journey Mgmt | No | Other | Non-System |  | 0 | 0 | 0 | 0 | 0 | 0
168 | SCADA Satellite Strategy | No | Other | Non-System |  | 0 | 0 | 0 | 0 | 0 | 0
169 | SCADA Resilience Project FEED | No | Other | Non-System |  | 0 | 0 | 0 | 0 | 0 | 0
170 | IOC SCADA GAP ANALYSIS | No | Other | Non-System |  | 0 | 0 | 0 | 0 | 0 | 0
171 | SCADA Resilience Phase 1 Recom | No | Other | Non-System |  | 0 | 0 | 0 | 0 | 0 | 0
172 | Melbourne Metro CRE | No | Other | Non-System |  | 0 | 0 | 0 | 0 | 0 | 0
173 | HR Systems Refresh | No | Other | Non-System |  | 0 | 0 | 0 | 0 | 0 | 0
174 | Historian Upgrade - version 2012 to 2015 | No | Other | Non-System |  | 0 | 0 | 0 | 0 | 0 | 0
175 | EAM System Upgrade 2018 | No | Other | Non-System |  | 0 | 0 | 0 | 0 | 0 | 0
176 | BizTalk Upgrade FY2018 | No | Other | Non-System |  | 0 | 0 | 0 | 0 | 0 | 0
177 | Code Management Software | No | Other | Non-System |  | 0 | 0 | 0 | 0 | 0 | 0
178 | X-Info Aware Version 2 | No | Other | Non-System |  | 0 | 0 | 0 | 0 | 0 | 0
179 | Adjustments required for differences in CWIP and FAR records | No | Other | Non-System |  | 0 | 0 | 0 | 0 | 0 | 0
180 | Sharepoint site | No | Other | Non-System |  | 0 | 0 | 0 | 0 | 0 | 0
181 | APA Grid | No | Other | Non-System |  | 0 | 0 | 0 | 0 | 0 | 0
182 | B&T projects | No | Other | Non-System |  | 0 | 0 | 0 | 0 | 0 | 0
183 | Dandenong Relocation | No | Other | Non-System |  | 0 | 0 | 0 | 0 | 0 | 0
184 | Victoria CRE | No | Other | Non-System |  | 0 | 0 | 0 | 0 | 0 | 0
185 | Access Arrangement Costs | No | Other | Non-System |  | 0 | 0 | 0 | 0 | 0 | 0
186 | Trans EAM Data Management Tool | No | Other | Non-System |  | 0 | 0 | 0 | 0 | 0 | 0
187 | EAM Site Stores/Warehouses | No | Other | Non-System |  | 0 | 0 | 0 | 0 | 0 | 0
188 | BI - Transmission Dashboard and Enterprise Pilot | No | Other | Non-System |  | 0 | 0 | 0 | 0 | 0 | 0
189 | APA Grid Future Initiatives Projects | No | Other | Non-System |  | 0 | 0 | 0 | 0 | 0 | 0
190 | GRC Platform | No | Other | Non-System |  | 0 | 0 | 0 | 0 | 0 | 0
191 | Direct Link Dispatch Display Application Replacement | No | Other | Non-System |  | 0 | 0 | 0 | 0 | 0 | 0
192 | T92 & DDN3 RTU Upgrade | No | Other | Replacement |  | 0 | 0 | 0 | 0 | 0 | 0
193 | SCS Vent Modifications | No | Other | Replacement |  | 0 | 0 | 0 | 0 | 0 | 0
194 | BCS Admin Board Upgrade | No | Buildings | Non-System |  | 0 | 0 | 0 | 0 | 0 | 0
195 | Pigging Program (T57 & T70) | No | Pipelines | Replacement |  | 0 | 0 | 0 | 0 | 0 | 0
196 | REMOTE CP MONITOR (37863) | No | Pipelines | Replacement |  | 0 | 0 | 0 | 0 | 0 | 0
197 | Maryvale Direct Assessment | No | Pipelines | Replacement |  | 0 | 0 | 0 | 0 | 0 | 0
198 | Wichelsea Bi Direction and Brooklyn Reconfiguration | No | Compressors | Augmentation |  | 0 | 0 | 0 | 0 | 0 | 0
199 | ILUKA WBH FIRE TUBE | No | Pipelines | Replacement |  | 0 | 0 | 0 | 0 | 0 | 0
200 | REMOTE CP MONITOR (38260) | No | Pipelines | Replacement |  | 0 | 0 | 0 | 0 | 0 | 0
201 | 0 | 0 | 0 | Replacement |  | 0 | 0 | 0 | 0 | 0 | 0
202 | 0 | 0 | 0 | Replacement |  | 0 | 0 | 0 | 0 | 0 | 0
203 | 0 | 0 | 0 | Replacement |  | 0 | 0 | 0 | 0 | 0 | 0
204 | 0 | 0 | 0 | Replacement |  | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | Replacement |  | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | Replacement |  | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | Replacement |  | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | Replacement |  | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | Replacement |  | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | Replacement |  | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | Replacement |  | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | Replacement |  | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | Replacement |  | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | Replacement |  | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | Replacement |  | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | Replacement |  | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | Replacement |  | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | Replacement |  | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | Replacement |  | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | Replacement |  | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | Replacement |  | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | Replacement |  | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | Replacement |  | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | Replacement |  | 0 | 0 | 0 | 0 | 0 | 0

## 4.1 Calc│Hist Incurred ($nom)
|  |  |  | Check | 0 | 0 | 0 | 0 | 0
4.1 Calc│Hist Incurred ($nom)
Capex # | Project Name | Class | Category |  | 2013 | 2014 | 2015 | 2016 | 2017 | Total
1 | Stonehaven CS - now Winchelsea | Compressors | Augmentation |  | 8134553.96 | 26606375.39 | 2492547.98 | 877.27 | 189.03 | 37234543.63
2 | Warragul Looping | Pipelines | Augmentation |  | 0 | 0 | 0 | 0 | 0 | 0
3 | Anglesea Pipeline Extension | Pipelines | Augmentation |  | 0 | 0 | 0 | 0 | 0 | 0
4 | Wollert CS A Unit reinstrumentation | Compressors | Replacement |  | 0 | 0 | 0 | 0 | 0 | 0
5 | BCS Filter | City Gates & Field Regs | Replacement |  | 0 | 0 | 0 | 0 | 0 | 0
6 | Wollert to Barnawartha Looping | Pipelines | Augmentation |  | 0 | 0 | 0 | 0 | 0 | 0
7 | Iona CS - Inlet Pressure Reduction | Compressors | Replacement |  | 104428.1 | 9056 | 0 | 0 | 0 | 113484.1
8 | Iona CS Control system replacement | Compressors | Replacement |  | 0 | 0 | 0 | 0 | 0 | 0
9 | SCS Cooler Upgrade | Compressors | Replacement |  | 0 | 0 | 0 | 0 | 0 | 0
10 | Rockbank PRS | City Gates & Field Regs | Replacement |  | 0 | 0 | 0 | 0 | 0 | 0
11 | BCS Emergency Lighting | Other | Replacement |  | 61810.95 | 0 | 0 | 0 | 0 | 61810.95
12 | GCS Emergency Lighting Upgrade | Other | Replacement |  | 879.8 | 0 | 0 | 0 | 0 | 879.8
13 | Wollert CS Emergency Lighting | Other | Replacement |  | 0 | 111330.8 | 0 | 0 | 0 | 111330.8
14 | Emergency - fully equipped caravan | Other | Replacement |  | 0 | 0 | 0 | 0 | 0 | 0
15 | Emergency - Gas blowdown and flaring sytem | Other | Replacement |  | 0 | 0 | 0 | 0 | 0 | 0
16 | Emergency - refurbish and re-testing of pipes | Other | Replacement |  | 0 | 40300 | 0 | 0 | 0 | 40300
17 | Emergency - SMR radio upgrade | Other | Replacement |  | 0 | 0 | 0 | 0 | 0 | 0
18 | Emergency BA escape sets | Other | Replacement |  | 0 | 0 | 0 | 0 | 0 | 0
19 | Emergency diesel fuel storage | Other | Replacement |  | 0 | 0 | 0 | 0 | 0 | 0
20 | Emergency Plidco fittings - Sleeve vent | Pipelines | Replacement |  | 0 | 0 | 0 | 0 | 135220 | 135220
21 | Emergency Response Equipment | Other | Replacement |  | 0 | 14416.72 | 38911 | 30371.33 | 401537.7 | 485236.75
22 | Emergency Spark Proof tools | Other | Replacement |  | 0 | 0 | 0 | 0 | 0 | 0
23 | Purchase and replacement of emergency fittings and Equipment | Other | Replacement |  | 59521.63 | 173679.9 | 0 | 0 | 0 | 233201.53
24 | Facilities Communication Systems Upgrade | Other | Replacement |  | 0 | 16081.25 | 0 | 0 | 0 | 16081.25
25 | GCS Station Valve Upgrade | Compressors | Replacement |  | 922.2 | 94508.09 | 0 | 0 | 0 | 95430.29
26 | GCS Unit 3 Turbine Overhaul | Compressors | Replacement |  | 0 | 0 | 0 | 0 | 0 | 0
27 | SMS - Compressor station vents-Various | Compressors | Replacement |  | 0 | 0 | 0 | 0 | 0 | 0
28 | AS 2885 Design Life reviews of Facilities&Pipelines | City Gates & Field Regs | Replacement |  | 890.75 | 142234.07 | 54126.05 | 67446.92 | 0 | 264697.79
29 | BCG Un-regulated Bypass Upgrade | City Gates & Field Regs | Replacement |  | 0 | 0 | 0 | 0 | 0 | 0
30 | Dandenong CG gas heater | City Gates & Field Regs | Replacement |  | 0 | 0 | 0 | 0 | 0 | 0
31 | Hazardous Area Rectification | City Gates & Field Regs | Replacement |  | 10313.6 | 32182 | 134741 | 142983.16 | 25485.2 | 345704.96
32 | Hazardous Areas Review | City Gates & Field Regs | Replacement |  | 34062.33 | 0 | 0 | 0 | 0 | 34062.33
33 | Heater upgrade - Laverton North CG | City Gates & Field Regs | Replacement |  | 5671 | 0 | 0 | 0 | 0 | 5671
34 | Odorant Dandenong Pump Upgrade 700 & 2800 kPa | Gas Quality | Replacement |  | 0 | 0 | 285847.41 | 6015.5 | 0 | 291862.91
35 | Regulator upgrade - Dandenong City Gate (exclude filters) | City Gates & Field Regs | Replacement |  | 479498.96 | 2616566.96 | 7811136.25 | 751879.8 | 59691.29 | 11718773.26
36 | Valve - Pipeline LNG plant Isolation Valve Actuator Replacement | City Gates & Field Regs | Replacement |  | 67874.3 | 307062.84 | 0 | -0.02 | 0 | 374937.12
37 | Valve - Pipeline to LNG plant UV325 valve replacement and loading valve | City Gates & Field Regs | Replacement |  | 67319.22 | 210131.45 | 0 | 0 | 0 | 277450.67
38 | Valve - Corio CG Un-regulated Bypass Upgrade | City Gates & Field Regs | Replacement |  | 0 | 0 | 0 | 0 | 0 | 0
39 | Valve - Tyers Branch Valve Actuator Replacement | Pipelines | Replacement |  | 0 | 0 | 0 | 0 | 0 | 0
40 | Valve - UniBolt Phase 3 Replacement | City Gates & Field Regs | Replacement |  | 1130.5 | 92576.04 | 30257.33 | 53832.91 | 210141.93 | 387938.71
41 | Pig Trap - Enclosure upgrade | City Gates & Field Regs | Replacement |  | 0 | 0 | 17709 | 84557.63 | 0 | 102266.63
42 | Pig Trap - Pipe Support Upgrade | City Gates & Field Regs | Replacement |  | 174 | 63266.31 | 250206.75 | 24895.18 | 1526.9 | 340069.14
43 | BCS Administration Building Distribution Board Upgrade | Compressors | Non-System |  | 0 | -52 | 0 | 0 | 56182.04 | 56130.04
44 | Equipment - Field Equipment | Other | Non-System |  | 78414.37 | 33433 | 0 | 0 | 56776.67 | 168624.04
45 | Equipment - Gas Detectors | Other | Non-System |  | 0 | 0 | 0 | 0 | 0 | 0
46 | Equipment - IT Purchases | Other | Non-System |  | 28090.5164 | 85086.328 | 94876.5278 | 73787.5668 | 79054.297 | 360895.2361
47 | Equipment - Test | Other | Non-System |  | 0 | 0 | 0 | 0 | 31930 | 31930
48 | Equipment - Victorian low value pool purchases | Other | Non-System |  | 52890.5047 | 215346.1092 | 550230.7606 | 173195.9057 | 336661.5806 | 1328324.8608
49 | Dandenong 180 Greens Road Office Redevelopment | Buildings | Non-System |  | 0 | 0 | 0 | 0 | 0 | 0
50 | Dandenong Asphalt Resurfacing | Other | Non-System |  | 0 | 0 | 0 | 0 | 0 | 0
51 | Dandenong Complex asbestos removal | Buildings | Non-System |  | 0 | 60923.51 | 0 | 0 | 0 | 60923.51
52 | Dandenong external surface repainting | Buildings | Non-System |  | 0 | 0 | 0 | 0 | 0 | 0
53 | Dandenong Office Purchases | Other | Non-System |  | 8861.6981 | 34769.95 | 31686.2177 | 0 | 0 | 75317.8658
54 | Dandenong Site - Storage shed | Buildings | Non-System |  | 11857.7292 | 66978.2157 | 0 | 0 | -86152.2199 | -7316.275
55 | Pigging - Tracking and locating tools | Other | Non-System |  | 0 | 0 | 0 | 0 | 0 | 0
56 | Pigging - Two portable liquid collectors for pigging | Other | Non-System |  | 0 | 0 | 0 | 0 | 0 | 0
57 | Pigging -Two portable dust collectors for pigging | Other | Non-System |  | 0 | 0 | 0 | 0 | 0 | 0
58 | Control Room - Additonal OE monitor | Other | Non-System |  | 0 | 0 | 0 | 0 | 0 | 0
59 | SCADA - Comms upgrade to IP network-VTS only | Other | Non-System |  | 0 | 0 | 0 | 11925 | 1372449.18 | 1384374.18
60 | SCADA - IT security | Other | Non-System |  | 0 | 0 | 0 | 0 | 0 | 0
61 | SCADA - Remote maintenance and engineering workstations [Control Room, Gooding, Brooklyn CS&CG, Wollert CS&CG, Springhurst, Iona] | Other | Non-System |  | 0 | 0 | 0 | 0 | 0 | 0
62 | SCADA - RTU/ PLC/HMI Development and Test bench [PC, iFix, Control Logix, Bristol Designer Tools] | Other | Non-System |  | 0 | 0 | 0 | 0 | 0 | 0
63 | SCADA System Upgrade | Other | Non-System |  | 0 | 0 | 25383.25 | 63489.53 | 650304.01 | 739176.79
64 | Dandenong Building exterior coatings | Buildings | Non-System |  | 0 | 0 | 0 | 0 | 0 | 0
65 | Dandenong site fire mains replacement | Buildings | Non-System |  | 4961.3378 | 88164.1814 | 1020411.517 | 30176.035 | 22378.8 | 1166091.8712
66 | Brooklyn guttering | Buildings | Non-System |  | 0 | 0 | 0 | 0 | 53670 | 53670
67 | Wollert Control Room guttering | Buildings | Non-System |  | 0 | 0 | 0 | 0 | 0 | 0
68 | Corporate IT | Other | Non-System |  | 211241.5961 | 302736.8717 | 276048.921 | 531059.9152 | 502162.3028 | 1823249.6069
69 | Liquid management - Brooklyn | City Gates & Field Regs | Replacement |  | 0 | 0 | 0 | 0 | 0 | 0
70 | Liquid management - Gooding | City Gates & Field Regs | Replacement |  | 0 | 0 | 0 | 0 | 0 | 0
71 | Liquid management - Longford | City Gates & Field Regs | Replacement |  | -4131.05 | 0 | 0 | 0 | 0 | -4131.05
72 | Liquid Management - Pakenham | City Gates & Field Regs | Replacement |  | 0 | 0 | 0 | 0 | 0 | 0
73 | CP - Cathodic Protection Replacement | Pipelines | Replacement |  | 18725 | 98704 | 20000 | 89800 | 33464.4 | 260693.4
74 | CP - Corrosion Protection Testing Equipment | Other | Replacement |  | 0 | 0 | 0 | 47690 | 12494 | 60184
75 | Pig Trap - A Branch Valve on Pipeline 108 to Newport Install(124) | Pipelines | Replacement |  | 0 | 0 | 20098.4 | 388795.23 | 0 | 408893.63
76 | Pig Trap - Dandenong to Princes Highway Pipeline Install (129) | City Gates & Field Regs | Replacement |  | 0 | 0 | 31113.5 | 260290.51 | 1385616.27 | 1677020.28
77 | Pig Trap - Laverton North to Laverton North Pipeline Install (162) | City Gates & Field Regs | Replacement |  | 0 | 0 | 0 | 0 | 0 | 0
78 | Pig Trap - Pakenham to Pakenham Pipeline Install (68) | City Gates & Field Regs | Replacement |  | 0 | 0 | 0 | 0 | 0 | 0
79 | Pigging Program (T1 Dandenong - Morwell) | Other | Replacement |  | 0 | 0 | 0 | 0 | 0 | 0
80 | Pigging Program (T56 Brooklyn - Ballan) | Other | Replacement |  | 0 | 0 | 140780.29 | 273457.91 | 13.35 | 414251.55
81 | Pigging Program (T59 Euro - Kyabram) | Other | Replacement |  | 0 | 0 | 0 | 0 | 173370.21 | 173370.21
82 | Pigging Program (T67 Guilford - Maryborough) | Other | Replacement |  | 0 | 0 | 0 | 0 | 0 | 0
83 | Pigging Program (T74 Keon Park - Wollert) | Other | Replacement |  | 5363.81 | 616839.03 | 37257.13 | 41434.17 | 0 | 700894.14
84 | Pigging Program (T92 Iona - Brooklyn) | Other | Replacement |  | 0 | 0 | 67224.28 | 188438.41 | 182993.22 | 438655.91
85 | Pig Trap - Princes Highway to Regent Street Pipeline Install(36) | City Gates & Field Regs | Replacement |  | 0 | 0 | 17158.9 | -17158.9 | 0 | 0
86 | Pig Trap - Somerton to Somerton Pipeline Install (238) | City Gates & Field Regs | Replacement |  | 0 | 1590 | 24041.28 | -25631.28 | 0 | 0
87 | Pig Trap - Tyers to Maryvale Pipeline Install (67) | City Gates & Field Regs | Replacement |  | 0 | 0 | 0 | 0 | 0 | 0
88 | Exposed pipe coating refurbishment | Pipelines | Replacement |  | 0 | 0 | 0 | 0 | 66170 | 66170
89 | BCS Safety and Process Control System and RTU Upgrade | Compressors | Replacement |  | 23570.02 | 15134.58 | 12066 | 0 | 0 | 50770.6
90 | CS Type B compliance upgrade | Compressors | Replacement |  | 0 | 0 | 1070 | 389055.47 | 1387215.29 | 1777340.76
91 | GCS GEA Fuel Gas Upgrade | Compressors | Replacement |  | 0 | 0 | 0 | 44673.16 | 4018.05 | 48691.21
92 | GCS Units 1,2,3&4 Suction/Discharge Actuated Valve Replacement | Compressors | Replacement |  | 0 | 0 | 0 | 31842.5 | 22711.09 | 54553.59
93 | Mothball BCS Stage 3 incl BCS8,9,10,11 | Compressors | Replacement |  | 0 | 0 | 0 | 0 | 0 | 0
94 | Mothball WCS station 'A' | Compressors | Replacement |  | 0 | 0 | 0 | 0 | 0 | 0
95 | Regulator Upgrade - Lara pneumatic control system upgrade | City Gates & Field Regs | Replacement |  | 0 | 0 | 5301 | 0 | 157902 | 163203
96 | Security - High Risk sites security upgrade | Other | Replacement |  | 17837.72 | 24900 | 0 | 0 | 0 | 42737.72
97 | Security - Small Site Facilities Fencing Upgrade | Other | Replacement |  | 0 | 0 | 0 | 0 | 0 | 0
98 | Zonal Chromatograph Bottle Regulator Panels Upgrades | Gas Quality | Replacement |  | 0 | 0 | 0 | 0 | 35251.2 | 35251.2
99 | Zonal Chromatograph Insertion Probes | Gas Quality | Replacement |  | 0 | 0 | 0 | 0 | 0 | 0
100 | Zonal Chromatograph Upgrades | Gas Quality | Replacement |  | 0 | 91009.78 | 0 | 334933 | 0 | 425942.78
101 | RTU & Control System Upgrade - Facilities | Other | Replacement |  | 98368.47 | 100004.42 | 8235.2 | 130842.63 | 70312.21 | 407762.93
102 | GCS Anti-Surge & Fast-Stop Valves Upgrade | Compressors | Replacement |  | 0 | 0 | 10038.5 | 543860.57 | 1023154.23 | 1577053.3
103 | GCS Control Room Fire Suppression System | Compressors | Replacement |  | 0 | 0 | 0 | 0 | 213359.56 | 213359.56
104 | GCS Units 1,2,3&4 Fire Suppression System | Compressors | Replacement |  | 0 | 0 | 0 | 0 | 0 | 0
105 | Iona CS - Unit Fire Suppression System | Compressors | Replacement |  | 0 | 0 | 0 | 0 | 0 | 0
106 | Wollert CG Control Hut Fire Suppression System | Compressors | Replacement |  | 0 | 0 | 0 | 0 | 0 | 0
107 | Wollert CS A/B Control Room Fire Suppression System | Compressors | Replacement |  | 0 | 0 | 0 | 1008 | 76860.99 | 77868.99
108 | BCG Control Hut Fire Suppression System | City Gates & Field Regs | Replacement |  | 0 | 0 | 0 | 0 | 40000 | 40000
109 | Valve - Actuate MLV's in T1 areas | Pipelines | Replacement |  | 0 | 0 | 0 | 5359.6 | 85787.9 | 91147.5
110 | Valve - Longford to Dandenong LV10 Vent Stack | Pipelines | Replacement |  | 34177.3 | 39851.75 | 0 | 0 | 0 | 74029.05
111 | BCS Station Isolation and Loading Valves | Compressors | Replacement |  | 2244.6 | 16577.75 | 183683.64 | 1608978.12 | 38092.44 | 1849576.55
112 | Iona CS - Capacity Aftercooler upgrade | Compressors | Replacement |  | 0 | 0 | 0 | 0 | 0 | 0
113 | BCS DEA Upgrade | Compressors | Replacement |  | 1160 | 17428 | 0 | 144959 | 426295.17 | 589842.17
114 | BCS GEA Upgrade | Compressors | Replacement |  | 0 | 0 | 0 | 0 | 0 | 0
115 | Pig Trap - Keon Park Install | City Gates & Field Regs | Replacement |  | 325106.72 | 1640823.98 | 0 | 0 | 0 | 1965930.7
116 | BCS Replacement of FSV, ASV & Other Valves | Compressors | Replacement |  | 0 | 0 | 0 | 0 | 0 | 0
117 | BCS Unit 10 & 11 Cooler Upgrade | Compressors | Replacement |  | 27089.84 | 889622.65 | 5007242.54 | 3272234.09 | 0 | 9196189.12
118 | SMS - GIS & Aerial Photography | Pipelines | Replacement |  | 0 | 0 | 87 | 144969.5 | 0 | 145056.5
119 | SMS - Vehicle Barrier Protection | Pipelines | Replacement |  | 0 | 0 | 0 | 0 | 0 | 0
120 | SMS - Site Hazops | Pipelines | Replacement |  | 0 | 0 | 0 | 0 | 0 | 0
121 | SMS - Bush Fire Impact Studies | Pipelines | Replacement |  | 0 | 0 | 0 | 0 | 0 | 0
122 | Wollert to Clonbinane Looping | Pipelines | Augmentation |  | 4006990.75 | 85648927.66 | 65640112.89 | 813975.86 | 366946.99 | 156476954.15
123 | MAOP Upgrade - Euroa to Springhurst | Pipelines | Augmentation |  | 0 | 0 | 0 | 0 | 0 | 0
124 | Valve - T60 Longford - Dandenong Upgrade hydraulic hand pump of actuators | Other | Replacement |  | 0 | 0 | 0 | 0 | 0 | 0
125 | VTS - BROOKLYN LARA LOOP | Pipelines | Replacement |  | 0 | 0 | 0 | 0 | 0 | 0
126 | VTS - WOLLERT 4 & 5 CAPEX | Compressors | Replacement |  | 3203.9 | 5158.96 | 0 | 0 | 0 | 8362.86
127 | VTS - MORWELL TYERS UPGRADE | City Gates & Field Regs | Replacement |  | 6147.52 | 0 | 0 | 0 | 0 | 6147.52
128 | VTS - MAOP UPGRADE CAPEX | City Gates & Field Regs | Replacement |  | 0 | -42.39 | 0 | 0 | 0 | -42.39
129 | VTS - BBP & BCP CG UPGRADE | City Gates & Field Regs | Replacement |  | 0 | 0 | 0 | 0 | 0 | 0
130 | VTS - BRANCH VALVE CASTLEMAINE | Pipelines | Replacement |  | 0 | 0 | 0 | 0 | 0 | 0
131 | VTS - EUROA CS NEW (PPOM) | Compressors | Replacement |  | 116664.37 | 121805.28 | 59020.54 | -2941.24 | 0 | 294548.95
132 | VTS - SUNBURY PIPE LOOP (NEW) | Pipelines | Replacement |  | 51715.09 | 38571.05 | 5019.95 | -654.99 | 0 | 94651.1
133 | VTS - BCS 8&9 COOLERS UPG (NEW | Compressors | Replacement |  | -12591.73 | 22820.08 | 0 | 0 | 0 | 10228.35
134 | VTS - BCS 12 FAST STOP VALVE | Compressors | Replacement |  | 0 | 0 | 0 | 0 | 0 | 0
135 | VTS - BCS 8 & 9 UNIT VALVES | Compressors | Replacement |  | 0 | 0 | 0 | 0 | 0 | 0
136 | PIGGING T91 CURDIEVALE | Other | Replacement |  | 0 | 17873 | 0 | 0 | 0 | 17873
137 | VTS - BROOKLYN FIRE SERVICE | Buildings | Non-System |  | 29482.73 | 11269.5 | 0 | 0 | 0 | 40752.23
138 | VTS - BCS LUBE OIL COOLER 8&9 | City Gates & Field Regs | Replacement |  | 109672.54 | 0 | 0 | 0 | 0 | 109672.54
139 | VNIE Looping 6 to 8 | Pipelines | Augmentation |  | 0 | 0 | 6392032.4513 | 74341242.7516 | 44559438.9085 | 125292714.1114
140 | VTS16.SIB42 WOLL SOFT STARTERS | Other | Replacement |  | 0 | 0 | 0 | 30881 | 0 | 30881
141 | VTS.SIB99 WCS STN-A DISCHRG LQ | Other | Replacement |  | 0 | 0 | 0 | 219226.8 | 5400 | 224626.8
142 | VTS17.SIB27 SCS CR EPS REMOVAL | Buildings | Non-System |  | 0 | 0 | 0 | 2856.8 | 321349.4 | 324206.2
143 | VTS17.SIB30 DND EMERG ENTRANCE | Buildings | Non-System |  | 0 | 0 | 0 | 24545.55 | 0 | 24545.55
144 | Corporate other | Other | Non-System |  | 242365.2632 | 340342.973 | 308327.8805 | 17522.8525 | 193217.0674 | 1101776.0366
145 | Market Services _APA Grid Prog | Other | Non-System |  | 0 | 0 | 153669.9247 | 156678.9204 | 0 | 310348.845
146 | APA Grid Perf & Resil Overhaul | Other | Non-System |  | 0 | 0 | 44725.1667 | 22022.8998 | 0 | 66748.0665
147 | APA Grid & Mrkt Srvs SIB Capex | Other | Non-System |  | 0 | 0 | 0 | 0 | 0 | 0
148 | APA Grid Extend | Other | Non-System |  | 0 | 0 | 0 | 80289.867 | 681495.7221 | 761785.5891
149 | APA Grid Services Initiatives | Other | Non-System |  | 0 | 0 | 0 | 188898.9119 | 93837.1179 | 282736.0298
150 | CORP SIB16 DANDENONG REFURB | Other | Non-System |  | 0 | 0 | 303211.3819 | 3462.88 | 0 | 306674.2619
151 | Data Centre | Other | Non-System |  | 65362.0189 | 895833.2344 | 79250.1745 | 0 | 0 | 1040445.4278
152 | Enterprise Asset Management | Other | Non-System |  | 806330.3274 | 1986550.9701 | 2564771.5454 | 1771.8759 | -11.219 | 5359413.4998
153 | Enterprise Content Management | Other | Non-System |  | 0 | 0 | 104729.0841 | 399680.7896 | 555995.9985 | 1060405.8722
154 | EAM Bus Support & Governance | Other | Non-System |  | 0 | 0 | 0 | 42640.3455 | 65.1413 | 42705.4868
155 | EAM TRANSMISSION ESTAB WORK | Other | Non-System |  | 0 | 0 | 0 | 199413.8739 | 247813.8633 | 447227.7372
156 | Oracle Integration with EAM | Other | Non-System |  | 0 | 0 | 0 | 10956.5236 | 0 | 10956.5236
157 | EAM Business Support-Reports | Other | Non-System |  | 0 | 0 | 0 | 5944.4937 | 3565.8563 | 9510.3501
158 | EC Upgrade | Other | Non-System |  | 0 | 0 | 0 | 256499.7136 | 139404.1118 | 395903.8254
159 | Finance Systems | Other | Non-System |  | 1751.8135 | 0 | 0 | 0 | 0 | 1751.8135
160 | Mobile phone CAPEX purchases | Other | Non-System |  | 0 | 22811.9773 | 27279.5795 | 34752.7222 | 21127.7494 | 105972.0283
161 | PPOM Phase 2 | Other | Non-System |  | 5453.1938 | 0 | 0 | 0 | 0 | 5453.1938
162 | Project Server Status Report | Other | Non-System |  | 7605.6406 | 4061.9411 | 0 | 0 | 0 | 11667.5817
163 | BI reporting | Other | Non-System |  | 33318.3814 | 2571.9179 | 0 | 0 | 0 | 35890.2993
164 | PPOM Snapshot Engine | Other | Non-System |  | 9285.9184 | 12608.9365 | 0 | 0 | 0 | 21894.8549
165 | APA Grid Ph.2 | Other | Non-System |  | 135912.9265 | 98899.2122 | 0 | 0 | 0 | 234812.1387
166 | APA Grid Ph. 3 | Other | Non-System |  | 2637.3633 | 0 | 0 | 0 | 0 | 2637.3633
167 | Vehicle Comms & Journey Mgmt | Other | Non-System |  | 0 | 2091.1818 | 85100.7826 | 156458.5302 | -8653.3782 | 234997.1164
168 | SCADA Satellite Strategy | Other | Non-System |  | 0 | 0 | 37193.7062 | 94128.7989 | 45922.7906 | 177245.2957
169 | SCADA Resilience Project FEED | Other | Non-System |  | 0 | 0 | 0 | 19777.1403 | 0 | 19777.1403
170 | IOC SCADA GAP ANALYSIS | Other | Non-System |  | 0 | 0 | 0 | 4246.8422 | 0 | 4246.8422
171 | SCADA Resilience Phase 1 Recom | Other | Non-System |  | 0 | 0 | 0 | 22462.5329 | 67609.9204 | 90072.4533
172 | Melbourne Metro CRE | Other | Non-System |  | 0 | 0 | 0 | 4584380.0134 | 1008115.8558 | 5592495.8692
173 | HR Systems Refresh | Other | Non-System |  | 0 | 0 | 0 | 0 | 152663.248 | 152663.248
174 | Historian Upgrade - version 2012 to 2015 | Other | Non-System |  | 0 | 0 | 0 | 0 | 41738.0552 | 41738.0552
175 | EAM System Upgrade 2018 | Other | Non-System |  | 0 | 0 | 0 | 0 | 109617.3011 | 109617.3011
176 | BizTalk Upgrade FY2018 | Other | Non-System |  | 0 | 0 | 0 | 0 | 101135.0037 | 101135.0037
177 | Code Management Software | Other | Non-System |  | 0 | 0 | 0 | 0 | 0 | 0
178 | X-Info Aware Version 2 | Other | Non-System |  | 0 | 0 | 0 | 0 | 0 | 0
179 | Adjustments required for differences in CWIP and FAR records | Other | Non-System |  | 0 | -26601 | 23200 | 0 | 0 | -3401
180 | Sharepoint site | Other | Non-System |  | 0 | 0 | 0 | 0 | 65134.503 | 65134.503
181 | APA Grid | Other | Non-System |  | 0 | 0 | 0 | 0 | 0 | 0
182 | B&T projects | Other | Non-System |  | 0 | 0 | 0 | 0 | 0 | 0
183 | Dandenong Relocation | Other | Non-System |  | 0 | 0 | 0 | 0 | 0 | 0
184 | Victoria CRE | Other | Non-System |  | 0 | 0 | 0 | 0 | 0 | 0
185 | Access Arrangement Costs | Other | Non-System |  | 0 | 0 | 0 | 0 | 0 | 0
186 | Trans EAM Data Management Tool | Other | Non-System |  | 0 | 0 | 0 | 2653.6996 | 0 | 2653.6996
187 | EAM Site Stores/Warehouses | Other | Non-System |  | 0 | 0 | 0 | 25238.5762 | 0 | 25238.5762
188 | BI - Transmission Dashboard and Enterprise Pilot | Other | Non-System |  | 0 | 0 | 0 | 0 | 47542.4471 | 47542.4471
189 | APA Grid Future Initiatives Projects | Other | Non-System |  | 0 | 0 | 0 | 0 | 121083.5996 | 121083.5996
190 | GRC Platform | Other | Non-System |  | 0 | 0 | 0 | 0 | 19591.6678 | 19591.6678
191 | Direct Link Dispatch Display Application Replacement | Other | Non-System |  | 0 | 0 | 0 | 0 | 11747.9477 | 11747.9477
192 | T92 & DDN3 RTU Upgrade | Other | Replacement |  | 0 | 0 | 0 | 5215.8 | 40207.33 | 45423.13
193 | SCS Vent Modifications | Other | Replacement |  | 0 | 0 | 0 | 6011.3 | 11569.73 | 17581.03
194 | BCS Admin Board Upgrade | Buildings | Non-System |  | 0 | 0 | 0 | 384 | 21276.8 | 21660.8
195 | Pigging Program (T57 & T70) | Pipelines | Replacement |  | 0 | 0 | 0 | 0 | 494213.62 | 494213.62
196 | REMOTE CP MONITOR (37863) | Pipelines | Replacement |  | 0 | 0 | 0 | 0 | 254005.25 | 254005.25
197 | Maryvale Direct Assessment | Pipelines | Replacement |  | 0 | 0 | 0 | 0 | 91167.02 | 91167.02
198 | Wichelsea Bi Direction and Brooklyn Reconfiguration | Compressors | Augmentation |  | 0 | 0 | 0 | 0 | 3179000.24 | 3179000.24
199 | ILUKA WBH FIRE TUBE | Pipelines | Replacement |  | 0 | 0 | 0 | 0 | 23875 | 23875
200 | REMOTE CP MONITOR (38260) | Pipelines | Replacement |  | 0 | 0 | 0 | 0 | 59511.13 | 59511.13
201 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
202 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
203 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
204 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0

## 4.2 Calc│Hist Com ($nom)
|  |  |  | Check | 0 | 0 | 0 | 0 | 0 | 0
4.2 Calc│Hist Com ($nom)
Capex # | Project Name | Class | Category |  | 2013 | 2014 | 2015 | 2016 | 2017 | Total
1 | Stonehaven CS - now Winchelsea | Compressors | Augmentation |  | 0 | 0 | 37233477.33 | 877.27 | 189.03 | 37234543.63
2 | Warragul Looping | Pipelines | Augmentation |  | 0 | 0 | 0 | 0 | 0 | 0
3 | Anglesea Pipeline Extension | Pipelines | Augmentation |  | 0 | 0 | 0 | 0 | 0 | 0
4 | Wollert CS A Unit reinstrumentation | Compressors | Replacement |  | 0 | 0 | 0 | 0 | 0 | 0
5 | BCS Filter | City Gates & Field Regs | Replacement |  | 0 | 0 | 0 | 0 | 0 | 0
6 | Wollert to Barnawartha Looping | Pipelines | Augmentation |  | 0 | 0 | 0 | 0 | 0 | 0
7 | Iona CS - Inlet Pressure Reduction | Compressors | Replacement |  | 104428.1 | 9056 | 0 | 0 | 0 | 113484.1
8 | Iona CS Control system replacement | Compressors | Replacement |  | 0 | 0 | 0 | 0 | 0 | 0
9 | SCS Cooler Upgrade | Compressors | Replacement |  | 0 | 0 | 0 | 0 | 0 | 0
10 | Rockbank PRS | City Gates & Field Regs | Replacement |  | 0 | 0 | 0 | 0 | 0 | 0
11 | BCS Emergency Lighting | Other | Replacement |  | 61810.95 | 0 | 0 | 0 | 0 | 61810.95
12 | GCS Emergency Lighting Upgrade | Other | Replacement |  | 879.8 | 0 | 0 | 0 | 0 | 879.8
13 | Wollert CS Emergency Lighting | Other | Replacement |  | 0 | 111330.8 | 0 | 0 | 0 | 111330.8
14 | Emergency - fully equipped caravan | Other | Replacement |  | 0 | 0 | 0 | 0 | 0 | 0
15 | Emergency - Gas blowdown and flaring sytem | Other | Replacement |  | 0 | 0 | 0 | 0 | 0 | 0
16 | Emergency - refurbish and re-testing of pipes | Other | Replacement |  | 0 | 40300 | 0 | 0 | 0 | 40300
17 | Emergency - SMR radio upgrade | Other | Replacement |  | 0 | 0 | 0 | 0 | 0 | 0
18 | Emergency BA escape sets | Other | Replacement |  | 0 | 0 | 0 | 0 | 0 | 0
19 | Emergency diesel fuel storage | Other | Replacement |  | 0 | 0 | 0 | 0 | 0 | 0
20 | Emergency Plidco fittings - Sleeve vent | Pipelines | Replacement |  | 0 | 0 | 0 | 0 | 135220 | 135220
21 | Emergency Response Equipment | Other | Replacement |  | 0 | 14416.72 | 38911 | 30371.33 | 401537.7 | 485236.75
22 | Emergency Spark Proof tools | Other | Replacement |  | 0 | 0 | 0 | 0 | 0 | 0
23 | Purchase and replacement of emergency fittings and Equipment | Other | Replacement |  | 0 | 233201.53 | 0 | 0 | 0 | 233201.53
24 | Facilities Communication Systems Upgrade | Other | Replacement |  | 0 | 16081.25 | 0 | 0 | 0 | 16081.25
25 | GCS Station Valve Upgrade | Compressors | Replacement |  | 0 | 95430.29 | 0 | 0 | 0 | 95430.29
26 | GCS Unit 3 Turbine Overhaul | Compressors | Replacement |  | 0 | 0 | 0 | 0 | 0 | 0
27 | SMS - Compressor station vents-Various | Compressors | Replacement |  | 0 | 0 | 0 | 0 | 0 | 0
28 | AS 2885 Design Life reviews of Facilities&Pipelines | City Gates & Field Regs | Replacement |  | 890.75 | 142234.07 | 54126.05 | 67446.92 | 0 | 264697.79
29 | BCG Un-regulated Bypass Upgrade | City Gates & Field Regs | Replacement |  | 0 | 0 | 0 | 0 | 0 | 0
30 | Dandenong CG gas heater | City Gates & Field Regs | Replacement |  | 0 | 0 | 0 | 0 | 0 | 0
31 | Hazardous Area Rectification | City Gates & Field Regs | Replacement |  | 10313.6 | 32182 | 134741 | 142983.16 | 25485.2 | 345704.96
32 | Hazardous Areas Review | City Gates & Field Regs | Replacement |  | 34062.33 | 0 | 0 | 0 | 0 | 34062.33
33 | Heater upgrade - Laverton North CG | City Gates & Field Regs | Replacement |  | 5671 | 0 | 0 | 0 | 0 | 5671
34 | Odorant Dandenong Pump Upgrade 700 & 2800 kPa | Gas Quality | Replacement |  | 0 | 0 | 285847.41 | 6015.5 | 0 | 291862.91
35 | Regulator upgrade - Dandenong City Gate (exclude filters) | City Gates & Field Regs | Replacement |  | 0 | 0 | 10907202.17 | 751879.8 | 59691.29 | 11718773.26
36 | Valve - Pipeline LNG plant Isolation Valve Actuator Replacement | City Gates & Field Regs | Replacement |  | 0 | 374937.14 | 0 | -0.02 | 0 | 374937.12
37 | Valve - Pipeline to LNG plant UV325 valve replacement and loading valve | City Gates & Field Regs | Replacement |  | 0 | 277450.67 | 0 | 0 | 0 | 277450.67
38 | Valve - Corio CG Un-regulated Bypass Upgrade | City Gates & Field Regs | Replacement |  | 0 | 0 | 0 | 0 | 0 | 0
39 | Valve - Tyers Branch Valve Actuator Replacement | Pipelines | Replacement |  | 0 | 0 | 0 | 0 | 0 | 0
40 | Valve - UniBolt Phase 3 Replacement | City Gates & Field Regs | Replacement |  | 1130.5 | 92576.04 | 30257.33 | 53832.91 | 210141.93 | 387938.71
41 | Pig Trap - Enclosure upgrade | City Gates & Field Regs | Replacement |  | 0 | 0 | 0 | 102266.63 | 0 | 102266.63
42 | Pig Trap - Pipe Support Upgrade | City Gates & Field Regs | Replacement |  | 174 | 63266.31 | 250206.75 | 24895.18 | 1526.9 | 340069.14
43 | BCS Administration Building Distribution Board Upgrade | Compressors | Non-System |  | 0 | -52 | 0 | 0 | 56182.04 | 56130.04
44 | Equipment - Field Equipment | Other | Non-System |  | 78414.37 | 33433 | 0 | 0 | 56776.67 | 168624.04
45 | Equipment - Gas Detectors | Other | Non-System |  | 0 | 0 | 0 | 0 | 0 | 0
46 | Equipment - IT Purchases | Other | Non-System |  | 28090.5164 | 85086.328 | 94876.5278 | 73787.5668 | 79054.297 | 360895.2361
47 | Equipment - Test | Other | Non-System |  | 0 | 0 | 0 | 0 | 31930 | 31930
48 | Equipment - Victorian low value pool purchases | Other | Non-System |  | 52890.5047 | 215346.1092 | 550230.7606 | 173195.9057 | 336661.5806 | 1328324.8608
49 | Dandenong 180 Greens Road Office Redevelopment | Buildings | Non-System |  | 0 | 0 | 0 | 0 | 0 | 0
50 | Dandenong Asphalt Resurfacing | Other | Non-System |  | 0 | 0 | 0 | 0 | 0 | 0
51 | Dandenong Complex asbestos removal | Buildings | Non-System |  | 0 | 60923.51 | 0 | 0 | 0 | 60923.51
52 | Dandenong external surface repainting | Buildings | Non-System |  | 0 | 0 | 0 | 0 | 0 | 0
53 | Dandenong Office Purchases | Other | Non-System |  | 8861.6981 | 34769.95 | 31686.2177 | 0 | 0 | 75317.8658
54 | Dandenong Site - Storage shed | Buildings | Non-System |  | 0 | 78835.9449 | 0 | 0 | -86152.2199 | -7316.275
55 | Pigging - Tracking and locating tools | Other | Non-System |  | 0 | 0 | 0 | 0 | 0 | 0
56 | Pigging - Two portable liquid collectors for pigging | Other | Non-System |  | 0 | 0 | 0 | 0 | 0 | 0
57 | Pigging -Two portable dust collectors for pigging | Other | Non-System |  | 0 | 0 | 0 | 0 | 0 | 0
58 | Control Room - Additonal OE monitor | Other | Non-System |  | 0 | 0 | 0 | 0 | 0 | 0
59 | SCADA - Comms upgrade to IP network-VTS only | Other | Non-System |  | 0 | 0 | 0 | 11925 | 1372449.18 | 1384374.18
60 | SCADA - IT security | Other | Non-System |  | 0 | 0 | 0 | 0 | 0 | 0
61 | SCADA - Remote maintenance and engineering workstations [Control Room, Gooding, Brooklyn CS&CG, Wollert CS&CG, Springhurst, Iona] | Other | Non-System |  | 0 | 0 | 0 | 0 | 0 | 0
62 | SCADA - RTU/ PLC/HMI Development and Test bench [PC, iFix, Control Logix, Bristol Designer Tools] | Other | Non-System |  | 0 | 0 | 0 | 0 | 0 | 0
63 | SCADA System Upgrade | Other | Non-System |  | 0 | 0 | 25383.25 | 63489.53 | 650304.01 | 739176.79
64 | Dandenong Building exterior coatings | Buildings | Non-System |  | 0 | 0 | 0 | 0 | 0 | 0
65 | Dandenong site fire mains replacement | Buildings | Non-System |  | 0 | 0 | 1113537.0362 | 30176.035 | 22378.8 | 1166091.8712
66 | Brooklyn guttering | Buildings | Non-System |  | 0 | 0 | 0 | 0 | 53670 | 53670
67 | Wollert Control Room guttering | Buildings | Non-System |  | 0 | 0 | 0 | 0 | 0 | 0
68 | Corporate IT | Other | Non-System |  | 211241.5961 | 302736.8717 | 276048.921 | 531059.9152 | 502162.3028 | 1823249.6069
69 | Liquid management - Brooklyn | City Gates & Field Regs | Replacement |  | 0 | 0 | 0 | 0 | 0 | 0
70 | Liquid management - Gooding | City Gates & Field Regs | Replacement |  | 0 | 0 | 0 | 0 | 0 | 0
71 | Liquid management - Longford | City Gates & Field Regs | Replacement |  | -4131.05 | 0 | 0 | 0 | 0 | -4131.05
72 | Liquid Management - Pakenham | City Gates & Field Regs | Replacement |  | 0 | 0 | 0 | 0 | 0 | 0
73 | CP - Cathodic Protection Replacement | Pipelines | Replacement |  | 18725 | 98704 | 20000 | 89800 | 33464.4 | 260693.4
74 | CP - Corrosion Protection Testing Equipment | Other | Replacement |  | 0 | 0 | 0 | 47690 | 12494 | 60184
75 | Pig Trap - A Branch Valve on Pipeline 108 to Newport Install(124) | Pipelines | Replacement |  | 0 | 0 | 0 | 0 | 0 | 0
76 | Pig Trap - Dandenong to Princes Highway Pipeline Install (129) | City Gates & Field Regs | Replacement |  | 0 | 0 | 0 | 0 | 1677020.28 | 1677020.28
77 | Pig Trap - Laverton North to Laverton North Pipeline Install (162) | City Gates & Field Regs | Replacement |  | 0 | 0 | 0 | 0 | 0 | 0
78 | Pig Trap - Pakenham to Pakenham Pipeline Install (68) | City Gates & Field Regs | Replacement |  | 0 | 0 | 0 | 0 | 0 | 0
79 | Pigging Program (T1 Dandenong - Morwell) | Other | Replacement |  | 0 | 0 | 0 | 0 | 0 | 0
80 | Pigging Program (T56 Brooklyn - Ballan) | Other | Replacement |  | 0 | 0 | 0 | 0 | 414251.55 | 414251.55
81 | Pigging Program (T59 Euro - Kyabram) | Other | Replacement |  | 0 | 0 | 0 | 0 | 173370.21 | 173370.21
82 | Pigging Program (T67 Guilford - Maryborough) | Other | Replacement |  | 0 | 0 | 0 | 0 | 0 | 0
83 | Pigging Program (T74 Keon Park - Wollert) | Other | Replacement |  | 0 | 622202.84 | 37257.13 | 41434.17 | 0 | 700894.14
84 | Pigging Program (T92 Iona - Brooklyn) | Other | Replacement |  | 0 | 0 | 0 | 0 | 438655.91 | 438655.91
85 | Pig Trap - Princes Highway to Regent Street Pipeline Install(36) | City Gates & Field Regs | Replacement |  | 0 | 0 | 0 | 0 | 0 | 0
86 | Pig Trap - Somerton to Somerton Pipeline Install (238) | City Gates & Field Regs | Replacement |  | 0 | 0 | 0 | 0 | 0 | 0
87 | Pig Trap - Tyers to Maryvale Pipeline Install (67) | City Gates & Field Regs | Replacement |  | 0 | 0 | 0 | 0 | 0 | 0
88 | Exposed pipe coating refurbishment | Pipelines | Replacement |  | 0 | 0 | 0 | 0 | 66170 | 66170
89 | BCS Safety and Process Control System and RTU Upgrade | Compressors | Replacement |  | 23570.02 | 0 | 27200.58 | 0 | 0 | 50770.6
90 | CS Type B compliance upgrade | Compressors | Replacement |  | 0 | 0 | 1070 | 163698.12 | 1612572.64 | 1777340.76
91 | GCS GEA Fuel Gas Upgrade | Compressors | Replacement |  | 0 | 0 | 0 | 44673.16 | 4018.05 | 48691.21
92 | GCS Units 1,2,3&4 Suction/Discharge Actuated Valve Replacement | Compressors | Replacement |  | 0 | 0 | 0 | 0 | 54553.59 | 54553.59
93 | Mothball BCS Stage 3 incl BCS8,9,10,11 | Compressors | Replacement |  | 0 | 0 | 0 | 0 | 0 | 0
94 | Mothball WCS station 'A' | Compressors | Replacement |  | 0 | 0 | 0 | 0 | 0 | 0
95 | Regulator Upgrade - Lara pneumatic control system upgrade | City Gates & Field Regs | Replacement |  | 0 | 0 | 0 | 0 | 163203 | 163203
96 | Security - High Risk sites security upgrade | Other | Replacement |  | 17837.72 | 24900 | 0 | 0 | 0 | 42737.72
97 | Security - Small Site Facilities Fencing Upgrade | Other | Replacement |  | 0 | 0 | 0 | 0 | 0 | 0
98 | Zonal Chromatograph Bottle Regulator Panels Upgrades | Gas Quality | Replacement |  | 0 | 0 | 0 | 0 | 35251.2 | 35251.2
99 | Zonal Chromatograph Insertion Probes | Gas Quality | Replacement |  | 0 | 0 | 0 | 0 | 0 | 0
100 | Zonal Chromatograph Upgrades | Gas Quality | Replacement |  | 0 | 91009.78 | 0 | 334933 | 0 | 425942.78
101 | RTU & Control System Upgrade - Facilities | Other | Replacement |  | 98368.47 | 100004.42 | 8235.2 | 130842.63 | 70312.21 | 407762.93
102 | GCS Anti-Surge & Fast-Stop Valves Upgrade | Compressors | Replacement |  | 0 | 0 | 0 | 0 | 0 | 0
103 | GCS Control Room Fire Suppression System | Compressors | Replacement |  | 0 | 0 | 0 | 0 | 213359.56 | 213359.56
104 | GCS Units 1,2,3&4 Fire Suppression System | Compressors | Replacement |  | 0 | 0 | 0 | 0 | 0 | 0
105 | Iona CS - Unit Fire Suppression System | Compressors | Replacement |  | 0 | 0 | 0 | 0 | 0 | 0
106 | Wollert CG Control Hut Fire Suppression System | Compressors | Replacement |  | 0 | 0 | 0 | 0 | 0 | 0
107 | Wollert CS A/B Control Room Fire Suppression System | Compressors | Replacement |  | 0 | 0 | 0 | 0 | 77868.99 | 77868.99
108 | BCG Control Hut Fire Suppression System | City Gates & Field Regs | Replacement |  | 0 | 0 | 0 | 0 | 40000 | 40000
109 | Valve - Actuate MLV's in T1 areas | Pipelines | Replacement |  | 0 | 0 | 0 | 0 | 91147.5 | 91147.5
110 | Valve - Longford to Dandenong LV10 Vent Stack | Pipelines | Replacement |  | 0 | 74029.05 | 0 | 0 | 0 | 74029.05
111 | BCS Station Isolation and Loading Valves | Compressors | Replacement |  | 0 | 0 | 0 | 1811484.11 | 38092.44 | 1849576.55
112 | Iona CS - Capacity Aftercooler upgrade | Compressors | Replacement |  | 0 | 0 | 0 | 0 | 0 | 0
113 | BCS DEA Upgrade | Compressors | Replacement |  | 0 | 0 | 0 | 0 | 589842.17 | 589842.17
114 | BCS GEA Upgrade | Compressors | Replacement |  | 0 | 0 | 0 | 0 | 0 | 0
115 | Pig Trap - Keon Park Install | City Gates & Field Regs | Replacement |  | 0 | 1965930.7 | 0 | 0 | 0 | 1965930.7
116 | BCS Replacement of FSV, ASV & Other Valves | Compressors | Replacement |  | 0 | 0 | 0 | 0 | 0 | 0
117 | BCS Unit 10 & 11 Cooler Upgrade | Compressors | Replacement |  | 0 | 0 | 0 | 9196189.12 | 0 | 9196189.12
118 | SMS - GIS & Aerial Photography | Pipelines | Replacement |  | 0 | 0 | 0 | 145056.5 | 0 | 145056.5
119 | SMS - Vehicle Barrier Protection | Pipelines | Replacement |  | 0 | 0 | 0 | 0 | 0 | 0
120 | SMS - Site Hazops | Pipelines | Replacement |  | 0 | 0 | 0 | 0 | 0 | 0
121 | SMS - Bush Fire Impact Studies | Pipelines | Replacement |  | 0 | 0 | 0 | 0 | 0 | 0
122 | Wollert to Clonbinane Looping | Pipelines | Augmentation |  | 0 | 32280328.01 | 123650906.7 | 813975.86 | -268256.01 | 156476954.56
123 | MAOP Upgrade - Euroa to Springhurst | Pipelines | Augmentation |  | 0 | 0 | 0 | 0 | 0 | 0
124 | Valve - T60 Longford - Dandenong Upgrade hydraulic hand pump of actuators | Other | Replacement |  | 0 | 0 | 0 | 0 | 0 | 0
125 | VTS - BROOKLYN LARA LOOP | Pipelines | Replacement |  | 0 | 0 | 0 | 0 | 0 | 0
126 | VTS - WOLLERT 4 & 5 CAPEX | Compressors | Replacement |  | 3203.9 | 5158.96 | 0 | 0 | 0 | 8362.86
127 | VTS - MORWELL TYERS UPGRADE | City Gates & Field Regs | Replacement |  | 6147.52 | 0 | 0 | 0 | 0 | 6147.52
128 | VTS - MAOP UPGRADE CAPEX | City Gates & Field Regs | Replacement |  | 0 | -42.39 | 0 | 0 | 0 | -42.39
129 | VTS - BBP & BCP CG UPGRADE | City Gates & Field Regs | Replacement |  | 0 | 0 | 0 | 0 | 0 | 0
130 | VTS - BRANCH VALVE CASTLEMAINE | Pipelines | Replacement |  | 0 | 0 | 0 | 0 | 0 | 0
131 | VTS - EUROA CS NEW (PPOM) | Compressors | Replacement |  | 116664.37 | 121805.28 | 59020.54 | -2941.24 | 0 | 294548.95
132 | VTS - SUNBURY PIPE LOOP (NEW) | Pipelines | Replacement |  | 51715.09 | 38571.05 | 5019.95 | -654.99 | 0 | 94651.1
133 | VTS - BCS 8&9 COOLERS UPG (NEW | Compressors | Replacement |  | -12591.73 | 22820.08 | 0 | 0 | 0 | 10228.35
134 | VTS - BCS 12 FAST STOP VALVE | Compressors | Replacement |  | 0 | 0 | 0 | 0 | 0 | 0
135 | VTS - BCS 8 & 9 UNIT VALVES | Compressors | Replacement |  | 0 | 0 | 0 | 0 | 0 | 0
136 | PIGGING T91 CURDIEVALE | Other | Replacement |  | 0 | 17873 | 0 | 0 | 0 | 17873
137 | VTS - BROOKLYN FIRE SERVICE | Buildings | Non-System |  | 0 | 40752.23 | 0 | 0 | 0 | 40752.23
138 | VTS - BCS LUBE OIL COOLER 8&9 | City Gates & Field Regs | Replacement |  | 109672.54 | 0 | 0 | 0 | 0 | 109672.54
139 | VNIE Looping 6 to 8 | Pipelines | Augmentation |  | 0 | 0 | 0 | 0 | 125292714.1114 | 125292714.1114
140 | VTS16.SIB42 WOLL SOFT STARTERS | Other | Replacement |  | 0 | 0 | 0 | 0 | 30881 | 30881
141 | VTS.SIB99 WCS STN-A DISCHRG LQ | Other | Replacement |  | 0 | 0 | 0 | 0 | 0 | 0
142 | VTS17.SIB27 SCS CR EPS REMOVAL | Buildings | Non-System |  | 0 | 0 | 0 | 0 | 324206.2 | 324206.2
143 | VTS17.SIB30 DND EMERG ENTRANCE | Buildings | Non-System |  | 0 | 0 | 0 | 0 | 24545.55 | 24545.55
144 | Corporate other | Other | Non-System |  | 242365.2632 | 340342.973 | 308327.8805 | 17522.8525 | 193217.0674 | 1101776.0366
145 | Market Services _APA Grid Prog | Other | Non-System |  | 0 | 0 | 0 | 310348.845 | 0 | 310348.845
146 | APA Grid Perf & Resil Overhaul | Other | Non-System |  | 0 | 0 | 44725.1667 | 22022.8998 | 0 | 66748.0665
147 | APA Grid & Mrkt Srvs SIB Capex | Other | Non-System |  | 0 | 0 | 0 | 0 | 0 | 0
148 | APA Grid Extend | Other | Non-System |  | 0 | 0 | 0 | 80289.867 | 681495.7221 | 761785.5891
149 | APA Grid Services Initiatives | Other | Non-System |  | 0 | 0 | 0 | 188898.9119 | 93837.1179 | 282736.0298
150 | CORP SIB16 DANDENONG REFURB | Other | Non-System |  | 0 | 0 | 303211.3819 | 3462.88 | 0 | 306674.2619
151 | Data Centre | Other | Non-System |  | 0 | 961195.2533 | 79250.1745 | 0 | 0 | 1040445.4278
152 | Enterprise Asset Management | Other | Non-System |  | 0 | 0 | 5357652.8429 | 1771.8759 | -11.219 | 5359413.4998
153 | Enterprise Content Management | Other | Non-System |  | 0 | 0 | 0 | 504409.8737 | 555995.9985 | 1060405.8722
154 | EAM Bus Support & Governance | Other | Non-System |  | 0 | 0 | 0 | 42640.3455 | 65.1413 | 42705.4868
155 | EAM TRANSMISSION ESTAB WORK | Other | Non-System |  | 0 | 0 | 0 | 199413.8739 | 247813.8633 | 447227.7372
156 | Oracle Integration with EAM | Other | Non-System |  | 0 | 0 | 0 | 10956.5236 | 0 | 10956.5236
157 | EAM Business Support-Reports | Other | Non-System |  | 0 | 0 | 0 | 5944.4937 | 3565.8563 | 9510.3501
158 | EC Upgrade | Other | Non-System |  | 0 | 0 | 0 | 256499.7136 | 139404.1118 | 395903.8254
159 | Finance Systems | Other | Non-System |  | 1751.8135 | 0 | 0 | 0 | 0 | 1751.8135
160 | Mobile phone CAPEX purchases | Other | Non-System |  | 0 | 22811.9773 | 27279.5795 | 34752.7222 | 21127.7494 | 105972.0283
161 | PPOM Phase 2 | Other | Non-System |  | 5453.1938 | 0 | 0 | 0 | 0 | 5453.1938
162 | Project Server Status Report | Other | Non-System |  | 7605.6406 | 4061.9411 | 0 | 0 | 0 | 11667.5817
163 | BI reporting | Other | Non-System |  | 33318.3814 | 2571.9179 | 0 | 0 | 0 | 35890.2993
164 | PPOM Snapshot Engine | Other | Non-System |  | 9285.9184 | 12608.9365 | 0 | 0 | 0 | 21894.8549
165 | APA Grid Ph.2 | Other | Non-System |  | 0 | 234812.1387 | 0 | 0 | 0 | 234812.1387
166 | APA Grid Ph. 3 | Other | Non-System |  | 0 | 2637.3633 | 0 | 0 | 0 | 2637.3633
167 | Vehicle Comms & Journey Mgmt | Other | Non-System |  | 0 | 0 | 0 | 243650.4946 | -8653.3782 | 234997.1164
168 | SCADA Satellite Strategy | Other | Non-System |  | 0 | 0 | 0 | 131322.5051 | 45922.7906 | 177245.2957
169 | SCADA Resilience Project FEED | Other | Non-System |  | 0 | 0 | 0 | 19777.1403 | 0 | 19777.1403
170 | IOC SCADA GAP ANALYSIS | Other | Non-System |  | 0 | 0 | 0 | 4246.8422 | 0 | 4246.8422
171 | SCADA Resilience Phase 1 Recom | Other | Non-System |  | 0 | 0 | 0 | 22462.5329 | 67609.9204 | 90072.4533
172 | Melbourne Metro CRE | Other | Non-System |  | 0 | 0 | 0 | 4584380.0134 | 1008115.8558 | 5592495.8692
173 | HR Systems Refresh | Other | Non-System |  | 0 | 0 | 0 | 0 | 152663.248 | 152663.248
174 | Historian Upgrade - version 2012 to 2015 | Other | Non-System |  | 0 | 0 | 0 | 0 | 41738.0552 | 41738.0552
175 | EAM System Upgrade 2018 | Other | Non-System |  | 0 | 0 | 0 | 0 | 109617.3011 | 109617.3011
176 | BizTalk Upgrade FY2018 | Other | Non-System |  | 0 | 0 | 0 | 0 | 101135.0037 | 101135.0037
177 | Code Management Software | Other | Non-System |  | 0 | 0 | 0 | 0 | 0 | 0
178 | X-Info Aware Version 2 | Other | Non-System |  | 0 | 0 | 0 | 0 | 0 | 0
179 | Adjustments required for differences in CWIP and FAR records | Other | Non-System |  | 0 | -26601 | 23200 | 0 | 0 | -3401
180 | Sharepoint site | Other | Non-System |  | 0 | 0 | 0 | 0 | 65134.503 | 65134.503
181 | APA Grid | Other | Non-System |  | 0 | 0 | 0 | 0 | 0 | 0
182 | B&T projects | Other | Non-System |  | 0 | 0 | 0 | 0 | 0 | 0
183 | Dandenong Relocation | Other | Non-System |  | 0 | 0 | 0 | 0 | 0 | 0
184 | Victoria CRE | Other | Non-System |  | 0 | 0 | 0 | 0 | 0 | 0
185 | Access Arrangement Costs | Other | Non-System |  | 0 | 0 | 0 | 0 | 0 | 0
186 | Trans EAM Data Management Tool | Other | Non-System |  | 0 | 0 | 0 | 2653.6996 | 0 | 2653.6996
187 | EAM Site Stores/Warehouses | Other | Non-System |  | 0 | 0 | 0 | 25238.5762 | 0 | 25238.5762
188 | BI - Transmission Dashboard and Enterprise Pilot | Other | Non-System |  | 0 | 0 | 0 | 0 | 47542.4471 | 47542.4471
189 | APA Grid Future Initiatives Projects | Other | Non-System |  | 0 | 0 | 0 | 0 | 121083.5996 | 121083.5996
190 | GRC Platform | Other | Non-System |  | 0 | 0 | 0 | 0 | 19591.6678 | 19591.6678
191 | Direct Link Dispatch Display Application Replacement | Other | Non-System |  | 0 | 0 | 0 | 0 | 11747.9477 | 11747.9477
192 | T92 & DDN3 RTU Upgrade | Other | Replacement |  | 0 | 0 | 0 | 0 | 45423.13 | 45423.13
193 | SCS Vent Modifications | Other | Replacement |  | 0 | 0 | 0 | 0 | 0 | 0
194 | BCS Admin Board Upgrade | Buildings | Non-System |  | 0 | 0 | 0 | 0 | 21660.8 | 21660.8
195 | Pigging Program (T57 & T70) | Pipelines | Replacement |  | 0 | 0 | 0 | 0 | 494213.62 | 494213.62
196 | REMOTE CP MONITOR (37863) | Pipelines | Replacement |  | 0 | 0 | 0 | 0 | 254005.25 | 254005.25
197 | Maryvale Direct Assessment | Pipelines | Replacement |  | 0 | 0 | 0 | 0 | 91167.02 | 91167.02
198 | Wichelsea Bi Direction and Brooklyn Reconfiguration | Compressors | Augmentation |  | 0 | 0 | 0 | 0 | 3179000.24 | 3179000.24
199 | ILUKA WBH FIRE TUBE | Pipelines | Replacement |  | 0 | 0 | 0 | 0 | 23875 | 23875
200 | REMOTE CP MONITOR (38260) | Pipelines | Replacement |  | 0 | 0 | 0 | 0 | 59511.13 | 59511.13
201 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
202 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
203 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
204 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0

## 5.0 Calc│Forecast Projects
| 5.0 Calc│Forecast Projects |  | Check | 295124406.0242 | 295124406.0242 | 0 |  |  |  |  | 12 | 15 | 13 | 16
Capex # | Project Name | Business case/ project code | Unit | Allocator | Year | 2018 | 2019 | 2020 | 2021 | 2022 | Labour | Contractor | Materials | Other | Check
1 | All CS buffer Air shutoff system for all compressors | 202 | 1 | VTS | 2016 | 381730.5067 | 190865.2533 | 0 | 0 | 0 | 23.66% | 1.964% | 74.37% | 0% | 100%
2 | WCS A Process Safety | 203 | 1 | VTS | 2016 | 0 | 0 | 1045505.76 | 0 | 0 | 23.66% | 27.69% | 48.65% | 0% | 100%
3 | Brooklyn Compressor Station | 204 | 1 | VTS | 2016 | 0 | 0 | 2297362.2833 | 2297362.2833 | 2297362.2833 | 25.12% | 28.49% | 46.38% | 0% | 100%
4 | Compressor Station Vent Stack Upgrade (BCS, WCS, GCS, SCS) | 205 | 1 | VTS | 2016 | 0 | 330397.72 | 330397.72 | 330397.72 | 0 | 23.66% | 26.54% | 29.62% | 20.18% | 100%
5 | Longford Odorant Pump Power Gas Upgrade | 206 | 1 | VTS | 2016 | 75569.2 | 0 | 0 | 0 | 0 | 28.57% | 33.54% | 32.83% | 5.06% | 100%
6 | GCS compressor unit vent valves & actuators replacement | 207a | 1 | VTS | 2016 | 139391.86 | 0 | 0 | 0 | 0 | 23.66% | 28.73% | 47.61% | 0% | 100%
7 | GCS unit discharge and station manifold check valves replacement | 207b | 1 | VTS | 2016 | 0 | 0 | 901953.34 | 0 | 0 | 24.64% | 18.78% | 56.58% | 0% | 100%
8 | GCS Decomm & removal of turbine oil reservoir & auto fill system | 207c | 1 | VTS | 2016 | 0 | 87971.74 | 0 | 0 | 0 | 23.66% | 75.6% | 0.74% | 0% | 100%
9 | BCS Instrument Air reliability upgrade | 208 | 1 | VTS | 2016 | 93782.9 | 0 | 0 | 0 | 0 | 23.66% | 48.4% | 27.93% | 0% | 100%
10 | Compressor lagging and pipe coating replacement (expand to GCS, Springhurst/BCS12/WCS A/WCS B, Euroa) | 209 | 1 | VTS | 2016 | 144918.75 | 144918.75 | 144918.75 | 144918.75 | 144918.75 | 23.66% | 76.34% | 0% | 0% | 100%
11 | Storage shed-Dandenong, Wollert & Springhurst | 210 | 1 | Victoria | 2016 | 0 | 648767 | 648767 | 648767 | 0 | 28.57% | 71.43% | 0% | 0% | 100%
12 | Iona CS aftercooler augmentation | 211 | 1 | VTS | 2016 | 0 | 0 | 0 | 1656341.4 | 0 | 28.57% | 37.41% | 34.02% | 0% | 100%
13 | Battery replacement | 212 | 1 | VTS | 2016 | 70284.2 | 70284.2 | 70284.2 | 70284.2 | 70284.2 | 32.67% | 14.76% | 48.02% | 4.553% | 100%
14 | Wollert CG Instrument Air Conversion | 216 | 1 | VTS | 2016 | 0 | 0 | 0 | 504246.51 | 0 | 23.66% | 56.54% | 19.8% | 0% | 100%
15 | Pit installation on LV03 bypass valves on T33 | 220 | 1 | VTS | 2016 | 0 | 0 | 230860 | 0 | 0 | 28.57% | 58.06% | 13.37% | 0% | 100%
16 | Dandenong water supply & fire main modification | 223 | 1 | Victoria | 2016 | 324178.4 | 0 | 0 | 0 | 0 | 28.57% | 71.43% | 0% | 0% | 100%
17 | Culcairn Injection Gas Quality equipment | 224 | 1 | VTS | 2016 | 973960.4 | 0 | 0 | 0 | 0 | 28.57% | 4.661% | 66.77% | 0% | 100%
18 | Positioner Replacement | 225 | 1 | VTS | 2016 | 101494.96 | 101494.96 | 101494.96 | 101494.96 | 101494.96 | 35.1% | 22.08% | 31.94% | 10.88% | 100%
19 | VTS Safety Management Study aerial photography | 227 | 1 | VTS | 2016 | 162466.1262 | 2780.5938 | 0 | 0 | 0 | 21.88% | 0% | 0% | 78.12% | 100%
20 | BLP Safety Measures for High Consequence areas-(urban growth, fracture control) | 230b | 1 | VTS | 2016 | 0 | 2492000 | 0 | 0 | 1869000 | 21.88% | 48.26% | 29.86% | 0% | 100%
21 | WOP Safety Measures for High Consequence areas-(urban growth, fracture control) | 230c | 1 | VTS | 2016 | 1120000 | 0 | 0 | 0 | 0 | 21.88% | 48.11% | 30.02% | 0% | 100%
22 | ILP Safety Measures for High Consequence areas-(urban growth, fracture control) | 230e | 1 | VTS | 2016 | 27000.6267 | 28057.2933 | 0 | 0 | 0 | 21.88% | 61.29% | 16.84% | 0% | 100%
23 | Turbine Overhauls | 235 | 1 | VTS | 2016 | 0 | 0 | 0 | 1004594.5846 | 3594396.2154 | 23.66% | 76.34% | 0% | 0% | 100%
24 | Iona CS Automation replacement | 236 | 1 | VTS | 2016 | 0 | 0 | 1173411.54 | 0 | 0 | 36.55% | 17.91% | 45.54% | 0% | 100%
25 | GCS Control Room and Unit Enclosure 1,2,3&4 Fire Suppression System | 237a | 1 | VTS | 2016 | 268558.9473 | 0 | 0 | 0 | 0 | 23.66% | 76.34% | 0% | 0% | 100%
26 | BCS MCC Room Fire Suppression System | 237b | 1 | VTS | 2016 | 0 | 0 | 268558.9473 | 0 | 0 | 23.66% | 76.34% | 0% | 0% | 100%
27 | Iona CS Control Room and Unit Enclosure Fire Suppression System | 237d | 1 | VTS | 2016 | 0 | 0 | 0 | 268558.9473 | 0 | 23.66% | 76.34% | 0% | 0% | 100%
28 | Lara City Gate Control Hut Fire Suppression System | 237e | 1 | VTS | 2016 | 0 | 0 | 0 | 0 | 82002.732 | 28.57% | 71.43% | 0% | 0% | 100%
29 | BCS Control Room Fire Suppression System | 237f | 1 | VTS | 2016 | 0 | 0 | 0 | 0 | 82002.732 | 28.57% | 71.43% | 0% | 0% | 100%
30 | Emergency- BA escape sets | 239a | 1 | Victoria | 2016 | 19083.52 | 0 | 0 | 0 | 0 | 21.88% | 0% | 78.12% | 0% | 100%
31 | Emergency- Response Equipment | 239b | 1 | Victoria | 2016 | 278309.12 | 278309.12 | 278309.12 | 278309.12 | 278309.12 | 21.88% | 0.258% | 77.87% | 0% | 100%
32 | Emergency- Spark Proof tools | 239c | 1 | Victoria | 2016 | 1945.6 | 1945.6 | 1945.6 | 1945.6 | 1945.6 | 58.88% | 0% | 41.12% | 0% | 100%
33 | Emergency - fully equipped caravan | 239d | 1 | Victoria | 2016 | 0 | 0 | 107878.4 | 0 | 0 | 21.88% | 4.542% | 73.58% | 0% | 100%
34 | Emergency diesel fuel storage | 239e | 1 | Victoria | 2016 | 0 | 0 | 0 | 123107.84 | 0 | 21.88% | 37% | 41.12% | 0% | 100%
35 | Vent stack for CL600 & 900 pipeline | 240 | 1 | VTS | 2016 | 210339.84 | 0 | 0 | 0 | 0 | 21.88% | 0% | 78.12% | 0% | 100%
36 | Remote CP/critical drainage bond monitoring | 241 | 1 | VTS | 2016 | 573053.7778 | 60456.5556 | 60456.5556 | 60456.5556 | 60456.5556 | 33.41% | 0% | 64.43% | 2.163% | 100%
37 | BCG Un-regulated Bypass Upgrade | 242 | 1 | VTS | 2016 | 0 | 0 | 342346.24 | 0 | 0 | 23.42% | 66.99% | 9.593% | 0% | 100%
38 | Security - Physical | 243 | 1 | Victoria | 2016 | 365236.384 | 365236.384 | 365236.384 | 365236.384 | 365236.384 | 37.33% | 62.67% | 0% | 0% | 100%
39 | CP - Cathodic Protection Replacement | 244 | 1 | VTS | 2016 | 232464.384 | 232464.384 | 232464.384 | 232464.384 | 232464.384 | 36.12% | 4.938% | 53.17% | 5.766% | 100%
40 | Equipment - Gas Detectors | 245 | 1 | Victoria | 2016 | 0 | 0 | 25000 | 25000 | 0 | 0% | 0% | 100% | 0% | 100%
41 | Regulator Upgrade - Lara pneumatic control system upgrade | 247 | 1 | VTS | 2016 | 0 | 619257.8 | 0 | 0 | 0 | 32.45% | 14.16% | 53.39% | 0% | 100%
42 | Hazardous Area Rectification | 249 | 1 | VTS | 2016 | 178000 | 178000 | 178000 | 178000 | 178000 | 11.24% | 50.56% | 38.2% | 0% | 100%
43 | Actuate MLV's in T1 areas | 250 | 1 | VTS | 2016 | 956710.4 | 956710.4 | 0 | 0 | 0 | 21.88% | 10.89% | 62.21% | 5.017% | 100%
44 | Asbestos removal and replacement | 251 | 1 | VTS | 2016 | 70000 | 70000 | 70000 | 70000 | 70000 | 28.57% | 71.43% | 0% | 0% | 100%
45 | T33 non-piggable and encased sections (unknown technical solution) | 257 | 1 | VTS | 2016 | 151759.04 | 151759.04 | 151759.04 | 151759.04 | 0 | 25.63% | 69.18% | 5.189% | 0% | 100%
46 | Pigging Program T57 Ballan - Ballarat | 258a | 1 | VTS | 2016 | 564768 | 0 | 0 | 0 | 0 | 22.3% | 74.14% | 3.564% | 0% | 100%
47 | Pigging Program T62 Derrimut - Sunbury | 258b | 1 | VTS | 2016 | 425799.68 | 0 | 0 | 0 | 0 | 22.44% | 75.1% | 2.461% | 0% | 100%
48 | Pigging Program T61 Packenham - Wollert | 258c | 1 | VTS | 2016 | 0 | 649896.96 | 0 | 0 | 0 | 22.24% | 70.48% | 7.276% | 0% | 100%
49 | Pigging Program T16 Dandenong – West Melbourne | 258d | 1 | VTS | 2016 | 0 | 0 | 0 | 1377768.96 | 0 | 22.05% | 74.52% | 3.432% | 0% | 100%
50 | Pigging Program T60 Longford -Dandenong | 258e | 1 | VTS | 2016 | 0 | 0 | 0 | 0 | 2380922.88 | 21.98% | 76.04% | 1.986% | 0% | 100%
51 | Pigging Program T33 South Melbourne – Brooklyn | 258f | 1 | VTS | 2016 | 0 | 0 | 0 | 1023660.8 | 0 | 22.11% | 73.27% | 4.619% | 0% | 100%
52 | Pigging Program T66-70 Mt Franklin -Kyneton - Bendigo | 258i | 1 | VTS | 2016 | 0 | 587336.96 | 0 | 0 | 0 | 22.28% | 74.29% | 3.427% | 0% | 100%
53 | Pigging Program T75 Wandong - Kyneton | 258k | 1 | VTS | 2016 | 0 | 521020.16 | 0 | 0 | 0 | 22.34% | 73.8% | 3.863% | 0% | 100%
54 | Pigging Program T24 Brooklyn - Corio | 258l | 1 | VTS | 2016 | 0 | 0 | 0 | 1380663.04 | 0 | 22.05% | 76.35% | 1.6% | 0% | 100%
55 | Pigging Program T70 Ballan – Bendigo | 258m | 1 | VTS | 2016 | 0 | 0 | 555975.68 | 0 | 0 | 22.31% | 75.81% | 1.885% | 0% | 100%
56 | Pigging Program T60 Longford – Tyers | 258n | 1 | VTS | 2016 | 0 | 0 | 0 | 0 | 748398.08 | 22.2% | 71.49% | 6.318% | 0% | 100%
57 | Pigging Program T63 Tyers - Morwell | 258o | 1 | VTS | 2016 | 0 | 0 | 0 | 611088.64 | 0 | 22.27% | 72.57% | 5.161% | 0% | 100%
58 | Pigging Program T96 & T98 Chiltern- Rutherglen – Koonoomoo | 258p | 1 | VTS | 2016 | 0 | 0 | 0 | 0 | 510551.04 | 22.35% | 74.99% | 2.669% | 0% | 100%
59 | Pigging Program T118 Trugannina-Plumpton | 258q | 1 | VTS | 2016 | 0 | 0 | 0 | 0 | 512325.12 | 22.34% | 71.5% | 6.156% | 0% | 100%
60 | Pigging Program James Street to Laverton Pipeline (253) | 258s | 1 | VTS | 2016 | 0 | 447777.28 | 0 | 0 | 0 | 22.41% | 72.66% | 4.933% | 0% | 100%
61 | Pigging Program Tyres to Maryvale (67) | 258u | 1 | VTS | 2016 | 383189.76 | 0 | 0 | 0 | 0 | 22.5% | 74.76% | 2.735% | 0% | 100%
62 | Pigging Program T108 Newport | 258v | 1 | VTS | 2016 | 473861.12 | 0 | 0 | 0 | 0 | 22.38% | 71.63% | 5.988% | 0% | 100%
63 | Pigging Program Inner Ring Main | 258w | 1 | VTS | 2016 | 0 | 0 | 3513.6 | 0 | 0 | 22.33% | 72.29% | 5.379% | 0% | 100%
64 | Pigging Program T1 Morwell - Dandenong Pigging and Repair Program | 258x | 1 | VTS | 2016 | 1987281.2739 | 1112357.7261 | 0 | 0 | 0 | 21.88% | 75.82% | 2.305% | 0% | 100%
65 | Pig Trap Installation James Street to Laverton Pipeline (253) | 259a | 1 | VTS | 2016 | 0 | 1894808.9075 | 207849.08 | 0 | 0 | 13.54% | 57.38% | 29.08% | 0% | 100%
66 | Pig Trap Installation Tyers to Maryvale Pipeline (67) | 259d | 1 | VTS | 2016 | 589874.5129 | 78499.3589 | 0 | 0 | 0 | 13.55% | 59.01% | 27.44% | 0% | 100%
67 | Liquid Management - Brooklyn | 260a | 1 | VTS | 2016 | 0 | 0 | 0 | 0 | 157005.8 | 29.27% | 55.05% | 15.68% | 0% | 100%
68 | Liquid Management - Pakenham | 260b | 1 | VTS | 2016 | 0 | 0 | 0 | 157005.8 | 0 | 29.27% | 55.05% | 15.68% | 0% | 100%
69 | RTU replacement | 262 | 1 | VTS | 2016 | 141816.64 | 141816.64 | 141816.64 | 141816.64 | 141816.64 | 71.47% | 16.49% | 9.837% | 2.196% | 100%
70 | Pipe Support replacement | 263 | 1 | VTS | 2016 | 164811.0408 | 164811.0408 | 164811.0408 | 164811.0408 | 164811.0408 | 28.57% | 71.43% | 0% | 0% | 100%
71 | HMI upgrade to CLEAR SCADA at BCS, SCS and WCS & CG, Longford | 264 | 1 | VTS | 2016 | 60928 | 60928 | 60928 | 60928 | 60928 | 58.51% | 1.313% | 35.45% | 4.727% | 100%
72 | BCS Unit 12 Inlet Filter Replacement/Augmentation | 267 | 1 | VTS | 2016 | 635719.42 | 0 | 0 | 0 | 0 | 23.66% | 39.83% | 36.51% | 0% | 100%
73 | Coogee decommissioning | 268 | 1 | VTS | 2016 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0%
74 | Compressor Type B Compliance | 271 | 1 | VTS | 2016 | 216718.54 | 216718.54 | 216718.54 | 216718.54 | 216718.54 | 33.45% | 30.5% | 36.05% | 0% | 100%
75 | Dandenong LNG Isolation Valve Upgrade | 275 | 1 | VTS | 2016 | 649021.8 | 0 | 0 | 0 | 0 | 29.4% | 40.97% | 29.64% | 0% | 100%
76 | Morwell-Dandenong Fatigue Crack Detection from High Loads | 276 | 1 | VTS | 2016 | 260832 | 0 | 0 | 0 | 0 | 25.56% | 67.79% | 6.653% | 0% | 100%
77 | Unibolt Enclosure Replacement | 277 | 1 | VTS | 2016 | 44464 | 44464 | 44464 | 44464 | 44464 | 28.57% | 60.18% | 11.25% | 0% | 100%
78 | WAN Upgrade (Satellite project) | 278 | 1 | VTS | 2016 | 946991.92 | 946991.92 | 946991.92 | 946991.92 | 946991.92 | 46.57% | 18.2% | 29.89% | 5.355% | 100%
79 | Warragul Looping 6" (Southern Route) | Warragul 6" (Sth) | 1 | VTS | 2016 | 5400000 | 2000000 | 0 | 0 | 0 | 34.54% | 12.78% | 52.68% | 0% | 100%
80 | Angelsea Pipeline (Western Route) | Anglesea | 1 | VTS | 2016 | 13620487.6931 | 12272008.9469 | 0 | 0 | 0 | 49.2% | 0% | 30.91% | 19.88% | 100%
81 | VNIE | VNIE | 1 | VTS | 2016 | 1583090.777 | 0 | 0 | 0 | 0 | 0% | 100% | 0% | 0% | 100%
82 | Wichelsea Bi Direction and Brooklyn Reconfiguration | WCS Bi-Dir and BCS reconfig | 1 | VTS | 2016 | 540000 | 0 | 0 | 0 | 0 | 55.56% | 11.11% | 33.33% | 0% | 100%
83 | WORM (50km x 20" Pipeline) | WORM (Pipeline) | 1 | VTS | 2016 | 15911166.8213 | 28997137.4367 | 48814496.7419 | 0 | 0 | 10.58% | 0% | 33.69% | 55.73% | 100%
84 | WORM (C50 at Wollert) | WORM (C50) | 1 | VTS | 2016 | 7043662.34 | 12092299.2911 | 6176723.3689 | 0 | 0 | 37.05% | 0% | 60.4% | 2.553% | 100%
85 | WORM (PRS at Wollert) | WORM (PRS) | 1 | VTS | 2016 | 0 | 1641722.0833 | 1959224.9167 | 0 | 0 | 42.22% | 0% | 54.63% | 3.152% | 100%
86 | Enterprise Content Management | APA | 1 | APA | 2016 | 0 | 0 | 0 | 0 | 0 | 30% | 65% | 5% | 0% | 100%
87 | Victoria CRE | APA | 1 | APA | 2016 | 0 | 0 | 0 | 0 | 0 | 30% | 65% | 5% | 0% | 100%
88 | APA Grid Energy Components Upgrade | APA | 1 | APA | 2016 | 0 | 0 | 0 | 0 | 0 | 30% | 65% | 5% | 0% | 100%
89 | APA Grid Extend Program | APA | 1 | APA | 2016 | 2500000 | 0 | 0 | 0 | 0 | 30% | 65% | 5% | 0% | 100%
90 | APA Grid Services Initiatives Program | APA | 1 | APA | 2016 | 0 | 0 | 0 | 0 | 0 | 30% | 65% | 5% | 0% | 100%
91 | Hyperion Upgrade to 11.1.2.4 | APA | 1 | APA | 2016 | 0 | 0 | 0 | 0 | 0 | 30% | 65% | 5% | 0% | 100%
92 | BI - Transmission Dashboard and Enterprise Pilot | APA | 1 | APA | 2016 | 2000000 | 1500000 | 0 | 0 | 0 | 30% | 65% | 5% | 0% | 100%
93 | HR Systems Refresh | APA | 1 | APA | 2016 | 0 | 0 | 0 | 0 | 0 | 30% | 65% | 5% | 0% | 100%
94 | Transmission EAM Data Management Tool | APA | 1 | APA | 2016 | 0 | 0 | 0 | 0 | 0 | 30% | 65% | 5% | 0% | 100%
95 | SharePoint Upgrade | APA | 1 | APA | 2016 | 243778.5 | 0 | 0 | 0 | 0 | 30% | 65% | 5% | 0% | 100%
96 | eForm Digitisation | APA | 1 | APA | 2016 | 0 | 0 | 1607603.75 | 4147396.25 | 0 | 30% | 65% | 5% | 0% | 100%
97 | Historian Upgrade - version 2012 to 2015 | APA | 1 | APA | 2016 | 0 | 0 | 0 | 0 | 0 | 30% | 65% | 5% | 0% | 100%
98 | Hazardous Area Platform | APA | 1 | APA | 2016 | 1552491.3 | 0 | 0 | 0 | 0 | 30% | 65% | 5% | 0% | 100%
99 | PPM Refresh | APA | 1 | APA | 2016 | 3000000 | 0 | 0 | 0 | 0 | 30% | 65% | 5% | 0% | 100%
100 | BizTalk Upgrade FY2018 | APA | 1 | APA | 2016 | 0 | 604848.9048 | 670918.5097 | 0 | 0 | 30% | 65% | 5% | 0% | 100%
101 | Automated Testing Tool | APA | 1 | APA | 2016 | 632204.9999 | 0 | 0 | 0 | 0 | 30% | 65% | 5% | 0% | 100%
102 | Code Management Software | APA | 1 | APA | 2016 | 905930.625 | 0 | 0 | 0 | 0 | 30% | 65% | 5% | 0% | 100%
103 | CRM Upgrade | APA | 1 | APA | 2016 | 1408186.2 | 59047.8 | 0 | 0 | 0 | 30% | 65% | 5% | 0% | 100%
104 | X-Info Aware Version 2 | APA | 1 | APA | 2016 | 430081.5 | 0 | 0 | 0 | 0 | 30% | 65% | 5% | 0% | 100%
105 | Supplier Qualification and Compliance | APA | 1 | APA | 2016 | 697848.96 | 185555.04 | 0 | 0 | 0 | 30% | 65% | 5% | 0% | 100%
106 | Oracle eBS Upgrade to 12.2 | APA | 1 | APA | 2016 | 267113.0161 | 1276243.5381 | 0 | 0 | 0 | 30% | 65% | 5% | 0% | 100%
107 | BizTalk System Upgrade 2020 | APA | 1 | APA | 2016 | 0 | 604848.9048 | 670918.5097 | 0 | 0 | 30% | 65% | 5% | 0% | 100%
108 | Applications Renewal | APA | 1 | APA | 2016 | 6900000 | 8620000 | 6900000 | 8620000 | 6900000 | 30% | 65% | 5% | 0% | 100%
109 | Infrastructure Renewal | APA | 1 | APA | 2016 | 2250000 | 750000 | 750000 | 750000 | 0 | 30% | 65% | 5% | 0% | 100%
110 | Dandenong Relocation | APA | 1 | APA | 2016 | 0 | 0 | 0 | 0 | 0 | 50% | 0% | 50% | 0% | 100%
- | 0 | - | 1 | - | 2016 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0%
- | 0 | - | 1 | - | 2016 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0%
- | 0 | - | 1 | - | 2016 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0%
- | 0 | - | 1 | - | 2016 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0%
- | 0 | - | 1 | - | 2016 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0%
- | 0 | - | 1 | - | 2016 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0%
- | 0 | - | 1 | - | 2016 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0%
- | 0 | - | 1 | - | 2016 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0%
- | 0 | - | 1 | - | 2016 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0%
- | 0 | - |  | - |  | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0%
- | 0 | - |  | - |  | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0%
- | 0 | - |  | - |  | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0%
- | 0 | - |  | - |  | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0%
- | 0 | - |  | - |  | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0%
- | 0 | - |  | - |  | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0%
- | 0 | - |  | - |  | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0%
- | 0 | - |  | - |  | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0%
- | 0 | - |  | - |  | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0%
- | 0 | - |  | - |  | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0%
- | 0 | - |  | - |  | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0%
- | 0 | - |  | - |  | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0%
- | 0 | - |  | - |  | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0%
- | 0 | - |  | - |  | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0%
- | 0 | - |  | - |  | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0%
- | 0 | - |  | - |  | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0%
- | 0 | - |  | - |  | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0%
- | 0 | - |  | - |  | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0%
- | 0 | - |  | - |  | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0%
- | 0 | - |  | - |  | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0%
- | 0 | - |  | - |  | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0%
- | 0 | - |  | - |  | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0%
- | 0 | - |  | - |  | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0%
- | 0 | - |  | - |  | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0%
- | 0 | - |  | - |  | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0%
- | 0 | - |  | - |  | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0%
- | 0 | - |  | - |  | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0%
- | 0 | - |  | - |  | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0%
- | 0 | - |  | - |  | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0%
- | 0 | - |  | - |  | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0%
- | 0 | - |  | - |  | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0%
- | 0 | - |  | - |  | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0%
- | 0 | - |  | - |  | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0%
- | 0 | - |  | - |  | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0%
- | 0 | - |  | - |  | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0%
- | 0 | - |  | - |  | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0%
- | 0 | - |  | - |  | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0%
- | 0 | - |  | - |  | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0%
- | 0 | - |  | - |  | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0%
- | 0 | - |  | - |  | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0%
- | 0 | - |  | - |  | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0%
- | 0 | - |  | - |  | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0%
- | 0 | - |  | - |  | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0%
- | 0 | - |  | - |  | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0%
- | 0 | - |  | - |  | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0%
- | 0 | - |  | - |  | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0%
- | 0 | - |  | - |  | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0%
- | 0 | - |  | - |  | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0%
- | 0 | - |  | - |  | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0%
- | 0 | - |  | - |  | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0%
- | 0 | - |  | - |  | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0%
- | 0 | - |  | - |  | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0%
- | 0 | - |  | - |  | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0%
- | 0 | - |  | - |  | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0%
- | 0 | - |  | - |  | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0%
- | 0 | - |  | - |  | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0%
- | 0 | - |  | - |  | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0%
- | 0 | - |  | - |  | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0%
- | 0 | - |  | - |  | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0%
- | 0 | - |  | - |  | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0%
- | 0 | - |  | - |  | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0%
- | 0 | - |  | - |  | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0%
- | 0 | - |  | - |  | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0%
- | 0 | - |  | - |  | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0%
- | 0 | - |  | - |  | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0%
- | 0 | - |  | - |  | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0%
- | 0 | - |  | - |  | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0%
- | 0 | - |  | - |  | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0%
- | 0 | - |  | - |  | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0%

## 5.1 Calc│$ million
| 5.1 Calc│$ million | Check picking up all projects | 0 |  | Check values | 0 | 0 | 0 | 0 | 0
Capex # | Project Name | Business case/ project code | Unit Input | Converter |  | 2018 | 2019 | 2020 | 2021 | 2022
1 | All CS buffer Air shutoff system for all compressors | 202 | 1 | 1e-06 |  | 0.38173 | 0.19087 | 0 | 0 | 0
2 | WCS A Process Safety | 203 | 1 | 1e-06 |  | 0 | 0 | 1.0455 | 0 | 0
3 | Brooklyn Compressor Station | 204 | 1 | 1e-06 |  | 0 | 0 | 2.2974 | 2.2974 | 2.2974
4 | Compressor Station Vent Stack Upgrade (BCS, WCS, GCS, SCS) | 205 | 1 | 1e-06 |  | 0 | 0.3304 | 0.3304 | 0.3304 | 0
5 | Longford Odorant Pump Power Gas Upgrade | 206 | 1 | 1e-06 |  | 0.075569 | 0 | 0 | 0 | 0
6 | GCS compressor unit vent valves & actuators replacement | 207a | 1 | 1e-06 |  | 0.13939 | 0 | 0 | 0 | 0
7 | GCS unit discharge and station manifold check valves replacement | 207b | 1 | 1e-06 |  | 0 | 0 | 0.90195 | 0 | 0
8 | GCS Decomm & removal of turbine oil reservoir & auto fill system | 207c | 1 | 1e-06 |  | 0 | 0.087972 | 0 | 0 | 0
9 | BCS Instrument Air reliability upgrade | 208 | 1 | 1e-06 |  | 0.093783 | 0 | 0 | 0 | 0
10 | Compressor lagging and pipe coating replacement (expand to GCS, Springhurst/BCS12/WCS A/WCS B, Euroa) | 209 | 1 | 1e-06 |  | 0.14492 | 0.14492 | 0.14492 | 0.14492 | 0.14492
11 | Storage shed-Dandenong, Wollert & Springhurst | 210 | 1 | 1e-06 |  | 0 | 0.64877 | 0.64877 | 0.64877 | 0
12 | Iona CS aftercooler augmentation | 211 | 1 | 1e-06 |  | 0 | 0 | 0 | 1.6563 | 0
13 | Battery replacement | 212 | 1 | 1e-06 |  | 0.070284 | 0.070284 | 0.070284 | 0.070284 | 0.070284
14 | Wollert CG Instrument Air Conversion | 216 | 1 | 1e-06 |  | 0 | 0 | 0 | 0.50425 | 0
15 | Pit installation on LV03 bypass valves on T33 | 220 | 1 | 1e-06 |  | 0 | 0 | 0.23086 | 0 | 0
16 | Dandenong water supply & fire main modification | 223 | 1 | 1e-06 |  | 0.32418 | 0 | 0 | 0 | 0
17 | Culcairn Injection Gas Quality equipment | 224 | 1 | 1e-06 |  | 0.97396 | 0 | 0 | 0 | 0
18 | Positioner Replacement | 225 | 1 | 1e-06 |  | 0.10149 | 0.10149 | 0.10149 | 0.10149 | 0.10149
19 | VTS Safety Management Study aerial photography | 227 | 1 | 1e-06 |  | 0.16247 | 0.0027806 | 0 | 0 | 0
20 | BLP Safety Measures for High Consequence areas-(urban growth, fracture control) | 230b | 1 | 1e-06 |  | 0 | 2.492 | 0 | 0 | 1.869
21 | WOP Safety Measures for High Consequence areas-(urban growth, fracture control) | 230c | 1 | 1e-06 |  | 1.12 | 0 | 0 | 0 | 0
22 | ILP Safety Measures for High Consequence areas-(urban growth, fracture control) | 230e | 1 | 1e-06 |  | 0.027001 | 0.028057 | 0 | 0 | 0
23 | Turbine Overhauls | 235 | 1 | 1e-06 |  | 0 | 0 | 0 | 1.0046 | 3.5944
24 | Iona CS Automation replacement | 236 | 1 | 1e-06 |  | 0 | 0 | 1.1734 | 0 | 0
25 | GCS Control Room and Unit Enclosure 1,2,3&4 Fire Suppression System | 237a | 1 | 1e-06 |  | 0.26856 | 0 | 0 | 0 | 0
26 | BCS MCC Room Fire Suppression System | 237b | 1 | 1e-06 |  | 0 | 0 | 0.26856 | 0 | 0
27 | Iona CS Control Room and Unit Enclosure Fire Suppression System | 237d | 1 | 1e-06 |  | 0 | 0 | 0 | 0.26856 | 0
28 | Lara City Gate Control Hut Fire Suppression System | 237e | 1 | 1e-06 |  | 0 | 0 | 0 | 0 | 0.082003
29 | BCS Control Room Fire Suppression System | 237f | 1 | 1e-06 |  | 0 | 0 | 0 | 0 | 0.082003
30 | Emergency- BA escape sets | 239a | 1 | 1e-06 |  | 0.019084 | 0 | 0 | 0 | 0
31 | Emergency- Response Equipment | 239b | 1 | 1e-06 |  | 0.27831 | 0.27831 | 0.27831 | 0.27831 | 0.27831
32 | Emergency- Spark Proof tools | 239c | 1 | 1e-06 |  | 0.0019456 | 0.0019456 | 0.0019456 | 0.0019456 | 0.0019456
33 | Emergency - fully equipped caravan | 239d | 1 | 1e-06 |  | 0 | 0 | 0.10788 | 0 | 0
34 | Emergency diesel fuel storage | 239e | 1 | 1e-06 |  | 0 | 0 | 0 | 0.12311 | 0
35 | Vent stack for CL600 & 900 pipeline | 240 | 1 | 1e-06 |  | 0.21034 | 0 | 0 | 0 | 0
36 | Remote CP/critical drainage bond monitoring | 241 | 1 | 1e-06 |  | 0.57305 | 0.060457 | 0.060457 | 0.060457 | 0.060457
37 | BCG Un-regulated Bypass Upgrade | 242 | 1 | 1e-06 |  | 0 | 0 | 0.34235 | 0 | 0
38 | Security - Physical | 243 | 1 | 1e-06 |  | 0.36524 | 0.36524 | 0.36524 | 0.36524 | 0.36524
39 | CP - Cathodic Protection Replacement | 244 | 1 | 1e-06 |  | 0.23246 | 0.23246 | 0.23246 | 0.23246 | 0.23246
40 | Equipment - Gas Detectors | 245 | 1 | 1e-06 |  | 0 | 0 | 0.025 | 0.025 | 0
41 | Regulator Upgrade - Lara pneumatic control system upgrade | 247 | 1 | 1e-06 |  | 0 | 0.61926 | 0 | 0 | 0
42 | Hazardous Area Rectification | 249 | 1 | 1e-06 |  | 0.178 | 0.178 | 0.178 | 0.178 | 0.178
43 | Actuate MLV's in T1 areas | 250 | 1 | 1e-06 |  | 0.95671 | 0.95671 | 0 | 0 | 0
44 | Asbestos removal and replacement | 251 | 1 | 1e-06 |  | 0.07 | 0.07 | 0.07 | 0.07 | 0.07
45 | T33 non-piggable and encased sections (unknown technical solution) | 257 | 1 | 1e-06 |  | 0.15176 | 0.15176 | 0.15176 | 0.15176 | 0
46 | Pigging Program T57 Ballan - Ballarat | 258a | 1 | 1e-06 |  | 0.56477 | 0 | 0 | 0 | 0
47 | Pigging Program T62 Derrimut - Sunbury | 258b | 1 | 1e-06 |  | 0.4258 | 0 | 0 | 0 | 0
48 | Pigging Program T61 Packenham - Wollert | 258c | 1 | 1e-06 |  | 0 | 0.6499 | 0 | 0 | 0
49 | Pigging Program T16 Dandenong – West Melbourne | 258d | 1 | 1e-06 |  | 0 | 0 | 0 | 1.3778 | 0
50 | Pigging Program T60 Longford -Dandenong | 258e | 1 | 1e-06 |  | 0 | 0 | 0 | 0 | 2.3809
51 | Pigging Program T33 South Melbourne – Brooklyn | 258f | 1 | 1e-06 |  | 0 | 0 | 0 | 1.0237 | 0
52 | Pigging Program T66-70 Mt Franklin -Kyneton - Bendigo | 258i | 1 | 1e-06 |  | 0 | 0.58734 | 0 | 0 | 0
53 | Pigging Program T75 Wandong - Kyneton | 258k | 1 | 1e-06 |  | 0 | 0.52102 | 0 | 0 | 0
54 | Pigging Program T24 Brooklyn - Corio | 258l | 1 | 1e-06 |  | 0 | 0 | 0 | 1.3807 | 0
55 | Pigging Program T70 Ballan – Bendigo | 258m | 1 | 1e-06 |  | 0 | 0 | 0.55598 | 0 | 0
56 | Pigging Program T60 Longford – Tyers | 258n | 1 | 1e-06 |  | 0 | 0 | 0 | 0 | 0.7484
57 | Pigging Program T63 Tyers - Morwell | 258o | 1 | 1e-06 |  | 0 | 0 | 0 | 0.61109 | 0
58 | Pigging Program T96 & T98 Chiltern- Rutherglen – Koonoomoo | 258p | 1 | 1e-06 |  | 0 | 0 | 0 | 0 | 0.51055
59 | Pigging Program T118 Trugannina-Plumpton | 258q | 1 | 1e-06 |  | 0 | 0 | 0 | 0 | 0.51233
60 | Pigging Program James Street to Laverton Pipeline (253) | 258s | 1 | 1e-06 |  | 0 | 0.44778 | 0 | 0 | 0
61 | Pigging Program Tyres to Maryvale (67) | 258u | 1 | 1e-06 |  | 0.38319 | 0 | 0 | 0 | 0
62 | Pigging Program T108 Newport | 258v | 1 | 1e-06 |  | 0.47386 | 0 | 0 | 0 | 0
63 | Pigging Program Inner Ring Main | 258w | 1 | 1e-06 |  | 0 | 0 | 0.0035136 | 0 | 0
64 | Pigging Program T1 Morwell - Dandenong Pigging and Repair Program | 258x | 1 | 1e-06 |  | 1.9873 | 1.1124 | 0 | 0 | 0
65 | Pig Trap Installation James Street to Laverton Pipeline (253) | 259a | 1 | 1e-06 |  | 0 | 1.8948 | 0.20785 | 0 | 0
66 | Pig Trap Installation Tyers to Maryvale Pipeline (67) | 259d | 1 | 1e-06 |  | 0.58987 | 0.078499 | 0 | 0 | 0
67 | Liquid Management - Brooklyn | 260a | 1 | 1e-06 |  | 0 | 0 | 0 | 0 | 0.15701
68 | Liquid Management - Pakenham | 260b | 1 | 1e-06 |  | 0 | 0 | 0 | 0.15701 | 0
69 | RTU replacement | 262 | 1 | 1e-06 |  | 0.14182 | 0.14182 | 0.14182 | 0.14182 | 0.14182
70 | Pipe Support replacement | 263 | 1 | 1e-06 |  | 0.16481 | 0.16481 | 0.16481 | 0.16481 | 0.16481
71 | HMI upgrade to CLEAR SCADA at BCS, SCS and WCS & CG, Longford | 264 | 1 | 1e-06 |  | 0.060928 | 0.060928 | 0.060928 | 0.060928 | 0.060928
72 | BCS Unit 12 Inlet Filter Replacement/Augmentation | 267 | 1 | 1e-06 |  | 0.63572 | 0 | 0 | 0 | 0
73 | Coogee decommissioning | 268 | 1 | 1e-06 |  | 0 | 0 | 0 | 0 | 0
74 | Compressor Type B Compliance | 271 | 1 | 1e-06 |  | 0.21672 | 0.21672 | 0.21672 | 0.21672 | 0.21672
75 | Dandenong LNG Isolation Valve Upgrade | 275 | 1 | 1e-06 |  | 0.64902 | 0 | 0 | 0 | 0
76 | Morwell-Dandenong Fatigue Crack Detection from High Loads | 276 | 1 | 1e-06 |  | 0.26083 | 0 | 0 | 0 | 0
77 | Unibolt Enclosure Replacement | 277 | 1 | 1e-06 |  | 0.044464 | 0.044464 | 0.044464 | 0.044464 | 0.044464
78 | WAN Upgrade (Satellite project) | 278 | 1 | 1e-06 |  | 0.94699 | 0.94699 | 0.94699 | 0.94699 | 0.94699
79 | Warragul Looping 6" (Southern Route) | Warragul 6" (Sth) | 1 | 1e-06 |  | 5.4 | 2 | 0 | 0 | 0
80 | Angelsea Pipeline (Western Route) | Anglesea | 1 | 1e-06 |  | 13.6205 | 12.272 | 0 | 0 | 0
81 | VNIE | VNIE | 1 | 1e-06 |  | 1.5831 | 0 | 0 | 0 | 0
82 | Wichelsea Bi Direction and Brooklyn Reconfiguration | WCS Bi-Dir and BCS reconfig | 1 | 1e-06 |  | 0.54 | 0 | 0 | 0 | 0
83 | WORM (50km x 20" Pipeline) | WORM (Pipeline) | 1 | 1e-06 |  | 15.9112 | 28.9971 | 48.8145 | 0 | 0
84 | WORM (C50 at Wollert) | WORM (C50) | 1 | 1e-06 |  | 7.0437 | 12.0923 | 6.1767 | 0 | 0
85 | WORM (PRS at Wollert) | WORM (PRS) | 1 | 1e-06 |  | 0 | 1.6417 | 1.9592 | 0 | 0
86 | Enterprise Content Management | APA | 1 | 1e-06 |  | 0 | 0 | 0 | 0 | 0
87 | Victoria CRE | APA | 1 | 1e-06 |  | 0 | 0 | 0 | 0 | 0
88 | APA Grid Energy Components Upgrade | APA | 1 | 1e-06 |  | 0 | 0 | 0 | 0 | 0
89 | APA Grid Extend Program | APA | 1 | 1e-06 |  | 2.5 | 0 | 0 | 0 | 0
90 | APA Grid Services Initiatives Program | APA | 1 | 1e-06 |  | 0 | 0 | 0 | 0 | 0
91 | Hyperion Upgrade to 11.1.2.4 | APA | 1 | 1e-06 |  | 0 | 0 | 0 | 0 | 0
92 | BI - Transmission Dashboard and Enterprise Pilot | APA | 1 | 1e-06 |  | 2 | 1.5 | 0 | 0 | 0
93 | HR Systems Refresh | APA | 1 | 1e-06 |  | 0 | 0 | 0 | 0 | 0
94 | Transmission EAM Data Management Tool | APA | 1 | 1e-06 |  | 0 | 0 | 0 | 0 | 0
95 | SharePoint Upgrade | APA | 1 | 1e-06 |  | 0.24378 | 0 | 0 | 0 | 0
96 | eForm Digitisation | APA | 1 | 1e-06 |  | 0 | 0 | 1.6076 | 4.1474 | 0
97 | Historian Upgrade - version 2012 to 2015 | APA | 1 | 1e-06 |  | 0 | 0 | 0 | 0 | 0
98 | Hazardous Area Platform | APA | 1 | 1e-06 |  | 1.5525 | 0 | 0 | 0 | 0
99 | PPM Refresh | APA | 1 | 1e-06 |  | 3 | 0 | 0 | 0 | 0
100 | BizTalk Upgrade FY2018 | APA | 1 | 1e-06 |  | 0 | 0.60485 | 0.67092 | 0 | 0
101 | Automated Testing Tool | APA | 1 | 1e-06 |  | 0.6322 | 0 | 0 | 0 | 0
102 | Code Management Software | APA | 1 | 1e-06 |  | 0.90593 | 0 | 0 | 0 | 0
103 | CRM Upgrade | APA | 1 | 1e-06 |  | 1.4082 | 0.059048 | 0 | 0 | 0
104 | X-Info Aware Version 2 | APA | 1 | 1e-06 |  | 0.43008 | 0 | 0 | 0 | 0
105 | Supplier Qualification and Compliance | APA | 1 | 1e-06 |  | 0.69785 | 0.18556 | 0 | 0 | 0
106 | Oracle eBS Upgrade to 12.2 | APA | 1 | 1e-06 |  | 0.26711 | 1.2762 | 0 | 0 | 0
107 | BizTalk System Upgrade 2020 | APA | 1 | 1e-06 |  | 0 | 0.60485 | 0.67092 | 0 | 0
108 | Applications Renewal | APA | 1 | 1e-06 |  | 6.9 | 8.62 | 6.9 | 8.62 | 6.9
109 | Infrastructure Renewal | APA | 1 | 1e-06 |  | 2.25 | 0.75 | 0.75 | 0.75 | 0
110 | Dandenong Relocation | APA | 1 | 1e-06 |  | 0 | 0 | 0 | 0 | 0
- | 0 | - | 1 | 1e-06 |  | 0 | 0 | 0 | 0 | 0
- | 0 | - | 1 | 1e-06 |  | 0 | 0 | 0 | 0 | 0
- | 0 | - | 1 | 1e-06 |  | 0 | 0 | 0 | 0 | 0
- | 0 | - | 1 | 1e-06 |  | 0 | 0 | 0 | 0 | 0
- | 0 | - | 1 | 1e-06 |  | 0 | 0 | 0 | 0 | 0
- | 0 | - | 1 | 1e-06 |  | 0 | 0 | 0 | 0 | 0
- | 0 | - | 1 | 1e-06 |  | 0 | 0 | 0 | 0 | 0
- | 0 | - | 1 | 1e-06 |  | 0 | 0 | 0 | 0 | 0
- | 0 | - | 1 | 1e-06 |  | 0 | 0 | 0 | 0 | 0
- | 0 | - | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
- | 0 | - | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
- | 0 | - | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
- | 0 | - | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
- | 0 | - | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
- | 0 | - | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
- | 0 | - | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
- | 0 | - | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
- | 0 | - | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
- | 0 | - | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
- | 0 | - | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
- | 0 | - | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
- | 0 | - | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
- | 0 | - | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
- | 0 | - | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
- | 0 | - | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
- | 0 | - | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
- | 0 | - | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
- | 0 | - | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
- | 0 | - | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
- | 0 | - | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
- | 0 | - | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
- | 0 | - | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
- | 0 | - | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
- | 0 | - | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
- | 0 | - | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
- | 0 | - | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
- | 0 | - | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
- | 0 | - | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
- | 0 | - | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
- | 0 | - | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
- | 0 | - | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
- | 0 | - | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
- | 0 | - | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
- | 0 | - | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
- | 0 | - | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
- | 0 | - | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
- | 0 | - | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
- | 0 | - | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
- | 0 | - | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
- | 0 | - | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
- | 0 | - | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
- | 0 | - | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
- | 0 | - | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
- | 0 | - | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
- | 0 | - | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
- | 0 | - | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
- | 0 | - | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
- | 0 | - | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
- | 0 | - | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
- | 0 | - | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
- | 0 | - | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
- | 0 | - | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
- | 0 | - | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
- | 0 | - | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
- | 0 | - | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
- | 0 | - | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
- | 0 | - | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
- | 0 | - | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
- | 0 | - | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
- | 0 | - | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
- | 0 | - | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
- | 0 | - | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
- | 0 | - | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
- | 0 | - | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
- | 0 | - | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
- | 0 | - | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
- | 0 | - | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
- | 0 | - | 0 | 0 |  | 0 | 0 | 0 | 0 | 0

## 5.2 Calc│VTS
| 5.2 Calc│VTS | Check picking up all projects | 0 |  | Check values | 0 | 0 | 0 | 0 | 0
Capex # | Project Name | Business case/ project code | Allocator Class | Allocator |  | 2018 | 2019 | 2020 | 2021 | 2022
1 | All CS buffer Air shutoff system for all compressors | 202 | VTS | 100% |  | 0.38173 | 0.19087 | 0 | 0 | 0
2 | WCS A Process Safety | 203 | VTS | 100% |  | 0 | 0 | 1.0455 | 0 | 0
3 | Brooklyn Compressor Station | 204 | VTS | 100% |  | 0 | 0 | 2.2974 | 2.2974 | 2.2974
4 | Compressor Station Vent Stack Upgrade (BCS, WCS, GCS, SCS) | 205 | VTS | 100% |  | 0 | 0.3304 | 0.3304 | 0.3304 | 0
5 | Longford Odorant Pump Power Gas Upgrade | 206 | VTS | 100% |  | 0.075569 | 0 | 0 | 0 | 0
6 | GCS compressor unit vent valves & actuators replacement | 207a | VTS | 100% |  | 0.13939 | 0 | 0 | 0 | 0
7 | GCS unit discharge and station manifold check valves replacement | 207b | VTS | 100% |  | 0 | 0 | 0.90195 | 0 | 0
8 | GCS Decomm & removal of turbine oil reservoir & auto fill system | 207c | VTS | 100% |  | 0 | 0.087972 | 0 | 0 | 0
9 | BCS Instrument Air reliability upgrade | 208 | VTS | 100% |  | 0.093783 | 0 | 0 | 0 | 0
10 | Compressor lagging and pipe coating replacement (expand to GCS, Springhurst/BCS12/WCS A/WCS B, Euroa) | 209 | VTS | 100% |  | 0.14492 | 0.14492 | 0.14492 | 0.14492 | 0.14492
11 | Storage shed-Dandenong, Wollert & Springhurst | 210 | Victoria | 92.63% |  | 0 | 0.60098 | 0.60098 | 0.60098 | 0
12 | Iona CS aftercooler augmentation | 211 | VTS | 100% |  | 0 | 0 | 0 | 1.6563 | 0
13 | Battery replacement | 212 | VTS | 100% |  | 0.070284 | 0.070284 | 0.070284 | 0.070284 | 0.070284
14 | Wollert CG Instrument Air Conversion | 216 | VTS | 100% |  | 0 | 0 | 0 | 0.50425 | 0
15 | Pit installation on LV03 bypass valves on T33 | 220 | VTS | 100% |  | 0 | 0 | 0.23086 | 0 | 0
16 | Dandenong water supply & fire main modification | 223 | Victoria | 92.63% |  | 0.3003 | 0 | 0 | 0 | 0
17 | Culcairn Injection Gas Quality equipment | 224 | VTS | 100% |  | 0.97396 | 0 | 0 | 0 | 0
18 | Positioner Replacement | 225 | VTS | 100% |  | 0.10149 | 0.10149 | 0.10149 | 0.10149 | 0.10149
19 | VTS Safety Management Study aerial photography | 227 | VTS | 100% |  | 0.16247 | 0.0027806 | 0 | 0 | 0
20 | BLP Safety Measures for High Consequence areas-(urban growth, fracture control) | 230b | VTS | 100% |  | 0 | 2.492 | 0 | 0 | 1.869
21 | WOP Safety Measures for High Consequence areas-(urban growth, fracture control) | 230c | VTS | 100% |  | 1.12 | 0 | 0 | 0 | 0
22 | ILP Safety Measures for High Consequence areas-(urban growth, fracture control) | 230e | VTS | 100% |  | 0.027001 | 0.028057 | 0 | 0 | 0
23 | Turbine Overhauls | 235 | VTS | 100% |  | 0 | 0 | 0 | 1.0046 | 3.5944
24 | Iona CS Automation replacement | 236 | VTS | 100% |  | 0 | 0 | 1.1734 | 0 | 0
25 | GCS Control Room and Unit Enclosure 1,2,3&4 Fire Suppression System | 237a | VTS | 100% |  | 0.26856 | 0 | 0 | 0 | 0
26 | BCS MCC Room Fire Suppression System | 237b | VTS | 100% |  | 0 | 0 | 0.26856 | 0 | 0
27 | Iona CS Control Room and Unit Enclosure Fire Suppression System | 237d | VTS | 100% |  | 0 | 0 | 0 | 0.26856 | 0
28 | Lara City Gate Control Hut Fire Suppression System | 237e | VTS | 100% |  | 0 | 0 | 0 | 0 | 0.082003
29 | BCS Control Room Fire Suppression System | 237f | VTS | 100% |  | 0 | 0 | 0 | 0 | 0.082003
30 | Emergency- BA escape sets | 239a | Victoria | 92.63% |  | 0.017678 | 0 | 0 | 0 | 0
31 | Emergency- Response Equipment | 239b | Victoria | 92.63% |  | 0.25781 | 0.25781 | 0.25781 | 0.25781 | 0.25781
32 | Emergency- Spark Proof tools | 239c | Victoria | 92.63% |  | 0.0018023 | 0.0018023 | 0.0018023 | 0.0018023 | 0.0018023
33 | Emergency - fully equipped caravan | 239d | Victoria | 92.63% |  | 0 | 0 | 0.099932 | 0 | 0
34 | Emergency diesel fuel storage | 239e | Victoria | 92.63% |  | 0 | 0 | 0 | 0.11404 | 0
35 | Vent stack for CL600 & 900 pipeline | 240 | VTS | 100% |  | 0.21034 | 0 | 0 | 0 | 0
36 | Remote CP/critical drainage bond monitoring | 241 | VTS | 100% |  | 0.57305 | 0.060457 | 0.060457 | 0.060457 | 0.060457
37 | BCG Un-regulated Bypass Upgrade | 242 | VTS | 100% |  | 0 | 0 | 0.34235 | 0 | 0
38 | Security - Physical | 243 | Victoria | 92.63% |  | 0.33833 | 0.33833 | 0.33833 | 0.33833 | 0.33833
39 | CP - Cathodic Protection Replacement | 244 | VTS | 100% |  | 0.23246 | 0.23246 | 0.23246 | 0.23246 | 0.23246
40 | Equipment - Gas Detectors | 245 | Victoria | 92.63% |  | 0 | 0 | 0.023158 | 0.023158 | 0
41 | Regulator Upgrade - Lara pneumatic control system upgrade | 247 | VTS | 100% |  | 0 | 0.61926 | 0 | 0 | 0
42 | Hazardous Area Rectification | 249 | VTS | 100% |  | 0.178 | 0.178 | 0.178 | 0.178 | 0.178
43 | Actuate MLV's in T1 areas | 250 | VTS | 100% |  | 0.95671 | 0.95671 | 0 | 0 | 0
44 | Asbestos removal and replacement | 251 | VTS | 100% |  | 0.07 | 0.07 | 0.07 | 0.07 | 0.07
45 | T33 non-piggable and encased sections (unknown technical solution) | 257 | VTS | 100% |  | 0.15176 | 0.15176 | 0.15176 | 0.15176 | 0
46 | Pigging Program T57 Ballan - Ballarat | 258a | VTS | 100% |  | 0.56477 | 0 | 0 | 0 | 0
47 | Pigging Program T62 Derrimut - Sunbury | 258b | VTS | 100% |  | 0.4258 | 0 | 0 | 0 | 0
48 | Pigging Program T61 Packenham - Wollert | 258c | VTS | 100% |  | 0 | 0.6499 | 0 | 0 | 0
49 | Pigging Program T16 Dandenong – West Melbourne | 258d | VTS | 100% |  | 0 | 0 | 0 | 1.3778 | 0
50 | Pigging Program T60 Longford -Dandenong | 258e | VTS | 100% |  | 0 | 0 | 0 | 0 | 2.3809
51 | Pigging Program T33 South Melbourne – Brooklyn | 258f | VTS | 100% |  | 0 | 0 | 0 | 1.0237 | 0
52 | Pigging Program T66-70 Mt Franklin -Kyneton - Bendigo | 258i | VTS | 100% |  | 0 | 0.58734 | 0 | 0 | 0
53 | Pigging Program T75 Wandong - Kyneton | 258k | VTS | 100% |  | 0 | 0.52102 | 0 | 0 | 0
54 | Pigging Program T24 Brooklyn - Corio | 258l | VTS | 100% |  | 0 | 0 | 0 | 1.3807 | 0
55 | Pigging Program T70 Ballan – Bendigo | 258m | VTS | 100% |  | 0 | 0 | 0.55598 | 0 | 0
56 | Pigging Program T60 Longford – Tyers | 258n | VTS | 100% |  | 0 | 0 | 0 | 0 | 0.7484
57 | Pigging Program T63 Tyers - Morwell | 258o | VTS | 100% |  | 0 | 0 | 0 | 0.61109 | 0
58 | Pigging Program T96 & T98 Chiltern- Rutherglen – Koonoomoo | 258p | VTS | 100% |  | 0 | 0 | 0 | 0 | 0.51055
59 | Pigging Program T118 Trugannina-Plumpton | 258q | VTS | 100% |  | 0 | 0 | 0 | 0 | 0.51233
60 | Pigging Program James Street to Laverton Pipeline (253) | 258s | VTS | 100% |  | 0 | 0.44778 | 0 | 0 | 0
61 | Pigging Program Tyres to Maryvale (67) | 258u | VTS | 100% |  | 0.38319 | 0 | 0 | 0 | 0
62 | Pigging Program T108 Newport | 258v | VTS | 100% |  | 0.47386 | 0 | 0 | 0 | 0
63 | Pigging Program Inner Ring Main | 258w | VTS | 100% |  | 0 | 0 | 0.0035136 | 0 | 0
64 | Pigging Program T1 Morwell - Dandenong Pigging and Repair Program | 258x | VTS | 100% |  | 1.9873 | 1.1124 | 0 | 0 | 0
65 | Pig Trap Installation James Street to Laverton Pipeline (253) | 259a | VTS | 100% |  | 0 | 1.8948 | 0.20785 | 0 | 0
66 | Pig Trap Installation Tyers to Maryvale Pipeline (67) | 259d | VTS | 100% |  | 0.58987 | 0.078499 | 0 | 0 | 0
67 | Liquid Management - Brooklyn | 260a | VTS | 100% |  | 0 | 0 | 0 | 0 | 0.15701
68 | Liquid Management - Pakenham | 260b | VTS | 100% |  | 0 | 0 | 0 | 0.15701 | 0
69 | RTU replacement | 262 | VTS | 100% |  | 0.14182 | 0.14182 | 0.14182 | 0.14182 | 0.14182
70 | Pipe Support replacement | 263 | VTS | 100% |  | 0.16481 | 0.16481 | 0.16481 | 0.16481 | 0.16481
71 | HMI upgrade to CLEAR SCADA at BCS, SCS and WCS & CG, Longford | 264 | VTS | 100% |  | 0.060928 | 0.060928 | 0.060928 | 0.060928 | 0.060928
72 | BCS Unit 12 Inlet Filter Replacement/Augmentation | 267 | VTS | 100% |  | 0.63572 | 0 | 0 | 0 | 0
73 | Coogee decommissioning | 268 | VTS | 100% |  | 0 | 0 | 0 | 0 | 0
74 | Compressor Type B Compliance | 271 | VTS | 100% |  | 0.21672 | 0.21672 | 0.21672 | 0.21672 | 0.21672
75 | Dandenong LNG Isolation Valve Upgrade | 275 | VTS | 100% |  | 0.64902 | 0 | 0 | 0 | 0
76 | Morwell-Dandenong Fatigue Crack Detection from High Loads | 276 | VTS | 100% |  | 0.26083 | 0 | 0 | 0 | 0
77 | Unibolt Enclosure Replacement | 277 | VTS | 100% |  | 0.044464 | 0.044464 | 0.044464 | 0.044464 | 0.044464
78 | WAN Upgrade (Satellite project) | 278 | VTS | 100% |  | 0.94699 | 0.94699 | 0.94699 | 0.94699 | 0.94699
79 | Warragul Looping 6" (Southern Route) | Warragul 6" (Sth) | VTS | 100% |  | 5.4 | 2 | 0 | 0 | 0
80 | Angelsea Pipeline (Western Route) | Anglesea | VTS | 100% |  | 13.6205 | 12.272 | 0 | 0 | 0
81 | VNIE | VNIE | VTS | 100% |  | 1.5831 | 0 | 0 | 0 | 0
82 | Wichelsea Bi Direction and Brooklyn Reconfiguration | WCS Bi-Dir and BCS reconfig | VTS | 100% |  | 0.54 | 0 | 0 | 0 | 0
83 | WORM (50km x 20" Pipeline) | WORM (Pipeline) | VTS | 100% |  | 15.9112 | 28.9971 | 48.8145 | 0 | 0
84 | WORM (C50 at Wollert) | WORM (C50) | VTS | 100% |  | 7.0437 | 12.0923 | 6.1767 | 0 | 0
85 | WORM (PRS at Wollert) | WORM (PRS) | VTS | 100% |  | 0 | 1.6417 | 1.9592 | 0 | 0
86 | Enterprise Content Management | APA | APA | 10.45% |  | 0 | 0 | 0 | 0 | 0
87 | Victoria CRE | APA | APA | 10.45% |  | 0 | 0 | 0 | 0 | 0
88 | APA Grid Energy Components Upgrade | APA | APA | 10.45% |  | 0 | 0 | 0 | 0 | 0
89 | APA Grid Extend Program | APA | APA | 10.45% |  | 0.26122 | 0 | 0 | 0 | 0
90 | APA Grid Services Initiatives Program | APA | APA | 10.45% |  | 0 | 0 | 0 | 0 | 0
91 | Hyperion Upgrade to 11.1.2.4 | APA | APA | 10.45% |  | 0 | 0 | 0 | 0 | 0
92 | BI - Transmission Dashboard and Enterprise Pilot | APA | APA | 10.45% |  | 0.20898 | 0.15673 | 0 | 0 | 0
93 | HR Systems Refresh | APA | APA | 10.45% |  | 0 | 0 | 0 | 0 | 0
94 | Transmission EAM Data Management Tool | APA | APA | 10.45% |  | 0 | 0 | 0 | 0 | 0
95 | SharePoint Upgrade | APA | APA | 10.45% |  | 0.025472 | 0 | 0 | 0 | 0
96 | eForm Digitisation | APA | APA | 10.45% |  | 0 | 0 | 0.16798 | 0.43336 | 0
97 | Historian Upgrade - version 2012 to 2015 | APA | APA | 10.45% |  | 0 | 0 | 0 | 0 | 0
98 | Hazardous Area Platform | APA | APA | 10.45% |  | 0.16222 | 0 | 0 | 0 | 0
99 | PPM Refresh | APA | APA | 10.45% |  | 0.31347 | 0 | 0 | 0 | 0
100 | BizTalk Upgrade FY2018 | APA | APA | 10.45% |  | 0 | 0.0632 | 0.070104 | 0 | 0
101 | Automated Testing Tool | APA | APA | 10.45% |  | 0.066058 | 0 | 0 | 0 | 0
102 | Code Management Software | APA | APA | 10.45% |  | 0.09466 | 0 | 0 | 0 | 0
103 | CRM Upgrade | APA | APA | 10.45% |  | 0.14714 | 0.0061698 | 0 | 0 | 0
104 | X-Info Aware Version 2 | APA | APA | 10.45% |  | 0.044939 | 0 | 0 | 0 | 0
105 | Supplier Qualification and Compliance | APA | APA | 10.45% |  | 0.072917 | 0.019388 | 0 | 0 | 0
106 | Oracle eBS Upgrade to 12.2 | APA | APA | 10.45% |  | 0.02791 | 0.13335 | 0 | 0 | 0
107 | BizTalk System Upgrade 2020 | APA | APA | 10.45% |  | 0 | 0.0632 | 0.070104 | 0 | 0
108 | Applications Renewal | APA | APA | 10.45% |  | 0.72097 | 0.90069 | 0.72097 | 0.90069 | 0.72097
109 | Infrastructure Renewal | APA | APA | 10.45% |  | 0.2351 | 0.078367 | 0.078367 | 0.078367 | 0
110 | Dandenong Relocation | APA | APA | 10.45% |  | 0 | 0 | 0 | 0 | 0
- | 0 | - | - | 0% |  | 0 | 0 | 0 | 0 | 0
- | 0 | - | - | 0% |  | 0 | 0 | 0 | 0 | 0
- | 0 | - | - | 0% |  | 0 | 0 | 0 | 0 | 0
- | 0 | - | - | 0% |  | 0 | 0 | 0 | 0 | 0
- | 0 | - | - | 0% |  | 0 | 0 | 0 | 0 | 0
- | 0 | - | - | 0% |  | 0 | 0 | 0 | 0 | 0
- | 0 | - | - | 0% |  | 0 | 0 | 0 | 0 | 0
- | 0 | - | - | 0% |  | 0 | 0 | 0 | 0 | 0
- | 0 | - | - | 0% |  | 0 | 0 | 0 | 0 | 0
- | 0 | - | - | 0% |  | 0 | 0 | 0 | 0 | 0
- | 0 | - | - | 0% |  | 0 | 0 | 0 | 0 | 0
- | 0 | - | - | 0% |  | 0 | 0 | 0 | 0 | 0
- | 0 | - | - | 0% |  | 0 | 0 | 0 | 0 | 0
- | 0 | - | - | 0% |  | 0 | 0 | 0 | 0 | 0
- | 0 | - | - | 0% |  | 0 | 0 | 0 | 0 | 0
- | 0 | - | - | 0% |  | 0 | 0 | 0 | 0 | 0
- | 0 | - | - | 0% |  | 0 | 0 | 0 | 0 | 0
- | 0 | - | - | 0% |  | 0 | 0 | 0 | 0 | 0
- | 0 | - | - | 0% |  | 0 | 0 | 0 | 0 | 0
- | 0 | - | - | 0% |  | 0 | 0 | 0 | 0 | 0
- | 0 | - | - | 0% |  | 0 | 0 | 0 | 0 | 0
- | 0 | - | - | 0% |  | 0 | 0 | 0 | 0 | 0
- | 0 | - | - | 0% |  | 0 | 0 | 0 | 0 | 0
- | 0 | - | - | 0% |  | 0 | 0 | 0 | 0 | 0
- | 0 | - | - | 0% |  | 0 | 0 | 0 | 0 | 0
- | 0 | - | - | 0% |  | 0 | 0 | 0 | 0 | 0
- | 0 | - | - | 0% |  | 0 | 0 | 0 | 0 | 0
- | 0 | - | - | 0% |  | 0 | 0 | 0 | 0 | 0
- | 0 | - | - | 0% |  | 0 | 0 | 0 | 0 | 0
- | 0 | - | - | 0% |  | 0 | 0 | 0 | 0 | 0
- | 0 | - | - | 0% |  | 0 | 0 | 0 | 0 | 0
- | 0 | - | - | 0% |  | 0 | 0 | 0 | 0 | 0
- | 0 | - | - | 0% |  | 0 | 0 | 0 | 0 | 0
- | 0 | - | - | 0% |  | 0 | 0 | 0 | 0 | 0
- | 0 | - | - | 0% |  | 0 | 0 | 0 | 0 | 0
- | 0 | - | - | 0% |  | 0 | 0 | 0 | 0 | 0
- | 0 | - | - | 0% |  | 0 | 0 | 0 | 0 | 0
- | 0 | - | - | 0% |  | 0 | 0 | 0 | 0 | 0
- | 0 | - | - | 0% |  | 0 | 0 | 0 | 0 | 0
- | 0 | - | - | 0% |  | 0 | 0 | 0 | 0 | 0
- | 0 | - | - | 0% |  | 0 | 0 | 0 | 0 | 0
- | 0 | - | - | 0% |  | 0 | 0 | 0 | 0 | 0
- | 0 | - | - | 0% |  | 0 | 0 | 0 | 0 | 0
- | 0 | - | - | 0% |  | 0 | 0 | 0 | 0 | 0
- | 0 | - | - | 0% |  | 0 | 0 | 0 | 0 | 0
- | 0 | - | - | 0% |  | 0 | 0 | 0 | 0 | 0
- | 0 | - | - | 0% |  | 0 | 0 | 0 | 0 | 0
- | 0 | - | - | 0% |  | 0 | 0 | 0 | 0 | 0
- | 0 | - | - | 0% |  | 0 | 0 | 0 | 0 | 0
- | 0 | - | - | 0% |  | 0 | 0 | 0 | 0 | 0
- | 0 | - | - | 0% |  | 0 | 0 | 0 | 0 | 0
- | 0 | - | - | 0% |  | 0 | 0 | 0 | 0 | 0
- | 0 | - | - | 0% |  | 0 | 0 | 0 | 0 | 0
- | 0 | - | - | 0% |  | 0 | 0 | 0 | 0 | 0
- | 0 | - | - | 0% |  | 0 | 0 | 0 | 0 | 0
- | 0 | - | - | 0% |  | 0 | 0 | 0 | 0 | 0
- | 0 | - | - | 0% |  | 0 | 0 | 0 | 0 | 0
- | 0 | - | - | 0% |  | 0 | 0 | 0 | 0 | 0
- | 0 | - | - | 0% |  | 0 | 0 | 0 | 0 | 0
- | 0 | - | - | 0% |  | 0 | 0 | 0 | 0 | 0
- | 0 | - | - | 0% |  | 0 | 0 | 0 | 0 | 0
- | 0 | - | - | 0% |  | 0 | 0 | 0 | 0 | 0
- | 0 | - | - | 0% |  | 0 | 0 | 0 | 0 | 0
- | 0 | - | - | 0% |  | 0 | 0 | 0 | 0 | 0
- | 0 | - | - | 0% |  | 0 | 0 | 0 | 0 | 0
- | 0 | - | - | 0% |  | 0 | 0 | 0 | 0 | 0
- | 0 | - | - | 0% |  | 0 | 0 | 0 | 0 | 0
- | 0 | - | - | 0% |  | 0 | 0 | 0 | 0 | 0
- | 0 | - | - | 0% |  | 0 | 0 | 0 | 0 | 0
- | 0 | - | - | 0% |  | 0 | 0 | 0 | 0 | 0
- | 0 | - | - | 0% |  | 0 | 0 | 0 | 0 | 0
- | 0 | - | - | 0% |  | 0 | 0 | 0 | 0 | 0
- | 0 | - | - | 0% |  | 0 | 0 | 0 | 0 | 0
- | 0 | - | - | 0% |  | 0 | 0 | 0 | 0 | 0
- | 0 | - | - | 0% |  | 0 | 0 | 0 | 0 | 0
- | 0 | - | - | 0% |  | 0 | 0 | 0 | 0 | 0
- | 0 | - | - | 0% |  | 0 | 0 | 0 | 0 | 0
- | 0 | - | - | 0% |  | 0 | 0 | 0 | 0 | 0

## 5.3 Calc│Forecast $2017
| 5.3 Calc│Forecast $2017 | Check picking up projects | 0 |  | Check values | 0 | 0 | 0 | 0 | 0
Capex # | Project Name | Business case/ project code | Input currency | conversion |  | 2018 | 2019 | 2020 | 2021 | 2022
1 | All CS buffer Air shutoff system for all compressors | 202 | 2016 | 1.02 |  | 0.38937 | 0.19468 | 0 | 0 | 0
2 | WCS A Process Safety | 203 | 2016 | 1.02 |  | 0 | 0 | 1.0664 | 0 | 0
3 | Brooklyn Compressor Station | 204 | 2016 | 1.02 |  | 0 | 0 | 2.3433 | 2.3433 | 2.3433
4 | Compressor Station Vent Stack Upgrade (BCS, WCS, GCS, SCS) | 205 | 2016 | 1.02 |  | 0 | 0.33701 | 0.33701 | 0.33701 | 0
5 | Longford Odorant Pump Power Gas Upgrade | 206 | 2016 | 1.02 |  | 0.077081 | 0 | 0 | 0 | 0
6 | GCS compressor unit vent valves & actuators replacement | 207a | 2016 | 1.02 |  | 0.14218 | 0 | 0 | 0 | 0
7 | GCS unit discharge and station manifold check valves replacement | 207b | 2016 | 1.02 |  | 0 | 0 | 0.91999 | 0 | 0
8 | GCS Decomm & removal of turbine oil reservoir & auto fill system | 207c | 2016 | 1.02 |  | 0 | 0.089731 | 0 | 0 | 0
9 | BCS Instrument Air reliability upgrade | 208 | 2016 | 1.02 |  | 0.095659 | 0 | 0 | 0 | 0
10 | Compressor lagging and pipe coating replacement (expand to GCS, Springhurst/BCS12/WCS A/WCS B, Euroa) | 209 | 2016 | 1.02 |  | 0.14782 | 0.14782 | 0.14782 | 0.14782 | 0.14782
11 | Storage shed-Dandenong, Wollert & Springhurst | 210 | 2016 | 1.02 |  | 0 | 0.613 | 0.613 | 0.613 | 0
12 | Iona CS aftercooler augmentation | 211 | 2016 | 1.02 |  | 0 | 0 | 0 | 1.6895 | 0
13 | Battery replacement | 212 | 2016 | 1.02 |  | 0.07169 | 0.07169 | 0.07169 | 0.07169 | 0.07169
14 | Wollert CG Instrument Air Conversion | 216 | 2016 | 1.02 |  | 0 | 0 | 0 | 0.51433 | 0
15 | Pit installation on LV03 bypass valves on T33 | 220 | 2016 | 1.02 |  | 0 | 0 | 0.23548 | 0 | 0
16 | Dandenong water supply & fire main modification | 223 | 2016 | 1.02 |  | 0.30631 | 0 | 0 | 0 | 0
17 | Culcairn Injection Gas Quality equipment | 224 | 2016 | 1.02 |  | 0.99344 | 0 | 0 | 0 | 0
18 | Positioner Replacement | 225 | 2016 | 1.02 |  | 0.10352 | 0.10352 | 0.10352 | 0.10352 | 0.10352
19 | VTS Safety Management Study aerial photography | 227 | 2016 | 1.02 |  | 0.16572 | 0.0028362 | 0 | 0 | 0
20 | BLP Safety Measures for High Consequence areas-(urban growth, fracture control) | 230b | 2016 | 1.02 |  | 0 | 2.5418 | 0 | 0 | 1.9064
21 | WOP Safety Measures for High Consequence areas-(urban growth, fracture control) | 230c | 2016 | 1.02 |  | 1.1424 | 0 | 0 | 0 | 0
22 | ILP Safety Measures for High Consequence areas-(urban growth, fracture control) | 230e | 2016 | 1.02 |  | 0.027541 | 0.028618 | 0 | 0 | 0
23 | Turbine Overhauls | 235 | 2016 | 1.02 |  | 0 | 0 | 0 | 1.0247 | 3.6663
24 | Iona CS Automation replacement | 236 | 2016 | 1.02 |  | 0 | 0 | 1.1969 | 0 | 0
25 | GCS Control Room and Unit Enclosure 1,2,3&4 Fire Suppression System | 237a | 2016 | 1.02 |  | 0.27393 | 0 | 0 | 0 | 0
26 | BCS MCC Room Fire Suppression System | 237b | 2016 | 1.02 |  | 0 | 0 | 0.27393 | 0 | 0
27 | Iona CS Control Room and Unit Enclosure Fire Suppression System | 237d | 2016 | 1.02 |  | 0 | 0 | 0 | 0.27393 | 0
28 | Lara City Gate Control Hut Fire Suppression System | 237e | 2016 | 1.02 |  | 0 | 0 | 0 | 0 | 0.083643
29 | BCS Control Room Fire Suppression System | 237f | 2016 | 1.02 |  | 0 | 0 | 0 | 0 | 0.083643
30 | Emergency- BA escape sets | 239a | 2016 | 1.02 |  | 0.018031 | 0 | 0 | 0 | 0
31 | Emergency- Response Equipment | 239b | 2016 | 1.02 |  | 0.26296 | 0.26296 | 0.26296 | 0.26296 | 0.26296
32 | Emergency- Spark Proof tools | 239c | 2016 | 1.02 |  | 0.0018383 | 0.0018383 | 0.0018383 | 0.0018383 | 0.0018383
33 | Emergency - fully equipped caravan | 239d | 2016 | 1.02 |  | 0 | 0 | 0.10193 | 0 | 0
34 | Emergency diesel fuel storage | 239e | 2016 | 1.02 |  | 0 | 0 | 0 | 0.11632 | 0
35 | Vent stack for CL600 & 900 pipeline | 240 | 2016 | 1.02 |  | 0.21455 | 0 | 0 | 0 | 0
36 | Remote CP/critical drainage bond monitoring | 241 | 2016 | 1.02 |  | 0.58451 | 0.061666 | 0.061666 | 0.061666 | 0.061666
37 | BCG Un-regulated Bypass Upgrade | 242 | 2016 | 1.02 |  | 0 | 0 | 0.34919 | 0 | 0
38 | Security - Physical | 243 | 2016 | 1.02 |  | 0.3451 | 0.3451 | 0.3451 | 0.3451 | 0.3451
39 | CP - Cathodic Protection Replacement | 244 | 2016 | 1.02 |  | 0.23711 | 0.23711 | 0.23711 | 0.23711 | 0.23711
40 | Equipment - Gas Detectors | 245 | 2016 | 1.02 |  | 0 | 0 | 0.023622 | 0.023622 | 0
41 | Regulator Upgrade - Lara pneumatic control system upgrade | 247 | 2016 | 1.02 |  | 0 | 0.63164 | 0 | 0 | 0
42 | Hazardous Area Rectification | 249 | 2016 | 1.02 |  | 0.18156 | 0.18156 | 0.18156 | 0.18156 | 0.18156
43 | Actuate MLV's in T1 areas | 250 | 2016 | 1.02 |  | 0.97584 | 0.97584 | 0 | 0 | 0
44 | Asbestos removal and replacement | 251 | 2016 | 1.02 |  | 0.0714 | 0.0714 | 0.0714 | 0.0714 | 0.0714
45 | T33 non-piggable and encased sections (unknown technical solution) | 257 | 2016 | 1.02 |  | 0.15479 | 0.15479 | 0.15479 | 0.15479 | 0
46 | Pigging Program T57 Ballan - Ballarat | 258a | 2016 | 1.02 |  | 0.57606 | 0 | 0 | 0 | 0
47 | Pigging Program T62 Derrimut - Sunbury | 258b | 2016 | 1.02 |  | 0.43432 | 0 | 0 | 0 | 0
48 | Pigging Program T61 Packenham - Wollert | 258c | 2016 | 1.02 |  | 0 | 0.66289 | 0 | 0 | 0
49 | Pigging Program T16 Dandenong – West Melbourne | 258d | 2016 | 1.02 |  | 0 | 0 | 0 | 1.4053 | 0
50 | Pigging Program T60 Longford -Dandenong | 258e | 2016 | 1.02 |  | 0 | 0 | 0 | 0 | 2.4285
51 | Pigging Program T33 South Melbourne – Brooklyn | 258f | 2016 | 1.02 |  | 0 | 0 | 0 | 1.0441 | 0
52 | Pigging Program T66-70 Mt Franklin -Kyneton - Bendigo | 258i | 2016 | 1.02 |  | 0 | 0.59908 | 0 | 0 | 0
53 | Pigging Program T75 Wandong - Kyneton | 258k | 2016 | 1.02 |  | 0 | 0.53144 | 0 | 0 | 0
54 | Pigging Program T24 Brooklyn - Corio | 258l | 2016 | 1.02 |  | 0 | 0 | 0 | 1.4083 | 0
55 | Pigging Program T70 Ballan – Bendigo | 258m | 2016 | 1.02 |  | 0 | 0 | 0.5671 | 0 | 0
56 | Pigging Program T60 Longford – Tyers | 258n | 2016 | 1.02 |  | 0 | 0 | 0 | 0 | 0.76337
57 | Pigging Program T63 Tyers - Morwell | 258o | 2016 | 1.02 |  | 0 | 0 | 0 | 0.62331 | 0
58 | Pigging Program T96 & T98 Chiltern- Rutherglen – Koonoomoo | 258p | 2016 | 1.02 |  | 0 | 0 | 0 | 0 | 0.52076
59 | Pigging Program T118 Trugannina-Plumpton | 258q | 2016 | 1.02 |  | 0 | 0 | 0 | 0 | 0.52257
60 | Pigging Program James Street to Laverton Pipeline (253) | 258s | 2016 | 1.02 |  | 0 | 0.45673 | 0 | 0 | 0
61 | Pigging Program Tyres to Maryvale (67) | 258u | 2016 | 1.02 |  | 0.39085 | 0 | 0 | 0 | 0
62 | Pigging Program T108 Newport | 258v | 2016 | 1.02 |  | 0.48334 | 0 | 0 | 0 | 0
63 | Pigging Program Inner Ring Main | 258w | 2016 | 1.02 |  | 0 | 0 | 0.0035839 | 0 | 0
64 | Pigging Program T1 Morwell - Dandenong Pigging and Repair Program | 258x | 2016 | 1.02 |  | 2.027 | 1.1346 | 0 | 0 | 0
65 | Pig Trap Installation James Street to Laverton Pipeline (253) | 259a | 2016 | 1.02 |  | 0 | 1.9327 | 0.21201 | 0 | 0
66 | Pig Trap Installation Tyers to Maryvale Pipeline (67) | 259d | 2016 | 1.02 |  | 0.60167 | 0.080069 | 0 | 0 | 0
67 | Liquid Management - Brooklyn | 260a | 2016 | 1.02 |  | 0 | 0 | 0 | 0 | 0.16015
68 | Liquid Management - Pakenham | 260b | 2016 | 1.02 |  | 0 | 0 | 0 | 0.16015 | 0
69 | RTU replacement | 262 | 2016 | 1.02 |  | 0.14465 | 0.14465 | 0.14465 | 0.14465 | 0.14465
70 | Pipe Support replacement | 263 | 2016 | 1.02 |  | 0.16811 | 0.16811 | 0.16811 | 0.16811 | 0.16811
71 | HMI upgrade to CLEAR SCADA at BCS, SCS and WCS & CG, Longford | 264 | 2016 | 1.02 |  | 0.062147 | 0.062147 | 0.062147 | 0.062147 | 0.062147
72 | BCS Unit 12 Inlet Filter Replacement/Augmentation | 267 | 2016 | 1.02 |  | 0.64843 | 0 | 0 | 0 | 0
73 | Coogee decommissioning | 268 | 2016 | 1.02 |  | 0 | 0 | 0 | 0 | 0
74 | Compressor Type B Compliance | 271 | 2016 | 1.02 |  | 0.22105 | 0.22105 | 0.22105 | 0.22105 | 0.22105
75 | Dandenong LNG Isolation Valve Upgrade | 275 | 2016 | 1.02 |  | 0.662 | 0 | 0 | 0 | 0
76 | Morwell-Dandenong Fatigue Crack Detection from High Loads | 276 | 2016 | 1.02 |  | 0.26605 | 0 | 0 | 0 | 0
77 | Unibolt Enclosure Replacement | 277 | 2016 | 1.02 |  | 0.045353 | 0.045353 | 0.045353 | 0.045353 | 0.045353
78 | WAN Upgrade (Satellite project) | 278 | 2016 | 1.02 |  | 0.96593 | 0.96593 | 0.96593 | 0.96593 | 0.96593
79 | Warragul Looping 6" (Southern Route) | Warragul 6" (Sth) | 2016 | 1.02 |  | 5.508 | 2.04 | 0 | 0 | 0
80 | Angelsea Pipeline (Western Route) | Anglesea | 2016 | 1.02 |  | 13.8929 | 12.5174 | 0 | 0 | 0
81 | VNIE | VNIE | 2016 | 1.02 |  | 1.6148 | 0 | 0 | 0 | 0
82 | Wichelsea Bi Direction and Brooklyn Reconfiguration | WCS Bi-Dir and BCS reconfig | 2016 | 1.02 |  | 0.5508 | 0 | 0 | 0 | 0
83 | WORM (50km x 20" Pipeline) | WORM (Pipeline) | 2016 | 1.02 |  | 16.2294 | 29.5771 | 49.7908 | 0 | 0
84 | WORM (C50 at Wollert) | WORM (C50) | 2016 | 1.02 |  | 7.1845 | 12.3341 | 6.3003 | 0 | 0
85 | WORM (PRS at Wollert) | WORM (PRS) | 2016 | 1.02 |  | 0 | 1.6746 | 1.9984 | 0 | 0
86 | Enterprise Content Management | APA | 2016 | 1.02 |  | 0 | 0 | 0 | 0 | 0
87 | Victoria CRE | APA | 2016 | 1.02 |  | 0 | 0 | 0 | 0 | 0
88 | APA Grid Energy Components Upgrade | APA | 2016 | 1.02 |  | 0 | 0 | 0 | 0 | 0
89 | APA Grid Extend Program | APA | 2016 | 1.02 |  | 0.26645 | 0 | 0 | 0 | 0
90 | APA Grid Services Initiatives Program | APA | 2016 | 1.02 |  | 0 | 0 | 0 | 0 | 0
91 | Hyperion Upgrade to 11.1.2.4 | APA | 2016 | 1.02 |  | 0 | 0 | 0 | 0 | 0
92 | BI - Transmission Dashboard and Enterprise Pilot | APA | 2016 | 1.02 |  | 0.21316 | 0.15987 | 0 | 0 | 0
93 | HR Systems Refresh | APA | 2016 | 1.02 |  | 0 | 0 | 0 | 0 | 0
94 | Transmission EAM Data Management Tool | APA | 2016 | 1.02 |  | 0 | 0 | 0 | 0 | 0
95 | SharePoint Upgrade | APA | 2016 | 1.02 |  | 0.025982 | 0 | 0 | 0 | 0
96 | eForm Digitisation | APA | 2016 | 1.02 |  | 0 | 0 | 0.17134 | 0.44202 | 0
97 | Historian Upgrade - version 2012 to 2015 | APA | 2016 | 1.02 |  | 0 | 0 | 0 | 0 | 0
98 | Hazardous Area Platform | APA | 2016 | 1.02 |  | 0.16546 | 0 | 0 | 0 | 0
99 | PPM Refresh | APA | 2016 | 1.02 |  | 0.31974 | 0 | 0 | 0 | 0
100 | BizTalk Upgrade FY2018 | APA | 2016 | 1.02 |  | 0 | 0.064464 | 0.071506 | 0 | 0
101 | Automated Testing Tool | APA | 2016 | 1.02 |  | 0.06738 | 0 | 0 | 0 | 0
102 | Code Management Software | APA | 2016 | 1.02 |  | 0.096553 | 0 | 0 | 0 | 0
103 | CRM Upgrade | APA | 2016 | 1.02 |  | 0.15008 | 0.0062932 | 0 | 0 | 0
104 | X-Info Aware Version 2 | APA | 2016 | 1.02 |  | 0.045838 | 0 | 0 | 0 | 0
105 | Supplier Qualification and Compliance | APA | 2016 | 1.02 |  | 0.074376 | 0.019776 | 0 | 0 | 0
106 | Oracle eBS Upgrade to 12.2 | APA | 2016 | 1.02 |  | 0.028469 | 0.13602 | 0 | 0 | 0
107 | BizTalk System Upgrade 2020 | APA | 2016 | 1.02 |  | 0 | 0.064464 | 0.071506 | 0 | 0
108 | Applications Renewal | APA | 2016 | 1.02 |  | 0.73539 | 0.91871 | 0.73539 | 0.91871 | 0.73539
109 | Infrastructure Renewal | APA | 2016 | 1.02 |  | 0.2398 | 0.079934 | 0.079934 | 0.079934 | 0
110 | Dandenong Relocation | APA | 2016 | 1.02 |  | 0 | 0 | 0 | 0 | 0
- | 0 | - | 2016 | 1.02 |  | 0 | 0 | 0 | 0 | 0
- | 0 | - | 2016 | 1.02 |  | 0 | 0 | 0 | 0 | 0
- | 0 | - | 2016 | 1.02 |  | 0 | 0 | 0 | 0 | 0
- | 0 | - | 2016 | 1.02 |  | 0 | 0 | 0 | 0 | 0
- | 0 | - | 2016 | 1.02 |  | 0 | 0 | 0 | 0 | 0
- | 0 | - | 2016 | 1.02 |  | 0 | 0 | 0 | 0 | 0
- | 0 | - | 2016 | 1.02 |  | 0 | 0 | 0 | 0 | 0
- | 0 | - | 2016 | 1.02 |  | 0 | 0 | 0 | 0 | 0
- | 0 | - | 2016 | 1.02 |  | 0 | 0 | 0 | 0 | 0
- | 0 | - | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
- | 0 | - | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
- | 0 | - | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
- | 0 | - | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
- | 0 | - | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
- | 0 | - | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
- | 0 | - | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
- | 0 | - | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
- | 0 | - | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
- | 0 | - | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
- | 0 | - | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
- | 0 | - | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
- | 0 | - | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
- | 0 | - | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
- | 0 | - | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
- | 0 | - | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
- | 0 | - | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
- | 0 | - | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
- | 0 | - | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
- | 0 | - | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
- | 0 | - | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
- | 0 | - | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
- | 0 | - | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
- | 0 | - | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
- | 0 | - | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
- | 0 | - | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
- | 0 | - | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
- | 0 | - | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
- | 0 | - | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
- | 0 | - | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
- | 0 | - | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
- | 0 | - | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
- | 0 | - | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
- | 0 | - | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
- | 0 | - | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
- | 0 | - | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
- | 0 | - | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
- | 0 | - | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
- | 0 | - | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
- | 0 | - | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
- | 0 | - | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
- | 0 | - | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
- | 0 | - | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
- | 0 | - | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
- | 0 | - | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
- | 0 | - | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
- | 0 | - | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
- | 0 | - | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
- | 0 | - | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
- | 0 | - | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
- | 0 | - | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
- | 0 | - | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
- | 0 | - | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
- | 0 | - | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
- | 0 | - | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
- | 0 | - | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
- | 0 | - | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
- | 0 | - | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
- | 0 | - | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
- | 0 | - | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
- | 0 | - | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
- | 0 | - | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
- | 0 | - | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
- | 0 | - | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
- | 0 | - | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
- | 0 | - | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
- | 0 | - | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
- | 0 | - | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
- | 0 | - | 0 | 0 |  | 0 | 0 | 0 | 0 | 0

## 5.4 Calc│Escalators
5.4 Calc│Escalators
Capex # | Project Name | Labour | Contractor | Materials | Other | 2018 | 2019 | 2020 | 2021 | 2022
1 | All CS buffer Air shutoff system for all compressors | 23.66% | 1.964% | 74.37% | 0% | 1 | 1 | 1 | 1 | 1 | 100%
2 | WCS A Process Safety | 23.66% | 27.69% | 48.65% | 0% | 1 | 1 | 1 | 1 | 1 | 100%
3 | Brooklyn Compressor Station | 25.12% | 28.49% | 46.38% | 0% | 1 | 1 | 1 | 1 | 1 | 100%
4 | Compressor Station Vent Stack Upgrade (BCS, WCS, GCS, SCS) | 23.66% | 26.54% | 29.62% | 20.18% | 1 | 1 | 1 | 1 | 1 | 100%
5 | Longford Odorant Pump Power Gas Upgrade | 28.57% | 33.54% | 32.83% | 5.06% | 1 | 1 | 1 | 1 | 1 | 100%
6 | GCS compressor unit vent valves & actuators replacement | 23.66% | 28.73% | 47.61% | 0% | 1 | 1 | 1 | 1 | 1 | 100%
7 | GCS unit discharge and station manifold check valves replacement | 24.64% | 18.78% | 56.58% | 0% | 1 | 1 | 1 | 1 | 1 | 100%
8 | GCS Decomm & removal of turbine oil reservoir & auto fill system | 23.66% | 75.6% | 0.74% | 0% | 1 | 1 | 1 | 1 | 1 | 100%
9 | BCS Instrument Air reliability upgrade | 23.66% | 48.4% | 27.93% | 0% | 1 | 1 | 1 | 1 | 1 | 100%
10 | Compressor lagging and pipe coating replacement (expand to GCS, Springhurst/BCS12/WCS A/WCS B, Euroa) | 23.66% | 76.34% | 0% | 0% | 1 | 1 | 1 | 1 | 1 | 100%
11 | Storage shed-Dandenong, Wollert & Springhurst | 28.57% | 71.43% | 0% | 0% | 1 | 1 | 1 | 1 | 1 | 100%
12 | Iona CS aftercooler augmentation | 28.57% | 37.41% | 34.02% | 0% | 1 | 1 | 1 | 1 | 1 | 100%
13 | Battery replacement | 32.67% | 14.76% | 48.02% | 4.553% | 1 | 1 | 1 | 1 | 1 | 100%
14 | Wollert CG Instrument Air Conversion | 23.66% | 56.54% | 19.8% | 0% | 1 | 1 | 1 | 1 | 1 | 100%
15 | Pit installation on LV03 bypass valves on T33 | 28.57% | 58.06% | 13.37% | 0% | 1 | 1 | 1 | 1 | 1 | 100%
16 | Dandenong water supply & fire main modification | 28.57% | 71.43% | 0% | 0% | 1 | 1 | 1 | 1 | 1 | 100%
17 | Culcairn Injection Gas Quality equipment | 28.57% | 4.661% | 66.77% | 0% | 1 | 1 | 1 | 1 | 1 | 100%
18 | Positioner Replacement | 35.1% | 22.08% | 31.94% | 10.88% | 1 | 1 | 1 | 1 | 1 | 100%
19 | VTS Safety Management Study aerial photography | 21.88% | 0% | 0% | 78.12% | 1 | 1 | 1 | 1 | 1 | 100%
20 | BLP Safety Measures for High Consequence areas-(urban growth, fracture control) | 21.88% | 48.26% | 29.86% | 0% | 1 | 1 | 1 | 1 | 1 | 100%
21 | WOP Safety Measures for High Consequence areas-(urban growth, fracture control) | 21.88% | 48.11% | 30.02% | 0% | 1 | 1 | 1 | 1 | 1 | 100%
22 | ILP Safety Measures for High Consequence areas-(urban growth, fracture control) | 21.88% | 61.29% | 16.84% | 0% | 1 | 1 | 1 | 1 | 1 | 100%
23 | Turbine Overhauls | 23.66% | 76.34% | 0% | 0% | 1 | 1 | 1 | 1 | 1 | 100%
24 | Iona CS Automation replacement | 36.55% | 17.91% | 45.54% | 0% | 1 | 1 | 1 | 1 | 1 | 100%
25 | GCS Control Room and Unit Enclosure 1,2,3&4 Fire Suppression System | 23.66% | 76.34% | 0% | 0% | 1 | 1 | 1 | 1 | 1 | 100%
26 | BCS MCC Room Fire Suppression System | 23.66% | 76.34% | 0% | 0% | 1 | 1 | 1 | 1 | 1 | 100%
27 | Iona CS Control Room and Unit Enclosure Fire Suppression System | 23.66% | 76.34% | 0% | 0% | 1 | 1 | 1 | 1 | 1 | 100%
28 | Lara City Gate Control Hut Fire Suppression System | 28.57% | 71.43% | 0% | 0% | 1 | 1 | 1 | 1 | 1 | 100%
29 | BCS Control Room Fire Suppression System | 28.57% | 71.43% | 0% | 0% | 1 | 1 | 1 | 1 | 1 | 100%
30 | Emergency- BA escape sets | 21.88% | 0% | 78.12% | 0% | 1 | 1 | 1 | 1 | 1 | 100%
31 | Emergency- Response Equipment | 21.88% | 0.258% | 77.87% | 0% | 1 | 1 | 1 | 1 | 1 | 100%
32 | Emergency- Spark Proof tools | 58.88% | 0% | 41.12% | 0% | 1 | 1 | 1 | 1 | 1 | 100%
33 | Emergency - fully equipped caravan | 21.88% | 4.542% | 73.58% | 0% | 1 | 1 | 1 | 1 | 1 | 100%
34 | Emergency diesel fuel storage | 21.88% | 37% | 41.12% | 0% | 1 | 1 | 1 | 1 | 1 | 100%
35 | Vent stack for CL600 & 900 pipeline | 21.88% | 0% | 78.12% | 0% | 1 | 1 | 1 | 1 | 1 | 100%
36 | Remote CP/critical drainage bond monitoring | 33.41% | 0% | 64.43% | 2.163% | 1 | 1 | 1 | 1 | 1 | 100%
37 | BCG Un-regulated Bypass Upgrade | 23.42% | 66.99% | 9.593% | 0% | 1 | 1 | 1 | 1 | 1 | 100%
38 | Security - Physical | 37.33% | 62.67% | 0% | 0% | 1 | 1 | 1 | 1 | 1 | 100%
39 | CP - Cathodic Protection Replacement | 36.12% | 4.938% | 53.17% | 5.766% | 1 | 1 | 1 | 1 | 1 | 100%
40 | Equipment - Gas Detectors | 0% | 0% | 100% | 0% | 1 | 1 | 1 | 1 | 1 | 100%
41 | Regulator Upgrade - Lara pneumatic control system upgrade | 32.45% | 14.16% | 53.39% | 0% | 1 | 1 | 1 | 1 | 1 | 100%
42 | Hazardous Area Rectification | 11.24% | 50.56% | 38.2% | 0% | 1 | 1 | 1 | 1 | 1 | 100%
43 | Actuate MLV's in T1 areas | 21.88% | 10.89% | 62.21% | 5.017% | 1 | 1 | 1 | 1 | 1 | 100%
44 | Asbestos removal and replacement | 28.57% | 71.43% | 0% | 0% | 1 | 1 | 1 | 1 | 1 | 100%
45 | T33 non-piggable and encased sections (unknown technical solution) | 25.63% | 69.18% | 5.189% | 0% | 1 | 1 | 1 | 1 | 1 | 100%
46 | Pigging Program T57 Ballan - Ballarat | 22.3% | 74.14% | 3.564% | 0% | 1 | 1 | 1 | 1 | 1 | 100%
47 | Pigging Program T62 Derrimut - Sunbury | 22.44% | 75.1% | 2.461% | 0% | 1 | 1 | 1 | 1 | 1 | 100%
48 | Pigging Program T61 Packenham - Wollert | 22.24% | 70.48% | 7.276% | 0% | 1 | 1 | 1 | 1 | 1 | 100%
49 | Pigging Program T16 Dandenong – West Melbourne | 22.05% | 74.52% | 3.432% | 0% | 1 | 1 | 1 | 1 | 1 | 100%
50 | Pigging Program T60 Longford -Dandenong | 21.98% | 76.04% | 1.986% | 0% | 1 | 1 | 1 | 1 | 1 | 100%
51 | Pigging Program T33 South Melbourne – Brooklyn | 22.11% | 73.27% | 4.619% | 0% | 1 | 1 | 1 | 1 | 1 | 100%
52 | Pigging Program T66-70 Mt Franklin -Kyneton - Bendigo | 22.28% | 74.29% | 3.427% | 0% | 1 | 1 | 1 | 1 | 1 | 100%
53 | Pigging Program T75 Wandong - Kyneton | 22.34% | 73.8% | 3.863% | 0% | 1 | 1 | 1 | 1 | 1 | 100%
54 | Pigging Program T24 Brooklyn - Corio | 22.05% | 76.35% | 1.6% | 0% | 1 | 1 | 1 | 1 | 1 | 100%
55 | Pigging Program T70 Ballan – Bendigo | 22.31% | 75.81% | 1.885% | 0% | 1 | 1 | 1 | 1 | 1 | 100%
56 | Pigging Program T60 Longford – Tyers | 22.2% | 71.49% | 6.318% | 0% | 1 | 1 | 1 | 1 | 1 | 100%
57 | Pigging Program T63 Tyers - Morwell | 22.27% | 72.57% | 5.161% | 0% | 1 | 1 | 1 | 1 | 1 | 100%
58 | Pigging Program T96 & T98 Chiltern- Rutherglen – Koonoomoo | 22.35% | 74.99% | 2.669% | 0% | 1 | 1 | 1 | 1 | 1 | 100%
59 | Pigging Program T118 Trugannina-Plumpton | 22.34% | 71.5% | 6.156% | 0% | 1 | 1 | 1 | 1 | 1 | 100%
60 | Pigging Program James Street to Laverton Pipeline (253) | 22.41% | 72.66% | 4.933% | 0% | 1 | 1 | 1 | 1 | 1 | 100%
61 | Pigging Program Tyres to Maryvale (67) | 22.5% | 74.76% | 2.735% | 0% | 1 | 1 | 1 | 1 | 1 | 100%
62 | Pigging Program T108 Newport | 22.38% | 71.63% | 5.988% | 0% | 1 | 1 | 1 | 1 | 1 | 100%
63 | Pigging Program Inner Ring Main | 22.33% | 72.29% | 5.379% | 0% | 1 | 1 | 1 | 1 | 1 | 100%
64 | Pigging Program T1 Morwell - Dandenong Pigging and Repair Program | 21.88% | 75.82% | 2.305% | 0% | 1 | 1 | 1 | 1 | 1 | 100%
65 | Pig Trap Installation James Street to Laverton Pipeline (253) | 13.54% | 57.38% | 29.08% | 0% | 1 | 1 | 1 | 1 | 1 | 100%
66 | Pig Trap Installation Tyers to Maryvale Pipeline (67) | 13.55% | 59.01% | 27.44% | 0% | 1 | 1 | 1 | 1 | 1 | 100%
67 | Liquid Management - Brooklyn | 29.27% | 55.05% | 15.68% | 0% | 1 | 1 | 1 | 1 | 1 | 100%
68 | Liquid Management - Pakenham | 29.27% | 55.05% | 15.68% | 0% | 1 | 1 | 1 | 1 | 1 | 100%
69 | RTU replacement | 71.47% | 16.49% | 9.837% | 2.196% | 1 | 1 | 1 | 1 | 1 | 100%
70 | Pipe Support replacement | 28.57% | 71.43% | 0% | 0% | 1 | 1 | 1 | 1 | 1 | 100%
71 | HMI upgrade to CLEAR SCADA at BCS, SCS and WCS & CG, Longford | 58.51% | 1.313% | 35.45% | 4.727% | 1 | 1 | 1 | 1 | 1 | 100%
72 | BCS Unit 12 Inlet Filter Replacement/Augmentation | 23.66% | 39.83% | 36.51% | 0% | 1 | 1 | 1 | 1 | 1 | 100%
73 | Coogee decommissioning | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0%
74 | Compressor Type B Compliance | 33.45% | 30.5% | 36.05% | 0% | 1 | 1 | 1 | 1 | 1 | 100%
75 | Dandenong LNG Isolation Valve Upgrade | 29.4% | 40.97% | 29.64% | 0% | 1 | 1 | 1 | 1 | 1 | 100%
76 | Morwell-Dandenong Fatigue Crack Detection from High Loads | 25.56% | 67.79% | 6.653% | 0% | 1 | 1 | 1 | 1 | 1 | 100%
77 | Unibolt Enclosure Replacement | 28.57% | 60.18% | 11.25% | 0% | 1 | 1 | 1 | 1 | 1 | 100%
78 | WAN Upgrade (Satellite project) | 46.57% | 18.2% | 29.89% | 5.355% | 1 | 1 | 1 | 1 | 1 | 100%
79 | Warragul Looping 6" (Southern Route) | 34.54% | 12.78% | 52.68% | 0% | 1 | 1 | 1 | 1 | 1 | 100%
80 | Angelsea Pipeline (Western Route) | 49.2% | 0% | 30.91% | 19.88% | 1 | 1 | 1 | 1 | 1 | 100%
81 | VNIE | 0% | 100% | 0% | 0% | 1 | 1 | 1 | 1 | 1 | 100%
82 | Wichelsea Bi Direction and Brooklyn Reconfiguration | 55.56% | 11.11% | 33.33% | 0% | 1 | 1 | 1 | 1 | 1 | 100%
83 | WORM (50km x 20" Pipeline) | 10.58% | 0% | 33.69% | 55.73% | 1 | 1 | 1 | 1 | 1 | 100%
84 | WORM (C50 at Wollert) | 37.05% | 0% | 60.4% | 2.553% | 1 | 1 | 1 | 1 | 1 | 100%
85 | WORM (PRS at Wollert) | 42.22% | 0% | 54.63% | 3.152% | 1 | 1 | 1 | 1 | 1 | 100%
86 | Enterprise Content Management | 30% | 65% | 5% | 0% | 1 | 1 | 1 | 1 | 1 | 100%
87 | Victoria CRE | 30% | 65% | 5% | 0% | 1 | 1 | 1 | 1 | 1 | 100%
88 | APA Grid Energy Components Upgrade | 30% | 65% | 5% | 0% | 1 | 1 | 1 | 1 | 1 | 100%
89 | APA Grid Extend Program | 30% | 65% | 5% | 0% | 1 | 1 | 1 | 1 | 1 | 100%
90 | APA Grid Services Initiatives Program | 30% | 65% | 5% | 0% | 1 | 1 | 1 | 1 | 1 | 100%
91 | Hyperion Upgrade to 11.1.2.4 | 30% | 65% | 5% | 0% | 1 | 1 | 1 | 1 | 1 | 100%
92 | BI - Transmission Dashboard and Enterprise Pilot | 30% | 65% | 5% | 0% | 1 | 1 | 1 | 1 | 1 | 100%
93 | HR Systems Refresh | 30% | 65% | 5% | 0% | 1 | 1 | 1 | 1 | 1 | 100%
94 | Transmission EAM Data Management Tool | 30% | 65% | 5% | 0% | 1 | 1 | 1 | 1 | 1 | 100%
95 | SharePoint Upgrade | 30% | 65% | 5% | 0% | 1 | 1 | 1 | 1 | 1 | 100%
96 | eForm Digitisation | 30% | 65% | 5% | 0% | 1 | 1 | 1 | 1 | 1 | 100%
97 | Historian Upgrade - version 2012 to 2015 | 30% | 65% | 5% | 0% | 1 | 1 | 1 | 1 | 1 | 100%
98 | Hazardous Area Platform | 30% | 65% | 5% | 0% | 1 | 1 | 1 | 1 | 1 | 100%
99 | PPM Refresh | 30% | 65% | 5% | 0% | 1 | 1 | 1 | 1 | 1 | 100%
100 | BizTalk Upgrade FY2018 | 30% | 65% | 5% | 0% | 1 | 1 | 1 | 1 | 1 | 100%
101 | Automated Testing Tool | 30% | 65% | 5% | 0% | 1 | 1 | 1 | 1 | 1 | 100%
102 | Code Management Software | 30% | 65% | 5% | 0% | 1 | 1 | 1 | 1 | 1 | 100%
103 | CRM Upgrade | 30% | 65% | 5% | 0% | 1 | 1 | 1 | 1 | 1 | 100%
104 | X-Info Aware Version 2 | 30% | 65% | 5% | 0% | 1 | 1 | 1 | 1 | 1 | 100%
105 | Supplier Qualification and Compliance | 30% | 65% | 5% | 0% | 1 | 1 | 1 | 1 | 1 | 100%
106 | Oracle eBS Upgrade to 12.2 | 30% | 65% | 5% | 0% | 1 | 1 | 1 | 1 | 1 | 100%
107 | BizTalk System Upgrade 2020 | 30% | 65% | 5% | 0% | 1 | 1 | 1 | 1 | 1 | 100%
108 | Applications Renewal | 30% | 65% | 5% | 0% | 1 | 1 | 1 | 1 | 1 | 100%
109 | Infrastructure Renewal | 30% | 65% | 5% | 0% | 1 | 1 | 1 | 1 | 1 | 100%
110 | Dandenong Relocation | 50% | 0% | 50% | 0% | 1 | 1 | 1 | 1 | 1 | 100%
- | 0 | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0%
- | 0 | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0%
- | 0 | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0%
- | 0 | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0%
- | 0 | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0%
- | 0 | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0%
- | 0 | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0%
- | 0 | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0%
- | 0 | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0%
- | 0 | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0%
- | 0 | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0%
- | 0 | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0%
- | 0 | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0%
- | 0 | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0%
- | 0 | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0%
- | 0 | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0%
- | 0 | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0%
- | 0 | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0%
- | 0 | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0%
- | 0 | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0%
- | 0 | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0%
- | 0 | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0%
- | 0 | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0%
- | 0 | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0%
- | 0 | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0%
- | 0 | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0%
- | 0 | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0%
- | 0 | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0%
- | 0 | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0%
- | 0 | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0%
- | 0 | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0%
- | 0 | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0%
- | 0 | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0%
- | 0 | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0%
- | 0 | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0%
- | 0 | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0%
- | 0 | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0%
- | 0 | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0%
- | 0 | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0%
- | 0 | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0%
- | 0 | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0%
- | 0 | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0%
- | 0 | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0%
- | 0 | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0%
- | 0 | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0%
- | 0 | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0%
- | 0 | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0%
- | 0 | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0%
- | 0 | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0%
- | 0 | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0%
- | 0 | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0%
- | 0 | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0%
- | 0 | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0%
- | 0 | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0%
- | 0 | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0%
- | 0 | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0%
- | 0 | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0%
- | 0 | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0%
- | 0 | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0%
- | 0 | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0%
- | 0 | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0%
- | 0 | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0%
- | 0 | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0%
- | 0 | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0%
- | 0 | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0%
- | 0 | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0%
- | 0 | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0%
- | 0 | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0%
- | 0 | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0%
- | 0 | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0%
- | 0 | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0%
- | 0 | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0%
- | 0 | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0%
- | 0 | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0%
- | 0 | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0%
- | 0 | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0%
- | 0 | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0%
- | 0 | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0%

## 5.5 Calc│Escalated capex
[6 empty] | 62.0904 | 73.6522 | 70.7093 | 16.2642 | 16.306
| 5.5 Calc│Escalated capex | Check pickup all projects | 0 |  | Check values | 0 | 0 | 0 | 0 | 0
Capex # | Project Name | Project number | Asset class | Asset category |  | 2018 | 2019 | 2020 | 2021 | 2022 | Forecast total | Zones | Business Cases
1 | All CS buffer Air shutoff system for all compressors | 202 | Compressors | Replacement |  | 0.38937 | 0.19468 | 0 | 0 | 0 | 0.58405 |  | 202
2 | WCS A Process Safety | 203 | Compressors | Replacement |  | 0 | 0 | 1.0664 | 0 | 0 | 1.0664 |  | 203
3 | Brooklyn Compressor Station | 204 | Compressors | Replacement |  | 0 | 0 | 2.3433 | 2.3433 | 2.3433 | 7.0299 |  | 204
4 | Compressor Station Vent Stack Upgrade (BCS, WCS, GCS, SCS) | 205 | Compressors | Replacement |  | 0 | 0.33701 | 0.33701 | 0.33701 | 0 | 1.011 |  | 205
5 | Longford Odorant Pump Power Gas Upgrade | 206 | Odourant Plants | Replacement |  | 0.077081 | 0 | 0 | 0 | 0 | 0.077081 |  | 206
6 | GCS compressor unit vent valves & actuators replacement | 207a | Compressors | Replacement |  | 0.14218 | 0 | 0 | 0 | 0 | 0.14218 |  | 207
7 | GCS unit discharge and station manifold check valves replacement | 207b | Compressors | Replacement |  | 0 | 0 | 0.91999 | 0 | 0 | 0.91999 |  | 207
8 | GCS Decomm & removal of turbine oil reservoir & auto fill system | 207c | Compressors | Replacement |  | 0 | 0.089731 | 0 | 0 | 0 | 0.089731 |  | 207
9 | BCS Instrument Air reliability upgrade | 208 | Compressors | Replacement |  | 0.095659 | 0 | 0 | 0 | 0 | 0.095659 |  | 208
10 | Compressor lagging and pipe coating replacement (expand to GCS, Springhurst/BCS12/WCS A/WCS B, Euroa) | 209 | Compressors | Replacement |  | 0.14782 | 0.14782 | 0.14782 | 0.14782 | 0.14782 | 0.73909 |  | 209
11 | Storage shed-Dandenong, Wollert & Springhurst | 210 | Buildings | Non-System |  | 0 | 0.613 | 0.613 | 0.613 | 0 | 1.839 |  | 210
12 | Iona CS aftercooler augmentation | 211 | Compressors | Replacement |  | 0 | 0 | 0 | 1.6895 | 0 | 1.6895 |  | 211
13 | Battery replacement | 212 | Other | Replacement |  | 0.07169 | 0.07169 | 0.07169 | 0.07169 | 0.07169 | 0.35845 |  | 212
14 | Wollert CG Instrument Air Conversion | 216 | City Gates & Field Regs | Replacement |  | 0 | 0 | 0 | 0.51433 | 0 | 0.51433 |  | 216
15 | Pit installation on LV03 bypass valves on T33 | 220 | Pipelines | Replacement |  | 0 | 0 | 0.23548 | 0 | 0 | 0.23548 |  | 220
16 | Dandenong water supply & fire main modification | 223 | Buildings | Non-System |  | 0.30631 | 0 | 0 | 0 | 0 | 0.30631 |  | 223
17 | Culcairn Injection Gas Quality equipment | 224 | Gas Quality | Replacement |  | 0.99344 | 0 | 0 | 0 | 0 | 0.99344 |  | 224
18 | Positioner Replacement | 225 | Other | Replacement |  | 0.10352 | 0.10352 | 0.10352 | 0.10352 | 0.10352 | 0.51762 |  | 225
19 | VTS Safety Management Study aerial photography | 227 | Other | Replacement |  | 0.16572 | 0.0028362 | 0 | 0 | 0 | 0.16855 |  | 227
20 | BLP Safety Measures for High Consequence areas-(urban growth, fracture control) | 230b | Pipelines | Replacement |  | 0 | 2.5418 | 0 | 0 | 1.9064 | 4.4482 |  | 230
21 | WOP Safety Measures for High Consequence areas-(urban growth, fracture control) | 230c | Pipelines | Replacement |  | 1.1424 | 0 | 0 | 0 | 0 | 1.1424 |  | 230
22 | ILP Safety Measures for High Consequence areas-(urban growth, fracture control) | 230e | Pipelines | Replacement |  | 0.027541 | 0.028618 | 0 | 0 | 0 | 0.056159 |  | 230
23 | Turbine Overhauls | 235 | Compressors | Replacement |  | 0 | 0 | 0 | 1.0247 | 3.6663 | 4.691 |  | 235
24 | Iona CS Automation replacement | 236 | Compressors | Replacement |  | 0 | 0 | 1.1969 | 0 | 0 | 1.1969 |  | 236
25 | GCS Control Room and Unit Enclosure 1,2,3&4 Fire Suppression System | 237a | Compressors | Replacement |  | 0.27393 | 0 | 0 | 0 | 0 | 0.27393 |  | 237
26 | BCS MCC Room Fire Suppression System | 237b | Compressors | Replacement |  | 0 | 0 | 0.27393 | 0 | 0 | 0.27393 |  | 237
27 | Iona CS Control Room and Unit Enclosure Fire Suppression System | 237d | Compressors | Replacement |  | 0 | 0 | 0 | 0.27393 | 0 | 0.27393 |  | 237
28 | Lara City Gate Control Hut Fire Suppression System | 237e | City Gates & Field Regs | Replacement |  | 0 | 0 | 0 | 0 | 0.083643 | 0.083643 |  | 237
29 | BCS Control Room Fire Suppression System | 237f | Compressors | Non-System |  | 0 | 0 | 0 | 0 | 0.083643 | 0.083643 |  | 237
30 | Emergency- BA escape sets | 239a | Other | Replacement |  | 0.018031 | 0 | 0 | 0 | 0 | 0.018031 |  | 239
31 | Emergency- Response Equipment | 239b | Other | Replacement |  | 0.26296 | 0.26296 | 0.26296 | 0.26296 | 0.26296 | 1.3148 |  | 239
32 | Emergency- Spark Proof tools | 239c | Other | Replacement |  | 0.0018383 | 0.0018383 | 0.0018383 | 0.0018383 | 0.0018383 | 0.0091917 |  | 239
33 | Emergency - fully equipped caravan | 239d | Other | Replacement |  | 0 | 0 | 0.10193 | 0 | 0 | 0.10193 |  | 239
34 | Emergency diesel fuel storage | 239e | Other | Replacement |  | 0 | 0 | 0 | 0.11632 | 0 | 0.11632 |  | 239
35 | Vent stack for CL600 & 900 pipeline | 240 | Pipelines | Replacement |  | 0.21455 | 0 | 0 | 0 | 0 | 0.21455 |  | 240
36 | Remote CP/critical drainage bond monitoring | 241 | Other | Replacement |  | 0.58451 | 0.061666 | 0.061666 | 0.061666 | 0.061666 | 0.83118 |  | 241
37 | BCG Un-regulated Bypass Upgrade | 242 | City Gates & Field Regs | Replacement |  | 0 | 0 | 0.34919 | 0 | 0 | 0.34919 |  | 242
38 | Security - Physical | 243 | Buildings | Non-System |  | 0.3451 | 0.3451 | 0.3451 | 0.3451 | 0.3451 | 1.7255 |  | 243
39 | CP - Cathodic Protection Replacement | 244 | Other | Replacement |  | 0.23711 | 0.23711 | 0.23711 | 0.23711 | 0.23711 | 1.1856 |  | 244
40 | Equipment - Gas Detectors | 245 | Other | Non-System |  | 0 | 0 | 0.023622 | 0.023622 | 0 | 0.047243 |  | 245
41 | Regulator Upgrade - Lara pneumatic control system upgrade | 247 | City Gates & Field Regs | Replacement |  | 0 | 0.63164 | 0 | 0 | 0 | 0.63164 |  | 247
42 | Hazardous Area Rectification | 249 | Other | Replacement |  | 0.18156 | 0.18156 | 0.18156 | 0.18156 | 0.18156 | 0.9078 |  | 249
43 | Actuate MLV's in T1 areas | 250 | Pipelines | Replacement |  | 0.97584 | 0.97584 | 0 | 0 | 0 | 1.9517 |  | 250
44 | Asbestos removal and replacement | 251 | Other | Non-System |  | 0.0714 | 0.0714 | 0.0714 | 0.0714 | 0.0714 | 0.357 |  | 251
45 | T33 non-piggable and encased sections (unknown technical solution) | 257 | Other | Replacement |  | 0.15479 | 0.15479 | 0.15479 | 0.15479 | 0 | 0.61918 |  | 257
46 | Pigging Program T57 Ballan - Ballarat | 258a | Other | Replacement |  | 0.57606 | 0 | 0 | 0 | 0 | 0.57606 |  | 258
47 | Pigging Program T62 Derrimut - Sunbury | 258b | Other | Replacement |  | 0.43432 | 0 | 0 | 0 | 0 | 0.43432 |  | 258
48 | Pigging Program T61 Packenham - Wollert | 258c | Other | Replacement |  | 0 | 0.66289 | 0 | 0 | 0 | 0.66289 |  | 258
49 | Pigging Program T16 Dandenong – West Melbourne | 258d | Other | Replacement |  | 0 | 0 | 0 | 1.4053 | 0 | 1.4053 |  | 258
50 | Pigging Program T60 Longford -Dandenong | 258e | Other | Replacement |  | 0 | 0 | 0 | 0 | 2.4285 | 2.4285 |  | 258
51 | Pigging Program T33 South Melbourne – Brooklyn | 258f | Other | Replacement |  | 0 | 0 | 0 | 1.0441 | 0 | 1.0441 |  | 258
52 | Pigging Program T66-70 Mt Franklin -Kyneton - Bendigo | 258i | Other | Replacement |  | 0 | 0.59908 | 0 | 0 | 0 | 0.59908 |  | 258
53 | Pigging Program T75 Wandong - Kyneton | 258k | Other | Replacement |  | 0 | 0.53144 | 0 | 0 | 0 | 0.53144 |  | 258
54 | Pigging Program T24 Brooklyn - Corio | 258l | Other | Replacement |  | 0 | 0 | 0 | 1.4083 | 0 | 1.4083 |  | 258
55 | Pigging Program T70 Ballan – Bendigo | 258m | Other | Replacement |  | 0 | 0 | 0.5671 | 0 | 0 | 0.5671 |  | 258
56 | Pigging Program T60 Longford – Tyers | 258n | Other | Replacement |  | 0 | 0 | 0 | 0 | 0.76337 | 0.76337 |  | 258
57 | Pigging Program T63 Tyers - Morwell | 258o | Other | Replacement |  | 0 | 0 | 0 | 0.62331 | 0 | 0.62331 |  | 258
58 | Pigging Program T96 & T98 Chiltern- Rutherglen – Koonoomoo | 258p | Other | Replacement |  | 0 | 0 | 0 | 0 | 0.52076 | 0.52076 |  | 258
59 | Pigging Program T118 Trugannina-Plumpton | 258q | Other | Replacement |  | 0 | 0 | 0 | 0 | 0.52257 | 0.52257 |  | 258
60 | Pigging Program James Street to Laverton Pipeline (253) | 258s | Other | Replacement |  | 0 | 0.45673 | 0 | 0 | 0 | 0.45673 |  | 258
61 | Pigging Program Tyres to Maryvale (67) | 258u | Other | Replacement |  | 0.39085 | 0 | 0 | 0 | 0 | 0.39085 |  | 258
62 | Pigging Program T108 Newport | 258v | Other | Replacement |  | 0.48334 | 0 | 0 | 0 | 0 | 0.48334 |  | 258
63 | Pigging Program Inner Ring Main | 258w | Other | Replacement |  | 0 | 0 | 0.0035839 | 0 | 0 | 0.0035839 |  | 258
64 | Pigging Program T1 Morwell - Dandenong Pigging and Repair Program | 258x | Other | Replacement |  | 2.027 | 1.1346 | 0 | 0 | 0 | 3.1616 |  | 258
65 | Pig Trap Installation James Street to Laverton Pipeline (253) | 259a | Pipelines | Replacement |  | 0 | 1.9327 | 0.21201 | 0 | 0 | 2.1447 |  | 259
66 | Pig Trap Installation Tyers to Maryvale Pipeline (67) | 259d | Pipelines | Replacement |  | 0.60167 | 0.080069 | 0 | 0 | 0 | 0.68174 |  | 259
67 | Liquid Management - Brooklyn | 260a | City Gates & Field Regs | Replacement |  | 0 | 0 | 0 | 0 | 0.16015 | 0.16015 |  | 260
68 | Liquid Management - Pakenham | 260b | City Gates & Field Regs | Replacement |  | 0 | 0 | 0 | 0.16015 | 0 | 0.16015 |  | 260
69 | RTU replacement | 262 | Other | Replacement |  | 0.14465 | 0.14465 | 0.14465 | 0.14465 | 0.14465 | 0.72326 |  | 262
70 | Pipe Support replacement | 263 | Pipelines | Replacement |  | 0.16811 | 0.16811 | 0.16811 | 0.16811 | 0.16811 | 0.84054 |  | 263
71 | HMI upgrade to CLEAR SCADA at BCS, SCS and WCS & CG, Longford | 264 | Other | Non-System |  | 0.062147 | 0.062147 | 0.062147 | 0.062147 | 0.062147 | 0.31073 |  | 264
72 | BCS Unit 12 Inlet Filter Replacement/Augmentation | 267 | Compressors | Replacement |  | 0.64843 | 0 | 0 | 0 | 0 | 0.64843 |  | 267
73 | Coogee decommissioning | 268 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 268
74 | Compressor Type B Compliance | 271 | Compressors | Replacement |  | 0.22105 | 0.22105 | 0.22105 | 0.22105 | 0.22105 | 1.1053 |  | 271
75 | Dandenong LNG Isolation Valve Upgrade | 275 | Pipelines | Replacement |  | 0.662 | 0 | 0 | 0 | 0 | 0.662 |  | 275
76 | Morwell-Dandenong Fatigue Crack Detection from High Loads | 276 | Pipelines | Replacement |  | 0.26605 | 0 | 0 | 0 | 0 | 0.26605 |  | 276
77 | Unibolt Enclosure Replacement | 277 | Other | Replacement |  | 0.045353 | 0.045353 | 0.045353 | 0.045353 | 0.045353 | 0.22677 |  | 277
78 | WAN Upgrade (Satellite project) | 278 | Other | Non-System |  | 0.96593 | 0.96593 | 0.96593 | 0.96593 | 0.96593 | 4.8297 |  | 278
79 | Warragul Looping 6" (Southern Route) | Warragul 6" (Sth) | Pipelines | Augmentation |  | 5.508 | 2.04 | 0 | 0 | 0 | 7.548 | 1 Longford to Tyers (loop end) | War
80 | Angelsea Pipeline (Western Route) | Anglesea | Pipelines | Augmentation |  | 13.8929 | 12.5174 | 0 | 0 | 0 | 26.4103 | 3 Tyers to Morwell & Maryvale lateral | Ang
81 | VNIE | VNIE | Pipelines | Augmentation |  | 1.6148 | 0 | 0 | 0 | 0 | 1.6148 | 25 Chiltern Valley to Koonoomoo | VNI
82 | Wichelsea Bi Direction and Brooklyn Reconfiguration | WCS Bi-Dir and BCS reconfig | Compressors | Augmentation |  | 0.5508 | 0 | 0 | 0 | 0 | 0.5508 | 22 Deer Park to Sunbury | WCS
83 | WORM (50km x 20" Pipeline) | WORM (Pipeline) | Pipelines | Augmentation |  | 16.2294 | 29.5771 | 49.7908 | 0 | 0 | 95.5973 | 21 Wollert to Keon Park | WOR
84 | WORM (C50 at Wollert) | WORM (C50) | Compressors | Augmentation |  | 7.1845 | 12.3341 | 6.3003 | 0 | 0 | 25.8189 | 22 Wollert to Keon Park | WOR
85 | WORM (PRS at Wollert) | WORM (PRS) | City Gates & Field Regs | Augmentation |  | 0 | 1.6746 | 1.9984 | 0 | 0 | 3.673 | 23 Wollert to Keon Park | WOR
86 | Enterprise Content Management | APA | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | APA
87 | Victoria CRE | APA | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | APA
88 | APA Grid Energy Components Upgrade | APA | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | APA
89 | APA Grid Extend Program | APA | Other | Non-System |  | 0.26645 | 0 | 0 | 0 | 0 | 0.26645 |  | APA
90 | APA Grid Services Initiatives Program | APA | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | APA
91 | Hyperion Upgrade to 11.1.2.4 | APA | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | APA
92 | BI - Transmission Dashboard and Enterprise Pilot | APA | Other | Non-System |  | 0.21316 | 0.15987 | 0 | 0 | 0 | 0.37303 |  | APA
93 | HR Systems Refresh | APA | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | APA
94 | Transmission EAM Data Management Tool | APA | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | APA
95 | SharePoint Upgrade | APA | Other | Non-System |  | 0.025982 | 0 | 0 | 0 | 0 | 0.025982 |  | APA
96 | eForm Digitisation | APA | Other | Non-System |  | 0 | 0 | 0.17134 | 0.44202 | 0 | 0.61336 |  | APA
97 | Historian Upgrade - version 2012 to 2015 | APA | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | APA
98 | Hazardous Area Platform | APA | Other | Non-System |  | 0.16546 | 0 | 0 | 0 | 0 | 0.16546 |  | APA
99 | PPM Refresh | APA | Other | Non-System |  | 0.31974 | 0 | 0 | 0 | 0 | 0.31974 |  | APA
100 | BizTalk Upgrade FY2018 | APA | Other | Non-System |  | 0 | 0.064464 | 0.071506 | 0 | 0 | 0.13597 |  | APA
101 | Automated Testing Tool | APA | Other | Non-System |  | 0.06738 | 0 | 0 | 0 | 0 | 0.06738 |  | APA
102 | Code Management Software | APA | Other | Non-System |  | 0.096553 | 0 | 0 | 0 | 0 | 0.096553 |  | APA
103 | CRM Upgrade | APA | Other | Non-System |  | 0.15008 | 0.0062932 | 0 | 0 | 0 | 0.15638 |  | APA
104 | X-Info Aware Version 2 | APA | Other | Non-System |  | 0.045838 | 0 | 0 | 0 | 0 | 0.045838 |  | APA
105 | Supplier Qualification and Compliance | APA | Other | Non-System |  | 0.074376 | 0.019776 | 0 | 0 | 0 | 0.094152 |  | APA
106 | Oracle eBS Upgrade to 12.2 | APA | Other | Non-System |  | 0.028469 | 0.13602 | 0 | 0 | 0 | 0.16449 |  | APA
107 | BizTalk System Upgrade 2020 | APA | Other | Non-System |  | 0 | 0.064464 | 0.071506 | 0 | 0 | 0.13597 |  | APA
108 | Applications Renewal | APA | Other | Non-System |  | 0.73539 | 0.91871 | 0.73539 | 0.91871 | 0.73539 | 4.0436 |  | APA
109 | Infrastructure Renewal | APA | Other | Non-System |  | 0.2398 | 0.079934 | 0.079934 | 0.079934 | 0 | 0.4796 |  | APA
110 | Dandenong Relocation | APA | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | APA
- | 0 | - | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | -
- | 0 | - | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | -
- | 0 | - | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | -
- | 0 | - | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | -
- | 0 | - | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | -
- | 0 | - | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | -
- | 0 | - | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | -
- | 0 | - | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | -
- | 0 | - | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | -
- | 0 | - | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | -
- | 0 | - | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | -
- | 0 | - | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | -
- | 0 | - | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | -
- | 0 | - | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | -
- | 0 | - | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | -
- | 0 | - | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | -
- | 0 | - | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | -
- | 0 | - | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | -
- | 0 | - | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | -
- | 0 | - | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | -
- | 0 | - |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | -
- | 0 | - | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | -
- | 0 | - | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | -
- | 0 | - | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | -
- | 0 | - | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | -
- | 0 | - | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | -
- | 0 | - | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | -
- | 0 | - | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | -
- | 0 | - | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | -
- | 0 | - | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | -
- | 0 | - | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | -
- | 0 | - | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | -
- | 0 | - | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | -
- | 0 | - | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | -
- | 0 | - | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | -
- | 0 | - | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | -
- | 0 | - | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | -
- | 0 | - | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | -
- | 0 | - | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | -
- | 0 | - | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | -
- | 0 | - | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | -
- | 0 | - | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | -
- | 0 | - | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | -
- | 0 | - | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | -
- | 0 | - | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | -
- | 0 | - | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | -
- | 0 | - | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | -
- | 0 | - | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | -
- | 0 | - | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | -
- | 0 | - | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | -
- | 0 | - | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | -
- | 0 | - | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | -
- | 0 | - | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | -
- | 0 | - | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | -
- | 0 | - | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | -
- | 0 | - | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | -
- | 0 | - | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | -
- | 0 | - | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | -
- | 0 | - | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | -
- | 0 | - | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | -
- | 0 | - | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | -
- | 0 | - | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | -
- | 0 | - | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | -
- | 0 | - | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | -
- | 0 | - | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | -
- | 0 | - | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | -
- | 0 | - | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | -
- | 0 | - | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | -
- | 0 | - | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | -
- | 0 | - | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | -
- | 0 | - | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | -
- | 0 | - | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | -
- | 0 | - | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | -
- | 0 | - | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | -
- | 0 | - | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | -
- | 0 | - | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | -
- | 0 | - | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | -
- | 0 | - | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | -

## 5.6 Calc│As Commissioned
| 5.6 Calc│As Commissioned | Check pickup all projects | 0
Capex # | Project Name | Project number | Asset class | Asset category | Completion Year | 2018 | 2019 | 2020 | 2021 | 2022 | Forecast total
1 | All CS buffer Air shutoff system for all compressors | 202 | Compressors | Replacement | 2019 | 0 | 0.58405 | 0 | 0 | 0 | 0.58405
2 | WCS A Process Safety | 203 | Compressors | Replacement | 2020 | 0 | 0 | 1.0664 | 0 | 0 | 1.0664
3 | Brooklyn Compressor Station | 204 | Compressors | Replacement | 2018 | 7.0299 | 0 | 0 | 0 | 0 | 7.0299
4 | Compressor Station Vent Stack Upgrade (BCS, WCS, GCS, SCS) | 205 | Compressors | Replacement | 2021 | 0 | 0 | 0 | 1.011 | 0 | 1.011
5 | Longford Odorant Pump Power Gas Upgrade | 206 | Odourant Plants | Replacement | 2018 | 0.077081 | 0 | 0 | 0 | 0 | 0.077081
6 | GCS compressor unit vent valves & actuators replacement | 207a | Compressors | Replacement | 2018 | 0.14218 | 0 | 0 | 0 | 0 | 0.14218
7 | GCS unit discharge and station manifold check valves replacement | 207b | Compressors | Replacement | 2020 | 0 | 0 | 0.91999 | 0 | 0 | 0.91999
8 | GCS Decomm & removal of turbine oil reservoir & auto fill system | 207c | Compressors | Replacement | 2019 | 0 | 0.089731 | 0 | 0 | 0 | 0.089731
9 | BCS Instrument Air reliability upgrade | 208 | Compressors | Replacement | 2018 | 0.095659 | 0 | 0 | 0 | 0 | 0.095659
10 | Compressor lagging and pipe coating replacement (expand to GCS, Springhurst/BCS12/WCS A/WCS B, Euroa) | 209 | Compressors | Replacement | incurred | 0.14782 | 0.14782 | 0.14782 | 0.14782 | 0.14782 | 0.73909
11 | Storage shed-Dandenong, Wollert & Springhurst | 210 | Buildings | Non-System | 2021 | 0 | 0 | 0 | 1.839 | 0 | 1.839
12 | Iona CS aftercooler augmentation | 211 | Compressors | Replacement | 2021 | 0 | 0 | 0 | 1.6895 | 0 | 1.6895
13 | Battery replacement | 212 | Other | Replacement | incurred | 0.07169 | 0.07169 | 0.07169 | 0.07169 | 0.07169 | 0.35845
14 | Wollert CG Instrument Air Conversion | 216 | City Gates & Field Regs | Replacement | 2021 | 0 | 0 | 0 | 0.51433 | 0 | 0.51433
15 | Pit installation on LV03 bypass valves on T33 | 220 | Pipelines | Replacement | 2020 | 0 | 0 | 0.23548 | 0 | 0 | 0.23548
16 | Dandenong water supply & fire main modification | 223 | Buildings | Non-System | 2018 | 0.30631 | 0 | 0 | 0 | 0 | 0.30631
17 | Culcairn Injection Gas Quality equipment | 224 | Gas Quality | Replacement | 2018 | 0.99344 | 0 | 0 | 0 | 0 | 0.99344
18 | Positioner Replacement | 225 | Other | Replacement | incurred | 0.10352 | 0.10352 | 0.10352 | 0.10352 | 0.10352 | 0.51762
19 | VTS Safety Management Study aerial photography | 227 | Other | Replacement | 2019 | 0 | 0.16855 | 0 | 0 | 0 | 0.16855
20 | BLP Safety Measures for High Consequence areas-(urban growth, fracture control) | 230b | Pipelines | Replacement | 2019 | 0 | 4.4482 | 0 | 0 | 0 | 4.4482
21 | WOP Safety Measures for High Consequence areas-(urban growth, fracture control) | 230c | Pipelines | Replacement | 2019 | 0 | 1.1424 | 0 | 0 | 0 | 1.1424
22 | ILP Safety Measures for High Consequence areas-(urban growth, fracture control) | 230e | Pipelines | Replacement | 2019 | 0 | 0.056159 | 0 | 0 | 0 | 0.056159
23 | Turbine Overhauls | 235 | Compressors | Replacement | 2022 | 0 | 0 | 0 | 0 | 4.691 | 4.691
24 | Iona CS Automation replacement | 236 | Compressors | Replacement | 2020 | 0 | 0 | 1.1969 | 0 | 0 | 1.1969
25 | GCS Control Room and Unit Enclosure 1,2,3&4 Fire Suppression System | 237a | Compressors | Replacement | 2018 | 0.27393 | 0 | 0 | 0 | 0 | 0.27393
26 | BCS MCC Room Fire Suppression System | 237b | Compressors | Replacement | 2020 | 0 | 0 | 0.27393 | 0 | 0 | 0.27393
27 | Iona CS Control Room and Unit Enclosure Fire Suppression System | 237d | Compressors | Replacement | 2021 | 0 | 0 | 0 | 0.27393 | 0 | 0.27393
28 | Lara City Gate Control Hut Fire Suppression System | 237e | City Gates & Field Regs | Replacement | 2022 | 0 | 0 | 0 | 0 | 0.083643 | 0.083643
29 | BCS Control Room Fire Suppression System | 237f | Compressors | Non-System | 2022 | 0 | 0 | 0 | 0 | 0.083643 | 0.083643
30 | Emergency- BA escape sets | 239a | Other | Replacement | 2018 | 0.018031 | 0 | 0 | 0 | 0 | 0.018031
31 | Emergency- Response Equipment | 239b | Other | Replacement | incurred | 0.26296 | 0.26296 | 0.26296 | 0.26296 | 0.26296 | 1.3148
32 | Emergency- Spark Proof tools | 239c | Other | Replacement | incurred | 0.0018383 | 0.0018383 | 0.0018383 | 0.0018383 | 0.0018383 | 0.0091917
33 | Emergency - fully equipped caravan | 239d | Other | Replacement | 2020 | 0 | 0 | 0.10193 | 0 | 0 | 0.10193
34 | Emergency diesel fuel storage | 239e | Other | Replacement | 2021 | 0 | 0 | 0 | 0.11632 | 0 | 0.11632
35 | Vent stack for CL600 & 900 pipeline | 240 | Pipelines | Replacement | 2018 | 0.21455 | 0 | 0 | 0 | 0 | 0.21455
36 | Remote CP/critical drainage bond monitoring | 241 | Other | Replacement | incurred | 0.58451 | 0.061666 | 0.061666 | 0.061666 | 0.061666 | 0.83118
37 | BCG Un-regulated Bypass Upgrade | 242 | City Gates & Field Regs | Replacement | 2020 | 0 | 0 | 0.34919 | 0 | 0 | 0.34919
38 | Security - Physical | 243 | Buildings | Non-System | incurred | 0.3451 | 0.3451 | 0.3451 | 0.3451 | 0.3451 | 1.7255
39 | CP - Cathodic Protection Replacement | 244 | Other | Replacement | incurred | 0.23711 | 0.23711 | 0.23711 | 0.23711 | 0.23711 | 1.1856
40 | Equipment - Gas Detectors | 245 | Other | Non-System | 2021 | 0 | 0 | 0 | 0.047243 | 0 | 0.047243
41 | Regulator Upgrade - Lara pneumatic control system upgrade | 247 | City Gates & Field Regs | Replacement | 2019 | 0 | 0.63164 | 0 | 0 | 0 | 0.63164
42 | Hazardous Area Rectification | 249 | Other | Replacement | incurred | 0.18156 | 0.18156 | 0.18156 | 0.18156 | 0.18156 | 0.9078
43 | Actuate MLV's in T1 areas | 250 | Pipelines | Replacement | 2019 | 0 | 1.9517 | 0 | 0 | 0 | 1.9517
44 | Asbestos removal and replacement | 251 | Other | Non-System | incurred | 0.0714 | 0.0714 | 0.0714 | 0.0714 | 0.0714 | 0.357
45 | T33 non-piggable and encased sections (unknown technical solution) | 257 | Other | Replacement | incurred | 0.15479 | 0.15479 | 0.15479 | 0.15479 | 0 | 0.61918
46 | Pigging Program T57 Ballan - Ballarat | 258a | Other | Replacement | 2018 | 0.57606 | 0 | 0 | 0 | 0 | 0.57606
47 | Pigging Program T62 Derrimut - Sunbury | 258b | Other | Replacement | 2018 | 0.43432 | 0 | 0 | 0 | 0 | 0.43432
48 | Pigging Program T61 Packenham - Wollert | 258c | Other | Replacement | 2019 | 0 | 0.66289 | 0 | 0 | 0 | 0.66289
49 | Pigging Program T16 Dandenong – West Melbourne | 258d | Other | Replacement | 2021 | 0 | 0 | 0 | 1.4053 | 0 | 1.4053
50 | Pigging Program T60 Longford -Dandenong | 258e | Other | Replacement | 2022 | 0 | 0 | 0 | 0 | 2.4285 | 2.4285
51 | Pigging Program T33 South Melbourne – Brooklyn | 258f | Other | Replacement | 2021 | 0 | 0 | 0 | 1.0441 | 0 | 1.0441
52 | Pigging Program T66-70 Mt Franklin -Kyneton - Bendigo | 258i | Other | Replacement | 2019 | 0 | 0.59908 | 0 | 0 | 0 | 0.59908
53 | Pigging Program T75 Wandong - Kyneton | 258k | Other | Replacement | 2019 | 0 | 0.53144 | 0 | 0 | 0 | 0.53144
54 | Pigging Program T24 Brooklyn - Corio | 258l | Other | Replacement | 2021 | 0 | 0 | 0 | 1.4083 | 0 | 1.4083
55 | Pigging Program T70 Ballan – Bendigo | 258m | Other | Replacement | 2019 | 0 | 0.5671 | 0 | 0 | 0 | 0.5671
56 | Pigging Program T60 Longford – Tyers | 258n | Other | Replacement | 2022 | 0 | 0 | 0 | 0 | 0.76337 | 0.76337
57 | Pigging Program T63 Tyers - Morwell | 258o | Other | Replacement | 2021 | 0 | 0 | 0 | 0.62331 | 0 | 0.62331
58 | Pigging Program T96 & T98 Chiltern- Rutherglen – Koonoomoo | 258p | Other | Replacement | 2022 | 0 | 0 | 0 | 0 | 0.52076 | 0.52076
59 | Pigging Program T118 Trugannina-Plumpton | 258q | Other | Replacement | 2022 | 0 | 0 | 0 | 0 | 0.52257 | 0.52257
60 | Pigging Program James Street to Laverton Pipeline (253) | 258s | Other | Replacement | 2019 | 0 | 0.45673 | 0 | 0 | 0 | 0.45673
61 | Pigging Program Tyres to Maryvale (67) | 258u | Other | Replacement | 2018 | 0.39085 | 0 | 0 | 0 | 0 | 0.39085
62 | Pigging Program T108 Newport | 258v | Other | Replacement | 2018 | 0.48334 | 0 | 0 | 0 | 0 | 0.48334
63 | Pigging Program Inner Ring Main | 258w | Other | Replacement | 2020 | 0 | 0 | 0.0035839 | 0 | 0 | 0.0035839
64 | Pigging Program T1 Morwell - Dandenong Pigging and Repair Program | 258x | Other | Replacement | 2019 | 0 | 3.1616 | 0 | 0 | 0 | 3.1616
65 | Pig Trap Installation James Street to Laverton Pipeline (253) | 259a | Pipelines | Replacement | 2020 | 0 | 0 | 2.1447 | 0 | 0 | 2.1447
66 | Pig Trap Installation Tyers to Maryvale Pipeline (67) | 259d | Pipelines | Replacement | 2019 | 0 | 0.68174 | 0 | 0 | 0 | 0.68174
67 | Liquid Management - Brooklyn | 260a | City Gates & Field Regs | Replacement | 2022 | 0 | 0 | 0 | 0 | 0.16015 | 0.16015
68 | Liquid Management - Pakenham | 260b | City Gates & Field Regs | Replacement | 2021 | 0 | 0 | 0 | 0.16015 | 0 | 0.16015
69 | RTU replacement | 262 | Other | Replacement | incurred | 0.14465 | 0.14465 | 0.14465 | 0.14465 | 0.14465 | 0.72326
70 | Pipe Support replacement | 263 | Pipelines | Replacement | incurred | 0.16811 | 0.16811 | 0.16811 | 0.16811 | 0.16811 | 0.84054
71 | HMI upgrade to CLEAR SCADA at BCS, SCS and WCS & CG, Longford | 264 | Other | Non-System | incurred | 0.062147 | 0.062147 | 0.062147 | 0.062147 | 0.062147 | 0.31073
72 | BCS Unit 12 Inlet Filter Replacement/Augmentation | 267 | Compressors | Replacement | 2018 | 0.64843 | 0 | 0 | 0 | 0 | 0.64843
73 | Coogee decommissioning | 268 | 0 | 0 | 2022 | 0 | 0 | 0 | 0 | 0 | 0
74 | Compressor Type B Compliance | 271 | Compressors | Replacement | incurred | 0.22105 | 0.22105 | 0.22105 | 0.22105 | 0.22105 | 1.1053
75 | Dandenong LNG Isolation Valve Upgrade | 275 | Pipelines | Replacement | 2018 | 0.662 | 0 | 0 | 0 | 0 | 0.662
76 | Morwell-Dandenong Fatigue Crack Detection from High Loads | 276 | Pipelines | Replacement | 2018 | 0.26605 | 0 | 0 | 0 | 0 | 0.26605
77 | Unibolt Enclosure Replacement | 277 | Other | Replacement | incurred | 0.045353 | 0.045353 | 0.045353 | 0.045353 | 0.045353 | 0.22677
78 | WAN Upgrade (Satellite project) | 278 | Other | Non-System | incurred | 0.96593 | 0.96593 | 0.96593 | 0.96593 | 0.96593 | 4.8297
79 | Warragul Looping 6" (Southern Route) | Warragul 6" (Sth) | Pipelines | Augmentation | 2020 | 0 | 0 | 7.548 | 0 | 0 | 7.548
80 | Angelsea Pipeline (Western Route) | Anglesea | Pipelines | Augmentation | 2019 | 0 | 26.4103 | 0 | 0 | 0 | 26.4103
81 | VNIE | VNIE | Pipelines | Augmentation | 2018 | 1.6148 | 0 | 0 | 0 | 0 | 1.6148
82 | Wichelsea Bi Direction and Brooklyn Reconfiguration | WCS Bi-Dir and BCS reconfig | Compressors | Augmentation | 2018 | 0.5508 | 0 | 0 | 0 | 0 | 0.5508
83 | WORM (50km x 20" Pipeline) | WORM (Pipeline) | Pipelines | Augmentation | 2020 | 0 | 0 | 95.5973 | 0 | 0 | 95.5973
84 | WORM (C50 at Wollert) | WORM (C50) | Compressors | Augmentation | 2020 | 0 | 0 | 25.8189 | 0 | 0 | 25.8189
85 | WORM (PRS at Wollert) | WORM (PRS) | City Gates & Field Regs | Augmentation | 2020 | 0 | 0 | 3.673 | 0 | 0 | 3.673
86 | Enterprise Content Management | APA | 0 | 0 | 2018 | 0 | 0 | 0 | 0 | 0 | 0
87 | Victoria CRE | APA | 0 | 0 | 2018 | 0 | 0 | 0 | 0 | 0 | 0
88 | APA Grid Energy Components Upgrade | APA | 0 | 0 | 2018 | 0 | 0 | 0 | 0 | 0 | 0
89 | APA Grid Extend Program | APA | Other | Non-System | 2018 | 0.26645 | 0 | 0 | 0 | 0 | 0.26645
90 | APA Grid Services Initiatives Program | APA | 0 | 0 | 2018 | 0 | 0 | 0 | 0 | 0 | 0
91 | Hyperion Upgrade to 11.1.2.4 | APA | 0 | 0 | 2018 | 0 | 0 | 0 | 0 | 0 | 0
92 | BI - Transmission Dashboard and Enterprise Pilot | APA | Other | Non-System | 2018 | 0.37303 | 0 | 0 | 0 | 0 | 0.37303
93 | HR Systems Refresh | APA | 0 | 0 | 2018 | 0 | 0 | 0 | 0 | 0 | 0
94 | Transmission EAM Data Management Tool | APA | 0 | 0 | 2018 | 0 | 0 | 0 | 0 | 0 | 0
95 | SharePoint Upgrade | APA | Other | Non-System | 2018 | 0.025982 | 0 | 0 | 0 | 0 | 0.025982
96 | eForm Digitisation | APA | Other | Non-System | 2018 | 0.61336 | 0 | 0 | 0 | 0 | 0.61336
97 | Historian Upgrade - version 2012 to 2015 | APA | 0 | 0 | 2018 | 0 | 0 | 0 | 0 | 0 | 0
98 | Hazardous Area Platform | APA | Other | Non-System | 2018 | 0.16546 | 0 | 0 | 0 | 0 | 0.16546
99 | PPM Refresh | APA | Other | Non-System | 2018 | 0.31974 | 0 | 0 | 0 | 0 | 0.31974
100 | BizTalk Upgrade FY2018 | APA | Other | Non-System | 2018 | 0.13597 | 0 | 0 | 0 | 0 | 0.13597
101 | Automated Testing Tool | APA | Other | Non-System | 2018 | 0.06738 | 0 | 0 | 0 | 0 | 0.06738
102 | Code Management Software | APA | Other | Non-System | 2018 | 0.096553 | 0 | 0 | 0 | 0 | 0.096553
103 | CRM Upgrade | APA | Other | Non-System | 2018 | 0.15638 | 0 | 0 | 0 | 0 | 0.15638
104 | X-Info Aware Version 2 | APA | Other | Non-System | 2018 | 0.045838 | 0 | 0 | 0 | 0 | 0.045838
105 | Supplier Qualification and Compliance | APA | Other | Non-System | 2018 | 0.094152 | 0 | 0 | 0 | 0 | 0.094152
106 | Oracle eBS Upgrade to 12.2 | APA | Other | Non-System | 2018 | 0.16449 | 0 | 0 | 0 | 0 | 0.16449
107 | BizTalk System Upgrade 2020 | APA | Other | Non-System | 2018 | 0.13597 | 0 | 0 | 0 | 0 | 0.13597
108 | Applications Renewal | APA | Other | Non-System | 2018 | 4.0436 | 0 | 0 | 0 | 0 | 4.0436
109 | Infrastructure Renewal | VTS01 | Other | Non-System | 2018 | 0.4796 | 0 | 0 | 0 | 0 | 0.4796
110 | Dandenong Relocation | VTS02 | 0 | 0 | 2017 | 0 | 0 | 0 | 0 | 0 | 0
- | GCS Anti-Surge & Fast-Stop Valves Upgrade | VTS | Compressors | Replacement | 2018 | 1.5771 | 0 | 0 | 0 | 0 | 1.5771
- | VTS.SIB99 WCS STN-A DISCHRG LQ | VTS | Other | Replacement | 2018 | 0.22463 | 0 | 0 | 0 | 0 | 0.22463
- | SCS Vent Modifications | VTS | Other | Replacement | 2018 | 0.017581 | 0 | 0 | 0 | 0 | 0.017581
- | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0
- | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0
- | 0 | - | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
- | 0 | - | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
- | 0 | - | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
- | 0 | - | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
- | 0 | - | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
- | 0 | - | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
- | 0 | - | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
- | 0 | - | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
- | 0 | - | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
- | 0 | - | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
- | 0 | - | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
- | 0 | - | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
- | 0 | - | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
- | 0 | - | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
- | 0 | - | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
- | 0 | - | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
- | 0 | - | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
- | 0 | - | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
- | 0 | - | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
- | 0 | - | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
- | 0 | - | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
- | 0 | - | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
- | 0 | - | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
- | 0 | - | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
- | 0 | - | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
- | 0 | - | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
- | 0 | - | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
- | 0 | - | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
- | 0 | - | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
- | 0 | - | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
- | 0 | - | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
- | 0 | - | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
- | 0 | - | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
- | 0 | - | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
- | 0 | - | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
- | 0 | - | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
- | 0 | - | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
- | 0 | - | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
- | 0 | - | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
- | 0 | - | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
- | 0 | - | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
- | 0 | - | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
- | 0 | - | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
- | 0 | - | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
- | 0 | - | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
- | 0 | - | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
- | 0 | - | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
- | 0 | - | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
- | 0 | - | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
- | 0 | - | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
- | 0 | - | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
- | 0 | - | 0 | 0 | [6 empty] | 0
- | 0 | - | 0 | 0 | [6 empty] | 0
- | 0 | - | 0 | 0 | [6 empty] | 0
- | 0 | - | 0 | 0 | [6 empty] | 0
- | 0 | - | 0 | 0 | [6 empty] | 0
- | 0 | - | 0 | 0 | [6 empty] | 0
- | 0 | - | 0 | 0 | [6 empty] | 0
- | 0 | - | 0 | 0 | [6 empty] | 0
- | 0 | - | 0 | 0 | [6 empty] | 0
- | 0 | - | 0 | 0 | [6 empty] | 0
- | 0 | - | 0 | 0 | [6 empty] | 0
- | 0 | - | 0 | 0 | [6 empty] | 0
- | 0 | - | 0 | 0 | [6 empty] | 0
- | 0 | - | 0 | 0 | [6 empty] | 0
- | 0 | - | 0 | 0 | [6 empty] | 0
- | 0 | - | 0 | 0 | [6 empty] | 0
- | 0 | - | 0 | 0 | [6 empty] | 0
- | 0 | - | 0 | 0 | [6 empty] | 0
- | 0 | - | 0 | 0 | [6 empty] | 0
- | 0 | - | 0 | 0 | [6 empty] | 0
- | 0 | - | 0 | 0 | [6 empty] | 0
- | 0 | - | 0 | 0 | [6 empty] | 0