## PTRM Inputs
PTRM - As Incurred | [5 empty] | PTRM - As Commissioned |  |  |  | Ok | Global Error Check
AER Draft Decision
PTRM As incurred - Total | 2015 | 2016 | 2017 | 2018 | total | PTRM As commissioned - Total | 2015 | 2016 | 2017 | 2018 | total
TL | 15.4096 | 42.3751 | 25.7075 | 46.3436 | 129.8358 | TL | 10.8378 | 40.1517 | 24.1948 | 50.3384 | 125.5227
Cables | 1.349 | 3.5432 | 1.3057 | 0.27019 | 6.4681 | Cables | 1.2236 | 0 | 5.1131 | 0.54038 | 6.877
Subs | 130.779 | 109.0599 | 120.1113 | 94.2107 | 454.1608 | Subs | 159.9675 | 100.1057 | 111.6771 | 158.88 | 530.6303
Sec Sys | 27.2874 | 31.9115 | 25.9809 | 30.3219 | 115.5016 | Sec Sys | 18.7101 | 39.7919 | 15.9328 | 38.3892 | 112.824
Comms | 22.5052 | 12.8232 | 6.949 | 7.0438 | 49.3212 | Comms | 28.6645 | 40.7196 | 10.9491 | 9.2721 | 89.6053
Bus. IT | 21.1148 | 19.6596 | 18.1156 | 20.7918 | 79.6818 | Bus. IT | 21.1148 | 19.6596 | 18.1156 | 20.7918 | 79.6818
MV & MP | 11.4832 | 9.1857 | 10.7817 | 11.7719 | 43.2224 | MV & MP | 11.4832 | 9.1857 | 10.7817 | 11.7719 | 43.2224
TL Life Ext | 5.5047 | 6.1697 | 4.5911 | 7.1878 | 23.4532 | TL Life Ext | 3.5521 | 4.3007 | 7.7008 | 0.79256 | 16.3462
Equity Raising |  |  |  |  | 0 | Equity Raising |  |  |  |  | 0
Land | 5.4088 | 4.6773 | 9.4469 | 1.159 | 20.692 | Land | 18.7752 | 1.8899 | 16.0645 | 2.4265 | 39.1561
Total | 240.8416 | 239.405 | 222.9896 | 219.1007 | 922.3369 | Total | 274.3287 | 255.8047 | 220.5294 | 293.2028 | 1043.8657
Check | 0 | 0 | 0 | 0 | 0 |  | 5.6843e-14 | 0 | 0 | 0 | 0

## Capex Incurred Summary
| Capex Incurred ($M) | Costs (Real $2014) Including Real Escalation
| Regulated Asset Class | 2010 | 2011 | 2012 | 2013 | 2014 | 2015 | 2016 | 2017 | 2018 | 2015-18 Total
TL | Transmission Lines | 72.1523 | 78.5067 | 58.9419 | 83.8055 | 78.9449 | 15.4096 | 42.3751 | 25.7075 | 46.3436 | 129.8358
Subs | Substations | 272.7006 | 212.8528 | 200.7973 | 237.3036 | 246.19 | 130.779 | 109.0599 | 120.1113 | 94.2107 | 454.1608
Sec Sys | Secondary Systems | 14.1282 | 11.4059 | 23.4121 | 24.9842 | 33.3616 | 27.2874 | 31.9115 | 25.9809 | 30.3219 | 115.5016
Comms | Communications | 34.2048 | 28.5917 | 22.6185 | 24.2975 | 47.8655 | 22.5052 | 12.8232 | 6.949 | 7.0438 | 49.3212
Land | Land and Easements | 20.3279 | 28.1826 | 22.2295 | 43.4084 | 32.0665 | 5.4088 | 4.6773 | 9.4469 | 1.159 | 20.692
Cables | Underground Cables | 1.762 | 2.6781 | 10.7008 | 46.6113 | 70.7863 | 1.349 | 3.5432 | 1.3057 | 0.27019 | 6.4681
TL Life Ext | Transmission Line Life Extension | 0 | 0 | 0 | 0 | 0 | 5.5047 | 6.1697 | 4.5911 | 7.1878 | 23.4532
MV & MP | Motor Vehicles, Moveable Plant and Minor Plant | 13.6194 | 10.6422 | 13.8273 | 10.2469 | 15.6114 | 11.4832 | 9.1857 | 10.7817 | 11.7719 | 43.2224
Bus. IT | Business and Information Technology | 14.9027 | 15.8249 | 20.1659 | 25.2189 | 25.1482 | 21.1148 | 19.6596 | 18.1156 | 20.7918 | 79.6818
| Costs (Real $2014) Including Real Escalation | 443.7981 | 388.6848 | 372.6935 | 495.8763 | 549.9744 | 240.8416 | 239.405 | 222.9896 | 219.1007 | 922.3369
Check | 3.6948e-13 | 5.6843e-14 | 5.6843e-14 | 0 | 1.1369e-13 | 0 | 2.8422e-14 | 5.6843e-14 | 2.8422e-14 | 2.8422e-14
| Real Cost Escalation | 0 | 0 | 0 | 0 | 0.045904 | 0.80354 | 3.9029 | 6.1628 | 8.053 | 18.9223
| Costs (Real $2014) Excluding Real Escalation | 443.7981 | 388.6848 | 372.6935 | 495.8763 | 549.9285 | 240.0381 | 235.502 | 216.8267 | 211.0477 | 903.4146
| Capex by Project Category | 2010 | 2011 | 2012 | 2013 | 2014 | 2015 | 2016 | 2017 | 2018 | 2015-18 Total
Load Driven | PS Augmentation | 245.9013 | 179.8446 | 163.35 | 251.2124 | 229.9969 | 16.9243 | 4.8228 | 22.6907 | 20.6977 | 65.1355
Non-Load Driven | PS Connections | 1.1284 | 1.1172 | 2.6201 | 2.6317 | 5.6656 | 4.7136 | 0.94998 | 1.123 | 0.19171 | 6.9782
Load Driven | PS Easements | 10.1709 | 18.2131 | 10.0251 | 17.7109 | 3.0665 | 0.90128 | 2.1522 | 7.8477 | 0 | 10.9012
Non-Load Driven | PS Replacement | 94.9714 | 113.4991 | 87.0894 | 100.3759 | 170.9309 | 136.5964 | 158.4707 | 127.497 | 134.5623 | 557.1264
Non-Load Driven | PS Network Asset Replacement | 45.5142 | 34.7766 | 40.5734 | 49.7374 | 41.7299 | 24.2754 | 22.994 | 22.5206 | 20.7081 | 90.498
Non-Load Driven | PS Network-Other | 0 | 0 | 0 | 0 | 2.0703 | 2.5027 | 1.445 | 1.511 | 1.165 | 6.6237
Non-Load Driven | PS Security/Compliance | 15.2616 | 10.3558 | 22.5075 | 17.5412 | 24.3184 | 17.9847 | 10.1968 | 7.5806 | 10.3773 | 46.1394
Business IT | PS Information Technology | 15.4387 | 15.8249 | 20.1659 | 25.2189 | 20.9174 | 19.3508 | 19.6596 | 18.1156 | 20.7918 | 77.9178
Support the Business | PS Facilities | 1.7923 | 4.4115 | 12.5347 | 21.2009 | 37.7375 | 8.612 | 10.9733 | 4.8327 | 0 | 24.418
Support the Business | PS Motor Vehicles | 13.6194 | 10.6422 | 13.8273 | 10.2469 | 13.5411 | 8.9805 | 7.7407 | 9.2707 | 10.6069 | 36.5987
Non-Load Driven | PS Western Sydney Supply | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Costs (Real $2014) Including Real Escalation | 443.7981 | 388.6848 | 372.6935 | 495.8763 | 549.9744 | 240.8416 | 239.405 | 222.9896 | 219.1007 | 922.3369
Check | 4.5475e-13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Capex by Project Component | 2010 | 2011 | 2012 | 2013 | 2014 | 2015 | 2016 | 2017 | 2018 | 2015-18 Total
| CPI Only | 443.7981 | 388.6848 | 372.6935 | 495.0547 | 538.5247 | 205.4285 | 141.6852 | 108.1878 | 111.9774 | 567.279
| EGW Wages | 0 | 0 | 0 | 0.56383 | 4.7315 | 13.6801 | 31.7239 | 35.7411 | 34.8972 | 116.0423
| Wages General | 0 | 0 | 0 | 0 | 0.0089196 | 0.075718 | 0.211 | 0.361 | 0.041938 | 0.68966
| Copper | 0 | 0 | 0 | 0.013301 | 0.14845 | 0.76117 | 1.1992 | 2.6605 | 2.7136 | 7.3345
| Aluminium | 0 | 0 | 0 | 0.0041852 | 0.029463 | 0.12077 | 0.33702 | 0.63705 | 0.47729 | 1.5721
| Steel | 0 | 0 | 0 | 0.0018013 | 0.041704 | 0.26559 | 0.46628 | 1.3588 | 1.5394 | 3.63
| Oil | 0 | 0 | 0 | 0.00062785 | 0.016428 | 0.11714 | 0.17505 | 0.39593 | 0.58583 | 1.2739
| Construction | 0 | 0 | 0 | 0.23792 | 5.6274 | 20.0669 | 60.9693 | 64.9604 | 66.4648 | 212.4615
| Property - Res. | 0 | 0 | 0 | 0 | 0.0045463 | 0 | 0 | 0 | 0 | 0
| Property - Ind. | 0 | 0 | 0 | 0 | 0.83197 | 0.065212 | 0.12724 | 0.016063 | 0 | 0.20851
| Property - Rural | 0 | 0 | 0 | 0 | 0 | 0.03977 | 0.47348 | 1.7265 | 0 | 2.2398
| Property - Agr. | 0 | 0 | 0 | 0 | 0.0092908 | 0.22072 | 2.0372 | 6.9443 | 0.40329 | 9.6055
| Costs (Real $2014) Including Real Escalation | 443.7981 | 388.6848 | 372.6935 | 495.8763 | 549.9744 | 240.8416 | 239.405 | 222.9896 | 219.1007 | 922.3369
Check | 1.3358e-12 | 2.2737e-13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Capex Commissioned Summary
| Capex Commissioned ($M) | Costs (Real $2014) Including Real Escalation
Transitional
|  | Unadjusted | Adjustment | Adjusted
| Regulated Asset Class | 2015 | 2015 | 2015 | 2016 | 2017 | 2018 | 2015-18 Total
TL | Transmission Lines | 15.8503 | 5.0125 | 10.8378 | 40.1517 | 24.1948 | 50.3384 | 125.5227
Subs | Substations | 284.3401 | 124.3725 | 159.9675 | 100.1057 | 111.6771 | 158.88 | 530.6303
Sec Sys | Secondary Systems | 23.2365 | 4.5264 | 18.7101 | 39.7919 | 15.9328 | 38.3892 | 112.824
Comms | Communications | 33.1757 | 4.5112 | 28.6645 | 40.7196 | 10.9491 | 9.2721 | 89.6053
Land | Land and Easements | 58.7602 | 39.9851 | 18.7752 | 1.8899 | 16.0645 | 2.4265 | 39.1561
Cables | Underground Cables | 113.5737 | 112.3502 | 1.2236 | 0 | 5.1131 | 0.54038 | 6.877
TL Life Ext | Transmission Line Life Extension | 3.5521 | 0 | 3.5521 | 4.3007 | 7.7008 | 0.79256 | 16.3462
MV & MP | Motor Vehicles, Moveable Plant and Minor Plant | 11.4832 | 0 | 11.4832 | 9.1857 | 10.7817 | 11.7719 | 43.2224
Bus. IT | Business and Information Technology | 21.1148 | 0 | 21.1148 | 19.6596 | 18.1156 | 20.7918 | 79.6818
| Costs (Real $2014) Including Real Escalation | 565.0866 | 290.7579 | 274.3287 | 255.8047 | 220.5294 | 293.2028 | 1043.8657
Check | 1.9895e-13 | 1.1369e-13 | 0 | 0 | 0 | 2.8422e-14 | 5.6843e-14
| Real Cost (Commodity) Escalation | 0.80354 | 0 | 0.80354 | 3.9029 | 6.1628 | 8.053 | 18.9223
| Costs (Real $2014) Excluding Real Escalation | 564.2831 | 290.7579 | 273.5252 | 251.9018 | 214.3666 | 285.1498 | 1024.9434
Transitional
|  | Unadjusted | Adjustment | Adjusted
| Capex by Project Category | 2015 | 2015 | 2015 | 2016 | 2017 | 2018 | 2015-18 Total
Load Driven | PS Augmentation | 270.6538 | 250.0505 | 20.6033 | 0 | 0 | 51.7971 | 72.4004
Non-Load Driven | PS Connections | 5.8679 | 0 | 5.8679 | 2.9524 | 0.95989 | 1.4712 | 11.2514
Load Driven | PS Easements | 13.8141 | 0 | 13.8141 | 0.36555 | 12.4111 | 0 | 26.5908
Non-Load Driven | PS Replacement | 196.784 | 40.7074 | 156.0766 | 167.7323 | 149.6095 | 176.4154 | 649.8338
Non-Load Driven | PS Network Asset Replacement | 24.2754 | 0 | 24.2754 | 22.994 | 22.5206 | 20.7081 | 90.498
Non-Load Driven | PS Network-Other | 2.5027 | 0 | 2.5027 | 1.445 | 1.511 | 1.165 | 6.6237
Non-Load Driven | PS Security/Compliance | 14.2455 | 0 | 14.2455 | 21.9419 | 1.2983 | 10.2474 | 47.7331
Business IT | PS Information Technology | 19.3508 | 0 | 19.3508 | 19.6596 | 18.1156 | 20.7918 | 77.9178
Support the Business | PS Facilities | 8.612 | 0 | 8.612 | 10.9733 | 4.8327 | 0 | 24.418
Support the Business | PS Motor Vehicles | 8.9805 | 0 | 8.9805 | 7.7407 | 9.2707 | 10.6069 | 36.5987
Non-Load Driven | PS Western Sydney Supply | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Costs (Real $2014) Including Real Escalation | 565.0866 | 290.7579 | 274.3287 | 255.8047 | 220.5294 | 293.2028 | 1043.8657
Check | 3.4106e-13 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Transitional
|  | Unadjusted | Adjustment | Adjusted
| Capex by Project Component | 2015 | 2015 | 2015 | 2016 | 2017 | 2018 | 2015-18 Total
| CPI Only | 556.3987 | 290.7579 | 265.6408 | 193.8472 | 156.3426 | 127.8876 | 743.7181
| EGW Wages | 3.4456 | 0 | 3.4456 | 21.4831 | 14.9208 | 56.1993 | 96.0488
| Wages General | 0 | 0 | 0 | 0.11268 | 0.38057 | 0.11653 | 0.60978
| Copper | 0.19522 | 0 | 0.19522 | 0.64413 | 0.46186 | 4.5119 | 5.8131
| Aluminium | 0.029689 | 0 | 0.029689 | 0.26658 | 0.0256 | 1.0217 | 1.3436
| Steel | 0.040885 | 0 | 0.040885 | 0.25981 | 0.055041 | 2.7608 | 3.1165
| Oil | 0.023606 | 0 | 0.023606 | 0.10585 | 0.033395 | 0.87139 | 1.0342
| Construction | 4.8934 | 0 | 4.8934 | 38.8708 | 36.9157 | 98.6021 | 179.2819
| Property - Res. | 0 | 0 | 0 | 0 | 0.0045463 | 0 | 0.0045463
| Property - Ind. | 0.059539 | 0 | 0.059539 | 0 | 0.98095 | 0 | 1.0405
| Property - Rural | 0 | 0 | 0 | 0 | 2.2398 | 0 | 2.2398
| Property - Agr. | 0 | 0 | 0 | 0.21455 | 8.1686 | 1.2316 | 9.6148
| Costs (Real $2014) Including Real Escalation | 565.0866 | 290.7579 | 274.3287 | 255.8047 | 220.5294 | 293.2028 | 1043.8657
Check | 1.9895e-13 | 1.1369e-13 | 0 | 0 | 0 | 0 | 0 | 0

## Cost Escalators
Cost Escalators
CPI
Financial Year: | 2013 | 2014
Forecast CPI | 2.503% | 2.93%
Cumulative CPI to Report Year 2014 | 102.9% | 100%
Annual Escalation (Real Commodity escalation, no CPI escalation )
Financial Year: | CPI Only | EGW Wages | Wages General | Copper | Aluminium | Steel | Oil | Construction | Property - Res. | Property - Ind. | Property - Rural | Property - Agr.
2014 | 0% | -0.2467% | 1.1% | 0.12% | 0.72% | 7.74% | 18.61% | 1.3% | 5.6% | -2.6% | 4.6% | -1.1%
2015 | 0% | 0.79% | 0.79% | 0% | 0% | 0% | 0% | 2.17% | 6.2% | -0.8% | 4.4% | -1.2%
2016 | 0% | 0.75% | 0.75% | 0% | 0% | 0% | 0% | 2.25% | 5.1% | -0.1% | 3.9% | -0.2%
2017 | 0% | 1.22% | 1.22% | 0% | 0% | 0% | 0% | 2.2% | 1.3% | 1% | 1.7% | -0.7%
2018 | 0% | 1.43% | 1.43% | 0% | 0% | 0% | 0% | 2.12% | -0.6% | 2.3% | 1.1% | 2%
Cumulative Escalation (Real Commodity escalation, no CPI escalation )
Financial Year: | CPI Only | EGW Wages | Wages General | Copper | Aluminium | Steel | Oil | Construction | Property - Res. | Property - Ind. | Property - Rural | Property - Agr.
2014 | 100% | 99.75% | 101.1% | 100.1% | 100.7% | 107.7% | 118.6% | 101.3% | 105.6% | 97.4% | 104.6% | 98.9%
2015 | 100% | 100.5% | 101.9% | 100.1% | 100.7% | 107.7% | 118.6% | 103.5% | 112.1% | 96.62% | 109.2% | 97.71%
2016 | 100% | 101.3% | 102.7% | 100.1% | 100.7% | 107.7% | 118.6% | 105.8% | 117.9% | 96.52% | 113.5% | 97.52%
2017 | 100% | 102.5% | 103.9% | 100.1% | 100.7% | 107.7% | 118.6% | 108.2% | 119.4% | 97.49% | 115.4% | 96.84%
2018 | 100% | 104% | 105.4% | 100.1% | 100.7% | 107.7% | 118.6% | 110.4% | 118.7% | 99.73% | 116.7% | 98.77%
Regulatory Asset Classes
Item | Name | Description
Reg Asset Class 1 | TL | Transmission Lines
Reg Asset Class 2 | Subs | Substations
Reg Asset Class 3 | Sec Sys | Secondary Systems
Reg Asset Class 4 | Comms | Communications
Reg Asset Class 5 | Land | Land and Easements
Reg Asset Class 6 | Cables | Underground Cables
Reg Asset Class 7 | TL Life Ext | Transmission Line Life Extension
Reg Asset Class 8 | MV & MP | Motor Vehicles, Moveable Plant and Minor Plant
Reg Asset Class 9 | Bus. IT | Business and Information Technology
Project Components
Description | Name | Description
Project Component 1 | CPI Only | Inflation Amount to be escalated by CPI (no commodity esc.)
Project Component 2 | EGW Wages | Electricity Gas and Water Wages
Project Component 3 | Wages General | General Wages
Project Component 4 | Copper | Copper
Project Component 5 | Aluminium | Aluminium
Project Component 6 | Steel | Steel
Project Component 7 | Oil | Crude Oil
Project Component 8 | Construction | Construction
Project Component 9 | Property - Res. | Property - Residential
Project Component 10 | Property - Ind. | Property - Industrial
Project Component 11 | Property - Rural | Property - Rural
Project Component 12 | Property - Agr. | Property - Agricultural
Capex by Project Category
Category | Grouping | Network or Non-Network
PS Augmentation | Load Driven | Network
PS Connections | Non-Load Driven | Network
PS Easements | Load Driven | Network
PS Replacement | Non-Load Driven | Network
PS Network Asset Replacement | Non-Load Driven | Network
PS Network-Other | Non-Load Driven | Network
PS Security/Compliance | Non-Load Driven | Network
PS Information Technology | Business IT | Non-Network
PS Facilities | Support the Business | Non-Network
PS Motor Vehicles | Support the Business | Non-Network
PS Western Sydney Supply | Non-Load Driven | Network
Capex Commissioned 2015 - Transitional Adjustment
Program \ Project No. | Program \ Project Grouping |  | Program \ Project Name
6650 | Western Sydney Supply Project |  | Holroyd - Rookwood 330kV Cable
6651 | Western Sydney Supply Project |  | Rookwood Road 330/132kV Substation
6314 | Substation Renewal |  | Upper Tumut Switching Station Renewal
7298 | SVC Control System Replacement |  | Kemps Creek SVC Control System Replacement
Note on B9: No Real escalation.
Note on B17: No Real escalation.

## Input Data
Program \ Project Cost Inputs
[7 empty] | 431166228.7153 | 377621678.7021 | 362085534.8328 | 481762191.4819 | 536596731.8353 | 234205495.8987 | 229796269.1771 | 211469068.0202 | 205653132.2916
[7 empty] | Capex Incurred | [8 empty] | Capex by Regulatory Asset Class (%) - Calculated | [8 empty] | 1.11e-12% | Capex by Component (%) | [11 empty] | 4.996e-13%
Program \ Project No. | Program \ Project Grouping | Program \ Project Name | Program \ Project Category | Committed / Future | Commissioning Date | Effective Estimate Year | 2010 | 2011 | 2012 | 2013 | 2014 | 2015 | 2016 | 2017 | 2018 | Reg Asset Class 1 TL | Reg Asset Class 2 Subs | Reg Asset Class 3 Sec Sys | Reg Asset Class 4 Comms | Reg Asset Class 5 Land | Reg Asset Class 6 Cables | Reg Asset Class 7 TL Life Ext | Reg Asset Class 8 MV & MP | Reg Asset Class 9 Bus. IT | Check | CPI Only | EGW Wages | Wages General | Copper | Aluminium | Steel | Oil | Construction | Property - Res. | Property - Ind. | Property - Rural | Property - Agr. | Check
6716 | Communications | Establishment of Gigabit Ethernet CDN Network | PS Facilities | Input_Prog_Commit | 0 | 2013 | -0.93146 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
5161 | Non HV Buildings & Civil Work | Building Improvements | PS Facilities | Input_Prog_Commit | 0 | 2013 | 3086017.5927 | 3644494.6624 | 5282894.724 | 5226536.6306 | 0 | 0 | 0 | 0 | 0 | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
5976 | Non HV Buildings & Civil Work | HO Refurbishment | PS Facilities | Input_Prog_Commit | 0 | 2013 | -1446786.6279 | 1284.0948 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
5989 | Non HV Buildings & Civil Work | Sydney West Warehouse Extension | PS Facilities | Input_Prog_Commit | 0 | 2013 | 102063.2783 | 121664.9013 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
7332 | Non HV Buildings & Civil Work | Strategic Accomodation | PS Facilities | Input_Prog_Commit | 0 | 2013 | 0 | 481753.2862 | 6895028.8912 | 0 | 0 | 0 | 0 | 0 | 0 | 4.654% | 74.47% | 2.327% | 2.327% | 16.23% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
7332 | Non HV Buildings & Civil Work | Strategic Accomodation | PS Facilities | Input_Prog_Commit | 0 | 2014 | 0 | 0 | 0 | 0 | 37683457.2129 | 8612015 | 10973300 | 4832700 | 0 | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
7332 | Non HV Buildings & Civil Work | Strategic Accomodation | PS Facilities | Input_Prog_Commit | 0 | 2013 | 0 | 0 | 0 | 15370970.1463 | 0 | 0 | 0 | 0 | 0 | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
7517 | Non HV Buildings & Civil Work | Newcastle Mezzanine Floor | PS Facilities | Input_Prog_Commit | 0 | 2013 | 0 | 36711.2563 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
8050 | Non HV Buildings & Civil Work | Haymarket Blast Wall | PS Facilities | Input_Prog_Commit | 0 | 2014 | 0 | 0 | 0 | 0 | 54078 | 0 | 0 | 0 | 0 | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
6420 | Information Technology | Video Conferencing & Collaboration | PS Information Technology | Input_Prog_Commit | 0 | 2013 | 520743.3125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
ICT Applications | Information Technology | Capital Program Delivery | PS Information Technology | Input_Prog_Commit | 0 | 2013 | 2672971.2207 | 895263.7212 | 23525.8231 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
ICT Applications | Information Technology | Finance & Information Systems | PS Information Technology | Input_Prog_Commit | 0 | 2013 | 2677587.5084 | 9423444.2928 | 12204307.2839 | 19630733.6237 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
ICT Applications | Information Technology | Network Planning & Performance | PS Information Technology | Input_Prog_Commit | 0 | 2013 | 773619.5683 | 385802.2267 | 11550.7667 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
ICT Applications | Information Technology | Network Services & Operations | PS Information Technology | Input_Prog_Commit | 0 | 2013 | 98115.2897 | 267262.0319 | 72318.3395 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
ICT Applications | Information Technology | People, Strategy & Corporate Services | PS Information Technology | Input_Prog_Commit | 0 | 2013 | 73228.8116 | 80129.041 | 3467.8758 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
ICT Applications | Information Technology | 0 | PS Information Technology | Input_Prog_Commit | 0 | 2013 | 0 | 0 | 0 | 0 | 12318000 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
ICT Corporate Data Network | Information Technology | Finance & Information Systems | PS Information Technology | Input_Prog_Commit | 0 | 2013 | 2230293.3736 | 1032197.3954 | 1059277.0223 | 785259.752 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
ICT Corporate Data Network | Information Technology | 0 | PS Information Technology | Input_Prog_Commit | 0 | 2013 | 0 | 0 | 0 | 0 | 1780000 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
ICT Infrastructure | Information Technology | Finance & Information Systems | PS Information Technology | Input_Prog_Commit | 0 | 2013 | 5208288.8757 | 3266074.2741 | 6217517.5044 | 4085132.965 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
ICT Infrastructure | Information Technology | Network Services & Operations | PS Information Technology | Input_Prog_Commit | 0 | 2013 | 323387.4297 | 79284.4587 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
ICT Infrastructure | Information Technology | 0 | PS Information Technology | Input_Prog_Commit | 0 | 2013 | 0 | 0 | 0 | 0 | 6224000 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
0 | Information Technology | Finance & Information Systems | PS Information Technology | Input_Prog_Commit | 0 | 2013 | 421039.5278 | -55003.7779 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
5739 | Motor Vehicles & Mobile Plant | TG Mobile Plant | PS Motor Vehicles | Input_Prog_Commit | 0 | 2013 | 0 | 0 | 0 | 0 | 3821897.73 | 2919314 | 1762500 | 1643591 | 2177280 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
5777 | Motor Vehicles & Mobile Plant | TG Business Vehicles | PS Motor Vehicles | Input_Prog_Commit | 0 | 2013 | 0 | 0 | 0 | 0 | 9333827.29 | 5805532.93 | 5757850 | 7363208.2403 | 8127669.902 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
0 | Motor Vehicles & Mobile Plant | Capital Program Delivery | PS Motor Vehicles | Input_Prog_Commit | 0 | 2013 | -448.2722 | 75486.0721 | 86165.1823 | 149631.6448 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
0 | Motor Vehicles & Mobile Plant | Finance & Information Systems | PS Motor Vehicles | Input_Prog_Commit | 0 | 2013 | 2106.4088 | 59336.263 | 13117.0611 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
0 | Motor Vehicles & Mobile Plant | Network Planning & Performance | PS Motor Vehicles | Input_Prog_Commit | 0 | 2013 | 0 | 18750.9704 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
0 | Motor Vehicles & Mobile Plant | Network Services & Operations | PS Motor Vehicles | Input_Prog_Commit | 0 | 2013 | 1130126.8606 | 2449379.13 | 3412979.4573 | 1496117.1501 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
0 | Motor Vehicles & Mobile Plant | People, Strategy & Corporate Services | PS Motor Vehicles | Input_Prog_Commit | 0 | 2013 | 19805.6127 | 71920.7732 | 201147.3761 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
0 | Motor Vehicles & Mobile Plant | People, Strategy & Corporate Services | PS Motor Vehicles | Input_Prog_Commit | 0 | 2013 | 12080139.67 | 7664426.3663 | 9720307.2195 | 8309457.5354 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
6424 | Cables | 42 Tunnel (Sydney Park) Water Treatment Plant | PS Network Asset Replacement | Input_Prog_Commit | 0 | 2013 | 114509.3553 | -151176.3758 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
0 | Cables | Network Asset Replacement | PS Network Asset Replacement | Input_Prog_Commit | 0 | 2013 | 113824.9195 | 50853.8913 | 31889.0702 | 22926.6871 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
4967 | Communications | Installation of PLC Voice Equipment | PS Network Asset Replacement | Input_Prog_Commit | 0 | 2014 | 0 | 0 | 0 | 0 | 294643.72 | 616030.3382 | 410686.8921 | 359351.0306 | 0 | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
4968 | Communications | Installation of PLC Intertrips | PS Network Asset Replacement | Input_Prog_Commit | 0 | 2014 | 0 | 0 | 0 | 0 | 231724.2 | 214601.9484 | 321902.9226 | 107300.9742 | 160951.4613 | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
4969 | Communications | Installation of VF Intertrips | PS Network Asset Replacement | Input_Prog_Commit | 0 | 2014 | 0 | 0 | 0 | 0 | 214381.8 | 49609.466 | 198437.864 | 173633.131 | 148828.398 | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
7425 | Communications | SSZ Upgrade Work | PS Network Asset Replacement | Input_Prog_Commit | 0 | 2014 | 0 | 0 | 0 | 0 | 150921.55 | 64383.7393 | 32191.8696 | 72431.7067 | 24143.9022 | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
0 | Communications | Network Asset Replacement | PS Network Asset Replacement | Input_Prog_Commit | 0 | 2013 | 1316139.2509 | 1420926.4034 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
0 | Communications | Network Asset Replacement | PS Network Asset Replacement | Input_Prog_Commit | 0 | 2013 | 0 | 0 | 362475.1341 | 3189385.4311 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
4978 | Controls & Alarms | Installation of RTU Equipment | PS Network Asset Replacement | Input_Prog_Commit | 0 | 2014 | 0 | 0 | 0 | 0 | 4256648.5 | 1720008.344 | 2408011.6816 | 630669.7261 | 802670.5605 | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
0 | Controls & Alarms | Network Asset Replacement | PS Network Asset Replacement | Input_Prog_Commit | 0 | 2013 | 1792090.7067 | 2564493.2478 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
0 | Controls & Alarms | Network Asset Replacement | PS Network Asset Replacement | Input_Prog_Commit | 0 | 2013 | 0 | 0 | 3439884.5666 | 2573616.4427 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
5071 | HV Buildings & Civil Work | Perimeter Security Fence | PS Network Asset Replacement | Input_Prog_Commit | 0 | 2014 | 0 | 0 | 0 | 0 | 104325 | 0 | 0 | 0 | 0 | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
5077 | HV Buildings & Civil Work | Switchyard Security Fence | PS Network Asset Replacement | Input_Prog_Commit | 0 | 2014 | 0 | 0 | 0 | 0 | 6140 | 0 | 0 | 0 | 0 | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
5098 | HV Buildings & Civil Work | Fire Protection Systems | PS Network Asset Replacement | Input_Prog_Commit | 0 | 2014 | 0 | 0 | 0 | 0 | 10000 | 0 | 185243.8 | 185243.8 | 0 | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
5161 | HV Buildings & Civil Work | Depot Building Improvements and Upgrades | PS Network Asset Replacement | Input_Prog_Commit | 0 | 2014 | 0 | 0 | 0 | 0 | 5503690.66 | 605500 | 0 | 140000 | 0 | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
5201 | HV Buildings & Civil Work | Substations Building and Property | PS Network Asset Replacement | Input_Prog_Commit | 0 | 2014 | 0 | 0 | 0 | 0 | 5746712.86 | 2767571.3753 | 797354.6093 | 633792.9637 | 338151.9137 | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
5949 | HV Buildings & Civil Work | Air Conditioning in Relay Rooms | PS Network Asset Replacement | Input_Prog_Commit | 0 | 2014 | 0 | 0 | 0 | 0 | 628112.28 | 486190.586 | 0 | 0 | 0 | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
6337 | HV Buildings & Civil Work | Security Fence Replace D-Pales | PS Network Asset Replacement | Input_Prog_Commit | 0 | 2014 | 0 | 0 | 0 | 0 | 54145 | 0 | 0 | 0 | 0 | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
0 | HV Buildings & Civil Work | Network Asset Replacement | PS Network Asset Replacement | Input_Prog_Commit | 0 | 2013 | 1738239.5029 | 1208290.992 | 4756775.9097 | 4817161.6991 | 0 | 0 | 0 | 0 | 0 | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
5651 | IT | SCADA Upgrade | PS Network Asset Replacement | Input_Prog_Commit | 0 | 2014 | 0 | 0 | 0 | 0 | 3390986.24 | 1414000 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
8238 | IT | SCADA Facilities Augmentation | PS Network Asset Replacement | Input_Prog_Commit | 0 | 2014 | 0 | 0 | 0 | 0 | 776869.15 | 350000 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
5923 | Metering | Replacement of Siements 7EC Meters | PS Network Asset Replacement | Input_Prog_Commit | 0 | 2014 | 0 | 0 | 0 | 0 | 301214.46 | 0 | 0 | 225716.0873 | 0 | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
5925 | Metering | Replacement of Email A1R-AL Meters | PS Network Asset Replacement | Input_Prog_Commit | 0 | 2014 | 0 | 0 | 0 | 0 | 339838 | 0 | 0 | 0 | 0 | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
5926 | Metering | Replacement of CEWE CEP/CEQ Meters | PS Network Asset Replacement | Input_Prog_Commit | 0 | 2014 | 0 | 0 | 0 | 0 | 525100.06 | 309705.3178 | 0 | 0 | 0 | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
5927 | Metering | Replacement of Ferrari Disc Pulsing Meters | PS Network Asset Replacement | Input_Prog_Commit | 0 | 2014 | 0 | 0 | 0 | 0 | 91317.93 | 213232.133 | 142154.7553 | 244822.0786 | 157949.7281 | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
6296 | Metering | Upgrade Site Metering Schemes | PS Network Asset Replacement | Input_Prog_Commit | 0 | 2014 | 0 | 0 | 0 | 0 | 213620.2 | 338574.1309 | 451432.1746 | 42014.847 | 565984.7665 | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
0 | Metering | Network Asset Replacement | PS Network Asset Replacement | Input_Prog_Commit | 0 | 2013 | 1224175.0351 | 727800.6411 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
0 | Metering | Network Asset Replacement | PS Network Asset Replacement | Input_Prog_Commit | 0 | 2013 | 0 | 0 | 1731342.5769 | 3015697.0808 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
4946 | Protection | Replacement of H-Type Relays - Key Metro Sites | PS Network Asset Replacement | Input_Prog_Commit | 0 | 2014 | 0 | 0 | 0 | 0 | 16250.04 | 0 | 0 | 0 | 0 | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
4947 | Protection | Replacement of H-Type Relays - Remaining Sites | PS Network Asset Replacement | Input_Prog_Commit | 0 | 2014 | 0 | 0 | 0 | 0 | -11273.55 | 0 | 0 | 0 | 53666.7779 | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
4954 | Protection | Replacement of CSD IMS Fault Recorders | PS Network Asset Replacement | Input_Prog_Commit | 0 | 2014 | 0 | 0 | 0 | 0 | 143294.98 | 0 | 0 | 75548.3354 | 151096.6708 | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
4957 | Protection | Replacement of TS Relays | PS Network Asset Replacement | Input_Prog_Commit | 0 | 2014 | 0 | 0 | 0 | 0 | 74092 | 0 | 0 | 0 | 0 | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
4960 | Protection | Replacement of THS Relays | PS Network Asset Replacement | Input_Prog_Commit | 0 | 2014 | 0 | 0 | 0 | 0 | 447256.73 | 437187.8645 | 105443.2979 | 160220.8008 | 0 | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
4961 | Protection | Replacement of THR Relays | PS Network Asset Replacement | Input_Prog_Commit | 0 | 2014 | 0 | 0 | 0 | 0 | 95573.85 | 0 | 1676638.1969 | 695827.8889 | 581578.9005 | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
4962 | Protection | Replacement of YTG Relays | PS Network Asset Replacement | Input_Prog_Commit | 0 | 2014 | 0 | 0 | 0 | 0 | 953174.56 | 894827.3543 | 1361313.1876 | 1115177.9936 | 710336.0258 | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
5150 | Protection | Replacement of RAZFE Relays | PS Network Asset Replacement | Input_Prog_Commit | 0 | 2014 | 0 | 0 | 0 | 0 | 515695.39 | 0 | 214821.5198 | 104110.4618 | 104110.4618 | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
5541 | Protection | Replacement of Optimho Relays | PS Network Asset Replacement | Input_Prog_Commit | 0 | 2014 | 0 | 0 | 0 | 0 | 28456.62 | 0 | 213055.5645 | 105722.0088 | 678178.1697 | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
5921 | Protection | Replacement of D202,D203,D21SE,D22SE Transformer Differential Relays | PS Network Asset Replacement | Input_Prog_Commit | 0 | 2014 | 0 | 0 | 0 | 0 | 901778.34 | 219733.2407 | 137868.9318 | 273086.3383 | 126565.81 | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
5922 | Protection | Replacement of DB Transformer Differential Relays | PS Network Asset Replacement | Input_Prog_Commit | 0 | 2014 | 0 | 0 | 0 | 0 | 998355.41 | 285044.4285 | 605907.2498 | 731258.7899 | 192639.783 | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
5929 | Protection | Replacement of Feeder OC & EF Protection | PS Network Asset Replacement | Input_Prog_Commit | 0 | 2014 | 0 | 0 | 0 | 0 | 95618.82 | 195019.6416 | 104110.4618 | 52055.2309 | 260276.1544 | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
6291 | Protection | GPS Clocks | PS Network Asset Replacement | Input_Prog_Commit | 0 | 2014 | 0 | 0 | 0 | 0 | 146990.16 | 131809.4363 | 131809.4363 | 105447.549 | 79085.6618 | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
6351 | Protection | Replacement of Siemens 7SA502 & 7SA511 Relays | PS Network Asset Replacement | Input_Prog_Commit | 0 | 2014 | 0 | 0 | 0 | 0 | 30000 | 0 | 0 | 0 | 0 | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
6353 | Protection | Replacement of HO2 Pilot Wire Relays | PS Network Asset Replacement | Input_Prog_Commit | 0 | 2014 | 0 | 0 | 0 | 0 | 83553.52 | 276715.1738 | 0 | 0 | 0 | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
6612 | Protection | Relay Replacement For 940/941 132kV Feeders | PS Network Asset Replacement | Input_Prog_Commit | 0 | 2013 | -38.5498 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
6725 | Protection | Replacement of MBCI Pilot Wire Relays | PS Network Asset Replacement | Input_Prog_Commit | 0 | 2014 | 0 | 0 | 0 | 0 | 210249.19 | 157326.302 | 0 | 0 | 0 | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
6865 | Protection | Replacement of Quadramho Relays | PS Network Asset Replacement | Input_Prog_Commit | 0 | 2014 | 0 | 0 | 0 | 0 | 30000 | 155947.6967 | 488786.5879 | 107333.5558 | 1144801.984 | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
6866 | Protection | Replacement of 7SA513 Relays | PS Network Asset Replacement | Input_Prog_Commit | 0 | 2014 | 0 | 0 | 0 | 0 | 28683.24 | 270667.1115 | 0 | 0 | 380470.3498 | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
7576 | Protection | Remote Interrogation of Protection Relays | PS Network Asset Replacement | Input_Prog_Commit | 0 | 2014 | 0 | 0 | 0 | 0 | 86468.15 | 0 | 0 | 0 | 0 | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
7746 | Protection | Replacement of EDMI Fault Recorders | PS Network Asset Replacement | Input_Prog_Commit | 0 | 2014 | 0 | 0 | 0 | 0 | 29534.54 | 0 | 0 | 0 | 0 | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
7747 | Protection | Install Fault Recorders | PS Network Asset Replacement | Input_Prog_Commit | 0 | 2014 | 0 | 0 | 0 | 0 | 315833.55 | 475511.4002 | 0 | 0 | 75548.3354 | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
7750 | Protection | Replacement of 7SD511 Relays | PS Network Asset Replacement | Input_Prog_Commit | 0 | 2014 | 0 | 0 | 0 | 0 | 207431.23 | 169726.494 | 0 | 107333.5558 | 193316.1563 | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
8266 | Protection | Efficient Relay Replacements | PS Network Asset Replacement | Input_Prog_Commit | 0 | 2014 | 0 | 0 | 0 | 0 | 99286.81 | 67608.7033 | 0 | 0 | 0 | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
0 | Protection | Network Asset Replacement | PS Network Asset Replacement | Input_Prog_Commit | 0 | 2013 | 3935376.8883 | 5300873.8838 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
0 | Protection | Network Asset Replacement | PS Network Asset Replacement | Input_Prog_Commit | 0 | 2013 | 0 | 0 | 6892164.5226 | 7010155.6106 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
6702 | SCADA | Data Centre Infrastructure | PS Network Asset Replacement | Input_Prog_Commit | 0 | 2014 | 0 | 0 | 0 | 0 | 63000 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
7910 | SCADA | Sydney North SCADA Fibre Marshalling Kiosk | PS Network Asset Replacement | Input_Prog_Commit | 0 | 2013 | 0 | 0 | 0 | 141436.2608 | 0 | 0 | 0 | 0 | 0 | 0% | 30% | 25% | 45% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
0 | SCADA | Network Asset Replacement | PS Network Asset Replacement | Input_Prog_Commit | 0 | 2013 | 1481023.3347 | 1669809.5524 | 1505378.8628 | 875306.6495 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
4882 | Substations | Transformer and Reactor Life Extension | PS Network Asset Replacement | Input_Prog_Commit | 0 | 2013 | 0 | 45908.4948 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 95% | 5% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
4882 | Substations | Transformer and Reactor Life Extension | PS Network Asset Replacement | Input_Prog_Commit | 0 | 2014 | 0 | 0 | 0 | 0 | 1229767.99 | 1672635.403 | 1357883.1598 | 1937337.6463 | 2096757.5095 | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
4884 | Substations | Unplanned Transformer and Reactor Replacement | PS Network Asset Replacement | Input_Prog_Commit | 0 | 2013 | 0 | 0 | 0 | -4471.8787 | 0 | 0 | 0 | 0 | 0 | 0% | 95% | 5% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
4904 | Substations | Replacement of ABB 132kV HLD CBs | PS Network Asset Replacement | Input_Prog_Commit | 0 | 2014 | 0 | 0 | 0 | 0 | 904575.7912 | 328900.9578 | 584375.4313 | 876563.147 | 146093.8578 | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
4905 | Substations | Replacement of DELLE 66kV HPGE CBs | PS Network Asset Replacement | Input_Prog_Commit | 0 | 2014 | 0 | 0 | 0 | 0 | 4505.17 | 42000 | 0 | 1199660 | 218120 | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
4906 | Substations | Replacement of Instrument Transformers with No Sampling Point | PS Network Asset Replacement | Input_Prog_Commit | 0 | 2014 | 0 | 0 | 0 | 0 | 92539 | 44058.5732 | 264351.4393 | 484645.0661 | 176234.8 | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
4907 | Substations | Replacement of Substation Batteries - 50V As Required | PS Network Asset Replacement | Input_Prog_Commit | 0 | 2014 | 0 | 0 | 0 | 0 | 176623 | 115096.8 | 60468.1 | 155608.0904 | 100979.3904 | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
4908 | Substations | Replacement of Substation Batteries - 110V As Required | PS Network Asset Replacement | Input_Prog_Commit | 0 | 2014 | 0 | 0 | 0 | 0 | 304594.4 | 127382.367 | 38891.7101 | 122485.1304 | 122485.1304 | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
4909 | Substations | Replacement of Substation Batteries - 240V As Required | PS Network Asset Replacement | Input_Prog_Commit | 0 | 2014 | 0 | 0 | 0 | 0 | 50122.29 | 0 | 0 | 0 | 0 | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
4910 | Substations | Replacement of High DGA Instrument Transformers 132kV As Required | PS Network Asset Replacement | Input_Prog_Commit | 0 | 2014 | 0 | 0 | 0 | 0 | 190208.27 | 330671.4855 | 1126394.8697 | 206914.2855 | 211114.4 | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
4914 | Substations | Replacement of Isolators & Earth Switches > 220kV | PS Network Asset Replacement | Input_Prog_Commit | 0 | 2014 | 0 | 0 | 0 | 0 | 224045.88 | 396893.1775 | 396893.1775 | 396893.1775 | 396893.1775 | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
4915 | Substations | Replacement of Isolators & Earth Switches 132kV | PS Network Asset Replacement | Input_Prog_Commit | 0 | 2014 | 0 | 0 | 0 | 0 | 350000 | 119078.863 | 119078.863 | 119078.863 | 119078.863 | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
4920 | Substations | Condition Monitoring DGA | PS Network Asset Replacement | Input_Prog_Commit | 0 | 2014 | 0 | 0 | 0 | 0 | 13555.63 | 0 | 0 | 0 | 0 | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
4928 | Substations | Replacement of Current Transformers | PS Network Asset Replacement | Input_Prog_Commit | 0 | 2014 | 0 | 0 | 0 | 0 | 147261.73 | 286443.5494 | 81048.3729 | 324193.4916 | 132175.7197 | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
4929 | Substations | Replacement of Ducon CTs and CVTs | PS Network Asset Replacement | Input_Prog_Commit | 0 | 2014 | 0 | 0 | 0 | 0 | 856591.48 | 370258.7 | 0 | 0 | 0 | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
5085 | Substations | Replacement of High DGA Instrument Transformers > 220kV As Required | PS Network Asset Replacement | Input_Prog_Commit | 0 | 2014 | 0 | 0 | 0 | 0 | 839312.3 | 702276.226 | 842730 | 702275 | 978985.616 | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
5087 | Substations | Replacement of High DGA Instrument Transformers < 66kV As Required | PS Network Asset Replacement | Input_Prog_Commit | 0 | 2014 | 0 | 0 | 0 | 0 | -5656.23 | 109117.4 | 169308.3 | 126719.6 | 128189.6 | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
5517 | Substations | Replacement of Merlin Gerin FA2 CBs | PS Network Asset Replacement | Input_Prog_Commit | 0 | 2014 | 0 | 0 | 0 | 0 | 3244920.67 | 1964249.1353 | 1415207.5451 | 283041.5451 | 1415207.5902 | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
5519 | Substations | Replacement of Sprecher & Schuh CBs | PS Network Asset Replacement | Input_Prog_Commit | 0 | 2014 | 0 | 0 | 0 | 0 | 253771.94 | 0 | 0 | 0 | 0 | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
5916 | Substations | Replacement of CBs Approaching Rated Operations | PS Network Asset Replacement | Input_Prog_Commit | 0 | 2014 | 0 | 0 | 0 | 0 | 1080000 | 0 | 0 | 0 | 0 | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
6103 | Substations | Sydney South Substation 330kV Bus Coupling | PS Network Asset Replacement | Input_Prog_Commit | 0 | 2013 | 3410.5914 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
6338 | Substations | Security Fence Disturbance Detection | PS Network Asset Replacement | Input_Prog_Commit | 0 | 2014 | 0 | 0 | 0 | 0 | 20589.44 | 0 | 70000 | 0 | 0 | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
6340 | Substations | Security Lighting Upgrade | PS Network Asset Replacement | Input_Prog_Commit | 0 | 2014 | 0 | 0 | 0 | 0 | 63189.1 | 87500 | 748330.1 | 417601.8 | 877265.9 | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
7308 | Substations | Replacment of Capacitor CBs | PS Network Asset Replacement | Input_Prog_Commit | 0 | 2013 | 265.3715 | -178.8011 | 0 | -8677.7107 | 0 | 0 | 0 | 0 | 0 | 0% | 90% | 5% | 5% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
7469 | Substations | Liddell 330kV 84 Line Connection | PS Network Asset Replacement | Input_Prog_Commit | 0 | 2014 | 0 | 0 | 0 | 0 | 23136.18 | 0 | 0 | 0 | 0 | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
7753 | Substations | SF6 CT Monitoring | PS Network Asset Replacement | Input_Prog_Commit | 0 | 2014 | 0 | 0 | 0 | 0 | 29321.77 | 0 | 0 | 0 | 0 | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
8273 | Substations | Online Condition Monitoring | PS Network Asset Replacement | Input_Prog_Commit | 0 | 2014 | 0 | 0 | 0 | 0 | 126699 | 42155.4059 | 179055.8309 | 370242.5678 | 88252.9962 | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
0 | Substations | Network Asset Replacement | PS Network Asset Replacement | Input_Prog_Commit | 0 | 2013 | -6.0355 | 31754.3952 | 0 | 2910.9537 | 0 | 0 | 0 | 0 | 0 | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
0 | Substations | Network Asset Replacement | PS Network Asset Replacement | Input_Prog_Commit | 0 | 2013 | 4870294.0465 | 3855778.5856 | 5604808.9185 | 5805952.6551 | 0 | 0 | 0 | 0 | 0 | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
0 | Substations | Network Asset Replacement | PS Network Asset Replacement | Input_Prog_Commit | 0 | 2013 | 9520017.4576 | 7984801.8582 | 8658982.6988 | 4875642.3049 | 0 | 0 | 0 | 0 | 0 | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
0 | Substations | Network Asset Replacement | PS Network Asset Replacement | Input_Prog_Commit | 0 | 2013 | 3207529.813 | 2868049.7807 | 2932580.3051 | 11170059.9115 | 0 | 0 | 0 | 0 | 0 | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
0 | Substations | Network Asset Replacement | PS Network Asset Replacement | Input_Prog_Commit | 0 | 2013 | 183472.3668 | 382133.726 | 183427.0877 | 99526.2573 | 0 | 0 | 0 | 0 | 0 | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
0 | Substations | Network Asset Replacement | PS Network Asset Replacement | Input_Prog_Commit | 0 | 2013 | 6201263.0376 | 1659215.4393 | 154953.1425 | 1949067.5556 | 0 | 0 | 0 | 0 | 0 | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
4939 | Transmission Lines | Aging Wood Poles | PS Network Asset Replacement | Input_Prog_Commit | 0 | 2014 | 0 | 0 | 0 | 0 | 3080503.11 | 1050000 | 0 | 0 | 0 | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
4943 | Transmission Lines | Emergency Structures (Guyed Masts) | PS Network Asset Replacement | Input_Prog_Commit | 0 | 2013 | 118930.2552 | 61167.0884 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
0 | Transmission Lines | Transmission Line Minor Upgrades | PS Network Asset Replacement | Input_Prog_Commit | 0 | 2013 | 945714.2497 | 763939.5774 | 922721.5813 | 228323.6158 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
0 | Transmission Lines | Network Asset Replacement | PS Network Asset Replacement | Input_Prog_Commit | 0 | 2013 | 7452479.6363 | 3342284.484 | 2241130.776 | 2557751.1884 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
8165 | Misc Assets & Office Equipment | Misc Assets & Office Equipment | PS Network-Other | Input_Prog_Commit | 0 | 2014 | 0 | 0 | 0 | 0 | 2070254 | 2502731 | 1445000 | 1511000 | 1165000 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
4931 | Substations | CCTV | PS Security/Compliance | Input_Prog_Commit | 0 | 2013 | 1036481.2285 | 79593.7359 | 85255.773 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
4979 | Substations | RRS Security | PS Security/Compliance | Input_Prog_Commit | 0 | 2013 | 293002.0786 | 112253.0785 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
5071 | Substations | Security Perimeter Fence | PS Security/Compliance | Input_Prog_Commit | 0 | 2013 | 2507518.9958 | 1199763.148 | 1086343.9484 | 377653.3828 | 0 | 0 | 0 | 0 | 0 | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
5073 | Substations | Replace Lock & Key System | PS Security/Compliance | Input_Prog_Commit | 0 | 2013 | 88209.6458 | 49634.8401 | 3795.1458 | -16943.103 | 0 | 0 | 0 | 0 | 0 | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
5077 | Substations | Security Delineation Fence | PS Security/Compliance | Input_Prog_Commit | 0 | 2013 | 1805429.1203 | 1062951.5483 | 57534.8028 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
5100 | Substations | Intrusion Detection | PS Security/Compliance | Input_Prog_Commit | 0 | 2013 | 1605207.1035 | 458045.9421 | 5575.4602 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
6337 | Substations | Security Fence Replace D-Pales | PS Security/Compliance | Input_Prog_Commit | 0 | 2013 | 752001.3635 | 1533.8749 | 115942.453 | 172459.416 | 0 | 0 | 0 | 0 | 0 | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
6338 | Substations | Fence Disturbance Detection | PS Security/Compliance | Input_Prog_Commit | 0 | 2013 | 0 | 0 | 24439.6955 | 388588.989 | 0 | 0 | 0 | 0 | 0 | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
6340 | Substations | Security Lighting Upgrade | PS Security/Compliance | Input_Prog_Commit | 0 | 2013 | 0 | 226844.5613 | 188093.7998 | 77886.6193 | 0 | 0 | 0 | 0 | 0 | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
7076 | Substations | Southern Region | PS Security/Compliance | Input_Prog_Commit | 0 | 2013 | 0 | 0 | 0 | 4059.9866 | 0 | 0 | 0 | 0 | 0 | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
0 | Information Technology | ICT Applications | PS Information Technology | Input_Prog_Future | 0 | 2013 | 0 | 0 | 0 | 0 | 0 | 11350000 | 10650000 | 10750000 | 9950000 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
0 | Information Technology | ICT Corporate Data Network | PS Information Technology | Input_Prog_Future | 0 | 2013 | 0 | 0 | 0 | 0 | 0 | 2750000 | 3750000 | 3000000 | 2000000 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
0 | Information Technology | ICT Infrastructure | PS Information Technology | Input_Prog_Future | 0 | 2013 | 0 | 0 | 0 | 0 | 0 | 4700000 | 4700000 | 3850000 | 8250000 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
4907 | Communications | 50V Batteries | PS Network Asset Replacement | Input_Prog_Future | 0 | 2013 | 0 | 0 | 0 | 0 | 0 | 202556.2 | 243068 | 162045.1 | 202556.2 | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 68.43% | 31.57% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
5068 | Communications | 50V Battery Chargers | PS Network Asset Replacement | Input_Prog_Future | 0 | 2013 | 0 | 0 | 0 | 0 | 0 | 58849 | 117697.3 | 98081.2 | 137314.1 | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 45.4% | 54.6% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
4972 | Communications | 50V Power Systems | PS Network Asset Replacement | Input_Prog_Future | 0 | 2014 | 0 | 0 | 0 | 0 | 0 | 98189.728 | 145975.9817 | 145975.9817 | 97317.3212 | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
8222 | Communications | Hammonds Hill Radio Repeater Site Mains Power | PS Network Asset Replacement | Input_Prog_Future | 0 | 2014 | 0 | 0 | 0 | 0 | 0 | 35000 | 0 | 0 | 0 | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
8260 | Communications | CAS and BAS Equipment | PS Network Asset Replacement | Input_Prog_Future | 0 | 2014 | 0 | 0 | 0 | 0 | 0 | 201894.4301 | 190018.2871 | 201894.4301 | 201894.4301 | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
7770 | Metering | Replacement of E1 Meters | PS Network Asset Replacement | Input_Prog_Future | 0 | 2014 | 0 | 0 | 0 | 0 | 0 | 0 | 225716.0873 | 0 | 0 | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
8043 | Metering | Replacement of EDMI MK III Energy Meters | PS Network Asset Replacement | Input_Prog_Future | 0 | 2014 | 0 | 0 | 0 | 0 | 0 | 137104.8155 | 8476.1834 | 64870.0438 | 24849.8532 | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
4949 | Protection | Replacement of D202 Relays | PS Network Asset Replacement | Input_Prog_Future | 0 | 2014 | 0 | 0 | 0 | 0 | 0 | 68934.4659 | 0 | 0 | 0 | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
4956 | Protection | Replacement of TH1A Relays | PS Network Asset Replacement | Input_Prog_Future | 0 | 2014 | 0 | 0 | 0 | 0 | 0 | 60131.6994 | 0 | 0 | 0 | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
5919 | Protection | Replacement of THR Relays | PS Network Asset Replacement | Input_Prog_Future | 0 | 2014 | 0 | 0 | 0 | 0 | 0 | 0 | 6464.9215 | 565226.6985 | 1250916.0603 | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
5920 | Protection | Replacement of YTG Relays | PS Network Asset Replacement | Input_Prog_Future | 0 | 2014 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 419228.9491 | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
6864 | Protection | Replacement of Micromho Relays | PS Network Asset Replacement | Input_Prog_Future | 0 | 2014 | 0 | 0 | 0 | 0 | 0 | 383263.989 | 0 | 0 | 479272.9941 | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
7556 | Protection | Replacement of RADSB Transformer Differential Relays | PS Network Asset Replacement | Input_Prog_Future | 0 | 2014 | 0 | 0 | 0 | 0 | 0 | 131230.288 | 135217.4065 | 65615.144 | 137868.9318 | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
7748 | Protection | Replacement of DLN90 Relays | PS Network Asset Replacement | Input_Prog_Future | 0 | 2014 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
8020 | Protection | Replacement of LFCB102 Relays | PS Network Asset Replacement | Input_Prog_Future | 0 | 2014 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 80110.4004 | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
8261 | Protection | Secondary System Technology Upgrades | PS Network Asset Replacement | Input_Prog_Future | 0 | 2014 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2809671.6161 | 1456870.3049 | 0% | 0% | 84.52% | 15.48% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
5518 | Substations | Replacement of Merlin Gerin FA4 CBs | PS Network Asset Replacement | Input_Prog_Future | 0 | 2014 | 0 | 0 | 0 | 0 | 0 | 608783.0902 | 1521957.6353 | 1217566.1353 | 0 | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
6860 | Substations | Replacement of ASEA 66kV HLR CBs | PS Network Asset Replacement | Input_Prog_Future | 0 | 2014 | 0 | 0 | 0 | 0 | 0 | 0 | 327180 | 109060 | 0 | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
6861 | Substations | Replacement of Magrini 11kV MAG12MG500 CBs | PS Network Asset Replacement | Input_Prog_Future | 0 | 2014 | 0 | 0 | 0 | 0 | 0 | 109059.7589 | 0 | 0 | 0 | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
6862 | Substations | Replacement of Siemens 330kV 3AQ2 CBs | PS Network Asset Replacement | Input_Prog_Future | 0 | 2014 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 566083.0451 | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
6863 | Substations | Replacement of Siemens 330kV 3AS2 CBs | PS Network Asset Replacement | Input_Prog_Future | 0 | 2014 | 0 | 0 | 0 | 0 | 0 | 566083 | 566083 | 283041.5 | 0 | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
7308 | Substations | Replacement of Capacitor CBs | PS Network Asset Replacement | Input_Prog_Future | 0 | 2014 | 0 | 0 | 0 | 0 | 0 | 294409.8713 | 678089.1784 | 857940.5497 | 790815.614 | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
7799 | Substations | Replacement of Sprecher HGF215 CBs | PS Network Asset Replacement | Input_Prog_Future | 0 | 2014 | 0 | 0 | 0 | 0 | 0 | 126000 | 0 | 0 | 0 | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
8082 | Substations | Replacement of Sprecher HGF215 CBs | PS Network Asset Replacement | Input_Prog_Future | 0 | 2014 | 0 | 0 | 0 | 0 | 0 | 0 | 283041.5451 | 283041.5451 | 283041.5451 | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
8101 | Substations | Replacement of Magrini MAG38MGE-0 CBs | PS Network Asset Replacement | Input_Prog_Future | 0 | 2014 | 0 | 0 | 0 | 0 | 0 | 0 | 536512.9545 | 670641.1931 | 268256.4773 | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
4918 | Substations | Removal of PCB from In Service Equipment | PS Network Asset Replacement | Input_Prog_Future | 0 | 2014 | 0 | 0 | 0 | 0 | 0 | 101357.0855 | 105557.2 | 519385.6566 | 0 | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
8253 | Substations | Management of CTs with PCB Contamination | PS Network Asset Replacement | Input_Prog_Future | 0 | 2014 | 0 | 0 | 0 | 0 | 0 | 144540.9119 | 385864.5881 | 107380 | 0 | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
4916 | Substations | Replace Isolator and Earth Switch - 66kV and Below as Required | PS Network Asset Replacement | Input_Prog_Future | 0 | 2014 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 92142.863 | 92142.863 | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
5066 | Substations | 110V Battery Chargers | PS Network Asset Replacement | Input_Prog_Future | 0 | 2014 | 0 | 0 | 0 | 0 | 0 | 65692.4278 | 43794.9519 | 65692.4278 | 65692.4278 | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
5068 | Substations | 50V Battery Chargers | PS Network Asset Replacement | Input_Prog_Future | 0 | 2014 | 0 | 0 | 0 | 0 | 0 | 58848.8408 | 19616.2803 | 19616.2803 | 0 | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
8274 | Substations | Fault Throwing Switches | PS Network Asset Replacement | Input_Prog_Future | 0 | 2014 | 0 | 0 | 0 | 0 | 0 | 140000 | 0 | 0 | 0 | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
6370 | Cable Minor Projects | 42 Cable Tunnel Life Extension | PS Augmentation | Input_Proj_Commit | 2011 | 2013 | 30698.1382 | 33877.2473 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
5657 | Capacitor Bank | Muswellbrook No.1 132kV Capacitor Bank Detuning | PS Augmentation | Input_Proj_Commit | 2010 | 2013 | -80.4021 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
6234 | Capacitor Bank | Capacitor Banks | PS Augmentation | Input_Proj_Commit | 2010 | 2013 | 6.9013 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
6192 | Capacitor Bank | Beryl 66kV Capacitor Bank | PS Augmentation | Input_Proj_Commit | 2011 | 2013 | 193.8394 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
6211 | Capacitor Bank | Sydney North & East 330kV 2 x 200 MVAr Capacitor Banks | PS Augmentation | Input_Proj_Commit | 2011 | 2013 | 105206.4713 | 554764.8041 | -17865.7352 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 99% | 1% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
6241 | Capacitor Bank | Sydney North & East 330kV 2 x 200 MVAr Capacitor Banks | PS Augmentation | Input_Proj_Commit | 2011 | 2013 | 0 | -491.2459 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
6258 | Capacitor Bank | Regentville 330kV Capacitor Bank | PS Augmentation | Input_Proj_Commit | 2011 | 2013 | 0 | -202.2735 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 99% | 1% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
6384 | Capacitor Bank | Sydney Area 200MVAr Capacitor Bank | PS Augmentation | Input_Proj_Commit | 2011 | 2013 | -0.2117 | -1581.099 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 99% | 1% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
6579 | Capacitor Bank | Beryl No.2 66kV Capacitor Bank | PS Augmentation | Input_Proj_Commit | 2011 | 2013 | 1944723.7478 | 1049022.6489 | 224336.1094 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 94% | 6% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
6936 | Capacitor Bank | Capacitor Banks | PS Augmentation | Input_Proj_Commit | 2011 | 2013 | 0 | 9.391 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
7268 | Capacitor Bank | Regentville 132kV Capacitor Bank | PS Augmentation | Input_Proj_Commit | 2011 | 2013 | 0 | 3829.1766 | 3233.7281 | -6801.5275 | 0 | 0 | 0 | 0 | 0 | 0% | 95% | 5% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
7270 | Capacitor Bank | Sydney Area No.2 200MVAr Capacitor Bank | PS Augmentation | Input_Proj_Commit | 2011 | 2013 | 0 | 4735.8481 | -4373.9023 | -260.0581 | 0 | 0 | 0 | 0 | 0 | 0% | 99% | 1% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
7274 | Capacitor Bank | Tumut 132kV Capacitor Bank | PS Augmentation | Input_Proj_Commit | 2011 | 2013 | 0 | 30836.089 | 85.5103 | 0 | -28688.4106 | 0 | 0 | 0 | 0 | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
7326 | Capacitor Bank | Beryl No.2 66kV Capacitor Bank | PS Augmentation | Input_Proj_Commit | 2011 | 2013 | 0 | 0 | 268.9129 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 99% | 1% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
7828 | Capacitor Bank | Port Macquarie No.3 Capacitor Bank | PS Augmentation | Input_Proj_Commit | 2012 | 2013 | 0 | 0 | 2372.2977 | 2347.3827 | 0 | 0 | 0 | 0 | 0 | 0% | 90% | 5% | 5% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
6239 | Capacitor Bank | Tamworth Capacitor Banks | PS Augmentation | Input_Proj_Commit | 2013 | 2013 | 1879.2039 | 0 | 0 | -1623.2831 | 0 | 0 | 0 | 0 | 0 | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
7269 | Capacitor Bank | Sydney South 200 MVAr Capacitor Bank | PS Augmentation | Input_Proj_Commit | 2014 | 2013 | 0 | 29921.0699 | 90937.8 | 1275232.6634 | 3680346 | 0 | 0 | 0 | 0 | 0% | 90% | 5% | 5% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
6383 | Capacitor Bank | Canberra 132kV 120MVAr Capacitor Bank | PS Augmentation | Input_Proj_Commit | 2015 | 2013 | -6.3191 | -9539.9128 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
7265 | Capacitor Bank | Canberra 132kV 120MVAr Capacitor Bank | PS Augmentation | Input_Proj_Commit | 2015 | 2013 | 0 | 6941.0205 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 99% | 1% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
7266 | Capacitor Bank | Canberra 132kV 120MVAr Capacitor Bank | PS Augmentation | Input_Proj_Commit | 2015 | 2013 | -5.6205 | 223.2147 | 0 | 90436.5589 | 2728773.89 | 774639.93 | 0 | 0 | 0 | 0% | 95% | 5% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
7276 | Capacitor Bank | Yass 132kV 80MVAr Capacitor Bank | PS Augmentation | Input_Proj_Commit | 2015 | 2013 | -5.1654 | 4467.1764 | 1618.4384 | 81698.0799 | 2103212.69 | 1187443.63 | 0 | 0 | 0 | 0% | 95% | 5% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
5893 | Capacity of Armidale to Coffs Harbour | Armidale 132kV Phase Shifting Transformer | PS Augmentation | Input_Proj_Commit | 2011 | 2013 | 14084.9478 | 7231.8009 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
6719 | Capacity of Armidale to Coffs Harbour | Line 96C Armidale to Coffs Harbour Upgrade | PS Augmentation | Input_Proj_Commit | 2011 | 2013 | 334261.8371 | 4105600.8067 | 571275.5495 | 86766.2649 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
5907 | Capacity of Coffs Harbour to Kempsey | Coffs Harbour to Kempsey Transmission Line Upgrade from 66kV to 132kV | PS Augmentation | Input_Proj_Commit | 2010 | 2013 | 2690761.2345 | 261866.2995 | 40011.6009 | 34582.0538 | 0 | 0 | 0 | 0 | 0 | 90.02% | 0% | 0% | 0% | 9.981% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
3912 | Capacity of Kempsey to Port Macquarie | Kempsey to Port Macquarie 132kV Transmission Line | PS Augmentation | Input_Proj_Commit | 2012 | 2013 | 11283339.2645 | 11024603.2243 | 7096165.6657 | 278178.3872 | 0 | 0 | 0 | 0 | 0 | 85% | 5% | 0% | 0% | 10% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
5553 | Capacity of Queensland to NSW Interconnector | Bulli Creek to Dumaresq Terminal Equipment Upgrade | PS Augmentation | Input_Proj_Commit | 2013 | 2013 | 165.9802 | 0 | 0 | -4877.9219 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
6098 | Capacity of Queensland to NSW Interconnector | Armidale 330kV Static VAR Compensator | PS Augmentation | Input_Proj_Commit | 2013 | 2013 | 497.2209 | 3771.3635 | 23527.8701 | 12627.5218 | 0 | 0 | 0 | 0 | 0 | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
7674 | Capacity of Queensland to NSW Interconnector | Tamworth 330kV Switching Station | PS Augmentation | Input_Proj_Commit | 2013 | 2013 | 0 | 0 | 34488.1392 | -33576.2805 | 0 | 0 | 0 | 0 | 0 | 5% | 80% | 2.5% | 2.5% | 10% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
7339 | Capacity of Queensland to NSW Interconnector | Reinforcement of NSW to Queensland Interconnection Capacity | PS Augmentation | Input_Proj_Commit | 2013 | 2013 | 0 | 0 | 680696.5891 | 1032942.5343 | -1648817.8691 | 0 | 0 | 0 | 0 | 3.645% | 96.36% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
5932 | Capacity of Snowy Lines | Snowy Assets Rehabilitation of 64, 65 and 66 Lines | PS Augmentation | Input_Proj_Commit | 2009 | 2013 | 15363.0093 | 45450.9181 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 98.33% | 0% | 0% | 0% | 1.673% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
5964 | Capacity of Tamworth to Armidale | 86 Line Tamworth to Armidale 330kV Transmission Line Uprating | PS Augmentation | Input_Proj_Commit | 2011 | 2013 | 613528.4593 | 2480722.9945 | -159968.2639 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
6925 | Capacity of Victoria to NSW Interconnector | Yass 132kV 80MVAr Capacitor Bank | PS Augmentation | Input_Proj_Commit | 2015 | 2013 | 0 | 0 | 0 | 40403.4254 | 0 | 0 | 0 | 0 | 0 | 0% | 90% | 5% | 5% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
6925 | Capacity of Victoria to NSW Interconnector | Yass 132kV 80MVAr Capacitor Bank | PS Augmentation | Input_Proj_Commit | 2015 | 2013 | 0 | 0 | 0 | 40403.4254 | 0 | 0 | 0 | 0 | 0 | 0% | 90% | 5% | 5% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
7407 | Capacity of Yass to Marulan | Yass to Bannaby and Marulan 330kV Line Uprating | PS Augmentation | Input_Proj_Commit | 2013 | 2013 | 0 | 0 | 15115.6109 | -7453.1413 | 0 | 0 | 0 | 0 | 0 | 90% | 10% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
6971 | Communications | Lismore Marshalling Kiosk Installation | PS Augmentation | Input_Proj_Commit | 2010 | 2013 | 22173.7026 | 369.4004 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
6876 | Communications | Sydney West Protection/Communications Upgrade | PS Augmentation | Input_Proj_Commit | 2011 | 2013 | 97450.5978 | 449347.1319 | 29254.9528 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
7064 | Communications | Tuggerah Provision of Fibre Marshalling Kiosk | PS Augmentation | Input_Proj_Commit | 2011 | 2013 | 0 | 2672.4294 | 842.8118 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
7278 | Communications | Albury to Mulwala Tripping Scheme | PS Augmentation | Input_Proj_Commit | 2011 | 2013 | 0 | 68404.0136 | -67034.8529 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
6973 | Communications | Murray Substation Station & Lower Tumut Switching Station OPGW & Protection Upgrade | PS Augmentation | Input_Proj_Commit | 2012 | 2013 | 567999.6849 | 260294.6432 | 492451.6581 | -686.9893 | 0 | 0 | 0 | 0 | 0 | 0% | 30% | 25% | 45% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
7530 | Communications | Vales Point DNSP Communications Upgrade | PS Augmentation | Input_Proj_Commit | 2012 | 2013 | 0 | 5074.7613 | 82624.0567 | 654.0681 | 0 | 0 | 0 | 0 | 0 | 0% | 30% | 25% | 45% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
7533 | Communications | Sydney East DNSP Communications Upgrade | PS Augmentation | Input_Proj_Commit | 2012 | 2013 | 0 | 0 | 323973.8055 | 2947.1998 | 0 | 0 | 0 | 0 | 0 | 0% | 30% | 25% | 45% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
6875 | Communications | Regentville Protection/Communications Upgrade | PS Augmentation | Input_Proj_Commit | 2013 | 2013 | 122367.0651 | 137218.9794 | 136276.7235 | 39720.014 | 0 | 0 | 0 | 0 | 0 | 0% | 30% | 25% | 45% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
7028 | Communications | Armidale - Dumaresq OPGW - OLTE Upgrades | PS Augmentation | Input_Proj_Commit | 2013 | 2013 | 0 | 1817981.2045 | 2615513.4713 | 92485.2258 | 0 | 0 | 0 | 0 | 0 | 0% | 30% | 25% | 45% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
P0001221 | Communications | Fibre Connections at Dapto for Endeavour Energy | PS Augmentation | Input_Proj_Commit | 2014 | 2013 | 0 | 0 | 0 | 0 | 101434.89 | 0 | 0 | 0 | 0 | 0% | 45% | 5% | 50% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
5645 | Control System | Armidale Static VAR Compensator Power Oscillation Damper | PS Augmentation | Input_Proj_Commit | 2009 | 2013 | 17542.0488 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
6992 | Control System | Real-Time Line Rating on Lines 8 and 16 | PS Augmentation | Input_Proj_Commit | 2011 | 2013 | 277.3429 | 82381.6073 | 1278.1589 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
5606 | Control System | SCADA Operations Circuit Breakers Check Synchronism | PS Augmentation | Input_Proj_Commit | 2013 | 2013 | -13.4744 | 0 | 0 | -87012.9179 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
5837 | Control System | SCADA Control For Loadshed of Tomago Aluminum | PS Augmentation | Input_Proj_Commit | 2013 | 2013 | 0 | -8234.3144 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
6457 | Control System | SCADA Control For Loadshed of Tomago Aluminum | PS Augmentation | Input_Proj_Commit | 2013 | 2013 | 1040.2105 | 10325.8649 | 112386.3813 | 452777.0525 | 0 | 0 | 0 | 0 | 0 | 0% | 30% | 25% | 45% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
7564 | Control System | Smart Grid Monitor Installation | PS Augmentation | Input_Proj_Commit | 2013 | 2013 | 0 | 0 | 48136.687 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 30% | 25% | 45% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
7846 | Control System | Current Transducer Installation at Bannaby & Bayswater | PS Augmentation | Input_Proj_Commit | 2013 | 2013 | 0 | 0 | 74920.2045 | 215555.8082 | 0 | 0 | 0 | 0 | 0 | 0% | 30% | 25% | 45% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
7739 | Easements | Bannaby to Yass 500kV Transmission Line | PS Augmentation | Input_Proj_Commit | 2013 | 2013 | 2.6462 | 3164.4398 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60% | 25% | 0% | 0% | 15% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
6030 | Fault Level Equipment Upgrade | Munmorah Substation Short Circuit Fault Level Upgrade | PS Augmentation | Input_Proj_Commit | 2010 | 2013 | 1666.6929 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
6041 | Fault Level Equipment Upgrade | Sydney North Fault Level Upgrade | PS Augmentation | Input_Proj_Commit | 2011 | 2013 | 2070513.7357 | 1392095.8323 | 13669.9405 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
6231 | Fault Level Equipment Upgrade | Dapto Fault Level Upgrade | PS Augmentation | Input_Proj_Commit | 2011 | 2013 | 2220716.0685 | 138258.0756 | 0 | 8529.8333 | 0 | 0 | 0 | 0 | 0 | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
6699 | Fault Level Equipment Upgrade | Sydney South Fault Level Upgrade | PS Augmentation | Input_Proj_Commit | 2011 | 2013 | 32074.0562 | -31305.4329 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
7538 | Fault Level Equipment Upgrade | Sydney South Fault Level Upgrade | PS Augmentation | Input_Proj_Commit | 2011 | 2013 | 0 | 30366.9001 | 0 | -28972.2061 | 0 | 0 | 0 | 0 | 0 | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
5840 | Reactor Installation | 41 Cable 330kV Shunt Reactor | PS Augmentation | Input_Proj_Commit | 2011 | 2013 | 9696972.0067 | -448330.0411 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
6184 | Reactor Installation | 41 Cable 330kV Series Reactor | PS Augmentation | Input_Proj_Commit | 2011 | 2013 | 22.281 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
6906 | Reactor Installation | Yass 330kV Shunt Reactor | PS Augmentation | Input_Proj_Commit | 2011 | 2013 | 0 | 66481.4083 | 104457.8494 | 101775.5889 | 0 | 0 | 0 | 0 | 0 | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
5915 | Reinforcement of Supply To The New England Area | Glen Innes to Inverell Transmission Line 132kV Line Bays | PS Augmentation | Input_Proj_Commit | 2012 | 2013 | 219252.0113 | 1887050.5954 | 509802.6713 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
7472 | Reinforcement of the Victoria/NSW Interconnection | Uprating Lines 8, 16 & 18 Between Dapto and Marulan | PS Augmentation | Input_Proj_Commit | 2011 | 2013 | 0 | 0 | 26904.6756 | 148324.7192 | 0 | 0 | 0 | 0 | 0 | 90% | 10% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
7473 | SCADA | Yanco SCADA | PS Augmentation | Input_Proj_Commit | 2012 | 2013 | -1.5454 | -76.0992 | 308741.394 | 41707.5006 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
5830 | SCADA | Provision of SCADA Facilities At Existing 132kV Substations | PS Augmentation | Input_Proj_Commit | 2013 | 2013 | -42.2969 | 9019.5331 | 0 | -120801.9543 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
5951 | SCADA | Provision of SCADA Facilities At Existing 132kV Substations | PS Augmentation | Input_Proj_Commit | 2013 | 2013 | 140.7461 | 0 | 0 | -6163.9989 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
6375 | SCADA | 132kV and 66kV Operational Info To TransGrid & Nemmco | PS Augmentation | Input_Proj_Commit | 2013 | 2013 | -24.4721 | 0 | -37208.502 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
6376 | SCADA | 132kV and 66kV Operational Info To TransGrid & Nemmco | PS Augmentation | Input_Proj_Commit | 2013 | 2013 | -21.3707 | 0 | -64994.0873 | 31637.7913 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
6437 | SCADA | 132kV and 66kV Operational Info To TransGrid & Nemmco | PS Augmentation | Input_Proj_Commit | 2013 | 2013 | -0.73035 | 0 | 0 | -3167.161 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
7292 | SCADA | Finley SCADA | PS Augmentation | Input_Proj_Commit | 2013 | 2013 | 1746.6928 | 141.6606 | 102539.7606 | 254655.4935 | 0 | 0 | 0 | 0 | 0 | 0% | 45% | 5% | 50% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
7640 | SCADA | Inverell SCADA | PS Augmentation | Input_Proj_Commit | 2013 | 2013 | 0 | 0 | 789.7703 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
7368 | Secondary System Renewal | Jindera No.1 and No.2 Transformer Bay Ratings | PS Augmentation | Input_Proj_Commit | 2014 | 2013 | 0 | 0 | 0 | 1508.2855 | 0 | 0 | 0 | 0 | 0 | 0% | 30% | 25% | 45% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
6158 | Substation Minor Projects | Switchbay at Finley | PS Augmentation | Input_Proj_Commit | 2010 | 2013 | 264.3765 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
5378 | Substation Minor Projects | Armidale 330kV Substation Connection of 89 Lismore Line | PS Augmentation | Input_Proj_Commit | 2011 | 2013 | 0 | 32217.2804 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
6374 | Substation Minor Projects | Haymarket Substation Ausgrid 132kV Cables | PS Augmentation | Input_Proj_Commit | 2011 | 2013 | 2098305.5105 | 224542.5309 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
6765 | Substation Minor Projects | Sydney South Feeder 916/917 Protection Replacement | PS Augmentation | Input_Proj_Commit | 2011 | 2013 | 357950.7218 | 135261.5169 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
6821 | Substation Minor Projects | Wallerawang Auxiliary Power Supply Rearrangements | PS Augmentation | Input_Proj_Commit | 2011 | 2013 | 557109.8326 | 72787.8383 | 14753.3879 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
6872 | Substation Minor Projects | Connection to Jesmond Substation | PS Augmentation | Input_Proj_Commit | 2011 | 2013 | 1919.5638 | 44682.3843 | 0 | -44417.7168 | 0 | 0 | 0 | 0 | 0 | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
6223 | Substation Minor Projects | Vineyard Line Bays | PS Augmentation | Input_Proj_Commit | 2012 | 2013 | 0 | -3653.6195 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
6720 | Substation Minor Projects | Manildra 132kV Swithbay | PS Augmentation | Input_Proj_Commit | 2012 | 2013 | -0.75152 | 0 | 0 | -1059.7977 | 0 | 0 | 0 | 0 | 0 | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
6816 | Substation Minor Projects | Port Macquarie 33kV Switchbays and Installation of Auto Reclose Facilities | PS Augmentation | Input_Proj_Commit | 2012 | 2013 | 758625.2571 | 1056272.9735 | 589691.3913 | 878710.0696 | 0 | 0 | 0 | 0 | 0 | 0% | 90% | 5% | 5% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
6102 | Substation Minor Projects | Liddell 84 Line Connection - Additional Circuit Breaker Installation | PS Augmentation | Input_Proj_Commit | 2013 | 2013 | 4453.7868 | -13241.8613 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
6274 | Substation Minor Projects | Newcastle Substation - Provision of 132kV Switchbay | PS Augmentation | Input_Proj_Commit | 2013 | 2013 | 30851.7766 | -32759.8411 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 90% | 5% | 5% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
6607 | Substation Minor Projects | Griffith 132kV Substation - 33kV Connection | PS Augmentation | Input_Proj_Commit | 2013 | 2013 | 825174.7108 | 1350105.6718 | 265777.6637 | 65841.4875 | 0 | 0 | 0 | 0 | 0 | 0% | 90% | 5% | 5% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
7307 | Substation Minor Projects | Newcastle Substation - Provision of 132kV Switchbay | PS Augmentation | Input_Proj_Commit | 2013 | 2013 | 0 | 54058.6104 | 2307.0766 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 90% | 5% | 5% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
7469 | Substation Minor Projects | Liddell 84 Line Connection - Additional Circuit Breaker Installation | PS Augmentation | Input_Proj_Commit | 2013 | 2013 | 0 | 14832.3513 | 505050.0271 | 3717878.7524 | 0 | 0 | 0 | 0 | 0 | 0% | 90% | 5% | 5% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
7511 | Substation Minor Projects | Munmorah - Supply To Lake Munmorah Zone Substation | PS Augmentation | Input_Proj_Commit | 2013 | 2013 | 0 | 1588.7233 | 130615.1454 | 398650.8236 | 0 | 0 | 0 | 0 | 0 | 0% | 90% | 5% | 5% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
7512 | Substation Minor Projects | Vales Point - Supply To Lake Munmorah Zone Substation | PS Augmentation | Input_Proj_Commit | 2013 | 2013 | 0 | 0 | 83212.7372 | 392193.1555 | 0 | 0 | 0 | 0 | 0 | 0% | 90% | 5% | 5% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
7521 | Substation Minor Projects | Newcastle 952 Feeder Connection to Rathmines | PS Augmentation | Input_Proj_Commit | 2013 | 2013 | 0 | 13014.9687 | 206555.4289 | 118431.5169 | 0 | 0 | 0 | 0 | 0 | 0% | 90% | 5% | 5% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
7683 | Substation Minor Projects | Connection to Morvern Substation | PS Augmentation | Input_Proj_Commit | 2013 | 2013 | 0 | 0 | 0 | 174154.9678 | 0 | 0 | 0 | 0 | 0 | 0% | 90% | 5% | 5% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
7825 | Substation Minor Projects | Connection of Charlestown Zone Substation | PS Augmentation | Input_Proj_Commit | 2013 | 2013 | 0 | 0 | 6166.8845 | 91357.5946 | 0 | 0 | 0 | 0 | 0 | 0% | 90% | 5% | 5% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
7862 | Substation Minor Projects | Sydney North Substation 257 & 258 132kV Feeder Augmentation | PS Augmentation | Input_Proj_Commit | 2013 | 2013 | 0 | 0 | 35857.2958 | 39001.8185 | 0 | 0 | 0 | 0 | 0 | 0% | 90% | 5% | 5% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
6105 | Substation Minor Projects | Sydney West Substation 330kV Bus Coupling | PS Augmentation | Input_Proj_Commit | 2014 | 2013 | 7421.2033 | 0 | 0 | -8949.1059 | 0 | 0 | 0 | 0 | 0 | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
6107 | Substation Minor Projects | Sydney West Substation 20 Line Bus Coupling | PS Augmentation | Input_Proj_Commit | 2014 | 2013 | 9.4416 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
8039 | Substation Minor Projects | Jindera No.1 and No.2 Transformer Bay Ratings | PS Augmentation | Input_Proj_Commit | 2014 | 2013 | 0 | 0 | 0 | 2871.7471 | 63800 | 0 | 0 | 0 | 0 | 0% | 90% | 5% | 5% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
6262 | Substation Renewal | Orange North Substation | PS Augmentation | Input_Proj_Commit | 2010 | 2013 | -8.2032 | 0 | -28028.1952 | -7916.8576 | 0 | 0 | 0 | 0 | 0 | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
5963 | Substation Renewal | Murray Switching Station | PS Augmentation | Input_Proj_Commit | 2012 | 2013 | 2336872.7678 | 5407219.919 | 2546534.672 | 89657.0452 | 0 | 0 | 0 | 0 | 0 | 0% | 90% | 5% | 5% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
6709 | Substation Renewal | Orange North Substation | PS Augmentation | Input_Proj_Commit | 2013 | 2013 | 2401636.873 | 7338410.245 | 16630244.4838 | 4695549.5959 | 0 | 0 | 0 | 0 | 0 | 10% | 70% | 5% | 10% | 5% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
5715 | Supply to ACT | Williamsdale 330/132kV Substation | PS Augmentation | Input_Proj_Commit | 2012 | 2013 | 13351183.0377 | 16631954.9679 | 17943719.1244 | 7863407.3348 | 0 | 0 | 0 | 0 | 0 | 5% | 80% | 2.5% | 2.5% | 10% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
7401 | Supply to Darlington Point | Darling Point to Colleambally 132kV Line | PS Augmentation | Input_Proj_Commit | 2011 | 2013 | 2541.2619 | -235.5501 | 0 | -12422.868 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
6969 | Supply to Gunnedah, Narrabri and Moree | Installation of Phase Shifting Transformer on 969 Line | PS Augmentation | Input_Proj_Commit | 2018 | 2013 | 90388.4203 | 88648.9649 | 23676.6576 | 442320.8735 | 0 | 0 | 0 | 0 | 0 | 85% | 5% | 0% | 0% | 10% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
5714 | Supply to Macarthur | Macarthur 330/132kV Substation | PS Augmentation | Input_Proj_Commit | 2010 | 2013 | 1699167.2846 | 523017.7148 | -1137.7241 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 79.66% | 6.265% | 3.58% | 10.5% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
7400 | Supply to South Coast | Tomerong Substation Establishment | PS Augmentation | Input_Proj_Commit | 2014 | 2013 | 74977.7689 | 39778.81 | 283139.3074 | 338365.1201 | -833973.1598 | 0 | 0 | 0 | 0 | 28.3% | 23.9% | 0% | 0% | 47.8% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
6910 | Supply to Sydney Inner Metropolitan Area and CBD | Beaconsfield West To Haymarket 330kV Cable | PS Augmentation | Input_Proj_Commit | 2014 | 2013 | 7834.2856 | 90019.1432 | 783347.019 | 14466318.7935 | 857461 | 0 | 0 | 0 | 0 | 0% | 5% | 0% | 0% | 20% | 75% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
6704 | Supply to the ACT | Wallaroo 330kV Switching Station | PS Augmentation | Input_Proj_Commit | 2018 | 2013 | 462083.2277 | 410978.306 | 221911.8637 | 9242.3809 | 0 | 0 | 0 | 0 | 0 | 5% | 80% | 2.5% | 2.5% | 10% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
6346 | Supply to the Cabonne Area | Manildra to Parkes 132kV Transmission Line | PS Augmentation | Input_Proj_Commit | 2012 | 2013 | 3541380.8587 | 20900649.5074 | 17251228.9714 | 408437.5779 | 0 | 0 | 0 | 0 | 0 | 85% | 5% | 0% | 0% | 10% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
7147 | Supply to the Cabonne Area | Manildra to Parkes 132kV Transmission Line | PS Augmentation | Input_Proj_Commit | 2012 | 2013 | 0 | 62559.3548 | 1696830.4634 | -14316.47 | 0 | 0 | 0 | 0 | 0 | 0% | 90% | 5% | 5% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
8155 | Supply to the Cabonne Area | Manildra to Parkes 132kV Transmission Line | PS Augmentation | Input_Proj_Commit | 2012 | 2013 | 0 | 0 | 0 | 1886403.6122 | 0 | 0 | 0 | 0 | 0 | 10% | 70% | 5% | 10% | 5% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
6662 | Supply to the Lower Mid North Coast | Tomago-Tarro-Stroud 330/132kV Transmission Line | PS Augmentation | Input_Proj_Commit | 2014 | 2013 | 1468506.5436 | 2423393.6471 | 8652966.8753 | 47513413.9491 | 28748641.44 | 0 | 0 | 0 | 0 | 85% | 5% | 0% | 0% | 10% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
6967 | Supply to the Mid North Coast | Stroud-Taree 330kV Transmission Line Construction | PS Augmentation | Input_Proj_Commit | 2014 | 2013 | 6415.3511 | 258578.2889 | 1146230.2783 | -1357245.2891 | 0 | 0 | 0 | 0 | 0 | 65% | 10% | 0% | 0% | 25% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
5880 | Supply to the New England Area | Glen Innes to Inverell 132kV Transmission Line | PS Augmentation | Input_Proj_Commit | 2012 | 2013 | 7859945.3332 | 9082235.8814 | 7610269.7084 | 769854.9856 | 0 | 0 | 0 | 0 | 0 | 85% | 5% | 0% | 0% | 10% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
7513 | Supply to Tomago | Tomago 330/132kV Substation - Establishment of 132kV Busbar and Connections | PS Augmentation | Input_Proj_Commit | 2014 | 2013 | 0 | 887919.7379 | 8417298.1636 | 5700728.4982 | 43615.21 | 0 | 0 | 0 | 0 | 0.01449% | 89.97% | 4.993% | 4.993% | 0.02898% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
7745 | Supply to Tomago | Sydney South - Tail Ending 91F and 91J | PS Augmentation | Input_Proj_Commit | 2014 | 2013 | 0 | 0 | 15911.2695 | 88851.1155 | 0 | 0 | 0 | 0 | 0 | 0% | 90% | 5% | 5% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
5968 | Supply to Tomago Area | Establishment of 132kV Busbar at Tomago 330kV Substation | PS Augmentation | Input_Proj_Commit | 2011 | 2013 | 22249988.1982 | 14311310.7374 | 738527.7885 | 1355754.9033 | 0 | 0 | 0 | 0 | 0 | 0% | 87.83% | 0% | 0% | 12.17% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
6036 | Supply to Wagga Wagga | Wagga North 132/66kV Substation Establishment | PS Augmentation | Input_Proj_Commit | 2011 | 2013 | 2756229.684 | 556296.4582 | 4737.3766 | -55292.5179 | 0 | 0 | 0 | 0 | 0 | 0% | 95.15% | 0% | 0% | 4.853% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
4419 | Supply to Wellington | Wollar to Wellington 330kV Transmission Line | PS Augmentation | Input_Proj_Commit | 2010 | 2013 | 14957850.1288 | 15000181.4476 | 2835881.5536 | 268790.0687 | 0 | 0 | 0 | 0 | 0 | 99.09% | 0% | 0% | 0% | 0.9108% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
4429 | Supply to Wellington | Wollar 330kV Switching Station | PS Augmentation | Input_Proj_Commit | 2010 | 2013 | 29636995.6247 | 134119.6362 | 375.8564 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 95.95% | 1.999% | 1.999% | 0.05088% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
7644 | SVC Control System Replacement | Armidale SVC Transformer | PS Augmentation | Input_Proj_Commit | 2013 | 2013 | 0 | 0 | 0 | 73577.9781 | -71546.2057 | 0 | 0 | 0 | 0 | 0% | 21.64% | 39.18% | 39.18% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
5670 | Transformer Additions | Parkes No.2 Transformer | PS Augmentation | Input_Proj_Commit | 2009 | 2013 | 3477.1063 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
5816 | Transformer Additions | Tuggerah No.2 Transformer | PS Augmentation | Input_Proj_Commit | 2009 | 2013 | 156424.3103 | 41339.1021 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
5852 | Transformer Additions | Marulan No.2 Transformer | PS Augmentation | Input_Proj_Commit | 2009 | 2013 | -4683.6357 | 0 | 0 | 55192.3546 | 0 | 0 | 0 | 0 | 0 | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
6320 | Transformer Additions | Koolkhan No.3 Transformer | PS Augmentation | Input_Proj_Commit | 2010 | 2013 | 5264739.1285 | 407587.6349 | 148099.9215 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 82% | 18% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
6668 | Transformer Additions | Sydney North No.5 Transformer | PS Augmentation | Input_Proj_Commit | 2011 | 2013 | 8420546.6673 | 6122748.6073 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 100% | 0% | 0% | 0.001066% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
6696 | Transformer Additions | Waratah West No.2 Transformer & Bus Section | PS Augmentation | Input_Proj_Commit | 2011 | 2013 | 10499195.191 | 12243870.8756 | 96543.7043 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 89% | 11% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
6727 | Transformer Additions | Vineyard No.3 Transformer | PS Augmentation | Input_Proj_Commit | 2012 | 2013 | 9044650.4199 | 5311311.3521 | 4244829.4204 | 84375.9466 | 0 | 0 | 0 | 0 | 0 | 0% | 95% | 5% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
6907 | Transformer Additions | Munmorah No.2 Transformer | PS Augmentation | Input_Proj_Commit | 2013 | 2013 | 0 | 2375.7189 | 0 | -2266.5976 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
7456 | Transformer Additions | Eraring No.2 Transformer | PS Augmentation | Input_Proj_Commit | 2013 | 2013 | 0 | 40795.3843 | 3583.1094 | -42476.4579 | 0 | 0 | 0 | 0 | 0 | 0% | 95% | 5% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
7684 | Transformer Additions | Coffs Harbour No. 2 330/132kV Transformer Installation | PS Augmentation | Input_Proj_Commit | 2014 | 2013 | 0 | 0 | 0 | 106075.063 | -103145.9205 | 0 | 0 | 0 | 0 | 2.687% | 92.45% | 4.866% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
7338 | Transformer Replacement | Marulan No.4 Transformer | PS Augmentation | Input_Proj_Commit | 2009 | 2013 | 0 | 0 | 1913.9075 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 95% | 5% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
4563 | Transformer Replacement | Wellington 330kV Transformer Replacement & Shunt Reactor | PS Augmentation | Input_Proj_Commit | 2010 | 2013 | 3223810.3278 | 67949.5156 | 3757.8658 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
5691 | Transformer Replacement | Finley No.1 & No.2 Transformer Replacement | PS Augmentation | Input_Proj_Commit | 2010 | 2013 | 1042818.4044 | 6672.5347 | 22349.2741 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 84% | 16% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
6363 | Transformer Replacement | Sydney South No.3 & No.4 Transformer Replacements | PS Augmentation | Input_Proj_Commit | 2011 | 2013 | 2438179.5241 | 1267833.9982 | 667440.4005 | -44002.4558 | 0 | 0 | 0 | 0 | 0 | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
6446 | Transformer Replacement | Coffs Harbour 132/66kV Transformer Replacements | PS Augmentation | Input_Proj_Commit | 2011 | 2013 | 3690158.3083 | 400319.9023 | 532.0651 | -105677.5243 | 0 | 0 | 0 | 0 | 0 | 0% | 88.88% | 11.12% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
6458 | Transformer Replacement | Cowra 132/66kV Transformer Replacement | PS Augmentation | Input_Proj_Commit | 2011 | 2013 | 6511300.3694 | 302697.6981 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
7093 | Transformer Replacement | Kempsey 66/33kV Transformer Replacement | PS Augmentation | Input_Proj_Commit | 2013 | 2013 | 0 | 49601.7239 | 32509.3954 | 46411.4427 | 0 | 0 | 0 | 0 | 0 | 0% | 95% | 5% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
7633 | Transformer Replacement | Kempsey 66kV Bus and No.2 Transformer Replacement | PS Augmentation | Input_Proj_Commit | 2013 | 2013 | 0 | 0 | 0 | 332.6523 | -323.4665 | 0 | 0 | 0 | 0 | 0% | 35.58% | 64.42% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
7409 | Transformer Replacement | Koolkhan - 967 Line Deviation Works | PS Augmentation | Input_Proj_Commit | 2014 | 2013 | 0 | 88048.4465 | -86286.0348 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
5881 | Transmission Line Rearrangement | 24 Line Vales Point to Newcastle 330kV Turn In | PS Augmentation | Input_Proj_Commit | 2009 | 2013 | 51007.0427 | 5930.1904 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33% | 67% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
7573 | Transmission Line Rearrangement | Koolkhan - 967 Line Deviation Works | PS Augmentation | Input_Proj_Commit | 2014 | 2013 | 0 | 0 | 0 | -139226.9651 | 694998.75 | 0 | 0 | 0 | 0 | 85% | 5% | 0% | 0% | 10% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
7399 | Transmission Line Renewal | 86 Line Tamworth to Armidale Condition | PS Augmentation | Input_Proj_Commit | 2011 | 2013 | 0 | 305.151 | -299.0227 | 0 | 0 | 0 | 0 | 0 | 0 | 90% | 10% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
5940 | Transmission Line Renewal | Tamworth to Gunnedah 66kV Transmission Line Refurbishment | PS Augmentation | Input_Proj_Commit | 2012 | 2013 | 7167986.6613 | 829325.4659 | 262810.1149 | 123017.1001 | 0 | 0 | 0 | 0 | 0 | 85% | 5% | 0% | 0% | 10% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
7705 | Transmission Line Renewal | 964 Line Port Macquarie to Taree Condition | PS Augmentation | Input_Proj_Commit | 2012 | 2013 | 4575.1733 | 1851.558 | -86303.9752 | 29910.1657 | 0 | 0 | 0 | 0 | 0 | 183.7% | -27.9% | 0% | 0% | -55.8% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
5527 | Western 500kV Upgrade | Bayswater 500/330kV Switchyard Development | PS Augmentation | Input_Proj_Commit | 2009 | 2013 | 693842.5543 | 24150.5267 | 16525.8076 | 75203.2325 | 0 | 0 | 0 | 0 | 0 | 0% | 99.94% | 0% | 0% | 0.06453% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
5535 | Western 500kV Upgrade | Mt Piper 500/330kV Switchyard Development | PS Augmentation | Input_Proj_Commit | 2009 | 2013 | 2863136.7936 | 716831.2596 | 170685.4169 | 0 | 0 | 0 | 0 | 0 | 0 | 86% | 14% | 0% | 0% | 1.326e-08% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
5965 | Western 500kV Upgrade | Wallerawang 330kV Fault Rating Upgrade | PS Augmentation | Input_Proj_Commit | 2009 | 2013 | 5933.7745 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
5967 | Western 500kV Upgrade | Uprating of Lines 330kV 8 and 16 Lines | PS Augmentation | Input_Proj_Commit | 2009 | 2013 | 2244.1995 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 0% | -0.001592% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
6229 | Western 500kV Upgrade | Bayswater-Liddell Reduct In Fault Clearing Times | PS Augmentation | Input_Proj_Commit | 2009 | 2013 | 177773.1712 | 5267.1479 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
5864 | Western 500kV Upgrade | Bannaby 500/330kV Substation Development | PS Augmentation | Input_Proj_Commit | 2011 | 2013 | 27199621.1909 | 6040724.7675 | 274825.5642 | 50087.5916 | 0 | 0 | 0 | 0 | 0 | 0% | 90.77% | 4.933% | 2.96% | 1.336% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
6648 | Western Sydney Supply Project | Holroyd 330kV Substation Establishment | PS Augmentation | Input_Proj_Commit | 2014 | 2013 | 1238215.8154 | 5423764.8744 | 19341913.1981 | 30509306.1705 | 21243018.97 | 0 | 0 | 0 | 0 | 5% | 80% | 2.5% | 2.5% | 10% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
6664 | Western Sydney Supply Project | Sydney West to Holroyd 330kV Transmission Line | PS Augmentation | Input_Proj_Commit | 2014 | 2013 | 3429917.3743 | 4550359.7431 | 1807823.9263 | 28395209.0155 | 41101516.35 | 0 | 0 | 0 | 0 | 90% | 10% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
6988 | Western Sydney Supply Project | Sydney West 330kV Connections For Holroyd Substation | PS Augmentation | Input_Proj_Commit | 2014 | 2013 | 30415.1748 | 283199.8745 | 2973128.9696 | 11607463.1226 | 1268171.21 | 0 | 0 | 0 | 0 | 0% | 90% | 5% | 5% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
6650 | Western Sydney Supply Project | Holroyd - Rookwood 330kV Cable | PS Augmentation | Input_Proj_Commit | 2015 | 2013 | 1192041.2624 | 2085540.8219 | 10913680.8458 | 43687716.5206 | 87657484.88 | 1585000 | 0 | 0 | 0 | 0% | 5% | 0% | 0% | 20% | 75% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
6651 | Western Sydney Supply Project | Rookwood Road 330/132kV Substation | PS Augmentation | Input_Proj_Commit | 2015 | 2013 | 4902333.1804 | 5799746.2541 | 15859641.2904 | 35210843.8535 | 35624259.14 | 11381140.91 | 0 | 0 | 0 | 5% | 80% | 2.5% | 2.5% | 10% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
6344 | Protection Change | Sydney West to West Wetherill Park Substation 93M Feeder Protection Upgrade | PS Connections | Input_Proj_Commit | 2009 | 2013 | 38.0947 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
P0001491 | Protection Change | Protection Changes on Macarthur Lines | PS Connections | Input_Proj_Commit | 2014 | 2013 | 0 | 0 | 0 | 0 | 99999.99 | 0 | 0 | 0 | 0 | 0% | 30% | 25% | 45% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
P0001497 | Protection Change | Taree Distance Relay Replacement for Essential Energy | PS Connections | Input_Proj_Commit | 2014 | 2013 | 0 | 0 | 0 | 0 | 141586 | 0 | 0 | 0 | 0 | 0% | 30% | 25% | 45% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
6053 | Substation Minor Projects | Provision of Switchbays at Taree Substation | PS Connections | Input_Proj_Commit | 2009 | 2013 | 1509.5193 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
6287 | Substation Minor Projects | Connection of Morisset Zone Substation | PS Connections | Input_Proj_Commit | 2009 | 2013 | -7.4305 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
6518 | Substation Minor Projects | Argenton 132kV Substation Connection | PS Connections | Input_Proj_Commit | 2009 | 2013 | 12153.0527 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
6618 | Substation Minor Projects | Connection of Kingsford Substation at Beaconsfield West | PS Connections | Input_Proj_Commit | 2009 | 2013 | 11818.4037 | 0 | 0 | 4377.7359 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
6638 | Substation Minor Projects | Mayfield West & Kooragang Zone Substation Connection | PS Connections | Input_Proj_Commit | 2009 | 2013 | 167648.5258 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 67% | 33% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
6640 | Substation Minor Projects | Narrabri Substation 66kV Switchbay Renames | PS Connections | Input_Proj_Commit | 2009 | 2013 | -19.5925 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
6697 | Substation Minor Projects | Beryl 66kV Bay to Dunedoo | PS Connections | Input_Proj_Commit | 2010 | 2013 | 4789.3461 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
6345 | Substation Minor Projects | Sydney North 132kV Switchbays For Galston | PS Connections | Input_Proj_Commit | 2011 | 2013 | 677693.3803 | 83978.2443 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
6724 | Substation Minor Projects | Tenterfield 22kV Switchbay | PS Connections | Input_Proj_Commit | 2011 | 2013 | 20131.715 | 540.0089 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
6856 | Substation Minor Projects | Connection to Kurri Zone Substation at Newcastle | PS Connections | Input_Proj_Commit | 2011 | 2013 | 79467.6816 | 105641.6721 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
7134 | Substation Minor Projects | Connection of Jesmond Zone Substation | PS Connections | Input_Proj_Commit | 2011 | 2013 | 0 | 130525.0282 | 2383.4952 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
7283 | Substation Minor Projects | Tenterfield 22kV Switchbay | PS Connections | Input_Proj_Commit | 2011 | 2013 | 0 | 1542.4192 | -1511.5657 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
7285 | Substation Minor Projects | Cooma 132kV Installation of New Line Bay | PS Connections | Input_Proj_Commit | 2013 | 2013 | 25592.6665 | 585761.0052 | 1003097.3335 | 10978.2467 | 0 | 0 | 0 | 0 | 0 | 0% | 90% | 5% | 5% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
7422 | Substation Minor Projects | Hawks Nest 132/66kV Substation Line Connection | PS Connections | Input_Proj_Commit | 2013 | 2013 | 49942.8048 | 41913.8753 | 1028558.0437 | 882470.5619 | 0 | 0 | 0 | 0 | 0 | 85% | 5% | 0% | 0% | 10% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
7565 | Substation Minor Projects | Uprate Broken Hill 52 & 62 22kV Line Switchbays | PS Connections | Input_Proj_Commit | 2014 | 2013 | 0 | 0 | 4041.3072 | 67394.7489 | 0 | 0 | 0 | 0 | 0 | 0% | 90% | 5% | 5% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
7668 | Substation Minor Projects | Wellington Substation 132kV Switchbay and Double Circuit (Strung On One Side) To Mitchell Highway | PS Connections | Input_Proj_Commit | 2014 | 2013 | 0 | 2.8721 | 0 | 586677.0067 | 1886123.86 | 0 | 0 | 0 | 0 | 0% | 92.38% | 3.809% | 3.809% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
7826 | Substation Minor Projects | Connection to Broadmeadow Zone Substation at Waratah West | PS Connections | Input_Proj_Commit | 2014 | 2013 | 0 | 0 | 3594.1753 | 167851.6254 | 74769.74 | 0 | 0 | 0 | 0 | 0% | 90% | 5% | 5% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
8178 | Substation Minor Projects | Connection to Herons Creek Substation | PS Connections | Input_Proj_Commit | 2014 | 2013 | 659.2424 | 64.0634 | -14945.1533 | 22994.1038 | 237886.66 | 0 | 0 | 0 | 0 | 81.98% | 8.023% | 0.1778% | 0.1778% | 9.644% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
P0000899 | Substation Minor Projects | Connection of Abbotsbury Zone Substation at Sydney West | PS Connections | Input_Proj_Commit | 2014 | 2013 | 0 | 0 | 0 | 0 | 423000 | 0 | 0 | 0 | 0 | 0% | 90% | 5% | 5% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
P0000909 | Substation Minor Projects | Reduce AVR Settings at Vineyard Substation | PS Connections | Input_Proj_Commit | 2014 | 2013 | 0 | 0 | 0 | 3975.7124 | 0 | 0 | 0 | 0 | 0 | 0% | 30% | 25% | 45% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
6157 | Substation Minor Projects | Supply to Gulgong West | PS Connections | Input_Proj_Commit | 2015 | 2013 | -12.6382 | 0 | 0 | -23181.9323 | 0 | 0 | 0 | 0 | 0 | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
6222 | Substation Minor Projects | Sydney West 132kV Line Bays | PS Connections | Input_Proj_Commit | 2015 | 2013 | 0 | -4821.7309 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 90% | 5% | 5% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
6986 | Substation Minor Projects | Supply to Belmore Park Zone Substation | PS Connections | Input_Proj_Commit | 2015 | 2013 | 1093.0604 | 35315.3839 | 356056.1962 | 622474.3765 | 386548.88 | 22245.52 | 0 | 0 | 0 | 0% | 90% | 5% | 5% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
7126 | Substation Minor Projects | Sydney West 132kV Line Bays | PS Connections | Input_Proj_Commit | 2015 | 2013 | 0 | 34828.8593 | 3413.972 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 90% | 5% | 5% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
7311 | Substation Minor Projects | Sydney West 132kV Line Bays | PS Connections | Input_Proj_Commit | 2015 | 2013 | 0 | 4826.5659 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
7313 | Substation Minor Projects | Tamworth 66kV Line Bay | PS Connections | Input_Proj_Commit | 2015 | 2013 | 0 | 3945.5466 | 16186.5507 | 20600.3948 | -39015.3398 | 0 | 0 | 0 | 0 | 0% | 90% | 5% | 5% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
7661 | Substation Minor Projects | Supply to Temora | PS Connections | Input_Proj_Commit | 2015 | 2013 | 0 | 0 | 0 | 31927.6756 | 0 | 0 | 0 | 0 | 0 | 0% | 90% | 5% | 5% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
8092 | Substation Minor Projects | Supply to Parkes Town | PS Connections | Input_Proj_Commit | 2015 | 2013 | 0 | 0 | 0 | 1635.3674 | 1182 | 250000 | 0 | 0 | 0 | 0% | 90% | 5% | 5% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
8095 | Substation Minor Projects | Supply to Googong | PS Connections | Input_Proj_Commit | 2015 | 2013 | 0 | 0 | 0 | 949.896 | 0 | 250000 | 0 | 0 | 0 | 0% | 90% | 5% | 5% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
6176 | Substation Minor Projects | Supply to Molong | PS Connections | Input_Proj_Commit | 2016 | 2013 | 0 | -6507.2364 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
7532 | Substation Minor Projects | Connection of Gwawley Bay | PS Connections | Input_Proj_Commit | 2016 | 2013 | 0 | 0 | -199.713 | 20096.6999 | 0 | 0 | 0 | 0 | 0 | 0% | 90% | 5% | 5% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
7094 | Substation Minor Projects | Supply to Marsden Park | PS Connections | Input_Proj_Commit | 2016 | 2013 | 8713.8824 | 3657.287 | -3583.9902 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 90% | 5% | 5% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
8093 | Substation Minor Projects | Supply to Molong | PS Connections | Input_Proj_Commit | 2016 | 2013 | 0 | 0 | 0 | 10573.8182 | 0 | 0 | 0 | 0 | 0 | 0% | 90% | 5% | 5% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
6964 | Substation Minor Projects | Supply to Nabiac | PS Connections | Input_Proj_Commit | 2017 | 2013 | 6130.3448 | 57904.2755 | 121387.2036 | 187142.6322 | 0 | 0 | 0 | 0 | 0 | 85% | 5% | 0% | 0% | 10% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
P0002435 | Substation Minor Projects | Supply to Gloucester | PS Connections | Input_Proj_Commit | 2017 | 2013 | 0 | 0 | 0 | 0 | 100000 | 460000 | 0 | 0 | 0 | 85% | 5% | 0% | 0% | 10% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
6174 | Substation Minor Projects | Supply to Googong | PS Connections | Input_Proj_Commit | 2018 | 2013 | 28899.347 | -28510.6621 | -2673.8414 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
7320 | Substation Minor Projects | Supply to Googong | PS Connections | Input_Proj_Commit | 2018 | 2013 | 0 | 32965.0692 | 31478.7363 | -62097.5051 | 0 | 0 | 0 | 0 | 0 | 0% | 90% | 5% | 5% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
7392 | Transformer Additions | Macarthur 330/132kV No.2 Transformer Installation | PS Connections | Input_Proj_Commit | 2014 | 2013 | 0 | 1797.6294 | -1761.6474 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
890 | Easements | Koolkhan to Coffs Harbour 132kV Transmission Line Easements | PS Easements | Input_Proj_Commit | 2009 | 2013 | 29056.5947 | 12188.1466 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
2007 | Easements | Coffs Harbour to Kempsey 132kV Transmission Line Easements | PS Easements | Input_Proj_Commit | 2009 | 2013 | 24342.242 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
3133 | Easements | Cable Easements | PS Easements | Input_Proj_Commit | 2009 | 2013 | 13760.0262 | 1015.3552 | 2044.3294 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
3954 | Easements | Coffs Harbour 132kV Transmission Line Upgrade Easements | PS Easements | Input_Proj_Commit | 2009 | 2013 | 166.446 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
3955 | Easements | Darlington Point to Buronga Strategic Easement Acquisition | PS Easements | Input_Proj_Commit | 2009 | 2013 | 41108.2769 | 1290.4116 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
4240 | Easements | Miscellaneous State Forests Easements | PS Easements | Input_Proj_Commit | 2009 | 2013 | -0.074094 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
4254 | Easements | Ivanhoe Coal | PS Easements | Input_Proj_Commit | 2009 | 2013 | -89944.261 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
4300 | Easements | Miscellaneous Statewide NPWS Easements | PS Easements | Input_Proj_Commit | 2009 | 2013 | 30329.5649 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
4400 | Easements | Miscellaneous Sydney Catchment Authority Easements | PS Easements | Input_Proj_Commit | 2009 | 2013 | 329.8858 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
905 | Easements | Miscellaneous Easements | PS Easements | Input_Proj_Commit | 2010 | 2013 | 4646001.0113 | 36817.2326 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
6961 | Easements | Bannaby to South Creek Lines 500kV Easement Acquisitions | PS Easements | Input_Proj_Commit | 2013 | 2013 | 781.9414 | 1332059.3946 | -1286425.288 | 511416.3394 | 0 | 0 | 0 | 0 | 0 | 60% | 25% | 0% | 0% | 15% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
6673 | Easements | Dumaresq to Lismore 330kV Strategic Easement Acquisition | PS Easements | Input_Proj_Commit | 2014 | 2013 | 3580788.5606 | 3547121.667 | 3663494.0617 | 3265332.4639 | 568178 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
7460 | Easements | Kemps Creek to Liverpool 330kV Easement Acquisition | PS Easements | Input_Proj_Commit | 2014 | 2013 | 87268.8791 | 127266.1928 | 7075332.898 | 1213383.073 | 0 | 0 | 0 | 0 | 0 | 65% | 10% | 0% | 0% | 25% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
7790 | Easements | Strategic Easement for Sydney West to Holroyd Second 330kV Line | PS Easements | Input_Proj_Commit | 2015 | 2013 | 0 | 0 | 26037.7881 | 0 | -24649.3394 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
6923 | Powering Sydney's Future | Rookwood 330kV Substation - Cable Bays For Beaconsfield West | PS Easements | Input_Proj_Commit | 2017 | 2013 | 0 | 1556.3972 | -1525.3247 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 90% | 5% | 5% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
7562 | Powering Sydney's Future | Haymarket Additional 330 kV Switchbays and Beaconsfield West Bay | PS Easements | Input_Proj_Commit | 2017 | 2013 | 0 | 0 | 6857.1325 | -6675.8255 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
4759 | Property | Marulan Substation Outstanding Land Acquisition | PS Easements | Input_Proj_Commit | 2009 | 2013 | 428646.6433 | 237.3994 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
5827 | Property | Miscellaneous Substation Site Rights Acquisition | PS Easements | Input_Proj_Commit | 2009 | 2013 | 468.6737 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
7396 | Property | Richmond Vale 500kV Strategic Property Acquisition | PS Easements | Input_Proj_Commit | 2013 | 2013 | 2410.4126 | 1632.641 | -1263.7925 | 0 | 0 | 0 | 0 | 0 | 0 | 5% | 80% | 2.5% | 2.5% | 10% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
7457 | Property | South Creek 500/330kV Substation Strategic Site Acquisition | PS Easements | Input_Proj_Commit | 2013 | 2013 | 914533.9924 | 12376121.0499 | 34722.0826 | 74096.389 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
5994 | Property | Lismore Substations 330kV Augmentation | PS Easements | Input_Proj_Commit | 2014 | 2013 | -0.02117 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 90% | 5% | 5% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
6751 | Property | Tenterfield Substation | PS Easements | Input_Proj_Commit | 2014 | 2013 | 47022.9775 | 10041.0249 | -63063.7379 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
6939 | Property | Tenterfield Substation | PS Easements | Input_Proj_Commit | 2014 | 2013 | 0 | 1662.0641 | 0 | -1585.7095 | 0 | 0 | 0 | 0 | 0 | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
6911 | Property | Strategic Property Acquisition at Beryl | PS Easements | Input_Proj_Commit | 2015 | 2013 | 11441.4473 | 157147.3638 | -164945.5674 | 200671.6933 | 50000 | 700000 | 0 | 0 | 0 | 1.07% | 17.13% | 0.5352% | 0.5352% | 80.73% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
7548 | Property | Property Acquisition at Sydney West | PS Easements | Input_Proj_Commit | 2015 | 2013 | 0 | 0 | 140484.0498 | 12074684.2001 | 250000 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
6115 | Property | Strategic Property Acquisition at Surry Hills | PS Easements | Input_Proj_Commit | 2016 | 2013 | 84996.651 | -105389.9641 | 0 | -5284.9131 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
6276 | Property | Strategic Property Acquisition at Surry Hills | PS Easements | Input_Proj_Commit | 2016 | 2013 | -0.22228 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
6966 | Property | Strategic Property Acquisition at Maraylya | PS Easements | Input_Proj_Commit | 2016 | 2013 | 27888.0224 | 179490.9941 | 77819.586 | 95301.2433 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
7672 | Property | Property Extension at Richmond Vale | PS Easements | Input_Proj_Commit | 2016 | 2013 | 0 | 0 | 12381.1308 | -12053.7559 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
P0002472 | Property | Strategic Property Acquisition at Surry Hills | PS Easements | Input_Proj_Commit | 2016 | 2013 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
8252 | Property | Strategic Property Adjoining Armidale 330kV Switchyard | PS Easements | Input_Proj_Commit | 2017 | 2013 | 0 | 0 | 0 | 0 | 1025000 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
P0002217 | Property | Strategic Property Acquisition in Sydney | PS Easements | Input_Proj_Commit | 2017 | 2013 | 0 | 14413.9813 | 218815.8673 | -202210.5837 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
7300 | Substation Minor Projects | Connection to Lismore Substation | PS Easements | Input_Proj_Commit | 2014 | 2013 | 0 | 1.3327 | -969.4877 | -324.4713 | 0 | 0 | 0 | 0 | 0 | 0% | 90% | 5% | 5% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
7020 | Cable Minor Projects | Sydney Park Groundwater Treatment Plant | PS Replacement | Input_Proj_Commit | 2011 | 2013 | 0 | 1897337.7082 | 96210.3195 | 51011.5349 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
5120 | Cable Minor Projects | Tunnel Defects and Omissions Works | PS Replacement | Input_Proj_Commit | 2012 | 2013 | 1082583.375 | 1282515.2152 | 1630052.8399 | 1697583.6036 | 0 | 0 | 0 | 0 | 0 | 0% | 5% | 0% | 0% | 20% | 75% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
7480 | Cable Minor Projects | Cable 42 Accessories | PS Replacement | Input_Proj_Commit | 2014 | 2013 | 0 | 11129.1217 | 534593.8074 | 527875.7256 | 2650709.3 | 0 | 0 | 0 | 0 | 0% | 5% | 0% | 0% | 20% | 75% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
7916 | Cable Minor Projects | 42 Cable Monitoring System Replacement | PS Replacement | Input_Proj_Commit | 2016 | 2013 | 0 | 0 | 0 | 0 | 0 | 210000 | 52500 | 0 | 0 | 0% | 30% | 25% | 45% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
8223 | Cable Minor Projects | 42 Cable Tunnel Accessories Replacement | PS Replacement | Input_Proj_Commit | 2018 | 2013 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 350000 | 350000 | 0% | 5% | 0% | 0% | 20% | 75% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
7641 | Capacitor Bank | Kempsey No.1 Capacitor Replacement | PS Replacement | Input_Proj_Commit | 2009 | 2013 | 0 | 0 | 7127.1591 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 95% | 5% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
5470 | Capacitor Bank | Dapto Substation 132kV Capacitor Banks Replacement | PS Replacement | Input_Proj_Commit | 2011 | 2013 | 1865.1156 | 6959.3273 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
6197 | Capacitor Bank | Wellington No.2 132kV Capacitor | PS Replacement | Input_Proj_Commit | 2011 | 2013 | 36881.2694 | 2825.32 | -40029.278 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
6147 | Capacitor Bank | Griffith No.1 & No.2 33kV Capacitor Banks | PS Replacement | Input_Proj_Commit | 2013 | 2013 | -25631.3328 | -822.3384 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
6201 | Capacitor Bank | Sydney West No.1 Capacitor Bank | PS Replacement | Input_Proj_Commit | 2013 | 2013 | 3998.1112 | -6292.8549 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
6858 | Capacitor Bank | Griffith No.1 & No.2 33kV Capacitor Banks | PS Replacement | Input_Proj_Commit | 2013 | 2013 | 679364.667 | 338015.6751 | 1067682.9134 | 717585.3371 | 0 | 0 | 0 | 0 | 0 | 0% | 95% | 5% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
7273 | Capacitor Bank | Sydney West No.1 Capacitor Bank | PS Replacement | Input_Proj_Commit | 2013 | 2013 | 0 | 33905.1414 | 43298.5426 | 2219328.1826 | 0 | 0 | 0 | 0 | 0 | 0% | 95% | 5% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
6193 | Capacitor Bank | Coffs Harbour No.1 Capacitor | PS Replacement | Input_Proj_Commit | 2014 | 2013 | 13276.3327 | -37217.8641 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 95% | 5% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
7026 | Capacitor Bank | Coffs Harbour No.3 Capacitor | PS Replacement | Input_Proj_Commit | 2014 | 2013 | 0 | 243539.0358 | 413909.7806 | 1504821.8485 | 432318 | 0 | 0 | 0 | 0 | 0% | 94.17% | 5% | 0.8331% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
7474 | Capacitor Bank | Canberra No.1 132kV 80MVAr Capacitor | PS Replacement | Input_Proj_Commit | 2015 | 2013 | 0 | 10809.0525 | 5818.4752 | 102044.5771 | 1781799.13 | 1815284.45 | 0 | 0 | 0 | 0% | 95% | 5% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
7272 | Capacitor Bank | Sydney North No.1 & No.2 Capacitors | PS Replacement | Input_Proj_Commit | 2016 | 2013 | 0 | -191.3535 | -2532.8091 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 95% | 5% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
6712 | Capacitor Bank | New 66kV Capacitor at Panorama | PS Replacement | Input_Proj_Commit | 2017 | 2013 | -1.7147 | -2669.2474 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
6196 | Capacitor Bank | Taree No.3 132kV Capacitor | PS Replacement | Input_Proj_Commit | 2018 | 2013 | 49.2087 | -2376.1838 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 95% | 5% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
7643 | Capacitor Bank | Taree No.4 & No.5 Capacitors | PS Replacement | Input_Proj_Commit | 2018 | 2013 | 0 | 0 | 7103.4984 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 95% | 5% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
7757 | Capacitor Bank | Taree No.3 132kV Capacitor | PS Replacement | Input_Proj_Commit | 2018 | 2013 | 0 | 0 | 1774.3737 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 99% | 1% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
6152 | Capacitor Bank | Canberra No.1 132kV 80MVAr Capacitor | PS Replacement | Input_Proj_Commit | 2019 | 2013 | 48.7853 | -3576.9727 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
7344 | Capacitor Bank | Broken Hill No.3 and No.4 Capacitors | PS Replacement | Input_Proj_Commit | 2020 | 2013 | 0 | 0 | 0 | 5813.8904 | 0 | 0 | 0 | 0 | 0 | 0% | 99% | 1% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
7333 | Capacitor Bank | Newcastle No.1 Capacitor | PS Replacement | Input_Proj_Commit | 2021 | 2013 | 0 | 0 | 2420.7123 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 99% | 1% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
7334 | Capacitor Bank | Newcastle No.2 Capacitor | PS Replacement | Input_Proj_Commit | 2021 | 2013 | 0 | 0 | 457.4688 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 99% | 1% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
5642 | Communications | MMRN Modifications - Sydney - Newcastle | PS Replacement | Input_Proj_Commit | 2009 | 2013 | -31.6909 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
5946 | Communications | Port Macquarie & Taree Radio Network Modification | PS Replacement | Input_Proj_Commit | 2009 | 2013 | -29.7327 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
5947 | Communications | Kempsey & Nambucca Microwave Radio Modification | PS Replacement | Input_Proj_Commit | 2009 | 2013 | -1.0161 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
5948 | Communications | Koolkhan Microwave Radio Network Modification | PS Replacement | Input_Proj_Commit | 2009 | 2013 | -0.35988 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
4167 | Communications | OPGW Backup North & West NSW | PS Replacement | Input_Proj_Commit | 2011 | 2013 | -77073.4954 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 75% | 25% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
4339 | Communications | OPGW Backup - Southern Region | PS Replacement | Input_Proj_Commit | 2011 | 2013 | -78344.0841 | 900.4315 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0.004589% | 100% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
5488 | Communications | North Coast Microwave Radio Network - Extension To Coffs Harbour 330 and Lismore 330 Substations | PS Replacement | Input_Proj_Commit | 2011 | 2013 | 1108.1014 | 101388.0611 | 71325.6849 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
5607 | Communications | South Western NSW Replacement | PS Replacement | Input_Proj_Commit | 2011 | 2013 | -20.3757 | -116072.5324 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
5731 | Communications | Augmentation of Fault Clearing Times on Selected Transmission Line | PS Replacement | Input_Proj_Commit | 2011 | 2013 | -40478.9577 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
6037 | Communications | Mount Piper 132kV - 330kV Substation No.2 Intertrip On 94Y Line | PS Replacement | Input_Proj_Commit | 2011 | 2013 | -0.6986 | 0 | -10026.733 | -4172.7372 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
6154 | Communications | SCADA Comms to Beryl Substation | PS Replacement | Input_Proj_Commit | 2011 | 2013 | 0 | -1832.4764 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
6243 | Communications | North Coast Microwave Replacement | PS Replacement | Input_Proj_Commit | 2011 | 2013 | 46886.4231 | 3299.3955 | 0 | -92639.1572 | 0 | 0 | 0 | 0 | 0 | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
6245 | Communications | Replace PNX Telephone Network - Technical Services | PS Replacement | Input_Proj_Commit | 2011 | 2013 | 1355.6163 | 1404.8806 | -8001.8423 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
6281 | Communications | Communications Upgrade and Replacement | PS Replacement | Input_Proj_Commit | 2011 | 2013 | 18207130.8264 | 5884812.5436 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 100% | -1.872e-08% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
6589 | Communications | Armidale to Dumaresq OPGW PSR 216 | PS Replacement | Input_Proj_Commit | 2011 | 2013 | -11.3469 | -16393.4285 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
6642 | Communications | Augmentation of Optical Terminal Equipment Between Armidale & Dumaresq | PS Replacement | Input_Proj_Commit | 2011 | 2013 | -1.2702 | 0 | 0 | -1817.9718 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
6772 | Communications | OPGW Installation For Protection at Murray and Lower Tumut Switching Station | PS Replacement | Input_Proj_Commit | 2011 | 2013 | 12255.4395 | -13166.5266 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
6842 | Communications | Lismore 330 Substation - Augmentation of Communications Services | PS Replacement | Input_Proj_Commit | 2011 | 2013 | 699.7081 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
6848 | Communications | Communications Upgrade & Replacement (SP9) | PS Replacement | Input_Proj_Commit | 2011 | 2013 | 2512415.0128 | 2428506.7267 | 1207637.6722 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
6960 | Communications | Western Microwave Extension - TSP 46 & 47 | PS Replacement | Input_Proj_Commit | 2011 | 2013 | 3245701.7761 | 6365107.4855 | 1826806.8736 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
7287 | Communications | Southern NSW Microwave Radio | PS Replacement | Input_Proj_Commit | 2011 | 2013 | 0 | 2736.1002 | -3162.8779 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 30% | 25% | 45% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
7288 | Communications | Beryl SCADA Microwave Radio | PS Replacement | Input_Proj_Commit | 2011 | 2013 | 0 | 1834.3153 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
8022 | Communications | Dumaresq Protection & Communication Replacement | PS Replacement | Input_Proj_Commit | 2014 | 2013 | 0 | 0 | 0 | 8722.5013 | 0 | 0 | 0 | 0 | 0 | 0% | 30% | 25% | 45% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
7462 | Communications | Spur Microwave System Replacement | PS Replacement | Input_Proj_Commit | 2015 | 2013 | 13362.6412 | -1837.0737 | 29355.518 | 421885.6763 | 0 | 0 | 0 | 0 | 0 | 0% | 45% | 5% | 50% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
7466 | Communications | Albury to Hume District Communications Augmentation | PS Replacement | Input_Proj_Commit | 2017 | 2013 | 0 | 0 | 0 | 69820.3836 | 0 | 0 | 0 | 0 | 0 | 0% | 45% | 5% | 50% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
6056 | Control System | Modification of Autoreclose Facilities | PS Replacement | Input_Proj_Commit | 2009 | 2013 | -0.074094 | 0 | 0 | -2263.6603 | 0 | 0 | 0 | 0 | 0 | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
6380 | Control System | Jindera to Albury Transmission Lines | PS Replacement | Input_Proj_Commit | 2016 | 2013 | 47985.6438 | -70032.1192 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
7670 | Control System | Modification of Auto Reclose Facilities At Ingleburn and Panorama | PS Replacement | Input_Proj_Commit | 2017 | 2013 | 0 | 0 | 396.6114 | -386.1247 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
6847 | Fault Recorders | Travelling Wave Fault Locators Installation | PS Replacement | Input_Proj_Commit | 2011 | 2013 | 94262.0226 | 54488.6133 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
7788 | Oil Containment | Murray Oil Containment Upgrade | PS Replacement | Input_Proj_Commit | 2014 | 2013 | 0 | 0 | 319.2006 | 83410.3687 | 2862531.45 | 0 | 0 | 0 | 0 | 0% | 90% | 5% | 5% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
8023 | Oil Containment | Beryl Oil Containment Upgrade | PS Replacement | Input_Proj_Commit | 2016 | 2013 | 0 | 0 | 0 | 1987.9006 | 0 | 0 | 0 | 0 | 0 | 0% | 90% | 5% | 5% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
8027 | Oil Containment | Muswellbrook Oil Containment Upgrade | PS Replacement | Input_Proj_Commit | 2016 | 2013 | 0 | 0 | 0 | 9743.6806 | 0 | 0 | 0 | 0 | 0 | 0% | 90% | 5% | 5% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
8078 | Oil Containment | Inverell Oil Containment Upgrade | PS Replacement | Input_Proj_Commit | 2016 | 2013 | 0 | 0 | 0 | 1228.6225 | 0 | 0 | 0 | 0 | 0 | 0% | 90% | 5% | 5% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
5641 | Oil Containment | Yass Oil Contaimnent Upgrade | PS Replacement | Input_Proj_Commit | 2017 | 2013 | -8839.2064 | 222.4605 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
8032 | Oil Containment | Sydney South Oil Containment Upgrade | PS Replacement | Input_Proj_Commit | 2018 | 2013 | 0 | 0 | 0 | 315.413 | 0 | 0 | 0 | 0 | 0 | 0% | 90% | 5% | 5% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
7680 | Property | Yass Strategic Site Acquisition | PS Replacement | Input_Proj_Commit | 2014 | 2013 | 0 | 0 | 17051.879 | -16601.0067 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
6916 | Reactor Installation | Vales Point to Munmorah 330kV Line 23 Series Reactor Replacement | PS Replacement | Input_Proj_Commit | 2009 | 2013 | 0 | 7025.4363 | -6831.8013 | -51.6095 | 0 | 0 | 0 | 0 | 0 | 0% | 95% | 5% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
5577 | Reactor Replacement | Munmorah Substation Line 23 330kV Reactor Replacement | PS Replacement | Input_Proj_Commit | 2009 | 2013 | -527148.862 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
5627 | Reactor Replacement | Tamworth Substation - Replacement of Shunt Reactors | PS Replacement | Input_Proj_Commit | 2009 | 2013 | 48007.7131 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
6706 | Reactor Replacement | Beaconsfield Shunt Reactor | PS Replacement | Input_Proj_Commit | 2009 | 2013 | -187.1287 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
7849 | Reactor Replacement | Armidale No.1 330kV 50MVAr Reactor Replacement | PS Replacement | Input_Proj_Commit | 2014 | 2013 | 0 | 0 | 2459.033 | 1346380.0095 | 3288058.17 | 0 | 0 | 0 | 0 | 0% | 90% | 5% | 5% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
7346 | Reactor Replacement | Buronga X2 220kV Reactor | PS Replacement | Input_Proj_Commit | 2016 | 2013 | 0 | 0 | 4079.8304 | 50489.5855 | 0 | 0 | 0 | 0 | 0 | 0% | 90% | 5% | 5% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
7342 | Reactor Replacement | Broken Hill No.1 & No.2 220kV Reactors | PS Replacement | Input_Proj_Commit | 2018 | 2013 | 0 | 0 | 3294.8185 | 42280.0739 | 0 | 0 | 0 | 0 | 0 | 0% | 90% | 5% | 5% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
7325 | Reactor Replacement | Beaconsfield West No.1 132kV Reactor | PS Replacement | Input_Proj_Commit | 2019 | 2013 | 0 | 0 | 95.8776 | 20665.567 | 0 | 0 | 0 | 0 | 0 | 0% | 90% | 5% | 5% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
6922 | Reinforcement of Supply to the Orange Area | 944 Line Wallerawang to Orange North Rebuild | PS Replacement | Input_Proj_Commit | 2014 | 2013 | 0 | 18052.3106 | -17709.6278 | 0 | 0 | 0 | 0 | 0 | 0 | 85% | 5% | 0% | 0% | 10% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
6251 | SCADA | SCADA to Tumut | PS Replacement | Input_Proj_Commit | 2015 | 2013 | 3842.049 | -6019.0692 | -7448.7388 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
6255 | SCADA | SCADA to Molong | PS Replacement | Input_Proj_Commit | 2015 | 2013 | 0 | -1208.9815 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
7303 | SCADA | SCADA to Molong | PS Replacement | Input_Proj_Commit | 2015 | 2013 | 0 | 1210.1902 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
7318 | SCADA | SCADA to Tumut | PS Replacement | Input_Proj_Commit | 2015 | 2013 | 0 | 50760.7646 | 7448.7388 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
6277 | SCADA | SCADA to Albury | PS Replacement | Input_Proj_Commit | 2016 | 2013 | -1.0902 | -2343.5787 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
7279 | SCADA | SCADA to Albury | PS Replacement | Input_Proj_Commit | 2016 | 2013 | 0 | 5440.5251 | 0 | 446.4573 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
6247 | SCADA | SCADA to Cooma | PS Replacement | Input_Proj_Commit | 2017 | 2013 | -0.89971 | 0 | 0 | -1235.7193 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
7297 | SCADA | SCADA to Hume | PS Replacement | Input_Proj_Commit | 2017 | 2013 | 0 | 62883.6597 | 232.7589 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
6278 | SCADA | ANM SCADA | PS Replacement | Input_Proj_Commit | 2018 | 2013 | -1.2067 | -1708.7196 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
7280 | SCADA | ANM SCADA | PS Replacement | Input_Proj_Commit | 2018 | 2013 | 0 | 5533.4744 | -5422.694 | 416.5621 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 107.1% | -7.07% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
6461 | Secondary System Renewal | Lismore Substation Control System Replacement | PS Replacement | Input_Proj_Commit | 2011 | 2013 | 1003646.1718 | 916836.4553 | 775.5051 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
6715 | Secondary System Renewal | Dapto Secondary System Replacement | PS Replacement | Input_Proj_Commit | 2014 | 2013 | 4770741.3682 | 3173358.6525 | 1482566.0188 | 1217624.9251 | 1272807.22 | 0 | 0 | 0 | 0 | 0% | 30% | 25% | 45% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
7083 | Secondary System Renewal | Guthega Secondary System Renewal | PS Replacement | Input_Proj_Commit | 2014 | 2013 | 0 | 15585.1404 | 5620.8782 | 577324.7733 | 2543190.68 | 550021.759 | 0 | 0 | 0 | 0% | 30% | 25% | 45% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
7455 | Secondary System Renewal | Guthega Secondary System Renewal | PS Replacement | Input_Proj_Commit | 2014 | 2013 | 0 | 32263.5432 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
7669 | Secondary System Renewal | Yass Secondary System Renewal | PS Replacement | Input_Proj_Commit | 2014 | 2013 | 0 | 0 | 0 | 1003.3585 | 0 | 0 | 0 | 0 | 0 | 0% | 30% | 25% | 45% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
7151 | Secondary System Renewal | Tumut Secondary System Renewal | PS Replacement | Input_Proj_Commit | 2015 | 2013 | 0 | 30387.6141 | 158305.7441 | 1989980.4758 | 13635901.38 | 0 | 0 | 0 | 0 | 0% | 30% | 25% | 45% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
7301 | Secondary System Renewal | Molong Secondary System Renewal | PS Replacement | Input_Proj_Commit | 2015 | 2013 | 0 | 36532.7646 | -35801.4803 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 30% | 25% | 45% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
6985 | Secondary System Renewal | Sydney West Secondary System Renewal | PS Replacement | Input_Proj_Commit | 2016 | 2013 | 46909.5508 | 709790.5022 | 2124534.2686 | 4755830.174 | 19584356.0433 | 5213073.1683 | 3424107.0173 | 0 | 0 | 0% | 30% | 25% | 45% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
7061 | Secondary System Renewal | Griffith Secondary System Renewal | PS Replacement | Input_Proj_Commit | 2016 | 2013 | 0 | 13875.4704 | 659457.3793 | 1588240.9502 | 11272327.94 | 3746590.834 | 0 | 0 | 0 | 0% | 30% | 25% | 45% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
7353 | Secondary System Renewal | Balranald Secondary System Renewal | PS Replacement | Input_Proj_Commit | 2016 | 2013 | 0 | -349.8125 | 396.9961 | 44956.6788 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
7062 | Secondary System Renewal | Kangaroo Valley Secondary System Renewal | PS Replacement | Input_Proj_Commit | 2016 | 2013 | 0 | 14266.2666 | 11473.7357 | -24604.6423 | 0 | 0 | 0 | 0 | 0 | 0% | 30% | 25% | 45% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
7350 | Secondary System Renewal | Albury Secondary System Renewal | PS Replacement | Input_Proj_Commit | 2016 | 2013 | 0 | 0 | 0 | 21270.6672 | 0 | 0 | 0 | 0 | 0 | 0% | 30% | 25% | 45% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
7366 | Secondary System Renewal | Hume Secondary System Renewal | PS Replacement | Input_Proj_Commit | 2017 | 2013 | 1426.5133 | -59442.7688 | 0 | 4506.4639 | 0 | 0 | 0 | 0 | 0 | 0% | 30% | 25% | 45% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
7365 | Secondary System Renewal | Deniliquin Secondary System Renewal | PS Replacement | Input_Proj_Commit | 2018 | 2013 | 0 | 0 | 0 | 4661.2528 | 0 | 0 | 0 | 0 | 0 | 0% | 30% | 25% | 45% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
7638 | Secondary System Renewal | Sydney North Secondary System Renewal | PS Replacement | Input_Proj_Commit | 2019 | 2013 | 0 | 0 | 0 | 33551.5206 | 0 | 0 | 0 | 0 | 0 | 0% | 30% | 25% | 45% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
6928 | Secondary System Renewal | Liddell Secondary System Renewal | PS Replacement | Input_Proj_Commit | 2020 | 2013 | 0 | 2413.9958 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 90% | 5% | 5% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
7351 | Secondary System Renewal | Beryl Secondary System Renewal | PS Replacement | Input_Proj_Commit | 2020 | 2013 | 0 | 0 | -374.2568 | 364.3809 | 0 | 0 | 0 | 0 | 0 | 0% | 30% | 25% | 45% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
7354 | Secondary System Renewal | Buronga Secondary System Renewal | PS Replacement | Input_Proj_Commit | 2020 | 2013 | 0 | 0 | 374.2568 | 2925.456 | 0 | 0 | 0 | 0 | 0 | 0% | 30% | 25% | 45% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
7651 | Secondary System Renewal | Liddell Secondary System Renewal | PS Replacement | Input_Proj_Commit | 2020 | 2013 | 0 | 0 | 0 | 15670.4396 | 0 | 0 | 0 | 0 | 0 | 0% | 30% | 25% | 45% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
7667 | Secondary System Renewal | Avon Secondary System Renewal | PS Replacement | Input_Proj_Commit | 2021 | 2013 | 0 | 0 | 0 | 21132.5065 | 0 | 0 | 0 | 0 | 0 | 0% | 30% | 25% | 45% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
6364 | Substation Minor Projects | Double Breaker Autoreclose Modifications at Various Sites | PS Replacement | Input_Proj_Commit | 2009 | 2013 | 463.1167 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
4025 | Substation Minor Projects | Communications Upgrade and Replacement | PS Replacement | Input_Proj_Commit | 2011 | 2013 | 0 | 0 | 266317.3929 | -222690.5498 | 0 | 0 | 0 | 0 | 0 | 0% | 90% | 5% | 5% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
6874 | Substation Minor Projects | Tumut 132/66kV Synchronism-Check System on Feeder 850 | PS Replacement | Input_Proj_Commit | 2011 | 2013 | 104783.1323 | 6080.4879 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
7827 | Substation Minor Projects | Replacement of Line 11 Wave Trap at Sydney South | PS Replacement | Input_Proj_Commit | 2014 | 2013 | 0 | 0 | 0 | 26863.1376 | 149167.53 | 0 | 0 | 0 | 0 | 0% | 90% | 5% | 5% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
P0000885 | Substation Minor Projects | Armidale AC System Replacement | PS Replacement | Input_Proj_Commit | 2014 | 2013 | 0 | 0 | 0 | 0 | 405519.17 | 0 | 0 | 0 | 0 | 0% | 30% | 25% | 45% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
P0002189 | Substation Minor Projects | Modifications of Secondary Systems for a 66kV Switchbay at Beryl | PS Replacement | Input_Proj_Commit | 2014 | 2013 | 0 | 0 | 0 | 0 | 455000 | 0 | 0 | 0 | 0 | 0% | 30% | 25% | 45% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
6106 | Substation Minor Projects | Newcastle Substation 330kV Bus Coupling | PS Replacement | Input_Proj_Commit | 2015 | 2013 | 4115.6448 | 0 | -15728.4035 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
8176 | Substation Minor Projects | Lower Tumut 11kV Switchboard Replacement | PS Replacement | Input_Proj_Commit | 2015 | 2013 | 0 | 0 | 0 | 0 | 0 | 179550 | 0 | 0 | 0 | 0% | 90% | 5% | 5% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
7682 | Substation Minor Projects | Murray 11kV Switchboard Replacement | PS Replacement | Input_Proj_Commit | 2015 | 2013 | 0 | 0 | 0 | 0 | 0 | 179550 | 0 | 0 | 0 | 0% | 90% | 5% | 5% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
8083 | Substation Minor Projects | Dapto 415V AC System Replacement | PS Replacement | Input_Proj_Commit | 2015 | 2013 | 0 | 0 | 0 | 6998.4142 | 0 | 0 | 0 | 0 | 0 | 0% | 90% | 5% | 5% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
6040 | Substation Minor Projects | Sydney West 132kV Disconnector Replacement | PS Replacement | Input_Proj_Commit | 2016 | 2013 | 31798.2586 | 169774.9457 | 170247.2451 | 17060.5536 | 0 | 0 | 0 | 0 | 0 | 0% | 90% | 5% | 5% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
5811 | Substation Minor Projects | Tamworth 66kV Line Bay | PS Replacement | Input_Proj_Commit | 2017 | 2013 | 0 | 0 | -18506.5864 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
8120 | Substation Minor Projects | Tamworth 66kV Line Bay | PS Replacement | Input_Proj_Commit | 2017 | 2013 | 0 | -3805.415 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 90% | 5% | 5% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
8073 | Substation Minor Projects | Removal of SICAM from Haymarket GIS | PS Replacement | Input_Proj_Commit | 2017 | 2013 | 0 | 0 | 0 | 11890.0861 | 0 | 0 | 0 | 0 | 0 | 0% | 90% | 5% | 5% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
5738 | Substation Minor Projects | Supply to Nabiac | PS Replacement | Input_Proj_Commit | 2018 | 2013 | 0 | 0 | -1466.4111 | 0 | 0 | 0 | 0 | 0 | 0 | 10% | 70% | 5% | 10% | 5% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
6432 | Substation Minor Projects | Taree 33kV Line Bay | PS Replacement | Input_Proj_Commit | 2018 | 2013 | 0 | -1132.2624 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
7315 | Substation Minor Projects | Taree 33kV Line Bay | PS Replacement | Input_Proj_Commit | 2018 | 2013 | 0 | 1133.3988 | -1110.7224 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
6915 | Substation Minor Projects | Canberra 330kV Substation - Uprating to 362kV | PS Replacement | Input_Proj_Commit | 2019 | 2013 | 0 | 0 | 94.359 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 90% | 5% | 5% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
7029 | Substation Minor Projects | Junee East Switching Station Second Supply to Temora | PS Replacement | Input_Proj_Commit | 2020 | 2013 | 0 | 0 | -465.0419 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 90% | 5% | 5% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
8062 | Substation Minor Projects | Wagga 132 - 99X Line Wave Trap | PS Replacement | Input_Proj_Commit | 2020 | 2013 | 0 | 0 | 0 | 1193.0696 | 0 | 0 | 0 | 0 | 0 | 0% | 90% | 5% | 5% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
5430 | Substation Renewal | Glen Innes 132kV Substation Rebuild | PS Replacement | Input_Proj_Commit | 2009 | 2013 | -20241.0666 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
7337 | Substation Renewal | Kempsey 132kV Substation Condition | PS Replacement | Input_Proj_Commit | 2009 | 2013 | 0 | 0 | 0 | 153.3302 | 0 | 0 | 0 | 0 | 0 | 0% | 90% | 5% | 5% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
6313 | Substation Renewal | Beaconsfield West Substation Renewal | PS Replacement | Input_Proj_Commit | 2013 | 2013 | -87.314 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
6570 | Substation Renewal | Beaconsfield West Substation Renewal | PS Replacement | Input_Proj_Commit | 2013 | 2013 | 23967483.7176 | 53996105.7475 | 33853161.606 | 11325503.7806 | 0 | 0 | 0 | 0 | 0 | 0% | 90% | 5% | 5% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
7563 | Substation Renewal | Beaconsfield West Substation Renewal | PS Replacement | Input_Proj_Commit | 2013 | 2013 | 0 | 0 | 2476.1634 | -2410.692 | 0 | 0 | 0 | 0 | 0 | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
6336 | Substation Renewal | Queanbeyan Substation Renewal | PS Replacement | Input_Proj_Commit | 2014 | 2013 | 15353786.2732 | 431497.9935 | 716010.6527 | 1216010.927 | 797932 | 0 | 0 | 0 | 0 | 0% | 82.61% | 11.59% | 3.953% | 1.84% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
6314 | Substation Renewal | Upper Tumut Switching Station Renewal | PS Replacement | Input_Proj_Commit | 2015 | 2013 | 475707.9272 | 6155838.3218 | 10001209.6239 | 12116025.171 | 10873863.67 | 3990035.371 | 0 | 0 | 0 | 0% | 90% | 5% | 5% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
6838 | Substation Renewal | Wallerawang 132 Substation Renewal | PS Replacement | Input_Proj_Commit | 2015 | 2013 | 690351.4549 | 3288703.2836 | 14471788.979 | 23930855.782 | 20817565.87 | 734889.057 | 0 | 0 | 0 | 10% | 70% | 5% | 10% | 5% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
6931 | Substation Renewal | Lower Tumut Substation Renewal | PS Replacement | Input_Proj_Commit | 2015 | 2013 | 0 | 0 | -227.2816 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 90% | 5% | 5% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
7479 | Substation Renewal | Yanco Substation Renewal | PS Replacement | Input_Proj_Commit | 2016 | 2013 | 0 | 773.8957 | 150162.4949 | 142539.8567 | 1584728.31 | 8289665.965 | 3676858.472 | 0 | 0 | 0% | 90% | 5% | 5% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
6912 | Substation Renewal | Tamworth 132 Substation Renewal | PS Replacement | Input_Proj_Commit | 2017 | 2013 | 6127.3599 | 71636.5873 | 155544.7523 | 602717.9679 | 1756094.3 | 19484912.916 | 8799823.998 | 0 | 0 | 10% | 70% | 5% | 10% | 5% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
6965 | Substation Renewal | Cooma Substation Renewal | PS Replacement | Input_Proj_Commit | 2017 | 2013 | 0 | 242373.0009 | 113946.8679 | 1036142.8038 | 1981022.38 | 19822966.548 | 5746247.507 | 0 | 0 | 10% | 70% | 5% | 10% | 5% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
7027 | Substation Renewal | Orange Substation Renewal | PS Replacement | Input_Proj_Commit | 2017 | 2013 | 0 | 141307.0751 | 258721.3042 | 273675.9843 | 2089984.94 | 3021127.298 | 11845316.014 | 0 | 0 | 0% | 90% | 5% | 5% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
6962 | Substation Renewal | Burrinjuck Substation Renewal | PS Replacement | Input_Proj_Commit | 2017 | 2013 | 0 | 37162.0965 | -36194.0723 | -218.2461 | 0 | 0 | 0 | 0 | 0 | 10% | 70% | 5% | 10% | 5% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
7378 | Substation Renewal | Vales Point Substation Renewal | PS Replacement | Input_Proj_Commit | 2018 | 2013 | 6574.1124 | 4196.1388 | 265676.2886 | 191301.9446 | 0 | 0 | 0 | 0 | 0 | 0% | 89.83% | 5.056% | 5.112% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
8076 | Substation Renewal | Taree Substation 33kV Switchyard Renewal | PS Replacement | Input_Proj_Commit | 2018 | 2013 | 0 | -94.7573 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 90% | 5% | 5% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
6350 | Substation Renewal | Canberra Substation Renewal | PS Replacement | Input_Proj_Commit | 2019 | 2013 | 0 | 0 | -166800.1564 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 30% | 25% | 45% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
7398 | Substation Renewal | Canberra Substation Renewal | PS Replacement | Input_Proj_Commit | 2019 | 2013 | 0 | 0 | 381.7994 | -181.4709 | 0 | 0 | 0 | 0 | 0 | 0% | 90% | 5% | 5% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
7406 | Substation Renewal | Wagga 132kV Substation Renewal | PS Replacement | Input_Proj_Commit | 2020 | 2013 | 0 | 0 | 0 | -2.2276 | 0 | 0 | 0 | 0 | 0 | 65% | 10% | 0% | 0% | 25% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
7544 | Substation Renewal | Wagga 132kV Substation Renewal | PS Replacement | Input_Proj_Commit | 2020 | 2013 | 30132.1055 | 12231.0312 | 50.1763 | 0 | 0 | 0 | 0 | 0 | 0 | 85% | 5% | 0% | 0% | 10% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
6914 | Substation Renewal | Wagga 132kV Substation Renewal | PS Replacement | Input_Proj_Commit | 2020 | 2013 | 10772.1493 | 2656.0545 | -10557.5021 | 34492.1118 | 0 | 0 | 0 | 0 | 0 | 0% | 90% | 5% | 5% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
7678 | Substation Renewal | Munmorah Substation Renewal | PS Replacement | Input_Proj_Commit | 2020 | 2013 | 79812.5978 | 80389.6284 | 73793.9513 | -93795.0179 | 0 | 0 | 0 | 0 | 0 | 0% | 89.41% | 5% | 5.588% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
7298 | SVC Control System Replacement | Kemps Creek SVC Control System Replacement | PS Replacement | Input_Proj_Commit | 2015 | 2013 | 86302.9528 | 1291.5273 | 68665.4406 | 89348.1769 | -319499.5073 | 0 | 0 | 0 | 0 | 0% | 30% | 25% | 45% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
7822 | SVC Control System Replacement | Broken Hill SVC Control System Replacement | PS Replacement | Input_Proj_Commit | 2015 | 2013 | 10611.6732 | 0 | 90644.4671 | 312781.0119 | 8948030.1 | 4441577 | 0 | 0 | 0 | 0% | 90% | 5% | 5% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
7091 | SVC Control System Replacement | Armidale SVC Control System Replacement | PS Replacement | Input_Proj_Commit | 2018 | 2013 | 3377.842 | -242.9162 | -29594.6451 | 0.0098567 | 0 | 0 | 0 | 0 | 0 | 0% | 30% | 25% | 45% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
5533 | Transformer Replacement | Sydney West No.2 Transformer Replacement | PS Replacement | Input_Proj_Commit | 2009 | 2013 | 45487.8642 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
6393 | Transformer Replacement | Kempsey 132kV Substation 66/33kV 2 x 25MVA Transformer Replacements | PS Replacement | Input_Proj_Commit | 2009 | 2013 | -2.4874 | 1211.4196 | 0 | -4729.0075 | 0 | 0 | 0 | 0 | 0 | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
6415 | Transformer Replacement | Kempsey 2x60MVA 132/33kV Transformer | PS Replacement | Input_Proj_Commit | 2009 | 2013 | 185227.3144 | -752.6548 | -13884.0908 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 95% | 5% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
6694 | Transformer Replacement | Tuggerah Substation No.1 Transformer Replacement | PS Replacement | Input_Proj_Commit | 2009 | 2013 | 661409.2819 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
5677 | Transformer Replacement | Sydney South No.1 & No.2 Transformers | PS Replacement | Input_Proj_Commit | 2011 | 2013 | 1694802.8335 | 292044.5013 | 0 | 99733.4767 | 0 | 0 | 0 | 0 | 0 | 0% | 97.02% | 2.975% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
5878 | Transformer Replacement | Orange No.1 & No.2 Transformer Replacement | PS Replacement | Input_Proj_Commit | 2011 | 2013 | 3611733.7269 | 1980890.7433 | 76540.1008 | 49.1946 | 0 | 0 | 0 | 0 | 0 | 0% | 98% | 2% | 0% | -3.419e-17% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
6172 | Transformer Replacement | Wallerawang 132kV Transformer Replacements | PS Replacement | Input_Proj_Commit | 2012 | 2013 | 1659.5482 | 469.4265 | -2641.3017 | 0 | 0 | 0 | 0 | 0 | 0 | 10% | 70% | 5% | 10% | 5% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
6721 | Transformer Replacement | Wallerawang 330/132kV Transformer Replacements & Relocation | PS Replacement | Input_Proj_Commit | 2012 | 2013 | 4253517.3847 | 14865233.9149 | 4127993.1333 | 16577.9125 | 0 | 0 | 0 | 0 | 0 | 0% | 95% | 5% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
6834 | Transformer Replacement | Narrabri No.1 & No.3 Transformer Replacements | PS Replacement | Input_Proj_Commit | 2013 | 2013 | 581000.4 | 1298874.7369 | 1894396.0145 | 7218451.0162 | 0 | 0 | 0 | 0 | 0 | 0% | 95% | 5% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
5619 | Transformer Replacement | Yass No.3 Transformer | PS Replacement | Input_Proj_Commit | 2014 | 2013 | 64202.7934 | -64188.3386 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 95% | 5% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
5889 | Transformer Replacement | Sydney East No.4 Transformer | PS Replacement | Input_Proj_Commit | 2014 | 2013 | 6791.0373 | 0 | -669724.4745 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
6851 | Transformer Replacement | Dapto Substation Temporary Transformer Installation (System Spare) | PS Replacement | Input_Proj_Commit | 2014 | 2013 | 44358.7732 | 9173.2398 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 95% | 5% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
6984 | Transformer Replacement | Dapto Substation Temporary Transformer Installation (System Spare) | PS Replacement | Input_Proj_Commit | 2014 | 2013 | 98015.1381 | 888606.9553 | 550208.7271 | 1856999.8028 | 1216102.58 | 0 | 0 | 0 | 0 | 0% | 90% | 5% | 5% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
7140 | Transformer Replacement | Yass No.3 Transformer | PS Replacement | Input_Proj_Commit | 2014 | 2013 | 0 | 343083.8245 | 1638200.159 | 551888.0616 | 1311415.77 | 0 | 0 | 0 | 0 | 0% | 90% | 5% | 5% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
7262 | Transformer Replacement | Sydney East No.4 Transformer | PS Replacement | Input_Proj_Commit | 2014 | 2013 | 0 | 0 | 360331.2747 | 3636148.5792 | 9569961.09 | 0 | 0 | 0 | 0 | 0% | 90% | 5% | 5% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
7628 | Transformer Replacement | Surge Arresters Installation At 330kV Line Entries | PS Replacement | Input_Proj_Commit | 2014 | 2013 | 0 | 0 | 453991.8065 | 431318.7441 | 975242.45 | 0 | 0 | 0 | 0 | 0% | 90% | 5% | 5% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
6919 | Transformer Replacement | Kemps Creek Replace No.1 and No.2 Transformer VCC | PS Replacement | Input_Proj_Commit | 2015 | 2013 | 0 | 0 | -53.0314 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 95% | 5% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
7085 | Transformer Replacement | Yanco Transformer Replacement | PS Replacement | Input_Proj_Commit | 2015 | 2013 | 10725.4069 | 42337.7828 | 538234.9395 | 3578218.1732 | 6963387.67 | 1002715.574 | 0 | 0 | 0 | 0% | 90% | 5% | 5% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
7471 | Transformer Replacement | Newcastle No.1, No.2 and No.3 Transformer Replacement | PS Replacement | Input_Proj_Commit | 2015 | 2013 | 44454.2904 | 819.0634 | 412979.545 | 4875126.2971 | 15802355.12 | 2603298.6 | 0 | 0 | 0 | 0% | 90% | 5% | 5% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
7092 | Transformer Replacement | Griffith Transformer Replacement | PS Replacement | Input_Proj_Commit | 2016 | 2013 | 36909.6366 | 3087.0802 | 39776.4527 | 1462514.9744 | 5657236.43 | 4219796.504 | 0 | 0 | 0 | 0% | 90% | 5% | 5% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
7356, 7357, 7563 | Transformer Replacement | Beaconsfield West No.1 & No.2 330kV Transformers | PS Replacement | Input_Proj_Commit | 2018 | 2013 | 0 | 0 | 0 | 1420066.1841 | 0 | 0 | 0 | 0 | 0 | 0% | 95% | 5% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
7284 | Transformer Replacement | Canberra No.2 Transformer Replacement | PS Replacement | Input_Proj_Commit | 2019 | 2013 | 981.9306 | 4.1325 | -6307.3801 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 103.4% | 0% | 0% | -3.424% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
6379 | Transformer Replacement | Wagga 132 No.2 Transformer Replacement | PS Replacement | Input_Proj_Commit | 2020 | 2013 | 5254.6538 | 0 | 0 | -12728.9764 | 0 | 0 | 0 | 0 | 0 | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
6021 | Transmission Line Life Extension | 11 Line Dapto to Sydney South Life Extension | PS Replacement | Input_Proj_Commit | 2013 | 2013 | 4246.3777 | 1783785.1897 | 2804456.3346 | 0 | 0 | 0 | 0 | 0 | 0 | 85% | 5% | 0% | 0% | 10% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
7779 | Transmission Line Life Extension | 21 Line Sydney North to Tuggerah Life Extension | PS Replacement | Input_Proj_Commit | 2015 | 2013 | 0 | 0 | 0 | 0 | 0 | 3451000 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
7706 | Transmission Line Life Extension | 8 Line Dapto to Marulan Life Extension | PS Replacement | Input_Proj_Commit | 2016 | 2013 | 0 | 0 | 0 | 0 | 0 | 0 | 1918000 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
7716 | Transmission Line Life Extension | 24 Line Vales Point to Eraring Life Extension | PS Replacement | Input_Proj_Commit | 2016 | 2013 | 0 | 0 | 0 | 0 | 0 | 1129800 | 0 | 0 | 1130500 | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
7322 | Transmission Line Life Extension | 11 Line Dapto to Sydney South Life Extension | PS Replacement | Input_Proj_Commit | 2017 | 2013 | 0 | 0 | 0 | 0 | 0 | 0 | 2109800 | 0 | 0 | 85% | 5% | 0% | 0% | 10% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
7703 | Transmission Line Life Extension | 22 Line Vales Point to Structure 136 Life Extension | PS Replacement | Input_Proj_Commit | 2017 | 2013 | 0 | 0 | 0 | 0 | 0 | 0 | 3021200 | 3021900 | 0 | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
7720 | Transmission Line Life Extension | 18 Line Kangaroo Valley to Dapto Life Extension | PS Replacement | Input_Proj_Commit | 2017 | 2013 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1438500 | 0 | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
7915 | Transmission Line Life Extension | 17 Line Avon to Picton Rd Life Extension | PS Replacement | Input_Proj_Commit | 2018 | 2013 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 770000 | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
7697 | Transmission Line Life Extension | 26 Line Sydney North to Vales Point Life Extension | PS Replacement | Input_Proj_Commit | 2019 | 2013 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1054900 | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
7715 | Transmission Line Life Extension | 959/92Z Line Sydney North to Sydney East Life Extension | PS Replacement | Input_Proj_Commit | 2019 | 2013 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2972900 | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
7727 | Transmission Line Life Extension | 10 Line Avon to Dapto Life Extension | PS Replacement | Input_Proj_Commit | 2019 | 2013 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1054900 | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
7728 | Transmission Line Life Extension | 23 Line Munmorah to Vales Point Life Extension | PS Replacement | Input_Proj_Commit | 2019 | 2013 | 0 | 0 | 0 | 0 | 0 | 0 | 1054900 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
7761 | Transmission Line Life Extension | 2M Line Munmorah to Tuggerah Life Extension | PS Replacement | Input_Proj_Commit | 2019 | 2013 | 0 | 0 | 0 | 0 | 0 | 767200 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
7914 | Transmission Line Life Extension | 16 Line Structure 104 to 159 Life Extension | PS Replacement | Input_Proj_Commit | 2019 | 2013 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
7912 | Transmission Line Life Extension | 93 Line Eraring to Newcastle Life Extension | PS Replacement | Input_Proj_Commit | 2021 | 2013 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
7911 | Transmission Line Life Extension | 90 Line Eraring to Newcastle Life Extension | PS Replacement | Input_Proj_Commit | 2022 | 2013 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
P0002047 | Transmission Line Minor Projects | Reconstruction of Geehi Tee | PS Replacement | Input_Proj_Commit | 2015 | 2013 | 0 | 0 | 0 | 0 | 400000 | 1260000 | 0 | 0 | 0 | 85% | 5% | 0% | 0% | 10% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
5966 | Transmission Line Renewal | 990 Line Yass to Wagga 132kV Transmission Line Rebuild | PS Replacement | Input_Proj_Commit | 2010 | 2013 | 8943654.7297 | 687050.001 | 218902.8253 | 0 | 0 | 0 | 0 | 0 | 0 | 97.92% | 0% | 0% | 0% | 2.083% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
7264 | Transmission Line Renewal | 944 Line Wallerawang to Orange North Rebuild | PS Replacement | Input_Proj_Commit | 2014 | 2013 | 13912.1404 | 74560.4767 | 518947.6643 | 1520171.9073 | 3308727.44 | 0 | 0 | 0 | 0 | 85% | 5% | 0% | 0% | 10% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
7725 | Transmission Line Renewal | 99J Yanco to Griffith 132kV Line Partial Rebuild | PS Replacement | Input_Proj_Commit | 2019 | 2013 | 0 | 0 | 0 | 0 | 150000 | 210000 | 2205000 | 2170000 | 2240000 | 85% | 5% | 0% | 0% | 10% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
7744 | Transmission Line Wood Pole Replacement | Line 85 Armidale to Tamworth Temporary Pole Replacement | PS Replacement | Input_Proj_Commit | 2015 | 2013 | 0 | 0 | 0 | 47677.3726 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
7709 | Transmission Line Wood Pole Replacement | Line 973 Cowra To Yass Pole Replacements | PS Replacement | Input_Proj_Commit | 2016 | 2013 | 0 | 0 | 0 | 17819.122 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
7711 | Transmission Line Wood Pole Replacement | Line 970 Burrinjuck to Yass Pole Replacements | PS Replacement | Input_Proj_Commit | 2016 | 2013 | 0 | 0 | 0 | 19799.4132 | 0 | 0 | 0 | 0 | 0 | 85% | 5% | 0% | 0% | 10% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
7777 | Transmission Line Wood Pole Replacement | Line 96H Coffs Harbour To Koolkhan Wood Pole Replacement | PS Replacement | Input_Proj_Commit | 2016 | 2013 | 0 | 0 | 2904.9196 | 0 | 0 | 4850230 | 4850230 | 0 | 0 | 85% | 5% | 0% | 0% | 10% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
7699 | Transmission Line Wood Pole Replacement | Line 99F Uranquinty to Yanco Pole Replacements | PS Replacement | Input_Proj_Commit | 2018 | 2013 | 0 | 0 | 0 | 3851.3608 | 0 | 0 | 0 | 0 | 0 | 85% | 5% | 0% | 0% | 10% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
P0002076 | Cable Minor Projects | Cable 41 Temperature Monitoring | PS Security/Compliance | Input_Proj_Commit | 2014 | 2013 | 0 | 0 | 0 | 0 | 114000 | 0 | 0 | 0 | 0 | 0% | 30% | 25% | 45% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
7087 | Capacity of Victoria to NSW Interconnector | Snowy to Yass/Canberra Low Span Remediation | PS Security/Compliance | Input_Proj_Commit | 2019 | 2013 | 188086.9565 | 71202.5656 | -559702.0889 | -5182.6306 | 0 | 0 | 0 | 0 | 0 | 90% | 10% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
6244 | Communications | Replace FSX/FLX Multiplex Network | PS Security/Compliance | Input_Proj_Commit | 2014 | 2013 | 9414.8712 | -77056.6051 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
7044 | Communications | Northern Microwave Replacement | PS Security/Compliance | Input_Proj_Commit | 2014 | 2013 | 0 | 4642921.412 | 3792425.5375 | 3558285.6261 | 117777.29 | 0 | 0 | 0 | 0 | 0% | 45% | 5% | 50% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
7138 | Communications | Communications To Yanco and Colleambally | PS Security/Compliance | Input_Proj_Commit | 2014 | 2013 | 0 | 150569.1938 | 3623295.9905 | 2001520.6308 | 775287 | 0 | 0 | 0 | 0 | 0% | 45% | 5% | 50% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
7289 | Communications | Replace FSX/FLX Multiplex Network | PS Security/Compliance | Input_Proj_Commit | 2014 | 2013 | 0 | 135075.2257 | 2047935.153 | 622409.7563 | 4301901.55 | 0 | 0 | 0 | 0 | 0% | 39.08% | 12.89% | 48.03% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
7645 | Communications | Communications To Tumut/Gadara | PS Security/Compliance | Input_Proj_Commit | 2014 | 2013 | 0 | 5074.7613 | 0 | 3006408.9194 | 1205081 | 0 | 0 | 0 | 0 | 0% | 45% | 5% | 50% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
7786 | Communications | Kangaroo Valley Communications – Vacate 2Ghz Band and Migrate To 6.7Ghz Band | PS Security/Compliance | Input_Proj_Commit | 2014 | 2013 | 0 | 0 | 0 | 876805.2114 | 2229441.14 | 0 | 0 | 0 | 0 | 0% | 40.77% | 10.65% | 48.59% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
P0001927 | Communications | Haymarket 330kV Telecommunications Augmentation | PS Security/Compliance | Input_Proj_Commit | 2014 | 2013 | 0 | 0 | 0 | 0 | 137000 | 0 | 0 | 0 | 0 | 0% | 45% | 5% | 50% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
6700 | Communications | VHF Network Augmentationfor Control Room Access | PS Security/Compliance | Input_Proj_Commit | 2015 | 2013 | 22633.1675 | -29290.7048 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
7119 | Communications | VHF Network Augmentationfor Control Room Access | PS Security/Compliance | Input_Proj_Commit | 2015 | 2013 | 0 | 33965.6405 | -35503.1662 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 30% | 25% | 45% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
7286 | Communications | New England District Telecommunications Augmentation | PS Security/Compliance | Input_Proj_Commit | 2015 | 2013 | 21019.6314 | 28228.9732 | 73069.9893 | 228123.9436 | 2369231.03 | 1644715.275 | 0 | 0 | 0 | 0% | 45% | 5% | 50% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
8098 | Communications | VHF Network Augmentationfor Control Room Access | PS Security/Compliance | Input_Proj_Commit | 2015 | 2013 | 0 | 0 | 0 | 3403.5335 | 700000 | 210000 | 2100000 | 0 | 0 | 0% | 45.04% | 5% | 49.96% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
7783 | Communications | Northern Microwave Loop | PS Security/Compliance | Input_Proj_Commit | 2016 | 2013 | 454104.2055 | 122793.6235 | 29738.7956 | 393382.2233 | 1803480.4767 | 10020898.4167 | 623850.4207 | 0 | 0 | 0% | 44.98% | 5.02% | 49.99% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
6155 | Control System | Replacement of Electromechanical Underfrequency Relays | PS Security/Compliance | Input_Proj_Commit | 2011 | 2013 | 72538.0575 | 5201.2558 | 0 | 406.4984 | 0 | 0 | 0 | 0 | 0 | 0% | 99.67% | 0% | 0% | 0.3305% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
6941 | Control System | Auto Underfrequency Loadshedding Schemes Modification | PS Security/Compliance | Input_Proj_Commit | 2012 | 2013 | 43986.6223 | 979307.8507 | 548965.6287 | 53995.6479 | 0 | 0 | 0 | 0 | 0 | 0% | 30% | 25% | 45% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
P0002149 | Control System | Indication and Metering CT Ratio Changes at Dumaresq | PS Security/Compliance | Input_Proj_Commit | 2014 | 2013 | 0 | 0 | 0 | 0 | 58800 | 0 | 0 | 0 | 0 | 0% | 30% | 25% | 45% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
6113 | Control System | Multiple Contingency System Protection Scheme | PS Security/Compliance | Input_Proj_Commit | 2016 | 2013 | 0 | -3217.7175 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
7065 | Control System | Modification of Synchronising Angle at Gen Sites | PS Security/Compliance | Input_Proj_Commit | 2016 | 2013 | 0 | 0 | 0 | 0 | 1627653.3 | 1086432.228 | 96842.144 | 0 | 0 | 0% | 30% | 25% | 45% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
7505 | Control System | Modification of Synchronising Angle at Gen Sites | PS Security/Compliance | Input_Proj_Commit | 2016 | 2013 | 0 | 11256.8663 | 47531.7974 | -57014.9097 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
7316 | Control System | Multiple Contingency System Protection Scheme | PS Security/Compliance | Input_Proj_Commit | 2016 | 2013 | 0 | 3220.9408 | -3156.5198 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 30% | 25% | 45% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
P0001493 | Protection Change | Gadara 132kV Fault and Disturbance Recorder | PS Security/Compliance | Input_Proj_Commit | 2014 | 2013 | 0 | 0 | 0 | 0 | 170000 | 0 | 0 | 0 | 0 | 0% | 30% | 25% | 45% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
6832 | Quality of Supply | Voltage Unbalance Limits | PS Security/Compliance | Input_Proj_Commit | 2015 | 2013 | 74346.5762 | 10197.6554 | 1234.6546 | 14110.2588 | 0 | 0 | 0 | 0 | 0 | 90% | 10% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
7397 | Quality of Supply | Assessment of NER Quality of Supply Compliance | PS Security/Compliance | Input_Proj_Commit | 2019 | 2013 | 0 | 104657.7339 | 50763.9664 | -149272.7818 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
6254 | SCADA | SCADA to Gadara | PS Security/Compliance | Input_Proj_Commit | 2014 | 2013 | -2.4768 | -8200.0151 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
7290 | SCADA | SCADA to Deniliquin | PS Security/Compliance | Input_Proj_Commit | 2014 | 2013 | -1.3549 | -1990.4396 | 27259.605 | 72414.0547 | 405614.98 | 0 | 0 | 0 | 0 | 0% | 45% | 5% | 50% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
7293 | SCADA | SCADA to Gadara | PS Security/Compliance | Input_Proj_Commit | 2014 | 2013 | 0 | 9251.2193 | -9066.0433 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
7461 | SCADA | SCADA to Colleambally | PS Security/Compliance | Input_Proj_Commit | 2014 | 2013 | -1.7888 | 902.4668 | 49661.4245 | 251334.8643 | 293154.73 | 0 | 0 | 0 | 0 | 0% | 45% | 5% | 50% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
P0002366 | SCADA | SCADA to Tenterfield | PS Security/Compliance | Input_Proj_Commit | 2014 | 2013 | 1421.1891 | 0 | 0 | -5181.9702 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
7759 | Secondary System Renewal | Gadara Relay Replacement | PS Security/Compliance | Input_Proj_Commit | 2014 | 2013 | 0 | 0 | 0 | 2037.6866 | 0 | 0 | 0 | 0 | 0 | 0% | 30% | 25% | 45% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
7076 | Substation Minor Projects | Canberra Substation Noise Management | PS Security/Compliance | Input_Proj_Commit | 2014 | 2013 | 0 | 0 | 0 | 0 | 885000 | 0 | 0 | 0 | 0 | 0% | 90% | 5% | 5% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
P0001495 | Substation Minor Projects | Canberra Reduce AVR Settings | PS Security/Compliance | Input_Proj_Commit | 2014 | 2013 | 0 | 0 | 0 | 0 | 15000 | 0 | 0 | 0 | 0 | 0% | 30% | 25% | 45% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
6959 | Substation Minor Projects | Surge Arresters Instalation at 330kV Line Entries | PS Security/Compliance | Input_Proj_Commit | 2015 | 2013 | 37791.9219 | 11672.8498 | 133.6212 | 916440.5863 | 2253598.54 | 1844978.303 | 0 | 0 | 0 | 0% | 90.79% | 5% | 4.214% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
6335 | Transformer Replacement | Wagga Substation 330kV Transformer Replacements | PS Security/Compliance | Input_Proj_Commit | 2010 | 2013 | 5438709.5098 | -14182.4707 | 674.8994 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
6943 | Transformer Replacement | Munyang Transformer Replacement | PS Security/Compliance | Input_Proj_Commit | 2014 | 2013 | 219037.3199 | 655546.7783 | 10526968.6282 | 2725658.0135 | 100000 | 0 | 0 | 0 | 0 | 0% | 94.96% | 5% | 0.03506% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
7470 | Transmission Line Low Spans | 97G Line Murray to Guthega Low Spans Remediation | PS Security/Compliance | Input_Proj_Commit | 2014 | 2013 | 156232.736 | 9023.4589 | 95293.2759 | 1061516.8074 | 2884000 | 137785.3395 | 0 | 0 | 0 | 85% | 5% | 0% | 0% | 10% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
7459 | Transmission Line Low Spans | 999 Line Yass to Cowra Low Spans Remediation | PS Security/Compliance | Input_Proj_Commit | 2016 | 2013 | 0 | 13238.7723 | -12973.7698 | 7374.6428 | 0 | 0 | 0 | 0 | 0 | 85% | 5% | 0% | 0% | 10% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
7698 | Transmission Line Low Spans | 992 Line Burrinjuck to Tumut Low Spans Remediation | PS Security/Compliance | Input_Proj_Commit | 2016 | 2013 | 0 | 0 | 0 | 0 | 0 | 146325 | 300000 | 0 | 0 | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
6913 | Transmission Line Low Spans | 97K Line Cooma to Munyang Low Spans Remediation | PS Security/Compliance | Input_Proj_Commit | 2018 | 2013 | 0 | 1028.6514 | -1008.0514 | 0 | 0 | 0 | 0 | 0 | 0 | 85% | 5% | 0% | 0% | 10% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
7708 | Transmission Line Low Spans | 993 Line Gadara to Wagga Low Spans Remediation | PS Security/Compliance | Input_Proj_Commit | 2018 | 2013 | 0 | 0 | 0 | 0 | 0 | 0 | 279000 | 279000 | 45000 | 85% | 5% | 0% | 0% | 10% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
P0002240 | Transmission Line Low Spans | Southern Region Pole Lines Low Spans Remediation | PS Security/Compliance | Input_Proj_Commit | 2019 | 2013 | 0 | 0 | 0 | 0 | 0 | 103995 | 103995 | 207990 | 207990 | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
P0002243 | Transmission Line Low Spans | Central Region Pole Lines Low Spans Remediation | PS Security/Compliance | Input_Proj_Commit | 2019 | 2013 | 0 | 0 | 0 | 0 | 0 | 100140 | 100140 | 200280 | 200280 | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
P0002246 | Transmission Line Low Spans | Southern Region Tower Lines Low Spans Remediation | PS Security/Compliance | Input_Proj_Commit | 2019 | 2013 | 0 | 0 | 0 | 0 | 0 | 0 | 66145.35 | 132290.85 | 198436.2 | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
P0002249 | Transmission Line Low Spans | Northern Region Tower Lines Low Spans Remediation | PS Security/Compliance | Input_Proj_Commit | 2019 | 2013 | 0 | 0 | 6349.3557 | 3406.8749 | 0 | 0 | 87950.1 | 175900.05 | 263850.15 | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
P0002252 | Transmission Line Low Spans | Northern Region Pole Lines Low Spans Remediation | PS Security/Compliance | Input_Proj_Commit | 2019 | 2013 | 0 | 0 | 0 | 0 | 0 | 173295 | 173295 | 346590 | 346590 | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
P0002255 | Transmission Line Low Spans | Central Region Tower Lines Low Spans Remediation | PS Security/Compliance | Input_Proj_Commit | 2019 | 2013 | 0 | 0 | 0 | 0 | 0 | 0 | 83576.1 | 167152.35 | 250728.45 | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
6969 | Supply to Gunnedah, Narrabri and Moree | Installation of Phase Shifting Transformer on 969 Line | PS Augmentation | Input_Proj_Future | 2018 | 2013 | 0 | 0 | 0 | 0 | 0 | 287829 | 949979 | 2163912 | 11864415 | 1.504% | 95.6% | 2.154% | 0.7441% | 0% | 0% | 0% | 0% | 0% | 0% | 58.15% | 14.97% | 0% | 7.006% | 0.3167% | 5.992% | 2.631% | 10.93% | 0% | 0% | 0% | 0% | 0%
6704 | Supply to the ACT | Wallaroo 330kV Switching Station | PS Augmentation | Input_Proj_Future | 2018 | 2013 | 0 | 0 | 0 | 0 | 218539 | 1198254 | 3597904 | 18931068 | 7454919 | 22.27% | 67.94% | 4.72% | 1.88% | 3.185% | 0% | 0% | 0% | 0% | 0% | 21.61% | 19.04% | 0.3439% | 1.119% | 1.245% | 2.173% | 0.05852% | 51.23% | 0% | 0% | 0% | 3.185% | 0%
7661 | Substation Minor Projects | Supply to Temora | PS Connections | Input_Proj_Future | 2015 | 2013 | 0 | 0 | 0 | 0 | 1968263 | 286794 | 0 | 0 | 0 | 2.443% | 89.57% | 7.041% | 0.9472% | 0% | 0% | 0% | 0% | 0% | 0% | 80.74% | 2.674% | 0% | 1.807% | 0.5592% | 0.2925% | 0.1098% | 13.82% | 0% | 0% | 0% | 0% | 0%
P0000851 | Substation Minor Projects | Supply to Gulgong West | PS Connections | Input_Proj_Future | 2015 | 2013 | 0 | 0 | 0 | 0 | 114993 | 1336060 | 0 | 0 | 0 | 0% | 83.57% | 16.43% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 31.85% | 47.83% | 0% | 1.513% | 0.2426% | 0.2325% | 0.08644% | 18.25% | 0% | 0% | 0% | 0% | 0%
7094 | Substation Minor Projects | Supply to Marsden Park | PS Connections | Input_Proj_Future | 2016 | 2013 | 0 | 0 | 0 | 0 | 71269 | 1130374 | 386953 | 0 | 0 | 0% | 86% | 8.206% | 5.792% | 0% | 0% | 0% | 0% | 0% | 0% | 34.5% | 42.98% | 0% | 2.02% | 0.5843% | 0.6493% | 0.1176% | 19.15% | 0% | 0% | 0% | 0% | 0%
8093 | Substation Minor Projects | Supply to Molong | PS Connections | Input_Proj_Future | 2016 | 2013 | 0 | 0 | 0 | 0 | 32923 | 807608 | 374190 | 0 | 0 | 0% | 96.26% | 3.74% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40.78% | 35.66% | 0% | 1.175% | 1.683% | 0.5907% | 0.08287% | 20.03% | 0% | 0% | 0% | 0% | 0%
P0002157 | Substation Minor Projects | Supply to Googong | PS Connections | Input_Proj_Future | 2018 | 2013 | 0 | 0 | 0 | 0 | 0 | 3306 | 145800 | 1059136 | 178813 | 0% | 93.17% | 2.37% | 4.458% | 0% | 0% | 0% | 0% | 0% | 0% | 30.26% | 43.62% | 0% | 2.313% | 0.6692% | 0.7437% | 0.1346% | 22.26% | 0% | 0% | 0% | 0% | 0%
P0002186 | Easements | Easement Acquisition in the ACT | PS Easements | Input_Proj_Future | 2017 | 2013 | 0 | 0 | 0 | 0 | 0 | 175205 | 2069719 | 7555076 | 0 | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 22% | 78% | 0%
7673 | Property | Strategic Property Acquisition at Maraylya | PS Easements | Input_Proj_Future | 2016 | 2013 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 65.79% | 34.21% | 0% | 0%
P0002217 | Property | Strategic Property Acquisition in Sydney | PS Easements | Input_Proj_Future | 2017 | 2013 | 0 | 0 | 0 | 0 | 1131868 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 73.17% | 26.83% | 0% | 0% | 0% | 0% | 26.83% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.3977% | 72.77% | 0% | 0% | 0%
2001B | Cable Remediation | Cable 41 Backfill Rehabilitation | PS Replacement | Input_Proj_Future | 2017 | 2013 | 0 | 0 | 0 | 0 | 384533 | 463435 | 12849391.8 | 3683197 | 0 | 0% | 74.4% | 0% | 0% | 0% | 25.6% | 0% | 0% | 0% | 0% | 0% | 25.6% | 0% | 0% | 0% | 0% | 0% | 74.4% | 0% | 0% | 0% | 0% | 0%
7344 | Capacitor Bank | Broken Hill No.3 and No.4 Capacitors | PS Replacement | Input_Proj_Future | 2020 | 2013 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6290.9 | 0% | 94.69% | 5.312% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 41.31% | 34.78% | 0% | 2.439% | 0.1469% | 0.139% | 0.06087% | 21.13% | 0% | 0% | 0% | 0% | 0%
8022 | Communications | Dumaresq Protection & Communication Replacement | PS Replacement | Input_Proj_Future | 2014 | 2013 | 0 | 0 | 0 | 30347 | 594365 | 0 | 0 | 0 | 0 | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 18.13% | 81.87% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
7462 | Communications | Spur Microwave System Replacement | PS Replacement | Input_Proj_Future | 2015 | 2013 | 0 | 0 | 0 | 0 | 2765725 | 1015413 | 0 | 0 | 0 | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 16.6% | 21.42% | 0% | 0% | 0% | 0% | 0% | 61.98% | 0% | 0% | 0% | 0% | 0%
8222 | Communications | Hammonds Hill Radio Repeater Site Mains Power | PS Replacement | Input_Proj_Future | 2016 | 2013 | 0 | 0 | 0 | 0 | 0 | 380629.9 | 477324.4 | 0 | 0 | 0% | 47.89% | 0% | 47.21% | 4.895% | 0% | 0% | 0% | 0% | 0% | 8.997% | 43.36% | 0% | 1.492% | 0.03557% | 0.8055% | 0.3975% | 40.02% | 0% | 0% | 0% | 4.895% | 0%
P0002577 | Communications | Communications Between Lismore and Coffs Harbour | PS Replacement | Input_Proj_Future | 2016 | 2013 | 0 | 0 | 0 | 0 | 131574 | 854954.1 | 8755090.4 | 0 | 0 | 97.56% | 0.4618% | 0% | 1.983% | 0% | 0% | 0% | 0% | 0% | 0% | 5.794% | 12.85% | 0% | 0% | 0% | 0% | 0% | 81.35% | 0% | 0% | 0% | 0% | 0%
P0002583 | Communications | Communications Between Wallerawang and Orange North via Panorama Substation | PS Replacement | Input_Proj_Future | 2016 | 2013 | 0 | 0 | 0 | 0 | 94127 | 515001.9 | 6859734 | 0 | 0 | 76.04% | 18.95% | 0.3052% | 2.586% | 2.117% | 0% | 0% | 0% | 0% | 0% | 6.1% | 10.14% | 0% | 0% | 0% | 0% | 0% | 81.64% | 0% | 0% | 0% | 2.117% | 0%
P0002589 | Communications | Communications Between Williamsdale and Cooma | PS Replacement | Input_Proj_Future | 2016 | 2013 | 0 | 0 | 0 | 0 | 33417 | 172379.2 | 4592109.2 | 0 | 0 | 97.52% | 0.4678% | 0% | 2.009% | 0% | 0% | 0% | 0% | 0% | 0% | 10.14% | 12.27% | 0% | 0% | 0% | 0% | 0% | 77.59% | 0% | 0% | 0% | 0% | 0%
P0002579 | Communications | Communications Between Coffs Harbour and Port Macquarie | PS Replacement | Input_Proj_Future | 2017 | 2013 | 0 | 0 | 0 | 0 | 0 | 79666.3 | 640336.9 | 8185201.5 | 0 | 96% | 0.7546% | 0% | 3.241% | 0% | 0% | 0% | 0% | 0% | 0% | 7.145% | 12.8% | 0% | 0% | 0% | 0% | 0% | 80.06% | 0% | 0% | 0% | 0% | 0%
P0002585 | Communications | Communications Between Wellington and Orange North | PS Replacement | Input_Proj_Future | 2017 | 2013 | 0 | 0 | 0 | 0 | 0 | 39293.1 | 206048.5 | 5499292.4 | 0 | 94.94% | 1.121% | 0.5929% | 3.349% | 0% | 0% | 0% | 0% | 0% | 0% | 8.026% | 12.73% | 0% | 0% | 0% | 0% | 0% | 79.24% | 0% | 0% | 0% | 0% | 0%
P0002581 | Communications | Communications Between Port Macquarie and Stroud - Includes Waratah West to Tomago | PS Replacement | Input_Proj_Future | 2018 | 2013 | 0 | 0 | 0 | 0 | 0 | 0 | 96027.4 | 841446.9 | 9436502.6 | 90.53% | 5.25% | 0% | 3.71% | 0.5061% | 0% | 0% | 0% | 0% | 0% | 7.298% | 12.17% | 0% | 0% | 0% | 0% | 0% | 80.03% | 0% | 0% | 0% | 0.5061% | 0%
P0002587 | Communications | Communications Between Parkes and Cowra | PS Replacement | Input_Proj_Future | 2018 | 2013 | 0 | 0 | 0 | 0 | 0 | 0 | 54306 | 262612.7 | 6652914.8 | 95.99% | 0.924% | 0.3258% | 2.761% | 0% | 0% | 0% | 0% | 0% | 0% | 6.914% | 12.79% | 0% | 0% | 0% | 0% | 0% | 80.3% | 0% | 0% | 0% | 0% | 0%
P0002591 | Communications | Communications Between Uranquinty and Griffith | PS Replacement | Input_Proj_Future | 2019 | 2013 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 80142.3 | 628671.4 | 97.11% | 0.6118% | 0.1272% | 2.156% | 0% | 0% | 0% | 0% | 0% | 0% | 5.996% | 12.86% | 0% | 0% | 0% | 0% | 0% | 81.15% | 0% | 0% | 0% | 0% | 0%
P0002593 | Communications | Communications Between Yass and Wagga | PS Replacement | Input_Proj_Future | 2019 | 2013 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 80835.3 | 796096.7 | 94.73% | 1.784% | 0% | 3.486% | 0% | 0% | 0% | 0% | 0% | 0% | 7.312% | 12.8% | 0% | 0% | 0% | 0% | 0% | 79.88% | 0% | 0% | 0% | 0% | 0%
8118 | Disconnection of Munmorah Power Station | Disconnection of Munmorah Power Station | PS Replacement | Input_Proj_Future | 2015 | 2013 | 0 | 0 | 0 | 0 | 0 | 1822184 | 0 | 0 | 0 | 0% | 96.86% | 0% | 0% | 3.135% | 0% | 0% | 0% | 0% | 0% | 59.64% | 0.3322% | 0% | 1.778% | 0.03691% | 1.043% | 0.5045% | 33.53% | 0% | 3.135% | 0% | 0% | 0%
8023 | Oil Containment | Beryl Oil Containment Upgrade | PS Replacement | Input_Proj_Future | 2016 | 2013 | 0 | 0 | 0 | 0 | 97276 | 1080005.5 | 369711.3 | 0 | 0 | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 7.408% | 39.71% | 0% | 0.02629% | 0.001384% | 0.002767% | 0.002767% | 52.85% | 0% | 0% | 0% | 0% | 0%
8025 | Oil Containment | Deniliquin Oil Containment Upgrade | PS Replacement | Input_Proj_Future | 2016 | 2013 | 0 | 0 | 0 | 0 | 100985 | 1121183 | 383807.2 | 0 | 0 | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 13.02% | 21.44% | 0% | 0.1203% | 0.006331% | 0.01266% | 0.01266% | 65.4% | 0% | 0% | 0% | 0% | 0%
8026 | Oil Containment | Murrumburrah Oil Containment Upgrade | PS Replacement | Input_Proj_Future | 2016 | 2013 | 0 | 0 | 0 | 0 | 87688 | 973556.5 | 333271.4 | 0 | 0 | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 8.164% | 20.51% | 0% | 0.07291% | 0.003837% | 0.007674% | 0.007674% | 71.24% | 0% | 0% | 0% | 0% | 0%
8027 | Oil Containment | Muswellbrook Oil Containment Upgrade | PS Replacement | Input_Proj_Future | 2016 | 2013 | 0 | 0 | 0 | 0 | 14816 | 931294 | 241975.3 | 0 | 0 | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 12.82% | 9.984% | 0% | 0% | 0% | 0% | 0% | 77.2% | 0% | 0% | 0% | 0% | 0%
8078 | Oil Containment | Inverell Oil Containment Upgrade | PS Replacement | Input_Proj_Future | 2016 | 2013 | 0 | 0 | 0 | 0 | 53182 | 903922.6 | 416705.8 | 0 | 0 | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 8.248% | 39.32% | 0% | 0% | 0% | 0% | 0% | 52.43% | 0% | 0% | 0% | 0% | 0%
8024 | Oil Containment | Panorama Oil Containment Upgrade | PS Replacement | Input_Proj_Future | 2017 | 2013 | 0 | 0 | 0 | 0 | 0 | 68286.4 | 1083073.6 | 370762 | 0 | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 7.431% | 18.43% | 0% | 0.06553% | 0.003449% | 0.006898% | 0.006898% | 74.05% | 0% | 0% | 0% | 0% | 0%
8029 | Oil Containment | Mount Piper 132 Oil Containment Upgrade | PS Replacement | Input_Proj_Future | 2017 | 2013 | 0 | 0 | 0 | 0 | 0 | 43122.1 | 1061846.1 | 489238.4 | 0 | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 7.199% | 15.98% | 0% | 0.03754% | 0.001976% | 0.003952% | 0.003952% | 76.78% | 0% | 0% | 0% | 0% | 0%
8079 | Oil Containment | Dapto Oil Containment Upgrade | PS Replacement | Input_Proj_Future | 2017 | 2013 | 0 | 0 | 0 | 0 | 0 | 17508.4 | 1607684.4 | 417618.6 | 0 | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 4.043% | 41.12% | 0% | 0% | 0% | 0% | 0% | 54.83% | 0% | 0% | 0% | 0% | 0%
8094 | Oil Containment | Yass Oil Containment Upgrade | PS Replacement | Input_Proj_Future | 2017 | 2013 | 0 | 0 | 0 | 0 | 0 | 8328.6 | 747881.4 | 194320 | 0 | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 5.818% | 40.36% | 0% | 0% | 0% | 0% | 0% | 53.82% | 0% | 0% | 0% | 0% | 0%
P0001472 | Oil Containment | Mount Piper 500 Oil Containment Upgrade | PS Replacement | Input_Proj_Future | 2017 | 2013 | 0 | 0 | 0 | 0 | 0 | 56324.1 | 1245146 | 154627.2 | 0 | 0% | 90.39% | 0% | 0% | 9.615% | 0% | 0% | 0% | 0% | 0% | 8.699% | 25.78% | 0% | 0.0411% | 0.002163% | 0.004327% | 0.004327% | 55.86% | 0% | 9.615% | 0% | 0% | 0%
8032 | Oil Containment | Sydney South Oil Containment Upgrade | PS Replacement | Input_Proj_Future | 2018 | 2013 | 0 | 0 | 0 | 0 | 0 | 0 | 25757.2 | 2312946.3 | 600966.1 | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 8.287% | 15.73% | 0% | 0% | 0% | 0% | 0% | 75.98% | 0% | 0% | 0% | 0% | 0%
P0002051 | Protection Change | Sydney North Lines 926 and 927 Protection Relay Replacement | PS Replacement | Input_Proj_Future | 2014 | 2013 | 0 | 0 | 0 | 0 | 620453 | 0 | 0 | 0 | 0 | 0% | 2.868% | 88.42% | 7.092% | 1.621% | 0% | 0% | 0% | 0% | 0% | 27.56% | 71.3% | 0% | 0.3079% | 0.0162% | 0.03241% | 0.03241% | 0.7453% | 0% | 0% | 0% | 0% | 0%
P0002053 | Protection Change | Sydney South Lines 91J and 91F Protection Relay Replacement | PS Replacement | Input_Proj_Future | 2014 | 2013 | 0 | 0 | 0 | 0 | 492664 | 0 | 0 | 0 | 0 | 0% | 0% | 97.54% | 1.989% | 0.4712% | 0% | 0% | 0% | 0% | 0% | 27.3% | 72.7% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
7346 | Reactor Replacement | Buronga X2 220kV Reactor | PS Replacement | Input_Proj_Future | 2016 | 2013 | 0 | 0 | 0 | 0 | 318588 | 2751600.6 | 581725.2 | 0 | 0 | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 67.94% | 0.1324% | 0% | 3.156% | 0.1274% | 2.832% | 1.231% | 24.58% | 0% | 0% | 0% | 0% | 0%
7342 | Reactor Replacement | Broken Hill No.1 & No.2 220kV Reactors | PS Replacement | Input_Proj_Future | 2018 | 2013 | 0 | 0 | 0 | 0 | 0 | 0 | 179930.8 | 3580056.9 | 2765501.2 | 0% | 99.63% | 0% | 0% | 0.3736% | 0% | 0% | 0% | 0% | 0% | 40.44% | 28.11% | 0% | 3.348% | 0.05651% | 3.01% | 1.333% | 23.71% | 0% | 0% | 0% | 0% | 0%
7325 | Reactor Replacement | Beaconsfield West No.1 132kV Reactor | PS Replacement | Input_Proj_Future | 2019 | 2013 | 0 | 0 | 0 | 0 | 0 | 0 | 9663.5 | 65932.3 | 254971.5 | 0% | 97.94% | 0% | 0% | 2.06% | 0% | 0% | 0% | 0% | 0% | 45.6% | 34.88% | 0% | 5.576% | 0.003333% | 4.968% | 2.212% | 6.763% | 0% | 0% | 0% | 0% | 0%
0588B | Secondary System Renewal | Molong SCADA Remediation | PS Replacement | Input_Proj_Future | 2015 | 2013 | 0 | 0 | 0 | 0 | 170216 | 88524.1 | 0 | 0 | 0 | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 21.03% | 78.97% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
7062 | Secondary System Renewal | Kangaroo Valley Secondary System Replacement | PS Replacement | Input_Proj_Future | 2016 | 2013 | 0 | 0 | 0 | 0 | 0 | 626042.2 | 3898708.8 | 0 | 0 | 0% | 19.14% | 76.88% | 2.907% | 1.078% | 0% | 0% | 0% | 0% | 0% | 21.92% | 47.3% | 1.671% | 0.7545% | 0.03971% | 0.1194% | 0.07942% | 28.12% | 0% | 0% | 0% | 0% | 0%
7350 | Secondary System Renewal | Albury Secondary System Replacement | PS Replacement | Input_Proj_Future | 2016 | 2013 | 0 | 0 | 0 | 0 | 1294326 | 5203797.9 | 1554613.2 | 0 | 0 | 0% | 15.18% | 81.19% | 3.366% | 0.265% | 0% | 0% | 0% | 0% | 0% | 27.31% | 38.49% | 0.3945% | 0.9309% | 0.09879% | 0.1431% | 0.09591% | 32.53% | 0% | 0% | 0% | 0% | 0%
7353 | Secondary System Renewal | Balranald Secondary System Replacement | PS Replacement | Input_Proj_Future | 2016 | 2013 | 0 | 0 | 0 | 0 | 0 | 446400.5 | 2799036.1 | 0 | 0 | 0% | 12.1% | 87.82% | 0% | 0.08346% | 0% | 0% | 0% | 0% | 0% | 34.34% | 52.37% | 0% | 0.5678% | 0.02522% | 0.05044% | 0.05044% | 12.59% | 0% | 0% | 0% | 0% | 0%
7366 | Secondary System Renewal | Hume Secondary System Replacement | PS Replacement | Input_Proj_Future | 2017 | 2013 | 0 | 0 | 0 | 0 | 0 | 13412 | 838110.7 | 2000891.9 | 0 | 0% | 23.32% | 73.88% | 2.795% | 0% | 0% | 0% | 0% | 0% | 0% | 26.19% | 35.13% | 0% | 0.8772% | 0.04617% | 0.1558% | 0.09234% | 37.5% | 0% | 0% | 0% | 0% | 0%
7365 | Secondary System Renewal | Deniliquin Secondary System Replacement | PS Replacement | Input_Proj_Future | 2018 | 2013 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 598060.4 | 3620739.5 | 0% | 10.18% | 89.82% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 27.6% | 62.59% | 0% | 0.2351% | 0.01237% | 0.02474% | 0.02474% | 9.517% | 0% | 0% | 0% | 0% | 0%
7655 | Secondary System Renewal | Haymarket Secondary System Replacement | PS Replacement | Input_Proj_Future | 2018 | 2013 | 0 | 0 | 0 | 0 | 0 | 0 | 730905 | 2861911.5 | 2807182.7 | 0% | 7.524% | 29.55% | 62.92% | 0% | 0% | 0% | 0% | 0% | 0% | 28.91% | 64.52% | 0% | 0.6066% | 0.03192% | 0.06385% | 0.06385% | 5.8% | 0% | 0% | 0% | 0% | 0%
7675 | Secondary System Renewal | ANM Secondary System Replacement | PS Replacement | Input_Proj_Future | 2018 | 2013 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 932320.9 | 2561230 | 0% | 15.14% | 79.54% | 5.32% | 0% | 0% | 0% | 0% | 0% | 0% | 22% | 63.46% | 0% | 0.2441% | 0.03866% | 0.04509% | 0.02156% | 14.18% | 0% | 0% | 0% | 0% | 0%
8075 | Secondary System Renewal | Taree Secondary System Replacement | PS Replacement | Input_Proj_Future | 2018 | 2013 | 0 | 0 | 0 | 0 | 544762 | 2066056.3 | 5047351.4 | 6949616.8 | 3663366 | 0% | 22.63% | 73.11% | 4.261% | 0% | 0% | 0% | 0% | 0% | 0% | 33.04% | 35.06% | 0% | 1.421% | 0.07783% | 0.1898% | 0.1483% | 30.06% | 0% | 0% | 0% | 0% | 0%
7467 | Secondary System Renewal | Murrumburrah Secondary System Replacement | PS Replacement | Input_Proj_Future | 2019 | 2013 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 484764.7 | 0% | 11.18% | 88.82% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 25.98% | 63.21% | 0% | 0.2316% | 0.01219% | 0.02438% | 0.02438% | 10.52% | 0% | 0% | 0% | 0% | 0%
7638 | Secondary System Renewal | Sydney North Secondary System Replacement | PS Replacement | Input_Proj_Future | 2019 | 2013 | 0 | 0 | 0 | 0 | 1076023 | 9331418.6 | 11870280.1 | 3974807.2 | 1013087.6 | 0% | 43.57% | 54.12% | 2.202% | 0.1032% | 0% | 0% | 0% | 0% | 0% | 23.1% | 27.09% | 0.2571% | 1.772% | 0.09329% | 0.2087% | 0.1866% | 47.29% | 0% | 0% | 0% | 0% | 0%
7756 | Secondary System Renewal | Armidale Secondary System Replacement | PS Replacement | Input_Proj_Future | 2019 | 2013 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 140383.6 | 3239719 | 0% | 8.531% | 89.71% | 1.761% | 0% | 0% | 0% | 0% | 0% | 0% | 28.2% | 64.2% | 0% | 0.3544% | 0.03028% | 0.04767% | 0.03481% | 7.124% | 0% | 0% | 0% | 0% | 0%
7351 | Secondary System Renewal | Beryl Secondary System Replacement | PS Replacement | Input_Proj_Future | 2020 | 2013 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 12.15% | 87.73% | 0.1116% | 0% | 0% | 0% | 0% | 0% | 0% | 25.58% | 62.89% | 0% | 0.3312% | 0.04683% | 0.06108% | 0.02854% | 11.07% | 0% | 0% | 0% | 0% | 0%
7354 | Secondary System Renewal | Buronga Secondary System Replacement | PS Replacement | Input_Proj_Future | 2020 | 2013 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 297808 | 0% | 16.75% | 17.1% | 66.15% | 0% | 0% | 0% | 0% | 0% | 0% | 23.38% | 57.69% | 0% | 0.2059% | 0.01084% | 0.02167% | 0.02167% | 18.68% | 0% | 0% | 0% | 0% | 0%
7651 | Secondary System Renewal | Liddell Secondary System Replacement | PS Replacement | Input_Proj_Future | 2020 | 2013 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 339093.3 | 2297556.1 | 0% | 29.59% | 18.66% | 51.76% | 0% | 0% | 0% | 0% | 0% | 0% | 34.58% | 29.96% | 0% | 1.422% | 0.08377% | 0.1646% | 0.1483% | 33.64% | 0% | 0% | 0% | 0% | 0%
7667 | Secondary System Renewal | Avon Secondary System Replacement | PS Replacement | Input_Proj_Future | 2021 | 2013 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 27.28% | 67.15% | 5.566% | 0% | 0% | 0% | 0% | 0% | 0% | 27.64% | 35.01% | 0% | 1.112% | 0.1202% | 0.19% | 0.1068% | 35.83% | 0% | 0% | 0% | 0% | 0%
8193 | Secondary System Renewal | Sydney South Secondary System Replacement | PS Replacement | Input_Proj_Future | 2022 | 2013 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 488495.7 | 2858886.1 | 0% | 31.59% | 67.4% | 1.01% | 0% | 0% | 0% | 0% | 0% | 0% | 40.17% | 28.69% | 0% | 2.468% | 0.1328% | 0.2618% | 0.2591% | 28.02% | 0% | 0% | 0% | 0% | 0%
P0001205 | Substation Minor Projects | Cowra Duplicated DC & AC Supplies | PS Replacement | Input_Proj_Future | 2014 | 2013 | 0 | 0 | 0 | 135515 | 323277 | 0 | 0 | 0 | 0 | 0% | 12.99% | 82.73% | 0% | 4.274% | 0% | 0% | 0% | 0% | 0% | 8.941% | 79.16% | 0% | 0.4186% | 0.02203% | 0.04407% | 0.04407% | 11.37% | 0% | 0% | 0% | 0% | 0%
8083 | Substation Minor Projects | Dapto 415V AC System Replacement | PS Replacement | Input_Proj_Future | 2015 | 2013 | 0 | 0 | 0 | 0 | 56820 | 2452661.4 | 0 | 0 | 0 | 0% | 62.51% | 34.07% | 0% | 3.423% | 0% | 0% | 0% | 0% | 0% | 28.23% | 30.91% | 0% | 3.684% | 0.1939% | 0.3878% | 0.3878% | 36.21% | 0% | 0% | 0% | 0% | 0%
6040 | Substation Minor Projects | Sydney West 132kV Disconnector Replacement | PS Replacement | Input_Proj_Future | 2016 | 2013 | 0 | 0 | 0 | 490198 | 536323 | 2448573.4 | 365637.3 | 0 | 0 | 0% | 97.91% | 0% | 0% | 2.089% | 0% | 0% | 0% | 0% | 0% | 43.56% | 19.49% | 0% | 2.098% | 0.7876% | 0.185% | 0.03134% | 33.84% | 0% | 0% | 0% | 0% | 0%
P0002049 | Substation Minor Projects | Sydney South AC System Replacement | PS Replacement | Input_Proj_Future | 2017 | 2013 | 0 | 0 | 0 | 0 | 0 | 0 | 417972.1 | 3461460.8 | 0 | 0% | 69.37% | 30.01% | 0% | 0.6284% | 0% | 0% | 0% | 0% | 0% | 26.73% | 23.93% | 0% | 6.645% | 0.3497% | 0.6995% | 0.6995% | 40.94% | 0% | 0% | 0% | 0% | 0%
6962 | Substation Renewal | Burrinjuck Substation Renewal | PS Replacement | Input_Proj_Future | 2017 | 2013 | 0 | 0 | 0 | 0 | 0 | 344418.2 | 2203861.1 | 6767975.9 | 0 | 0% | 80.47% | 12.38% | 3.131% | 4.023% | 0% | 0% | 0% | 0% | 0% | 44.83% | 31.35% | 3.893% | 1.605% | 0.09767% | 0.2149% | 0.01319% | 15.67% | 0% | 0% | 0% | 2.329% | 0%
7378 | Substation Renewal | Vales Point Substation Renewal | PS Replacement | Input_Proj_Future | 2018 | 2013 | 0 | 0 | 0 | 0 | 170345 | 964586 | 1933472.8 | 17298952.3 | 10579369.5 | 2.1% | 90.06% | 6.089% | 1.035% | 0.7167% | 0% | 0% | 0% | 0% | 0% | 28.74% | 24.59% | 0% | 2.195% | 1.23% | 0.7319% | 0.1271% | 42.39% | 0% | 0% | 0% | 0% | 0%
8076 | Substation Renewal | Taree Substation 33kV Switchyard Renewal | PS Replacement | Input_Proj_Future | 2018 | 2013 | 0 | 0 | 0 | 0 | 0 | 303461.9 | 954332.4 | 4330864.3 | 496780.9 | 0% | 80.91% | 16.46% | 2.63% | 0% | 0% | 0% | 0% | 0% | 0% | 42.64% | 30.6% | 0% | 2.345% | 0.06334% | 0.1197% | 0.1045% | 24.13% | 0% | 0% | 0% | 0% | 0%
7398 | Substation Renewal | Canberra Substation Renewal | PS Replacement | Input_Proj_Future | 2019 | 2013 | 0 | 0 | 0 | 88505 | 468470 | 1138146.1 | 1910934.2 | 7227701.6 | 22133202 | 0% | 87.51% | 10.76% | 1.725% | 0% | 0% | 0% | 0% | 0% | 0% | 45.53% | 15.26% | 0% | 2.007% | 0.1804% | 0.8499% | 0.4129% | 35.77% | 0% | 0% | 0% | 0% | 0%
6914 | Substation Renewal | Wagga 132 Substation Renewal | PS Replacement | Input_Proj_Future | 2020 | 2013 | 0 | 0 | 0 | 0 | 0 | 0 | 371686.7 | 1204609.7 | 4932412.1 | 2.306% | 87.61% | 8.864% | 1.223% | 0% | 0% | 0% | 0% | 0% | 0% | 47.15% | 20.58% | 0.2093% | 1.799% | 0.858% | 0.9629% | 0.3203% | 28.12% | 0% | 0% | 0% | 0% | 0%
7678 | Substation Renewal | Munmorah Substation Renewal | PS Replacement | Input_Proj_Future | 2020 | 2013 | 0 | 0 | 0 | 0 | 18952 | 158125.1 | 456511.3 | 1060847.2 | 3493000 | 0% | 91.14% | 8.319% | 0.5399% | 0% | 0% | 0% | 0% | 0% | 0% | 42.36% | 15.38% | 0% | 1.15% | 1.291% | 0.7803% | 0.0942% | 38.95% | 0% | 0% | 0% | 0% | 0%
7657 | Substation Renewal | Newcastle Substation Renewal | PS Replacement | Input_Proj_Future | 2021 | 2013 | 0 | 0 | 0 | 0 | 0 | 20871.9 | 466203.5 | 1085481.6 | 1706852.7 | 0% | 96.91% | 1.875% | 1.219% | 0% | 0% | 0% | 0% | 0% | 0% | 45.75% | 16.98% | 0% | 1.395% | 0.4619% | 0.1693% | 0.02591% | 35.22% | 0% | 0% | 0% | 0% | 0%
7091 | SVC Control System Replacement | Armidale SVC Control System Replacement | PS Replacement | Input_Proj_Future | 2018 | 2013 | 0 | 0 | 0 | 0 | 0 | 0 | 24195.5 | 1393917.7 | 4866318.8 | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 80.7% | 14.38% | 0% | 3.676% | 0% | 0% | 0% | 1.248% | 0% | 0% | 0% | 0% | 0%
7363 | Transformer Replacement | Forbes No.1 & No.2 132kV Transformers | PS Replacement | Input_Proj_Future | 2018 | 2013 | 0 | 0 | 0 | 0 | 25748 | 368169.2 | 2207478.7 | 2767985.5 | 465390.1 | 0% | 96.78% | 3.223% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 34.67% | 30.37% | 0% | 4.058% | 0.6433% | 2.916% | 1.239% | 26.11% | 0% | 0% | 0% | 0% | 0%
7528 | Transformer Replacement | Tamworth 330 No.2 330kV Transformer | PS Replacement | Input_Proj_Future | 2018 | 2013 | 0 | 0 | 0 | 0 | 89761 | 292619.6 | 475428.1 | 5660517.1 | 1199831.5 | 0% | 97.74% | 2.257% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 37.51% | 18.5% | 0% | 4.426% | 0.1768% | 3.583% | 1.591% | 34.21% | 0% | 0% | 0% | 0% | 0%
7356, 7357, 7563 | Transformer Replacement | Beaconsfield West No.1 & No.2 330kV Transformers | PS Replacement | Input_Proj_Future | 2018 | 2013 | 0 | 0 | 0 | 0 | 1205893 | 636323.1 | 6219278.8 | 14941544.8 | 2597537.6 | 0% | 96.57% | 1.795% | 1.149% | 0.4883% | 0% | 0% | 0% | 0% | 0% | 39.74% | 18.22% | 0% | 1.363% | 0.0475% | 0.09325% | 0.0486% | 40.48% | 0% | 0% | 0% | 0% | 0%
7711 | Transmission Line Wood Pole Replacement | Line 970 Burrinjuck to Yass Pole Replacements | PS Replacement | Input_Proj_Future | 2016 | 2013 | 0 | 0 | 0 | 0 | 22381 | 191294.6 | 9084599.3 | 0 | 0 | 98.31% | 0.2016% | 0% | 0% | 1.49% | 0% | 0% | 0% | 0% | 0% | 12.56% | 20.57% | 0% | 0% | 1.723% | 0.1436% | 0% | 65% | 0% | 0% | 0% | 0% | 0%
7699 | Transmission Line Wood Pole Replacement | Line 99F Uranquinty to Yanco Pole Replacements | PS Replacement | Input_Proj_Future | 2018 | 2013 | 0 | 0 | 0 | 0 | 0 | 61987.1 | 219655.8 | 512969.8 | 18082820.7 | 97.78% | 0.4828% | 0% | 0% | 1.736% | 0% | 0% | 0% | 0% | 0% | 6.936% | 14.23% | 0% | 0% | 0.002169% | 0.0001808% | 0% | 78.39% | 0% | 0% | 0% | 0.445% | 0%
6002H | Wallerawang to Orange Transmission Line Replacement | New 66kV Capacitor at Panorama | PS Replacement | Input_Proj_Future | 2016 | 2013 | 0 | 0 | 0 | 0 | 0 | 84356.3 | 1077164.9 | 0 | 0 | 0% | 94.79% | 5.212% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 48.65% | 35.98% | 0% | 3.061% | 0.4251% | 0.1911% | 0.06066% | 11.63% | 0% | 0% | 0% | 0% | 0%
6002I | Wallerawang to Orange Transmission Line Replacement | New 66kV Capacitor at Orange | PS Replacement | Input_Proj_Future | 2016 | 2013 | 0 | 0 | 0 | 0 | 0 | 89096.7 | 1137698.1 | 0 | 0 | 0% | 95.07% | 4.934% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 46.73% | 36.61% | 0% | 3.57% | 0.1741% | 0.234% | 0.1281% | 12.55% | 0% | 0% | 0% | 0% | 0%
6002J | Wallerawang to Orange Transmission Line Replacement | New 132kV Capacitor at Orange North | PS Replacement | Input_Proj_Future | 2016 | 2013 | 0 | 0 | 0 | 0 | 0 | 89557.3 | 1143585.8 | 0 | 0 | 0% | 95.09% | 4.909% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 51.18% | 31.58% | 0% | 3.559% | 0.3698% | 0.2216% | 0.1078% | 12.98% | 0% | 0% | 0% | 0% | 0%
6002K | Wallerawang to Orange Transmission Line Replacement | New Series Reactor on Line 94X at Wallerawang | PS Replacement | Input_Proj_Future | 2016 | 2013 | 0 | 0 | 0 | 0 | 0 | 118129.2 | 1508425.8 | 0 | 0 | 0% | 97.76% | 2.24% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 43.67% | 28.62% | 0% | 5.133% | 0.1597% | 4.342% | 1.801% | 16.27% | 0% | 0% | 0% | 0% | 0%
6002L | Wallerawang to Orange Transmission Line Replacement | New Series Reactor on Line 949 at Mt Piper | PS Replacement | Input_Proj_Future | 2019 | 2013 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 118129.2 | 0% | 97.76% | 2.24% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 43.67% | 28.62% | 0% | 5.133% | 0.1597% | 4.342% | 1.801% | 16.27% | 0% | 0% | 0% | 0% | 0%
7839 | Cable Remediation | Sydney South 330kV Series Reactor Reconfiguration | PS Security/Compliance | Input_Proj_Future | 2018 | 2013 | 0 | 0 | 0 | 0 | 0 | 90715.1 | 407414.7 | 2356405.1 | 3161861.5 | 6.644% | 90.14% | 1.09% | 0% | 2.127% | 0% | 0% | 0% | 0% | 0% | 18.19% | 34.21% | 0% | 4.514% | 0.535% | 0.6489% | 0.4285% | 41.48% | 0% | 0% | 0% | 0% | 0%
7646 | Communications | Communications to Beryl and Ilford | PS Security/Compliance | Input_Proj_Future | 2017 | 2013 | 0 | 0 | 0 | 0 | 0 | 66377.5 | 622927.2 | 526151.5 | 0 | 0% | 41.18% | 0% | 58.82% | 0% | 0% | 0% | 0% | 0% | 0% | 13.47% | 41.24% | 0% | 0% | 0% | 0% | 0% | 45.29% | 0% | 0% | 0% | 0% | 0%
7316 | Control System | Multiple Contingency System Protection Scheme | PS Security/Compliance | Input_Proj_Future | 2016 | 2013 | 0 | 0 | 0 | 0 | 0 | 612770.9 | 3953371.1 | 0 | 0 | 0% | 2.82% | 70.71% | 26.47% | 0% | 0% | 0% | 0% | 0% | 0% | 32.92% | 65.11% | 0% | 0.5357% | 0.0282% | 0.05639% | 0.05639% | 1.297% | 0% | 0% | 0% | 0% | 0%
P0001885 | Protection Change | Gadara Protection Change | PS Security/Compliance | Input_Proj_Future | 2014 | 2013 | 0 | 0 | 0 | 334492 | 68458 | 0 | 0 | 0 | 0 | 0% | 0% | 80.87% | 19.13% | 0% | 0% | 0% | 0% | 0% | 0% | 21.44% | 78.56% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
6832 | Quality of Supply | Voltage Unbalance Limits | PS Security/Compliance | Input_Proj_Future | 2015 | 2013 | 0 | 0 | 0 | 0 | 128405 | 667552.9 | 0 | 0 | 0 | 94.36% | 0.5364% | 0% | 0% | 5.104% | 0% | 0% | 0% | 0% | 0% | 22.38% | 62.84% | 0% | 0% | 0.3142% | 0.02619% | 0% | 14.43% | 0% | 0% | 0% | 0% | 0%
7397 | Quality of Supply | Assessment of NER Quality of Supply Compliance | PS Security/Compliance | Input_Proj_Future | 2019 | 2013 | 0 | 0 | 0 | 0 | 0 | 0 | 352405.9 | 851841.2 | 851841.2 | 0% | 87.34% | 12.66% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 32.76% | 44.47% | 0% | 2.195% | 0.648% | 0.5828% | 0.1477% | 19.19% | 0% | 0% | 0% | 0% | 0%
P0002366 | SCADA | SCADA to Tenterfield | PS Security/Compliance | Input_Proj_Future | 2014 | 2013 | 0 | 0 | 0 | 121367 | 517430 | 0 | 0 | 0 | 0 | 0% | 10.65% | 12.73% | 76.63% | 0% | 0% | 0% | 0% | 0% | 0% | 48.59% | 36.1% | 0% | 0.2439% | 0.01284% | 0.02567% | 0.02567% | 15% | 0% | 0% | 0% | 0% | 0%
P0002155 | Supply to ACT | Canberra Substation 330kV Bypass | PS Security/Compliance | Input_Proj_Future | 2015 | 2013 | 0 | 0 | 0 | 0 | 98186 | 400903.3 | 0 | 0 | 0 | 34.94% | 3.875% | 0% | 61.18% | 0% | 0% | 0% | 0% | 0% | 0% | 36.23% | 33.66% | 0% | 0% | 0.8943% | 0.07453% | 0% | 29.15% | 0% | 0% | 0% | 0% | 0%
6913 | Transmission Line Low Spans | Line 97K Cooma to Munyang Low Span Remediation | PS Security/Compliance | Input_Proj_Future | 2018 | 2013 | 0 | 0 | 0 | 0 | 0 | 66391.35 | 72752.25 | 214014.6 | 2043099.6 | 53.61% | 46.39% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 19.46% | 20.22% | 0% | 0% | 0% | 0% | 0% | 60.32% | 0% | 0% | 0% | 0% | 0%
8089 | Transmission Line Low Spans | Lines 4 & 5 Yass to Marulan Low Span Remediation | PS Security/Compliance | Input_Proj_Future | 2018 | 2013 | 0 | 0 | 0 | 0 | 0 | 6684.9 | 13555.5 | 38069.55 | 387434.7 | 45.19% | 54.81% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 11.59% | 29.14% | 0% | 0% | 0% | 0% | 0% | 59.27% | 0% | 0% | 0% | 0% | 0%
8090 | Transmission Line Low Spans | Snowy to Yass/Canberra Low Span Remediation | PS Security/Compliance | Input_Proj_Future | 2019 | 2013 | 0 | 0 | 0 | 0 | 363613 | 73460.55 | 374675.7 | 1604405.55 | 1604405.55 | 43.93% | 56.07% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 10.67% | 19.58% | 0% | 0.05751% | 0.02456% | 0.651% | 0.0009597% | 69.02% | 0% | 0% | 0% | 0% | 0%
8086 | Transmission Line Low Spans | Line 96H Clarence River Crossing Conductor Height | PS Security/Compliance | Input_Proj_Future | 2023 | 2013 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 96.52% | 0% | 0% | 0% | 3.478% | 0% | 0% | 0% | 0% | 0% | 15% | 19.06% | 0% | 0% | 1.221% | 5.058% | 0% | 56.18% | 0% | 0% | 0% | 3.478% | 0%
Total Capex | [6 empty] | 2010 | 2011 | 2012 | 2013 | 2014 | 2015 | 2016 | 2017 | 2018
Programs Committed | [6 empty] | 82278859.2794 | 66977009.0335 | 86189100.7583 | 104379315.4533 | 115015387.334 | 40514843.2 | 37379837.903 | 29521857.505 | 25608136.4243
Projects Committed | [6 empty] | 348887369.4359 | 310644669.6686 | 275896434.0745 | 376182452.0287 | 405074707.5013 | 123252319.5965 | 52718777.123 | 8489603.25 | 11086074.8
[7 empty] | 431166228.7153 | 377621678.7021 | 362085534.8328 | 480561767.4819 | 520090094.8353 | 163767162.7965 | 90098615.026 | 38011460.755 | 36694211.2243
Programs Future | [6 empty] | 0 | 0 | 0 | 0 | 0 | 22391929.6023 | 24640331.5011 | 25938888.3651 | 26754231.5173
Projects Committed | [6 empty] | 0 | 0 | 0 | 1200424 | 16506637 | 48046403.5 | 115057322.65 | 147518718.9 | 142204689.55
[7 empty] | 0 | 0 | 0 | 1200424 | 16506637 | 70438333.1023 | 139697654.1511 | 173457607.2651 | 168958921.0673
Grand Total | [6 empty] | 431166228.7153 | 377621678.7021 | 362085534.8328 | 481762191.4819 | 536596731.8353 | 234205495.8987 | 229796269.1771 | 211469068.0202 | 205653132.2916
Check | 1.1623e-06 | [5 empty] | 3.5763e-07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Note on F4: "0" indicates commissioning year equals year capex incurred.

## Costs ($2014) Excl Real Esc
Costs (Real $2014) Excluding Real Escalation
[7 empty] | 443798051.8222 | 388684813.8203 | 372693509.4861 | 495876318.1855 | 549928540.5127 | 240038063.5323 | 235502046.9625 | 216826741.2923 | 211047729.4952 | 564947788.3876 | 253636321.3778 | 217722635.413 | 282997952.9447
[7 empty] | Capex Incurred | [8 empty] | Capex Commissioned |  |  |  | Capex Commissioned 2015 - Transitional Adjustment
Program \ Project No. | Program \ Project Grouping | Program \ Project Name | Program \ Project Category | Committed / Future | Commissioning Date | Effective Estimate Year | 2010 | 2011 | 2012 | 2013 | 2014 | 2015 | 2016 | 2017 | 2018 | 2015 | 2016 | 2017 | 2018 | 2015
6716 | Communications | Establishment of Gigabit Ethernet CDN Network | PS Facilities | Input_Prog_Commit | 0 | 2013 | -0.95875 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5161 | Non HV Buildings & Civil Work | Building Improvements | PS Facilities | Input_Prog_Commit | 0 | 2013 | 3176428.2644 | 3751266.9669 | 5437667.0304 | 5379657.821 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5976 | Non HV Buildings & Civil Work | HO Refurbishment | PS Facilities | Input_Prog_Commit | 0 | 2013 | -1489172.9549 | 1321.7148 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5989 | Non HV Buildings & Civil Work | Sydney West Warehouse Extension | PS Facilities | Input_Prog_Commit | 0 | 2013 | 105053.4134 | 125229.3027 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7332 | Non HV Buildings & Civil Work | Strategic Accomodation | PS Facilities | Input_Prog_Commit | 0 | 2013 | 0 | 495867.152 | 7097031.6907 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7332 | Non HV Buildings & Civil Work | Strategic Accomodation | PS Facilities | Input_Prog_Commit | 0 | 2014 | 0 | 0 | 0 | 0 | 37683457.2129 | 8612015 | 10973300 | 4832700 | 0 | 8612015 | 10973300 | 4832700 | 0 | 0
7332 | Non HV Buildings & Civil Work | Strategic Accomodation | PS Facilities | Input_Prog_Commit | 0 | 2013 | 0 | 0 | 0 | 15821291.5373 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7517 | Non HV Buildings & Civil Work | Newcastle Mezzanine Floor | PS Facilities | Input_Prog_Commit | 0 | 2013 | 0 | 37786.7814 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8050 | Non HV Buildings & Civil Work | Haymarket Blast Wall | PS Facilities | Input_Prog_Commit | 0 | 2014 | 0 | 0 | 0 | 0 | 54078 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6420 | Information Technology | Video Conferencing & Collaboration | PS Information Technology | Input_Prog_Commit | 0 | 2013 | 535999.4642 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
ICT Applications | Information Technology | Capital Program Delivery | PS Information Technology | Input_Prog_Commit | 0 | 2013 | 2751280.9244 | 921492.1505 | 24215.0562 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
ICT Applications | Information Technology | Finance & Information Systems | PS Information Technology | Input_Prog_Commit | 0 | 2013 | 2756032.4549 | 9699521.7623 | 12561855.3489 | 20205852.7728 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
ICT Applications | Information Technology | Network Planning & Performance | PS Information Technology | Input_Prog_Commit | 0 | 2013 | 796284.204 | 397105.0263 | 11889.168 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
ICT Applications | Information Technology | Network Services & Operations | PS Information Technology | Input_Prog_Commit | 0 | 2013 | 100989.7611 | 275091.9742 | 74437.0408 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
ICT Applications | Information Technology | People, Strategy & Corporate Services | PS Information Technology | Input_Prog_Commit | 0 | 2013 | 75374.187 | 82476.5715 | 3569.4737 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
ICT Applications | Information Technology | 0 | PS Information Technology | Input_Prog_Commit | 0 | 2013 | 0 | 0 | 0 | 0 | 12678878.9062 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
ICT Corporate Data Network | Information Technology | Finance & Information Systems | PS Information Technology | Input_Prog_Commit | 0 | 2013 | 2295633.9998 | 1062437.5534 | 1090310.5288 | 808265.4088 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
ICT Corporate Data Network | Information Technology | 0 | PS Information Technology | Input_Prog_Commit | 0 | 2013 | 0 | 0 | 0 | 0 | 1832148.4375 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
ICT Infrastructure | Information Technology | Finance & Information Systems | PS Information Technology | Input_Prog_Commit | 0 | 2013 | 5360875.4639 | 3361760.0439 | 6399671.3375 | 4204814.5948 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
ICT Infrastructure | Information Technology | Network Services & Operations | PS Information Technology | Input_Prog_Commit | 0 | 2013 | 332861.6708 | 81607.2456 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
ICT Infrastructure | Information Technology | 0 | PS Information Technology | Input_Prog_Commit | 0 | 2013 | 0 | 0 | 0 | 0 | 6406343.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | Information Technology | Finance & Information Systems | PS Information Technology | Input_Prog_Commit | 0 | 2013 | 433374.6702 | -56615.2168 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5739 | Motor Vehicles & Mobile Plant | TG Mobile Plant | PS Motor Vehicles | Input_Prog_Commit | 0 | 2013 | 0 | 0 | 0 | 0 | 3933867.3901 | 3004840.7773 | 1814135.7422 | 1691743.0801 | 2241067.5 | 3004840.7773 | 1814135.7422 | 1691743.0801 | 2241067.5 | 0
5777 | Motor Vehicles & Mobile Plant | TG Business Vehicles | PS Motor Vehicles | Input_Prog_Commit | 0 | 2013 | 0 | 0 | 0 | 0 | 9607279.2614 | 5975616.9026 | 5926537.0117 | 7578927.2318 | 8365785.2312 | 5975616.9026 | 5926537.0117 | 7578927.2318 | 8365785.2312 | 0
0 | Motor Vehicles & Mobile Plant | Capital Program Delivery | PS Motor Vehicles | Input_Prog_Commit | 0 | 2013 | -461.4051 | 77697.5781 | 88689.5528 | 154015.3844 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | Motor Vehicles & Mobile Plant | Finance & Information Systems | PS Motor Vehicles | Input_Prog_Commit | 0 | 2013 | 2168.12 | 61074.63 | 13501.35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | Motor Vehicles & Mobile Plant | Network Planning & Performance | PS Motor Vehicles | Input_Prog_Commit | 0 | 2013 | 0 | 19300.3152 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | Motor Vehicles & Mobile Plant | Network Services & Operations | PS Motor Vehicles | Input_Prog_Commit | 0 | 2013 | 1163236.046 | 2521138.2842 | 3512969.0898 | 1539948.7072 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | Motor Vehicles & Mobile Plant | People, Strategy & Corporate Services | PS Motor Vehicles | Input_Prog_Commit | 0 | 2013 | 20385.8552 | 74027.8271 | 207040.3656 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | Motor Vehicles & Mobile Plant | People, Strategy & Corporate Services | PS Motor Vehicles | Input_Prog_Commit | 0 | 2013 | 12434050.0119 | 7888970.1075 | 10005081.8451 | 8552898.6741 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6424 | Cables | 42 Tunnel (Sydney Park) Water Treatment Plant | PS Network Asset Replacement | Input_Prog_Commit | 0 | 2013 | 117864.1216 | -155605.3712 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | Cables | Network Asset Replacement | PS Network Asset Replacement | Input_Prog_Commit | 0 | 2013 | 117159.6339 | 52343.7514 | 32823.3203 | 23598.3674 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4967 | Communications | Installation of PLC Voice Equipment | PS Network Asset Replacement | Input_Prog_Commit | 0 | 2014 | 0 | 0 | 0 | 0 | 294643.72 | 616030.3382 | 410686.8921 | 359351.0306 | 0 | 616030.3382 | 410686.8921 | 359351.0306 | 0 | 0
4968 | Communications | Installation of PLC Intertrips | PS Network Asset Replacement | Input_Prog_Commit | 0 | 2014 | 0 | 0 | 0 | 0 | 231724.2 | 214601.9484 | 321902.9226 | 107300.9742 | 160951.4613 | 214601.9484 | 321902.9226 | 107300.9742 | 160951.4613 | 0
4969 | Communications | Installation of VF Intertrips | PS Network Asset Replacement | Input_Prog_Commit | 0 | 2014 | 0 | 0 | 0 | 0 | 214381.8 | 49609.466 | 198437.864 | 173633.131 | 148828.398 | 49609.466 | 198437.864 | 173633.131 | 148828.398 | 0
7425 | Communications | SSZ Upgrade Work | PS Network Asset Replacement | Input_Prog_Commit | 0 | 2014 | 0 | 0 | 0 | 0 | 150921.55 | 64383.7393 | 32191.8696 | 72431.7067 | 24143.9022 | 64383.7393 | 32191.8696 | 72431.7067 | 24143.9022 | 0
0 | Communications | Network Asset Replacement | PS Network Asset Replacement | Input_Prog_Commit | 0 | 2013 | 1354698.018 | 1462555.1067 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | Communications | Network Asset Replacement | PS Network Asset Replacement | Input_Prog_Commit | 0 | 2013 | 0 | 0 | 373094.5228 | 3282824.4574 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4978 | Controls & Alarms | Installation of RTU Equipment | PS Network Asset Replacement | Input_Prog_Commit | 0 | 2014 | 0 | 0 | 0 | 0 | 4256648.5 | 1720008.344 | 2408011.6816 | 630669.7261 | 802670.5605 | 1720008.344 | 2408011.6816 | 630669.7261 | 802670.5605 | 0
0 | Controls & Alarms | Network Asset Replacement | PS Network Asset Replacement | Input_Prog_Commit | 0 | 2013 | 1844593.3641 | 2639624.8859 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | Controls & Alarms | Network Asset Replacement | PS Network Asset Replacement | Input_Prog_Commit | 0 | 2013 | 0 | 0 | 3540662.4348 | 2649015.362 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5071 | HV Buildings & Civil Work | Perimeter Security Fence | PS Network Asset Replacement | Input_Prog_Commit | 0 | 2014 | 0 | 0 | 0 | 0 | 104325 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5077 | HV Buildings & Civil Work | Switchyard Security Fence | PS Network Asset Replacement | Input_Prog_Commit | 0 | 2014 | 0 | 0 | 0 | 0 | 6140 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5098 | HV Buildings & Civil Work | Fire Protection Systems | PS Network Asset Replacement | Input_Prog_Commit | 0 | 2014 | 0 | 0 | 0 | 0 | 10000 | 0 | 185243.8 | 185243.8 | 0 | 0 | 185243.8 | 185243.8 | 0 | 0
5161 | HV Buildings & Civil Work | Depot Building Improvements and Upgrades | PS Network Asset Replacement | Input_Prog_Commit | 0 | 2014 | 0 | 0 | 0 | 0 | 5503690.66 | 605500 | 0 | 140000 | 0 | 605500 | 0 | 140000 | 0 | 0
5201 | HV Buildings & Civil Work | Substations Building and Property | PS Network Asset Replacement | Input_Prog_Commit | 0 | 2014 | 0 | 0 | 0 | 0 | 5746712.86 | 2767571.3753 | 797354.6093 | 633792.9637 | 338151.9137 | 2767571.3753 | 797354.6093 | 633792.9637 | 338151.9137 | 0
5949 | HV Buildings & Civil Work | Air Conditioning in Relay Rooms | PS Network Asset Replacement | Input_Prog_Commit | 0 | 2014 | 0 | 0 | 0 | 0 | 628112.28 | 486190.586 | 0 | 0 | 0 | 486190.586 | 0 | 0 | 0 | 0
6337 | HV Buildings & Civil Work | Security Fence Replace D-Pales | PS Network Asset Replacement | Input_Prog_Commit | 0 | 2014 | 0 | 0 | 0 | 0 | 54145 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | HV Buildings & Civil Work | Network Asset Replacement | PS Network Asset Replacement | Input_Prog_Commit | 0 | 2013 | 1789164.4883 | 1243690.1421 | 4896134.579 | 4958289.4833 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5651 | IT | SCADA Upgrade | PS Network Asset Replacement | Input_Prog_Commit | 0 | 2014 | 0 | 0 | 0 | 0 | 3390986.24 | 1414000 | 0 | 0 | 0 | 1414000 | 0 | 0 | 0 | 0
8238 | IT | SCADA Facilities Augmentation | PS Network Asset Replacement | Input_Prog_Commit | 0 | 2014 | 0 | 0 | 0 | 0 | 776869.15 | 350000 | 0 | 0 | 0 | 350000 | 0 | 0 | 0 | 0
5923 | Metering | Replacement of Siements 7EC Meters | PS Network Asset Replacement | Input_Prog_Commit | 0 | 2014 | 0 | 0 | 0 | 0 | 301214.46 | 0 | 0 | 225716.0873 | 0 | 0 | 0 | 225716.0873 | 0 | 0
5925 | Metering | Replacement of Email A1R-AL Meters | PS Network Asset Replacement | Input_Prog_Commit | 0 | 2014 | 0 | 0 | 0 | 0 | 339838 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5926 | Metering | Replacement of CEWE CEP/CEQ Meters | PS Network Asset Replacement | Input_Prog_Commit | 0 | 2014 | 0 | 0 | 0 | 0 | 525100.06 | 309705.3178 | 0 | 0 | 0 | 309705.3178 | 0 | 0 | 0 | 0
5927 | Metering | Replacement of Ferrari Disc Pulsing Meters | PS Network Asset Replacement | Input_Prog_Commit | 0 | 2014 | 0 | 0 | 0 | 0 | 91317.93 | 213232.133 | 142154.7553 | 244822.0786 | 157949.7281 | 213232.133 | 142154.7553 | 244822.0786 | 157949.7281 | 0
6296 | Metering | Upgrade Site Metering Schemes | PS Network Asset Replacement | Input_Prog_Commit | 0 | 2014 | 0 | 0 | 0 | 0 | 213620.2 | 338574.1309 | 451432.1746 | 42014.847 | 565984.7665 | 338574.1309 | 451432.1746 | 42014.847 | 565984.7665 | 0
0 | Metering | Network Asset Replacement | PS Network Asset Replacement | Input_Prog_Commit | 0 | 2013 | 1260039.5381 | 749122.9255 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | Metering | Network Asset Replacement | PS Network Asset Replacement | Input_Prog_Commit | 0 | 2013 | 0 | 0 | 1782065.5039 | 3104047.5812 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4946 | Protection | Replacement of H-Type Relays - Key Metro Sites | PS Network Asset Replacement | Input_Prog_Commit | 0 | 2014 | 0 | 0 | 0 | 0 | 16250.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4947 | Protection | Replacement of H-Type Relays - Remaining Sites | PS Network Asset Replacement | Input_Prog_Commit | 0 | 2014 | 0 | 0 | 0 | 0 | -11273.55 | 0 | 0 | 0 | 53666.7779 | 0 | 0 | 0 | 53666.7779 | 0
4954 | Protection | Replacement of CSD IMS Fault Recorders | PS Network Asset Replacement | Input_Prog_Commit | 0 | 2014 | 0 | 0 | 0 | 0 | 143294.98 | 0 | 0 | 75548.3354 | 151096.6708 | 0 | 0 | 75548.3354 | 151096.6708 | 0
4957 | Protection | Replacement of TS Relays | PS Network Asset Replacement | Input_Prog_Commit | 0 | 2014 | 0 | 0 | 0 | 0 | 74092 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4960 | Protection | Replacement of THS Relays | PS Network Asset Replacement | Input_Prog_Commit | 0 | 2014 | 0 | 0 | 0 | 0 | 447256.73 | 437187.8645 | 105443.2979 | 160220.8008 | 0 | 437187.8645 | 105443.2979 | 160220.8008 | 0 | 0
4961 | Protection | Replacement of THR Relays | PS Network Asset Replacement | Input_Prog_Commit | 0 | 2014 | 0 | 0 | 0 | 0 | 95573.85 | 0 | 1676638.1969 | 695827.8889 | 581578.9005 | 0 | 1676638.1969 | 695827.8889 | 581578.9005 | 0
4962 | Protection | Replacement of YTG Relays | PS Network Asset Replacement | Input_Prog_Commit | 0 | 2014 | 0 | 0 | 0 | 0 | 953174.56 | 894827.3543 | 1361313.1876 | 1115177.9936 | 710336.0258 | 894827.3543 | 1361313.1876 | 1115177.9936 | 710336.0258 | 0
5150 | Protection | Replacement of RAZFE Relays | PS Network Asset Replacement | Input_Prog_Commit | 0 | 2014 | 0 | 0 | 0 | 0 | 515695.39 | 0 | 214821.5198 | 104110.4618 | 104110.4618 | 0 | 214821.5198 | 104110.4618 | 104110.4618 | 0
5541 | Protection | Replacement of Optimho Relays | PS Network Asset Replacement | Input_Prog_Commit | 0 | 2014 | 0 | 0 | 0 | 0 | 28456.62 | 0 | 213055.5645 | 105722.0088 | 678178.1697 | 0 | 213055.5645 | 105722.0088 | 678178.1697 | 0
5921 | Protection | Replacement of D202,D203,D21SE,D22SE Transformer Differential Relays | PS Network Asset Replacement | Input_Prog_Commit | 0 | 2014 | 0 | 0 | 0 | 0 | 901778.34 | 219733.2407 | 137868.9318 | 273086.3383 | 126565.81 | 219733.2407 | 137868.9318 | 273086.3383 | 126565.81 | 0
5922 | Protection | Replacement of DB Transformer Differential Relays | PS Network Asset Replacement | Input_Prog_Commit | 0 | 2014 | 0 | 0 | 0 | 0 | 998355.41 | 285044.4285 | 605907.2498 | 731258.7899 | 192639.783 | 285044.4285 | 605907.2498 | 731258.7899 | 192639.783 | 0
5929 | Protection | Replacement of Feeder OC & EF Protection | PS Network Asset Replacement | Input_Prog_Commit | 0 | 2014 | 0 | 0 | 0 | 0 | 95618.82 | 195019.6416 | 104110.4618 | 52055.2309 | 260276.1544 | 195019.6416 | 104110.4618 | 52055.2309 | 260276.1544 | 0
6291 | Protection | GPS Clocks | PS Network Asset Replacement | Input_Prog_Commit | 0 | 2014 | 0 | 0 | 0 | 0 | 146990.16 | 131809.4363 | 131809.4363 | 105447.549 | 79085.6618 | 131809.4363 | 131809.4363 | 105447.549 | 79085.6618 | 0
6351 | Protection | Replacement of Siemens 7SA502 & 7SA511 Relays | PS Network Asset Replacement | Input_Prog_Commit | 0 | 2014 | 0 | 0 | 0 | 0 | 30000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6353 | Protection | Replacement of HO2 Pilot Wire Relays | PS Network Asset Replacement | Input_Prog_Commit | 0 | 2014 | 0 | 0 | 0 | 0 | 83553.52 | 276715.1738 | 0 | 0 | 0 | 276715.1738 | 0 | 0 | 0 | 0
6612 | Protection | Relay Replacement For 940/941 132kV Feeders | PS Network Asset Replacement | Input_Prog_Commit | 0 | 2013 | -39.6792 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6725 | Protection | Replacement of MBCI Pilot Wire Relays | PS Network Asset Replacement | Input_Prog_Commit | 0 | 2014 | 0 | 0 | 0 | 0 | 210249.19 | 157326.302 | 0 | 0 | 0 | 157326.302 | 0 | 0 | 0 | 0
6865 | Protection | Replacement of Quadramho Relays | PS Network Asset Replacement | Input_Prog_Commit | 0 | 2014 | 0 | 0 | 0 | 0 | 30000 | 155947.6967 | 488786.5879 | 107333.5558 | 1144801.984 | 155947.6967 | 488786.5879 | 107333.5558 | 1144801.984 | 0
6866 | Protection | Replacement of 7SA513 Relays | PS Network Asset Replacement | Input_Prog_Commit | 0 | 2014 | 0 | 0 | 0 | 0 | 28683.24 | 270667.1115 | 0 | 0 | 380470.3498 | 270667.1115 | 0 | 0 | 380470.3498 | 0
7576 | Protection | Remote Interrogation of Protection Relays | PS Network Asset Replacement | Input_Prog_Commit | 0 | 2014 | 0 | 0 | 0 | 0 | 86468.15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7746 | Protection | Replacement of EDMI Fault Recorders | PS Network Asset Replacement | Input_Prog_Commit | 0 | 2014 | 0 | 0 | 0 | 0 | 29534.54 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7747 | Protection | Install Fault Recorders | PS Network Asset Replacement | Input_Prog_Commit | 0 | 2014 | 0 | 0 | 0 | 0 | 315833.55 | 475511.4002 | 0 | 0 | 75548.3354 | 475511.4002 | 0 | 0 | 75548.3354 | 0
7750 | Protection | Replacement of 7SD511 Relays | PS Network Asset Replacement | Input_Prog_Commit | 0 | 2014 | 0 | 0 | 0 | 0 | 207431.23 | 169726.494 | 0 | 107333.5558 | 193316.1563 | 169726.494 | 0 | 107333.5558 | 193316.1563 | 0
8266 | Protection | Efficient Relay Replacements | PS Network Asset Replacement | Input_Prog_Commit | 0 | 2014 | 0 | 0 | 0 | 0 | 99286.81 | 67608.7033 | 0 | 0 | 0 | 67608.7033 | 0 | 0 | 0 | 0
0 | Protection | Network Asset Replacement | PS Network Asset Replacement | Input_Prog_Commit | 0 | 2013 | 4050671.1331 | 5456172.9233 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | Protection | Network Asset Replacement | PS Network Asset Replacement | Input_Prog_Commit | 0 | 2013 | 0 | 0 | 7094083.4051 | 7215531.2632 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6702 | SCADA | Data Centre Infrastructure | PS Network Asset Replacement | Input_Prog_Commit | 0 | 2014 | 0 | 0 | 0 | 0 | 63000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7910 | SCADA | Sydney North SCADA Fibre Marshalling Kiosk | PS Network Asset Replacement | Input_Prog_Commit | 0 | 2013 | 0 | 0 | 0 | 145579.9013 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | SCADA | Network Asset Replacement | PS Network Asset Replacement | Input_Prog_Commit | 0 | 2013 | 1524412.6902 | 1718729.7541 | 1549481.7592 | 900950.399 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4882 | Substations | Transformer and Reactor Life Extension | PS Network Asset Replacement | Input_Prog_Commit | 0 | 2013 | 0 | 47253.4702 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4882 | Substations | Transformer and Reactor Life Extension | PS Network Asset Replacement | Input_Prog_Commit | 0 | 2014 | 0 | 0 | 0 | 0 | 1229767.99 | 1672635.403 | 1357883.1598 | 1937337.6463 | 2096757.5095 | 1672635.403 | 1357883.1598 | 1937337.6463 | 2096757.5095 | 0
4884 | Substations | Unplanned Transformer and Reactor Replacement | PS Network Asset Replacement | Input_Prog_Commit | 0 | 2013 | 0 | 0 | 0 | -4602.8908 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4904 | Substations | Replacement of ABB 132kV HLD CBs | PS Network Asset Replacement | Input_Prog_Commit | 0 | 2014 | 0 | 0 | 0 | 0 | 904575.7912 | 328900.9578 | 584375.4313 | 876563.147 | 146093.8578 | 328900.9578 | 584375.4313 | 876563.147 | 146093.8578 | 0
4905 | Substations | Replacement of DELLE 66kV HPGE CBs | PS Network Asset Replacement | Input_Prog_Commit | 0 | 2014 | 0 | 0 | 0 | 0 | 4505.17 | 42000 | 0 | 1199660 | 218120 | 42000 | 0 | 1199660 | 218120 | 0
4906 | Substations | Replacement of Instrument Transformers with No Sampling Point | PS Network Asset Replacement | Input_Prog_Commit | 0 | 2014 | 0 | 0 | 0 | 0 | 92539 | 44058.5732 | 264351.4393 | 484645.0661 | 176234.8 | 44058.5732 | 264351.4393 | 484645.0661 | 176234.8 | 0
4907 | Substations | Replacement of Substation Batteries - 50V As Required | PS Network Asset Replacement | Input_Prog_Commit | 0 | 2014 | 0 | 0 | 0 | 0 | 176623 | 115096.8 | 60468.1 | 155608.0904 | 100979.3904 | 115096.8 | 60468.1 | 155608.0904 | 100979.3904 | 0
4908 | Substations | Replacement of Substation Batteries - 110V As Required | PS Network Asset Replacement | Input_Prog_Commit | 0 | 2014 | 0 | 0 | 0 | 0 | 304594.4 | 127382.367 | 38891.7101 | 122485.1304 | 122485.1304 | 127382.367 | 38891.7101 | 122485.1304 | 122485.1304 | 0
4909 | Substations | Replacement of Substation Batteries - 240V As Required | PS Network Asset Replacement | Input_Prog_Commit | 0 | 2014 | 0 | 0 | 0 | 0 | 50122.29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4910 | Substations | Replacement of High DGA Instrument Transformers 132kV As Required | PS Network Asset Replacement | Input_Prog_Commit | 0 | 2014 | 0 | 0 | 0 | 0 | 190208.27 | 330671.4855 | 1126394.8697 | 206914.2855 | 211114.4 | 330671.4855 | 1126394.8697 | 206914.2855 | 211114.4 | 0
4914 | Substations | Replacement of Isolators & Earth Switches > 220kV | PS Network Asset Replacement | Input_Prog_Commit | 0 | 2014 | 0 | 0 | 0 | 0 | 224045.88 | 396893.1775 | 396893.1775 | 396893.1775 | 396893.1775 | 396893.1775 | 396893.1775 | 396893.1775 | 396893.1775 | 0
4915 | Substations | Replacement of Isolators & Earth Switches 132kV | PS Network Asset Replacement | Input_Prog_Commit | 0 | 2014 | 0 | 0 | 0 | 0 | 350000 | 119078.863 | 119078.863 | 119078.863 | 119078.863 | 119078.863 | 119078.863 | 119078.863 | 119078.863 | 0
4920 | Substations | Condition Monitoring DGA | PS Network Asset Replacement | Input_Prog_Commit | 0 | 2014 | 0 | 0 | 0 | 0 | 13555.63 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4928 | Substations | Replacement of Current Transformers | PS Network Asset Replacement | Input_Prog_Commit | 0 | 2014 | 0 | 0 | 0 | 0 | 147261.73 | 286443.5494 | 81048.3729 | 324193.4916 | 132175.7197 | 286443.5494 | 81048.3729 | 324193.4916 | 132175.7197 | 0
4929 | Substations | Replacement of Ducon CTs and CVTs | PS Network Asset Replacement | Input_Prog_Commit | 0 | 2014 | 0 | 0 | 0 | 0 | 856591.48 | 370258.7 | 0 | 0 | 0 | 370258.7 | 0 | 0 | 0 | 0
5085 | Substations | Replacement of High DGA Instrument Transformers > 220kV As Required | PS Network Asset Replacement | Input_Prog_Commit | 0 | 2014 | 0 | 0 | 0 | 0 | 839312.3 | 702276.226 | 842730 | 702275 | 978985.616 | 702276.226 | 842730 | 702275 | 978985.616 | 0
5087 | Substations | Replacement of High DGA Instrument Transformers < 66kV As Required | PS Network Asset Replacement | Input_Prog_Commit | 0 | 2014 | 0 | 0 | 0 | 0 | -5656.23 | 109117.4 | 169308.3 | 126719.6 | 128189.6 | 109117.4 | 169308.3 | 126719.6 | 128189.6 | 0
5517 | Substations | Replacement of Merlin Gerin FA2 CBs | PS Network Asset Replacement | Input_Prog_Commit | 0 | 2014 | 0 | 0 | 0 | 0 | 3244920.67 | 1964249.1353 | 1415207.5451 | 283041.5451 | 1415207.5902 | 1964249.1353 | 1415207.5451 | 283041.5451 | 1415207.5902 | 0
5519 | Substations | Replacement of Sprecher & Schuh CBs | PS Network Asset Replacement | Input_Prog_Commit | 0 | 2014 | 0 | 0 | 0 | 0 | 253771.94 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5916 | Substations | Replacement of CBs Approaching Rated Operations | PS Network Asset Replacement | Input_Prog_Commit | 0 | 2014 | 0 | 0 | 0 | 0 | 1080000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6103 | Substations | Sydney South Substation 330kV Bus Coupling | PS Network Asset Replacement | Input_Prog_Commit | 0 | 2013 | 3510.5111 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6338 | Substations | Security Fence Disturbance Detection | PS Network Asset Replacement | Input_Prog_Commit | 0 | 2014 | 0 | 0 | 0 | 0 | 20589.44 | 0 | 70000 | 0 | 0 | 0 | 70000 | 0 | 0 | 0
6340 | Substations | Security Lighting Upgrade | PS Network Asset Replacement | Input_Prog_Commit | 0 | 2014 | 0 | 0 | 0 | 0 | 63189.1 | 87500 | 748330.1 | 417601.8 | 877265.9 | 87500 | 748330.1 | 417601.8 | 877265.9 | 0
7308 | Substations | Replacment of Capacitor CBs | PS Network Asset Replacement | Input_Prog_Commit | 0 | 2013 | 273.146 | -184.0394 | 0 | -8931.9405 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7469 | Substations | Liddell 330kV 84 Line Connection | PS Network Asset Replacement | Input_Prog_Commit | 0 | 2014 | 0 | 0 | 0 | 0 | 23136.18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7753 | Substations | SF6 CT Monitoring | PS Network Asset Replacement | Input_Prog_Commit | 0 | 2014 | 0 | 0 | 0 | 0 | 29321.77 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8273 | Substations | Online Condition Monitoring | PS Network Asset Replacement | Input_Prog_Commit | 0 | 2014 | 0 | 0 | 0 | 0 | 126699 | 42155.4059 | 179055.8309 | 370242.5678 | 88252.9962 | 42155.4059 | 179055.8309 | 370242.5678 | 88252.9962 | 0
0 | Substations | Network Asset Replacement | PS Network Asset Replacement | Input_Prog_Commit | 0 | 2013 | -6.2123 | 32684.6998 | 0 | 2996.2355 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | Substations | Network Asset Replacement | PS Network Asset Replacement | Input_Prog_Commit | 0 | 2013 | 5012978.4424 | 3968740.8489 | 5769012.3047 | 5976048.9243 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | Substations | Network Asset Replacement | PS Network Asset Replacement | Input_Prog_Commit | 0 | 2013 | 9798924.219 | 8218731.6001 | 8912663.8325 | 5018483.388 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | Substations | Network Asset Replacement | PS Network Asset Replacement | Input_Prog_Commit | 0 | 2013 | 3301500.413 | 2952074.6767 | 3018495.7437 | 11497307.7605 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | Substations | Network Asset Replacement | PS Network Asset Replacement | Input_Prog_Commit | 0 | 2013 | 188847.5338 | 393329.0501 | 188800.9282 | 102442.0657 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | Substations | Network Asset Replacement | PS Network Asset Replacement | Input_Prog_Commit | 0 | 2013 | 6382940.6657 | 1707825.2667 | 159492.7853 | 2006169.1441 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4939 | Transmission Lines | Aging Wood Poles | PS Network Asset Replacement | Input_Prog_Commit | 0 | 2014 | 0 | 0 | 0 | 0 | 3080503.11 | 1050000 | 0 | 0 | 0 | 1050000 | 0 | 0 | 0 | 0
4943 | Transmission Lines | Emergency Structures (Guyed Masts) | PS Network Asset Replacement | Input_Prog_Commit | 0 | 2013 | 122414.54 | 62959.093 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | Transmission Lines | Transmission Line Minor Upgrades | PS Network Asset Replacement | Input_Prog_Commit | 0 | 2013 | 973420.7218 | 786320.6197 | 949754.4401 | 235012.7843 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | Transmission Lines | Network Asset Replacement | PS Network Asset Replacement | Input_Prog_Commit | 0 | 2013 | 7670814.0006 | 3440202.9747 | 2306788.9043 | 2632685.3052 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8165 | Misc Assets & Office Equipment | Misc Assets & Office Equipment | PS Network-Other | Input_Prog_Commit | 0 | 2014 | 0 | 0 | 0 | 0 | 2070254 | 2502731 | 1445000 | 1511000 | 1165000 | 2502731 | 1445000 | 1511000 | 1165000 | 0
4931 | Substations | CCTV | PS Security/Compliance | Input_Prog_Commit | 0 | 2013 | 1066846.8895 | 81925.5837 | 87753.5007 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4979 | Substations | RRS Security | PS Security/Compliance | Input_Prog_Commit | 0 | 2013 | 301586.1239 | 115541.7429 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5071 | Substations | Security Perimeter Fence | PS Security/Compliance | Input_Prog_Commit | 0 | 2013 | 2580981.4664 | 1234912.459 | 1118170.4312 | 388717.4468 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5073 | Substations | Replace Lock & Key System | PS Security/Compliance | Input_Prog_Commit | 0 | 2013 | 90793.9127 | 51088.9858 | 3906.3317 | -17439.483 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5077 | Substations | Security Delineation Fence | PS Security/Compliance | Input_Prog_Commit | 0 | 2013 | 1858322.5516 | 1094092.707 | 59220.3927 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5100 | Substations | Intrusion Detection | PS Security/Compliance | Input_Prog_Commit | 0 | 2013 | 1652234.6554 | 471465.2568 | 5738.8038 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6337 | Substations | Security Fence Replace D-Pales | PS Security/Compliance | Input_Prog_Commit | 0 | 2013 | 774032.6535 | 1578.8126 | 119339.2045 | 177511.9379 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6338 | Substations | Fence Disturbance Detection | PS Security/Compliance | Input_Prog_Commit | 0 | 2013 | 0 | 0 | 25155.7022 | 399973.432 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6340 | Substations | Security Lighting Upgrade | PS Security/Compliance | Input_Prog_Commit | 0 | 2013 | 0 | 233490.3981 | 193604.3604 | 80168.4539 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7076 | Substations | Southern Region | PS Security/Compliance | Input_Prog_Commit | 0 | 2013 | 0 | 0 | 0 | 4178.9315 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | Information Technology | ICT Applications | PS Information Technology | Input_Prog_Future | 0 | 2013 | 0 | 0 | 0 | 0 | 0 | 11682519.5312 | 10962011.7188 | 11064941.4062 | 10241503.9062 | 11682519.5312 | 10962011.7188 | 11064941.4062 | 10241503.9062 | 0
0 | Information Technology | ICT Corporate Data Network | PS Information Technology | Input_Prog_Future | 0 | 2013 | 0 | 0 | 0 | 0 | 0 | 2830566.4062 | 3859863.2812 | 3087890.625 | 2058593.75 | 2830566.4062 | 3859863.2812 | 3087890.625 | 2058593.75 | 0
0 | Information Technology | ICT Infrastructure | PS Information Technology | Input_Prog_Future | 0 | 2013 | 0 | 0 | 0 | 0 | 0 | 4837695.3125 | 4837695.3125 | 3962792.9688 | 8491699.2188 | 4837695.3125 | 4837695.3125 | 3962792.9688 | 8491699.2188 | 0
4907 | Communications | 50V Batteries | PS Network Asset Replacement | Input_Prog_Future | 0 | 2013 | 0 | 0 | 0 | 0 | 0 | 208490.4637 | 250189.1328 | 166792.515 | 208490.4637 | 208490.4637 | 250189.1328 | 166792.515 | 208490.4637 | 0
5068 | Communications | 50V Battery Chargers | PS Network Asset Replacement | Input_Prog_Future | 0 | 2013 | 0 | 0 | 0 | 0 | 0 | 60573.0918 | 121145.4631 | 100954.6727 | 141336.974 | 60573.0918 | 121145.4631 | 100954.6727 | 141336.974 | 0
4972 | Communications | 50V Power Systems | PS Network Asset Replacement | Input_Prog_Future | 0 | 2014 | 0 | 0 | 0 | 0 | 0 | 98189.728 | 145975.9817 | 145975.9817 | 97317.3212 | 98189.728 | 145975.9817 | 145975.9817 | 97317.3212 | 0
8222 | Communications | Hammonds Hill Radio Repeater Site Mains Power | PS Network Asset Replacement | Input_Prog_Future | 0 | 2014 | 0 | 0 | 0 | 0 | 0 | 35000 | 0 | 0 | 0 | 35000 | 0 | 0 | 0 | 0
8260 | Communications | CAS and BAS Equipment | PS Network Asset Replacement | Input_Prog_Future | 0 | 2014 | 0 | 0 | 0 | 0 | 0 | 201894.4301 | 190018.2871 | 201894.4301 | 201894.4301 | 201894.4301 | 190018.2871 | 201894.4301 | 201894.4301 | 0
7770 | Metering | Replacement of E1 Meters | PS Network Asset Replacement | Input_Prog_Future | 0 | 2014 | 0 | 0 | 0 | 0 | 0 | 0 | 225716.0873 | 0 | 0 | 0 | 225716.0873 | 0 | 0 | 0
8043 | Metering | Replacement of EDMI MK III Energy Meters | PS Network Asset Replacement | Input_Prog_Future | 0 | 2014 | 0 | 0 | 0 | 0 | 0 | 137104.8155 | 8476.1834 | 64870.0438 | 24849.8532 | 137104.8155 | 8476.1834 | 64870.0438 | 24849.8532 | 0
4949 | Protection | Replacement of D202 Relays | PS Network Asset Replacement | Input_Prog_Future | 0 | 2014 | 0 | 0 | 0 | 0 | 0 | 68934.4659 | 0 | 0 | 0 | 68934.4659 | 0 | 0 | 0 | 0
4956 | Protection | Replacement of TH1A Relays | PS Network Asset Replacement | Input_Prog_Future | 0 | 2014 | 0 | 0 | 0 | 0 | 0 | 60131.6994 | 0 | 0 | 0 | 60131.6994 | 0 | 0 | 0 | 0
5919 | Protection | Replacement of THR Relays | PS Network Asset Replacement | Input_Prog_Future | 0 | 2014 | 0 | 0 | 0 | 0 | 0 | 0 | 6464.9215 | 565226.6985 | 1250916.0603 | 0 | 6464.9215 | 565226.6985 | 1250916.0603 | 0
5920 | Protection | Replacement of YTG Relays | PS Network Asset Replacement | Input_Prog_Future | 0 | 2014 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 419228.9491 | 0 | 0 | 0 | 419228.9491 | 0
6864 | Protection | Replacement of Micromho Relays | PS Network Asset Replacement | Input_Prog_Future | 0 | 2014 | 0 | 0 | 0 | 0 | 0 | 383263.989 | 0 | 0 | 479272.9941 | 383263.989 | 0 | 0 | 479272.9941 | 0
7556 | Protection | Replacement of RADSB Transformer Differential Relays | PS Network Asset Replacement | Input_Prog_Future | 0 | 2014 | 0 | 0 | 0 | 0 | 0 | 131230.288 | 135217.4065 | 65615.144 | 137868.9318 | 131230.288 | 135217.4065 | 65615.144 | 137868.9318 | 0
7748 | Protection | Replacement of DLN90 Relays | PS Network Asset Replacement | Input_Prog_Future | 0 | 2014 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8020 | Protection | Replacement of LFCB102 Relays | PS Network Asset Replacement | Input_Prog_Future | 0 | 2014 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 80110.4004 | 0 | 0 | 0 | 80110.4004 | 0
8261 | Protection | Secondary System Technology Upgrades | PS Network Asset Replacement | Input_Prog_Future | 0 | 2014 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2809671.6161 | 1456870.3049 | 0 | 0 | 2809671.6161 | 1456870.3049 | 0
5518 | Substations | Replacement of Merlin Gerin FA4 CBs | PS Network Asset Replacement | Input_Prog_Future | 0 | 2014 | 0 | 0 | 0 | 0 | 0 | 608783.0902 | 1521957.6353 | 1217566.1353 | 0 | 608783.0902 | 1521957.6353 | 1217566.1353 | 0 | 0
6860 | Substations | Replacement of ASEA 66kV HLR CBs | PS Network Asset Replacement | Input_Prog_Future | 0 | 2014 | 0 | 0 | 0 | 0 | 0 | 0 | 327180 | 109060 | 0 | 0 | 327180 | 109060 | 0 | 0
6861 | Substations | Replacement of Magrini 11kV MAG12MG500 CBs | PS Network Asset Replacement | Input_Prog_Future | 0 | 2014 | 0 | 0 | 0 | 0 | 0 | 109059.7589 | 0 | 0 | 0 | 109059.7589 | 0 | 0 | 0 | 0
6862 | Substations | Replacement of Siemens 330kV 3AQ2 CBs | PS Network Asset Replacement | Input_Prog_Future | 0 | 2014 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 566083.0451 | 0 | 0 | 0 | 566083.0451 | 0
6863 | Substations | Replacement of Siemens 330kV 3AS2 CBs | PS Network Asset Replacement | Input_Prog_Future | 0 | 2014 | 0 | 0 | 0 | 0 | 0 | 566083 | 566083 | 283041.5 | 0 | 566083 | 566083 | 283041.5 | 0 | 0
7308 | Substations | Replacement of Capacitor CBs | PS Network Asset Replacement | Input_Prog_Future | 0 | 2014 | 0 | 0 | 0 | 0 | 0 | 294409.8713 | 678089.1784 | 857940.5497 | 790815.614 | 294409.8713 | 678089.1784 | 857940.5497 | 790815.614 | 0
7799 | Substations | Replacement of Sprecher HGF215 CBs | PS Network Asset Replacement | Input_Prog_Future | 0 | 2014 | 0 | 0 | 0 | 0 | 0 | 126000 | 0 | 0 | 0 | 126000 | 0 | 0 | 0 | 0
8082 | Substations | Replacement of Sprecher HGF215 CBs | PS Network Asset Replacement | Input_Prog_Future | 0 | 2014 | 0 | 0 | 0 | 0 | 0 | 0 | 283041.5451 | 283041.5451 | 283041.5451 | 0 | 283041.5451 | 283041.5451 | 283041.5451 | 0
8101 | Substations | Replacement of Magrini MAG38MGE-0 CBs | PS Network Asset Replacement | Input_Prog_Future | 0 | 2014 | 0 | 0 | 0 | 0 | 0 | 0 | 536512.9545 | 670641.1931 | 268256.4773 | 0 | 536512.9545 | 670641.1931 | 268256.4773 | 0
4918 | Substations | Removal of PCB from In Service Equipment | PS Network Asset Replacement | Input_Prog_Future | 0 | 2014 | 0 | 0 | 0 | 0 | 0 | 101357.0855 | 105557.2 | 519385.6566 | 0 | 101357.0855 | 105557.2 | 519385.6566 | 0 | 0
8253 | Substations | Management of CTs with PCB Contamination | PS Network Asset Replacement | Input_Prog_Future | 0 | 2014 | 0 | 0 | 0 | 0 | 0 | 144540.9119 | 385864.5881 | 107380 | 0 | 144540.9119 | 385864.5881 | 107380 | 0 | 0
4916 | Substations | Replace Isolator and Earth Switch - 66kV and Below as Required | PS Network Asset Replacement | Input_Prog_Future | 0 | 2014 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 92142.863 | 92142.863 | 0 | 0 | 92142.863 | 92142.863 | 0
5066 | Substations | 110V Battery Chargers | PS Network Asset Replacement | Input_Prog_Future | 0 | 2014 | 0 | 0 | 0 | 0 | 0 | 65692.4278 | 43794.9519 | 65692.4278 | 65692.4278 | 65692.4278 | 43794.9519 | 65692.4278 | 65692.4278 | 0
5068 | Substations | 50V Battery Chargers | PS Network Asset Replacement | Input_Prog_Future | 0 | 2014 | 0 | 0 | 0 | 0 | 0 | 58848.8408 | 19616.2803 | 19616.2803 | 0 | 58848.8408 | 19616.2803 | 19616.2803 | 0 | 0
8274 | Substations | Fault Throwing Switches | PS Network Asset Replacement | Input_Prog_Future | 0 | 2014 | 0 | 0 | 0 | 0 | 0 | 140000 | 0 | 0 | 0 | 140000 | 0 | 0 | 0 | 0
6370 | Cable Minor Projects | 42 Cable Tunnel Life Extension | PS Augmentation | Input_Proj_Commit | 2011 | 2013 | 31597.4977 | 34869.7448 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5657 | Capacitor Bank | Muswellbrook No.1 132kV Capacitor Bank Detuning | PS Augmentation | Input_Proj_Commit | 2010 | 2013 | -82.7577 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6234 | Capacitor Bank | Capacitor Banks | PS Augmentation | Input_Proj_Commit | 2010 | 2013 | 7.1035 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6192 | Capacitor Bank | Beryl 66kV Capacitor Bank | PS Augmentation | Input_Proj_Commit | 2011 | 2013 | 199.5183 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6211 | Capacitor Bank | Sydney North & East 330kV 2 x 200 MVAr Capacitor Banks | PS Augmentation | Input_Proj_Commit | 2011 | 2013 | 108288.6921 | 571017.6792 | -18389.1454 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6241 | Capacitor Bank | Sydney North & East 330kV 2 x 200 MVAr Capacitor Banks | PS Augmentation | Input_Proj_Commit | 2011 | 2013 | 0 | -505.6379 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6258 | Capacitor Bank | Regentville 330kV Capacitor Bank | PS Augmentation | Input_Proj_Commit | 2011 | 2013 | 0 | -208.1995 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6384 | Capacitor Bank | Sydney Area 200MVAr Capacitor Bank | PS Augmentation | Input_Proj_Commit | 2011 | 2013 | -0.2179 | -1627.4202 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6579 | Capacitor Bank | Beryl No.2 66kV Capacitor Bank | PS Augmentation | Input_Proj_Commit | 2011 | 2013 | 2001698.0764 | 1079755.7343 | 230908.4564 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6936 | Capacitor Bank | Capacitor Banks | PS Augmentation | Input_Proj_Commit | 2011 | 2013 | 0 | 9.6661 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7268 | Capacitor Bank | Regentville 132kV Capacitor Bank | PS Augmentation | Input_Proj_Commit | 2011 | 2013 | 0 | 3941.3595 | 3328.4663 | -7000.791 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7270 | Capacitor Bank | Sydney Area No.2 200MVAr Capacitor Bank | PS Augmentation | Input_Proj_Commit | 2011 | 2013 | 0 | 4874.5937 | -4502.044 | -267.6769 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7274 | Capacitor Bank | Tumut 132kV Capacitor Bank | PS Augmentation | Input_Proj_Commit | 2011 | 2013 | 0 | 31739.4901 | 88.0155 | 0 | -29528.8914 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7326 | Capacitor Bank | Beryl No.2 66kV Capacitor Bank | PS Augmentation | Input_Proj_Commit | 2011 | 2013 | 0 | 0 | 276.7912 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7828 | Capacitor Bank | Port Macquarie No.3 Capacitor Bank | PS Augmentation | Input_Proj_Commit | 2012 | 2013 | 0 | 0 | 2441.7986 | 2416.1537 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6239 | Capacitor Bank | Tamworth Capacitor Banks | PS Augmentation | Input_Proj_Commit | 2013 | 2013 | 1934.2587 | 0 | 0 | -1670.8402 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7269 | Capacitor Bank | Sydney South 200 MVAr Capacitor Bank | PS Augmentation | Input_Proj_Commit | 2014 | 2013 | 0 | 30797.6638 | 93601.9933 | 1312592.9954 | 3788168.6367 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6383 | Capacitor Bank | Canberra 132kV 120MVAr Capacitor Bank | PS Augmentation | Input_Proj_Commit | 2015 | 2013 | -6.5043 | -9819.4024 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -9825.9067 | 0 | 0 | 0 | 0
7265 | Capacitor Bank | Canberra 132kV 120MVAr Capacitor Bank | PS Augmentation | Input_Proj_Commit | 2015 | 2013 | 0 | 7144.3707 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7144.3707 | 0 | 0 | 0 | 0
7266 | Capacitor Bank | Canberra 132kV 120MVAr Capacitor Bank | PS Augmentation | Input_Proj_Commit | 2015 | 2013 | -5.7852 | 229.7542 | 0 | 93086.0675 | 2808718.4376 | 797334.4592 | 0 | 0 | 0 | 3699362.9332 | 0 | 0 | 0 | 0
7276 | Capacitor Bank | Yass 132kV 80MVAr Capacitor Bank | PS Augmentation | Input_Proj_Commit | 2015 | 2013 | -5.3167 | 4598.0507 | 1665.8536 | 84091.5784 | 2164830.2493 | 1222232.0176 | 0 | 0 | 0 | 3477412.4328 | 0 | 0 | 0 | 0
5893 | Capacity of Armidale to Coffs Harbour | Armidale 132kV Phase Shifting Transformer | PS Augmentation | Input_Proj_Commit | 2011 | 2013 | 14497.5928 | 7443.6701 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6719 | Capacity of Armidale to Coffs Harbour | Line 96C Armidale to Coffs Harbour Upgrade | PS Augmentation | Input_Proj_Commit | 2011 | 2013 | 344054.6643 | 4225882.0803 | 588012.1378 | 89308.2453 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5907 | Capacity of Coffs Harbour to Kempsey | Coffs Harbour to Kempsey Transmission Line Upgrade from 66kV to 132kV | PS Augmentation | Input_Proj_Commit | 2010 | 2013 | 2769592.13 | 269538.1637 | 41183.8158 | 35595.1999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3912 | Capacity of Kempsey to Port Macquarie | Kempsey to Port Macquarie 132kV Transmission Line | PS Augmentation | Input_Proj_Commit | 2012 | 2013 | 11613905.8445 | 11347589.6469 | 7304061.1442 | 286328.1447 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5553 | Capacity of Queensland to NSW Interconnector | Bulli Creek to Dumaresq Terminal Equipment Upgrade | PS Augmentation | Input_Proj_Commit | 2013 | 2013 | 170.8429 | 0 | 0 | -5020.8297 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6098 | Capacity of Queensland to NSW Interconnector | Armidale 330kV Static VAR Compensator | PS Augmentation | Input_Proj_Commit | 2013 | 2013 | 511.7879 | 3881.8527 | 24217.1632 | 12997.4688 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7674 | Capacity of Queensland to NSW Interconnector | Tamworth 330kV Switching Station | PS Augmentation | Input_Proj_Commit | 2013 | 2013 | 0 | 0 | 35498.5339 | -34559.9606 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7339 | Capacity of Queensland to NSW Interconnector | Reinforcement of NSW to Queensland Interconnection Capacity | PS Augmentation | Input_Proj_Commit | 2013 | 2013 | 0 | 0 | 700638.872 | 1063204.5226 | -1697123.0801 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5932 | Capacity of Snowy Lines | Snowy Assets Rehabilitation of 64, 65 and 66 Lines | PS Augmentation | Input_Proj_Commit | 2009 | 2013 | 15813.0974 | 46782.488 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5964 | Capacity of Tamworth to Armidale | 86 Line Tamworth to Armidale 330kV Transmission Line Uprating | PS Augmentation | Input_Proj_Commit | 2011 | 2013 | 631502.9259 | 2553400.426 | -164654.8341 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6925 | Capacity of Victoria to NSW Interconnector | Yass 132kV 80MVAr Capacitor Bank | PS Augmentation | Input_Proj_Commit | 2015 | 2013 | 0 | 0 | 0 | 41587.1195 | 0 | 0 | 0 | 0 | 0 | 41587.1195 | 0 | 0 | 0 | 0
6925 | Capacity of Victoria to NSW Interconnector | Yass 132kV 80MVAr Capacitor Bank | PS Augmentation | Input_Proj_Commit | 2015 | 2013 | 0 | 0 | 0 | 41587.1195 | 0 | 0 | 0 | 0 | 0 | 41587.1195 | 0 | 0 | 0 | 0
7407 | Capacity of Yass to Marulan | Yass to Bannaby and Marulan 330kV Line Uprating | PS Augmentation | Input_Proj_Commit | 2013 | 2013 | 0 | 0 | 15558.4511 | -7671.495 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6971 | Communications | Lismore Marshalling Kiosk Installation | PS Augmentation | Input_Proj_Commit | 2010 | 2013 | 22823.3228 | 380.2227 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6876 | Communications | Sydney West Protection/Communications Upgrade | PS Augmentation | Input_Proj_Commit | 2011 | 2013 | 100305.5958 | 462511.5986 | 30112.0315 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7064 | Communications | Tuggerah Provision of Fibre Marshalling Kiosk | PS Augmentation | Input_Proj_Commit | 2011 | 2013 | 0 | 2750.7232 | 867.5036 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7278 | Communications | Albury to Mulwala Tripping Scheme | PS Augmentation | Input_Proj_Commit | 2011 | 2013 | 0 | 70408.0374 | -68998.7647 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6973 | Communications | Murray Substation Station & Lower Tumut Switching Station OPGW & Protection Upgrade | PS Augmentation | Input_Proj_Commit | 2012 | 2013 | 584640.3006 | 267920.4628 | 506878.9528 | -707.116 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7530 | Communications | Vales Point DNSP Communications Upgrade | PS Augmentation | Input_Proj_Commit | 2012 | 2013 | 0 | 5223.436 | 85044.6834 | 673.2302 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7533 | Communications | Sydney East DNSP Communications Upgrade | PS Augmentation | Input_Proj_Commit | 2012 | 2013 | 0 | 0 | 333465.2256 | 3033.5435 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6875 | Communications | Regentville Protection/Communications Upgrade | PS Augmentation | Input_Proj_Commit | 2013 | 2013 | 125952.0377 | 141239.0667 | 140269.2056 | 40883.6863 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7028 | Communications | Armidale - Dumaresq OPGW - OLTE Upgrades | PS Augmentation | Input_Proj_Commit | 2013 | 2013 | 0 | 1871242.3726 | 2692139.8426 | 95194.7539 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P0001221 | Communications | Fibre Connections at Dapto for Endeavour Energy | PS Augmentation | Input_Proj_Commit | 2014 | 2013 | 0 | 0 | 0 | 0 | 104406.6153 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5645 | Control System | Armidale Static VAR Compensator Power Oscillation Damper | PS Augmentation | Input_Proj_Commit | 2009 | 2013 | 18055.976 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6992 | Control System | Real-Time Line Rating on Lines 8 and 16 | PS Augmentation | Input_Proj_Commit | 2011 | 2013 | 285.4682 | 84795.131 | 1315.605 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5606 | Control System | SCADA Operations Circuit Breakers Check Synchronism | PS Augmentation | Input_Proj_Commit | 2013 | 2013 | -13.8692 | 0 | 0 | -89562.1245 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5837 | Control System | SCADA Control For Loadshed of Tomago Aluminum | PS Augmentation | Input_Proj_Commit | 2013 | 2013 | 0 | -8475.5541 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6457 | Control System | SCADA Control For Loadshed of Tomago Aluminum | PS Augmentation | Input_Proj_Commit | 2013 | 2013 | 1070.6854 | 10628.3805 | 115678.9511 | 466042.0052 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7564 | Control System | Smart Grid Monitor Installation | PS Augmentation | Input_Proj_Commit | 2013 | 2013 | 0 | 0 | 49546.9415 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7846 | Control System | Current Transducer Installation at Bannaby & Bayswater | PS Augmentation | Input_Proj_Commit | 2013 | 2013 | 0 | 0 | 77115.1323 | 221870.9197 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7739 | Easements | Bannaby to Yass 500kV Transmission Line | PS Augmentation | Input_Proj_Commit | 2013 | 2013 | 2.7237 | 3257.148 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6030 | Fault Level Equipment Upgrade | Munmorah Substation Short Circuit Fault Level Upgrade | PS Augmentation | Input_Proj_Commit | 2010 | 2013 | 1715.5218 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6041 | Fault Level Equipment Upgrade | Sydney North Fault Level Upgrade | PS Augmentation | Input_Proj_Commit | 2011 | 2013 | 2131173.3178 | 1432879.8899 | 14070.427 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6231 | Fault Level Equipment Upgrade | Dapto Fault Level Upgrade | PS Augmentation | Input_Proj_Commit | 2011 | 2013 | 2285776.1096 | 142308.6051 | 0 | 8779.7307 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6699 | Fault Level Equipment Upgrade | Sydney South Fault Level Upgrade | PS Augmentation | Input_Proj_Commit | 2011 | 2013 | 33013.7258 | -32222.5843 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7538 | Fault Level Equipment Upgrade | Sydney South Fault Level Upgrade | PS Augmentation | Input_Proj_Commit | 2011 | 2013 | 0 | 31256.5554 | 0 | -29821.0012 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5840 | Reactor Installation | 41 Cable 330kV Shunt Reactor | PS Augmentation | Input_Proj_Commit | 2011 | 2013 | 9981062.9834 | -461464.7102 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6184 | Reactor Installation | 41 Cable 330kV Series Reactor | PS Augmentation | Input_Proj_Commit | 2011 | 2013 | 22.9338 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6906 | Reactor Installation | Yass 330kV Shunt Reactor | PS Augmentation | Input_Proj_Commit | 2011 | 2013 | 0 | 68429.1058 | 107518.138 | 104757.2956 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5915 | Reinforcement of Supply To The New England Area | Glen Innes to Inverell Transmission Line 132kV Line Bays | PS Augmentation | Input_Proj_Commit | 2012 | 2013 | 225675.4101 | 1942335.2808 | 524738.2964 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7472 | Reinforcement of the Victoria/NSW Interconnection | Uprating Lines 8, 16 & 18 Between Dapto and Marulan | PS Augmentation | Input_Proj_Commit | 2011 | 2013 | 0 | 0 | 27692.8985 | 152670.17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7473 | SCADA | Yanco SCADA | PS Augmentation | Input_Proj_Commit | 2012 | 2013 | -1.5907 | -78.3287 | 317786.5521 | 42929.4001 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5830 | SCADA | Provision of SCADA Facilities At Existing 132kV Substations | PS Augmentation | Input_Proj_Commit | 2013 | 2013 | -43.536 | 9283.7772 | 0 | -124341.0741 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5951 | SCADA | Provision of SCADA Facilities At Existing 132kV Substations | PS Augmentation | Input_Proj_Commit | 2013 | 2013 | 144.8695 | 0 | 0 | -6344.5848 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6375 | SCADA | 132kV and 66kV Operational Info To TransGrid & Nemmco | PS Augmentation | Input_Proj_Commit | 2013 | 2013 | -25.189 | 0 | -38298.5948 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6376 | SCADA | 132kV and 66kV Operational Info To TransGrid & Nemmco | PS Augmentation | Input_Proj_Commit | 2013 | 2013 | -21.9968 | 0 | -66898.211 | 32564.6797 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6437 | SCADA | 132kV and 66kV Operational Info To TransGrid & Nemmco | PS Augmentation | Input_Proj_Commit | 2013 | 2013 | -0.75175 | 0 | 0 | -3259.9489 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7292 | SCADA | Finley SCADA | PS Augmentation | Input_Proj_Commit | 2013 | 2013 | 1797.8655 | 145.8109 | 105543.8551 | 262116.1036 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7640 | SCADA | Inverell SCADA | PS Augmentation | Input_Proj_Commit | 2013 | 2013 | 0 | 0 | 812.9081 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7368 | Secondary System Renewal | Jindera No.1 and No.2 Transformer Bay Ratings | PS Augmentation | Input_Proj_Commit | 2014 | 2013 | 0 | 0 | 0 | 1552.4735 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6158 | Substation Minor Projects | Switchbay at Finley | PS Augmentation | Input_Proj_Commit | 2010 | 2013 | 272.1219 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5378 | Substation Minor Projects | Armidale 330kV Substation Connection of 89 Lismore Line | PS Augmentation | Input_Proj_Commit | 2011 | 2013 | 0 | 33161.146 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6374 | Substation Minor Projects | Haymarket Substation Ausgrid 132kV Cables | PS Augmentation | Input_Proj_Commit | 2011 | 2013 | 2159779.3048 | 231120.9253 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6765 | Substation Minor Projects | Sydney South Feeder 916/917 Protection Replacement | PS Augmentation | Input_Proj_Commit | 2011 | 2013 | 368437.5593 | 139224.2566 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6821 | Substation Minor Projects | Wallerawang Auxiliary Power Supply Rearrangements | PS Augmentation | Input_Proj_Commit | 2011 | 2013 | 573431.4097 | 74920.2945 | 15185.6161 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6872 | Substation Minor Projects | Connection to Jesmond Substation | PS Augmentation | Input_Proj_Commit | 2011 | 2013 | 1975.801 | 45991.4385 | 0 | -45719.0171 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6223 | Substation Minor Projects | Vineyard Line Bays | PS Augmentation | Input_Proj_Commit | 2012 | 2013 | 0 | -3760.6591 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6720 | Substation Minor Projects | Manildra 132kV Swithbay | PS Augmentation | Input_Proj_Commit | 2012 | 2013 | -0.77354 | 0 | 0 | -1090.8464 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6816 | Substation Minor Projects | Port Macquarie 33kV Switchbays and Installation of Auto Reclose Facilities | PS Augmentation | Input_Proj_Commit | 2012 | 2013 | 780850.6064 | 1087218.4708 | 606967.5063 | 904453.5287 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6102 | Substation Minor Projects | Liddell 84 Line Connection - Additional Circuit Breaker Installation | PS Augmentation | Input_Proj_Commit | 2013 | 2013 | 4584.2688 | -13629.8065 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6274 | Substation Minor Projects | Newcastle Substation - Provision of 132kV Switchbay | PS Augmentation | Input_Proj_Commit | 2013 | 2013 | 31755.6372 | -33719.602 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6607 | Substation Minor Projects | Griffith 132kV Substation - 33kV Connection | PS Augmentation | Input_Proj_Commit | 2013 | 2013 | 849349.7512 | 1389659.549 | 273564.1187 | 67770.4373 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7307 | Substation Minor Projects | Newcastle Substation - Provision of 132kV Switchbay | PS Augmentation | Input_Proj_Commit | 2013 | 2013 | 0 | 55642.3588 | 2374.6667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7469 | Substation Minor Projects | Liddell 84 Line Connection - Additional Circuit Breaker Installation | PS Augmentation | Input_Proj_Commit | 2013 | 2013 | 0 | 15266.8928 | 519846.4146 | 3826800.9815 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7511 | Substation Minor Projects | Munmorah - Supply To Lake Munmorah Zone Substation | PS Augmentation | Input_Proj_Commit | 2013 | 2013 | 0 | 1635.268 | 134441.761 | 410330.047 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7512 | Substation Minor Projects | Vales Point - Supply To Lake Munmorah Zone Substation | PS Augmentation | Input_Proj_Commit | 2013 | 2013 | 0 | 0 | 85650.6103 | 403683.1894 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7521 | Substation Minor Projects | Newcastle 952 Feeder Connection to Rathmines | PS Augmentation | Input_Proj_Commit | 2013 | 2013 | 0 | 13396.2667 | 212606.8575 | 121901.1902 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7683 | Substation Minor Projects | Connection to Morvern Substation | PS Augmentation | Input_Proj_Commit | 2013 | 2013 | 0 | 0 | 0 | 179257.1642 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7825 | Substation Minor Projects | Connection of Charlestown Zone Substation | PS Augmentation | Input_Proj_Commit | 2013 | 2013 | 0 | 0 | 6347.555 | 94034.0866 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7862 | Substation Minor Projects | Sydney North Substation 257 & 258 132kV Feeder Augmentation | PS Augmentation | Input_Proj_Commit | 2013 | 2013 | 0 | 0 | 36907.8025 | 40144.4499 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6105 | Substation Minor Projects | Sydney West Substation 330kV Bus Coupling | PS Augmentation | Input_Proj_Commit | 2014 | 2013 | 7638.6213 | 0 | 0 | -9211.2867 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6107 | Substation Minor Projects | Sydney West Substation 20 Line Bus Coupling | PS Augmentation | Input_Proj_Commit | 2014 | 2013 | 9.7183 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8039 | Substation Minor Projects | Jindera No.1 and No.2 Transformer Bay Ratings | PS Augmentation | Input_Proj_Commit | 2014 | 2013 | 0 | 0 | 0 | 2955.8803 | 65669.1406 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6262 | Substation Renewal | Orange North Substation | PS Augmentation | Input_Proj_Commit | 2010 | 2013 | -8.4435 | 0 | -28849.3337 | -8148.7968 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5963 | Substation Renewal | Murray Switching Station | PS Augmentation | Input_Proj_Commit | 2012 | 2013 | 2405335.8372 | 5565634.5651 | 2621140.1799 | 92283.7164 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6709 | Substation Renewal | Orange North Substation | PS Augmentation | Input_Proj_Commit | 2013 | 2013 | 2471997.3283 | 7553402.7327 | 17117458.6777 | 4833114.5255 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5715 | Supply to ACT | Williamsdale 330/132kV Substation | PS Augmentation | Input_Proj_Commit | 2012 | 2013 | 13742330.9782 | 17119219.2736 | 18469414.0206 | 8093780.5965 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7401 | Supply to Darlington Point | Darling Point to Colleambally 132kV Line | PS Augmentation | Input_Proj_Commit | 2011 | 2013 | 2615.7129 | -242.451 | 0 | -12786.8193 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6969 | Supply to Gunnedah, Narrabri and Moree | Installation of Phase Shifting Transformer on 969 Line | PS Augmentation | Input_Proj_Commit | 2018 | 2013 | 93036.5186 | 91246.1026 | 24370.3097 | 455279.4929 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 663932.4237 | 0
5714 | Supply to Macarthur | Macarthur 330/132kV Substation | PS Augmentation | Input_Proj_Commit | 2010 | 2013 | 1748947.5762 | 538340.4994 | -1171.0558 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7400 | Supply to South Coast | Tomerong Substation Establishment | PS Augmentation | Input_Proj_Commit | 2014 | 2013 | 77174.3832 | 40944.2049 | 291434.4043 | 348278.1607 | -858405.9672 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6910 | Supply to Sydney Inner Metropolitan Area and CBD | Beaconsfield West To Haymarket 330kV Cable | PS Augmentation | Input_Proj_Commit | 2014 | 2013 | 8063.8057 | 92656.4228 | 806296.6386 | 14890136.7269 | 882581.9277 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6704 | Supply to the ACT | Wallaroo 330kV Switching Station | PS Augmentation | Input_Proj_Commit | 2018 | 2013 | 475620.8222 | 423018.6861 | 228413.1879 | 9513.1538 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1136565.85 | 0
6346 | Supply to the Cabonne Area | Manildra to Parkes 132kV Transmission Line | PS Augmentation | Input_Proj_Commit | 2012 | 2013 | 3645132.251 | 21512973.2234 | 17756636.0701 | 420403.5225 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7147 | Supply to the Cabonne Area | Manildra to Parkes 132kV Transmission Line | PS Augmentation | Input_Proj_Commit | 2012 | 2013 | 0 | 64392.1484 | 1746542.2934 | -14735.8978 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8155 | Supply to the Cabonne Area | Manildra to Parkes 132kV Transmission Line | PS Augmentation | Input_Proj_Commit | 2012 | 2013 | 0 | 0 | 0 | 1941669.3431 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6662 | Supply to the Lower Mid North Coast | Tomago-Tarro-Stroud 330/132kV Transmission Line | PS Augmentation | Input_Proj_Commit | 2014 | 2013 | 1511529.1962 | 2494391.5079 | 8906471.7643 | 48905408.4984 | 29590886.7947 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6967 | Supply to the Mid North Coast | Stroud-Taree 330kV Transmission Line Construction | PS Augmentation | Input_Proj_Commit | 2014 | 2013 | 6603.3008 | 266153.8247 | 1179811.2435 | -1397008.3346 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5880 | Supply to the New England Area | Glen Innes to Inverell 132kV Transmission Line | PS Augmentation | Input_Proj_Commit | 2012 | 2013 | 8090217.1691 | 9348317.0107 | 7833226.8287 | 792409.3309 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7513 | Supply to Tomago | Tomago 330/132kV Substation - Establishment of 132kV Busbar and Connections | PS Augmentation | Input_Proj_Commit | 2014 | 2013 | 0 | 913933.0115 | 8663898.6958 | 5867742.0284 | 44892.9994 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7745 | Supply to Tomago | Sydney South - Tail Ending 91F and 91J | PS Augmentation | Input_Proj_Commit | 2014 | 2013 | 0 | 0 | 16377.42 | 91454.1756 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5968 | Supply to Tomago Area | Establishment of 132kV Busbar at Tomago 330kV Substation | PS Augmentation | Input_Proj_Commit | 2011 | 2013 | 22901843.3212 | 14730587.4192 | 760164.3448 | 1395474.2852 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6036 | Supply to Wagga Wagga | Wagga North 132/66kV Substation Establishment | PS Augmentation | Input_Proj_Commit | 2011 | 2013 | 2836978.6005 | 572594.206 | 4876.167 | -56912.4159 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4419 | Supply to Wellington | Wollar to Wellington 330kV Transmission Line | PS Augmentation | Input_Proj_Commit | 2010 | 2013 | 15396068.3943 | 15439639.8884 | 2918964.021 | 276664.7777 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4429 | Supply to Wellington | Wollar 330kV Switching Station | PS Augmentation | Input_Proj_Commit | 2010 | 2013 | 30505266.9809 | 138048.9224 | 386.8679 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7644 | SVC Control System Replacement | Armidale SVC Transformer | PS Augmentation | Input_Proj_Commit | 2013 | 2013 | 0 | 0 | 0 | 75733.5829 | -73642.286 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5670 | Transformer Additions | Parkes No.2 Transformer | PS Augmentation | Input_Proj_Commit | 2009 | 2013 | 3578.9746 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5816 | Transformer Additions | Tuggerah No.2 Transformer | PS Augmentation | Input_Proj_Commit | 2009 | 2013 | 161007.0537 | 42550.2086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5852 | Transformer Additions | Marulan No.2 Transformer | PS Augmentation | Input_Proj_Commit | 2009 | 2013 | -4820.8516 | 0 | 0 | 56809.3181 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6320 | Transformer Additions | Koolkhan No.3 Transformer | PS Augmentation | Input_Proj_Commit | 2010 | 2013 | 5418979.5326 | 419528.6789 | 152438.7863 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6668 | Transformer Additions | Sydney North No.5 Transformer | PS Augmentation | Input_Proj_Commit | 2011 | 2013 | 8667242.3705 | 6302126.0079 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6696 | Transformer Additions | Waratah West No.2 Transformer & Bus Section | PS Augmentation | Input_Proj_Commit | 2011 | 2013 | 10806788.8002 | 12602578.0301 | 99372.1331 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6727 | Transformer Additions | Vineyard No.3 Transformer | PS Augmentation | Input_Proj_Commit | 2012 | 2013 | 9309630.4127 | 5466916.1769 | 4369189.6573 | 86847.8981 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6907 | Transformer Additions | Munmorah No.2 Transformer | PS Augmentation | Input_Proj_Commit | 2013 | 2013 | 0 | 2445.32 | 0 | -2333.0018 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7456 | Transformer Additions | Eraring No.2 Transformer | PS Augmentation | Input_Proj_Commit | 2013 | 2013 | 0 | 41990.5616 | 3688.0833 | -43720.8854 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7684 | Transformer Additions | Coffs Harbour No. 2 330/132kV Transformer Installation | PS Augmentation | Input_Proj_Commit | 2014 | 2013 | 0 | 0 | 0 | 109182.7308 | -106167.7736 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7338 | Transformer Replacement | Marulan No.4 Transformer | PS Augmentation | Input_Proj_Commit | 2009 | 2013 | 0 | 0 | 1969.979 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4563 | Transformer Replacement | Wellington 330kV Transformer Replacement & Shunt Reactor | PS Augmentation | Input_Proj_Commit | 2010 | 2013 | 3318257.896 | 69940.224 | 3867.9596 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5691 | Transformer Replacement | Finley No.1 & No.2 Transformer Replacement | PS Augmentation | Input_Proj_Commit | 2010 | 2013 | 1073369.7248 | 6868.0191 | 23004.038 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6363 | Transformer Replacement | Sydney South No.3 & No.4 Transformer Replacements | PS Augmentation | Input_Proj_Commit | 2011 | 2013 | 2509610.5649 | 1304977.5724 | 686994.3185 | -45291.5903 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6446 | Transformer Replacement | Coffs Harbour 132/66kV Transformer Replacements | PS Augmentation | Input_Proj_Commit | 2011 | 2013 | 3798268.415 | 412048.0244 | 547.6529 | -108773.5455 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6458 | Transformer Replacement | Cowra 132/66kV Transformer Replacement | PS Augmentation | Input_Proj_Commit | 2011 | 2013 | 6702061.1224 | 311565.7948 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7093 | Transformer Replacement | Kempsey 66/33kV Transformer Replacement | PS Augmentation | Input_Proj_Commit | 2013 | 2013 | 0 | 51054.8994 | 33461.8191 | 47771.1529 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7633 | Transformer Replacement | Kempsey 66kV Bus and No.2 Transformer Replacement | PS Augmentation | Input_Proj_Commit | 2013 | 2013 | 0 | 0 | 0 | 342.398 | -332.9431 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7409 | Transformer Replacement | Koolkhan - 967 Line Deviation Works | PS Augmentation | Input_Proj_Commit | 2014 | 2013 | 0 | 90627.9908 | -88813.946 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5881 | Transmission Line Rearrangement | 24 Line Vales Point to Newcastle 330kV Turn In | PS Augmentation | Input_Proj_Commit | 2009 | 2013 | 52501.3897 | 6103.9264 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7573 | Transmission Line Rearrangement | Koolkhan - 967 Line Deviation Works | PS Augmentation | Input_Proj_Commit | 2014 | 2013 | 0 | 0 | 0 | -143305.88 | 715360.0415 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7399 | Transmission Line Renewal | 86 Line Tamworth to Armidale Condition | PS Augmentation | Input_Proj_Commit | 2011 | 2013 | 0 | 314.091 | -307.7832 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5940 | Transmission Line Renewal | Tamworth to Gunnedah 66kV Transmission Line Refurbishment | PS Augmentation | Input_Proj_Commit | 2012 | 2013 | 7377986.2705 | 853622.1104 | 270509.63 | 126621.1167 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7705 | Transmission Line Renewal | 964 Line Port Macquarie to Taree Condition | PS Augmentation | Input_Proj_Commit | 2012 | 2013 | 4709.2115 | 1905.8028 | -88832.412 | 30786.44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5527 | Western 500kV Upgrade | Bayswater 500/330kV Switchyard Development | PS Augmentation | Input_Proj_Commit | 2009 | 2013 | 714169.9729 | 24858.0617 | 17009.9621 | 77406.4522 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5535 | Western 500kV Upgrade | Mt Piper 500/330kV Switchyard Development | PS Augmentation | Input_Proj_Commit | 2009 | 2013 | 2947017.7544 | 737832.1754 | 175685.9662 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5965 | Western 500kV Upgrade | Wallerawang 330kV Fault Rating Upgrade | PS Augmentation | Input_Proj_Commit | 2009 | 2013 | 6107.6155 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5967 | Western 500kV Upgrade | Uprating of Lines 330kV 8 and 16 Lines | PS Augmentation | Input_Proj_Commit | 2009 | 2013 | 2309.9476 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6229 | Western 500kV Upgrade | Bayswater-Liddell Reduct In Fault Clearing Times | PS Augmentation | Input_Proj_Commit | 2009 | 2013 | 182981.3696 | 5421.4588 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5864 | Western 500kV Upgrade | Bannaby 500/330kV Substation Development | PS Augmentation | Input_Proj_Commit | 2011 | 2013 | 27996485.093 | 6217699.1259 | 282877.0944 | 51555.0015 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6648 | Western Sydney Supply Project | Holroyd 330kV Substation Establishment | PS Augmentation | Input_Proj_Commit | 2014 | 2013 | 1274491.6693 | 5582664.236 | 19908570.8114 | 31403133.4998 | 21865373.0414 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6664 | Western Sydney Supply Project | Sydney West to Holroyd 330kV Transmission Line | PS Augmentation | Input_Proj_Commit | 2014 | 2013 | 3530403.2349 | 4683671.0637 | 1860787.5179 | 29227099.9046 | 42305662.3368 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6988 | Western Sydney Supply Project | Sydney West 330kV Connections For Holroyd Substation | PS Augmentation | Input_Proj_Commit | 2014 | 2013 | 31306.2444 | 291496.7458 | 3060232.3574 | 11947525.5187 | 1305324.6634 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6650 | Western Sydney Supply Project | Holroyd - Rookwood 330kV Cable | PS Augmentation | Input_Proj_Commit | 2015 | 2013 | 1226964.3462 | 2146640.6506 | 11233417.5893 | 44967630.0905 | 90225575.2573 | 1631435.5469 | 0 | 0 | 0 | 151431663.4808 | 0 | 0 | 0 | 149800227.934
6651 | Western Sydney Supply Project | Rookwood Road 330/132kV Substation | PS Augmentation | Input_Proj_Commit | 2015 | 2013 | 5045956.2228 | 5969660.6952 | 16324279.2188 | 36242411.5445 | 36667938.607 | 11714572.7726 | 0 | 0 | 0 | 111964819.0609 | 0 | 0 | 0 | 100250246.2883
6344 | Protection Change | Sydney West to West Wetherill Park Substation 93M Feeder Protection Upgrade | PS Connections | Input_Proj_Commit | 2009 | 2013 | 39.2107 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P0001491 | Protection Change | Protection Changes on Macarthur Lines | PS Connections | Input_Proj_Commit | 2014 | 2013 | 0 | 0 | 0 | 0 | 102929.6772 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P0001497 | Protection Change | Taree Distance Relay Replacement for Essential Energy | PS Connections | Input_Proj_Commit | 2014 | 2013 | 0 | 0 | 0 | 0 | 145734.0273 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6053 | Substation Minor Projects | Provision of Switchbays at Taree Substation | PS Connections | Input_Proj_Commit | 2009 | 2013 | 1553.7435 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6287 | Substation Minor Projects | Connection of Morisset Zone Substation | PS Connections | Input_Proj_Commit | 2009 | 2013 | -7.6482 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6518 | Substation Minor Projects | Argenton 132kV Substation Connection | PS Connections | Input_Proj_Commit | 2009 | 2013 | 12509.0992 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6618 | Substation Minor Projects | Connection of Kingsford Substation at Beaconsfield West | PS Connections | Input_Proj_Commit | 2009 | 2013 | 12164.646 | 0 | 0 | 4505.9899 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6638 | Substation Minor Projects | Mayfield West & Kooragang Zone Substation Connection | PS Connections | Input_Proj_Commit | 2009 | 2013 | 172560.1037 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6640 | Substation Minor Projects | Narrabri Substation 66kV Switchbay Renames | PS Connections | Input_Proj_Commit | 2009 | 2013 | -20.1665 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6697 | Substation Minor Projects | Beryl 66kV Bay to Dunedoo | PS Connections | Input_Proj_Commit | 2010 | 2013 | 4929.659 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6345 | Substation Minor Projects | Sydney North 132kV Switchbays For Galston | PS Connections | Input_Proj_Commit | 2011 | 2013 | 697547.6786 | 86438.5445 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6724 | Substation Minor Projects | Tenterfield 22kV Switchbay | PS Connections | Input_Proj_Commit | 2011 | 2013 | 20721.5113 | 555.8295 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6856 | Substation Minor Projects | Connection to Kurri Zone Substation at Newcastle | PS Connections | Input_Proj_Commit | 2011 | 2013 | 81795.8363 | 108736.643 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7134 | Substation Minor Projects | Connection of Jesmond Zone Substation | PS Connections | Input_Proj_Commit | 2011 | 2013 | 0 | 134349.0037 | 2453.3241 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7283 | Substation Minor Projects | Tenterfield 22kV Switchbay | PS Connections | Input_Proj_Commit | 2011 | 2013 | 0 | 1587.6072 | -1555.8499 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7285 | Substation Minor Projects | Cooma 132kV Installation of New Line Bay | PS Connections | Input_Proj_Commit | 2013 | 2013 | 26342.4517 | 602921.9722 | 1032484.9507 | 11299.8751 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7422 | Substation Minor Projects | Hawks Nest 132/66kV Substation Line Connection | PS Connections | Input_Proj_Commit | 2013 | 2013 | 51405.9729 | 43141.8208 | 1058691.5802 | 908324.1917 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7565 | Substation Minor Projects | Uprate Broken Hill 52 & 62 22kV Line Switchbays | PS Connections | Input_Proj_Commit | 2014 | 2013 | 0 | 0 | 4159.7049 | 69369.2044 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7668 | Substation Minor Projects | Wellington Substation 132kV Switchbay and Double Circuit (Strung On One Side) To Mitchell Highway | PS Connections | Input_Proj_Commit | 2014 | 2013 | 0 | 2.9562 | 0 | 603864.8096 | 1941381.395 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7826 | Substation Minor Projects | Connection to Broadmeadow Zone Substation at Waratah West | PS Connections | Input_Proj_Commit | 2014 | 2013 | 0 | 0 | 3699.4734 | 172769.1535 | 76960.2597 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8178 | Substation Minor Projects | Connection to Herons Creek Substation | PS Connections | Input_Proj_Commit | 2014 | 2013 | 678.5562 | 65.9403 | -15382.9995 | 23667.7592 | 244855.9957 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P0000899 | Substation Minor Projects | Connection of Abbotsbury Zone Substation at Sydney West | PS Connections | Input_Proj_Commit | 2014 | 2013 | 0 | 0 | 0 | 0 | 435392.5781 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P0000909 | Substation Minor Projects | Reduce AVR Settings at Vineyard Substation | PS Connections | Input_Proj_Commit | 2014 | 2013 | 0 | 0 | 0 | 4092.1884 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6157 | Substation Minor Projects | Supply to Gulgong West | PS Connections | Input_Proj_Commit | 2015 | 2013 | -13.0085 | 0 | 0 | -23861.0905 | 0 | 0 | 0 | 0 | 0 | -23874.099 | 0 | 0 | 0 | 0
6222 | Substation Minor Projects | Sydney West 132kV Line Bays | PS Connections | Input_Proj_Commit | 2015 | 2013 | 0 | -4962.9926 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -4962.9926 | 0 | 0 | 0 | 0
6986 | Substation Minor Projects | Supply to Belmore Park Zone Substation | PS Connections | Input_Proj_Commit | 2015 | 2013 | 1125.0836 | 36350.0142 | 366487.5301 | 640710.9305 | 397873.5542 | 22897.2442 | 0 | 0 | 0 | 1465444.3569 | 0 | 0 | 0 | 0
7126 | Substation Minor Projects | Sydney West 132kV Line Bays | PS Connections | Input_Proj_Commit | 2015 | 2013 | 0 | 35849.236 | 3513.9907 | 0 | 0 | 0 | 0 | 0 | 0 | 39363.2267 | 0 | 0 | 0 | 0
7311 | Substation Minor Projects | Sydney West 132kV Line Bays | PS Connections | Input_Proj_Commit | 2015 | 2013 | 0 | 4967.9692 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4967.9692 | 0 | 0 | 0 | 0
7313 | Substation Minor Projects | Tamworth 66kV Line Bay | PS Connections | Input_Proj_Commit | 2015 | 2013 | 0 | 4061.1388 | 16660.766 | 21203.922 | -40158.3674 | 0 | 0 | 0 | 0 | 1767.4594 | 0 | 0 | 0 | 0
7661 | Substation Minor Projects | Supply to Temora | PS Connections | Input_Proj_Commit | 2015 | 2013 | 0 | 0 | 0 | 32863.0568 | 0 | 0 | 0 | 0 | 0 | 32863.0568 | 0 | 0 | 0 | 0
8092 | Substation Minor Projects | Supply to Parkes Town | PS Connections | Input_Proj_Commit | 2015 | 2013 | 0 | 0 | 0 | 1683.2785 | 1216.6289 | 257324.2188 | 0 | 0 | 0 | 260224.1262 | 0 | 0 | 0 | 0
8095 | Substation Minor Projects | Supply to Googong | PS Connections | Input_Proj_Commit | 2015 | 2013 | 0 | 0 | 0 | 977.7249 | 0 | 257324.2188 | 0 | 0 | 0 | 258301.9437 | 0 | 0 | 0 | 0
6176 | Substation Minor Projects | Supply to Molong | PS Connections | Input_Proj_Commit | 2016 | 2013 | 0 | -6697.8781 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -6697.8781 | 0 | 0 | 0
7532 | Substation Minor Projects | Connection of Gwawley Bay | PS Connections | Input_Proj_Commit | 2016 | 2013 | 0 | 0 | -205.5639 | 20685.4704 | 0 | 0 | 0 | 0 | 0 | 0 | 20479.9064 | 0 | 0 | 0
7094 | Substation Minor Projects | Supply to Marsden Park | PS Connections | Input_Proj_Commit | 2016 | 2013 | 8969.1719 | 3764.4341 | -3688.9899 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9044.616 | 0 | 0 | 0
8093 | Substation Minor Projects | Supply to Molong | PS Connections | Input_Proj_Commit | 2016 | 2013 | 0 | 0 | 0 | 10883.598 | 0 | 0 | 0 | 0 | 0 | 0 | 10883.598 | 0 | 0 | 0
6964 | Substation Minor Projects | Supply to Nabiac | PS Connections | Input_Proj_Commit | 2017 | 2013 | 6309.9447 | 59600.6898 | 124943.4693 | 192625.3265 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 383479.4304 | 0 | 0
P0002435 | Substation Minor Projects | Supply to Gloucester | PS Connections | Input_Proj_Commit | 2017 | 2013 | 0 | 0 | 0 | 0 | 102929.6875 | 473476.5625 | 0 | 0 | 0 | 0 | 0 | 576406.25 | 0 | 0
6174 | Substation Minor Projects | Supply to Googong | PS Connections | Input_Proj_Commit | 2018 | 2013 | 29746.0075 | -29345.9354 | -2752.1765 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -2352.1045 | 0
7320 | Substation Minor Projects | Supply to Googong | PS Connections | Input_Proj_Commit | 2018 | 2013 | 0 | 33930.8427 | 32400.9649 | -63916.7679 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2415.0398 | 0
7392 | Transformer Additions | Macarthur 330/132kV No.2 Transformer Installation | PS Connections | Input_Proj_Commit | 2014 | 2013 | 0 | 1850.2943 | -1813.2581 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
890 | Easements | Koolkhan to Coffs Harbour 132kV Transmission Line Easements | PS Easements | Input_Proj_Commit | 2009 | 2013 | 29907.8622 | 12545.2212 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2007 | Easements | Coffs Harbour to Kempsey 132kV Transmission Line Easements | PS Easements | Input_Proj_Commit | 2009 | 2013 | 25055.3936 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3133 | Easements | Cable Easements | PS Easements | Input_Proj_Commit | 2009 | 2013 | 14163.152 | 1045.1019 | 2104.2219 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3954 | Easements | Coffs Harbour 132kV Transmission Line Upgrade Easements | PS Easements | Input_Proj_Commit | 2009 | 2013 | 171.3223 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3955 | Easements | Darlington Point to Buronga Strategic Easement Acquisition | PS Easements | Input_Proj_Commit | 2009 | 2013 | 42312.6209 | 1328.2166 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4240 | Easements | Miscellaneous State Forests Easements | PS Easements | Input_Proj_Commit | 2009 | 2013 | -0.076264 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4254 | Easements | Ivanhoe Coal | PS Easements | Input_Proj_Commit | 2009 | 2013 | -92579.3468 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4300 | Easements | Miscellaneous Statewide NPWS Easements | PS Easements | Input_Proj_Commit | 2009 | 2013 | 31218.1264 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4400 | Easements | Miscellaneous Sydney Catchment Authority Easements | PS Easements | Input_Proj_Commit | 2009 | 2013 | 339.5505 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
905 | Easements | Miscellaneous Easements | PS Easements | Input_Proj_Commit | 2010 | 2013 | 4782114.3222 | 37895.8625 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6961 | Easements | Bannaby to South Creek Lines 500kV Easement Acquisitions | PS Easements | Input_Proj_Commit | 2013 | 2013 | 804.8498 | 1371084.5722 | -1324113.5289 | 526399.24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6673 | Easements | Dumaresq to Lismore 330kV Strategic Easement Acquisition | PS Easements | Input_Proj_Commit | 2014 | 2013 | 3685694.4755 | 3651041.2471 | 3770822.9893 | 3360996.5009 | 584823.8398 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7460 | Easements | Kemps Creek to Liverpool 330kV Easement Acquisition | PS Easements | Input_Proj_Commit | 2014 | 2013 | 89825.5846 | 130994.6945 | 7282618.0415 | 1248931.4052 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7790 | Easements | Strategic Easement for Sydney West to Holroyd Second 330kV Line | PS Easements | Input_Proj_Commit | 2015 | 2013 | 0 | 0 | 26800.6139 | 0 | -25371.488 | 0 | 0 | 0 | 0 | 1429.1259 | 0 | 0 | 0 | 0
6923 | Powering Sydney's Future | Rookwood 330kV Substation - Cable Bays For Beaconsfield West | PS Easements | Input_Proj_Commit | 2017 | 2013 | 0 | 1601.9948 | -1570.012 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31.9828 | 0 | 0
7562 | Powering Sydney's Future | Haymarket Additional 330 kV Switchbays and Beaconsfield West Bay | PS Easements | Input_Proj_Commit | 2017 | 2013 | 0 | 0 | 7058.025 | -6871.4063 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 186.6187 | 0 | 0
4759 | Property | Marulan Substation Outstanding Land Acquisition | PS Easements | Input_Proj_Commit | 2009 | 2013 | 441204.6505 | 244.3544 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5827 | Property | Miscellaneous Substation Site Rights Acquisition | PS Easements | Input_Proj_Commit | 2009 | 2013 | 482.4044 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7396 | Property | Richmond Vale 500kV Strategic Property Acquisition | PS Easements | Input_Proj_Commit | 2013 | 2013 | 2481.0302 | 1680.4723 | -1300.8177 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7457 | Property | South Creek 500/330kV Substation Strategic Site Acquisition | PS Easements | Input_Proj_Commit | 2013 | 2013 | 941326.9804 | 12738702.7213 | 35739.3311 | 76267.1816 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5994 | Property | Lismore Substations 330kV Augmentation | PS Easements | Input_Proj_Commit | 2014 | 2013 | -0.02179 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6751 | Property | Tenterfield Substation | PS Easements | Input_Proj_Commit | 2014 | 2013 | 48400.6038 | 10335.1956 | -64911.3083 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6939 | Property | Tenterfield Substation | PS Easements | Input_Proj_Commit | 2014 | 2013 | 0 | 1710.7574 | 0 | -1632.1658 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6911 | Property | Strategic Property Acquisition at Beryl | PS Easements | Input_Proj_Commit | 2015 | 2013 | 11776.646 | 161751.2905 | -169777.9571 | 206550.7468 | 51464.8438 | 720507.8125 | 0 | 0 | 0 | 982273.3824 | 0 | 0 | 0 | 0
7548 | Property | Property Acquisition at Sydney West | PS Easements | Input_Proj_Commit | 2015 | 2013 | 0 | 0 | 144599.7935 | 12428434.7138 | 257324.2188 | 0 | 0 | 0 | 0 | 12830358.726 | 0 | 0 | 0 | 0
6115 | Property | Strategic Property Acquisition at Surry Hills | PS Easements | Input_Proj_Commit | 2016 | 2013 | 87486.7873 | -108477.5607 | 0 | -5439.7446 | 0 | 0 | 0 | 0 | 0 | 0 | -26430.518 | 0 | 0 | 0
6276 | Property | Strategic Property Acquisition at Surry Hills | PS Easements | Input_Proj_Commit | 2016 | 2013 | -0.22879 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -0.22879 | 0 | 0 | 0
6966 | Property | Strategic Property Acquisition at Maraylya | PS Easements | Input_Proj_Commit | 2016 | 2013 | 28705.0543 | 184749.5194 | 80099.4567 | 98093.2719 | 0 | 0 | 0 | 0 | 0 | 0 | 391647.3023 | 0 | 0 | 0
7672 | Property | Property Extension at Richmond Vale | PS Easements | Input_Proj_Commit | 2016 | 2013 | 0 | 0 | 12743.8592 | -12406.8933 | 0 | 0 | 0 | 0 | 0 | 0 | 336.9659 | 0 | 0 | 0
P0002472 | Property | Strategic Property Acquisition at Surry Hills | PS Easements | Input_Proj_Commit | 2016 | 2013 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8252 | Property | Strategic Property Adjoining Armidale 330kV Switchyard | PS Easements | Input_Proj_Commit | 2017 | 2013 | 0 | 0 | 0 | 0 | 1055029.2969 | 0 | 0 | 0 | 0 | 0 | 0 | 1055029.2969 | 0 | 0
P0002217 | Property | Strategic Property Acquisition in Sydney | PS Easements | Input_Proj_Commit | 2017 | 2013 | 0 | 14836.2659 | 225226.4884 | -208134.7218 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31928.0324 | 0 | 0
7300 | Substation Minor Projects | Connection to Lismore Substation | PS Easements | Input_Proj_Commit | 2014 | 2013 | 0 | 1.3718 | -997.8907 | -333.9773 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7020 | Cable Minor Projects | Sydney Park Groundwater Treatment Plant | PS Replacement | Input_Proj_Commit | 2011 | 2013 | 0 | 1952923.7738 | 99028.9812 | 52506.0135 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5120 | Cable Minor Projects | Tunnel Defects and Omissions Works | PS Replacement | Input_Proj_Commit | 2012 | 2013 | 1114299.6849 | 1320088.9031 | 1677808.2942 | 1747317.4982 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7480 | Cable Minor Projects | Cable 42 Accessories | PS Replacement | Input_Proj_Commit | 2014 | 2013 | 0 | 11455.1702 | 550255.7354 | 543340.8348 | 2728366.799 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7916 | Cable Minor Projects | 42 Cable Monitoring System Replacement | PS Replacement | Input_Proj_Commit | 2016 | 2013 | 0 | 0 | 0 | 0 | 0 | 216152.3438 | 54038.0859 | 0 | 0 | 0 | 270190.4297 | 0 | 0 | 0
8223 | Cable Minor Projects | 42 Cable Tunnel Accessories Replacement | PS Replacement | Input_Proj_Commit | 2018 | 2013 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 360253.9062 | 360253.9062 | 0 | 0 | 0 | 720507.8125 | 0
7641 | Capacitor Bank | Kempsey No.1 Capacitor Replacement | PS Replacement | Input_Proj_Commit | 2009 | 2013 | 0 | 0 | 7335.9625 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5470 | Capacitor Bank | Dapto Substation 132kV Capacitor Banks Replacement | PS Replacement | Input_Proj_Commit | 2011 | 2013 | 1919.7576 | 7163.2138 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6197 | Capacitor Bank | Wellington No.2 132kV Capacitor | PS Replacement | Input_Proj_Commit | 2011 | 2013 | 37961.7753 | 2908.093 | -41202.0108 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6147 | Capacitor Bank | Griffith No.1 & No.2 33kV Capacitor Banks | PS Replacement | Input_Proj_Commit | 2013 | 2013 | -26382.2508 | -846.4304 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6201 | Capacitor Bank | Sydney West No.1 Capacitor Bank | PS Replacement | Input_Proj_Commit | 2013 | 2013 | 4115.2434 | -6477.2158 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6858 | Capacitor Bank | Griffith No.1 & No.2 33kV Capacitor Banks | PS Replacement | Input_Proj_Commit | 2013 | 2013 | 699267.9288 | 347918.4781 | 1098962.6862 | 738608.345 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7273 | Capacitor Bank | Sydney West No.1 Capacitor Bank | PS Replacement | Input_Proj_Commit | 2013 | 2013 | 0 | 34898.4561 | 44567.0546 | 2284347.5629 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6193 | Capacitor Bank | Coffs Harbour No.1 Capacitor | PS Replacement | Input_Proj_Commit | 2014 | 2013 | 13665.2878 | -38308.2312 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7026 | Capacitor Bank | Coffs Harbour No.3 Capacitor | PS Replacement | Input_Proj_Commit | 2014 | 2013 | 0 | 250673.9685 | 426036.0437 | 1548908.4261 | 444983.5664 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7474 | Capacitor Bank | Canberra No.1 132kV 80MVAr Capacitor | PS Replacement | Input_Proj_Commit | 2015 | 2013 | 0 | 11125.724 | 5988.9383 | 105034.1643 | 1834000.2764 | 1868466.6116 | 0 | 0 | 0 | 3824615.7146 | 0 | 0 | 0 | 0
7272 | Capacitor Bank | Sydney North No.1 & No.2 Capacitors | PS Replacement | Input_Proj_Commit | 2016 | 2013 | 0 | -196.9595 | -2607.0125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -2803.972 | 0 | 0 | 0
6712 | Capacitor Bank | New 66kV Capacitor at Panorama | PS Replacement | Input_Proj_Commit | 2017 | 2013 | -1.765 | -2747.448 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -2749.213 | 0 | 0
6196 | Capacitor Bank | Taree No.3 132kV Capacitor | PS Replacement | Input_Proj_Commit | 2018 | 2013 | 50.6504 | -2445.7986 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -2395.1482 | 0
7643 | Capacitor Bank | Taree No.4 & No.5 Capacitors | PS Replacement | Input_Proj_Commit | 2018 | 2013 | 0 | 0 | 7311.6087 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7311.6087 | 0
7757 | Capacitor Bank | Taree No.3 132kV Capacitor | PS Replacement | Input_Proj_Commit | 2018 | 2013 | 0 | 0 | 1826.3573 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1826.3573 | 0
6152 | Capacitor Bank | Canberra No.1 132kV 80MVAr Capacitor | PS Replacement | Input_Proj_Commit | 2019 | 2013 | 50.2146 | -3681.7668 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7344 | Capacitor Bank | Broken Hill No.3 and No.4 Capacitors | PS Replacement | Input_Proj_Commit | 2020 | 2013 | 0 | 0 | 0 | 5984.2192 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7333 | Capacitor Bank | Newcastle No.1 Capacitor | PS Replacement | Input_Proj_Commit | 2021 | 2013 | 0 | 0 | 2491.6316 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7334 | Capacitor Bank | Newcastle No.2 Capacitor | PS Replacement | Input_Proj_Commit | 2021 | 2013 | 0 | 0 | 470.8713 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5642 | Communications | MMRN Modifications - Sydney - Newcastle | PS Replacement | Input_Proj_Commit | 2009 | 2013 | -32.6193 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5946 | Communications | Port Macquarie & Taree Radio Network Modification | PS Replacement | Input_Proj_Commit | 2009 | 2013 | -30.6038 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5947 | Communications | Kempsey & Nambucca Microwave Radio Modification | PS Replacement | Input_Proj_Commit | 2009 | 2013 | -1.0459 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5948 | Communications | Koolkhan Microwave Radio Network Modification | PS Replacement | Input_Proj_Commit | 2009 | 2013 | -0.37043 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4167 | Communications | OPGW Backup North & West NSW | PS Replacement | Input_Proj_Commit | 2011 | 2013 | -79331.508 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4339 | Communications | OPGW Backup - Southern Region | PS Replacement | Input_Proj_Commit | 2011 | 2013 | -80639.3209 | 926.8114 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5488 | Communications | North Coast Microwave Radio Network - Extension To Coffs Harbour 330 and Lismore 330 Substations | PS Replacement | Input_Proj_Commit | 2011 | 2013 | 1140.5653 | 104358.4145 | 73415.3046 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5607 | Communications | South Western NSW Replacement | PS Replacement | Input_Proj_Commit | 2011 | 2013 | -20.9727 | -119473.0949 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5731 | Communications | Augmentation of Fault Clearing Times on Selected Transmission Line | PS Replacement | Input_Proj_Commit | 2011 | 2013 | -41664.8646 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6037 | Communications | Mount Piper 132kV - 330kV Substation No.2 Intertrip On 94Y Line | PS Replacement | Input_Proj_Commit | 2011 | 2013 | -0.71906 | 0 | -10320.4849 | -4294.9853 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6154 | Communications | SCADA Comms to Beryl Substation | PS Replacement | Input_Proj_Commit | 2011 | 2013 | 0 | -1886.1622 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6243 | Communications | North Coast Microwave Replacement | PS Replacement | Input_Proj_Commit | 2011 | 2013 | 48260.0487 | 3396.0575 | 0 | -95353.195 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6245 | Communications | Replace PNX Telephone Network - Technical Services | PS Replacement | Input_Proj_Commit | 2011 | 2013 | 1395.3316 | 1446.0392 | -8236.2713 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6281 | Communications | Communications Upgrade and Replacement | PS Replacement | Input_Proj_Commit | 2011 | 2013 | 18740542.8623 | 6057219.1611 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6589 | Communications | Armidale to Dumaresq OPGW PSR 216 | PS Replacement | Input_Proj_Commit | 2011 | 2013 | -11.6793 | -16873.7047 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6642 | Communications | Augmentation of Optical Terminal Equipment Between Armidale & Dumaresq | PS Replacement | Input_Proj_Commit | 2011 | 2013 | -1.3074 | 0 | 0 | -1871.2327 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6772 | Communications | OPGW Installation For Protection at Murray and Lower Tumut Switching Station | PS Replacement | Input_Proj_Commit | 2011 | 2013 | 12614.4856 | -13552.2647 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6842 | Communications | Lismore 330 Substation - Augmentation of Communications Services | PS Replacement | Input_Proj_Commit | 2011 | 2013 | 720.2074 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6848 | Communications | Communications Upgrade & Replacement (SP9) | PS Replacement | Input_Proj_Commit | 2011 | 2013 | 2586020.9214 | 2499654.3847 | 1243017.6821 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6960 | Communications | Western Microwave Extension - TSP 46 & 47 | PS Replacement | Input_Proj_Commit | 2011 | 2013 | 3340790.6953 | 6551585.2438 | 1880326.6062 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7287 | Communications | Southern NSW Microwave Radio | PS Replacement | Input_Proj_Commit | 2011 | 2013 | 0 | 2816.2594 | -3255.5404 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7288 | Communications | Beryl SCADA Microwave Radio | PS Replacement | Input_Proj_Commit | 2011 | 2013 | 0 | 1888.055 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8022 | Communications | Dumaresq Protection & Communication Replacement | PS Replacement | Input_Proj_Commit | 2014 | 2013 | 0 | 0 | 0 | 8978.0434 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7462 | Communications | Spur Microwave System Replacement | PS Replacement | Input_Proj_Commit | 2015 | 2013 | 13754.1248 | -1890.8942 | 30215.5429 | 434245.6082 | 0 | 0 | 0 | 0 | 0 | 476324.3817 | 0 | 0 | 0 | 0
7466 | Communications | Albury to Hume District Communications Augmentation | PS Replacement | Input_Proj_Commit | 2017 | 2013 | 0 | 0 | 0 | 71865.9027 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 71865.9027 | 0 | 0
6056 | Control System | Modification of Autoreclose Facilities | PS Replacement | Input_Proj_Commit | 2009 | 2013 | -0.076264 | 0 | 0 | -2329.9785 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6380 | Control System | Jindera to Albury Transmission Lines | PS Replacement | Input_Proj_Commit | 2016 | 2013 | 49391.4732 | -72083.8415 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -22692.3683 | 0 | 0 | 0
7670 | Control System | Modification of Auto Reclose Facilities At Ingleburn and Panorama | PS Replacement | Input_Proj_Commit | 2017 | 2013 | 0 | 0 | 408.2308 | -397.437 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10.7939 | 0 | 0
6847 | Fault Recorders | Travelling Wave Fault Locators Installation | PS Replacement | Input_Proj_Commit | 2011 | 2013 | 97023.6053 | 56084.9594 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7788 | Oil Containment | Murray Oil Containment Upgrade | PS Replacement | Input_Proj_Commit | 2014 | 2013 | 0 | 0 | 328.5521 | 85854.0318 | 2946394.6761 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8023 | Oil Containment | Beryl Oil Containment Upgrade | PS Replacement | Input_Proj_Commit | 2016 | 2013 | 0 | 0 | 0 | 2046.1398 | 0 | 0 | 0 | 0 | 0 | 0 | 2046.1398 | 0 | 0 | 0
8027 | Oil Containment | Muswellbrook Oil Containment Upgrade | PS Replacement | Input_Proj_Commit | 2016 | 2013 | 0 | 0 | 0 | 10029.14 | 0 | 0 | 0 | 0 | 0 | 0 | 10029.14 | 0 | 0 | 0
8078 | Oil Containment | Inverell Oil Containment Upgrade | PS Replacement | Input_Proj_Commit | 2016 | 2013 | 0 | 0 | 0 | 1264.6173 | 0 | 0 | 0 | 0 | 0 | 0 | 1264.6173 | 0 | 0 | 0
5641 | Oil Containment | Yass Oil Contaimnent Upgrade | PS Replacement | Input_Proj_Commit | 2017 | 2013 | -9098.1675 | 228.9779 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -8869.1896 | 0 | 0
8032 | Oil Containment | Sydney South Oil Containment Upgrade | PS Replacement | Input_Proj_Commit | 2018 | 2013 | 0 | 0 | 0 | 324.6537 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 324.6537 | 0
7680 | Property | Yass Strategic Site Acquisition | PS Replacement | Input_Proj_Commit | 2014 | 2013 | 0 | 0 | 17551.4458 | -17087.3643 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6916 | Reactor Installation | Vales Point to Munmorah 330kV Line 23 Series Reactor Replacement | PS Replacement | Input_Proj_Commit | 2009 | 2013 | 0 | 7231.2596 | -7031.9518 | -53.1215 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5577 | Reactor Replacement | Munmorah Substation Line 23 330kV Reactor Replacement | PS Replacement | Input_Proj_Commit | 2009 | 2013 | -542592.6764 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5627 | Reactor Replacement | Tamworth Substation - Replacement of Shunt Reactors | PS Replacement | Input_Proj_Commit | 2009 | 2013 | 49414.1891 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6706 | Reactor Replacement | Beaconsfield Shunt Reactor | PS Replacement | Input_Proj_Commit | 2009 | 2013 | -192.6109 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7849 | Reactor Replacement | Armidale No.1 330kV 50MVAr Reactor Replacement | PS Replacement | Input_Proj_Commit | 2014 | 2013 | 0 | 0 | 2531.075 | 1385824.7363 | 3384387.9992 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7346 | Reactor Replacement | Buronga X2 220kV Reactor | PS Replacement | Input_Proj_Commit | 2016 | 2013 | 0 | 0 | 4199.3566 | 51968.7726 | 0 | 0 | 0 | 0 | 0 | 0 | 56168.1292 | 0 | 0 | 0
7342 | Reactor Replacement | Broken Hill No.1 & No.2 220kV Reactors | PS Replacement | Input_Proj_Commit | 2018 | 2013 | 0 | 0 | 3391.3464 | 43518.7479 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 46910.0943 | 0
7325 | Reactor Replacement | Beaconsfield West No.1 132kV Reactor | PS Replacement | Input_Proj_Commit | 2019 | 2013 | 0 | 0 | 98.6865 | 21271.0035 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6922 | Reinforcement of Supply to the Orange Area | 944 Line Wallerawang to Orange North Rebuild | PS Replacement | Input_Proj_Commit | 2014 | 2013 | 0 | 18581.1869 | -18228.4646 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6251 | SCADA | SCADA to Tumut | PS Replacement | Input_Proj_Commit | 2015 | 2013 | 3954.609 | -6195.4091 | -7666.9636 | 0 | 0 | 0 | 0 | 0 | 0 | -9907.7637 | 0 | 0 | 0 | 0
6255 | SCADA | SCADA to Molong | PS Replacement | Input_Proj_Commit | 2015 | 2013 | 0 | -1244.4009 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1244.4009 | 0 | 0 | 0 | 0
7303 | SCADA | SCADA to Molong | PS Replacement | Input_Proj_Commit | 2015 | 2013 | 0 | 1245.645 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1245.645 | 0 | 0 | 0 | 0
7318 | SCADA | SCADA to Tumut | PS Replacement | Input_Proj_Commit | 2015 | 2013 | 0 | 52247.8964 | 7666.9636 | 0 | 0 | 0 | 0 | 0 | 0 | 59914.86 | 0 | 0 | 0 | 0
6277 | SCADA | SCADA to Albury | PS Replacement | Input_Proj_Commit | 2016 | 2013 | -1.1222 | -2412.2383 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -2413.3604 | 0 | 0 | 0
7279 | SCADA | SCADA to Albury | PS Replacement | Input_Proj_Commit | 2016 | 2013 | 0 | 5599.9155 | 0 | 459.5371 | 0 | 0 | 0 | 0 | 0 | 0 | 6059.4526 | 0 | 0 | 0
6247 | SCADA | SCADA to Cooma | PS Replacement | Input_Proj_Commit | 2017 | 2013 | -0.92607 | 0 | 0 | -1271.922 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1272.8481 | 0 | 0
7297 | SCADA | SCADA to Hume | PS Replacement | Input_Proj_Commit | 2017 | 2013 | 0 | 64725.9544 | 239.578 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 64965.5324 | 0 | 0
6278 | SCADA | ANM SCADA | PS Replacement | Input_Proj_Commit | 2018 | 2013 | -1.242 | -1758.7797 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1760.0217 | 0
7280 | SCADA | ANM SCADA | PS Replacement | Input_Proj_Commit | 2018 | 2013 | 0 | 5695.5879 | -5581.562 | 428.766 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 542.792 | 0
6461 | Secondary System Renewal | Lismore Substation Control System Replacement | PS Replacement | Input_Proj_Commit | 2011 | 2013 | 1033049.8682 | 943696.8984 | 798.225 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6715 | Secondary System Renewal | Dapto Secondary System Replacement | PS Replacement | Input_Proj_Commit | 2014 | 2013 | 4910509.1817 | 3266328.1443 | 1526000.5701 | 1253297.5303 | 1310096.494 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7083 | Secondary System Renewal | Guthega Secondary System Renewal | PS Replacement | Input_Proj_Commit | 2014 | 2013 | 0 | 16041.7364 | 5785.5524 | 594238.585 | 2617698.2195 | 566135.6777 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7455 | Secondary System Renewal | Guthega Secondary System Renewal | PS Replacement | Input_Proj_Commit | 2014 | 2013 | 0 | 33208.7642 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7669 | Secondary System Renewal | Yass Secondary System Renewal | PS Replacement | Input_Proj_Commit | 2014 | 2013 | 0 | 0 | 0 | 1032.7537 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7151 | Secondary System Renewal | Tumut Secondary System Renewal | PS Replacement | Input_Proj_Commit | 2015 | 2013 | 0 | 31277.8762 | 162943.6077 | 2048280.685 | 14035390.6782 | 0 | 0 | 0 | 0 | 16277892.8471 | 0 | 0 | 0 | 0
7301 | Secondary System Renewal | Molong Secondary System Renewal | PS Replacement | Input_Proj_Commit | 2015 | 2013 | 0 | 37603.0604 | -36850.3518 | 0 | 0 | 0 | 0 | 0 | 0 | 752.7086 | 0 | 0 | 0 | 0
6985 | Secondary System Renewal | Sydney West Secondary System Renewal | PS Replacement | Input_Proj_Commit | 2016 | 2013 | 48283.8541 | 730585.1458 | 2186776.4835 | 4895161.1361 | 20158116.4743 | 5365799.9213 | 3524422.6526 | 0 | 0 | 0 | 36909145.6677 | 0 | 0 | 0
7061 | Secondary System Renewal | Griffith Secondary System Renewal | PS Replacement | Input_Proj_Commit | 2016 | 2013 | 0 | 14281.9783 | 678777.4197 | 1634771.4468 | 11602571.9226 | 3856354.2373 | 0 | 0 | 0 | 0 | 17786757.0048 | 0 | 0 | 0
7353 | Secondary System Renewal | Balranald Secondary System Renewal | PS Replacement | Input_Proj_Commit | 2016 | 2013 | 0 | -360.061 | 408.6268 | 46273.769 | 0 | 0 | 0 | 0 | 0 | 0 | 46322.3349 | 0 | 0 | 0
7062 | Secondary System Renewal | Kangaroo Valley Secondary System Renewal | PS Replacement | Input_Proj_Commit | 2016 | 2013 | 0 | 14684.2236 | 11809.8803 | -25325.4814 | 0 | 0 | 0 | 0 | 0 | 0 | 1168.6225 | 0 | 0 | 0
7350 | Secondary System Renewal | Albury Secondary System Renewal | PS Replacement | Input_Proj_Commit | 2016 | 2013 | 0 | 0 | 0 | 21893.8313 | 0 | 0 | 0 | 0 | 0 | 0 | 21893.8313 | 0 | 0 | 0
7366 | Secondary System Renewal | Hume Secondary System Renewal | PS Replacement | Input_Proj_Commit | 2017 | 2013 | 1468.3057 | -61184.2562 | 0 | 4638.4892 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -55077.4614 | 0 | 0
7365 | Secondary System Renewal | Deniliquin Secondary System Renewal | PS Replacement | Input_Proj_Commit | 2018 | 2013 | 0 | 0 | 0 | 4797.813 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4797.813 | 0
7638 | Secondary System Renewal | Sydney North Secondary System Renewal | PS Replacement | Input_Proj_Commit | 2019 | 2013 | 0 | 0 | 0 | 34534.4753 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6928 | Secondary System Renewal | Liddell Secondary System Renewal | PS Replacement | Input_Proj_Commit | 2020 | 2013 | 0 | 2484.7183 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7351 | Secondary System Renewal | Beryl Secondary System Renewal | PS Replacement | Input_Proj_Commit | 2020 | 2013 | 0 | 0 | -385.2213 | 375.0561 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7354 | Secondary System Renewal | Buronga Secondary System Renewal | PS Replacement | Input_Proj_Commit | 2020 | 2013 | 0 | 0 | 385.2213 | 3011.1627 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7651 | Secondary System Renewal | Liddell Secondary System Renewal | PS Replacement | Input_Proj_Commit | 2020 | 2013 | 0 | 0 | 0 | 16129.5345 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7667 | Secondary System Renewal | Avon Secondary System Renewal | PS Replacement | Input_Proj_Commit | 2021 | 2013 | 0 | 0 | 0 | 21751.6229 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6364 | Substation Minor Projects | Double Breaker Autoreclose Modifications at Various Sites | PS Replacement | Input_Proj_Commit | 2009 | 2013 | 476.6846 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4025 | Substation Minor Projects | Communications Upgrade and Replacement | PS Replacement | Input_Proj_Commit | 2011 | 2013 | 0 | 0 | 274119.6603 | -229214.687 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6874 | Substation Minor Projects | Tumut 132/66kV Synchronism-Check System on Feeder 850 | PS Replacement | Input_Proj_Commit | 2011 | 2013 | 107852.9506 | 6258.6271 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7827 | Substation Minor Projects | Replacement of Line 11 Wave Trap at Sydney South | PS Replacement | Input_Proj_Commit | 2014 | 2013 | 0 | 0 | 0 | 27650.1436 | 153537.6725 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P0000885 | Substation Minor Projects | Armidale AC System Replacement | PS Replacement | Input_Proj_Commit | 2014 | 2013 | 0 | 0 | 0 | 0 | 417399.6144 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P0002189 | Substation Minor Projects | Modifications of Secondary Systems for a 66kV Switchbay at Beryl | PS Replacement | Input_Proj_Commit | 2014 | 2013 | 0 | 0 | 0 | 0 | 468330.0781 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6106 | Substation Minor Projects | Newcastle Substation 330kV Bus Coupling | PS Replacement | Input_Proj_Commit | 2015 | 2013 | 4236.2204 | 0 | -16189.1966 | 0 | 0 | 0 | 0 | 0 | 0 | -11952.9762 | 0 | 0 | 0 | 0
8176 | Substation Minor Projects | Lower Tumut 11kV Switchboard Replacement | PS Replacement | Input_Proj_Commit | 2015 | 2013 | 0 | 0 | 0 | 0 | 0 | 184810.2539 | 0 | 0 | 0 | 184810.2539 | 0 | 0 | 0 | 0
7682 | Substation Minor Projects | Murray 11kV Switchboard Replacement | PS Replacement | Input_Proj_Commit | 2015 | 2013 | 0 | 0 | 0 | 0 | 0 | 184810.2539 | 0 | 0 | 0 | 184810.2539 | 0 | 0 | 0 | 0
8083 | Substation Minor Projects | Dapto 415V AC System Replacement | PS Replacement | Input_Proj_Commit | 2015 | 2013 | 0 | 0 | 0 | 7203.4459 | 0 | 0 | 0 | 0 | 0 | 7203.4459 | 0 | 0 | 0 | 0
6040 | Substation Minor Projects | Sydney West 132kV Disconnector Replacement | PS Replacement | Input_Proj_Commit | 2016 | 2013 | 32729.8483 | 174748.821 | 175234.9574 | 17560.3745 | 0 | 0 | 0 | 0 | 0 | 0 | 400274.0012 | 0 | 0 | 0
5811 | Substation Minor Projects | Tamworth 66kV Line Bay | PS Replacement | Input_Proj_Commit | 2017 | 2013 | 0 | 0 | -19048.7716 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -19048.7716 | 0 | 0
8120 | Substation Minor Projects | Tamworth 66kV Line Bay | PS Replacement | Input_Proj_Commit | 2017 | 2013 | 0 | -3916.9017 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -3916.9017 | 0 | 0
8073 | Substation Minor Projects | Removal of SICAM from Haymarket GIS | PS Replacement | Input_Proj_Commit | 2017 | 2013 | 0 | 0 | 0 | 12238.4285 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12238.4285 | 0 | 0
5738 | Substation Minor Projects | Supply to Nabiac | PS Replacement | Input_Proj_Commit | 2018 | 2013 | 0 | 0 | -1509.3724 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1509.3724 | 0
6432 | Substation Minor Projects | Taree 33kV Line Bay | PS Replacement | Input_Proj_Commit | 2018 | 2013 | 0 | -1165.4342 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1165.4342 | 0
7315 | Substation Minor Projects | Taree 33kV Line Bay | PS Replacement | Input_Proj_Commit | 2018 | 2013 | 0 | 1166.6039 | -1143.2631 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23.3408 | 0
6915 | Substation Minor Projects | Canberra 330kV Substation - Uprating to 362kV | PS Replacement | Input_Proj_Commit | 2019 | 2013 | 0 | 0 | 97.1234 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7029 | Substation Minor Projects | Junee East Switching Station Second Supply to Temora | PS Replacement | Input_Proj_Commit | 2020 | 2013 | 0 | 0 | -478.6661 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8062 | Substation Minor Projects | Wagga 132 - 99X Line Wave Trap | PS Replacement | Input_Proj_Commit | 2020 | 2013 | 0 | 0 | 0 | 1228.0228 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5430 | Substation Renewal | Glen Innes 132kV Substation Rebuild | PS Replacement | Input_Proj_Commit | 2009 | 2013 | -20834.0666 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7337 | Substation Renewal | Kempsey 132kV Substation Condition | PS Replacement | Input_Proj_Commit | 2009 | 2013 | 0 | 0 | 0 | 157.8223 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6313 | Substation Renewal | Beaconsfield West Substation Renewal | PS Replacement | Input_Proj_Commit | 2013 | 2013 | -89.872 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6570 | Substation Renewal | Beaconsfield West Substation Renewal | PS Replacement | Input_Proj_Commit | 2013 | 2013 | 24669656.0921 | 55578022.9081 | 34844953.4499 | 11657305.6492 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7563 | Substation Renewal | Beaconsfield West Substation Renewal | PS Replacement | Input_Proj_Commit | 2013 | 2013 | 0 | 0 | 2548.7072 | -2481.3178 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6336 | Substation Renewal | Queanbeyan Substation Renewal | PS Replacement | Input_Proj_Commit | 2014 | 2013 | 15803604.2305 | 444139.5363 | 736987.5273 | 1251636.2471 | 821308.9141 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6314 | Substation Renewal | Upper Tumut Switching Station Renewal | PS Replacement | Input_Proj_Commit | 2015 | 2013 | 489644.6829 | 6336185.1476 | 10294213.8121 | 12470986.846 | 11192433.8947 | 4106930.9385 | 0 | 0 | 0 | 44890395.3218 | 0 | 0 | 0 | 40783464.3833
6838 | Substation Renewal | Wallerawang 132 Substation Renewal | PS Replacement | Input_Proj_Commit | 2015 | 2013 | 710576.5952 | 3385052.0126 | 14895767.1717 | 24631955.0725 | 21427455.4951 | 756419.0098 | 0 | 0 | 0 | 65807225.3569 | 0 | 0 | 0 | 0
6931 | Substation Renewal | Lower Tumut Substation Renewal | PS Replacement | Input_Proj_Commit | 2015 | 2013 | 0 | 0 | -233.9402 | 0 | 0 | 0 | 0 | 0 | 0 | -233.9402 | 0 | 0 | 0 | 0
7479 | Substation Renewal | Yanco Substation Renewal | PS Replacement | Input_Proj_Commit | 2016 | 2013 | 0 | 796.5684 | 154561.7868 | 146715.8291 | 1631155.8972 | 8532527.2726 | 3784578.935 | 0 | 0 | 0 | 14250336.2891 | 0 | 0 | 0
6912 | Substation Renewal | Tamworth 132 Substation Renewal | PS Replacement | Input_Proj_Commit | 2017 | 2013 | 6306.8724 | 73735.3154 | 160101.7275 | 620375.7209 | 1807542.3752 | 20055759.9741 | 9057631.3417 | 0 | 0 | 0 | 0 | 31781453.3271 | 0 | 0
6965 | Substation Renewal | Cooma Substation Renewal | PS Replacement | Input_Proj_Commit | 2017 | 2013 | 0 | 249473.7724 | 117285.1551 | 1066498.55 | 2039060.145 | 20403717.5211 | 5914594.6019 | 0 | 0 | 0 | 0 | 29790629.7455 | 0 | 0
7027 | Substation Renewal | Orange Substation Renewal | PS Replacement | Input_Proj_Commit | 2017 | 2013 | 0 | 145446.9308 | 266301.03 | 281693.8354 | 2151214.9675 | 3109636.8868 | 12192346.7566 | 0 | 0 | 0 | 0 | 18146640.4072 | 0 | 0
6962 | Substation Renewal | Burrinjuck Substation Renewal | PS Replacement | Input_Proj_Commit | 2017 | 2013 | 0 | 38250.8298 | -37254.4455 | -224.64 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 771.7443 | 0 | 0
7378 | Substation Renewal | Vales Point Substation Renewal | PS Replacement | Input_Proj_Commit | 2018 | 2013 | 6766.7134 | 4319.0726 | 273459.7736 | 196906.4938 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 481452.0534 | 0
8076 | Substation Renewal | Taree Substation 33kV Switchyard Renewal | PS Replacement | Input_Proj_Commit | 2018 | 2013 | 0 | -97.5333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -97.5333 | 0
6350 | Substation Renewal | Canberra Substation Renewal | PS Replacement | Input_Proj_Commit | 2019 | 2013 | 0 | 0 | -171686.8797 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7398 | Substation Renewal | Canberra Substation Renewal | PS Replacement | Input_Proj_Commit | 2019 | 2013 | 0 | 0 | 392.985 | -186.7875 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7406 | Substation Renewal | Wagga 132kV Substation Renewal | PS Replacement | Input_Proj_Commit | 2020 | 2013 | 0 | 0 | 0 | -2.2929 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7544 | Substation Renewal | Wagga 132kV Substation Renewal | PS Replacement | Input_Proj_Commit | 2020 | 2013 | 31014.8821 | 12589.3622 | 51.6463 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6914 | Substation Renewal | Wagga 132kV Substation Renewal | PS Replacement | Input_Proj_Commit | 2020 | 2013 | 11087.7397 | 2733.8686 | -10866.8039 | 35502.6229 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7678 | Substation Renewal | Munmorah Substation Renewal | PS Replacement | Input_Proj_Commit | 2020 | 2013 | 82150.8575 | 82744.7933 | 75955.8835 | -96542.9188 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7298 | SVC Control System Replacement | Kemps Creek SVC Control System Replacement | PS Replacement | Input_Proj_Commit | 2015 | 2013 | 88831.3596 | 1329.365 | 70677.1234 | 91965.7993 | -328859.8444 | 0 | 0 | 0 | 0 | -76056.1971 | 0 | 0 | 0 | -76056.1971
7822 | SVC Control System Replacement | Broken Hill SVC Control System Replacement | PS Replacement | Input_Proj_Commit | 2015 | 2013 | 10922.5621 | 0 | 93300.0667 | 321944.5181 | 9210179.4193 | 4571701.3262 | 0 | 0 | 0 | 14208047.8924 | 0 | 0 | 0 | 0
7091 | SVC Control System Replacement | Armidale SVC Control System Replacement | PS Replacement | Input_Proj_Commit | 2018 | 2013 | 3476.8023 | -250.0329 | -30461.6757 | 0.010145 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -27234.8962 | 0
5533 | Transformer Replacement | Sydney West No.2 Transformer Replacement | PS Replacement | Input_Proj_Commit | 2009 | 2013 | 46820.5165 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6393 | Transformer Replacement | Kempsey 132kV Substation 66/33kV 2 x 25MVA Transformer Replacements | PS Replacement | Input_Proj_Commit | 2009 | 2013 | -2.5603 | 1246.9104 | 0 | -4867.5526 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6415 | Transformer Replacement | Kempsey 2x60MVA 132/33kV Transformer | PS Replacement | Input_Proj_Commit | 2009 | 2013 | 190653.8959 | -774.7053 | -14290.8513 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6694 | Transformer Replacement | Tuggerah Substation No.1 Transformer Replacement | PS Replacement | Input_Proj_Commit | 2009 | 2013 | 680786.5069 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5677 | Transformer Replacement | Sydney South No.1 & No.2 Transformers | PS Replacement | Input_Proj_Commit | 2011 | 2013 | 1744455.2603 | 300600.4925 | 0 | 102655.3559 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5878 | Transformer Replacement | Orange No.1 & No.2 Transformer Replacement | PS Replacement | Input_Proj_Commit | 2011 | 2013 | 3717546.2384 | 2038924.6518 | 78782.4865 | 50.6358 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6172 | Transformer Replacement | Wallerawang 132kV Transformer Replacements | PS Replacement | Input_Proj_Commit | 2012 | 2013 | 1708.1678 | 483.1793 | -2718.6836 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6721 | Transformer Replacement | Wallerawang 330/132kV Transformer Replacements & Relocation | PS Replacement | Input_Proj_Commit | 2012 | 2013 | 4378132.1518 | 15300738.8147 | 4248930.4321 | 17063.5935 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6834 | Transformer Replacement | Narrabri No.1 & No.3 Transformer Replacements | PS Replacement | Input_Proj_Commit | 2013 | 2013 | 598021.8961 | 1336927.7077 | 1949895.8978 | 7429929.0733 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5619 | Transformer Replacement | Yass No.3 Transformer | PS Replacement | Input_Proj_Commit | 2014 | 2013 | 66083.7346 | -66068.8563 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5889 | Transformer Replacement | Sydney East No.4 Transformer | PS Replacement | Input_Proj_Commit | 2014 | 2013 | 6989.9935 | 0 | -689345.3087 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6851 | Transformer Replacement | Dapto Substation Temporary Transformer Installation (System Spare) | PS Replacement | Input_Proj_Commit | 2014 | 2013 | 45658.3466 | 9441.9871 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6984 | Transformer Replacement | Dapto Substation Temporary Transformer Installation (System Spare) | PS Replacement | Input_Proj_Commit | 2014 | 2013 | 100886.6753 | 914640.3622 | 566328.1234 | 1911404.0939 | 1251730.5853 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7140 | Transformer Replacement | Yass No.3 Transformer | PS Replacement | Input_Proj_Commit | 2014 | 2013 | 0 | 353135.1084 | 1686194.3043 | 568056.6572 | 1349836.1539 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7262 | Transformer Replacement | Sydney East No.4 Transformer | PS Replacement | Input_Proj_Commit | 2014 | 2013 | 0 | 0 | 370887.855 | 3742676.3696 | 9850331.0438 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7628 | Transformer Replacement | Surge Arresters Installation At 330kV Line Entries | PS Replacement | Input_Proj_Commit | 2014 | 2013 | 0 | 0 | 467292.3477 | 443955.0354 | 1003814.0062 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6919 | Transformer Replacement | Kemps Creek Replace No.1 and No.2 Transformer VCC | PS Replacement | Input_Proj_Commit | 2015 | 2013 | 0 | 0 | -54.585 | 0 | 0 | 0 | 0 | 0 | 0 | -54.585 | 0 | 0 | 0 | 0
7085 | Transformer Replacement | Yanco Transformer Replacement | PS Replacement | Input_Proj_Commit | 2015 | 2013 | 11039.6278 | 43578.1475 | 554003.5412 | 3683048.7838 | 7167393.1681 | 1032092.0068 | 0 | 0 | 0 | 12491155.2753 | 0 | 0 | 0 | 0
7471 | Transformer Replacement | Newcastle No.1, No.2 and No.3 Transformer Replacement | PS Replacement | Input_Proj_Commit | 2015 | 2013 | 45756.6622 | 843.0594 | 425078.5551 | 5017952.2629 | 16265314.7427 | 2679567.1137 | 0 | 0 | 0 | 24434512.396 | 0 | 0 | 0 | 0
7092 | Transformer Replacement | Griffith Transformer Replacement | PS Replacement | Input_Proj_Commit | 2016 | 2013 | 37990.9736 | 3177.522 | 40941.7785 | 1505362.0928 | 5822975.7785 | 4343423.3547 | 0 | 0 | 0 | 0 | 11753871.5001 | 0 | 0 | 0
7356, 7357, 7563 | Transformer Replacement | Beaconsfield West No.1 & No.2 330kV Transformers | PS Replacement | Input_Proj_Commit | 2018 | 2013 | 0 | 0 | 0 | 1461669.6856 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1461669.6856 | 0
7284 | Transformer Replacement | Canberra No.2 Transformer Replacement | PS Replacement | Input_Proj_Commit | 2019 | 2013 | 1010.6981 | 4.2535 | -6492.1667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6379 | Transformer Replacement | Wagga 132 No.2 Transformer Replacement | PS Replacement | Input_Proj_Commit | 2020 | 2013 | 5408.5988 | 0 | 0 | -13101.8956 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6021 | Transmission Line Life Extension | 11 Line Dapto to Sydney South Life Extension | PS Replacement | Input_Proj_Commit | 2013 | 2013 | 4370.7833 | 1836044.5215 | 2886618.1413 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7779 | Transmission Line Life Extension | 21 Line Sydney North to Tuggerah Life Extension | PS Replacement | Input_Proj_Commit | 2015 | 2013 | 0 | 0 | 0 | 0 | 0 | 3552103.5156 | 0 | 0 | 0 | 3552103.5156 | 0 | 0 | 0 | 0
7706 | Transmission Line Life Extension | 8 Line Dapto to Marulan Life Extension | PS Replacement | Input_Proj_Commit | 2016 | 2013 | 0 | 0 | 0 | 0 | 0 | 0 | 1974191.4062 | 0 | 0 | 0 | 1974191.4062 | 0 | 0 | 0
7716 | Transmission Line Life Extension | 24 Line Vales Point to Eraring Life Extension | PS Replacement | Input_Proj_Commit | 2016 | 2013 | 0 | 0 | 0 | 0 | 0 | 1162899.6094 | 0 | 0 | 1163620.1172 | 0 | 2326519.7266 | 0 | 0 | 0
7322 | Transmission Line Life Extension | 11 Line Dapto to Sydney South Life Extension | PS Replacement | Input_Proj_Commit | 2017 | 2013 | 0 | 0 | 0 | 0 | 0 | 0 | 2171610.5469 | 0 | 0 | 0 | 0 | 2171610.5469 | 0 | 0
7703 | Transmission Line Life Extension | 22 Line Vales Point to Structure 136 Life Extension | PS Replacement | Input_Proj_Commit | 2017 | 2013 | 0 | 0 | 0 | 0 | 0 | 0 | 3109711.7188 | 3110432.2266 | 0 | 0 | 0 | 6220143.9453 | 0 | 0
7720 | Transmission Line Life Extension | 18 Line Kangaroo Valley to Dapto Life Extension | PS Replacement | Input_Proj_Commit | 2017 | 2013 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1480643.5547 | 0 | 0 | 0 | 1480643.5547 | 0 | 0
7915 | Transmission Line Life Extension | 17 Line Avon to Picton Rd Life Extension | PS Replacement | Input_Proj_Commit | 2018 | 2013 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 792558.5938 | 0 | 0 | 0 | 792558.5938 | 0
7697 | Transmission Line Life Extension | 26 Line Sydney North to Vales Point Life Extension | PS Replacement | Input_Proj_Commit | 2019 | 2013 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1085805.2734 | 0 | 0 | 0 | 0 | 0
7715 | Transmission Line Life Extension | 959/92Z Line Sydney North to Sydney East Life Extension | PS Replacement | Input_Proj_Commit | 2019 | 2013 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3059996.6797 | 0 | 0 | 0 | 0 | 0
7727 | Transmission Line Life Extension | 10 Line Avon to Dapto Life Extension | PS Replacement | Input_Proj_Commit | 2019 | 2013 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1085805.2734 | 0 | 0 | 0 | 0 | 0
7728 | Transmission Line Life Extension | 23 Line Munmorah to Vales Point Life Extension | PS Replacement | Input_Proj_Commit | 2019 | 2013 | 0 | 0 | 0 | 0 | 0 | 0 | 1085805.2734 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7761 | Transmission Line Life Extension | 2M Line Munmorah to Tuggerah Life Extension | PS Replacement | Input_Proj_Commit | 2019 | 2013 | 0 | 0 | 0 | 0 | 0 | 789676.5625 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7914 | Transmission Line Life Extension | 16 Line Structure 104 to 159 Life Extension | PS Replacement | Input_Proj_Commit | 2019 | 2013 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7912 | Transmission Line Life Extension | 93 Line Eraring to Newcastle Life Extension | PS Replacement | Input_Proj_Commit | 2021 | 2013 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7911 | Transmission Line Life Extension | 90 Line Eraring to Newcastle Life Extension | PS Replacement | Input_Proj_Commit | 2022 | 2013 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P0002047 | Transmission Line Minor Projects | Reconstruction of Geehi Tee | PS Replacement | Input_Proj_Commit | 2015 | 2013 | 0 | 0 | 0 | 0 | 411718.75 | 1296914.0625 | 0 | 0 | 0 | 1708632.8125 | 0 | 0 | 0 | 0
5966 | Transmission Line Renewal | 990 Line Yass to Wagga 132kV Transmission Line Rebuild | PS Replacement | Input_Proj_Commit | 2010 | 2013 | 9205675.8643 | 707178.419 | 225315.9941 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7264 | Transmission Line Renewal | 944 Line Wallerawang to Orange North Rebuild | PS Replacement | Input_Proj_Commit | 2014 | 2013 | 14319.7226 | 76744.8656 | 534151.2091 | 1564708.1937 | 3405662.8142 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7725 | Transmission Line Renewal | 99J Yanco to Griffith 132kV Line Partial Rebuild | PS Replacement | Input_Proj_Commit | 2019 | 2013 | 0 | 0 | 0 | 0 | 154394.5312 | 216152.3438 | 2269599.6094 | 2233574.2188 | 2305625 | 0 | 0 | 0 | 0 | 0
7744 | Transmission Line Wood Pole Replacement | Line 85 Armidale to Tamworth Temporary Pole Replacement | PS Replacement | Input_Proj_Commit | 2015 | 2013 | 0 | 0 | 0 | 49074.1707 | 0 | 0 | 0 | 0 | 0 | 49074.1707 | 0 | 0 | 0 | 0
7709 | Transmission Line Wood Pole Replacement | Line 973 Cowra To Yass Pole Replacements | PS Replacement | Input_Proj_Commit | 2016 | 2013 | 0 | 0 | 0 | 18341.1666 | 0 | 0 | 0 | 0 | 0 | 0 | 18341.1666 | 0 | 0 | 0
7711 | Transmission Line Wood Pole Replacement | Line 970 Burrinjuck to Yass Pole Replacements | PS Replacement | Input_Proj_Commit | 2016 | 2013 | 0 | 0 | 0 | 20379.4742 | 0 | 0 | 0 | 0 | 0 | 0 | 20379.4742 | 0 | 0 | 0
7777 | Transmission Line Wood Pole Replacement | Line 96H Coffs Harbour To Koolkhan Wood Pole Replacement | PS Replacement | Input_Proj_Commit | 2016 | 2013 | 0 | 0 | 2990.0246 | 0 | 0 | 4992326.582 | 4992326.582 | 0 | 0 | 0 | 9987643.1887 | 0 | 0 | 0
7699 | Transmission Line Wood Pole Replacement | Line 99F Uranquinty to Yanco Pole Replacements | PS Replacement | Input_Proj_Commit | 2018 | 2013 | 0 | 0 | 0 | 3964.1937 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3964.1937 | 0
P0002076 | Cable Minor Projects | Cable 41 Temperature Monitoring | PS Security/Compliance | Input_Proj_Commit | 2014 | 2013 | 0 | 0 | 0 | 0 | 117339.8438 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7087 | Capacity of Victoria to NSW Interconnector | Snowy to Yass/Canberra Low Span Remediation | PS Security/Compliance | Input_Proj_Commit | 2019 | 2013 | 193597.3165 | 73288.5782 | -576099.611 | -5334.4655 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6244 | Communications | Replace FSX/FLX Multiplex Network | PS Security/Compliance | Input_Proj_Commit | 2014 | 2013 | 9690.6975 | -79314.1228 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7044 | Communications | Northern Microwave Replacement | PS Security/Compliance | Input_Proj_Commit | 2014 | 2013 | 0 | 4778944.5002 | 3903531.7544 | 3662532.2753 | 121227.7965 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7138 | Communications | Communications To Yanco and Colleambally | PS Security/Compliance | Input_Proj_Commit | 2014 | 2013 | 0 | 154980.4006 | 3729447.2402 | 2060158.9306 | 798000.4863 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7289 | Communications | Replace FSX/FLX Multiplex Network | PS Security/Compliance | Input_Proj_Commit | 2014 | 2013 | 0 | 139032.5077 | 2107933.2532 | 640644.4171 | 4427933.822 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7645 | Communications | Communications To Tumut/Gadara | PS Security/Compliance | Input_Proj_Commit | 2014 | 2013 | 0 | 5223.436 | 0 | 3094487.3057 | 1240386.1074 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7786 | Communications | Kangaroo Valley Communications – Vacate 2Ghz Band and Migrate To 6.7Ghz Band | PS Security/Compliance | Input_Proj_Commit | 2014 | 2013 | 0 | 0 | 0 | 902492.8641 | 2294756.7984 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P0001927 | Communications | Haymarket 330kV Telecommunications Augmentation | PS Security/Compliance | Input_Proj_Commit | 2014 | 2013 | 0 | 0 | 0 | 0 | 141013.6719 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6700 | Communications | VHF Network Augmentationfor Control Room Access | PS Security/Compliance | Input_Proj_Commit | 2015 | 2013 | 23296.2486 | -30148.831 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -6852.5824 | 0 | 0 | 0 | 0
7119 | Communications | VHF Network Augmentationfor Control Room Access | PS Security/Compliance | Input_Proj_Commit | 2015 | 2013 | 0 | 34960.7277 | -36543.2981 | 0 | 0 | 0 | 0 | 0 | 0 | -1582.5704 | 0 | 0 | 0 | 0
7286 | Communications | New England District Telecommunications Augmentation | PS Security/Compliance | Input_Proj_Commit | 2015 | 2013 | 21635.4409 | 29055.9939 | 75210.7116 | 234807.2623 | 2438642.0953 | 1692900.2928 | 0 | 0 | 0 | 4492251.7968 | 0 | 0 | 0 | 0
8098 | Communications | VHF Network Augmentationfor Control Room Access | PS Security/Compliance | Input_Proj_Commit | 2015 | 2013 | 0 | 0 | 0 | 3503.2464 | 720507.8125 | 216152.3438 | 2161523.4375 | 0 | 0 | 3101686.8401 | 0 | 0 | 0 | 0
7783 | Communications | Northern Microwave Loop | PS Security/Compliance | Input_Proj_Commit | 2016 | 2013 | 467408.0396 | 126391.093 | 30610.0494 | 404907.0931 | 1856316.8188 | 10314479.425 | 642127.2885 | 0 | 0 | 0 | 13842239.8073 | 0 | 0 | 0
6155 | Control System | Replacement of Electromechanical Underfrequency Relays | PS Security/Compliance | Input_Proj_Commit | 2011 | 2013 | 74663.1959 | 5353.6364 | 0 | 418.4076 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6941 | Control System | Auto Underfrequency Loadshedding Schemes Modification | PS Security/Compliance | Input_Proj_Commit | 2012 | 2013 | 45275.2928 | 1007998.5104 | 565048.6061 | 55577.5516 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P0002149 | Control System | Indication and Metering CT Ratio Changes at Dumaresq | PS Security/Compliance | Input_Proj_Commit | 2014 | 2013 | 0 | 0 | 0 | 0 | 60522.6562 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6113 | Control System | Multiple Contingency System Protection Scheme | PS Security/Compliance | Input_Proj_Commit | 2016 | 2013 | 0 | -3311.9866 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -3311.9866 | 0 | 0 | 0
7065 | Control System | Modification of Synchronising Angle at Gen Sites | PS Security/Compliance | Input_Proj_Commit | 2016 | 2013 | 0 | 0 | 0 | 0 | 1675338.4553 | 1118261.2972 | 99679.3162 | 0 | 0 | 0 | 2893279.0686 | 0 | 0 | 0
7505 | Control System | Modification of Synchronising Angle at Gen Sites | PS Security/Compliance | Input_Proj_Commit | 2016 | 2013 | 0 | 11586.6573 | 48924.3306 | -58685.2684 | 0 | 0 | 0 | 0 | 0 | 0 | 1825.7195 | 0 | 0 | 0
7316 | Control System | Multiple Contingency System Protection Scheme | PS Security/Compliance | Input_Proj_Commit | 2016 | 2013 | 0 | 3315.3043 | -3248.996 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 66.3083 | 0 | 0 | 0
P0001493 | Protection Change | Gadara 132kV Fault and Disturbance Recorder | PS Security/Compliance | Input_Proj_Commit | 2014 | 2013 | 0 | 0 | 0 | 0 | 174980.4688 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6832 | Quality of Supply | Voltage Unbalance Limits | PS Security/Compliance | Input_Proj_Commit | 2015 | 2013 | 76524.6985 | 10496.4148 | 1270.8261 | 14523.6453 | 0 | 0 | 0 | 0 | 0 | 102815.5848 | 0 | 0 | 0 | 0
7397 | Quality of Supply | Assessment of NER Quality of Supply Compliance | PS Security/Compliance | Input_Proj_Commit | 2019 | 2013 | 0 | 107723.8785 | 52251.192 | -153646.0079 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6254 | SCADA | SCADA to Gadara | PS Security/Compliance | Input_Proj_Commit | 2014 | 2013 | -2.5494 | -8440.2499 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7290 | SCADA | SCADA to Deniliquin | PS Security/Compliance | Input_Proj_Commit | 2014 | 2013 | -1.3945 | -2048.7532 | 28058.2263 | 74535.5602 | 417498.2314 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7293 | SCADA | SCADA to Gadara | PS Security/Compliance | Input_Proj_Commit | 2014 | 2013 | 0 | 9522.2511 | -9331.6501 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7461 | SCADA | SCADA to Colleambally | PS Security/Compliance | Input_Proj_Commit | 2014 | 2013 | -1.8412 | 928.9062 | 51116.349 | 258698.1904 | 301743.2475 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P0002366 | SCADA | SCADA to Tenterfield | PS Security/Compliance | Input_Proj_Commit | 2014 | 2013 | 1462.8255 | 0 | 0 | -5333.7857 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7759 | Secondary System Renewal | Gadara Relay Replacement | PS Security/Compliance | Input_Proj_Commit | 2014 | 2013 | 0 | 0 | 0 | 2097.3844 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7076 | Substation Minor Projects | Canberra Substation Noise Management | PS Security/Compliance | Input_Proj_Commit | 2014 | 2013 | 0 | 0 | 0 | 0 | 910927.7344 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P0001495 | Substation Minor Projects | Canberra Reduce AVR Settings | PS Security/Compliance | Input_Proj_Commit | 2014 | 2013 | 0 | 0 | 0 | 0 | 15439.4531 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6959 | Substation Minor Projects | Surge Arresters Instalation at 330kV Line Entries | PS Security/Compliance | Input_Proj_Commit | 2015 | 2013 | 38899.1071 | 12014.8278 | 137.5359 | 943289.4316 | 2319621.9347 | 1899030.4017 | 0 | 0 | 0 | 5212993.2389 | 0 | 0 | 0 | 0
6335 | Transformer Replacement | Wagga Substation 330kV Transformer Replacements | PS Security/Compliance | Input_Proj_Commit | 2010 | 2013 | 5598046.7025 | -14597.9727 | 694.6719 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6943 | Transformer Replacement | Munyang Transformer Replacement | PS Security/Compliance | Input_Proj_Commit | 2014 | 2013 | 225454.4288 | 674752.2504 | 10835375.9122 | 2805511.2756 | 102929.6875 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7470 | Transmission Line Low Spans | 97G Line Murray to Guthega Low Spans Remediation | PS Security/Compliance | Input_Proj_Commit | 2014 | 2013 | 160809.8669 | 9287.818 | 98085.0711 | 1092615.9327 | 2968492.1875 | 141822.0194 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7459 | Transmission Line Low Spans | 999 Line Yass to Cowra Low Spans Remediation | PS Security/Compliance | Input_Proj_Commit | 2016 | 2013 | 0 | 13626.627 | -13353.8607 | 7590.6968 | 0 | 0 | 0 | 0 | 0 | 0 | 7863.4631 | 0 | 0 | 0
7698 | Transmission Line Low Spans | 992 Line Burrinjuck to Tumut Low Spans Remediation | PS Security/Compliance | Input_Proj_Commit | 2016 | 2013 | 0 | 0 | 0 | 0 | 0 | 150611.8652 | 308789.0625 | 0 | 0 | 0 | 459400.9277 | 0 | 0 | 0
6913 | Transmission Line Low Spans | 97K Line Cooma to Munyang Low Spans Remediation | PS Security/Compliance | Input_Proj_Commit | 2018 | 2013 | 0 | 1058.7876 | -1037.5841 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21.2035 | 0
7708 | Transmission Line Low Spans | 993 Line Gadara to Wagga Low Spans Remediation | PS Security/Compliance | Input_Proj_Commit | 2018 | 2013 | 0 | 0 | 0 | 0 | 0 | 0 | 287173.8281 | 287173.8281 | 46318.3594 | 0 | 0 | 0 | 620666.0156 | 0
P0002240 | Transmission Line Low Spans | Southern Region Pole Lines Low Spans Remediation | PS Security/Compliance | Input_Proj_Commit | 2019 | 2013 | 0 | 0 | 0 | 0 | 0 | 107041.7285 | 107041.7285 | 214083.457 | 214083.457 | 0 | 0 | 0 | 0 | 0
P0002243 | Transmission Line Low Spans | Central Region Pole Lines Low Spans Remediation | PS Security/Compliance | Input_Proj_Commit | 2019 | 2013 | 0 | 0 | 0 | 0 | 0 | 103073.7891 | 103073.7891 | 206147.5781 | 206147.5781 | 0 | 0 | 0 | 0 | 0
P0002246 | Transmission Line Low Spans | Southern Region Tower Lines Low Spans Remediation | PS Security/Compliance | Input_Proj_Commit | 2019 | 2013 | 0 | 0 | 0 | 0 | 0 | 0 | 68083.2021 | 136166.5585 | 204249.7605 | 0 | 0 | 0 | 0 | 0
P0002249 | Transmission Line Low Spans | Northern Region Tower Lines Low Spans Remediation | PS Security/Compliance | Input_Proj_Commit | 2019 | 2013 | 0 | 0 | 6535.372 | 3506.6857 | 0 | 0 | 90526.7631 | 181053.3718 | 271580.1349 | 0 | 0 | 0 | 0 | 0
P0002252 | Transmission Line Low Spans | Northern Region Pole Lines Low Spans Remediation | PS Security/Compliance | Input_Proj_Commit | 2019 | 2013 | 0 | 0 | 0 | 0 | 0 | 178372.002 | 178372.002 | 356744.0039 | 356744.0039 | 0 | 0 | 0 | 0 | 0
P0002255 | Transmission Line Low Spans | Central Region Tower Lines Low Spans Remediation | PS Security/Compliance | Input_Proj_Commit | 2019 | 2013 | 0 | 0 | 0 | 0 | 0 | 0 | 86024.6186 | 172049.3915 | 258074.0101 | 0 | 0 | 0 | 0 | 0
6969 | Supply to Gunnedah, Narrabri and Moree | Installation of Phase Shifting Transformer on 969 Line | PS Augmentation | Input_Proj_Future | 2018 | 2013 | 0 | 0 | 0 | 0 | 0 | 296261.4902 | 977810.416 | 2227307.8594 | 12212005.2832 | 0 | 0 | 0 | 15713385.0488 | 0
6704 | Supply to the ACT | Wallaroo 330kV Switching Station | PS Augmentation | Input_Proj_Future | 2018 | 2013 | 0 | 0 | 0 | 0 | 224941.5098 | 1233359.0977 | 3703311.3438 | 19485689.1328 | 7673324.8301 | 0 | 0 | 0 | 32320625.9141 | 0
7661 | Substation Minor Projects | Supply to Temora | PS Connections | Input_Proj_Future | 2015 | 2013 | 0 | 0 | 0 | 0 | 2025926.9551 | 295196.168 | 0 | 0 | 0 | 2321123.123 | 0 | 0 | 0 | 0
P0000851 | Substation Minor Projects | Supply to Gulgong West | PS Connections | Input_Proj_Future | 2015 | 2013 | 0 | 0 | 0 | 0 | 118361.9355 | 1375202.3828 | 0 | 0 | 0 | 1493564.3184 | 0 | 0 | 0 | 0
7094 | Substation Minor Projects | Supply to Marsden Park | PS Connections | Input_Proj_Future | 2016 | 2013 | 0 | 0 | 0 | 0 | 73356.959 | 1163490.4258 | 398289.5137 | 0 | 0 | 0 | 1635136.8984 | 0 | 0 | 0
8093 | Substation Minor Projects | Supply to Molong | PS Connections | Input_Proj_Future | 2016 | 2013 | 0 | 0 | 0 | 0 | 33887.541 | 831268.3906 | 385152.5977 | 0 | 0 | 0 | 1250308.5293 | 0 | 0 | 0
P0002157 | Substation Minor Projects | Supply to Googong | PS Connections | Input_Proj_Future | 2018 | 2013 | 0 | 0 | 0 | 0 | 0 | 3402.8555 | 150071.4844 | 1090165.375 | 184051.6621 | 0 | 0 | 0 | 1427691.377 | 0
P0002186 | Easements | Easement Acquisition in the ACT | PS Easements | Input_Proj_Future | 2017 | 2013 | 0 | 0 | 0 | 0 | 0 | 180337.959 | 2130355.2988 | 7776416.1172 | 0 | 0 | 0 | 10087109.375 | 0 | 0
7673 | Property | Strategic Property Acquisition at Maraylya | PS Easements | Input_Proj_Future | 2016 | 2013 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P0002217 | Property | Strategic Property Acquisition in Sydney | PS Easements | Input_Proj_Future | 2017 | 2013 | 0 | 0 | 0 | 0 | 1165028.1953 | 0 | 0 | 0 | 0 | 0 | 0 | 1165028.1953 | 0 | 0
2001B | Cable Remediation | Cable 41 Backfill Rehabilitation | PS Replacement | Input_Proj_Future | 2017 | 2013 | 0 | 0 | 0 | 0 | 395798.6152 | 477012.1973 | 13225838.8254 | 3791103.1621 | 0 | 0 | 0 | 17889752.8 | 0 | 0
7344 | Capacitor Bank | Broken Hill No.3 and No.4 Capacitors | PS Replacement | Input_Proj_Future | 2020 | 2013 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6475.2037 | 0 | 0 | 0 | 0 | 0
8022 | Communications | Dumaresq Protection & Communication Replacement | PS Replacement | Input_Proj_Future | 2014 | 2013 | 0 | 0 | 0 | 31236.0723 | 611778.0371 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7462 | Communications | Spur Microwave System Replacement | PS Replacement | Input_Proj_Future | 2015 | 2013 | 0 | 0 | 0 | 0 | 2846752.0996 | 1045161.4277 | 0 | 0 | 0 | 3891913.5273 | 0 | 0 | 0 | 0
8222 | Communications | Hammonds Hill Radio Repeater Site Mains Power | PS Replacement | Input_Proj_Future | 2016 | 2013 | 0 | 0 | 0 | 0 | 0 | 391781.1666 | 491308.5133 | 0 | 0 | 0 | 883089.6799 | 0 | 0 | 0
P0002577 | Communications | Communications Between Lismore and Coffs Harbour | PS Replacement | Input_Proj_Future | 2016 | 2013 | 0 | 0 | 0 | 0 | 135428.707 | 880001.5834 | 9011587.1891 | 0 | 0 | 0 | 10027017.4795 | 0 | 0 | 0
P0002583 | Communications | Communications Between Wallerawang and Orange North via Panorama Substation | PS Replacement | Input_Proj_Future | 2016 | 2013 | 0 | 0 | 0 | 0 | 96884.627 | 530089.8463 | 7060702.7695 | 0 | 0 | 0 | 7687677.2428 | 0 | 0 | 0
P0002589 | Communications | Communications Between Williamsdale and Cooma | PS Replacement | Input_Proj_Future | 2016 | 2013 | 0 | 0 | 0 | 0 | 34396.0137 | 177429.3719 | 4726643.6492 | 0 | 0 | 0 | 4938469.0348 | 0 | 0 | 0
P0002579 | Communications | Communications Between Coffs Harbour and Port Macquarie | PS Replacement | Input_Proj_Future | 2017 | 2013 | 0 | 0 | 0 | 0 | 0 | 82000.2736 | 659096.7701 | 8425002.3252 | 0 | 0 | 0 | 9166099.3689 | 0 | 0
P0002585 | Communications | Communications Between Wellington and Orange North | PS Replacement | Input_Proj_Future | 2017 | 2013 | 0 | 0 | 0 | 0 | 0 | 40444.265 | 212085.0771 | 5660404.482 | 0 | 0 | 0 | 5912933.8242 | 0 | 0
P0002581 | Communications | Communications Between Port Macquarie and Stroud - Includes Waratah West to Tomago | PS Replacement | Input_Proj_Future | 2018 | 2013 | 0 | 0 | 0 | 0 | 0 | 0 | 98840.7027 | 866098.6646 | 9712962.6371 | 0 | 0 | 0 | 10677902.0045 | 0
P0002587 | Communications | Communications Between Parkes and Cowra | PS Replacement | Input_Proj_Future | 2018 | 2013 | 0 | 0 | 0 | 0 | 0 | 0 | 55896.9961 | 270306.4314 | 6847824.4133 | 0 | 0 | 0 | 7174027.8408 | 0
P0002591 | Communications | Communications Between Uranquinty and Griffith | PS Replacement | Input_Proj_Future | 2019 | 2013 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 82490.2189 | 647089.5074 | 0 | 0 | 0 | 0 | 0
P0002593 | Communications | Communications Between Yass and Wagga | PS Replacement | Input_Proj_Future | 2019 | 2013 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 83203.5217 | 819419.8455 | 0 | 0 | 0 | 0 | 0
8118 | Disconnection of Munmorah Power Station | Disconnection of Munmorah Power Station | PS Replacement | Input_Proj_Future | 2015 | 2013 | 0 | 0 | 0 | 0 | 0 | 1875568.2969 | 0 | 0 | 0 | 1875568.2969 | 0 | 0 | 0 | 0
8023 | Oil Containment | Beryl Oil Containment Upgrade | PS Replacement | Input_Proj_Future | 2016 | 2013 | 0 | 0 | 0 | 0 | 100125.8828 | 1111646.2861 | 380542.6857 | 0 | 0 | 0 | 1592314.8547 | 0 | 0 | 0
8025 | Oil Containment | Deniliquin Oil Containment Upgrade | PS Replacement | Input_Proj_Future | 2016 | 2013 | 0 | 0 | 0 | 0 | 103943.5449 | 1154030.1582 | 395051.5516 | 0 | 0 | 0 | 1653025.2547 | 0 | 0 | 0
8026 | Oil Containment | Murrumburrah Oil Containment Upgrade | PS Replacement | Input_Proj_Future | 2016 | 2013 | 0 | 0 | 0 | 0 | 90256.9844 | 1002078.6631 | 343035.2105 | 0 | 0 | 0 | 1435370.858 | 0 | 0 | 0
8027 | Oil Containment | Muswellbrook Oil Containment Upgrade | PS Replacement | Input_Proj_Future | 2016 | 2013 | 0 | 0 | 0 | 0 | 15250.0625 | 958578.0039 | 249064.4201 | 0 | 0 | 0 | 1222892.4865 | 0 | 0 | 0
8078 | Oil Containment | Inverell Oil Containment Upgrade | PS Replacement | Input_Proj_Future | 2016 | 2013 | 0 | 0 | 0 | 0 | 54740.0664 | 930404.7074 | 428913.9777 | 0 | 0 | 0 | 1414058.7516 | 0 | 0 | 0
8024 | Oil Containment | Panorama Oil Containment Upgrade | PS Replacement | Input_Proj_Future | 2017 | 2013 | 0 | 0 | 0 | 0 | 0 | 70286.9781 | 1114804.2719 | 381624.168 | 0 | 0 | 0 | 1566715.418 | 0 | 0
8029 | Oil Containment | Mount Piper 132 Oil Containment Upgrade | PS Replacement | Input_Proj_Future | 2017 | 2013 | 0 | 0 | 0 | 0 | 0 | 44385.4428 | 1092954.8725 | 503571.5563 | 0 | 0 | 0 | 1640911.8715 | 0 | 0
8079 | Oil Containment | Dapto Oil Containment Upgrade | PS Replacement | Input_Proj_Future | 2017 | 2013 | 0 | 0 | 0 | 0 | 0 | 18021.3414 | 1654784.5289 | 429853.5199 | 0 | 0 | 0 | 2102659.3902 | 0 | 0
8094 | Oil Containment | Yass Oil Containment Upgrade | PS Replacement | Input_Proj_Future | 2017 | 2013 | 0 | 0 | 0 | 0 | 0 | 8572.602 | 769791.9879 | 200012.9688 | 0 | 0 | 0 | 978377.5586 | 0 | 0
P0001472 | Oil Containment | Mount Piper 500 Oil Containment Upgrade | PS Replacement | Input_Proj_Future | 2017 | 2013 | 0 | 0 | 0 | 0 | 0 | 57974.2201 | 1281624.8867 | 159157.2938 | 0 | 0 | 0 | 1498756.4006 | 0 | 0
8032 | Oil Containment | Sydney South Oil Containment Upgrade | PS Replacement | Input_Proj_Future | 2018 | 2013 | 0 | 0 | 0 | 0 | 0 | 0 | 26511.8055 | 2380708.3986 | 618572.5287 | 0 | 0 | 0 | 3025792.7328 | 0
P0002051 | Protection Change | Sydney North Lines 926 and 927 Protection Relay Replacement | PS Replacement | Input_Proj_Future | 2014 | 2013 | 0 | 0 | 0 | 0 | 638630.334 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P0002053 | Protection Change | Sydney South Lines 91J and 91F Protection Relay Replacement | PS Replacement | Input_Proj_Future | 2014 | 2013 | 0 | 0 | 0 | 0 | 507097.5156 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7346 | Reactor Replacement | Buronga X2 220kV Reactor | PS Replacement | Input_Proj_Future | 2016 | 2013 | 0 | 0 | 0 | 0 | 327921.6328 | 2832213.8988 | 598767.9305 | 0 | 0 | 0 | 3758903.4621 | 0 | 0 | 0
7342 | Reactor Replacement | Broken Hill No.1 & No.2 220kV Reactors | PS Replacement | Input_Proj_Future | 2018 | 2013 | 0 | 0 | 0 | 0 | 0 | 0 | 185202.2102 | 3684941.3795 | 2846521.743 | 0 | 0 | 0 | 6716665.3326 | 0
7325 | Reactor Replacement | Beaconsfield West No.1 132kV Reactor | PS Replacement | Input_Proj_Future | 2019 | 2013 | 0 | 0 | 0 | 0 | 0 | 0 | 9946.6104 | 67863.9104 | 262441.3682 | 0 | 0 | 0 | 0 | 0
0588B | Secondary System Renewal | Molong SCADA Remediation | PS Replacement | Input_Proj_Future | 2015 | 2013 | 0 | 0 | 0 | 0 | 175202.7969 | 91117.5795 | 0 | 0 | 0 | 266320.3764 | 0 | 0 | 0 | 0
7062 | Secondary System Renewal | Kangaroo Valley Secondary System Replacement | PS Replacement | Input_Proj_Future | 2016 | 2013 | 0 | 0 | 0 | 0 | 0 | 644383.2801 | 4012928.7844 | 0 | 0 | 0 | 4657312.0645 | 0 | 0 | 0
7350 | Secondary System Renewal | Albury Secondary System Replacement | PS Replacement | Input_Proj_Future | 2016 | 2013 | 0 | 0 | 0 | 0 | 1332245.707 | 5356252.9166 | 1600158.5086 | 0 | 0 | 0 | 8288657.1322 | 0 | 0 | 0
7353 | Secondary System Renewal | Balranald Secondary System Replacement | PS Replacement | Input_Proj_Future | 2016 | 2013 | 0 | 0 | 0 | 0 | 0 | 459478.6396 | 2881039.1107 | 0 | 0 | 0 | 3340517.7504 | 0 | 0 | 0
7366 | Secondary System Renewal | Hume Secondary System Replacement | PS Replacement | Input_Proj_Future | 2017 | 2013 | 0 | 0 | 0 | 0 | 0 | 13804.9297 | 862664.7244 | 2059511.7799 | 0 | 0 | 0 | 2935981.434 | 0 | 0
7365 | Secondary System Renewal | Deniliquin Secondary System Replacement | PS Replacement | Input_Proj_Future | 2018 | 2013 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 615581.7008 | 3726815.8525 | 0 | 0 | 0 | 4342397.5533 | 0
7655 | Secondary System Renewal | Haymarket Secondary System Replacement | PS Replacement | Input_Proj_Future | 2018 | 2013 | 0 | 0 | 0 | 0 | 0 | 0 | 752318.2324 | 2945756.5635 | 2889424.3807 | 0 | 0 | 0 | 6587499.1766 | 0
7675 | Secondary System Renewal | ANM Secondary System Replacement | PS Replacement | Input_Proj_Future | 2018 | 2013 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 959634.9889 | 2636266.0352 | 0 | 0 | 0 | 3595901.024 | 0
8075 | Secondary System Renewal | Taree Secondary System Replacement | PS Replacement | Input_Proj_Future | 2018 | 2013 | 0 | 0 | 0 | 0 | 560721.8242 | 2126585.2932 | 5195223.023 | 7153218.8547 | 3770691.1758 | 0 | 0 | 0 | 18806440.1709 | 0
7467 | Secondary System Renewal | Murrumburrah Secondary System Replacement | PS Replacement | Input_Proj_Future | 2019 | 2013 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 498966.7908 | 0 | 0 | 0 | 0 | 0
7638 | Secondary System Renewal | Sydney North Secondary System Replacement | PS Replacement | Input_Proj_Future | 2019 | 2013 | 0 | 0 | 0 | 0 | 1107547.1113 | 9604800.0043 | 12218042.2123 | 4091256.6297 | 1042767.9008 | 0 | 0 | 0 | 0 | 0
7756 | Secondary System Renewal | Armidale Secondary System Replacement | PS Replacement | Input_Proj_Future | 2019 | 2013 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 144496.4008 | 3334632.6426 | 0 | 0 | 0 | 0 | 0
7351 | Secondary System Renewal | Beryl Secondary System Replacement | PS Replacement | Input_Proj_Future | 2020 | 2013 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7354 | Secondary System Renewal | Buronga Secondary System Replacement | PS Replacement | Input_Proj_Future | 2020 | 2013 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 306532.8438 | 0 | 0 | 0 | 0 | 0
7651 | Secondary System Renewal | Liddell Secondary System Replacement | PS Replacement | Input_Proj_Future | 2020 | 2013 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 349027.674 | 2364867.3139 | 0 | 0 | 0 | 0 | 0
7667 | Secondary System Renewal | Avon Secondary System Replacement | PS Replacement | Input_Proj_Future | 2021 | 2013 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8193 | Secondary System Renewal | Sydney South Secondary System Replacement | PS Replacement | Input_Proj_Future | 2022 | 2013 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 502807.0975 | 2942642.5287 | 0 | 0 | 0 | 0 | 0
P0001205 | Substation Minor Projects | Cowra Duplicated DC & AC Supplies | PS Replacement | Input_Proj_Future | 2014 | 2013 | 0 | 0 | 0 | 139485.166 | 332748.0059 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8083 | Substation Minor Projects | Dapto 415V AC System Replacement | PS Replacement | Input_Proj_Future | 2015 | 2013 | 0 | 0 | 0 | 0 | 58484.6484 | 2524516.7145 | 0 | 0 | 0 | 2583001.3629 | 0 | 0 | 0 | 0
6040 | Substation Minor Projects | Sydney West 132kV Disconnector Replacement | PS Replacement | Input_Proj_Future | 2016 | 2013 | 0 | 0 | 0 | 504559.2695 | 552035.5879 | 2520308.9488 | 376349.3303 | 0 | 0 | 0 | 3953253.1365 | 0 | 0 | 0
P0002049 | Substation Minor Projects | Sydney South AC System Replacement | PS Replacement | Input_Proj_Future | 2017 | 2013 | 0 | 0 | 0 | 0 | 0 | 0 | 430217.3764 | 3562870.7844 | 0 | 0 | 0 | 3993088.1607 | 0 | 0
6962 | Substation Renewal | Burrinjuck Substation Renewal | PS Replacement | Input_Proj_Future | 2017 | 2013 | 0 | 0 | 0 | 0 | 0 | 354508.577 | 2268427.3432 | 6966256.4439 | 0 | 0 | 0 | 9589192.3641 | 0 | 0
7378 | Substation Renewal | Vales Point Substation Renewal | PS Replacement | Input_Proj_Future | 2018 | 2013 | 0 | 0 | 0 | 0 | 175335.5762 | 992845.3555 | 1990117.5109 | 17805757.5432 | 10889311.9658 | 0 | 0 | 0 | 31853367.9516 | 0
8076 | Substation Renewal | Taree Substation 33kV Switchyard Renewal | PS Replacement | Input_Proj_Future | 2018 | 2013 | 0 | 0 | 0 | 0 | 0 | 312352.3854 | 982291.357 | 4457745.09 | 511335.0279 | 0 | 0 | 0 | 6263723.8604 | 0
7398 | Substation Renewal | Canberra Substation Renewal | PS Replacement | Input_Proj_Future | 2019 | 2013 | 0 | 0 | 0 | 91097.9199 | 482194.707 | 1171490.224 | 1966918.6004 | 7439450.6703 | 22781635.6523 | 0 | 0 | 0 | 0 | 0
6914 | Substation Renewal | Wagga 132 Substation Renewal | PS Replacement | Input_Proj_Future | 2020 | 2013 | 0 | 0 | 0 | 0 | 0 | 0 | 382575.9588 | 1239900.9998 | 5076916.3607 | 0 | 0 | 0 | 0 | 0
7678 | Substation Renewal | Munmorah Substation Renewal | PS Replacement | Input_Proj_Future | 2020 | 2013 | 0 | 0 | 0 | 0 | 19507.2344 | 162757.6713 | 469885.6545 | 1091926.7078 | 3595333.9844 | 0 | 0 | 0 | 0 | 0
7657 | Substation Renewal | Newcastle Substation Renewal | PS Replacement | Input_Proj_Future | 2021 | 2013 | 0 | 0 | 0 | 0 | 0 | 21483.3814 | 479861.8057 | 1117282.8188 | 1756858.1502 | 0 | 0 | 0 | 0 | 0
7091 | SVC Control System Replacement | Armidale SVC Control System Replacement | PS Replacement | Input_Proj_Future | 2018 | 2013 | 0 | 0 | 0 | 0 | 0 | 0 | 24904.3525 | 1434755.1326 | 5008886.7336 | 0 | 0 | 0 | 6468546.2188 | 0
7363 | Transformer Replacement | Forbes No.1 & No.2 132kV Transformers | PS Replacement | Input_Proj_Future | 2018 | 2013 | 0 | 0 | 0 | 0 | 26502.3359 | 378955.407 | 2272150.9275 | 2849078.8252 | 479024.5756 | 0 | 0 | 0 | 6005712.0713 | 0
7528 | Transformer Replacement | Tamworth 330 No.2 330kV Transformer | PS Replacement | Input_Proj_Future | 2018 | 2013 | 0 | 0 | 0 | 0 | 92390.7168 | 301192.4398 | 489356.6576 | 5826352.5619 | 1234982.8135 | 0 | 0 | 0 | 7944275.1896 | 0
7356, 7357, 7563 | Transformer Replacement | Beaconsfield West No.1 & No.2 330kV Transformers | PS Replacement | Input_Proj_Future | 2018 | 2013 | 0 | 0 | 0 | 0 | 1241221.8965 | 654965.3783 | 6401484.2336 | 15379285.3703 | 2673637.3344 | 0 | 0 | 0 | 26350594.2131 | 0
7711 | Transmission Line Wood Pole Replacement | Line 970 Burrinjuck to Yass Pole Replacements | PS Replacement | Input_Proj_Future | 2016 | 2013 | 0 | 0 | 0 | 0 | 23036.6934 | 196898.934 | 9350749.6701 | 0 | 0 | 0 | 9570685.2975 | 0 | 0 | 0
7699 | Transmission Line Wood Pole Replacement | Line 99F Uranquinty to Yanco Pole Replacements | PS Replacement | Input_Proj_Future | 2018 | 2013 | 0 | 0 | 0 | 0 | 0 | 63803.1283 | 226091.0285 | 527998.2121 | 18612590.8377 | 0 | 0 | 0 | 19430483.2066 | 0
6002H | Wallerawang to Orange Transmission Line Replacement | New 66kV Capacitor at Panorama | PS Replacement | Input_Proj_Future | 2016 | 2013 | 0 | 0 | 0 | 0 | 0 | 86827.676 | 1108722.4654 | 0 | 0 | 0 | 1195550.1414 | 0 | 0 | 0
6002I | Wallerawang to Orange Transmission Line Replacement | New 66kV Capacitor at Orange | PS Replacement | Input_Proj_Future | 2016 | 2013 | 0 | 0 | 0 | 0 | 0 | 91706.9549 | 1171029.099 | 0 | 0 | 0 | 1262736.0539 | 0 | 0 | 0
6002J | Wallerawang to Orange Transmission Line Replacement | New 132kV Capacitor at Orange North | PS Replacement | Input_Proj_Future | 2016 | 2013 | 0 | 0 | 0 | 0 | 0 | 92181.049 | 1177089.2902 | 0 | 0 | 0 | 1269270.3393 | 0 | 0 | 0
6002K | Wallerawang to Orange Transmission Line Replacement | New Series Reactor on Line 94X at Wallerawang | PS Replacement | Input_Proj_Future | 2016 | 2013 | 0 | 0 | 0 | 0 | 0 | 121590.0164 | 1552617.9621 | 0 | 0 | 0 | 1674207.9785 | 0 | 0 | 0
6002L | Wallerawang to Orange Transmission Line Replacement | New Series Reactor on Line 949 at Mt Piper | PS Replacement | Input_Proj_Future | 2019 | 2013 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 121590.0164 | 0 | 0 | 0 | 0 | 0
7839 | Cable Remediation | Sydney South 330kV Series Reactor Reconfiguration | PS Security/Compliance | Input_Proj_Future | 2018 | 2013 | 0 | 0 | 0 | 0 | 0 | 93372.7689 | 419350.6775 | 2425440.4057 | 3254494.1611 | 0 | 0 | 0 | 6192658.0133 | 0
7646 | Communications | Communications to Beryl and Ilford | PS Security/Compliance | Input_Proj_Future | 2017 | 2013 | 0 | 0 | 0 | 0 | 0 | 68322.1533 | 641177.0203 | 541566.0947 | 0 | 0 | 0 | 1251065.2684 | 0 | 0
7316 | Control System | Multiple Contingency System Protection Scheme | PS Security/Compliance | Input_Proj_Future | 2016 | 2013 | 0 | 0 | 0 | 0 | 0 | 630723.1725 | 4069192.5189 | 0 | 0 | 0 | 4699915.6914 | 0 | 0 | 0
P0001885 | Protection Change | Gadara Protection Change | PS Security/Compliance | Input_Proj_Future | 2014 | 2013 | 0 | 0 | 0 | 344291.5703 | 70463.6055 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6832 | Quality of Supply | Voltage Unbalance Limits | PS Security/Compliance | Input_Proj_Future | 2015 | 2013 | 0 | 0 | 0 | 0 | 132166.8652 | 687110.1139 | 0 | 0 | 0 | 819276.9791 | 0 | 0 | 0 | 0
7397 | Quality of Supply | Assessment of NER Quality of Supply Compliance | PS Security/Compliance | Input_Proj_Future | 2019 | 2013 | 0 | 0 | 0 | 0 | 0 | 0 | 362730.2916 | 876797.4852 | 876797.4852 | 0 | 0 | 0 | 0 | 0
P0002366 | SCADA | SCADA to Tenterfield | PS Security/Compliance | Input_Proj_Future | 2014 | 2013 | 0 | 0 | 0 | 124922.6738 | 532589.082 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P0002155 | Supply to ACT | Canberra Substation 330kV Bypass | PS Security/Compliance | Input_Proj_Future | 2015 | 2013 | 0 | 0 | 0 | 0 | 101062.543 | 412648.5139 | 0 | 0 | 0 | 513711.0568 | 0 | 0 | 0 | 0
6913 | Transmission Line Low Spans | Line 97K Cooma to Munyang Low Span Remediation | PS Security/Compliance | Input_Proj_Future | 2018 | 2013 | 0 | 0 | 0 | 0 | 0 | 68336.4091 | 74883.6636 | 220284.559 | 2102956.0336 | 0 | 0 | 0 | 2466460.6652 | 0
8089 | Transmission Line Low Spans | Lines 4 & 5 Yass to Marulan Low Span Remediation | PS Security/Compliance | Input_Proj_Future | 2018 | 2013 | 0 | 0 | 0 | 0 | 0 | 6880.7467 | 13952.6338 | 39184.8688 | 398785.326 | 0 | 0 | 0 | 458803.5753 | 0
8090 | Transmission Line Low Spans | Snowy to Yass/Canberra Low Span Remediation | PS Security/Compliance | Input_Proj_Future | 2019 | 2013 | 0 | 0 | 0 | 0 | 374265.7246 | 75612.7146 | 385652.5271 | 1651409.6188 | 1651409.6188 | 0 | 0 | 0 | 0 | 0
8086 | Transmission Line Low Spans | Line 96H Clarence River Crossing Conductor Height | PS Security/Compliance | Input_Proj_Future | 2023 | 2013 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total Capex | [6 empty] | 2010 | 2011 | 2012 | 2013 | 2014 | 2015 | 2016 | 2017 | 2018 | 2015 | 2016 | 2017 | 2018 | 2015
Programs Committed | [6 empty] | 84689372.7349 | 68939226.095 | 88714172.0696 | 107437303.2107 | 115996180.0592 | 40770453.9499 | 37600160.6569 | 29785728.5765 | 25910039.2535 | 40770453.9499 | 37600160.6569 | 29785728.5765 | 25910039.2535 | 0
Projects Committed | [6 empty] | 359108679.0873 | 319745587.7253 | 283979337.4166 | 387203422.3029 | 416942130.5726 | 126863227.3972 | 54263272.5465 | 8738322.0952 | 11410862.1477 | 487462486.1892 | 113415319.4935 | 91697101.1542 | 5908975.0207 | 290757882.4084
[7 empty] | 443798051.8222 | 388684813.8203 | 372693509.4861 | 494640725.5136 | 532938310.6318 | 167633681.347 | 91863433.2035 | 38524050.6717 | 37320901.4011 | 528232940.139 | 151015480.1505 | 121482829.7307 | 31819014.2742 | 290757882.4084
Programs Future | [6 empty] | 0 | 0 | 0 | 0 | 0 | 22950369.2078 | 25210471.1095 | 26462134.2528 | 27355985.53 | 22950369.2078 | 25210471.1095 | 26462134.2528 | 27355985.53 | 0
Projects Future | [6 empty] | 0 | 0 | 0 | 1235592.6719 | 16990229.8809 | 49454012.9775 | 118428142.6495 | 151840556.3678 | 146370842.5642 | 13764479.0408 | 77410370.1178 | 69777671.4295 | 223822953.1405 | 0
[7 empty] | 0 | 0 | 0 | 1235592.6719 | 16990229.8809 | 72404382.1853 | 143638613.759 | 178302690.6206 | 173726828.0941 | 36714848.2486 | 102620841.2273 | 96239805.6823 | 251178938.6705 | 0
Grand Total | [6 empty] | 443798051.8222 | 388684813.8203 | 372693509.4861 | 495876318.1855 | 549928540.5127 | 240038063.5323 | 235502046.9625 | 216826741.2923 | 211047729.4952 | 564947788.3876 | 253636321.3778 | 217722635.413 | 282997952.9447 | 290757882.4084
Check | 1.0729e-06 | [5 empty] | 2.3842e-07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Note on F4: "0" indicates commissioning year equals year capex incurred.

## Costs ($2014) Incl Real Esc
Costs (Real $2014) Including Real Escalation
[7 empty] | 443798051.8222 | 388684813.8203 | 372693509.4861 | 495876318.1855 | 549974444.9423 | 240841605.3795 | 239404964.0801 | 222989583.994 | 219100736.7362 | 565086631.7779 | 255804676.5845 | 220529437.7715 | 293202812.3637
[7 empty] | Capex Incurred | [8 empty] | Capex Commissioned |  |  |  | Real Weighted Escalators |  |  |  |  | Capex Commissioned 2015 - Transitional Adjustment
Program \ Project No. | Program \ Project Grouping | Program \ Project Name | Program \ Project Category | Committed / Future | Commissioning Date | Effective Estimate Year | 2010 | 2011 | 2012 | 2013 | 2014 | 2015 | 2016 | 2017 | 2018 | 2015 | 2016 | 2017 | 2018 | 2014 | 2015 | 2016 | 2017 | 2018 | 2015
6716 | Communications | Establishment of Gigabit Ethernet CDN Network | PS Facilities | Input_Prog_Commit | 0 | 2013 | -0.95875 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
5161 | Non HV Buildings & Civil Work | Building Improvements | PS Facilities | Input_Prog_Commit | 0 | 2013 | 3176428.2644 | 3751266.9669 | 5437667.0304 | 5379657.821 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
5976 | Non HV Buildings & Civil Work | HO Refurbishment | PS Facilities | Input_Prog_Commit | 0 | 2013 | -1489172.9549 | 1321.7148 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
5989 | Non HV Buildings & Civil Work | Sydney West Warehouse Extension | PS Facilities | Input_Prog_Commit | 0 | 2013 | 105053.4134 | 125229.3027 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
7332 | Non HV Buildings & Civil Work | Strategic Accomodation | PS Facilities | Input_Prog_Commit | 0 | 2013 | 0 | 495867.152 | 7097031.6907 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
7332 | Non HV Buildings & Civil Work | Strategic Accomodation | PS Facilities | Input_Prog_Commit | 0 | 2014 | 0 | 0 | 0 | 0 | 37683457.2129 | 8612015 | 10973300 | 4832700 | 0 | 8612015 | 10973300 | 4832700 | 0 | 100% | 100% | 100% | 100% | 100% | 0
7332 | Non HV Buildings & Civil Work | Strategic Accomodation | PS Facilities | Input_Prog_Commit | 0 | 2013 | 0 | 0 | 0 | 15821291.5373 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
7517 | Non HV Buildings & Civil Work | Newcastle Mezzanine Floor | PS Facilities | Input_Prog_Commit | 0 | 2013 | 0 | 37786.7814 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
8050 | Non HV Buildings & Civil Work | Haymarket Blast Wall | PS Facilities | Input_Prog_Commit | 0 | 2014 | 0 | 0 | 0 | 0 | 54078 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
6420 | Information Technology | Video Conferencing & Collaboration | PS Information Technology | Input_Prog_Commit | 0 | 2013 | 535999.4642 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
ICT Applications | Information Technology | Capital Program Delivery | PS Information Technology | Input_Prog_Commit | 0 | 2013 | 2751280.9244 | 921492.1505 | 24215.0562 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
ICT Applications | Information Technology | Finance & Information Systems | PS Information Technology | Input_Prog_Commit | 0 | 2013 | 2756032.4549 | 9699521.7623 | 12561855.3489 | 20205852.7728 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
ICT Applications | Information Technology | Network Planning & Performance | PS Information Technology | Input_Prog_Commit | 0 | 2013 | 796284.204 | 397105.0263 | 11889.168 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
ICT Applications | Information Technology | Network Services & Operations | PS Information Technology | Input_Prog_Commit | 0 | 2013 | 100989.7611 | 275091.9742 | 74437.0408 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
ICT Applications | Information Technology | People, Strategy & Corporate Services | PS Information Technology | Input_Prog_Commit | 0 | 2013 | 75374.187 | 82476.5715 | 3569.4737 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
ICT Applications | Information Technology | 0 | PS Information Technology | Input_Prog_Commit | 0 | 2013 | 0 | 0 | 0 | 0 | 12678878.9062 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
ICT Corporate Data Network | Information Technology | Finance & Information Systems | PS Information Technology | Input_Prog_Commit | 0 | 2013 | 2295633.9998 | 1062437.5534 | 1090310.5288 | 808265.4088 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
ICT Corporate Data Network | Information Technology | 0 | PS Information Technology | Input_Prog_Commit | 0 | 2013 | 0 | 0 | 0 | 0 | 1832148.4375 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
ICT Infrastructure | Information Technology | Finance & Information Systems | PS Information Technology | Input_Prog_Commit | 0 | 2013 | 5360875.4639 | 3361760.0439 | 6399671.3375 | 4204814.5948 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
ICT Infrastructure | Information Technology | Network Services & Operations | PS Information Technology | Input_Prog_Commit | 0 | 2013 | 332861.6708 | 81607.2456 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
ICT Infrastructure | Information Technology | 0 | PS Information Technology | Input_Prog_Commit | 0 | 2013 | 0 | 0 | 0 | 0 | 6406343.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
0 | Information Technology | Finance & Information Systems | PS Information Technology | Input_Prog_Commit | 0 | 2013 | 433374.6702 | -56615.2168 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
5739 | Motor Vehicles & Mobile Plant | TG Mobile Plant | PS Motor Vehicles | Input_Prog_Commit | 0 | 2013 | 0 | 0 | 0 | 0 | 3933867.3901 | 3004840.7773 | 1814135.7422 | 1691743.0801 | 2241067.5 | 3004840.7773 | 1814135.7422 | 1691743.0801 | 2241067.5 | 100% | 100% | 100% | 100% | 100% | 0
5777 | Motor Vehicles & Mobile Plant | TG Business Vehicles | PS Motor Vehicles | Input_Prog_Commit | 0 | 2013 | 0 | 0 | 0 | 0 | 9607279.2614 | 5975616.9026 | 5926537.0117 | 7578927.2318 | 8365785.2312 | 5975616.9026 | 5926537.0117 | 7578927.2318 | 8365785.2312 | 100% | 100% | 100% | 100% | 100% | 0
0 | Motor Vehicles & Mobile Plant | Capital Program Delivery | PS Motor Vehicles | Input_Prog_Commit | 0 | 2013 | -461.4051 | 77697.5781 | 88689.5528 | 154015.3844 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
0 | Motor Vehicles & Mobile Plant | Finance & Information Systems | PS Motor Vehicles | Input_Prog_Commit | 0 | 2013 | 2168.12 | 61074.63 | 13501.35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
0 | Motor Vehicles & Mobile Plant | Network Planning & Performance | PS Motor Vehicles | Input_Prog_Commit | 0 | 2013 | 0 | 19300.3152 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
0 | Motor Vehicles & Mobile Plant | Network Services & Operations | PS Motor Vehicles | Input_Prog_Commit | 0 | 2013 | 1163236.046 | 2521138.2842 | 3512969.0898 | 1539948.7072 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
0 | Motor Vehicles & Mobile Plant | People, Strategy & Corporate Services | PS Motor Vehicles | Input_Prog_Commit | 0 | 2013 | 20385.8552 | 74027.8271 | 207040.3656 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
0 | Motor Vehicles & Mobile Plant | People, Strategy & Corporate Services | PS Motor Vehicles | Input_Prog_Commit | 0 | 2013 | 12434050.0119 | 7888970.1075 | 10005081.8451 | 8552898.6741 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
6424 | Cables | 42 Tunnel (Sydney Park) Water Treatment Plant | PS Network Asset Replacement | Input_Prog_Commit | 0 | 2013 | 117864.1216 | -155605.3712 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
0 | Cables | Network Asset Replacement | PS Network Asset Replacement | Input_Prog_Commit | 0 | 2013 | 117159.6339 | 52343.7514 | 32823.3203 | 23598.3674 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
4967 | Communications | Installation of PLC Voice Equipment | PS Network Asset Replacement | Input_Prog_Commit | 0 | 2014 | 0 | 0 | 0 | 0 | 294643.72 | 616030.3382 | 410686.8921 | 359351.0306 | 0 | 616030.3382 | 410686.8921 | 359351.0306 | 0 | 100% | 100% | 100% | 100% | 100% | 0
4968 | Communications | Installation of PLC Intertrips | PS Network Asset Replacement | Input_Prog_Commit | 0 | 2014 | 0 | 0 | 0 | 0 | 231724.2 | 214601.9484 | 321902.9226 | 107300.9742 | 160951.4613 | 214601.9484 | 321902.9226 | 107300.9742 | 160951.4613 | 100% | 100% | 100% | 100% | 100% | 0
4969 | Communications | Installation of VF Intertrips | PS Network Asset Replacement | Input_Prog_Commit | 0 | 2014 | 0 | 0 | 0 | 0 | 214381.8 | 49609.466 | 198437.864 | 173633.131 | 148828.398 | 49609.466 | 198437.864 | 173633.131 | 148828.398 | 100% | 100% | 100% | 100% | 100% | 0
7425 | Communications | SSZ Upgrade Work | PS Network Asset Replacement | Input_Prog_Commit | 0 | 2014 | 0 | 0 | 0 | 0 | 150921.55 | 64383.7393 | 32191.8696 | 72431.7067 | 24143.9022 | 64383.7393 | 32191.8696 | 72431.7067 | 24143.9022 | 100% | 100% | 100% | 100% | 100% | 0
0 | Communications | Network Asset Replacement | PS Network Asset Replacement | Input_Prog_Commit | 0 | 2013 | 1354698.018 | 1462555.1067 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
0 | Communications | Network Asset Replacement | PS Network Asset Replacement | Input_Prog_Commit | 0 | 2013 | 0 | 0 | 373094.5228 | 3282824.4574 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
4978 | Controls & Alarms | Installation of RTU Equipment | PS Network Asset Replacement | Input_Prog_Commit | 0 | 2014 | 0 | 0 | 0 | 0 | 4256648.5 | 1720008.344 | 2408011.6816 | 630669.7261 | 802670.5605 | 1720008.344 | 2408011.6816 | 630669.7261 | 802670.5605 | 100% | 100% | 100% | 100% | 100% | 0
0 | Controls & Alarms | Network Asset Replacement | PS Network Asset Replacement | Input_Prog_Commit | 0 | 2013 | 1844593.3641 | 2639624.8859 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
0 | Controls & Alarms | Network Asset Replacement | PS Network Asset Replacement | Input_Prog_Commit | 0 | 2013 | 0 | 0 | 3540662.4348 | 2649015.362 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
5071 | HV Buildings & Civil Work | Perimeter Security Fence | PS Network Asset Replacement | Input_Prog_Commit | 0 | 2014 | 0 | 0 | 0 | 0 | 104325 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
5077 | HV Buildings & Civil Work | Switchyard Security Fence | PS Network Asset Replacement | Input_Prog_Commit | 0 | 2014 | 0 | 0 | 0 | 0 | 6140 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
5098 | HV Buildings & Civil Work | Fire Protection Systems | PS Network Asset Replacement | Input_Prog_Commit | 0 | 2014 | 0 | 0 | 0 | 0 | 10000 | 0 | 185243.8 | 185243.8 | 0 | 0 | 185243.8 | 185243.8 | 0 | 100% | 100% | 100% | 100% | 100% | 0
5161 | HV Buildings & Civil Work | Depot Building Improvements and Upgrades | PS Network Asset Replacement | Input_Prog_Commit | 0 | 2014 | 0 | 0 | 0 | 0 | 5503690.66 | 605500 | 0 | 140000 | 0 | 605500 | 0 | 140000 | 0 | 100% | 100% | 100% | 100% | 100% | 0
5201 | HV Buildings & Civil Work | Substations Building and Property | PS Network Asset Replacement | Input_Prog_Commit | 0 | 2014 | 0 | 0 | 0 | 0 | 5746712.86 | 2767571.3753 | 797354.6093 | 633792.9637 | 338151.9137 | 2767571.3753 | 797354.6093 | 633792.9637 | 338151.9137 | 100% | 100% | 100% | 100% | 100% | 0
5949 | HV Buildings & Civil Work | Air Conditioning in Relay Rooms | PS Network Asset Replacement | Input_Prog_Commit | 0 | 2014 | 0 | 0 | 0 | 0 | 628112.28 | 486190.586 | 0 | 0 | 0 | 486190.586 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
6337 | HV Buildings & Civil Work | Security Fence Replace D-Pales | PS Network Asset Replacement | Input_Prog_Commit | 0 | 2014 | 0 | 0 | 0 | 0 | 54145 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
0 | HV Buildings & Civil Work | Network Asset Replacement | PS Network Asset Replacement | Input_Prog_Commit | 0 | 2013 | 1789164.4883 | 1243690.1421 | 4896134.579 | 4958289.4833 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
5651 | IT | SCADA Upgrade | PS Network Asset Replacement | Input_Prog_Commit | 0 | 2014 | 0 | 0 | 0 | 0 | 3390986.24 | 1414000 | 0 | 0 | 0 | 1414000 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
8238 | IT | SCADA Facilities Augmentation | PS Network Asset Replacement | Input_Prog_Commit | 0 | 2014 | 0 | 0 | 0 | 0 | 776869.15 | 350000 | 0 | 0 | 0 | 350000 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
5923 | Metering | Replacement of Siements 7EC Meters | PS Network Asset Replacement | Input_Prog_Commit | 0 | 2014 | 0 | 0 | 0 | 0 | 301214.46 | 0 | 0 | 225716.0873 | 0 | 0 | 0 | 225716.0873 | 0 | 100% | 100% | 100% | 100% | 100% | 0
5925 | Metering | Replacement of Email A1R-AL Meters | PS Network Asset Replacement | Input_Prog_Commit | 0 | 2014 | 0 | 0 | 0 | 0 | 339838 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
5926 | Metering | Replacement of CEWE CEP/CEQ Meters | PS Network Asset Replacement | Input_Prog_Commit | 0 | 2014 | 0 | 0 | 0 | 0 | 525100.06 | 309705.3178 | 0 | 0 | 0 | 309705.3178 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
5927 | Metering | Replacement of Ferrari Disc Pulsing Meters | PS Network Asset Replacement | Input_Prog_Commit | 0 | 2014 | 0 | 0 | 0 | 0 | 91317.93 | 213232.133 | 142154.7553 | 244822.0786 | 157949.7281 | 213232.133 | 142154.7553 | 244822.0786 | 157949.7281 | 100% | 100% | 100% | 100% | 100% | 0
6296 | Metering | Upgrade Site Metering Schemes | PS Network Asset Replacement | Input_Prog_Commit | 0 | 2014 | 0 | 0 | 0 | 0 | 213620.2 | 338574.1309 | 451432.1746 | 42014.847 | 565984.7665 | 338574.1309 | 451432.1746 | 42014.847 | 565984.7665 | 100% | 100% | 100% | 100% | 100% | 0
0 | Metering | Network Asset Replacement | PS Network Asset Replacement | Input_Prog_Commit | 0 | 2013 | 1260039.5381 | 749122.9255 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
0 | Metering | Network Asset Replacement | PS Network Asset Replacement | Input_Prog_Commit | 0 | 2013 | 0 | 0 | 1782065.5039 | 3104047.5812 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
4946 | Protection | Replacement of H-Type Relays - Key Metro Sites | PS Network Asset Replacement | Input_Prog_Commit | 0 | 2014 | 0 | 0 | 0 | 0 | 16250.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
4947 | Protection | Replacement of H-Type Relays - Remaining Sites | PS Network Asset Replacement | Input_Prog_Commit | 0 | 2014 | 0 | 0 | 0 | 0 | -11273.55 | 0 | 0 | 0 | 53666.7779 | 0 | 0 | 0 | 53666.7779 | 100% | 100% | 100% | 100% | 100% | 0
4954 | Protection | Replacement of CSD IMS Fault Recorders | PS Network Asset Replacement | Input_Prog_Commit | 0 | 2014 | 0 | 0 | 0 | 0 | 143294.98 | 0 | 0 | 75548.3354 | 151096.6708 | 0 | 0 | 75548.3354 | 151096.6708 | 100% | 100% | 100% | 100% | 100% | 0
4957 | Protection | Replacement of TS Relays | PS Network Asset Replacement | Input_Prog_Commit | 0 | 2014 | 0 | 0 | 0 | 0 | 74092 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
4960 | Protection | Replacement of THS Relays | PS Network Asset Replacement | Input_Prog_Commit | 0 | 2014 | 0 | 0 | 0 | 0 | 447256.73 | 437187.8645 | 105443.2979 | 160220.8008 | 0 | 437187.8645 | 105443.2979 | 160220.8008 | 0 | 100% | 100% | 100% | 100% | 100% | 0
4961 | Protection | Replacement of THR Relays | PS Network Asset Replacement | Input_Prog_Commit | 0 | 2014 | 0 | 0 | 0 | 0 | 95573.85 | 0 | 1676638.1969 | 695827.8889 | 581578.9005 | 0 | 1676638.1969 | 695827.8889 | 581578.9005 | 100% | 100% | 100% | 100% | 100% | 0
4962 | Protection | Replacement of YTG Relays | PS Network Asset Replacement | Input_Prog_Commit | 0 | 2014 | 0 | 0 | 0 | 0 | 953174.56 | 894827.3543 | 1361313.1876 | 1115177.9936 | 710336.0258 | 894827.3543 | 1361313.1876 | 1115177.9936 | 710336.0258 | 100% | 100% | 100% | 100% | 100% | 0
5150 | Protection | Replacement of RAZFE Relays | PS Network Asset Replacement | Input_Prog_Commit | 0 | 2014 | 0 | 0 | 0 | 0 | 515695.39 | 0 | 214821.5198 | 104110.4618 | 104110.4618 | 0 | 214821.5198 | 104110.4618 | 104110.4618 | 100% | 100% | 100% | 100% | 100% | 0
5541 | Protection | Replacement of Optimho Relays | PS Network Asset Replacement | Input_Prog_Commit | 0 | 2014 | 0 | 0 | 0 | 0 | 28456.62 | 0 | 213055.5645 | 105722.0088 | 678178.1697 | 0 | 213055.5645 | 105722.0088 | 678178.1697 | 100% | 100% | 100% | 100% | 100% | 0
5921 | Protection | Replacement of D202,D203,D21SE,D22SE Transformer Differential Relays | PS Network Asset Replacement | Input_Prog_Commit | 0 | 2014 | 0 | 0 | 0 | 0 | 901778.34 | 219733.2407 | 137868.9318 | 273086.3383 | 126565.81 | 219733.2407 | 137868.9318 | 273086.3383 | 126565.81 | 100% | 100% | 100% | 100% | 100% | 0
5922 | Protection | Replacement of DB Transformer Differential Relays | PS Network Asset Replacement | Input_Prog_Commit | 0 | 2014 | 0 | 0 | 0 | 0 | 998355.41 | 285044.4285 | 605907.2498 | 731258.7899 | 192639.783 | 285044.4285 | 605907.2498 | 731258.7899 | 192639.783 | 100% | 100% | 100% | 100% | 100% | 0
5929 | Protection | Replacement of Feeder OC & EF Protection | PS Network Asset Replacement | Input_Prog_Commit | 0 | 2014 | 0 | 0 | 0 | 0 | 95618.82 | 195019.6416 | 104110.4618 | 52055.2309 | 260276.1544 | 195019.6416 | 104110.4618 | 52055.2309 | 260276.1544 | 100% | 100% | 100% | 100% | 100% | 0
6291 | Protection | GPS Clocks | PS Network Asset Replacement | Input_Prog_Commit | 0 | 2014 | 0 | 0 | 0 | 0 | 146990.16 | 131809.4363 | 131809.4363 | 105447.549 | 79085.6618 | 131809.4363 | 131809.4363 | 105447.549 | 79085.6618 | 100% | 100% | 100% | 100% | 100% | 0
6351 | Protection | Replacement of Siemens 7SA502 & 7SA511 Relays | PS Network Asset Replacement | Input_Prog_Commit | 0 | 2014 | 0 | 0 | 0 | 0 | 30000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
6353 | Protection | Replacement of HO2 Pilot Wire Relays | PS Network Asset Replacement | Input_Prog_Commit | 0 | 2014 | 0 | 0 | 0 | 0 | 83553.52 | 276715.1738 | 0 | 0 | 0 | 276715.1738 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
6612 | Protection | Relay Replacement For 940/941 132kV Feeders | PS Network Asset Replacement | Input_Prog_Commit | 0 | 2013 | -39.6792 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
6725 | Protection | Replacement of MBCI Pilot Wire Relays | PS Network Asset Replacement | Input_Prog_Commit | 0 | 2014 | 0 | 0 | 0 | 0 | 210249.19 | 157326.302 | 0 | 0 | 0 | 157326.302 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
6865 | Protection | Replacement of Quadramho Relays | PS Network Asset Replacement | Input_Prog_Commit | 0 | 2014 | 0 | 0 | 0 | 0 | 30000 | 155947.6967 | 488786.5879 | 107333.5558 | 1144801.984 | 155947.6967 | 488786.5879 | 107333.5558 | 1144801.984 | 100% | 100% | 100% | 100% | 100% | 0
6866 | Protection | Replacement of 7SA513 Relays | PS Network Asset Replacement | Input_Prog_Commit | 0 | 2014 | 0 | 0 | 0 | 0 | 28683.24 | 270667.1115 | 0 | 0 | 380470.3498 | 270667.1115 | 0 | 0 | 380470.3498 | 100% | 100% | 100% | 100% | 100% | 0
7576 | Protection | Remote Interrogation of Protection Relays | PS Network Asset Replacement | Input_Prog_Commit | 0 | 2014 | 0 | 0 | 0 | 0 | 86468.15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
7746 | Protection | Replacement of EDMI Fault Recorders | PS Network Asset Replacement | Input_Prog_Commit | 0 | 2014 | 0 | 0 | 0 | 0 | 29534.54 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
7747 | Protection | Install Fault Recorders | PS Network Asset Replacement | Input_Prog_Commit | 0 | 2014 | 0 | 0 | 0 | 0 | 315833.55 | 475511.4002 | 0 | 0 | 75548.3354 | 475511.4002 | 0 | 0 | 75548.3354 | 100% | 100% | 100% | 100% | 100% | 0
7750 | Protection | Replacement of 7SD511 Relays | PS Network Asset Replacement | Input_Prog_Commit | 0 | 2014 | 0 | 0 | 0 | 0 | 207431.23 | 169726.494 | 0 | 107333.5558 | 193316.1563 | 169726.494 | 0 | 107333.5558 | 193316.1563 | 100% | 100% | 100% | 100% | 100% | 0
8266 | Protection | Efficient Relay Replacements | PS Network Asset Replacement | Input_Prog_Commit | 0 | 2014 | 0 | 0 | 0 | 0 | 99286.81 | 67608.7033 | 0 | 0 | 0 | 67608.7033 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
0 | Protection | Network Asset Replacement | PS Network Asset Replacement | Input_Prog_Commit | 0 | 2013 | 4050671.1331 | 5456172.9233 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
0 | Protection | Network Asset Replacement | PS Network Asset Replacement | Input_Prog_Commit | 0 | 2013 | 0 | 0 | 7094083.4051 | 7215531.2632 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
6702 | SCADA | Data Centre Infrastructure | PS Network Asset Replacement | Input_Prog_Commit | 0 | 2014 | 0 | 0 | 0 | 0 | 63000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
7910 | SCADA | Sydney North SCADA Fibre Marshalling Kiosk | PS Network Asset Replacement | Input_Prog_Commit | 0 | 2013 | 0 | 0 | 0 | 145579.9013 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
0 | SCADA | Network Asset Replacement | PS Network Asset Replacement | Input_Prog_Commit | 0 | 2013 | 1524412.6902 | 1718729.7541 | 1549481.7592 | 900950.399 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
4882 | Substations | Transformer and Reactor Life Extension | PS Network Asset Replacement | Input_Prog_Commit | 0 | 2013 | 0 | 47253.4702 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
4882 | Substations | Transformer and Reactor Life Extension | PS Network Asset Replacement | Input_Prog_Commit | 0 | 2014 | 0 | 0 | 0 | 0 | 1229767.99 | 1672635.403 | 1357883.1598 | 1937337.6463 | 2096757.5095 | 1672635.403 | 1357883.1598 | 1937337.6463 | 2096757.5095 | 100% | 100% | 100% | 100% | 100% | 0
4884 | Substations | Unplanned Transformer and Reactor Replacement | PS Network Asset Replacement | Input_Prog_Commit | 0 | 2013 | 0 | 0 | 0 | -4602.8908 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
4904 | Substations | Replacement of ABB 132kV HLD CBs | PS Network Asset Replacement | Input_Prog_Commit | 0 | 2014 | 0 | 0 | 0 | 0 | 904575.7912 | 328900.9578 | 584375.4313 | 876563.147 | 146093.8578 | 328900.9578 | 584375.4313 | 876563.147 | 146093.8578 | 100% | 100% | 100% | 100% | 100% | 0
4905 | Substations | Replacement of DELLE 66kV HPGE CBs | PS Network Asset Replacement | Input_Prog_Commit | 0 | 2014 | 0 | 0 | 0 | 0 | 4505.17 | 42000 | 0 | 1199660 | 218120 | 42000 | 0 | 1199660 | 218120 | 100% | 100% | 100% | 100% | 100% | 0
4906 | Substations | Replacement of Instrument Transformers with No Sampling Point | PS Network Asset Replacement | Input_Prog_Commit | 0 | 2014 | 0 | 0 | 0 | 0 | 92539 | 44058.5732 | 264351.4393 | 484645.0661 | 176234.8 | 44058.5732 | 264351.4393 | 484645.0661 | 176234.8 | 100% | 100% | 100% | 100% | 100% | 0
4907 | Substations | Replacement of Substation Batteries - 50V As Required | PS Network Asset Replacement | Input_Prog_Commit | 0 | 2014 | 0 | 0 | 0 | 0 | 176623 | 115096.8 | 60468.1 | 155608.0904 | 100979.3904 | 115096.8 | 60468.1 | 155608.0904 | 100979.3904 | 100% | 100% | 100% | 100% | 100% | 0
4908 | Substations | Replacement of Substation Batteries - 110V As Required | PS Network Asset Replacement | Input_Prog_Commit | 0 | 2014 | 0 | 0 | 0 | 0 | 304594.4 | 127382.367 | 38891.7101 | 122485.1304 | 122485.1304 | 127382.367 | 38891.7101 | 122485.1304 | 122485.1304 | 100% | 100% | 100% | 100% | 100% | 0
4909 | Substations | Replacement of Substation Batteries - 240V As Required | PS Network Asset Replacement | Input_Prog_Commit | 0 | 2014 | 0 | 0 | 0 | 0 | 50122.29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
4910 | Substations | Replacement of High DGA Instrument Transformers 132kV As Required | PS Network Asset Replacement | Input_Prog_Commit | 0 | 2014 | 0 | 0 | 0 | 0 | 190208.27 | 330671.4855 | 1126394.8697 | 206914.2855 | 211114.4 | 330671.4855 | 1126394.8697 | 206914.2855 | 211114.4 | 100% | 100% | 100% | 100% | 100% | 0
4914 | Substations | Replacement of Isolators & Earth Switches > 220kV | PS Network Asset Replacement | Input_Prog_Commit | 0 | 2014 | 0 | 0 | 0 | 0 | 224045.88 | 396893.1775 | 396893.1775 | 396893.1775 | 396893.1775 | 396893.1775 | 396893.1775 | 396893.1775 | 396893.1775 | 100% | 100% | 100% | 100% | 100% | 0
4915 | Substations | Replacement of Isolators & Earth Switches 132kV | PS Network Asset Replacement | Input_Prog_Commit | 0 | 2014 | 0 | 0 | 0 | 0 | 350000 | 119078.863 | 119078.863 | 119078.863 | 119078.863 | 119078.863 | 119078.863 | 119078.863 | 119078.863 | 100% | 100% | 100% | 100% | 100% | 0
4920 | Substations | Condition Monitoring DGA | PS Network Asset Replacement | Input_Prog_Commit | 0 | 2014 | 0 | 0 | 0 | 0 | 13555.63 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
4928 | Substations | Replacement of Current Transformers | PS Network Asset Replacement | Input_Prog_Commit | 0 | 2014 | 0 | 0 | 0 | 0 | 147261.73 | 286443.5494 | 81048.3729 | 324193.4916 | 132175.7197 | 286443.5494 | 81048.3729 | 324193.4916 | 132175.7197 | 100% | 100% | 100% | 100% | 100% | 0
4929 | Substations | Replacement of Ducon CTs and CVTs | PS Network Asset Replacement | Input_Prog_Commit | 0 | 2014 | 0 | 0 | 0 | 0 | 856591.48 | 370258.7 | 0 | 0 | 0 | 370258.7 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
5085 | Substations | Replacement of High DGA Instrument Transformers > 220kV As Required | PS Network Asset Replacement | Input_Prog_Commit | 0 | 2014 | 0 | 0 | 0 | 0 | 839312.3 | 702276.226 | 842730 | 702275 | 978985.616 | 702276.226 | 842730 | 702275 | 978985.616 | 100% | 100% | 100% | 100% | 100% | 0
5087 | Substations | Replacement of High DGA Instrument Transformers < 66kV As Required | PS Network Asset Replacement | Input_Prog_Commit | 0 | 2014 | 0 | 0 | 0 | 0 | -5656.23 | 109117.4 | 169308.3 | 126719.6 | 128189.6 | 109117.4 | 169308.3 | 126719.6 | 128189.6 | 100% | 100% | 100% | 100% | 100% | 0
5517 | Substations | Replacement of Merlin Gerin FA2 CBs | PS Network Asset Replacement | Input_Prog_Commit | 0 | 2014 | 0 | 0 | 0 | 0 | 3244920.67 | 1964249.1353 | 1415207.5451 | 283041.5451 | 1415207.5902 | 1964249.1353 | 1415207.5451 | 283041.5451 | 1415207.5902 | 100% | 100% | 100% | 100% | 100% | 0
5519 | Substations | Replacement of Sprecher & Schuh CBs | PS Network Asset Replacement | Input_Prog_Commit | 0 | 2014 | 0 | 0 | 0 | 0 | 253771.94 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
5916 | Substations | Replacement of CBs Approaching Rated Operations | PS Network Asset Replacement | Input_Prog_Commit | 0 | 2014 | 0 | 0 | 0 | 0 | 1080000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
6103 | Substations | Sydney South Substation 330kV Bus Coupling | PS Network Asset Replacement | Input_Prog_Commit | 0 | 2013 | 3510.5111 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
6338 | Substations | Security Fence Disturbance Detection | PS Network Asset Replacement | Input_Prog_Commit | 0 | 2014 | 0 | 0 | 0 | 0 | 20589.44 | 0 | 70000 | 0 | 0 | 0 | 70000 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
6340 | Substations | Security Lighting Upgrade | PS Network Asset Replacement | Input_Prog_Commit | 0 | 2014 | 0 | 0 | 0 | 0 | 63189.1 | 87500 | 748330.1 | 417601.8 | 877265.9 | 87500 | 748330.1 | 417601.8 | 877265.9 | 100% | 100% | 100% | 100% | 100% | 0
7308 | Substations | Replacment of Capacitor CBs | PS Network Asset Replacement | Input_Prog_Commit | 0 | 2013 | 273.146 | -184.0394 | 0 | -8931.9405 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
7469 | Substations | Liddell 330kV 84 Line Connection | PS Network Asset Replacement | Input_Prog_Commit | 0 | 2014 | 0 | 0 | 0 | 0 | 23136.18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
7753 | Substations | SF6 CT Monitoring | PS Network Asset Replacement | Input_Prog_Commit | 0 | 2014 | 0 | 0 | 0 | 0 | 29321.77 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
8273 | Substations | Online Condition Monitoring | PS Network Asset Replacement | Input_Prog_Commit | 0 | 2014 | 0 | 0 | 0 | 0 | 126699 | 42155.4059 | 179055.8309 | 370242.5678 | 88252.9962 | 42155.4059 | 179055.8309 | 370242.5678 | 88252.9962 | 100% | 100% | 100% | 100% | 100% | 0
0 | Substations | Network Asset Replacement | PS Network Asset Replacement | Input_Prog_Commit | 0 | 2013 | -6.2123 | 32684.6998 | 0 | 2996.2355 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
0 | Substations | Network Asset Replacement | PS Network Asset Replacement | Input_Prog_Commit | 0 | 2013 | 5012978.4424 | 3968740.8489 | 5769012.3047 | 5976048.9243 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
0 | Substations | Network Asset Replacement | PS Network Asset Replacement | Input_Prog_Commit | 0 | 2013 | 9798924.219 | 8218731.6001 | 8912663.8325 | 5018483.388 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
0 | Substations | Network Asset Replacement | PS Network Asset Replacement | Input_Prog_Commit | 0 | 2013 | 3301500.413 | 2952074.6767 | 3018495.7437 | 11497307.7605 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
0 | Substations | Network Asset Replacement | PS Network Asset Replacement | Input_Prog_Commit | 0 | 2013 | 188847.5338 | 393329.0501 | 188800.9282 | 102442.0657 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
0 | Substations | Network Asset Replacement | PS Network Asset Replacement | Input_Prog_Commit | 0 | 2013 | 6382940.6657 | 1707825.2667 | 159492.7853 | 2006169.1441 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
4939 | Transmission Lines | Aging Wood Poles | PS Network Asset Replacement | Input_Prog_Commit | 0 | 2014 | 0 | 0 | 0 | 0 | 3080503.11 | 1050000 | 0 | 0 | 0 | 1050000 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
4943 | Transmission Lines | Emergency Structures (Guyed Masts) | PS Network Asset Replacement | Input_Prog_Commit | 0 | 2013 | 122414.54 | 62959.093 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
0 | Transmission Lines | Transmission Line Minor Upgrades | PS Network Asset Replacement | Input_Prog_Commit | 0 | 2013 | 973420.7218 | 786320.6197 | 949754.4401 | 235012.7843 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
0 | Transmission Lines | Network Asset Replacement | PS Network Asset Replacement | Input_Prog_Commit | 0 | 2013 | 7670814.0006 | 3440202.9747 | 2306788.9043 | 2632685.3052 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
8165 | Misc Assets & Office Equipment | Misc Assets & Office Equipment | PS Network-Other | Input_Prog_Commit | 0 | 2014 | 0 | 0 | 0 | 0 | 2070254 | 2502731 | 1445000 | 1511000 | 1165000 | 2502731 | 1445000 | 1511000 | 1165000 | 100% | 100% | 100% | 100% | 100% | 0
4931 | Substations | CCTV | PS Security/Compliance | Input_Prog_Commit | 0 | 2013 | 1066846.8895 | 81925.5837 | 87753.5007 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
4979 | Substations | RRS Security | PS Security/Compliance | Input_Prog_Commit | 0 | 2013 | 301586.1239 | 115541.7429 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
5071 | Substations | Security Perimeter Fence | PS Security/Compliance | Input_Prog_Commit | 0 | 2013 | 2580981.4664 | 1234912.459 | 1118170.4312 | 388717.4468 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
5073 | Substations | Replace Lock & Key System | PS Security/Compliance | Input_Prog_Commit | 0 | 2013 | 90793.9127 | 51088.9858 | 3906.3317 | -17439.483 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
5077 | Substations | Security Delineation Fence | PS Security/Compliance | Input_Prog_Commit | 0 | 2013 | 1858322.5516 | 1094092.707 | 59220.3927 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
5100 | Substations | Intrusion Detection | PS Security/Compliance | Input_Prog_Commit | 0 | 2013 | 1652234.6554 | 471465.2568 | 5738.8038 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
6337 | Substations | Security Fence Replace D-Pales | PS Security/Compliance | Input_Prog_Commit | 0 | 2013 | 774032.6535 | 1578.8126 | 119339.2045 | 177511.9379 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
6338 | Substations | Fence Disturbance Detection | PS Security/Compliance | Input_Prog_Commit | 0 | 2013 | 0 | 0 | 25155.7022 | 399973.432 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
6340 | Substations | Security Lighting Upgrade | PS Security/Compliance | Input_Prog_Commit | 0 | 2013 | 0 | 233490.3981 | 193604.3604 | 80168.4539 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
7076 | Substations | Southern Region | PS Security/Compliance | Input_Prog_Commit | 0 | 2013 | 0 | 0 | 0 | 4178.9315 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
0 | Information Technology | ICT Applications | PS Information Technology | Input_Prog_Future | 0 | 2013 | 0 | 0 | 0 | 0 | 0 | 11682519.5312 | 10962011.7188 | 11064941.4062 | 10241503.9062 | 11682519.5312 | 10962011.7188 | 11064941.4062 | 10241503.9062 | 100% | 100% | 100% | 100% | 100% | 0
0 | Information Technology | ICT Corporate Data Network | PS Information Technology | Input_Prog_Future | 0 | 2013 | 0 | 0 | 0 | 0 | 0 | 2830566.4062 | 3859863.2812 | 3087890.625 | 2058593.75 | 2830566.4062 | 3859863.2812 | 3087890.625 | 2058593.75 | 100% | 100% | 100% | 100% | 100% | 0
0 | Information Technology | ICT Infrastructure | PS Information Technology | Input_Prog_Future | 0 | 2013 | 0 | 0 | 0 | 0 | 0 | 4837695.3125 | 4837695.3125 | 3962792.9688 | 8491699.2188 | 4837695.3125 | 4837695.3125 | 3962792.9688 | 8491699.2188 | 100% | 100% | 100% | 100% | 100% | 0
4907 | Communications | 50V Batteries | PS Network Asset Replacement | Input_Prog_Future | 0 | 2013 | 0 | 0 | 0 | 0 | 0 | 208846.8157 | 251212.4356 | 168125.541 | 211121.9427 | 208846.8157 | 251212.4356 | 168125.541 | 211121.9427 | 99.92% | 100.2% | 100.4% | 100.8% | 101.3% | 0
5068 | Communications | 50V Battery Chargers | PS Network Asset Replacement | Input_Prog_Future | 0 | 2013 | 0 | 0 | 0 | 0 | 0 | 60752.1142 | 122002.2593 | 102349.8299 | 144421.612 | 60752.1142 | 122002.2593 | 102349.8299 | 144421.612 | 99.87% | 100.3% | 100.7% | 101.4% | 102.2% | 0
4972 | Communications | 50V Power Systems | PS Network Asset Replacement | Input_Prog_Future | 0 | 2014 | 0 | 0 | 0 | 0 | 0 | 98189.728 | 145975.9817 | 145975.9817 | 97317.3212 | 98189.728 | 145975.9817 | 145975.9817 | 97317.3212 | 100% | 100% | 100% | 100% | 100% | 0
8222 | Communications | Hammonds Hill Radio Repeater Site Mains Power | PS Network Asset Replacement | Input_Prog_Future | 0 | 2014 | 0 | 0 | 0 | 0 | 0 | 35000 | 0 | 0 | 0 | 35000 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
8260 | Communications | CAS and BAS Equipment | PS Network Asset Replacement | Input_Prog_Future | 0 | 2014 | 0 | 0 | 0 | 0 | 0 | 201894.4301 | 190018.2871 | 201894.4301 | 201894.4301 | 201894.4301 | 190018.2871 | 201894.4301 | 201894.4301 | 100% | 100% | 100% | 100% | 100% | 0
7770 | Metering | Replacement of E1 Meters | PS Network Asset Replacement | Input_Prog_Future | 0 | 2014 | 0 | 0 | 0 | 0 | 0 | 0 | 225716.0873 | 0 | 0 | 0 | 225716.0873 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
8043 | Metering | Replacement of EDMI MK III Energy Meters | PS Network Asset Replacement | Input_Prog_Future | 0 | 2014 | 0 | 0 | 0 | 0 | 0 | 137104.8155 | 8476.1834 | 64870.0438 | 24849.8532 | 137104.8155 | 8476.1834 | 64870.0438 | 24849.8532 | 100% | 100% | 100% | 100% | 100% | 0
4949 | Protection | Replacement of D202 Relays | PS Network Asset Replacement | Input_Prog_Future | 0 | 2014 | 0 | 0 | 0 | 0 | 0 | 68934.4659 | 0 | 0 | 0 | 68934.4659 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
4956 | Protection | Replacement of TH1A Relays | PS Network Asset Replacement | Input_Prog_Future | 0 | 2014 | 0 | 0 | 0 | 0 | 0 | 60131.6994 | 0 | 0 | 0 | 60131.6994 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
5919 | Protection | Replacement of THR Relays | PS Network Asset Replacement | Input_Prog_Future | 0 | 2014 | 0 | 0 | 0 | 0 | 0 | 0 | 6464.9215 | 565226.6985 | 1250916.0603 | 0 | 6464.9215 | 565226.6985 | 1250916.0603 | 100% | 100% | 100% | 100% | 100% | 0
5920 | Protection | Replacement of YTG Relays | PS Network Asset Replacement | Input_Prog_Future | 0 | 2014 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 419228.9491 | 0 | 0 | 0 | 419228.9491 | 100% | 100% | 100% | 100% | 100% | 0
6864 | Protection | Replacement of Micromho Relays | PS Network Asset Replacement | Input_Prog_Future | 0 | 2014 | 0 | 0 | 0 | 0 | 0 | 383263.989 | 0 | 0 | 479272.9941 | 383263.989 | 0 | 0 | 479272.9941 | 100% | 100% | 100% | 100% | 100% | 0
7556 | Protection | Replacement of RADSB Transformer Differential Relays | PS Network Asset Replacement | Input_Prog_Future | 0 | 2014 | 0 | 0 | 0 | 0 | 0 | 131230.288 | 135217.4065 | 65615.144 | 137868.9318 | 131230.288 | 135217.4065 | 65615.144 | 137868.9318 | 100% | 100% | 100% | 100% | 100% | 0
7748 | Protection | Replacement of DLN90 Relays | PS Network Asset Replacement | Input_Prog_Future | 0 | 2014 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
8020 | Protection | Replacement of LFCB102 Relays | PS Network Asset Replacement | Input_Prog_Future | 0 | 2014 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 80110.4004 | 0 | 0 | 0 | 80110.4004 | 100% | 100% | 100% | 100% | 100% | 0
8261 | Protection | Secondary System Technology Upgrades | PS Network Asset Replacement | Input_Prog_Future | 0 | 2014 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2809671.6161 | 1456870.3049 | 0 | 0 | 2809671.6161 | 1456870.3049 | 100% | 100% | 100% | 100% | 100% | 0
5518 | Substations | Replacement of Merlin Gerin FA4 CBs | PS Network Asset Replacement | Input_Prog_Future | 0 | 2014 | 0 | 0 | 0 | 0 | 0 | 608783.0902 | 1521957.6353 | 1217566.1353 | 0 | 608783.0902 | 1521957.6353 | 1217566.1353 | 0 | 100% | 100% | 100% | 100% | 100% | 0
6860 | Substations | Replacement of ASEA 66kV HLR CBs | PS Network Asset Replacement | Input_Prog_Future | 0 | 2014 | 0 | 0 | 0 | 0 | 0 | 0 | 327180 | 109060 | 0 | 0 | 327180 | 109060 | 0 | 100% | 100% | 100% | 100% | 100% | 0
6861 | Substations | Replacement of Magrini 11kV MAG12MG500 CBs | PS Network Asset Replacement | Input_Prog_Future | 0 | 2014 | 0 | 0 | 0 | 0 | 0 | 109059.7589 | 0 | 0 | 0 | 109059.7589 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
6862 | Substations | Replacement of Siemens 330kV 3AQ2 CBs | PS Network Asset Replacement | Input_Prog_Future | 0 | 2014 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 566083.0451 | 0 | 0 | 0 | 566083.0451 | 100% | 100% | 100% | 100% | 100% | 0
6863 | Substations | Replacement of Siemens 330kV 3AS2 CBs | PS Network Asset Replacement | Input_Prog_Future | 0 | 2014 | 0 | 0 | 0 | 0 | 0 | 566083 | 566083 | 283041.5 | 0 | 566083 | 566083 | 283041.5 | 0 | 100% | 100% | 100% | 100% | 100% | 0
7308 | Substations | Replacement of Capacitor CBs | PS Network Asset Replacement | Input_Prog_Future | 0 | 2014 | 0 | 0 | 0 | 0 | 0 | 294409.8713 | 678089.1784 | 857940.5497 | 790815.614 | 294409.8713 | 678089.1784 | 857940.5497 | 790815.614 | 100% | 100% | 100% | 100% | 100% | 0
7799 | Substations | Replacement of Sprecher HGF215 CBs | PS Network Asset Replacement | Input_Prog_Future | 0 | 2014 | 0 | 0 | 0 | 0 | 0 | 126000 | 0 | 0 | 0 | 126000 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
8082 | Substations | Replacement of Sprecher HGF215 CBs | PS Network Asset Replacement | Input_Prog_Future | 0 | 2014 | 0 | 0 | 0 | 0 | 0 | 0 | 283041.5451 | 283041.5451 | 283041.5451 | 0 | 283041.5451 | 283041.5451 | 283041.5451 | 100% | 100% | 100% | 100% | 100% | 0
8101 | Substations | Replacement of Magrini MAG38MGE-0 CBs | PS Network Asset Replacement | Input_Prog_Future | 0 | 2014 | 0 | 0 | 0 | 0 | 0 | 0 | 536512.9545 | 670641.1931 | 268256.4773 | 0 | 536512.9545 | 670641.1931 | 268256.4773 | 100% | 100% | 100% | 100% | 100% | 0
4918 | Substations | Removal of PCB from In Service Equipment | PS Network Asset Replacement | Input_Prog_Future | 0 | 2014 | 0 | 0 | 0 | 0 | 0 | 101357.0855 | 105557.2 | 519385.6566 | 0 | 101357.0855 | 105557.2 | 519385.6566 | 0 | 100% | 100% | 100% | 100% | 100% | 0
8253 | Substations | Management of CTs with PCB Contamination | PS Network Asset Replacement | Input_Prog_Future | 0 | 2014 | 0 | 0 | 0 | 0 | 0 | 144540.9119 | 385864.5881 | 107380 | 0 | 144540.9119 | 385864.5881 | 107380 | 0 | 100% | 100% | 100% | 100% | 100% | 0
4916 | Substations | Replace Isolator and Earth Switch - 66kV and Below as Required | PS Network Asset Replacement | Input_Prog_Future | 0 | 2014 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 92142.863 | 92142.863 | 0 | 0 | 92142.863 | 92142.863 | 100% | 100% | 100% | 100% | 100% | 0
5066 | Substations | 110V Battery Chargers | PS Network Asset Replacement | Input_Prog_Future | 0 | 2014 | 0 | 0 | 0 | 0 | 0 | 65692.4278 | 43794.9519 | 65692.4278 | 65692.4278 | 65692.4278 | 43794.9519 | 65692.4278 | 65692.4278 | 100% | 100% | 100% | 100% | 100% | 0
5068 | Substations | 50V Battery Chargers | PS Network Asset Replacement | Input_Prog_Future | 0 | 2014 | 0 | 0 | 0 | 0 | 0 | 58848.8408 | 19616.2803 | 19616.2803 | 0 | 58848.8408 | 19616.2803 | 19616.2803 | 0 | 100% | 100% | 100% | 100% | 100% | 0
8274 | Substations | Fault Throwing Switches | PS Network Asset Replacement | Input_Prog_Future | 0 | 2014 | 0 | 0 | 0 | 0 | 0 | 140000 | 0 | 0 | 0 | 140000 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
6370 | Cable Minor Projects | 42 Cable Tunnel Life Extension | PS Augmentation | Input_Proj_Commit | 2011 | 2013 | 31597.4977 | 34869.7448 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
5657 | Capacitor Bank | Muswellbrook No.1 132kV Capacitor Bank Detuning | PS Augmentation | Input_Proj_Commit | 2010 | 2013 | -82.7577 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
6234 | Capacitor Bank | Capacitor Banks | PS Augmentation | Input_Proj_Commit | 2010 | 2013 | 7.1035 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
6192 | Capacitor Bank | Beryl 66kV Capacitor Bank | PS Augmentation | Input_Proj_Commit | 2011 | 2013 | 199.5183 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
6211 | Capacitor Bank | Sydney North & East 330kV 2 x 200 MVAr Capacitor Banks | PS Augmentation | Input_Proj_Commit | 2011 | 2013 | 108288.6921 | 571017.6792 | -18389.1454 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
6241 | Capacitor Bank | Sydney North & East 330kV 2 x 200 MVAr Capacitor Banks | PS Augmentation | Input_Proj_Commit | 2011 | 2013 | 0 | -505.6379 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
6258 | Capacitor Bank | Regentville 330kV Capacitor Bank | PS Augmentation | Input_Proj_Commit | 2011 | 2013 | 0 | -208.1995 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
6384 | Capacitor Bank | Sydney Area 200MVAr Capacitor Bank | PS Augmentation | Input_Proj_Commit | 2011 | 2013 | -0.2179 | -1627.4202 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
6579 | Capacitor Bank | Beryl No.2 66kV Capacitor Bank | PS Augmentation | Input_Proj_Commit | 2011 | 2013 | 2001698.0764 | 1079755.7343 | 230908.4564 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
6936 | Capacitor Bank | Capacitor Banks | PS Augmentation | Input_Proj_Commit | 2011 | 2013 | 0 | 9.6661 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
7268 | Capacitor Bank | Regentville 132kV Capacitor Bank | PS Augmentation | Input_Proj_Commit | 2011 | 2013 | 0 | 3941.3595 | 3328.4663 | -7000.791 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
7270 | Capacitor Bank | Sydney Area No.2 200MVAr Capacitor Bank | PS Augmentation | Input_Proj_Commit | 2011 | 2013 | 0 | 4874.5937 | -4502.044 | -267.6769 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
7274 | Capacitor Bank | Tumut 132kV Capacitor Bank | PS Augmentation | Input_Proj_Commit | 2011 | 2013 | 0 | 31739.4901 | 88.0155 | 0 | -29528.8914 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
7326 | Capacitor Bank | Beryl No.2 66kV Capacitor Bank | PS Augmentation | Input_Proj_Commit | 2011 | 2013 | 0 | 0 | 276.7912 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
7828 | Capacitor Bank | Port Macquarie No.3 Capacitor Bank | PS Augmentation | Input_Proj_Commit | 2012 | 2013 | 0 | 0 | 2441.7986 | 2416.1537 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
6239 | Capacitor Bank | Tamworth Capacitor Banks | PS Augmentation | Input_Proj_Commit | 2013 | 2013 | 1934.2587 | 0 | 0 | -1670.8402 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
7269 | Capacitor Bank | Sydney South 200 MVAr Capacitor Bank | PS Augmentation | Input_Proj_Commit | 2014 | 2013 | 0 | 30797.6638 | 93601.9933 | 1312592.9954 | 3788168.6367 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
6383 | Capacitor Bank | Canberra 132kV 120MVAr Capacitor Bank | PS Augmentation | Input_Proj_Commit | 2015 | 2013 | -6.5043 | -9819.4024 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -9825.9067 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
7265 | Capacitor Bank | Canberra 132kV 120MVAr Capacitor Bank | PS Augmentation | Input_Proj_Commit | 2015 | 2013 | 0 | 7144.3707 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7144.3707 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
7266 | Capacitor Bank | Canberra 132kV 120MVAr Capacitor Bank | PS Augmentation | Input_Proj_Commit | 2015 | 2013 | -5.7852 | 229.7542 | 0 | 93086.0675 | 2808718.4376 | 797334.4592 | 0 | 0 | 0 | 3699362.9332 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
7276 | Capacitor Bank | Yass 132kV 80MVAr Capacitor Bank | PS Augmentation | Input_Proj_Commit | 2015 | 2013 | -5.3167 | 4598.0507 | 1665.8536 | 84091.5784 | 2164830.2493 | 1222232.0176 | 0 | 0 | 0 | 3477412.4328 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
5893 | Capacity of Armidale to Coffs Harbour | Armidale 132kV Phase Shifting Transformer | PS Augmentation | Input_Proj_Commit | 2011 | 2013 | 14497.5928 | 7443.6701 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
6719 | Capacity of Armidale to Coffs Harbour | Line 96C Armidale to Coffs Harbour Upgrade | PS Augmentation | Input_Proj_Commit | 2011 | 2013 | 344054.6643 | 4225882.0803 | 588012.1378 | 89308.2453 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
5907 | Capacity of Coffs Harbour to Kempsey | Coffs Harbour to Kempsey Transmission Line Upgrade from 66kV to 132kV | PS Augmentation | Input_Proj_Commit | 2010 | 2013 | 2769592.13 | 269538.1637 | 41183.8158 | 35595.1999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
3912 | Capacity of Kempsey to Port Macquarie | Kempsey to Port Macquarie 132kV Transmission Line | PS Augmentation | Input_Proj_Commit | 2012 | 2013 | 11613905.8445 | 11347589.6469 | 7304061.1442 | 286328.1447 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
5553 | Capacity of Queensland to NSW Interconnector | Bulli Creek to Dumaresq Terminal Equipment Upgrade | PS Augmentation | Input_Proj_Commit | 2013 | 2013 | 170.8429 | 0 | 0 | -5020.8297 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
6098 | Capacity of Queensland to NSW Interconnector | Armidale 330kV Static VAR Compensator | PS Augmentation | Input_Proj_Commit | 2013 | 2013 | 511.7879 | 3881.8527 | 24217.1632 | 12997.4688 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
7674 | Capacity of Queensland to NSW Interconnector | Tamworth 330kV Switching Station | PS Augmentation | Input_Proj_Commit | 2013 | 2013 | 0 | 0 | 35498.5339 | -34559.9606 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
7339 | Capacity of Queensland to NSW Interconnector | Reinforcement of NSW to Queensland Interconnection Capacity | PS Augmentation | Input_Proj_Commit | 2013 | 2013 | 0 | 0 | 700638.872 | 1063204.5226 | -1697123.0801 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
5932 | Capacity of Snowy Lines | Snowy Assets Rehabilitation of 64, 65 and 66 Lines | PS Augmentation | Input_Proj_Commit | 2009 | 2013 | 15813.0974 | 46782.488 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
5964 | Capacity of Tamworth to Armidale | 86 Line Tamworth to Armidale 330kV Transmission Line Uprating | PS Augmentation | Input_Proj_Commit | 2011 | 2013 | 631502.9259 | 2553400.426 | -164654.8341 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
6925 | Capacity of Victoria to NSW Interconnector | Yass 132kV 80MVAr Capacitor Bank | PS Augmentation | Input_Proj_Commit | 2015 | 2013 | 0 | 0 | 0 | 41587.1195 | 0 | 0 | 0 | 0 | 0 | 41587.1195 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
6925 | Capacity of Victoria to NSW Interconnector | Yass 132kV 80MVAr Capacitor Bank | PS Augmentation | Input_Proj_Commit | 2015 | 2013 | 0 | 0 | 0 | 41587.1195 | 0 | 0 | 0 | 0 | 0 | 41587.1195 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
7407 | Capacity of Yass to Marulan | Yass to Bannaby and Marulan 330kV Line Uprating | PS Augmentation | Input_Proj_Commit | 2013 | 2013 | 0 | 0 | 15558.4511 | -7671.495 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
6971 | Communications | Lismore Marshalling Kiosk Installation | PS Augmentation | Input_Proj_Commit | 2010 | 2013 | 22823.3228 | 380.2227 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
6876 | Communications | Sydney West Protection/Communications Upgrade | PS Augmentation | Input_Proj_Commit | 2011 | 2013 | 100305.5958 | 462511.5986 | 30112.0315 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
7064 | Communications | Tuggerah Provision of Fibre Marshalling Kiosk | PS Augmentation | Input_Proj_Commit | 2011 | 2013 | 0 | 2750.7232 | 867.5036 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
7278 | Communications | Albury to Mulwala Tripping Scheme | PS Augmentation | Input_Proj_Commit | 2011 | 2013 | 0 | 70408.0374 | -68998.7647 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
6973 | Communications | Murray Substation Station & Lower Tumut Switching Station OPGW & Protection Upgrade | PS Augmentation | Input_Proj_Commit | 2012 | 2013 | 584640.3006 | 267920.4628 | 506878.9528 | -707.116 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
7530 | Communications | Vales Point DNSP Communications Upgrade | PS Augmentation | Input_Proj_Commit | 2012 | 2013 | 0 | 5223.436 | 85044.6834 | 673.2302 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
7533 | Communications | Sydney East DNSP Communications Upgrade | PS Augmentation | Input_Proj_Commit | 2012 | 2013 | 0 | 0 | 333465.2256 | 3033.5435 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
6875 | Communications | Regentville Protection/Communications Upgrade | PS Augmentation | Input_Proj_Commit | 2013 | 2013 | 125952.0377 | 141239.0667 | 140269.2056 | 40883.6863 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
7028 | Communications | Armidale - Dumaresq OPGW - OLTE Upgrades | PS Augmentation | Input_Proj_Commit | 2013 | 2013 | 0 | 1871242.3726 | 2692139.8426 | 95194.7539 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
P0001221 | Communications | Fibre Connections at Dapto for Endeavour Energy | PS Augmentation | Input_Proj_Commit | 2014 | 2013 | 0 | 0 | 0 | 0 | 104406.6153 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
5645 | Control System | Armidale Static VAR Compensator Power Oscillation Damper | PS Augmentation | Input_Proj_Commit | 2009 | 2013 | 18055.976 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
6992 | Control System | Real-Time Line Rating on Lines 8 and 16 | PS Augmentation | Input_Proj_Commit | 2011 | 2013 | 285.4682 | 84795.131 | 1315.605 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
5606 | Control System | SCADA Operations Circuit Breakers Check Synchronism | PS Augmentation | Input_Proj_Commit | 2013 | 2013 | -13.8692 | 0 | 0 | -89562.1245 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
5837 | Control System | SCADA Control For Loadshed of Tomago Aluminum | PS Augmentation | Input_Proj_Commit | 2013 | 2013 | 0 | -8475.5541 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
6457 | Control System | SCADA Control For Loadshed of Tomago Aluminum | PS Augmentation | Input_Proj_Commit | 2013 | 2013 | 1070.6854 | 10628.3805 | 115678.9511 | 466042.0052 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
7564 | Control System | Smart Grid Monitor Installation | PS Augmentation | Input_Proj_Commit | 2013 | 2013 | 0 | 0 | 49546.9415 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
7846 | Control System | Current Transducer Installation at Bannaby & Bayswater | PS Augmentation | Input_Proj_Commit | 2013 | 2013 | 0 | 0 | 77115.1323 | 221870.9197 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
7739 | Easements | Bannaby to Yass 500kV Transmission Line | PS Augmentation | Input_Proj_Commit | 2013 | 2013 | 2.7237 | 3257.148 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
6030 | Fault Level Equipment Upgrade | Munmorah Substation Short Circuit Fault Level Upgrade | PS Augmentation | Input_Proj_Commit | 2010 | 2013 | 1715.5218 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
6041 | Fault Level Equipment Upgrade | Sydney North Fault Level Upgrade | PS Augmentation | Input_Proj_Commit | 2011 | 2013 | 2131173.3178 | 1432879.8899 | 14070.427 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
6231 | Fault Level Equipment Upgrade | Dapto Fault Level Upgrade | PS Augmentation | Input_Proj_Commit | 2011 | 2013 | 2285776.1096 | 142308.6051 | 0 | 8779.7307 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
6699 | Fault Level Equipment Upgrade | Sydney South Fault Level Upgrade | PS Augmentation | Input_Proj_Commit | 2011 | 2013 | 33013.7258 | -32222.5843 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
7538 | Fault Level Equipment Upgrade | Sydney South Fault Level Upgrade | PS Augmentation | Input_Proj_Commit | 2011 | 2013 | 0 | 31256.5554 | 0 | -29821.0012 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
5840 | Reactor Installation | 41 Cable 330kV Shunt Reactor | PS Augmentation | Input_Proj_Commit | 2011 | 2013 | 9981062.9834 | -461464.7102 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
6184 | Reactor Installation | 41 Cable 330kV Series Reactor | PS Augmentation | Input_Proj_Commit | 2011 | 2013 | 22.9338 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
6906 | Reactor Installation | Yass 330kV Shunt Reactor | PS Augmentation | Input_Proj_Commit | 2011 | 2013 | 0 | 68429.1058 | 107518.138 | 104757.2956 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
5915 | Reinforcement of Supply To The New England Area | Glen Innes to Inverell Transmission Line 132kV Line Bays | PS Augmentation | Input_Proj_Commit | 2012 | 2013 | 225675.4101 | 1942335.2808 | 524738.2964 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
7472 | Reinforcement of the Victoria/NSW Interconnection | Uprating Lines 8, 16 & 18 Between Dapto and Marulan | PS Augmentation | Input_Proj_Commit | 2011 | 2013 | 0 | 0 | 27692.8985 | 152670.17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
7473 | SCADA | Yanco SCADA | PS Augmentation | Input_Proj_Commit | 2012 | 2013 | -1.5907 | -78.3287 | 317786.5521 | 42929.4001 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
5830 | SCADA | Provision of SCADA Facilities At Existing 132kV Substations | PS Augmentation | Input_Proj_Commit | 2013 | 2013 | -43.536 | 9283.7772 | 0 | -124341.0741 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
5951 | SCADA | Provision of SCADA Facilities At Existing 132kV Substations | PS Augmentation | Input_Proj_Commit | 2013 | 2013 | 144.8695 | 0 | 0 | -6344.5848 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
6375 | SCADA | 132kV and 66kV Operational Info To TransGrid & Nemmco | PS Augmentation | Input_Proj_Commit | 2013 | 2013 | -25.189 | 0 | -38298.5948 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
6376 | SCADA | 132kV and 66kV Operational Info To TransGrid & Nemmco | PS Augmentation | Input_Proj_Commit | 2013 | 2013 | -21.9968 | 0 | -66898.211 | 32564.6797 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
6437 | SCADA | 132kV and 66kV Operational Info To TransGrid & Nemmco | PS Augmentation | Input_Proj_Commit | 2013 | 2013 | -0.75175 | 0 | 0 | -3259.9489 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
7292 | SCADA | Finley SCADA | PS Augmentation | Input_Proj_Commit | 2013 | 2013 | 1797.8655 | 145.8109 | 105543.8551 | 262116.1036 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
7640 | SCADA | Inverell SCADA | PS Augmentation | Input_Proj_Commit | 2013 | 2013 | 0 | 0 | 812.9081 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
7368 | Secondary System Renewal | Jindera No.1 and No.2 Transformer Bay Ratings | PS Augmentation | Input_Proj_Commit | 2014 | 2013 | 0 | 0 | 0 | 1552.4735 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
6158 | Substation Minor Projects | Switchbay at Finley | PS Augmentation | Input_Proj_Commit | 2010 | 2013 | 272.1219 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
5378 | Substation Minor Projects | Armidale 330kV Substation Connection of 89 Lismore Line | PS Augmentation | Input_Proj_Commit | 2011 | 2013 | 0 | 33161.146 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
6374 | Substation Minor Projects | Haymarket Substation Ausgrid 132kV Cables | PS Augmentation | Input_Proj_Commit | 2011 | 2013 | 2159779.3048 | 231120.9253 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
6765 | Substation Minor Projects | Sydney South Feeder 916/917 Protection Replacement | PS Augmentation | Input_Proj_Commit | 2011 | 2013 | 368437.5593 | 139224.2566 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
6821 | Substation Minor Projects | Wallerawang Auxiliary Power Supply Rearrangements | PS Augmentation | Input_Proj_Commit | 2011 | 2013 | 573431.4097 | 74920.2945 | 15185.6161 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
6872 | Substation Minor Projects | Connection to Jesmond Substation | PS Augmentation | Input_Proj_Commit | 2011 | 2013 | 1975.801 | 45991.4385 | 0 | -45719.0171 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
6223 | Substation Minor Projects | Vineyard Line Bays | PS Augmentation | Input_Proj_Commit | 2012 | 2013 | 0 | -3760.6591 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
6720 | Substation Minor Projects | Manildra 132kV Swithbay | PS Augmentation | Input_Proj_Commit | 2012 | 2013 | -0.77354 | 0 | 0 | -1090.8464 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
6816 | Substation Minor Projects | Port Macquarie 33kV Switchbays and Installation of Auto Reclose Facilities | PS Augmentation | Input_Proj_Commit | 2012 | 2013 | 780850.6064 | 1087218.4708 | 606967.5063 | 904453.5287 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
6102 | Substation Minor Projects | Liddell 84 Line Connection - Additional Circuit Breaker Installation | PS Augmentation | Input_Proj_Commit | 2013 | 2013 | 4584.2688 | -13629.8065 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
6274 | Substation Minor Projects | Newcastle Substation - Provision of 132kV Switchbay | PS Augmentation | Input_Proj_Commit | 2013 | 2013 | 31755.6372 | -33719.602 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
6607 | Substation Minor Projects | Griffith 132kV Substation - 33kV Connection | PS Augmentation | Input_Proj_Commit | 2013 | 2013 | 849349.7512 | 1389659.549 | 273564.1187 | 67770.4373 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
7307 | Substation Minor Projects | Newcastle Substation - Provision of 132kV Switchbay | PS Augmentation | Input_Proj_Commit | 2013 | 2013 | 0 | 55642.3588 | 2374.6667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
7469 | Substation Minor Projects | Liddell 84 Line Connection - Additional Circuit Breaker Installation | PS Augmentation | Input_Proj_Commit | 2013 | 2013 | 0 | 15266.8928 | 519846.4146 | 3826800.9815 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
7511 | Substation Minor Projects | Munmorah - Supply To Lake Munmorah Zone Substation | PS Augmentation | Input_Proj_Commit | 2013 | 2013 | 0 | 1635.268 | 134441.761 | 410330.047 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
7512 | Substation Minor Projects | Vales Point - Supply To Lake Munmorah Zone Substation | PS Augmentation | Input_Proj_Commit | 2013 | 2013 | 0 | 0 | 85650.6103 | 403683.1894 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
7521 | Substation Minor Projects | Newcastle 952 Feeder Connection to Rathmines | PS Augmentation | Input_Proj_Commit | 2013 | 2013 | 0 | 13396.2667 | 212606.8575 | 121901.1902 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
7683 | Substation Minor Projects | Connection to Morvern Substation | PS Augmentation | Input_Proj_Commit | 2013 | 2013 | 0 | 0 | 0 | 179257.1642 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
7825 | Substation Minor Projects | Connection of Charlestown Zone Substation | PS Augmentation | Input_Proj_Commit | 2013 | 2013 | 0 | 0 | 6347.555 | 94034.0866 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
7862 | Substation Minor Projects | Sydney North Substation 257 & 258 132kV Feeder Augmentation | PS Augmentation | Input_Proj_Commit | 2013 | 2013 | 0 | 0 | 36907.8025 | 40144.4499 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
6105 | Substation Minor Projects | Sydney West Substation 330kV Bus Coupling | PS Augmentation | Input_Proj_Commit | 2014 | 2013 | 7638.6213 | 0 | 0 | -9211.2867 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
6107 | Substation Minor Projects | Sydney West Substation 20 Line Bus Coupling | PS Augmentation | Input_Proj_Commit | 2014 | 2013 | 9.7183 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
8039 | Substation Minor Projects | Jindera No.1 and No.2 Transformer Bay Ratings | PS Augmentation | Input_Proj_Commit | 2014 | 2013 | 0 | 0 | 0 | 2955.8803 | 65669.1406 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
6262 | Substation Renewal | Orange North Substation | PS Augmentation | Input_Proj_Commit | 2010 | 2013 | -8.4435 | 0 | -28849.3337 | -8148.7968 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
5963 | Substation Renewal | Murray Switching Station | PS Augmentation | Input_Proj_Commit | 2012 | 2013 | 2405335.8372 | 5565634.5651 | 2621140.1799 | 92283.7164 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
6709 | Substation Renewal | Orange North Substation | PS Augmentation | Input_Proj_Commit | 2013 | 2013 | 2471997.3283 | 7553402.7327 | 17117458.6777 | 4833114.5255 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
5715 | Supply to ACT | Williamsdale 330/132kV Substation | PS Augmentation | Input_Proj_Commit | 2012 | 2013 | 13742330.9782 | 17119219.2736 | 18469414.0206 | 8093780.5965 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
7401 | Supply to Darlington Point | Darling Point to Colleambally 132kV Line | PS Augmentation | Input_Proj_Commit | 2011 | 2013 | 2615.7129 | -242.451 | 0 | -12786.8193 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
6969 | Supply to Gunnedah, Narrabri and Moree | Installation of Phase Shifting Transformer on 969 Line | PS Augmentation | Input_Proj_Commit | 2018 | 2013 | 93036.5186 | 91246.1026 | 24370.3097 | 455279.4929 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 663932.4237 | 100% | 100% | 100% | 100% | 100% | 0
5714 | Supply to Macarthur | Macarthur 330/132kV Substation | PS Augmentation | Input_Proj_Commit | 2010 | 2013 | 1748947.5762 | 538340.4994 | -1171.0558 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
7400 | Supply to South Coast | Tomerong Substation Establishment | PS Augmentation | Input_Proj_Commit | 2014 | 2013 | 77174.3832 | 40944.2049 | 291434.4043 | 348278.1607 | -858405.9672 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
6910 | Supply to Sydney Inner Metropolitan Area and CBD | Beaconsfield West To Haymarket 330kV Cable | PS Augmentation | Input_Proj_Commit | 2014 | 2013 | 8063.8057 | 92656.4228 | 806296.6386 | 14890136.7269 | 882581.9277 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
6704 | Supply to the ACT | Wallaroo 330kV Switching Station | PS Augmentation | Input_Proj_Commit | 2018 | 2013 | 475620.8222 | 423018.6861 | 228413.1879 | 9513.1538 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1136565.85 | 100% | 100% | 100% | 100% | 100% | 0
6346 | Supply to the Cabonne Area | Manildra to Parkes 132kV Transmission Line | PS Augmentation | Input_Proj_Commit | 2012 | 2013 | 3645132.251 | 21512973.2234 | 17756636.0701 | 420403.5225 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
7147 | Supply to the Cabonne Area | Manildra to Parkes 132kV Transmission Line | PS Augmentation | Input_Proj_Commit | 2012 | 2013 | 0 | 64392.1484 | 1746542.2934 | -14735.8978 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
8155 | Supply to the Cabonne Area | Manildra to Parkes 132kV Transmission Line | PS Augmentation | Input_Proj_Commit | 2012 | 2013 | 0 | 0 | 0 | 1941669.3431 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
6662 | Supply to the Lower Mid North Coast | Tomago-Tarro-Stroud 330/132kV Transmission Line | PS Augmentation | Input_Proj_Commit | 2014 | 2013 | 1511529.1962 | 2494391.5079 | 8906471.7643 | 48905408.4984 | 29590886.7947 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
6967 | Supply to the Mid North Coast | Stroud-Taree 330kV Transmission Line Construction | PS Augmentation | Input_Proj_Commit | 2014 | 2013 | 6603.3008 | 266153.8247 | 1179811.2435 | -1397008.3346 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
5880 | Supply to the New England Area | Glen Innes to Inverell 132kV Transmission Line | PS Augmentation | Input_Proj_Commit | 2012 | 2013 | 8090217.1691 | 9348317.0107 | 7833226.8287 | 792409.3309 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
7513 | Supply to Tomago | Tomago 330/132kV Substation - Establishment of 132kV Busbar and Connections | PS Augmentation | Input_Proj_Commit | 2014 | 2013 | 0 | 913933.0115 | 8663898.6958 | 5867742.0284 | 44892.9994 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
7745 | Supply to Tomago | Sydney South - Tail Ending 91F and 91J | PS Augmentation | Input_Proj_Commit | 2014 | 2013 | 0 | 0 | 16377.42 | 91454.1756 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
5968 | Supply to Tomago Area | Establishment of 132kV Busbar at Tomago 330kV Substation | PS Augmentation | Input_Proj_Commit | 2011 | 2013 | 22901843.3212 | 14730587.4192 | 760164.3448 | 1395474.2852 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
6036 | Supply to Wagga Wagga | Wagga North 132/66kV Substation Establishment | PS Augmentation | Input_Proj_Commit | 2011 | 2013 | 2836978.6005 | 572594.206 | 4876.167 | -56912.4159 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
4419 | Supply to Wellington | Wollar to Wellington 330kV Transmission Line | PS Augmentation | Input_Proj_Commit | 2010 | 2013 | 15396068.3943 | 15439639.8884 | 2918964.021 | 276664.7777 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
4429 | Supply to Wellington | Wollar 330kV Switching Station | PS Augmentation | Input_Proj_Commit | 2010 | 2013 | 30505266.9809 | 138048.9224 | 386.8679 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
7644 | SVC Control System Replacement | Armidale SVC Transformer | PS Augmentation | Input_Proj_Commit | 2013 | 2013 | 0 | 0 | 0 | 75733.5829 | -73642.286 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
5670 | Transformer Additions | Parkes No.2 Transformer | PS Augmentation | Input_Proj_Commit | 2009 | 2013 | 3578.9746 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
5816 | Transformer Additions | Tuggerah No.2 Transformer | PS Augmentation | Input_Proj_Commit | 2009 | 2013 | 161007.0537 | 42550.2086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
5852 | Transformer Additions | Marulan No.2 Transformer | PS Augmentation | Input_Proj_Commit | 2009 | 2013 | -4820.8516 | 0 | 0 | 56809.3181 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
6320 | Transformer Additions | Koolkhan No.3 Transformer | PS Augmentation | Input_Proj_Commit | 2010 | 2013 | 5418979.5326 | 419528.6789 | 152438.7863 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
6668 | Transformer Additions | Sydney North No.5 Transformer | PS Augmentation | Input_Proj_Commit | 2011 | 2013 | 8667242.3705 | 6302126.0079 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
6696 | Transformer Additions | Waratah West No.2 Transformer & Bus Section | PS Augmentation | Input_Proj_Commit | 2011 | 2013 | 10806788.8002 | 12602578.0301 | 99372.1331 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
6727 | Transformer Additions | Vineyard No.3 Transformer | PS Augmentation | Input_Proj_Commit | 2012 | 2013 | 9309630.4127 | 5466916.1769 | 4369189.6573 | 86847.8981 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
6907 | Transformer Additions | Munmorah No.2 Transformer | PS Augmentation | Input_Proj_Commit | 2013 | 2013 | 0 | 2445.32 | 0 | -2333.0018 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
7456 | Transformer Additions | Eraring No.2 Transformer | PS Augmentation | Input_Proj_Commit | 2013 | 2013 | 0 | 41990.5616 | 3688.0833 | -43720.8854 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
7684 | Transformer Additions | Coffs Harbour No. 2 330/132kV Transformer Installation | PS Augmentation | Input_Proj_Commit | 2014 | 2013 | 0 | 0 | 0 | 109182.7308 | -106167.7736 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
7338 | Transformer Replacement | Marulan No.4 Transformer | PS Augmentation | Input_Proj_Commit | 2009 | 2013 | 0 | 0 | 1969.979 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
4563 | Transformer Replacement | Wellington 330kV Transformer Replacement & Shunt Reactor | PS Augmentation | Input_Proj_Commit | 2010 | 2013 | 3318257.896 | 69940.224 | 3867.9596 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
5691 | Transformer Replacement | Finley No.1 & No.2 Transformer Replacement | PS Augmentation | Input_Proj_Commit | 2010 | 2013 | 1073369.7248 | 6868.0191 | 23004.038 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
6363 | Transformer Replacement | Sydney South No.3 & No.4 Transformer Replacements | PS Augmentation | Input_Proj_Commit | 2011 | 2013 | 2509610.5649 | 1304977.5724 | 686994.3185 | -45291.5903 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
6446 | Transformer Replacement | Coffs Harbour 132/66kV Transformer Replacements | PS Augmentation | Input_Proj_Commit | 2011 | 2013 | 3798268.415 | 412048.0244 | 547.6529 | -108773.5455 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
6458 | Transformer Replacement | Cowra 132/66kV Transformer Replacement | PS Augmentation | Input_Proj_Commit | 2011 | 2013 | 6702061.1224 | 311565.7948 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
7093 | Transformer Replacement | Kempsey 66/33kV Transformer Replacement | PS Augmentation | Input_Proj_Commit | 2013 | 2013 | 0 | 51054.8994 | 33461.8191 | 47771.1529 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
7633 | Transformer Replacement | Kempsey 66kV Bus and No.2 Transformer Replacement | PS Augmentation | Input_Proj_Commit | 2013 | 2013 | 0 | 0 | 0 | 342.398 | -332.9431 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
7409 | Transformer Replacement | Koolkhan - 967 Line Deviation Works | PS Augmentation | Input_Proj_Commit | 2014 | 2013 | 0 | 90627.9908 | -88813.946 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
5881 | Transmission Line Rearrangement | 24 Line Vales Point to Newcastle 330kV Turn In | PS Augmentation | Input_Proj_Commit | 2009 | 2013 | 52501.3897 | 6103.9264 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
7573 | Transmission Line Rearrangement | Koolkhan - 967 Line Deviation Works | PS Augmentation | Input_Proj_Commit | 2014 | 2013 | 0 | 0 | 0 | -143305.88 | 715360.0415 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
7399 | Transmission Line Renewal | 86 Line Tamworth to Armidale Condition | PS Augmentation | Input_Proj_Commit | 2011 | 2013 | 0 | 314.091 | -307.7832 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
5940 | Transmission Line Renewal | Tamworth to Gunnedah 66kV Transmission Line Refurbishment | PS Augmentation | Input_Proj_Commit | 2012 | 2013 | 7377986.2705 | 853622.1104 | 270509.63 | 126621.1167 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
7705 | Transmission Line Renewal | 964 Line Port Macquarie to Taree Condition | PS Augmentation | Input_Proj_Commit | 2012 | 2013 | 4709.2115 | 1905.8028 | -88832.412 | 30786.44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
5527 | Western 500kV Upgrade | Bayswater 500/330kV Switchyard Development | PS Augmentation | Input_Proj_Commit | 2009 | 2013 | 714169.9729 | 24858.0617 | 17009.9621 | 77406.4522 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
5535 | Western 500kV Upgrade | Mt Piper 500/330kV Switchyard Development | PS Augmentation | Input_Proj_Commit | 2009 | 2013 | 2947017.7544 | 737832.1754 | 175685.9662 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
5965 | Western 500kV Upgrade | Wallerawang 330kV Fault Rating Upgrade | PS Augmentation | Input_Proj_Commit | 2009 | 2013 | 6107.6155 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
5967 | Western 500kV Upgrade | Uprating of Lines 330kV 8 and 16 Lines | PS Augmentation | Input_Proj_Commit | 2009 | 2013 | 2309.9476 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
6229 | Western 500kV Upgrade | Bayswater-Liddell Reduct In Fault Clearing Times | PS Augmentation | Input_Proj_Commit | 2009 | 2013 | 182981.3696 | 5421.4588 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
5864 | Western 500kV Upgrade | Bannaby 500/330kV Substation Development | PS Augmentation | Input_Proj_Commit | 2011 | 2013 | 27996485.093 | 6217699.1259 | 282877.0944 | 51555.0015 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
6648 | Western Sydney Supply Project | Holroyd 330kV Substation Establishment | PS Augmentation | Input_Proj_Commit | 2014 | 2013 | 1274491.6693 | 5582664.236 | 19908570.8114 | 31403133.4998 | 21865373.0414 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
6664 | Western Sydney Supply Project | Sydney West to Holroyd 330kV Transmission Line | PS Augmentation | Input_Proj_Commit | 2014 | 2013 | 3530403.2349 | 4683671.0637 | 1860787.5179 | 29227099.9046 | 42305662.3368 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
6988 | Western Sydney Supply Project | Sydney West 330kV Connections For Holroyd Substation | PS Augmentation | Input_Proj_Commit | 2014 | 2013 | 31306.2444 | 291496.7458 | 3060232.3574 | 11947525.5187 | 1305324.6634 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
6650 | Western Sydney Supply Project | Holroyd - Rookwood 330kV Cable | PS Augmentation | Input_Proj_Commit | 2015 | 2013 | 1226964.3462 | 2146640.6506 | 11233417.5893 | 44967630.0905 | 90225575.2573 | 1631435.5469 | 0 | 0 | 0 | 151431663.4808 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 149800227.934
6651 | Western Sydney Supply Project | Rookwood Road 330/132kV Substation | PS Augmentation | Input_Proj_Commit | 2015 | 2013 | 5045956.2228 | 5969660.6952 | 16324279.2188 | 36242411.5445 | 36667938.607 | 11714572.7726 | 0 | 0 | 0 | 111964819.0609 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 100250246.2883
6344 | Protection Change | Sydney West to West Wetherill Park Substation 93M Feeder Protection Upgrade | PS Connections | Input_Proj_Commit | 2009 | 2013 | 39.2107 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
P0001491 | Protection Change | Protection Changes on Macarthur Lines | PS Connections | Input_Proj_Commit | 2014 | 2013 | 0 | 0 | 0 | 0 | 102929.6772 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
P0001497 | Protection Change | Taree Distance Relay Replacement for Essential Energy | PS Connections | Input_Proj_Commit | 2014 | 2013 | 0 | 0 | 0 | 0 | 145734.0273 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
6053 | Substation Minor Projects | Provision of Switchbays at Taree Substation | PS Connections | Input_Proj_Commit | 2009 | 2013 | 1553.7435 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
6287 | Substation Minor Projects | Connection of Morisset Zone Substation | PS Connections | Input_Proj_Commit | 2009 | 2013 | -7.6482 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
6518 | Substation Minor Projects | Argenton 132kV Substation Connection | PS Connections | Input_Proj_Commit | 2009 | 2013 | 12509.0992 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
6618 | Substation Minor Projects | Connection of Kingsford Substation at Beaconsfield West | PS Connections | Input_Proj_Commit | 2009 | 2013 | 12164.646 | 0 | 0 | 4505.9899 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
6638 | Substation Minor Projects | Mayfield West & Kooragang Zone Substation Connection | PS Connections | Input_Proj_Commit | 2009 | 2013 | 172560.1037 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
6640 | Substation Minor Projects | Narrabri Substation 66kV Switchbay Renames | PS Connections | Input_Proj_Commit | 2009 | 2013 | -20.1665 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
6697 | Substation Minor Projects | Beryl 66kV Bay to Dunedoo | PS Connections | Input_Proj_Commit | 2010 | 2013 | 4929.659 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
6345 | Substation Minor Projects | Sydney North 132kV Switchbays For Galston | PS Connections | Input_Proj_Commit | 2011 | 2013 | 697547.6786 | 86438.5445 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
6724 | Substation Minor Projects | Tenterfield 22kV Switchbay | PS Connections | Input_Proj_Commit | 2011 | 2013 | 20721.5113 | 555.8295 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
6856 | Substation Minor Projects | Connection to Kurri Zone Substation at Newcastle | PS Connections | Input_Proj_Commit | 2011 | 2013 | 81795.8363 | 108736.643 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
7134 | Substation Minor Projects | Connection of Jesmond Zone Substation | PS Connections | Input_Proj_Commit | 2011 | 2013 | 0 | 134349.0037 | 2453.3241 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
7283 | Substation Minor Projects | Tenterfield 22kV Switchbay | PS Connections | Input_Proj_Commit | 2011 | 2013 | 0 | 1587.6072 | -1555.8499 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
7285 | Substation Minor Projects | Cooma 132kV Installation of New Line Bay | PS Connections | Input_Proj_Commit | 2013 | 2013 | 26342.4517 | 602921.9722 | 1032484.9507 | 11299.8751 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
7422 | Substation Minor Projects | Hawks Nest 132/66kV Substation Line Connection | PS Connections | Input_Proj_Commit | 2013 | 2013 | 51405.9729 | 43141.8208 | 1058691.5802 | 908324.1917 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
7565 | Substation Minor Projects | Uprate Broken Hill 52 & 62 22kV Line Switchbays | PS Connections | Input_Proj_Commit | 2014 | 2013 | 0 | 0 | 4159.7049 | 69369.2044 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
7668 | Substation Minor Projects | Wellington Substation 132kV Switchbay and Double Circuit (Strung On One Side) To Mitchell Highway | PS Connections | Input_Proj_Commit | 2014 | 2013 | 0 | 2.9562 | 0 | 603864.8096 | 1941381.395 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
7826 | Substation Minor Projects | Connection to Broadmeadow Zone Substation at Waratah West | PS Connections | Input_Proj_Commit | 2014 | 2013 | 0 | 0 | 3699.4734 | 172769.1535 | 76960.2597 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
8178 | Substation Minor Projects | Connection to Herons Creek Substation | PS Connections | Input_Proj_Commit | 2014 | 2013 | 678.5562 | 65.9403 | -15382.9995 | 23667.7592 | 244855.9957 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
P0000899 | Substation Minor Projects | Connection of Abbotsbury Zone Substation at Sydney West | PS Connections | Input_Proj_Commit | 2014 | 2013 | 0 | 0 | 0 | 0 | 435392.5781 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
P0000909 | Substation Minor Projects | Reduce AVR Settings at Vineyard Substation | PS Connections | Input_Proj_Commit | 2014 | 2013 | 0 | 0 | 0 | 4092.1884 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
6157 | Substation Minor Projects | Supply to Gulgong West | PS Connections | Input_Proj_Commit | 2015 | 2013 | -13.0085 | 0 | 0 | -23861.0905 | 0 | 0 | 0 | 0 | 0 | -23874.099 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
6222 | Substation Minor Projects | Sydney West 132kV Line Bays | PS Connections | Input_Proj_Commit | 2015 | 2013 | 0 | -4962.9926 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -4962.9926 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
6986 | Substation Minor Projects | Supply to Belmore Park Zone Substation | PS Connections | Input_Proj_Commit | 2015 | 2013 | 1125.0836 | 36350.0142 | 366487.5301 | 640710.9305 | 397873.5542 | 22897.2442 | 0 | 0 | 0 | 1465444.3569 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
7126 | Substation Minor Projects | Sydney West 132kV Line Bays | PS Connections | Input_Proj_Commit | 2015 | 2013 | 0 | 35849.236 | 3513.9907 | 0 | 0 | 0 | 0 | 0 | 0 | 39363.2267 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
7311 | Substation Minor Projects | Sydney West 132kV Line Bays | PS Connections | Input_Proj_Commit | 2015 | 2013 | 0 | 4967.9692 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4967.9692 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
7313 | Substation Minor Projects | Tamworth 66kV Line Bay | PS Connections | Input_Proj_Commit | 2015 | 2013 | 0 | 4061.1388 | 16660.766 | 21203.922 | -40158.3674 | 0 | 0 | 0 | 0 | 1767.4594 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
7661 | Substation Minor Projects | Supply to Temora | PS Connections | Input_Proj_Commit | 2015 | 2013 | 0 | 0 | 0 | 32863.0568 | 0 | 0 | 0 | 0 | 0 | 32863.0568 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
8092 | Substation Minor Projects | Supply to Parkes Town | PS Connections | Input_Proj_Commit | 2015 | 2013 | 0 | 0 | 0 | 1683.2785 | 1216.6289 | 257324.2188 | 0 | 0 | 0 | 260224.1262 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
8095 | Substation Minor Projects | Supply to Googong | PS Connections | Input_Proj_Commit | 2015 | 2013 | 0 | 0 | 0 | 977.7249 | 0 | 257324.2188 | 0 | 0 | 0 | 258301.9437 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
6176 | Substation Minor Projects | Supply to Molong | PS Connections | Input_Proj_Commit | 2016 | 2013 | 0 | -6697.8781 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -6697.8781 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
7532 | Substation Minor Projects | Connection of Gwawley Bay | PS Connections | Input_Proj_Commit | 2016 | 2013 | 0 | 0 | -205.5639 | 20685.4704 | 0 | 0 | 0 | 0 | 0 | 0 | 20479.9064 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
7094 | Substation Minor Projects | Supply to Marsden Park | PS Connections | Input_Proj_Commit | 2016 | 2013 | 8969.1719 | 3764.4341 | -3688.9899 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9044.616 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
8093 | Substation Minor Projects | Supply to Molong | PS Connections | Input_Proj_Commit | 2016 | 2013 | 0 | 0 | 0 | 10883.598 | 0 | 0 | 0 | 0 | 0 | 0 | 10883.598 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
6964 | Substation Minor Projects | Supply to Nabiac | PS Connections | Input_Proj_Commit | 2017 | 2013 | 6309.9447 | 59600.6898 | 124943.4693 | 192625.3265 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 383479.4304 | 0 | 100% | 100% | 100% | 100% | 100% | 0
P0002435 | Substation Minor Projects | Supply to Gloucester | PS Connections | Input_Proj_Commit | 2017 | 2013 | 0 | 0 | 0 | 0 | 102929.6875 | 473476.5625 | 0 | 0 | 0 | 0 | 0 | 576406.25 | 0 | 100% | 100% | 100% | 100% | 100% | 0
6174 | Substation Minor Projects | Supply to Googong | PS Connections | Input_Proj_Commit | 2018 | 2013 | 29746.0075 | -29345.9354 | -2752.1765 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -2352.1045 | 100% | 100% | 100% | 100% | 100% | 0
7320 | Substation Minor Projects | Supply to Googong | PS Connections | Input_Proj_Commit | 2018 | 2013 | 0 | 33930.8427 | 32400.9649 | -63916.7679 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2415.0398 | 100% | 100% | 100% | 100% | 100% | 0
7392 | Transformer Additions | Macarthur 330/132kV No.2 Transformer Installation | PS Connections | Input_Proj_Commit | 2014 | 2013 | 0 | 1850.2943 | -1813.2581 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
890 | Easements | Koolkhan to Coffs Harbour 132kV Transmission Line Easements | PS Easements | Input_Proj_Commit | 2009 | 2013 | 29907.8622 | 12545.2212 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
2007 | Easements | Coffs Harbour to Kempsey 132kV Transmission Line Easements | PS Easements | Input_Proj_Commit | 2009 | 2013 | 25055.3936 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
3133 | Easements | Cable Easements | PS Easements | Input_Proj_Commit | 2009 | 2013 | 14163.152 | 1045.1019 | 2104.2219 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
3954 | Easements | Coffs Harbour 132kV Transmission Line Upgrade Easements | PS Easements | Input_Proj_Commit | 2009 | 2013 | 171.3223 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
3955 | Easements | Darlington Point to Buronga Strategic Easement Acquisition | PS Easements | Input_Proj_Commit | 2009 | 2013 | 42312.6209 | 1328.2166 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
4240 | Easements | Miscellaneous State Forests Easements | PS Easements | Input_Proj_Commit | 2009 | 2013 | -0.076264 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
4254 | Easements | Ivanhoe Coal | PS Easements | Input_Proj_Commit | 2009 | 2013 | -92579.3468 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
4300 | Easements | Miscellaneous Statewide NPWS Easements | PS Easements | Input_Proj_Commit | 2009 | 2013 | 31218.1264 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
4400 | Easements | Miscellaneous Sydney Catchment Authority Easements | PS Easements | Input_Proj_Commit | 2009 | 2013 | 339.5505 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
905 | Easements | Miscellaneous Easements | PS Easements | Input_Proj_Commit | 2010 | 2013 | 4782114.3222 | 37895.8625 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
6961 | Easements | Bannaby to South Creek Lines 500kV Easement Acquisitions | PS Easements | Input_Proj_Commit | 2013 | 2013 | 804.8498 | 1371084.5722 | -1324113.5289 | 526399.24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
6673 | Easements | Dumaresq to Lismore 330kV Strategic Easement Acquisition | PS Easements | Input_Proj_Commit | 2014 | 2013 | 3685694.4755 | 3651041.2471 | 3770822.9893 | 3360996.5009 | 584823.8398 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
7460 | Easements | Kemps Creek to Liverpool 330kV Easement Acquisition | PS Easements | Input_Proj_Commit | 2014 | 2013 | 89825.5846 | 130994.6945 | 7282618.0415 | 1248931.4052 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
7790 | Easements | Strategic Easement for Sydney West to Holroyd Second 330kV Line | PS Easements | Input_Proj_Commit | 2015 | 2013 | 0 | 0 | 26800.6139 | 0 | -25371.488 | 0 | 0 | 0 | 0 | 1429.1259 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
6923 | Powering Sydney's Future | Rookwood 330kV Substation - Cable Bays For Beaconsfield West | PS Easements | Input_Proj_Commit | 2017 | 2013 | 0 | 1601.9948 | -1570.012 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31.9828 | 0 | 100% | 100% | 100% | 100% | 100% | 0
7562 | Powering Sydney's Future | Haymarket Additional 330 kV Switchbays and Beaconsfield West Bay | PS Easements | Input_Proj_Commit | 2017 | 2013 | 0 | 0 | 7058.025 | -6871.4063 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 186.6187 | 0 | 100% | 100% | 100% | 100% | 100% | 0
4759 | Property | Marulan Substation Outstanding Land Acquisition | PS Easements | Input_Proj_Commit | 2009 | 2013 | 441204.6505 | 244.3544 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
5827 | Property | Miscellaneous Substation Site Rights Acquisition | PS Easements | Input_Proj_Commit | 2009 | 2013 | 482.4044 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
7396 | Property | Richmond Vale 500kV Strategic Property Acquisition | PS Easements | Input_Proj_Commit | 2013 | 2013 | 2481.0302 | 1680.4723 | -1300.8177 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
7457 | Property | South Creek 500/330kV Substation Strategic Site Acquisition | PS Easements | Input_Proj_Commit | 2013 | 2013 | 941326.9804 | 12738702.7213 | 35739.3311 | 76267.1816 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
5994 | Property | Lismore Substations 330kV Augmentation | PS Easements | Input_Proj_Commit | 2014 | 2013 | -0.02179 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
6751 | Property | Tenterfield Substation | PS Easements | Input_Proj_Commit | 2014 | 2013 | 48400.6038 | 10335.1956 | -64911.3083 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
6939 | Property | Tenterfield Substation | PS Easements | Input_Proj_Commit | 2014 | 2013 | 0 | 1710.7574 | 0 | -1632.1658 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
6911 | Property | Strategic Property Acquisition at Beryl | PS Easements | Input_Proj_Commit | 2015 | 2013 | 11776.646 | 161751.2905 | -169777.9571 | 206550.7468 | 51464.8438 | 720507.8125 | 0 | 0 | 0 | 982273.3824 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
7548 | Property | Property Acquisition at Sydney West | PS Easements | Input_Proj_Commit | 2015 | 2013 | 0 | 0 | 144599.7935 | 12428434.7138 | 257324.2188 | 0 | 0 | 0 | 0 | 12830358.726 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
6115 | Property | Strategic Property Acquisition at Surry Hills | PS Easements | Input_Proj_Commit | 2016 | 2013 | 87486.7873 | -108477.5607 | 0 | -5439.7446 | 0 | 0 | 0 | 0 | 0 | 0 | -26430.518 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
6276 | Property | Strategic Property Acquisition at Surry Hills | PS Easements | Input_Proj_Commit | 2016 | 2013 | -0.22879 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -0.22879 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
6966 | Property | Strategic Property Acquisition at Maraylya | PS Easements | Input_Proj_Commit | 2016 | 2013 | 28705.0543 | 184749.5194 | 80099.4567 | 98093.2719 | 0 | 0 | 0 | 0 | 0 | 0 | 391647.3023 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
7672 | Property | Property Extension at Richmond Vale | PS Easements | Input_Proj_Commit | 2016 | 2013 | 0 | 0 | 12743.8592 | -12406.8933 | 0 | 0 | 0 | 0 | 0 | 0 | 336.9659 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
P0002472 | Property | Strategic Property Acquisition at Surry Hills | PS Easements | Input_Proj_Commit | 2016 | 2013 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
8252 | Property | Strategic Property Adjoining Armidale 330kV Switchyard | PS Easements | Input_Proj_Commit | 2017 | 2013 | 0 | 0 | 0 | 0 | 1055029.2969 | 0 | 0 | 0 | 0 | 0 | 0 | 1055029.2969 | 0 | 100% | 100% | 100% | 100% | 100% | 0
P0002217 | Property | Strategic Property Acquisition in Sydney | PS Easements | Input_Proj_Commit | 2017 | 2013 | 0 | 14836.2659 | 225226.4884 | -208134.7218 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31928.0324 | 0 | 100% | 100% | 100% | 100% | 100% | 0
7300 | Substation Minor Projects | Connection to Lismore Substation | PS Easements | Input_Proj_Commit | 2014 | 2013 | 0 | 1.3718 | -997.8907 | -333.9773 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
7020 | Cable Minor Projects | Sydney Park Groundwater Treatment Plant | PS Replacement | Input_Proj_Commit | 2011 | 2013 | 0 | 1952923.7738 | 99028.9812 | 52506.0135 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
5120 | Cable Minor Projects | Tunnel Defects and Omissions Works | PS Replacement | Input_Proj_Commit | 2012 | 2013 | 1114299.6849 | 1320088.9031 | 1677808.2942 | 1747317.4982 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
7480 | Cable Minor Projects | Cable 42 Accessories | PS Replacement | Input_Proj_Commit | 2014 | 2013 | 0 | 11455.1702 | 550255.7354 | 543340.8348 | 2728366.799 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
7916 | Cable Minor Projects | 42 Cable Monitoring System Replacement | PS Replacement | Input_Proj_Commit | 2016 | 2013 | 0 | 0 | 0 | 0 | 0 | 216152.3438 | 54038.0859 | 0 | 0 | 0 | 270190.4297 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
8223 | Cable Minor Projects | 42 Cable Tunnel Accessories Replacement | PS Replacement | Input_Proj_Commit | 2018 | 2013 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 360253.9062 | 360253.9062 | 0 | 0 | 0 | 720507.8125 | 100% | 100% | 100% | 100% | 100% | 0
7641 | Capacitor Bank | Kempsey No.1 Capacitor Replacement | PS Replacement | Input_Proj_Commit | 2009 | 2013 | 0 | 0 | 7335.9625 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
5470 | Capacitor Bank | Dapto Substation 132kV Capacitor Banks Replacement | PS Replacement | Input_Proj_Commit | 2011 | 2013 | 1919.7576 | 7163.2138 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
6197 | Capacitor Bank | Wellington No.2 132kV Capacitor | PS Replacement | Input_Proj_Commit | 2011 | 2013 | 37961.7753 | 2908.093 | -41202.0108 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
6147 | Capacitor Bank | Griffith No.1 & No.2 33kV Capacitor Banks | PS Replacement | Input_Proj_Commit | 2013 | 2013 | -26382.2508 | -846.4304 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
6201 | Capacitor Bank | Sydney West No.1 Capacitor Bank | PS Replacement | Input_Proj_Commit | 2013 | 2013 | 4115.2434 | -6477.2158 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
6858 | Capacitor Bank | Griffith No.1 & No.2 33kV Capacitor Banks | PS Replacement | Input_Proj_Commit | 2013 | 2013 | 699267.9288 | 347918.4781 | 1098962.6862 | 738608.345 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
7273 | Capacitor Bank | Sydney West No.1 Capacitor Bank | PS Replacement | Input_Proj_Commit | 2013 | 2013 | 0 | 34898.4561 | 44567.0546 | 2284347.5629 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
6193 | Capacitor Bank | Coffs Harbour No.1 Capacitor | PS Replacement | Input_Proj_Commit | 2014 | 2013 | 13665.2878 | -38308.2312 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
7026 | Capacitor Bank | Coffs Harbour No.3 Capacitor | PS Replacement | Input_Proj_Commit | 2014 | 2013 | 0 | 250673.9685 | 426036.0437 | 1548908.4261 | 444983.5664 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
7474 | Capacitor Bank | Canberra No.1 132kV 80MVAr Capacitor | PS Replacement | Input_Proj_Commit | 2015 | 2013 | 0 | 11125.724 | 5988.9383 | 105034.1643 | 1834000.2764 | 1868466.6116 | 0 | 0 | 0 | 3824615.7146 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
7272 | Capacitor Bank | Sydney North No.1 & No.2 Capacitors | PS Replacement | Input_Proj_Commit | 2016 | 2013 | 0 | -196.9595 | -2607.0125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -2803.972 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
6712 | Capacitor Bank | New 66kV Capacitor at Panorama | PS Replacement | Input_Proj_Commit | 2017 | 2013 | -1.765 | -2747.448 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -2749.213 | 0 | 100% | 100% | 100% | 100% | 100% | 0
6196 | Capacitor Bank | Taree No.3 132kV Capacitor | PS Replacement | Input_Proj_Commit | 2018 | 2013 | 50.6504 | -2445.7986 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -2395.1482 | 100% | 100% | 100% | 100% | 100% | 0
7643 | Capacitor Bank | Taree No.4 & No.5 Capacitors | PS Replacement | Input_Proj_Commit | 2018 | 2013 | 0 | 0 | 7311.6087 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7311.6087 | 100% | 100% | 100% | 100% | 100% | 0
7757 | Capacitor Bank | Taree No.3 132kV Capacitor | PS Replacement | Input_Proj_Commit | 2018 | 2013 | 0 | 0 | 1826.3573 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1826.3573 | 100% | 100% | 100% | 100% | 100% | 0
6152 | Capacitor Bank | Canberra No.1 132kV 80MVAr Capacitor | PS Replacement | Input_Proj_Commit | 2019 | 2013 | 50.2146 | -3681.7668 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
7344 | Capacitor Bank | Broken Hill No.3 and No.4 Capacitors | PS Replacement | Input_Proj_Commit | 2020 | 2013 | 0 | 0 | 0 | 5984.2192 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
7333 | Capacitor Bank | Newcastle No.1 Capacitor | PS Replacement | Input_Proj_Commit | 2021 | 2013 | 0 | 0 | 2491.6316 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
7334 | Capacitor Bank | Newcastle No.2 Capacitor | PS Replacement | Input_Proj_Commit | 2021 | 2013 | 0 | 0 | 470.8713 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
5642 | Communications | MMRN Modifications - Sydney - Newcastle | PS Replacement | Input_Proj_Commit | 2009 | 2013 | -32.6193 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
5946 | Communications | Port Macquarie & Taree Radio Network Modification | PS Replacement | Input_Proj_Commit | 2009 | 2013 | -30.6038 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
5947 | Communications | Kempsey & Nambucca Microwave Radio Modification | PS Replacement | Input_Proj_Commit | 2009 | 2013 | -1.0459 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
5948 | Communications | Koolkhan Microwave Radio Network Modification | PS Replacement | Input_Proj_Commit | 2009 | 2013 | -0.37043 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
4167 | Communications | OPGW Backup North & West NSW | PS Replacement | Input_Proj_Commit | 2011 | 2013 | -79331.508 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
4339 | Communications | OPGW Backup - Southern Region | PS Replacement | Input_Proj_Commit | 2011 | 2013 | -80639.3209 | 926.8114 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
5488 | Communications | North Coast Microwave Radio Network - Extension To Coffs Harbour 330 and Lismore 330 Substations | PS Replacement | Input_Proj_Commit | 2011 | 2013 | 1140.5653 | 104358.4145 | 73415.3046 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
5607 | Communications | South Western NSW Replacement | PS Replacement | Input_Proj_Commit | 2011 | 2013 | -20.9727 | -119473.0949 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
5731 | Communications | Augmentation of Fault Clearing Times on Selected Transmission Line | PS Replacement | Input_Proj_Commit | 2011 | 2013 | -41664.8646 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
6037 | Communications | Mount Piper 132kV - 330kV Substation No.2 Intertrip On 94Y Line | PS Replacement | Input_Proj_Commit | 2011 | 2013 | -0.71906 | 0 | -10320.4849 | -4294.9853 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
6154 | Communications | SCADA Comms to Beryl Substation | PS Replacement | Input_Proj_Commit | 2011 | 2013 | 0 | -1886.1622 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
6243 | Communications | North Coast Microwave Replacement | PS Replacement | Input_Proj_Commit | 2011 | 2013 | 48260.0487 | 3396.0575 | 0 | -95353.195 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
6245 | Communications | Replace PNX Telephone Network - Technical Services | PS Replacement | Input_Proj_Commit | 2011 | 2013 | 1395.3316 | 1446.0392 | -8236.2713 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
6281 | Communications | Communications Upgrade and Replacement | PS Replacement | Input_Proj_Commit | 2011 | 2013 | 18740542.8623 | 6057219.1611 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
6589 | Communications | Armidale to Dumaresq OPGW PSR 216 | PS Replacement | Input_Proj_Commit | 2011 | 2013 | -11.6793 | -16873.7047 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
6642 | Communications | Augmentation of Optical Terminal Equipment Between Armidale & Dumaresq | PS Replacement | Input_Proj_Commit | 2011 | 2013 | -1.3074 | 0 | 0 | -1871.2327 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
6772 | Communications | OPGW Installation For Protection at Murray and Lower Tumut Switching Station | PS Replacement | Input_Proj_Commit | 2011 | 2013 | 12614.4856 | -13552.2647 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
6842 | Communications | Lismore 330 Substation - Augmentation of Communications Services | PS Replacement | Input_Proj_Commit | 2011 | 2013 | 720.2074 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
6848 | Communications | Communications Upgrade & Replacement (SP9) | PS Replacement | Input_Proj_Commit | 2011 | 2013 | 2586020.9214 | 2499654.3847 | 1243017.6821 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
6960 | Communications | Western Microwave Extension - TSP 46 & 47 | PS Replacement | Input_Proj_Commit | 2011 | 2013 | 3340790.6953 | 6551585.2438 | 1880326.6062 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
7287 | Communications | Southern NSW Microwave Radio | PS Replacement | Input_Proj_Commit | 2011 | 2013 | 0 | 2816.2594 | -3255.5404 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
7288 | Communications | Beryl SCADA Microwave Radio | PS Replacement | Input_Proj_Commit | 2011 | 2013 | 0 | 1888.055 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
8022 | Communications | Dumaresq Protection & Communication Replacement | PS Replacement | Input_Proj_Commit | 2014 | 2013 | 0 | 0 | 0 | 8978.0434 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
7462 | Communications | Spur Microwave System Replacement | PS Replacement | Input_Proj_Commit | 2015 | 2013 | 13754.1248 | -1890.8942 | 30215.5429 | 434245.6082 | 0 | 0 | 0 | 0 | 0 | 476324.3817 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
7466 | Communications | Albury to Hume District Communications Augmentation | PS Replacement | Input_Proj_Commit | 2017 | 2013 | 0 | 0 | 0 | 71865.9027 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 71865.9027 | 0 | 100% | 100% | 100% | 100% | 100% | 0
6056 | Control System | Modification of Autoreclose Facilities | PS Replacement | Input_Proj_Commit | 2009 | 2013 | -0.076264 | 0 | 0 | -2329.9785 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
6380 | Control System | Jindera to Albury Transmission Lines | PS Replacement | Input_Proj_Commit | 2016 | 2013 | 49391.4732 | -72083.8415 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -22692.3683 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
7670 | Control System | Modification of Auto Reclose Facilities At Ingleburn and Panorama | PS Replacement | Input_Proj_Commit | 2017 | 2013 | 0 | 0 | 408.2308 | -397.437 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10.7939 | 0 | 100% | 100% | 100% | 100% | 100% | 0
6847 | Fault Recorders | Travelling Wave Fault Locators Installation | PS Replacement | Input_Proj_Commit | 2011 | 2013 | 97023.6053 | 56084.9594 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
7788 | Oil Containment | Murray Oil Containment Upgrade | PS Replacement | Input_Proj_Commit | 2014 | 2013 | 0 | 0 | 328.5521 | 85854.0318 | 2946394.6761 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
8023 | Oil Containment | Beryl Oil Containment Upgrade | PS Replacement | Input_Proj_Commit | 2016 | 2013 | 0 | 0 | 0 | 2046.1398 | 0 | 0 | 0 | 0 | 0 | 0 | 2046.1398 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
8027 | Oil Containment | Muswellbrook Oil Containment Upgrade | PS Replacement | Input_Proj_Commit | 2016 | 2013 | 0 | 0 | 0 | 10029.14 | 0 | 0 | 0 | 0 | 0 | 0 | 10029.14 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
8078 | Oil Containment | Inverell Oil Containment Upgrade | PS Replacement | Input_Proj_Commit | 2016 | 2013 | 0 | 0 | 0 | 1264.6173 | 0 | 0 | 0 | 0 | 0 | 0 | 1264.6173 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
5641 | Oil Containment | Yass Oil Contaimnent Upgrade | PS Replacement | Input_Proj_Commit | 2017 | 2013 | -9098.1675 | 228.9779 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -8869.1896 | 0 | 100% | 100% | 100% | 100% | 100% | 0
8032 | Oil Containment | Sydney South Oil Containment Upgrade | PS Replacement | Input_Proj_Commit | 2018 | 2013 | 0 | 0 | 0 | 324.6537 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 324.6537 | 100% | 100% | 100% | 100% | 100% | 0
7680 | Property | Yass Strategic Site Acquisition | PS Replacement | Input_Proj_Commit | 2014 | 2013 | 0 | 0 | 17551.4458 | -17087.3643 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
6916 | Reactor Installation | Vales Point to Munmorah 330kV Line 23 Series Reactor Replacement | PS Replacement | Input_Proj_Commit | 2009 | 2013 | 0 | 7231.2596 | -7031.9518 | -53.1215 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
5577 | Reactor Replacement | Munmorah Substation Line 23 330kV Reactor Replacement | PS Replacement | Input_Proj_Commit | 2009 | 2013 | -542592.6764 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
5627 | Reactor Replacement | Tamworth Substation - Replacement of Shunt Reactors | PS Replacement | Input_Proj_Commit | 2009 | 2013 | 49414.1891 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
6706 | Reactor Replacement | Beaconsfield Shunt Reactor | PS Replacement | Input_Proj_Commit | 2009 | 2013 | -192.6109 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
7849 | Reactor Replacement | Armidale No.1 330kV 50MVAr Reactor Replacement | PS Replacement | Input_Proj_Commit | 2014 | 2013 | 0 | 0 | 2531.075 | 1385824.7363 | 3384387.9992 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
7346 | Reactor Replacement | Buronga X2 220kV Reactor | PS Replacement | Input_Proj_Commit | 2016 | 2013 | 0 | 0 | 4199.3566 | 51968.7726 | 0 | 0 | 0 | 0 | 0 | 0 | 56168.1292 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
7342 | Reactor Replacement | Broken Hill No.1 & No.2 220kV Reactors | PS Replacement | Input_Proj_Commit | 2018 | 2013 | 0 | 0 | 3391.3464 | 43518.7479 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 46910.0943 | 100% | 100% | 100% | 100% | 100% | 0
7325 | Reactor Replacement | Beaconsfield West No.1 132kV Reactor | PS Replacement | Input_Proj_Commit | 2019 | 2013 | 0 | 0 | 98.6865 | 21271.0035 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
6922 | Reinforcement of Supply to the Orange Area | 944 Line Wallerawang to Orange North Rebuild | PS Replacement | Input_Proj_Commit | 2014 | 2013 | 0 | 18581.1869 | -18228.4646 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
6251 | SCADA | SCADA to Tumut | PS Replacement | Input_Proj_Commit | 2015 | 2013 | 3954.609 | -6195.4091 | -7666.9636 | 0 | 0 | 0 | 0 | 0 | 0 | -9907.7637 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
6255 | SCADA | SCADA to Molong | PS Replacement | Input_Proj_Commit | 2015 | 2013 | 0 | -1244.4009 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1244.4009 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
7303 | SCADA | SCADA to Molong | PS Replacement | Input_Proj_Commit | 2015 | 2013 | 0 | 1245.645 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1245.645 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
7318 | SCADA | SCADA to Tumut | PS Replacement | Input_Proj_Commit | 2015 | 2013 | 0 | 52247.8964 | 7666.9636 | 0 | 0 | 0 | 0 | 0 | 0 | 59914.86 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
6277 | SCADA | SCADA to Albury | PS Replacement | Input_Proj_Commit | 2016 | 2013 | -1.1222 | -2412.2383 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -2413.3604 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
7279 | SCADA | SCADA to Albury | PS Replacement | Input_Proj_Commit | 2016 | 2013 | 0 | 5599.9155 | 0 | 459.5371 | 0 | 0 | 0 | 0 | 0 | 0 | 6059.4526 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
6247 | SCADA | SCADA to Cooma | PS Replacement | Input_Proj_Commit | 2017 | 2013 | -0.92607 | 0 | 0 | -1271.922 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1272.8481 | 0 | 100% | 100% | 100% | 100% | 100% | 0
7297 | SCADA | SCADA to Hume | PS Replacement | Input_Proj_Commit | 2017 | 2013 | 0 | 64725.9544 | 239.578 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 64965.5324 | 0 | 100% | 100% | 100% | 100% | 100% | 0
6278 | SCADA | ANM SCADA | PS Replacement | Input_Proj_Commit | 2018 | 2013 | -1.242 | -1758.7797 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1760.0217 | 100% | 100% | 100% | 100% | 100% | 0
7280 | SCADA | ANM SCADA | PS Replacement | Input_Proj_Commit | 2018 | 2013 | 0 | 5695.5879 | -5581.562 | 428.766 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 542.792 | 100% | 100% | 100% | 100% | 100% | 0
6461 | Secondary System Renewal | Lismore Substation Control System Replacement | PS Replacement | Input_Proj_Commit | 2011 | 2013 | 1033049.8682 | 943696.8984 | 798.225 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
6715 | Secondary System Renewal | Dapto Secondary System Replacement | PS Replacement | Input_Proj_Commit | 2014 | 2013 | 4910509.1817 | 3266328.1443 | 1526000.5701 | 1253297.5303 | 1310096.494 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
7083 | Secondary System Renewal | Guthega Secondary System Renewal | PS Replacement | Input_Proj_Commit | 2014 | 2013 | 0 | 16041.7364 | 5785.5524 | 594238.585 | 2617698.2195 | 566135.6777 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
7455 | Secondary System Renewal | Guthega Secondary System Renewal | PS Replacement | Input_Proj_Commit | 2014 | 2013 | 0 | 33208.7642 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
7669 | Secondary System Renewal | Yass Secondary System Renewal | PS Replacement | Input_Proj_Commit | 2014 | 2013 | 0 | 0 | 0 | 1032.7537 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
7151 | Secondary System Renewal | Tumut Secondary System Renewal | PS Replacement | Input_Proj_Commit | 2015 | 2013 | 0 | 31277.8762 | 162943.6077 | 2048280.685 | 14035390.6782 | 0 | 0 | 0 | 0 | 16277892.8471 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
7301 | Secondary System Renewal | Molong Secondary System Renewal | PS Replacement | Input_Proj_Commit | 2015 | 2013 | 0 | 37603.0604 | -36850.3518 | 0 | 0 | 0 | 0 | 0 | 0 | 752.7086 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
6985 | Secondary System Renewal | Sydney West Secondary System Renewal | PS Replacement | Input_Proj_Commit | 2016 | 2013 | 48283.8541 | 730585.1458 | 2186776.4835 | 4895161.1361 | 20158116.4743 | 5365799.9213 | 3524422.6526 | 0 | 0 | 0 | 36909145.6677 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
7061 | Secondary System Renewal | Griffith Secondary System Renewal | PS Replacement | Input_Proj_Commit | 2016 | 2013 | 0 | 14281.9783 | 678777.4197 | 1634771.4468 | 11602571.9226 | 3856354.2373 | 0 | 0 | 0 | 0 | 17786757.0048 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
7353 | Secondary System Renewal | Balranald Secondary System Renewal | PS Replacement | Input_Proj_Commit | 2016 | 2013 | 0 | -360.061 | 408.6268 | 46273.769 | 0 | 0 | 0 | 0 | 0 | 0 | 46322.3349 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
7062 | Secondary System Renewal | Kangaroo Valley Secondary System Renewal | PS Replacement | Input_Proj_Commit | 2016 | 2013 | 0 | 14684.2236 | 11809.8803 | -25325.4814 | 0 | 0 | 0 | 0 | 0 | 0 | 1168.6225 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
7350 | Secondary System Renewal | Albury Secondary System Renewal | PS Replacement | Input_Proj_Commit | 2016 | 2013 | 0 | 0 | 0 | 21893.8313 | 0 | 0 | 0 | 0 | 0 | 0 | 21893.8313 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
7366 | Secondary System Renewal | Hume Secondary System Renewal | PS Replacement | Input_Proj_Commit | 2017 | 2013 | 1468.3057 | -61184.2562 | 0 | 4638.4892 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -55077.4614 | 0 | 100% | 100% | 100% | 100% | 100% | 0
7365 | Secondary System Renewal | Deniliquin Secondary System Renewal | PS Replacement | Input_Proj_Commit | 2018 | 2013 | 0 | 0 | 0 | 4797.813 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4797.813 | 100% | 100% | 100% | 100% | 100% | 0
7638 | Secondary System Renewal | Sydney North Secondary System Renewal | PS Replacement | Input_Proj_Commit | 2019 | 2013 | 0 | 0 | 0 | 34534.4753 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
6928 | Secondary System Renewal | Liddell Secondary System Renewal | PS Replacement | Input_Proj_Commit | 2020 | 2013 | 0 | 2484.7183 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
7351 | Secondary System Renewal | Beryl Secondary System Renewal | PS Replacement | Input_Proj_Commit | 2020 | 2013 | 0 | 0 | -385.2213 | 375.0561 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
7354 | Secondary System Renewal | Buronga Secondary System Renewal | PS Replacement | Input_Proj_Commit | 2020 | 2013 | 0 | 0 | 385.2213 | 3011.1627 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
7651 | Secondary System Renewal | Liddell Secondary System Renewal | PS Replacement | Input_Proj_Commit | 2020 | 2013 | 0 | 0 | 0 | 16129.5345 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
7667 | Secondary System Renewal | Avon Secondary System Renewal | PS Replacement | Input_Proj_Commit | 2021 | 2013 | 0 | 0 | 0 | 21751.6229 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
6364 | Substation Minor Projects | Double Breaker Autoreclose Modifications at Various Sites | PS Replacement | Input_Proj_Commit | 2009 | 2013 | 476.6846 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
4025 | Substation Minor Projects | Communications Upgrade and Replacement | PS Replacement | Input_Proj_Commit | 2011 | 2013 | 0 | 0 | 274119.6603 | -229214.687 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
6874 | Substation Minor Projects | Tumut 132/66kV Synchronism-Check System on Feeder 850 | PS Replacement | Input_Proj_Commit | 2011 | 2013 | 107852.9506 | 6258.6271 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
7827 | Substation Minor Projects | Replacement of Line 11 Wave Trap at Sydney South | PS Replacement | Input_Proj_Commit | 2014 | 2013 | 0 | 0 | 0 | 27650.1436 | 153537.6725 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
P0000885 | Substation Minor Projects | Armidale AC System Replacement | PS Replacement | Input_Proj_Commit | 2014 | 2013 | 0 | 0 | 0 | 0 | 417399.6144 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
P0002189 | Substation Minor Projects | Modifications of Secondary Systems for a 66kV Switchbay at Beryl | PS Replacement | Input_Proj_Commit | 2014 | 2013 | 0 | 0 | 0 | 0 | 468330.0781 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
6106 | Substation Minor Projects | Newcastle Substation 330kV Bus Coupling | PS Replacement | Input_Proj_Commit | 2015 | 2013 | 4236.2204 | 0 | -16189.1966 | 0 | 0 | 0 | 0 | 0 | 0 | -11952.9762 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
8176 | Substation Minor Projects | Lower Tumut 11kV Switchboard Replacement | PS Replacement | Input_Proj_Commit | 2015 | 2013 | 0 | 0 | 0 | 0 | 0 | 184810.2539 | 0 | 0 | 0 | 184810.2539 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
7682 | Substation Minor Projects | Murray 11kV Switchboard Replacement | PS Replacement | Input_Proj_Commit | 2015 | 2013 | 0 | 0 | 0 | 0 | 0 | 184810.2539 | 0 | 0 | 0 | 184810.2539 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
8083 | Substation Minor Projects | Dapto 415V AC System Replacement | PS Replacement | Input_Proj_Commit | 2015 | 2013 | 0 | 0 | 0 | 7203.4459 | 0 | 0 | 0 | 0 | 0 | 7203.4459 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
6040 | Substation Minor Projects | Sydney West 132kV Disconnector Replacement | PS Replacement | Input_Proj_Commit | 2016 | 2013 | 32729.8483 | 174748.821 | 175234.9574 | 17560.3745 | 0 | 0 | 0 | 0 | 0 | 0 | 400274.0012 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
5811 | Substation Minor Projects | Tamworth 66kV Line Bay | PS Replacement | Input_Proj_Commit | 2017 | 2013 | 0 | 0 | -19048.7716 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -19048.7716 | 0 | 100% | 100% | 100% | 100% | 100% | 0
8120 | Substation Minor Projects | Tamworth 66kV Line Bay | PS Replacement | Input_Proj_Commit | 2017 | 2013 | 0 | -3916.9017 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -3916.9017 | 0 | 100% | 100% | 100% | 100% | 100% | 0
8073 | Substation Minor Projects | Removal of SICAM from Haymarket GIS | PS Replacement | Input_Proj_Commit | 2017 | 2013 | 0 | 0 | 0 | 12238.4285 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12238.4285 | 0 | 100% | 100% | 100% | 100% | 100% | 0
5738 | Substation Minor Projects | Supply to Nabiac | PS Replacement | Input_Proj_Commit | 2018 | 2013 | 0 | 0 | -1509.3724 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1509.3724 | 100% | 100% | 100% | 100% | 100% | 0
6432 | Substation Minor Projects | Taree 33kV Line Bay | PS Replacement | Input_Proj_Commit | 2018 | 2013 | 0 | -1165.4342 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1165.4342 | 100% | 100% | 100% | 100% | 100% | 0
7315 | Substation Minor Projects | Taree 33kV Line Bay | PS Replacement | Input_Proj_Commit | 2018 | 2013 | 0 | 1166.6039 | -1143.2631 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23.3408 | 100% | 100% | 100% | 100% | 100% | 0
6915 | Substation Minor Projects | Canberra 330kV Substation - Uprating to 362kV | PS Replacement | Input_Proj_Commit | 2019 | 2013 | 0 | 0 | 97.1234 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
7029 | Substation Minor Projects | Junee East Switching Station Second Supply to Temora | PS Replacement | Input_Proj_Commit | 2020 | 2013 | 0 | 0 | -478.6661 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
8062 | Substation Minor Projects | Wagga 132 - 99X Line Wave Trap | PS Replacement | Input_Proj_Commit | 2020 | 2013 | 0 | 0 | 0 | 1228.0228 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
5430 | Substation Renewal | Glen Innes 132kV Substation Rebuild | PS Replacement | Input_Proj_Commit | 2009 | 2013 | -20834.0666 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
7337 | Substation Renewal | Kempsey 132kV Substation Condition | PS Replacement | Input_Proj_Commit | 2009 | 2013 | 0 | 0 | 0 | 157.8223 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
6313 | Substation Renewal | Beaconsfield West Substation Renewal | PS Replacement | Input_Proj_Commit | 2013 | 2013 | -89.872 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
6570 | Substation Renewal | Beaconsfield West Substation Renewal | PS Replacement | Input_Proj_Commit | 2013 | 2013 | 24669656.0921 | 55578022.9081 | 34844953.4499 | 11657305.6492 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
7563 | Substation Renewal | Beaconsfield West Substation Renewal | PS Replacement | Input_Proj_Commit | 2013 | 2013 | 0 | 0 | 2548.7072 | -2481.3178 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
6336 | Substation Renewal | Queanbeyan Substation Renewal | PS Replacement | Input_Proj_Commit | 2014 | 2013 | 15803604.2305 | 444139.5363 | 736987.5273 | 1251636.2471 | 821308.9141 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
6314 | Substation Renewal | Upper Tumut Switching Station Renewal | PS Replacement | Input_Proj_Commit | 2015 | 2013 | 489644.6829 | 6336185.1476 | 10294213.8121 | 12470986.846 | 11192433.8947 | 4106930.9385 | 0 | 0 | 0 | 44890395.3218 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 40783464.3833
6838 | Substation Renewal | Wallerawang 132 Substation Renewal | PS Replacement | Input_Proj_Commit | 2015 | 2013 | 710576.5952 | 3385052.0126 | 14895767.1717 | 24631955.0725 | 21427455.4951 | 756419.0098 | 0 | 0 | 0 | 65807225.3569 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
6931 | Substation Renewal | Lower Tumut Substation Renewal | PS Replacement | Input_Proj_Commit | 2015 | 2013 | 0 | 0 | -233.9402 | 0 | 0 | 0 | 0 | 0 | 0 | -233.9402 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
7479 | Substation Renewal | Yanco Substation Renewal | PS Replacement | Input_Proj_Commit | 2016 | 2013 | 0 | 796.5684 | 154561.7868 | 146715.8291 | 1631155.8972 | 8532527.2726 | 3784578.935 | 0 | 0 | 0 | 14250336.2891 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
6912 | Substation Renewal | Tamworth 132 Substation Renewal | PS Replacement | Input_Proj_Commit | 2017 | 2013 | 6306.8724 | 73735.3154 | 160101.7275 | 620375.7209 | 1807542.3752 | 20055759.9741 | 9057631.3417 | 0 | 0 | 0 | 0 | 31781453.3271 | 0 | 100% | 100% | 100% | 100% | 100% | 0
6965 | Substation Renewal | Cooma Substation Renewal | PS Replacement | Input_Proj_Commit | 2017 | 2013 | 0 | 249473.7724 | 117285.1551 | 1066498.55 | 2039060.145 | 20403717.5211 | 5914594.6019 | 0 | 0 | 0 | 0 | 29790629.7455 | 0 | 100% | 100% | 100% | 100% | 100% | 0
7027 | Substation Renewal | Orange Substation Renewal | PS Replacement | Input_Proj_Commit | 2017 | 2013 | 0 | 145446.9308 | 266301.03 | 281693.8354 | 2151214.9675 | 3109636.8868 | 12192346.7566 | 0 | 0 | 0 | 0 | 18146640.4072 | 0 | 100% | 100% | 100% | 100% | 100% | 0
6962 | Substation Renewal | Burrinjuck Substation Renewal | PS Replacement | Input_Proj_Commit | 2017 | 2013 | 0 | 38250.8298 | -37254.4455 | -224.64 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 771.7443 | 0 | 100% | 100% | 100% | 100% | 100% | 0
7378 | Substation Renewal | Vales Point Substation Renewal | PS Replacement | Input_Proj_Commit | 2018 | 2013 | 6766.7134 | 4319.0726 | 273459.7736 | 196906.4938 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 481452.0534 | 100% | 100% | 100% | 100% | 100% | 0
8076 | Substation Renewal | Taree Substation 33kV Switchyard Renewal | PS Replacement | Input_Proj_Commit | 2018 | 2013 | 0 | -97.5333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -97.5333 | 100% | 100% | 100% | 100% | 100% | 0
6350 | Substation Renewal | Canberra Substation Renewal | PS Replacement | Input_Proj_Commit | 2019 | 2013 | 0 | 0 | -171686.8797 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
7398 | Substation Renewal | Canberra Substation Renewal | PS Replacement | Input_Proj_Commit | 2019 | 2013 | 0 | 0 | 392.985 | -186.7875 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
7406 | Substation Renewal | Wagga 132kV Substation Renewal | PS Replacement | Input_Proj_Commit | 2020 | 2013 | 0 | 0 | 0 | -2.2929 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
7544 | Substation Renewal | Wagga 132kV Substation Renewal | PS Replacement | Input_Proj_Commit | 2020 | 2013 | 31014.8821 | 12589.3622 | 51.6463 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
6914 | Substation Renewal | Wagga 132kV Substation Renewal | PS Replacement | Input_Proj_Commit | 2020 | 2013 | 11087.7397 | 2733.8686 | -10866.8039 | 35502.6229 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
7678 | Substation Renewal | Munmorah Substation Renewal | PS Replacement | Input_Proj_Commit | 2020 | 2013 | 82150.8575 | 82744.7933 | 75955.8835 | -96542.9188 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
7298 | SVC Control System Replacement | Kemps Creek SVC Control System Replacement | PS Replacement | Input_Proj_Commit | 2015 | 2013 | 88831.3596 | 1329.365 | 70677.1234 | 91965.7993 | -328859.8444 | 0 | 0 | 0 | 0 | -76056.1971 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | -76056.1971
7822 | SVC Control System Replacement | Broken Hill SVC Control System Replacement | PS Replacement | Input_Proj_Commit | 2015 | 2013 | 10922.5621 | 0 | 93300.0667 | 321944.5181 | 9210179.4193 | 4571701.3262 | 0 | 0 | 0 | 14208047.8924 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
7091 | SVC Control System Replacement | Armidale SVC Control System Replacement | PS Replacement | Input_Proj_Commit | 2018 | 2013 | 3476.8023 | -250.0329 | -30461.6757 | 0.010145 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -27234.8962 | 100% | 100% | 100% | 100% | 100% | 0
5533 | Transformer Replacement | Sydney West No.2 Transformer Replacement | PS Replacement | Input_Proj_Commit | 2009 | 2013 | 46820.5165 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
6393 | Transformer Replacement | Kempsey 132kV Substation 66/33kV 2 x 25MVA Transformer Replacements | PS Replacement | Input_Proj_Commit | 2009 | 2013 | -2.5603 | 1246.9104 | 0 | -4867.5526 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
6415 | Transformer Replacement | Kempsey 2x60MVA 132/33kV Transformer | PS Replacement | Input_Proj_Commit | 2009 | 2013 | 190653.8959 | -774.7053 | -14290.8513 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
6694 | Transformer Replacement | Tuggerah Substation No.1 Transformer Replacement | PS Replacement | Input_Proj_Commit | 2009 | 2013 | 680786.5069 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
5677 | Transformer Replacement | Sydney South No.1 & No.2 Transformers | PS Replacement | Input_Proj_Commit | 2011 | 2013 | 1744455.2603 | 300600.4925 | 0 | 102655.3559 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
5878 | Transformer Replacement | Orange No.1 & No.2 Transformer Replacement | PS Replacement | Input_Proj_Commit | 2011 | 2013 | 3717546.2384 | 2038924.6518 | 78782.4865 | 50.6358 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
6172 | Transformer Replacement | Wallerawang 132kV Transformer Replacements | PS Replacement | Input_Proj_Commit | 2012 | 2013 | 1708.1678 | 483.1793 | -2718.6836 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
6721 | Transformer Replacement | Wallerawang 330/132kV Transformer Replacements & Relocation | PS Replacement | Input_Proj_Commit | 2012 | 2013 | 4378132.1518 | 15300738.8147 | 4248930.4321 | 17063.5935 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
6834 | Transformer Replacement | Narrabri No.1 & No.3 Transformer Replacements | PS Replacement | Input_Proj_Commit | 2013 | 2013 | 598021.8961 | 1336927.7077 | 1949895.8978 | 7429929.0733 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
5619 | Transformer Replacement | Yass No.3 Transformer | PS Replacement | Input_Proj_Commit | 2014 | 2013 | 66083.7346 | -66068.8563 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
5889 | Transformer Replacement | Sydney East No.4 Transformer | PS Replacement | Input_Proj_Commit | 2014 | 2013 | 6989.9935 | 0 | -689345.3087 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
6851 | Transformer Replacement | Dapto Substation Temporary Transformer Installation (System Spare) | PS Replacement | Input_Proj_Commit | 2014 | 2013 | 45658.3466 | 9441.9871 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
6984 | Transformer Replacement | Dapto Substation Temporary Transformer Installation (System Spare) | PS Replacement | Input_Proj_Commit | 2014 | 2013 | 100886.6753 | 914640.3622 | 566328.1234 | 1911404.0939 | 1251730.5853 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
7140 | Transformer Replacement | Yass No.3 Transformer | PS Replacement | Input_Proj_Commit | 2014 | 2013 | 0 | 353135.1084 | 1686194.3043 | 568056.6572 | 1349836.1539 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
7262 | Transformer Replacement | Sydney East No.4 Transformer | PS Replacement | Input_Proj_Commit | 2014 | 2013 | 0 | 0 | 370887.855 | 3742676.3696 | 9850331.0438 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
7628 | Transformer Replacement | Surge Arresters Installation At 330kV Line Entries | PS Replacement | Input_Proj_Commit | 2014 | 2013 | 0 | 0 | 467292.3477 | 443955.0354 | 1003814.0062 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
6919 | Transformer Replacement | Kemps Creek Replace No.1 and No.2 Transformer VCC | PS Replacement | Input_Proj_Commit | 2015 | 2013 | 0 | 0 | -54.585 | 0 | 0 | 0 | 0 | 0 | 0 | -54.585 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
7085 | Transformer Replacement | Yanco Transformer Replacement | PS Replacement | Input_Proj_Commit | 2015 | 2013 | 11039.6278 | 43578.1475 | 554003.5412 | 3683048.7838 | 7167393.1681 | 1032092.0068 | 0 | 0 | 0 | 12491155.2753 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
7471 | Transformer Replacement | Newcastle No.1, No.2 and No.3 Transformer Replacement | PS Replacement | Input_Proj_Commit | 2015 | 2013 | 45756.6622 | 843.0594 | 425078.5551 | 5017952.2629 | 16265314.7427 | 2679567.1137 | 0 | 0 | 0 | 24434512.396 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
7092 | Transformer Replacement | Griffith Transformer Replacement | PS Replacement | Input_Proj_Commit | 2016 | 2013 | 37990.9736 | 3177.522 | 40941.7785 | 1505362.0928 | 5822975.7785 | 4343423.3547 | 0 | 0 | 0 | 0 | 11753871.5001 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
7356, 7357, 7563 | Transformer Replacement | Beaconsfield West No.1 & No.2 330kV Transformers | PS Replacement | Input_Proj_Commit | 2018 | 2013 | 0 | 0 | 0 | 1461669.6856 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1461669.6856 | 100% | 100% | 100% | 100% | 100% | 0
7284 | Transformer Replacement | Canberra No.2 Transformer Replacement | PS Replacement | Input_Proj_Commit | 2019 | 2013 | 1010.6981 | 4.2535 | -6492.1667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
6379 | Transformer Replacement | Wagga 132 No.2 Transformer Replacement | PS Replacement | Input_Proj_Commit | 2020 | 2013 | 5408.5988 | 0 | 0 | -13101.8956 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
6021 | Transmission Line Life Extension | 11 Line Dapto to Sydney South Life Extension | PS Replacement | Input_Proj_Commit | 2013 | 2013 | 4370.7833 | 1836044.5215 | 2886618.1413 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
7779 | Transmission Line Life Extension | 21 Line Sydney North to Tuggerah Life Extension | PS Replacement | Input_Proj_Commit | 2015 | 2013 | 0 | 0 | 0 | 0 | 0 | 3552103.5156 | 0 | 0 | 0 | 3552103.5156 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
7706 | Transmission Line Life Extension | 8 Line Dapto to Marulan Life Extension | PS Replacement | Input_Proj_Commit | 2016 | 2013 | 0 | 0 | 0 | 0 | 0 | 0 | 1974191.4062 | 0 | 0 | 0 | 1974191.4062 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
7716 | Transmission Line Life Extension | 24 Line Vales Point to Eraring Life Extension | PS Replacement | Input_Proj_Commit | 2016 | 2013 | 0 | 0 | 0 | 0 | 0 | 1162899.6094 | 0 | 0 | 1163620.1172 | 0 | 2326519.7266 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
7322 | Transmission Line Life Extension | 11 Line Dapto to Sydney South Life Extension | PS Replacement | Input_Proj_Commit | 2017 | 2013 | 0 | 0 | 0 | 0 | 0 | 0 | 2171610.5469 | 0 | 0 | 0 | 0 | 2171610.5469 | 0 | 100% | 100% | 100% | 100% | 100% | 0
7703 | Transmission Line Life Extension | 22 Line Vales Point to Structure 136 Life Extension | PS Replacement | Input_Proj_Commit | 2017 | 2013 | 0 | 0 | 0 | 0 | 0 | 0 | 3109711.7188 | 3110432.2266 | 0 | 0 | 0 | 6220143.9453 | 0 | 100% | 100% | 100% | 100% | 100% | 0
7720 | Transmission Line Life Extension | 18 Line Kangaroo Valley to Dapto Life Extension | PS Replacement | Input_Proj_Commit | 2017 | 2013 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1480643.5547 | 0 | 0 | 0 | 1480643.5547 | 0 | 100% | 100% | 100% | 100% | 100% | 0
7915 | Transmission Line Life Extension | 17 Line Avon to Picton Rd Life Extension | PS Replacement | Input_Proj_Commit | 2018 | 2013 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 792558.5938 | 0 | 0 | 0 | 792558.5938 | 100% | 100% | 100% | 100% | 100% | 0
7697 | Transmission Line Life Extension | 26 Line Sydney North to Vales Point Life Extension | PS Replacement | Input_Proj_Commit | 2019 | 2013 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1085805.2734 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
7715 | Transmission Line Life Extension | 959/92Z Line Sydney North to Sydney East Life Extension | PS Replacement | Input_Proj_Commit | 2019 | 2013 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3059996.6797 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
7727 | Transmission Line Life Extension | 10 Line Avon to Dapto Life Extension | PS Replacement | Input_Proj_Commit | 2019 | 2013 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1085805.2734 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
7728 | Transmission Line Life Extension | 23 Line Munmorah to Vales Point Life Extension | PS Replacement | Input_Proj_Commit | 2019 | 2013 | 0 | 0 | 0 | 0 | 0 | 0 | 1085805.2734 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
7761 | Transmission Line Life Extension | 2M Line Munmorah to Tuggerah Life Extension | PS Replacement | Input_Proj_Commit | 2019 | 2013 | 0 | 0 | 0 | 0 | 0 | 789676.5625 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
7914 | Transmission Line Life Extension | 16 Line Structure 104 to 159 Life Extension | PS Replacement | Input_Proj_Commit | 2019 | 2013 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
7912 | Transmission Line Life Extension | 93 Line Eraring to Newcastle Life Extension | PS Replacement | Input_Proj_Commit | 2021 | 2013 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
7911 | Transmission Line Life Extension | 90 Line Eraring to Newcastle Life Extension | PS Replacement | Input_Proj_Commit | 2022 | 2013 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
P0002047 | Transmission Line Minor Projects | Reconstruction of Geehi Tee | PS Replacement | Input_Proj_Commit | 2015 | 2013 | 0 | 0 | 0 | 0 | 411718.75 | 1296914.0625 | 0 | 0 | 0 | 1708632.8125 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
5966 | Transmission Line Renewal | 990 Line Yass to Wagga 132kV Transmission Line Rebuild | PS Replacement | Input_Proj_Commit | 2010 | 2013 | 9205675.8643 | 707178.419 | 225315.9941 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
7264 | Transmission Line Renewal | 944 Line Wallerawang to Orange North Rebuild | PS Replacement | Input_Proj_Commit | 2014 | 2013 | 14319.7226 | 76744.8656 | 534151.2091 | 1564708.1937 | 3405662.8142 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
7725 | Transmission Line Renewal | 99J Yanco to Griffith 132kV Line Partial Rebuild | PS Replacement | Input_Proj_Commit | 2019 | 2013 | 0 | 0 | 0 | 0 | 154394.5312 | 216152.3438 | 2269599.6094 | 2233574.2188 | 2305625 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
7744 | Transmission Line Wood Pole Replacement | Line 85 Armidale to Tamworth Temporary Pole Replacement | PS Replacement | Input_Proj_Commit | 2015 | 2013 | 0 | 0 | 0 | 49074.1707 | 0 | 0 | 0 | 0 | 0 | 49074.1707 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
7709 | Transmission Line Wood Pole Replacement | Line 973 Cowra To Yass Pole Replacements | PS Replacement | Input_Proj_Commit | 2016 | 2013 | 0 | 0 | 0 | 18341.1666 | 0 | 0 | 0 | 0 | 0 | 0 | 18341.1666 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
7711 | Transmission Line Wood Pole Replacement | Line 970 Burrinjuck to Yass Pole Replacements | PS Replacement | Input_Proj_Commit | 2016 | 2013 | 0 | 0 | 0 | 20379.4742 | 0 | 0 | 0 | 0 | 0 | 0 | 20379.4742 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
7777 | Transmission Line Wood Pole Replacement | Line 96H Coffs Harbour To Koolkhan Wood Pole Replacement | PS Replacement | Input_Proj_Commit | 2016 | 2013 | 0 | 0 | 2990.0246 | 0 | 0 | 4992326.582 | 4992326.582 | 0 | 0 | 0 | 9987643.1887 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
7699 | Transmission Line Wood Pole Replacement | Line 99F Uranquinty to Yanco Pole Replacements | PS Replacement | Input_Proj_Commit | 2018 | 2013 | 0 | 0 | 0 | 3964.1937 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3964.1937 | 100% | 100% | 100% | 100% | 100% | 0
P0002076 | Cable Minor Projects | Cable 41 Temperature Monitoring | PS Security/Compliance | Input_Proj_Commit | 2014 | 2013 | 0 | 0 | 0 | 0 | 117339.8438 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
7087 | Capacity of Victoria to NSW Interconnector | Snowy to Yass/Canberra Low Span Remediation | PS Security/Compliance | Input_Proj_Commit | 2019 | 2013 | 193597.3165 | 73288.5782 | -576099.611 | -5334.4655 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
6244 | Communications | Replace FSX/FLX Multiplex Network | PS Security/Compliance | Input_Proj_Commit | 2014 | 2013 | 9690.6975 | -79314.1228 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
7044 | Communications | Northern Microwave Replacement | PS Security/Compliance | Input_Proj_Commit | 2014 | 2013 | 0 | 4778944.5002 | 3903531.7544 | 3662532.2753 | 121227.7965 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
7138 | Communications | Communications To Yanco and Colleambally | PS Security/Compliance | Input_Proj_Commit | 2014 | 2013 | 0 | 154980.4006 | 3729447.2402 | 2060158.9306 | 798000.4863 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
7289 | Communications | Replace FSX/FLX Multiplex Network | PS Security/Compliance | Input_Proj_Commit | 2014 | 2013 | 0 | 139032.5077 | 2107933.2532 | 640644.4171 | 4427933.822 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
7645 | Communications | Communications To Tumut/Gadara | PS Security/Compliance | Input_Proj_Commit | 2014 | 2013 | 0 | 5223.436 | 0 | 3094487.3057 | 1240386.1074 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
7786 | Communications | Kangaroo Valley Communications – Vacate 2Ghz Band and Migrate To 6.7Ghz Band | PS Security/Compliance | Input_Proj_Commit | 2014 | 2013 | 0 | 0 | 0 | 902492.8641 | 2294756.7984 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
P0001927 | Communications | Haymarket 330kV Telecommunications Augmentation | PS Security/Compliance | Input_Proj_Commit | 2014 | 2013 | 0 | 0 | 0 | 0 | 141013.6719 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
6700 | Communications | VHF Network Augmentationfor Control Room Access | PS Security/Compliance | Input_Proj_Commit | 2015 | 2013 | 23296.2486 | -30148.831 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -6852.5824 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
7119 | Communications | VHF Network Augmentationfor Control Room Access | PS Security/Compliance | Input_Proj_Commit | 2015 | 2013 | 0 | 34960.7277 | -36543.2981 | 0 | 0 | 0 | 0 | 0 | 0 | -1582.5704 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
7286 | Communications | New England District Telecommunications Augmentation | PS Security/Compliance | Input_Proj_Commit | 2015 | 2013 | 21635.4409 | 29055.9939 | 75210.7116 | 234807.2623 | 2438642.0953 | 1692900.2928 | 0 | 0 | 0 | 4492251.7968 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
8098 | Communications | VHF Network Augmentationfor Control Room Access | PS Security/Compliance | Input_Proj_Commit | 2015 | 2013 | 0 | 0 | 0 | 3503.2464 | 720507.8125 | 216152.3438 | 2161523.4375 | 0 | 0 | 3101686.8401 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
7783 | Communications | Northern Microwave Loop | PS Security/Compliance | Input_Proj_Commit | 2016 | 2013 | 467408.0396 | 126391.093 | 30610.0494 | 404907.0931 | 1856316.8188 | 10314479.425 | 642127.2885 | 0 | 0 | 0 | 13842239.8073 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
6155 | Control System | Replacement of Electromechanical Underfrequency Relays | PS Security/Compliance | Input_Proj_Commit | 2011 | 2013 | 74663.1959 | 5353.6364 | 0 | 418.4076 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
6941 | Control System | Auto Underfrequency Loadshedding Schemes Modification | PS Security/Compliance | Input_Proj_Commit | 2012 | 2013 | 45275.2928 | 1007998.5104 | 565048.6061 | 55577.5516 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
P0002149 | Control System | Indication and Metering CT Ratio Changes at Dumaresq | PS Security/Compliance | Input_Proj_Commit | 2014 | 2013 | 0 | 0 | 0 | 0 | 60522.6562 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
6113 | Control System | Multiple Contingency System Protection Scheme | PS Security/Compliance | Input_Proj_Commit | 2016 | 2013 | 0 | -3311.9866 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -3311.9866 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
7065 | Control System | Modification of Synchronising Angle at Gen Sites | PS Security/Compliance | Input_Proj_Commit | 2016 | 2013 | 0 | 0 | 0 | 0 | 1675338.4553 | 1118261.2972 | 99679.3162 | 0 | 0 | 0 | 2893279.0686 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
7505 | Control System | Modification of Synchronising Angle at Gen Sites | PS Security/Compliance | Input_Proj_Commit | 2016 | 2013 | 0 | 11586.6573 | 48924.3306 | -58685.2684 | 0 | 0 | 0 | 0 | 0 | 0 | 1825.7195 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
7316 | Control System | Multiple Contingency System Protection Scheme | PS Security/Compliance | Input_Proj_Commit | 2016 | 2013 | 0 | 3315.3043 | -3248.996 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 66.3083 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
P0001493 | Protection Change | Gadara 132kV Fault and Disturbance Recorder | PS Security/Compliance | Input_Proj_Commit | 2014 | 2013 | 0 | 0 | 0 | 0 | 174980.4688 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
6832 | Quality of Supply | Voltage Unbalance Limits | PS Security/Compliance | Input_Proj_Commit | 2015 | 2013 | 76524.6985 | 10496.4148 | 1270.8261 | 14523.6453 | 0 | 0 | 0 | 0 | 0 | 102815.5848 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
7397 | Quality of Supply | Assessment of NER Quality of Supply Compliance | PS Security/Compliance | Input_Proj_Commit | 2019 | 2013 | 0 | 107723.8785 | 52251.192 | -153646.0079 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
6254 | SCADA | SCADA to Gadara | PS Security/Compliance | Input_Proj_Commit | 2014 | 2013 | -2.5494 | -8440.2499 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
7290 | SCADA | SCADA to Deniliquin | PS Security/Compliance | Input_Proj_Commit | 2014 | 2013 | -1.3945 | -2048.7532 | 28058.2263 | 74535.5602 | 417498.2314 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
7293 | SCADA | SCADA to Gadara | PS Security/Compliance | Input_Proj_Commit | 2014 | 2013 | 0 | 9522.2511 | -9331.6501 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
7461 | SCADA | SCADA to Colleambally | PS Security/Compliance | Input_Proj_Commit | 2014 | 2013 | -1.8412 | 928.9062 | 51116.349 | 258698.1904 | 301743.2475 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
P0002366 | SCADA | SCADA to Tenterfield | PS Security/Compliance | Input_Proj_Commit | 2014 | 2013 | 1462.8255 | 0 | 0 | -5333.7857 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
7759 | Secondary System Renewal | Gadara Relay Replacement | PS Security/Compliance | Input_Proj_Commit | 2014 | 2013 | 0 | 0 | 0 | 2097.3844 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
7076 | Substation Minor Projects | Canberra Substation Noise Management | PS Security/Compliance | Input_Proj_Commit | 2014 | 2013 | 0 | 0 | 0 | 0 | 910927.7344 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
P0001495 | Substation Minor Projects | Canberra Reduce AVR Settings | PS Security/Compliance | Input_Proj_Commit | 2014 | 2013 | 0 | 0 | 0 | 0 | 15439.4531 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
6959 | Substation Minor Projects | Surge Arresters Instalation at 330kV Line Entries | PS Security/Compliance | Input_Proj_Commit | 2015 | 2013 | 38899.1071 | 12014.8278 | 137.5359 | 943289.4316 | 2319621.9347 | 1899030.4017 | 0 | 0 | 0 | 5212993.2389 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
6335 | Transformer Replacement | Wagga Substation 330kV Transformer Replacements | PS Security/Compliance | Input_Proj_Commit | 2010 | 2013 | 5598046.7025 | -14597.9727 | 694.6719 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
6943 | Transformer Replacement | Munyang Transformer Replacement | PS Security/Compliance | Input_Proj_Commit | 2014 | 2013 | 225454.4288 | 674752.2504 | 10835375.9122 | 2805511.2756 | 102929.6875 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
7470 | Transmission Line Low Spans | 97G Line Murray to Guthega Low Spans Remediation | PS Security/Compliance | Input_Proj_Commit | 2014 | 2013 | 160809.8669 | 9287.818 | 98085.0711 | 1092615.9327 | 2968492.1875 | 141822.0194 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
7459 | Transmission Line Low Spans | 999 Line Yass to Cowra Low Spans Remediation | PS Security/Compliance | Input_Proj_Commit | 2016 | 2013 | 0 | 13626.627 | -13353.8607 | 7590.6968 | 0 | 0 | 0 | 0 | 0 | 0 | 7863.4631 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
7698 | Transmission Line Low Spans | 992 Line Burrinjuck to Tumut Low Spans Remediation | PS Security/Compliance | Input_Proj_Commit | 2016 | 2013 | 0 | 0 | 0 | 0 | 0 | 150611.8652 | 308789.0625 | 0 | 0 | 0 | 459400.9277 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
6913 | Transmission Line Low Spans | 97K Line Cooma to Munyang Low Spans Remediation | PS Security/Compliance | Input_Proj_Commit | 2018 | 2013 | 0 | 1058.7876 | -1037.5841 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21.2035 | 100% | 100% | 100% | 100% | 100% | 0
7708 | Transmission Line Low Spans | 993 Line Gadara to Wagga Low Spans Remediation | PS Security/Compliance | Input_Proj_Commit | 2018 | 2013 | 0 | 0 | 0 | 0 | 0 | 0 | 287173.8281 | 287173.8281 | 46318.3594 | 0 | 0 | 0 | 620666.0156 | 100% | 100% | 100% | 100% | 100% | 0
P0002240 | Transmission Line Low Spans | Southern Region Pole Lines Low Spans Remediation | PS Security/Compliance | Input_Proj_Commit | 2019 | 2013 | 0 | 0 | 0 | 0 | 0 | 107041.7285 | 107041.7285 | 214083.457 | 214083.457 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
P0002243 | Transmission Line Low Spans | Central Region Pole Lines Low Spans Remediation | PS Security/Compliance | Input_Proj_Commit | 2019 | 2013 | 0 | 0 | 0 | 0 | 0 | 103073.7891 | 103073.7891 | 206147.5781 | 206147.5781 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
P0002246 | Transmission Line Low Spans | Southern Region Tower Lines Low Spans Remediation | PS Security/Compliance | Input_Proj_Commit | 2019 | 2013 | 0 | 0 | 0 | 0 | 0 | 0 | 68083.2021 | 136166.5585 | 204249.7605 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
P0002249 | Transmission Line Low Spans | Northern Region Tower Lines Low Spans Remediation | PS Security/Compliance | Input_Proj_Commit | 2019 | 2013 | 0 | 0 | 6535.372 | 3506.6857 | 0 | 0 | 90526.7631 | 181053.3718 | 271580.1349 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
P0002252 | Transmission Line Low Spans | Northern Region Pole Lines Low Spans Remediation | PS Security/Compliance | Input_Proj_Commit | 2019 | 2013 | 0 | 0 | 0 | 0 | 0 | 178372.002 | 178372.002 | 356744.0039 | 356744.0039 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
P0002255 | Transmission Line Low Spans | Central Region Tower Lines Low Spans Remediation | PS Security/Compliance | Input_Proj_Commit | 2019 | 2013 | 0 | 0 | 0 | 0 | 0 | 0 | 86024.6186 | 172049.3915 | 258074.0101 | 0 | 0 | 0 | 0 | 100% | 100% | 100% | 100% | 100% | 0
6969 | Supply to Gunnedah, Narrabri and Moree | Installation of Phase Shifting Transformer on 969 Line | PS Augmentation | Input_Proj_Future | 2018 | 2013 | 0 | 0 | 0 | 0 | 0 | 300490.7774 | 995361.6477 | 2277075.06 | 12542278.7713 | 0 | 0 | 0 | 16115206.2563 | 101.1% | 101.4% | 101.8% | 102.2% | 102.7% | 0
6704 | Supply to the ACT | Wallaroo 330kV Switching Station | PS Augmentation | Input_Proj_Future | 2018 | 2013 | 0 | 0 | 0 | 0 | 226689.7705 | 1258252.9999 | 3827424.0521 | 20413602.7002 | 8155412.7872 | 0 | 0 | 0 | 33881382.3099 | 100.8% | 102% | 103.4% | 104.8% | 106.3% | 0
7661 | Substation Minor Projects | Supply to Temora | PS Connections | Input_Proj_Future | 2015 | 2013 | 0 | 0 | 0 | 0 | 2030431.1586 | 296811.4757 | 0 | 0 | 0 | 2327242.6343 | 0 | 0 | 0 | 100.2% | 100.5% | 100.9% | 101.2% | 101.6% | 0
P0000851 | Substation Minor Projects | Supply to Gulgong West | PS Connections | Input_Proj_Future | 2015 | 2013 | 0 | 0 | 0 | 0 | 118547.6096 | 1388059.1163 | 0 | 0 | 0 | 1506606.7258 | 0 | 0 | 0 | 100.2% | 100.9% | 101.7% | 102.7% | 103.9% | 0
7094 | Substation Minor Projects | Supply to Marsden Park | PS Connections | Input_Proj_Future | 2016 | 2013 | 0 | 0 | 0 | 0 | 73519.5718 | 1174908.65 | 405265.4001 | 0 | 0 | 0 | 1653693.622 | 0 | 0 | 100.2% | 101% | 101.8% | 102.7% | 103.8% | 0
8093 | Substation Minor Projects | Supply to Molong | PS Connections | Input_Proj_Future | 2016 | 2013 | 0 | 0 | 0 | 0 | 33971.2667 | 839317.9821 | 391714.2473 | 0 | 0 | 0 | 1265003.4961 | 0 | 0 | 100.2% | 101% | 101.7% | 102.6% | 103.6% | 0
P0002157 | Substation Minor Projects | Supply to Googong | PS Connections | Input_Proj_Future | 2018 | 2013 | 0 | 0 | 0 | 0 | 0 | 3440.4629 | 153001.6993 | 1122978.579 | 191708.1073 | 0 | 0 | 0 | 1471128.8485 | 100.3% | 101.1% | 102% | 103% | 104.2% | 0
P0002186 | Easements | Easement Acquisition in the ACT | PS Easements | Input_Proj_Future | 2017 | 2013 | 0 | 0 | 0 | 0 | 0 | 180772.2561 | 2152198.8543 | 7847744.9981 | 0 | 0 | 0 | 10180716.1084 | 0 | 100.2% | 100.2% | 101% | 100.9% | 102.7% | 0
7673 | Property | Strategic Property Acquisition at Maraylya | PS Easements | Input_Proj_Future | 2016 | 2013 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 99.86% | 100.9% | 102.3% | 103.6% | 105.5% | 0
P0002217 | Property | Strategic Property Acquisition in Sydney | PS Easements | Input_Proj_Future | 2017 | 2013 | 0 | 0 | 0 | 0 | 1143244.1448 | 0 | 0 | 0 | 0 | 0 | 0 | 1143244.1448 | 0 | 98.13% | 97.59% | 97.54% | 98.25% | 99.88% | 0
2001B | Cable Remediation | Cable 41 Backfill Rehabilitation | PS Replacement | Input_Proj_Future | 2017 | 2013 | 0 | 0 | 0 | 0 | 399377.0732 | 490088.9486 | 13843096.8644 | 4045700.5457 | 0 | 0 | 0 | 18778263.4318 | 0 | 100.9% | 102.7% | 104.7% | 106.7% | 108.8% | 0
7344 | Capacitor Bank | Broken Hill No.3 and No.4 Capacitors | PS Replacement | Input_Proj_Future | 2020 | 2013 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6709.8268 | 0 | 0 | 0 | 0 | 100.2% | 101% | 101.7% | 102.6% | 103.6% | 0
8022 | Communications | Dumaresq Protection & Communication Replacement | PS Replacement | Input_Proj_Future | 2014 | 2013 | 0 | 0 | 0 | 31236.0723 | 610542.281 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 99.8% | 100.4% | 101.1% | 102.1% | 103.3% | 0
7462 | Communications | Spur Microwave System Replacement | PS Replacement | Input_Proj_Future | 2015 | 2013 | 0 | 0 | 0 | 0 | 2868185.6258 | 1069034.5855 | 0 | 0 | 0 | 3937220.2113 | 0 | 0 | 0 | 100.8% | 102.3% | 103.9% | 105.6% | 107.3% | 0
8222 | Communications | Hammonds Hill Radio Repeater Site Mains Power | PS Replacement | Input_Proj_Future | 2016 | 2013 | 0 | 0 | 0 | 0 | 0 | 398288.8493 | 505607.295 | 0 | 0 | 0 | 903896.1442 | 0 | 0 | 100.5% | 101.7% | 102.9% | 104.3% | 106% | 0
P0002577 | Communications | Communications Between Lismore and Coffs Harbour | PS Replacement | Input_Proj_Future | 2016 | 2013 | 0 | 0 | 0 | 0 | 136818.0266 | 905657.6956 | 9453772.4231 | 0 | 0 | 0 | 10496248.1453 | 0 | 0 | 101% | 102.9% | 104.9% | 107% | 109% | 0
P0002583 | Communications | Communications Between Wallerawang and Orange North via Panorama Substation | PS Replacement | Input_Proj_Future | 2016 | 2013 | 0 | 0 | 0 | 0 | 97866.0534 | 545263.1005 | 7402149.5784 | 0 | 0 | 0 | 8045278.7323 | 0 | 0 | 101% | 102.9% | 104.8% | 106.8% | 108.9% | 0
P0002589 | Communications | Communications Between Williamsdale and Cooma | PS Replacement | Input_Proj_Future | 2016 | 2013 | 0 | 0 | 0 | 0 | 34732.5391 | 182363.1209 | 4947853.6133 | 0 | 0 | 0 | 5164949.2734 | 0 | 0 | 101% | 102.8% | 104.7% | 106.6% | 108.6% | 0
P0002579 | Communications | Communications Between Coffs Harbour and Port Macquarie | PS Replacement | Input_Proj_Future | 2017 | 2013 | 0 | 0 | 0 | 0 | 0 | 84353.5226 | 690935.0103 | 9002334.9051 | 0 | 0 | 0 | 9777623.4379 | 0 | 101% | 102.9% | 104.8% | 106.9% | 108.9% | 0
P0002585 | Communications | Communications Between Wellington and Orange North | PS Replacement | Input_Proj_Future | 2017 | 2013 | 0 | 0 | 0 | 0 | 0 | 41593.2906 | 222227.7292 | 6044440.761 | 0 | 0 | 0 | 6308261.7808 | 0 | 101% | 102.8% | 104.8% | 106.8% | 108.8% | 0
P0002581 | Communications | Communications Between Port Macquarie and Stroud - Includes Waratah West to Tomago | PS Replacement | Input_Proj_Future | 2018 | 2013 | 0 | 0 | 0 | 0 | 0 | 0 | 103593.2906 | 925153.3965 | 10571748.9503 | 0 | 0 | 0 | 11600495.6374 | 101% | 102.9% | 104.8% | 106.8% | 108.8% | 0
P0002587 | Communications | Communications Between Parkes and Cowra | PS Replacement | Input_Proj_Future | 2018 | 2013 | 0 | 0 | 0 | 0 | 0 | 0 | 58605.0348 | 288882.5836 | 7457344.1784 | 0 | 0 | 0 | 7804831.7968 | 101% | 102.9% | 104.8% | 106.9% | 108.9% | 0
P0002591 | Communications | Communications Between Uranquinty and Griffith | PS Replacement | Input_Proj_Future | 2019 | 2013 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 88217.6058 | 705277.314 | 0 | 0 | 0 | 0 | 101% | 102.9% | 104.9% | 106.9% | 109% | 0
P0002593 | Communications | Communications Between Yass and Wagga | PS Replacement | Input_Proj_Future | 2019 | 2013 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 88893.5926 | 892005.0497 | 0 | 0 | 0 | 0 | 101% | 102.9% | 104.8% | 106.8% | 108.9% | 0
8118 | Disconnection of Munmorah Power Station | Disconnection of Munmorah Power Station | PS Replacement | Input_Proj_Future | 2015 | 2013 | 0 | 0 | 0 | 0 | 0 | 1898931.4296 | 0 | 0 | 0 | 1898931.4296 | 0 | 0 | 0 | 100.5% | 101.2% | 102% | 102.8% | 103.7% | 0
8023 | Oil Containment | Beryl Oil Containment Upgrade | PS Replacement | Input_Proj_Future | 2016 | 2013 | 0 | 0 | 0 | 0 | 100716.4967 | 1134597.0205 | 394222.23 | 0 | 0 | 0 | 1629535.7472 | 0 | 0 | 100.6% | 102.1% | 103.6% | 105.3% | 107.1% | 0
8025 | Oil Containment | Deniliquin Oil Containment Upgrade | PS Replacement | Input_Proj_Future | 2016 | 2013 | 0 | 0 | 0 | 0 | 104775.9026 | 1181810.4183 | 411216.0865 | 0 | 0 | 0 | 1697802.4074 | 0 | 0 | 100.8% | 102.4% | 104.1% | 105.9% | 107.7% | 0
8026 | Oil Containment | Murrumburrah Oil Containment Upgrade | PS Replacement | Input_Proj_Future | 2016 | 2013 | 0 | 0 | 0 | 0 | 91049.1047 | 1028184.5719 | 358192.9683 | 0 | 0 | 0 | 1477426.6449 | 0 | 0 | 100.9% | 102.6% | 104.4% | 106.3% | 108.3% | 0
8027 | Oil Containment | Muswellbrook Oil Containment Upgrade | PS Replacement | Input_Proj_Future | 2016 | 2013 | 0 | 0 | 0 | 0 | 15399.3496 | 984982.6456 | 260589.9959 | 0 | 0 | 0 | 1260971.9911 | 0 | 0 | 101% | 102.8% | 104.6% | 106.5% | 108.5% | 0
8078 | Oil Containment | Inverell Oil Containment Upgrade | PS Replacement | Input_Proj_Future | 2016 | 2013 | 0 | 0 | 0 | 0 | 55060.0574 | 949449.6692 | 444202.1836 | 0 | 0 | 0 | 1448711.9102 | 0 | 0 | 100.6% | 102% | 103.6% | 105.3% | 107% | 0
8024 | Oil Containment | Panorama Oil Containment Upgrade | PS Replacement | Input_Proj_Future | 2017 | 2013 | 0 | 0 | 0 | 0 | 0 | 72179.2857 | 1165591.9852 | 406458.9713 | 0 | 0 | 0 | 1644230.2421 | 0 | 100.9% | 102.7% | 104.6% | 106.5% | 108.5% | 0
8029 | Oil Containment | Mount Piper 132 Oil Containment Upgrade | PS Replacement | Input_Proj_Future | 2017 | 2013 | 0 | 0 | 0 | 0 | 0 | 45616.4158 | 1144124.1842 | 537143.0934 | 0 | 0 | 0 | 1726883.6933 | 0 | 101% | 102.8% | 104.7% | 106.7% | 108.7% | 0
8079 | Oil Containment | Dapto Oil Containment Upgrade | PS Replacement | Input_Proj_Future | 2017 | 2013 | 0 | 0 | 0 | 0 | 0 | 18407.1357 | 1716470.7667 | 453549.4831 | 0 | 0 | 0 | 2188427.3855 | 0 | 100.6% | 102.1% | 103.7% | 105.5% | 107.4% | 0
8094 | Oil Containment | Yass Oil Containment Upgrade | PS Replacement | Input_Proj_Future | 2017 | 2013 | 0 | 0 | 0 | 0 | 0 | 8752.7276 | 797957.2882 | 210834.9357 | 0 | 0 | 0 | 1017544.9515 | 0 | 100.6% | 102.1% | 103.7% | 105.4% | 107.2% | 0
P0001472 | Oil Containment | Mount Piper 500 Oil Containment Upgrade | PS Replacement | Input_Proj_Future | 2017 | 2013 | 0 | 0 | 0 | 0 | 0 | 59000.2428 | 1323349.4987 | 167063.289 | 0 | 0 | 0 | 1549413.0305 | 0 | 100.4% | 101.8% | 103.3% | 105% | 106.8% | 0
8032 | Oil Containment | Sydney South Oil Containment Upgrade | PS Replacement | Input_Proj_Future | 2018 | 2013 | 0 | 0 | 0 | 0 | 0 | 0 | 27739.6034 | 2537705.1501 | 671567.8909 | 0 | 0 | 0 | 3237012.6444 | 100.9% | 102.7% | 104.6% | 106.6% | 108.6% | 0
P0002051 | Protection Change | Sydney North Lines 926 and 927 Protection Relay Replacement | PS Replacement | Input_Proj_Future | 2014 | 2013 | 0 | 0 | 0 | 0 | 637626.3096 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 99.84% | 100.4% | 101% | 101.9% | 102.9% | 0
P0002053 | Protection Change | Sydney South Lines 91J and 91F Protection Relay Replacement | PS Replacement | Input_Proj_Future | 2014 | 2013 | 0 | 0 | 0 | 0 | 506187.9613 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 99.82% | 100.4% | 100.9% | 101.8% | 102.9% | 0
7346 | Reactor Replacement | Buronga X2 220kV Reactor | PS Replacement | Input_Proj_Future | 2016 | 2013 | 0 | 0 | 0 | 0 | 330454.1582 | 2869419.9105 | 610067.1689 | 0 | 0 | 0 | 3809941.2376 | 0 | 0 | 100.8% | 101.3% | 101.9% | 102.5% | 103% | 0
7342 | Reactor Replacement | Broken Hill No.1 & No.2 220kV Reactors | PS Replacement | Input_Proj_Future | 2018 | 2013 | 0 | 0 | 0 | 0 | 0 | 0 | 189333.8173 | 3800285.3993 | 2962825.3062 | 0 | 0 | 0 | 6952444.5228 | 100.7% | 101.5% | 102.2% | 103.1% | 104.1% | 0
7325 | Reactor Replacement | Beaconsfield West No.1 132kV Reactor | PS Replacement | Input_Proj_Future | 2019 | 2013 | 0 | 0 | 0 | 0 | 0 | 0 | 10110.611 | 69382.2409 | 270062.1292 | 0 | 0 | 0 | 0 | 100.8% | 101.2% | 101.6% | 102.2% | 102.9% | 0
0588B | Secondary System Renewal | Molong SCADA Remediation | PS Replacement | Input_Proj_Future | 2015 | 2013 | 0 | 0 | 0 | 0 | 174861.4393 | 91507.0761 | 0 | 0 | 0 | 266368.5154 | 0 | 0 | 0 | 99.81% | 100.4% | 101% | 102% | 103.2% | 0
7062 | Secondary System Renewal | Kangaroo Valley Secondary System Replacement | PS Replacement | Input_Proj_Future | 2016 | 2013 | 0 | 0 | 0 | 0 | 0 | 652738.2958 | 4106060.3056 | 0 | 0 | 0 | 4758798.6014 | 0 | 0 | 100.3% | 101.3% | 102.3% | 103.6% | 104.9% | 0
7350 | Secondary System Renewal | Albury Secondary System Replacement | PS Replacement | Input_Proj_Future | 2016 | 2013 | 0 | 0 | 0 | 0 | 1337082.1054 | 5430415.9728 | 1639129.114 | 0 | 0 | 0 | 8406627.1922 | 0 | 0 | 100.4% | 101.4% | 102.4% | 103.7% | 105% | 0
7353 | Secondary System Renewal | Balranald Secondary System Replacement | PS Replacement | Input_Proj_Future | 2016 | 2013 | 0 | 0 | 0 | 0 | 0 | 462870.3528 | 2922131.5918 | 0 | 0 | 0 | 3385001.9446 | 0 | 0 | 100% | 100.7% | 101.4% | 102.4% | 103.4% | 0
7366 | Secondary System Renewal | Hume Secondary System Replacement | PS Replacement | Input_Proj_Future | 2017 | 2013 | 0 | 0 | 0 | 0 | 0 | 14016.5254 | 885706.6376 | 2141445.8671 | 0 | 0 | 0 | 3041169.0301 | 0 | 100.4% | 101.5% | 102.7% | 104% | 105.4% | 0
7365 | Secondary System Renewal | Deniliquin Secondary System Replacement | PS Replacement | Input_Proj_Future | 2018 | 2013 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 630153.3615 | 3857365.123 | 0 | 0 | 0 | 4487518.4846 | 99.98% | 100.7% | 101.4% | 102.4% | 103.5% | 0
7655 | Secondary System Renewal | Haymarket Secondary System Replacement | PS Replacement | Input_Proj_Future | 2018 | 2013 | 0 | 0 | 0 | 0 | 0 | 0 | 761282.5844 | 3008323.9845 | 2981973.1232 | 0 | 0 | 0 | 6751579.6921 | 99.93% | 100.6% | 101.2% | 102.1% | 103.2% | 0
7675 | Secondary System Renewal | ANM Secondary System Replacement | PS Replacement | Input_Proj_Future | 2018 | 2013 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 986227.4024 | 2742423.2909 | 0 | 0 | 0 | 3728650.6933 | 100% | 100.8% | 101.7% | 102.8% | 104% | 0
8075 | Secondary System Renewal | Taree Secondary System Replacement | PS Replacement | Input_Proj_Future | 2018 | 2013 | 0 | 0 | 0 | 0 | 562677.8559 | 2153932.6658 | 5312137.4049 | 7395257.4471 | 3943653.3943 | 0 | 0 | 0 | 19367658.768 | 100.3% | 101.3% | 102.3% | 103.4% | 104.6% | 0
7467 | Secondary System Renewal | Murrumburrah Secondary System Replacement | PS Replacement | Input_Proj_Future | 2019 | 2013 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 517091.0702 | 0 | 0 | 0 | 0 | 99.99% | 100.7% | 101.4% | 102.5% | 103.6% | 0
7638 | Secondary System Renewal | Sydney North Secondary System Replacement | PS Replacement | Input_Proj_Future | 2019 | 2013 | 0 | 0 | 0 | 0 | 1114241.7566 | 9783409.8007 | 12605004.6744 | 4279708.6832 | 1106289.2669 | 0 | 0 | 0 | 0 | 100.6% | 101.9% | 103.2% | 104.6% | 106.1% | 0
7756 | Secondary System Renewal | Armidale Secondary System Replacement | PS Replacement | Input_Proj_Future | 2019 | 2013 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 147699.7301 | 3445395.5003 | 0 | 0 | 0 | 0 | 99.95% | 100.6% | 101.3% | 102.2% | 103.3% | 0
7351 | Secondary System Renewal | Beryl Secondary System Replacement | PS Replacement | Input_Proj_Future | 2020 | 2013 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 100.7% | 101.5% | 102.5% | 103.7% | 0
7354 | Secondary System Renewal | Buronga Secondary System Replacement | PS Replacement | Input_Proj_Future | 2020 | 2013 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 319601.0322 | 0 | 0 | 0 | 0 | 100.1% | 101% | 101.8% | 103% | 104.3% | 0
7651 | Secondary System Renewal | Liddell Secondary System Replacement | PS Replacement | Input_Proj_Future | 2020 | 2013 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 361397.6963 | 2477309.1751 | 0 | 0 | 0 | 0 | 100.4% | 101.4% | 102.4% | 103.5% | 104.8% | 0
7667 | Secondary System Renewal | Avon Secondary System Replacement | PS Replacement | Input_Proj_Future | 2021 | 2013 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100.4% | 101.5% | 102.6% | 103.8% | 105.2% | 0
8193 | Secondary System Renewal | Sydney South Secondary System Replacement | PS Replacement | Input_Proj_Future | 2022 | 2013 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 518313.1616 | 3064676.6192 | 0 | 0 | 0 | 0 | 100.4% | 101.2% | 102.1% | 103.1% | 104.1% | 0
P0001205 | Substation Minor Projects | Cowra Duplicated DC & AC Supplies | PS Replacement | Input_Proj_Future | 2014 | 2013 | 0 | 0 | 0 | 139485.166 | 332630.6212 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 99.96% | 100.8% | 101.7% | 102.9% | 104.4% | 0
8083 | Substation Minor Projects | Dapto 415V AC System Replacement | PS Replacement | Input_Proj_Future | 2015 | 2013 | 0 | 0 | 0 | 0 | 58778.5138 | 2563445.4322 | 0 | 0 | 0 | 2622223.9461 | 0 | 0 | 0 | 100.5% | 101.5% | 102.6% | 103.8% | 105.1% | 0
6040 | Substation Minor Projects | Sydney West 132kV Disconnector Replacement | PS Replacement | Input_Proj_Future | 2016 | 2013 | 0 | 0 | 0 | 504559.2695 | 554354.9726 | 2553517.3879 | 384827.1617 | 0 | 0 | 0 | 3997258.7918 | 0 | 0 | 100.4% | 101.3% | 102.3% | 103.3% | 104.3% | 0
P0002049 | Substation Minor Projects | Sydney South AC System Replacement | PS Replacement | Input_Proj_Future | 2017 | 2013 | 0 | 0 | 0 | 0 | 0 | 0 | 442652.8087 | 3710354.6532 | 0 | 0 | 0 | 4153007.4619 | 0 | 100.7% | 101.8% | 102.9% | 104.1% | 105.4% | 0
6962 | Substation Renewal | Burrinjuck Substation Renewal | PS Replacement | Input_Proj_Future | 2017 | 2013 | 0 | 0 | 0 | 0 | 0 | 357204.0354 | 2299888.1481 | 7117567.9465 | 0 | 0 | 0 | 9774660.13 | 0 | 100.2% | 100.8% | 101.4% | 102.2% | 103.1% | 0
7378 | Substation Renewal | Vales Point Substation Renewal | PS Replacement | Input_Proj_Future | 2018 | 2013 | 0 | 0 | 0 | 0 | 176356.465 | 1009801.9637 | 2047442.3982 | 18548488.101 | 11488636.5893 | 0 | 0 | 0 | 33270725.5172 | 100.6% | 101.7% | 102.9% | 104.2% | 105.5% | 0
8076 | Substation Renewal | Taree Substation 33kV Switchyard Renewal | PS Replacement | Input_Proj_Future | 2018 | 2013 | 0 | 0 | 0 | 0 | 0 | 315606.4278 | 1000311.0823 | 4581420.746 | 530644.6317 | 0 | 0 | 0 | 6427982.8878 | 100.3% | 101% | 101.8% | 102.8% | 103.8% | 0
7398 | Substation Renewal | Canberra Substation Renewal | PS Replacement | Input_Proj_Future | 2019 | 2013 | 0 | 0 | 0 | 91097.9199 | 484960.8812 | 1188829.9251 | 2014677.5058 | 7696066.4275 | 23805259.854 | 0 | 0 | 0 | 0 | 100.6% | 101.5% | 102.4% | 103.4% | 104.5% | 0
6914 | Substation Renewal | Wagga 132 Substation Renewal | PS Replacement | Input_Proj_Future | 2020 | 2013 | 0 | 0 | 0 | 0 | 0 | 0 | 390429.9396 | 1276657.6531 | 5275628.3153 | 0 | 0 | 0 | 0 | 100.5% | 101.2% | 102.1% | 103% | 103.9% | 0
7678 | Substation Renewal | Munmorah Substation Renewal | PS Replacement | Input_Proj_Future | 2020 | 2013 | 0 | 0 | 0 | 0 | 19615.8981 | 165255.1631 | 481903.1365 | 1131830.6888 | 3766941.1926 | 0 | 0 | 0 | 0 | 100.6% | 101.5% | 102.6% | 103.7% | 104.8% | 0
7657 | Substation Renewal | Newcastle Substation Renewal | PS Replacement | Input_Proj_Future | 2021 | 2013 | 0 | 0 | 0 | 0 | 0 | 21772.729 | 490874.7613 | 1154430.8027 | 1833832.6626 | 0 | 0 | 0 | 0 | 100.4% | 101.3% | 102.3% | 103.3% | 104.4% | 0
7091 | SVC Control System Replacement | Armidale SVC Control System Replacement | PS Replacement | Input_Proj_Future | 2018 | 2013 | 0 | 0 | 0 | 0 | 0 | 0 | 24969.9367 | 1441499.4039 | 5044423.1896 | 0 | 0 | 0 | 6510892.5302 | 99.99% | 100.1% | 100.3% | 100.5% | 100.7% | 0
7363 | Transformer Replacement | Forbes No.1 & No.2 132kV Transformers | PS Replacement | Input_Proj_Future | 2018 | 2013 | 0 | 0 | 0 | 0 | 26695.8623 | 384804.3588 | 2326237.3801 | 2944908.2356 | 500137.0078 | 0 | 0 | 0 | 6182782.8446 | 100.7% | 101.5% | 102.4% | 103.4% | 104.4% | 0
7528 | Transformer Replacement | Tamworth 330 No.2 330kV Transformer | PS Replacement | Input_Proj_Future | 2018 | 2013 | 0 | 0 | 0 | 0 | 93295.2953 | 306845.6351 | 503123.0195 | 6049986.7348 | 1295423.3064 | 0 | 0 | 0 | 8248673.991 | 101% | 101.9% | 102.8% | 103.8% | 104.9% | 0
7356, 7357, 7563 | Transformer Replacement | Beaconsfield West No.1 & No.2 330kV Transformers | PS Replacement | Input_Proj_Future | 2018 | 2013 | 0 | 0 | 0 | 0 | 1247422.1339 | 665005.845 | 6568758.8271 | 15960732.8416 | 2806679.3784 | 0 | 0 | 0 | 27248599.026 | 100.5% | 101.5% | 102.6% | 103.8% | 105% | 0
7711 | Transmission Line Wood Pole Replacement | Line 970 Burrinjuck to Yass Pole Replacements | PS Replacement | Input_Proj_Future | 2016 | 2013 | 0 | 0 | 0 | 0 | 23225.0946 | 201641.8807 | 9732040.9622 | 0 | 0 | 0 | 9956907.9375 | 0 | 0 | 100.8% | 102.4% | 104.1% | 105.8% | 107.6% | 0
7699 | Transmission Line Wood Pole Replacement | Line 99F Uranquinty to Yanco Pole Replacements | PS Replacement | Input_Proj_Future | 2018 | 2013 | 0 | 0 | 0 | 0 | 0 | 65595.4212 | 236809.9492 | 563579.0525 | 20241829.1917 | 0 | 0 | 0 | 21107813.6145 | 101% | 102.8% | 104.7% | 106.7% | 108.8% | 0
6002H | Wallerawang to Orange Transmission Line Replacement | New 66kV Capacitor at Panorama | PS Replacement | Input_Proj_Future | 2016 | 2013 | 0 | 0 | 0 | 0 | 0 | 87378.6297 | 1121769.2989 | 0 | 0 | 0 | 1209147.9285 | 0 | 0 | 100.1% | 100.6% | 101.2% | 101.9% | 102.7% | 0
6002I | Wallerawang to Orange Transmission Line Replacement | New 66kV Capacitor at Orange | PS Replacement | Input_Proj_Future | 2016 | 2013 | 0 | 0 | 0 | 0 | 0 | 92334.9759 | 1185704.6213 | 0 | 0 | 0 | 1278039.5972 | 0 | 0 | 100.1% | 100.7% | 101.3% | 102% | 102.8% | 0
6002J | Wallerawang to Orange Transmission Line Replacement | New 132kV Capacitor at Orange North | PS Replacement | Input_Proj_Future | 2016 | 2013 | 0 | 0 | 0 | 0 | 0 | 92797.7936 | 1191325.0771 | 0 | 0 | 0 | 1284122.8706 | 0 | 0 | 100.1% | 100.7% | 101.2% | 101.9% | 102.7% | 0
6002K | Wallerawang to Orange Transmission Line Replacement | New Series Reactor on Line 94X at Wallerawang | PS Replacement | Input_Proj_Future | 2016 | 2013 | 0 | 0 | 0 | 0 | 0 | 123295.5156 | 1583628.9839 | 0 | 0 | 0 | 1706924.4995 | 0 | 0 | 100.8% | 101.4% | 102% | 102.7% | 103.5% | 0
6002L | Wallerawang to Orange Transmission Line Replacement | New Series Reactor on Line 949 at Mt Piper | PS Replacement | Input_Proj_Future | 2019 | 2013 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 125873.0162 | 0 | 0 | 0 | 0 | 100.8% | 101.4% | 102% | 102.7% | 103.5% | 0
7839 | Cable Remediation | Sydney South 330kV Series Reactor Reconfiguration | PS Security/Compliance | Input_Proj_Future | 2018 | 2013 | 0 | 0 | 0 | 0 | 0 | 95030.5915 | 431928.6447 | 2531865.6645 | 3444573.6775 | 0 | 0 | 0 | 6503398.5782 | 100.6% | 101.8% | 103% | 104.4% | 105.8% | 0
7646 | Communications | Communications to Beryl and Ilford | PS Security/Compliance | Input_Proj_Future | 2017 | 2013 | 0 | 0 | 0 | 0 | 0 | 69557.0959 | 661522.4991 | 567221.1812 | 0 | 0 | 0 | 1298300.7762 | 0 | 100.5% | 101.8% | 103.2% | 104.7% | 106.4% | 0
7316 | Control System | Multiple Contingency System Protection Scheme | PS Security/Compliance | Input_Proj_Future | 2016 | 2013 | 0 | 0 | 0 | 0 | 0 | 633331.2739 | 4107225.2366 | 0 | 0 | 0 | 4740556.5105 | 0 | 0 | 99.87% | 100.4% | 100.9% | 101.8% | 102.8% | 0
P0001885 | Protection Change | Gadara Protection Change | PS Security/Compliance | Input_Proj_Future | 2014 | 2013 | 0 | 0 | 0 | 344291.5703 | 70327.0284 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 99.81% | 100.4% | 101% | 102% | 103.1% | 0
6832 | Quality of Supply | Voltage Unbalance Limits | PS Security/Compliance | Input_Proj_Future | 2015 | 2013 | 0 | 0 | 0 | 0 | 132215.5656 | 692945.9776 | 0 | 0 | 0 | 825161.5432 | 0 | 0 | 0 | 100% | 100.8% | 101.7% | 102.8% | 104% | 0
7397 | Quality of Supply | Assessment of NER Quality of Supply Compliance | PS Security/Compliance | Input_Proj_Future | 2019 | 2013 | 0 | 0 | 0 | 0 | 0 | 0 | 369166.4766 | 901092.143 | 910668.1513 | 0 | 0 | 0 | 0 | 100.2% | 101% | 101.8% | 102.8% | 103.9% | 0
P0002366 | SCADA | SCADA to Tenterfield | PS Security/Compliance | Input_Proj_Future | 2014 | 2013 | 0 | 0 | 0 | 124922.6738 | 533191.4374 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100.1% | 100.7% | 101.3% | 102.1% | 103% | 0
P0002155 | Supply to ACT | Canberra Substation 330kV Bypass | PS Security/Compliance | Input_Proj_Future | 2015 | 2013 | 0 | 0 | 0 | 0 | 101373.8996 | 417658.1514 | 0 | 0 | 0 | 519032.0511 | 0 | 0 | 0 | 100.3% | 101.2% | 102.1% | 103.2% | 104.4% | 0
6913 | Transmission Line Low Spans | Line 97K Cooma to Munyang Low Span Remediation | PS Security/Compliance | Input_Proj_Future | 2018 | 2013 | 0 | 0 | 0 | 0 | 0 | 69853.1937 | 77711.8363 | 232248.3036 | 2252489.3678 | 0 | 0 | 0 | 2632302.7014 | 100.7% | 102.2% | 103.8% | 105.4% | 107.1% | 0
8089 | Transmission Line Low Spans | Lines 4 & 5 Yass to Marulan Low Span Remediation | PS Security/Compliance | Input_Proj_Future | 2018 | 2013 | 0 | 0 | 0 | 0 | 0 | 7034.2692 | 14487.183 | 41367.9377 | 428125.7079 | 0 | 0 | 0 | 491015.0977 | 100.7% | 102.2% | 103.8% | 105.6% | 107.4% | 0
8090 | Transmission Line Low Spans | Snowy to Yass/Canberra Low Span Remediation | PS Security/Compliance | Input_Proj_Future | 2019 | 2013 | 0 | 0 | 0 | 0 | 377633.023 | 77556.7809 | 402335.3533 | 1753377.7454 | 1784250.5413 | 0 | 0 | 0 | 0 | 100.9% | 102.6% | 104.3% | 106.2% | 108% | 0
8086 | Transmission Line Low Spans | Line 96H Clarence River Crossing Conductor Height | PS Security/Compliance | Input_Proj_Future | 2023 | 2013 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 101% | 102.4% | 103.8% | 105.4% | 107% | 0
Total Capex | [6 empty] | 2010 | 2011 | 2012 | 2013 | 2014 | 2015 | 2016 | 2017 | 2018 | 2015 | 2016 | 2017 | 2018 | [5 empty] | 2015
Programs Committed | [6 empty] | 84689372.7349 | 68939226.095 | 88714172.0696 | 107437303.2107 | 115996180.0592 | 40770453.9499 | 37600160.6569 | 29785728.5765 | 25910039.2535 | 40770453.9499 | 37600160.6569 | 29785728.5765 | 25910039.2535 | [5 empty] | 0
Projects Committed | [6 empty] | 359108679.0873 | 319745587.7253 | 283979337.4166 | 387203422.3029 | 416942130.5726 | 126863227.3972 | 54263272.5465 | 8738322.0952 | 11410862.1477 | 487462486.1892 | 113415319.4935 | 91697101.1542 | 5908975.0207 | [5 empty] | 290757882.4084
[7 empty] | 443798051.8222 | 388684813.8203 | 372693509.4861 | 494640725.5136 | 532938310.6318 | 167633681.347 | 91863433.2035 | 38524050.6717 | 37320901.4011 | 528232940.139 | 151015480.1505 | 121482829.7307 | 31819014.2742 | [5 empty] | 290757882.4084
Programs Future | [6 empty] | 0 | 0 | 0 | 0 | 0 | 22950904.5822 | 25212351.2085 | 26464862.436 | 27361701.6469 | 22950904.5822 | 25212351.2085 | 26464862.436 | 27361701.6469 | [5 empty] | 0
Projects Future | [6 empty] | 0 | 0 | 0 | 1235592.6719 | 17036134.3105 | 50257019.4502 | 122329179.6681 | 158000670.8863 | 154418133.6881 | 13902787.0566 | 79576845.2255 | 72581745.6049 | 234022096.4426 | [5 empty] | 0
[7 empty] | 0 | 0 | 0 | 1235592.6719 | 17036134.3105 | 73207924.0325 | 147541530.8766 | 184465533.3223 | 181779835.3351 | 36853691.6389 | 104789196.434 | 99046608.0408 | 261383798.0895 | [5 empty] | 0
Grand Total | [6 empty] | 443798051.8222 | 388684813.8203 | 372693509.4861 | 495876318.1855 | 549974444.9423 | 240841605.3795 | 239404964.0801 | 222989583.994 | 219100736.7362 | 565086631.7779 | 255804676.5845 | 220529437.7715 | 293202812.3637 | [5 empty] | 290757882.4084
Check | 1.1325e-06 | [5 empty] | 2.3842e-07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Note on F4: "0" indicates commissioning year equals year capex incurred.

## Error Checks
Global Error Check | Ok
Sheet
Input Data | Ok | 1.1623e-06
Costs Real $2014 | Ok | 1.0729e-06
Costs ($2014) & Real Escalation | Ok | 1.1325e-06
Capex Incurred Summary | Ok | 2.16e-12
Capex Commissioned Summary | Ok | 7.3896e-13
PTRM Inputs | Ok | 5.6843e-14