## PV-Time
#VALUE!
Inputs
Action | Cost ($m) | Year
Purchase Easement | 8.68 | 2018
Purchase Easement | 8.68 | 2019
Purchase Easement | 8.67 | 2020
| Cost ($) | Start
Maintenance of Easement | 25000 | 2021
| Cost ($m) | Year
Increase in construction cost from delaying easement acquisition | 18 | 2027
Discount rate | 5.77%
|  | Forecast Access Arrangement Period |  |  |  |  | Subsequent Access Arrangement Period
Present Value Analysis | 2017 | 2018 | 2019 | 2020 | 2021 | 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | 2029
Cahsflow
Purchase Easement |  | 8680000 | 8680000 | 8670000 | 25000 | 25000 | 25000 | 25000 | 25000 | 25000 | 25000 | 25000 | 25000
Delay purchase |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8680000 | 8680000 | 8670000 | 18000000
Present Value index | 1 | 0.94545 | 0.89387 | 0.84511 | 0.79901 | 0.75542 | 0.71421 | 0.67525 | 0.63841 | 0.60358 | 0.57066 | 0.53953 | 0.51009
Present value casflow
Purchase Easement |  | 8206485.771 | 7758802.8468 | 7327090.984 | 19975.1473 | 18885.4565 | 17855.2108 | 16881.1675 | 15960.2604 | 15089.591 | 14266.4187 | 13488.1523 | 12752.3421
Delay purchase |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5239106.0074 | 4953300.5648 | 4677691.2143 | 9181686.3468
Present Value
Purchase Easement | 23437533.3485
Delay Purchase | 24051784.1334
Overall Economic Value | 614250.7849

## PV-Increase Cost
#VALUE!
Inputs
Action | Cost ($m) | Year
Purchase Easement | 8.68 | 2018
Purchase Easement | 8.68 | 2019
Purchase Easement | 8.67 | 2020
| Cost ($) | Start
Maintenance of Easement | 25000 | 2021
Discount rate | 5.77%
Budget for Project (real 2017 $m)
Sub Totals | 100
Cost increase | 7.223%
|  | Forecast Access Arrangement Period |  |  |  |  | Subsequent Access Arrangement Period
Present Value Analysis | 2017 | 2018 | 2019 | 2020 | 2021 | 2022 | 2023 | 2024 | 2025
Cahsflow
Purchase Easement |  | 8680000 | 8680000 | 8670000 | 25000 | 25000 | 25000 | 25000 | 73970000
Delay purchase |  | 0 | 0 | 0 | 0 | 9306961.7485 | 9306961.7485 | 9296239.4423 | 79312898.679
Present Value index | 1 | 0.94545 | 0.89387 | 0.84511 | 0.79901 | 0.75542 | 0.71421 | 0.67525 | 0.63841
Present value casflow
Purchase Easement |  | 8206485.771 | 7758802.8468 | 7327090.984 | 19975.1473 | 18885.4565 | 17855.2108 | 16881.1675 | 47223218.5837
Delay purchase |  | 0 | 0 | 0 | 0 | 7030648.8472 | 6647110.5674 | 6277254.9929 | 50634180.7601
Present Value
Purchase Easement | 70589195.1676
Delay Purchase | 70589195.1676
Overall Economic Value | 0
Cost increase breakeven | 7.223%