## Capex input
Instructions: Enter values for historic and forecast project spends in the coloured cells below. Grey cells will auto fill. | Inputs required |  | Prev AA | Earlier AA | Forecast AA | Project type/name
NOMINAL | [11 empty] | $2015/16
Capital expenditure by driver over the earlier access arrangement period ($nominal) | [11 empty] | Capital expenditure by driver over the earlier access arrangement period ($2015/16)
$'000 nominal | 2010/11 | 2011/12 | 2012/13 | 2013/14 | 2014/15 | 2015/16 E | Total |  |  |  |  | $'000 2015/16 | 2010/11 | 2011/12 | 2012/13 | 2013/14 | 2014/15 | 2015/16E | Total
AER Final Decision | [11 empty] | AER Final Decision
Expansion | 1134.8977 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Expansion | 1260.6002 | 0 | 0 | 0 | 0 | 0 | 0
Replacement | 4508.5261 | 15364.8975 | 1468.5423 | 1213.8408 | 1205.5556 | 1220.2386 | 20473.0748 |  |  |  |  | Replacement | 5007.8954 | 16862.7454 | 1574.0759 | 1262.9847 | 1235.6945 | 1220.2386 | 22155.7392
Non-system | 84.9102 | 113.275 | 114.4116 | 456.5423 | 120.1571 | 357.1641 | 1161.55 |  |  |  |  | Non-system | 94.315 | 124.3176 | 122.6335 | 475.026 | 123.1611 | 357.1641 | 1202.3022
Total Forecast | 5728.334 | 15478.1725 | 1582.9538 | 1670.3831 | 1325.7128 | 1577.4027 | 21634.6248 |  |  |  |  | Total Forecast | 6362.8105 | 16987.0631 | 1696.7094 | 1738.0107 | 1358.8556 | 1577.4027 | 23358.0414 | ok
Actual capital expenditure | [11 empty] | Actual capital expenditure
Expansion | 2726.4218 | 855.003 | 732.1055 | 535.8386 | 54.5726 | 0 | 2177.5197 |  |  |  |  | Expansion | 3028.4033 | 938.353 | 784.7167 | 557.5327 | 55.9369 | 0 | 2336.5393
Replacement | 964.1309 | 3087.8095 | 13598.1157 | 2084.4047 | 2196.1802 | 12435.4443 | 33401.9544 | Updated to reflect |  |  |  | Replacement | 1070.9191 | 3388.8248 | 14575.315 | 2168.7946 | 2251.0847 | 12435.4443 | 34819.4633
Non-system | 384.4581 | 173.3333 | 1500.8964 | 1495.0048 | 1851.8505 | 2388.9006 | 7409.9855 | AER escalators |  |  |  | Non-system | 427.0411 | 190.2307 | 1608.7551 | 1555.532 | 1898.1468 | 2388.9006 | 7641.5651
Total Actual | 4075.0109 | 4116.1457 | 15831.1177 | 4115.248 | 4102.6033 | 14824.3449 | 42989.4596 |  |  |  |  | Total Actual | 4526.3636 | 4517.4085 | 16968.7868 | 4281.8592 | 4205.1684 | 14824.3449 | 44797.5677 | ok
Variance between approved forecast and actual | [11 empty] | Variance between approved forecast and actual
Expansion | 1591.5241 | 855.003 | 732.1055 | 535.8386 | 54.5726 | 0 | 2177.5197 |  |  |  |  | Expansion | 1767.8031 | 938.353 | 784.7167 | 557.5327 | 55.9369 | 0 | 2336.5393
Replacement | -3544.3952 | -12277.088 | 12129.5735 | 870.5639 | 990.6246 | 11215.2056 | 12928.8796 |  |  |  |  | Replacement | -3936.9762 | -13473.9207 | 13001.2391 | 905.8098 | 1015.3902 | 11215.2056 | 12663.7241
Non-system | 299.5479 | 60.0582 | 1386.4849 | 1038.4625 | 1731.6934 | 2031.7366 | 6248.4355 |  |  |  |  | Non-system | 332.7261 | 65.913 | 1486.1216 | 1080.506 | 1774.9857 | 2031.7366 | 6439.2629
Total variance | -1653.3231 | -11362.0268 | 14248.1639 | 2444.865 | 2776.8905 | 13246.9422 | 21354.8348 |  |  |  |  | Total variance | -1836.447 | -12469.6546 | 15272.0774 | 2543.8485 | 2846.3128 | 13246.9422 | 21439.5263 | ok
Capital expenditure by asset class over the earlier access arrangement period ($nominal) | [11 empty] | Capital expenditure by asset class over the earlier access arrangement period ($2015/16)
$'000 nominal | 2010/11 | 2011/12 | 2012/13 | 2013/14 | 2014/15 | 2015/16 E | Total |  |  |  |  | $'000 2015/16 | 2010/11 | 2011/12 | 2012/13 | 2013/14 | 2014/15 | 2015/16 | Total
Pipeline | 591.701 | 2321.7686 | 13316.306 | 1310.4955 | 1121.3965 | 9762.3551 | 27832.3217 |  |  |  |  | Pipeline | 657.2384 | 2548.1063 | 14273.2536 | 1363.5526 | 1149.4315 | 9762.3551 | 29096.6991
Compression | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Compression | 0 | 0 | 0 | 0 | 0 | 0 | 0
Meter Stations | 2975.1448 | 1425.1925 | 747.8602 | 813.4838 | 754.6196 | 1620.9187 | 5362.0747 |  |  |  |  | Meter Stations | 3304.6751 | 1564.1275 | 801.6035 | 846.4187 | 773.4851 | 1620.9187 | 5606.5535
SCADA & Communications | 0 | 0 | 0 | 176.8631 | 176.0194 | 2883.471 | 3236.3535 |  |  |  |  | SCADA & Communications | 0 | 0 | 0 | 184.0236 | 180.4199 | 2883.471 | 3247.9145
Operation & Management facilities | 508.1651 | 369.1846 | 1766.9515 | 1814.4058 | 2050.5677 | 557.6 | 6558.7096 |  |  |  |  | Operation & Management facilities | 564.4501 | 405.1746 | 1893.9296 | 1887.8644 | 2101.8319 | 557.6 | 6846.4006
Building | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Building | 0 | 0 | 0 | 0 | 0 | 0 | 0
Return tariff payments | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Return tariff payments | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total | 4075.0109 | 4116.1457 | 15831.1177 | 4115.248 | 4102.6033 | 14824.3449 | 42989.4596 |  |  |  |  | Total | 4526.3636 | 4517.4085 | 16968.7868 | 4281.8592 | 4205.1684 | 14824.3449 | 44797.5677 | ok
| 0 | ok | ok | ok | ok | check | [6 empty] | ok | ok | ok | ok | ok | check | ok
Capital expenditure by project over the earlier access arrangement period ($nominal) | [11 empty] | AER approved capital expenditure by project over the earlier access arrangement period ($2015/16)
$'000 nominal | 2010/11 | 2011/12 | 2012/13 | 2013/14 | 2014/15 | 2015/16 E | Total | Total project |  |  |  | $'000 2015/16 | 2010/11 | 2011/12 | 2012/13 | 2013/14 | 2014/15 | 2015/16 E | Total | Total project
AER Final Decision | [11 empty] | AER Final Decision
Katherine meter station upgrade | 1134.8977 | 0 | 0 | 0 | 0 | 0 | 0 | 1134.8977 |  |  |  | Katherine meter station upgrade | 1260.6002 | 0 | 0 | 0 | 0 | 0 | 0 | 1260.6002
Channel Island meter station upgrade | 314.7891 | -94.4111 | 0 | 0 | 0 | 0 | -94.4111 | 220.3781 |  |  |  | Channel Island meter station upgrade | 349.6555 | -103.6148 | 0 | 0 | 0 | 0 | -103.6148 | 246.0408
Palm Valley slamshut and filter | 228.8434 | 48.2546 | 0 | 0 | 0 | 0 | 48.2546 | 277.098 |  |  |  | Palm Valley slamshut and filter | 254.1904 | 52.9587 | 0 | 0 | 0 | 0 | 52.9587 | 307.149
Channel Island bridge project | 1349.2443 | 5435.9803 | 0 | 0 | 0 | 0 | 5435.9803 | 6785.2246 |  |  |  | Channel Island bridge project | 1498.688 | 5965.9072 | 0 | 0 | 0 | 0 | 5965.9072 | 7464.5952
Ultrasonic meter upgrade - Channel Island | 30.0292 | -30.4213 | 0 | 0 | 0 | 0 | -30.4213 | -0.39212 |  |  |  | Ultrasonic meter upgrade - Channel Island | 33.3553 | -33.387 | 0 | 0 | 0 | 0 | -33.387 | -0.031678
DCG oil vessel | 40.3841 | -40.9115 | 0 | 0 | 0 | 0 | -40.9115 | -0.52734 |  |  |  | DCG oil vessel | 44.8571 | -44.8997 | 0 | 0 | 0 | 0 | -44.8997 | -0.042602
DCG moisture analyser | 100.4426 | -101.7542 | 0 | 0 | 0 | 0 | -101.7542 | -1.3116 |  |  |  | DCG moisture analyser | 111.5677 | -111.6737 | 0 | 0 | 0 | 0 | -111.6737 | -0.10596
DCG C9 gas chromatograph | 142.8977 | -144.7637 | 0 | 0 | 0 | 0 | -144.7637 | -1.866 |  |  |  | DCG C9 gas chromatograph | 158.7252 | -158.876 | 0 | 0 | 0 | 0 | -158.876 | -0.15075
Hazardous areas assess. & equip. replacement | 288.9019 | 718.5732 | 0 | 0 | 0 | 0 | 718.5732 | 1007.4751 |  |  |  | Hazardous areas assess. & equip. replacement | 320.901 | 788.6234 | 0 | 0 | 0 | 0 | 788.6234 | 1109.5244
Heat shrink sleeve replacement | 400.7349 | 121.6854 | 0 | 0 | 0 | 0 | 121.6854 | 522.4203 |  |  |  | Heat shrink sleeve replacement | 445.1207 | 133.5479 | 0 | 0 | 0 | 0 | 133.5479 | 578.6686
Bidirectional pigging | 228.8434 | 217.1455 | 0 | 0 | 0 | 0 | 217.1455 | 445.9889 |  |  |  | Bidirectional pigging | 254.1904 | 238.3139 | 0 | 0 | 0 | 0 | 238.3139 | 492.5043
Cathodic protection stage 2 | 1046.881 | 2762.0487 | 0 | 0 | 0 | 0 | 2762.0487 | 3808.9297 |  |  |  | Cathodic protection stage 2 | 1162.8347 | 3031.3072 | 0 | 0 | 0 | 0 | 3031.3072 | 4194.1418
Anchor block repairs | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | Anchor block repairs | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Below ground station pipework recoating | 0 | 5058.336 | 0 | 0 | 0 | 0 | 5058.336 | 5058.336 |  |  |  | Below ground station pipework recoating | 0 | 5551.4482 | 0 | 0 | 0 | 0 | 5551.4482 | 5551.4482
Elliott heaters | 0 | 448.9771 | 0 | 0 | 0 | 0 | 448.9771 | 448.9771 |  |  |  | Elliott heaters | 0 | 492.7457 | 0 | 0 | 0 | 0 | 492.7457 | 492.7457
Total - SP | 5306.8894 | 14398.7391 | 0 | 0 | 0 | 0 | 14398.7391 | 19705.6285 |  |  |  | Total - SP | 5894.6862 | 15802.4011 | 0 | 0 | 0 | 0 | 15802.4011 | 21697.0873
Routine replacement & non system | 421.4447 | 1079.4334 | 1582.9538 | 1670.3831 | 1325.7128 | 1577.4027 | 7235.8857 |  |  |  |  | Routine replacement & non system | 468.1243 | 1184.662 | 1696.7094 | 1738.0107 | 1358.8556 | 1577.4027 | 7555.6403 | 8023.7647
Total Forecast | 5728.334 | 15478.1725 | 1582.9538 | 1670.3831 | 1325.7128 | 1577.4027 | 21634.6248 |  |  |  |  | Total Forecast | 6362.8105 | 16987.0631 | 1696.7094 | 1738.0107 | 1358.8556 | 1577.4027 | 23358.0414
Actual capital expenditure | [8 empty] | Asset class | Driver |  | Actual capital expenditure
Katherine meter station upgrade | 1123.575 |  | 709.125 | 2.312 | 0 | 0 | 711.437 | 1835.012 | Meter Stations | Expansion |  | Katherine meter station upgrade | 1248.0234 |  | 760.0847 | 2.4056 | 0 | 0 | 762.4903 | 2010.5137
Channel Island meter station upgrade | 1602.8468 | 855.003 | 16.8365 |  |  | 0 | 871.8395 | 2474.6864 | Meter Stations | Expansion |  | Channel Island meter station upgrade | 1780.3799 | 938.353 | 18.0464 |  |  | 0 | 956.3995 | 2736.7794
Palm Valley slamshut and filter | 0 |  |  | 108.3627 | 246.3564 | 0 | 354.7191 | 354.7191 | Meter Stations | Replacement |  | Palm Valley slamshut and filter | 0 |  |  | 112.7499 | 252.5153 | 0 | 365.2652 | 365.2652
Channel Island bridge project | 68.16 |  |  | 110.744 | 221.547 | 516.6513 | 848.9423 | 917.1023 | Pipeline | Replacement |  | Channel Island bridge project | 75.7095 |  |  | 115.2276 | 227.0857 | 516.6513 | 858.9646 | 934.6741
Ultrasonic meter upgrade - Channel Island | 2010/11: 0; 2015/16 E: 0 | 0 | 0 | Meter Stations | Replacement |  | Ultrasonic meter upgrade - Channel Island | 0 |  |  |  |  | 0 | 0 | 0
DCG oil vessel | 0 |  | 15.1546 | 0 | 21.863 | 0 | 37.0176 | 37.0176 | Meter Stations | Replacement |  | DCG oil vessel | 0 |  | 16.2437 | 0 | 22.4096 | 0 | 38.6533 | 38.6533
DCG moisture analyser | 3.0464 | 5.6797 | 0 | 0 | 0 | 0 | 5.6797 | 8.7261 | Meter Stations | Replacement |  | DCG moisture analyser | 3.3838 | 6.2333 | 0 | 0 | 0 | 0 | 6.2333 | 9.6172
DCG C9 gas chromatograph | 225.745 | 43.1933 | 0 | 0 | 0 | 0 | 43.1933 | 268.9384 | Meter Stations | Replacement |  | DCG C9 gas chromatograph | 250.7488 | 47.404 | 0 | 0 | 0 | 0 | 47.404 | 298.1528
Hazardous areas assess. & equip. replacement | 19.9316 | 521.3165 | 0.6 | 0 | 0 | 205.738 | 727.6545 | 747.5861 | Meter Stations | Replacement |  | Hazardous areas assess. & equip. replacement | 22.1392 | 572.1371 | 0.64312 | 0 | 0 | 205.738 | 778.5182 | 800.6574
Heat shrink sleeve replacement | 1.62 | 719.8579 | 595.4908 | 602.9952 | 390.478 | 0 | 2308.822 | 2310.442 | Pipeline | Replacement |  | Heat shrink sleeve replacement | 1.7994 | 790.0333 | 638.2845 | 627.4083 | 400.24 | 0 | 2455.966 | 2457.7655
Bidirectional pigging | 88.9413 | 793.9232 | 3596.3413 | 298.3408 | 0 | 0 | 4688.6053 | 4777.5467 | Pipeline | Replacement |  | Bidirectional pigging | 98.7926 | 871.3189 | 3854.7846 | 310.4195 | 0 | 0 | 5036.523 | 5135.3156
Cathodic protection stage 2 | 212.8886 | 381.9957 | 3321.6727 | 151.8123 | 0 | 0 | 3855.4806 | 4068.3692 | Pipeline | Replacement |  | Cathodic protection stage 2 | 236.4684 | 419.2346 | 3560.3775 | 157.9586 | 0 | 0 | 4137.5706 | 4374.039
Anchor block repairs | 76.2566 | 51.3135 | 594.09 | 25.4613 | 0 | 0 | 670.8649 | 747.1214 | Pipeline | Replacement |  | Anchor block repairs | 84.7028 | 56.3158 | 636.783 | 26.4921 | 0 | 0 | 719.591 | 804.2938
Below ground station pipework recoating | 143.8345 | 374.6783 | 5208.7112 | 90.4107 | 0 | 0 | 5673.8001 | 5817.6345 | Pipeline | Replacement |  | Below ground station pipework recoating | 159.7657 | 411.2038 | 5583.0239 | 94.0711 | 0 | 0 | 6088.2988 | 6248.0645
Elliott heaters | 2015/16 E: 0 | 0 | 0 | Meter Stations | Replacement |  | Elliott heaters | [5 empty] | 0 | 0 | 0
Total - SP | 3566.8458 | 3746.9611 | 14058.0222 | 1390.4389 | 880.2445 | 722.3892 | 20798.0559 | 24364.9017 |  |  |  | Total - SP | 3961.9135 | 4112.2338 | 15068.2716 | 1446.7327 | 902.2506 | 722.3892 | 22251.8779 | 26213.7914
Routine replacement & non system | 123.707 | 195.8514 | 266.0551 | 319.401 | 198.7172 | 250.1 | 1230.1247 | 1353.8317 | Operation & Management facilities | Replacement |  | Routine replacement & non system | 137.4089 | 214.944 | 285.1746 | 332.3324 | 203.6852 | 250.1 | 1286.2361 | 1423.645
Motor vehicles | 0 | 81.2318 | 634.7767 | 643.8439 | 392.3652 | 307.5 | 2059.7176 | 2059.7176 | Operation & Management facilities | Non-system |  | Motor vehicles | 0 | 89.1506 | 680.3936 | 669.9108 | 402.1743 | 307.5 | 2149.1293 | 2149.1293
Integrity Data Tool | 0 | 2.3619 | 125.9402 | 14.1669 | 0 | 0 | 142.4691 | 142.4691 | Operation & Management facilities | Non-system |  | Integrity Data Tool | 0 | 2.5922 | 134.9906 | 14.7405 | 0 | 0 | 152.3233 | 152.3233
Corporate assets & non system | 384.4581 | 89.7396 | 740.1795 | 836.9939 | 1459.4853 | 0 | 3126.3983 | 3510.8564 | Operation & Management facilities | Non-system |  | Corporate assets & non system | 427.0411 | 98.4878 | 793.3709 | 870.8807 | 1495.9725 | 0 | 3258.7119 | 3685.753
Noonamah Offtake | 0 |  | 6.144 | 533.5266 | 54.5726 | 0 | 594.2432 | 594.2432 | Meter Stations | Expansion |  | Noonamah Offtake | 0 |  | 6.5855 | 555.1271 | 55.9369 | 0 | 617.6495 | 617.6495
Below ground station pipe work recoating - Phase 2 | 0 |  |  | 30.7312 | 491.5202 | 9107.4586 | 9629.7101 | 9629.7101 | Pipeline | Replacement |  | Below ground station pipe work recoating - Phase 2 | 0 |  |  | 31.9754 | 503.8082 | 9107.4586 | 9643.2423 | 9643.2423
Replace site batteries | 2015/16 E: 47.29 | 47.29 | 47.29 | Meter Stations | Replacement |  | Replace site batteries | [5 empty] | 47.29 | 47.29 | 47.29
Replace battery chargers at 240 V sites | 0 | 0 | 0 | 0 | 16.3195 | 51.4483 | 67.7678 | 67.7678 | Meter Stations | Replacement |  | Replace battery chargers at 240 V sites | 0 | 0 | 0 | 0 | 16.7275 | 51.4483 | 68.1758 | 68.1758
Single loop controller replacement | 0 | 0 | 0 | 0 | 19.2606 | 177.2841 | 196.5447 | 196.5447 | Meter Stations | Replacement |  | Single loop controller replacement | 0 | 0 | 0 | 0 | 19.7421 | 177.2841 | 197.0262 | 197.0262
Earthing and lightning upgrades | 0 | 0 | 0 | 0 | 17.8513 | 138.2452 | 156.0965 | 156.0965 | Pipeline | Replacement |  | Earthing and lightning upgrades | 0 | 0 | 0 | 0 | 18.2975 | 138.2452 | 156.5428 | 156.5428
Transfer satellite providers and update IP configuration | 0 |  |  | 176.8631 | 106.8517 | 0 | 283.7147 | 283.7147 | SCADA & Communications | Replacement |  | Transfer satellite providers and update IP configuration | 0 |  |  | 184.0236 | 109.523 | 0 | 293.5466 | 293.5466
Clear SCADA | 0 | 0 | 0 | 0 | 69.1677 | 762.7699 | 831.9376 | 831.9376 | SCADA & Communications | Replacement |  | Clear SCADA | 0 | 0 | 0 | 0 | 70.8969 | 762.7699 | 833.6668 | 833.6668
Cathodic protection unit replacement | 2015/16 E: 28.7749 | 28.7749 | 28.7749 | Meter Stations | Replacement |  | Cathodic protection unit replacement | [5 empty] | 28.7749 | 28.7749 | 28.7749
New cathodic protection sites | 0 | 0 | 0 | 0 | 103.9184 | 468.1334 | 572.0517 | 572.0517 | Meter Stations | Replacement |  | New cathodic protection sites | 0 | 0 | 0 | 0 | 106.5163 | 468.1334 | 574.6497 | 574.6497
AC mitigation | 0 | 0 | 0 | 0 | 33.4927 | 206.845 | 240.3376 | 240.3376 | Meter Stations | Replacement |  | AC mitigation | 0 | 0 | 0 | 0 | 34.33 | 206.845 | 241.175 | 241.175
Replace mainline valve actuators | 2015/16 E: 145.7377 | 145.7377 | 145.7377 | Meter Stations | Replacement |  | Replace mainline valve actuators | [5 empty] | 145.7377 | 145.7377 | 145.7377
Wizard controller replacement | 0 | 0 | 0 | 0 | 5.005 | 9.2524 | 14.2574 | 14.2574 | Meter Stations | Replacement |  | Wizard controller replacement | 0 | 0 | 0 | 0 | 5.1301 | 9.2524 | 14.3825 | 14.3825
Slops tanks | 2015/16 E: 20.6476 | 20.6476 |  | Meter Stations | Replacement |  | Slops tanks | 0 | 0 | 0 | 0 | 0 | 20.6476 | 20.6476 | 20.6476
Ladder access | 0 | 0 | 0 | 0 | 4.8702 | 19.6152 | 24.4854 | 24.4854 | Meter Stations | Replacement |  | Ladder access | 0 | 0 | 0 | 0 | 4.992 | 19.6152 | 24.6072 | 24.6072
Pine Creek station upgrades | 2015/16 E: 61.6384 | 61.6384 | 61.6384 | Meter Stations | Replacement |  | Pine Creek station upgrades | [5 empty] | 61.6384 | 61.6384 | 61.6384
Replace CP Ground Beds | 0 |  |  | 169.2825 | 216.9257 | 0 | 386.2082 | 386.2082 | Meter Stations | Replacement |  | Replace CP Ground Beds | 0 |  |  | 176.1361 | 222.3489 | 0 | 398.485 | 398.485
Replace CUG Radio | 2015/16 E: 102.5 | 102.5 | 102.5 | Meter Stations | Replacement |  | Replace CUG Radio | [5 empty] | 102.5 | 102.5 | 102.5
RTU replacement | 2015/16 E: 39.0306 | 39.0306 | 39.0306 | Meter Stations | Replacement |  | RTU replacement | [5 empty] | 39.0306 | 39.0306 | 39.0306
Site hut upgrades | 2015/16 E: 39.3005 | 39.3005 | 39.3005 | SCADA & Communications | Replacement |  | Site hut upgrades | [5 empty] | 39.3005 | 39.3005 | 39.3005
Solar panel replacement | 0 | 0 | 0 | 0 | 32.0356 | 36.983 | 69.0186 | 69.0186 | Meter Stations | Replacement |  | Solar panel replacement | 0 | 0 | 0 | 0 | 32.8365 | 36.983 | 69.8195 | 69.8195
Energy Components | 2015/16 E: 1118.5324 | 1118.5324 | 1118.5324 | SCADA & Communications | Non-system |  | Energy Components | [5 empty] | 1118.5324 | 1118.5324 | 1118.5324
IT Applications renewal program | 2015/16 E: 601.4644 | 601.4644 | 601.4644 | SCADA & Communications | Non-system |  | IT Applications renewal program | [5 empty] | 601.4644 | 601.4644 | 601.4644
IT Infrastructure renewal program | 2015/16 E: 171.1913 | 171.1913 | 171.1913 | SCADA & Communications | Non-system |  | IT Infrastructure renewal program | [5 empty] | 171.1913 | 171.1913 | 171.1913
Vehicle tracking | 2015/16 E: 190.2125 | 190.2125 | 190.2125 | SCADA & Communications | Non-system |  | Vehicle tracking | [5 empty] | 190.2125 | 190.2125 | 190.2125
<insert project name> | [11 empty] | <insert project name> | bar: 2010/11
<insert project name> | [6 empty] | 0 | 0 |  |  |  | <insert project name> |  |  |  |  | 0 | 0 | 0 | 0 | bar: 2010/11
Total Actual | 4075.0109 | 4116.1457 | 15831.1177 | 4115.248 | 4102.6033 | 14824.3449 | 42989.4596 | 47043.8229 |  |  |  | Total Actual | 4526.3636 | 4517.4085 | 16968.7868 | 4281.8592 | 4205.1684 | 14824.3449 | 44797.5677 | 49323.9313
| 0 | 0 | ok | ok | ok | check | [6 empty] | ok | ok | ok | ok | ok | check | ok
Check against separate file which contains workings | 0 | 0 | 0 | 0 | 0
Check back to AMPmasterescalated | 2015/16 E: 0
Forecast capital expenditure by driver ($nominal) | [11 empty] | Forecast capital expenditure by driver ($2015/16)
$'000 nominal | 2016/17 | 2017/18 | 2018/19 | 2019/20 | 2020/21 | 2021/22 | 2022/23 | 2023/24 | 2024/25 | 2025/26 | Total | $'000 2015/16 | 2016/17F | 2017/18F | 2018/19F | 2019/20F | 2020/21F | 2021/22F | 2022/23F | 2023/24F | 2024/25F | 2025/26F | Total - 10 year | Total - 5 year
Expansion | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Expansion | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Replacement | 16183.9809 | 1672.0667 | 1336.8253 | 1391.9333 | 1266.0018 | 1338.6827 | 1393.5473 | 1443.1183 | 1450.3811 | 1494.6342 | 28971.1714 | Replacement | 15789.2497 | 1591.4971 | 1241.3752 | 1261.0229 | 1118.9611 | 1154.3419 | 1172.3429 | 1184.4344 | 1161.3612 | 1167.6058 | 26842.1922 | 21002.1059
Non-system | 4478.9658 | 986.2323 | 1080.1904 | 1168.5776 | 1465.8217 | 1067.5896 | 1132.2342 | 1206.1725 | 1148.8182 | 1151.9038 | 14886.5063 | Non-system | 4369.7228 | 938.7101 | 1003.0642 | 1058.6737 | 1295.5728 | 920.5792 | 952.5093 | 989.9619 | 919.8913 | 899.8654 | 13348.5507 | 8665.7436
Total Forecast | 20662.9468 | 2658.299 | 2417.0157 | 2560.5109 | 2731.8235 | 2406.2723 | 2525.7815 | 2649.2908 | 2599.1992 | 2646.538 | 43857.6777 | Total Forecast | 20158.9724 | 2530.2072 | 2244.4394 | 2319.6965 | 2414.5339 | 2074.921 | 2124.8522 | 2174.3963 | 2081.2525 | 2067.4713 | 40190.7428 | 29667.8495 | ok
Forecast capital expenditure by asset class ($nominal) | [11 empty] | Forecast capital expenditure by asset class ($2015/16)
$'000 nominal | 2016/17 | 2017/18 | 2018/19 | 2019/20 | 2020/21 | 2021/22 | 2022/23 | 2023/24 | 2024/25 | 2025/26 | Total | $'000 2015/16 | 2016/17 | 2017/18 | 2018/19 | 2019/20 | 2020/21 | 2021/22 | 2022/23 | 2023/24 | 2024/25 | 2025/26 | Total - 10 year | Total - 5 year
Pipeline | 14696.8827 | 271.4034 | 281.9614 | 291.6177 | 301.6073 | 311.6623 | 322.0548 | 330.4027 | 341.4227 | 352.8127 | 17501.8276 | Pipeline | 14338.4222 | 258.3256 | 261.8292 | 264.1912 | 266.5769 | 268.7454 | 270.9335 | 271.1769 | 273.3868 | 275.6167 | 16749.2044 | 15389.345
Compression | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Compression | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Meter Stations | 1224.3369 | 1124.5997 | 764.8246 | 795.5931 | 644.2454 | 690.6636 | 718.1077 | 741.4408 | 718.8877 | 732.0035 | 8154.703 | Meter Stations | 1194.475 | 1070.4102 | 710.2156 | 720.7681 | 569.4191 | 595.5571 | 604.119 | 608.535 | 575.6338 | 571.84 | 7220.9728 | 4265.288
SCADA & Communications | 699.2373 | 753.624 | 682.8178 | 679.8093 | 797.8383 | 725.2481 | 781.3342 | 846.5 | 780.1538 | 774.0229 | 7520.5856 | SCADA & Communications | 682.1828 | 717.3101 | 634.0642 | 615.8737 | 705.1728 | 625.3792 | 657.3093 | 694.7619 | 624.6913 | 604.6654 | 6561.4107 | 3354.6036
Operation & Management facilities | 867.9213 | 508.672 | 687.412 | 793.4909 | 988.1326 | 678.6982 | 704.2848 | 730.9474 | 758.735 | 787.6989 | 7505.993 | Operation & Management facilities | 846.7525 | 484.1613 | 638.3303 | 718.8636 | 873.3652 | 585.2393 | 592.4903 | 599.9226 | 607.5406 | 615.3491 | 6562.0149 | 3561.473
Building | 3174.5685 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3174.5685 | Building | 3097.14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3097.14 | 3097.14
Return tariff payments | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Return tariff payments | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total | 20662.9468 | 2658.299 | 2417.0157 | 2560.5109 | 2731.8235 | 2406.2723 | 2525.7815 | 2649.2908 | 2599.1992 | 2646.538 | 43857.6777 | Total | 20158.9724 | 2530.2072 | 2244.4394 | 2319.6965 | 2414.5339 | 2074.921 | 2124.8522 | 2174.3963 | 2081.2525 | 2067.4713 | 40190.7428 | 29667.8495 | ok
[13 empty] | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok |  | ok
Forecast capital expenditure by project ($nominal) | [11 empty] | Forecast capital expenditure by project ($2015/16)
$'000 nominal | 2016/17 | 2017/18 | 2018/19 | 2019/20 | 2020/21 | 2021/22 | 2022/23 | 2023/24 | 2024/25 | 2025/26 | Total | $'000 2015/16 | 2016/17 | 2017/18 | 2018/19 | 2019/20 | 2020/21 | 2021/22 | 2022/23 | 2023/24 | 2024/25 | 2025/26 | Total - 10 year | Asset class | Driver | Total - 5 year
Below ground station pipe work recoating - Phase 2 | 3575.9646 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3575.9646 | Below ground station pipe work recoating - Phase 2 | 3488.7459 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3488.7459 | Pipeline | Replacement | 3488.7459
Heat shrink sleeve replacement | 52.9568 | 271.4034 | 281.9614 | 291.6177 | 301.6073 | 311.6623 | 322.0548 | 330.4027 | 341.4227 | 352.8127 | 2857.9016 | Heat shrink sleeve replacement | 51.6651 | 258.3256 | 261.8292 | 264.1912 | 266.5769 | 268.7454 | 270.9335 | 271.1769 | 273.3868 | 275.6167 | 2462.4474 | Pipeline | Replacement | 1102.588
Replace site batteries | 84.8265 | 113.9813 | 13.3515 | 40.0493 | 0 | 0 | 42.2961 | 53.72 | 51.2891 | 0 | 399.5137 | Replace site batteries | 82.7576 | 108.489 | 12.3982 | 36.2826 | 0 | 0 | 35.5822 | 44.0905 | 41.0686 | 0 | 360.6688 | Meter Stations | Replacement | 239.9274
Replace battery chargers at 240 V sites | 28.4767 | 24.9503 | 27.3247 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 80.7517 | Replace battery chargers at 240 V sites | 27.7821 | 23.7481 | 25.3737 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 76.9039 | Meter Stations | Replacement | 76.9039
Single loop controller replacement | 42.3238 | 0 | 11.2491 | 11.6219 | 12.0072 | 12.3073 | 0 | 0 | 0 | 0 | 89.5092 | Single loop controller replacement | 41.2915 | 0 | 10.4459 | 10.5288 | 10.6126 | 10.6126 | 0 | 0 | 0 | 0 | 83.4914 | Meter Stations | Replacement | 72.8788
Hazardous areas assess. & equip. replacement | 263.6018 | 162.3629 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 425.9647 | Hazardous areas assess. & equip. replacement | 257.1725 | 154.5393 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 411.7118 | Meter Stations | Replacement | 411.7118
Cathodic protection unit replacement | 29.4943 | 30.3022 | 31.1236 | 31.9958 | 32.8931 | 33.7154 | 17.3726 | 17.8554 | 36.7041 | 51.1989 | 312.6553 | Cathodic protection unit replacement | 28.7749 | 28.8421 | 28.9013 | 28.9866 | 29.0727 | 29.0727 | 14.615 | 14.6548 | 29.39 | 39.9965 | 272.3065 | Meter Stations | Replacement | 144.5776
New cathodic protection sites | 355.2273 | 379.7017 | 0 | 405.1286 | 0 | 430.4777 | 0 | 456.6898 | 0 | 485.7451 | 2512.9702 | New cathodic protection sites | 346.5633 | 361.4056 | 0 | 367.0265 | 0 | 371.1996 | 0 | 374.8266 | 0 | 379.4633 | 2200.4848 | Meter Stations | Replacement | 1074.9953
Channel Island bridge project | 11067.9614 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11067.9614 | Channel Island bridge project | 10798.0111 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10798.0111 | Pipeline | Replacement | 10798.0111
Replace mainline valve actuators | 93.8338 | 0 | 98.7936 | 0 | 100.5922 | 0 | 108.421 | 0 | 111.6239 | 0 | 513.2646 | Replace mainline valve actuators | 91.5452 | 0 | 91.7397 | 0 | 88.9089 | 0 | 91.2108 | 0 | 89.3805 | 0 | 452.785 | Meter Stations | Replacement | 272.1937
Wizard controller replacement | 31.6124 | 0 | 16.6894 | 0 | 17.6524 | 0 | 18.66 | 0 | 0 | 0 | 84.6142 | Wizard controller replacement | 30.8413 | 0 | 15.4977 | 0 | 15.6022 | 0 | 15.698 | 0 | 0 | 0 | 77.6393 | Meter Stations | Replacement | 61.9413
Gas chromatograph upgrades | 210.2574 | 215.6355 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 425.8929 | Gas chromatograph upgrades | 205.1291 | 205.245 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 410.3741 | Meter Stations | Replacement | 410.3741
Moisture analyser upgrades | 0 | 0 | 110.5949 | 113.4525 | 0 | 0 | 0 | 0 | 0 | 0 | 224.0474 | Moisture analyser upgrades | 0 | 0 | 102.6984 | 102.7824 | 0 | 0 | 0 | 0 | 0 | 0 | 205.4807 | Meter Stations | Replacement | 205.4807
Replace CP Ground Beds | 0 | 75.9658 | 0 | 81.5439 | 0 | 87.0851 | 0 | 92.2864 | 0 | 98.479 | 435.3603 | Replace CP Ground Beds | 0 | 72.3053 | 0 | 73.8747 | 0 | 75.0932 | 0 | 75.7438 | 0 | 76.9317 | 373.9487 | Meter Stations | Replacement | 146.1801
RTU replacement | 37.9008 | 41.0825 | 45.5081 | 43.334 | 44.2879 | 50.439 | 61.8122 | 35.3032 | 46.0486 | 42.8815 | 448.5978 | RTU replacement | 36.9764 | 39.1029 | 42.2588 | 39.2585 | 39.144 | 43.4934 | 52.0005 | 28.975 | 36.8724 | 33.4989 | 391.5808 | Meter Stations | Replacement | 196.7407
Site hut upgrades | 20.1415 | 41.3595 | 41.8291 | 45.6443 | 44.83 | 45.0267 | 47.9511 | 50.6133 | 0 | 0 | 337.3955 | Site hut upgrades | 19.6503 | 39.3666 | 38.8425 | 41.3515 | 39.6232 | 38.8264 | 40.3396 | 41.5407 | 0 | 0 | 299.5407 | Meter Stations | Replacement | 178.834
Solar panel replacement | 26.6406 | 39.258 | 29.2059 | 22.823 | 28.496 | 31.6124 | 32.8016 | 34.9726 | 60.4963 | 53.6991 | 360.0053 | Solar panel replacement | 25.9908 | 37.3663 | 27.1205 | 20.6765 | 25.1863 | 27.2593 | 27.5948 | 28.7036 | 48.4411 | 41.9496 | 310.2889 | Meter Stations | Replacement | 136.3405
Water bath heater upgrades | 0 | 0 | 339.1547 | 0 | 363.4866 | 0 | 388.793 | 0 | 412.7258 | 0 | 1504.1601 | Water bath heater upgrades | 0 | 0 | 314.9389 | 0 | 321.2692 | 0 | 327.078 | 0 | 330.4813 | 0 | 1293.7673 | Meter Stations | Replacement | 636.208
Routine replacement | 262.7613 | 276.0636 | 290.0393 | 304.7226 | 320.1491 | 336.3567 | 353.3848 | 371.2749 | 390.0706 | 409.818 | 3314.6409 | Routine replacement | 256.3525 | 262.7613 | 269.3303 | 276.0636 | 282.9652 | 290.0393 | 297.2903 | 304.7226 | 312.3406 | 320.1491 | 2872.0149 | Operation & Management facilities | Replacement | 1347.473
Motor vehicles | 605.16 | 232.6084 | 397.3726 | 488.7683 | 667.9834 | 342.3415 | 350.9 | 359.6725 | 368.6643 | 377.881 | 4191.3521 | Motor vehicles | 590.4 | 221.4 | 369 | 442.8 | 590.4 | 295.2 | 295.2 | 295.2 | 295.2 | 295.2 | 3690 | Operation & Management facilities | Non-system | 2214
Building modifications | 3174.5685 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3174.5685 | Building modifications | 3097.14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3097.14 | Building | Non-system | 3097.14
IT Applications renewal program | 640.747 | 633.4308 | 682.8178 | 679.8093 | 731.1001 | 725.2481 | 781.3342 | 773.1478 | 780.1538 | 774.0229 | 7201.8118 | IT Applications renewal program | 625.119 | 602.9086 | 634.0642 | 615.8737 | 646.186 | 625.3792 | 657.3093 | 634.5584 | 624.6913 | 604.6654 | 6270.755 | SCADA & Communications | Non-system | 3124.1514
IT Infrastructure renewal program | 58.4904 | 120.1931 | 0 | 0 | 66.7382 | 0 | 0 | 73.3522 | 0 | 0 | 318.7738 | IT Infrastructure renewal program | 57.0638 | 114.4015 | 0 | 0 | 58.9868 | 0 | 0 | 60.2035 | 0 | 0 | 290.6557 | SCADA & Communications | Non-system | 230.4522
<insert project name> | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | <insert project name> | [13 empty] | 0
<insert project name> | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | <insert project name> | [10 empty] | 0 |  |  | 0
Total | 20662.9468 | 2658.299 | 2417.0157 | 2560.5109 | 2731.8235 | 2406.2723 | 2525.7815 | 2649.2908 | 2599.1992 | 2646.538 | 43857.6777 | Total | 20158.9724 | 2530.2072 | 2244.4394 | 2319.6965 | 2414.5339 | 2074.921 | 2124.8522 | 2174.3963 | 2081.2525 | 2067.4713 | 40190.7428 |  |  | 29667.8495 | ok
[13 empty] | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok |  |  |  | ok
[12 empty] | Check back to AMPmasterescalated | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | $'000 2015/16 | 2016/17 | 2017/18 | 2018/19 | 2019/20 | 2020/21
[12 empty] | Pipeline | 14338.4222 | 258.3256 | 261.8292 | 264.1912 | 266.5769
[12 empty] | Compression | 0 | 0 | 0 | 0 | 0
[12 empty] | Meter Stations | 1194.475 | 1070.4102 | 710.2156 | 720.7681 | 569.4191
[12 empty] | SCADA & Communications | 682.1828 | 717.3101 | 634.0642 | 615.8737 | 705.1728
[12 empty] | Operation & Management facilities | 846.7525 | 484.1613 | 638.3303 | 718.8636 | 873.3652
[12 empty] | Building | 3097.14 | 0 | 0 | 0 | 0
[12 empty] | Return tariff payments | 0 | 0 | 0 | 0 | 0
[12 empty] | Total | 20158.9724 | 2530.2072 | 2244.4394 | 2319.6965 | 2414.5339
[12 empty] | Pipeline | 3252.0818 | 2374.8132 | 2392.4041 | 2415.0305 | 2437.8831
[12 empty] | Compression | 0 | 0 | 0 | 0 | 0
[12 empty] | Meter Stations | 1195.0577 | 1070.9323 | 710.5621 | 721.1196 | 569.6968
[12 empty] | SCADA & Communications | 682.5155 | 717.66 | 634.3735 | 616.1741 | 705.5168
[12 empty] | Operation & Management facilities | 847.1656 | 484.3975 | 638.6417 | 719.2143 | 873.7912
[12 empty] | Building | 3098.6508 | 0 | 0 | 0 | 0
[12 empty] | Return tariff payments | 0 | 0 | 0 | 0 | 0
[12 empty] | Total | 9075.4714 | 4647.8031 | 4375.9814 | 4471.5385 | 4586.888
0
0
[12 empty] | Pipeline | 11086.3403 | -2116.4876 | -2130.575 | -2150.8393 | -2171.3063
[12 empty] | Compression | 0 | 0 | 0 | 0 | 0
[12 empty] | Meter Stations | -0.58267 | -0.52215 | -0.34645 | -0.35159 | -0.27777
[12 empty] | SCADA & Communications | -0.33277 | -0.34991 | -0.3093 | -0.30043 | -0.34399
[12 empty] | Operation & Management facilities | -0.41305 | -0.23618 | -0.31138 | -0.35067 | -0.42603
[12 empty] | Building | -1.5108 | 0 | 0 | 0 | 0
[12 empty] | Return tariff payments | 0 | 0 | 0 | 0 | 0
[12 empty] | Total | 11083.501 | -2117.5959 | -2131.5421 | -2151.842 | -2172.354

## AMP-MASTER
| Prepared in $2014/15 |  | $,000 | [11 empty] | Project splits for escalation
Item Ref. | Description | Access Arrangement Description | Category | FY16 (15-16) | FY17 (16-17) | FY18 (17-18) | FY19 (18-19) | FY20 (19-20) | FY21 (20-21) | FY22 (21-22) | FY23 (22-23) | FY24 (23-24) | FY25 (24-25) | FY26 (25-26) | Direct labour % | Director contractor % | Direct material % | Other Direct % | Overheads % | Total
1 | Below ground station pipe work recoating - Phase 2 | Below ground station pipe work recoating - Phase 2 | SIB CAPEX | 8810000 | 3374800 | [9 empty] | 12% | 83% | 0% | 5% | 0% | 100%
2 | Heat shrink sleeve replacement program | Heat shrink sleeve replacement | SIB CAPEX |  | 50000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 0% | 90% | 10% | 0% | 0% | 100%
3 | Replace site batteries | Replace site batteries | SIB CAPEX | 46000 | 80500 | 105250 | 12000 | 35000 |  |  | 34000 | 42000 | 39000 |  | 33% | 0% | 67% | 0% | 0% | 100%
4 | Replace battery chargers at 240 V sites | Replace battery chargers at 240 V sites | SIB CAPEX | 50000 | 27000 | 23000 | 24500 | [7 empty] | 43% | 0% | 57% | 0% | 0% | 100%
5 | Single loop controller replacement | Single loop controller replacement | SIB CAPEX | 171739 | 40000 |  | 10000 | 10000 | 10000 | 10000 |  |  |  |  | 79% | 0% | 21% | 0% | 0% | 100%
6 | Hazardous areas equipment upgrades | Hazardous areas assess. & equip. replacement | SIB CAPEX | 200000 | 250000 | 150000 | [8 empty] | 19% | 21% | 60% | 0% | 0% | 100%
7 | Earthing and lightning upgrades | Earthing and lightning upgrades | SIB CAPEX | 134149 | [10 empty] | 22% | 38% | 40% | 0% | 0% | 100%
8 | Transfer satellite providers and update IP configuration | Transfer satellite providers and update IP configuration | SIB CAPEX | [11 empty] | 50% | 0% | 50% | 0% | 0% | 100%
9 | Clear SCADA | Clear SCADA | SIB CAPEX | 740832 | [10 empty] | 50% | 0% | 50% | 0% | 0% | 100%
10 | Cathodic protection unit replacement | Cathodic protection unit replacement | SIB CAPEX | 28000 | 28000 | 28000 | 28000 | 28000 | 28000 | 28000 | 14000 | 14000 | 28000 | 38000 | 29% | 0% | 71% | 0% | 0% | 100%
11 | New cathodic protection sites | New cathodic protection sites | SIB CAPEX | 453978 | 350000 | 350000 |  | 350000 |  | 350000 |  | 350000 |  | 350000 | 17% | 50% | 29% | 4% | 0% | 100%
12 | AC mitigation | AC mitigation | Growth CAPEX | 200000 | [10 empty] | 10% | 90% | 0% | 0% | 0% | 100%
13 | Channel Island bridge upgrade | Channel Island bridge project | Growth CAPEX | 233371 | 10450000 | [9 empty] | 20% | 70% | 10% | 0% | 0% | 100%
14 | Replace mainline valve actuators | Replace mainline valve actuators | SIB CAPEX | 95000 | 89200 |  | 89200 |  | 86200 |  | 88200 |  | 86200 |  | 14% |  | 86% | 0% | 0% | 100%
15 | Replace Tennant Creek mainline valve actuator | Replace mainline valve actuators | SIB CAPEX | 47000 | [10 empty] | 15% | 0% | 85% | 0% | 0% | 100%
16 | Wizard controller replacement | Wizard controller replacement | SIB CAPEX | 9000 | 30000 |  | 15000 |  | 15000 |  | 15000 |  |  |  | 33% | 0% | 67% | 0% | 0% | 100%
17 | Slops tanks | Slops tanks | SIB CAPEX | 20000 | [10 empty] | 20% | 60% | 20% | 0% | 0% | 100%
18 | Ladder access | Ladder access | SIB CAPEX | 19000 | [10 empty] | 20% | 60% | 20% | 0% | 0% | 100%
19 | Channel Island bridge upgrade FEED | Channel Island bridge project | Growth CAPEX | 266629 | [10 empty] | 20% | 70% | 10% | 0% | 0% | 100%
20 | AGP General | Routine replacement | SIB CAPEX | 244000 | 250100 | 256352.5 | 262761.3125 | 269330.3453 | 276063.6039 | 282965.194 | 290039.3239 | 297290.307 | 304722.5647 | 312340.6288 | 0% | 0% | 100% | 0% | 0% | 100%
21 | AGP Motor Vehicles | Motor vehicles | SIB CAPEX | 300000 | 576000 | 216000 | 360000 | 432000 | 576000 | 288000 | 288000 | 288000 | 288000 | 288000 | 0% | 0% | 100% | 0% | 0% | 100%
22 | Building modifications | Building modifications | SIB CAPEX |  | 3000000 | [9 empty] | 0% | 80% | 20% | 0% | 0% | 100%
23 | Gas chromatograph upgrades | Gas chromatograph upgrades | SIB CAPEX |  | 200000 | 200000 | [8 empty] | 7% |  | 93% | 0% | 0% | 100%
24 | Moisture analyser upgrades | Moisture analyser upgrades | SIB CAPEX |  |  |  | 100000 | 100000 | [6 empty] | 8% | 0% | 92% | 0% | 0% | 100%
25 | Pine Creek station upgrades | Pine Creek station upgrades | SIB CAPEX | 60000 | [10 empty] | 5% | 20% | 75% | 0% | 0% | 100%
26 | Replace CP Ground Beds | Replace CP Ground Beds | SIB CAPEX |  |  | 70000 |  | 70000 |  | 70000 |  | 70000 |  | 70000 | 0% | 86% | 14% | 0% | 0% | 100%
27 | Replace CUG Radio | Replace CUG Radio | SIB CAPEX | 100000 | [10 empty] | 0% | 0% | 100% | 0% | 0% | 100%
28 | RTU replacement | RTU replacement | SIB CAPEX | 38000 | 36000 | 38000 | 41000 | 38000 | 37800 | 42000 | 50000 | 27800 | 35300 | 32000 | 23% | 0% | 77% | 0% | 0% | 100%
29 | Site hut upgrades | Site hut upgrades | SIB CAPEX | 38000 | 19000 | 38000 | 37000 | 39000 | 37000 | 36000 | 37000 | 38000 |  |  | 21% | 79% | 0% | 0% | 0% | 100%
30 | Solar panel replacement | Solar panel replacement | SIB CAPEX | 36000 | 25300 | 36300 | 26300 | 20000 | 24300 | 26300 | 26500 | 27500 | 46300 | 40000 | 25% | 0% | 75% | 0% | 0% | 100%
31 | Water bath heater upgrades | Water bath heater upgrades | SIB CAPEX |  |  |  | 300000 |  | 300000 |  | 300000 |  | 300000 |  | 5% | 95% | 0% | 0% | 0% | 100%
32 | Energy Components | Energy Components | SIB CAPEX | 1082000 | [10 empty] | 30% | 65% | 5% | 0% | 0% | 100%
33 | Vehicle tracking | Vehicle tracking | SIB CAPEX | 184000 | [10 empty] | 30% | 65% | 5% | 0% | 0% | 100%
34 | IT Applications renewal program | IT Applications renewal program | SIB CAPEX | 581820 | 604702 | 581820 | 604702 | 581820 | 604702 | 581820 | 604702 | 581820 | 567902 | 545020 | 30% | 65% | 5% | 0% | 0% | 100%
35 | IT Infrastructure renewal program | IT Infrastructure renewal program | SIB CAPEX | 165600 | 55200 | 110400 |  |  | 55200 |  |  | 55200 |  |  | 30% | 65% | 5% | 0% | 0% | 100%
|  |  |  | 14354118 | 19535802 | 2453122.5 | 2160463.3125 | 2223150.3453 | 2300265.6039 | 1965085.194 | 1997441.3239 | 2041610.307 | 1945424.5647 | 1925360.6288

## AMPmasterescalated
| Prepared in $2014/15 |  | $,000 |  | 1000
Item Ref. | AMP Description | Access Arrangement Description | Category | FY16 (15-16) | FY17 (16-17) | FY18 (17-18) | FY19 (18-19) | FY20 (19-20) | FY21 (20-21) | FY22 (21-22) | FY23 (22-23) | FY24 (23-24) | FY25 (24-25) | FY26 (25-26)
1 | Below ground station pipe work recoating - Phase 2 | Below ground station pipe work recoating - Phase 2 | SIB CAPEX | 8885325.5 | 3403654.54 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | Heat shrink sleeve replacement program | Heat shrink sleeve replacement | SIB CAPEX | 0 | 50405 | 252025 | 255443.0884 | 257747.5193 | 260074.9945 | 262190.6694 | 264325.3855 | 264562.8114 | 266718.8767 | 268894.3466
3 | Replace site batteries | Replace site batteries | SIB CAPEX | 46136.62 | 80739.085 | 105842.9532 | 12095.7984 | 35397.706 | 0 | 0 | 34714.3592 | 43015.1257 | 40066.9303 | 0
4 | Replace battery chargers at 240 V sites | Replace battery chargers at 240 V sites | SIB CAPEX | 50193.5 | 27104.49 | 23168.8421 | 24754.8575 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | Single loop controller replacement | Single loop controller replacement | SIB CAPEX | 172960.0643 | 40284.4 | 0 | 10191.1129 | 10272.024 | 10353.7443 | 10353.7443 | 0 | 0 | 0 | 0
6 | Hazardous areas equipment upgrades | Hazardous areas assess. & equip. replacement | SIB CAPEX | 200720 | 250900 | 150770.052 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | Earthing and lightning upgrades | Earthing and lightning upgrades | SIB CAPEX | 134873.4046 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8 | Transfer satellite providers and update IP configuration | Transfer satellite providers and update IP configuration | SIB CAPEX | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9 | Clear SCADA | Clear SCADA | SIB CAPEX | 744165.744 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10 | Cathodic protection unit replacement | Cathodic protection unit replacement | SIB CAPEX | 28073.08 | 28073.08 | 28138.6246 | 28196.435 | 28279.5994 | 28363.5954 | 28363.5954 | 14258.4936 | 14297.3601 | 28673.1526 | 39020.9663
11 | New cathodic protection sites | New cathodic protection sites | SIB CAPEX | 456715.4873 | 338110.5 | 352590.784 | 0 | 358074.6368 | 0 | 362145.9081 | 0 | 365684.4941 | 0 | 370208.08
12 | AC mitigation | AC mitigation | Growth CAPEX | 201800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13 | Channel Island bridge upgrade | Channel Island bridge project | Growth CAPEX | 235261.3051 | 10534645 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14 | Replace mainline valve actuators | Replace mainline valve actuators | SIB CAPEX | 95119.7 | 89312.392 | 0 | 89502.1035 | 0 | 86740.3779 | 0 | 88986.1772 | 0 | 87200.4441 | 0
15 | Replace Tennant Creek mainline valve actuator | Replace mainline valve actuators | SIB CAPEX | 47063.45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16 | Wizard controller replacement | Wizard controller replacement | SIB CAPEX | 9026.73 | 30089.1 | 0 | 15119.7479 | 0 | 15221.6499 | 0 | 15315.1585 | 0 | 0 | 0
17 | Slops tanks | Slops tanks | SIB CAPEX | 20144 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
18 | Ladder access | Ladder access | SIB CAPEX | 19136.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
19 | Channel Island bridge upgrade FEED | Channel Island bridge project | Growth CAPEX | 268788.6949 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20 | AGP General | Routine replacement | SIB CAPEX | 244000 | 250100 | 256352.5 | 262761.3125 | 269330.3453 | 276063.6039 | 282965.194 | 290039.3239 | 297290.307 | 304722.5647 | 312340.6288
21 | AGP Motor Vehicles | Motor vehicles | SIB CAPEX | 300000 | 576000 | 216000 | 360000 | 432000 | 576000 | 288000 | 288000 | 288000 | 288000 | 288000
22 | Building modifications | Building modifications | SIB CAPEX | 0 | 3021600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23 | Gas chromatograph upgrades | Gas chromatograph upgrades | SIB CAPEX | 0 | 200126 | 200239.008 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24 | Moisture analyser upgrades | Moisture analyser upgrades | SIB CAPEX | 0 | 0 | 0 | 100193.532 | 100275.4674 | 0 | 0 | 0 | 0 | 0 | 0
25 | Pine Creek station upgrades | Pine Creek station upgrades | SIB CAPEX | 60135 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
26 | Replace CP Ground Beds | Replace CP Ground Beds | SIB CAPEX | 0 | 0 | 70541.8 | 0 | 72072.8918 | 0 | 73261.6813 | 0 | 73896.3611 | 0 | 75055.2874
27 | Replace CUG Radio | Replace CUG Radio | SIB CAPEX | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
28 | RTU replacement | RTU replacement | SIB CAPEX | 38078.66 | 36074.52 | 38149.2093 | 41228.1259 | 38300.9481 | 38189.2978 | 42432.5531 | 50732.1864 | 28268.3055 | 35973.0697 | 32681.8795
29 | Site hut upgrades | Site hut upgrades | SIB CAPEX | 38342 | 19171 | 38406.4146 | 37895.0856 | 40342.9033 | 38656.7769 | 37879.4204 | 39355.7301 | 40527.469 | 0 | 0
30 | Solar panel replacement | Solar panel replacement | SIB CAPEX | 36081 | 25356.925 | 36454.9284 | 26459.0591 | 20172.1671 | 24572.0249 | 26594.4137 | 26921.803 | 28003.5346 | 47259.5741 | 40926.4667
31 | Water bath heater upgrades | Water bath heater upgrades | SIB CAPEX | 0 | 0 | 0 | 307257.4512 | 0 | 313433.326 | 0 | 319100.5139 | 0 | 322420.7524 | 0
32 | Energy Components | Energy Components | SIB CAPEX | 1091251.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
33 | Vehicle tracking | Vehicle tracking | SIB CAPEX | 185573.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
34 | IT Applications renewal program | IT Applications renewal program | SIB CAPEX | 586794.561 | 609872.2021 | 588203.4963 | 618599.2183 | 600852.3493 | 630425.3371 | 610126.0174 | 641277.3768 | 619081.3602 | 609454.9052 | 589917.4776
35 | IT Infrastructure renewal program | IT Infrastructure renewal program | SIB CAPEX | 167015.88 | 55671.96 | 111611.2646 | 0 | 0 | 57548.1454 | 0 | 0 | 58735.1605 | 0 | 0
|  |  |  | 14462775.4812 | 19667290.1941 | 2468494.8772 | 2189696.9283 | 2263118.5577 | 2355642.8738 | 2024313.1972 | 2073026.508 | 2121362.2892 | 2030490.2698 | 2017045.133
|  | $'000 $2015/16 | 2014/15 | 2015/16 | 2016/17 | 2017/18 | 2018/19 | 2019/20 | 2020/21 | 2021/22 | 2022/23 | 2023/24 | 2024/25 | 2025/26
|  | Internal labour |  | 0.9% | 0% | 0.8% | 0.7% | 1% | 1% | 0.9% | 0.9% | 0.9% | 0.9% | 0.9%
|  | External labour |  | 0.9% | 0% | 0.8% | 0.7% | 1% | 1% | 0.9% | 0.9% | 0.9% | 0.9% | 0.9%
Materials and other | bar: 2015/16 to 2025/26
AER draft decesion table 7.5

## CPI
|  |  |  | Source: | www.abs.gov.au/ausstats/abs%40.nsf/mf/6401.0
Consumer Price Index
(Weighted average of eight capital cities)
Indexation numbers to be applied to the cost to calculate the "indexed cost base" of assets
acquired after 19 September 1985 are :
[6 empty] | Annual | Annual | Annual | Annual
| Year | March | June | September | December | March | June | September | Dec
| 1985 | 37.9 | 38.8 | 39.7 | 40.5
| 1986 | 41.4 | 42.1 | 43.2 | 44.4 |  |  | 8.816% | 9.63%
| 1987 | 45.3 | 46 | 46.8 | 47.6 | 9.42% | 9.264% | 8.333% | 7.207%
| 1988 | 48.4 | 49.3 | 50.2 | 51.2 | 6.843% | 7.174% | 7.265% | 7.563%
| 1989 | 51.7 | 53 | 54.2 | 55.2 | 6.818% | 7.505% | 7.968% | 7.812%
| 1990 | 56.2 | 57.1 | 57.5 | 59 | 8.704% | 7.736% | 6.089% | 6.884%
| 1991 | 58.9 | 59 | 59.3 | 59.9 | 4.804% | 3.327% | 3.13% | 1.525%
| 1992 | 59.9 | 59.7 | 59.8 | 60.1 | 1.698% | 1.186% | 0.8432% | 0.3339%
| 1993 | 60.6 | 60.8 | 61.1 | 61.2 | 1.169% | 1.843% | 2.174% | 1.83%
| 1994 | 61.5 | 61.9 | 62.3 | 62.8 | 1.485% | 1.809% | 1.964% | 2.614%
| 1995 | 63.8 | 64.7 | 65.5 | 66 | 3.74% | 4.523% | 5.136% | 5.096%
| 1996 | 66.2 | 66.7 | 66.9 | 67 | 3.762% | 3.091% | 2.137% | 1.515%
| 1997 | 67.1 | 66.9 | 66.6 | 66.8 | 1.36% | 0.2999% | -0.4484% | -0.2985%
| 1998 | 67 | 67.4 | 67.5 | 67.8 | -0.149% | 0.7474% | 1.351% | 1.497%
| 1999 | 67.8 | 68.1 | 68.7 | 69.1 | 1.194% | 1.039% | 1.778% | 1.917%
| 2000 | 69.7 | 70.2 | 72.9 | 73.1 | 2.802% | 3.084% | 6.114% | 5.789%
| 2001 | 73.9 | 74.5 | 74.7 | 75.4 | 6.026% | 6.125% | 2.469% | 3.146%
| 2002 | 76.1 | 76.6 | 77.1 | 77.6 | 2.977% | 2.819% | 3.213% | 2.918%
| 2003 | 78.6 | 78.6 | 79.1 | 79.5 | 3.285% | 2.611% | 2.594% | 2.448%
| 2004 | 80.2 | 80.6 | 80.9 | 81.5 | 2.036% | 2.545% | 2.276% | 2.516%
| 2005 | 82.1 | 82.6 | 83.4 | 83.8 | 2.369% | 2.481% | 3.09% | 2.822%
| 2006 | 84.5 | 85.9 | 86.7 | 86.6 | 2.923% | 3.995% | 3.957% | 3.341%
| 2007 | 86.6 | 87.7 | 88.3 | 89.1 | 2.485% | 2.095% | 1.845% | 2.887%
| 2008 | 90.3 | 91.6 | 92.7 | 92.4 | 4.273% | 4.447% | 4.983% | 3.704%
| 2009 | 92.5 | 92.9 | 93.8 | 94.3 | 2.436% | 1.419% | 1.187% | 2.056%
| 2010 | 95.2 | 95.8 | 96.5 | 96.9 | 2.919% | 3.122% | 2.878% | 2.757%
| 2011 | 98.3 | 99.2 | 99.8 | 99.8 | 3.256% | 3.549% | 3.42% | 2.993%
| 2012 | 99.9 | 100.4 | 101.8 | 102 | 1.628% | 1.21% | 2.004% | 2.204%
| 2013 | 102.4 | 102.8 | 104 | 104.8 | 2.503% | 2.39% | 2.161% | 2.745%
| 2014 | 105.4 | 105.9 |  |  | 2.93% | 3.016%
| 2015 | 106.8 | 107.5
| 2016 | 109.47 | 110.1875
| 2017 | 112.2067 | 112.9422
| 2018 | 115.0119 | 115.7657
| 2019 | 117.8872 | 118.6599
| 2020 | 120.8344 | 121.6264
| 2021 | 123.8553 | 124.667
| 2022 | 126.9516 | 127.7837
| 2023 | 130.1254 | 130.9783
| 2024 | 133.3786 | 134.2528
| 2025 | 136.713 | 137.6091
| 2026 | 140.1309 | 141.0493
| * | Estimated
| f | Indexation is frozen at 30 September 1999
| Forecast inflation |  | 102.5%

## AER calc sheet
NOTE: This is an AER input sheet and should not be changed. It has been password protected. The password is 'AER'
AER capex project calculation ($'000, 2009-10)
Numbers from submissions
| 2010-11 | 2011-12 | 2012-13 | 2013-14 | 2014-15 | 2015-16
Katherine meter station upgrade | 2010-11: 1096
Channel Island meter station upgrade | 2010-11: 304; 2011-12: -90
Palm Valley slamshut and filter | 2010-11: 221; 2011-12: 46
Channel Island bridge project | 2010-11: 1303; 2011-12: 5182
Ultrasonic meter upgrade - Channel Island | 29 | -29 | 0 | 0 | 0 | 0
DCG oil vessel | 39 | -39 | 0 | 0 | 0 | 0
DCG moisture analyser | 97 | -97 | 0 | 0 | 0 | 0
DCG C9 gas chromatograph | 138 | -138 | 0 | 0 | 0 | 0
Hazardous areas assessment and equipment replacement | 2010-11: 279; 2011-12: 685
Heat shrink sleeve replacement | 2010-11: 387; 2011-12: 116
Bidirectional pigging | 2010-11: 221; 2011-12: 207
Cathodic protection stage 2 | 2010-11: 1011; 2011-12: 2633
Anchor block repairs | 2010-11: 0; 2011-12: 0
Below ground station pipework recoating | 2010-11: 0; 2011-12: 4822
Elliott heaters | 2010-11: 0; 2011-12: 428
Routine (non-special projects) replacement and non-system capex | 407 | 1029 | 1473 | 1509 | 1185 | 1385
Total | 5532 | 14755 | 1473 | 1509 | 1185 | 1385
Total 2010-11 and 2011-12 | 2010-11: 20287
Total enhanced integrity program | 2011-12: 17755
De-escalation
| 2010-11 | 2011-12 | 2012-13 | 2013-14 | 2014-15 | 2015-16
Katherine meter station upgrade | 1096 | 0 | 0 | 0 | 0 | 0
Channel Island meter station upgrade | 304 | -89.5968 | 0 | 0 | 0 | 0
Palm Valley slamshut and filter | 221 | 45.7939 | 0 | 0 | 0 | 0
Channel Island bridge project | 1303 | 5158.7855 | 0 | 0 | 0 | 0
Ultrasonic meter upgrade - Channel Island | 29 | -28.8701 | 0 | 0 | 0 | 0
DCG oil vessel | 39 | -38.8253 | 0 | 0 | 0 | 0
DCG moisture analyser | 97 | -96.5655 | 0 | 0 | 0 | 0
DCG C9 gas chromatograph | 138 | -137.3818 | 0 | 0 | 0 | 0
Hazardous areas assessment and equipment replacement | 279 | 681.9313 | 0 | 0 | 0 | 0
Heat shrink sleeve replacement | 387 | 115.4803 | 0 | 0 | 0 | 0
Bidirectional pigging | 221 | 206.0727 | 0 | 0 | 0 | 0
Cathodic protection stage 2 | 1011 | 2621.2046 | 0 | 0 | 0 | 0
Anchor block repairs | 0 | 0 | 0 | 0 | 0 | 0
Below ground station pipework recoating | 0 | 4800.3982 | 0 | 0 | 0 | 0
Elliott heaters | 0 | 426.0826 | 0 | 0 | 0 | 0
Routine (non-special projects) replacement and non-system capex | 407 | 1024.3902 | 1459.832 | 1488.8105 | 1163.9078 | 1354.2538
Total | 5532 | 14688.9 | 1459.832 | 1488.8105 | 1163.9078 | 1354.2538
AER escalation
| 2010-11 | 2011-12 | 2012-13 | 2013-14 | 2014-15 | 2015-16
Katherine meter station upgrade | 1096 | 0 | 0 | 0 | 0 | 0
Channel Island meter station upgrade | 304 | -90.0855 | 0 | 0 | 0 | 0
Palm Valley slamshut and filter | 221 | 46.0437 | 0 | 0 | 0 | 0
Channel Island bridge project | 1303 | 5186.9215 | 0 | 0 | 0 | 0
Ultrasonic meter upgrade - Channel Island | 29 | -29.0275 | 0 | 0 | 0 | 0
DCG oil vessel | 39 | -39.037 | 0 | 0 | 0 | 0
DCG moisture analyser | 97 | -97.0921 | 0 | 0 | 0 | 0 |  | Routine project breakdown
DCG C9 gas chromatograph | 138 | -138.1311 | 0 | 0 | 0 | 0 |  |  | 2010-11 | 2011-12 | 2012-13 | 2013-14 | 2014-15 | 2015-16
Hazardous areas assessment and equipment replacement | 279 | 685.6506 | 0 | 0 | 0 | 0 |  | Expansion | 0 | 0 | 0 | 0 | 0 | 0
Heat shrink sleeve replacement | 387 | 116.1102 | 0 | 0 | 0 | 0 |  | Replacement | 0.79853 | 0.89506 | 0.92772 | 0.72668 | 0.90936 | 0.77357
Bidirectional pigging | 221 | 207.1966 | 0 | 0 | 0 | 0 |  | Non-system | 0.20147 | 0.10494 | 0.072277 | 0.27332 | 0.090636 | 0.22643
Cathodic protection stage 2 | 1011 | 2635.5006 | 0 | 0 | 0 | 0 |  | Pipeline | 0 | 0.63554 | 0.61842 | 0.60972 | 0.68915 | 0.63785
Anchor block repairs | 0 | 0 | 0 | 0 | 0 | 0 |  | Compression | 0 | 0 | 0 | 0 | 0 | 0
Below ground station pipework recoating | 0 | 4826.5796 | 0 | 0 | 0 | 0 |  | Meter stations | 0 | 0.11067 | 0.077992 | 0.0084476 | 0.095072 | 0.010214
Elliott heaters | 0 | 428.4065 | 0 | 0 | 0 | 0 |  | SCADA & communications | 0 | 0.13517 | 0.21675 | 0.29824 | 0.11482 | 0.2573
Routine (non-special projects) replacement and non-system capex | 407 | 1029.9773 | 1475.1651 | 1511.0736 | 1181.4259 | 1371.4366 |  | O&M facilities | 1 | 0.11787 | 0.086039 | 0.082896 | 0.10039 | 0.093724
Total | 5532 | 14769.0132 | 1475.1651 | 1511.0736 | 1181.4259 | 1371.4366 |  | Buildings | 0 | 0.00075161 | 0.0008002 | 0.00069987 | 0.00056701 | 0.00091722
Final allocations | 2010-11 | 2011-12 | 2012-13 | 2013-14 | 2014-15 | 2015-16 | Total
Expansion | 1096 | 0 | 0 | 0 | 0 | 0 | 1096
Replacement | 4354 | 14660.9281 | 1368.5443 | 1098.0732 | 1074.3463 | 1060.9085 | 23616.8004
Non-system | 82 | 108.0851 | 106.6209 | 413.0005 | 107.0796 | 310.5281 | 1127.3142
Pipeline | 2922 | 14055.3076 | 912.2773 | 921.3259 | 814.1834 | 874.7652 | 20499.8594
Compression | 0 | 0 | 0 | 0 | 0 | 0 | 0
Meter stations | 2203 | 452.3095 | 115.051 | 12.7649 | 112.3209 | 14.0082 | 2909.4546
SCADA & communications | 0 | 139.223 | 319.7347 | 450.6632 | 135.6515 | 352.8687 | 1398.1411
O&M facilities | 407 | 121.3989 | 126.9217 | 125.2621 | 118.6001 | 128.5366 | 1027.7195
Buildings | 0 | 0.77415 | 1.1804 | 1.0576 | 0.66988 | 1.2579 | 4.9399
Total | 5532 | 14769.0132 | 1475.1651 | 1511.0736 | 1181.4259 | 1371.4366 | 25840.1145
Access arrangement (2011-16) totals
Expansion | 2010-11: 0
Replacement | 2010-11: 19262.8004
Non-system | 2010-11: 1045.3142
Pipeline | 2010-11: 17577.8594
Compression | 2010-11: 0
Meter stations | 2010-11: 706.4546
SCADA & communications | 2010-11: 1398.1411
O&M facilities | 2010-11: 620.7195
Buildings | 2010-11: 4.9399
Total | 2010-11: 20308.1145
Conversion to $m, 2010-11
| 2010-11 | 2011-12 | 2012-13 | 2013-14 | 2014-15 | 2015-16
Expansion | 1.1325 | 0 | 0 | 0 | 0 | 0
Replacement | 4.499 | 15.1491 | 1.4141 | 1.1346 | 1.1101 | 1.0962 |  | Inflation multiplier: | 1.0333
Non-system | 0.084731 | 0.11168 | 0.11017 | 0.42675 | 0.11065 | 0.32087
Pipeline | 3.0193 | 14.5233 | 0.94266 | 0.95201 | 0.8413 | 0.90389
Compression | 0 | 0 | 0 | 0 | 0 | 0
Meter stations | 2.2764 | 0.46737 | 0.11888 | 0.01319 | 0.11606 | 0.014475
SCADA & communications | 0 | 0.14386 | 0.33038 | 0.46567 | 0.14017 | 0.36462
O&M facilities | 0.42055 | 0.12544 | 0.13115 | 0.12943 | 0.12255 | 0.13282
Buildings | 0 | 0.00079992 | 0.0012197 | 0.0010928 | 0.00069219 | 0.0012998
Total | 5.7162 | 15.2608 | 1.5243 | 1.5614 | 1.2208 | 1.4171
[5 empty] | Total: | 26.7006
[5 empty] | Total (Access arrangement period): | 20.9844
|  | 0 | 0 | 0 | 0 | 0 | 0
|  | 15.1491 | 1.4141 | 1.1346 | 1.1101 | 1.0962 | 19.9043
|  | 0.11168 | 0.11017 | 0.42675 | 0.11065 | 0.32087 | 1.0801
Note on B10: Ben McCarthy: Numbers from updated (March) submission.
Note on C10: Ben McCarthy: Original December expenditure from 2010-11 deferred into 2011-12. See sheet AER11/2308.
Note on C26: Ben McCarthy: See sheet 3.
Note on I61: Ben McCarthy: See spreadsheet AER2011-000774. Values give the proportion of routine expenditure allocated to each asset class and either expansion, replacement or non-system. Final AER calculation allocates routine expenditure in same proportions as evidenced in NT Gas's response to AER.NTGAS.40.

## AER Cost escalators
NOTE: This is an AER input sheet and should not be changed. It has been password protected. The password is 'AER'
Cost escalators
De-escalation
| 2011-12 | 2012-13 | 2013-14 | 2014-15 | 2015-16
Capex | 1.0045 | 1.009 | 1.0136 | 1.0181 | 1.0227
AER escalation
| 2011-12 | 2012-13 | 2013-14 | 2014-15 | 2015-16
Capex | 1.0055 | 1.0105 | 1.015 | 1.0151 | 1.0127

## AERCalculation of routine capex
NOTE: This is an AER input sheet and should not be changed. It has been password protected. The password is 'AER'
Calculation of routine capex in Dec submission
| 2011-12 | 2012-13 | 2013-14 | 2014-15 | 2015-16
Channel Island piggability | 3223
Southbound piggability | 161
Cathodic protection stage 2 | 1684
Hazardous areas assessment | 368
Palm valley filtration and slamshut | 107
Below ground station recoating | 1934
Sub total special projects | 7477 | 0 | 0 | 0 | 0
Total forecast capex | 8506 | 1473 | 1509 | 1185 | 1385
Original proposal routine capex (total minus sub-total special projects) | 1029 | 1473 | 1509 | 1185 | 1385

## RIN Capex Detailed Info
|  |  |  | FY17 (16-17) | [5 empty] | FY18 (17-18) | [5 empty] | FY19 (18-19) | [5 empty] | FY20 (19-20) | [5 empty] | FY21 (20-21) | [5 empty] | FY22 (21-22) | [5 empty] | FY23 (22-23) | [5 empty] | FY24 (23-24) | [5 empty] | FY25 (24-25) | [5 empty] | FY26 (25-26)
Item Ref. | AMP Description | Access Arrangement Description | Category | Direct labour | Director contractor | Direct material | Other Direct | Overheads | Total | Direct labour | Director contractor | Direct material | Other Direct | Overheads | Total | Direct labour | Director contractor | Direct material | Other Direct | Overheads | Total | Direct labour | Director contractor | Direct material | Other Direct | Overheads | Total | Direct labour | Director contractor | Direct material | Other Direct | Overheads | Total | Direct labour | Director contractor | Direct material | Other Direct | Overheads | Total | Direct labour | Director contractor | Direct material | Other Direct | Overheads | Total | Direct labour | Director contractor | Direct material | Other Direct | Overheads | Total | Direct labour | Director contractor | Direct material | Other Direct | Overheads | Total | Direct labour | Director contractor | Direct material | Other Direct | Overheads | Total | Grand Total
1 | Below ground station pipe work recoating - Phase 2 | Below ground station pipe work recoating - Phase 2 | SIB CAPEX | 418649.5084 | 2895659.0999 | 0 | 174437.2952 | 0 | 3488745.9035 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3488745.9035
2 | Heat shrink sleeve replacement program | Heat shrink sleeve replacement | SIB CAPEX | 0 | 46498.6125 | 5166.5125 | 0 | 0 | 51665.125 | 0 | 232493.0625 | 25832.5625 | 0 | 0 | 258325.625 | 0 | 235646.249 | 26182.9166 | 0 | 0 | 261829.1656 | 0 | 237772.0865 | 26419.1207 | 0 | 0 | 264191.2073 | 0 | 239919.1824 | 26657.6869 | 0 | 0 | 266576.8693 | 0 | 241870.8925 | 26874.5436 | 0 | 0 | 268745.4362 | 0 | 243840.1681 | 27093.352 | 0 | 0 | 270933.5201 | 0 | 244059.1935 | 27117.6882 | 0 | 0 | 271176.8817 | 0 | 246048.1638 | 27338.6849 | 0 | 0 | 273386.8487 | 0 | 248055.0348 | 27561.6705 | 0 | 0 | 275616.7053 | 2462447.3841
3 | Replace site batteries | Replace site batteries | SIB CAPEX | 27309.9955 | 0 | 55447.5666 | 0 | 0 | 82757.5621 | 35801.3789 | 0 | 72687.6481 | 0 | 0 | 108489.0271 | 4091.4038 | 0 | 8306.7895 | 0 | 0 | 12398.1933 | 11973.2741 | 0 | 24309.3746 | 0 | 0 | 36282.6486 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11742.132 | 0 | 23840.0862 | 0 | 0 | 35582.2182 | 14549.8663 | 0 | 29540.6376 | 0 | 0 | 44090.5039 | 13552.6392 | 0 | 27515.9644 | 0 | 0 | 41068.6036 | 0 | 0 | 0 | 0 | 0 | 0 | 360668.7568
4 | Replace battery chargers at 240 V sites | Replace battery chargers at 240 V sites | SIB CAPEX | 11946.304 | 0 | 15835.7983 | 0 | 0 | 27782.1022 | 10211.6671 | 0 | 13536.396 | 0 | 0 | 23748.0631 | 10910.7034 | 0 | 14463.0255 | 0 | 0 | 25373.7289 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 76903.8943
5 | Single loop controller replacement | Single loop controller replacement | SIB CAPEX | 32620.2929 | 0 | 8671.2171 | 0 | 0 | 41291.51 | 0 | 0 | 0 | 0 | 0 | 0 | 8252.2537 | 0 | 2193.637 | 0 | 0 | 10445.8907 | 8317.7714 | 0 | 2211.0532 | 0 | 0 | 10528.8246 | 8383.9444 | 0 | 2228.6434 | 0 | 0 | 10612.5879 | 8383.9444 | 0 | 2228.6434 | 0 | 0 | 10612.5879 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 83491.401
6 | Hazardous areas equipment upgrades | Hazardous areas assess. & equip. replacement | SIB CAPEX | 48862.775 | 54006.225 | 154303.5 | 0 | 0 | 257172.5 | 29362.4676 | 32453.2537 | 92723.582 | 0 | 0 | 154539.3033 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 411711.8033
7 | Earthing and lightning upgrades | Earthing and lightning upgrades | SIB CAPEX | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8 | Transfer satellite providers and update IP configuration | Transfer satellite providers and update IP configuration | SIB CAPEX | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9 | Clear SCADA | Clear SCADA | SIB CAPEX | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10 | Cathodic protection unit replacement | Cathodic protection unit replacement | SIB CAPEX | 8344.723 | 0 | 20430.184 | 0 | 0 | 28774.907 | 8364.2062 | 0 | 20477.8841 | 0 | 0 | 28842.0903 | 8381.3903 | 0 | 20519.9556 | 0 | 0 | 28901.3459 | 8406.1109 | 0 | 20580.4784 | 0 | 0 | 28986.5893 | 8431.0787 | 0 | 20641.6065 | 0 | 0 | 29072.6852 | 8431.0787 | 0 | 20641.6065 | 0 | 0 | 29072.6852 | 4238.3372 | 0 | 10376.6187 | 0 | 0 | 14614.956 | 4249.8903 | 0 | 10404.9038 | 0 | 0 | 14654.7941 | 8523.0946 | 0 | 20866.8868 | 0 | 0 | 29389.9814 | 11598.9822 | 0 | 28397.5083 | 0 | 0 | 39996.4905 | 272306.5249
11 | New cathodic protection sites | New cathodic protection sites | SIB CAPEX | 58915.7546 | 173281.6312 | 100503.3461 | 13862.5305 | 0 | 346563.2625 | 61438.9441 | 180702.7768 | 104807.6105 | 14456.2221 | 0 | 361405.5536 | 0 | 0 | 0 | 0 | 0 | 0 | 62394.5055 | 183513.2513 | 106437.6858 | 14681.0601 | 0 | 367026.5027 | 0 | 0 | 0 | 0 | 0 | 0 | 63103.9245 | 185599.7779 | 107647.8712 | 14847.9822 | 0 | 371199.5558 | 0 | 0 | 0 | 0 | 0 | 0 | 63720.5231 | 187413.3032 | 108699.7159 | 14993.0643 | 0 | 374826.6065 | 0 | 0 | 0 | 0 | 0 | 0 | 64508.7579 | 189731.641 | 110044.3518 | 15178.5313 | 0 | 379463.282 | 2200484.763
12 | AC mitigation | AC mitigation | Growth CAPEX | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13 | Channel Island bridge upgrade | Channel Island bridge project | Growth CAPEX | 2159602.225 | 7558607.7875 | 1079801.1125 | 0 | 0 | 10798011.125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10798011.125
14 | Replace mainline valve actuators | Replace mainline valve actuators | SIB CAPEX | 12816.3283 | 0 | 78728.8735 | 0 | 0 | 91545.2018 | 0 | 0 | 0 | 0 | 0 | 0 | 12843.5519 | 0 | 78896.1042 | 0 | 0 | 91739.6561 | 0 | 0 | 0 | 0 | 0 | 0 | 12447.2442 | 0 | 76461.6431 | 0 | 0 | 88908.8874 | 0 | 0 | 0 | 0 | 0 | 0 | 12769.5164 | 0 | 78441.3152 | 0 | 0 | 91210.8316 | 0 | 0 | 0 | 0 | 0 | 0 | 12513.2637 | 0 | 76867.1914 | 0 | 0 | 89380.4552 | 0 | 0 | 0 | 0 | 0 | 0 | 452785.032
15 | Replace Tennant Creek mainline valve actuator | Replace mainline valve actuators | SIB CAPEX | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16 | Wizard controller replacement | Wizard controller replacement | SIB CAPEX | 10177.6381 | 0 | 20663.6894 | 0 | 0 | 30841.3275 | 0 | 0 | 0 | 0 | 0 | 0 | 5114.2547 | 0 | 10383.4869 | 0 | 0 | 15497.7416 | 0 | 0 | 0 | 0 | 0 | 0 | 5148.7231 | 0 | 10453.4681 | 0 | 0 | 15602.1911 | 0 | 0 | 0 | 0 | 0 | 0 | 5180.3524 | 0 | 10517.6851 | 0 | 0 | 15698.0374 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 77639.2977
17 | Slops tanks | Slops tanks | SIB CAPEX | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
18 | Ladder access | Ladder access | SIB CAPEX | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
19 | Channel Island bridge upgrade FEED | Channel Island bridge project | Growth CAPEX | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20 | AGP General | Routine replacement | SIB CAPEX | 0 | 0 | 256352.5 | 0 | 0 | 256352.5 | 0 | 0 | 262761.3125 | 0 | 0 | 262761.3125 | 0 | 0 | 269330.3453 | 0 | 0 | 269330.3453 | 0 | 0 | 276063.6039 | 0 | 0 | 276063.6039 | 0 | 0 | 282965.194 | 0 | 0 | 282965.194 | 0 | 0 | 290039.3239 | 0 | 0 | 290039.3239 | 0 | 0 | 297290.307 | 0 | 0 | 297290.307 | 0 | 0 | 304722.5647 | 0 | 0 | 304722.5647 | 0 | 0 | 312340.6288 | 0 | 0 | 312340.6288 | 0 | 0 | 320149.1445 | 0 | 0 | 320149.1445 | 2872014.9246
21 | AGP Motor Vehicles | Motor vehicles | SIB CAPEX | 0 | 0 | 590400 | 0 | 0 | 590400 | 0 | 0 | 221400 | 0 | 0 | 221400 | 0 | 0 | 369000 | 0 | 0 | 369000 | 0 | 0 | 442800 | 0 | 0 | 442800 | 0 | 0 | 590400 | 0 | 0 | 590400 | 0 | 0 | 295200 | 0 | 0 | 295200 | 0 | 0 | 295200 | 0 | 0 | 295200 | 0 | 0 | 295200 | 0 | 0 | 295200 | 0 | 0 | 295200 | 0 | 0 | 295200 | 0 | 0 | 295200 | 0 | 0 | 295200 | 3690000
22 | Building modifications | Building modifications | SIB CAPEX | 0 | 2477712 | 619428 | 0 | 0 | 3097140 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3097140
23 | Gas chromatograph upgrades | Gas chromatograph upgrades | SIB CAPEX | 14359.0405 | 0 | 190770.1095 | 0 | 0 | 205129.15 | 14367.1488 | 0 | 190877.8344 | 0 | 0 | 205244.9832 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 410374.1332
24 | Moisture analyser upgrades | Moisture analyser upgrades | SIB CAPEX | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8215.8696 | 0 | 94482.5007 | 0 | 0 | 102698.3703 | 8222.5883 | 0 | 94559.7657 | 0 | 0 | 102782.354 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 205480.7244
25 | Pine Creek station upgrades | Pine Creek station upgrades | SIB CAPEX | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
26 | Replace CP Ground Beds | Replace CP Ground Beds | SIB CAPEX | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 62182.5967 | 10122.7483 | 0 | 0 | 72305.345 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 63532.2541 | 10342.46 | 0 | 0 | 73874.7141 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 64580.1721 | 10513.0513 | 0 | 0 | 75093.2234 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 65139.6423 | 10604.1278 | 0 | 0 | 75743.7701 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 66161.2358 | 10770.4337 | 0 | 0 | 76931.6696 | 373948.7222
27 | Replace CUG Radio | Replace CUG Radio | SIB CAPEX | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
28 | RTU replacement | RTU replacement | SIB CAPEX | 8504.5681 | 0 | 28471.8149 | 0 | 0 | 36976.383 | 8993.6761 | 0 | 30109.2634 | 0 | 0 | 39102.9395 | 9719.5307 | 0 | 32539.2984 | 0 | 0 | 42258.829 | 9029.4485 | 0 | 30229.0233 | 0 | 0 | 39258.4718 | 9003.127 | 0 | 30140.9033 | 0 | 0 | 39144.0302 | 10003.4744 | 0 | 33489.8925 | 0 | 0 | 43493.3669 | 11960.1129 | 0 | 40040.3781 | 0 | 0 | 52000.491 | 6664.253 | 0 | 22310.7601 | 0 | 0 | 28975.0131 | 8480.6512 | 0 | 28391.7453 | 0 | 0 | 36872.3965 | 7704.7531 | 0 | 25794.1734 | 0 | 0 | 33498.9265 | 391580.8476
29 | Site hut upgrades | Site hut upgrades | SIB CAPEX | 4126.5577 | 15523.7172 | 0 | 0 | 0 | 19650.275 | 8266.9807 | 31099.5942 | 0 | 0 | 0 | 39366.5749 | 8156.9172 | 30685.5456 | 0 | 0 | 0 | 38842.4628 | 8683.8099 | 32667.666 | 0 | 0 | 0 | 41351.4759 | 8320.8712 | 31302.3251 | 0 | 0 | 0 | 39623.1963 | 8153.5452 | 30672.8607 | 0 | 0 | 0 | 38826.4059 | 8471.3209 | 31868.3024 | 0 | 0 | 0 | 40339.6233 | 8723.5377 | 32817.118 | 0 | 0 | 0 | 41540.6557 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 299540.6699
30 | Solar panel replacement | Solar panel replacement | SIB CAPEX | 6497.712 | 0 | 19493.1361 | 0 | 0 | 25990.8481 | 9341.5754 | 0 | 28024.7262 | 0 | 0 | 37366.3016 | 6780.1339 | 0 | 20340.4017 | 0 | 0 | 27120.5356 | 5169.1178 | 0 | 15507.3535 | 0 | 0 | 20676.4713 | 6296.5814 | 0 | 18889.7441 | 0 | 0 | 25186.3255 | 6814.8185 | 0 | 20444.4556 | 0 | 0 | 27259.2741 | 6898.712 | 0 | 20696.1361 | 0 | 0 | 27594.8481 | 7175.9057 | 0 | 21527.7172 | 0 | 0 | 28703.623 | 12110.2659 | 0 | 36330.7976 | 0 | 0 | 48441.0634 | 10487.4071 | 0 | 31462.2213 | 0 | 0 | 41949.6284 | 310288.919
31 | Water bath heater upgrades | Water bath heater upgrades | SIB CAPEX | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15746.9444 | 299191.9431 | 0 | 0 | 0 | 314938.8875 | 0 | 0 | 0 | 0 | 0 | 0 | 16063.458 | 305205.7012 | 0 | 0 | 0 | 321269.1591 | 0 | 0 | 0 | 0 | 0 | 0 | 16353.9013 | 310724.1254 | 0 | 0 | 0 | 327078.0268 | 0 | 0 | 0 | 0 | 0 | 0 | 16524.0636 | 313957.2076 | 0 | 0 | 0 | 330481.2712 | 0 | 0 | 0 | 0 | 0 | 0 | 1293767.3446
32 | Energy Components | Energy Components | SIB CAPEX | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
33 | Vehicle tracking | Vehicle tracking | SIB CAPEX | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
34 | IT Applications renewal program | IT Applications renewal program | SIB CAPEX | 187535.7021 | 406327.3546 | 31255.9504 | 0 | 0 | 625119.0072 | 180872.5751 | 391890.5794 | 30145.4292 | 0 | 0 | 602908.5837 | 190219.2596 | 412141.7292 | 31703.2099 | 0 | 0 | 634064.1988 | 184762.0974 | 400317.8777 | 30793.6829 | 0 | 0 | 615873.658 | 193855.7912 | 420020.8808 | 32309.2985 | 0 | 0 | 646185.9705 | 187613.7504 | 406496.4591 | 31268.9584 | 0 | 0 | 625379.1679 | 197192.7934 | 427251.0523 | 32865.4656 | 0 | 0 | 657309.3112 | 190367.5183 | 412462.9562 | 31727.9197 | 0 | 0 | 634558.3942 | 187407.3834 | 406049.3306 | 31234.5639 | 0 | 0 | 624691.2779 | 181399.6244 | 393032.5195 | 30233.2707 | 0 | 0 | 604665.4146 | 6270754.9838
35 | IT Infrastructure renewal program | IT Infrastructure renewal program | SIB CAPEX | 17119.1277 | 37091.4433 | 2853.1879 | 0 | 0 | 57063.759 | 34320.4639 | 74361.0051 | 5720.0773 | 0 | 0 | 114401.5463 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17696.0547 | 38341.4519 | 2949.3425 | 0 | 0 | 58986.849 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18061.0619 | 39132.3007 | 3010.177 | 0 | 0 | 60203.5395 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 290655.6938
|  |  |  | 3027388.253 | 13664707.8714 | 3278576.4989 | 188299.8257 | 0 | 20158972.449 | 401341.084 | 1005182.8684 | 1109227.0745 | 14456.2221 | 0 | 2530207.2491 | 288432.2132 | 977665.467 | 978341.6714 | 0 | 0 | 2244439.3515 | 306958.7239 | 917803.1357 | 1080253.602 | 14681.0601 | 0 | 2319696.5216 | 285646.8738 | 1034789.5413 | 1094097.5305 | 0 | 0 | 2414533.9456 | 292504.5361 | 929220.1623 | 838348.3464 | 14847.9822 | 0 | 2074921.0271 | 274807.1786 | 1013683.6482 | 836361.3439 | 0 | 0 | 2124852.1707 | 313512.5562 | 981024.514 | 864866.2119 | 14993.0643 | 0 | 2174396.3464 | 259111.3615 | 966054.702 | 856086.463 | 0 | 0 | 2081252.5265 | 275699.5247 | 896980.4311 | 879612.7742 | 15178.5313 | 0 | 2067471.2613 | 40190742.8488
[9 empty] | 0 | [5 empty] | 0 | [5 empty] | 0 | [5 empty] | 0 | [5 empty] | 0 | [5 empty] | 0 | [5 empty] | 0 | [5 empty] | 0 | [5 empty] | 0 | [5 empty] | 0 | 0

## RIN Schedule
Capex Info required to be reported as part of RIN.
If required
Forecast capex | (Real $June 2016)
| 2016-17 | 2017-18 | 2018-19 | 2019-20 | 2020-21 | 2021-22 | 2022-23 | 2023-24 | 2024-25 | 2025-26
| Forecast | Forecast | Forecast | Forecast | Forecast | Forecast | Forecast | Forecast | Forecast | Forecast
| $000 | $000 | $000 | $000 | $000 | $000 | $000 | $000 | $000 | $000
direct labour costs | 3027.3883 | 401.3411 | 288.4322 | 306.9587 | 285.6469 | 292.5045 | 274.8072 | 313.5126 | 259.1114 | 275.6995
direct materials costs | 13664.7079 | 1005.1829 | 977.6655 | 917.8031 | 1034.7895 | 929.2202 | 1013.6836 | 981.0245 | 966.0547 | 896.9804
direct contractor costs | 3278.5765 | 1109.2271 | 978.3417 | 1080.2536 | 1094.0975 | 838.3483 | 836.3613 | 864.8662 | 856.0865 | 879.6128
other direct costs | 188.2998 | 14.4562 | 0 | 14.6811 | 0 | 14.848 | 0 | 14.9931 | 0 | 15.1785
overheads | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total capex | 20158.9724 | 2530.2072 | 2244.4394 | 2319.6965 | 2414.5339 | 2074.921 | 2124.8522 | 2174.3963 | 2081.2525 | 2067.4713
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0