## RIN clauses 6.12,6.14 and 6.15
Project Identification | [5 empty] | Un-escalated Direct Costs ($2016, $000s) | [5 empty] | Costing Methodology | [9 empty] | Cost Estimation Derivation | [7 empty] | Rules Alignment | [7 empty] | Documentation
CAPEX Category | Sub-Category | Activity | AA Identifier | Project Title | Project Summary | FY17 | FY18 | FY19 | FY20 | FY21 | AA2017 Total | Check | Gate 1 or Gate 0 | PEM used for Gate 0 or Gate 1 | Historical Average | Volume X Unit Rate | Market Expansion Unit Rate Model | SIB Meter Replacement Unit Rate Model | Land | Other | Comments | Check | DERIVED FROM COMPETITIVE TENDER PROCESSES | DERIVED FROM COMPETITIVE TENDER PROCESSES FOR SIMILAR PROJECTS | DERIVED FROM ESTIMATES OBTAINED CONTR./MANUF. 6.14 (E) | DERIVED FROM INDEPENDENT BENCHMARKS 6.14 (F) | DERIVED FROM HISTORICAL COSTS FOR SIMILAR PROJECTS 6.14 (G) | REFLECTIVE OF ANY RISK, CONTINGENCY, UNCERTAINTY ETC. 6.14 (H) | COMMENTS | Check | PV OF EXPECTED INCREMENTAL REV.GENERATED AS A RESULT OF THE CAPEX > PV OF CAPEX | CAPEX IS NECESSARY TO MAINTAIN AND IMPROVE SAFETY OF SERVICE | CAPEX IS NECESSARY TO MAINTAIN INTEGRITY OF SERVICE | CAPEX IS NECESSARY TO COMPLY WITH A REGULATORY OBLIGATION OR REQUIREMENT | CAPEX IS NECESSARY TO MAINTAIN THE SERVICE PROVIDERS CAPACITY TO MEET LEVELS OF DEMAND FOR SERVICES EXISTING AT THE TIME THE CAPEX IS INCURRED | CAPEX IS AN AGGREGATE AMOUNT DIVISIBLE INTO TWO PARTS… | COMMENTS | Check | OPPORTUNITY BRIEF | FEASIBILITY ASSESSMENT / SUPPORTING DOC | STRATEGY/ POLICY/ AMP | GATE 0 or 1 | PEM | MANDATE (RFE)
[23 empty] | RIN 6.14 (A) | RIN 6.14 (B) | RIN 6.14 (C) | RIN 6.14 (D) | RIN 6.14 (E) | RIN 6.14 (F) |  |  | 79(2)(b) | 79(2)(c)(i) | 79(2)(c)(ii) | 79(2)(c)(iii) | 79(2)(c)(iv) | 79(2)(d)
ME | GNMEM Infill | 406 | 1 | Mains - Infill | Required for short mains extensions to supply E to G, medium density and I&C that are not on line-of -main. | [6 empty] | 2 |  |  |  | 1 | 1 |  |  |  |  | 1 |  | 1 | [5 empty] | 2 | 1 |  |  | 1 |  |  |  | 1 |  |  | 1 |  |  | N/A
ME | GNMEM New Estates | 407 | 2 | Mains - New Estates | Required for reticulation of new estates opening up for up for residential development | [6 empty] | 2 |  |  |  | 1 | 1 |  |  |  |  | 1 |  | 1 | [5 empty] | 2 | 1 |  |  | 1 |  |  |  | 1 |  |  | 1 |  |  | N/A
ME | GNMEM I&C Contract | 408 | 3 | Mains - I&C Contract Market | Required for mains extensions to supply I&C contract customers that are not on line-of-main. | [6 empty] | 2 |  |  | 1 |  | 1 |  |  |  |  | 1 |  |  |  |  | 1 |  |  | 2 | 1 |  |  | 1 |  |  |  | 1 |  |  | 1 |  |  | N/A
ME | GNMEM Industrial & Commercial | 409 | 4 | Mains - I&C Tariff | Required for mains extensions to supply I&C that are not on line-of-main | [6 empty] | 2 |  |  |  | 1 | 1 |  |  |  |  | 1 |  | 1 | [5 empty] | 2 | 1 |  |  | 1 |  |  |  | 1 |  |  | 1 |  |  | N/A
ME | GNMEM Medium Density | 410 | 5 | Mains - Medium Density | Required for Medium Density developments that require internal reticulation to facilitate connections. | [6 empty] | 2 |  |  |  | 1 | 1 |  |  |  |  | 1 |  | 1 | [5 empty] | 2 | 1 |  |  | 1 |  |  |  | 1 |  |  | 1 |  |  | N/A
ME | GNMEC Infill | 400 | 8 | Connections - Infill | Required for the services and meters for electricity customers who wish to connect to gas. | [6 empty] | 2 |  |  |  | 1 | 1 |  |  |  |  | 1 |  | 1 | [5 empty] | 2 | 1 |  |  | 1 |  |  |  | 1 |  |  | 1 |  |  | N/A
ME | GNMEC New Estates | 401 | 9 | Connections - New Estates | Required for the services and meters for new homes that are being connected to gas. | [6 empty] | 2 |  |  |  | 1 | 1 |  |  |  |  | 1 |  | 1 | [5 empty] | 2 | 1 |  |  | 1 |  |  |  | 1 |  |  | 1 |  |  | N/A
ME | GNMEC I&C Contract | 402 | 10 | Connections - I&C Contract Market | Required for the services and meters for I&C contract customers who are being connected to gas | [6 empty] | 2 |  |  | 1 |  | 1 |  |  |  |  | 1 |  |  |  |  | 1 |  |  | 2 | 1 |  |  | 1 |  |  |  | 1 |  |  | 1 |  |  | N/A
ME | GNMEC Industrial & Commercial | 403 | 11 | Connections - I&C Tariff | Required for the services and meters for industrial and commercial customers who are being connected to gas | [6 empty] | 2 |  |  |  | 1 | 1 |  |  |  |  | 1 |  | 1 | [5 empty] | 2 | 1 |  |  | 1 |  |  |  | 1 |  |  | 1 |  |  | N/A
ME | GNMEC Medium Density | 404 | 12 | Connections - Medium Density | Required for the services and meters for medium density developments which are being connected to gas | [6 empty] | 2 |  |  |  | 1 | 1 |  |  |  |  | 1 |  | 1 | [5 empty] | 2 | 1 |  |  | 1 |  |  |  | 1 |  |  | 1 |  |  | N/A
ME | GNMEMTR Residential | 415 | 15 | New Meter - Infill | Estimated supply & installation of meters in established areas | [6 empty] | 2 |  |  |  | 1 | 1 |  |  |  |  | 1 |  | 1 | [5 empty] | 2 | 1 |  |  | 1 |  |  |  | 1 |  |  | 1 |  |  | N/A
ME | GNMEMTR Residential | 416 | 16 | New Meter - New Estates | Estimated supply & installation of meters in new homes | [6 empty] | 2 |  |  |  | 1 | 1 |  |  |  |  | 1 |  | 1 | [5 empty] | 2 | 1 |  |  | 1 |  |  |  | 1 |  |  | 1 |  |  | N/A
ME | GNMEMTR Industrial & Commercial | 417 | 17 | New Meter - I&C Contract Market | Estimated supply & installation of HP I&C meter sets in established areas | [6 empty] | 2 |  |  | 1 |  | 1 |  |  |  |  | 1 |  |  |  |  | 1 |  |  | 2 | 1 |  |  | 1 |  |  |  | 1 |  |  | 1 |  |  | N/A
ME | GNMEMTR Industrial & Commercial | 418 | 18 | New Meter - I & C Tariff | Estimated supply & installation of I&C meter sets in established areas | [6 empty] | 2 |  |  |  | 1 | 1 |  |  |  |  | 1 |  | 1 | [5 empty] | 2 | 1 |  |  | 1 |  |  |  | 1 |  |  | 1 |  |  | N/A
ME | GNMEMTR Residential | 419 | 19 | New Meter - Medium Density | Estimated supply & installation of hot/cold water meter sets in established areas, both medium density and High Rise | [6 empty] | 2 |  |  |  | 1 | 1 |  |  |  |  | 1 |  | 1 | [5 empty] | 2 | 1 |  |  | 1 |  |  |  | 1 |  |  | 1 |  |  | N/A
ME | GNMEMTR Residential | 423 | 20 | New - Meter Data Loggers & Metreteks | Estimated supply & installation of data loggers and metretek units for domestic | [6 empty] | 2 |  |  |  | 1 | 1 |  |  |  |  | 1 |  | 1 | [5 empty] | 2 | 1 |  |  | 1 |  |  |  | 2 |  | 1 | 1 |  |  | N/A
CDP | GNCDM Medium Pressure | 414 | 29 | Allocations: Winter performance outcomes | Miscellaneous capacity development projects identified through winter | [6 empty] | 1 |  |  | 1 | [6 empty] | 1 |  |  |  |  | 1 |  |  | 2 |  |  | 1 |  | 1 |  |  | 2 | 1 |  | 1 |  |  | As required
CDP | GNCDM Medium Pressure | 414 | 30 | Allocations: Interconnections - ActewAGL | Field identified security of supply upgrades | [6 empty] | 1 |  |  | 1 | [6 empty] | 1 |  |  |  |  | 1 |  |  | 2 |  |  | 1 |  | 1 |  |  | 2 | 1 |  | 1 |  |  | As required
CDP | GNCDM High Pressure | 414 | 34 | Molonglo Secondary Extension Stage 2 CDP | Lay 2.5km of 200mm ST continuing from Stage 1 including 7000 SDRS installation at Denman Prospect | [6 empty] | 2 | 1 | 1 | [7 empty] | 1 |  | 1 | [5 empty] | 2 |  |  | 1 |  | 1 |  |  | 4 | 1 | 1 | 1 | 1 |  | Complete
CDP | GNCDM High Pressure | 414 | 35 | Molonglo Primary Main Extension Stage 1 CDP | Lay ~3.5km of 250mm ST (primary main, to operate as sec until Molonglo PRS installation) from Phillip PRS along Tuggeranong Pkwy to Heysen St. Lay 500m of 100mm ST (secondary) to connect with sec netwk along Heysen St. | [6 empty] | 2 | 1 | 1 | [7 empty] | 1 |  | 1 | [5 empty] | 2 |  |  | 1 |  | 1 |  |  | 4 | 1 | 1 | 1 | 1 |  | Complete
CDP | GNCDM High Pressure | 414 | 42 | Taylor Secondary Main CDP | Lay ~2kms of 150NB to provide supply to the new suburb of Taylor and a 7000 box DR installation. | [6 empty] | 1 |  |  | 1 | [6 empty] | 1 |  | 1 | [5 empty] | 2 |  |  | 1 |  | 1 |  |  | 3 | 1 | 1 | 1 |  |  | Complete
CDP | GNCDM High Pressure | 414 | 43 | West Belconnen Secondary Main (Southern Cross Dr West) | Approx 3kms of 200mm ST. Timing of estate growth unknown. From end of secondary main on southern cross drive. Incl 7000 scmh DR. Scope and Timing of the project is subject to change as project is driven by new estate growth in the area. | [6 empty] | 2 | 1 | 1 | [7 empty] | 1 |  | 1 | [5 empty] | 2 |  |  | 1 |  | 1 |  |  | 4 | 1 | 1 | 1 | 1 |  | 0
CDP | GNCDM High Pressure | 414 | 44 | West Belconnen Secondary Main (Stockdill Dr) | ~1.3kms of 200mm ST. Timing of estate growth unknown. From 150mm secondary main on at the cnr of Spofforth St and Stockdill Dr. Incl 7000 scmh DR. Scope and timing is subject to change as project is driven by new estate growth in the area. | [6 empty] | 1 |  |  | 1 | [6 empty] | 1 |  | 1 | [5 empty] | 2 |  |  | 1 |  | 1 |  |  | 3 | 1 | 1 | 1 |  |  | 1
CDP | GNCDM High Pressure | 414 | 46 | Molonglo Secondary Main Extension Stage 3 | Lay 3.2kms of 200mm ST continuing from Stage 2 to proposed future location of Molonglo PRS. Incl 7000 scmh SDRS. | [6 empty] | 1 |  |  | 1 | [6 empty] | 1 |  | 1 | [5 empty] | 2 |  |  | 1 |  | 1 |  |  | 3 | 1 | 1 | 1 |  |  | 0
CDP | GNCDM Medium Pressure | 414 | 56 | Belconnen - Florey - Ratcliffe Cr CDP | Lay 500m of 110PE in Ratcliffe Cres, interconnecting the 110PE at the cnr or Krefft St to the 50NY on John Cleland Cres | [6 empty] | 3 | 1 | 1 |  | 1 | [5 empty] | 1 |  | 1 | [5 empty] | 2 |  |  | 1 |  | 1 |  |  | 2 |  |  | 1 | 1 |  | RuGS
CDP | GNCDF High Pressure - Land | 414 | 57 | Belconnen Primary Regulating Station (PRS) - Secure land FY19 | Upgrade secondary mains (Gungahlin to Belconnen) to Primary operating pressures. Install new PRS at Belconnen. Buy land to secure location in FY19 | [6 empty] | 1 | [6 empty] | 1 |  |  | 1 |  |  |  | 1 |  |  |  | 2 |  |  | 1 |  | 1 |  |  | 3 | 1 | 1 | 1 |  |  | 0
CDP | GNCDM Medium Pressure | 414 | 58 | Gungahlin - Harrison - Well Station Dr CDP | Lay 830m of 160mm PE along Wells Station Rd from 110mm PE mains in Hoskins St to 160mm PE mains at Flemington Rd | [6 empty] | 3 | 1 | 1 |  | 1 | [5 empty] | 1 |  | 1 | [5 empty] | 2 |  |  | 1 |  | 1 |  |  | 2 |  |  | 1 | 1 |  | RuGS
CDP | GNCDF Medium Pressure | 414 | 59 | Weston Ck - Warramanga DR29 (1050-210kPa) CDP | Replace current DR 29 1600 box to a low DP Mooney Regulator set 7000 box. | [6 empty] | 1 |  |  | 1 | [6 empty] | 1 |  |  |  |  | 1 |  |  | 2 |  |  | 1 |  | 1 |  |  | 2 | 1 |  | 1 |  |  | RuGS
CDP | GNCDM Medium Pressure | 414 | 82 | Belconnen - Charnwood - Bettington Cct CDP | Lay a 110mm PE road crossing from the 110mm PE to the 32mm NY on Bettington Rd. | [6 empty] | 3 | 1 | 1 |  | 1 | [5 empty] | 1 |  | 1 | [5 empty] | 2 |  |  | 1 |  | 1 |  |  | 2 |  |  | 1 | 1 |  | 0
CDP | GNCDM Medium Pressure | 414 | 83 | Queanbeyan - Queanbeyan - Early St CDP | 35m of 50mm NY to connect 75mm NY and 50mm NY at the corner of Stormaway Road/Uriarra Road 20m of 110mm PE road crossing corner of Early Street/ Ross Road (2019) | [6 empty] | 3 | 1 | 1 |  | 1 | [5 empty] | 1 |  | 1 | [5 empty] | 2 |  |  | 1 |  | 1 |  |  | 2 |  |  | 1 | 1 |  | 0
CDP | GNCDM Medium Pressure | 414 | 86 | Gungahlin - Palmerston - Kosciusko Ave CDP | Lay 200m of 50mm NY from 75mm NY on #100 Koscuisko Ave to #13 Yalga Cl (along pedestrian access). | [6 empty] | 3 | 1 | 1 |  | 1 | [5 empty] | 1 |  | 1 | [5 empty] | 2 |  |  | 1 |  | 1 |  |  | 2 |  |  | 1 | 1 |  | 0
CDP | GNCDM Medium Pressure | 414 | 87 | Woden - Hughes - Wisdom St CDP | Lay 200m of 50mm NY main along Wisdom St connecting the existing 50NY main at Wisdom Pl and Boake Pl | [6 empty] | 3 | 1 | 1 |  | 1 | [5 empty] | 1 |  | 1 | [5 empty] | 2 |  |  | 1 |  | 1 |  |  | 2 |  |  | 1 | 1 |  | 0
CDP | GNCDM Medium Pressure | 414 | 88 | Belconnen - Fraser - Bingley Cr CDP | Lay 210m of 50NY in Bingley Cres interconnecting the 75NY at the Corner of Moroney St to the 32NY at the corner of Brophy St. | [6 empty] | 3 | 1 | 1 |  | 1 | [5 empty] | 1 |  | 1 | [5 empty] | 2 |  |  | 1 |  | 1 |  |  | 2 |  |  | 1 | 1 |  | 0
CDP | GNCDM Medium Pressure | 414 | 90 | Belconnen - Florey - Clements St CDP | Lay 220m of 50mm NY in Clements St, interconnecting the 110mm PE in Krefft St with the 32mm NY on the cnr of Clements St and Melbor Cct. | [6 empty] | 3 | 1 | 1 |  | 1 | [5 empty] | 1 |  | 1 | [5 empty] | 2 |  |  | 1 |  | 1 |  |  | 2 |  |  | 1 | 1 |  | 0
CDP | GNCDM Medium Pressure | 414 | 92 | Belconnen - Dunlop - Courtneidge St CDP | Lay 300m of 50mm NY from the 110mm PE in Kerrigan St to the 32mm NY near 19 Courtneidge St. | [6 empty] | 3 | 1 | 1 |  | 1 | [5 empty] | 1 |  | 1 | [5 empty] | 2 |  |  | 1 |  | 1 |  |  | 2 |  |  | 1 | 1 |  | 0
CDP | GNCDM Medium Pressure | 414 | 95 | Belconnen - Charnwood - Lhotsky St Stage 1 CDP | Lay 200m of 110PE in Lhotsky St interconnecting the 110PE at the corner of Florey De to the 32NY at the Corner of Cartwright St | [6 empty] | 3 | 1 | 1 |  | 1 | [5 empty] | 1 |  | 1 | [5 empty] | 2 |  |  | 1 |  | 1 |  |  | 2 |  |  | 1 | 1 |  | 0
CDP | GNCDM Medium Pressure | 414 | 96 | Belconnen - Kaleen - Onkaparinga Cr CDP | Lay 400m of 50NY in Onkaparinga Cres from the 110PE in Maribymong Ave to the 32NY at the Corner of Nambucca St | [6 empty] | 3 | 1 | 1 |  | 1 | [5 empty] | 1 |  | 1 | [5 empty] | 2 |  |  | 1 |  | 1 |  |  | 2 |  |  | 1 | 1 |  | 0
CDP | GNCDM Medium Pressure | 414 | 98 | Tuggeranong - Bonython - Woodcock Dr Stage 1 CDP | Lay 235m of 110mm PE along and across Woodcock Dr, interconnecting the 110mm PE mains on Drakeford Dr and Reay Pl | [6 empty] | 3 | 1 | 1 |  | 1 | [5 empty] | 1 |  | 1 | [5 empty] | 2 |  |  | 1 |  | 1 |  |  | 2 |  |  | 1 | 1 |  | 0
CDP | GNCDM Medium Pressure | 414 | 100 | Belconnen - Fraser- Tillyard Dr Stage 1 CDP | Lay 350m of 110PE from the 110PE on Tillyard Dr near Daley Cres to the 32NY at the Corner of Daley Cres | [6 empty] | 3 | 1 | 1 |  | 1 | [5 empty] | 1 |  | 1 | [5 empty] | 2 |  |  | 1 |  | 1 |  |  | 2 |  |  | 1 | 1 |  | 0
CDP | GNCDM Medium Pressure | 414 | 102 | Belconnen - Higgins - Fullagar Cr CDP | Lay 500m of 110PE in Fullagar Cres Interconnecting the 110PE on Starke St to the 40PE on Cussen St | [6 empty] | 3 | 1 | 1 |  | 1 | [5 empty] | 1 |  | 1 | [5 empty] | 2 |  |  | 1 |  | 1 |  |  | 2 |  |  | 1 | 1 |  | 0
CDP | GNCDM Medium Pressure | 414 | 103 | Nth Canberra - Ainslie - Duffy St CDP | Lay 600m of 110mm PE from the 110mm PE on Majura Ave along Officer Cres and Agnew St to the 32mm NY on the south side of Duffy St | [6 empty] | 3 | 1 | 1 |  | 1 | [5 empty] | 1 |  | 1 | [5 empty] | 2 |  |  | 1 |  | 1 |  |  | 2 |  |  | 1 | 1 |  | 0
CDP | GNCDM Medium Pressure | 414 | 105 | Woden - Isaacs - Yamba Dr CDP | Lay 850m of 110mm PE main connecting existing 110PE main to the existing 110mm PE at the corner of Dorsch Street and Julia Flynn Ave (2019) | [6 empty] | 3 | 1 | 1 |  | 1 | [5 empty] | 1 |  | 1 | [5 empty] | 2 |  |  | 1 |  | 1 |  |  | 2 |  |  | 1 | 1 |  | 0
CDP | GNCDM Medium Pressure | 414 | 107 | Belconnen - Kaleen - Maribymong Ave Stage 2 CDP | Lay 1.3km of 110PE in Maribymong Ave, Interconnecting the 110PE Laid in 2016 with the 110PE at the cnr of Ellenborough St | [6 empty] | 3 | 1 | 1 |  | 1 | [5 empty] | 1 |  | 1 | [5 empty] | 2 |  |  | 1 |  | 1 |  |  | 2 |  |  | 1 | 1 |  | 0
SIB | GNRUF High Pressure | 424 | 141 | Hoskinstown CTS Upgrade | Initial review (FEED) in FY15 Install second meter and control valve run to ensure sufficient capacity for emergency supply of entire ACT network | [6 empty] | 2 | 1 | 1 | [7 empty] | 1 |  | 1 | [5 empty] | 2 |  |  | 1 |  | 1 |  |  | 4 | 1 | 1 | 1 | 1 |  | 0
SIB | GNRUF High Pressure | 424 | 143 | ACT Facilities Compliance Upgrade Program | Leveraging JGN E&I program on HP facilities upgrade for ACT assets | [6 empty] | 1 | [7 empty] | 1 | JGN estimates | 1 |  |  |  |  | 1 |  |  | 3 |  | 1 | 1 | 1 |  |  |  | 2 | 1 |  | 1 |  |  | Required
SIB | GNRUF High Pressure | 424 | 146 | Watson CTS Outlet - Pressure Limiting Station | Required to support operations after the additional gas via Hoskinstown (Nov 2014) proposal | [6 empty] | 1 | [7 empty] | 1 | JGN estimate for Coolamon POTS upgrade | 1 |  |  |  |  | 1 |  |  | 2 |  |  | 1 |  | 1 |  |  | 2 | 1 |  | 1 |  |  | 0
SIB | GNRUF High Pressure | 424 | 147 | Fyshwick Noise reduction | Noise reduction now required due to additional gas through Hoskinstown (Nov 2014) affecting operation times and current permit | [6 empty] | 2 | 1 | 1 | [7 empty] | 1 |  | 1 | [5 empty] | 1 |  |  |  | 1 |  |  |  | 3 | 1 |  | 1 | 1 |  | 0
SIB | GNRUF High Pressure | 425 | 171 | Phillip PRS Capacity Upgrade | Facility Upgrade to capacity of 80,000scmh | [6 empty] | 1 |  |  | 1 | [6 empty] | 1 |  |  |  |  | 1 |  |  | 2 |  |  | 1 |  | 1 |  |  | 2 | 1 |  | 1 |  |  | AA Estimate?
SIB | GNRUF High Pressure | 425 | 172 | Watson PRS Upgrade | Subject to capacity findings, future upgrades may be required. NB: May move to align with metering on second run project | [6 empty] | 1 |  |  | 1 | [6 empty] | 1 |  |  |  |  | 1 |  |  | 2 |  |  | 1 |  | 1 |  |  | 2 | 1 |  | 1 |  |  | Required
SIB | GNRUF High Pressure | 425 | 134 | Minor Capital Works - HP Facilities | Allocation for end of life assets e.g. filters etc. FY15 key projects identified | [6 empty] | 1 |  |  | 1 | [5 empty] | allocation | 1 |  |  |  |  | 1 |  |  | 4 |  | 1 | 1 | 1 | 1 |  |  | 1 | 1 |  |  |  |  | As required
SIB | GNRUM Medium Pressure | 462 | 132 | Minor Capital Works - Standards Works | PROVISION: For minor works identified during field work to be addressed (i.e. under ASA but not Asset Mngt identified new standard etc) e.g. shallow services, riser replacement, broken paddock markers etc | [6 empty] | 1 |  |  | 1 | [5 empty] | allocation | 1 |  |  |  |  | 1 |  |  | 3 |  | 1 | 1 | 1 |  |  |  | 1 |  |  | 1 |  |  | As required
SIB | GNRUM Medium Pressure | 462 | 133 | Minor Capital Works - Valves in High Risk Areas (HRAs) and for Bushfires | High risk area valving is continually reviewed. The provision of additional valves is to ensure safety is maintained. May include steel flex risers. Assumed $5K for valve and $5K for restoration | [6 empty] | 1 |  |  | 1 | [5 empty] | allocation | 1 |  |  |  |  | 1 |  |  | 2 |  | 1 | 1 |  |  |  |  | 1 |  |  | 1 |  |  | As required
SIB | GNRUM High Pressure | 462 | 150 | Canberra Primary Main Isolation Valve | Investigate need for and timing of an isolation valve of the Canberra Primary Main | [6 empty] | 1 | [7 empty] | 1 | carry over from AA11-15 | 1 |  |  |  |  | 1 |  |  | 2 |  |  | 1 | 1 |  |  |  | 2 | 1 | 1 |  |  |  | Required
SIB | GNRUM High Pressure | 462 | 152 | Paddock Markers - Secondary Mains | Bring the marking of the HP network up to the required level as per the Australian Standard for HP mains. May also include high risk medium pressure mains, e.g. one way feed to a large customer base | [6 empty] | 1 | [7 empty] | 1 |  | 1 |  |  |  |  | 1 |  |  | 2 |  | 1 |  | 1 |  |  |  | 1 | 1 |  |  |  |  | As required
SIB | GNRUM High Pressure | 462 | 153 | Hoskinstown to Fyshwick Pigging Run | Inline pigging inspection to monitor pipeline condition and intergrity | [6 empty] | 1 |  |  | 1 | [6 empty] | 1 |  |  |  |  | 1 |  |  | 3 |  | 1 | 1 | 1 |  |  |  | 2 | 1 |  | 1 |  |  | 0
SIB | GNRUM Medium Pressure | 462 | 154 | Inlet Piping Rectification | Implement long term solution in nominated shopping centres to replace current measures to support compliance with relevant safety and compliance requirements. | [6 empty] | 1 | 1 | [8 empty] | 1 |  | 1 | [5 empty] | 2 |  | 1 |  | 1 |  |  |  | 4 | 1 | 1 | 1 | 1 |  | Required
SIB | GNRUM High Pressure | 462 | 155 | Secondary Mains Washaways | Initial year is to investigate via routine maintence and FY$15 are to estimate if work required. Actions may include potential issues with exposed mains such as Kings Ave bridge secondary joints | [6 empty] | 1 |  |  | 1 | [5 empty] | allocation | 1 |  |  |  |  | 1 |  |  | 3 |  | 1 | 1 | 1 |  |  |  | 0 | [5 empty] | Post WD inspection - Required
SIB | GNRUF High Pressure | 462 | 160 | Hoskinstown - Fyshwick Trunk Main Pigging Facilities | 0 | [6 empty] | 1 |  |  | 1 | [6 empty] | 1 |  |  |  |  | 1 |  |  | 3 |  | 1 | 1 | 1 |  |  |  | 1 |  |  | 1 |  |  | 0
SIB | GNRUM High Pressure | 462 | 162 | Hoskinstown to Fyshwick integrity digs | Integrity digs on the Hoskinstown to Fyshwick Pipeline to support integrity management of the asset | [6 empty] | 2 | 1 | 1 | [7 empty] | 2 |  | 1 |  |  | 1 |  |  | 3 |  | 1 | 1 | 1 |  |  |  | 3 | 1 |  | 1 | 1 |  | 0
SIB | GNRUM High Pressure | 462 | 163 | Canberra Primary Main Integrity Digs | Integrity digs on the Canberra Primary Main to support integrity management of the asset | [6 empty] | 2 | 1 | 1 | [7 empty] | 2 |  | 1 |  |  | 1 |  |  | 3 |  | 1 | 1 | 1 |  |  |  | 3 | 1 |  | 1 | 1 |  | 0
SIB | GNRU 3rd Party Relocations | 412 | 179 | ActewAGL Funded Relocation Projects | This amount is for relocations which are not recoverable from the person requesting the work. | [6 empty] | 1 |  |  | 1 | [6 empty] | 1 |  |  |  |  | 1 |  |  | 1 |  |  |  |  | 1 |  |  | 0 | [5 empty] | As required
SIB | GNRUM Industrial & Commercial | 420 | 1 | I&C Meter Capacity Upgrade | 0 | [6 empty] | 1 | [5 empty] | 1 |  |  |  | 1 |  | 1 | [5 empty] | 2 | 1 |  |  |  | 1 |  |  | 2 | 1 |  | 1 |  |  | N/A
SIB | GNRUM Industrial & Commercial | 514 | 2 | Planned Replacement of I&C Aged Gas Meters | 0 | [6 empty] | 1 | [5 empty] | 1 |  |  |  | 1 |  | 1 | [5 empty] | 2 |  |  |  | 1 | 1 |  |  | 2 | 1 |  | 1 |  |  | N/A
SIB | GNRUM Industrial & Commercial | 514 | 3 | Planned Replacement of I&C Aged Contract Gas Meters (Turbine Like for Like) | 0 | [6 empty] | 1 | [5 empty] | 1 |  |  |  | 1 |  | 1 | [5 empty] | 2 |  |  |  | 1 | 1 |  |  | 2 | 1 |  | 1 |  |  | N/A
SIB | GNRUM Industrial & Commercial | 514 | 4 | Planned Replacement of I&C Metreteks (NBN & Aged) | Address implications for meters and SCADA equipment and possible works | [6 empty] | 1 | [5 empty] | 1 |  |  |  | 1 |  | 1 | [5 empty] | 2 |  |  |  | 1 | 1 |  |  | 3 | 1 | 1 | 1 |  |  | Required
SIB | GNRUM Residential | 516 | 5 | Planned Replacement of Residential Aged Gas Meters | 0 | [6 empty] | 1 | [5 empty] | 1 |  |  |  | 1 |  | 1 | [5 empty] | 2 |  |  |  | 1 | 1 |  |  | 2 | 1 |  | 1 |  |  | N/A
SIB | GNRUM Residential | 516 | 6 | Planned Statistical Sampling of Residential Gas Meters | 0 | [6 empty] | 1 | [5 empty] | 1 |  |  |  | 1 |  | 1 | [5 empty] | 2 |  |  |  | 1 | 1 |  |  | 2 | 1 |  | 1 |  |  | N/A
SIB | GNRUM Residential | 516 | 8 | Planned Replacement of Residential Hot Water Meters | 0 | [6 empty] | 1 | [5 empty] | 1 |  |  |  | 1 |  | 1 | [5 empty] | 2 |  |  |  | 1 | 1 |  |  | 2 | 1 |  | 1 |  |  | N/A
SIB | GNRUM Residential | 516 | 9 | Planned Replacement of MDL Communications | 0 | [6 empty] | 1 | [5 empty] | 1 |  |  |  | 1 |  | 1 | [5 empty] | 2 |  |  |  | 1 | 1 |  |  | 3 | 1 | 1 | 1
SIB | GNRUM Residential | 516 | 10 | Planned Replacement of MDL | 0 | [6 empty] | 1 | [5 empty] | 1 |  |  |  | 1 |  | 1 | [5 empty] | 2 |  |  |  | 1 | 1 |  |  | 3 | 1 | 1 | 1 |  |  | N/A
SIB | GNRUM Industrial & Commercial | 515 | 11 | Defective Replacement of I&C Gas Meters | 0 | [6 empty] | 1 | [5 empty] | 1 |  |  |  | 1 |  | 1 | [5 empty] | 2 |  |  |  | 1 | 1 |  |  | 2 | 1 |  | 1 |  |  | N/A
SIB | GNRUM Residential | 517 | 12 | Residential Defective Meter Replacement | 0 | [6 empty] | 1 | [5 empty] | 1 |  |  |  | 1 |  | 1 | [5 empty] | 2 |  |  |  | 1 | 1 |  |  | 2 | 1 |  | 1 |  |  | N/A
SIB | GNRUM Residential | 517 | 13 | Residential Defective Hot Water Meters Replacement | 0 | [6 empty] | 1 | [5 empty] | 1 |  |  |  | 1 |  | 1 | [5 empty] | 2 |  |  |  | 1 | 1 |  |  | 2 | 1 |  | 1 |  |  | N/A
SIB | GNRUM Residential | 536 | 14 | Residential Defective Regulator Replacement | 0 | [6 empty] | 1 | [5 empty] | 1 |  |  |  | 1 |  | 1 | [5 empty] | 3 |  | 1 |  | 1 | 1 |  |  | 2 | 1 |  | 1 |  |  | N/A
SIB | GNRUM Residential | 536 | 15 | Field Failure testing | 0 | [6 empty] | 1 | [5 empty] | 1 |  |  |  | 1 |  |  | 1 |  |  |  |  | 2 |  |  |  | 1 | 1 |  |  | 2 | 1 |  | 1
Non-Dist | GIS | DSOF | 181 | GIS Upgrade | 0 | [6 empty] | 1 | [7 empty] | 1 | Desktop estimate | 1 |  |  |  |  | 1 |  |  | 2 |  | 1 | 1 |  |  |  |  | 2 | 1 |  | 1
Construction Mgt Fee | Construction Mgt Fee | 490 | - | Construction Management Fee (ACT) | Management Fee introduced in FY14. Note unit rates reduced as a result | [6 empty] | 1 |  |  | 1 | [5 empty] | Fee adjustment spreadsheet | 1 |  |  |  |  | 1 |  |  | 5 | 1 | 1 | 1 | 1 | 1 |  |  | 1 |  |  | 1 |  |  | N/A
Note on AN20: Jasmin Wu: with VW
Note on AN21: Jasmin Wu: same OB as 414-29
Note on P26: For DA
Note on P27: For DA