## Contents
AusNet Services - Transmission
TRR Capex Forecast Model (2017-18 to 2021-22)
1. Key Assumptions
2. Lookups
3. Project Inputs - Master sheet
4. Individual project sheets (46 in total)
5. Outputs:-
5.1 - Forecast Capex As Incurred
| a. | Direct Expenditure Forecast Summary - As Incurred
| b. | Total Expenditure Forecast - Summary by Asset Class (As Incurred)
| c. | Total Expenditure Forecast - Summary by Replacement Driver (As Incurred)
| d. | Selected As Incurred Forecasts
5.2 - Forecast Capex As Commissioned
| a. | Total Expenditure Forecast - Summary by Asset Class (As Commissioned)
| b. | Total Expenditure Forecast - Summary by Replacement Driver (As Commissioned)
5.3 - Reset RIN outputs:
2.1 Expenditure Summary
2.6 Non Network
2.10 Overheads
2.12 Input Tables
6. Error Checks:-
Error Checks Summary

## Assumptions
Timing Assumptions
Calendar format - Regulatory Years | 1 Apr - 31 Mar
Model start date (year) | 2015/16
Input Dollars stated in | $ 2015/16
Output Table Dollars stated in | $ Mar 2017
Escalation Assumptions
Inflation
|  | 2011-09-30 | 2012-09-30 | 2013-09-30 | 2014-09-30 | 2015-09-30 | 2016-03-31 | 2017-09-30 | 2018-09-30 | 2019-09-30 | 2020-09-30 | 2021-09-30 | 2022-09-30
|  | Actual | Actual | Actual | Actual | Actual | Actual | Forecast | Forecast | Forecast | Forecast | Forecast | Forecast
Applies to year |  | 2012/13 | 2013/14 | 2014/15 | 2015/16 | 2016/17 | End '17 | 2017/18 | 2018/19 | 2019/20 | 2020/21 | 2021/22 | 2022/23
CPI - 8 Capital cities (Prior Sept qtr, Re-based in Sep-12) |  | 99.8 | 101.8 | 104 | 106.4 | 108 | 108.2 | 109.782 | 111.5934 | 113.4347 | 115.3064 | 117.2089 | 119.1429
Annual inflation (Sept to Sept) |  | 3.52% | 2.004% | 2.161% | 2.308% | 1.504% | 0.1852% | 1.65% | 1.65% | 1.65% | 1.65% | 1.65% | 1.65%
Inflation index - nominal to $ March 2017 |  | 1.0842 | 1.0629 | 1.0404 | 1.0169 | 1.0019 | 1 | 0.98559 | 0.96959 | 0.95385 | 0.93837 | 0.92314 | 0.90815
Inflation index - nominal to $ 2015/16 |  | 1.0661 | 1.0452 | 1.0231 | 1 | 0.98519 | 0.98336 | 0.96919 | 0.95346 | 0.93798 | 0.92276 | 0.90778 | 0.89305
Inflation index - $2015/16 to nominal |  |  |  |  | 1 | 1.015 | 1.0169 | 1.0318 | 1.0488 | 1.0661 | 1.0837 | 1.1016 | 1.1198
Labour Escalation |  | 2015/16: Base year for escalation - 2015/16
|  | 2012/13 | 2013/14 | 2014/15 | 2015/16 | 2016/17 | 2017/18 | 2018/19 | 2019/20 | 2020/21 | 2021/22 | 2022/23
Internal labour escalation rates - Average of CIE (Vic) and DAE (National) utilities forecasts |  |  |  |  | 0.5875% | 0.66% | 0.805% | 0.81% | 0.8275% | 0.895% | 0.91% | 0.91%
Internal labour index |  |  |  | 1 | 1.0059 | 1.0125 | 1.0207 | 1.0289 | 1.0374 | 1.0467 | 1.0563 | 1.0659
External labour escalation rates - Average of CIE (Vic) and DAE (National) construction forecasts |  |  |  |  | 0.41% | 0.6625% | 1.038% | 1.042% | 1.008% | 1.09% | 1.115% | 1.115%
External labour index |  |  |  | 1 | 1.0041 | 1.0108 | 1.0212 | 1.0319 | 1.0423 | 1.0536 | 1.0654 | 1.0773
Materials Escalation
Real cost escalation rates
Asset Category type |  |  |  |  | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 | 2022
Secondary | bar: 2016 to 2022
Switchgear | bar: 2016 to 2022
Transformers | bar: 2016 to 2022
Reactive | bar: 2016 to 2022
Lines and towers | bar: 2016 to 2022
Establishment | bar: 2016 to 2022
Communications | bar: 2016 to 2022
Non System - Other | bar: 2016 to 2022
Land | bar: 2016 to 2022
Easements | bar: 2016 to 2022
Vehicles | bar: 2016 to 2022
Premises | bar: 2016 to 2022
IT | bar: 2016 to 2022
Real cost escalation index
Base year for escalation - 2015/16
Asset Category type |  | 2012/13 | 2013/14 | 2014/15 | 2015/16 | 2016/17 | 2017/18 | 2018/19 | 2019/20 | 2020/21 | 2021/22 | 2022/23
Secondary | bar: 2014/15 to Base year for escalation - 2015/16 2021/22
Switchgear | bar: 2014/15 to Base year for escalation - 2015/16 2021/22
Transformers | bar: 2014/15 to Base year for escalation - 2015/16 2021/22
Reactive | bar: 2014/15 to Base year for escalation - 2015/16 2021/22
Lines and towers | bar: 2014/15 to Base year for escalation - 2015/16 2021/22
Establishment | bar: 2014/15 to Base year for escalation - 2015/16 2021/22
Communications | bar: 2014/15 to Base year for escalation - 2015/16 2021/22
Non System - Other | bar: 2014/15 to Base year for escalation - 2015/16 2021/22
Land | bar: 2014/15 to Base year for escalation - 2015/16 2021/22
Easements | bar: 2014/15 to Base year for escalation - 2015/16 2021/22
Vehicles | bar: 2014/15 to Base year for escalation - 2015/16 2021/22
Premises | bar: 2014/15 to Base year for escalation - 2015/16 2021/22
IT | bar: 2014/15 to Base year for escalation - 2015/16 2021/22
Capital Efficiency
Capital Efficiency Factor - to apply to regulatory years 2018-22 |  | Base year for escalation - 2015/16 2017/18: 0.89%; Base year for escalation - 2015/16 2018/19: (positive values have the effect of reducing Capex)
Capitalised Overhead Assumptions
|  | 2012/13 | 2013/14 | 2014/15 | 2015/16 | 2016/17 | 2017/18 | 2018/19 | 2019/20 | 2020/21 | 2021/22 | 2022/23
|  | Actual | Actual | Actual | Actual | Forecast | Forecast | Forecast | Forecast | Forecast | Forecast | Forecast
Network Overheads - Replacement Capex only
Repex Overheads - $m, nomimal |  | 11.5812 | 8.7599 | 9.6608 | 10.1641 | 10.292 | 10.9745 | 11.499 | 11.7997 | 9.5675 | 8.1815
Repex Overheads - $m, real $2015/16 |  | 12.3471 | 9.1557 | 9.8837 | 10.1641 | 10.1395 | 10.6364 | 10.9639 | 11.0679 | 8.8285 | 7.427
Direct Replacement Capex (As Incurred) - $m, real $2015/16 |  | 151.0589 | 116.3045 | 121.3601 | 120.6393 | 139.6753 | 138.896 | 121.6407 | 123.408 | 111.0747 | 92.821
Repex Overhead rate |  | 8.174% | 7.872% | 8.144% | 8.425% | 7.259% | 7.658% | 9.013% | 8.969% | 7.948% | 8.001% | 8.318%
Non Network Overheads - General | bar: 2012/13 to 2022/23
Non Network Overheads - IT
IT Capitalised overheads - $m, nominal |  | 0.56065 | 0.86737 | 0.85461 | 0.83507 | 1.5683 | 1.5487 | 1.3864 | 1.2347 | 0.87814 | 0.76024
IT Capitalised overheads - $m, real $2015/16 |  | 0.59773 | 0.90656 | 0.87433 | 0.83507 | 1.5451 | 1.501 | 1.3219 | 1.1581 | 0.81031 | 0.69013
Direct IT Capex (As Incurred) - $m, real $2015/16 |  | 13.3615 | 17.7003 | 18.8519 | 7.878 | 17.6544 | 23.575 | 21.3998 | 12.7624 | 10.6724 | 9.0896
IT Capex OH rate |  | 4.474% | 5.122% | 4.638% | 10.6% | 8.752% | 6.367% | 6.177% | 9.075% | 7.593% | 7.593% | 7.361%
Historical Direct Capex and Overheads as per Historical CA RIN data
Total OHDs from above - $2015/16 |  | 12.9448 | 10.0623 | 10.7581 | 10.9992 | 11.6847 | 12.1374 | 12.2857 | 12.2261 | 9.6388 | 8.1171
Total OHDs - $ Nominal |  | 12.1418 | 9.6273 | 10.5154 | 10.9992 | 11.8604 | 12.5232 | 12.8854 | 13.0344 | 10.4456 | 8.9417
| OH Summary Tbl |  |  | Prior | 2015-16 | 2016-17 | 2017-18 | 2018-19 | 2019-20 | 2020-21 | 2021-22 | 2022-23
| Repex_OHD |  |  | 8.008% | 8.425% | 7.259% | 7.658% | 9.013% | 8.969% | 7.948% | 8.001% | 8.318%
| Non_IT_OHD |  |  | 0% | bar: 2015-16 to 2022-23
| IT_OHD |  |  | 4.88% | 10.6% | 8.752% | 6.367% | 6.177% | 9.075% | 7.593% | 7.593% | 7.361%
[7 empty] | 2017/18 | 2018/19 | 2019/20 | 2020/21 | 2021/22
Fixed Overheads Split | [6 empty] | 0.75 | 0.75 | 0.75 | 0.75 | 0.75
Variable Overheads Split | [6 empty] | 0.25 | 0.25 | 0.25 | 0.25 | 0.25
Repex Overheads
$m, real $2015/16 | [6 empty] | 2017/18 | 2018/19 | 2019/20 | 2020/21 | 2021/22
Repex Overheads - Fixed | [6 empty] | 7.9015 | 8.0668 | 8.2036 | 6.6214 | 5.5703
Repex Overheads - Variable (before amendments) | [6 empty] | 2.6338 | 2.6889 | 2.7345 | 2.2071 | 1.8568
Repex Overheads - Variable (including reduction/increase) | [6 empty] | 2.7349 | 2.897 | 2.8643 | 2.2071 | 1.8568
Repex Overheads - Total | [6 empty] | 10.6364 | 10.9639 | 11.0679 | 8.8285 | 7.427
IT Overheads
$m, real $2015/16 | [6 empty] | 2017/18 | 2018/19 | 2019/20 | 2020/21 | 2021/22
IT Capitalised overheads - Fixed | [6 empty] | 1.1257 | 0.9914 | 0.86861 | 0.60773 | 0.5176
IT Capitalised overheads - Variable (before amendments) | [6 empty] | 0.37524 | 0.33047 | 0.28954 | 0.20258 | 0.17253
IT Capitalised overheads - Variable (including reduction/increase) | [6 empty] | 0.37524 | 0.33047 | 0.28954 | 0.20258 | 0.17253
IT Capitalised overheads - Total | [6 empty] | 1.501 | 1.3219 | 1.1581 | 0.81031 | 0.69013
Initial Proposal Capex (Including real costs escalators, excluding Efficiency factors)
$m, real $2015/16 | [6 empty] | 2017/18 | 2018/19 | 2019/20 | 2020/21 | 2021/22
Direct Replacement Capex (As Incurred) | [6 empty] | 133.764 | 112.9031 | 117.8152 | 111.0747 | 92.821
Direct IT Capex (As Incurred) | [6 empty] | 23.575 | 21.3998 | 12.7624 | 10.6724 | 9.0896
Total Direct | [6 empty] | 157.3389 | 134.3029 | 130.5776 | 121.747 | 101.9105
Initial Proposal Overhead ($m, real $2015/16) | [6 empty] | 2017/18 | 2018/19 | 2019/20 | 2020/21 | 2021/22
Repex | [6 empty] | 10.5354 | 10.7558 | 10.9381 | 8.8285 | 7.427
IT | [6 empty] | 1.501 | 1.3219 | 1.1581 | 0.81031 | 0.69013
Total | [6 empty] | 12.0364 | 12.0776 | 12.0963 | 9.6388 | 8.1171

## Lookups
Asset Category 1 | Project Category 2 |  | Overhead Category | RIN Exp Category
Secondary | Replacement - Major Station |  | Repex_OHD | Transmission Towers | Replacement
Switchgear | Replacement - Major Station CBD |  | Non_IT_OHD | Transmission Tower Support Structures | Replacement
Transformers | Replacement - Other |  | IT_OHD | Conductors | Replacement
Reactive | Security and Compliance |  |  | Transmission Cables | Replacement
Towers and Conductor | Non Network - Other |  |  | Substation Switchbays | Replacement
Establishment | Non Network - Vehicles |  |  | Substation Power Transformers | Replacement
Communications | Non Network - Premises |  |  | Substation Reactive Plant | Replacement
Inventory | Non Network - IT |  |  | Scada Network Control And Protection Systems | Replacement
IT |  |  |  | Other - Replacement | Replacement
Vehicles | Project Category 1 |  |  | It And Communications | Non Network
Other (non-network) | Network |  |  | Motor Vehicles | Non Network
Premises | Non Network |  |  | Buildings And Property | Non Network
Land |  |  |  | Other - Non Network | Non Network
Easements | Denominations
| Thousands | 1000
| Millions | 1000000

## Project_Inputs
Table of Contents
Project Input Control Sheet
[10 empty] | As Incurred Capex - Direct ($000's) - All values expressed in $2015/16 | [12 empty] | As Commissioned Capex %'s | [9 empty] | As Commissioned Capex - Direct ($000's) - Expressed in $2015/16
Proj No | Oracle ID | SAP ID | Project name | Location | Bus Case - Y/N | Target compl | Project category 1 | Project category 2 | Overhead Category | Prior (Actual) | 2014-15 (Actual) | 2015-16 (Actual) | 2016-17 (Forecast) | 2017-18 (Forecast) | 2018-19 (Forecast) | 2019-20 (Forecast) | 2020-21 (Forecast) | 2021-22 (Forecast) | 2022-23 (Forecast) | Forecast Period Total | Overall Forecast Total | Prior Capex (to Mar-15) | Prior | 2015-16 | 2016-17 | 2017-18 | 2018-19 | 2019-20 | 2020-21 | 2021-22 | 2022-23 | Total | Prior | 2015-16 | 2016-17 | 2017-18 | 2018-19 | 2019-20 | 2020-21 | 2021-22 | 2022-23 | Total | Check
1 | XC17 | TD-0003437 | FBTS Refurbishment | FBTS | Yes | 2017 | Network | Replacement - Major Station | Repex_OHD | 87.7807 | 59.5435 | 172.3798 | 7921.1797 | 3437.554 | 0 | 0 | 0 | 0 | 0 | 3437.554 | 11678.4377 | 147.3242 |  | 2016-17: 71.1%; 2017-18: 28.1%; 2018-19: 0.8% | 100% | 0 | 0 | 8303.3692 | 3281.641 | 93.4275 | 0 | 0 | 0 | 0 | 11678.4377 | 0
2 | XC28 | TD-0003456 | HWPS 220kV Switchyard Redevelopment Stage 4 | HWPS | Yes | 2018 | Network | Replacement - Major Station | Repex_OHD | 35.9876 | 18.5658 | 2960.7521 | 7604.2597 | 7713.246 | 3649.602 | 0 | 0 | 0 | 0 | 11362.848 | 21982.4132 | 54.5534 |  | 2016-17: 40.48%; 2017-18: 41.4%; 2018-19: 18.12% | 100% | 0 | 0 | 8898.4809 | 9100.7191 | 3983.2133 | 0 | 0 | 0 | 0 | 21982.4132 | 0
3 | XA09 | TD-0003317 | RTS Redevelopment Project | RTS | Yes | 2017 | Network | Replacement - Major Station CBD | Repex_OHD | 53035.2186 | 36789.5484 | 29819.1972 | 22138.7516 | 11436.882 | 1094.058 | 0 | 0 | 0 | 0 | 12530.94 | 154313.6557 | 89824.767 | 28.13% | 2015-16: 20.47%; 2016-17: 24%; 2017-18: 20%; 2018-19: 7.4% | 100% | 43410.4116 | 31585.5749 | 37035.2774 | 30862.7311 | 11419.6607 | 0 | 0 | 0 | 0 | 154313.6557 | 0
4 | XB59 | TD-0003414 | HTS Rebuild | HTS | Yes | 2017 | Network | Replacement - Major Station | Repex_OHD | 1354.2014 | 6450.9802 | 13467.3399 | 18923.223 | 3639.548 | 0 | 0 | 0 | 0 | 0 | 3639.548 | 43835.2925 | 7805.1816 |  | 2015-16: 2.237%; 2016-17: 29%; 2017-18: 34%; 2018-19: 34.76% | 100% | 0 | 980.4086 | 12712.2348 | 14903.9994 | 15238.6496 | 0 | 0 | 0 | 0 | 43835.2925 | 0
5 | XC19 | TD-0003439 | SMTS H2 Transformer Replacement | SMTS | Yes | 2019 | Network | Replacement - Major Station | Repex_OHD | 162.7385 | 24.9616 | 2351.9049 | 8414.7736 | 16207.048 | 816.202 |  |  |  |  | 17023.25 | 27977.6286 | 187.7001 |  | 2016-17: 41%; 2017-18: 56%; 2018-19: 3% | 100% | 0 | 0 | 11470.8277 | 15667.472 | 839.3289 | 0 | 0 | 0 | 0 | 27977.6286 | 0
6 | Various |  | Other committed projects |  |  |  | Network | Replacement - Major Station | Repex_OHD | 0 | 0 | 54.8798 | 318.7414 | 544.2139 | 0 | 0 | 0 | 0 | 0 | 544.2139 | 917.8352 | 0 | [9 empty] | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | XC21 | TD-0003451, TD-0006252 | RWTS B4 220/66kV Transformer and 66kV CB Replacement | RWTS |  | 2018 | Network | Replacement - Major Station | Repex_OHD | 0 | 0 | 39.4335 | 3590 | 6076 | 3867 | 0 | 0 | 0 | 0 | 9943 | 13572.4335 | 0 | [9 empty] | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8 | XC15 | TD-0003435 | TSTS B2 Transformer and 66kV CB Replacement | TSTS |  | 2021 | Network | Replacement - Major Station | Repex_OHD | 34.298 | 1.5175 | -33.6604 | 0 | 0 | 0 | 581 | 7551 | 12778 | 0 | 20910 | 20912.1551 | 35.8155 | [9 empty] | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9 | XB61 | TD-0003415 | SVTS Redevelopment Stage 1 | SVTS |  | 2021 | Network | Replacement - Major Station | Repex_OHD | 152.4665 | 13.6869 | 25.8698 | 369.7401 | 1307 | 7841 | 16988 | 20908 | 17968 | 0 | 65012 | 65573.7633 | 166.1534 | [9 empty] | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10 | XA14 | TD-0003319 | WMTS Redevelopment | WMTS | Yes | 2021 | Network | Replacement - Major Station CBD | Repex_OHD | 5569.4154 | 4189.3259 | 1215.0169 | 7285.5183 | 20885 | 21896 | 25995 | 16000 | 7148 | 0 | 91924 | 110183.2765 | 9758.7413 |  | 0% | 0% | 19.79% | 26.12% | 33.24% | 14.41% | 6.438% | 0% | 100% | 0 | 0 | 0 | 21802.8867 | 28779.8104 | 36628.8496 | 15878.1612 | 7093.5685 | 0 | 110183.2765 | 0
11 | 284A | TD-0004189 | HYTS 500kV and 275kV CB Replacement | HYTS |  | 2018 | Network | Replacement - Major Station | Repex_OHD | 0 | 0 | 27.0944 | 1800 | 3046 | 1938 | 0 | 0 | 0 | 0 | 4984 | 6811.0944 | 0 | [9 empty] | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12 | 285A | TD-0004190 | FBTS Transformer and Circuit Breaker Replacement | FBTS |  | 2020 | Network | Replacement - Major Station | Repex_OHD | 0 | 0 | 0 | 0 | 638 | 8289 | 14027 | 8926 | 0 |  | 31880 | 31880 | 0 | [9 empty] | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13 | XB12 | TD-0003375 | Glenrowan Terminal Station Redevelopment Project | GNTS | Yes | 2015 | Network | Replacement - Major Station | Repex_OHD | 15381.8006 | 4875.2386 | 1585.6739 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 21842.7131 | 20257.0393 | 89.28% | 2015-16: 6.572%; 2016-17: 4.144% | 100% | 19502.0864 | 1435.4784 | 905.1484 | 0 | 0 | 0 | 0 | 0 | 0 | 21842.7131 | 0
14 | XB54 | TD-0003400 | Ringwood Terminal Station (RWTS) 220kV Circuit Breaker Replacements | RWTS | Yes | 2015 | Network | Replacement - Major Station | Repex_OHD | 7979.0778 | 5233.286 | 399.4162 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 13611.78 | 13212.3638 | 95.3% | 2015-16: 3.16%; 2016-17: 1.541% | 100% | 12971.8516 | 430.1323 | 209.796 | 0 | 0 | 0 | 0 | 0 | 0 | 13611.78 | 0
15 | XB56 | TD-0003412 | HWPS CB Replacement Stage 3 | HWPS | Yes | 2015 | Network | Replacement - Major Station | Repex_OHD | 1741.2866 | 3596.7492 | 1619.3073 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 6957.3431 | 5338.0358 | 55.15% | 2015-16: 42.32%; 2016-17: 2.532% | 100% | 3836.7384 | 2944.4592 | 176.1455 | 0 | 0 | 0 | 0 | 0 | 0 | 6957.3431 | 0
16 | XB64 | TD-0003416 | MWTS B2 Transformer Replacement | MWTS | Yes | 2016 | Network | Replacement - Major Station | Repex_OHD | 261.1162 | 2274.3955 | 3371.1761 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 5906.6878 | 2535.5117 |  | 2015-16: 83.32%; 2016-17: 16.68% | 100% | 0 | 4921.4296 | 985.2582 | 0 | 0 | 0 | 0 | 0 | 0 | 5906.6878 | 0
17 | XC16 | TD-0003436 | TTS Bus Tie CB Replacement | TTS | Yes | 2016 | Network | Replacement - Major Station | Repex_OHD | 159.8213 | 88.6499 | 740.0775 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 988.5487 | 248.4712 |  | 2016-17: 100% | 100% | 0 | 0 | 988.5487 | 0 | 0 | 0 | 0 | 0 | 0 | 988.5487 | 0
18 | XC18 | TD-0003438 | YPS 220kV CB Replacement | YPS | Yes | 2017 | Network | Replacement - Major Station | Repex_OHD | 596.6378 | 2617.94 | 3530.5755 | 4301.1878 | 0 | 0 | 0 | 0 | 0 |  | 0 | 11046.3411 | 3214.5777 |  | 2016-17: 59%; 2017-18: 41% | 100% | 0 | 0 | 6517.3412 | 4528.9999 | 0 | 0 | 0 | 0 | 0 | 11046.3411 | 0
19 |  |  | Other station transformer replacement |  |  |  | Network | Replacement - Major Station | Repex_OHD |  | 9613.3377 | 612.6528 | 881.5477 | [6 empty] | 0 | 11107.5382 | 9613.3377 | [9 empty] | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20 | X834, XC72 | TD-0003273, TD-0003522 | Power transformers - Bushings replacement |  |  |  | Network | Replacement - Other | Repex_OHD | 930.565 | 1232.3021 | -190.9089 | 1752.1671 | 680 | 680 | 680 | 680 | 680 |  | 3400 | 7124.1254 | 2162.8671 | [9 empty] | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
21 |  |  | Power transformers - life extension |  |  |  | Network | Replacement - Other | Repex_OHD |  | 0 | 0 | 0 | 1256 | 1256 | 1256 | 1256 | 1256 |  | 6280 | 6280 | 0 | [9 empty] | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22 | XC69 | TD-0003509 | Power transformers - improved safe access |  |  |  | Network | Security and Compliance | Repex_OHD |  | 0 | 10.3732 | 1001.7588 | 500 | 500 | 500 | 500 | 500 |  | 2500 | 3512.132 | 0 | [9 empty] | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23 |  |  | Circuit breakers |  |  |  | Network | Replacement - Other | Repex_OHD |  | 1831.3157 | 2149.4687 | 1001.7588 | 5922.4 | 5922.4 | 5922.4 | 5922.4 | 5922.4 |  | 29612 | 34594.5432 | 1831.3157 | [9 empty] | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24 | Various |  | Instrument transformers |  |  |  | Network | Security and Compliance | Repex_OHD |  | 492.1801 | 1292.6728 | 2595.4659 | 1480 | 1480 | 1480 | 1480 | 1480 |  | 7400 | 11780.3189 | 492.1801 | [9 empty] | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
25 |  |  | Disconnectors |  |  |  | Network | Replacement - Other | Repex_OHD |  | 0 | 0 | 0 | 848 | 2440 | 2440 | 2440 | 2440 |  | 10608 | 10608 | 0 | [9 empty] | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
26 | Various |  | Syn Cons |  |  |  | Network | Replacement - Other | Repex_OHD |  | 1746.2856 | 634.5129 | 2126.0599 | 0 | 0 | 0 | 0 | 0 |  | 0 | 4506.8584 | 1746.2856 | [9 empty] | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
27 |  |  | Reactive plant |  |  |  | Network | Replacement - Other | Repex_OHD |  | 2779.9674 | 238.1366 | 7558.7252 | 164 | 164 | 164 | 164 | 164 |  | 820 | 11396.8292 | 2779.9674 | [9 empty] | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
28 |  |  | On-line monitoring |  |  |  | Network | Replacement - Other | Repex_OHD |  | 0 | 0 | 0 | 170 | 200 | 100 | 100 | 100 |  | 670 | 670 | 0 | [9 empty] | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
29 | Various |  | Fire protection systems |  |  |  | Network | Security and Compliance | Repex_OHD |  | 2142.867 | 2646.2623 | 2375.079 | 1755 | 1755 | 1755 | 1755 | 1755 |  | 8775 | 15939.2083 | 2142.867 | [9 empty] | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
30 |  |  | Civils |  |  |  | Network | Replacement - Other | Repex_OHD |  | 0 | 0 | 0 | 1770 | 1770 | 1770 | 1770 | 1770 |  | 8850 | 8850 | 0 | [9 empty] | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
31 |  |  | Infrastructure security |  |  |  | Network | Security and Compliance | Repex_OHD |  | 878.7768 | 1369.4976 | 1764.4902 | 2500 | 2500 | 2500 | 2500 | 2500 |  | 12500 | 16512.7647 | 878.7768 | [9 empty] | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
32 |  |  | Structure fall arrests |  |  |  | Network | Security and Compliance | Repex_OHD |  | 43.0176 | 1105.0453 | 182.138 | 7.7189 | 341.2823 | 529.4755 | 0 | 0 |  | 878.4767 | 2208.6776 | 43.0176 | [9 empty] | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
33 |  |  | Earth wires (incl. OPGW) |  |  |  | Network | Replacement - Other | Repex_OHD |  | 3075.3117 | 4950.8754 | 0 | 3802 | 3802 | 3802 | 3802 | 3802 |  | 19010 | 27036.1871 | 3075.3117 | [9 empty] | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
34 |  |  | Conductor |  |  |  | Network | Replacement - Other | Repex_OHD |  | 678.5432 | 45.8929 | 409.8104 | 0 | 0 | 0 | 0 | 0 |  | 0 | 1134.2464 | 678.5432 | [9 empty] | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35 |  |  | Insulators |  |  |  | Network | Security and Compliance | Repex_OHD |  | 1189.1556 | 5624.7899 | 638.0293 | 1134.162 | 1069.909 | 1069.909 | 1069.909 | 886.865 |  | 5230.754 | 12682.7288 | 1189.1556 | [9 empty] | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
36 |  |  | Towers |  |  |  | Network | Replacement - Other | Repex_OHD |  | 59.9269 | 1948.1516 | 0 | 23.35 | 3518.887 | 0 | 0 | 0 |  | 3542.237 | 5550.3156 | 59.9269 | [9 empty] | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
37 |  |  | Tower fall arrests |  |  |  | Network | Security and Compliance | Repex_OHD |  | 2358.21 | 6866.3098 | 5102.5949 | 4314 | 4314 | 4314 | 4314 | 4314 |  | 21570 | 35897.1147 | 2358.21 | [9 empty] | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
38 |  |  | Secondary & Protection program |  |  |  | Network | Replacement - Other | Repex_OHD |  | 14085.5614 | 18538.5375 | 12766.8144 | 20805 | 17688 | 15005 | 14280 | 15117 |  | 82895 | 128285.9132 | 14085.5614 | [9 empty] | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
39 |  |  | Comms program |  |  |  | Network | Replacement - Other | Repex_OHD |  | 8855.1719 | 4497.9635 | 13342.8803 | 8693.0078 | 11740.1138 | 13320.8849 | 12264.9512 | 7436.5035 |  | 53455.4613 | 80151.477 | 8855.1719 | [9 empty] | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
40 |  |  | Comms program - safety and security |  |  |  | Network | Security and Compliance | Repex_OHD |  | 0 | 338.5066 | 406.1676 | 1333.185 | 283.3425 | 754.8975 | 0 | 1377.5 |  | 3748.925 | 4493.5993 | 0 | [9 empty] | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
41 |  |  | Other station works |  |  |  | Network | Replacement - Other | Repex_OHD |  | 4835.9026 | 6614.1253 | 2182.8864 | [6 empty] | 0 | 13632.9143 | 4835.9026 | [9 empty] | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
42 |  |  | ERTS B1, B3 & B4 Transformer replacements |  |  | 2019 | Network | Replacement - Major Station | Repex_OHD |  | 0 | 0 | 0 | 5067.7926 | 8576.037 | 5456.9407 | 0 | 0 |  | 19100.7704 | 19100.7704 | 0 | [9 empty] | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
43 |  |  | Buildings & Property |  |  |  | Non Network | Non Network - Premises | Non_IT_OHD |  | 131.3762 | 0 | 517.7863 | 213 | 574.9 | 91.75 | 201.53 | 979.33 |  | 2060.51 | 2709.6725 | 131.3762 | [9 empty] | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
44 |  |  | Non Network - Other |  |  |  | Non Network | Non Network - Other | Non_IT_OHD |  | 2153.2519 | 1549.7952 | 2527.7625 | 2838.704 | 2838.704 | 2838.704 | 2838.704 | 2838.704 |  | 14193.5199 | 20424.3294 | 2153.2519 | [9 empty] | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
45 |  |  | IT Strategy |  |  |  | Non Network | Non Network - IT | IT_OHD | 11265.4606 | 18851.8761 | 7878.0357 | 17538.2019 | 23279.633 | 21004.214 | 12452.477 | 10346.502 | 8754.113 |  | 75836.939 | 131370.5134 | 30117.3368 | [9 empty] | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
46 |  |  | Motor Vehicles |  |  |  | Non Network | Non Network - Vehicles | Non_IT_OHD |  | 792.9599 | 670.1585 | 872.8106 | 1867.8901 | 1465.7382 | 2021.3429 | 1697.5047 | 1697.5047 |  | 8749.9806 | 11085.9096 | 792.9599 | [9 empty] | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | TOTAL | [6 empty] | 98747.8725 | 144061.6864 | 130737.2897 | 160212.3103 | 165355.3353 | 145275.3898 | 137815.7815 | 122767.5009 | 103664.9202 | 0 | 674878.9277 | 1208638.0866

## Proj_1
Go To: | Table of Contents
Master Inputs
|  | XC17 |  | Business case? | Yes
| Project name | FBTS Refurbishment
| Project category 1 | Network |  |  | Shaded cells = Inputs
| Project category 2 | Replacement - Major Station
| Regulatory classification | Prescribed
| Overhead Category | Repex_OHD |  | $000's | $000's | $000's | $000's | $000's | $000's | $000's | $000's | $000's | Project | 2017-22
|  |  |  | Prior | 2015-16 | 2016-17 | 2017-18 | 2018-19 | 2019-20 | 2020-21 | 2021-22 | 2022-23 | Total | Total | Check
| Project timing | Direct Expenditure (As incurred) - $ 2015/16 |  | 147.3242 | 172.3798 | 7921.1797 | 3437.554 | 0 | 0 | 0 | 0 | 0 | 11678.4377 | 3437.554 | ok
| (excluding real cost escalators) | Assumed year commissioned (no BC)
|  | As Commissioned Capex (Direct) - $ 2015/16 |  | 0 | 0 | 8303.3692 | 3281.641 | 93.4275 | 0 | 0 | 0 | 0 | 11678.4377 | 3375.0685 | ok
| Asset class | Secondary |  | 20.09% | 20.09% | 20.09% | 20.09% | 20.09% | 20.09% | 20.09% | 20.09% | 20.09%
|  | Switchgear |  | 62.08% | 62.08% | 62.08% | 62.08% | 62.08% | 62.08% | 62.08% | 62.08% | 62.08%
|  | Transformers |  | 0% | bar: 2015-16 to 2022-23
|  | Reactive |  | 0% | bar: 2015-16 to 2022-23
|  | Lines and towers |  | 0% | bar: 2015-16 to 2022-23
|  | Establishment |  | 15.9% | 15.9% | 15.9% | 15.9% | 15.9% | 15.9% | 15.9% | 15.9% | 15.9%
|  | Communications |  | 1.934% | 1.934% | 1.934% | 1.934% | 1.934% | 1.934% | 1.934% | 1.934% | 1.934%
Non System
Land
Easements
|  |  | Total | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
| Input costs % | Labour - internal |  | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10%
|  | Labour - external |  | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50%
|  | Materials |  | 40% | 40% | 40% | 40% | 40% | 40% | 40% | 40% | 40%
|  |  | Total | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
Material Escalation
| (By Asset Class) | Secondary |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Switchgear |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Transformers |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Reactive |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Lines and towers |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Establishment |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Communications |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Non System |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Land |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Easements |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Total Material escalation |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Labour Escalation | Internal Labour |  | 0 | 0 | 9.9124 | 7.1035 | 0 | 0 | 0 | 0 | 0 | 17.0159 | 7.1035
|  | External Labour |  | 0 | 0 | 42.5849 | 36.5046 | 0 | 0 | 0 | 0 | 0 | 79.0895 | 36.5046
|  | Total Labour Escalation |  | 0 | 0 | 52.4973 | 43.6082 | 0 | 0 | 0 | 0 | 0 | 96.1054 | 43.6082
|  | Total Escalation |  | 0 | 0 | 52.4973 | 43.6082 | 0 | 0 | 0 | 0 | 0 | 96.1054 | 43.6082
|  | Escalation factors |  | 0 | 0 | 0.0066275 | 0.012686 | 0 | 0 | 0 | 0 | 0 | 0.0082293 | 0.012686
| Direct Expenditure (Escalated) | Total labour - internal |  | 14.9817 | 17.5296 | 815.5985 | 356.7945 | 0 | 0 | 0 | 0 | 0 | 1204.9043 | 356.7945
| (as incurred) | Total labour - external |  | 74.9083 | 87.648 | 4070.8977 | 1784.9762 | 0 | 0 | 0 | 0 | 0 | 6018.4301 | 1784.9762
|  | Total materials |  | 59.9266 | 70.1184 | 3222.0739 | 1398.2832 | 0 | 0 | 0 | 0 | 0 | 4750.4021 | 1398.2832
|  | Total Direct - As Incurred $ Mar 2017 |  | 149.8165 | 175.2959 | 8108.5701 | 3540.054 | 0 | 0 | 0 | 0 | 0 | 11973.7365 | 3540.054 | ok
| Capitalised Overheads | Overhead rate (applied to direct expenditure) |  | 8.008% | 8.425% | 7.259% | 7.658% | 9.013% | 8.969% | 7.948% | 8.001% | 8.318%
|  | Total overhead (as incurred) |  | 11.9976 | 14.769 | 588.631 | 271.0918 | 0 | 0 | 0 | 0 | 0 | 886.4894 | 271.0918
|  | Total incl Overhead - As Incurred $ Mar 2017 |  | 161.8141 | 190.065 | 8697.2011 | 3811.1458 | 0 | 0 | 0 | 0 | 0 | 12860.2259 | 3811.1458
|  | Total overheads (As incurred) - Cumulative |  | 11.9976 | 26.7666 | 615.3976 | 886.4894 | 886.4894 | 886.4894 | 886.4894 | 886.4894 | 886.4894
|  | Labour & Material Escalation - Cumulative |  | 0 | 0 | 52.4973 | 96.1054 | 96.1054 | 96.1054 | 96.1054 | 96.1054 | 96.1054
Expenditure By Asset Class - As Incurred
| Asset class breakdown | Secondary |  | 32.5084 | 38.184 | 1747.2645 | 765.6578 | 0 | 0 | 0 | 0 | 0 | 2583.6147 | 765.6578
| (fully absorbed) | Switchgear |  | 100.4505 | 117.988 | 5399.0256 | 2365.8731 | 0 | 0 | 0 | 0 | 0 | 7983.3373 | 2365.8731
| (as incurred) | Transformers |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Reactive |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Lines and towers |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Establishment |  | 25.7262 | 30.2177 | 1382.733 | 605.9187 | 0 | 0 | 0 | 0 | 0 | 2044.5956 | 605.9187
|  | Communications |  | 3.129 | 3.6753 | 168.1779 | 73.6962 | 0 | 0 | 0 | 0 | 0 | 248.6784 | 73.6962
|  | Non System |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Land |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Easements |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Total incl Overhead - As Incurred $ Mar 2017 |  | 161.8141 | 190.065 | 8697.2011 | 3811.1458 | 0 | 0 | 0 | 0 | 0 | 12860.2259 | 3811.1458
|  |  | Check | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| As Commissioned Capex | Direct Expenditure (As Commissioned) - $ 2015/16 |  | 0 | 0 | 8303.3692 | 3281.641 | 93.4275 | 0 | 0 | 0 | 0 | 11678.4377 | 3375.0685
|  | Labour & Material Escalation - $ 2015/16 |  | 0 | 0 | 52.4973 | 42.8393 | 0.76884 | 0 | 0 | 0 | 0 | 96.1054 | 43.6082
|  | Total Direct Expenditure - $ 2015/16 |  | 0 | 0 | 8355.8665 | 3324.4803 | 94.1963 | 0 | 0 | 0 | 0 | 11774.5431 | 3418.6766
|  | Total Direct Expenditure - $ Mar 2017 |  | 0 | 0 | 8497.2251 | 3380.7215 | 95.7899 | 0 | 0 | 0 | 0 | 11973.7365 | 3476.5114
|  | Total overheads (As Commissioned) |  | 0 | 0 | 620.0342 | 259.3633 | 7.0919 | 0 | 0 | 0 | 0 | 886.4894 | 266.4552
|  | Total incl Overhead - As commissioned $ Mar 2017 |  | 0 | 0 | 9117.2593 | 3640.0848 | 102.8818 | 0 | 0 | 0 | 0 | 12860.2259 | 3742.9666
|  | Total overheads (As Comm) - Cumulative |  | 0 | 0 | 620.0342 | 879.3975 | 886.4894 | 886.4894 | 886.4894 | 886.4894 | 886.4894
|  | Total real cost escalation (As Comm) - Cumulative |  | 0 | 0 | 52.4973 | 95.3366 | 96.1054 | 96.1054 | 96.1054 | 96.1054 | 96.1054
Expenditure By Asset Class - As Commissioned
| Asset class breakdown | Secondary |  | 0 | 0 | 1831.6541 | 731.2917 | 20.6689 | 0 | 0 | 0 | 0 | 2583.6147 | 751.9606
| (fully absorbed) | Switchgear |  | 0 | 0 | 5659.7883 | 2259.6823 | 63.8667 | 0 | 0 | 0 | 0 | 7983.3373 | 2323.549
| (as commissioned) | Transformers |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Reactive |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Lines and towers |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Establishment |  | 0 | 0 | 1449.5164 | 578.7224 | 16.3568 | 0 | 0 | 0 | 0 | 2044.5956 | 595.0792
|  | Communications |  | 0 | 0 | 176.3006 | 70.3884 | 1.9894 | 0 | 0 | 0 | 0 | 248.6784 | 72.3778
|  | Non System |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Land |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Easements |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Total incl Overhead - As commissioned $ Mar 2017 |  | 0 | 0 | 9117.2593 | 3640.0848 | 102.8818 | 0 | 0 | 0 | 0 | 12860.2259 | 3742.9666
|  |  | Check | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0
| Expenditure splits for RIN |  |  |  | 2015-16 | 2016-17 | 2017-18 | 2018-19 | 2019-20 | 2020-21 | 2021-22 | 2022-23
| Repex Category | Transmission Towers | bar: 2015-16 to 2022-23
Transmission Tower Support Structures | bar: 2015-16 to 2022-23
Conductors | bar: 2015-16 to 2022-23
Transmission Cables | bar: 2015-16 to 2022-23
|  | Substation Switchbays |  |  | 62.08% | 62.08% | 62.08% | 62.08% | 62.08% | 62.08% | 62.08% | 62.08%
Substation Power Transformers | bar: 2015-16 to 2022-23
Substation Reactive Plant | bar: 2015-16 to 2022-23
|  | Scada Network Control And Protection Systems |  |  | 22.02% | 22.02% | 22.02% | 22.02% | 22.02% | 22.02% | 22.02% | 22.02%
|  | Other |  |  | 15.9% | 15.9% | 15.9% | 15.9% | 15.9% | 15.9% | 15.9% | 15.9%
|  | Total |  |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
| Direct Expenditures | Materials - $ Mar 2017 |  |  | 2015-16 | 2016-17 | 2017-18 | 2018-19 | 2019-20 | 2020-21 | 2021-22 | 2022-23 | Total | 2017-22 Total
| (As Incurred) | Transmission Towers |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Transmission Tower Support Structures |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Conductors |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Transmission Cables |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Substation Switchbays |  |  | 43.5279 | 2000.1905 | 868.0226 | 0 | 0 | 0 | 0 | 0 | 2911.7411 | 868.0226
|  | Substation Power Transformers |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Substation Reactive Plant |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Scada Network Control And Protection Systems |  |  | 15.4426 | 709.6188 | 307.9532 | 0 | 0 | 0 | 0 | 0 | 1033.0146 | 307.9532
|  | Other |  |  | 11.1478 | 512.2646 | 222.3074 | 0 | 0 | 0 | 0 | 0 | 745.7198 | 222.3074
|  | Total Materials |  |  | 70.1184 | 3222.0739 | 1398.2832 | 0 | 0 | 0 | 0 | 0 | 4690.4755 | 1398.2832
|  | Labour (Internal) - $ Mar 2017 |  |  | 2015-16 | 2016-17 | 2017-18 | 2018-19 | 2019-20 | 2020-21 | 2021-22 | 2022-23 | Total | 2017-22 Total
|  | Transmission Towers |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Transmission Tower Support Structures |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Conductors |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Transmission Cables |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Substation Switchbays |  |  | 10.882 | 506.3051 | 221.49 | 0 | 0 | 0 | 0 | 0 | 738.6771 | 221.49
|  | Substation Power Transformers |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Substation Reactive Plant |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Scada Network Control And Protection Systems |  |  | 3.8607 | 179.6247 | 78.5792 | 0 | 0 | 0 | 0 | 0 | 262.0646 | 78.5792
|  | Other |  |  | 2.787 | 129.6687 | 56.7253 | 0 | 0 | 0 | 0 | 0 | 189.181 | 56.7253
|  | Total Internal Labour |  |  | 17.5296 | 815.5985 | 356.7945 | 0 | 0 | 0 | 0 | 0 | 1189.9227 | 356.7945
|  | Labour (External) - $ Mar 2017 |  |  | 2015-16 | 2016-17 | 2017-18 | 2018-19 | 2019-20 | 2020-21 | 2021-22 | 2022-23 | Total | 2017-22 Total
|  | Transmission Towers |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Transmission Tower Support Structures |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Conductors |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Transmission Cables |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Substation Switchbays |  |  | 54.4099 | 2527.1212 | 1108.0729 | 0 | 0 | 0 | 0 | 0 | 3689.6039 | 1108.0729
|  | Substation Power Transformers |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Substation Reactive Plant |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Scada Network Control And Protection Systems |  |  | 19.3033 | 896.5609 | 393.1172 | 0 | 0 | 0 | 0 | 0 | 1308.9813 | 393.1172
|  | Other |  |  | 13.9348 | 647.2156 | 283.7862 | 0 | 0 | 0 | 0 | 0 | 944.9366 | 283.7862
|  | Total External Labour |  |  | 87.648 | 4070.8977 | 1784.9762 | 0 | 0 | 0 | 0 | 0 | 5943.5219 | 1784.9762
|  | Total Direct - $ Mar 2017 |  |  | 2015-16 | 2016-17 | 2017-18 | 2018-19 | 2019-20 | 2020-21 | 2021-22 | 2022-23 | Total | 2017-22 Total
|  | Transmission Towers |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Transmission Tower Support Structures |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Conductors |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Transmission Cables |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Substation Switchbays |  |  | 108.8198 | 5033.6168 | 2197.5854 | 0 | 0 | 0 | 0 | 0 | 7340.022 | 2197.5854
|  | Substation Power Transformers |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Substation Reactive Plant |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Scada Network Control And Protection Systems |  |  | 38.6066 | 1785.8043 | 779.6496 | 0 | 0 | 0 | 0 | 0 | 2604.0605 | 779.6496
|  | Other |  |  | 27.8696 | 1289.1489 | 562.8189 | 0 | 0 | 0 | 0 | 0 | 1879.8375 | 562.8189
|  | Total Direct - $ Mar 2017 |  |  | 175.2959 | 8108.5701 | 3540.054 | 0 | 0 | 0 | 0 | 0 | 11823.92 | 3540.054

## Proj_2
Go To: | Table of Contents
Master Inputs
|  | XC28 |  | Business case? | Yes
| Project name | HWPS 220kV Switchyard Redevelopment Stage 4
| Project category 1 | Network |  |  | Shaded cells = Inputs
| Project category 2 | Replacement - Major Station
| Regulatory classification | Prescribed
| Overhead Category | Repex_OHD |  | $000's | $000's | $000's | $000's | $000's | $000's | $000's | $000's | $000's | Project | 2017-22
|  |  |  | Prior | 2015-16 | 2016-17 | 2017-18 | 2018-19 | 2019-20 | 2020-21 | 2021-22 | 2022-23 | Total | Total | Check
| Project timing | Direct Expenditure (As incurred) - $ 2015/16 |  | 54.5534 | 2960.7521 | 7604.2597 | 7713.246 | 3649.602 | 0 | 0 | 0 | 0 | 21982.4132 | 11362.848 | ok
| (excluding real cost escalators) | Assumed year commissioned (no BC)
|  | Direct Expenditure (As Commissioned) - $ 2015/16 |  | 0 | 0 | 8898.4809 | 9100.7191 | 3983.2133 | 0 | 0 | 0 | 0 | 21982.4132 | 13083.9323 | ok
| Asset class | Secondary |  | 5.578% | 5.578% | 5.578% | 5.578% | 5.578% | 5.578% | 5.578% | 5.578% | 5.578%
|  | Switchgear |  | 64.39% | 64.39% | 64.39% | 64.39% | 64.39% | 64.39% | 64.39% | 64.39% | 64.39%
Transformers
Reactive
Lines and towers
|  | Establishment |  | 30.03% | 30.03% | 30.03% | 30.03% | 30.03% | 30.03% | 30.03% | 30.03% | 30.03%
Communications
Non System
Land
Easements
|  |  | Total | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
| Input costs % | Labour - internal |  | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10%
|  | Labour - external |  | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50%
|  | Materials |  | 40% | 40% | 40% | 40% | 40% | 40% | 40% | 40% | 40%
|  |  | Total | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
Material Escalation
| (By Asset Class) | Secondary |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Switchgear |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Transformers |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Reactive |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Lines and towers |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Establishment |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Communications |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Non System |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Land |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Easements |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Total Material escalation |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Labour Escalation | Internal Labour |  | 0 | 0 | 9.5158 | 15.939 | 10.559 | 0 | 0 | 0 | 0 | 36.0138 | 26.498
|  | External Labour |  | 0 | 0 | 40.8811 | 81.9097 | 58.184 | 0 | 0 | 0 | 0 | 180.9749 | 140.0937
|  | Total Labour Escalation |  | 0 | 0 | 50.3969 | 97.8488 | 68.743 | 0 | 0 | 0 | 0 | 216.9887 | 166.5918
|  | Total Escalation |  | 0 | 0 | 50.3969 | 97.8488 | 68.743 | 0 | 0 | 0 | 0 | 216.9887 | 166.5918
|  | Escalation factors |  | 0 | 0 | 0.0066275 | 0.012686 | 0.018836 | 0 | 0 | 0 | 0 | 0.009871 | 0.014661
| Direct Expenditure (Escalated) | Total labour - internal |  | 5.5476 | 301.084 | 782.9671 | 800.582 | 381.872 | 0 | 0 | 0 | 0 | 2272.0527 | 1182.454
| (as incurred) | Total labour - external |  | 27.7381 | 1505.42 | 3908.0243 | 4005.162 | 1914.84 | 0 | 0 | 0 | 0 | 11361.1845 | 5920.0021
|  | Total materials |  | 22.1905 | 1204.336 | 3093.1613 | 3137.4933 | 1484.5374 | 0 | 0 | 0 | 0 | 8941.7185 | 4622.0307
|  | Total Direct - As Incurred $ Mar 2017 |  | 55.4763 | 3010.8401 | 7784.1527 | 7943.2373 | 3781.2493 | 0 | 0 | 0 | 0 | 22574.9557 | 11724.4867 | ok
| Capitalised Overheads | Overhead rate (applied to direct expenditure) |  | 8.008% | 8.425% | 7.259% | 7.658% | 9.013% | 8.969% | 7.948% | 8.001% | 8.318%
|  | Total overhead (as incurred) |  | 4.4426 | 253.6688 | 565.0803 | 608.2808 | 340.8158 | 0 | 0 | 0 | 0 | 1772.2883 | 949.0965
|  | Total incl Overhead - As Incurred $ Mar 2017 |  | 59.9189 | 3264.5089 | 8349.233 | 8551.5181 | 4122.0651 | 0 | 0 | 0 | 0 | 24347.244 | 12673.5832
|  | Total overheads (As incurred) - Cumulative |  | 4.4426 | 258.1114 | 823.1918 | 1431.4725 | 1772.2883 | 1772.2883 | 1772.2883 | 1772.2883 | 1772.2883
|  | Labour & Material Escalation - Cumulative |  | 0 | 0 | 50.3969 | 148.2457 | 216.9887 | 216.9887 | 216.9887 | 216.9887 | 216.9887
Expenditure By Asset Class - As Incurred
| Asset class breakdown | Secondary |  | 3.3421 | 182.084 | 465.6938 | 476.9766 | 229.9157 | 0 | 0 | 0 | 0 | 1358.0121 | 706.8923
| (fully absorbed) | Switchgear |  | 38.5831 | 2102.09 | 5376.2572 | 5506.5131 | 2654.2896 | 0 | 0 | 0 | 0 | 15677.7331 | 8160.8027
| (as incurred) | Transformers |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Reactive |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Lines and towers |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Establishment |  | 17.9937 | 980.3349 | 2507.282 | 2568.0284 | 1237.8598 | 0 | 0 | 0 | 0 | 7311.4988 | 3805.8882
|  | Communications |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Non System |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Land |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Easements |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Total incl Overhead - As Incurred $ Mar 2017 |  | 59.9189 | 3264.5089 | 8349.233 | 8551.5181 | 4122.0651 | 0 | 0 | 0 | 0 | 24347.244 | 12673.5832
|  |  | Check | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| As Commissioned Capex | Direct Expenditure (As Commissioned) - $ 2015/16 |  | 0 | 0 | 8898.4809 | 9100.7191 | 3983.2133 | 0 | 0 | 0 | 0 | 21982.4132 | 13083.9323
|  | Labour & Material Escalation - $ 2015/16 |  | 0 | 0 | 50.3969 | 95.1511 | 71.4407 | 0 | 0 | 0 | 0 | 216.9887 | 166.5918
|  | Total Direct Expenditure - $ 2015/16 |  | 0 | 0 | 8948.8778 | 9195.8701 | 4054.654 | 0 | 0 | 0 | 0 | 22199.4019 | 13250.5241
|  | Total Direct Expenditure - $ Mar 2017 |  | 0 | 0 | 9100.2686 | 9351.4394 | 4123.2477 | 0 | 0 | 0 | 0 | 22574.9557 | 13474.6871
|  | Total overheads (As Commissioned) |  | 0 | 0 | 690.4095 | 715.0139 | 366.865 | 0 | 0 | 0 | 0 | 1772.2883 | 1081.8789
|  | Total incl Overhead - As commissioned $ Mar 2017 |  | 0 | 0 | 9790.678 | 10066.4532 | 4490.1127 | 0 | 0 | 0 | 0 | 24347.244 | 14556.566
|  | Total overheads (As Comm) - Cumulative |  | 0 | 0 | 690.4095 | 1405.4233 | 1772.2883 | 1772.2883 | 1772.2883 | 1772.2883 | 1772.2883
|  | Total real cost escalation (As Comm) - Cumulative |  | 0 | 0 | 50.3969 | 145.548 | 216.9887 | 216.9887 | 216.9887 | 216.9887 | 216.9887
Expenditure By Asset Class - As Commissioned
| Asset class breakdown | Secondary |  | 0 | 0 | 546.093 | 561.4749 | 250.4443 | 0 | 0 | 0 | 0 | 1358.0121 | 811.9191
| (fully absorbed) | Switchgear |  | 0 | 0 | 6304.4358 | 6482.0136 | 2891.2837 | 0 | 0 | 0 | 0 | 15677.7331 | 9373.2973
| (as commissioned) | Transformers |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Reactive |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Lines and towers |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Establishment |  | 0 | 0 | 2940.1492 | 3022.9648 | 1348.3848 | 0 | 0 | 0 | 0 | 7311.4988 | 4371.3496
|  | Communications |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Non System |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Land |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Easements |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Total incl Overhead - As commissioned $ Mar 2017 |  | 0 | 0 | 9790.678 | 10066.4532 | 4490.1127 | 0 | 0 | 0 | 0 | 24347.244 | 14556.566
|  |  | Check | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0
| Expenditure splits for RIN |  |  |  | 2015-16 | 2016-17 | 2017-18 | 2018-19 | 2019-20 | 2020-21 | 2021-22 | 2022-23
| Repex Category | Transmission Towers | bar: 2015-16 to 2022-23
Transmission Tower Support Structures | bar: 2015-16 to 2022-23
Conductors | bar: 2015-16 to 2022-23
Transmission Cables | bar: 2015-16 to 2022-23
|  | Substation Switchbays |  |  | 64.39% | 64.39% | 64.39% | 64.39% | 64.39% | 64.39% | 64.39% | 64.39%
Substation Power Transformers | bar: 2015-16 to 2022-23
Substation Reactive Plant | bar: 2015-16 to 2022-23
|  | Scada Network Control And Protection Systems |  |  | 5.578% | 5.578% | 5.578% | 5.578% | 5.578% | 5.578% | 5.578% | 5.578%
|  | Other |  |  | 30.03% | 30.03% | 30.03% | 30.03% | 30.03% | 30.03% | 30.03% | 30.03%
|  | Total |  |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
| Direct Expenditures | Materials - $ Mar 2017 |  |  | 2015-16 | 2016-17 | 2017-18 | 2018-19 | 2019-20 | 2020-21 | 2021-22 | 2022-23 | Total | 2017-22 Total
| (As Incurred) | Transmission Towers |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Transmission Tower Support Structures |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Conductors |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Transmission Cables |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Substation Switchbays |  |  | 775.4988 | 1991.7555 | 2020.3019 | 955.9267 | 0 | 0 | 0 | 0 | 5743.4829 | 2976.2286
|  | Substation Power Transformers |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Substation Reactive Plant |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Scada Network Control And Protection Systems |  |  | 67.174 | 172.5267 | 174.9994 | 82.8028 | 0 | 0 | 0 | 0 | 497.503 | 257.8022
|  | Other |  |  | 361.6632 | 928.8791 | 942.192 | 445.8079 | 0 | 0 | 0 | 0 | 2678.5421 | 1387.9999
|  | Total Materials |  |  | 1204.336 | 3093.1613 | 3137.4933 | 1484.5374 | 0 | 0 | 0 | 0 | 8919.5279 | 4622.0307
|  | Labour (Internal) - $ Mar 2017 |  |  | 2015-16 | 2016-17 | 2017-18 | 2018-19 | 2019-20 | 2020-21 | 2021-22 | 2022-23 | Total | 2017-22 Total
|  | Transmission Towers |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Transmission Tower Support Structures |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Conductors |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Transmission Cables |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Substation Switchbays |  |  | 193.8747 | 504.17 | 515.5126 | 245.8959 | 0 | 0 | 0 | 0 | 1459.4531 | 761.4085
|  | Substation Power Transformers |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Substation Reactive Plant |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Scada Network Control And Protection Systems |  |  | 16.7935 | 43.6714 | 44.6539 | 21.2996 | 0 | 0 | 0 | 0 | 126.4185 | 65.9535
|  | Other |  |  | 90.4158 | 235.1257 | 240.4155 | 114.6765 | 0 | 0 | 0 | 0 | 680.6335 | 355.092
|  | Total Internal Labour |  |  | 301.084 | 782.9671 | 800.582 | 381.872 | 0 | 0 | 0 | 0 | 2266.5051 | 1182.454
|  | Labour (External) - $ Mar 2017 |  |  | 2015-16 | 2016-17 | 2017-18 | 2018-19 | 2019-20 | 2020-21 | 2021-22 | 2022-23 | Total | 2017-22 Total
|  | Transmission Towers |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Transmission Tower Support Structures |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Conductors |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Transmission Cables |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Substation Switchbays |  |  | 969.3735 | 2516.464 | 2579.0131 | 1233.0082 | 0 | 0 | 0 | 0 | 7297.8588 | 3812.0213
|  | Substation Power Transformers |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Substation Reactive Plant |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Scada Network Control And Protection Systems |  |  | 83.9676 | 217.9772 | 223.3952 | 106.8037 | 0 | 0 | 0 | 0 | 632.1437 | 330.1989
|  | Other |  |  | 452.079 | 1173.5831 | 1202.7537 | 575.0281 | 0 | 0 | 0 | 0 | 3403.4439 | 1777.7818
|  | Total External Labour |  |  | 1505.42 | 3908.0243 | 4005.162 | 1914.84 | 0 | 0 | 0 | 0 | 11333.4464 | 5920.0021
|  | Total Direct - $ Mar 2017 |  |  | 2015-16 | 2016-17 | 2017-18 | 2018-19 | 2019-20 | 2020-21 | 2021-22 | 2022-23 | Total | 2017-22 Total
|  | Transmission Towers |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Transmission Tower Support Structures |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Conductors |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Transmission Cables |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Substation Switchbays |  |  | 1938.747 | 5012.3894 | 5114.8276 | 2434.8307 | 0 | 0 | 0 | 0 | 14500.7948 | 7549.6583
|  | Substation Power Transformers |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Substation Reactive Plant |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Scada Network Control And Protection Systems |  |  | 167.9351 | 434.1754 | 443.0486 | 210.9061 | 0 | 0 | 0 | 0 | 1256.0652 | 653.9547
|  | Other |  |  | 904.1579 | 2337.5879 | 2385.3612 | 1135.5125 | 0 | 0 | 0 | 0 | 6762.6195 | 3520.8737
|  | Total Direct - $ Mar 2017 |  |  | 3010.8401 | 7784.1527 | 7943.2373 | 3781.2493 | 0 | 0 | 0 | 0 | 22519.4794 | 11724.4867

## Proj_3
Go To: | Table of Contents
Master Inputs
|  | XA09 |  | Business case? | Yes
| Project name | RTS Redevelopment Project
| Project category 1 | Network |  |  | Shaded cells = Inputs
| Project category 2 | Replacement - Major Station CBD
| Regulatory classification | Prescribed
| Overhead Category | Repex_OHD |  | $000's | $000's | $000's | $000's | $000's | $000's | $000's | $000's | $000's | Project | 2017-22
|  |  |  | Prior | 2015-16 | 2016-17 | 2017-18 | 2018-19 | 2019-20 | 2020-21 | 2021-22 | 2022-23 | Total | Total | Check
| Project timing | Direct Expenditure (As incurred) - $ 2015/16 |  | 89824.767 | 29819.1972 | 22138.7516 | 11436.882 | 1094.058 | 0 | 0 | 0 | 0 | 154313.6557 | 12530.94 | ok
| (excluding real cost escalators) | Assumed year commissioned (no BC)
|  | Direct Expenditure (As Commissioned) - $ 2015/16 |  | 43410.4116 | 31585.5749 | 37035.2774 | 30862.7311 | 11419.6607 | 0 | 0 | 0 | 0 | 154313.6557 | 42282.3919 | ok
| Asset class | Secondary |  | 6.349% | 6.349% | 6.349% | 6.349% | 6.349% | 6.349% | 6.349% | 6.349% | 6.349%
|  | Switchgear |  | 43.22% | 43.22% | 43.22% | 43.22% | 43.22% | 43.22% | 43.22% | 43.22% | 43.22%
|  | Transformers |  | 34.11% | 34.11% | 34.11% | 34.11% | 34.11% | 34.11% | 34.11% | 34.11% | 34.11%
|  | Reactive |  | 0% | bar: 2015-16 to 2022-23
|  | Lines and towers |  | 9.917% | 9.917% | 9.917% | 9.917% | 9.917% | 9.917% | 9.917% | 9.917% | 9.917%
|  | Establishment |  | 6.403% | 6.403% | 6.403% | 6.403% | 6.403% | 6.403% | 6.403% | 6.403% | 6.403%
Communications
Non System
Land
Easements
|  |  | Total | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
| Input costs % | Labour - internal |  | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10%
|  | Labour - external |  | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50%
|  | Materials |  | 40% | 40% | 40% | 40% | 40% | 40% | 40% | 40% | 40%
|  |  | Total | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
Material Escalation
| (By Asset Class) | Secondary |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Switchgear |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Transformers |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Reactive |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Lines and towers |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Establishment |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Communications |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Non System |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Land |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Easements |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Total Material escalation |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Labour Escalation | Internal Labour |  | 0 | 0 | 27.7039 | 23.6338 | 3.1653 | 0 | 0 | 0 | 0 | 54.503 | 26.7991
|  | External Labour |  | 0 | 0 | 119.0197 | 121.4523 | 17.4421 | 0 | 0 | 0 | 0 | 257.9142 | 138.8944
|  | Total Labour Escalation |  | 0 | 0 | 146.7237 | 145.0861 | 20.6074 | 0 | 0 | 0 | 0 | 312.4172 | 165.6935
|  | Total Escalation |  | 0 | 0 | 146.7237 | 145.0861 | 20.6074 | 0 | 0 | 0 | 0 | 312.4172 | 165.6935
|  | Escalation factors |  | 0 | 0 | 0.0066275 | 0.012686 | 0.018836 | 0 | 0 | 0 | 0 | 0.0020246 | 0.013223
| Direct Expenditure (Escalated) | Total labour - internal |  | 9134.4359 | 3032.3657 | 2279.5005 | 1187.0699 | 114.4755 | 0 | 0 | 0 | 0 | 15747.8476 | 1301.5454
| (as incurred) | Total labour - external |  | 45672.1794 | 15161.8286 | 11377.6729 | 5938.6885 | 574.0204 | 0 | 0 | 0 | 0 | 78724.3899 | 6512.7089
|  | Total materials |  | 36537.7436 | 12129.4629 | 9005.3117 | 4652.1452 | 445.0266 | 0 | 0 | 0 | 0 | 62769.69 | 5097.1718
|  | Total Direct - As Incurred $ Mar 2017 |  | 91344.3589 | 30323.6573 | 22662.4851 | 11777.9037 | 1133.5225 | 0 | 0 | 0 | 0 | 157241.9275 | 12911.4262 | ok
| Capitalised Overheads | Overhead rate (applied to direct expenditure) |  | 8.008% | 8.425% | 7.259% | 7.658% | 9.013% | 8.969% | 7.948% | 8.001% | 8.318%
|  | Total overhead (as incurred) |  | 7315.0133 | 2554.8239 | 1645.1533 | 901.9335 | 102.1679 | 0 | 0 | 0 | 0 | 12519.092 | 1004.1015
|  | Total incl Overhead - As Incurred $ Mar 2017 |  | 98659.3722 | 32878.4812 | 24307.6385 | 12679.8372 | 1235.6904 | 0 | 0 | 0 | 0 | 169761.0194 | 13915.5276
|  | Total overheads (As incurred) - Cumulative |  | 7315.0133 | 9869.8372 | 11514.9905 | 12416.924 | 12519.092 | 12519.092 | 12519.092 | 12519.092 | 12519.092
|  | Labour & Material Escalation - Cumulative |  | 0 | 0 | 146.7237 | 291.8098 | 312.4172 | 312.4172 | 312.4172 | 312.4172 | 312.4172
Expenditure By Asset Class - As Incurred
| Asset class breakdown | Secondary |  | 6264.3212 | 2087.6006 | 1543.3998 | 805.0991 | 78.4595 | 0 | 0 | 0 | 0 | 10778.8802 | 883.5586
| (fully absorbed) | Switchgear |  | 42644.5556 | 14211.4042 | 10506.7407 | 5480.7365 | 534.1152 | 0 | 0 | 0 | 0 | 73377.5523 | 6014.8517
| (as incurred) | Transformers |  | 33649.5181 | 11213.7856 | 8290.5486 | 4324.682 | 421.454 | 0 | 0 | 0 | 0 | 57899.9884 | 4746.136
|  | Reactive |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Lines and towers |  | 9783.9678 | 3260.5316 | 2410.5683 | 1257.4489 | 122.5424 | 0 | 0 | 0 | 0 | 16835.0589 | 1379.9913
|  | Establishment |  | 6317.0094 | 2105.1591 | 1556.3811 | 811.8707 | 79.1194 | 0 | 0 | 0 | 0 | 10869.5397 | 890.9901
|  | Communications |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Non System |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Land |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Easements |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Total incl Overhead - As Incurred $ Mar 2017 |  | 98659.3722 | 32878.4812 | 24307.6385 | 12679.8372 | 1235.6904 | 0 | 0 | 0 | 0 | 169761.0194 | 13915.5276
|  |  | Check | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| As Commissioned Capex | Direct Expenditure (As Commissioned) - $ 2015/16 |  | 43410.4116 | 31585.5749 | 37035.2774 | 30862.7311 | 11419.6607 | 0 | 0 | 0 | 0 | 154313.6557 | 42282.3919
|  | Labour & Material Escalation - $ 2015/16 |  | 0 | 0 | 115.9354 | 156.209 | 40.2727 | 0 | 0 | 0 | 0 | 312.4172 | 196.4818
|  | Total Direct Expenditure - $ 2015/16 |  | 43410.4116 | 31585.5749 | 37151.2128 | 31018.9402 | 11459.9334 | 0 | 0 | 0 | 0 | 154626.0729 | 42478.8736
|  | Total Direct Expenditure - $ Mar 2017 |  | 44144.7982 | 32119.9173 | 37779.7107 | 31543.6967 | 11653.8045 | 0 | 0 | 0 | 0 | 157241.9275 | 43197.5012
|  | Total overheads (As Commissioned) |  | 3535.1913 | 2651.4824 | 2912.0301 | 2481.4328 | 938.9553 | 0 | 0 | 0 | 0 | 12519.092 | 3420.3881
|  | Total incl Overhead - As commissioned $ Mar 2017 |  | 47679.9896 | 34771.3998 | 40691.7408 | 34025.1295 | 12592.7598 | 0 | 0 | 0 | 0 | 169761.0194 | 46617.8893
|  | Total overheads (As Comm) - Cumulative |  | 3535.1913 | 6186.6738 | 9098.7038 | 11580.1367 | 12519.092 | 12519.092 | 12519.092 | 12519.092 | 12519.092
|  | Total real cost escalation (As Comm) - Cumulative |  | 0 | 0 | 115.9354 | 272.1445 | 312.4172 | 312.4172 | 312.4172 | 312.4172 | 312.4172
Expenditure By Asset Class - As Commissioned
| Asset class breakdown | Secondary |  | 3027.414 | 2207.7904 | 2583.6991 | 2160.4064 | 799.5702 | 0 | 0 | 0 | 0 | 10778.8802 | 2959.9766
| (fully absorbed) | Switchgear |  | 20609.2125 | 15029.5999 | 17588.6098 | 14707.0319 | 5443.0981 | 0 | 0 | 0 | 0 | 73377.5523 | 20150.13
| (as commissioned) | Transformers |  | 16262.101 | 11859.3989 | 13878.6356 | 11604.8703 | 4294.9827 | 0 | 0 | 0 | 0 | 57899.9884 | 15899.853
|  | Reactive |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Lines and towers |  | 4728.3848 | 3448.2507 | 4035.366 | 3374.2438 | 1248.8135 | 0 | 0 | 0 | 0 | 16835.0589 | 4623.0572
|  | Establishment |  | 3052.8772 | 2226.3598 | 2605.4302 | 2178.5773 | 806.2952 | 0 | 0 | 0 | 0 | 10869.5397 | 2984.8725
|  | Communications |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Non System |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Land |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Easements |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Total incl Overhead - As commissioned $ Mar 2017 |  | 47679.9896 | 34771.3998 | 40691.7408 | 34025.1295 | 12592.7598 | 0 | 0 | 0 | 0 | 169761.0194 | 46617.8893
|  |  | Check | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0
| Expenditure splits for RIN |  |  |  | 2015-16 | 2016-17 | 2017-18 | 2018-19 | 2019-20 | 2020-21 | 2021-22 | 2022-23
| Repex Category | Transmission Towers |  |  | 4.958% | 4.958% | 4.958% | 4.958% | 4.958% | 4.958% | 4.958% | 4.958%
Transmission Tower Support Structures | bar: 2015-16 to 2022-23
|  | Conductors |  |  | 4.958% | 4.958% | 4.958% | 4.958% | 4.958% | 4.958% | 4.958% | 4.958%
Transmission Cables | bar: 2015-16 to 2022-23
|  | Substation Switchbays |  |  | 43.22% | 43.22% | 43.22% | 43.22% | 43.22% | 43.22% | 43.22% | 43.22%
|  | Substation Power Transformers |  |  | 34.11% | 34.11% | 34.11% | 34.11% | 34.11% | 34.11% | 34.11% | 34.11%
Substation Reactive Plant | bar: 2015-16 to 2022-23
|  | Scada Network Control And Protection Systems |  |  | 6.349% | 6.349% | 6.349% | 6.349% | 6.349% | 6.349% | 6.349% | 6.349%
|  | Other |  |  | 6.403% | 6.403% | 6.403% | 6.403% | 6.403% | 6.403% | 6.403% | 6.403%
|  | Total |  |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
| Direct Expenditures | Materials - $ Mar 2017 |  |  | 2015-16 | 2016-17 | 2017-18 | 2018-19 | 2019-20 | 2020-21 | 2021-22 | 2022-23 | Total | 2017-22 Total
| (As Incurred) | Transmission Towers |  |  | 601.4344 | 446.5246 | 230.6747 | 22.0665 | 0 | 0 | 0 | 0 | 1300.7001 | 252.7411
|  | Transmission Tower Support Structures |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Conductors |  |  | 601.4344 | 446.5246 | 230.6747 | 22.0665 | 0 | 0 | 0 | 0 | 1300.7001 | 252.7411
|  | Transmission Cables |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Substation Switchbays |  |  | 5242.8426 | 3892.4586 | 2010.8446 | 192.3584 | 0 | 0 | 0 | 0 | 11338.5041 | 2203.203
|  | Substation Power Transformers |  |  | 4136.9672 | 3071.4203 | 1586.6961 | 151.7842 | 0 | 0 | 0 | 0 | 8946.8678 | 1738.4803
|  | Substation Reactive Plant |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Scada Network Control And Protection Systems |  |  | 770.1534 | 571.7872 | 295.3853 | 28.2567 | 0 | 0 | 0 | 0 | 1665.5826 | 323.6421
|  | Other |  |  | 776.631 | 576.5964 | 297.8698 | 28.4944 | 0 | 0 | 0 | 0 | 1679.5916 | 326.3642
|  | Total Materials |  |  | 12129.4629 | 9005.3117 | 4652.1452 | 445.0266 | 0 | 0 | 0 | 0 | 26231.9465 | 5097.1718
|  | Labour (Internal) - $ Mar 2017 |  |  | 2015-16 | 2016-17 | 2017-18 | 2018-19 | 2019-20 | 2020-21 | 2021-22 | 2022-23 | Total | 2017-22 Total
|  | Transmission Towers |  |  | 150.3586 | 113.0281 | 58.8604 | 5.6762 | 0 | 0 | 0 | 0 | 327.9233 | 64.5366
|  | Transmission Tower Support Structures |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Conductors |  |  | 150.3586 | 113.0281 | 58.8604 | 5.6762 | 0 | 0 | 0 | 0 | 327.9233 | 64.5366
|  | Transmission Cables |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Substation Switchbays |  |  | 1310.7106 | 985.292 | 513.0994 | 49.4809 | 0 | 0 | 0 | 0 | 2858.583 | 562.5804
|  | Substation Power Transformers |  |  | 1034.2418 | 777.4638 | 404.8711 | 39.0439 | 0 | 0 | 0 | 0 | 2255.6206 | 443.915
|  | Substation Reactive Plant |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Scada Network Control And Protection Systems |  |  | 192.5384 | 144.7356 | 75.3723 | 7.2686 | 0 | 0 | 0 | 0 | 419.9148 | 82.6409
|  | Other |  |  | 194.1578 | 145.953 | 76.0063 | 7.3297 | 0 | 0 | 0 | 0 | 423.4467 | 83.336
|  | Total Internal Labour |  |  | 3032.3657 | 2279.5005 | 1187.0699 | 114.4755 | 0 | 0 | 0 | 0 | 6613.4117 | 1301.5454
|  | Labour (External) - $ Mar 2017 |  |  | 2015-16 | 2016-17 | 2017-18 | 2018-19 | 2019-20 | 2020-21 | 2021-22 | 2022-23 | Total | 2017-22 Total
|  | Transmission Towers |  |  | 751.793 | 564.1572 | 294.4674 | 28.4626 | 0 | 0 | 0 | 0 | 1638.8801 | 322.93
|  | Transmission Tower Support Structures |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Conductors |  |  | 751.793 | 564.1572 | 294.4674 | 28.4626 | 0 | 0 | 0 | 0 | 1638.8801 | 322.93
|  | Transmission Cables |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Substation Switchbays |  |  | 6553.5532 | 4917.8886 | 2566.9405 | 248.1148 | 0 | 0 | 0 | 0 | 14286.497 | 2815.0552
|  | Substation Power Transformers |  |  | 5171.2089 | 3880.5559 | 2025.4944 | 195.7798 | 0 | 0 | 0 | 0 | 11273.0391 | 2221.2742
|  | Substation Reactive Plant |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Scada Network Control And Protection Systems |  |  | 962.6918 | 722.4189 | 377.0737 | 36.4471 | 0 | 0 | 0 | 0 | 2098.6315 | 413.5208
|  | Other |  |  | 970.7888 | 728.4951 | 380.2452 | 36.7537 | 0 | 0 | 0 | 0 | 2116.2827 | 416.9988
|  | Total External Labour |  |  | 15161.8286 | 11377.6729 | 5938.6885 | 574.0204 | 0 | 0 | 0 | 0 | 33052.2105 | 6512.7089
|  | Total Direct - $ Mar 2017 |  |  | 2015-16 | 2016-17 | 2017-18 | 2018-19 | 2019-20 | 2020-21 | 2021-22 | 2022-23 | Total | 2017-22 Total
|  | Transmission Towers |  |  | 1503.5859 | 1123.7099 | 584.0024 | 56.2052 | 0 | 0 | 0 | 0 | 3267.5035 | 640.2077
|  | Transmission Tower Support Structures |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Conductors |  |  | 1503.5859 | 1123.7099 | 584.0024 | 56.2052 | 0 | 0 | 0 | 0 | 3267.5035 | 640.2077
|  | Transmission Cables |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Substation Switchbays |  |  | 13107.1064 | 9795.6391 | 5090.8845 | 489.9541 | 0 | 0 | 0 | 0 | 28483.5842 | 5580.8386
|  | Substation Power Transformers |  |  | 10342.4179 | 7729.4401 | 4017.0617 | 386.6078 | 0 | 0 | 0 | 0 | 22475.5275 | 4403.6695
|  | Substation Reactive Plant |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Scada Network Control And Protection Systems |  |  | 1925.3835 | 1438.9417 | 747.8313 | 71.9724 | 0 | 0 | 0 | 0 | 4184.129 | 819.8037
|  | Other |  |  | 1941.5776 | 1451.0444 | 754.1212 | 72.5777 | 0 | 0 | 0 | 0 | 4219.321 | 826.699
|  | Total Direct - $ Mar 2017 |  |  | 30323.6573 | 22662.4851 | 11777.9037 | 1133.5225 | 0 | 0 | 0 | 0 | 65897.5686 | 12911.4262

## Proj_4
Go To: | Table of Contents
Master Inputs
|  | XB59 |  | Business case? | Yes
| Project name | HTS Rebuild
| Project category 1 | Network |  |  | Shaded cells = Inputs
| Project category 2 | Replacement - Major Station
| Regulatory classification | Prescribed
| Overhead Category | Repex_OHD |  | $000's | $000's | $000's | $000's | $000's | $000's | $000's | $000's | $000's | Project | 2017-22
|  |  |  | Prior | 2015-16 | 2016-17 | 2017-18 | 2018-19 | 2019-20 | 2020-21 | 2021-22 | 2022-23 | Total | Total | Check
| Project timing | Direct Expenditure (As incurred) - $ 2015/16 |  | 7805.1816 | 13467.3399 | 18923.223 | 3639.548 | 0 | 0 | 0 | 0 | 0 | 43835.2925 | 3639.548 | ok
| (excluding real cost escalators) | Assumed year commissioned (no BC)
|  | Direct Expenditure (As Commissioned) - $ 2015/16 |  | 0 | 980.4086 | 12712.2348 | 14903.9994 | 15238.6496 | 0 | 0 | 0 | 0 | 43835.2925 | 30142.649 | ok
| Asset class | Secondary |  | 13.06% | 13.06% | 13.06% | 13.06% | 13.06% | 13.06% | 13.06% | 13.06% | 13.06%
|  | Switchgear |  | 40.95% | 40.95% | 40.95% | 40.95% | 40.95% | 40.95% | 40.95% | 40.95% | 40.95%
|  | Transformers |  | 32.88% | 32.88% | 32.88% | 32.88% | 32.88% | 32.88% | 32.88% | 32.88% | 32.88%
|  | Reactive |  | 0% | bar: 2015-16 to 2022-23
|  | Lines and towers |  | 1.417% | 1.417% | 1.417% | 1.417% | 1.417% | 1.417% | 1.417% | 1.417% | 1.417%
|  | Establishment |  | 11.35% | 11.35% | 11.35% | 11.35% | 11.35% | 11.35% | 11.35% | 11.35% | 11.35%
|  | Communications |  | 0.333% | 0.333% | 0.333% | 0.333% | 0.333% | 0.333% | 0.333% | 0.333% | 0.333%
Non System
Land
Easements
|  |  | Total | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
| Input costs % | Labour - internal |  | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10%
|  | Labour - external |  | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50%
|  | Materials |  | 40% | 40% | 40% | 40% | 40% | 40% | 40% | 40% | 40%
|  |  | Total | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
Material Escalation
| (By Asset Class) | Secondary |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Switchgear |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Transformers |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Reactive |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Lines and towers |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Establishment |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Communications |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Non System |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Land |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Easements |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Total Material escalation |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Labour Escalation | Internal Labour |  | 0 | 0 | 23.6801 | 7.5209 | 0 | 0 | 0 | 0 | 0 | 31.201 | 7.5209
|  | External Labour |  | 0 | 0 | 101.7328 | 38.6497 | 0 | 0 | 0 | 0 | 0 | 140.3824 | 38.6497
|  | Total Labour Escalation |  | 0 | 0 | 125.4129 | 46.1706 | 0 | 0 | 0 | 0 | 0 | 171.5835 | 46.1706
|  | Total Escalation |  | 0 | 0 | 125.4129 | 46.1706 | 0 | 0 | 0 | 0 | 0 | 171.5835 | 46.1706
|  | Escalation factors |  | 0 | 0 | 0.0066275 | 0.012686 | 0 | 0 | 0 | 0 | 0 | 0.0039143 | 0.012686
| Direct Expenditure (Escalated) | Total labour - internal |  | 793.7224 | 1369.5171 | 1948.416 | 377.7601 | 0 | 0 | 0 | 0 | 0 | 4489.4156 | 377.7601
| (as incurred) | Total labour - external |  | 3968.6121 | 6847.5854 | 9725.1302 | 1889.8632 | 0 | 0 | 0 | 0 | 0 | 22431.1908 | 1889.8632
|  | Total materials |  | 3174.8897 | 5478.0683 | 7697.3411 | 1480.4477 | 0 | 0 | 0 | 0 | 0 | 17830.7468 | 1480.4477
|  | Total Direct - As Incurred $ Mar 2017 |  | 7937.2241 | 13695.1708 | 19370.8873 | 3748.071 | 0 | 0 | 0 | 0 | 0 | 44751.3532 | 3748.071 | ok
| Capitalised Overheads | Overhead rate (applied to direct expenditure) |  | 8.008% | 8.425% | 7.259% | 7.658% | 9.013% | 8.969% | 7.948% | 8.001% | 8.318%
|  | Total overhead (as incurred) |  | 635.6266 | 1153.8433 | 1406.2041 | 287.0214 | 0 | 0 | 0 | 0 | 0 | 3482.6954 | 287.0214
|  | Total incl Overhead - As Incurred $ Mar 2017 |  | 8572.8507 | 14849.0141 | 20777.0914 | 4035.0924 | 0 | 0 | 0 | 0 | 0 | 48234.0486 | 4035.0924
|  | Total overheads (As incurred) - Cumulative |  | 635.6266 | 1789.4699 | 3195.674 | 3482.6954 | 3482.6954 | 3482.6954 | 3482.6954 | 3482.6954 | 3482.6954
|  | Labour & Material Escalation - Cumulative |  | 0 | 0 | 125.4129 | 171.5835 | 171.5835 | 171.5835 | 171.5835 | 171.5835 | 171.5835
Expenditure By Asset Class - As Incurred
| Asset class breakdown | Secondary |  | 1119.8988 | 1939.7739 | 2714.1775 | 527.117 | 0 | 0 | 0 | 0 | 0 | 6300.9672 | 527.117
| (fully absorbed) | Switchgear |  | 3510.7923 | 6081.0349 | 8508.7277 | 1652.4692 | 0 | 0 | 0 | 0 | 0 | 19753.024 | 1652.4692
| (as incurred) | Transformers |  | 2818.8051 | 4882.4456 | 6831.6332 | 1326.7628 | 0 | 0 | 0 | 0 | 0 | 15859.6467 | 1326.7628
|  | Reactive |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Lines and towers |  | 121.4518 | 210.3663 | 294.3495 | 57.1653 | 0 | 0 | 0 | 0 | 0 | 683.3329 | 57.1653
|  | Establishment |  | 973.3563 | 1685.9482 | 2359.0185 | 458.142 | 0 | 0 | 0 | 0 | 0 | 5476.465 | 458.142
|  | Communications |  | 28.5464 | 49.4452 | 69.1849 | 13.4363 | 0 | 0 | 0 | 0 | 0 | 160.6128 | 13.4363
|  | Non System |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Land |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Easements |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Total incl Overhead - As Incurred $ Mar 2017 |  | 8572.8507 | 14849.0141 | 20777.0914 | 4035.0924 | 0 | 0 | 0 | 0 | 0 | 48234.0486 | 4035.0924
|  |  | Check | 0 | 0 | 0 | 4.0927e-12 | 0 | 0 | 0 | 0 | 0 | 0 | 4.0927e-12
| As Commissioned Capex | Direct Expenditure (As Commissioned) - $ 2015/16 |  | 0 | 980.4086 | 12712.2348 | 14903.9994 | 15238.6496 | 0 | 0 | 0 | 0 | 43835.2925 | 30142.649
|  | Labour & Material Escalation - $ 2015/16 |  | 0 | 0 | 42.7218 | 69.2134 | 59.6483 | 0 | 0 | 0 | 0 | 171.5835 | 128.8617
|  | Total Direct Expenditure - $ 2015/16 |  | 0 | 980.4086 | 12754.9566 | 14973.2128 | 15298.2979 | 0 | 0 | 0 | 0 | 44006.876 | 30271.5108
|  | Total Direct Expenditure - $ Mar 2017 |  | 0 | 996.9945 | 12970.7359 | 15226.5191 | 15557.1037 | 0 | 0 | 0 | 0 | 44751.3532 | 30783.6228
|  | Total overheads (As Commissioned) |  | 0 | 82.4731 | 1006.1303 | 1183.3878 | 1210.7043 | 0 | 0 | 0 | 0 | 3482.6954 | 2394.092
|  | Total incl Overhead - As commissioned $ Mar 2017 |  | 0 | 1079.4676 | 13976.8662 | 16409.9068 | 16767.808 | 0 | 0 | 0 | 0 | 48234.0486 | 33177.7148
|  | Total overheads (As Comm) - Cumulative |  | 0 | 82.4731 | 1088.6034 | 2271.9912 | 3482.6954 | 3482.6954 | 3482.6954 | 3482.6954 | 3482.6954
|  | Total real cost escalation (As Comm) - Cumulative |  | 0 | 0 | 42.7218 | 111.9352 | 171.5835 | 171.5835 | 171.5835 | 171.5835 | 171.5835
Expenditure By Asset Class - As Commissioned
| Asset class breakdown | Secondary |  | 0 | 141.0143 | 1825.8425 | 2143.6783 | 2190.4321 | 0 | 0 | 0 | 0 | 6300.9672 | 4334.1104
| (fully absorbed) | Switchgear |  | 0 | 442.0684 | 5723.869 | 6720.2587 | 6866.828 | 0 | 0 | 0 | 0 | 19753.024 | 13587.0866
| (as commissioned) | Transformers |  | 0 | 354.9355 | 4595.6781 | 5395.6765 | 5513.3566 | 0 | 0 | 0 | 0 | 15859.6467 | 10909.0331
|  | Reactive |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Lines and towers |  | 0 | 15.2928 | 198.0106 | 232.4795 | 237.5499 | 0 | 0 | 0 | 0 | 683.3329 | 470.0295
|  | Establishment |  | 0 | 122.5621 | 1586.925 | 1863.171 | 1903.8069 | 0 | 0 | 0 | 0 | 5476.465 | 3766.9779
|  | Communications |  | 0 | 3.5945 | 46.5411 | 54.6428 | 55.8345 | 0 | 0 | 0 | 0 | 160.6128 | 110.4773
|  | Non System |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Land |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Easements |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Total incl Overhead - As commissioned $ Mar 2017 |  | 0 | 1079.4676 | 13976.8662 | 16409.9068 | 16767.808 | 0 | 0 | 0 | 0 | 48234.0486 | 33177.7148
|  |  | Check | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0
| Expenditure splits for RIN |  |  |  | 2015-16 | 2016-17 | 2017-18 | 2018-19 | 2019-20 | 2020-21 | 2021-22 | 2022-23
| Repex Category | Transmission Towers |  |  | 0.7084% | 0.7084% | 0.7084% | 0.7084% | 0.7084% | 0.7084% | 0.7084% | 0.7084%
Transmission Tower Support Structures | bar: 2015-16 to 2022-23
|  | Conductors |  |  | 0.7084% | 0.7084% | 0.7084% | 0.7084% | 0.7084% | 0.7084% | 0.7084% | 0.7084%
Transmission Cables | bar: 2015-16 to 2022-23
|  | Substation Switchbays |  |  | 40.95% | 40.95% | 40.95% | 40.95% | 40.95% | 40.95% | 40.95% | 40.95%
|  | Substation Power Transformers |  |  | 32.88% | 32.88% | 32.88% | 32.88% | 32.88% | 32.88% | 32.88% | 32.88%
Substation Reactive Plant | bar: 2015-16 to 2022-23
|  | Scada Network Control And Protection Systems |  |  | 13.4% | 13.4% | 13.4% | 13.4% | 13.4% | 13.4% | 13.4% | 13.4%
|  | Other |  |  | 11.35% | 11.35% | 11.35% | 11.35% | 11.35% | 11.35% | 11.35% | 11.35%
|  | Total |  |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
| Direct Expenditures | Materials - $ Mar 2017 |  |  | 2015-16 | 2016-17 | 2017-18 | 2018-19 | 2019-20 | 2020-21 | 2021-22 | 2022-23 | Total | 2017-22 Total
| (As Incurred) | Transmission Towers |  |  | 38.804 | 54.5242 | 10.4868 | 0 | 0 | 0 | 0 | 0 | 103.8149 | 10.4868
|  | Transmission Tower Support Structures |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Conductors |  |  | 38.804 | 54.5242 | 10.4868 | 0 | 0 | 0 | 0 | 0 | 103.8149 | 10.4868
|  | Transmission Cables |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Substation Switchbays |  |  | 2243.4031 | 3152.2497 | 606.2796 | 0 | 0 | 0 | 0 | 0 | 6001.9324 | 606.2796
|  | Substation Power Transformers |  |  | 1801.222 | 2530.9323 | 486.7802 | 0 | 0 | 0 | 0 | 0 | 4818.9344 | 486.7802
|  | Substation Reactive Plant |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Scada Network Control And Protection Systems |  |  | 733.8587 | 1031.1592 | 198.3253 | 0 | 0 | 0 | 0 | 0 | 1963.3432 | 198.3253
|  | Other |  |  | 621.9766 | 873.9515 | 168.0891 | 0 | 0 | 0 | 0 | 0 | 1664.0173 | 168.0891
|  | Total Materials |  |  | 5478.0683 | 7697.3411 | 1480.4477 | 0 | 0 | 0 | 0 | 0 | 14655.8571 | 1480.4477
|  | Labour (Internal) - $ Mar 2017 |  |  | 2015-16 | 2016-17 | 2017-18 | 2018-19 | 2019-20 | 2020-21 | 2021-22 | 2022-23 | Total | 2017-22 Total
|  | Transmission Towers |  |  | 9.701 | 13.8016 | 2.6759 | 0 | 0 | 0 | 0 | 0 | 26.1785 | 2.6759
|  | Transmission Tower Support Structures |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Conductors |  |  | 9.701 | 13.8016 | 2.6759 | 0 | 0 | 0 | 0 | 0 | 26.1785 | 2.6759
|  | Transmission Cables |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Substation Switchbays |  |  | 560.8508 | 797.9241 | 154.702 | 0 | 0 | 0 | 0 | 0 | 1513.4768 | 154.702
|  | Substation Power Transformers |  |  | 450.3055 | 640.6509 | 124.2098 | 0 | 0 | 0 | 0 | 0 | 1215.1662 | 124.2098
|  | Substation Reactive Plant |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Scada Network Control And Protection Systems |  |  | 183.4647 | 261.0157 | 50.6059 | 0 | 0 | 0 | 0 | 0 | 495.0863 | 50.6059
|  | Other |  |  | 155.4941 | 221.222 | 42.8907 | 0 | 0 | 0 | 0 | 0 | 419.6068 | 42.8907
|  | Total Internal Labour |  |  | 1369.5171 | 1948.416 | 377.7601 | 0 | 0 | 0 | 0 | 0 | 3695.6932 | 377.7601
|  | Labour (External) - $ Mar 2017 |  |  | 2015-16 | 2016-17 | 2017-18 | 2018-19 | 2019-20 | 2020-21 | 2021-22 | 2022-23 | Total | 2017-22 Total
|  | Transmission Towers |  |  | 48.505 | 68.8881 | 13.3869 | 0 | 0 | 0 | 0 | 0 | 130.7799 | 13.3869
|  | Transmission Tower Support Structures |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Conductors |  |  | 48.505 | 68.8881 | 13.3869 | 0 | 0 | 0 | 0 | 0 | 130.7799 | 13.3869
|  | Transmission Cables |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Substation Switchbays |  |  | 2804.2539 | 3982.679 | 773.9452 | 0 | 0 | 0 | 0 | 0 | 7560.8781 | 773.9452
|  | Substation Power Transformers |  |  | 2251.5275 | 3197.6816 | 621.3984 | 0 | 0 | 0 | 0 | 0 | 6070.6075 | 621.3984
|  | Substation Reactive Plant |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Scada Network Control And Protection Systems |  |  | 917.3234 | 1302.808 | 253.1718 | 0 | 0 | 0 | 0 | 0 | 2473.3033 | 253.1718
|  | Other |  |  | 777.4707 | 1104.1855 | 214.5739 | 0 | 0 | 0 | 0 | 0 | 2096.2301 | 214.5739
|  | Total External Labour |  |  | 6847.5854 | 9725.1302 | 1889.8632 | 0 | 0 | 0 | 0 | 0 | 18462.5787 | 1889.8632
|  | Total Direct - $ Mar 2017 |  |  | 2015-16 | 2016-17 | 2017-18 | 2018-19 | 2019-20 | 2020-21 | 2021-22 | 2022-23 | Total | 2017-22 Total
|  | Transmission Towers |  |  | 97.0099 | 137.2139 | 26.5495 | 0 | 0 | 0 | 0 | 0 | 260.7733 | 26.5495
|  | Transmission Tower Support Structures |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Conductors |  |  | 97.0099 | 137.2139 | 26.5495 | 0 | 0 | 0 | 0 | 0 | 260.7733 | 26.5495
|  | Transmission Cables |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Substation Switchbays |  |  | 5608.5078 | 7932.8527 | 1534.9269 | 0 | 0 | 0 | 0 | 0 | 15076.2873 | 1534.9269
|  | Substation Power Transformers |  |  | 4503.0549 | 6369.2648 | 1232.3884 | 0 | 0 | 0 | 0 | 0 | 12104.7081 | 1232.3884
|  | Substation Reactive Plant |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Scada Network Control And Protection Systems |  |  | 1834.6468 | 2594.983 | 502.103 | 0 | 0 | 0 | 0 | 0 | 4931.7328 | 502.103
|  | Other |  |  | 1554.9415 | 2199.359 | 425.5537 | 0 | 0 | 0 | 0 | 0 | 4179.8542 | 425.5537
|  | Total Direct - $ Mar 2017 |  |  | 13695.1708 | 19370.8873 | 3748.071 | 0 | 0 | 0 | 0 | 0 | 36814.129 | 3748.071

## Proj_5
Go To: | Table of Contents
Master Inputs
|  | XC19 |  | Business case? | Yes
| Project name | SMTS H2 Transformer Replacement
| Project category 1 | Network |  |  | Shaded cells = Inputs
| Project category 2 | Replacement - Major Station
| Regulatory classification | Prescribed
| Overhead Category | Repex_OHD |  | $000's | $000's | $000's | $000's | $000's | $000's | $000's | $000's | $000's | Project | 2017-22
|  |  |  | Prior | 2015-16 | 2016-17 | 2017-18 | 2018-19 | 2019-20 | 2020-21 | 2021-22 | 2022-23 | Total | Total | Check
| Project timing | Direct Expenditure (As incurred) - $ 2015/16 |  | 187.7001 | 2351.9049 | 8414.7736 | 16207.048 | 816.202 | 0 | 0 | 0 | 0 | 27977.6286 | 17023.25 | ok
| (excluding real cost escalators) | Assumed year commissioned (no BC)
|  | Direct Expenditure (As Commissioned) - $ 2015/16 |  | 0 | 0 | 11470.8277 | 15667.472 | 839.3289 | 0 | 0 | 0 | 0 | 27977.6286 | 16506.8009 | ok
| Asset class | Secondary |  | 13.06% | 13.06% | 13.06% | 13.06% | 13.06% | 13.06% | 13.06% | 13.06% | 13.06%
|  | Switchgear |  | 40.95% | 40.95% | 40.95% | 40.95% | 40.95% | 40.95% | 40.95% | 40.95% | 40.95%
|  | Transformers |  | 32.88% | 32.88% | 32.88% | 32.88% | 32.88% | 32.88% | 32.88% | 32.88% | 32.88%
|  | Reactive |  | 0% | bar: 2015-16 to 2022-23
|  | Lines and towers |  | 1.417% | 1.417% | 1.417% | 1.417% | 1.417% | 1.417% | 1.417% | 1.417% | 1.417%
|  | Establishment |  | 11.35% | 11.35% | 11.35% | 11.35% | 11.35% | 11.35% | 11.35% | 11.35% | 11.35%
|  | Communications |  | 0.333% | 0.333% | 0.333% | 0.333% | 0.333% | 0.333% | 0.333% | 0.333% | 0.333%
Non System
Land
Easements
|  |  | Total | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
| Input costs % | Labour - internal |  | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10%
|  | Labour - external |  | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50%
|  | Materials |  | 40% | 40% | 40% | 40% | 40% | 40% | 40% | 40% | 40%
|  |  | Total | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
Material Escalation
| (By Asset Class) | Secondary |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Switchgear |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Transformers |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Reactive |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Lines and towers |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Establishment |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Communications |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Non System |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Land |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Easements |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Total Material escalation |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Labour Escalation | Internal Labour |  | 0 | 0 | 10.5301 | 33.4911 | 2.3614 | 0 | 0 | 0 | 0 | 46.3826 | 35.8525
|  | External Labour |  | 0 | 0 | 45.2385 | 172.1084 | 13.0124 | 0 | 0 | 0 | 0 | 230.3593 | 185.1208
|  | Total Labour Escalation |  | 0 | 0 | 55.7686 | 205.5995 | 15.3738 | 0 | 0 | 0 | 0 | 276.7419 | 220.9733
|  | Total Escalation |  | 0 | 0 | 55.7686 | 205.5995 | 15.3738 | 0 | 0 | 0 | 0 | 276.7419 | 220.9733
|  | Escalation factors |  | 0 | 0 | 0.0066275 | 0.012686 | 0.018836 | 0 | 0 | 0 | 0 | 0.0098915 | 0.012981
| Direct Expenditure (Escalated) | Total labour - internal |  | 19.0875 | 239.1693 | 866.4211 | 1682.1804 | 85.4024 | 0 | 0 | 0 | 0 | 2892.2607 | 1767.5828
| (as incurred) | Total labour - external |  | 95.4377 | 1195.8464 | 4324.5682 | 8415.6337 | 428.2375 | 0 | 0 | 0 | 0 | 14459.7235 | 8843.8712
|  | Total materials |  | 76.3502 | 956.6771 | 3422.8515 | 6592.491 | 332.004 | 0 | 0 | 0 | 0 | 11380.3737 | 6924.4949
|  | Total Direct - As Incurred $ Mar 2017 |  | 190.8755 | 2391.6928 | 8613.8408 | 16690.3051 | 845.6438 | 0 | 0 | 0 | 0 | 28732.3579 | 17535.9489 | ok
| Capitalised Overheads | Overhead rate (applied to direct expenditure) |  | 8.008% | 8.425% | 7.259% | 7.658% | 9.013% | 8.969% | 7.948% | 8.001% | 8.318%
|  | Total overhead (as incurred) |  | 15.2856 | 201.5045 | 625.3105 | 1278.1176 | 76.2205 | 0 | 0 | 0 | 0 | 2196.4387 | 1354.3381
|  | Total incl Overhead - As Incurred $ Mar 2017 |  | 206.1611 | 2593.1973 | 9239.1513 | 17968.4227 | 921.8643 | 0 | 0 | 0 | 0 | 30928.7967 | 18890.287
|  | Total overheads (As incurred) - Cumulative |  | 15.2856 | 216.7902 | 842.1006 | 2120.2182 | 2196.4387 | 2196.4387 | 2196.4387 | 2196.4387 | 2196.4387
|  | Labour & Material Escalation - Cumulative |  | 0 | 0 | 55.7686 | 261.3681 | 276.7419 | 276.7419 | 276.7419 | 276.7419 | 276.7419
Expenditure By Asset Class - As Incurred
| Asset class breakdown | Secondary |  | 26.9315 | 338.7576 | 1206.9397 | 2347.2722 | 120.4261 | 0 | 0 | 0 | 0 | 4040.3271 | 2467.6983
| (fully absorbed) | Switchgear |  | 84.428 | 1061.9778 | 3783.6587 | 7358.5091 | 377.526 | 0 | 0 | 0 | 0 | 12666.0996 | 7736.0351
| (as incurred) | Transformers |  | 67.787 | 852.6589 | 3037.8888 | 5908.126 | 303.1146 | 0 | 0 | 0 | 0 | 10169.5752 | 6211.2405
|  | Reactive |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Lines and towers |  | 2.9207 | 36.7379 | 130.8913 | 254.5591 | 13.0601 | 0 | 0 | 0 | 0 | 438.169 | 267.6191
|  | Establishment |  | 23.4074 | 294.4301 | 1049.0077 | 2040.124 | 104.6679 | 0 | 0 | 0 | 0 | 3511.6371 | 2144.7919
|  | Communications |  | 0.68649 | 8.635 | 30.7651 | 59.8324 | 3.0697 | 0 | 0 | 0 | 0 | 102.9887 | 62.9021
|  | Non System |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Land |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Easements |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Total incl Overhead - As Incurred $ Mar 2017 |  | 206.1611 | 2593.1973 | 9239.1513 | 17968.4227 | 921.8643 | 0 | 0 | 0 | 0 | 30928.7967 | 18890.287
|  |  | Check | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| As Commissioned Capex | Direct Expenditure (As Commissioned) - $ 2015/16 |  | 0 | 0 | 11470.8277 | 15667.472 | 839.3289 | 0 | 0 | 0 | 0 | 27977.6286 | 16506.8009
|  | Labour & Material Escalation - $ 2015/16 |  | 0 | 0 | 55.7686 | 205.377 | 15.5963 | 0 | 0 | 0 | 0 | 276.7419 | 220.9733
|  | Total Direct Expenditure - $ 2015/16 |  | 0 | 0 | 11526.5963 | 15872.849 | 854.9252 | 0 | 0 | 0 | 0 | 28254.3705 | 16727.7742
|  | Total Direct Expenditure - $ Mar 2017 |  | 0 | 0 | 11721.5951 | 16141.3746 | 869.3882 | 0 | 0 | 0 | 0 | 28732.3579 | 17010.7628
|  | Total overheads (As Commissioned) |  | 0 | 0 | 881.6007 | 1236.8122 | 78.0258 | 0 | 0 | 0 | 0 | 2196.4387 | 1314.838
|  | Total incl Overhead - As commissioned $ Mar 2017 |  | 0 | 0 | 12603.1958 | 17378.1868 | 947.414 | 0 | 0 | 0 | 0 | 30928.7967 | 18325.6008
|  | Total overheads (As Comm) - Cumulative |  | 0 | 0 | 881.6007 | 2118.4129 | 2196.4387 | 2196.4387 | 2196.4387 | 2196.4387 | 2196.4387
|  | Total real cost escalation (As Comm) - Cumulative |  | 0 | 0 | 55.7686 | 261.1455 | 276.7419 | 276.7419 | 276.7419 | 276.7419 | 276.7419
Expenditure By Asset Class - As Commissioned
| Asset class breakdown | Secondary |  | 0 | 0 | 1646.3956 | 2270.1678 | 123.7637 | 0 | 0 | 0 | 0 | 4040.3271 | 2393.9315
| (fully absorbed) | Switchgear |  | 0 | 0 | 5161.3173 | 7116.7931 | 387.9892 | 0 | 0 | 0 | 0 | 12666.0996 | 7504.7823
| (as commissioned) | Transformers |  | 0 | 0 | 4144.0069 | 5714.0528 | 311.5154 | 0 | 0 | 0 | 0 | 10169.5752 | 6025.5683
|  | Reactive |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Lines and towers |  | 0 | 0 | 178.5498 | 246.1972 | 13.422 | 0 | 0 | 0 | 0 | 438.169 | 259.6192
|  | Establishment |  | 0 | 0 | 1430.9593 | 1973.1089 | 107.5688 | 0 | 0 | 0 | 0 | 3511.6371 | 2080.6778
|  | Communications |  | 0 | 0 | 41.9669 | 57.867 | 3.1548 | 0 | 0 | 0 | 0 | 102.9887 | 61.0218
|  | Non System |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Land |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Easements |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Total incl Overhead - As commissioned $ Mar 2017 |  | 0 | 0 | 12603.1958 | 17378.1868 | 947.414 | 0 | 0 | 0 | 0 | 30928.7967 | 18325.6008
|  |  | Check | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0
| Expenditure splits for RIN |  |  |  | 2015-16 | 2016-17 | 2017-18 | 2018-19 | 2019-20 | 2020-21 | 2021-22 | 2022-23
| Repex Category | Transmission Towers |  |  | 0.7084% | 0.7084% | 0.7084% | 0.7084% | 0.7084% | 0.7084% | 0.7084% | 0.7084%
Transmission Tower Support Structures | bar: 2015-16 to 2022-23
|  | Conductors |  |  | 0.7084% | 0.7084% | 0.7084% | 0.7084% | 0.7084% | 0.7084% | 0.7084% | 0.7084%
Transmission Cables | bar: 2015-16 to 2022-23
|  | Substation Switchbays |  |  | 40.95% | 40.95% | 40.95% | 40.95% | 40.95% | 40.95% | 40.95% | 40.95%
|  | Substation Power Transformers |  |  | 32.88% | 32.88% | 32.88% | 32.88% | 32.88% | 32.88% | 32.88% | 32.88%
Substation Reactive Plant | bar: 2015-16 to 2022-23
|  | Scada Network Control And Protection Systems |  |  | 13.4% | 13.4% | 13.4% | 13.4% | 13.4% | 13.4% | 13.4% | 13.4%
|  | Other |  |  | 11.35% | 11.35% | 11.35% | 11.35% | 11.35% | 11.35% | 11.35% | 11.35%
|  | Total |  |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
| Direct Expenditures | Materials - $ Mar 2017 |  |  | 2015-16 | 2016-17 | 2017-18 | 2018-19 | 2019-20 | 2020-21 | 2021-22 | 2022-23 | Total | 2017-22 Total
| (As Incurred) | Transmission Towers |  |  | 6.7766 | 24.2458 | 46.698 | 2.3518 | 0 | 0 | 0 | 0 | 80.0722 | 49.0497
|  | Transmission Tower Support Structures |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Conductors |  |  | 6.7766 | 24.2458 | 46.698 | 2.3518 | 0 | 0 | 0 | 0 | 80.0722 | 49.0497
|  | Transmission Cables |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Substation Switchbays |  |  | 391.7827 | 1401.7415 | 2699.7865 | 135.9638 | 0 | 0 | 0 | 0 | 4629.2744 | 2835.7502
|  | Substation Power Transformers |  |  | 314.5612 | 1125.4543 | 2167.6509 | 109.1649 | 0 | 0 | 0 | 0 | 3716.8313 | 2276.8158
|  | Substation Reactive Plant |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Scada Network Control And Protection Systems |  |  | 128.1594 | 458.5356 | 883.1502 | 44.4763 | 0 | 0 | 0 | 0 | 1514.3214 | 927.6264
|  | Other |  |  | 108.6205 | 388.6285 | 748.5075 | 37.6955 | 0 | 0 | 0 | 0 | 1283.4521 | 786.203
|  | Total Materials |  |  | 956.6771 | 3422.8515 | 6592.491 | 332.004 | 0 | 0 | 0 | 0 | 11304.0235 | 6924.4949
|  | Labour (Internal) - $ Mar 2017 |  |  | 2015-16 | 2016-17 | 2017-18 | 2018-19 | 2019-20 | 2020-21 | 2021-22 | 2022-23 | Total | 2017-22 Total
|  | Transmission Towers |  |  | 1.6942 | 6.1373 | 11.9157 | 0.60495 | 0 | 0 | 0 | 0 | 20.3522 | 12.5207
|  | Transmission Tower Support Structures |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Conductors |  |  | 1.6942 | 6.1373 | 11.9157 | 0.60495 | 0 | 0 | 0 | 0 | 20.3522 | 12.5207
|  | Transmission Cables |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Substation Switchbays |  |  | 97.9457 | 354.8206 | 688.8941 | 34.9744 | 0 | 0 | 0 | 0 | 1176.6347 | 723.8684
|  | Substation Power Transformers |  |  | 78.6403 | 284.8845 | 553.1111 | 28.0808 | 0 | 0 | 0 | 0 | 944.7167 | 581.1919
|  | Substation Reactive Plant |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Scada Network Control And Protection Systems |  |  | 32.0398 | 116.0684 | 225.35 | 11.4408 | 0 | 0 | 0 | 0 | 384.899 | 236.7908
|  | Other |  |  | 27.1551 | 98.3729 | 190.9938 | 9.6965 | 0 | 0 | 0 | 0 | 326.2184 | 200.6903
|  | Total Internal Labour |  |  | 239.1693 | 866.4211 | 1682.1804 | 85.4024 | 0 | 0 | 0 | 0 | 2873.1731 | 1767.5828
|  | Labour (External) - $ Mar 2017 |  |  | 2015-16 | 2016-17 | 2017-18 | 2018-19 | 2019-20 | 2020-21 | 2021-22 | 2022-23 | Total | 2017-22 Total
|  | Transmission Towers |  |  | 8.4708 | 30.6331 | 59.6122 | 3.0334 | 0 | 0 | 0 | 0 | 101.7496 | 62.6457
|  | Transmission Tower Support Structures |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Conductors |  |  | 8.4708 | 30.6331 | 59.6122 | 3.0334 | 0 | 0 | 0 | 0 | 101.7496 | 62.6457
|  | Transmission Cables |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Substation Switchbays |  |  | 489.7284 | 1771.0166 | 3446.4081 | 175.3737 | 0 | 0 | 0 | 0 | 5882.5268 | 3621.7818
|  | Substation Power Transformers |  |  | 393.2015 | 1421.9442 | 2767.1112 | 140.8071 | 0 | 0 | 0 | 0 | 4723.064 | 2907.9183
|  | Substation Reactive Plant |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Scada Network Control And Protection Systems |  |  | 160.1992 | 579.3323 | 1127.3839 | 57.368 | 0 | 0 | 0 | 0 | 1924.2835 | 1184.7519
|  | Other |  |  | 135.7757 | 491.0089 | 955.506 | 48.6218 | 0 | 0 | 0 | 0 | 1630.9124 | 1004.1278
|  | Total External Labour |  |  | 1195.8464 | 4324.5682 | 8415.6337 | 428.2375 | 0 | 0 | 0 | 0 | 14364.2858 | 8843.8712
|  | Total Direct - $ Mar 2017 |  |  | 2015-16 | 2016-17 | 2017-18 | 2018-19 | 2019-20 | 2020-21 | 2021-22 | 2022-23 | Total | 2017-22 Total
|  | Transmission Towers |  |  | 16.9416 | 61.0162 | 118.226 | 5.9901 | 0 | 0 | 0 | 0 | 202.1739 | 124.2161
|  | Transmission Tower Support Structures |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Conductors |  |  | 16.9416 | 61.0162 | 118.226 | 5.9901 | 0 | 0 | 0 | 0 | 202.1739 | 124.2161
|  | Transmission Cables |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Substation Switchbays |  |  | 979.4567 | 3527.5787 | 6835.0886 | 346.3118 | 0 | 0 | 0 | 0 | 11688.436 | 7181.4005
|  | Substation Power Transformers |  |  | 786.403 | 2832.2829 | 5487.8732 | 278.0528 | 0 | 0 | 0 | 0 | 9384.6119 | 5765.926
|  | Substation Reactive Plant |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Scada Network Control And Protection Systems |  |  | 320.3984 | 1153.9363 | 2235.8841 | 113.285 | 0 | 0 | 0 | 0 | 3823.5039 | 2349.1691
|  | Other |  |  | 271.5514 | 978.0103 | 1895.0073 | 96.0139 | 0 | 0 | 0 | 0 | 3240.5828 | 1991.0211
|  | Total Direct - $ Mar 2017 |  |  | 2391.6928 | 8613.8408 | 16690.3051 | 845.6438 | 0 | 0 | 0 | 0 | 28541.4824 | 17535.9489

## Proj_6
Go To: | Table of Contents
Master Inputs
|  | Various |  | Business case? | 0
| Project name | Other committed projects
| Project category 1 | Network |  |  | Shaded cells = Inputs
| Project category 2 | Replacement - Major Station
| Regulatory classification | Prescribed
| Overhead Category | Repex_OHD |  | $000's | $000's | $000's | $000's | $000's | $000's | $000's | $000's | $000's | Project | 2017-22
|  |  |  | Prior | 2015-16 | 2016-17 | 2017-18 | 2018-19 | 2019-20 | 2020-21 | 2021-22 | 2022-23 | Total | Total | Check
| Project timing | Direct Expenditure (As incurred) - $ 2015/16 |  | 0 | 54.8798 | 318.7414 | 544.2139 | 0 | 0 | 0 | 0 | 0 | 917.8352 | 544.2139 | ok
| (excluding real cost escalators) | Assumed year commissioned (no BC) | bar: 2015-16 to 2022-23
|  | Direct Expenditure (As Commissioned) - $ 2015/16 |  | 0 | 0 | 0 | 917.8352 | 0 | 0 | 0 | 0 | 0 | 917.8352 | 917.8352 | ok
| Asset class | Secondary |  | 13.06% | 13.06% | 13.06% | 13.06% | 13.06% | 13.06% | 13.06% | 13.06% | 13.06%
|  | Switchgear |  | 40.95% | 40.95% | 40.95% | 40.95% | 40.95% | 40.95% | 40.95% | 40.95% | 40.95%
|  | Transformers |  | 32.88% | 32.88% | 32.88% | 32.88% | 32.88% | 32.88% | 32.88% | 32.88% | 32.88%
|  | Reactive |  | 0% | bar: 2015-16 to 2022-23
|  | Lines and towers |  | 1.417% | 1.417% | 1.417% | 1.417% | 1.417% | 1.417% | 1.417% | 1.417% | 1.417%
|  | Establishment |  | 11.35% | 11.35% | 11.35% | 11.35% | 11.35% | 11.35% | 11.35% | 11.35% | 11.35%
|  | Communications |  | 0.333% | 0.333% | 0.333% | 0.333% | 0.333% | 0.333% | 0.333% | 0.333% | 0.333%
Non System
Land
Easements
|  |  | Total | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
| Input costs % | Labour - internal |  | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10%
|  | Labour - external |  | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50%
|  | Materials |  | 40% | 40% | 40% | 40% | 40% | 40% | 40% | 40% | 40%
|  |  | Total | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
Material Escalation
| (By Asset Class) | Secondary |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Switchgear |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Transformers |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Reactive |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Lines and towers |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Establishment |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Communications |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Non System |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Land |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Easements |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Total Material escalation |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Labour Escalation | Internal Labour |  | 0 | 0 | 0.39887 | 1.1246 | 0 | 0 | 0 | 0 | 0 | 1.5235 | 1.1246
|  | External Labour |  | 0 | 0 | 1.7136 | 5.7792 | 0 | 0 | 0 | 0 | 0 | 7.4928 | 5.7792
|  | Total Labour Escalation |  | 0 | 0 | 2.1124 | 6.9038 | 0 | 0 | 0 | 0 | 0 | 9.0162 | 6.9038
|  | Total Escalation |  | 0 | 0 | 2.1124 | 6.9038 | 0 | 0 | 0 | 0 | 0 | 9.0162 | 6.9038
|  | Escalation factors |  | 0 | 0 | 0.0066275 | 0.012686 | 0 | 0 | 0 | 0 | 0 | 0.0098234 | 0.012686
| Direct Expenditure (Escalated) | Total labour - internal |  | 0 | 5.5808 | 32.819 | 56.4857 | 0 | 0 | 0 | 0 | 0 | 94.8855 | 56.4857
| (as incurred) | Total labour - external |  | 0 | 27.9041 | 163.8094 | 282.5872 | 0 | 0 | 0 | 0 | 0 | 474.3008 | 282.5872
|  | Total materials |  | 0 | 22.3233 | 129.6535 | 221.3682 | 0 | 0 | 0 | 0 | 0 | 373.345 | 221.3682
|  | Total Direct - As Incurred $ Mar 2017 |  | 0 | 55.8083 | 326.2818 | 560.4411 | 0 | 0 | 0 | 0 | 0 | 942.5312 | 560.4411 | ok
| Capitalised Overheads | Overhead rate (applied to direct expenditure) |  | 8.008% | 8.425% | 7.259% | 7.658% | 9.013% | 8.969% | 7.948% | 8.001% | 8.318%
|  | Total overhead (as incurred) |  | 0 | 4.7019 | 23.686 | 42.9177 | 0 | 0 | 0 | 0 | 0 | 71.3057 | 42.9177
|  | Total incl Overhead - As Incurred $ Mar 2017 |  | 0 | 60.5102 | 349.9679 | 603.3588 | 0 | 0 | 0 | 0 | 0 | 1013.8369 | 603.3588
|  | Total overheads (As incurred) - Cumulative |  | 0 | 4.7019 | 28.388 | 71.3057 | 71.3057 | 71.3057 | 71.3057 | 71.3057 | 71.3057
|  | Labour & Material Escalation - Cumulative |  | 0 | 0 | 2.1124 | 9.0162 | 9.0162 | 9.0162 | 9.0162 | 9.0162 | 9.0162
Expenditure By Asset Class - As Incurred
| Asset class breakdown | Secondary |  | 0 | 7.9046 | 45.7174 | 78.8187 | 0 | 0 | 0 | 0 | 0 | 132.4407 | 78.8187
| (fully absorbed) | Switchgear |  | 0 | 24.7804 | 143.3204 | 247.0902 | 0 | 0 | 0 | 0 | 0 | 415.191 | 247.0902
| (as incurred) | Transformers |  | 0 | 19.8961 | 115.0715 | 198.388 | 0 | 0 | 0 | 0 | 0 | 333.3557 | 198.388
|  | Reactive |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Lines and towers |  | 0 | 0.85725 | 4.958 | 8.5478 | 0 | 0 | 0 | 0 | 0 | 14.3631 | 8.5478
|  | Establishment |  | 0 | 6.8703 | 39.7351 | 68.505 | 0 | 0 | 0 | 0 | 0 | 115.1104 | 68.505
|  | Communications |  | 0 | 0.20149 | 1.1653 | 2.0091 | 0 | 0 | 0 | 0 | 0 | 3.3759 | 2.0091
|  | Non System |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Land |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Easements |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Total incl Overhead - As Incurred $ Mar 2017 |  | 0 | 60.5102 | 349.9679 | 603.3588 | 0 | 0 | 0 | 0 | 0 | 1013.8369 | 603.3588
|  |  | Check | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| As Commissioned Capex | Direct Expenditure (As Commissioned) - $ 2015/16 |  | 0 | 0 | 0 | 917.8352 | 0 | 0 | 0 | 0 | 0 | 917.8352 | 917.8352
|  | Labour & Material Escalation - $ 2015/16 |  | 0 | 0 | 0 | 9.0162 | 0 | 0 | 0 | 0 | 0 | 9.0162 | 9.0162
|  | Total Direct Expenditure - $ 2015/16 |  | 0 | 0 | 0 | 926.8514 | 0 | 0 | 0 | 0 | 0 | 926.8514 | 926.8514
|  | Total Direct Expenditure - $ Mar 2017 |  | 0 | 0 | 0 | 942.5312 | 0 | 0 | 0 | 0 | 0 | 942.5312 | 942.5312
|  | Total overheads (As Commissioned) |  | 0 | 0 | 0 | 71.3057 | 0 | 0 | 0 | 0 | 0 | 71.3057 | 71.3057
|  | Total incl Overhead - As commissioned $ Mar 2017 |  | 0 | 0 | 0 | 1013.8369 | 0 | 0 | 0 | 0 | 0 | 1013.8369 | 1013.8369
|  | Total overheads (As Comm) - Cumulative |  | 0 | 0 | 0 | 71.3057 | 71.3057 | 71.3057 | 71.3057 | 71.3057 | 71.3057
|  | Total real cost escalation (As Comm) - Cumulative |  | 0 | 0 | 0 | 9.0162 | 9.0162 | 9.0162 | 9.0162 | 9.0162 | 9.0162
Expenditure By Asset Class - As Commissioned
| Asset class breakdown | Secondary |  | 0 | 0 | 0 | 132.4407 | 0 | 0 | 0 | 0 | 0 | 132.4407 | 132.4407
| (fully absorbed) | Switchgear |  | 0 | 0 | 0 | 415.191 | 0 | 0 | 0 | 0 | 0 | 415.191 | 415.191
| (as commissioned) | Transformers |  | 0 | 0 | 0 | 333.3557 | 0 | 0 | 0 | 0 | 0 | 333.3557 | 333.3557
|  | Reactive |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Lines and towers |  | 0 | 0 | 0 | 14.3631 | 0 | 0 | 0 | 0 | 0 | 14.3631 | 14.3631
|  | Establishment |  | 0 | 0 | 0 | 115.1104 | 0 | 0 | 0 | 0 | 0 | 115.1104 | 115.1104
|  | Communications |  | 0 | 0 | 0 | 3.3759 | 0 | 0 | 0 | 0 | 0 | 3.3759 | 3.3759
|  | Non System |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Land |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Easements |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Total incl Overhead - As commissioned $ Mar 2017 |  | 0 | 0 | 0 | 1013.8369 | 0 | 0 | 0 | 0 | 0 | 1013.8369 | 1013.8369
|  |  | Check | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0
| Expenditure splits for RIN |  |  |  | 2015-16 | 2016-17 | 2017-18 | 2018-19 | 2019-20 | 2020-21 | 2021-22 | 2022-23
| Repex Category | Transmission Towers |  |  | 0.7084% | 0.7084% | 0.7084% | 0.7084% | 0.7084% | 0.7084% | 0.7084% | 0.7084%
Transmission Tower Support Structures | bar: 2015-16 to 2022-23
|  | Conductors |  |  | 0.7084% | 0.7084% | 0.7084% | 0.7084% | 0.7084% | 0.7084% | 0.7084% | 0.7084%
Transmission Cables | bar: 2015-16 to 2022-23
|  | Substation Switchbays |  |  | 40.95% | 40.95% | 40.95% | 40.95% | 40.95% | 40.95% | 40.95% | 40.95%
|  | Substation Power Transformers |  |  | 32.88% | 32.88% | 32.88% | 32.88% | 32.88% | 32.88% | 32.88% | 32.88%
Substation Reactive Plant | bar: 2015-16 to 2022-23
|  | Scada Network Control And Protection Systems |  |  | 13.4% | 13.4% | 13.4% | 13.4% | 13.4% | 13.4% | 13.4% | 13.4%
|  | Other |  |  | 11.35% | 11.35% | 11.35% | 11.35% | 11.35% | 11.35% | 11.35% | 11.35%
|  | Total |  |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
| Direct Expenditures | Materials - $ Mar 2017 |  |  | 2015-16 | 2016-17 | 2017-18 | 2018-19 | 2019-20 | 2020-21 | 2021-22 | 2022-23 | Total | 2017-22 Total
| (As Incurred) | Transmission Towers |  |  | 0.15813 | 0.9184 | 1.5681 | 0 | 0 | 0 | 0 | 0 | 2.6446 | 1.5681
|  | Transmission Tower Support Structures |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Conductors |  |  | 0.15813 | 0.9184 | 1.5681 | 0 | 0 | 0 | 0 | 0 | 2.6446 | 1.5681
|  | Transmission Cables |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Substation Switchbays |  |  | 9.1419 | 53.0963 | 90.6557 | 0 | 0 | 0 | 0 | 0 | 152.8939 | 90.6557
|  | Substation Power Transformers |  |  | 7.34 | 42.6308 | 72.7872 | 0 | 0 | 0 | 0 | 0 | 122.7581 | 72.7872
|  | Substation Reactive Plant |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Scada Network Control And Protection Systems |  |  | 2.9905 | 17.3688 | 29.6552 | 0 | 0 | 0 | 0 | 0 | 50.0144 | 29.6552
|  | Other |  |  | 2.5346 | 14.7208 | 25.134 | 0 | 0 | 0 | 0 | 0 | 42.3894 | 25.134
|  | Total Materials |  |  | 22.3233 | 129.6535 | 221.3682 | 0 | 0 | 0 | 0 | 0 | 373.345 | 221.3682
|  | Labour (Internal) - $ Mar 2017 |  |  | 2015-16 | 2016-17 | 2017-18 | 2018-19 | 2019-20 | 2020-21 | 2021-22 | 2022-23 | Total | 2017-22 Total
|  | Transmission Towers |  |  | 0.039532 | 0.23247 | 0.40012 | 0 | 0 | 0 | 0 | 0 | 0.67212 | 0.40012
|  | Transmission Tower Support Structures |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Conductors |  |  | 0.039532 | 0.23247 | 0.40012 | 0 | 0 | 0 | 0 | 0 | 0.67212 | 0.40012
|  | Transmission Cables |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Substation Switchbays |  |  | 2.2855 | 13.4402 | 23.1323 | 0 | 0 | 0 | 0 | 0 | 38.8579 | 23.1323
|  | Substation Power Transformers |  |  | 1.835 | 10.7911 | 18.5728 | 0 | 0 | 0 | 0 | 0 | 31.1989 | 18.5728
|  | Substation Reactive Plant |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Scada Network Control And Protection Systems |  |  | 0.74762 | 4.3965 | 7.567 | 0 | 0 | 0 | 0 | 0 | 12.7111 | 7.567
|  | Other |  |  | 0.63364 | 3.7262 | 6.4133 | 0 | 0 | 0 | 0 | 0 | 10.7732 | 6.4133
|  | Total Internal Labour |  |  | 5.5808 | 32.819 | 56.4857 | 0 | 0 | 0 | 0 | 0 | 94.8855 | 56.4857
|  | Labour (External) - $ Mar 2017 |  |  | 2015-16 | 2016-17 | 2017-18 | 2018-19 | 2019-20 | 2020-21 | 2021-22 | 2022-23 | Total | 2017-22 Total
|  | Transmission Towers |  |  | 0.19766 | 1.1603 | 2.0017 | 0 | 0 | 0 | 0 | 0 | 3.3597 | 2.0017
|  | Transmission Tower Support Structures |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Conductors |  |  | 0.19766 | 1.1603 | 2.0017 | 0 | 0 | 0 | 0 | 0 | 3.3597 | 2.0017
|  | Transmission Cables |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Substation Switchbays |  |  | 11.4274 | 67.084 | 115.7264 | 0 | 0 | 0 | 0 | 0 | 194.2378 | 115.7264
|  | Substation Power Transformers |  |  | 9.175 | 53.8615 | 92.9164 | 0 | 0 | 0 | 0 | 0 | 155.953 | 92.9164
|  | Substation Reactive Plant |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Scada Network Control And Protection Systems |  |  | 3.7381 | 21.9444 | 37.8562 | 0 | 0 | 0 | 0 | 0 | 63.5388 | 37.8562
|  | Other |  |  | 3.1682 | 18.5988 | 32.0848 | 0 | 0 | 0 | 0 | 0 | 53.8518 | 32.0848
|  | Total External Labour |  |  | 27.9041 | 163.8094 | 282.5872 | 0 | 0 | 0 | 0 | 0 | 474.3008 | 282.5872
|  | Total Direct - $ Mar 2017 |  |  | 2015-16 | 2016-17 | 2017-18 | 2018-19 | 2019-20 | 2020-21 | 2021-22 | 2022-23 | Total | 2017-22 Total
|  | Transmission Towers |  |  | 0.39532 | 2.3112 | 3.9699 | 0 | 0 | 0 | 0 | 0 | 6.6764 | 3.9699
|  | Transmission Tower Support Structures |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Conductors |  |  | 0.39532 | 2.3112 | 3.9699 | 0 | 0 | 0 | 0 | 0 | 6.6764 | 3.9699
|  | Transmission Cables |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Substation Switchbays |  |  | 22.8549 | 133.6204 | 229.5144 | 0 | 0 | 0 | 0 | 0 | 385.9896 | 229.5144
|  | Substation Power Transformers |  |  | 18.3501 | 107.2834 | 184.2764 | 0 | 0 | 0 | 0 | 0 | 309.91 | 184.2764
|  | Substation Reactive Plant |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Scada Network Control And Protection Systems |  |  | 7.4762 | 43.7097 | 75.0784 | 0 | 0 | 0 | 0 | 0 | 126.2644 | 75.0784
|  | Other |  |  | 6.3364 | 37.0458 | 63.6321 | 0 | 0 | 0 | 0 | 0 | 107.0144 | 63.6321
|  | Total Direct - $ Mar 2017 |  |  | 55.8083 | 326.2818 | 560.4411 | 0 | 0 | 0 | 0 | 0 | 942.5312 | 560.4411

## Proj_7
Go To: | Table of Contents
Master Inputs
|  | XC21 |  | Business case? | 0
| Project name | RWTS B4 220/66kV Transformer and 66kV CB Replacement
| Project category 1 | Network |  |  | Shaded cells = Inputs
| Project category 2 | Replacement - Major Station
| Regulatory classification | Prescribed
| Overhead Category | Repex_OHD |  | $000's | $000's | $000's | $000's | $000's | $000's | $000's | $000's | $000's | Project | 2017-22
|  |  |  | Prior | 2015-16 | 2016-17 | 2017-18 | 2018-19 | 2019-20 | 2020-21 | 2021-22 | 2022-23 | Total | Total | Check
| Project timing | Direct Expenditure (As incurred) - $ 2015/16 |  | 0 | 39.4335 | 3590 | 6076 | 3867 | 0 | 0 | 0 | 0 | 13572.4335 | 9943 | ok
| (excluding real cost escalators) | Assumed year commissioned (no BC) | bar: 2015-16 to 2022-23
|  | Direct Expenditure (As Commissioned) - $ 2015/16 |  | 0 | 0 | 0 | 0 | 13572.4335 | 0 | 0 | 0 | 0 | 13572.4335 | 13572.4335 | ok
| Asset class | Secondary |  | 13.06% | 13.06% | 13.06% | 13.06% | 13.06% | 13.06% | 13.06% | 13.06% | 13.06%
|  | Switchgear |  | 40.95% | 40.95% | 40.95% | 40.95% | 40.95% | 40.95% | 40.95% | 40.95% | 40.95%
|  | Transformers |  | 32.88% | 32.88% | 32.88% | 32.88% | 32.88% | 32.88% | 32.88% | 32.88% | 32.88%
|  | Reactive |  | 0% | bar: 2015-16 to 2022-23
|  | Lines and towers |  | 1.417% | 1.417% | 1.417% | 1.417% | 1.417% | 1.417% | 1.417% | 1.417% | 1.417%
|  | Establishment |  | 11.35% | 11.35% | 11.35% | 11.35% | 11.35% | 11.35% | 11.35% | 11.35% | 11.35%
|  | Communications |  | 0.333% | 0.333% | 0.333% | 0.333% | 0.333% | 0.333% | 0.333% | 0.333% | 0.333%
Non System
Land
Easements
|  |  | Total | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
| Input costs % | Labour - internal |  | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10%
|  | Labour - external |  | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50%
|  | Materials |  | 40% | 40% | 40% | 40% | 40% | 40% | 40% | 40% | 40%
|  |  | Total | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
Material Escalation
| (By Asset Class) | Secondary |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Switchgear |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Transformers |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Reactive |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Lines and towers |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Establishment |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Communications |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Non System |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Land |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Easements |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Total Material escalation |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Labour Escalation | Internal Labour |  | 0 | 0 | 4.4924 | 12.5558 | 11.188 | 0 | 0 | 0 | 0 | 28.2362 | 23.7437
|  | External Labour |  | 0 | 0 | 19.3001 | 64.5232 | 61.6499 | 0 | 0 | 0 | 0 | 145.4732 | 126.1731
|  | Total Labour Escalation |  | 0 | 0 | 23.7926 | 77.079 | 72.8379 | 0 | 0 | 0 | 0 | 173.7094 | 149.9168
|  | Total Escalation |  | 0 | 0 | 23.7926 | 77.079 | 72.8379 | 0 | 0 | 0 | 0 | 173.7094 | 149.9168
|  | Escalation factors |  | 0 | 0 | 0.0066275 | 0.012686 | 0.018836 | 0 | 0 | 0 | 0 | 0.012799 | 0.015078
| Direct Expenditure (Escalated) | Total labour - internal |  | 0 | 4.0101 | 369.6418 | 630.6471 | 404.6192 | 0 | 0 | 0 | 0 | 1408.9181 | 1035.2663
| (as incurred) | Total labour - external |  | 0 | 20.0503 | 1844.9932 | 3155.0095 | 2028.9024 | 0 | 0 | 0 | 0 | 7048.9554 | 5183.9119
|  | Total materials |  | 0 | 16.0402 | 1460.2932 | 2471.5158 | 1572.9677 | 0 | 0 | 0 | 0 | 5520.8169 | 4044.4835
|  | Total Direct - As Incurred $ Mar 2017 |  | 0 | 40.1006 | 3674.9282 | 6257.1724 | 4006.4893 | 0 | 0 | 0 | 0 | 13978.6904 | 10263.6617 | ok
| Capitalised Overheads | Overhead rate (applied to direct expenditure) |  | 8.008% | 8.425% | 7.259% | 7.658% | 9.013% | 8.969% | 7.948% | 8.001% | 8.318%
|  | Total overhead (as incurred) |  | 0 | 3.3785 | 266.7766 | 479.1645 | 361.1173 | 0 | 0 | 0 | 0 | 1110.437 | 840.2819
|  | Total incl Overhead - As Incurred $ Mar 2017 |  | 0 | 43.4791 | 3941.7047 | 6736.3369 | 4367.6066 | 0 | 0 | 0 | 0 | 15089.1274 | 11103.9435
|  | Total overheads (As incurred) - Cumulative |  | 0 | 3.3785 | 270.1551 | 749.3197 | 1110.437 | 1110.437 | 1110.437 | 1110.437 | 1110.437
|  | Labour & Material Escalation - Cumulative |  | 0 | 0 | 23.7926 | 100.8716 | 173.7094 | 173.7094 | 173.7094 | 173.7094 | 173.7094
Expenditure By Asset Class - As Incurred
| Asset class breakdown | Secondary |  | 0 | 5.6798 | 514.9174 | 879.9891 | 570.5543 | 0 | 0 | 0 | 0 | 1971.1407 | 1450.5435
| (fully absorbed) | Switchgear |  | 0 | 17.8058 | 1614.2246 | 2758.6949 | 1788.6419 | 0 | 0 | 0 | 0 | 6179.3672 | 4547.3368
| (as incurred) | Transformers |  | 0 | 14.2962 | 1296.0563 | 2214.9483 | 1436.0954 | 0 | 0 | 0 | 0 | 4961.3963 | 3651.0437
|  | Reactive |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Lines and towers |  | 0 | 0.61597 | 55.8422 | 95.4338 | 61.876 | 0 | 0 | 0 | 0 | 213.768 | 157.3098
|  | Establishment |  | 0 | 4.9366 | 447.5388 | 764.8397 | 495.8954 | 0 | 0 | 0 | 0 | 1713.2105 | 1260.7351
|  | Communications |  | 0 | 0.14478 | 13.1253 | 22.4311 | 14.5435 | 0 | 0 | 0 | 0 | 50.2447 | 36.9746
|  | Non System |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Land |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Easements |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Total incl Overhead - As Incurred $ Mar 2017 |  | 0 | 43.4791 | 3941.7047 | 6736.3369 | 4367.6066 | 0 | 0 | 0 | 0 | 15089.1274 | 11103.9435
|  |  | Check | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| As Commissioned Capex | Direct Expenditure (As Commissioned) - $ 2015/16 |  | 0 | 0 | 0 | 0 | 13572.4335 | 0 | 0 | 0 | 0 | 13572.4335 | 13572.4335
|  | Labour & Material Escalation - $ 2015/16 |  | 0 | 0 | 0 | 0 | 173.7094 | 0 | 0 | 0 | 0 | 173.7094 | 173.7094
|  | Total Direct Expenditure - $ 2015/16 |  | 0 | 0 | 0 | 0 | 13746.1429 | 0 | 0 | 0 | 0 | 13746.1429 | 13746.1429
|  | Total Direct Expenditure - $ Mar 2017 |  | 0 | 0 | 0 | 0 | 13978.6904 | 0 | 0 | 0 | 0 | 13978.6904 | 13978.6904
|  | Total overheads (As Commissioned) |  | 0 | 0 | 0 | 0 | 1110.437 | 0 | 0 | 0 | 0 | 1110.437 | 1110.437
|  | Total incl Overhead - As commissioned $ Mar 2017 |  | 0 | 0 | 0 | 0 | 15089.1274 | 0 | 0 | 0 | 0 | 15089.1274 | 15089.1274
|  | Total overheads (As Comm) - Cumulative |  | 0 | 0 | 0 | 0 | 1110.437 | 1110.437 | 1110.437 | 1110.437 | 1110.437
|  | Total real cost escalation (As Comm) - Cumulative |  | 0 | 0 | 0 | 0 | 173.7094 | 173.7094 | 173.7094 | 173.7094 | 173.7094
Expenditure By Asset Class - As Commissioned
| Asset class breakdown | Secondary |  | 0 | 0 | 0 | 0 | 1971.1407 | 0 | 0 | 0 | 0 | 1971.1407 | 1971.1407
| (fully absorbed) | Switchgear |  | 0 | 0 | 0 | 0 | 6179.3672 | 0 | 0 | 0 | 0 | 6179.3672 | 6179.3672
| (as commissioned) | Transformers |  | 0 | 0 | 0 | 0 | 4961.3963 | 0 | 0 | 0 | 0 | 4961.3963 | 4961.3963
|  | Reactive |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Lines and towers |  | 0 | 0 | 0 | 0 | 213.768 | 0 | 0 | 0 | 0 | 213.768 | 213.768
|  | Establishment |  | 0 | 0 | 0 | 0 | 1713.2105 | 0 | 0 | 0 | 0 | 1713.2105 | 1713.2105
|  | Communications |  | 0 | 0 | 0 | 0 | 50.2447 | 0 | 0 | 0 | 0 | 50.2447 | 50.2447
|  | Non System |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Land |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Easements |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Total incl Overhead - As commissioned $ Mar 2017 |  | 0 | 0 | 0 | 0 | 15089.1274 | 0 | 0 | 0 | 0 | 15089.1274 | 15089.1274
|  |  | Check | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0
| Expenditure splits for RIN |  |  |  | 2015-16 | 2016-17 | 2017-18 | 2018-19 | 2019-20 | 2020-21 | 2021-22 | 2022-23
| Repex Category | Transmission Towers |  |  | 0.7084% | 0.7084% | 0.7084% | 0.7084% | 0.7084% | 0.7084% | 0.7084% | 0.7084%
Transmission Tower Support Structures | bar: 2015-16 to 2022-23
|  | Conductors |  |  | 0.7084% | 0.7084% | 0.7084% | 0.7084% | 0.7084% | 0.7084% | 0.7084% | 0.7084%
Transmission Cables | bar: 2015-16 to 2022-23
|  | Substation Switchbays |  |  | 40.95% | 40.95% | 40.95% | 40.95% | 40.95% | 40.95% | 40.95% | 40.95%
|  | Substation Power Transformers |  |  | 32.88% | 32.88% | 32.88% | 32.88% | 32.88% | 32.88% | 32.88% | 32.88%
Substation Reactive Plant | bar: 2015-16 to 2022-23
|  | Scada Network Control And Protection Systems |  |  | 13.4% | 13.4% | 13.4% | 13.4% | 13.4% | 13.4% | 13.4% | 13.4%
|  | Other |  |  | 11.35% | 11.35% | 11.35% | 11.35% | 11.35% | 11.35% | 11.35% | 11.35%
|  | Total |  |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
| Direct Expenditures | Materials - $ Mar 2017 |  |  | 2015-16 | 2016-17 | 2017-18 | 2018-19 | 2019-20 | 2020-21 | 2021-22 | 2022-23 | Total | 2017-22 Total
| (As Incurred) | Transmission Towers |  |  | 0.11362 | 10.344 | 17.507 | 11.1421 | 0 | 0 | 0 | 0 | 39.1068 | 28.6491
|  | Transmission Tower Support Structures |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Conductors |  |  | 0.11362 | 10.344 | 17.507 | 11.1421 | 0 | 0 | 0 | 0 | 39.1068 | 28.6491
|  | Transmission Cables |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Substation Switchbays |  |  | 6.5689 | 598.0258 | 1012.1462 | 644.1688 | 0 | 0 | 0 | 0 | 2260.9097 | 1656.315
|  | Substation Power Transformers |  |  | 5.2741 | 480.1532 | 812.6493 | 517.2013 | 0 | 0 | 0 | 0 | 1815.278 | 1329.8506
|  | Substation Reactive Plant |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Scada Network Control And Protection Systems |  |  | 2.1488 | 195.6253 | 331.0918 | 210.7195 | 0 | 0 | 0 | 0 | 739.5854 | 541.8113
|  | Other |  |  | 1.8212 | 165.8008 | 280.6144 | 178.5938 | 0 | 0 | 0 | 0 | 626.8303 | 459.2082
|  | Total Materials |  |  | 16.0402 | 1460.2932 | 2471.5158 | 1572.9677 | 0 | 0 | 0 | 0 | 5520.8169 | 4044.4835
|  | Labour (Internal) - $ Mar 2017 |  |  | 2015-16 | 2016-17 | 2017-18 | 2018-19 | 2019-20 | 2020-21 | 2021-22 | 2022-23 | Total | 2017-22 Total
|  | Transmission Towers |  |  | 0.028405 | 2.6184 | 4.4672 | 2.8661 | 0 | 0 | 0 | 0 | 9.9801 | 7.3333
|  | Transmission Tower Support Structures |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Conductors |  |  | 0.028405 | 2.6184 | 4.4672 | 2.8661 | 0 | 0 | 0 | 0 | 9.9801 | 7.3333
|  | Transmission Cables |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Substation Switchbays |  |  | 1.6422 | 151.3773 | 258.2654 | 165.7015 | 0 | 0 | 0 | 0 | 576.9865 | 423.9669
|  | Substation Power Transformers |  |  | 1.3185 | 121.5404 | 207.3606 | 133.0412 | 0 | 0 | 0 | 0 | 463.2608 | 340.4018
|  | Substation Reactive Plant |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Scada Network Control And Protection Systems |  |  | 0.5372 | 49.5183 | 84.4834 | 54.204 | 0 | 0 | 0 | 0 | 188.743 | 138.6874
|  | Other |  |  | 0.4553 | 41.9689 | 71.6033 | 45.9402 | 0 | 0 | 0 | 0 | 159.9677 | 117.5435
|  | Total Internal Labour |  |  | 4.0101 | 369.6418 | 630.6471 | 404.6192 | 0 | 0 | 0 | 0 | 1408.9181 | 1035.2663
|  | Labour (External) - $ Mar 2017 |  |  | 2015-16 | 2016-17 | 2017-18 | 2018-19 | 2019-20 | 2020-21 | 2021-22 | 2022-23 | Total | 2017-22 Total
|  | Transmission Towers |  |  | 0.14203 | 13.069 | 22.3485 | 14.3718 | 0 | 0 | 0 | 0 | 49.9314 | 36.7203
|  | Transmission Tower Support Structures |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Conductors |  |  | 0.14203 | 13.069 | 22.3485 | 14.3718 | 0 | 0 | 0 | 0 | 49.9314 | 36.7203
|  | Transmission Cables |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Substation Switchbays |  |  | 8.2111 | 755.5699 | 1292.0537 | 830.8852 | 0 | 0 | 0 | 0 | 2886.7199 | 2122.9389
|  | Substation Power Transformers |  |  | 6.5927 | 606.6449 | 1037.3862 | 667.1154 | 0 | 0 | 0 | 0 | 2317.7391 | 1704.5016
|  | Substation Reactive Plant |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Scada Network Control And Protection Systems |  |  | 2.686 | 247.1609 | 422.6547 | 271.7979 | 0 | 0 | 0 | 0 | 944.2995 | 694.4526
|  | Other |  |  | 2.2765 | 209.4794 | 358.2179 | 230.3604 | 0 | 0 | 0 | 0 | 800.3342 | 588.5783
|  | Total External Labour |  |  | 20.0503 | 1844.9932 | 3155.0095 | 2028.9024 | 0 | 0 | 0 | 0 | 7048.9554 | 5183.9119
|  | Total Direct - $ Mar 2017 |  |  | 2015-16 | 2016-17 | 2017-18 | 2018-19 | 2019-20 | 2020-21 | 2021-22 | 2022-23 | Total | 2017-22 Total
|  | Transmission Towers |  |  | 0.28405 | 26.0314 | 44.3228 | 28.38 | 0 | 0 | 0 | 0 | 99.0182 | 72.7028
|  | Transmission Tower Support Structures |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Conductors |  |  | 0.28405 | 26.0314 | 44.3228 | 28.38 | 0 | 0 | 0 | 0 | 99.0182 | 72.7028
|  | Transmission Cables |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Substation Switchbays |  |  | 16.4222 | 1504.9731 | 2562.4653 | 1640.7555 | 0 | 0 | 0 | 0 | 5724.616 | 4203.2208
|  | Substation Power Transformers |  |  | 13.1853 | 1208.3386 | 2057.3961 | 1317.3579 | 0 | 0 | 0 | 0 | 4596.2779 | 3374.754
|  | Substation Reactive Plant |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Scada Network Control And Protection Systems |  |  | 5.372 | 492.3046 | 838.2299 | 536.7215 | 0 | 0 | 0 | 0 | 1872.6279 | 1374.9514
|  | Other |  |  | 4.553 | 417.2491 | 710.4356 | 454.8944 | 0 | 0 | 0 | 0 | 1587.1321 | 1165.33
|  | Total Direct - $ Mar 2017 |  |  | 40.1006 | 3674.9282 | 6257.1724 | 4006.4893 | 0 | 0 | 0 | 0 | 13978.6904 | 10263.6617

## Proj_8
Go To: | Table of Contents
Master Inputs
|  | XC15 |  | Business case? | 0
| Project name | TSTS B2 Transformer and 66kV CB Replacement
| Project category 1 | Network |  |  | Shaded cells = Inputs
| Project category 2 | Replacement - Major Station
| Regulatory classification | Prescribed
| Overhead Category | Repex_OHD |  | $000's | $000's | $000's | $000's | $000's | $000's | $000's | $000's | $000's | Project | 2017-22
|  |  |  | Prior | 2015-16 | 2016-17 | 2017-18 | 2018-19 | 2019-20 | 2020-21 | 2021-22 | 2022-23 | Total | Total | Check
| Project timing | Direct Expenditure (As incurred) - $ 2015/16 |  | 35.8155 | -33.6604 | 0 | 0 | 0 | 581 | 7551 | 12778 | 0 | 20912.1551 | 20910 | ok
| (excluding real cost escalators) | Assumed year commissioned (no BC) | bar: 2015-16 to 2022-23
|  | Direct Expenditure (As Commissioned) - $ 2015/16 |  | 0 | 0 | 0 | 0 | 0 | 0 | 8134.1551 | 12778 | 0 | 20912.1551 | 20912.1551 | ok
| Asset class | Secondary |  | 13.06% | 13.06% | 13.06% | 13.06% | 13.06% | 13.06% | 13.06% | 13.06% | 13.06%
|  | Switchgear |  | 40.95% | 40.95% | 40.95% | 40.95% | 40.95% | 40.95% | 40.95% | 40.95% | 40.95%
|  | Transformers |  | 32.88% | 32.88% | 32.88% | 32.88% | 32.88% | 32.88% | 32.88% | 32.88% | 32.88%
|  | Reactive |  | 0% | bar: 2015-16 to 2022-23
|  | Lines and towers |  | 1.417% | 1.417% | 1.417% | 1.417% | 1.417% | 1.417% | 1.417% | 1.417% | 1.417%
|  | Establishment |  | 11.35% | 11.35% | 11.35% | 11.35% | 11.35% | 11.35% | 11.35% | 11.35% | 11.35%
|  | Communications |  | 0.333% | 0.333% | 0.333% | 0.333% | 0.333% | 0.333% | 0.333% | 0.333% | 0.333%
Non System
Land
Easements
|  |  | Total | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
| Input costs % | Labour - internal |  | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10%
|  | Labour - external |  | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50%
|  | Materials |  | 40% | 40% | 40% | 40% | 40% | 40% | 40% | 40% | 40%
|  |  | Total | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
Material Escalation
| (By Asset Class) | Secondary |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Switchgear |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Transformers |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Reactive |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Lines and towers |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Establishment |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Communications |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Non System |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Land |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Easements |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Total Material escalation |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Labour Escalation | Internal Labour |  | 0 | 0 | 0 | 0 | 0 | 2.1756 | 35.2869 | 71.8848 | 0 | 109.3474 | 109.3474
|  | External Labour |  | 0 | 0 | 0 | 0 | 0 | 12.2827 | 202.5263 | 417.7789 | 0 | 632.588 | 632.588
|  | Total Labour Escalation |  | 0 | 0 | 0 | 0 | 0 | 14.4584 | 237.8132 | 489.6638 | 0 | 741.9353 | 741.9353
|  | Total Escalation |  | 0 | 0 | 0 | 0 | 0 | 14.4584 | 237.8132 | 489.6638 | 0 | 741.9353 | 741.9353
|  | Escalation factors |  | 0 | 0 | 0 | 0 | 0 | 0.024885 | 0.031494 | 0.038321 | 0 | 0.035479 | 0.035482
| Direct Expenditure (Escalated) | Total labour - internal |  | 3.6421 | -3.423 | 0 | 0 | 0 | 61.2953 | 803.7581 | 1372.5178 | 0 | 2237.7904 | 2237.5713
| (as incurred) | Total labour - external |  | 18.2107 | -17.1149 | 0 | 0 | 0 | 307.905 | 4045.3237 | 6921.9312 | 0 | 11276.2557 | 11275.1599
|  | Total materials |  | 14.5686 | -13.6919 | 0 | 0 | 0 | 236.3316 | 3071.497 | 5197.6677 | 0 | 8506.3729 | 8505.4962
|  | Total Direct - As Incurred $ Mar 2017 |  | 36.4214 | -34.2298 | 0 | 0 | 0 | 605.5319 | 7920.5788 | 13492.1167 | 0 | 22020.4191 | 22018.2275 | ok
| Capitalised Overheads | Overhead rate (applied to direct expenditure) |  | 8.008% | 8.425% | 7.259% | 7.658% | 9.013% | 8.969% | 7.948% | 8.001% | 8.318%
|  | Total overhead (as incurred) |  | 2.9167 | -2.8839 | 0 | 0 | 0 | 54.3076 | 629.548 | 1079.5616 | 0 | 1763.4499 | 1763.4172
|  | Total incl Overhead - As Incurred $ Mar 2017 |  | 39.3381 | -37.1138 | 0 | 0 | 0 | 659.8395 | 8550.1268 | 14571.6783 | 0 | 23783.869 | 23781.6446
|  | Total overheads (As incurred) - Cumulative |  | 2.9167 | 0.032764 | 0.032764 | 0.032764 | 0.032764 | 54.3404 | 683.8884 | 1763.4499 | 1763.4499
|  | Labour & Material Escalation - Cumulative |  | 0 | 0 | 0 | 0 | 0 | 14.4584 | 252.2716 | 741.9353 | 741.9353
Expenditure By Asset Class - As Incurred
| Asset class breakdown | Secondary |  | 5.1389 | -4.8483 | 0 | 0 | 0 | 86.1969 | 1116.9303 | 1903.5447 | 0 | 3106.9625 | 3106.6719
| (fully absorbed) | Switchgear |  | 16.1099 | -15.199 | 0 | 0 | 0 | 270.2204 | 3501.4863 | 5967.4591 | 0 | 9740.0767 | 9739.1658
| (as incurred) | Transformers |  | 12.9346 | -12.2032 | 0 | 0 | 0 | 216.9592 | 2811.3334 | 4791.2559 | 0 | 7820.2798 | 7819.5485
|  | Reactive |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Lines and towers |  | 0.5573 | -0.52579 | 0 | 0 | 0 | 9.348 | 121.1299 | 206.4373 | 0 | 336.9466 | 336.9151
|  | Establishment |  | 4.4664 | -4.2139 | 0 | 0 | 0 | 74.9178 | 970.7763 | 1654.4596 | 0 | 2700.4063 | 2700.1537
|  | Communications |  | 0.13099 | -0.12358 | 0 | 0 | 0 | 2.1972 | 28.4708 | 48.5217 | 0 | 79.197 | 79.1896
|  | Non System |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Land |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Easements |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Total incl Overhead - As Incurred $ Mar 2017 |  | 39.3381 | -37.1138 | 0 | 0 | 0 | 659.8395 | 8550.1268 | 14571.6783 | 0 | 23783.869 | 23781.6446
|  |  | Check | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| As Commissioned Capex | Direct Expenditure (As Commissioned) - $ 2015/16 |  | 0 | 0 | 0 | 0 | 0 | 0 | 8134.1551 | 12778 | 0 | 20912.1551 | 20912.1551
|  | Labour & Material Escalation - $ 2015/16 |  | 0 | 0 | 0 | 0 | 0 | 0 | 252.2716 | 489.6638 | 0 | 741.9353 | 741.9353
|  | Total Direct Expenditure - $ 2015/16 |  | 0 | 0 | 0 | 0 | 0 | 0 | 8386.4267 | 13267.6638 | 0 | 21654.0905 | 21654.0905
|  | Total Direct Expenditure - $ Mar 2017 |  | 0 | 0 | 0 | 0 | 0 | 0 | 8528.3023 | 13492.1167 | 0 | 22020.4191 | 22020.4191
|  | Total overheads (As Commissioned) |  | 0 | 0 | 0 | 0 | 0 | 0 | 683.8884 | 1079.5616 | 0 | 1763.4499 | 1763.4499
|  | Total incl Overhead - As commissioned $ Mar 2017 |  | 0 | 0 | 0 | 0 | 0 | 0 | 9212.1907 | 14571.6783 | 0 | 23783.869 | 23783.869
|  | Total overheads (As Comm) - Cumulative |  | 0 | 0 | 0 | 0 | 0 | 0 | 683.8884 | 1763.4499 | 1763.4499
|  | Total real cost escalation (As Comm) - Cumulative |  | 0 | 0 | 0 | 0 | 0 | 0 | 252.2716 | 741.9353 | 741.9353
Expenditure By Asset Class - As Commissioned
| Asset class breakdown | Secondary |  | 0 | 0 | 0 | 0 | 0 | 0 | 1203.4178 | 1903.5447 | 0 | 3106.9625 | 3106.9625
| (fully absorbed) | Switchgear |  | 0 | 0 | 0 | 0 | 0 | 0 | 3772.6177 | 5967.4591 | 0 | 9740.0767 | 9740.0767
| (as commissioned) | Transformers |  | 0 | 0 | 0 | 0 | 0 | 0 | 3029.024 | 4791.2559 | 0 | 7820.2798 | 7820.2798
|  | Reactive |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Lines and towers |  | 0 | 0 | 0 | 0 | 0 | 0 | 130.5093 | 206.4373 | 0 | 336.9466 | 336.9466
|  | Establishment |  | 0 | 0 | 0 | 0 | 0 | 0 | 1045.9466 | 1654.4596 | 0 | 2700.4063 | 2700.4063
|  | Communications |  | 0 | 0 | 0 | 0 | 0 | 0 | 30.6753 | 48.5217 | 0 | 79.197 | 79.197
|  | Non System |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Land |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Easements |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Total incl Overhead - As commissioned $ Mar 2017 |  | 0 | 0 | 0 | 0 | 0 | 0 | 9212.1907 | 14571.6783 | 0 | 23783.869 | 23783.869
|  |  | Check | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0
| Expenditure splits for RIN |  |  |  | 2015-16 | 2016-17 | 2017-18 | 2018-19 | 2019-20 | 2020-21 | 2021-22 | 2022-23
| Repex Category | Transmission Towers |  |  | 0.7084% | 0.7084% | 0.7084% | 0.7084% | 0.7084% | 0.7084% | 0.7084% | 0.7084%
Transmission Tower Support Structures | bar: 2015-16 to 2022-23
|  | Conductors |  |  | 0.7084% | 0.7084% | 0.7084% | 0.7084% | 0.7084% | 0.7084% | 0.7084% | 0.7084%
Transmission Cables | bar: 2015-16 to 2022-23
|  | Substation Switchbays |  |  | 40.95% | 40.95% | 40.95% | 40.95% | 40.95% | 40.95% | 40.95% | 40.95%
|  | Substation Power Transformers |  |  | 32.88% | 32.88% | 32.88% | 32.88% | 32.88% | 32.88% | 32.88% | 32.88%
Substation Reactive Plant | bar: 2015-16 to 2022-23
|  | Scada Network Control And Protection Systems |  |  | 13.4% | 13.4% | 13.4% | 13.4% | 13.4% | 13.4% | 13.4% | 13.4%
|  | Other |  |  | 11.35% | 11.35% | 11.35% | 11.35% | 11.35% | 11.35% | 11.35% | 11.35%
|  | Total |  |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
| Direct Expenditures | Materials - $ Mar 2017 |  |  | 2015-16 | 2016-17 | 2017-18 | 2018-19 | 2019-20 | 2020-21 | 2021-22 | 2022-23 | Total | 2017-22 Total
| (As Incurred) | Transmission Towers |  |  | -0.096987 | 0 | 0 | 0 | 1.6741 | 21.757 | 36.8177 | 0 | 60.1518 | 60.2488
|  | Transmission Tower Support Structures |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Conductors |  |  | -0.096987 | 0 | 0 | 0 | 1.6741 | 21.757 | 36.8177 | 0 | 60.1518 | 60.2488
|  | Transmission Cables |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Substation Switchbays |  |  | -5.6072 | 0 | 0 | 0 | 96.7836 | 1257.8532 | 2128.5722 | 0 | 3477.6018 | 3483.209
|  | Substation Power Transformers |  |  | -4.502 | 0 | 0 | 0 | 77.7073 | 1009.9268 | 1709.0245 | 0 | 2792.1566 | 2796.6586
|  | Substation Reactive Plant |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Scada Network Control And Protection Systems |  |  | -1.8342 | 0 | 0 | 0 | 31.6597 | 411.4671 | 696.2954 | 0 | 1137.588 | 1139.4222
|  | Other |  |  | -1.5546 | 0 | 0 | 0 | 26.8329 | 348.7359 | 590.1401 | 0 | 964.1544 | 965.709
|  | Total Materials |  |  | -13.6919 | 0 | 0 | 0 | 236.3316 | 3071.497 | 5197.6677 | 0 | 8491.8043 | 8505.4962
|  | Labour (Internal) - $ Mar 2017 |  |  | 2015-16 | 2016-17 | 2017-18 | 2018-19 | 2019-20 | 2020-21 | 2021-22 | 2022-23 | Total | 2017-22 Total
|  | Transmission Towers |  |  | -0.024247 | 0 | 0 | 0 | 0.43419 | 5.6934 | 9.7222 | 0 | 15.8256 | 15.8499
|  | Transmission Tower Support Structures |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Conductors |  |  | -0.024247 | 0 | 0 | 0 | 0.43419 | 5.6934 | 9.7222 | 0 | 15.8256 | 15.8499
|  | Transmission Cables |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Substation Switchbays |  |  | -1.4018 | 0 | 0 | 0 | 25.1019 | 329.1586 | 562.0797 | 0 | 914.9384 | 916.3402
|  | Substation Power Transformers |  |  | -1.1255 | 0 | 0 | 0 | 20.1543 | 264.2805 | 451.2922 | 0 | 734.6015 | 735.727
|  | Substation Reactive Plant |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Scada Network Control And Protection Systems |  |  | -0.45855 | 0 | 0 | 0 | 8.2113 | 107.6739 | 183.8667 | 0 | 299.2933 | 299.7519
|  | Other |  |  | -0.38864 | 0 | 0 | 0 | 6.9594 | 91.2582 | 155.8349 | 0 | 253.6639 | 254.0525
|  | Total Internal Labour |  |  | -3.423 | 0 | 0 | 0 | 61.2953 | 803.7581 | 1372.5178 | 0 | 2234.1483 | 2237.5713
|  | Labour (External) - $ Mar 2017 |  |  | 2015-16 | 2016-17 | 2017-18 | 2018-19 | 2019-20 | 2020-21 | 2021-22 | 2022-23 | Total | 2017-22 Total
|  | Transmission Towers |  |  | -0.12123 | 0 | 0 | 0 | 2.181 | 28.6551 | 49.0316 | 0 | 79.7465 | 79.8677
|  | Transmission Tower Support Structures |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Conductors |  |  | -0.12123 | 0 | 0 | 0 | 2.181 | 28.6551 | 49.0316 | 0 | 79.7465 | 79.8677
|  | Transmission Cables |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Substation Switchbays |  |  | -7.009 | 0 | 0 | 0 | 126.0946 | 1656.6591 | 2834.7003 | 0 | 4610.4451 | 4617.4541
|  | Substation Power Transformers |  |  | -5.6275 | 0 | 0 | 0 | 101.241 | 1330.1269 | 2275.9728 | 0 | 3701.7132 | 3707.3407
|  | Substation Reactive Plant |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Scada Network Control And Protection Systems |  |  | -2.2928 | 0 | 0 | 0 | 41.2479 | 541.9239 | 927.283 | 0 | 1508.162 | 1510.4547
|  | Other |  |  | -1.9432 | 0 | 0 | 0 | 34.9593 | 459.3036 | 785.9119 | 0 | 1278.2317 | 1280.1749
|  | Total External Labour |  |  | -17.1149 | 0 | 0 | 0 | 307.905 | 4045.3237 | 6921.9312 | 0 | 11258.045 | 11275.1599
|  | Total Direct - $ Mar 2017 |  |  | 2015-16 | 2016-17 | 2017-18 | 2018-19 | 2019-20 | 2020-21 | 2021-22 | 2022-23 | Total | 2017-22 Total
|  | Transmission Towers |  |  | -0.24247 | 0 | 0 | 0 | 4.2893 | 56.1055 | 95.5716 | 0 | 155.7239 | 155.9664
|  | Transmission Tower Support Structures |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Conductors |  |  | -0.24247 | 0 | 0 | 0 | 4.2893 | 56.1055 | 95.5716 | 0 | 155.7239 | 155.9664
|  | Transmission Cables |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Substation Switchbays |  |  | -14.018 | 0 | 0 | 0 | 247.9801 | 3243.671 | 5525.3522 | 0 | 9002.9854 | 9017.0033
|  | Substation Power Transformers |  |  | -11.255 | 0 | 0 | 0 | 199.1026 | 2604.3342 | 4436.2895 | 0 | 7228.4713 | 7239.7262
|  | Substation Reactive Plant |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Scada Network Control And Protection Systems |  |  | -4.5855 | 0 | 0 | 0 | 81.1189 | 1061.0649 | 1807.445 | 0 | 2945.0432 | 2949.6288
|  | Other |  |  | -3.8864 | 0 | 0 | 0 | 68.7517 | 899.2978 | 1531.8869 | 0 | 2496.0499 | 2499.9364
|  | Total Direct - $ Mar 2017 |  |  | -34.2298 | 0 | 0 | 0 | 605.5319 | 7920.5788 | 13492.1167 | 0 | 21983.9976 | 22018.2275

## Proj_9
Go To: | Table of Contents
Master Inputs
|  | XB61 |  | Business case? | 0
| Project name | SVTS Redevelopment Stage 1
| Project category 1 | Network |  |  | Shaded cells = Inputs
| Project category 2 | Replacement - Major Station
| Regulatory classification | Prescribed
| Overhead Category | Repex_OHD |  | $000's | $000's | $000's | $000's | $000's | $000's | $000's | $000's | $000's | Project | 2017-22
|  |  |  | Prior | 2015-16 | 2016-17 | 2017-18 | 2018-19 | 2019-20 | 2020-21 | 2021-22 | 2022-23 | Total | Total | Check
| Project timing | Direct Expenditure (As incurred) - $ 2015/16 |  | 166.1534 | 25.8698 | 369.7401 | 1307 | 7841 | 16988 | 20908 | 17968 | 0 | 65573.7633 | 65012 | ok
| (excluding real cost escalators) | Assumed year commissioned (no BC) | bar: 2015-16 to 2022-23
|  | Direct Expenditure (As Commissioned) - $ 2015/16 |  | 0 | 0 | 0 | 0 | 0 | 26697.7633 | 20908 | 17968 | 0 | 65573.7633 | 65573.7633 | ok
| Asset class | Secondary |  | 13.06% | 13.06% | 13.06% | 13.06% | 13.06% | 13.06% | 13.06% | 13.06% | 13.06%
|  | Switchgear |  | 40.95% | 40.95% | 40.95% | 40.95% | 40.95% | 40.95% | 40.95% | 40.95% | 40.95%
|  | Transformers |  | 32.88% | 32.88% | 32.88% | 32.88% | 32.88% | 32.88% | 32.88% | 32.88% | 32.88%
|  | Reactive |  | 0% | bar: 2015-16 to 2022-23
|  | Lines and towers |  | 1.417% | 1.417% | 1.417% | 1.417% | 1.417% | 1.417% | 1.417% | 1.417% | 1.417%
|  | Establishment |  | 11.35% | 11.35% | 11.35% | 11.35% | 11.35% | 11.35% | 11.35% | 11.35% | 11.35%
|  | Communications |  | 0.333% | 0.333% | 0.333% | 0.333% | 0.333% | 0.333% | 0.333% | 0.333% | 0.333%
Non System
Land
Easements
|  |  | Total | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
| Input costs % | Labour - internal |  | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10%
|  | Labour - external |  | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50%
|  | Materials |  | 40% | 40% | 40% | 40% | 40% | 40% | 40% | 40% | 40%
|  |  | Total | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
Material Escalation
| (By Asset Class) | Secondary |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Switchgear |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Transformers |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Reactive |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Lines and towers |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Establishment |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Communications |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Non System |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Land |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Easements |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Total Material escalation |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Labour Escalation | Internal Labour |  | 0 | 0 | 0.46268 | 2.7009 | 22.6855 | 63.6138 | 97.7061 | 101.082 | 0 | 288.251 | 287.7883
|  | External Labour |  | 0 | 0 | 1.9878 | 13.8795 | 125.0057 | 359.138 | 560.776 | 587.4669 | 0 | 1648.2538 | 1646.266
|  | Total Labour Escalation |  | 0 | 0 | 2.4504 | 16.5804 | 147.6911 | 422.7518 | 658.4821 | 688.549 | 0 | 1936.5047 | 1934.0543
|  | Total Escalation |  | 0 | 0 | 2.4504 | 16.5804 | 147.6911 | 422.7518 | 658.4821 | 688.549 | 0 | 1936.5047 | 1934.0543
|  | Escalation factors |  | 0 | 0 | 0.0066275 | 0.012686 | 0.018836 | 0.024885 | 0.031494 | 0.038321 | 0 | 0.029532 | 0.029749
| Direct Expenditure (Escalated) | Total labour - internal |  | 16.8964 | 2.6307 | 38.07 | 135.6576 | 820.4341 | 1792.2291 | 2225.5297 | 1929.9891 | 0 | 6961.4368 | 6903.8396
| (as incurred) | Total labour - external |  | 84.4821 | 13.1537 | 190.0189 | 678.6698 | 4113.9447 | 9002.9091 | 11201.1162 | 9733.3902 | 0 | 35017.6847 | 34730.0299
|  | Total materials |  | 67.5857 | 10.523 | 150.398 | 531.6444 | 3189.4594 | 6910.1564 | 8504.6827 | 7308.788 | 0 | 26673.2375 | 26444.7308
|  | Total Direct - As Incurred $ Mar 2017 |  | 168.9643 | 26.3075 | 378.4869 | 1345.9717 | 8123.8382 | 17705.2946 | 21931.3286 | 18972.1673 | 0 | 68652.359 | 68078.6003 | ok
| Capitalised Overheads | Overhead rate (applied to direct expenditure) |  | 8.008% | 8.425% | 7.259% | 7.658% | 9.013% | 8.969% | 7.948% | 8.001% | 8.318%
|  | Total overhead (as incurred) |  | 13.5309 | 2.2165 | 27.4758 | 103.0724 | 732.2268 | 1587.9128 | 1743.1585 | 1518.0437 | 0 | 5727.6373 | 5684.4142
|  | Total incl Overhead - As Incurred $ Mar 2017 |  | 182.4952 | 28.5239 | 405.9627 | 1449.0442 | 8856.065 | 19293.2073 | 23674.487 | 20490.211 | 0 | 74379.9963 | 73763.0145
|  | Total overheads (As incurred) - Cumulative |  | 13.5309 | 15.7474 | 43.2232 | 146.2956 | 878.5224 | 2466.4352 | 4209.5936 | 5727.6373 | 5727.6373
|  | Labour & Material Escalation - Cumulative |  | 0 | 0 | 2.4504 | 19.0308 | 166.7219 | 589.4737 | 1247.9558 | 1936.5047 | 1936.5047
Expenditure By Asset Class - As Incurred
| Asset class breakdown | Secondary |  | 23.8399 | 3.7262 | 53.0322 | 189.2932 | 1156.8959 | 2520.333 | 3092.6735 | 2676.7014 | 0 | 9716.4955 | 9635.8972
| (fully absorbed) | Switchgear |  | 74.7363 | 11.6812 | 166.2517 | 593.4191 | 3626.7755 | 7901.0408 | 9695.2822 | 8391.2431 | 0 | 30460.4299 | 30207.7607
| (as incurred) | Transformers |  | 60.0055 | 9.3788 | 133.483 | 476.4545 | 2911.9277 | 6343.7232 | 7784.3144 | 6737.3052 | 0 | 24456.5923 | 24253.7249
|  | Reactive |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Lines and towers |  | 2.5854 | 0.4041 | 5.7513 | 20.5286 | 125.4641 | 273.3273 | 335.397 | 290.2853 | 0 | 1053.7432 | 1045.0024
|  | Establishment |  | 20.7204 | 3.2386 | 46.0928 | 164.5236 | 1005.5123 | 2190.5392 | 2687.9871 | 2326.4463 | 0 | 8445.0603 | 8375.0085
|  | Communications |  | 0.60768 | 0.094981 | 1.3518 | 4.8251 | 29.4895 | 64.2437 | 78.8328 | 68.2296 | 0 | 247.6752 | 245.6208
|  | Non System |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Land |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Easements |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Total incl Overhead - As Incurred $ Mar 2017 |  | 182.4952 | 28.5239 | 405.9627 | 1449.0442 | 8856.065 | 19293.2073 | 23674.487 | 20490.211 | 0 | 74379.9963 | 73763.0145
|  |  | Check | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| As Commissioned Capex | Direct Expenditure (As Commissioned) - $ 2015/16 |  | 0 | 0 | 0 | 0 | 0 | 26697.7633 | 20908 | 17968 | 0 | 65573.7633 | 65573.7633
|  | Labour & Material Escalation - $ 2015/16 |  | 0 | 0 | 0 | 0 | 0 | 589.4737 | 658.4821 | 688.549 | 0 | 1936.5047 | 1936.5047
|  | Total Direct Expenditure - $ 2015/16 |  | 0 | 0 | 0 | 0 | 0 | 27287.237 | 21566.4821 | 18656.549 | 0 | 67510.268 | 67510.268
|  | Total Direct Expenditure - $ Mar 2017 |  | 0 | 0 | 0 | 0 | 0 | 27748.8632 | 21931.3286 | 18972.1673 | 0 | 68652.359 | 68652.359
|  | Total overheads (As Commissioned) |  | 0 | 0 | 0 | 0 | 0 | 2466.4352 | 1743.1585 | 1518.0437 | 0 | 5727.6373 | 5727.6373
|  | Total incl Overhead - As commissioned $ Mar 2017 |  | 0 | 0 | 0 | 0 | 0 | 30215.2983 | 23674.487 | 20490.211 | 0 | 74379.9963 | 74379.9963
|  | Total overheads (As Comm) - Cumulative |  | 0 | 0 | 0 | 0 | 0 | 2466.4352 | 4209.5936 | 5727.6373 | 5727.6373
|  | Total real cost escalation (As Comm) - Cumulative |  | 0 | 0 | 0 | 0 | 0 | 589.4737 | 1247.9558 | 1936.5047 | 1936.5047
Expenditure By Asset Class - As Commissioned
| Asset class breakdown | Secondary |  | 0 | 0 | 0 | 0 | 0 | 3947.1205 | 3092.6735 | 2676.7014 | 0 | 9716.4955 | 9716.4955
| (fully absorbed) | Switchgear |  | 0 | 0 | 0 | 0 | 0 | 12373.9045 | 9695.2822 | 8391.2431 | 0 | 30460.4299 | 30460.4299
| (as commissioned) | Transformers |  | 0 | 0 | 0 | 0 | 0 | 9934.9727 | 7784.3144 | 6737.3052 | 0 | 24456.5923 | 24456.5923
|  | Reactive |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Lines and towers |  | 0 | 0 | 0 | 0 | 0 | 428.0609 | 335.397 | 290.2853 | 0 | 1053.7432 | 1053.7432
|  | Establishment |  | 0 | 0 | 0 | 0 | 0 | 3430.6269 | 2687.9871 | 2326.4463 | 0 | 8445.0603 | 8445.0603
|  | Communications |  | 0 | 0 | 0 | 0 | 0 | 100.6128 | 78.8328 | 68.2296 | 0 | 247.6752 | 247.6752
|  | Non System |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Land |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Easements |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Total incl Overhead - As commissioned $ Mar 2017 |  | 0 | 0 | 0 | 0 | 0 | 30215.2983 | 23674.487 | 20490.211 | 0 | 74379.9963 | 74379.9963
|  |  | Check | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0
| Expenditure splits for RIN |  |  |  | 2015-16 | 2016-17 | 2017-18 | 2018-19 | 2019-20 | 2020-21 | 2021-22 | 2022-23
| Repex Category | Transmission Towers |  |  | 0.7084% | 0.7084% | 0.7084% | 0.7084% | 0.7084% | 0.7084% | 0.7084% | 0.7084%
Transmission Tower Support Structures | bar: 2015-16 to 2022-23
|  | Conductors |  |  | 0.7084% | 0.7084% | 0.7084% | 0.7084% | 0.7084% | 0.7084% | 0.7084% | 0.7084%
Transmission Cables | bar: 2015-16 to 2022-23
|  | Substation Switchbays |  |  | 40.95% | 40.95% | 40.95% | 40.95% | 40.95% | 40.95% | 40.95% | 40.95%
|  | Substation Power Transformers |  |  | 32.88% | 32.88% | 32.88% | 32.88% | 32.88% | 32.88% | 32.88% | 32.88%
Substation Reactive Plant | bar: 2015-16 to 2022-23
|  | Scada Network Control And Protection Systems |  |  | 13.4% | 13.4% | 13.4% | 13.4% | 13.4% | 13.4% | 13.4% | 13.4%
|  | Other |  |  | 11.35% | 11.35% | 11.35% | 11.35% | 11.35% | 11.35% | 11.35% | 11.35%
|  | Total |  |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
| Direct Expenditures | Materials - $ Mar 2017 |  |  | 2015-16 | 2016-17 | 2017-18 | 2018-19 | 2019-20 | 2020-21 | 2021-22 | 2022-23 | Total | 2017-22 Total
| (As Incurred) | Transmission Towers |  |  | 0.07454 | 1.0653 | 3.7659 | 22.5926 | 48.9482 | 60.243 | 51.7719 | 0 | 188.4615 | 187.3216
|  | Transmission Tower Support Structures |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Conductors |  |  | 0.07454 | 1.0653 | 3.7659 | 22.5926 | 48.9482 | 60.243 | 51.7719 | 0 | 188.4615 | 187.3216
|  | Transmission Cables |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Substation Switchbays |  |  | 4.3094 | 61.5917 | 217.7214 | 1306.1617 | 2829.8783 | 3482.8758 | 2993.1276 | 0 | 10895.6659 | 10829.7648
|  | Substation Power Transformers |  |  | 3.46 | 49.4518 | 174.8079 | 1048.7135 | 2272.1012 | 2796.3911 | 2403.1737 | 0 | 8748.0991 | 8695.1873
|  | Substation Reactive Plant |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Scada Network Control And Protection Systems |  |  | 1.4097 | 20.1478 | 71.2207 | 427.2697 | 925.7056 | 1139.3132 | 979.1075 | 0 | 3564.1741 | 3542.6166
|  | Other |  |  | 1.1948 | 17.0761 | 60.3626 | 362.1293 | 784.575 | 965.6166 | 829.8354 | 0 | 3020.7898 | 3002.5189
|  | Total Materials |  |  | 10.523 | 150.398 | 531.6444 | 3189.4594 | 6910.1564 | 8504.6827 | 7308.788 | 0 | 26605.6518 | 26444.7308
|  | Labour (Internal) - $ Mar 2017 |  |  | 2015-16 | 2016-17 | 2017-18 | 2018-19 | 2019-20 | 2020-21 | 2021-22 | 2022-23 | Total | 2017-22 Total
|  | Transmission Towers |  |  | 0.018635 | 0.26967 | 0.96093 | 5.8116 | 12.6953 | 15.7646 | 13.6711 | 0 | 49.1917 | 48.9034
|  | Transmission Tower Support Structures |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Conductors |  |  | 0.018635 | 0.26967 | 0.96093 | 5.8116 | 12.6953 | 15.7646 | 13.6711 | 0 | 49.1917 | 48.9034
|  | Transmission Cables |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Substation Switchbays |  |  | 1.0774 | 15.5906 | 55.5551 | 335.9879 | 733.9617 | 911.4089 | 790.3778 | 0 | 2843.9593 | 2827.2914
|  | Substation Power Transformers |  |  | 0.86501 | 12.5177 | 44.605 | 269.7637 | 589.2957 | 731.7676 | 634.5921 | 0 | 2283.4068 | 2270.0242
|  | Substation Reactive Plant |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Scada Network Control And Protection Systems |  |  | 0.35242 | 5.1 | 18.1731 | 109.9079 | 240.0925 | 298.1387 | 258.5472 | 0 | 930.3118 | 924.8594
|  | Other |  |  | 0.29869 | 4.3224 | 15.4025 | 93.1516 | 203.4886 | 252.6853 | 219.1298 | 0 | 788.479 | 783.8578
|  | Total Internal Labour |  |  | 2.6307 | 38.07 | 135.6576 | 820.4341 | 1792.2291 | 2225.5297 | 1929.9891 | 0 | 6944.5404 | 6903.8396
|  | Labour (External) - $ Mar 2017 |  |  | 2015-16 | 2016-17 | 2017-18 | 2018-19 | 2019-20 | 2020-21 | 2021-22 | 2022-23 | Total | 2017-22 Total
|  | Transmission Towers |  |  | 0.093175 | 1.346 | 4.8074 | 29.1412 | 63.7722 | 79.3432 | 68.9466 | 0 | 247.4498 | 246.0106
|  | Transmission Tower Support Structures |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Conductors |  |  | 0.093175 | 1.346 | 4.8074 | 29.1412 | 63.7722 | 79.3432 | 68.9466 | 0 | 247.4498 | 246.0106
|  | Transmission Cables |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Substation Switchbays |  |  | 5.3868 | 77.8174 | 277.9319 | 1684.7611 | 3686.9117 | 4587.1314 | 3986.0616 | 0 | 14306.0019 | 14222.7977
|  | Substation Power Transformers |  |  | 4.325 | 62.4794 | 223.1507 | 1352.6899 | 2960.2109 | 3682.9947 | 3200.3975 | 0 | 11486.2481 | 11419.4437
|  | Substation Reactive Plant |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Scada Network Control And Protection Systems |  |  | 1.7621 | 25.4555 | 90.9167 | 551.1165 | 1206.0571 | 1500.5356 | 1303.9146 | 0 | 4679.7582 | 4652.5405
|  | Other |  |  | 1.4935 | 21.5746 | 77.0558 | 467.0948 | 1022.1849 | 1271.768 | 1105.1233 | 0 | 3966.2949 | 3943.2268
|  | Total External Labour |  |  | 13.1537 | 190.0189 | 678.6698 | 4113.9447 | 9002.9091 | 11201.1162 | 9733.3902 | 0 | 34933.2025 | 34730.0299
|  | Total Direct - $ Mar 2017 |  |  | 2015-16 | 2016-17 | 2017-18 | 2018-19 | 2019-20 | 2020-21 | 2021-22 | 2022-23 | Total | 2017-22 Total
|  | Transmission Towers |  |  | 0.18635 | 2.681 | 9.5342 | 57.5453 | 125.4157 | 155.3508 | 134.3896 | 0 | 485.1029 | 482.2356
|  | Transmission Tower Support Structures |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Conductors |  |  | 0.18635 | 2.681 | 9.5342 | 57.5453 | 125.4157 | 155.3508 | 134.3896 | 0 | 485.1029 | 482.2356
|  | Transmission Cables |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Substation Switchbays |  |  | 10.7735 | 154.9997 | 551.2084 | 3326.9107 | 7250.7517 | 8981.4161 | 7769.5671 | 0 | 28045.6271 | 27879.8539
|  | Substation Power Transformers |  |  | 8.6501 | 124.4488 | 442.5636 | 2671.1671 | 5821.6078 | 7211.1534 | 6238.1632 | 0 | 22517.754 | 22384.6552
|  | Substation Reactive Plant |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Scada Network Control And Protection Systems |  |  | 3.5242 | 50.7033 | 180.3105 | 1088.2941 | 2371.8552 | 2937.9875 | 2541.5693 | 0 | 9174.244 | 9120.0165
|  | Other |  |  | 2.9869 | 42.9732 | 152.8208 | 922.3757 | 2010.2486 | 2490.0699 | 2154.0885 | 0 | 7775.5637 | 7729.6036
|  | Total Direct - $ Mar 2017 |  |  | 26.3075 | 378.4869 | 1345.9717 | 8123.8382 | 17705.2946 | 21931.3286 | 18972.1673 | 0 | 68483.3947 | 68078.6003

## Proj_10
Go To: | Table of Contents
Master Inputs
|  | XA14 |  | Business case? | Yes
| Project name | WMTS Redevelopment
| Project category 1 | Network |  |  | Shaded cells = Inputs
| Project category 2 | Replacement - Major Station CBD
| Regulatory classification | Prescribed
| Overhead Category | Repex_OHD |  | $000's | $000's | $000's | $000's | $000's | $000's | $000's | $000's | $000's | Project | 2017-22
|  |  |  | Prior | 2015-16 | 2016-17 | 2017-18 | 2018-19 | 2019-20 | 2020-21 | 2021-22 | 2022-23 | Total | Total | Check
| Project timing | Direct Expenditure (As incurred) - $ 2015/16 |  | 9758.7413 | 1215.0169 | 7285.5183 | 20885 | 21896 | 25995 | 16000 | 7148 | 0 | 110183.2765 | 91924 | ok
| (excluding real cost escalators) | Assumed year commissioned (no BC)
|  | Direct Expenditure (As Commissioned) - $ 2015/16 |  | 0 | 0 | 0 | 21802.8867 | 28779.8104 | 36628.8496 | 15878.1612 | 7093.5685 | 0 | 110183.2765 | 110183.2765 | ok
| Asset class | Secondary |  | 8.545% | 8.545% | 8.545% | 8.545% | 8.545% | 8.545% | 8.545% | 8.545% | 8.545%
|  | Switchgear |  | 49.85% | 49.85% | 49.85% | 49.85% | 49.85% | 49.85% | 49.85% | 49.85% | 49.85%
|  | Transformers |  | 16.1% | 16.1% | 16.1% | 16.1% | 16.1% | 16.1% | 16.1% | 16.1% | 16.1%
|  | Reactive |  | 0% | bar: 2015-16 to 2022-23
|  | Lines and towers |  | 0% | bar: 2015-16 to 2022-23
|  | Establishment |  | 25.51% | 25.51% | 25.51% | 25.51% | 25.51% | 25.51% | 25.51% | 25.51% | 25.51%
|  | Communications |  | 0% | bar: 2015-16 to 2022-23
Non System
Land
Easements
|  |  | Total | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
| Input costs % | Labour - internal |  | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10%
|  | Labour - external |  | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50%
|  | Materials |  | 40% | 40% | 40% | 40% | 40% | 40% | 40% | 40% | 40%
|  |  | Total | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
Material Escalation
| (By Asset Class) | Secondary |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Switchgear |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Transformers |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Reactive |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Lines and towers |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Establishment |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Communications |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Non System |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Land |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Easements |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Total Material escalation |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Labour Escalation | Internal Labour |  | 0 | 0 | 9.1169 | 43.1578 | 63.3493 | 97.3417 | 74.7703 | 40.2123 | 0 | 327.9483 | 318.8314
|  | External Labour |  | 0 | 0 | 39.1675 | 221.7853 | 349.0784 | 549.5521 | 429.1379 | 233.7051 | 0 | 1822.4264 | 1783.2589
|  | Total Labour Escalation |  | 0 | 0 | 48.2845 | 264.9431 | 412.4277 | 646.8938 | 503.9082 | 273.9174 | 0 | 2150.3747 | 2102.0902
|  | Total Escalation |  | 0 | 0 | 48.2845 | 264.9431 | 412.4277 | 646.8938 | 503.9082 | 273.9174 | 0 | 2150.3747 | 2102.0902
|  | Escalation factors |  | 0 | 0 | 0.0066275 | 0.012686 | 0.018836 | 0.024885 | 0.031494 | 0.038321 | 0 | 0.019516 | 0.022868
| Direct Expenditure (Escalated) | Total labour - internal |  | 992.3833 | 123.5572 | 750.1481 | 2167.7197 | 2291.0631 | 2742.4649 | 1703.1029 | 767.7851 | 0 | 11538.2242 | 9672.1357
| (as incurred) | Total labour - external |  | 4961.9164 | 617.7859 | 3744.2149 | 10844.6961 | 11488.1944 | 13776.2316 | 8571.7361 | 3872.1212 | 0 | 57876.8966 | 48552.9794
|  | Total materials |  | 3969.5331 | 494.2287 | 2963.5078 | 8495.3271 | 8906.5684 | 10573.906 | 6508.2707 | 2907.5699 | 0 | 44818.9117 | 37391.6421
|  | Total Direct - As Incurred $ Mar 2017 |  | 9923.8328 | 1235.5717 | 7457.8708 | 21507.7429 | 22685.8259 | 27092.6025 | 16783.1097 | 7547.4762 | 0 | 114234.0325 | 95616.7572 | ok
| Capitalised Overheads | Overhead rate (applied to direct expenditure) |  | 8.008% | 8.425% | 7.259% | 7.658% | 9.013% | 8.969% | 7.948% | 8.001% | 8.318%
|  | Total overhead (as incurred) |  | 794.7176 | 104.0992 | 541.3943 | 1647.0295 | 2044.7441 | 2429.8206 | 1333.9648 | 603.9056 | 0 | 9499.6757 | 8059.4646
|  | Total incl Overhead - As Incurred $ Mar 2017 |  | 10718.5504 | 1339.6709 | 7999.2652 | 23154.7724 | 24730.5699 | 29522.4231 | 18117.0745 | 8151.3818 | 0 | 123733.7082 | 103676.2217
|  | Total overheads (As incurred) - Cumulative |  | 794.7176 | 898.8168 | 1440.2111 | 3087.2406 | 5131.9847 | 7561.8053 | 8895.77 | 9499.6757 | 9499.6757
|  | Labour & Material Escalation - Cumulative |  | 0 | 0 | 48.2845 | 313.2276 | 725.6553 | 1372.5491 | 1876.4573 | 2150.3747 | 2150.3747
Expenditure By Asset Class - As Incurred
| Asset class breakdown | Secondary |  | 915.8472 | 114.4683 | 683.4977 | 1978.4609 | 2113.105 | 2522.5452 | 1548.0145 | 696.4953 | 0 | 10572.4341 | 8858.621
| (fully absorbed) | Switchgear |  | 5343.2887 | 667.8374 | 3987.7019 | 11542.8514 | 12328.3999 | 14717.1796 | 9031.516 | 4063.5333 | 0 | 61682.3083 | 51683.4803
| (as incurred) | Transformers |  | 1725.2133 | 215.6279 | 1287.5284 | 3726.8958 | 3980.5297 | 4751.8064 | 2916.0489 | 1312.0125 | 0 | 19915.6629 | 16687.2934
|  | Reactive |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Lines and towers |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Establishment |  | 2734.2012 | 341.7374 | 2040.5372 | 5906.5643 | 6308.5354 | 7530.892 | 4621.495 | 2079.3407 | 0 | 31563.303 | 26446.8272
|  | Communications |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Non System |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Land |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Easements |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Total incl Overhead - As Incurred $ Mar 2017 |  | 10718.5504 | 1339.6709 | 7999.2652 | 23154.7724 | 24730.57 | 29522.4232 | 18117.0745 | 8151.3818 | 0 | 123733.7083 | 103676.2218
|  |  | Check | 1.0719e-05 | 1.3397e-06 | 7.9993e-06 | 2.3155e-05 | 2.4731e-05 | 2.9522e-05 | 1.8117e-05 | 8.1514e-06 | 0 | 0.00012373 | 0.00010368
| As Commissioned Capex | Direct Expenditure (As Commissioned) - $ 2015/16 |  | 0 | 0 | 0 | 21802.8867 | 28779.8104 | 36628.8496 | 15878.1612 | 7093.5685 | 0 | 110183.2765 | 110183.2765
|  | Labour & Material Escalation - $ 2015/16 |  | 0 | 0 | 0 | 313.2276 | 288.1065 | 773.9947 | 502.1197 | 272.9261 | 0 | 2150.3747 | 2150.3747
|  | Total Direct Expenditure - $ 2015/16 |  | 0 | 0 | 0 | 22116.1143 | 29067.9169 | 37402.8444 | 16380.281 | 7366.4946 | 0 | 112333.6512 | 112333.6512
|  | Total Direct Expenditure - $ Mar 2017 |  | 0 | 0 | 0 | 22490.2591 | 29559.6674 | 38035.5993 | 16657.391 | 7491.1158 | 0 | 114234.0325 | 114234.0325
|  | Total overheads (As Commissioned) |  | 0 | 0 | 0 | 1730.4127 | 2522.347 | 3324.3603 | 1323.3495 | 599.2062 | 0 | 9499.6757 | 9499.6757
|  | Total incl Overhead - As commissioned $ Mar 2017 |  | 0 | 0 | 0 | 24220.6718 | 32082.0144 | 41359.9596 | 17980.7405 | 8090.322 | 0 | 123733.7082 | 123733.7082
|  | Total overheads (As Comm) - Cumulative |  | 0 | 0 | 0 | 1730.4127 | 4252.7597 | 7577.12 | 8900.4695 | 9499.6757 | 9499.6757
|  | Total real cost escalation (As Comm) - Cumulative |  | 0 | 0 | 0 | 313.2276 | 601.3341 | 1375.3289 | 1877.4486 | 2150.3747 | 2150.3747
Expenditure By Asset Class - As Commissioned
| Asset class breakdown | Secondary |  | 0 | 0 | 0 | 2069.5368 | 2741.2496 | 3534.0042 | 1536.3655 | 691.278 | 0 | 10572.4341 | 10572.4341
| (fully absorbed) | Switchgear |  | 0 | 0 | 0 | 12074.2113 | 15993.1577 | 20618.2924 | 8963.5524 | 4033.0945 | 0 | 61682.3083 | 61682.3083
| (as commissioned) | Transformers |  | 0 | 0 | 0 | 3898.4586 | 5163.7876 | 6657.127 | 2894.1052 | 1302.1846 | 0 | 19915.663 | 19915.663
|  | Reactive |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Lines and towers |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Establishment |  | 0 | 0 | 0 | 6178.4651 | 8183.8196 | 10550.536 | 4586.7175 | 2063.7649 | 0 | 31563.3031 | 31563.3031
|  | Communications |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Non System |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Land |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Easements |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Total incl Overhead - As commissioned $ Mar 2017 |  | 0 | 0 | 0 | 24220.6718 | 32082.0144 | 41359.9597 | 17980.7405 | 8090.322 | 0 | 123733.7085 | 123733.7085
|  |  | Check | 0 | 0 | 0 | 4.8441e-05 | 6.4164e-05 | 8.272e-05 | 3.5961e-05 | 1.6181e-05 | 0 | 0.00024747 | 0.00024747
0.00012373
| Expenditure splits for RIN |  |  |  | 2015-16 | 2016-17 | 2017-18 | 2018-19 | 2019-20 | 2020-21 | 2021-22 | 2022-23
| Repex Category | Transmission Towers | bar: 2015-16 to 2022-23
Transmission Tower Support Structures | bar: 2015-16 to 2022-23
Conductors | bar: 2015-16 to 2022-23
Transmission Cables | bar: 2015-16 to 2022-23
|  | Substation Switchbays |  |  | 49.85% | 49.85% | 49.85% | 49.85% | 49.85% | 49.85% | 49.85% | 49.85%
|  | Substation Power Transformers |  |  | 16.1% | 16.1% | 16.1% | 16.1% | 16.1% | 16.1% | 16.1% | 16.1%
Substation Reactive Plant | bar: 2015-16 to 2022-23
|  | Scada Network Control And Protection Systems |  |  | 8.545% | 8.545% | 8.545% | 8.545% | 8.545% | 8.545% | 8.545% | 8.545%
|  | Other |  |  | 25.51% | 25.51% | 25.51% | 25.51% | 25.51% | 25.51% | 25.51% | 25.51%
|  | Total |  |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
| Direct Expenditures | Materials - $ Mar 2017 |  |  | 2015-16 | 2016-17 | 2017-18 | 2018-19 | 2019-20 | 2020-21 | 2021-22 | 2022-23 | Total | 2017-22 Total
| (As Incurred) | Transmission Towers |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Transmission Tower Support Structures |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Conductors |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Transmission Cables |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Substation Switchbays |  |  | 246.3772 | 1477.3339 | 4234.993 | 4440.0003 | 5271.1823 | 3244.4284 | 1449.4484 | 0 | 20363.7634 | 18640.0523
|  | Substation Power Transformers |  |  | 79.549 | 476.9939 | 1367.3725 | 1433.5642 | 1701.9319 | 1047.5442 | 467.9904 | 0 | 6574.946 | 6018.4032
|  | Substation Reactive Plant |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Scada Network Control And Protection Systems |  |  | 42.2294 | 253.2171 | 725.8837 | 761.0223 | 903.488 | 556.0996 | 248.4375 | 0 | 3490.3776 | 3194.9311
|  | Other |  |  | 126.0731 | 755.9629 | 2167.0779 | 2271.9817 | 2697.3038 | 1660.1985 | 741.6937 | 0 | 10420.2916 | 9538.2556
|  | Total Materials |  |  | 494.2287 | 2963.5078 | 8495.3271 | 8906.5684 | 10573.906 | 6508.2707 | 2907.5699 | 0 | 40849.3786 | 37391.6421
|  | Labour (Internal) - $ Mar 2017 |  |  | 2015-16 | 2016-17 | 2017-18 | 2018-19 | 2019-20 | 2020-21 | 2021-22 | 2022-23 | Total | 2017-22 Total
|  | Transmission Towers |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Transmission Tower Support Structures |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Conductors |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Transmission Cables |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Substation Switchbays |  |  | 61.5943 | 373.9552 | 1080.6268 | 1142.1145 | 1367.1421 | 849.0113 | 382.7474 | 0 | 5257.1916 | 4821.6421
|  | Substation Power Transformers |  |  | 19.8872 | 120.7407 | 348.9071 | 368.76 | 441.4157 | 274.1244 | 123.5795 | 0 | 1697.4147 | 1556.7867
|  | Substation Reactive Plant |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Scada Network Control And Protection Systems |  |  | 10.5574 | 64.0965 | 185.2209 | 195.76 | 234.3301 | 145.5217 | 65.6034 | 0 | 901.09 | 826.4362
|  | Other |  |  | 31.5183 | 191.3557 | 552.9649 | 584.4286 | 699.577 | 434.4455 | 195.8547 | 0 | 2690.1447 | 2467.2707
|  | Total Internal Labour |  |  | 123.5572 | 750.1481 | 2167.7197 | 2291.0631 | 2742.4649 | 1703.1029 | 767.7851 | 0 | 10545.841 | 9672.1357
|  | Labour (External) - $ Mar 2017 |  |  | 2015-16 | 2016-17 | 2017-18 | 2018-19 | 2019-20 | 2020-21 | 2021-22 | 2022-23 | Total | 2017-22 Total
|  | Transmission Towers |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Transmission Tower Support Structures |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Conductors |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Transmission Cables |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Substation Switchbays |  |  | 307.9715 | 1866.523 | 5406.1735 | 5726.9628 | 6867.5689 | 4273.0835 | 1930.2854 | 0 | 26378.5687 | 24204.0741
|  | Substation Power Transformers |  |  | 99.4362 | 602.6533 | 1745.5172 | 1849.092 | 2217.3649 | 1379.671 | 623.2405 | 0 | 8516.9751 | 7814.8856
|  | Substation Reactive Plant |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Scada Network Control And Protection Systems |  |  | 52.7868 | 319.9247 | 926.6257 | 981.6095 | 1177.1109 | 732.4125 | 330.8536 | 0 | 4521.3237 | 4148.6122
|  | Other |  |  | 157.5914 | 955.1139 | 2766.3798 | 2930.5301 | 3514.1869 | 2186.5691 | 987.7416 | 0 | 13498.1128 | 12385.4075
|  | Total External Labour |  |  | 617.7859 | 3744.2149 | 10844.6961 | 11488.1944 | 13776.2316 | 8571.7361 | 3872.1212 | 0 | 52914.9802 | 48552.9795
|  | Total Direct - $ Mar 2017 |  |  | 2015-16 | 2016-17 | 2017-18 | 2018-19 | 2019-20 | 2020-21 | 2021-22 | 2022-23 | Total | 2017-22 Total
|  | Transmission Towers |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Transmission Tower Support Structures |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Conductors |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Transmission Cables |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Substation Switchbays |  |  | 615.943 | 3717.8122 | 10721.7932 | 11309.0776 | 13505.8933 | 8366.5232 | 3762.4812 | 0 | 51999.5237 | 47665.7685
|  | Substation Power Transformers |  |  | 198.8725 | 1200.3879 | 3461.7968 | 3651.4162 | 4360.7126 | 2701.3395 | 1214.8104 | 0 | 16789.3358 | 15390.0755
|  | Substation Reactive Plant |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Scada Network Control And Protection Systems |  |  | 105.5735 | 637.2382 | 1837.7304 | 1938.3918 | 2314.929 | 1434.0338 | 644.8946 | 0 | 8912.7913 | 8169.9796
|  | Other |  |  | 315.1827 | 1902.4326 | 5486.4226 | 5786.9404 | 6911.0676 | 4281.2131 | 1925.29 | 0 | 26608.549 | 24390.9338
|  | Total Direct - $ Mar 2017 |  |  | 1235.5717 | 7457.8708 | 21507.7429 | 22685.8259 | 27092.6026 | 16783.1097 | 7547.4762 | 0 | 104310.1999 | 95616.7573

## Proj_11
Go To: | Table of Contents
Master Inputs
|  | 284A |  | Business case? | 0
| Project name | HYTS 500kV and 275kV CB Replacement
| Project category 1 | Network |  |  | Shaded cells = Inputs
| Project category 2 | Replacement - Major Station
| Regulatory classification | Prescribed
| Overhead Category | Repex_OHD |  | $000's | $000's | $000's | $000's | $000's | $000's | $000's | $000's | $000's | Project | 2017-22
|  |  |  | Prior | 2015-16 | 2016-17 | 2017-18 | 2018-19 | 2019-20 | 2020-21 | 2021-22 | 2022-23 | Total | Total | Check
| Project timing | Direct Expenditure (As incurred) - $ 2015/16 |  | 0 | 27.0944 | 1800 | 3046 | 1938 | 0 | 0 | 0 | 0 | 6811.0944 | 4984 | ok
| (excluding real cost escalators) | Assumed year commissioned (no BC) | bar: 2015-16 to 2022-23
|  | Direct Expenditure (As Commissioned) - $ 2015/16 |  | 0 | 0 | 0 | 4873.0944 | 1938 | 0 | 0 | 0 | 0 | 6811.0944 | 6811.0944 | ok
| Asset class | Secondary |  | 13.06% | 13.06% | 13.06% | 13.06% | 13.06% | 13.06% | 13.06% | 13.06% | 13.06%
|  | Switchgear |  | 40.95% | 40.95% | 40.95% | 40.95% | 40.95% | 40.95% | 40.95% | 40.95% | 40.95%
|  | Transformers |  | 32.88% | 32.88% | 32.88% | 32.88% | 32.88% | 32.88% | 32.88% | 32.88% | 32.88%
|  | Reactive |  | 0% | bar: 2015-16 to 2022-23
|  | Lines and towers |  | 1.417% | 1.417% | 1.417% | 1.417% | 1.417% | 1.417% | 1.417% | 1.417% | 1.417%
|  | Establishment |  | 11.35% | 11.35% | 11.35% | 11.35% | 11.35% | 11.35% | 11.35% | 11.35% | 11.35%
|  | Communications |  | 0.333% | 0.333% | 0.333% | 0.333% | 0.333% | 0.333% | 0.333% | 0.333% | 0.333%
Non System
Land
Easements
|  |  | Total | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
| Input costs % | Labour - internal |  | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10%
|  | Labour - external |  | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50%
|  | Materials |  | 40% | 40% | 40% | 40% | 40% | 40% | 40% | 40% | 40%
|  |  | Total | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
Material Escalation
| (By Asset Class) | Secondary |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Switchgear |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Transformers |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Reactive |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Lines and towers |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Establishment |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Communications |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Non System |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Land |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Easements |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Total Material escalation |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Labour Escalation | Internal Labour |  | 0 | 0 | 2.2525 | 6.2944 | 5.607 | 0 | 0 | 0 | 0 | 14.1539 | 11.9014
|  | External Labour |  | 0 | 0 | 9.6769 | 32.3466 | 30.8967 | 0 | 0 | 0 | 0 | 72.9202 | 63.2433
|  | Total Labour Escalation |  | 0 | 0 | 11.9294 | 38.641 | 36.5037 | 0 | 0 | 0 | 0 | 87.0741 | 75.1447
|  | Total Escalation |  | 0 | 0 | 11.9294 | 38.641 | 36.5037 | 0 | 0 | 0 | 0 | 87.0741 | 75.1447
|  | Escalation factors |  | 0 | 0 | 0.0066275 | 0.012686 | 0.018836 | 0 | 0 | 0 | 0 | 0.012784 | 0.015077
| Direct Expenditure (Escalated) | Total labour - internal |  | 0 | 2.7553 | 185.3357 | 316.1539 | 202.7804 | 0 | 0 | 0 | 0 | 707.0253 | 518.9343
| (as incurred) | Total labour - external |  | 0 | 13.7764 | 925.0662 | 1581.6588 | 1016.8122 | 0 | 0 | 0 | 0 | 3537.3136 | 2598.4711
|  | Total materials |  | 0 | 11.0211 | 732.1805 | 1239.012 | 788.3143 | 0 | 0 | 0 | 0 | 2770.5279 | 2027.3263
|  | Total Direct - As Incurred $ Mar 2017 |  | 0 | 27.5527 | 1842.5824 | 3136.8248 | 2007.9069 | 0 | 0 | 0 | 0 | 7014.8668 | 5144.7317 | ok
| Capitalised Overheads | Overhead rate (applied to direct expenditure) |  | 8.008% | 8.425% | 7.259% | 7.658% | 9.013% | 8.969% | 7.948% | 8.001% | 8.318%
|  | Total overhead (as incurred) |  | 0 | 2.3214 | 133.7598 | 240.2132 | 180.9789 | 0 | 0 | 0 | 0 | 557.2733 | 421.1921
|  | Total incl Overhead - As Incurred $ Mar 2017 |  | 0 | 29.8741 | 1976.3422 | 3377.0379 | 2188.8858 | 0 | 0 | 0 | 0 | 7572.1401 | 5565.9238
|  | Total overheads (As incurred) - Cumulative |  | 0 | 2.3214 | 136.0812 | 376.2944 | 557.2733 | 557.2733 | 557.2733 | 557.2733 | 557.2733
|  | Labour & Material Escalation - Cumulative |  | 0 | 0 | 11.9294 | 50.5704 | 87.0741 | 87.0741 | 87.0741 | 87.0741 | 87.0741
Expenditure By Asset Class - As Incurred
| Asset class breakdown | Secondary |  | 0 | 3.9025 | 258.1759 | 441.1532 | 285.9411 | 0 | 0 | 0 | 0 | 989.1727 | 727.0943
| (fully absorbed) | Switchgear |  | 0 | 12.2342 | 809.3605 | 1382.9797 | 896.4024 | 0 | 0 | 0 | 0 | 3100.9768 | 2279.3821
| (as incurred) | Transformers |  | 0 | 9.8228 | 649.8333 | 1110.3905 | 719.7189 | 0 | 0 | 0 | 0 | 2489.7654 | 1830.1094
|  | Reactive |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Lines and towers |  | 0 | 0.42323 | 27.9989 | 47.8426 | 31.01 | 0 | 0 | 0 | 0 | 107.2747 | 78.8526
|  | Establishment |  | 0 | 3.3919 | 224.3927 | 383.4269 | 248.5248 | 0 | 0 | 0 | 0 | 859.7363 | 631.9517
|  | Communications |  | 0 | 0.099477 | 6.581 | 11.2451 | 7.2887 | 0 | 0 | 0 | 0 | 25.2142 | 18.5338
|  | Non System |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Land |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Easements |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Total incl Overhead - As Incurred $ Mar 2017 |  | 0 | 29.8741 | 1976.3422 | 3377.0379 | 2188.8858 | 0 | 0 | 0 | 0 | 7572.1401 | 5565.9238
|  |  | Check | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| As Commissioned Capex | Direct Expenditure (As Commissioned) - $ 2015/16 |  | 0 | 0 | 0 | 4873.0944 | 1938 | 0 | 0 | 0 | 0 | 6811.0944 | 6811.0944
|  | Labour & Material Escalation - $ 2015/16 |  | 0 | 0 | 0 | 50.5704 | 36.5037 | 0 | 0 | 0 | 0 | 87.0741 | 87.0741
|  | Total Direct Expenditure - $ 2015/16 |  | 0 | 0 | 0 | 4923.6648 | 1974.5037 | 0 | 0 | 0 | 0 | 6898.1685 | 6898.1685
|  | Total Direct Expenditure - $ Mar 2017 |  | 0 | 0 | 0 | 5006.9599 | 2007.9069 | 0 | 0 | 0 | 0 | 7014.8668 | 7014.8668
|  | Total overheads (As Commissioned) |  | 0 | 0 | 0 | 376.2944 | 180.9789 | 0 | 0 | 0 | 0 | 557.2733 | 557.2733
|  | Total incl Overhead - As commissioned $ Mar 2017 |  | 0 | 0 | 0 | 5383.2542 | 2188.8858 | 0 | 0 | 0 | 0 | 7572.1401 | 7572.1401
|  | Total overheads (As Comm) - Cumulative |  | 0 | 0 | 0 | 376.2944 | 557.2733 | 557.2733 | 557.2733 | 557.2733 | 557.2733
|  | Total real cost escalation (As Comm) - Cumulative |  | 0 | 0 | 0 | 50.5704 | 87.0741 | 87.0741 | 87.0741 | 87.0741 | 87.0741
Expenditure By Asset Class - As Commissioned
| Asset class breakdown | Secondary |  | 0 | 0 | 0 | 703.2316 | 285.9411 | 0 | 0 | 0 | 0 | 989.1727 | 989.1727
| (fully absorbed) | Switchgear |  | 0 | 0 | 0 | 2204.5744 | 896.4024 | 0 | 0 | 0 | 0 | 3100.9768 | 3100.9768
| (as commissioned) | Transformers |  | 0 | 0 | 0 | 1770.0465 | 719.7189 | 0 | 0 | 0 | 0 | 2489.7654 | 2489.7654
|  | Reactive |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Lines and towers |  | 0 | 0 | 0 | 76.2647 | 31.01 | 0 | 0 | 0 | 0 | 107.2747 | 107.2747
|  | Establishment |  | 0 | 0 | 0 | 611.2115 | 248.5248 | 0 | 0 | 0 | 0 | 859.7363 | 859.7363
|  | Communications |  | 0 | 0 | 0 | 17.9255 | 7.2887 | 0 | 0 | 0 | 0 | 25.2142 | 25.2142
|  | Non System |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Land |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Easements |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Total incl Overhead - As commissioned $ Mar 2017 |  | 0 | 0 | 0 | 5383.2542 | 2188.8858 | 0 | 0 | 0 | 0 | 7572.1401 | 7572.1401
|  |  | Check | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0
| Expenditure splits for RIN |  |  |  | 2015-16 | 2016-17 | 2017-18 | 2018-19 | 2019-20 | 2020-21 | 2021-22 | 2022-23
| Repex Category | Transmission Towers |  |  | 0.7084% | 0.7084% | 0.7084% | 0.7084% | 0.7084% | 0.7084% | 0.7084% | 0.7084%
Transmission Tower Support Structures | bar: 2015-16 to 2022-23
|  | Conductors |  |  | 0.7084% | 0.7084% | 0.7084% | 0.7084% | 0.7084% | 0.7084% | 0.7084% | 0.7084%
Transmission Cables | bar: 2015-16 to 2022-23
|  | Substation Switchbays |  |  | 40.95% | 40.95% | 40.95% | 40.95% | 40.95% | 40.95% | 40.95% | 40.95%
|  | Substation Power Transformers |  |  | 32.88% | 32.88% | 32.88% | 32.88% | 32.88% | 32.88% | 32.88% | 32.88%
Substation Reactive Plant | bar: 2015-16 to 2022-23
|  | Scada Network Control And Protection Systems |  |  | 13.4% | 13.4% | 13.4% | 13.4% | 13.4% | 13.4% | 13.4% | 13.4%
|  | Other |  |  | 11.35% | 11.35% | 11.35% | 11.35% | 11.35% | 11.35% | 11.35% | 11.35%
|  | Total |  |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
| Direct Expenditures | Materials - $ Mar 2017 |  |  | 2015-16 | 2016-17 | 2017-18 | 2018-19 | 2019-20 | 2020-21 | 2021-22 | 2022-23 | Total | 2017-22 Total
| (As Incurred) | Transmission Towers |  |  | 0.078068 | 5.1864 | 8.7766 | 5.584 | 0 | 0 | 0 | 0 | 19.6251 | 14.3606
|  | Transmission Tower Support Structures |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Conductors |  |  | 0.078068 | 5.1864 | 8.7766 | 5.584 | 0 | 0 | 0 | 0 | 19.6251 | 14.3606
|  | Transmission Cables |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Substation Switchbays |  |  | 4.5134 | 299.8458 | 507.4058 | 322.834 | 0 | 0 | 0 | 0 | 1134.599 | 830.2398
|  | Substation Power Transformers |  |  | 3.6238 | 240.7454 | 407.3946 | 259.2025 | 0 | 0 | 0 | 0 | 910.9663 | 666.5971
|  | Substation Reactive Plant |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Scada Network Control And Protection Systems |  |  | 1.4764 | 98.0851 | 165.9818 | 105.605 | 0 | 0 | 0 | 0 | 371.1483 | 271.5868
|  | Other |  |  | 1.2513 | 83.1313 | 140.6767 | 89.5047 | 0 | 0 | 0 | 0 | 314.5641 | 230.1814
|  | Total Materials |  |  | 11.0211 | 732.1805 | 1239.012 | 788.3143 | 0 | 0 | 0 | 0 | 2770.5279 | 2027.3263
|  | Labour (Internal) - $ Mar 2017 |  |  | 2015-16 | 2016-17 | 2017-18 | 2018-19 | 2019-20 | 2020-21 | 2021-22 | 2022-23 | Total | 2017-22 Total
|  | Transmission Towers |  |  | 0.019517 | 1.3128 | 2.2395 | 1.4364 | 0 | 0 | 0 | 0 | 5.0082 | 3.6759
|  | Transmission Tower Support Structures |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Conductors |  |  | 0.019517 | 1.3128 | 2.2395 | 1.4364 | 0 | 0 | 0 | 0 | 5.0082 | 3.6759
|  | Transmission Cables |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Substation Switchbays |  |  | 1.1284 | 75.8995 | 129.4728 | 83.0436 | 0 | 0 | 0 | 0 | 289.5442 | 212.5163
|  | Substation Power Transformers |  |  | 0.90595 | 60.9395 | 103.9533 | 66.6754 | 0 | 0 | 0 | 0 | 232.4742 | 170.6287
|  | Substation Reactive Plant |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Scada Network Control And Protection Systems |  |  | 0.3691 | 24.8281 | 42.3529 | 27.1651 | 0 | 0 | 0 | 0 | 94.7153 | 69.518
|  | Other |  |  | 0.31283 | 21.0429 | 35.8959 | 23.0236 | 0 | 0 | 0 | 0 | 80.2752 | 58.9195
|  | Total Internal Labour |  |  | 2.7553 | 185.3357 | 316.1539 | 202.7804 | 0 | 0 | 0 | 0 | 707.0253 | 518.9343
|  | Labour (External) - $ Mar 2017 |  |  | 2015-16 | 2016-17 | 2017-18 | 2018-19 | 2019-20 | 2020-21 | 2021-22 | 2022-23 | Total | 2017-22 Total
|  | Transmission Towers |  |  | 0.097585 | 6.5527 | 11.2037 | 7.2026 | 0 | 0 | 0 | 0 | 25.0566 | 18.4063
|  | Transmission Tower Support Structures |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Conductors |  |  | 0.097585 | 6.5527 | 11.2037 | 7.2026 | 0 | 0 | 0 | 0 | 25.0566 | 18.4063
|  | Transmission Cables |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Substation Switchbays |  |  | 5.6418 | 378.8373 | 647.728 | 416.4095 | 0 | 0 | 0 | 0 | 1448.6166 | 1064.1375
|  | Substation Power Transformers |  |  | 4.5298 | 304.1674 | 520.059 | 334.334 | 0 | 0 | 0 | 0 | 1163.0901 | 854.393
|  | Substation Reactive Plant |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Scada Network Control And Protection Systems |  |  | 1.8455 | 123.9247 | 211.8838 | 136.2153 | 0 | 0 | 0 | 0 | 473.8693 | 348.0991
|  | Other |  |  | 1.5642 | 105.0315 | 179.5806 | 115.4483 | 0 | 0 | 0 | 0 | 401.6245 | 295.0288
|  | Total External Labour |  |  | 13.7764 | 925.0662 | 1581.6588 | 1016.8122 | 0 | 0 | 0 | 0 | 3537.3136 | 2598.4711
|  | Total Direct - $ Mar 2017 |  |  | 2015-16 | 2016-17 | 2017-18 | 2018-19 | 2019-20 | 2020-21 | 2021-22 | 2022-23 | Total | 2017-22 Total
|  | Transmission Towers |  |  | 0.19517 | 13.052 | 22.2197 | 14.223 | 0 | 0 | 0 | 0 | 49.6899 | 36.4428
|  | Transmission Tower Support Structures |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Conductors |  |  | 0.19517 | 13.052 | 22.2197 | 14.223 | 0 | 0 | 0 | 0 | 49.6899 | 36.4428
|  | Transmission Cables |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Substation Switchbays |  |  | 11.2835 | 754.5826 | 1284.6065 | 822.2871 | 0 | 0 | 0 | 0 | 2872.7597 | 2106.8936
|  | Substation Power Transformers |  |  | 9.0595 | 605.8522 | 1031.4069 | 660.2119 | 0 | 0 | 0 | 0 | 2306.5306 | 1691.6189
|  | Substation Reactive Plant |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Scada Network Control And Protection Systems |  |  | 3.691 | 246.8379 | 420.2186 | 268.9853 | 0 | 0 | 0 | 0 | 939.7329 | 689.2039
|  | Other |  |  | 3.1283 | 209.2057 | 356.1532 | 227.9766 | 0 | 0 | 0 | 0 | 796.4638 | 584.1298
|  | Total Direct - $ Mar 2017 |  |  | 27.5527 | 1842.5824 | 3136.8248 | 2007.9069 | 0 | 0 | 0 | 0 | 7014.8668 | 5144.7317

## Proj_12
Go To: | Table of Contents
Master Inputs
|  | 285A |  | Business case? | 0
| Project name | FBTS Transformer and Circuit Breaker Replacement
| Project category 1 | Network |  |  | Shaded cells = Inputs
| Project category 2 | Replacement - Major Station
| Regulatory classification | Prescribed
| Overhead Category | Repex_OHD |  | $000's | $000's | $000's | $000's | $000's | $000's | $000's | $000's | $000's | Project | 2017-22
|  |  |  | Prior | 2015-16 | 2016-17 | 2017-18 | 2018-19 | 2019-20 | 2020-21 | 2021-22 | 2022-23 | Total | Total | Check
| Project timing | Direct Expenditure (As incurred) - $ 2015/16 |  | 0 | 0 | 0 | 638 | 8289 | 14027 | 8926 | 0 | 0 | 31880 | 31880 | ok
| (excluding real cost escalators) | Assumed year commissioned (no BC) | bar: 2015-16 to 2022-23
|  | Direct Expenditure (As Commissioned) - $ 2015/16 |  | 0 | 0 | 0 | 0 | 0 | 22954 | 8926 | 0 | 0 | 31880 | 31880 | ok
| Asset class | Secondary |  | 13.06% | 13.06% | 13.06% | 13.06% | 13.06% | 13.06% | 13.06% | 13.06% | 13.06%
|  | Switchgear |  | 40.95% | 40.95% | 40.95% | 40.95% | 40.95% | 40.95% | 40.95% | 40.95% | 40.95%
|  | Transformers |  | 32.88% | 32.88% | 32.88% | 32.88% | 32.88% | 32.88% | 32.88% | 32.88% | 32.88%
|  | Reactive |  | 0% | bar: 2015-16 to 2022-23
|  | Lines and towers |  | 1.417% | 1.417% | 1.417% | 1.417% | 1.417% | 1.417% | 1.417% | 1.417% | 1.417%
|  | Establishment |  | 11.35% | 11.35% | 11.35% | 11.35% | 11.35% | 11.35% | 11.35% | 11.35% | 11.35%
|  | Communications |  | 0.333% | 0.333% | 0.333% | 0.333% | 0.333% | 0.333% | 0.333% | 0.333% | 0.333%
Non System
Land
Easements
|  |  | Total | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
| Input costs % | Labour - internal |  | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10%
|  | Labour - external |  | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50%
|  | Materials |  | 40% | 40% | 40% | 40% | 40% | 40% | 40% | 40% | 40%
|  |  | Total | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
Material Escalation
| (By Asset Class) | Secondary |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Switchgear |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Transformers |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Reactive |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Lines and towers |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Establishment |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Communications |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Non System |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Land |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Easements |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Total Material escalation |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Labour Escalation | Internal Labour |  | 0 | 0 | 0 | 1.3184 | 23.9816 | 52.5259 | 41.7125 | 0 | 0 | 119.5385 | 119.5385
|  | External Labour |  | 0 | 0 | 0 | 6.7752 | 132.1479 | 296.5404 | 239.4053 | 0 | 0 | 674.8688 | 674.8688
|  | Total Labour Escalation |  | 0 | 0 | 0 | 8.0935 | 156.1296 | 349.0663 | 281.1178 | 0 | 0 | 794.4073 | 794.4073
|  | Total Escalation |  | 0 | 0 | 0 | 8.0935 | 156.1296 | 349.0663 | 281.1178 | 0 | 0 | 794.4073 | 794.4073
|  | Escalation factors |  | 0 | 0 | 0 | 0.012686 | 0.018836 | 0.024885 | 0.031494 | 0 | 0 | 0.024919 | 0.024919
| Direct Expenditure (Escalated) | Total labour - internal |  | 0 | 0 | 0 | 66.22 | 867.3101 | 1479.8444 | 950.1185 | 0 | 0 | 3363.4931 | 3363.4931
| (as incurred) | Total labour - external |  | 0 | 0 | 0 | 331.2864 | 4348.9972 | 7433.7065 | 4781.9573 | 0 | 0 | 16895.9474 | 16895.9474
|  | Total materials |  | 0 | 0 | 0 | 259.5173 | 3371.691 | 5705.7195 | 3630.8015 | 0 | 0 | 12967.7293 | 12967.7293
|  | Total Direct - As Incurred $ Mar 2017 |  | 0 | 0 | 0 | 657.0237 | 8587.9983 | 14619.2705 | 9362.8773 | 0 | 0 | 33227.1698 | 33227.1698 | ok
| Capitalised Overheads | Overhead rate (applied to direct expenditure) |  | 8.008% | 8.425% | 7.259% | 7.658% | 9.013% | 8.969% | 7.948% | 8.001% | 8.318%
|  | Total overhead (as incurred) |  | 0 | 0 | 0 | 50.3139 | 774.063 | 1311.1404 | 744.1856 | 0 | 0 | 2879.7028 | 2879.7028
|  | Total incl Overhead - As Incurred $ Mar 2017 |  | 0 | 0 | 0 | 707.3376 | 9362.0613 | 15930.4108 | 10107.0629 | 0 | 0 | 36106.8726 | 36106.8726
|  | Total overheads (As incurred) - Cumulative |  | 0 | 0 | 0 | 50.3139 | 824.3769 | 2135.5172 | 2879.7028 | 2879.7028 | 2879.7028
|  | Labour & Material Escalation - Cumulative |  | 0 | 0 | 0 | 8.0935 | 164.2231 | 513.2895 | 794.4073 | 794.4073 | 794.4073
Expenditure By Asset Class - As Incurred
| Asset class breakdown | Secondary |  | 0 | 0 | 0 | 92.4018 | 1222.9958 | 2081.0402 | 1320.3178 | 0 | 0 | 4716.7556 | 4716.7556
| (fully absorbed) | Switchgear |  | 0 | 0 | 0 | 289.672 | 3833.9934 | 6523.8933 | 4139.0898 | 0 | 0 | 14786.6485 | 14786.6485
| (as incurred) | Transformers |  | 0 | 0 | 0 | 232.5769 | 3078.3023 | 5238.0153 | 3323.2634 | 0 | 0 | 11872.1579 | 11872.1579
|  | Reactive |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Lines and towers |  | 0 | 0 | 0 | 10.0209 | 132.6325 | 225.6865 | 143.187 | 0 | 0 | 511.5269 | 511.5269
|  | Establishment |  | 0 | 0 | 0 | 80.3107 | 1062.9628 | 1808.7293 | 1147.5499 | 0 | 0 | 4099.5527 | 4099.5527
|  | Communications |  | 0 | 0 | 0 | 2.3553 | 31.1744 | 53.0461 | 33.6551 | 0 | 0 | 120.231 | 120.231
|  | Non System |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Land |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Easements |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Total incl Overhead - As Incurred $ Mar 2017 |  | 0 | 0 | 0 | 707.3376 | 9362.0613 | 15930.4108 | 10107.0629 | 0 | 0 | 36106.8726 | 36106.8726
|  |  | Check | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| As Commissioned Capex | Direct Expenditure (As Commissioned) - $ 2015/16 |  | 0 | 0 | 0 | 0 | 0 | 22954 | 8926 | 0 | 0 | 31880 | 31880
|  | Labour & Material Escalation - $ 2015/16 |  | 0 | 0 | 0 | 0 | 0 | 513.2895 | 281.1178 | 0 | 0 | 794.4073 | 794.4073
|  | Total Direct Expenditure - $ 2015/16 |  | 0 | 0 | 0 | 0 | 0 | 23467.2895 | 9207.1178 | 0 | 0 | 32674.4073 | 32674.4073
|  | Total Direct Expenditure - $ Mar 2017 |  | 0 | 0 | 0 | 0 | 0 | 23864.2925 | 9362.8773 | 0 | 0 | 33227.1698 | 33227.1698
|  | Total overheads (As Commissioned) |  | 0 | 0 | 0 | 0 | 0 | 2135.5172 | 744.1856 | 0 | 0 | 2879.7028 | 2879.7028
|  | Total incl Overhead - As commissioned $ Mar 2017 |  | 0 | 0 | 0 | 0 | 0 | 25999.8097 | 10107.0629 | 0 | 0 | 36106.8726 | 36106.8726
|  | Total overheads (As Comm) - Cumulative |  | 0 | 0 | 0 | 0 | 0 | 2135.5172 | 2879.7028 | 2879.7028 | 2879.7028
|  | Total real cost escalation (As Comm) - Cumulative |  | 0 | 0 | 0 | 0 | 0 | 513.2895 | 794.4073 | 794.4073 | 794.4073
Expenditure By Asset Class - As Commissioned
| Asset class breakdown | Secondary |  | 0 | 0 | 0 | 0 | 0 | 3396.4378 | 1320.3178 | 0 | 0 | 4716.7556 | 4716.7556
| (fully absorbed) | Switchgear |  | 0 | 0 | 0 | 0 | 0 | 10647.5587 | 4139.0898 | 0 | 0 | 14786.6485 | 14786.6485
| (as commissioned) | Transformers |  | 0 | 0 | 0 | 0 | 0 | 8548.8945 | 3323.2634 | 0 | 0 | 11872.1579 | 11872.1579
|  | Reactive |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Lines and towers |  | 0 | 0 | 0 | 0 | 0 | 368.3399 | 143.187 | 0 | 0 | 511.5269 | 511.5269
|  | Establishment |  | 0 | 0 | 0 | 0 | 0 | 2952.0028 | 1147.5499 | 0 | 0 | 4099.5527 | 4099.5527
|  | Communications |  | 0 | 0 | 0 | 0 | 0 | 86.5758 | 33.6551 | 0 | 0 | 120.231 | 120.231
|  | Non System |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Land |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Easements |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Total incl Overhead - As commissioned $ Mar 2017 |  | 0 | 0 | 0 | 0 | 0 | 25999.8097 | 10107.0629 | 0 | 0 | 36106.8726 | 36106.8726
|  |  | Check | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0
| Expenditure splits for RIN |  |  |  | 2015-16 | 2016-17 | 2017-18 | 2018-19 | 2019-20 | 2020-21 | 2021-22 | 2022-23
| Repex Category | Transmission Towers |  |  | 0.7084% | 0.7084% | 0.7084% | 0.7084% | 0.7084% | 0.7084% | 0.7084% | 0.7084%
Transmission Tower Support Structures | bar: 2015-16 to 2022-23
|  | Conductors |  |  | 0.7084% | 0.7084% | 0.7084% | 0.7084% | 0.7084% | 0.7084% | 0.7084% | 0.7084%
Transmission Cables | bar: 2015-16 to 2022-23
|  | Substation Switchbays |  |  | 40.95% | 40.95% | 40.95% | 40.95% | 40.95% | 40.95% | 40.95% | 40.95%
|  | Substation Power Transformers |  |  | 32.88% | 32.88% | 32.88% | 32.88% | 32.88% | 32.88% | 32.88% | 32.88%
Substation Reactive Plant | bar: 2015-16 to 2022-23
|  | Scada Network Control And Protection Systems |  |  | 13.4% | 13.4% | 13.4% | 13.4% | 13.4% | 13.4% | 13.4% | 13.4%
|  | Other |  |  | 11.35% | 11.35% | 11.35% | 11.35% | 11.35% | 11.35% | 11.35% | 11.35%
|  | Total |  |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
| Direct Expenditures | Materials - $ Mar 2017 |  |  | 2015-16 | 2016-17 | 2017-18 | 2018-19 | 2019-20 | 2020-21 | 2021-22 | 2022-23 | Total | 2017-22 Total
| (As Incurred) | Transmission Towers |  |  | 0 | 0 | 1.8383 | 23.8834 | 40.4165 | 25.7188 | 0 | 0 | 91.8571 | 91.8571
|  | Transmission Tower Support Structures |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Conductors |  |  | 0 | 0 | 1.8383 | 23.8834 | 40.4165 | 25.7188 | 0 | 0 | 91.8571 | 91.8571
|  | Transmission Cables |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Substation Switchbays |  |  | 0 | 0 | 106.2787 | 1380.79 | 2336.6319 | 1486.9021 | 0 | 0 | 5310.6027 | 5310.6027
|  | Substation Power Transformers |  |  | 0 | 0 | 85.3309 | 1108.6324 | 1876.0751 | 1193.8295 | 0 | 0 | 4263.8678 | 4263.8678
|  | Substation Reactive Plant |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Scada Network Control And Protection Systems |  |  | 0 | 0 | 34.7657 | 451.682 | 764.3556 | 486.3932 | 0 | 0 | 1737.1965 | 1737.1965
|  | Other |  |  | 0 | 0 | 29.4654 | 382.8198 | 647.824 | 412.239 | 0 | 0 | 1472.3482 | 1472.3482
|  | Total Materials |  |  | 0 | 0 | 259.5173 | 3371.691 | 5705.7195 | 3630.8015 | 0 | 0 | 12967.7293 | 12967.7293
|  | Labour (Internal) - $ Mar 2017 |  |  | 2015-16 | 2016-17 | 2017-18 | 2018-19 | 2019-20 | 2020-21 | 2021-22 | 2022-23 | Total | 2017-22 Total
|  | Transmission Towers |  |  | 0 | 0 | 0.46907 | 6.1436 | 10.4825 | 6.7302 | 0 | 0 | 23.8253 | 23.8253
|  | Transmission Tower Support Structures |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Conductors |  |  | 0 | 0 | 0.46907 | 6.1436 | 10.4825 | 6.7302 | 0 | 0 | 23.8253 | 23.8253
|  | Transmission Cables |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Substation Switchbays |  |  | 0 | 0 | 27.1187 | 355.1847 | 606.0325 | 389.0968 | 0 | 0 | 1377.4328 | 1377.4328
|  | Substation Power Transformers |  |  | 0 | 0 | 21.7735 | 285.1768 | 486.5818 | 312.4047 | 0 | 0 | 1105.9368 | 1105.9368
|  | Substation Reactive Plant |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Scada Network Control And Protection Systems |  |  | 0 | 0 | 8.871 | 116.1875 | 198.2445 | 127.2808 | 0 | 0 | 450.5838 | 450.5838
|  | Other |  |  | 0 | 0 | 7.5186 | 98.4739 | 168.0206 | 107.8759 | 0 | 0 | 381.889 | 381.889
|  | Total Internal Labour |  |  | 0 | 0 | 66.22 | 867.3101 | 1479.8444 | 950.1185 | 0 | 0 | 3363.4931 | 3363.4931
|  | Labour (External) - $ Mar 2017 |  |  | 2015-16 | 2016-17 | 2017-18 | 2018-19 | 2019-20 | 2020-21 | 2021-22 | 2022-23 | Total | 2017-22 Total
|  | Transmission Towers |  |  | 0 | 0 | 2.3467 | 30.8062 | 52.6567 | 33.8731 | 0 | 0 | 119.6826 | 119.6826
|  | Transmission Tower Support Structures |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Conductors |  |  | 0 | 0 | 2.3467 | 30.8062 | 52.6567 | 33.8731 | 0 | 0 | 119.6826 | 119.6826
|  | Transmission Cables |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Substation Switchbays |  |  | 0 | 0 | 135.6699 | 1781.0209 | 3044.2848 | 1958.3286 | 0 | 0 | 6919.3042 | 6919.3042
|  | Substation Power Transformers |  |  | 0 | 0 | 108.929 | 1429.9766 | 2444.2476 | 1572.3365 | 0 | 0 | 5555.4896 | 5555.4896
|  | Substation Reactive Plant |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Scada Network Control And Protection Systems |  |  | 0 | 0 | 44.3801 | 582.6049 | 995.842 | 640.6056 | 0 | 0 | 2263.4325 | 2263.4325
|  | Other |  |  | 0 | 0 | 37.6141 | 493.7825 | 844.0186 | 542.9406 | 0 | 0 | 1918.3558 | 1918.3558
|  | Total External Labour |  |  | 0 | 0 | 331.2864 | 4348.9972 | 7433.7065 | 4781.9573 | 0 | 0 | 16895.9474 | 16895.9474
|  | Total Direct - $ Mar 2017 |  |  | 2015-16 | 2016-17 | 2017-18 | 2018-19 | 2019-20 | 2020-21 | 2021-22 | 2022-23 | Total | 2017-22 Total
|  | Transmission Towers |  |  | 0 | 0 | 4.654 | 60.8332 | 103.5558 | 66.3221 | 0 | 0 | 235.3651 | 235.3651
|  | Transmission Tower Support Structures |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Conductors |  |  | 0 | 0 | 4.654 | 60.8332 | 103.5558 | 66.3221 | 0 | 0 | 235.3651 | 235.3651
|  | Transmission Cables |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Substation Switchbays |  |  | 0 | 0 | 269.0673 | 3516.9956 | 5986.9492 | 3834.3275 | 0 | 0 | 13607.3397 | 13607.3397
|  | Substation Power Transformers |  |  | 0 | 0 | 216.0334 | 2823.7857 | 4806.9045 | 3078.5706 | 0 | 0 | 10925.2942 | 10925.2942
|  | Substation Reactive Plant |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Scada Network Control And Protection Systems |  |  | 0 | 0 | 88.0169 | 1150.4744 | 1958.442 | 1254.2795 | 0 | 0 | 4451.2128 | 4451.2128
|  | Other |  |  | 0 | 0 | 74.5981 | 975.0762 | 1659.8632 | 1063.0555 | 0 | 0 | 3772.593 | 3772.593
|  | Total Direct - $ Mar 2017 |  |  | 0 | 0 | 657.0237 | 8587.9983 | 14619.2705 | 9362.8773 | 0 | 0 | 33227.1698 | 33227.1698

## Proj_13
Go To: | Table of Contents
Master Inputs
|  | XB12 |  | Business case? | Yes
| Project name | Glenrowan Terminal Station Redevelopment Project
| Project category 1 | Network |  |  | Shaded cells = Inputs
| Project category 2 | Replacement - Major Station
| Regulatory classification | Prescribed
| Overhead Category | Repex_OHD |  | $000's | $000's | $000's | $000's | $000's | $000's | $000's | $000's | $000's | Project | 2017-22
|  |  |  | Prior | 2015-16 | 2016-17 | 2017-18 | 2018-19 | 2019-20 | 2020-21 | 2021-22 | 2022-23 | Total | Total | Check
| Project timing | Direct Expenditure (As incurred) - $ 2015/16 |  | 20257.0393 | 1585.6739 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21842.7131 | 0 | ok
| (excluding real cost escalators) | Assumed year commissioned (no BC)
|  | Direct Expenditure (As Commissioned) - $ 2015/16 |  | 19502.0864 | 1435.4784 | 905.1484 | 0 | 0 | 0 | 0 | 0 | 0 | 21842.7131 | 0 | ok
| Asset class | Secondary |  | 7.343% | 7.343% | 7.343% | 7.343% | 7.343% | 7.343% | 7.343% | 7.343% | 7.343%
|  | Switchgear |  | 39.13% | 39.13% | 39.13% | 39.13% | 39.13% | 39.13% | 39.13% | 39.13% | 39.13%
|  | Transformers |  | 29.04% | 29.04% | 29.04% | 29.04% | 29.04% | 29.04% | 29.04% | 29.04% | 29.04%
|  | Reactive |  | 0% | bar: 2015-16 to 2022-23
|  | Lines and towers |  | 0% | bar: 2015-16 to 2022-23
|  | Establishment |  | 24.15% | 24.15% | 24.15% | 24.15% | 24.15% | 24.15% | 24.15% | 24.15% | 24.15%
|  | Communications |  | 0.333% | 0.333% | 0.333% | 0.333% | 0.333% | 0.333% | 0.333% | 0.333% | 0.333%
Non System
Land
Easements
|  |  | Total | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
| Input costs % | Labour - internal |  | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10%
|  | Labour - external |  | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50%
|  | Materials |  | 40% | 40% | 40% | 40% | 40% | 40% | 40% | 40% | 40%
|  |  | Total | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
Material Escalation
| (By Asset Class) | Secondary |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Switchgear |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Transformers |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Reactive |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Lines and towers |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Establishment |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Communications |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Non System |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Land |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Easements |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Total Material escalation |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Labour Escalation | Internal Labour |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | External Labour |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Total Labour Escalation |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Total Escalation |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Escalation factors |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Direct Expenditure (Escalated) | Total labour - internal |  | 2059.9734 | 161.2499 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2221.2233 | 0
| (as incurred) | Total labour - external |  | 10299.8668 | 806.2496 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11106.1164 | 0
|  | Total materials |  | 8239.8934 | 644.9997 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8884.8931 | 0
|  | Total Direct - As Incurred $ Mar 2017 |  | 20599.7335 | 1612.4992 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22212.2327 | 0 | ok
| Capitalised Overheads | Overhead rate (applied to direct expenditure) |  | 8.008% | 8.425% | 7.259% | 7.658% | 9.013% | 8.969% | 7.948% | 8.001% | 8.318%
|  | Total overhead (as incurred) |  | 1649.6621 | 135.856 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1785.5181 | 0
|  | Total incl Overhead - As Incurred $ Mar 2017 |  | 22249.3956 | 1748.3552 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23997.7508 | 0
|  | Total overheads (As incurred) - Cumulative |  | 1649.6621 | 1785.5181 | 1785.5181 | 1785.5181 | 1785.5181 | 1785.5181 | 1785.5181 | 1785.5181 | 1785.5181
|  | Labour & Material Escalation - Cumulative |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Expenditure By Asset Class - As Incurred
| Asset class breakdown | Secondary |  | 1633.6917 | 128.3753 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1762.067 | 0
| (fully absorbed) | Switchgear |  | 8706.4421 | 684.1513 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9390.5934 | 0
| (as incurred) | Transformers |  | 6462.2346 | 507.8017 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6970.0363 | 0
|  | Reactive |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Lines and towers |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Establishment |  | 5372.9398 | 422.2051 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5795.1449 | 0
|  | Communications |  | 74.0875 | 5.8218 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 79.9092 | 0
|  | Non System |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Land |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Easements |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Total incl Overhead - As Incurred $ Mar 2017 |  | 22249.3956 | 1748.3552 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23997.7508 | 0
|  |  | Check | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| As Commissioned Capex | Direct Expenditure (As Commissioned) - $ 2015/16 |  | 19502.0864 | 1435.4784 | 905.1484 | 0 | 0 | 0 | 0 | 0 | 0 | 21842.7131 | 0
|  | Labour & Material Escalation - $ 2015/16 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Total Direct Expenditure - $ 2015/16 |  | 19502.0864 | 1435.4784 | 905.1484 | 0 | 0 | 0 | 0 | 0 | 0 | 21842.7131 | 0
|  | Total Direct Expenditure - $ Mar 2017 |  | 19832.0089 | 1459.7628 | 920.4611 | 0 | 0 | 0 | 0 | 0 | 0 | 22212.2327 | 0
|  | Total overheads (As Commissioned) |  | 1588.1814 | 123.346 | 73.9908 | 0 | 0 | 0 | 0 | 0 | 0 | 1785.5181 | 0
|  | Total incl Overhead - As commissioned $ Mar 2017 |  | 21420.1903 | 1583.1087 | 994.4518 | 0 | 0 | 0 | 0 | 0 | 0 | 23997.7508 | 0
|  | Total overheads (As Comm) - Cumulative |  | 1588.1814 | 1711.5273 | 1785.5181 | 1785.5181 | 1785.5181 | 1785.5181 | 1785.5181 | 1785.5181 | 1785.5181
|  | Total real cost escalation (As Comm) - Cumulative |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Expenditure By Asset Class - As Commissioned
| Asset class breakdown | Secondary |  | 1572.8062 | 116.2419 | 73.019 | 0 | 0 | 0 | 0 | 0 | 0 | 1762.067 | 0
| (fully absorbed) | Switchgear |  | 8381.9646 | 619.4885 | 389.1403 | 0 | 0 | 0 | 0 | 0 | 0 | 9390.5934 | 0
| (as commissioned) | Transformers |  | 6221.3957 | 459.8067 | 288.834 | 0 | 0 | 0 | 0 | 0 | 0 | 6970.0363 | 0
|  | Reactive |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Lines and towers |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Establishment |  | 5172.6975 | 382.3002 | 240.1472 | 0 | 0 | 0 | 0 | 0 | 0 | 5795.1449 | 0
|  | Communications |  | 71.3263 | 5.2715 | 3.3114 | 0 | 0 | 0 | 0 | 0 | 0 | 79.9092 | 0
|  | Non System |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Land |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Easements |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Total incl Overhead - As commissioned $ Mar 2017 |  | 21420.1903 | 1583.1087 | 994.4518 | 0 | 0 | 0 | 0 | 0 | 0 | 23997.7508 | 0
|  |  | Check | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0
| Expenditure splits for RIN |  |  |  | 2015-16 | 2016-17 | 2017-18 | 2018-19 | 2019-20 | 2020-21 | 2021-22 | 2022-23
| Repex Category | Transmission Towers | bar: 2015-16 to 2022-23
Transmission Tower Support Structures | bar: 2015-16 to 2022-23
Conductors | bar: 2015-16 to 2022-23
Transmission Cables | bar: 2015-16 to 2022-23
|  | Substation Switchbays |  |  | 39.13% | 39.13% | 39.13% | 39.13% | 39.13% | 39.13% | 39.13% | 39.13%
|  | Substation Power Transformers |  |  | 29.04% | 29.04% | 29.04% | 29.04% | 29.04% | 29.04% | 29.04% | 29.04%
Substation Reactive Plant | bar: 2015-16 to 2022-23
|  | Scada Network Control And Protection Systems |  |  | 7.676% | 7.676% | 7.676% | 7.676% | 7.676% | 7.676% | 7.676% | 7.676%
|  | Other |  |  | 24.15% | 24.15% | 24.15% | 24.15% | 24.15% | 24.15% | 24.15% | 24.15%
|  | Total |  |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
| Direct Expenditures | Materials - $ Mar 2017 |  |  | 2015-16 | 2016-17 | 2017-18 | 2018-19 | 2019-20 | 2020-21 | 2021-22 | 2022-23 | Total | 2017-22 Total
| (As Incurred) | Transmission Towers |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Transmission Tower Support Structures |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Conductors |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Transmission Cables |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Substation Switchbays |  |  | 252.3957 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 252.3957 | 0
|  | Substation Power Transformers |  |  | 187.3372 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 187.3372 | 0
|  | Substation Reactive Plant |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Scada Network Control And Protection Systems |  |  | 49.5077 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 49.5077 | 0
|  | Other |  |  | 155.759 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 155.759 | 0
|  | Total Materials |  |  | 644.9997 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 644.9997 | 0
|  | Labour (Internal) - $ Mar 2017 |  |  | 2015-16 | 2016-17 | 2017-18 | 2018-19 | 2019-20 | 2020-21 | 2021-22 | 2022-23 | Total | 2017-22 Total
|  | Transmission Towers |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Transmission Tower Support Structures |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Conductors |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Transmission Cables |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Substation Switchbays |  |  | 63.0989 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 63.0989 | 0
|  | Substation Power Transformers |  |  | 46.8343 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 46.8343 | 0
|  | Substation Reactive Plant |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Scada Network Control And Protection Systems |  |  | 12.3769 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12.3769 | 0
|  | Other |  |  | 38.9398 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 38.9398 | 0
|  | Total Internal Labour |  |  | 161.2499 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 161.2499 | 0
|  | Labour (External) - $ Mar 2017 |  |  | 2015-16 | 2016-17 | 2017-18 | 2018-19 | 2019-20 | 2020-21 | 2021-22 | 2022-23 | Total | 2017-22 Total
|  | Transmission Towers |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Transmission Tower Support Structures |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Conductors |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Transmission Cables |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Substation Switchbays |  |  | 315.4947 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 315.4947 | 0
|  | Substation Power Transformers |  |  | 234.1715 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 234.1715 | 0
|  | Substation Reactive Plant |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Scada Network Control And Protection Systems |  |  | 61.8847 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 61.8847 | 0
|  | Other |  |  | 194.6988 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 194.6988 | 0
|  | Total External Labour |  |  | 806.2496 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 806.2496 | 0
|  | Total Direct - $ Mar 2017 |  |  | 2015-16 | 2016-17 | 2017-18 | 2018-19 | 2019-20 | 2020-21 | 2021-22 | 2022-23 | Total | 2017-22 Total
|  | Transmission Towers |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Transmission Tower Support Structures |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Conductors |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Transmission Cables |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Substation Switchbays |  |  | 630.9893 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 630.9893 | 0
|  | Substation Power Transformers |  |  | 468.343 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 468.343 | 0
|  | Substation Reactive Plant |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Scada Network Control And Protection Systems |  |  | 123.7693 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 123.7693 | 0
|  | Other |  |  | 389.3976 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 389.3976 | 0
|  | Total Direct - $ Mar 2017 |  |  | 1612.4992 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1612.4992 | 0

## Proj_14
Go To: | Table of Contents
Master Inputs
|  | XB54 |  | Business case? | Yes
| Project name | Ringwood Terminal Station (RWTS) 220kV Circuit Breaker Replacements
| Project category 1 | Network |  |  | Shaded cells = Inputs
| Project category 2 | Replacement - Major Station
| Regulatory classification | Prescribed
| Overhead Category | Repex_OHD |  | $000's | $000's | $000's | $000's | $000's | $000's | $000's | $000's | $000's | Project | 2017-22
|  |  |  | Prior | 2015-16 | 2016-17 | 2017-18 | 2018-19 | 2019-20 | 2020-21 | 2021-22 | 2022-23 | Total | Total | Check
| Project timing | Direct Expenditure (As incurred) - $ 2015/16 |  | 13212.3638 | 399.4162 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13611.78 | 0 | ok
| (excluding real cost escalators) | Assumed year commissioned (no BC)
|  | Direct Expenditure (As Commissioned) - $ 2015/16 |  | 12971.8516 | 430.1323 | 209.796 | 0 | 0 | 0 | 0 | 0 | 0 | 13611.78 | 0 | ok
| Asset class | Secondary
|  | Switchgear |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
Transformers
Reactive
Lines and towers
Establishment
Communications
Non System
Land
Easements
|  |  | Total | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
| Input costs % | Labour - internal |  | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10%
|  | Labour - external |  | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50%
|  | Materials |  | 40% | 40% | 40% | 40% | 40% | 40% | 40% | 40% | 40%
|  |  | Total | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
Material Escalation
| (By Asset Class) | Secondary |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Switchgear |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Transformers |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Reactive |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Lines and towers |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Establishment |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Communications |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Non System |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Land |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Easements |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Total Material escalation |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Labour Escalation | Internal Labour |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | External Labour |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Total Labour Escalation |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Total Escalation |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Escalation factors |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Direct Expenditure (Escalated) | Total labour - internal |  | 1343.5881 | 40.6173 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1384.2054 | 0
| (as incurred) | Total labour - external |  | 6717.9406 | 203.0866 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6921.0272 | 0
|  | Total materials |  | 5374.3525 | 162.4693 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5536.8218 | 0
|  | Total Direct - As Incurred $ Mar 2017 |  | 13435.8812 | 406.1732 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13842.0544 | 0 | ok
| Capitalised Overheads | Overhead rate (applied to direct expenditure) |  | 8.008% | 8.425% | 7.259% | 7.658% | 9.013% | 8.969% | 7.948% | 8.001% | 8.318%
|  | Total overhead (as incurred) |  | 1075.9685 | 34.2208 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1110.1893 | 0
|  | Total incl Overhead - As Incurred $ Mar 2017 |  | 14511.8497 | 440.3941 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14952.2437 | 0
|  | Total overheads (As incurred) - Cumulative |  | 1075.9685 | 1110.1893 | 1110.1893 | 1110.1893 | 1110.1893 | 1110.1893 | 1110.1893 | 1110.1893 | 1110.1893
|  | Labour & Material Escalation - Cumulative |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Expenditure By Asset Class - As Incurred
| Asset class breakdown | Secondary |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| (fully absorbed) | Switchgear |  | 14511.8497 | 440.3941 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14952.2437 | 0
| (as incurred) | Transformers |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Reactive |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Lines and towers |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Establishment |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Communications |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Non System |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Land |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Easements |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Total incl Overhead - As Incurred $ Mar 2017 |  | 14511.8497 | 440.3941 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14952.2437 | 0
|  |  | Check | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| As Commissioned Capex | Direct Expenditure (As Commissioned) - $ 2015/16 |  | 12971.8516 | 430.1323 | 209.796 | 0 | 0 | 0 | 0 | 0 | 0 | 13611.78 | 0
|  | Labour & Material Escalation - $ 2015/16 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Total Direct Expenditure - $ 2015/16 |  | 12971.8516 | 430.1323 | 209.796 | 0 | 0 | 0 | 0 | 0 | 0 | 13611.78 | 0
|  | Total Direct Expenditure - $ Mar 2017 |  | 13191.3002 | 437.409 | 213.3452 | 0 | 0 | 0 | 0 | 0 | 0 | 13842.0544 | 0
|  | Total overheads (As Commissioned) |  | 1056.382 | 36.6961 | 17.1112 | 0 | 0 | 0 | 0 | 0 | 0 | 1110.1893 | 0
|  | Total incl Overhead - As commissioned $ Mar 2017 |  | 14247.6822 | 474.1051 | 230.4564 | 0 | 0 | 0 | 0 | 0 | 0 | 14952.2437 | 0
|  | Total overheads (As Comm) - Cumulative |  | 1056.382 | 1093.0781 | 1110.1893 | 1110.1893 | 1110.1893 | 1110.1893 | 1110.1893 | 1110.1893 | 1110.1893
|  | Total real cost escalation (As Comm) - Cumulative |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Expenditure By Asset Class - As Commissioned
| Asset class breakdown | Secondary |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| (fully absorbed) | Switchgear |  | 14247.6822 | 474.1051 | 230.4564 | 0 | 0 | 0 | 0 | 0 | 0 | 14952.2437 | 0
| (as commissioned) | Transformers |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Reactive |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Lines and towers |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Establishment |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Communications |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Non System |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Land |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Easements |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Total incl Overhead - As commissioned $ Mar 2017 |  | 14247.6822 | 474.1051 | 230.4564 | 0 | 0 | 0 | 0 | 0 | 0 | 14952.2437 | 0
|  |  | Check | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0
| Expenditure splits for RIN |  |  |  | 2015-16 | 2016-17 | 2017-18 | 2018-19 | 2019-20 | 2020-21 | 2021-22 | 2022-23
| Repex Category | Transmission Towers | bar: 2015-16 to 2022-23
Transmission Tower Support Structures | bar: 2015-16 to 2022-23
Conductors | bar: 2015-16 to 2022-23
Transmission Cables | bar: 2015-16 to 2022-23
|  | Substation Switchbays |  |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
Substation Power Transformers | bar: 2015-16 to 2022-23
Substation Reactive Plant | bar: 2015-16 to 2022-23
Scada Network Control And Protection Systems | bar: 2015-16 to 2022-23
Other | bar: 2015-16 to 2022-23
|  | Total |  |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
| Direct Expenditures | Materials - $ Mar 2017 |  |  | 2015-16 | 2016-17 | 2017-18 | 2018-19 | 2019-20 | 2020-21 | 2021-22 | 2022-23 | Total | 2017-22 Total
| (As Incurred) | Transmission Towers |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Transmission Tower Support Structures |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Conductors |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Transmission Cables |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Substation Switchbays |  |  | 162.4693 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 162.4693 | 0
|  | Substation Power Transformers |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Substation Reactive Plant |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Scada Network Control And Protection Systems |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Other |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Total Materials |  |  | 162.4693 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 162.4693 | 0
|  | Labour (Internal) - $ Mar 2017 |  |  | 2015-16 | 2016-17 | 2017-18 | 2018-19 | 2019-20 | 2020-21 | 2021-22 | 2022-23 | Total | 2017-22 Total
|  | Transmission Towers |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Transmission Tower Support Structures |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Conductors |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Transmission Cables |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Substation Switchbays |  |  | 40.6173 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40.6173 | 0
|  | Substation Power Transformers |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Substation Reactive Plant |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Scada Network Control And Protection Systems |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Other |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Total Internal Labour |  |  | 40.6173 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40.6173 | 0
|  | Labour (External) - $ Mar 2017 |  |  | 2015-16 | 2016-17 | 2017-18 | 2018-19 | 2019-20 | 2020-21 | 2021-22 | 2022-23 | Total | 2017-22 Total
|  | Transmission Towers |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Transmission Tower Support Structures |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Conductors |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Transmission Cables |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Substation Switchbays |  |  | 203.0866 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 203.0866 | 0
|  | Substation Power Transformers |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Substation Reactive Plant |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Scada Network Control And Protection Systems |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Other |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Total External Labour |  |  | 203.0866 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 203.0866 | 0
|  | Total Direct - $ Mar 2017 |  |  | 2015-16 | 2016-17 | 2017-18 | 2018-19 | 2019-20 | 2020-21 | 2021-22 | 2022-23 | Total | 2017-22 Total
|  | Transmission Towers |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Transmission Tower Support Structures |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Conductors |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Transmission Cables |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Substation Switchbays |  |  | 406.1732 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 406.1732 | 0
|  | Substation Power Transformers |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Substation Reactive Plant |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Scada Network Control And Protection Systems |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Other |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Total Direct - $ Mar 2017 |  |  | 406.1732 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 406.1732 | 0

## Proj_15
Go To: | Table of Contents
Master Inputs
|  | XB56 |  | Business case? | Yes
| Project name | HWPS CB Replacement Stage 3
| Project category 1 | Network |  |  | Shaded cells = Inputs
| Project category 2 | Replacement - Major Station
| Regulatory classification | Prescribed
| Overhead Category | Repex_OHD |  | $000's | $000's | $000's | $000's | $000's | $000's | $000's | $000's | $000's | Project | 2017-22
|  |  |  | Prior | 2015-16 | 2016-17 | 2017-18 | 2018-19 | 2019-20 | 2020-21 | 2021-22 | 2022-23 | Total | Total | Check
| Project timing | Direct Expenditure (As incurred) - $ 2015/16 |  | 5338.0358 | 1619.3073 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6957.3431 | 0 | ok
| (excluding real cost escalators) | Assumed year commissioned (no BC)
|  | Direct Expenditure (As Commissioned) - $ 2015/16 |  | 3836.7384 | 2944.4592 | 176.1455 | 0 | 0 | 0 | 0 | 0 | 0 | 6957.3431 | 0 | ok
| Asset class | Secondary
|  | Switchgear |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
Transformers
Reactive
Lines and towers
Establishment
Communications
Non System
Land
Easements
|  |  | Total | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
| Input costs % | Labour - internal |  | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10%
|  | Labour - external |  | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50%
|  | Materials |  | 40% | 40% | 40% | 40% | 40% | 40% | 40% | 40% | 40%
|  |  | Total | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
Material Escalation
| (By Asset Class) | Secondary |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Switchgear |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Transformers |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Reactive |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Lines and towers |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Establishment |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Communications |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Non System |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Land |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Easements |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Total Material escalation |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Labour Escalation | Internal Labour |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | External Labour |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Total Labour Escalation |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Total Escalation |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Escalation factors |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Direct Expenditure (Escalated) | Total labour - internal |  | 542.8341 | 164.6702 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 707.5043 | 0
| (as incurred) | Total labour - external |  | 2714.1704 | 823.3508 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3537.5213 | 0
|  | Total materials |  | 2171.3364 | 658.6807 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2830.017 | 0
|  | Total Direct - As Incurred $ Mar 2017 |  | 5428.3409 | 1646.7016 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7075.0425 | 0 | ok
| Capitalised Overheads | Overhead rate (applied to direct expenditure) |  | 8.008% | 8.425% | 7.259% | 7.658% | 9.013% | 8.969% | 7.948% | 8.001% | 8.318%
|  | Total overhead (as incurred) |  | 434.7109 | 138.7376 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 573.4485 | 0
|  | Total incl Overhead - As Incurred $ Mar 2017 |  | 5863.0517 | 1785.4393 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7648.491 | 0
|  | Total overheads (As incurred) - Cumulative |  | 434.7109 | 573.4485 | 573.4485 | 573.4485 | 573.4485 | 573.4485 | 573.4485 | 573.4485 | 573.4485
|  | Labour & Material Escalation - Cumulative |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Expenditure By Asset Class - As Incurred
| Asset class breakdown | Secondary |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| (fully absorbed) | Switchgear |  | 5863.0517 | 1785.4393 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7648.491 | 0
| (as incurred) | Transformers |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Reactive |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Lines and towers |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Establishment |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Communications |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Non System |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Land |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Easements |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Total incl Overhead - As Incurred $ Mar 2017 |  | 5863.0517 | 1785.4393 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7648.491 | 0
|  |  | Check | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| As Commissioned Capex | Direct Expenditure (As Commissioned) - $ 2015/16 |  | 3836.7384 | 2944.4592 | 176.1455 | 0 | 0 | 0 | 0 | 0 | 0 | 6957.3431 | 0
|  | Labour & Material Escalation - $ 2015/16 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Total Direct Expenditure - $ 2015/16 |  | 3836.7384 | 2944.4592 | 176.1455 | 0 | 0 | 0 | 0 | 0 | 0 | 6957.3431 | 0
|  | Total Direct Expenditure - $ Mar 2017 |  | 3901.6456 | 2994.2715 | 179.1254 | 0 | 0 | 0 | 0 | 0 | 0 | 7075.0425 | 0
|  | Total overheads (As Commissioned) |  | 312.4505 | 246.4795 | 14.5185 | 0 | 0 | 0 | 0 | 0 | 0 | 573.4485 | 0
|  | Total incl Overhead - As commissioned $ Mar 2017 |  | 4214.0961 | 3240.751 | 193.644 | 0 | 0 | 0 | 0 | 0 | 0 | 7648.491 | 0
|  | Total overheads (As Comm) - Cumulative |  | 312.4505 | 558.93 | 573.4485 | 573.4485 | 573.4485 | 573.4485 | 573.4485 | 573.4485 | 573.4485
|  | Total real cost escalation (As Comm) - Cumulative |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Expenditure By Asset Class - As Commissioned
| Asset class breakdown | Secondary |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| (fully absorbed) | Switchgear |  | 4214.0961 | 3240.751 | 193.644 | 0 | 0 | 0 | 0 | 0 | 0 | 7648.491 | 0
| (as commissioned) | Transformers |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Reactive |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Lines and towers |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Establishment |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Communications |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Non System |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Land |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Easements |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Total incl Overhead - As commissioned $ Mar 2017 |  | 4214.0961 | 3240.751 | 193.644 | 0 | 0 | 0 | 0 | 0 | 0 | 7648.491 | 0
|  |  | Check | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0
| Expenditure splits for RIN |  |  |  | 2015-16 | 2016-17 | 2017-18 | 2018-19 | 2019-20 | 2020-21 | 2021-22 | 2022-23
| Repex Category | Transmission Towers | bar: 2015-16 to 2022-23
Transmission Tower Support Structures | bar: 2015-16 to 2022-23
Conductors | bar: 2015-16 to 2022-23
Transmission Cables | bar: 2015-16 to 2022-23
|  | Substation Switchbays |  |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
Substation Power Transformers | bar: 2015-16 to 2022-23
Substation Reactive Plant | bar: 2015-16 to 2022-23
Scada Network Control And Protection Systems | bar: 2015-16 to 2022-23
Other | bar: 2015-16 to 2022-23
|  | Total |  |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
| Direct Expenditures | Materials - $ Mar 2017 |  |  | 2015-16 | 2016-17 | 2017-18 | 2018-19 | 2019-20 | 2020-21 | 2021-22 | 2022-23 | Total | 2017-22 Total
| (As Incurred) | Transmission Towers |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Transmission Tower Support Structures |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Conductors |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Transmission Cables |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Substation Switchbays |  |  | 658.6807 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 658.6807 | 0
|  | Substation Power Transformers |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Substation Reactive Plant |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Scada Network Control And Protection Systems |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Other |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Total Materials |  |  | 658.6807 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 658.6807 | 0
|  | Labour (Internal) - $ Mar 2017 |  |  | 2015-16 | 2016-17 | 2017-18 | 2018-19 | 2019-20 | 2020-21 | 2021-22 | 2022-23 | Total | 2017-22 Total
|  | Transmission Towers |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Transmission Tower Support Structures |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Conductors |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Transmission Cables |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Substation Switchbays |  |  | 164.6702 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 164.6702 | 0
|  | Substation Power Transformers |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Substation Reactive Plant |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Scada Network Control And Protection Systems |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Other |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Total Internal Labour |  |  | 164.6702 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 164.6702 | 0
|  | Labour (External) - $ Mar 2017 |  |  | 2015-16 | 2016-17 | 2017-18 | 2018-19 | 2019-20 | 2020-21 | 2021-22 | 2022-23 | Total | 2017-22 Total
|  | Transmission Towers |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Transmission Tower Support Structures |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Conductors |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Transmission Cables |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Substation Switchbays |  |  | 823.3508 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 823.3508 | 0
|  | Substation Power Transformers |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Substation Reactive Plant |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Scada Network Control And Protection Systems |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Other |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Total External Labour |  |  | 823.3508 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 823.3508 | 0
|  | Total Direct - $ Mar 2017 |  |  | 2015-16 | 2016-17 | 2017-18 | 2018-19 | 2019-20 | 2020-21 | 2021-22 | 2022-23 | Total | 2017-22 Total
|  | Transmission Towers |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Transmission Tower Support Structures |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Conductors |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Transmission Cables |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Substation Switchbays |  |  | 1646.7016 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1646.7016 | 0
|  | Substation Power Transformers |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Substation Reactive Plant |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Scada Network Control And Protection Systems |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Other |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Total Direct - $ Mar 2017 |  |  | 1646.7016 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1646.7016 | 0

## Proj_16
Go To: | Table of Contents
Master Inputs
|  | XB64 |  | Business case? | Yes
| Project name | MWTS B2 Transformer Replacement
| Project category 1 | Network |  |  | Shaded cells = Inputs
| Project category 2 | Replacement - Major Station
| Regulatory classification | Prescribed
| Overhead Category | Repex_OHD |  | $000's | $000's | $000's | $000's | $000's | $000's | $000's | $000's | $000's | Project | 2017-22
|  |  |  | Prior | 2015-16 | 2016-17 | 2017-18 | 2018-19 | 2019-20 | 2020-21 | 2021-22 | 2022-23 | Total | Total | Check
| Project timing | Direct Expenditure (As incurred) - $ 2015/16 |  | 2535.5117 | 3371.1761 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5906.6878 | 0 | ok
| (excluding real cost escalators) | Assumed year commissioned (no BC)
|  | Direct Expenditure (As Commissioned) - $ 2015/16 |  | 0 | 4921.4296 | 985.2582 | 0 | 0 | 0 | 0 | 0 | 0 | 5906.6878 | 0 | ok
| Asset class | Secondary
Switchgear
|  | Transformers |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
Reactive
Lines and towers
Establishment
Communications
Non System
Land
Easements
|  |  | Total | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
| Input costs % | Labour - internal |  | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10%
|  | Labour - external |  | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50%
|  | Materials |  | 40% | 40% | 40% | 40% | 40% | 40% | 40% | 40% | 40%
|  |  | Total | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
Material Escalation
| (By Asset Class) | Secondary |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Switchgear |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Transformers |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Reactive |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Lines and towers |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Establishment |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Communications |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Non System |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Land |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Easements |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Total Material escalation |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Labour Escalation | Internal Labour |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | External Labour |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Total Labour Escalation |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Total Escalation |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Escalation factors |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Direct Expenditure (Escalated) | Total labour - internal |  | 257.8406 | 342.8207 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 600.6613 | 0
| (as incurred) | Total labour - external |  | 1289.2028 | 1714.1036 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3003.3065 | 0
|  | Total materials |  | 1031.3623 | 1371.2829 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2402.6452 | 0
|  | Total Direct - As Incurred $ Mar 2017 |  | 2578.4057 | 3428.2073 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6006.613 | 0 | ok
| Capitalised Overheads | Overhead rate (applied to direct expenditure) |  | 8.008% | 8.425% | 7.259% | 7.658% | 9.013% | 8.969% | 7.948% | 8.001% | 8.318%
|  | Total overhead (as incurred) |  | 206.4832 | 288.8328 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 495.3159 | 0
|  | Total incl Overhead - As Incurred $ Mar 2017 |  | 2784.8889 | 3717.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6501.9289 | 0
|  | Total overheads (As incurred) - Cumulative |  | 206.4832 | 495.3159 | 495.3159 | 495.3159 | 495.3159 | 495.3159 | 495.3159 | 495.3159 | 495.3159
|  | Labour & Material Escalation - Cumulative |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Expenditure By Asset Class - As Incurred
| Asset class breakdown | Secondary |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| (fully absorbed) | Switchgear |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| (as incurred) | Transformers |  | 2784.8889 | 3717.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6501.9289 | 0
|  | Reactive |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Lines and towers |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Establishment |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Communications |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Non System |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Land |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Easements |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Total incl Overhead - As Incurred $ Mar 2017 |  | 2784.8889 | 3717.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6501.9289 | 0
|  |  | Check | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| As Commissioned Capex | Direct Expenditure (As Commissioned) - $ 2015/16 |  | 0 | 4921.4296 | 985.2582 | 0 | 0 | 0 | 0 | 0 | 0 | 5906.6878 | 0
|  | Labour & Material Escalation - $ 2015/16 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Total Direct Expenditure - $ 2015/16 |  | 0 | 4921.4296 | 985.2582 | 0 | 0 | 0 | 0 | 0 | 0 | 5906.6878 | 0
|  | Total Direct Expenditure - $ Mar 2017 |  | 0 | 5004.6869 | 1001.9261 | 0 | 0 | 0 | 0 | 0 | 0 | 6006.613 | 0
|  | Total overheads (As Commissioned) |  | 0 | 412.6953 | 82.6206 | 0 | 0 | 0 | 0 | 0 | 0 | 495.3159 | 0
|  | Total incl Overhead - As commissioned $ Mar 2017 |  | 0 | 5417.3822 | 1084.5467 | 0 | 0 | 0 | 0 | 0 | 0 | 6501.9289 | 0
|  | Total overheads (As Comm) - Cumulative |  | 0 | 412.6953 | 495.3159 | 495.3159 | 495.3159 | 495.3159 | 495.3159 | 495.3159 | 495.3159
|  | Total real cost escalation (As Comm) - Cumulative |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Expenditure By Asset Class - As Commissioned
| Asset class breakdown | Secondary |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| (fully absorbed) | Switchgear |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| (as commissioned) | Transformers |  | 0 | 5417.3822 | 1084.5467 | 0 | 0 | 0 | 0 | 0 | 0 | 6501.9289 | 0
|  | Reactive |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Lines and towers |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Establishment |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Communications |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Non System |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Land |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Easements |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Total incl Overhead - As commissioned $ Mar 2017 |  | 0 | 5417.3822 | 1084.5467 | 0 | 0 | 0 | 0 | 0 | 0 | 6501.9289 | 0
|  |  | Check | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0
| Expenditure splits for RIN |  |  |  | 2015-16 | 2016-17 | 2017-18 | 2018-19 | 2019-20 | 2020-21 | 2021-22 | 2022-23
| Repex Category | Transmission Towers | bar: 2015-16 to 2022-23
Transmission Tower Support Structures | bar: 2015-16 to 2022-23
Conductors | bar: 2015-16 to 2022-23
Transmission Cables | bar: 2015-16 to 2022-23
Substation Switchbays | bar: 2015-16 to 2022-23
|  | Substation Power Transformers |  |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
Substation Reactive Plant | bar: 2015-16 to 2022-23
Scada Network Control And Protection Systems | bar: 2015-16 to 2022-23
Other | bar: 2015-16 to 2022-23
|  | Total |  |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
| Direct Expenditures | Materials - $ Mar 2017 |  |  | 2015-16 | 2016-17 | 2017-18 | 2018-19 | 2019-20 | 2020-21 | 2021-22 | 2022-23 | Total | 2017-22 Total
| (As Incurred) | Transmission Towers |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Transmission Tower Support Structures |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Conductors |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Transmission Cables |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Substation Switchbays |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Substation Power Transformers |  |  | 1371.2829 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1371.2829 | 0
|  | Substation Reactive Plant |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Scada Network Control And Protection Systems |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Other |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Total Materials |  |  | 1371.2829 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1371.2829 | 0
|  | Labour (Internal) - $ Mar 2017 |  |  | 2015-16 | 2016-17 | 2017-18 | 2018-19 | 2019-20 | 2020-21 | 2021-22 | 2022-23 | Total | 2017-22 Total
|  | Transmission Towers |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Transmission Tower Support Structures |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Conductors |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Transmission Cables |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Substation Switchbays |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Substation Power Transformers |  |  | 342.8207 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 342.8207 | 0
|  | Substation Reactive Plant |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Scada Network Control And Protection Systems |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Other |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Total Internal Labour |  |  | 342.8207 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 342.8207 | 0
|  | Labour (External) - $ Mar 2017 |  |  | 2015-16 | 2016-17 | 2017-18 | 2018-19 | 2019-20 | 2020-21 | 2021-22 | 2022-23 | Total | 2017-22 Total
|  | Transmission Towers |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Transmission Tower Support Structures |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Conductors |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Transmission Cables |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Substation Switchbays |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Substation Power Transformers |  |  | 1714.1036 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1714.1036 | 0
|  | Substation Reactive Plant |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Scada Network Control And Protection Systems |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Other |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Total External Labour |  |  | 1714.1036 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1714.1036 | 0
|  | Total Direct - $ Mar 2017 |  |  | 2015-16 | 2016-17 | 2017-18 | 2018-19 | 2019-20 | 2020-21 | 2021-22 | 2022-23 | Total | 2017-22 Total
|  | Transmission Towers |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Transmission Tower Support Structures |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Conductors |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Transmission Cables |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Substation Switchbays |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Substation Power Transformers |  |  | 3428.2073 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3428.2073 | 0
|  | Substation Reactive Plant |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Scada Network Control And Protection Systems |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Other |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Total Direct - $ Mar 2017 |  |  | 3428.2073 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3428.2073 | 0

## Proj_17
Go To: | Table of Contents
Master Inputs
|  | XC16 |  | Business case? | Yes
| Project name | TTS Bus Tie CB Replacement
| Project category 1 | Network |  |  | Shaded cells = Inputs
| Project category 2 | Replacement - Major Station
| Regulatory classification | Prescribed
| Overhead Category | Repex_OHD |  | $000's | $000's | $000's | $000's | $000's | $000's | $000's | $000's | $000's | Project | 2017-22
|  |  |  | Prior | 2015-16 | 2016-17 | 2017-18 | 2018-19 | 2019-20 | 2020-21 | 2021-22 | 2022-23 | Total | Total | Check
| Project timing | Direct Expenditure (As incurred) - $ 2015/16 |  | 248.4712 | 740.0775 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 988.5487 | 0 | ok
| (excluding real cost escalators) | Assumed year commissioned (no BC)
|  | Direct Expenditure (As Commissioned) - $ 2015/16 |  | 0 | 0 | 988.5487 | 0 | 0 | 0 | 0 | 0 | 0 | 988.5487 | 0 | ok
| Asset class | Secondary
|  | Switchgear |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
Transformers
Reactive
Lines and towers
Establishment
Communications
Non System
Land
Easements
|  |  | Total | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
| Input costs % | Labour - internal |  | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10%
|  | Labour - external |  | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50%
|  | Materials |  | 40% | 40% | 40% | 40% | 40% | 40% | 40% | 40% | 40%
|  |  | Total | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
Material Escalation
| (By Asset Class) | Secondary |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Switchgear |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Transformers |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Reactive |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Lines and towers |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Establishment |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Communications |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Non System |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Land |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Easements |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Total Material escalation |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Labour Escalation | Internal Labour |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | External Labour |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Total Labour Escalation |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Total Escalation |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Escalation factors |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Direct Expenditure (Escalated) | Total labour - internal |  | 25.2675 | 75.2598 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100.5272 | 0
| (as incurred) | Total labour - external |  | 126.3373 | 376.2988 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 502.6361 | 0
|  | Total materials |  | 101.0699 | 301.039 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 402.1089 | 0
|  | Total Direct - As Incurred $ Mar 2017 |  | 252.6747 | 752.5976 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1005.2723 | 0 | ok
| Capitalised Overheads | Overhead rate (applied to direct expenditure) |  | 8.008% | 8.425% | 7.259% | 7.658% | 9.013% | 8.969% | 7.948% | 8.001% | 8.318%
|  | Total overhead (as incurred) |  | 20.2346 | 63.4077 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 83.6424 | 0
|  | Total incl Overhead - As Incurred $ Mar 2017 |  | 272.9093 | 816.0054 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1088.9146 | 0
|  | Total overheads (As incurred) - Cumulative |  | 20.2346 | 83.6424 | 83.6424 | 83.6424 | 83.6424 | 83.6424 | 83.6424 | 83.6424 | 83.6424
|  | Labour & Material Escalation - Cumulative |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Expenditure By Asset Class - As Incurred
| Asset class breakdown | Secondary |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| (fully absorbed) | Switchgear |  | 272.9093 | 816.0054 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1088.9146 | 0
| (as incurred) | Transformers |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Reactive |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Lines and towers |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Establishment |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Communications |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Non System |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Land |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Easements |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Total incl Overhead - As Incurred $ Mar 2017 |  | 272.9093 | 816.0054 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1088.9146 | 0
|  |  | Check | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| As Commissioned Capex | Direct Expenditure (As Commissioned) - $ 2015/16 |  | 0 | 0 | 988.5487 | 0 | 0 | 0 | 0 | 0 | 0 | 988.5487 | 0
|  | Labour & Material Escalation - $ 2015/16 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Total Direct Expenditure - $ 2015/16 |  | 0 | 0 | 988.5487 | 0 | 0 | 0 | 0 | 0 | 0 | 988.5487 | 0
|  | Total Direct Expenditure - $ Mar 2017 |  | 0 | 0 | 1005.2723 | 0 | 0 | 0 | 0 | 0 | 0 | 1005.2723 | 0
|  | Total overheads (As Commissioned) |  | 0 | 0 | 83.6424 | 0 | 0 | 0 | 0 | 0 | 0 | 83.6424 | 0
|  | Total incl Overhead - As commissioned $ Mar 2017 |  | 0 | 0 | 1088.9146 | 0 | 0 | 0 | 0 | 0 | 0 | 1088.9146 | 0
|  | Total overheads (As Comm) - Cumulative |  | 0 | 0 | 83.6424 | 83.6424 | 83.6424 | 83.6424 | 83.6424 | 83.6424 | 83.6424
|  | Total real cost escalation (As Comm) - Cumulative |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Expenditure By Asset Class - As Commissioned
| Asset class breakdown | Secondary |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| (fully absorbed) | Switchgear |  | 0 | 0 | 1088.9146 | 0 | 0 | 0 | 0 | 0 | 0 | 1088.9146 | 0
| (as commissioned) | Transformers |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Reactive |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Lines and towers |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Establishment |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Communications |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Non System |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Land |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Easements |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Total incl Overhead - As commissioned $ Mar 2017 |  | 0 | 0 | 1088.9146 | 0 | 0 | 0 | 0 | 0 | 0 | 1088.9146 | 0
|  |  | Check | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0
| Expenditure splits for RIN |  |  |  | 2015-16 | 2016-17 | 2017-18 | 2018-19 | 2019-20 | 2020-21 | 2021-22 | 2022-23
| Repex Category | Transmission Towers | bar: 2015-16 to 2022-23
Transmission Tower Support Structures | bar: 2015-16 to 2022-23
Conductors | bar: 2015-16 to 2022-23
Transmission Cables | bar: 2015-16 to 2022-23
|  | Substation Switchbays |  |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
Substation Power Transformers | bar: 2015-16 to 2022-23
Substation Reactive Plant | bar: 2015-16 to 2022-23
Scada Network Control And Protection Systems | bar: 2015-16 to 2022-23
Other | bar: 2015-16 to 2022-23
|  | Total |  |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
| Direct Expenditures | Materials - $ Mar 2017 |  |  | 2015-16 | 2016-17 | 2017-18 | 2018-19 | 2019-20 | 2020-21 | 2021-22 | 2022-23 | Total | 2017-22 Total
| (As Incurred) | Transmission Towers |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Transmission Tower Support Structures |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Conductors |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Transmission Cables |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Substation Switchbays |  |  | 301.039 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 301.039 | 0
|  | Substation Power Transformers |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Substation Reactive Plant |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Scada Network Control And Protection Systems |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Other |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Total Materials |  |  | 301.039 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 301.039 | 0
|  | Labour (Internal) - $ Mar 2017 |  |  | 2015-16 | 2016-17 | 2017-18 | 2018-19 | 2019-20 | 2020-21 | 2021-22 | 2022-23 | Total | 2017-22 Total
|  | Transmission Towers |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Transmission Tower Support Structures |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Conductors |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Transmission Cables |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Substation Switchbays |  |  | 75.2598 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 75.2598 | 0
|  | Substation Power Transformers |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Substation Reactive Plant |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Scada Network Control And Protection Systems |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Other |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Total Internal Labour |  |  | 75.2598 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 75.2598 | 0
|  | Labour (External) - $ Mar 2017 |  |  | 2015-16 | 2016-17 | 2017-18 | 2018-19 | 2019-20 | 2020-21 | 2021-22 | 2022-23 | Total | 2017-22 Total
|  | Transmission Towers |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Transmission Tower Support Structures |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Conductors |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Transmission Cables |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Substation Switchbays |  |  | 376.2988 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 376.2988 | 0
|  | Substation Power Transformers |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Substation Reactive Plant |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Scada Network Control And Protection Systems |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Other |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Total External Labour |  |  | 376.2988 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 376.2988 | 0
|  | Total Direct - $ Mar 2017 |  |  | 2015-16 | 2016-17 | 2017-18 | 2018-19 | 2019-20 | 2020-21 | 2021-22 | 2022-23 | Total | 2017-22 Total
|  | Transmission Towers |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Transmission Tower Support Structures |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Conductors |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Transmission Cables |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Substation Switchbays |  |  | 752.5976 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 752.5976 | 0
|  | Substation Power Transformers |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Substation Reactive Plant |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Scada Network Control And Protection Systems |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Other |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Total Direct - $ Mar 2017 |  |  | 752.5976 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 752.5976 | 0

## Proj_18
Go To: | Table of Contents
Master Inputs
|  | XC18 |  | Business case? | Yes
| Project name | YPS 220kV CB Replacement
| Project category 1 | Network |  |  | Shaded cells = Inputs
| Project category 2 | Replacement - Major Station
| Regulatory classification | Prescribed
| Overhead Category | Repex_OHD |  | $000's | $000's | $000's | $000's | $000's | $000's | $000's | $000's | $000's | Project | 2017-22
|  |  |  | Prior | 2015-16 | 2016-17 | 2017-18 | 2018-19 | 2019-20 | 2020-21 | 2021-22 | 2022-23 | Total | Total | Check
| Project timing | Direct Expenditure (As incurred) - $ 2015/16 |  | 3214.5777 | 3530.5755 | 4301.1878 | 0 | 0 | 0 | 0 | 0 | 0 | 11046.3411 | 0 | ok
| (excluding real cost escalators) | Assumed year commissioned (no BC)
|  | Direct Expenditure (As Commissioned) - $ 2015/16 |  | 0 | 0 | 6517.3412 | 4528.9999 | 0 | 0 | 0 | 0 | 0 | 11046.3411 | 4528.9999 | ok
| Asset class | Secondary
|  | Switchgear |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
Transformers
Reactive
Lines and towers
Establishment
Communications
Non System
Land
Easements
|  |  | Total | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
| Input costs % | Labour - internal |  | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10%
|  | Labour - external |  | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50%
|  | Materials |  | 40% | 40% | 40% | 40% | 40% | 40% | 40% | 40% | 40%
|  |  | Total | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
Material Escalation
| (By Asset Class) | Secondary |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Switchgear |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Transformers |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Reactive |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Lines and towers |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Establishment |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Communications |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Non System |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Land |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Easements |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Total Material escalation |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Labour Escalation | Internal Labour |  | 0 | 0 | 5.3824 | 0 | 0 | 0 | 0 | 0 | 0 | 5.3824 | 0
|  | External Labour |  | 0 | 0 | 23.1235 | 0 | 0 | 0 | 0 | 0 | 0 | 23.1235 | 0
|  | Total Labour Escalation |  | 0 | 0 | 28.5059 | 0 | 0 | 0 | 0 | 0 | 0 | 28.5059 | 0
|  | Total Escalation |  | 0 | 0 | 28.5059 | 0 | 0 | 0 | 0 | 0 | 0 | 28.5059 | 0
|  | Escalation factors |  | 0 | 0 | 0.0066275 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0025806 | 0
| Direct Expenditure (Escalated) | Total labour - internal |  | 326.896 | 359.0303 | 442.8687 | 0 | 0 | 0 | 0 | 0 | 0 | 1128.795 | 0
| (as incurred) | Total labour - external |  | 1634.4798 | 1795.1517 | 2210.4909 | 0 | 0 | 0 | 0 | 0 | 0 | 5640.1224 | 0
|  | Total materials |  | 1307.5839 | 1436.1213 | 1749.5809 | 0 | 0 | 0 | 0 | 0 | 0 | 4493.2861 | 0
|  | Total Direct - As Incurred $ Mar 2017 |  | 3268.9597 | 3590.3033 | 4402.9405 | 0 | 0 | 0 | 0 | 0 | 0 | 11262.2035 | 0 | ok
| Capitalised Overheads | Overhead rate (applied to direct expenditure) |  | 8.008% | 8.425% | 7.259% | 7.658% | 9.013% | 8.969% | 7.948% | 8.001% | 8.318%
|  | Total overhead (as incurred) |  | 261.7839 | 302.4897 | 319.6257 | 0 | 0 | 0 | 0 | 0 | 0 | 883.8992 | 0
|  | Total incl Overhead - As Incurred $ Mar 2017 |  | 3530.7436 | 3892.793 | 4722.5662 | 0 | 0 | 0 | 0 | 0 | 0 | 12146.1027 | 0
|  | Total overheads (As incurred) - Cumulative |  | 261.7839 | 564.2736 | 883.8992 | 883.8992 | 883.8992 | 883.8992 | 883.8992 | 883.8992 | 883.8992
|  | Labour & Material Escalation - Cumulative |  | 0 | 0 | 28.5059 | 28.5059 | 28.5059 | 28.5059 | 28.5059 | 28.5059 | 28.5059
Expenditure By Asset Class - As Incurred
| Asset class breakdown | Secondary |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| (fully absorbed) | Switchgear |  | 3530.7436 | 3892.793 | 4722.5662 | 0 | 0 | 0 | 0 | 0 | 0 | 12146.1027 | 0
| (as incurred) | Transformers |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Reactive |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Lines and towers |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Establishment |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Communications |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Non System |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Land |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Easements |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Total incl Overhead - As Incurred $ Mar 2017 |  | 3530.7436 | 3892.793 | 4722.5662 | 0 | 0 | 0 | 0 | 0 | 0 | 12146.1027 | 0
|  |  | Check | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| As Commissioned Capex | Direct Expenditure (As Commissioned) - $ 2015/16 |  | 0 | 0 | 6517.3412 | 4528.9999 | 0 | 0 | 0 | 0 | 0 | 11046.3411 | 4528.9999
|  | Labour & Material Escalation - $ 2015/16 |  | 0 | 0 | 28.5059 | 0 | 0 | 0 | 0 | 0 | 0 | 28.5059 | 0
|  | Total Direct Expenditure - $ 2015/16 |  | 0 | 0 | 6545.8472 | 4528.9999 | 0 | 0 | 0 | 0 | 0 | 11074.847 | 4528.9999
|  | Total Direct Expenditure - $ Mar 2017 |  | 0 | 0 | 6656.5852 | 4605.6183 | 0 | 0 | 0 | 0 | 0 | 11262.2035 | 4605.6183
|  | Total overheads (As Commissioned) |  | 0 | 0 | 522.4333 | 361.4659 | 0 | 0 | 0 | 0 | 0 | 883.8992 | 361.4659
|  | Total incl Overhead - As commissioned $ Mar 2017 |  | 0 | 0 | 7179.0186 | 4967.0842 | 0 | 0 | 0 | 0 | 0 | 12146.1027 | 4967.0842
|  | Total overheads (As Comm) - Cumulative |  | 0 | 0 | 522.4333 | 883.8992 | 883.8992 | 883.8992 | 883.8992 | 883.8992 | 883.8992
|  | Total real cost escalation (As Comm) - Cumulative |  | 0 | 0 | 28.5059 | 28.5059 | 28.5059 | 28.5059 | 28.5059 | 28.5059 | 28.5059
Expenditure By Asset Class - As Commissioned
| Asset class breakdown | Secondary |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| (fully absorbed) | Switchgear |  | 0 | 0 | 7179.0186 | 4967.0842 | 0 | 0 | 0 | 0 | 0 | 12146.1027 | 4967.0842
| (as commissioned) | Transformers |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Reactive |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Lines and towers |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Establishment |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Communications |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Non System |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Land |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Easements |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Total incl Overhead - As commissioned $ Mar 2017 |  | 0 | 0 | 7179.0186 | 4967.0842 | 0 | 0 | 0 | 0 | 0 | 12146.1027 | 4967.0842
|  |  | Check | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0
| Expenditure splits for RIN |  |  |  | 2015-16 | 2016-17 | 2017-18 | 2018-19 | 2019-20 | 2020-21 | 2021-22 | 2022-23
| Repex Category | Transmission Towers | bar: 2015-16 to 2022-23
Transmission Tower Support Structures | bar: 2015-16 to 2022-23
Conductors | bar: 2015-16 to 2022-23
Transmission Cables | bar: 2015-16 to 2022-23
|  | Substation Switchbays |  |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
Substation Power Transformers | bar: 2015-16 to 2022-23
Substation Reactive Plant | bar: 2015-16 to 2022-23
Scada Network Control And Protection Systems | bar: 2015-16 to 2022-23
Other | bar: 2015-16 to 2022-23
|  | Total |  |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
| Direct Expenditures | Materials - $ Mar 2017 |  |  | 2015-16 | 2016-17 | 2017-18 | 2018-19 | 2019-20 | 2020-21 | 2021-22 | 2022-23 | Total | 2017-22 Total
| (As Incurred) | Transmission Towers |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Transmission Tower Support Structures |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Conductors |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Transmission Cables |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Substation Switchbays |  |  | 1436.1213 | 1749.5809 | 0 | 0 | 0 | 0 | 0 | 0 | 3185.7023 | 0
|  | Substation Power Transformers |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Substation Reactive Plant |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Scada Network Control And Protection Systems |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Other |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Total Materials |  |  | 1436.1213 | 1749.5809 | 0 | 0 | 0 | 0 | 0 | 0 | 3185.7023 | 0
|  | Labour (Internal) - $ Mar 2017 |  |  | 2015-16 | 2016-17 | 2017-18 | 2018-19 | 2019-20 | 2020-21 | 2021-22 | 2022-23 | Total | 2017-22 Total
|  | Transmission Towers |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Transmission Tower Support Structures |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Conductors |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Transmission Cables |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Substation Switchbays |  |  | 359.0303 | 442.8687 | 0 | 0 | 0 | 0 | 0 | 0 | 801.899 | 0
|  | Substation Power Transformers |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Substation Reactive Plant |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Scada Network Control And Protection Systems |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Other |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Total Internal Labour |  |  | 359.0303 | 442.8687 | 0 | 0 | 0 | 0 | 0 | 0 | 801.899 | 0
|  | Labour (External) - $ Mar 2017 |  |  | 2015-16 | 2016-17 | 2017-18 | 2018-19 | 2019-20 | 2020-21 | 2021-22 | 2022-23 | Total | 2017-22 Total
|  | Transmission Towers |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Transmission Tower Support Structures |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Conductors |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Transmission Cables |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Substation Switchbays |  |  | 1795.1517 | 2210.4909 | 0 | 0 | 0 | 0 | 0 | 0 | 4005.6425 | 0
|  | Substation Power Transformers |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Substation Reactive Plant |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Scada Network Control And Protection Systems |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Other |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Total External Labour |  |  | 1795.1517 | 2210.4909 | 0 | 0 | 0 | 0 | 0 | 0 | 4005.6425 | 0
|  | Total Direct - $ Mar 2017 |  |  | 2015-16 | 2016-17 | 2017-18 | 2018-19 | 2019-20 | 2020-21 | 2021-22 | 2022-23 | Total | 2017-22 Total
|  | Transmission Towers |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Transmission Tower Support Structures |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Conductors |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Transmission Cables |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Substation Switchbays |  |  | 3590.3033 | 4402.9405 | 0 | 0 | 0 | 0 | 0 | 0 | 7993.2438 | 0
|  | Substation Power Transformers |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Substation Reactive Plant |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Scada Network Control And Protection Systems |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Other |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Total Direct - $ Mar 2017 |  |  | 3590.3033 | 4402.9405 | 0 | 0 | 0 | 0 | 0 | 0 | 7993.2438 | 0

## Proj_19
Go To: | Table of Contents
Master Inputs
|  |  |  | Business case? | 0
| Project name | Other station transformer replacement
| Project category 1 | Network |  |  | Shaded cells = Inputs
| Project category 2 | Replacement - Major Station
| Regulatory classification | Prescribed
| Overhead Category | Repex_OHD |  | $000's | $000's | $000's | $000's | $000's | $000's | $000's | $000's | $000's | Project | 2017-22
|  |  |  | Prior | 2015-16 | 2016-17 | 2017-18 | 2018-19 | 2019-20 | 2020-21 | 2021-22 | 2022-23 | Total | Total | Check
| Project timing | Direct Expenditure (As incurred) - $ 2015/16 |  | 9613.3377 | 612.6528 | 881.5477 | 0 | 0 | 0 | 0 | 0 | 0 | 11107.5382 | 0 | ok
| (excluding real cost escalators) | Assumed year commissioned (no BC) |  | x | bar: 2015-16 to 2022-23
|  | Direct Expenditure (As Commissioned) - $ 2015/16 |  | 9613.3377 | 612.6528 | 881.5477 | 0 | 0 | 0 | 0 | 0 | 0 | 11107.5382 | 0 | ok
| Asset class | Secondary
Switchgear
|  | Transformers |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
Reactive
Lines and towers
Establishment
Communications
Non System
Land
Easements
|  |  | Total | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
| Input costs % | Labour - internal |  | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10%
|  | Labour - external |  | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50%
|  | Materials |  | 40% | 40% | 40% | 40% | 40% | 40% | 40% | 40% | 40%
|  |  | Total | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
Material Escalation
| (By Asset Class) | Secondary |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Switchgear |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Transformers |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Reactive |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Lines and towers |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Establishment |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Communications |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Non System |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Land |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Easements |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Total Material escalation |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Labour Escalation | Internal Labour |  | 0 | 0 | 1.1031 | 0 | 0 | 0 | 0 | 0 | 0 | 1.1031 | 0
|  | External Labour |  | 0 | 0 | 4.7393 | 0 | 0 | 0 | 0 | 0 | 0 | 4.7393 | 0
|  | Total Labour Escalation |  | 0 | 0 | 5.8424 | 0 | 0 | 0 | 0 | 0 | 0 | 5.8424 | 0
|  | Total Escalation |  | 0 | 0 | 5.8424 | 0 | 0 | 0 | 0 | 0 | 0 | 5.8424 | 0
|  | Escalation factors |  | 0 | 0 | 0.0066275 | 0 | 0 | 0 | 0 | 0 | 0 | 0.00052599 | 0
| Direct Expenditure (Escalated) | Total labour - internal |  | 977.5969 | 62.3017 | 90.7679 | 0 | 0 | 0 | 0 | 0 | 0 | 1130.6666 | 0
| (as incurred) | Total labour - external |  | 4887.9847 | 311.5086 | 453.05 | 0 | 0 | 0 | 0 | 0 | 0 | 5652.5433 | 0
|  | Total materials |  | 3910.3877 | 249.2069 | 358.5844 | 0 | 0 | 0 | 0 | 0 | 0 | 4518.1791 | 0
|  | Total Direct - As Incurred $ Mar 2017 |  | 9775.9693 | 623.0172 | 902.4024 | 0 | 0 | 0 | 0 | 0 | 0 | 11301.3889 | 0 | ok
| Capitalised Overheads | Overhead rate (applied to direct expenditure) |  | 8.008% | 8.425% | 7.259% | 7.658% | 9.013% | 8.969% | 7.948% | 8.001% | 8.318%
|  | Total overhead (as incurred) |  | 782.8764 | 52.4903 | 65.5087 | 0 | 0 | 0 | 0 | 0 | 0 | 900.8755 | 0
|  | Total incl Overhead - As Incurred $ Mar 2017 |  | 10558.8458 | 675.5076 | 967.9111 | 0 | 0 | 0 | 0 | 0 | 0 | 12202.2644 | 0
|  | Total overheads (As incurred) - Cumulative |  | 782.8764 | 835.3668 | 900.8755 | 900.8755 | 900.8755 | 900.8755 | 900.8755 | 900.8755 | 900.8755
|  | Labour & Material Escalation - Cumulative |  | 0 | 0 | 5.8424 | 5.8424 | 5.8424 | 5.8424 | 5.8424 | 5.8424 | 5.8424
Expenditure By Asset Class - As Incurred
| Asset class breakdown | Secondary |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| (fully absorbed) | Switchgear |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| (as incurred) | Transformers |  | 10558.8458 | 675.5076 | 967.9111 | 0 | 0 | 0 | 0 | 0 | 0 | 12202.2644 | 0
|  | Reactive |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Lines and towers |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Establishment |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Communications |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Non System |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Land |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Easements |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Total incl Overhead - As Incurred $ Mar 2017 |  | 10558.8458 | 675.5076 | 967.9111 | 0 | 0 | 0 | 0 | 0 | 0 | 12202.2644 | 0
|  |  | Check | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| As Commissioned Capex | Direct Expenditure (As Commissioned) - $ 2015/16 |  | 9613.3377 | 612.6528 | 881.5477 | 0 | 0 | 0 | 0 | 0 | 0 | 11107.5382 | 0
|  | Labour & Material Escalation - $ 2015/16 |  | 0 | 0 | 5.8424 | 0 | 0 | 0 | 0 | 0 | 0 | 5.8424 | 0
|  | Total Direct Expenditure - $ 2015/16 |  | 9613.3377 | 612.6528 | 887.3901 | 0 | 0 | 0 | 0 | 0 | 0 | 11113.3806 | 0
|  | Total Direct Expenditure - $ Mar 2017 |  | 9775.9693 | 623.0172 | 902.4024 | 0 | 0 | 0 | 0 | 0 | 0 | 11301.3889 | 0
|  | Total overheads (As Commissioned) |  | 782.8764 | 52.4903 | 65.5087 | 0 | 0 | 0 | 0 | 0 | 0 | 900.8755 | 0
|  | Total incl Overhead - As commissioned $ Mar 2017 |  | 10558.8458 | 675.5076 | 967.9111 | 0 | 0 | 0 | 0 | 0 | 0 | 12202.2644 | 0
|  | Total overheads (As Comm) - Cumulative |  | 782.8764 | 835.3668 | 900.8755 | 900.8755 | 900.8755 | 900.8755 | 900.8755 | 900.8755 | 900.8755
|  | Total real cost escalation (As Comm) - Cumulative |  | 0 | 0 | 5.8424 | 5.8424 | 5.8424 | 5.8424 | 5.8424 | 5.8424 | 5.8424
Expenditure By Asset Class - As Commissioned
| Asset class breakdown | Secondary |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| (fully absorbed) | Switchgear |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| (as commissioned) | Transformers |  | 10558.8458 | 675.5076 | 967.9111 | 0 | 0 | 0 | 0 | 0 | 0 | 12202.2644 | 0
|  | Reactive |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Lines and towers |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Establishment |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Communications |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Non System |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Land |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Easements |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Total incl Overhead - As commissioned $ Mar 2017 |  | 10558.8458 | 675.5076 | 967.9111 | 0 | 0 | 0 | 0 | 0 | 0 | 12202.2644 | 0
|  |  | Check | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0
| Expenditure splits for RIN |  |  |  | 2015-16 | 2016-17 | 2017-18 | 2018-19 | 2019-20 | 2020-21 | 2021-22 | 2022-23
| Repex Category | Transmission Towers | bar: 2015-16 to 2022-23
Transmission Tower Support Structures | bar: 2015-16 to 2022-23
Conductors | bar: 2015-16 to 2022-23
Transmission Cables | bar: 2015-16 to 2022-23
Substation Switchbays | bar: 2015-16 to 2022-23
|  | Substation Power Transformers |  |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
Substation Reactive Plant | bar: 2015-16 to 2022-23
Scada Network Control And Protection Systems | bar: 2015-16 to 2022-23
Other | bar: 2015-16 to 2022-23
|  | Total |  |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
| Direct Expenditures | Materials - $ Mar 2017 |  |  | 2015-16 | 2016-17 | 2017-18 | 2018-19 | 2019-20 | 2020-21 | 2021-22 | 2022-23 | Total | 2017-22 Total
| (As Incurred) | Transmission Towers |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Transmission Tower Support Structures |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Conductors |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Transmission Cables |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Substation Switchbays |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Substation Power Transformers |  |  | 249.2069 | 358.5844 | 0 | 0 | 0 | 0 | 0 | 0 | 607.7913 | 0
|  | Substation Reactive Plant |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Scada Network Control And Protection Systems |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Other |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Total Materials |  |  | 249.2069 | 358.5844 | 0 | 0 | 0 | 0 | 0 | 0 | 607.7913 | 0
|  | Labour (Internal) - $ Mar 2017 |  |  | 2015-16 | 2016-17 | 2017-18 | 2018-19 | 2019-20 | 2020-21 | 2021-22 | 2022-23 | Total | 2017-22 Total
|  | Transmission Towers |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Transmission Tower Support Structures |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Conductors |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Transmission Cables |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Substation Switchbays |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Substation Power Transformers |  |  | 62.3017 | 90.7679 | 0 | 0 | 0 | 0 | 0 | 0 | 153.0696 | 0
|  | Substation Reactive Plant |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Scada Network Control And Protection Systems |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Other |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Total Internal Labour |  |  | 62.3017 | 90.7679 | 0 | 0 | 0 | 0 | 0 | 0 | 153.0696 | 0
|  | Labour (External) - $ Mar 2017 |  |  | 2015-16 | 2016-17 | 2017-18 | 2018-19 | 2019-20 | 2020-21 | 2021-22 | 2022-23 | Total | 2017-22 Total
|  | Transmission Towers |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Transmission Tower Support Structures |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Conductors |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Transmission Cables |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Substation Switchbays |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Substation Power Transformers |  |  | 311.5086 | 453.05 | 0 | 0 | 0 | 0 | 0 | 0 | 764.5586 | 0
|  | Substation Reactive Plant |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Scada Network Control And Protection Systems |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Other |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Total External Labour |  |  | 311.5086 | 453.05 | 0 | 0 | 0 | 0 | 0 | 0 | 764.5586 | 0
|  | Total Direct - $ Mar 2017 |  |  | 2015-16 | 2016-17 | 2017-18 | 2018-19 | 2019-20 | 2020-21 | 2021-22 | 2022-23 | Total | 2017-22 Total
|  | Transmission Towers |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Transmission Tower Support Structures |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Conductors |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Transmission Cables |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Substation Switchbays |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Substation Power Transformers |  |  | 623.0172 | 902.4024 | 0 | 0 | 0 | 0 | 0 | 0 | 1525.4196 | 0
|  | Substation Reactive Plant |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Scada Network Control And Protection Systems |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Other |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Total Direct - $ Mar 2017 |  |  | 623.0172 | 902.4024 | 0 | 0 | 0 | 0 | 0 | 0 | 1525.4196 | 0

## Proj_20
Go To: | Table of Contents
Master Inputs
|  | X834, XC72 |  | Business case? | 0
| Project name | Power transformers - Bushings replacement
| Project category 1 | Network |  |  | Shaded cells = Inputs
| Project category 2 | Replacement - Other
| Regulatory classification | Prescribed
| Overhead Category | Repex_OHD |  | $000's | $000's | $000's | $000's | $000's | $000's | $000's | $000's | $000's | Project | 2017-22
|  |  |  | Prior | 2015-16 | 2016-17 | 2017-18 | 2018-19 | 2019-20 | 2020-21 | 2021-22 | 2022-23 | Total | Total | Check
| Project timing | Direct Expenditure (As incurred) - $ 2015/16 |  | 2162.8671 | -190.9089 | 1752.1671 | 680 | 680 | 680 | 680 | 680 | 0 | 7124.1254 | 3400 | ok
| (excluding real cost escalators) | Assumed year commissioned (no BC) |  | x | bar: 2015-16 to 2022-23
|  | Direct Expenditure (As Commissioned) - $ 2015/16 |  | 2162.8671 | -190.9089 | 1752.1671 | 680 | 680 | 680 | 680 | 680 | 0 | 7124.1254 | 3400 | ok
| Asset class | Secondary
Switchgear
|  | Transformers |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
Reactive
Lines and towers
Establishment
Communications
Non System
Land
Easements
|  |  | Total | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
| Input costs % | Labour - internal |  | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10%
|  | Labour - external |  | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50%
|  | Materials |  | 40% | 40% | 40% | 40% | 40% | 40% | 40% | 40% | 40%
|  |  | Total | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
Material Escalation
| (By Asset Class) | Secondary |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Switchgear |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Transformers |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Reactive |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Lines and towers |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Establishment |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Communications |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Non System |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Land |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Easements |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Total Material escalation |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Labour Escalation | Internal Labour |  | 0 | 0 | 2.1926 | 1.4052 | 1.9674 | 2.5463 | 3.1777 | 3.8255 | 0 | 15.1147 | 12.9221
|  | External Labour |  | 0 | 0 | 9.4198 | 7.2212 | 10.8409 | 14.3757 | 18.2384 | 22.2327 | 0 | 82.3286 | 72.9089
|  | Total Labour Escalation |  | 0 | 0 | 11.6124 | 8.6264 | 12.8083 | 16.922 | 21.4161 | 26.0582 | 0 | 97.4434 | 85.831
|  | Total Escalation |  | 0 | 0 | 11.6124 | 8.6264 | 12.8083 | 16.922 | 21.4161 | 26.0582 | 0 | 97.4434 | 85.831
|  | Escalation factors |  | 0 | 0 | 0.0066275 | 0.012686 | 0.018836 | 0.024885 | 0.031494 | 0.038321 | 0 | 0.013678 | 0.025244
| Direct Expenditure (Escalated) | Total labour - internal |  | 219.9457 | -19.4139 | 180.4106 | 70.5793 | 71.151 | 71.7398 | 72.3819 | 73.0405 | 0 | 739.8351 | 358.8926
| (as incurred) | Total labour - external |  | 1099.7285 | -97.0693 | 900.4837 | 353.0952 | 356.7762 | 360.3707 | 364.2988 | 368.3607 | 0 | 3706.0446 | 1802.9017
|  | Total materials |  | 879.7828 | -77.6554 | 712.7236 | 276.6015 | 276.6015 | 276.6015 | 276.6015 | 276.6015 | 0 | 2897.8585 | 1383.0075
|  | Total Direct - As Incurred $ Mar 2017 |  | 2199.457 | -194.1385 | 1793.6179 | 700.276 | 704.5288 | 708.712 | 713.2822 | 718.0028 | 0 | 7343.7381 | 3544.8018 | ok
| Capitalised Overheads | Overhead rate (applied to direct expenditure) |  | 8.008% | 8.425% | 7.259% | 7.658% | 9.013% | 8.969% | 7.948% | 8.001% | 8.318%
|  | Total overhead (as incurred) |  | 176.1363 | -16.3565 | 130.2053 | 53.6261 | 63.5014 | 63.5614 | 56.6935 | 57.4505 | 0 | 584.8179 | 294.8328
|  | Total incl Overhead - As Incurred $ Mar 2017 |  | 2375.5933 | -210.4951 | 1923.8233 | 753.9021 | 768.0301 | 772.2734 | 769.9757 | 775.4532 | 0 | 7928.556 | 3839.6345
|  | Total overheads (As incurred) - Cumulative |  | 176.1363 | 159.7798 | 289.9851 | 343.6112 | 407.1125 | 470.6739 | 527.3674 | 584.8179 | 584.8179
|  | Labour & Material Escalation - Cumulative |  | 0 | 0 | 11.6124 | 20.2388 | 33.0471 | 49.9691 | 71.3852 | 97.4434 | 97.4434
Expenditure By Asset Class - As Incurred
| Asset class breakdown | Secondary |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| (fully absorbed) | Switchgear |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| (as incurred) | Transformers |  | 2375.5933 | -210.4951 | 1923.8233 | 753.9021 | 768.0301 | 772.2734 | 769.9757 | 775.4532 | 0 | 7928.556 | 3839.6345
|  | Reactive |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Lines and towers |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Establishment |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Communications |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Non System |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Land |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Easements |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Total incl Overhead - As Incurred $ Mar 2017 |  | 2375.5933 | -210.4951 | 1923.8233 | 753.9021 | 768.0301 | 772.2734 | 769.9757 | 775.4532 | 0 | 7928.556 | 3839.6345
|  |  | Check | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| As Commissioned Capex | Direct Expenditure (As Commissioned) - $ 2015/16 |  | 2162.8671 | -190.9089 | 1752.1671 | 680 | 680 | 680 | 680 | 680 | 0 | 7124.1254 | 3400
|  | Labour & Material Escalation - $ 2015/16 |  | 0 | 0 | 11.6124 | 8.6264 | 12.8083 | 16.922 | 21.4161 | 26.0582 | 0 | 97.4434 | 85.831
|  | Total Direct Expenditure - $ 2015/16 |  | 2162.8671 | -190.9089 | 1763.7796 | 688.6264 | 692.8083 | 696.922 | 701.4161 | 706.0582 | 0 | 7221.5688 | 3485.831
|  | Total Direct Expenditure - $ Mar 2017 |  | 2199.457 | -194.1385 | 1793.6179 | 700.276 | 704.5288 | 708.712 | 713.2822 | 718.0028 | 0 | 7343.7381 | 3544.8018
|  | Total overheads (As Commissioned) |  | 176.1363 | -16.3565 | 130.2053 | 53.6261 | 63.5014 | 63.5614 | 56.6935 | 57.4505 | 0 | 584.8179 | 294.8328
|  | Total incl Overhead - As commissioned $ Mar 2017 |  | 2375.5933 | -210.4951 | 1923.8233 | 753.9021 | 768.0301 | 772.2734 | 769.9757 | 775.4532 | 0 | 7928.556 | 3839.6345
|  | Total overheads (As Comm) - Cumulative |  | 176.1363 | 159.7798 | 289.9851 | 343.6112 | 407.1125 | 470.6739 | 527.3674 | 584.8179 | 584.8179
|  | Total real cost escalation (As Comm) - Cumulative |  | 0 | 0 | 11.6124 | 20.2388 | 33.0471 | 49.9691 | 71.3852 | 97.4434 | 97.4434
Expenditure By Asset Class - As Commissioned
| Asset class breakdown | Secondary |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| (fully absorbed) | Switchgear |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| (as commissioned) | Transformers |  | 2375.5933 | -210.4951 | 1923.8233 | 753.9021 | 768.0301 | 772.2734 | 769.9757 | 775.4532 | 0 | 7928.556 | 3839.6345
|  | Reactive |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Lines and towers |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Establishment |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Communications |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Non System |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Land |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Easements |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Total incl Overhead - As commissioned $ Mar 2017 |  | 2375.5933 | -210.4951 | 1923.8233 | 753.9021 | 768.0301 | 772.2734 | 769.9757 | 775.4532 | 0 | 7928.556 | 3839.6345
|  |  | Check | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0
| Expenditure splits for RIN |  |  |  | 2015-16 | 2016-17 | 2017-18 | 2018-19 | 2019-20 | 2020-21 | 2021-22 | 2022-23
| Repex Category | Transmission Towers | bar: 2015-16 to 2022-23
Transmission Tower Support Structures | bar: 2015-16 to 2022-23
Conductors | bar: 2015-16 to 2022-23
Transmission Cables | bar: 2015-16 to 2022-23
Substation Switchbays | bar: 2015-16 to 2022-23
|  | Substation Power Transformers |  |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
Substation Reactive Plant | bar: 2015-16 to 2022-23
Scada Network Control And Protection Systems | bar: 2015-16 to 2022-23
Other | bar: 2015-16 to 2022-23
|  | Total |  |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
| Direct Expenditures | Materials - $ Mar 2017 |  |  | 2015-16 | 2016-17 | 2017-18 | 2018-19 | 2019-20 | 2020-21 | 2021-22 | 2022-23 | Total | 2017-22 Total
| (As Incurred) | Transmission Towers |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Transmission Tower Support Structures |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Conductors |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Transmission Cables |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Substation Switchbays |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Substation Power Transformers |  |  | -77.6554 | 712.7236 | 276.6015 | 276.6015 | 276.6015 | 276.6015 | 276.6015 | 0 | 2018.0757 | 1383.0075
|  | Substation Reactive Plant |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Scada Network Control And Protection Systems |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Other |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Total Materials |  |  | -77.6554 | 712.7236 | 276.6015 | 276.6015 | 276.6015 | 276.6015 | 276.6015 | 0 | 2018.0757 | 1383.0075
|  | Labour (Internal) - $ Mar 2017 |  |  | 2015-16 | 2016-17 | 2017-18 | 2018-19 | 2019-20 | 2020-21 | 2021-22 | 2022-23 | Total | 2017-22 Total
|  | Transmission Towers |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Transmission Tower Support Structures |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Conductors |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Transmission Cables |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Substation Switchbays |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Substation Power Transformers |  |  | -19.4139 | 180.4106 | 70.5793 | 71.151 | 71.7398 | 72.3819 | 73.0405 | 0 | 519.8894 | 358.8926
|  | Substation Reactive Plant |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Scada Network Control And Protection Systems |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Other |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Total Internal Labour |  |  | -19.4139 | 180.4106 | 70.5793 | 71.151 | 71.7398 | 72.3819 | 73.0405 | 0 | 519.8894 | 358.8926
|  | Labour (External) - $ Mar 2017 |  |  | 2015-16 | 2016-17 | 2017-18 | 2018-19 | 2019-20 | 2020-21 | 2021-22 | 2022-23 | Total | 2017-22 Total
|  | Transmission Towers |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Transmission Tower Support Structures |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Conductors |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Transmission Cables |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Substation Switchbays |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Substation Power Transformers |  |  | -97.0693 | 900.4837 | 353.0952 | 356.7762 | 360.3707 | 364.2988 | 368.3607 | 0 | 2606.3161 | 1802.9017
|  | Substation Reactive Plant |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Scada Network Control And Protection Systems |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Other |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Total External Labour |  |  | -97.0693 | 900.4837 | 353.0952 | 356.7762 | 360.3707 | 364.2988 | 368.3607 | 0 | 2606.3161 | 1802.9017
|  | Total Direct - $ Mar 2017 |  |  | 2015-16 | 2016-17 | 2017-18 | 2018-19 | 2019-20 | 2020-21 | 2021-22 | 2022-23 | Total | 2017-22 Total
|  | Transmission Towers |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Transmission Tower Support Structures |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Conductors |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Transmission Cables |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Substation Switchbays |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Substation Power Transformers |  |  | -194.1385 | 1793.6179 | 700.276 | 704.5288 | 708.712 | 713.2822 | 718.0028 | 0 | 5144.2812 | 3544.8018
|  | Substation Reactive Plant |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Scada Network Control And Protection Systems |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Other |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Total Direct - $ Mar 2017 |  |  | -194.1385 | 1793.6179 | 700.276 | 704.5288 | 708.712 | 713.2822 | 718.0028 | 0 | 5144.2812 | 3544.8018

## Proj_21
Go To: | Table of Contents
Master Inputs
|  |  |  | Business case? | 0
| Project name | Power transformers - life extension
| Project category 1 | Network |  |  | Shaded cells = Inputs
| Project category 2 | Replacement - Other
| Regulatory classification | Prescribed
| Overhead Category | Repex_OHD |  | $000's | $000's | $000's | $000's | $000's | $000's | $000's | $000's | $000's | Project | 2017-22
|  |  |  | Prior | 2015-16 | 2016-17 | 2017-18 | 2018-19 | 2019-20 | 2020-21 | 2021-22 | 2022-23 | Total | Total | Check
| Project timing | Direct Expenditure (As incurred) - $ 2015/16 |  | 0 | 0 | 0 | 1256 | 1256 | 1256 | 1256 | 1256 | 0 | 6280 | 6280 | ok
| (excluding real cost escalators) | Assumed year commissioned (no BC) | bar: 2015-16 to 2022-23
|  | Direct Expenditure (As Commissioned) - $ 2015/16 |  | 0 | 0 | 0 | 1256 | 1256 | 1256 | 1256 | 1256 | 0 | 6280 | 6280 | ok
| Asset class | Secondary
Switchgear
|  | Transformers |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
Reactive
Lines and towers
Establishment
Communications
Non System
Land
Easements
|  |  | Total | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
| Input costs % | Labour - internal |  | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10%
|  | Labour - external |  | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50%
|  | Materials |  | 40% | 40% | 40% | 40% | 40% | 40% | 40% | 40% | 40%
|  |  | Total | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
Material Escalation
| (By Asset Class) | Secondary |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Switchgear |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Transformers |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Reactive |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Lines and towers |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Establishment |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Communications |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Non System |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Land |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Easements |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Total Material escalation |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Labour Escalation | Internal Labour |  | 0 | 0 | 0 | 2.5955 | 3.6338 | 4.7033 | 5.8695 | 7.0658 | 0 | 23.8679 | 23.8679
|  | External Labour |  | 0 | 0 | 0 | 13.3379 | 20.0239 | 26.5527 | 33.6873 | 41.0651 | 0 | 134.6669 | 134.6669
|  | Total Labour Escalation |  | 0 | 0 | 0 | 15.9334 | 23.6577 | 31.256 | 39.5568 | 48.131 | 0 | 158.5348 | 158.5348
|  | Total Escalation |  | 0 | 0 | 0 | 15.9334 | 23.6577 | 31.256 | 39.5568 | 48.131 | 0 | 158.5348 | 158.5348
|  | Escalation factors |  | 0 | 0 | 0 | 0.012686 | 0.018836 | 0.024885 | 0.031494 | 0.038321 | 0 | 0.025244 | 0.025244
| Direct Expenditure (Escalated) | Total labour - internal |  | 0 | 0 | 0 | 130.3642 | 131.4201 | 132.5076 | 133.6936 | 134.9102 | 0 | 662.8957 | 662.8957
| (as incurred) | Total labour - external |  | 0 | 0 | 0 | 652.1876 | 658.9867 | 665.626 | 672.8813 | 680.3839 | 0 | 3330.0654 | 3330.0654
|  | Total materials |  | 0 | 0 | 0 | 510.8992 | 510.8992 | 510.8992 | 510.8992 | 510.8992 | 0 | 2554.4962 | 2554.4962
|  | Total Direct - As Incurred $ Mar 2017 |  | 0 | 0 | 0 | 1293.451 | 1301.3061 | 1309.0328 | 1317.4741 | 1326.1933 | 0 | 6547.4574 | 6547.4574 | ok
| Capitalised Overheads | Overhead rate (applied to direct expenditure) |  | 8.008% | 8.425% | 7.259% | 7.658% | 9.013% | 8.969% | 7.948% | 8.001% | 8.318%
|  | Total overhead (as incurred) |  | 0 | 0 | 0 | 99.0505 | 117.2908 | 117.4016 | 104.7162 | 106.1144 | 0 | 544.5734 | 544.5734
|  | Total incl Overhead - As Incurred $ Mar 2017 |  | 0 | 0 | 0 | 1392.5015 | 1418.5968 | 1426.4344 | 1422.1903 | 1432.3077 | 0 | 7092.0308 | 7092.0308
|  | Total overheads (As incurred) - Cumulative |  | 0 | 0 | 0 | 99.0505 | 216.3412 | 333.7428 | 438.4591 | 544.5734 | 544.5734
|  | Labour & Material Escalation - Cumulative |  | 0 | 0 | 0 | 15.9334 | 39.5911 | 70.847 | 110.4038 | 158.5348 | 158.5348
Expenditure By Asset Class - As Incurred
| Asset class breakdown | Secondary |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| (fully absorbed) | Switchgear |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| (as incurred) | Transformers |  | 0 | 0 | 0 | 1392.5015 | 1418.5968 | 1426.4344 | 1422.1903 | 1432.3077 | 0 | 7092.0308 | 7092.0308
|  | Reactive |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Lines and towers |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Establishment |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Communications |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Non System |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Land |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Easements |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Total incl Overhead - As Incurred $ Mar 2017 |  | 0 | 0 | 0 | 1392.5015 | 1418.5968 | 1426.4344 | 1422.1903 | 1432.3077 | 0 | 7092.0308 | 7092.0308
|  |  | Check | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| As Commissioned Capex | Direct Expenditure (As Commissioned) - $ 2015/16 |  | 0 | 0 | 0 | 1256 | 1256 | 1256 | 1256 | 1256 | 0 | 6280 | 6280
|  | Labour & Material Escalation - $ 2015/16 |  | 0 | 0 | 0 | 15.9334 | 23.6577 | 31.256 | 39.5568 | 48.131 | 0 | 158.5348 | 158.5348
|  | Total Direct Expenditure - $ 2015/16 |  | 0 | 0 | 0 | 1271.9334 | 1279.6577 | 1287.256 | 1295.5568 | 1304.131 | 0 | 6438.5348 | 6438.5348
|  | Total Direct Expenditure - $ Mar 2017 |  | 0 | 0 | 0 | 1293.451 | 1301.3061 | 1309.0328 | 1317.4741 | 1326.1933 | 0 | 6547.4574 | 6547.4574
|  | Total overheads (As Commissioned) |  | 0 | 0 | 0 | 99.0505 | 117.2908 | 117.4016 | 104.7162 | 106.1144 | 0 | 544.5734 | 544.5734
|  | Total incl Overhead - As commissioned $ Mar 2017 |  | 0 | 0 | 0 | 1392.5015 | 1418.5968 | 1426.4344 | 1422.1903 | 1432.3077 | 0 | 7092.0308 | 7092.0308
|  | Total overheads (As Comm) - Cumulative |  | 0 | 0 | 0 | 99.0505 | 216.3412 | 333.7428 | 438.4591 | 544.5734 | 544.5734
|  | Total real cost escalation (As Comm) - Cumulative |  | 0 | 0 | 0 | 15.9334 | 39.5911 | 70.847 | 110.4038 | 158.5348 | 158.5348
Expenditure By Asset Class - As Commissioned
| Asset class breakdown | Secondary |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| (fully absorbed) | Switchgear |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| (as commissioned) | Transformers |  | 0 | 0 | 0 | 1392.5015 | 1418.5968 | 1426.4344 | 1422.1903 | 1432.3077 | 0 | 7092.0308 | 7092.0308
|  | Reactive |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Lines and towers |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Establishment |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Communications |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Non System |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Land |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Easements |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Total incl Overhead - As commissioned $ Mar 2017 |  | 0 | 0 | 0 | 1392.5015 | 1418.5968 | 1426.4344 | 1422.1903 | 1432.3077 | 0 | 7092.0308 | 7092.0308
|  |  | Check | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0
| Expenditure splits for RIN |  |  |  | 2015-16 | 2016-17 | 2017-18 | 2018-19 | 2019-20 | 2020-21 | 2021-22 | 2022-23
| Repex Category | Transmission Towers | bar: 2015-16 to 2022-23
Transmission Tower Support Structures | bar: 2015-16 to 2022-23
Conductors | bar: 2015-16 to 2022-23
Transmission Cables | bar: 2015-16 to 2022-23
Substation Switchbays | bar: 2015-16 to 2022-23
|  | Substation Power Transformers |  |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
Substation Reactive Plant | bar: 2015-16 to 2022-23
Scada Network Control And Protection Systems | bar: 2015-16 to 2022-23
Other | bar: 2015-16 to 2022-23
|  | Total |  |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
| Direct Expenditures | Materials - $ Mar 2017 |  |  | 2015-16 | 2016-17 | 2017-18 | 2018-19 | 2019-20 | 2020-21 | 2021-22 | 2022-23 | Total | 2017-22 Total
| (As Incurred) | Transmission Towers |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Transmission Tower Support Structures |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Conductors |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Transmission Cables |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Substation Switchbays |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Substation Power Transformers |  |  | 0 | 0 | 510.8992 | 510.8992 | 510.8992 | 510.8992 | 510.8992 | 0 | 2554.4962 | 2554.4962
|  | Substation Reactive Plant |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Scada Network Control And Protection Systems |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Other |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Total Materials |  |  | 0 | 0 | 510.8992 | 510.8992 | 510.8992 | 510.8992 | 510.8992 | 0 | 2554.4962 | 2554.4962
|  | Labour (Internal) - $ Mar 2017 |  |  | 2015-16 | 2016-17 | 2017-18 | 2018-19 | 2019-20 | 2020-21 | 2021-22 | 2022-23 | Total | 2017-22 Total
|  | Transmission Towers |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Transmission Tower Support Structures |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Conductors |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Transmission Cables |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Substation Switchbays |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Substation Power Transformers |  |  | 0 | 0 | 130.3642 | 131.4201 | 132.5076 | 133.6936 | 134.9102 | 0 | 662.8957 | 662.8957
|  | Substation Reactive Plant |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Scada Network Control And Protection Systems |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Other |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Total Internal Labour |  |  | 0 | 0 | 130.3642 | 131.4201 | 132.5076 | 133.6936 | 134.9102 | 0 | 662.8957 | 662.8957
|  | Labour (External) - $ Mar 2017 |  |  | 2015-16 | 2016-17 | 2017-18 | 2018-19 | 2019-20 | 2020-21 | 2021-22 | 2022-23 | Total | 2017-22 Total
|  | Transmission Towers |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Transmission Tower Support Structures |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Conductors |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Transmission Cables |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Substation Switchbays |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Substation Power Transformers |  |  | 0 | 0 | 652.1876 | 658.9867 | 665.626 | 672.8813 | 680.3839 | 0 | 3330.0654 | 3330.0654
|  | Substation Reactive Plant |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Scada Network Control And Protection Systems |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Other |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Total External Labour |  |  | 0 | 0 | 652.1876 | 658.9867 | 665.626 | 672.8813 | 680.3839 | 0 | 3330.0654 | 3330.0654
|  | Total Direct - $ Mar 2017 |  |  | 2015-16 | 2016-17 | 2017-18 | 2018-19 | 2019-20 | 2020-21 | 2021-22 | 2022-23 | Total | 2017-22 Total
|  | Transmission Towers |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Transmission Tower Support Structures |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Conductors |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Transmission Cables |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Substation Switchbays |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Substation Power Transformers |  |  | 0 | 0 | 1293.451 | 1301.3061 | 1309.0328 | 1317.4741 | 1326.1933 | 0 | 6547.4574 | 6547.4574
|  | Substation Reactive Plant |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Scada Network Control And Protection Systems |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Other |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Total Direct - $ Mar 2017 |  |  | 0 | 0 | 1293.451 | 1301.3061 | 1309.0328 | 1317.4741 | 1326.1933 | 0 | 6547.4574 | 6547.4574

## Proj_22
Go To: | Table of Contents
Master Inputs
|  | XC69 |  | Business case? | 0
| Project name | Power transformers - improved safe access
| Project category 1 | Network |  |  | Shaded cells = Inputs
| Project category 2 | Security and Compliance
| Regulatory classification | Prescribed
| Overhead Category | Repex_OHD |  | $000's | $000's | $000's | $000's | $000's | $000's | $000's | $000's | $000's | Project | 2017-22
|  |  |  | Prior | 2015-16 | 2016-17 | 2017-18 | 2018-19 | 2019-20 | 2020-21 | 2021-22 | 2022-23 | Total | Total | Check
| Project timing | Direct Expenditure (As incurred) - $ 2015/16 |  | 0 | 10.3732 | 1001.7588 | 500 | 500 | 500 | 500 | 500 | 0 | 3512.132 | 2500 | ok
| (excluding real cost escalators) | Assumed year commissioned (no BC) | bar: 2015-16 to 2022-23
|  | Direct Expenditure (As Commissioned) - $ 2015/16 |  | 0 | 0 | 1012.132 | 500 | 500 | 500 | 500 | 500 | 0 | 3512.132 | 2500 | ok
| Asset class | Secondary
Switchgear
|  | Transformers |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
Reactive
Lines and towers
Establishment
Communications
Non System
Land
Easements
|  |  | Total | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
| Input costs % | Labour - internal |  | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10%
|  | Labour - external |  | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50%
|  | Materials |  | 40% | 40% | 40% | 40% | 40% | 40% | 40% | 40% | 40%
|  |  | Total | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
Material Escalation
| (By Asset Class) | Secondary |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Switchgear |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Transformers |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Reactive |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Lines and towers |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Establishment |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Communications |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Non System |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Land |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Easements |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Total Material escalation |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Labour Escalation | Internal Labour |  | 0 | 0 | 1.2536 | 1.0332 | 1.4466 | 1.8723 | 2.3366 | 2.8128 | 0 | 10.7551 | 9.5015
|  | External Labour |  | 0 | 0 | 5.3855 | 5.3097 | 7.9713 | 10.5703 | 13.4106 | 16.3476 | 0 | 58.995 | 53.6095
|  | Total Labour Escalation |  | 0 | 0 | 6.6391 | 6.3429 | 9.4179 | 12.4427 | 15.7471 | 19.1604 | 0 | 69.7501 | 63.111
|  | Total Escalation |  | 0 | 0 | 6.6391 | 6.3429 | 9.4179 | 12.4427 | 15.7471 | 19.1604 | 0 | 69.7501 | 63.111
|  | Escalation factors |  | 0 | 0 | 0.0066275 | 0.012686 | 0.018836 | 0.024885 | 0.031494 | 0.038321 | 0 | 0.01986 | 0.025244
| Direct Expenditure (Escalated) | Total labour - internal |  | 0 | 1.0549 | 103.1454 | 51.8966 | 52.3169 | 52.7499 | 53.222 | 53.7063 | 0 | 368.0918 | 263.8916
| (as incurred) | Total labour - external |  | 0 | 5.2744 | 514.8295 | 259.6288 | 262.3355 | 264.9785 | 267.8668 | 270.8535 | 0 | 1845.7669 | 1325.663
|  | Total materials |  | 0 | 4.2195 | 407.4823 | 203.3835 | 203.3835 | 203.3835 | 203.3835 | 203.3835 | 0 | 1428.6191 | 1016.9173
|  | Total Direct - As Incurred $ Mar 2017 |  | 0 | 10.5487 | 1025.4572 | 514.9089 | 518.0358 | 521.1118 | 524.4722 | 527.9432 | 0 | 3642.4778 | 2606.4719 | ok
| Capitalised Overheads | Overhead rate (applied to direct expenditure) |  | 8.008% | 8.425% | 7.259% | 7.658% | 9.013% | 8.969% | 7.948% | 8.001% | 8.318%
|  | Total overhead (as incurred) |  | 0 | 0.88875 | 74.4417 | 39.4309 | 46.6922 | 46.7363 | 41.6864 | 42.243 | 0 | 292.1193 | 216.7888
|  | Total incl Overhead - As Incurred $ Mar 2017 |  | 0 | 11.4375 | 1099.899 | 554.3398 | 564.728 | 567.8481 | 566.1586 | 570.1862 | 0 | 3934.5971 | 2823.2607
|  | Total overheads (As incurred) - Cumulative |  | 0 | 0.88875 | 75.3305 | 114.7614 | 161.4536 | 208.1899 | 249.8763 | 292.1193 | 292.1193
|  | Labour & Material Escalation - Cumulative |  | 0 | 0 | 6.6391 | 12.982 | 22.3999 | 34.8426 | 50.5897 | 69.7501 | 69.7501
Expenditure By Asset Class - As Incurred
| Asset class breakdown | Secondary |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| (fully absorbed) | Switchgear |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| (as incurred) | Transformers |  | 0 | 11.4375 | 1099.899 | 554.3398 | 564.728 | 567.8481 | 566.1586 | 570.1862 | 0 | 3934.5971 | 2823.2607
|  | Reactive |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Lines and towers |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Establishment |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Communications |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Non System |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Land |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Easements |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Total incl Overhead - As Incurred $ Mar 2017 |  | 0 | 11.4375 | 1099.899 | 554.3398 | 564.728 | 567.8481 | 566.1586 | 570.1862 | 0 | 3934.5971 | 2823.2607
|  |  | Check | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| As Commissioned Capex | Direct Expenditure (As Commissioned) - $ 2015/16 |  | 0 | 0 | 1012.132 | 500 | 500 | 500 | 500 | 500 | 0 | 3512.132 | 2500
|  | Labour & Material Escalation - $ 2015/16 |  | 0 | 0 | 6.6391 | 6.3429 | 9.4179 | 12.4427 | 15.7471 | 19.1604 | 0 | 69.7501 | 63.111
|  | Total Direct Expenditure - $ 2015/16 |  | 0 | 0 | 1018.7711 | 506.3429 | 509.4179 | 512.4427 | 515.7471 | 519.1604 | 0 | 3581.8821 | 2563.111
|  | Total Direct Expenditure - $ Mar 2017 |  | 0 | 0 | 1036.0059 | 514.9089 | 518.0358 | 521.1118 | 524.4722 | 527.9432 | 0 | 3642.4778 | 2606.4719
|  | Total overheads (As Commissioned) |  | 0 | 0 | 75.3305 | 39.4309 | 46.6922 | 46.7363 | 41.6864 | 42.243 | 0 | 292.1193 | 216.7888
|  | Total incl Overhead - As commissioned $ Mar 2017 |  | 0 | 0 | 1111.3364 | 554.3398 | 564.728 | 567.8481 | 566.1586 | 570.1862 | 0 | 3934.5971 | 2823.2607
|  | Total overheads (As Comm) - Cumulative |  | 0 | 0 | 75.3305 | 114.7614 | 161.4536 | 208.1899 | 249.8763 | 292.1193 | 292.1193
|  | Total real cost escalation (As Comm) - Cumulative |  | 0 | 0 | 6.6391 | 12.982 | 22.3999 | 34.8426 | 50.5897 | 69.7501 | 69.7501
Expenditure By Asset Class - As Commissioned
| Asset class breakdown | Secondary |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| (fully absorbed) | Switchgear |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| (as commissioned) | Transformers |  | 0 | 0 | 1111.3364 | 554.3398 | 564.728 | 567.8481 | 566.1586 | 570.1862 | 0 | 3934.5971 | 2823.2607
|  | Reactive |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Lines and towers |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Establishment |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Communications |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Non System |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Land |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Easements |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Total incl Overhead - As commissioned $ Mar 2017 |  | 0 | 0 | 1111.3364 | 554.3398 | 564.728 | 567.8481 | 566.1586 | 570.1862 | 0 | 3934.5971 | 2823.2607
|  |  | Check | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0
| Expenditure splits for RIN |  |  |  | 2015-16 | 2016-17 | 2017-18 | 2018-19 | 2019-20 | 2020-21 | 2021-22 | 2022-23
| Repex Category | Transmission Towers | bar: 2015-16 to 2022-23
Transmission Tower Support Structures | bar: 2015-16 to 2022-23
Conductors | bar: 2015-16 to 2022-23
Transmission Cables | bar: 2015-16 to 2022-23
Substation Switchbays | bar: 2015-16 to 2022-23
|  | Substation Power Transformers |  |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
Substation Reactive Plant | bar: 2015-16 to 2022-23
Scada Network Control And Protection Systems | bar: 2015-16 to 2022-23
Other | bar: 2015-16 to 2022-23
|  | Total |  |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
| Direct Expenditures | Materials - $ Mar 2017 |  |  | 2015-16 | 2016-17 | 2017-18 | 2018-19 | 2019-20 | 2020-21 | 2021-22 | 2022-23 | Total | 2017-22 Total
| (As Incurred) | Transmission Towers |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Transmission Tower Support Structures |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Conductors |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Transmission Cables |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Substation Switchbays |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Substation Power Transformers |  |  | 4.2195 | 407.4823 | 203.3835 | 203.3835 | 203.3835 | 203.3835 | 203.3835 | 0 | 1428.6191 | 1016.9173
|  | Substation Reactive Plant |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Scada Network Control And Protection Systems |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Other |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Total Materials |  |  | 4.2195 | 407.4823 | 203.3835 | 203.3835 | 203.3835 | 203.3835 | 203.3835 | 0 | 1428.6191 | 1016.9173
|  | Labour (Internal) - $ Mar 2017 |  |  | 2015-16 | 2016-17 | 2017-18 | 2018-19 | 2019-20 | 2020-21 | 2021-22 | 2022-23 | Total | 2017-22 Total
|  | Transmission Towers |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Transmission Tower Support Structures |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Conductors |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Transmission Cables |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Substation Switchbays |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Substation Power Transformers |  |  | 1.0549 | 103.1454 | 51.8966 | 52.3169 | 52.7499 | 53.222 | 53.7063 | 0 | 368.0918 | 263.8916
|  | Substation Reactive Plant |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Scada Network Control And Protection Systems |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Other |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Total Internal Labour |  |  | 1.0549 | 103.1454 | 51.8966 | 52.3169 | 52.7499 | 53.222 | 53.7063 | 0 | 368.0918 | 263.8916
|  | Labour (External) - $ Mar 2017 |  |  | 2015-16 | 2016-17 | 2017-18 | 2018-19 | 2019-20 | 2020-21 | 2021-22 | 2022-23 | Total | 2017-22 Total
|  | Transmission Towers |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Transmission Tower Support Structures |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Conductors |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Transmission Cables |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Substation Switchbays |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Substation Power Transformers |  |  | 5.2744 | 514.8295 | 259.6288 | 262.3355 | 264.9785 | 267.8668 | 270.8535 | 0 | 1845.7669 | 1325.663
|  | Substation Reactive Plant |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Scada Network Control And Protection Systems |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Other |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Total External Labour |  |  | 5.2744 | 514.8295 | 259.6288 | 262.3355 | 264.9785 | 267.8668 | 270.8535 | 0 | 1845.7669 | 1325.663
|  | Total Direct - $ Mar 2017 |  |  | 2015-16 | 2016-17 | 2017-18 | 2018-19 | 2019-20 | 2020-21 | 2021-22 | 2022-23 | Total | 2017-22 Total
|  | Transmission Towers |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Transmission Tower Support Structures |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Conductors |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Transmission Cables |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Substation Switchbays |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Substation Power Transformers |  |  | 10.5487 | 1025.4572 | 514.9089 | 518.0358 | 521.1118 | 524.4722 | 527.9432 | 0 | 3642.4778 | 2606.4719
|  | Substation Reactive Plant |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Scada Network Control And Protection Systems |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Other |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Total Direct - $ Mar 2017 |  |  | 10.5487 | 1025.4572 | 514.9089 | 518.0358 | 521.1118 | 524.4722 | 527.9432 | 0 | 3642.4778 | 2606.4719

## Proj_23
Go To: | Table of Contents
Master Inputs
|  |  |  | Business case? | 0
| Project name | Circuit breakers
| Project category 1 | Network |  |  | Shaded cells = Inputs
| Project category 2 | Replacement - Other
| Regulatory classification | Prescribed
| Overhead Category | Repex_OHD |  | $000's | $000's | $000's | $000's | $000's | $000's | $000's | $000's | $000's | Project | 2017-22
|  |  |  | Prior | 2015-16 | 2016-17 | 2017-18 | 2018-19 | 2019-20 | 2020-21 | 2021-22 | 2022-23 | Total | Total | Check
| Project timing | Direct Expenditure (As incurred) - $ 2015/16 |  | 1831.3157 | 2149.4687 | 1001.7588 | 5922.4 | 5922.4 | 5922.4 | 5922.4 | 5922.4 | 0 | 34594.5432 | 29612 | ok
| (excluding real cost escalators) | Assumed year commissioned (no BC) |  | x | bar: 2015-16 to 2022-23
|  | Direct Expenditure (As Commissioned) - $ 2015/16 |  | 1831.3157 | 2149.4687 | 1001.7588 | 5922.4 | 5922.4 | 5922.4 | 5922.4 | 5922.4 | 0 | 34594.5432 | 29612 | ok
| Asset class | Secondary
|  | Switchgear |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
Transformers
Reactive
Lines and towers
Establishment
Communications
Non System
Land
Easements
|  |  | Total | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
| Input costs % | Labour - internal |  | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10%
|  | Labour - external |  | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50%
|  | Materials |  | 40% | 40% | 40% | 40% | 40% | 40% | 40% | 40% | 40%
|  |  | Total | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
Material Escalation
| (By Asset Class) | Secondary |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Switchgear |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Transformers |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Reactive |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Lines and towers |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Establishment |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Communications |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Non System |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Land |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Easements |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Total Material escalation |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Labour Escalation | Internal Labour |  | 0 | 0 | 1.2536 | 12.2383 | 17.1346 | 22.1772 | 27.6762 | 33.3175 | 0 | 113.7975 | 112.5439
|  | External Labour |  | 0 | 0 | 5.3855 | 62.8921 | 94.4182 | 125.2036 | 158.8454 | 193.6339 | 0 | 640.3788 | 634.9932
|  | Total Labour Escalation |  | 0 | 0 | 6.6391 | 75.1304 | 111.5529 | 147.3808 | 186.5216 | 226.9514 | 0 | 754.1762 | 747.5371
|  | Total Escalation |  | 0 | 0 | 6.6391 | 75.1304 | 111.5529 | 147.3808 | 186.5216 | 226.9514 | 0 | 754.1762 | 747.5371
|  | Escalation factors |  | 0 | 0 | 0.0066275 | 0.012686 | 0.018836 | 0.024885 | 0.031494 | 0.038321 | 0 | 0.0218 | 0.025244
| Direct Expenditure (Escalated) | Total labour - internal |  | 186.2297 | 218.5832 | 103.1454 | 614.7045 | 619.6836 | 624.8115 | 630.4035 | 636.1402 | 0 | 3633.7015 | 3125.7433
| (as incurred) | Total labour - external |  | 931.1483 | 1092.916 | 514.8295 | 3075.2515 | 3107.311 | 3138.6172 | 3172.8281 | 3208.2052 | 0 | 18241.1069 | 15702.213
|  | Total materials |  | 744.9186 | 874.3328 | 407.4823 | 2409.0364 | 2409.0364 | 2409.0364 | 2409.0364 | 2409.0364 | 0 | 14071.9157 | 12045.182
|  | Total Direct - As Incurred $ Mar 2017 |  | 1862.2966 | 2185.8319 | 1025.4572 | 6098.9924 | 6136.031 | 6172.4651 | 6212.2681 | 6253.3818 | 0 | 35946.7241 | 30873.1383 | ok
| Capitalised Overheads | Overhead rate (applied to direct expenditure) |  | 8.008% | 8.425% | 7.259% | 7.658% | 9.013% | 8.969% | 7.948% | 8.001% | 8.318%
|  | Total overhead (as incurred) |  | 149.1359 | 184.1604 | 74.4417 | 467.0514 | 553.0596 | 553.5822 | 493.7671 | 500.3596 | 0 | 2975.5578 | 2567.8198
|  | Total incl Overhead - As Incurred $ Mar 2017 |  | 2011.4325 | 2369.9923 | 1099.899 | 6566.0438 | 6689.0906 | 6726.0473 | 6706.0351 | 6753.7414 | 0 | 38922.2819 | 33440.9581
|  | Total overheads (As incurred) - Cumulative |  | 149.1359 | 333.2963 | 407.738 | 874.7893 | 1427.8489 | 1981.4311 | 2475.1982 | 2975.5578 | 2975.5578
|  | Labour & Material Escalation - Cumulative |  | 0 | 0 | 6.6391 | 81.7696 | 193.3224 | 340.7032 | 527.2249 | 754.1762 | 754.1762
Expenditure By Asset Class - As Incurred
| Asset class breakdown | Secondary |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| (fully absorbed) | Switchgear |  | 2011.4325 | 2369.9923 | 1099.899 | 6566.0438 | 6689.0906 | 6726.0473 | 6706.0351 | 6753.7414 | 0 | 38922.2819 | 33440.9581
| (as incurred) | Transformers |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Reactive |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Lines and towers |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Establishment |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Communications |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Non System |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Land |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Easements |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Total incl Overhead - As Incurred $ Mar 2017 |  | 2011.4325 | 2369.9923 | 1099.899 | 6566.0438 | 6689.0906 | 6726.0473 | 6706.0351 | 6753.7414 | 0 | 38922.2819 | 33440.9581
|  |  | Check | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| As Commissioned Capex | Direct Expenditure (As Commissioned) - $ 2015/16 |  | 1831.3157 | 2149.4687 | 1001.7588 | 5922.4 | 5922.4 | 5922.4 | 5922.4 | 5922.4 | 0 | 34594.5432 | 29612
|  | Labour & Material Escalation - $ 2015/16 |  | 0 | 0 | 6.6391 | 75.1304 | 111.5529 | 147.3808 | 186.5216 | 226.9514 | 0 | 754.1762 | 747.5371
|  | Total Direct Expenditure - $ 2015/16 |  | 1831.3157 | 2149.4687 | 1008.3979 | 5997.5304 | 6033.9529 | 6069.7808 | 6108.9216 | 6149.3514 | 0 | 35348.7194 | 30359.5371
|  | Total Direct Expenditure - $ Mar 2017 |  | 1862.2966 | 2185.8319 | 1025.4572 | 6098.9924 | 6136.031 | 6172.4651 | 6212.2681 | 6253.3818 | 0 | 35946.7241 | 30873.1383
|  | Total overheads (As Commissioned) |  | 149.1359 | 184.1604 | 74.4417 | 467.0514 | 553.0596 | 553.5822 | 493.7671 | 500.3596 | 0 | 2975.5578 | 2567.8198
|  | Total incl Overhead - As commissioned $ Mar 2017 |  | 2011.4325 | 2369.9923 | 1099.899 | 6566.0438 | 6689.0906 | 6726.0473 | 6706.0351 | 6753.7414 | 0 | 38922.2819 | 33440.9581
|  | Total overheads (As Comm) - Cumulative |  | 149.1359 | 333.2963 | 407.738 | 874.7893 | 1427.8489 | 1981.4311 | 2475.1982 | 2975.5578 | 2975.5578
|  | Total real cost escalation (As Comm) - Cumulative |  | 0 | 0 | 6.6391 | 81.7696 | 193.3224 | 340.7032 | 527.2249 | 754.1762 | 754.1762
Expenditure By Asset Class - As Commissioned
| Asset class breakdown | Secondary |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| (fully absorbed) | Switchgear |  | 2011.4325 | 2369.9923 | 1099.899 | 6566.0438 | 6689.0906 | 6726.0473 | 6706.0351 | 6753.7414 | 0 | 38922.2819 | 33440.9581
| (as commissioned) | Transformers |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Reactive |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Lines and towers |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Establishment |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Communications |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Non System |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Land |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Easements |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Total incl Overhead - As commissioned $ Mar 2017 |  | 2011.4325 | 2369.9923 | 1099.899 | 6566.0438 | 6689.0906 | 6726.0473 | 6706.0351 | 6753.7414 | 0 | 38922.2819 | 33440.9581
|  |  | Check | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0
| Expenditure splits for RIN |  |  |  | 2015-16 | 2016-17 | 2017-18 | 2018-19 | 2019-20 | 2020-21 | 2021-22 | 2022-23
| Repex Category | Transmission Towers | bar: 2015-16 to 2022-23
Transmission Tower Support Structures | bar: 2015-16 to 2022-23
Conductors | bar: 2015-16 to 2022-23
Transmission Cables | bar: 2015-16 to 2022-23
|  | Substation Switchbays |  |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
Substation Power Transformers | bar: 2015-16 to 2022-23
Substation Reactive Plant | bar: 2015-16 to 2022-23
Scada Network Control And Protection Systems | bar: 2015-16 to 2022-23
Other | bar: 2015-16 to 2022-23
|  | Total |  |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
| Direct Expenditures | Materials - $ Mar 2017 |  |  | 2015-16 | 2016-17 | 2017-18 | 2018-19 | 2019-20 | 2020-21 | 2021-22 | 2022-23 | Total | 2017-22 Total
| (As Incurred) | Transmission Towers |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Transmission Tower Support Structures |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Conductors |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Transmission Cables |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Substation Switchbays |  |  | 874.3328 | 407.4823 | 2409.0364 | 2409.0364 | 2409.0364 | 2409.0364 | 2409.0364 | 0 | 13326.997 | 12045.182
|  | Substation Power Transformers |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Substation Reactive Plant |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Scada Network Control And Protection Systems |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Other |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Total Materials |  |  | 874.3328 | 407.4823 | 2409.0364 | 2409.0364 | 2409.0364 | 2409.0364 | 2409.0364 | 0 | 13326.997 | 12045.182
|  | Labour (Internal) - $ Mar 2017 |  |  | 2015-16 | 2016-17 | 2017-18 | 2018-19 | 2019-20 | 2020-21 | 2021-22 | 2022-23 | Total | 2017-22 Total
|  | Transmission Towers |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Transmission Tower Support Structures |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Conductors |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Transmission Cables |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Substation Switchbays |  |  | 218.5832 | 103.1454 | 614.7045 | 619.6836 | 624.8115 | 630.4035 | 636.1402 | 0 | 3447.4719 | 3125.7433
|  | Substation Power Transformers |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Substation Reactive Plant |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Scada Network Control And Protection Systems |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Other |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Total Internal Labour |  |  | 218.5832 | 103.1454 | 614.7045 | 619.6836 | 624.8115 | 630.4035 | 636.1402 | 0 | 3447.4719 | 3125.7433
|  | Labour (External) - $ Mar 2017 |  |  | 2015-16 | 2016-17 | 2017-18 | 2018-19 | 2019-20 | 2020-21 | 2021-22 | 2022-23 | Total | 2017-22 Total
|  | Transmission Towers |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Transmission Tower Support Structures |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Conductors |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Transmission Cables |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Substation Switchbays |  |  | 1092.916 | 514.8295 | 3075.2515 | 3107.311 | 3138.6172 | 3172.8281 | 3208.2052 | 0 | 17309.9586 | 15702.213
|  | Substation Power Transformers |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Substation Reactive Plant |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Scada Network Control And Protection Systems |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Other |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Total External Labour |  |  | 1092.916 | 514.8295 | 3075.2515 | 3107.311 | 3138.6172 | 3172.8281 | 3208.2052 | 0 | 17309.9586 | 15702.213
|  | Total Direct - $ Mar 2017 |  |  | 2015-16 | 2016-17 | 2017-18 | 2018-19 | 2019-20 | 2020-21 | 2021-22 | 2022-23 | Total | 2017-22 Total
|  | Transmission Towers |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Transmission Tower Support Structures |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Conductors |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Transmission Cables |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Substation Switchbays |  |  | 2185.8319 | 1025.4572 | 6098.9924 | 6136.031 | 6172.4651 | 6212.2681 | 6253.3818 | 0 | 34084.4275 | 30873.1383
|  | Substation Power Transformers |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Substation Reactive Plant |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Scada Network Control And Protection Systems |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Other |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Total Direct - $ Mar 2017 |  |  | 2185.8319 | 1025.4572 | 6098.9924 | 6136.031 | 6172.4651 | 6212.2681 | 6253.3818 | 0 | 34084.4275 | 30873.1383

## Proj_24
Go To: | Table of Contents
Master Inputs
|  | Various |  | Business case? | 0
| Project name | Instrument transformers
| Project category 1 | Network |  |  | Shaded cells = Inputs
| Project category 2 | Security and Compliance
| Regulatory classification | Prescribed
| Overhead Category | Repex_OHD |  | $000's | $000's | $000's | $000's | $000's | $000's | $000's | $000's | $000's | Project | 2017-22
|  |  |  | Prior | 2015-16 | 2016-17 | 2017-18 | 2018-19 | 2019-20 | 2020-21 | 2021-22 | 2022-23 | Total | Total | Check
| Project timing | Direct Expenditure (As incurred) - $ 2015/16 |  | 492.1801 | 1292.6728 | 2595.4659 | 1480 | 1480 | 1480 | 1480 | 1480 | 0 | 11780.3189 | 7400 | ok
| (excluding real cost escalators) | Assumed year commissioned (no BC) |  | x | bar: 2015-16 to 2022-23
|  | Direct Expenditure (As Commissioned) - $ 2015/16 |  | 492.1801 | 1292.6728 | 2595.4659 | 1480 | 1480 | 1480 | 1480 | 1480 | 0 | 11780.3189 | 7400 | ok
| Asset class | Secondary
|  | Switchgear |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
Transformers
Reactive
Lines and towers
Establishment
Communications
Non System
Land
Easements
|  |  | Total | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
| Input costs % | Labour - internal |  | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10%
|  | Labour - external |  | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50%
|  | Materials |  | 40% | 40% | 40% | 40% | 40% | 40% | 40% | 40% | 40%
|  |  | Total | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
Material Escalation
| (By Asset Class) | Secondary |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Switchgear |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Transformers |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Reactive |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Lines and towers |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Establishment |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Communications |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Non System |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Land |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Easements |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Total Material escalation |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Labour Escalation | Internal Labour |  | 0 | 0 | 3.2479 | 3.0583 | 4.2819 | 5.5421 | 6.9163 | 8.326 | 0 | 31.3725 | 28.1246
|  | External Labour |  | 0 | 0 | 13.9534 | 15.7166 | 23.595 | 31.2882 | 39.6953 | 48.3889 | 0 | 172.6374 | 158.684
|  | Total Labour Escalation |  | 0 | 0 | 17.2013 | 18.775 | 27.8769 | 36.8303 | 46.6115 | 56.7149 | 0 | 204.0099 | 186.8085
|  | Total Escalation |  | 0 | 0 | 17.2013 | 18.775 | 27.8769 | 36.8303 | 46.6115 | 56.7149 | 0 | 204.0099 | 186.8085
|  | Escalation factors |  | 0 | 0 | 0.0066275 | 0.012686 | 0.018836 | 0.024885 | 0.031494 | 0.038321 | 0 | 0.017318 | 0.025244
| Direct Expenditure (Escalated) | Total labour - internal |  | 50.0506 | 131.4541 | 267.2403 | 153.6138 | 154.8581 | 156.1396 | 157.537 | 158.9706 | 0 | 1229.8642 | 781.1192
| (as incurred) | Total labour - external |  | 250.2532 | 657.2707 | 1333.8766 | 768.5013 | 776.513 | 784.3363 | 792.8856 | 801.7263 | 0 | 6165.363 | 3923.9625
|  | Total materials |  | 200.2026 | 525.8165 | 1055.7497 | 602.015 | 602.015 | 602.015 | 602.015 | 602.015 | 0 | 4791.844 | 3010.0752
|  | Total Direct - As Incurred $ Mar 2017 |  | 500.5065 | 1314.5414 | 2656.8665 | 1524.1302 | 1533.3861 | 1542.4909 | 1552.4376 | 1562.7119 | 0 | 12187.0711 | 7715.1568 | ok
| Capitalised Overheads | Overhead rate (applied to direct expenditure) |  | 8.008% | 8.425% | 7.259% | 7.658% | 9.013% | 8.969% | 7.948% | 8.001% | 8.318%
|  | Total overhead (as incurred) |  | 40.0814 | 110.7525 | 192.8717 | 116.7155 | 138.2089 | 138.3395 | 123.3917 | 125.0392 | 0 | 985.4005 | 641.6948
|  | Total incl Overhead - As Incurred $ Mar 2017 |  | 540.5879 | 1425.2939 | 2849.7382 | 1640.8457 | 1671.595 | 1680.8304 | 1675.8294 | 1687.7511 | 0 | 13172.4716 | 8356.8516
|  | Total overheads (As incurred) - Cumulative |  | 40.0814 | 150.8339 | 343.7057 | 460.4212 | 598.6301 | 736.9695 | 860.3613 | 985.4005 | 985.4005
|  | Labour & Material Escalation - Cumulative |  | 0 | 0 | 17.2013 | 35.9763 | 63.8533 | 100.6835 | 147.295 | 204.0099 | 204.0099
Expenditure By Asset Class - As Incurred
| Asset class breakdown | Secondary |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| (fully absorbed) | Switchgear |  | 540.5879 | 1425.2939 | 2849.7382 | 1640.8457 | 1671.595 | 1680.8304 | 1675.8294 | 1687.7511 | 0 | 13172.4716 | 8356.8516
| (as incurred) | Transformers |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Reactive |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Lines and towers |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Establishment |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Communications |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Non System |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Land |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Easements |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Total incl Overhead - As Incurred $ Mar 2017 |  | 540.5879 | 1425.2939 | 2849.7382 | 1640.8457 | 1671.595 | 1680.8304 | 1675.8294 | 1687.7511 | 0 | 13172.4716 | 8356.8516
|  |  | Check | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| As Commissioned Capex | Direct Expenditure (As Commissioned) - $ 2015/16 |  | 492.1801 | 1292.6728 | 2595.4659 | 1480 | 1480 | 1480 | 1480 | 1480 | 0 | 11780.3189 | 7400
|  | Labour & Material Escalation - $ 2015/16 |  | 0 | 0 | 17.2013 | 18.775 | 27.8769 | 36.8303 | 46.6115 | 56.7149 | 0 | 204.0099 | 186.8085
|  | Total Direct Expenditure - $ 2015/16 |  | 492.1801 | 1292.6728 | 2612.6672 | 1498.775 | 1507.8769 | 1516.8303 | 1526.6115 | 1536.7149 | 0 | 11984.3287 | 7586.8085
|  | Total Direct Expenditure - $ Mar 2017 |  | 500.5065 | 1314.5414 | 2656.8665 | 1524.1302 | 1533.3861 | 1542.4909 | 1552.4376 | 1562.7119 | 0 | 12187.0711 | 7715.1568
|  | Total overheads (As Commissioned) |  | 40.0814 | 110.7525 | 192.8717 | 116.7155 | 138.2089 | 138.3395 | 123.3917 | 125.0392 | 0 | 985.4005 | 641.6948
|  | Total incl Overhead - As commissioned $ Mar 2017 |  | 540.5879 | 1425.2939 | 2849.7382 | 1640.8457 | 1671.595 | 1680.8304 | 1675.8294 | 1687.7511 | 0 | 13172.4716 | 8356.8516
|  | Total overheads (As Comm) - Cumulative |  | 40.0814 | 150.8339 | 343.7057 | 460.4212 | 598.6301 | 736.9695 | 860.3613 | 985.4005 | 985.4005
|  | Total real cost escalation (As Comm) - Cumulative |  | 0 | 0 | 17.2013 | 35.9763 | 63.8533 | 100.6835 | 147.295 | 204.0099 | 204.0099
Expenditure By Asset Class - As Commissioned
| Asset class breakdown | Secondary |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| (fully absorbed) | Switchgear |  | 540.5879 | 1425.2939 | 2849.7382 | 1640.8457 | 1671.595 | 1680.8304 | 1675.8294 | 1687.7511 | 0 | 13172.4716 | 8356.8516
| (as commissioned) | Transformers |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Reactive |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Lines and towers |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Establishment |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Communications |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Non System |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Land |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Easements |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Total incl Overhead - As commissioned $ Mar 2017 |  | 540.5879 | 1425.2939 | 2849.7382 | 1640.8457 | 1671.595 | 1680.8304 | 1675.8294 | 1687.7511 | 0 | 13172.4716 | 8356.8516
|  |  | Check | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0
| Expenditure splits for RIN |  |  |  | 2015-16 | 2016-17 | 2017-18 | 2018-19 | 2019-20 | 2020-21 | 2021-22 | 2022-23
| Repex Category | Transmission Towers | bar: 2015-16 to 2022-23
Transmission Tower Support Structures | bar: 2015-16 to 2022-23
Conductors | bar: 2015-16 to 2022-23
Transmission Cables | bar: 2015-16 to 2022-23
|  | Substation Switchbays |  |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
Substation Power Transformers | bar: 2015-16 to 2022-23
Substation Reactive Plant | bar: 2015-16 to 2022-23
Scada Network Control And Protection Systems | bar: 2015-16 to 2022-23
Other | bar: 2015-16 to 2022-23
|  | Total |  |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
| Direct Expenditures | Materials - $ Mar 2017 |  |  | 2015-16 | 2016-17 | 2017-18 | 2018-19 | 2019-20 | 2020-21 | 2021-22 | 2022-23 | Total | 2017-22 Total
| (As Incurred) | Transmission Towers |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Transmission Tower Support Structures |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Conductors |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Transmission Cables |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Substation Switchbays |  |  | 525.8165 | 1055.7497 | 602.015 | 602.015 | 602.015 | 602.015 | 602.015 | 0 | 4591.6414 | 3010.0752
|  | Substation Power Transformers |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Substation Reactive Plant |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Scada Network Control And Protection Systems |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Other |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Total Materials |  |  | 525.8165 | 1055.7497 | 602.015 | 602.015 | 602.015 | 602.015 | 602.015 | 0 | 4591.6414 | 3010.0752
|  | Labour (Internal) - $ Mar 2017 |  |  | 2015-16 | 2016-17 | 2017-18 | 2018-19 | 2019-20 | 2020-21 | 2021-22 | 2022-23 | Total | 2017-22 Total
|  | Transmission Towers |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Transmission Tower Support Structures |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Conductors |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Transmission Cables |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Substation Switchbays |  |  | 131.4541 | 267.2403 | 153.6138 | 154.8581 | 156.1396 | 157.537 | 158.9706 | 0 | 1179.8136 | 781.1192
|  | Substation Power Transformers |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Substation Reactive Plant |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Scada Network Control And Protection Systems |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Other |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Total Internal Labour |  |  | 131.4541 | 267.2403 | 153.6138 | 154.8581 | 156.1396 | 157.537 | 158.9706 | 0 | 1179.8136 | 781.1192
|  | Labour (External) - $ Mar 2017 |  |  | 2015-16 | 2016-17 | 2017-18 | 2018-19 | 2019-20 | 2020-21 | 2021-22 | 2022-23 | Total | 2017-22 Total
|  | Transmission Towers |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Transmission Tower Support Structures |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Conductors |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Transmission Cables |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Substation Switchbays |  |  | 657.2707 | 1333.8766 | 768.5013 | 776.513 | 784.3363 | 792.8856 | 801.7263 | 0 | 5915.1097 | 3923.9625
|  | Substation Power Transformers |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Substation Reactive Plant |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Scada Network Control And Protection Systems |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Other |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Total External Labour |  |  | 657.2707 | 1333.8766 | 768.5013 | 776.513 | 784.3363 | 792.8856 | 801.7263 | 0 | 5915.1097 | 3923.9625
|  | Total Direct - $ Mar 2017 |  |  | 2015-16 | 2016-17 | 2017-18 | 2018-19 | 2019-20 | 2020-21 | 2021-22 | 2022-23 | Total | 2017-22 Total
|  | Transmission Towers |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Transmission Tower Support Structures |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Conductors |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Transmission Cables |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Substation Switchbays |  |  | 1314.5414 | 2656.8665 | 1524.1302 | 1533.3861 | 1542.4909 | 1552.4376 | 1562.7119 | 0 | 11686.5647 | 7715.1568
|  | Substation Power Transformers |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Substation Reactive Plant |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Scada Network Control And Protection Systems |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Other |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Total Direct - $ Mar 2017 |  |  | 1314.5414 | 2656.8665 | 1524.1302 | 1533.3861 | 1542.4909 | 1552.4376 | 1562.7119 | 0 | 11686.5647 | 7715.1568

## Proj_25
Go To: | Table of Contents
Master Inputs
|  |  |  | Business case? | 0
| Project name | Disconnectors
| Project category 1 | Network |  |  | Shaded cells = Inputs
| Project category 2 | Replacement - Other
| Regulatory classification | Prescribed
| Overhead Category | Repex_OHD |  | $000's | $000's | $000's | $000's | $000's | $000's | $000's | $000's | $000's | Project | 2017-22
|  |  |  | Prior | 2015-16 | 2016-17 | 2017-18 | 2018-19 | 2019-20 | 2020-21 | 2021-22 | 2022-23 | Total | Total | Check
| Project timing | Direct Expenditure (As incurred) - $ 2015/16 |  | 0 | 0 | 0 | 848 | 2440 | 2440 | 2440 | 2440 | 0 | 10608 | 10608 | ok
| (excluding real cost escalators) | Assumed year commissioned (no BC) | bar: 2015-16 to 2022-23
|  | Direct Expenditure (As Commissioned) - $ 2015/16 |  | 0 | 0 | 0 | 848 | 2440 | 2440 | 2440 | 2440 | 0 | 10608 | 10608 | ok
| Asset class | Secondary
|  | Switchgear |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
Transformers
Reactive
Lines and towers
Establishment
Communications
Non System
Land
Easements
|  |  | Total | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
| Input costs % | Labour - internal |  | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10%
|  | Labour - external |  | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50%
|  | Materials |  | 40% | 40% | 40% | 40% | 40% | 40% | 40% | 40% | 40%
|  |  | Total | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
Material Escalation
| (By Asset Class) | Secondary |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Switchgear |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Transformers |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Reactive |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Lines and towers |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Establishment |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Communications |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Non System |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Land |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Easements |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Total Material escalation |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Labour Escalation | Internal Labour |  | 0 | 0 | 0 | 1.7524 | 7.0594 | 9.1369 | 11.4025 | 13.7266 | 0 | 43.0777 | 43.0777
|  | External Labour |  | 0 | 0 | 0 | 9.0052 | 38.8999 | 51.5833 | 65.4435 | 79.7762 | 0 | 244.7081 | 244.7081
|  | Total Labour Escalation |  | 0 | 0 | 0 | 10.7576 | 45.9592 | 60.7202 | 76.846 | 93.5029 | 0 | 287.7858 | 287.7858
|  | Total Escalation |  | 0 | 0 | 0 | 10.7576 | 45.9592 | 60.7202 | 76.846 | 93.5029 | 0 | 287.7858 | 287.7858
|  | Escalation factors |  | 0 | 0 | 0 | 0.012686 | 0.018836 | 0.024885 | 0.031494 | 0.038321 | 0 | 0.027129 | 0.027129
| Direct Expenditure (Escalated) | Total labour - internal |  | 0 | 0 | 0 | 88.0166 | 255.3066 | 257.4193 | 259.7232 | 262.0867 | 0 | 1122.5524 | 1122.5524
| (as incurred) | Total labour - external |  | 0 | 0 | 0 | 440.3305 | 1280.197 | 1293.095 | 1307.1898 | 1321.7649 | 0 | 5642.5772 | 5642.5772
|  | Total materials |  | 0 | 0 | 0 | 344.9383 | 992.5113 | 992.5113 | 992.5113 | 992.5113 | 0 | 4314.9835 | 4314.9835
|  | Total Direct - As Incurred $ Mar 2017 |  | 0 | 0 | 0 | 873.2854 | 2528.0149 | 2543.0256 | 2559.4242 | 2576.3629 | 0 | 11080.1131 | 11080.1131 | ok
| Capitalised Overheads | Overhead rate (applied to direct expenditure) |  | 8.008% | 8.425% | 7.259% | 7.658% | 9.013% | 8.969% | 7.948% | 8.001% | 8.318%
|  | Total overhead (as incurred) |  | 0 | 0 | 0 | 66.8748 | 227.8579 | 228.0732 | 203.4296 | 206.1457 | 0 | 932.3812 | 932.3812
|  | Total incl Overhead - As Incurred $ Mar 2017 |  | 0 | 0 | 0 | 940.1603 | 2755.8728 | 2771.0988 | 2762.8539 | 2782.5086 | 0 | 12012.4943 | 12012.4943
|  | Total overheads (As incurred) - Cumulative |  | 0 | 0 | 0 | 66.8748 | 294.7327 | 522.8059 | 726.2355 | 932.3812 | 932.3812
|  | Labour & Material Escalation - Cumulative |  | 0 | 0 | 0 | 10.7576 | 56.7168 | 117.437 | 194.283 | 287.7858 | 287.7858
Expenditure By Asset Class - As Incurred
| Asset class breakdown | Secondary |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| (fully absorbed) | Switchgear |  | 0 | 0 | 0 | 940.1603 | 2755.8728 | 2771.0988 | 2762.8539 | 2782.5086 | 0 | 12012.4943 | 12012.4943
| (as incurred) | Transformers |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Reactive |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Lines and towers |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Establishment |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Communications |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Non System |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Land |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Easements |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Total incl Overhead - As Incurred $ Mar 2017 |  | 0 | 0 | 0 | 940.1603 | 2755.8728 | 2771.0988 | 2762.8539 | 2782.5086 | 0 | 12012.4943 | 12012.4943
|  |  | Check | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| As Commissioned Capex | Direct Expenditure (As Commissioned) - $ 2015/16 |  | 0 | 0 | 0 | 848 | 2440 | 2440 | 2440 | 2440 | 0 | 10608 | 10608
|  | Labour & Material Escalation - $ 2015/16 |  | 0 | 0 | 0 | 10.7576 | 45.9592 | 60.7202 | 76.846 | 93.5029 | 0 | 287.7858 | 287.7858
|  | Total Direct Expenditure - $ 2015/16 |  | 0 | 0 | 0 | 858.7576 | 2485.9592 | 2500.7202 | 2516.846 | 2533.5029 | 0 | 10895.7858 | 10895.7858
|  | Total Direct Expenditure - $ Mar 2017 |  | 0 | 0 | 0 | 873.2854 | 2528.0149 | 2543.0256 | 2559.4242 | 2576.3629 | 0 | 11080.1131 | 11080.1131
|  | Total overheads (As Commissioned) |  | 0 | 0 | 0 | 66.8748 | 227.8579 | 228.0732 | 203.4296 | 206.1457 | 0 | 932.3812 | 932.3812
|  | Total incl Overhead - As commissioned $ Mar 2017 |  | 0 | 0 | 0 | 940.1603 | 2755.8728 | 2771.0988 | 2762.8539 | 2782.5086 | 0 | 12012.4943 | 12012.4943
|  | Total overheads (As Comm) - Cumulative |  | 0 | 0 | 0 | 66.8748 | 294.7327 | 522.8059 | 726.2355 | 932.3812 | 932.3812
|  | Total real cost escalation (As Comm) - Cumulative |  | 0 | 0 | 0 | 10.7576 | 56.7168 | 117.437 | 194.283 | 287.7858 | 287.7858
Expenditure By Asset Class - As Commissioned
| Asset class breakdown | Secondary |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| (fully absorbed) | Switchgear |  | 0 | 0 | 0 | 940.1603 | 2755.8728 | 2771.0988 | 2762.8539 | 2782.5086 | 0 | 12012.4943 | 12012.4943
| (as commissioned) | Transformers |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Reactive |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Lines and towers |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Establishment |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Communications |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Non System |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Land |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Easements |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Total incl Overhead - As commissioned $ Mar 2017 |  | 0 | 0 | 0 | 940.1603 | 2755.8728 | 2771.0988 | 2762.8539 | 2782.5086 | 0 | 12012.4943 | 12012.4943
|  |  | Check | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0
| Expenditure splits for RIN |  |  |  | 2015-16 | 2016-17 | 2017-18 | 2018-19 | 2019-20 | 2020-21 | 2021-22 | 2022-23
| Repex Category | Transmission Towers | bar: 2015-16 to 2022-23
Transmission Tower Support Structures | bar: 2015-16 to 2022-23
Conductors | bar: 2015-16 to 2022-23
Transmission Cables | bar: 2015-16 to 2022-23
|  | Substation Switchbays |  |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
Substation Power Transformers | bar: 2015-16 to 2022-23
Substation Reactive Plant | bar: 2015-16 to 2022-23
Scada Network Control And Protection Systems | bar: 2015-16 to 2022-23
Other | bar: 2015-16 to 2022-23
|  | Total |  |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
| Direct Expenditures | Materials - $ Mar 2017 |  |  | 2015-16 | 2016-17 | 2017-18 | 2018-19 | 2019-20 | 2020-21 | 2021-22 | 2022-23 | Total | 2017-22 Total
| (As Incurred) | Transmission Towers |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Transmission Tower Support Structures |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Conductors |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Transmission Cables |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Substation Switchbays |  |  | 0 | 0 | 344.9383 | 992.5113 | 992.5113 | 992.5113 | 992.5113 | 0 | 4314.9835 | 4314.9835
|  | Substation Power Transformers |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Substation Reactive Plant |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Scada Network Control And Protection Systems |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Other |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Total Materials |  |  | 0 | 0 | 344.9383 | 992.5113 | 992.5113 | 992.5113 | 992.5113 | 0 | 4314.9835 | 4314.9835
|  | Labour (Internal) - $ Mar 2017 |  |  | 2015-16 | 2016-17 | 2017-18 | 2018-19 | 2019-20 | 2020-21 | 2021-22 | 2022-23 | Total | 2017-22 Total
|  | Transmission Towers |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Transmission Tower Support Structures |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Conductors |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Transmission Cables |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Substation Switchbays |  |  | 0 | 0 | 88.0166 | 255.3066 | 257.4193 | 259.7232 | 262.0867 | 0 | 1122.5524 | 1122.5524
|  | Substation Power Transformers |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Substation Reactive Plant |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Scada Network Control And Protection Systems |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Other |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Total Internal Labour |  |  | 0 | 0 | 88.0166 | 255.3066 | 257.4193 | 259.7232 | 262.0867 | 0 | 1122.5524 | 1122.5524
|  | Labour (External) - $ Mar 2017 |  |  | 2015-16 | 2016-17 | 2017-18 | 2018-19 | 2019-20 | 2020-21 | 2021-22 | 2022-23 | Total | 2017-22 Total
|  | Transmission Towers |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Transmission Tower Support Structures |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Conductors |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Transmission Cables |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Substation Switchbays |  |  | 0 | 0 | 440.3305 | 1280.197 | 1293.095 | 1307.1898 | 1321.7649 | 0 | 5642.5772 | 5642.5772
|  | Substation Power Transformers |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Substation Reactive Plant |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Scada Network Control And Protection Systems |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Other |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Total External Labour |  |  | 0 | 0 | 440.3305 | 1280.197 | 1293.095 | 1307.1898 | 1321.7649 | 0 | 5642.5772 | 5642.5772
|  | Total Direct - $ Mar 2017 |  |  | 2015-16 | 2016-17 | 2017-18 | 2018-19 | 2019-20 | 2020-21 | 2021-22 | 2022-23 | Total | 2017-22 Total
|  | Transmission Towers |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Transmission Tower Support Structures |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Conductors |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Transmission Cables |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Substation Switchbays |  |  | 0 | 0 | 873.2854 | 2528.0149 | 2543.0256 | 2559.4242 | 2576.3629 | 0 | 11080.1131 | 11080.1131
|  | Substation Power Transformers |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Substation Reactive Plant |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Scada Network Control And Protection Systems |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Other |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Total Direct - $ Mar 2017 |  |  | 0 | 0 | 873.2854 | 2528.0149 | 2543.0256 | 2559.4242 | 2576.3629 | 0 | 11080.1131 | 11080.1131

## Proj_26
Go To: | Table of Contents
Master Inputs
|  | Various |  | Business case? | 0
| Project name | Syn Cons
| Project category 1 | Network |  |  | Shaded cells = Inputs
| Project category 2 | Replacement - Other
| Regulatory classification | Prescribed
| Overhead Category | Repex_OHD |  | $000's | $000's | $000's | $000's | $000's | $000's | $000's | $000's | $000's | Project | 2017-22
|  |  |  | Prior | 2015-16 | 2016-17 | 2017-18 | 2018-19 | 2019-20 | 2020-21 | 2021-22 | 2022-23 | Total | Total | Check
| Project timing | Direct Expenditure (As incurred) - $ 2015/16 |  | 1746.2856 | 634.5129 | 2126.0599 | 0 | 0 | 0 | 0 | 0 | 0 | 4506.8584 | 0 | ok
| (excluding real cost escalators) | Assumed year commissioned (no BC) |  | x | bar: 2015-16 to 2022-23
|  | Direct Expenditure (As Commissioned) - $ 2015/16 |  | 1746.2856 | 634.5129 | 2126.0599 | 0 | 0 | 0 | 0 | 0 | 0 | 4506.8584 | 0 | ok
| Asset class | Secondary
Switchgear
Transformers
|  | Reactive |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
Lines and towers
Establishment
Communications
Non System
Land
Easements
|  |  | Total | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
| Input costs % | Labour - internal |  | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10%
|  | Labour - external |  | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50%
|  | Materials |  | 40% | 40% | 40% | 40% | 40% | 40% | 40% | 40% | 40%
|  |  | Total | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
Material Escalation
| (By Asset Class) | Secondary |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Switchgear |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Transformers |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Reactive |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Lines and towers |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Establishment |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Communications |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Non System |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Land |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Easements |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Total Material escalation |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Labour Escalation | Internal Labour |  | 0 | 0 | 2.6605 | 0 | 0 | 0 | 0 | 0 | 0 | 2.6605 | 0
|  | External Labour |  | 0 | 0 | 11.4299 | 0 | 0 | 0 | 0 | 0 | 0 | 11.4299 | 0
|  | Total Labour Escalation |  | 0 | 0 | 14.0904 | 0 | 0 | 0 | 0 | 0 | 0 | 14.0904 | 0
|  | Total Escalation |  | 0 | 0 | 14.0904 | 0 | 0 | 0 | 0 | 0 | 0 | 14.0904 | 0
|  | Escalation factors |  | 0 | 0 | 0.0066275 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0031264 | 0
| Direct Expenditure (Escalated) | Total labour - internal |  | 177.5828 | 64.5247 | 218.9082 | 0 | 0 | 0 | 0 | 0 | 0 | 461.0157 | 0
| (as incurred) | Total labour - external |  | 887.914 | 322.6236 | 1092.6368 | 0 | 0 | 0 | 0 | 0 | 0 | 2303.1744 | 0
|  | Total materials |  | 710.3312 | 258.0988 | 864.8108 | 0 | 0 | 0 | 0 | 0 | 0 | 1833.2409 | 0
|  | Total Direct - As Incurred $ Mar 2017 |  | 1775.828 | 645.2471 | 2176.3559 | 0 | 0 | 0 | 0 | 0 | 0 | 4597.431 | 0 | ok
| Capitalised Overheads | Overhead rate (applied to direct expenditure) |  | 8.008% | 8.425% | 7.259% | 7.658% | 9.013% | 8.969% | 7.948% | 8.001% | 8.318%
|  | Total overhead (as incurred) |  | 142.2114 | 54.3633 | 157.9897 | 0 | 0 | 0 | 0 | 0 | 0 | 354.5643 | 0
|  | Total incl Overhead - As Incurred $ Mar 2017 |  | 1918.0394 | 699.6104 | 2334.3456 | 0 | 0 | 0 | 0 | 0 | 0 | 4951.9953 | 0
|  | Total overheads (As incurred) - Cumulative |  | 142.2114 | 196.5746 | 354.5643 | 354.5643 | 354.5643 | 354.5643 | 354.5643 | 354.5643 | 354.5643
|  | Labour & Material Escalation - Cumulative |  | 0 | 0 | 14.0904 | 14.0904 | 14.0904 | 14.0904 | 14.0904 | 14.0904 | 14.0904
Expenditure By Asset Class - As Incurred
| Asset class breakdown | Secondary |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| (fully absorbed) | Switchgear |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| (as incurred) | Transformers |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Reactive |  | 1918.0394 | 699.6104 | 2334.3456 | 0 | 0 | 0 | 0 | 0 | 0 | 4951.9953 | 0
|  | Lines and towers |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Establishment |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Communications |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Non System |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Land |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Easements |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Total incl Overhead - As Incurred $ Mar 2017 |  | 1918.0394 | 699.6104 | 2334.3456 | 0 | 0 | 0 | 0 | 0 | 0 | 4951.9953 | 0
|  |  | Check | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| As Commissioned Capex | Direct Expenditure (As Commissioned) - $ 2015/16 |  | 1746.2856 | 634.5129 | 2126.0599 | 0 | 0 | 0 | 0 | 0 | 0 | 4506.8584 | 0
|  | Labour & Material Escalation - $ 2015/16 |  | 0 | 0 | 14.0904 | 0 | 0 | 0 | 0 | 0 | 0 | 14.0904 | 0
|  | Total Direct Expenditure - $ 2015/16 |  | 1746.2856 | 634.5129 | 2140.1503 | 0 | 0 | 0 | 0 | 0 | 0 | 4520.9488 | 0
|  | Total Direct Expenditure - $ Mar 2017 |  | 1775.828 | 645.2471 | 2176.3559 | 0 | 0 | 0 | 0 | 0 | 0 | 4597.431 | 0
|  | Total overheads (As Commissioned) |  | 142.2114 | 54.3633 | 157.9897 | 0 | 0 | 0 | 0 | 0 | 0 | 354.5643 | 0
|  | Total incl Overhead - As commissioned $ Mar 2017 |  | 1918.0394 | 699.6104 | 2334.3456 | 0 | 0 | 0 | 0 | 0 | 0 | 4951.9953 | 0
|  | Total overheads (As Comm) - Cumulative |  | 142.2114 | 196.5746 | 354.5643 | 354.5643 | 354.5643 | 354.5643 | 354.5643 | 354.5643 | 354.5643
|  | Total real cost escalation (As Comm) - Cumulative |  | 0 | 0 | 14.0904 | 14.0904 | 14.0904 | 14.0904 | 14.0904 | 14.0904 | 14.0904
Expenditure By Asset Class - As Commissioned
| Asset class breakdown | Secondary |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| (fully absorbed) | Switchgear |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| (as commissioned) | Transformers |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Reactive |  | 1918.0394 | 699.6104 | 2334.3456 | 0 | 0 | 0 | 0 | 0 | 0 | 4951.9953 | 0
|  | Lines and towers |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Establishment |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Communications |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Non System |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Land |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Easements |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Total incl Overhead - As commissioned $ Mar 2017 |  | 1918.0394 | 699.6104 | 2334.3456 | 0 | 0 | 0 | 0 | 0 | 0 | 4951.9953 | 0
|  |  | Check | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0
| Expenditure splits for RIN |  |  |  | 2015-16 | 2016-17 | 2017-18 | 2018-19 | 2019-20 | 2020-21 | 2021-22 | 2022-23
| Repex Category | Transmission Towers | bar: 2015-16 to 2022-23
Transmission Tower Support Structures | bar: 2015-16 to 2022-23
Conductors | bar: 2015-16 to 2022-23
Transmission Cables | bar: 2015-16 to 2022-23
Substation Switchbays | bar: 2015-16 to 2022-23
Substation Power Transformers | bar: 2015-16 to 2022-23
|  | Substation Reactive Plant |  |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
Scada Network Control And Protection Systems | bar: 2015-16 to 2022-23
Other | bar: 2015-16 to 2022-23
|  | Total |  |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
| Direct Expenditures | Materials - $ Mar 2017 |  |  | 2015-16 | 2016-17 | 2017-18 | 2018-19 | 2019-20 | 2020-21 | 2021-22 | 2022-23 | Total | 2017-22 Total
| (As Incurred) | Transmission Towers |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Transmission Tower Support Structures |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Conductors |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Transmission Cables |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Substation Switchbays |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Substation Power Transformers |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Substation Reactive Plant |  |  | 258.0988 | 864.8108 | 0 | 0 | 0 | 0 | 0 | 0 | 1122.9097 | 0
|  | Scada Network Control And Protection Systems |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Other |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Total Materials |  |  | 258.0988 | 864.8108 | 0 | 0 | 0 | 0 | 0 | 0 | 1122.9097 | 0
|  | Labour (Internal) - $ Mar 2017 |  |  | 2015-16 | 2016-17 | 2017-18 | 2018-19 | 2019-20 | 2020-21 | 2021-22 | 2022-23 | Total | 2017-22 Total
|  | Transmission Towers |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Transmission Tower Support Structures |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Conductors |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Transmission Cables |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Substation Switchbays |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Substation Power Transformers |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Substation Reactive Plant |  |  | 64.5247 | 218.9082 | 0 | 0 | 0 | 0 | 0 | 0 | 283.4329 | 0
|  | Scada Network Control And Protection Systems |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Other |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Total Internal Labour |  |  | 64.5247 | 218.9082 | 0 | 0 | 0 | 0 | 0 | 0 | 283.4329 | 0
|  | Labour (External) - $ Mar 2017 |  |  | 2015-16 | 2016-17 | 2017-18 | 2018-19 | 2019-20 | 2020-21 | 2021-22 | 2022-23 | Total | 2017-22 Total
|  | Transmission Towers |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Transmission Tower Support Structures |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Conductors |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Transmission Cables |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Substation Switchbays |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Substation Power Transformers |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Substation Reactive Plant |  |  | 322.6236 | 1092.6368 | 0 | 0 | 0 | 0 | 0 | 0 | 1415.2604 | 0
|  | Scada Network Control And Protection Systems |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Other |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Total External Labour |  |  | 322.6236 | 1092.6368 | 0 | 0 | 0 | 0 | 0 | 0 | 1415.2604 | 0
|  | Total Direct - $ Mar 2017 |  |  | 2015-16 | 2016-17 | 2017-18 | 2018-19 | 2019-20 | 2020-21 | 2021-22 | 2022-23 | Total | 2017-22 Total
|  | Transmission Towers |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Transmission Tower Support Structures |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Conductors |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Transmission Cables |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Substation Switchbays |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Substation Power Transformers |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Substation Reactive Plant |  |  | 645.2471 | 2176.3559 | 0 | 0 | 0 | 0 | 0 | 0 | 2821.603 | 0
|  | Scada Network Control And Protection Systems |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Other |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Total Direct - $ Mar 2017 |  |  | 645.2471 | 2176.3559 | 0 | 0 | 0 | 0 | 0 | 0 | 2821.603 | 0

## Proj_27
Go To: | Table of Contents
Master Inputs
|  |  |  | Business case? | 0
| Project name | Reactive plant
| Project category 1 | Network |  |  | Shaded cells = Inputs
| Project category 2 | Replacement - Other
| Regulatory classification | Prescribed
| Overhead Category | Repex_OHD |  | $000's | $000's | $000's | $000's | $000's | $000's | $000's | $000's | $000's | Project | 2017-22
|  |  |  | Prior | 2015-16 | 2016-17 | 2017-18 | 2018-19 | 2019-20 | 2020-21 | 2021-22 | 2022-23 | Total | Total | Check
| Project timing | Direct Expenditure (As incurred) - $ 2015/16 |  | 2779.9674 | 238.1366 | 7558.7252 | 164 | 164 | 164 | 164 | 164 | 0 | 11396.8292 | 820 | ok
| (excluding real cost escalators) | Assumed year commissioned (no BC) |  | x | bar: 2015-16 to 2022-23
|  | Direct Expenditure (As Commissioned) - $ 2015/16 |  | 2779.9674 | 238.1366 | 7558.7252 | 164 | 164 | 164 | 164 | 164 | 0 | 11396.8292 | 820 | ok
| Asset class | Secondary
Switchgear
Transformers
|  | Reactive |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
Lines and towers
Establishment
Communications
Non System
Land
Easements
|  |  | Total | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
| Input costs % | Labour - internal |  | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10%
|  | Labour - external |  | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50%
|  | Materials |  | 40% | 40% | 40% | 40% | 40% | 40% | 40% | 40% | 40%
|  |  | Total | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
Material Escalation
| (By Asset Class) | Secondary |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Switchgear |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Transformers |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Reactive |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Lines and towers |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Establishment |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Communications |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Non System |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Land |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Easements |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Total Material escalation |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Labour Escalation | Internal Labour |  | 0 | 0 | 9.4588 | 0.3389 | 0.47448 | 0.61412 | 0.7664 | 0.92261 | 0 | 12.5753 | 3.1165
|  | External Labour |  | 0 | 0 | 40.6363 | 1.7416 | 2.6146 | 3.4671 | 4.3987 | 5.362 | 0 | 58.2202 | 17.5839
|  | Total Labour Escalation |  | 0 | 0 | 50.0951 | 2.0805 | 3.0891 | 4.0812 | 5.1651 | 6.2846 | 0 | 70.7955 | 20.7004
|  | Total Escalation |  | 0 | 0 | 50.0951 | 2.0805 | 3.0891 | 4.0812 | 5.1651 | 6.2846 | 0 | 70.7955 | 20.7004
|  | Escalation factors |  | 0 | 0 | 0.0066275 | 0.012686 | 0.018836 | 0.024885 | 0.031494 | 0.038321 | 0 | 0.0062119 | 0.025244
| Direct Expenditure (Escalated) | Total labour - internal |  | 282.6997 | 24.2165 | 778.2787 | 17.0221 | 17.16 | 17.302 | 17.4568 | 17.6157 | 0 | 1171.7513 | 86.5564
| (as incurred) | Total labour - external |  | 1413.4984 | 121.0826 | 3884.623 | 85.1583 | 86.046 | 86.9129 | 87.8603 | 88.8399 | 0 | 5854.0215 | 434.8175
|  | Total materials |  | 1130.7988 | 96.8661 | 3074.6394 | 66.7098 | 66.7098 | 66.7098 | 66.7098 | 66.7098 | 0 | 4635.8531 | 333.5489
|  | Total Direct - As Incurred $ Mar 2017 |  | 2826.9969 | 242.1652 | 7737.541 | 168.8901 | 169.9158 | 170.9247 | 172.0269 | 173.1654 | 0 | 11661.6259 | 854.9228 | ok
| Capitalised Overheads | Overhead rate (applied to direct expenditure) |  | 8.008% | 8.425% | 7.259% | 7.658% | 9.013% | 8.969% | 7.948% | 8.001% | 8.318%
|  | Total overhead (as incurred) |  | 226.3908 | 20.4029 | 561.6966 | 12.9333 | 15.315 | 15.3295 | 13.6731 | 13.8557 | 0 | 879.597 | 71.1067
|  | Total incl Overhead - As Incurred $ Mar 2017 |  | 3053.3877 | 262.5681 | 8299.2376 | 181.8234 | 185.2308 | 186.2542 | 185.7 | 187.0211 | 0 | 12541.2229 | 926.0295
|  | Total overheads (As incurred) - Cumulative |  | 226.3908 | 246.7936 | 808.4903 | 821.4236 | 836.7386 | 852.0681 | 865.7413 | 879.597 | 879.597
|  | Labour & Material Escalation - Cumulative |  | 0 | 0 | 50.0951 | 52.1756 | 55.2647 | 59.3459 | 64.5109 | 70.7955 | 70.7955
Expenditure By Asset Class - As Incurred
| Asset class breakdown | Secondary |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| (fully absorbed) | Switchgear |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| (as incurred) | Transformers |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Reactive |  | 3053.3877 | 262.5681 | 8299.2376 | 181.8234 | 185.2308 | 186.2542 | 185.7 | 187.0211 | 0 | 12541.2229 | 926.0295
|  | Lines and towers |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Establishment |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Communications |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Non System |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Land |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Easements |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Total incl Overhead - As Incurred $ Mar 2017 |  | 3053.3877 | 262.5681 | 8299.2376 | 181.8234 | 185.2308 | 186.2542 | 185.7 | 187.0211 | 0 | 12541.2229 | 926.0295
|  |  | Check | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| As Commissioned Capex | Direct Expenditure (As Commissioned) - $ 2015/16 |  | 2779.9674 | 238.1366 | 7558.7252 | 164 | 164 | 164 | 164 | 164 | 0 | 11396.8292 | 820
|  | Labour & Material Escalation - $ 2015/16 |  | 0 | 0 | 50.0951 | 2.0805 | 3.0891 | 4.0812 | 5.1651 | 6.2846 | 0 | 70.7955 | 20.7004
|  | Total Direct Expenditure - $ 2015/16 |  | 2779.9674 | 238.1366 | 7608.8203 | 166.0805 | 167.0891 | 168.0812 | 169.1651 | 170.2846 | 0 | 11467.6247 | 840.7004
|  | Total Direct Expenditure - $ Mar 2017 |  | 2826.9969 | 242.1652 | 7737.541 | 168.8901 | 169.9158 | 170.9247 | 172.0269 | 173.1654 | 0 | 11661.6259 | 854.9228
|  | Total overheads (As Commissioned) |  | 226.3908 | 20.4029 | 561.6966 | 12.9333 | 15.315 | 15.3295 | 13.6731 | 13.8557 | 0 | 879.597 | 71.1067
|  | Total incl Overhead - As commissioned $ Mar 2017 |  | 3053.3877 | 262.5681 | 8299.2376 | 181.8234 | 185.2308 | 186.2542 | 185.7 | 187.0211 | 0 | 12541.2229 | 926.0295
|  | Total overheads (As Comm) - Cumulative |  | 226.3908 | 246.7936 | 808.4903 | 821.4236 | 836.7386 | 852.0681 | 865.7413 | 879.597 | 879.597
|  | Total real cost escalation (As Comm) - Cumulative |  | 0 | 0 | 50.0951 | 52.1756 | 55.2647 | 59.3459 | 64.5109 | 70.7955 | 70.7955
Expenditure By Asset Class - As Commissioned
| Asset class breakdown | Secondary |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| (fully absorbed) | Switchgear |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| (as commissioned) | Transformers |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Reactive |  | 3053.3877 | 262.5681 | 8299.2376 | 181.8234 | 185.2308 | 186.2542 | 185.7 | 187.0211 | 0 | 12541.2229 | 926.0295
|  | Lines and towers |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Establishment |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Communications |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Non System |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Land |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Easements |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Total incl Overhead - As commissioned $ Mar 2017 |  | 3053.3877 | 262.5681 | 8299.2376 | 181.8234 | 185.2308 | 186.2542 | 185.7 | 187.0211 | 0 | 12541.2229 | 926.0295
|  |  | Check | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0
| Expenditure splits for RIN |  |  |  | 2015-16 | 2016-17 | 2017-18 | 2018-19 | 2019-20 | 2020-21 | 2021-22 | 2022-23
| Repex Category | Transmission Towers | bar: 2015-16 to 2022-23
Transmission Tower Support Structures | bar: 2015-16 to 2022-23
Conductors | bar: 2015-16 to 2022-23
Transmission Cables | bar: 2015-16 to 2022-23
Substation Switchbays | bar: 2015-16 to 2022-23
Substation Power Transformers | bar: 2015-16 to 2022-23
|  | Substation Reactive Plant |  |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
Scada Network Control And Protection Systems | bar: 2015-16 to 2022-23
Other | bar: 2015-16 to 2022-23
|  | Total |  |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
| Direct Expenditures | Materials - $ Mar 2017 |  |  | 2015-16 | 2016-17 | 2017-18 | 2018-19 | 2019-20 | 2020-21 | 2021-22 | 2022-23 | Total | 2017-22 Total
| (As Incurred) | Transmission Towers |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Transmission Tower Support Structures |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Conductors |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Transmission Cables |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Substation Switchbays |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Substation Power Transformers |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Substation Reactive Plant |  |  | 96.8661 | 3074.6394 | 66.7098 | 66.7098 | 66.7098 | 66.7098 | 66.7098 | 0 | 3505.0543 | 333.5489
|  | Scada Network Control And Protection Systems |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Other |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Total Materials |  |  | 96.8661 | 3074.6394 | 66.7098 | 66.7098 | 66.7098 | 66.7098 | 66.7098 | 0 | 3505.0543 | 333.5489
|  | Labour (Internal) - $ Mar 2017 |  |  | 2015-16 | 2016-17 | 2017-18 | 2018-19 | 2019-20 | 2020-21 | 2021-22 | 2022-23 | Total | 2017-22 Total
|  | Transmission Towers |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Transmission Tower Support Structures |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Conductors |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Transmission Cables |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Substation Switchbays |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Substation Power Transformers |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Substation Reactive Plant |  |  | 24.2165 | 778.2787 | 17.0221 | 17.16 | 17.302 | 17.4568 | 17.6157 | 0 | 889.0516 | 86.5564
|  | Scada Network Control And Protection Systems |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Other |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Total Internal Labour |  |  | 24.2165 | 778.2787 | 17.0221 | 17.16 | 17.302 | 17.4568 | 17.6157 | 0 | 889.0516 | 86.5564
|  | Labour (External) - $ Mar 2017 |  |  | 2015-16 | 2016-17 | 2017-18 | 2018-19 | 2019-20 | 2020-21 | 2021-22 | 2022-23 | Total | 2017-22 Total
|  | Transmission Towers |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Transmission Tower Support Structures |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Conductors |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Transmission Cables |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Substation Switchbays |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Substation Power Transformers |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Substation Reactive Plant |  |  | 121.0826 | 3884.623 | 85.1583 | 86.046 | 86.9129 | 87.8603 | 88.8399 | 0 | 4440.523 | 434.8175
|  | Scada Network Control And Protection Systems |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Other |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Total External Labour |  |  | 121.0826 | 3884.623 | 85.1583 | 86.046 | 86.9129 | 87.8603 | 88.8399 | 0 | 4440.523 | 434.8175
|  | Total Direct - $ Mar 2017 |  |  | 2015-16 | 2016-17 | 2017-18 | 2018-19 | 2019-20 | 2020-21 | 2021-22 | 2022-23 | Total | 2017-22 Total
|  | Transmission Towers |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Transmission Tower Support Structures |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Conductors |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Transmission Cables |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Substation Switchbays |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Substation Power Transformers |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Substation Reactive Plant |  |  | 242.1652 | 7737.541 | 168.8901 | 169.9158 | 170.9247 | 172.0269 | 173.1654 | 0 | 8834.629 | 854.9228
|  | Scada Network Control And Protection Systems |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Other |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Total Direct - $ Mar 2017 |  |  | 242.1652 | 7737.541 | 168.8901 | 169.9158 | 170.9247 | 172.0269 | 173.1654 | 0 | 8834.629 | 854.9228

## Proj_28
Go To: | Table of Contents
Master Inputs
|  |  |  | Business case? | 0
| Project name | On-line monitoring
| Project category 1 | Network |  |  | Shaded cells = Inputs
| Project category 2 | Replacement - Other
| Regulatory classification | Prescribed
| Overhead Category | Repex_OHD |  | $000's | $000's | $000's | $000's | $000's | $000's | $000's | $000's | $000's | Project | 2017-22
|  |  |  | Prior | 2015-16 | 2016-17 | 2017-18 | 2018-19 | 2019-20 | 2020-21 | 2021-22 | 2022-23 | Total | Total | Check
| Project timing | Direct Expenditure (As incurred) - $ 2015/16 |  | 0 | 0 | 0 | 170 | 200 | 100 | 100 | 100 | 0 | 670 | 670 | ok
| (excluding real cost escalators) | Assumed year commissioned (no BC) | bar: 2015-16 to 2022-23
|  | Direct Expenditure (As Commissioned) - $ 2015/16 |  | 0 | 0 | 0 | 170 | 200 | 100 | 100 | 100 | 0 | 670 | 670 | ok
| Asset class | Secondary
Switchgear
Transformers
Reactive
Lines and towers
|  | Establishment |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
Communications
Non System
Land
Easements
|  |  | Total | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
| Input costs % | Labour - internal |  | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10%
|  | Labour - external |  | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50%
|  | Materials |  | 40% | 40% | 40% | 40% | 40% | 40% | 40% | 40% | 40%
|  |  | Total | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
Material Escalation
| (By Asset Class) | Secondary |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Switchgear |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Transformers |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Reactive |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Lines and towers |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Establishment |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Communications |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Non System |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Land |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Easements |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Total Material escalation |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Labour Escalation | Internal Labour |  | 0 | 0 | 0 | 0.3513 | 0.57864 | 0.37446 | 0.46731 | 0.56257 | 0 | 2.3343 | 2.3343
|  | External Labour |  | 0 | 0 | 0 | 1.8053 | 3.1885 | 2.1141 | 2.6821 | 3.2695 | 0 | 13.0595 | 13.0595
|  | Total Labour Escalation |  | 0 | 0 | 0 | 2.1566 | 3.7672 | 2.4885 | 3.1494 | 3.8321 | 0 | 15.3938 | 15.3938
|  | Total Escalation |  | 0 | 0 | 0 | 2.1566 | 3.7672 | 2.4885 | 3.1494 | 3.8321 | 0 | 15.3938 | 15.3938
|  | Escalation factors |  | 0 | 0 | 0 | 0.012686 | 0.018836 | 0.024885 | 0.031494 | 0.038321 | 0 | 0.022976 | 0.022976
| Direct Expenditure (Escalated) | Total labour - internal |  | 0 | 0 | 0 | 17.6448 | 20.9268 | 10.55 | 10.6444 | 10.7413 | 0 | 70.5072 | 70.5072
| (as incurred) | Total labour - external |  | 0 | 0 | 0 | 88.2738 | 104.9342 | 52.9957 | 53.5734 | 54.1707 | 0 | 353.9477 | 353.9477
|  | Total materials |  | 0 | 0 | 0 | 69.1504 | 81.3534 | 40.6767 | 40.6767 | 40.6767 | 0 | 272.5338 | 272.5338
|  | Total Direct - As Incurred $ Mar 2017 |  | 0 | 0 | 0 | 175.069 | 207.2143 | 104.2224 | 104.8944 | 105.5886 | 0 | 696.9888 | 696.9888 | ok
| Capitalised Overheads | Overhead rate (applied to direct expenditure) |  | 8.008% | 8.425% | 7.259% | 7.658% | 9.013% | 8.969% | 7.948% | 8.001% | 8.318%
|  | Total overhead (as incurred) |  | 0 | 0 | 0 | 13.4065 | 18.6769 | 9.3473 | 8.3373 | 8.4486 | 0 | 58.2165 | 58.2165
|  | Total incl Overhead - As Incurred $ Mar 2017 |  | 0 | 0 | 0 | 188.4755 | 225.8912 | 113.5696 | 113.2317 | 114.0372 | 0 | 755.2053 | 755.2053
|  | Total overheads (As incurred) - Cumulative |  | 0 | 0 | 0 | 13.4065 | 32.0834 | 41.4306 | 49.7679 | 58.2165 | 58.2165
|  | Labour & Material Escalation - Cumulative |  | 0 | 0 | 0 | 2.1566 | 5.9237 | 8.4123 | 11.5617 | 15.3938 | 15.3938
Expenditure By Asset Class - As Incurred
| Asset class breakdown | Secondary |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| (fully absorbed) | Switchgear |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| (as incurred) | Transformers |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Reactive |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Lines and towers |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Establishment |  | 0 | 0 | 0 | 188.4755 | 225.8912 | 113.5696 | 113.2317 | 114.0372 | 0 | 755.2053 | 755.2053
|  | Communications |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Non System |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Land |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Easements |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Total incl Overhead - As Incurred $ Mar 2017 |  | 0 | 0 | 0 | 188.4755 | 225.8912 | 113.5696 | 113.2317 | 114.0372 | 0 | 755.2053 | 755.2053
|  |  | Check | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| As Commissioned Capex | Direct Expenditure (As Commissioned) - $ 2015/16 |  | 0 | 0 | 0 | 170 | 200 | 100 | 100 | 100 | 0 | 670 | 670
|  | Labour & Material Escalation - $ 2015/16 |  | 0 | 0 | 0 | 2.1566 | 3.7672 | 2.4885 | 3.1494 | 3.8321 | 0 | 15.3938 | 15.3938
|  | Total Direct Expenditure - $ 2015/16 |  | 0 | 0 | 0 | 172.1566 | 203.7672 | 102.4885 | 103.1494 | 103.8321 | 0 | 685.3938 | 685.3938
|  | Total Direct Expenditure - $ Mar 2017 |  | 0 | 0 | 0 | 175.069 | 207.2143 | 104.2224 | 104.8944 | 105.5886 | 0 | 696.9888 | 696.9888
|  | Total overheads (As Commissioned) |  | 0 | 0 | 0 | 13.4065 | 18.6769 | 9.3473 | 8.3373 | 8.4486 | 0 | 58.2165 | 58.2165
|  | Total incl Overhead - As commissioned $ Mar 2017 |  | 0 | 0 | 0 | 188.4755 | 225.8912 | 113.5696 | 113.2317 | 114.0372 | 0 | 755.2053 | 755.2053
|  | Total overheads (As Comm) - Cumulative |  | 0 | 0 | 0 | 13.4065 | 32.0834 | 41.4306 | 49.7679 | 58.2165 | 58.2165
|  | Total real cost escalation (As Comm) - Cumulative |  | 0 | 0 | 0 | 2.1566 | 5.9237 | 8.4123 | 11.5617 | 15.3938 | 15.3938
Expenditure By Asset Class - As Commissioned
| Asset class breakdown | Secondary |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| (fully absorbed) | Switchgear |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| (as commissioned) | Transformers |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Reactive |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Lines and towers |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Establishment |  | 0 | 0 | 0 | 188.4755 | 225.8912 | 113.5696 | 113.2317 | 114.0372 | 0 | 755.2053 | 755.2053
|  | Communications |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Non System |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Land |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Easements |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Total incl Overhead - As commissioned $ Mar 2017 |  | 0 | 0 | 0 | 188.4755 | 225.8912 | 113.5696 | 113.2317 | 114.0372 | 0 | 755.2053 | 755.2053
|  |  | Check | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0
| Expenditure splits for RIN |  |  |  | 2015-16 | 2016-17 | 2017-18 | 2018-19 | 2019-20 | 2020-21 | 2021-22 | 2022-23
| Repex Category | Transmission Towers | bar: 2015-16 to 2022-23
Transmission Tower Support Structures | bar: 2015-16 to 2022-23
Conductors | bar: 2015-16 to 2022-23
Transmission Cables | bar: 2015-16 to 2022-23
Substation Switchbays | bar: 2015-16 to 2022-23
Substation Power Transformers | bar: 2015-16 to 2022-23
Substation Reactive Plant | bar: 2015-16 to 2022-23
Scada Network Control And Protection Systems | bar: 2015-16 to 2022-23
|  | Other |  |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
|  | Total |  |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
| Direct Expenditures | Materials - $ Mar 2017 |  |  | 2015-16 | 2016-17 | 2017-18 | 2018-19 | 2019-20 | 2020-21 | 2021-22 | 2022-23 | Total | 2017-22 Total
| (As Incurred) | Transmission Towers |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Transmission Tower Support Structures |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Conductors |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Transmission Cables |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Substation Switchbays |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Substation Power Transformers |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Substation Reactive Plant |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Scada Network Control And Protection Systems |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Other |  |  | 0 | 0 | 69.1504 | 81.3534 | 40.6767 | 40.6767 | 40.6767 | 0 | 272.5338 | 272.5338
|  | Total Materials |  |  | 0 | 0 | 69.1504 | 81.3534 | 40.6767 | 40.6767 | 40.6767 | 0 | 272.5338 | 272.5338
|  | Labour (Internal) - $ Mar 2017 |  |  | 2015-16 | 2016-17 | 2017-18 | 2018-19 | 2019-20 | 2020-21 | 2021-22 | 2022-23 | Total | 2017-22 Total
|  | Transmission Towers |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Transmission Tower Support Structures |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Conductors |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Transmission Cables |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Substation Switchbays |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Substation Power Transformers |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Substation Reactive Plant |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Scada Network Control And Protection Systems |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Other |  |  | 0 | 0 | 17.6448 | 20.9268 | 10.55 | 10.6444 | 10.7413 | 0 | 70.5072 | 70.5072
|  | Total Internal Labour |  |  | 0 | 0 | 17.6448 | 20.9268 | 10.55 | 10.6444 | 10.7413 | 0 | 70.5072 | 70.5072
|  | Labour (External) - $ Mar 2017 |  |  | 2015-16 | 2016-17 | 2017-18 | 2018-19 | 2019-20 | 2020-21 | 2021-22 | 2022-23 | Total | 2017-22 Total
|  | Transmission Towers |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Transmission Tower Support Structures |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Conductors |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Transmission Cables |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Substation Switchbays |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Substation Power Transformers |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Substation Reactive Plant |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Scada Network Control And Protection Systems |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Other |  |  | 0 | 0 | 88.2738 | 104.9342 | 52.9957 | 53.5734 | 54.1707 | 0 | 353.9477 | 353.9477
|  | Total External Labour |  |  | 0 | 0 | 88.2738 | 104.9342 | 52.9957 | 53.5734 | 54.1707 | 0 | 353.9477 | 353.9477
|  | Total Direct - $ Mar 2017 |  |  | 2015-16 | 2016-17 | 2017-18 | 2018-19 | 2019-20 | 2020-21 | 2021-22 | 2022-23 | Total | 2017-22 Total
|  | Transmission Towers |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Transmission Tower Support Structures |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Conductors |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Transmission Cables |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Substation Switchbays |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Substation Power Transformers |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Substation Reactive Plant |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Scada Network Control And Protection Systems |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Other |  |  | 0 | 0 | 175.069 | 207.2143 | 104.2224 | 104.8944 | 105.5886 | 0 | 696.9888 | 696.9888
|  | Total Direct - $ Mar 2017 |  |  | 0 | 0 | 175.069 | 207.2143 | 104.2224 | 104.8944 | 105.5886 | 0 | 696.9888 | 696.9888

## Proj_29
Go To: | Table of Contents
Master Inputs
|  | Various |  | Business case? | 0
| Project name | Fire protection systems
| Project category 1 | Network |  |  | Shaded cells = Inputs
| Project category 2 | Security and Compliance
| Regulatory classification | Prescribed
| Overhead Category | Repex_OHD |  | $000's | $000's | $000's | $000's | $000's | $000's | $000's | $000's | $000's | Project | 2017-22
|  |  |  | Prior | 2015-16 | 2016-17 | 2017-18 | 2018-19 | 2019-20 | 2020-21 | 2021-22 | 2022-23 | Total | Total | Check
| Project timing | Direct Expenditure (As incurred) - $ 2015/16 |  | 2142.867 | 2646.2623 | 2375.079 | 1755 | 1755 | 1755 | 1755 | 1755 | 0 | 15939.2083 | 8775 | ok
| (excluding real cost escalators) | Assumed year commissioned (no BC) |  | x | bar: 2015-16 to 2022-23
|  | Direct Expenditure (As Commissioned) - $ 2015/16 |  | 2142.867 | 2646.2623 | 2375.079 | 1755 | 1755 | 1755 | 1755 | 1755 | 0 | 15939.2083 | 8775 | ok
| Asset class | Secondary
Switchgear
Transformers
Reactive
Lines and towers
|  | Establishment |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
Communications
Non System
Land
Easements
|  |  | Total | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
| Input costs % | Labour - internal |  | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10%
|  | Labour - external |  | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50%
|  | Materials |  | 40% | 40% | 40% | 40% | 40% | 40% | 40% | 40% | 40%
|  |  | Total | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
Material Escalation
| (By Asset Class) | Secondary |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Switchgear |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Transformers |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Reactive |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Lines and towers |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Establishment |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Communications |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Non System |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Land |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Easements |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Total Material escalation |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Labour Escalation | Internal Labour |  | 0 | 0 | 2.9721 | 3.6266 | 5.0775 | 6.5718 | 8.2014 | 9.8731 | 0 | 36.3225 | 33.3504
|  | External Labour |  | 0 | 0 | 12.7686 | 18.637 | 27.9792 | 37.1019 | 47.0711 | 57.38 | 0 | 200.9378 | 188.1692
|  | Total Labour Escalation |  | 0 | 0 | 15.7407 | 22.2636 | 33.0567 | 43.6737 | 55.2724 | 67.2531 | 0 | 237.2603 | 221.5196
|  | Total Escalation |  | 0 | 0 | 15.7407 | 22.2636 | 33.0567 | 43.6737 | 55.2724 | 67.2531 | 0 | 237.2603 | 221.5196
|  | Escalation factors |  | 0 | 0 | 0.0066275 | 0.012686 | 0.018836 | 0.024885 | 0.031494 | 0.038321 | 0 | 0.014885 | 0.025244
| Direct Expenditure (Escalated) | Total labour - internal |  | 217.9119 | 269.103 | 244.5483 | 182.157 | 183.6324 | 185.152 | 186.8091 | 188.5091 | 0 | 1657.8227 | 926.2595
| (as incurred) | Total labour - external |  | 1089.5593 | 1345.5149 | 1220.6141 | 911.2972 | 920.7975 | 930.0745 | 940.2123 | 950.6957 | 0 | 8308.7654 | 4653.0771
|  | Total materials |  | 871.6474 | 1076.412 | 966.1035 | 713.8759 | 713.8759 | 713.8759 | 713.8759 | 713.8759 | 0 | 6483.5426 | 3569.3797
|  | Total Direct - As Incurred $ Mar 2017 |  | 2179.1185 | 2691.0299 | 2431.2659 | 1807.3301 | 1818.3058 | 1829.1024 | 1840.8973 | 1853.0807 | 0 | 16450.1306 | 9148.7164 | ok
| Capitalised Overheads | Overhead rate (applied to direct expenditure) |  | 8.008% | 8.425% | 7.259% | 7.658% | 9.013% | 8.969% | 7.948% | 8.001% | 8.318%
|  | Total overhead (as incurred) |  | 174.5076 | 226.7242 | 176.4946 | 138.4025 | 163.8896 | 164.0444 | 146.3193 | 148.2729 | 0 | 1338.655 | 760.9286
|  | Total incl Overhead - As Incurred $ Mar 2017 |  | 2353.6261 | 2917.7541 | 2607.7604 | 1945.7326 | 1982.1954 | 1993.1469 | 1987.2166 | 2001.3535 | 0 | 17788.7856 | 9909.645
|  | Total overheads (As incurred) - Cumulative |  | 174.5076 | 401.2318 | 577.7263 | 716.1289 | 880.0184 | 1044.0629 | 1190.3821 | 1338.655 | 1338.655
|  | Labour & Material Escalation - Cumulative |  | 0 | 0 | 15.7407 | 38.0043 | 71.0611 | 114.7348 | 170.0072 | 237.2603 | 237.2603
Expenditure By Asset Class - As Incurred
| Asset class breakdown | Secondary |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| (fully absorbed) | Switchgear |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| (as incurred) | Transformers |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Reactive |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Lines and towers |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Establishment |  | 2353.6261 | 2917.7541 | 2607.7604 | 1945.7326 | 1982.1954 | 1993.1469 | 1987.2166 | 2001.3535 | 0 | 17788.7856 | 9909.645
|  | Communications |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Non System |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Land |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Easements |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Total incl Overhead - As Incurred $ Mar 2017 |  | 2353.6261 | 2917.7541 | 2607.7604 | 1945.7326 | 1982.1954 | 1993.1469 | 1987.2166 | 2001.3535 | 0 | 17788.7856 | 9909.645
|  |  | Check | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| As Commissioned Capex | Direct Expenditure (As Commissioned) - $ 2015/16 |  | 2142.867 | 2646.2623 | 2375.079 | 1755 | 1755 | 1755 | 1755 | 1755 | 0 | 15939.2083 | 8775
|  | Labour & Material Escalation - $ 2015/16 |  | 0 | 0 | 15.7407 | 22.2636 | 33.0567 | 43.6737 | 55.2724 | 67.2531 | 0 | 237.2603 | 221.5196
|  | Total Direct Expenditure - $ 2015/16 |  | 2142.867 | 2646.2623 | 2390.8197 | 1777.2636 | 1788.0567 | 1798.6737 | 1810.2724 | 1822.2531 | 0 | 16176.4686 | 8996.5196
|  | Total Direct Expenditure - $ Mar 2017 |  | 2179.1185 | 2691.0299 | 2431.2659 | 1807.3301 | 1818.3058 | 1829.1024 | 1840.8973 | 1853.0807 | 0 | 16450.1306 | 9148.7164
|  | Total overheads (As Commissioned) |  | 174.5076 | 226.7242 | 176.4946 | 138.4025 | 163.8896 | 164.0444 | 146.3193 | 148.2729 | 0 | 1338.655 | 760.9286
|  | Total incl Overhead - As commissioned $ Mar 2017 |  | 2353.6261 | 2917.7541 | 2607.7604 | 1945.7326 | 1982.1954 | 1993.1469 | 1987.2166 | 2001.3535 | 0 | 17788.7856 | 9909.645
|  | Total overheads (As Comm) - Cumulative |  | 174.5076 | 401.2318 | 577.7263 | 716.1289 | 880.0184 | 1044.0629 | 1190.3821 | 1338.655 | 1338.655
|  | Total real cost escalation (As Comm) - Cumulative |  | 0 | 0 | 15.7407 | 38.0043 | 71.0611 | 114.7348 | 170.0072 | 237.2603 | 237.2603
Expenditure By Asset Class - As Commissioned
| Asset class breakdown | Secondary |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| (fully absorbed) | Switchgear |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| (as commissioned) | Transformers |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Reactive |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Lines and towers |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Establishment |  | 2353.6261 | 2917.7541 | 2607.7604 | 1945.7326 | 1982.1954 | 1993.1469 | 1987.2166 | 2001.3535 | 0 | 17788.7856 | 9909.645
|  | Communications |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Non System |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Land |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Easements |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Total incl Overhead - As commissioned $ Mar 2017 |  | 2353.6261 | 2917.7541 | 2607.7604 | 1945.7326 | 1982.1954 | 1993.1469 | 1987.2166 | 2001.3535 | 0 | 17788.7856 | 9909.645
|  |  | Check | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0
| Expenditure splits for RIN |  |  |  | 2015-16 | 2016-17 | 2017-18 | 2018-19 | 2019-20 | 2020-21 | 2021-22 | 2022-23
| Repex Category | Transmission Towers | bar: 2015-16 to 2022-23
Transmission Tower Support Structures | bar: 2015-16 to 2022-23
Conductors | bar: 2015-16 to 2022-23
Transmission Cables | bar: 2015-16 to 2022-23
Substation Switchbays | bar: 2015-16 to 2022-23
Substation Power Transformers | bar: 2015-16 to 2022-23
Substation Reactive Plant | bar: 2015-16 to 2022-23
Scada Network Control And Protection Systems | bar: 2015-16 to 2022-23
|  | Other |  |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
|  | Total |  |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
| Direct Expenditures | Materials - $ Mar 2017 |  |  | 2015-16 | 2016-17 | 2017-18 | 2018-19 | 2019-20 | 2020-21 | 2021-22 | 2022-23 | Total | 2017-22 Total
| (As Incurred) | Transmission Towers |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Transmission Tower Support Structures |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Conductors |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Transmission Cables |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Substation Switchbays |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Substation Power Transformers |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Substation Reactive Plant |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Scada Network Control And Protection Systems |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Other |  |  | 1076.412 | 966.1035 | 713.8759 | 713.8759 | 713.8759 | 713.8759 | 713.8759 | 0 | 5611.8952 | 3569.3797
|  | Total Materials |  |  | 1076.412 | 966.1035 | 713.8759 | 713.8759 | 713.8759 | 713.8759 | 713.8759 | 0 | 5611.8952 | 3569.3797
|  | Labour (Internal) - $ Mar 2017 |  |  | 2015-16 | 2016-17 | 2017-18 | 2018-19 | 2019-20 | 2020-21 | 2021-22 | 2022-23 | Total | 2017-22 Total
|  | Transmission Towers |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Transmission Tower Support Structures |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Conductors |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Transmission Cables |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Substation Switchbays |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Substation Power Transformers |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Substation Reactive Plant |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Scada Network Control And Protection Systems |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Other |  |  | 269.103 | 244.5483 | 182.157 | 183.6324 | 185.152 | 186.8091 | 188.5091 | 0 | 1439.9108 | 926.2595
|  | Total Internal Labour |  |  | 269.103 | 244.5483 | 182.157 | 183.6324 | 185.152 | 186.8091 | 188.5091 | 0 | 1439.9108 | 926.2595
|  | Labour (External) - $ Mar 2017 |  |  | 2015-16 | 2016-17 | 2017-18 | 2018-19 | 2019-20 | 2020-21 | 2021-22 | 2022-23 | Total | 2017-22 Total
|  | Transmission Towers |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Transmission Tower Support Structures |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Conductors |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Transmission Cables |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Substation Switchbays |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Substation Power Transformers |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Substation Reactive Plant |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Scada Network Control And Protection Systems |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Other |  |  | 1345.5149 | 1220.6141 | 911.2972 | 920.7975 | 930.0745 | 940.2123 | 950.6957 | 0 | 7219.2061 | 4653.0771
|  | Total External Labour |  |  | 1345.5149 | 1220.6141 | 911.2972 | 920.7975 | 930.0745 | 940.2123 | 950.6957 | 0 | 7219.2061 | 4653.0771
|  | Total Direct - $ Mar 2017 |  |  | 2015-16 | 2016-17 | 2017-18 | 2018-19 | 2019-20 | 2020-21 | 2021-22 | 2022-23 | Total | 2017-22 Total
|  | Transmission Towers |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Transmission Tower Support Structures |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Conductors |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Transmission Cables |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Substation Switchbays |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Substation Power Transformers |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Substation Reactive Plant |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Scada Network Control And Protection Systems |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Other |  |  | 2691.0299 | 2431.2659 | 1807.3301 | 1818.3058 | 1829.1024 | 1840.8973 | 1853.0807 | 0 | 14271.0121 | 9148.7164
|  | Total Direct - $ Mar 2017 |  |  | 2691.0299 | 2431.2659 | 1807.3301 | 1818.3058 | 1829.1024 | 1840.8973 | 1853.0807 | 0 | 14271.0121 | 9148.7164

## Proj_30
Go To: | Table of Contents
Master Inputs
|  |  |  | Business case? | 0
| Project name | Civils
| Project category 1 | Network |  |  | Shaded cells = Inputs
| Project category 2 | Replacement - Other
| Regulatory classification | Prescribed
| Overhead Category | Repex_OHD |  | $000's | $000's | $000's | $000's | $000's | $000's | $000's | $000's | $000's | Project | 2017-22
|  |  |  | Prior | 2015-16 | 2016-17 | 2017-18 | 2018-19 | 2019-20 | 2020-21 | 2021-22 | 2022-23 | Total | Total | Check
| Project timing | Direct Expenditure (As incurred) - $ 2015/16 |  | 0 | 0 | 0 | 1770 | 1770 | 1770 | 1770 | 1770 | 0 | 8850 | 8850 | ok
| (excluding real cost escalators) | Assumed year commissioned (no BC) | bar: 2015-16 to 2022-23
|  | Direct Expenditure (As Commissioned) - $ 2015/16 |  | 0 | 0 | 0 | 1770 | 1770 | 1770 | 1770 | 1770 | 0 | 8850 | 8850 | ok
| Asset class | Secondary
Switchgear
Transformers
Reactive
Lines and towers
|  | Establishment |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
Communications
Non System
Land
Easements
|  |  | Total | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
| Input costs % | Labour - internal |  | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10%
|  | Labour - external |  | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50%
|  | Materials |  | 40% | 40% | 40% | 40% | 40% | 40% | 40% | 40% | 40%
|  |  | Total | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
Material Escalation
| (By Asset Class) | Secondary |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Switchgear |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Transformers |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Reactive |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Lines and towers |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Establishment |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Communications |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Non System |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Land |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Easements |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Total Material escalation |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Labour Escalation | Internal Labour |  | 0 | 0 | 0 | 3.6576 | 5.1209 | 6.628 | 8.2715 | 9.9574 | 0 | 33.6355 | 33.6355
|  | External Labour |  | 0 | 0 | 0 | 18.7963 | 28.2183 | 37.419 | 47.4734 | 57.8705 | 0 | 189.7775 | 189.7775
|  | Total Labour Escalation |  | 0 | 0 | 0 | 22.4539 | 33.3393 | 44.047 | 55.7448 | 67.8279 | 0 | 223.4129 | 223.4129
|  | Total Escalation |  | 0 | 0 | 0 | 22.4539 | 33.3393 | 44.047 | 55.7448 | 67.8279 | 0 | 223.4129 | 223.4129
|  | Escalation factors |  | 0 | 0 | 0 | 0.012686 | 0.018836 | 0.024885 | 0.031494 | 0.038321 | 0 | 0.025244 | 0.025244
| Direct Expenditure (Escalated) | Total labour - internal |  | 0 | 0 | 0 | 183.7139 | 185.2019 | 186.7345 | 188.4058 | 190.1203 | 0 | 934.1763 | 934.1763
| (as incurred) | Total labour - external |  | 0 | 0 | 0 | 919.0861 | 928.6675 | 938.0238 | 948.2483 | 958.8213 | 0 | 4692.847 | 4692.847
|  | Total materials |  | 0 | 0 | 0 | 719.9774 | 719.9774 | 719.9774 | 719.9774 | 719.9774 | 0 | 3599.8872 | 3599.8872
|  | Total Direct - As Incurred $ Mar 2017 |  | 0 | 0 | 0 | 1822.7774 | 1833.8469 | 1844.7358 | 1856.6315 | 1868.919 | 0 | 9226.9105 | 9226.9105 | ok
| Capitalised Overheads | Overhead rate (applied to direct expenditure) |  | 8.008% | 8.425% | 7.259% | 7.658% | 9.013% | 8.969% | 7.948% | 8.001% | 8.318%
|  | Total overhead (as incurred) |  | 0 | 0 | 0 | 139.5855 | 165.2903 | 165.4465 | 147.5699 | 149.5401 | 0 | 767.4323 | 767.4323
|  | Total incl Overhead - As Incurred $ Mar 2017 |  | 0 | 0 | 0 | 1962.3628 | 1999.1372 | 2010.1823 | 2004.2014 | 2018.4591 | 0 | 9994.3428 | 9994.3428
|  | Total overheads (As incurred) - Cumulative |  | 0 | 0 | 0 | 139.5855 | 304.8758 | 470.3223 | 617.8922 | 767.4323 | 767.4323
|  | Labour & Material Escalation - Cumulative |  | 0 | 0 | 0 | 22.4539 | 55.7932 | 99.8402 | 155.585 | 223.4129 | 223.4129
Expenditure By Asset Class - As Incurred
| Asset class breakdown | Secondary |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| (fully absorbed) | Switchgear |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| (as incurred) | Transformers |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Reactive |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Lines and towers |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Establishment |  | 0 | 0 | 0 | 1962.3628 | 1999.1372 | 2010.1823 | 2004.2014 | 2018.4591 | 0 | 9994.3428 | 9994.3428
|  | Communications |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Non System |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Land |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Easements |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Total incl Overhead - As Incurred $ Mar 2017 |  | 0 | 0 | 0 | 1962.3628 | 1999.1372 | 2010.1823 | 2004.2014 | 2018.4591 | 0 | 9994.3428 | 9994.3428
|  |  | Check | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| As Commissioned Capex | Direct Expenditure (As Commissioned) - $ 2015/16 |  | 0 | 0 | 0 | 1770 | 1770 | 1770 | 1770 | 1770 | 0 | 8850 | 8850
|  | Labour & Material Escalation - $ 2015/16 |  | 0 | 0 | 0 | 22.4539 | 33.3393 | 44.047 | 55.7448 | 67.8279 | 0 | 223.4129 | 223.4129
|  | Total Direct Expenditure - $ 2015/16 |  | 0 | 0 | 0 | 1792.4539 | 1803.3393 | 1814.047 | 1825.7448 | 1837.8279 | 0 | 9073.4129 | 9073.4129
|  | Total Direct Expenditure - $ Mar 2017 |  | 0 | 0 | 0 | 1822.7774 | 1833.8469 | 1844.7358 | 1856.6315 | 1868.919 | 0 | 9226.9105 | 9226.9105
|  | Total overheads (As Commissioned) |  | 0 | 0 | 0 | 139.5855 | 165.2903 | 165.4465 | 147.5699 | 149.5401 | 0 | 767.4323 | 767.4323
|  | Total incl Overhead - As commissioned $ Mar 2017 |  | 0 | 0 | 0 | 1962.3628 | 1999.1372 | 2010.1823 | 2004.2014 | 2018.4591 | 0 | 9994.3428 | 9994.3428
|  | Total overheads (As Comm) - Cumulative |  | 0 | 0 | 0 | 139.5855 | 304.8758 | 470.3223 | 617.8922 | 767.4323 | 767.4323
|  | Total real cost escalation (As Comm) - Cumulative |  | 0 | 0 | 0 | 22.4539 | 55.7932 | 99.8402 | 155.585 | 223.4129 | 223.4129
Expenditure By Asset Class - As Commissioned
| Asset class breakdown | Secondary |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| (fully absorbed) | Switchgear |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| (as commissioned) | Transformers |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Reactive |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Lines and towers |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Establishment |  | 0 | 0 | 0 | 1962.3628 | 1999.1372 | 2010.1823 | 2004.2014 | 2018.4591 | 0 | 9994.3428 | 9994.3428
|  | Communications |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Non System |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Land |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Easements |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Total incl Overhead - As commissioned $ Mar 2017 |  | 0 | 0 | 0 | 1962.3628 | 1999.1372 | 2010.1823 | 2004.2014 | 2018.4591 | 0 | 9994.3428 | 9994.3428
|  |  | Check | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0
| Expenditure splits for RIN |  |  |  | 2015-16 | 2016-17 | 2017-18 | 2018-19 | 2019-20 | 2020-21 | 2021-22 | 2022-23
| Repex Category | Transmission Towers | bar: 2015-16 to 2022-23
Transmission Tower Support Structures | bar: 2015-16 to 2022-23
Conductors | bar: 2015-16 to 2022-23
Transmission Cables | bar: 2015-16 to 2022-23
Substation Switchbays | bar: 2015-16 to 2022-23
Substation Power Transformers | bar: 2015-16 to 2022-23
Substation Reactive Plant | bar: 2015-16 to 2022-23
Scada Network Control And Protection Systems | bar: 2015-16 to 2022-23
|  | Other |  |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
|  | Total |  |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
| Direct Expenditures | Materials - $ Mar 2017 |  |  | 2015-16 | 2016-17 | 2017-18 | 2018-19 | 2019-20 | 2020-21 | 2021-22 | 2022-23 | Total | 2017-22 Total
| (As Incurred) | Transmission Towers |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Transmission Tower Support Structures |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Conductors |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Transmission Cables |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Substation Switchbays |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Substation Power Transformers |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Substation Reactive Plant |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Scada Network Control And Protection Systems |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Other |  |  | 0 | 0 | 719.9774 | 719.9774 | 719.9774 | 719.9774 | 719.9774 | 0 | 3599.8872 | 3599.8872
|  | Total Materials |  |  | 0 | 0 | 719.9774 | 719.9774 | 719.9774 | 719.9774 | 719.9774 | 0 | 3599.8872 | 3599.8872
|  | Labour (Internal) - $ Mar 2017 |  |  | 2015-16 | 2016-17 | 2017-18 | 2018-19 | 2019-20 | 2020-21 | 2021-22 | 2022-23 | Total | 2017-22 Total
|  | Transmission Towers |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Transmission Tower Support Structures |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Conductors |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Transmission Cables |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Substation Switchbays |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Substation Power Transformers |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Substation Reactive Plant |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Scada Network Control And Protection Systems |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Other |  |  | 0 | 0 | 183.7139 | 185.2019 | 186.7345 | 188.4058 | 190.1203 | 0 | 934.1763 | 934.1763
|  | Total Internal Labour |  |  | 0 | 0 | 183.7139 | 185.2019 | 186.7345 | 188.4058 | 190.1203 | 0 | 934.1763 | 934.1763
|  | Labour (External) - $ Mar 2017 |  |  | 2015-16 | 2016-17 | 2017-18 | 2018-19 | 2019-20 | 2020-21 | 2021-22 | 2022-23 | Total | 2017-22 Total
|  | Transmission Towers |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Transmission Tower Support Structures |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Conductors |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Transmission Cables |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Substation Switchbays |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Substation Power Transformers |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Substation Reactive Plant |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Scada Network Control And Protection Systems |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Other |  |  | 0 | 0 | 919.0861 | 928.6675 | 938.0238 | 948.2483 | 958.8213 | 0 | 4692.847 | 4692.847
|  | Total External Labour |  |  | 0 | 0 | 919.0861 | 928.6675 | 938.0238 | 948.2483 | 958.8213 | 0 | 4692.847 | 4692.847
|  | Total Direct - $ Mar 2017 |  |  | 2015-16 | 2016-17 | 2017-18 | 2018-19 | 2019-20 | 2020-21 | 2021-22 | 2022-23 | Total | 2017-22 Total
|  | Transmission Towers |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Transmission Tower Support Structures |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Conductors |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Transmission Cables |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Substation Switchbays |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Substation Power Transformers |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Substation Reactive Plant |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Scada Network Control And Protection Systems |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Other |  |  | 0 | 0 | 1822.7774 | 1833.8469 | 1844.7358 | 1856.6315 | 1868.919 | 0 | 9226.9105 | 9226.9105
|  | Total Direct - $ Mar 2017 |  |  | 0 | 0 | 1822.7774 | 1833.8469 | 1844.7358 | 1856.6315 | 1868.919 | 0 | 9226.9105 | 9226.9105

## Proj_31
Go To: | Table of Contents
Master Inputs
|  |  |  | Business case? | 0
| Project name | Infrastructure security
| Project category 1 | Network |  |  | Shaded cells = Inputs
| Project category 2 | Security and Compliance
| Regulatory classification | Prescribed
| Overhead Category | Repex_OHD |  | $000's | $000's | $000's | $000's | $000's | $000's | $000's | $000's | $000's | Project | 2017-22
|  |  |  | Prior | 2015-16 | 2016-17 | 2017-18 | 2018-19 | 2019-20 | 2020-21 | 2021-22 | 2022-23 | Total | Total | Check
| Project timing | Direct Expenditure (As incurred) - $ 2015/16 |  | 878.7768 | 1369.4976 | 1764.4902 | 2500 | 2500 | 2500 | 2500 | 2500 | 0 | 16512.7647 | 12500 | ok
| (excluding real cost escalators) | Assumed year commissioned (no BC) |  | x | bar: 2015-16 to 2022-23
|  | Direct Expenditure (As Commissioned) - $ 2015/16 |  | 878.7768 | 1369.4976 | 1764.4902 | 2500 | 2500 | 2500 | 2500 | 2500 | 0 | 16512.7647 | 12500 | ok
| Asset class | Secondary
Switchgear
Transformers
Reactive
Lines and towers
|  | Establishment |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
Communications
Non System
Land
Easements
|  |  | Total | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
| Input costs % | Labour - internal |  | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10%
|  | Labour - external |  | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50%
|  | Materials |  | 40% | 40% | 40% | 40% | 40% | 40% | 40% | 40% | 40%
|  |  | Total | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
Material Escalation
| (By Asset Class) | Secondary |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Switchgear |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Transformers |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Reactive |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Lines and towers |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Establishment |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Communications |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Non System |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Land |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Easements |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Total Material escalation |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Labour Escalation | Internal Labour |  | 0 | 0 | 2.208 | 5.1661 | 7.233 | 9.3616 | 11.6829 | 14.0642 | 0 | 49.7158 | 47.5077
|  | External Labour |  | 0 | 0 | 9.486 | 26.5484 | 39.8564 | 52.8517 | 67.0528 | 81.7379 | 0 | 277.5333 | 268.0473
|  | Total Labour Escalation |  | 0 | 0 | 11.6941 | 31.7145 | 47.0894 | 62.2133 | 78.7357 | 95.8021 | 0 | 327.2491 | 315.555
|  | Total Escalation |  | 0 | 0 | 11.6941 | 31.7145 | 47.0894 | 62.2133 | 78.7357 | 95.8021 | 0 | 327.2491 | 315.555
|  | Escalation factors |  | 0 | 0 | 0.0066275 | 0.012686 | 0.018836 | 0.024885 | 0.031494 | 0.038321 | 0 | 0.019818 | 0.025244
| Direct Expenditure (Escalated) | Total labour - internal |  | 89.3643 | 139.2666 | 181.6795 | 259.4828 | 261.5847 | 263.7493 | 266.1098 | 268.5314 | 0 | 1729.7684 | 1319.458
| (as incurred) | Total labour - external |  | 446.8217 | 696.3329 | 906.8168 | 1298.1441 | 1311.6773 | 1324.8924 | 1339.3338 | 1354.2673 | 0 | 8678.2864 | 6628.315
|  | Total materials |  | 357.4573 | 557.0663 | 717.7363 | 1016.9173 | 1016.9173 | 1016.9173 | 1016.9173 | 1016.9173 | 0 | 6716.8464 | 5084.5865
|  | Total Direct - As Incurred $ Mar 2017 |  | 893.6433 | 1392.6658 | 1806.2326 | 2574.5443 | 2590.1792 | 2605.559 | 2622.3609 | 2639.7161 | 0 | 17124.9012 | 13032.3595 | ok
| Capitalised Overheads | Overhead rate (applied to direct expenditure) |  | 8.008% | 8.425% | 7.259% | 7.658% | 9.013% | 8.969% | 7.948% | 8.001% | 8.318%
|  | Total overhead (as incurred) |  | 71.5645 | 117.3347 | 131.1211 | 197.1546 | 233.4609 | 233.6815 | 208.432 | 211.2149 | 0 | 1403.9642 | 1083.9439
|  | Total incl Overhead - As Incurred $ Mar 2017 |  | 965.2078 | 1510.0005 | 1937.3536 | 2771.6989 | 2823.6402 | 2839.2405 | 2830.7929 | 2850.931 | 0 | 18528.8653 | 14116.3034
|  | Total overheads (As incurred) - Cumulative |  | 71.5645 | 188.8991 | 320.0202 | 517.1748 | 750.6357 | 984.3173 | 1192.7493 | 1403.9642 | 1403.9642
|  | Labour & Material Escalation - Cumulative |  | 0 | 0 | 11.6941 | 43.4086 | 90.498 | 152.7113 | 231.4469 | 327.2491 | 327.2491
Expenditure By Asset Class - As Incurred
| Asset class breakdown | Secondary |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| (fully absorbed) | Switchgear |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| (as incurred) | Transformers |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Reactive |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Lines and towers |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Establishment |  | 965.2078 | 1510.0005 | 1937.3536 | 2771.6989 | 2823.6402 | 2839.2405 | 2830.7929 | 2850.931 | 0 | 18528.8653 | 14116.3034
|  | Communications |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Non System |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Land |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Easements |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Total incl Overhead - As Incurred $ Mar 2017 |  | 965.2078 | 1510.0005 | 1937.3536 | 2771.6989 | 2823.6402 | 2839.2405 | 2830.7929 | 2850.931 | 0 | 18528.8653 | 14116.3034
|  |  | Check | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| As Commissioned Capex | Direct Expenditure (As Commissioned) - $ 2015/16 |  | 878.7768 | 1369.4976 | 1764.4902 | 2500 | 2500 | 2500 | 2500 | 2500 | 0 | 16512.7647 | 12500
|  | Labour & Material Escalation - $ 2015/16 |  | 0 | 0 | 11.6941 | 31.7145 | 47.0894 | 62.2133 | 78.7357 | 95.8021 | 0 | 327.2491 | 315.555
|  | Total Direct Expenditure - $ 2015/16 |  | 878.7768 | 1369.4976 | 1776.1843 | 2531.7145 | 2547.0894 | 2562.2133 | 2578.7357 | 2595.8021 | 0 | 16840.0137 | 12815.555
|  | Total Direct Expenditure - $ Mar 2017 |  | 893.6433 | 1392.6658 | 1806.2326 | 2574.5443 | 2590.1792 | 2605.559 | 2622.3609 | 2639.7161 | 0 | 17124.9012 | 13032.3595
|  | Total overheads (As Commissioned) |  | 71.5645 | 117.3347 | 131.1211 | 197.1546 | 233.4609 | 233.6815 | 208.432 | 211.2149 | 0 | 1403.9642 | 1083.9439
|  | Total incl Overhead - As commissioned $ Mar 2017 |  | 965.2078 | 1510.0005 | 1937.3536 | 2771.6989 | 2823.6402 | 2839.2405 | 2830.7929 | 2850.931 | 0 | 18528.8653 | 14116.3034
|  | Total overheads (As Comm) - Cumulative |  | 71.5645 | 188.8991 | 320.0202 | 517.1748 | 750.6357 | 984.3173 | 1192.7493 | 1403.9642 | 1403.9642
|  | Total real cost escalation (As Comm) - Cumulative |  | 0 | 0 | 11.6941 | 43.4086 | 90.498 | 152.7113 | 231.4469 | 327.2491 | 327.2491
Expenditure By Asset Class - As Commissioned
| Asset class breakdown | Secondary |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| (fully absorbed) | Switchgear |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| (as commissioned) | Transformers |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Reactive |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Lines and towers |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Establishment |  | 965.2078 | 1510.0005 | 1937.3536 | 2771.6989 | 2823.6402 | 2839.2405 | 2830.7929 | 2850.931 | 0 | 18528.8653 | 14116.3034
|  | Communications |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Non System |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Land |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Easements |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Total incl Overhead - As commissioned $ Mar 2017 |  | 965.2078 | 1510.0005 | 1937.3536 | 2771.6989 | 2823.6402 | 2839.2405 | 2830.7929 | 2850.931 | 0 | 18528.8653 | 14116.3034
|  |  | Check | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0
| Expenditure splits for RIN |  |  |  | 2015-16 | 2016-17 | 2017-18 | 2018-19 | 2019-20 | 2020-21 | 2021-22 | 2022-23
| Repex Category | Transmission Towers | bar: 2015-16 to 2022-23
Transmission Tower Support Structures | bar: 2015-16 to 2022-23
Conductors | bar: 2015-16 to 2022-23
Transmission Cables | bar: 2015-16 to 2022-23
Substation Switchbays | bar: 2015-16 to 2022-23
Substation Power Transformers | bar: 2015-16 to 2022-23
Substation Reactive Plant | bar: 2015-16 to 2022-23
Scada Network Control And Protection Systems | bar: 2015-16 to 2022-23
|  | Other |  |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
|  | Total |  |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
| Direct Expenditures | Materials - $ Mar 2017 |  |  | 2015-16 | 2016-17 | 2017-18 | 2018-19 | 2019-20 | 2020-21 | 2021-22 | 2022-23 | Total | 2017-22 Total
| (As Incurred) | Transmission Towers |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Transmission Tower Support Structures |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Conductors |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Transmission Cables |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Substation Switchbays |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Substation Power Transformers |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Substation Reactive Plant |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Scada Network Control And Protection Systems |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Other |  |  | 557.0663 | 717.7363 | 1016.9173 | 1016.9173 | 1016.9173 | 1016.9173 | 1016.9173 | 0 | 6359.3891 | 5084.5865
|  | Total Materials |  |  | 557.0663 | 717.7363 | 1016.9173 | 1016.9173 | 1016.9173 | 1016.9173 | 1016.9173 | 0 | 6359.3891 | 5084.5865
|  | Labour (Internal) - $ Mar 2017 |  |  | 2015-16 | 2016-17 | 2017-18 | 2018-19 | 2019-20 | 2020-21 | 2021-22 | 2022-23 | Total | 2017-22 Total
|  | Transmission Towers |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Transmission Tower Support Structures |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Conductors |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Transmission Cables |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Substation Switchbays |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Substation Power Transformers |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Substation Reactive Plant |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Scada Network Control And Protection Systems |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Other |  |  | 139.2666 | 181.6795 | 259.4828 | 261.5847 | 263.7493 | 266.1098 | 268.5314 | 0 | 1640.4041 | 1319.458
|  | Total Internal Labour |  |  | 139.2666 | 181.6795 | 259.4828 | 261.5847 | 263.7493 | 266.1098 | 268.5314 | 0 | 1640.4041 | 1319.458
|  | Labour (External) - $ Mar 2017 |  |  | 2015-16 | 2016-17 | 2017-18 | 2018-19 | 2019-20 | 2020-21 | 2021-22 | 2022-23 | Total | 2017-22 Total
|  | Transmission Towers |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Transmission Tower Support Structures |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Conductors |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Transmission Cables |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Substation Switchbays |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Substation Power Transformers |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Substation Reactive Plant |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Scada Network Control And Protection Systems |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Other |  |  | 696.3329 | 906.8168 | 1298.1441 | 1311.6773 | 1324.8924 | 1339.3338 | 1354.2673 | 0 | 8231.4647 | 6628.315
|  | Total External Labour |  |  | 696.3329 | 906.8168 | 1298.1441 | 1311.6773 | 1324.8924 | 1339.3338 | 1354.2673 | 0 | 8231.4647 | 6628.315
|  | Total Direct - $ Mar 2017 |  |  | 2015-16 | 2016-17 | 2017-18 | 2018-19 | 2019-20 | 2020-21 | 2021-22 | 2022-23 | Total | 2017-22 Total
|  | Transmission Towers |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Transmission Tower Support Structures |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Conductors |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Transmission Cables |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Substation Switchbays |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Substation Power Transformers |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Substation Reactive Plant |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Scada Network Control And Protection Systems |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Other |  |  | 1392.6658 | 1806.2326 | 2574.5443 | 2590.1792 | 2605.559 | 2622.3609 | 2639.7161 | 0 | 16231.2579 | 13032.3595
|  | Total Direct - $ Mar 2017 |  |  | 1392.6658 | 1806.2326 | 2574.5443 | 2590.1792 | 2605.559 | 2622.3609 | 2639.7161 | 0 | 16231.2579 | 13032.3595

## Proj_32
Go To: | Table of Contents
Master Inputs
|  |  |  | Business case? | 0
| Project name | Structure fall arrests
| Project category 1 | Network |  |  | Shaded cells = Inputs
| Project category 2 | Security and Compliance
| Regulatory classification | Prescribed
| Overhead Category | Repex_OHD |  | $000's | $000's | $000's | $000's | $000's | $000's | $000's | $000's | $000's | Project | 2017-22
|  |  |  | Prior | 2015-16 | 2016-17 | 2017-18 | 2018-19 | 2019-20 | 2020-21 | 2021-22 | 2022-23 | Total | Total | Check
| Project timing | Direct Expenditure (As incurred) - $ 2015/16 |  | 43.0176 | 1105.0453 | 182.138 | 7.7189 | 341.2823 | 529.4755 | 0 | 0 | 0 | 2208.6776 | 878.4767 | ok
| (excluding real cost escalators) | Assumed year commissioned (no BC) | bar: 2015-16 to 2022-23
|  | Direct Expenditure (As Commissioned) - $ 2015/16 |  | 0 | 1148.0629 | 182.138 | 0 | 349.0012 | 529.4755 | 0 | 0 | 0 | 2208.6776 | 878.4767 | ok
| Asset class | Secondary
|  | Switchgear |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
Transformers
Reactive
Lines and towers
Establishment
Communications
Non System
Land
Easements
|  |  | Total | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
| Input costs % | Labour - internal |  | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10%
|  | Labour - external |  | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50%
|  | Materials |  | 40% | 40% | 40% | 40% | 40% | 40% | 40% | 40% | 40%
|  |  | Total | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
Material Escalation
| (By Asset Class) | Secondary |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Switchgear |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Transformers |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Reactive |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Lines and towers |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Establishment |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Communications |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Non System |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Land |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Easements |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Total Material escalation |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Labour Escalation | Internal Labour |  | 0 | 0 | 0.22792 | 0.015951 | 0.98739 | 1.9827 | 0 | 0 | 0 | 3.214 | 2.986
|  | External Labour |  | 0 | 0 | 0.97919 | 0.08197 | 5.4409 | 11.1935 | 0 | 0 | 0 | 17.6955 | 16.7164
|  | Total Labour Escalation |  | 0 | 0 | 1.2071 | 0.097921 | 6.4283 | 13.1762 | 0 | 0 | 0 | 20.9095 | 19.7024
|  | Total Escalation |  | 0 | 0 | 1.2071 | 0.097921 | 6.4283 | 13.1762 | 0 | 0 | 0 | 20.9095 | 19.7024
|  | Escalation factors |  | 0 | 0 | 0.0066275 | 0.012686 | 0.018836 | 0.024885 | 0 | 0 | 0 | 0.009467 | 0.022428
| Direct Expenditure (Escalated) | Total labour - internal |  | 4.3745 | 112.374 | 18.7537 | 0.80117 | 35.7097 | 55.8595 | 0 | 0 | 0 | 227.8726 | 92.3704
| (as incurred) | Total labour - external |  | 21.8727 | 561.8699 | 93.6054 | 4.0081 | 179.0609 | 280.5992 | 0 | 0 | 0 | 1141.0161 | 463.6682
|  | Total materials |  | 17.4981 | 449.4959 | 74.0877 | 3.1398 | 138.8223 | 215.3731 | 0 | 0 | 0 | 898.417 | 357.3353
|  | Total Direct - As Incurred $ Mar 2017 |  | 43.7454 | 1123.7397 | 186.4468 | 7.9491 | 353.5929 | 551.8318 | 0 | 0 | 0 | 2267.3057 | 913.3738 | ok
| Capitalised Overheads | Overhead rate (applied to direct expenditure) |  | 8.008% | 8.425% | 7.259% | 7.658% | 9.013% | 8.969% | 7.948% | 8.001% | 8.318%
|  | Total overhead (as incurred) |  | 3.5032 | 94.6771 | 13.5349 | 0.60873 | 31.8704 | 49.4915 | 0 | 0 | 0 | 193.6858 | 81.9706
|  | Total incl Overhead - As Incurred $ Mar 2017 |  | 47.2486 | 1218.4168 | 199.9816 | 8.5578 | 385.4634 | 601.3233 | 0 | 0 | 0 | 2460.9915 | 995.3445
|  | Total overheads (As incurred) - Cumulative |  | 3.5032 | 98.1803 | 111.7152 | 112.3239 | 144.1944 | 193.6858 | 193.6858 | 193.6858 | 193.6858
|  | Labour & Material Escalation - Cumulative |  | 0 | 0 | 1.2071 | 1.305 | 7.7333 | 20.9095 | 20.9095 | 20.9095 | 20.9095
Expenditure By Asset Class - As Incurred
| Asset class breakdown | Secondary |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| (fully absorbed) | Switchgear |  | 47.2486 | 1218.4168 | 199.9816 | 8.5578 | 385.4634 | 601.3233 | 0 | 0 | 0 | 2460.9915 | 995.3445
| (as incurred) | Transformers |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Reactive |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Lines and towers |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Establishment |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Communications |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Non System |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Land |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Easements |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Total incl Overhead - As Incurred $ Mar 2017 |  | 47.2486 | 1218.4168 | 199.9816 | 8.5578 | 385.4634 | 601.3233 | 0 | 0 | 0 | 2460.9915 | 995.3445
|  |  | Check | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| As Commissioned Capex | Direct Expenditure (As Commissioned) - $ 2015/16 |  | 0 | 1148.0629 | 182.138 | 0 | 349.0012 | 529.4755 | 0 | 0 | 0 | 2208.6776 | 878.4767
|  | Labour & Material Escalation - $ 2015/16 |  | 0 | 0 | 1.2071 | 0 | 6.5262 | 13.1762 | 0 | 0 | 0 | 20.9095 | 19.7024
|  | Total Direct Expenditure - $ 2015/16 |  | 0 | 1148.0629 | 183.3451 | 0 | 355.5274 | 542.6516 | 0 | 0 | 0 | 2229.5871 | 898.1791
|  | Total Direct Expenditure - $ Mar 2017 |  | 0 | 1167.4851 | 186.4468 | 0 | 361.542 | 551.8318 | 0 | 0 | 0 | 2267.3057 | 913.3738
|  | Total overheads (As Commissioned) |  | 0 | 98.1803 | 13.5349 | 0 | 32.4792 | 49.4915 | 0 | 0 | 0 | 193.6858 | 81.9706
|  | Total incl Overhead - As commissioned $ Mar 2017 |  | 0 | 1265.6654 | 199.9816 | 0 | 394.0212 | 601.3233 | 0 | 0 | 0 | 2460.9915 | 995.3445
|  | Total overheads (As Comm) - Cumulative |  | 0 | 98.1803 | 111.7152 | 111.7152 | 144.1944 | 193.6858 | 193.6858 | 193.6858 | 193.6858
|  | Total real cost escalation (As Comm) - Cumulative |  | 0 | 0 | 1.2071 | 1.2071 | 7.7333 | 20.9095 | 20.9095 | 20.9095 | 20.9095
Expenditure By Asset Class - As Commissioned
| Asset class breakdown | Secondary |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| (fully absorbed) | Switchgear |  | 0 | 1265.6654 | 199.9816 | 0 | 394.0212 | 601.3233 | 0 | 0 | 0 | 2460.9915 | 995.3445
| (as commissioned) | Transformers |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Reactive |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Lines and towers |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Establishment |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Communications |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Non System |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Land |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Easements |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Total incl Overhead - As commissioned $ Mar 2017 |  | 0 | 1265.6654 | 199.9816 | 0 | 394.0212 | 601.3233 | 0 | 0 | 0 | 2460.9915 | 995.3445
|  |  | Check | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0
| Expenditure splits for RIN |  |  |  | 2015-16 | 2016-17 | 2017-18 | 2018-19 | 2019-20 | 2020-21 | 2021-22 | 2022-23
| Repex Category | Transmission Towers | bar: 2015-16 to 2022-23
Transmission Tower Support Structures | bar: 2015-16 to 2022-23
Conductors | bar: 2015-16 to 2022-23
Transmission Cables | bar: 2015-16 to 2022-23
Substation Switchbays | bar: 2015-16 to 2022-23
Substation Power Transformers | bar: 2015-16 to 2022-23
Substation Reactive Plant | bar: 2015-16 to 2022-23
Scada Network Control And Protection Systems | bar: 2015-16 to 2022-23
|  | Other |  |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
|  | Total |  |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
| Direct Expenditures | Materials - $ Mar 2017 |  |  | 2015-16 | 2016-17 | 2017-18 | 2018-19 | 2019-20 | 2020-21 | 2021-22 | 2022-23 | Total | 2017-22 Total
| (As Incurred) | Transmission Towers |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Transmission Tower Support Structures |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Conductors |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Transmission Cables |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Substation Switchbays |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Substation Power Transformers |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Substation Reactive Plant |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Scada Network Control And Protection Systems |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Other |  |  | 449.4959 | 74.0877 | 3.1398 | 138.8223 | 215.3731 | 0 | 0 | 0 | 880.9188 | 357.3353
|  | Total Materials |  |  | 449.4959 | 74.0877 | 3.1398 | 138.8223 | 215.3731 | 0 | 0 | 0 | 880.9188 | 357.3353
|  | Labour (Internal) - $ Mar 2017 |  |  | 2015-16 | 2016-17 | 2017-18 | 2018-19 | 2019-20 | 2020-21 | 2021-22 | 2022-23 | Total | 2017-22 Total
|  | Transmission Towers |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Transmission Tower Support Structures |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Conductors |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Transmission Cables |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Substation Switchbays |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Substation Power Transformers |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Substation Reactive Plant |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Scada Network Control And Protection Systems |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Other |  |  | 112.374 | 18.7537 | 0.80117 | 35.7097 | 55.8595 | 0 | 0 | 0 | 223.498 | 92.3704
|  | Total Internal Labour |  |  | 112.374 | 18.7537 | 0.80117 | 35.7097 | 55.8595 | 0 | 0 | 0 | 223.498 | 92.3704
|  | Labour (External) - $ Mar 2017 |  |  | 2015-16 | 2016-17 | 2017-18 | 2018-19 | 2019-20 | 2020-21 | 2021-22 | 2022-23 | Total | 2017-22 Total
|  | Transmission Towers |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Transmission Tower Support Structures |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Conductors |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Transmission Cables |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Substation Switchbays |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Substation Power Transformers |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Substation Reactive Plant |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Scada Network Control And Protection Systems |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Other |  |  | 561.8699 | 93.6054 | 4.0081 | 179.0609 | 280.5992 | 0 | 0 | 0 | 1119.1434 | 463.6682
|  | Total External Labour |  |  | 561.8699 | 93.6054 | 4.0081 | 179.0609 | 280.5992 | 0 | 0 | 0 | 1119.1434 | 463.6682
|  | Total Direct - $ Mar 2017 |  |  | 2015-16 | 2016-17 | 2017-18 | 2018-19 | 2019-20 | 2020-21 | 2021-22 | 2022-23 | Total | 2017-22 Total
|  | Transmission Towers |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Transmission Tower Support Structures |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Conductors |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Transmission Cables |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Substation Switchbays |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Substation Power Transformers |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Substation Reactive Plant |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Scada Network Control And Protection Systems |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Other |  |  | 1123.7397 | 186.4468 | 7.9491 | 353.5929 | 551.8318 | 0 | 0 | 0 | 2223.5603 | 913.3738
|  | Total Direct - $ Mar 2017 |  |  | 1123.7397 | 186.4468 | 7.9491 | 353.5929 | 551.8318 | 0 | 0 | 0 | 2223.5603 | 913.3738

## Proj_33
Go To: | Table of Contents
Master Inputs
|  |  |  | Business case? | 0
| Project name | Earth wires (incl. OPGW)
| Project category 1 | Network |  |  | Shaded cells = Inputs
| Project category 2 | Replacement - Other
| Regulatory classification | Prescribed
| Overhead Category | Repex_OHD |  | $000's | $000's | $000's | $000's | $000's | $000's | $000's | $000's | $000's | Project | 2017-22
|  |  |  | Prior | 2015-16 | 2016-17 | 2017-18 | 2018-19 | 2019-20 | 2020-21 | 2021-22 | 2022-23 | Total | Total | Check
| Project timing | Direct Expenditure (As incurred) - $ 2015/16 |  | 3075.3117 | 4950.8754 | 0 | 3802 | 3802 | 3802 | 3802 | 3802 | 0 | 27036.1871 | 19010 | ok
| (excluding real cost escalators) | Assumed year commissioned (no BC) |  | x | bar: 2015-16 to 2022-23
|  | Direct Expenditure (As Commissioned) - $ 2015/16 |  | 3075.3117 | 4950.8754 | 0 | 3802 | 3802 | 3802 | 3802 | 3802 | 0 | 27036.1871 | 19010 | ok
| Asset class | Secondary
Switchgear
Transformers
Reactive
|  | Lines and towers |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
Establishment
Communications
Non System
Land
Easements
|  |  | Total | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
| Input costs % | Labour - internal |  | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10%
|  | Labour - external |  | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50%
|  | Materials |  | 40% | 40% | 40% | 40% | 40% | 40% | 40% | 40% | 40%
|  |  | Total | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
Material Escalation
| (By Asset Class) | Secondary |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Switchgear |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Transformers |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Reactive |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Lines and towers |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Establishment |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Communications |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Non System |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Land |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Easements |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Total Material escalation |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Labour Escalation | Internal Labour |  | 0 | 0 | 0 | 7.8566 | 10.9999 | 14.2371 | 17.7673 | 21.3888 | 0 | 72.2497 | 72.2497
|  | External Labour |  | 0 | 0 | 0 | 40.3748 | 60.6136 | 80.3769 | 101.9739 | 124.3071 | 0 | 407.6463 | 407.6463
|  | Total Labour Escalation |  | 0 | 0 | 0 | 48.2314 | 71.6135 | 94.614 | 119.7412 | 145.6959 | 0 | 479.896 | 479.896
|  | Total Escalation |  | 0 | 0 | 0 | 48.2314 | 71.6135 | 94.614 | 119.7412 | 145.6959 | 0 | 479.896 | 479.896
|  | Escalation factors |  | 0 | 0 | 0 | 0.012686 | 0.018836 | 0.024885 | 0.031494 | 0.038321 | 0 | 0.01775 | 0.025244
| Direct Expenditure (Escalated) | Total labour - internal |  | 312.7338 | 503.4631 | 0 | 394.6215 | 397.8179 | 401.1099 | 404.6998 | 408.3826 | 0 | 2822.8286 | 2006.6318
| (as incurred) | Total labour - external |  | 1563.6688 | 2517.3154 | 0 | 1974.2176 | 1994.7988 | 2014.8964 | 2036.8588 | 2059.5698 | 0 | 14161.3256 | 10080.3414
|  | Total materials |  | 1250.9351 | 2013.8523 | 0 | 1546.5278 | 1546.5278 | 1546.5278 | 1546.5278 | 1546.5278 | 0 | 10997.4265 | 7732.6391
|  | Total Direct - As Incurred $ Mar 2017 |  | 3127.3377 | 5034.6308 | 0 | 3915.3669 | 3939.1446 | 3962.5341 | 3988.0864 | 4014.4802 | 0 | 27981.5807 | 19819.6123 | ok
| Capitalised Overheads | Overhead rate (applied to direct expenditure) |  | 8.008% | 8.425% | 7.259% | 7.658% | 9.013% | 8.969% | 7.948% | 8.001% | 8.318%
|  | Total overhead (as incurred) |  | 250.4426 | 424.1769 | 0 | 299.8327 | 355.0474 | 355.3829 | 316.9834 | 321.2156 | 0 | 2323.0814 | 1648.4619
|  | Total incl Overhead - As Incurred $ Mar 2017 |  | 3377.7802 | 5458.8077 | 0 | 4215.1997 | 4294.1919 | 4317.917 | 4305.0698 | 4335.6958 | 0 | 30304.6622 | 21468.0742
|  | Total overheads (As incurred) - Cumulative |  | 250.4426 | 674.6195 | 674.6195 | 974.4522 | 1329.4995 | 1684.8824 | 2001.8658 | 2323.0814 | 2323.0814
|  | Labour & Material Escalation - Cumulative |  | 0 | 0 | 0 | 48.2314 | 119.845 | 214.459 | 334.2002 | 479.896 | 479.896
Expenditure By Asset Class - As Incurred
| Asset class breakdown | Secondary |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| (fully absorbed) | Switchgear |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| (as incurred) | Transformers |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Reactive |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Lines and towers |  | 3377.7802 | 5458.8077 | 0 | 4215.1997 | 4294.1919 | 4317.917 | 4305.0698 | 4335.6958 | 0 | 30304.6622 | 21468.0742
|  | Establishment |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Communications |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Non System |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Land |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Easements |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Total incl Overhead - As Incurred $ Mar 2017 |  | 3377.7802 | 5458.8077 | 0 | 4215.1997 | 4294.1919 | 4317.917 | 4305.0698 | 4335.6958 | 0 | 30304.6622 | 21468.0742
|  |  | Check | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| As Commissioned Capex | Direct Expenditure (As Commissioned) - $ 2015/16 |  | 3075.3117 | 4950.8754 | 0 | 3802 | 3802 | 3802 | 3802 | 3802 | 0 | 27036.1871 | 19010
|  | Labour & Material Escalation - $ 2015/16 |  | 0 | 0 | 0 | 48.2314 | 71.6135 | 94.614 | 119.7412 | 145.6959 | 0 | 479.896 | 479.896
|  | Total Direct Expenditure - $ 2015/16 |  | 3075.3117 | 4950.8754 | 0 | 3850.2314 | 3873.6135 | 3896.614 | 3921.7412 | 3947.6959 | 0 | 27516.0831 | 19489.896
|  | Total Direct Expenditure - $ Mar 2017 |  | 3127.3377 | 5034.6308 | 0 | 3915.3669 | 3939.1446 | 3962.5341 | 3988.0864 | 4014.4802 | 0 | 27981.5807 | 19819.6123
|  | Total overheads (As Commissioned) |  | 250.4426 | 424.1769 | 0 | 299.8327 | 355.0474 | 355.3829 | 316.9834 | 321.2156 | 0 | 2323.0814 | 1648.4619
|  | Total incl Overhead - As commissioned $ Mar 2017 |  | 3377.7802 | 5458.8077 | 0 | 4215.1997 | 4294.1919 | 4317.917 | 4305.0698 | 4335.6958 | 0 | 30304.6622 | 21468.0742
|  | Total overheads (As Comm) - Cumulative |  | 250.4426 | 674.6195 | 674.6195 | 974.4522 | 1329.4995 | 1684.8824 | 2001.8658 | 2323.0814 | 2323.0814
|  | Total real cost escalation (As Comm) - Cumulative |  | 0 | 0 | 0 | 48.2314 | 119.845 | 214.459 | 334.2002 | 479.896 | 479.896
Expenditure By Asset Class - As Commissioned
| Asset class breakdown | Secondary |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| (fully absorbed) | Switchgear |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| (as commissioned) | Transformers |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Reactive |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Lines and towers |  | 3377.7802 | 5458.8077 | 0 | 4215.1997 | 4294.1919 | 4317.917 | 4305.0698 | 4335.6958 | 0 | 30304.6622 | 21468.0742
|  | Establishment |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Communications |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Non System |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Land |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Easements |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Total incl Overhead - As commissioned $ Mar 2017 |  | 3377.7802 | 5458.8077 | 0 | 4215.1997 | 4294.1919 | 4317.917 | 4305.0698 | 4335.6958 | 0 | 30304.6622 | 21468.0742
|  |  | Check | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0
| Expenditure splits for RIN |  |  |  | 2015-16 | 2016-17 | 2017-18 | 2018-19 | 2019-20 | 2020-21 | 2021-22 | 2022-23
| Repex Category | Transmission Towers | bar: 2015-16 to 2022-23
Transmission Tower Support Structures | bar: 2015-16 to 2022-23
Conductors | bar: 2015-16 to 2022-23
Transmission Cables | bar: 2015-16 to 2022-23
Substation Switchbays | bar: 2015-16 to 2022-23
Substation Power Transformers | bar: 2015-16 to 2022-23
Substation Reactive Plant | bar: 2015-16 to 2022-23
Scada Network Control And Protection Systems | bar: 2015-16 to 2022-23
|  | Other |  |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
|  | Total |  |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
| Direct Expenditures | Materials - $ Mar 2017 |  |  | 2015-16 | 2016-17 | 2017-18 | 2018-19 | 2019-20 | 2020-21 | 2021-22 | 2022-23 | Total | 2017-22 Total
| (As Incurred) | Transmission Towers |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Transmission Tower Support Structures |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Conductors |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Transmission Cables |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Substation Switchbays |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Substation Power Transformers |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Substation Reactive Plant |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Scada Network Control And Protection Systems |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Other |  |  | 2013.8523 | 0 | 1546.5278 | 1546.5278 | 1546.5278 | 1546.5278 | 1546.5278 | 0 | 9746.4914 | 7732.6391
|  | Total Materials |  |  | 2013.8523 | 0 | 1546.5278 | 1546.5278 | 1546.5278 | 1546.5278 | 1546.5278 | 0 | 9746.4914 | 7732.6391
|  | Labour (Internal) - $ Mar 2017 |  |  | 2015-16 | 2016-17 | 2017-18 | 2018-19 | 2019-20 | 2020-21 | 2021-22 | 2022-23 | Total | 2017-22 Total
|  | Transmission Towers |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Transmission Tower Support Structures |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Conductors |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Transmission Cables |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Substation Switchbays |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Substation Power Transformers |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Substation Reactive Plant |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Scada Network Control And Protection Systems |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Other |  |  | 503.4631 | 0 | 394.6215 | 397.8179 | 401.1099 | 404.6998 | 408.3826 | 0 | 2510.0949 | 2006.6318
|  | Total Internal Labour |  |  | 503.4631 | 0 | 394.6215 | 397.8179 | 401.1099 | 404.6998 | 408.3826 | 0 | 2510.0949 | 2006.6318
|  | Labour (External) - $ Mar 2017 |  |  | 2015-16 | 2016-17 | 2017-18 | 2018-19 | 2019-20 | 2020-21 | 2021-22 | 2022-23 | Total | 2017-22 Total
|  | Transmission Towers |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Transmission Tower Support Structures |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Conductors |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Transmission Cables |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Substation Switchbays |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Substation Power Transformers |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Substation Reactive Plant |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Scada Network Control And Protection Systems |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Other |  |  | 2517.3154 | 0 | 1974.2176 | 1994.7988 | 2014.8964 | 2036.8588 | 2059.5698 | 0 | 12597.6568 | 10080.3414
|  | Total External Labour |  |  | 2517.3154 | 0 | 1974.2176 | 1994.7988 | 2014.8964 | 2036.8588 | 2059.5698 | 0 | 12597.6568 | 10080.3414
|  | Total Direct - $ Mar 2017 |  |  | 2015-16 | 2016-17 | 2017-18 | 2018-19 | 2019-20 | 2020-21 | 2021-22 | 2022-23 | Total | 2017-22 Total
|  | Transmission Towers |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Transmission Tower Support Structures |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Conductors |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Transmission Cables |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Substation Switchbays |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Substation Power Transformers |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Substation Reactive Plant |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Scada Network Control And Protection Systems |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Other |  |  | 5034.6308 | 0 | 3915.3669 | 3939.1446 | 3962.5341 | 3988.0864 | 4014.4802 | 0 | 24854.2431 | 19819.6123
|  | Total Direct - $ Mar 2017 |  |  | 5034.6308 | 0 | 3915.3669 | 3939.1446 | 3962.5341 | 3988.0864 | 4014.4802 | 0 | 24854.2431 | 19819.6123

## Proj_34
Go To: | Table of Contents
Master Inputs
|  |  |  | Business case? | 0
| Project name | Conductor
| Project category 1 | Network |  |  | Shaded cells = Inputs
| Project category 2 | Replacement - Other
| Regulatory classification | Prescribed
| Overhead Category | Repex_OHD |  | $000's | $000's | $000's | $000's | $000's | $000's | $000's | $000's | $000's | Project | 2017-22
|  |  |  | Prior | 2015-16 | 2016-17 | 2017-18 | 2018-19 | 2019-20 | 2020-21 | 2021-22 | 2022-23 | Total | Total | Check
| Project timing | Direct Expenditure (As incurred) - $ 2015/16 |  | 678.5432 | 45.8929 | 409.8104 | 0 | 0 | 0 | 0 | 0 | 0 | 1134.2464 | 0 | ok
| (excluding real cost escalators) | Assumed year commissioned (no BC) |  | x | bar: 2015-16 to 2022-23
|  | Direct Expenditure (As Commissioned) - $ 2015/16 |  | 678.5432 | 45.8929 | 409.8104 | 0 | 0 | 0 | 0 | 0 | 0 | 1134.2464 | 0 | ok
| Asset class | Secondary
Switchgear
Transformers
Reactive
|  | Lines and towers |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
Establishment
Communications
Non System
Land
Easements
|  |  | Total | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
| Input costs % | Labour - internal |  | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10%
|  | Labour - external |  | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50%
|  | Materials |  | 40% | 40% | 40% | 40% | 40% | 40% | 40% | 40% | 40%
|  |  | Total | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
Material Escalation
| (By Asset Class) | Secondary |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Switchgear |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Transformers |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Reactive |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Lines and towers |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Establishment |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Communications |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Non System |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Land |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Easements |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Total Material escalation |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Labour Escalation | Internal Labour |  | 0 | 0 | 0.51283 | 0 | 0 | 0 | 0 | 0 | 0 | 0.51283 | 0
|  | External Labour |  | 0 | 0 | 2.2032 | 0 | 0 | 0 | 0 | 0 | 0 | 2.2032 | 0
|  | Total Labour Escalation |  | 0 | 0 | 2.716 | 0 | 0 | 0 | 0 | 0 | 0 | 2.716 | 0
|  | Total Escalation |  | 0 | 0 | 2.716 | 0 | 0 | 0 | 0 | 0 | 0 | 2.716 | 0
|  | Escalation factors |  | 0 | 0 | 0.0066275 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0023945 | 0
| Direct Expenditure (Escalated) | Total labour - internal |  | 69.0022 | 4.6669 | 42.1958 | 0 | 0 | 0 | 0 | 0 | 0 | 115.865 | 0
| (as incurred) | Total labour - external |  | 345.0111 | 23.3346 | 210.6121 | 0 | 0 | 0 | 0 | 0 | 0 | 578.9579 | 0
|  | Total materials |  | 276.0089 | 18.6677 | 166.6973 | 0 | 0 | 0 | 0 | 0 | 0 | 461.3739 | 0
|  | Total Direct - As Incurred $ Mar 2017 |  | 690.0223 | 46.6693 | 419.5052 | 0 | 0 | 0 | 0 | 0 | 0 | 1156.1968 | 0 | ok
| Capitalised Overheads | Overhead rate (applied to direct expenditure) |  | 8.008% | 8.425% | 7.259% | 7.658% | 9.013% | 8.969% | 7.948% | 8.001% | 8.318%
|  | Total overhead (as incurred) |  | 55.2582 | 3.932 | 30.4534 | 0 | 0 | 0 | 0 | 0 | 0 | 89.6436 | 0
|  | Total incl Overhead - As Incurred $ Mar 2017 |  | 745.2804 | 50.6012 | 449.9587 | 0 | 0 | 0 | 0 | 0 | 0 | 1245.8403 | 0
|  | Total overheads (As incurred) - Cumulative |  | 55.2582 | 59.1901 | 89.6436 | 89.6436 | 89.6436 | 89.6436 | 89.6436 | 89.6436 | 89.6436
|  | Labour & Material Escalation - Cumulative |  | 0 | 0 | 2.716 | 2.716 | 2.716 | 2.716 | 2.716 | 2.716 | 2.716
Expenditure By Asset Class - As Incurred
| Asset class breakdown | Secondary |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| (fully absorbed) | Switchgear |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| (as incurred) | Transformers |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Reactive |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Lines and towers |  | 745.2804 | 50.6012 | 449.9587 | 0 | 0 | 0 | 0 | 0 | 0 | 1245.8403 | 0
|  | Establishment |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Communications |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Non System |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Land |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Easements |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Total incl Overhead - As Incurred $ Mar 2017 |  | 745.2804 | 50.6012 | 449.9587 | 0 | 0 | 0 | 0 | 0 | 0 | 1245.8403 | 0
|  |  | Check | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| As Commissioned Capex | Direct Expenditure (As Commissioned) - $ 2015/16 |  | 678.5432 | 45.8929 | 409.8104 | 0 | 0 | 0 | 0 | 0 | 0 | 1134.2464 | 0
|  | Labour & Material Escalation - $ 2015/16 |  | 0 | 0 | 2.716 | 0 | 0 | 0 | 0 | 0 | 0 | 2.716 | 0
|  | Total Direct Expenditure - $ 2015/16 |  | 678.5432 | 45.8929 | 412.5264 | 0 | 0 | 0 | 0 | 0 | 0 | 1136.9624 | 0
|  | Total Direct Expenditure - $ Mar 2017 |  | 690.0223 | 46.6693 | 419.5052 | 0 | 0 | 0 | 0 | 0 | 0 | 1156.1968 | 0
|  | Total overheads (As Commissioned) |  | 55.2582 | 3.932 | 30.4534 | 0 | 0 | 0 | 0 | 0 | 0 | 89.6436 | 0
|  | Total incl Overhead - As commissioned $ Mar 2017 |  | 745.2804 | 50.6012 | 449.9587 | 0 | 0 | 0 | 0 | 0 | 0 | 1245.8403 | 0
|  | Total overheads (As Comm) - Cumulative |  | 55.2582 | 59.1901 | 89.6436 | 89.6436 | 89.6436 | 89.6436 | 89.6436 | 89.6436 | 89.6436
|  | Total real cost escalation (As Comm) - Cumulative |  | 0 | 0 | 2.716 | 2.716 | 2.716 | 2.716 | 2.716 | 2.716 | 2.716
Expenditure By Asset Class - As Commissioned
| Asset class breakdown | Secondary |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| (fully absorbed) | Switchgear |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| (as commissioned) | Transformers |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Reactive |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Lines and towers |  | 745.2804 | 50.6012 | 449.9587 | 0 | 0 | 0 | 0 | 0 | 0 | 1245.8403 | 0
|  | Establishment |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Communications |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Non System |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Land |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Easements |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Total incl Overhead - As commissioned $ Mar 2017 |  | 745.2804 | 50.6012 | 449.9587 | 0 | 0 | 0 | 0 | 0 | 0 | 1245.8403 | 0
|  |  | Check | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0
| Expenditure splits for RIN |  |  |  | 2015-16 | 2016-17 | 2017-18 | 2018-19 | 2019-20 | 2020-21 | 2021-22 | 2022-23
| Repex Category | Transmission Towers | bar: 2015-16 to 2022-23
Transmission Tower Support Structures | bar: 2015-16 to 2022-23
|  | Conductors |  |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
Transmission Cables | bar: 2015-16 to 2022-23
Substation Switchbays | bar: 2015-16 to 2022-23
Substation Power Transformers | bar: 2015-16 to 2022-23
Substation Reactive Plant | bar: 2015-16 to 2022-23
Scada Network Control And Protection Systems | bar: 2015-16 to 2022-23
Other | bar: 2015-16 to 2022-23
|  | Total |  |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
| Direct Expenditures | Materials - $ Mar 2017 |  |  | 2015-16 | 2016-17 | 2017-18 | 2018-19 | 2019-20 | 2020-21 | 2021-22 | 2022-23 | Total | 2017-22 Total
| (As Incurred) | Transmission Towers |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Transmission Tower Support Structures |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Conductors |  |  | 18.6677 | 166.6973 | 0 | 0 | 0 | 0 | 0 | 0 | 185.365 | 0
|  | Transmission Cables |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Substation Switchbays |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Substation Power Transformers |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Substation Reactive Plant |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Scada Network Control And Protection Systems |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Other |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Total Materials |  |  | 18.6677 | 166.6973 | 0 | 0 | 0 | 0 | 0 | 0 | 185.365 | 0
|  | Labour (Internal) - $ Mar 2017 |  |  | 2015-16 | 2016-17 | 2017-18 | 2018-19 | 2019-20 | 2020-21 | 2021-22 | 2022-23 | Total | 2017-22 Total
|  | Transmission Towers |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Transmission Tower Support Structures |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Conductors |  |  | 4.6669 | 42.1958 | 0 | 0 | 0 | 0 | 0 | 0 | 46.8628 | 0
|  | Transmission Cables |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Substation Switchbays |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Substation Power Transformers |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Substation Reactive Plant |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Scada Network Control And Protection Systems |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Other |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Total Internal Labour |  |  | 4.6669 | 42.1958 | 0 | 0 | 0 | 0 | 0 | 0 | 46.8628 | 0
|  | Labour (External) - $ Mar 2017 |  |  | 2015-16 | 2016-17 | 2017-18 | 2018-19 | 2019-20 | 2020-21 | 2021-22 | 2022-23 | Total | 2017-22 Total
|  | Transmission Towers |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Transmission Tower Support Structures |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Conductors |  |  | 23.3346 | 210.6121 | 0 | 0 | 0 | 0 | 0 | 0 | 233.9467 | 0
|  | Transmission Cables |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Substation Switchbays |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Substation Power Transformers |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Substation Reactive Plant |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Scada Network Control And Protection Systems |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Other |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Total External Labour |  |  | 23.3346 | 210.6121 | 0 | 0 | 0 | 0 | 0 | 0 | 233.9467 | 0
|  | Total Direct - $ Mar 2017 |  |  | 2015-16 | 2016-17 | 2017-18 | 2018-19 | 2019-20 | 2020-21 | 2021-22 | 2022-23 | Total | 2017-22 Total
|  | Transmission Towers |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Transmission Tower Support Structures |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Conductors |  |  | 46.6693 | 419.5052 | 0 | 0 | 0 | 0 | 0 | 0 | 466.1745 | 0
|  | Transmission Cables |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Substation Switchbays |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Substation Power Transformers |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Substation Reactive Plant |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Scada Network Control And Protection Systems |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Other |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Total Direct - $ Mar 2017 |  |  | 46.6693 | 419.5052 | 0 | 0 | 0 | 0 | 0 | 0 | 466.1745 | 0

## Proj_35
Go To: | Table of Contents
Master Inputs
|  |  |  | Business case? | 0
| Project name | Insulators
| Project category 1 | Network |  |  | Shaded cells = Inputs
| Project category 2 | Security and Compliance
| Regulatory classification | Prescribed
| Overhead Category | Repex_OHD |  | $000's | $000's | $000's | $000's | $000's | $000's | $000's | $000's | $000's | Project | 2017-22
|  |  |  | Prior | 2015-16 | 2016-17 | 2017-18 | 2018-19 | 2019-20 | 2020-21 | 2021-22 | 2022-23 | Total | Total | Check
| Project timing | Direct Expenditure (As incurred) - $ 2015/16 |  | 1189.1556 | 5624.7899 | 638.0293 | 1134.162 | 1069.909 | 1069.909 | 1069.909 | 886.865 | 0 | 12682.7288 | 5230.754 | ok
| (excluding real cost escalators) | Assumed year commissioned (no BC) |  | x | bar: 2015-16 to 2022-23
|  | Direct Expenditure (As Commissioned) - $ 2015/16 |  | 1189.1556 | 5624.7899 | 638.0293 | 1134.162 | 1069.909 | 1069.909 | 1069.909 | 886.865 | 0 | 12682.7288 | 5230.754 | ok
| Asset class | Secondary
Switchgear
Transformers
Reactive
|  | Lines and towers |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
Establishment
Communications
Non System
Land
Easements
|  |  | Total | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
| Input costs % | Labour - internal |  | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10%
|  | Labour - external |  | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50%
|  | Materials |  | 40% | 40% | 40% | 40% | 40% | 40% | 40% | 40% | 40%
|  |  | Total | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
Material Escalation
| (By Asset Class) | Secondary |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Switchgear |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Transformers |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Reactive |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Lines and towers |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Establishment |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Communications |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Non System |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Land |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Easements |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Total Material escalation |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Labour Escalation | Internal Labour |  | 0 | 0 | 0.79842 | 2.3437 | 3.0954 | 4.0064 | 4.9998 | 4.9892 | 0 | 20.233 | 19.4346
|  | External Labour |  | 0 | 0 | 3.4301 | 12.0441 | 17.0571 | 22.6186 | 28.6962 | 28.9962 | 0 | 112.8422 | 109.4121
|  | Total Labour Escalation |  | 0 | 0 | 4.2285 | 14.3878 | 20.1525 | 26.625 | 33.696 | 33.9854 | 0 | 133.0753 | 128.8467
|  | Total Escalation |  | 0 | 0 | 4.2285 | 14.3878 | 20.1525 | 26.625 | 33.696 | 33.9854 | 0 | 133.0753 | 128.8467
|  | Escalation factors |  | 0 | 0 | 0.0066275 | 0.012686 | 0.018836 | 0.024885 | 0.031494 | 0.038321 | 0 | 0.010493 | 0.024633
| Direct Expenditure (Escalated) | Total labour - internal |  | 120.9273 | 571.9946 | 65.6942 | 117.7182 | 111.9487 | 112.8751 | 113.8853 | 95.2604 | 0 | 1310.3039 | 551.6878
| (as incurred) | Total labour - external |  | 604.6365 | 2859.9731 | 327.8996 | 588.9223 | 561.3501 | 567.0057 | 573.1861 | 480.4209 | 0 | 6563.3944 | 2770.8852
|  | Total materials |  | 483.7092 | 2287.9785 | 259.5292 | 461.3396 | 435.2036 | 435.2036 | 435.2036 | 360.7473 | 0 | 5158.9145 | 2127.6977
|  | Total Direct - As Incurred $ Mar 2017 |  | 1209.2729 | 5719.9461 | 653.123 | 1167.9801 | 1108.5024 | 1115.0844 | 1122.275 | 936.4287 | 0 | 13032.6128 | 5450.2707 | ok
| Capitalised Overheads | Overhead rate (applied to direct expenditure) |  | 8.008% | 8.425% | 7.259% | 7.658% | 9.013% | 8.969% | 7.948% | 8.001% | 8.318%
|  | Total overhead (as incurred) |  | 96.8407 | 481.916 | 47.4126 | 89.4421 | 99.9128 | 100.0072 | 89.2013 | 74.9276 | 0 | 1079.6603 | 453.491
|  | Total incl Overhead - As Incurred $ Mar 2017 |  | 1306.1136 | 6201.8621 | 700.5356 | 1257.4222 | 1208.4152 | 1215.0916 | 1211.4763 | 1011.3564 | 0 | 14112.273 | 5903.7617
|  | Total overheads (As incurred) - Cumulative |  | 96.8407 | 578.7566 | 626.1692 | 715.6113 | 815.5241 | 915.5313 | 1004.7326 | 1079.6603 | 1079.6603
|  | Labour & Material Escalation - Cumulative |  | 0 | 0 | 4.2285 | 18.6163 | 38.7688 | 65.3938 | 99.0898 | 133.0753 | 133.0753
Expenditure By Asset Class - As Incurred
| Asset class breakdown | Secondary |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| (fully absorbed) | Switchgear |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| (as incurred) | Transformers |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Reactive |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Lines and towers |  | 1306.1136 | 6201.8621 | 700.5356 | 1257.4222 | 1208.4152 | 1215.0916 | 1211.4763 | 1011.3564 | 0 | 14112.273 | 5903.7617
|  | Establishment |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Communications |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Non System |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Land |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Easements |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Total incl Overhead - As Incurred $ Mar 2017 |  | 1306.1136 | 6201.8621 | 700.5356 | 1257.4222 | 1208.4152 | 1215.0916 | 1211.4763 | 1011.3564 | 0 | 14112.273 | 5903.7617
|  |  | Check | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| As Commissioned Capex | Direct Expenditure (As Commissioned) - $ 2015/16 |  | 1189.1556 | 5624.7899 | 638.0293 | 1134.162 | 1069.909 | 1069.909 | 1069.909 | 886.865 | 0 | 12682.7288 | 5230.754
|  | Labour & Material Escalation - $ 2015/16 |  | 0 | 0 | 4.2285 | 14.3878 | 20.1525 | 26.625 | 33.696 | 33.9854 | 0 | 133.0753 | 128.8467
|  | Total Direct Expenditure - $ 2015/16 |  | 1189.1556 | 5624.7899 | 642.2578 | 1148.5498 | 1090.0615 | 1096.534 | 1103.605 | 920.8504 | 0 | 12815.8041 | 5359.6007
|  | Total Direct Expenditure - $ Mar 2017 |  | 1209.2729 | 5719.9461 | 653.123 | 1167.9801 | 1108.5024 | 1115.0844 | 1122.275 | 936.4287 | 0 | 13032.6128 | 5450.2707
|  | Total overheads (As Commissioned) |  | 96.8407 | 481.916 | 47.4126 | 89.4421 | 99.9128 | 100.0072 | 89.2013 | 74.9276 | 0 | 1079.6603 | 453.491
|  | Total incl Overhead - As commissioned $ Mar 2017 |  | 1306.1136 | 6201.8621 | 700.5356 | 1257.4222 | 1208.4152 | 1215.0916 | 1211.4763 | 1011.3564 | 0 | 14112.273 | 5903.7617
|  | Total overheads (As Comm) - Cumulative |  | 96.8407 | 578.7566 | 626.1692 | 715.6113 | 815.5241 | 915.5313 | 1004.7326 | 1079.6603 | 1079.6603
|  | Total real cost escalation (As Comm) - Cumulative |  | 0 | 0 | 4.2285 | 18.6163 | 38.7688 | 65.3938 | 99.0898 | 133.0753 | 133.0753
Expenditure By Asset Class - As Commissioned
| Asset class breakdown | Secondary |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| (fully absorbed) | Switchgear |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| (as commissioned) | Transformers |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Reactive |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Lines and towers |  | 1306.1136 | 6201.8621 | 700.5356 | 1257.4222 | 1208.4152 | 1215.0916 | 1211.4763 | 1011.3564 | 0 | 14112.273 | 5903.7617
|  | Establishment |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Communications |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Non System |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Land |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Easements |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Total incl Overhead - As commissioned $ Mar 2017 |  | 1306.1136 | 6201.8621 | 700.5356 | 1257.4222 | 1208.4152 | 1215.0916 | 1211.4763 | 1011.3564 | 0 | 14112.273 | 5903.7617
|  |  | Check | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0
| Expenditure splits for RIN |  |  |  | 2015-16 | 2016-17 | 2017-18 | 2018-19 | 2019-20 | 2020-21 | 2021-22 | 2022-23
| Repex Category | Transmission Towers | bar: 2015-16 to 2022-23
Transmission Tower Support Structures | bar: 2015-16 to 2022-23
|  | Conductors |  |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
Transmission Cables | bar: 2015-16 to 2022-23
Substation Switchbays | bar: 2015-16 to 2022-23
Substation Power Transformers | bar: 2015-16 to 2022-23
Substation Reactive Plant | bar: 2015-16 to 2022-23
Scada Network Control And Protection Systems | bar: 2015-16 to 2022-23
Other | bar: 2015-16 to 2022-23
|  | Total |  |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
| Direct Expenditures | Materials - $ Mar 2017 |  |  | 2015-16 | 2016-17 | 2017-18 | 2018-19 | 2019-20 | 2020-21 | 2021-22 | 2022-23 | Total | 2017-22 Total
| (As Incurred) | Transmission Towers |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Transmission Tower Support Structures |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Conductors |  |  | 2287.9785 | 259.5292 | 461.3396 | 435.2036 | 435.2036 | 435.2036 | 360.7473 | 0 | 4675.2053 | 2127.6977
|  | Transmission Cables |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Substation Switchbays |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Substation Power Transformers |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Substation Reactive Plant |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Scada Network Control And Protection Systems |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Other |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Total Materials |  |  | 2287.9785 | 259.5292 | 461.3396 | 435.2036 | 435.2036 | 435.2036 | 360.7473 | 0 | 4675.2053 | 2127.6977
|  | Labour (Internal) - $ Mar 2017 |  |  | 2015-16 | 2016-17 | 2017-18 | 2018-19 | 2019-20 | 2020-21 | 2021-22 | 2022-23 | Total | 2017-22 Total
|  | Transmission Towers |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Transmission Tower Support Structures |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Conductors |  |  | 571.9946 | 65.6942 | 117.7182 | 111.9487 | 112.8751 | 113.8853 | 95.2604 | 0 | 1189.3766 | 551.6878
|  | Transmission Cables |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Substation Switchbays |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Substation Power Transformers |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Substation Reactive Plant |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Scada Network Control And Protection Systems |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Other |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Total Internal Labour |  |  | 571.9946 | 65.6942 | 117.7182 | 111.9487 | 112.8751 | 113.8853 | 95.2604 | 0 | 1189.3766 | 551.6878
|  | Labour (External) - $ Mar 2017 |  |  | 2015-16 | 2016-17 | 2017-18 | 2018-19 | 2019-20 | 2020-21 | 2021-22 | 2022-23 | Total | 2017-22 Total
|  | Transmission Towers |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Transmission Tower Support Structures |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Conductors |  |  | 2859.9731 | 327.8996 | 588.9223 | 561.3501 | 567.0057 | 573.1861 | 480.4209 | 0 | 5958.7579 | 2770.8852
|  | Transmission Cables |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Substation Switchbays |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Substation Power Transformers |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Substation Reactive Plant |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Scada Network Control And Protection Systems |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Other |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Total External Labour |  |  | 2859.9731 | 327.8996 | 588.9223 | 561.3501 | 567.0057 | 573.1861 | 480.4209 | 0 | 5958.7579 | 2770.8852
|  | Total Direct - $ Mar 2017 |  |  | 2015-16 | 2016-17 | 2017-18 | 2018-19 | 2019-20 | 2020-21 | 2021-22 | 2022-23 | Total | 2017-22 Total
|  | Transmission Towers |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Transmission Tower Support Structures |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Conductors |  |  | 5719.9461 | 653.123 | 1167.9801 | 1108.5024 | 1115.0844 | 1122.275 | 936.4287 | 0 | 11823.3399 | 5450.2707
|  | Transmission Cables |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Substation Switchbays |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Substation Power Transformers |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Substation Reactive Plant |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Scada Network Control And Protection Systems |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Other |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Total Direct - $ Mar 2017 |  |  | 5719.9461 | 653.123 | 1167.9801 | 1108.5024 | 1115.0844 | 1122.275 | 936.4287 | 0 | 11823.3399 | 5450.2707

## Proj_36
Go To: | Table of Contents
Master Inputs
|  |  |  | Business case? | 0
| Project name | Towers
| Project category 1 | Network |  |  | Shaded cells = Inputs
| Project category 2 | Replacement - Other
| Regulatory classification | Prescribed
| Overhead Category | Repex_OHD |  | $000's | $000's | $000's | $000's | $000's | $000's | $000's | $000's | $000's | Project | 2017-22
|  |  |  | Prior | 2015-16 | 2016-17 | 2017-18 | 2018-19 | 2019-20 | 2020-21 | 2021-22 | 2022-23 | Total | Total | Check
| Project timing | Direct Expenditure (As incurred) - $ 2015/16 |  | 59.9269 | 1948.1516 | 0 | 23.35 | 3518.887 | 0 | 0 | 0 | 0 | 5550.3156 | 3542.237 | ok
| (excluding real cost escalators) | Assumed year commissioned (no BC) |  | x | bar: 2015-16 to 2022-23
|  | Direct Expenditure (As Commissioned) - $ 2015/16 |  | 59.9269 | 0 | 0 | 0 | 5490.3886 | 0 | 0 | 0 | 0 | 5550.3156 | 5490.3886 | ok
| Asset class | Secondary
Switchgear
Transformers
Reactive
|  | Lines and towers |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
Establishment
Communications
Non System
Land
Easements
|  |  | Total | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
| Input costs % | Labour - internal |  | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10%
|  | Labour - external |  | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50%
|  | Materials |  | 40% | 40% | 40% | 40% | 40% | 40% | 40% | 40% | 40%
|  |  | Total | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
Material Escalation
| (By Asset Class) | Secondary |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Switchgear |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Transformers |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Reactive |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Lines and towers |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Establishment |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Communications |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Non System |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Land |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Easements |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Total Material escalation |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Labour Escalation | Internal Labour |  | 0 | 0 | 0 | 0.048252 | 10.1808 | 0 | 0 | 0 | 0 | 10.2291 | 10.2291
|  | External Labour |  | 0 | 0 | 0 | 0.24796 | 56.1001 | 0 | 0 | 0 | 0 | 56.348 | 56.348
|  | Total Labour Escalation |  | 0 | 0 | 0 | 0.29621 | 66.2809 | 0 | 0 | 0 | 0 | 66.5771 | 66.5771
|  | Total Escalation |  | 0 | 0 | 0 | 0.29621 | 66.2809 | 0 | 0 | 0 | 0 | 66.5771 | 66.5771
|  | Escalation factors |  | 0 | 0 | 0 | 0.012686 | 0.018836 | 0 | 0 | 0 | 0 | 0.011995 | 0.018795
| Direct Expenditure (Escalated) | Total labour - internal |  | 6.0941 | 198.1109 | 0 | 2.4236 | 368.1947 | 0 | 0 | 0 | 0 | 574.8233 | 370.6183
| (as incurred) | Total labour - external |  | 30.4704 | 990.5545 | 0 | 12.1247 | 1846.2577 | 0 | 0 | 0 | 0 | 2879.4072 | 1858.3823
|  | Total materials |  | 24.3763 | 792.4436 | 0 | 9.498 | 1431.3668 | 0 | 0 | 0 | 0 | 2257.6847 | 1440.8648
|  | Total Direct - As Incurred $ Mar 2017 |  | 60.9407 | 1981.1091 | 0 | 24.0462 | 3645.8192 | 0 | 0 | 0 | 0 | 5711.9153 | 3669.8655 | ok
| Capitalised Overheads | Overhead rate (applied to direct expenditure) |  | 8.008% | 8.425% | 7.259% | 7.658% | 9.013% | 8.969% | 7.948% | 8.001% | 8.318%
|  | Total overhead (as incurred) |  | 4.8802 | 166.9121 | 0 | 1.8414 | 328.609 | 0 | 0 | 0 | 0 | 502.2428 | 330.4505
|  | Total incl Overhead - As Incurred $ Mar 2017 |  | 65.821 | 2148.0212 | 0 | 25.8877 | 3974.4283 | 0 | 0 | 0 | 0 | 6214.1581 | 4000.3159
|  | Total overheads (As incurred) - Cumulative |  | 4.8802 | 171.7923 | 171.7923 | 173.6337 | 502.2428 | 502.2428 | 502.2428 | 502.2428 | 502.2428
|  | Labour & Material Escalation - Cumulative |  | 0 | 0 | 0 | 0.29621 | 66.5771 | 66.5771 | 66.5771 | 66.5771 | 66.5771
Expenditure By Asset Class - As Incurred
| Asset class breakdown | Secondary |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| (fully absorbed) | Switchgear |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| (as incurred) | Transformers |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Reactive |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Lines and towers |  | 65.821 | 2148.0212 | 0 | 25.8877 | 3974.4283 | 0 | 0 | 0 | 0 | 6214.1581 | 4000.3159
|  | Establishment |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Communications |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Non System |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Land |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Easements |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Total incl Overhead - As Incurred $ Mar 2017 |  | 65.821 | 2148.0212 | 0 | 25.8877 | 3974.4283 | 0 | 0 | 0 | 0 | 6214.1581 | 4000.3159
|  |  | Check | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| As Commissioned Capex | Direct Expenditure (As Commissioned) - $ 2015/16 |  | 59.9269 | 0 | 0 | 0 | 5490.3886 | 0 | 0 | 0 | 0 | 5550.3156 | 5490.3886
|  | Labour & Material Escalation - $ 2015/16 |  | 0 | 0 | 0 | 0 | 66.5771 | 0 | 0 | 0 | 0 | 66.5771 | 66.5771
|  | Total Direct Expenditure - $ 2015/16 |  | 59.9269 | 0 | 0 | 0 | 5556.9657 | 0 | 0 | 0 | 0 | 5616.8927 | 5556.9657
|  | Total Direct Expenditure - $ Mar 2017 |  | 60.9407 | 0 | 0 | 0 | 5650.9746 | 0 | 0 | 0 | 0 | 5711.9153 | 5650.9746
|  | Total overheads (As Commissioned) |  | 4.8802 | 0 | 0 | 0 | 497.3625 | 0 | 0 | 0 | 0 | 502.2428 | 497.3625
|  | Total incl Overhead - As commissioned $ Mar 2017 |  | 65.821 | 0 | 0 | 0 | 6148.3371 | 0 | 0 | 0 | 0 | 6214.1581 | 6148.3371
|  | Total overheads (As Comm) - Cumulative |  | 4.8802 | 4.8802 | 4.8802 | 4.8802 | 502.2428 | 502.2428 | 502.2428 | 502.2428 | 502.2428
|  | Total real cost escalation (As Comm) - Cumulative |  | 0 | 0 | 0 | 0 | 66.5771 | 66.5771 | 66.5771 | 66.5771 | 66.5771
Expenditure By Asset Class - As Commissioned
| Asset class breakdown | Secondary |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| (fully absorbed) | Switchgear |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| (as commissioned) | Transformers |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Reactive |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Lines and towers |  | 65.821 | 0 | 0 | 0 | 6148.3371 | 0 | 0 | 0 | 0 | 6214.1581 | 6148.3371
|  | Establishment |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Communications |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Non System |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Land |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Easements |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Total incl Overhead - As commissioned $ Mar 2017 |  | 65.821 | 0 | 0 | 0 | 6148.3371 | 0 | 0 | 0 | 0 | 6214.1581 | 6148.3371
|  |  | Check | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0
| Expenditure splits for RIN |  |  |  | 2015-16 | 2016-17 | 2017-18 | 2018-19 | 2019-20 | 2020-21 | 2021-22 | 2022-23
| Repex Category | Transmission Towers |  |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
Transmission Tower Support Structures | bar: 2015-16 to 2022-23
Conductors | bar: 2015-16 to 2022-23
Transmission Cables | bar: 2015-16 to 2022-23
Substation Switchbays | bar: 2015-16 to 2022-23
Substation Power Transformers | bar: 2015-16 to 2022-23
Substation Reactive Plant | bar: 2015-16 to 2022-23
Scada Network Control And Protection Systems | bar: 2015-16 to 2022-23
Other | bar: 2015-16 to 2022-23
|  | Total |  |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
| Direct Expenditures | Materials - $ Mar 2017 |  |  | 2015-16 | 2016-17 | 2017-18 | 2018-19 | 2019-20 | 2020-21 | 2021-22 | 2022-23 | Total | 2017-22 Total
| (As Incurred) | Transmission Towers |  |  | 792.4436 | 0 | 9.498 | 1431.3668 | 0 | 0 | 0 | 0 | 2233.3085 | 1440.8648
|  | Transmission Tower Support Structures |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Conductors |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Transmission Cables |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Substation Switchbays |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Substation Power Transformers |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Substation Reactive Plant |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Scada Network Control And Protection Systems |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Other |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Total Materials |  |  | 792.4436 | 0 | 9.498 | 1431.3668 | 0 | 0 | 0 | 0 | 2233.3085 | 1440.8648
|  | Labour (Internal) - $ Mar 2017 |  |  | 2015-16 | 2016-17 | 2017-18 | 2018-19 | 2019-20 | 2020-21 | 2021-22 | 2022-23 | Total | 2017-22 Total
|  | Transmission Towers |  |  | 198.1109 | 0 | 2.4236 | 368.1947 | 0 | 0 | 0 | 0 | 568.7292 | 370.6183
|  | Transmission Tower Support Structures |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Conductors |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Transmission Cables |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Substation Switchbays |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Substation Power Transformers |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Substation Reactive Plant |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Scada Network Control And Protection Systems |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Other |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Total Internal Labour |  |  | 198.1109 | 0 | 2.4236 | 368.1947 | 0 | 0 | 0 | 0 | 568.7292 | 370.6183
|  | Labour (External) - $ Mar 2017 |  |  | 2015-16 | 2016-17 | 2017-18 | 2018-19 | 2019-20 | 2020-21 | 2021-22 | 2022-23 | Total | 2017-22 Total
|  | Transmission Towers |  |  | 990.5545 | 0 | 12.1247 | 1846.2577 | 0 | 0 | 0 | 0 | 2848.9369 | 1858.3823
|  | Transmission Tower Support Structures |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Conductors |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Transmission Cables |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Substation Switchbays |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Substation Power Transformers |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Substation Reactive Plant |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Scada Network Control And Protection Systems |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Other |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Total External Labour |  |  | 990.5545 | 0 | 12.1247 | 1846.2577 | 0 | 0 | 0 | 0 | 2848.9369 | 1858.3823
|  | Total Direct - $ Mar 2017 |  |  | 2015-16 | 2016-17 | 2017-18 | 2018-19 | 2019-20 | 2020-21 | 2021-22 | 2022-23 | Total | 2017-22 Total
|  | Transmission Towers |  |  | 1981.1091 | 0 | 24.0462 | 3645.8192 | 0 | 0 | 0 | 0 | 5650.9746 | 3669.8655
|  | Transmission Tower Support Structures |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Conductors |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Transmission Cables |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Substation Switchbays |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Substation Power Transformers |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Substation Reactive Plant |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Scada Network Control And Protection Systems |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Other |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Total Direct - $ Mar 2017 |  |  | 1981.1091 | 0 | 24.0462 | 3645.8192 | 0 | 0 | 0 | 0 | 5650.9746 | 3669.8655

## Proj_37
Go To: | Table of Contents
Master Inputs
|  |  |  | Business case? | 0
| Project name | Tower fall arrests
| Project category 1 | Network |  |  | Shaded cells = Inputs
| Project category 2 | Security and Compliance
| Regulatory classification | Prescribed
| Overhead Category | Repex_OHD |  | $000's | $000's | $000's | $000's | $000's | $000's | $000's | $000's | $000's | Project | 2017-22
|  |  |  | Prior | 2015-16 | 2016-17 | 2017-18 | 2018-19 | 2019-20 | 2020-21 | 2021-22 | 2022-23 | Total | Total | Check
| Project timing | Direct Expenditure (As incurred) - $ 2015/16 |  | 2358.21 | 6866.3098 | 5102.5949 | 4314 | 4314 | 4314 | 4314 | 4314 | 0 | 35897.1147 | 21570 | ok
| (excluding real cost escalators) | Assumed year commissioned (no BC) |  | x | bar: 2015-16 to 2022-23
|  | Direct Expenditure (As Commissioned) - $ 2015/16 |  | 2358.21 | 6866.3098 | 5102.5949 | 4314 | 4314 | 4314 | 4314 | 4314 | 0 | 35897.1147 | 21570 | ok
| Asset class | Secondary
Switchgear
Transformers
Reactive
|  | Lines and towers |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
Establishment
Communications
Non System
Land
Easements
|  |  | Total | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
| Input costs % | Labour - internal |  | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10%
|  | Labour - external |  | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50%
|  | Materials |  | 40% | 40% | 40% | 40% | 40% | 40% | 40% | 40% | 40%
|  |  | Total | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
Material Escalation
| (By Asset Class) | Secondary |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Switchgear |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Transformers |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Reactive |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Lines and towers |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Establishment |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Communications |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Non System |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Land |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Easements |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Total Material escalation |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Labour Escalation | Internal Labour |  | 0 | 0 | 6.3853 | 8.9147 | 12.4812 | 16.1543 | 20.1599 | 24.2691 | 0 | 88.3646 | 81.9793
|  | External Labour |  | 0 | 0 | 27.432 | 45.8119 | 68.7762 | 91.2009 | 115.7063 | 141.047 | 0 | 489.9743 | 462.5424
|  | Total Labour Escalation |  | 0 | 0 | 33.8172 | 54.7266 | 81.2574 | 107.3553 | 135.8663 | 165.3161 | 0 | 578.3389 | 544.5217
|  | Total Escalation |  | 0 | 0 | 33.8172 | 54.7266 | 81.2574 | 107.3553 | 135.8663 | 165.3161 | 0 | 578.3389 | 544.5217
|  | Escalation factors |  | 0 | 0 | 0.0066275 | 0.012686 | 0.018836 | 0.024885 | 0.031494 | 0.038321 | 0 | 0.016111 | 0.025244
| Direct Expenditure (Escalated) | Total labour - internal |  | 239.8105 | 698.2469 | 525.385 | 447.7636 | 451.3905 | 455.1257 | 459.1991 | 463.3778 | 0 | 3740.2991 | 2276.8568
| (as incurred) | Total labour - external |  | 1199.0523 | 3491.2346 | 2622.3545 | 2240.0775 | 2263.4303 | 2286.2344 | 2311.1543 | 2336.9237 | 0 | 18750.4617 | 11437.8203
|  | Total materials |  | 959.2418 | 2792.9877 | 2075.5668 | 1754.7925 | 1754.7925 | 1754.7925 | 1754.7925 | 1754.7925 | 0 | 14601.7587 | 8773.9624
|  | Total Direct - As Incurred $ Mar 2017 |  | 2398.1046 | 6982.4692 | 5223.3063 | 4442.6336 | 4469.6133 | 4496.1526 | 4525.146 | 4555.094 | 0 | 37092.5196 | 22488.6395 | ok
| Capitalised Overheads | Overhead rate (applied to direct expenditure) |  | 8.008% | 8.425% | 7.259% | 7.658% | 9.013% | 8.969% | 7.948% | 8.001% | 8.318%
|  | Total overhead (as incurred) |  | 192.0443 | 588.2859 | 379.1791 | 340.21 | 402.8601 | 403.2409 | 359.6703 | 364.4724 | 0 | 3029.9629 | 1870.4537
|  | Total incl Overhead - As Incurred $ Mar 2017 |  | 2590.1489 | 7570.7551 | 5602.4853 | 4782.8436 | 4872.4735 | 4899.3935 | 4884.8162 | 4919.5665 | 0 | 40122.4825 | 24359.0932
|  | Total overheads (As incurred) - Cumulative |  | 192.0443 | 780.3302 | 1159.5093 | 1499.7192 | 1902.5794 | 2305.8202 | 2665.4905 | 3029.9629 | 3029.9629
|  | Labour & Material Escalation - Cumulative |  | 0 | 0 | 33.8172 | 88.5438 | 169.8013 | 277.1565 | 413.0228 | 578.3389 | 578.3389
Expenditure By Asset Class - As Incurred
| Asset class breakdown | Secondary |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| (fully absorbed) | Switchgear |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| (as incurred) | Transformers |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Reactive |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Lines and towers |  | 2590.1489 | 7570.7551 | 5602.4853 | 4782.8436 | 4872.4735 | 4899.3935 | 4884.8162 | 4919.5665 | 0 | 40122.4825 | 24359.0932
|  | Establishment |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Communications |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Non System |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Land |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Easements |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Total incl Overhead - As Incurred $ Mar 2017 |  | 2590.1489 | 7570.7551 | 5602.4853 | 4782.8436 | 4872.4735 | 4899.3935 | 4884.8162 | 4919.5665 | 0 | 40122.4825 | 24359.0932
|  |  | Check | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| As Commissioned Capex | Direct Expenditure (As Commissioned) - $ 2015/16 |  | 2358.21 | 6866.3098 | 5102.5949 | 4314 | 4314 | 4314 | 4314 | 4314 | 0 | 35897.1147 | 21570
|  | Labour & Material Escalation - $ 2015/16 |  | 0 | 0 | 33.8172 | 54.7266 | 81.2574 | 107.3553 | 135.8663 | 165.3161 | 0 | 578.3389 | 544.5217
|  | Total Direct Expenditure - $ 2015/16 |  | 2358.21 | 6866.3098 | 5136.4121 | 4368.7266 | 4395.2574 | 4421.3553 | 4449.8663 | 4479.3161 | 0 | 36475.4536 | 22114.5217
|  | Total Direct Expenditure - $ Mar 2017 |  | 2398.1046 | 6982.4692 | 5223.3063 | 4442.6336 | 4469.6133 | 4496.1526 | 4525.146 | 4555.094 | 0 | 37092.5196 | 22488.6395
|  | Total overheads (As Commissioned) |  | 192.0443 | 588.2859 | 379.1791 | 340.21 | 402.8601 | 403.2409 | 359.6703 | 364.4724 | 0 | 3029.9629 | 1870.4537
|  | Total incl Overhead - As commissioned $ Mar 2017 |  | 2590.1489 | 7570.7551 | 5602.4853 | 4782.8436 | 4872.4735 | 4899.3935 | 4884.8162 | 4919.5665 | 0 | 40122.4825 | 24359.0932
|  | Total overheads (As Comm) - Cumulative |  | 192.0443 | 780.3302 | 1159.5093 | 1499.7192 | 1902.5794 | 2305.8202 | 2665.4905 | 3029.9629 | 3029.9629
|  | Total real cost escalation (As Comm) - Cumulative |  | 0 | 0 | 33.8172 | 88.5438 | 169.8013 | 277.1565 | 413.0228 | 578.3389 | 578.3389
Expenditure By Asset Class - As Commissioned
| Asset class breakdown | Secondary |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| (fully absorbed) | Switchgear |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| (as commissioned) | Transformers |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Reactive |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Lines and towers |  | 2590.1489 | 7570.7551 | 5602.4853 | 4782.8436 | 4872.4735 | 4899.3935 | 4884.8162 | 4919.5665 | 0 | 40122.4825 | 24359.0932
|  | Establishment |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Communications |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Non System |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Land |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Easements |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Total incl Overhead - As commissioned $ Mar 2017 |  | 2590.1489 | 7570.7551 | 5602.4853 | 4782.8436 | 4872.4735 | 4899.3935 | 4884.8162 | 4919.5665 | 0 | 40122.4825 | 24359.0932
|  |  | Check | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0
| Expenditure splits for RIN |  |  |  | 2015-16 | 2016-17 | 2017-18 | 2018-19 | 2019-20 | 2020-21 | 2021-22 | 2022-23
| Repex Category | Transmission Towers | bar: 2015-16 to 2022-23
Transmission Tower Support Structures | bar: 2015-16 to 2022-23
Conductors | bar: 2015-16 to 2022-23
Transmission Cables | bar: 2015-16 to 2022-23
Substation Switchbays | bar: 2015-16 to 2022-23
Substation Power Transformers | bar: 2015-16 to 2022-23
Substation Reactive Plant | bar: 2015-16 to 2022-23
Scada Network Control And Protection Systems | bar: 2015-16 to 2022-23
|  | Other |  |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
|  | Total |  |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
| Direct Expenditures | Materials - $ Mar 2017 |  |  | 2015-16 | 2016-17 | 2017-18 | 2018-19 | 2019-20 | 2020-21 | 2021-22 | 2022-23 | Total | 2017-22 Total
| (As Incurred) | Transmission Towers |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Transmission Tower Support Structures |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Conductors |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Transmission Cables |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Substation Switchbays |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Substation Power Transformers |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Substation Reactive Plant |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Scada Network Control And Protection Systems |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Other |  |  | 2792.9877 | 2075.5668 | 1754.7925 | 1754.7925 | 1754.7925 | 1754.7925 | 1754.7925 | 0 | 13642.5169 | 8773.9624
|  | Total Materials |  |  | 2792.9877 | 2075.5668 | 1754.7925 | 1754.7925 | 1754.7925 | 1754.7925 | 1754.7925 | 0 | 13642.5169 | 8773.9624
|  | Labour (Internal) - $ Mar 2017 |  |  | 2015-16 | 2016-17 | 2017-18 | 2018-19 | 2019-20 | 2020-21 | 2021-22 | 2022-23 | Total | 2017-22 Total
|  | Transmission Towers |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Transmission Tower Support Structures |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Conductors |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Transmission Cables |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Substation Switchbays |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Substation Power Transformers |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Substation Reactive Plant |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Scada Network Control And Protection Systems |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Other |  |  | 698.2469 | 525.385 | 447.7636 | 451.3905 | 455.1257 | 459.1991 | 463.3778 | 0 | 3500.4887 | 2276.8568
|  | Total Internal Labour |  |  | 698.2469 | 525.385 | 447.7636 | 451.3905 | 455.1257 | 459.1991 | 463.3778 | 0 | 3500.4887 | 2276.8568
|  | Labour (External) - $ Mar 2017 |  |  | 2015-16 | 2016-17 | 2017-18 | 2018-19 | 2019-20 | 2020-21 | 2021-22 | 2022-23 | Total | 2017-22 Total
|  | Transmission Towers |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Transmission Tower Support Structures |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Conductors |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Transmission Cables |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Substation Switchbays |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Substation Power Transformers |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Substation Reactive Plant |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Scada Network Control And Protection Systems |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Other |  |  | 3491.2346 | 2622.3545 | 2240.0775 | 2263.4303 | 2286.2344 | 2311.1543 | 2336.9237 | 0 | 17551.4094 | 11437.8203
|  | Total External Labour |  |  | 3491.2346 | 2622.3545 | 2240.0775 | 2263.4303 | 2286.2344 | 2311.1543 | 2336.9237 | 0 | 17551.4094 | 11437.8203
|  | Total Direct - $ Mar 2017 |  |  | 2015-16 | 2016-17 | 2017-18 | 2018-19 | 2019-20 | 2020-21 | 2021-22 | 2022-23 | Total | 2017-22 Total
|  | Transmission Towers |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Transmission Tower Support Structures |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Conductors |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Transmission Cables |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Substation Switchbays |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Substation Power Transformers |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Substation Reactive Plant |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Scada Network Control And Protection Systems |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Other |  |  | 6982.4692 | 5223.3063 | 4442.6336 | 4469.6133 | 4496.1526 | 4525.146 | 4555.094 | 0 | 34694.415 | 22488.6395
|  | Total Direct - $ Mar 2017 |  |  | 6982.4692 | 5223.3063 | 4442.6336 | 4469.6133 | 4496.1526 | 4525.146 | 4555.094 | 0 | 34694.415 | 22488.6395

## Proj_38
Go To: | Table of Contents
Master Inputs
|  |  |  | Business case? | 0
| Project name | Secondary & Protection program
| Project category 1 | Network |  |  | Shaded cells = Inputs
| Project category 2 | Replacement - Other
| Regulatory classification | Prescribed
| Overhead Category | Repex_OHD |  | $000's | $000's | $000's | $000's | $000's | $000's | $000's | $000's | $000's | Project | 2017-22
|  |  |  | Prior | 2015-16 | 2016-17 | 2017-18 | 2018-19 | 2019-20 | 2020-21 | 2021-22 | 2022-23 | Total | Total | Check
| Project timing | Direct Expenditure (As incurred) - $ 2015/16 |  | 14085.5614 | 18538.5375 | 12766.8144 | 20805 | 17688 | 15005 | 14280 | 15117 | 0 | 128285.9132 | 82895 | ok
| (excluding real cost escalators) | Assumed year commissioned (no BC) |  | x | bar: 2015-16 to 2022-23
|  | Direct Expenditure (As Commissioned) - $ 2015/16 |  | 14085.5614 | 18538.5375 | 12766.8144 | 20805 | 17688 | 15005 | 14280 | 15117 | 0 | 128285.9132 | 82895 | ok
| Asset class | Secondary |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
Switchgear
Transformers
Reactive
Lines and towers
Establishment
Communications
Non System
Land
Easements
|  |  | Total | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
| Input costs % | Labour - internal |  | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10%
|  | Labour - external |  | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50%
|  | Materials |  | 40% | 40% | 40% | 40% | 40% | 40% | 40% | 40% | 40%
|  |  | Total | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
Material Escalation
| (By Asset Class) | Secondary |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Switchgear |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Transformers |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Reactive |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Lines and towers |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Establishment |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Communications |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Non System |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Land |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Easements |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Total Material escalation |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Labour Escalation | Internal Labour |  | 0 | 0 | 15.9761 | 42.9925 | 51.1747 | 56.1882 | 66.7325 | 85.0433 | 0 | 318.1073 | 302.1312
|  | External Labour |  | 0 | 0 | 68.6354 | 220.9357 | 281.9921 | 317.216 | 383.0056 | 494.253 | 0 | 1766.0378 | 1697.4024
|  | Total Labour Escalation |  | 0 | 0 | 84.6115 | 263.9283 | 333.1668 | 373.4042 | 449.7381 | 579.2962 | 0 | 2084.1451 | 1999.5336
|  | Total Escalation |  | 0 | 0 | 84.6115 | 263.9283 | 333.1668 | 373.4042 | 449.7381 | 579.2962 | 0 | 2084.1451 | 1999.5336
|  | Escalation factors |  | 0 | 0 | 0.0066275 | 0.012686 | 0.018836 | 0.024885 | 0.031494 | 0.038321 | 0 | 0.016246 | 0.024121
| Direct Expenditure (Escalated) | Total labour - internal |  | 1432.3851 | 1885.2159 | 1314.5258 | 2159.4163 | 1850.7638 | 1583.0231 | 1520.0193 | 1623.7558 | 0 | 13369.1052 | 8736.9783
| (as incurred) | Total labour - external |  | 7161.9255 | 9426.0797 | 6561.1937 | 10803.1555 | 9280.3792 | 7952.0044 | 7650.2745 | 8188.9837 | 0 | 67023.9962 | 43874.7973
|  | Total materials |  | 5729.5404 | 7540.8637 | 5193.1177 | 8462.7857 | 7194.8932 | 6103.5376 | 5808.6316 | 6149.0955 | 0 | 52182.4654 | 33718.9436
|  | Total Direct - As Incurred $ Mar 2017 |  | 14323.8509 | 18852.1593 | 13068.8372 | 21425.3575 | 18326.0362 | 15638.5652 | 14978.9254 | 15961.8351 | 0 | 132575.5668 | 86330.7193 | ok
| Capitalised Overheads | Overhead rate (applied to direct expenditure) |  | 8.008% | 8.425% | 7.259% | 7.658% | 9.013% | 8.969% | 7.948% | 8.001% | 8.318%
|  | Total overhead (as incurred) |  | 1147.0786 | 1588.3291 | 948.7151 | 1640.7205 | 1651.7826 | 1402.5566 | 1190.5636 | 1277.1742 | 0 | 10846.9203 | 7162.7976
|  | Total incl Overhead - As Incurred $ Mar 2017 |  | 15470.9295 | 20440.4884 | 14017.5523 | 23066.078 | 19977.8188 | 17041.1217 | 16169.489 | 17239.0093 | 0 | 143422.4871 | 93493.5169
|  | Total overheads (As incurred) - Cumulative |  | 1147.0786 | 2735.4077 | 3684.1228 | 5324.8433 | 6976.626 | 8379.1825 | 9569.7461 | 10846.9203 | 10846.9203
|  | Labour & Material Escalation - Cumulative |  | 0 | 0 | 84.6115 | 348.5398 | 681.7066 | 1055.1108 | 1504.8489 | 2084.1451 | 2084.1451
Expenditure By Asset Class - As Incurred
| Asset class breakdown | Secondary |  | 15470.9295 | 20440.4884 | 14017.5523 | 23066.078 | 19977.8188 | 17041.1217 | 16169.489 | 17239.0093 | 0 | 143422.4871 | 93493.5169
| (fully absorbed) | Switchgear |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| (as incurred) | Transformers |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Reactive |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Lines and towers |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Establishment |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Communications |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Non System |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Land |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Easements |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Total incl Overhead - As Incurred $ Mar 2017 |  | 15470.9295 | 20440.4884 | 14017.5523 | 23066.078 | 19977.8188 | 17041.1217 | 16169.489 | 17239.0093 | 0 | 143422.4871 | 93493.5169
|  |  | Check | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| As Commissioned Capex | Direct Expenditure (As Commissioned) - $ 2015/16 |  | 14085.5614 | 18538.5375 | 12766.8144 | 20805 | 17688 | 15005 | 14280 | 15117 | 0 | 128285.9132 | 82895
|  | Labour & Material Escalation - $ 2015/16 |  | 0 | 0 | 84.6115 | 263.9283 | 333.1668 | 373.4042 | 449.7381 | 579.2962 | 0 | 2084.1451 | 1999.5336
|  | Total Direct Expenditure - $ 2015/16 |  | 14085.5614 | 18538.5375 | 12851.4259 | 21068.9283 | 18021.1668 | 15378.4042 | 14729.7381 | 15696.2962 | 0 | 130370.0583 | 84894.5336
|  | Total Direct Expenditure - $ Mar 2017 |  | 14323.8509 | 18852.1593 | 13068.8372 | 21425.3575 | 18326.0362 | 15638.5652 | 14978.9254 | 15961.8351 | 0 | 132575.5668 | 86330.7193
|  | Total overheads (As Commissioned) |  | 1147.0786 | 1588.3291 | 948.7151 | 1640.7205 | 1651.7826 | 1402.5566 | 1190.5636 | 1277.1742 | 0 | 10846.9203 | 7162.7976
|  | Total incl Overhead - As commissioned $ Mar 2017 |  | 15470.9295 | 20440.4884 | 14017.5523 | 23066.078 | 19977.8188 | 17041.1217 | 16169.489 | 17239.0093 | 0 | 143422.4871 | 93493.5169
|  | Total overheads (As Comm) - Cumulative |  | 1147.0786 | 2735.4077 | 3684.1228 | 5324.8433 | 6976.626 | 8379.1825 | 9569.7461 | 10846.9203 | 10846.9203
|  | Total real cost escalation (As Comm) - Cumulative |  | 0 | 0 | 84.6115 | 348.5398 | 681.7066 | 1055.1108 | 1504.8489 | 2084.1451 | 2084.1451
Expenditure By Asset Class - As Commissioned
| Asset class breakdown | Secondary |  | 15470.9295 | 20440.4884 | 14017.5523 | 23066.078 | 19977.8188 | 17041.1217 | 16169.489 | 17239.0093 | 0 | 143422.4871 | 93493.5169
| (fully absorbed) | Switchgear |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| (as commissioned) | Transformers |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Reactive |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Lines and towers |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Establishment |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Communications |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Non System |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Land |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Easements |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Total incl Overhead - As commissioned $ Mar 2017 |  | 15470.9295 | 20440.4884 | 14017.5523 | 23066.078 | 19977.8188 | 17041.1217 | 16169.489 | 17239.0093 | 0 | 143422.4871 | 93493.5169
|  |  | Check | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0
| Expenditure splits for RIN |  |  |  | 2015-16 | 2016-17 | 2017-18 | 2018-19 | 2019-20 | 2020-21 | 2021-22 | 2022-23
| Repex Category | Transmission Towers | bar: 2015-16 to 2022-23
Transmission Tower Support Structures | bar: 2015-16 to 2022-23
Conductors | bar: 2015-16 to 2022-23
Transmission Cables | bar: 2015-16 to 2022-23
Substation Switchbays | bar: 2015-16 to 2022-23
Substation Power Transformers | bar: 2015-16 to 2022-23
Substation Reactive Plant | bar: 2015-16 to 2022-23
|  | Scada Network Control And Protection Systems |  |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
Other | bar: 2015-16 to 2022-23
|  | Total |  |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
| Direct Expenditures | Materials - $ Mar 2017 |  |  | 2015-16 | 2016-17 | 2017-18 | 2018-19 | 2019-20 | 2020-21 | 2021-22 | 2022-23 | Total | 2017-22 Total
| (As Incurred) | Transmission Towers |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Transmission Tower Support Structures |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Conductors |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Transmission Cables |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Substation Switchbays |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Substation Power Transformers |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Substation Reactive Plant |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Scada Network Control And Protection Systems |  |  | 7540.8637 | 5193.1177 | 8462.7857 | 7194.8932 | 6103.5376 | 5808.6316 | 6149.0955 | 0 | 46452.9251 | 33718.9436
|  | Other |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Total Materials |  |  | 7540.8637 | 5193.1177 | 8462.7857 | 7194.8932 | 6103.5376 | 5808.6316 | 6149.0955 | 0 | 46452.9251 | 33718.9436
|  | Labour (Internal) - $ Mar 2017 |  |  | 2015-16 | 2016-17 | 2017-18 | 2018-19 | 2019-20 | 2020-21 | 2021-22 | 2022-23 | Total | 2017-22 Total
|  | Transmission Towers |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Transmission Tower Support Structures |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Conductors |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Transmission Cables |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Substation Switchbays |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Substation Power Transformers |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Substation Reactive Plant |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Scada Network Control And Protection Systems |  |  | 1885.2159 | 1314.5258 | 2159.4163 | 1850.7638 | 1583.0231 | 1520.0193 | 1623.7558 | 0 | 11936.7201 | 8736.9783
|  | Other |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Total Internal Labour |  |  | 1885.2159 | 1314.5258 | 2159.4163 | 1850.7638 | 1583.0231 | 1520.0193 | 1623.7558 | 0 | 11936.7201 | 8736.9783
|  | Labour (External) - $ Mar 2017 |  |  | 2015-16 | 2016-17 | 2017-18 | 2018-19 | 2019-20 | 2020-21 | 2021-22 | 2022-23 | Total | 2017-22 Total
|  | Transmission Towers |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Transmission Tower Support Structures |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Conductors |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Transmission Cables |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Substation Switchbays |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Substation Power Transformers |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Substation Reactive Plant |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Scada Network Control And Protection Systems |  |  | 9426.0797 | 6561.1937 | 10803.1555 | 9280.3792 | 7952.0044 | 7650.2745 | 8188.9837 | 0 | 59862.0707 | 43874.7973
|  | Other |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Total External Labour |  |  | 9426.0797 | 6561.1937 | 10803.1555 | 9280.3792 | 7952.0044 | 7650.2745 | 8188.9837 | 0 | 59862.0707 | 43874.7973
|  | Total Direct - $ Mar 2017 |  |  | 2015-16 | 2016-17 | 2017-18 | 2018-19 | 2019-20 | 2020-21 | 2021-22 | 2022-23 | Total | 2017-22 Total
|  | Transmission Towers |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Transmission Tower Support Structures |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Conductors |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Transmission Cables |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Substation Switchbays |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Substation Power Transformers |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Substation Reactive Plant |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Scada Network Control And Protection Systems |  |  | 18852.1593 | 13068.8372 | 21425.3575 | 18326.0362 | 15638.5652 | 14978.9254 | 15961.8351 | 0 | 118251.7159 | 86330.7193
|  | Other |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Total Direct - $ Mar 2017 |  |  | 18852.1593 | 13068.8372 | 21425.3575 | 18326.0362 | 15638.5652 | 14978.9254 | 15961.8351 | 0 | 118251.7159 | 86330.7193

## Proj_39
Go To: | Table of Contents
Master Inputs
|  |  |  | Business case? | 0
| Project name | Comms program
| Project category 1 | Network |  |  | Shaded cells = Inputs
| Project category 2 | Replacement - Other
| Regulatory classification | Prescribed
| Overhead Category | Repex_OHD |  | $000's | $000's | $000's | $000's | $000's | $000's | $000's | $000's | $000's | Project | 2017-22
|  |  |  | Prior | 2015-16 | 2016-17 | 2017-18 | 2018-19 | 2019-20 | 2020-21 | 2021-22 | 2022-23 | Total | Total | Check
| Project timing | Direct Expenditure (As incurred) - $ 2015/16 |  | 8855.1719 | 4497.9635 | 13342.8803 | 8693.0078 | 11740.1138 | 13320.8849 | 12264.9512 | 7436.5035 | 0 | 80151.477 | 53455.4613 | ok
| (excluding real cost escalators) | Assumed year commissioned (no BC) |  | x | bar: 2015-16 to 2022-23
|  | Direct Expenditure (As Commissioned) - $ 2015/16 |  | 8855.1719 | 4497.9635 | 13342.8803 | 8693.0078 | 11740.1138 | 13320.8849 | 12264.9512 | 7436.5035 | 0 | 80151.477 | 53455.4613 | ok
| Asset class | Secondary
Switchgear
Transformers
Reactive
Lines and towers
Establishment
|  | Communications |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
Non System
Land
Easements
|  |  | Total | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
| Input costs % | Labour - internal |  | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10%
|  | Labour - external |  | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50%
|  | Materials |  | 40% | 40% | 40% | 40% | 40% | 40% | 40% | 40% | 40%
|  |  | Total | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
Material Escalation
| (By Asset Class) | Secondary |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Switchgear |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Transformers |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Reactive |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Lines and towers |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Establishment |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Communications |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Non System |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Land |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Easements |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Total Material escalation |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Labour Escalation | Internal Labour |  | 0 | 0 | 16.697 | 17.9637 | 33.9664 | 49.8818 | 57.3159 | 41.8353 | 0 | 217.66 | 200.9631
|  | External Labour |  | 0 | 0 | 71.7324 | 92.3142 | 187.1675 | 281.6126 | 328.9597 | 243.1378 | 0 | 1204.9243 | 1133.1918
|  | Total Labour Escalation |  | 0 | 0 | 88.4294 | 110.2778 | 221.1339 | 331.4944 | 386.2756 | 284.9731 | 0 | 1422.5843 | 1334.1549
|  | Total Escalation |  | 0 | 0 | 88.4294 | 110.2778 | 221.1339 | 331.4944 | 386.2756 | 284.9731 | 0 | 1422.5843 | 1334.1549
|  | Escalation factors |  | 0 | 0 | 0.0066275 | 0.012686 | 0.018836 | 0.024885 | 0.031494 | 0.038321 | 0 | 0.017749 | 0.024958
| Direct Expenditure (Escalated) | Total labour - internal |  | 900.4977 | 457.4057 | 1373.84 | 902.2746 | 1228.4135 | 1405.3495 | 1305.5296 | 798.774 | 0 | 8372.0846 | 5640.3411
| (as incurred) | Total labour - external |  | 4502.4887 | 2287.0284 | 6857.2488 | 4513.9109 | 6159.6963 | 7059.4959 | 6570.7453 | 4028.4055 | 0 | 41979.0198 | 28332.2539
|  | Total materials |  | 3601.991 | 1829.6228 | 5427.4423 | 3536.028 | 4775.4899 | 5418.4953 | 4988.9764 | 3024.9236 | 0 | 32602.9692 | 21743.9132
|  | Total Direct - As Incurred $ Mar 2017 |  | 9004.9774 | 4574.0569 | 13658.5311 | 8952.2134 | 12163.5997 | 13883.3406 | 12865.2514 | 7852.1031 | 0 | 82954.0736 | 55716.5082 | ok
| Capitalised Overheads | Overhead rate (applied to direct expenditure) |  | 8.008% | 8.425% | 7.259% | 7.658% | 9.013% | 8.969% | 7.948% | 8.001% | 8.318%
|  | Total overhead (as incurred) |  | 721.1341 | 385.3727 | 991.5231 | 685.5466 | 1096.3431 | 1245.1379 | 1022.5633 | 628.2801 | 0 | 6775.9009 | 4677.871
|  | Total incl Overhead - As Incurred $ Mar 2017 |  | 9726.1115 | 4959.4296 | 14650.0542 | 9637.76 | 13259.9427 | 15128.4786 | 13887.8147 | 8480.3833 | 0 | 89729.9745 | 60394.3792
|  | Total overheads (As incurred) - Cumulative |  | 721.1341 | 1106.5068 | 2098.0299 | 2783.5765 | 3879.9196 | 5125.0575 | 6147.6208 | 6775.9009 | 6775.9009
|  | Labour & Material Escalation - Cumulative |  | 0 | 0 | 88.4294 | 198.7072 | 419.8411 | 751.3356 | 1137.6112 | 1422.5843 | 1422.5843
Expenditure By Asset Class - As Incurred
| Asset class breakdown | Secondary |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| (fully absorbed) | Switchgear |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| (as incurred) | Transformers |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Reactive |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Lines and towers |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Establishment |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Communications |  | 9726.1115 | 4959.4296 | 14650.0542 | 9637.76 | 13259.9427 | 15128.4786 | 13887.8147 | 8480.3833 | 0 | 89729.9745 | 60394.3792
|  | Non System |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Land |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Easements |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Total incl Overhead - As Incurred $ Mar 2017 |  | 9726.1115 | 4959.4296 | 14650.0542 | 9637.76 | 13259.9427 | 15128.4786 | 13887.8147 | 8480.3833 | 0 | 89729.9745 | 60394.3792
|  |  | Check | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| As Commissioned Capex | Direct Expenditure (As Commissioned) - $ 2015/16 |  | 8855.1719 | 4497.9635 | 13342.8803 | 8693.0078 | 11740.1138 | 13320.8849 | 12264.9512 | 7436.5035 | 0 | 80151.477 | 53455.4613
|  | Labour & Material Escalation - $ 2015/16 |  | 0 | 0 | 88.4294 | 110.2778 | 221.1339 | 331.4944 | 386.2756 | 284.9731 | 0 | 1422.5843 | 1334.1549
|  | Total Direct Expenditure - $ 2015/16 |  | 8855.1719 | 4497.9635 | 13431.3097 | 8803.2857 | 11961.2477 | 13652.3793 | 12651.2268 | 7721.4767 | 0 | 81574.0613 | 54789.6162
|  | Total Direct Expenditure - $ Mar 2017 |  | 9004.9774 | 4574.0569 | 13658.5311 | 8952.2134 | 12163.5997 | 13883.3406 | 12865.2514 | 7852.1031 | 0 | 82954.0736 | 55716.5082
|  | Total overheads (As Commissioned) |  | 721.1341 | 385.3727 | 991.5231 | 685.5466 | 1096.3431 | 1245.1379 | 1022.5633 | 628.2801 | 0 | 6775.9009 | 4677.871
|  | Total incl Overhead - As commissioned $ Mar 2017 |  | 9726.1115 | 4959.4296 | 14650.0542 | 9637.76 | 13259.9427 | 15128.4786 | 13887.8147 | 8480.3833 | 0 | 89729.9745 | 60394.3792
|  | Total overheads (As Comm) - Cumulative |  | 721.1341 | 1106.5068 | 2098.0299 | 2783.5765 | 3879.9196 | 5125.0575 | 6147.6208 | 6775.9009 | 6775.9009
|  | Total real cost escalation (As Comm) - Cumulative |  | 0 | 0 | 88.4294 | 198.7072 | 419.8411 | 751.3356 | 1137.6112 | 1422.5843 | 1422.5843
Expenditure By Asset Class - As Commissioned
| Asset class breakdown | Secondary |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| (fully absorbed) | Switchgear |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| (as commissioned) | Transformers |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Reactive |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Lines and towers |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Establishment |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Communications |  | 9726.1115 | 4959.4296 | 14650.0542 | 9637.76 | 13259.9427 | 15128.4786 | 13887.8147 | 8480.3833 | 0 | 89729.9745 | 60394.3792
|  | Non System |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Land |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Easements |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Total incl Overhead - As commissioned $ Mar 2017 |  | 9726.1115 | 4959.4296 | 14650.0542 | 9637.76 | 13259.9427 | 15128.4786 | 13887.8147 | 8480.3833 | 0 | 89729.9745 | 60394.3792
|  |  | Check | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0
| Expenditure splits for RIN |  |  |  | 2015-16 | 2016-17 | 2017-18 | 2018-19 | 2019-20 | 2020-21 | 2021-22 | 2022-23
| Repex Category | Transmission Towers | bar: 2015-16 to 2022-23
Transmission Tower Support Structures | bar: 2015-16 to 2022-23
Conductors | bar: 2015-16 to 2022-23
Transmission Cables | bar: 2015-16 to 2022-23
Substation Switchbays | bar: 2015-16 to 2022-23
Substation Power Transformers | bar: 2015-16 to 2022-23
Substation Reactive Plant | bar: 2015-16 to 2022-23
|  | Scada Network Control And Protection Systems |  |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
Other | bar: 2015-16 to 2022-23
|  | Total |  |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
| Direct Expenditures | Materials - $ Mar 2017 |  |  | 2015-16 | 2016-17 | 2017-18 | 2018-19 | 2019-20 | 2020-21 | 2021-22 | 2022-23 | Total | 2017-22 Total
| (As Incurred) | Transmission Towers |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Transmission Tower Support Structures |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Conductors |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Transmission Cables |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Substation Switchbays |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Substation Power Transformers |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Substation Reactive Plant |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Scada Network Control And Protection Systems |  |  | 1829.6228 | 5427.4423 | 3536.028 | 4775.4899 | 5418.4953 | 4988.9764 | 3024.9236 | 0 | 29000.9783 | 21743.9132
|  | Other |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Total Materials |  |  | 1829.6228 | 5427.4423 | 3536.028 | 4775.4899 | 5418.4953 | 4988.9764 | 3024.9236 | 0 | 29000.9783 | 21743.9132
|  | Labour (Internal) - $ Mar 2017 |  |  | 2015-16 | 2016-17 | 2017-18 | 2018-19 | 2019-20 | 2020-21 | 2021-22 | 2022-23 | Total | 2017-22 Total
|  | Transmission Towers |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Transmission Tower Support Structures |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Conductors |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Transmission Cables |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Substation Switchbays |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Substation Power Transformers |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Substation Reactive Plant |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Scada Network Control And Protection Systems |  |  | 457.4057 | 1373.84 | 902.2746 | 1228.4135 | 1405.3495 | 1305.5296 | 798.774 | 0 | 7471.5868 | 5640.3411
|  | Other |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Total Internal Labour |  |  | 457.4057 | 1373.84 | 902.2746 | 1228.4135 | 1405.3495 | 1305.5296 | 798.774 | 0 | 7471.5868 | 5640.3411
|  | Labour (External) - $ Mar 2017 |  |  | 2015-16 | 2016-17 | 2017-18 | 2018-19 | 2019-20 | 2020-21 | 2021-22 | 2022-23 | Total | 2017-22 Total
|  | Transmission Towers |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Transmission Tower Support Structures |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Conductors |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Transmission Cables |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Substation Switchbays |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Substation Power Transformers |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Substation Reactive Plant |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Scada Network Control And Protection Systems |  |  | 2287.0284 | 6857.2488 | 4513.9109 | 6159.6963 | 7059.4959 | 6570.7453 | 4028.4055 | 0 | 37476.5311 | 28332.2539
|  | Other |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Total External Labour |  |  | 2287.0284 | 6857.2488 | 4513.9109 | 6159.6963 | 7059.4959 | 6570.7453 | 4028.4055 | 0 | 37476.5311 | 28332.2539
|  | Total Direct - $ Mar 2017 |  |  | 2015-16 | 2016-17 | 2017-18 | 2018-19 | 2019-20 | 2020-21 | 2021-22 | 2022-23 | Total | 2017-22 Total
|  | Transmission Towers |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Transmission Tower Support Structures |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Conductors |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Transmission Cables |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Substation Switchbays |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Substation Power Transformers |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Substation Reactive Plant |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Scada Network Control And Protection Systems |  |  | 4574.0569 | 13658.5311 | 8952.2134 | 12163.5997 | 13883.3406 | 12865.2514 | 7852.1031 | 0 | 73949.0962 | 55716.5082
|  | Other |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Total Direct - $ Mar 2017 |  |  | 4574.0569 | 13658.5311 | 8952.2134 | 12163.5997 | 13883.3406 | 12865.2514 | 7852.1031 | 0 | 73949.0962 | 55716.5082

## Proj_40
Go To: | Table of Contents
Master Inputs
|  |  |  | Business case? | 0
| Project name | Comms program - safety and security
| Project category 1 | Network |  |  | Shaded cells = Inputs
| Project category 2 | Security and Compliance
| Regulatory classification | Prescribed
| Overhead Category | Repex_OHD |  | $000's | $000's | $000's | $000's | $000's | $000's | $000's | $000's | $000's | Project | 2017-22
|  |  |  | Prior | 2015-16 | 2016-17 | 2017-18 | 2018-19 | 2019-20 | 2020-21 | 2021-22 | 2022-23 | Total | Total | Check
| Project timing | Direct Expenditure (As incurred) - $ 2015/16 |  | 0 | 338.5066 | 406.1676 | 1333.185 | 283.3425 | 754.8975 | 0 | 1377.5 | 0 | 4493.5993 | 3748.925 | ok
| (excluding real cost escalators) | Assumed year commissioned (no BC) | bar: 2015-16 to 2022-23
|  | Direct Expenditure (As Commissioned) - $ 2015/16 |  | 0 | 338.5066 | 406.1676 | 1333.185 | 283.3425 | 754.8975 | 0 | 1377.5 | 0 | 4493.5993 | 3748.925 | ok
| Asset class | Secondary
Switchgear
Transformers
Reactive
Lines and towers
Establishment
|  | Communications |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
Non System
Land
Easements
|  |  | Total | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
| Input costs % | Labour - internal |  | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10%
|  | Labour - external |  | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50%
|  | Materials |  | 40% | 40% | 40% | 40% | 40% | 40% | 40% | 40% | 40%
|  |  | Total | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
Material Escalation
| (By Asset Class) | Secondary |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Switchgear |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Transformers |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Reactive |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Lines and towers |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Establishment |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Communications |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Non System |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Land |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Easements |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Total Material escalation |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Labour Escalation | Internal Labour |  | 0 | 0 | 0.50827 | 2.755 | 0.81976 | 2.8268 | 0 | 7.7494 | 0 | 14.6592 | 14.1509
|  | External Labour |  | 0 | 0 | 2.1836 | 14.1576 | 4.5172 | 15.9591 | 0 | 45.0376 | 0 | 81.855 | 79.6714
|  | Total Labour Escalation |  | 0 | 0 | 2.6919 | 16.9125 | 5.337 | 18.7859 | 0 | 52.787 | 0 | 96.5142 | 93.8223
|  | Total Escalation |  | 0 | 0 | 2.6919 | 16.9125 | 5.337 | 18.7859 | 0 | 52.787 | 0 | 96.5142 | 93.8223
|  | Escalation factors (applied to $2015/16 Capex) |  | 0 | 0 | 0.0066275 | 0.012686 | 0.018836 | 0.024885 | 0 | 0.038321 | 0 | 0.021478 | 0.025026
| Direct Expenditure (Escalated) | Total labour - internal |  | 0 | 34.4233 | 41.8208 | 138.3755 | 29.6472 | 79.6415 | 0 | 147.9608 | 0 | 471.869 | 395.625
| (as incurred) | Total labour - external |  | 0 | 172.1166 | 208.74 | 692.2665 | 148.6616 | 400.0632 | 0 | 746.2013 | 0 | 2368.0492 | 1987.1926
|  | Total materials |  | 0 | 137.6933 | 165.2156 | 542.2956 | 115.2544 | 307.0673 | 0 | 560.3214 | 0 | 1827.8475 | 1524.9387
|  | Total Direct - As Incurred $ Mar 2017 |  | 0 | 344.2332 | 415.7763 | 1372.9375 | 293.5631 | 786.772 | 0 | 1454.4835 | 0 | 4667.7657 | 3907.7562 | ok
| Capitalised Overheads | Overhead rate (applied to direct expenditure) |  | 8.008% | 8.425% | 7.259% | 7.658% | 9.013% | 8.969% | 7.948% | 8.001% | 8.318%
|  | Total overhead (as incurred) |  | 0 | 29.0023 | 30.1827 | 105.1374 | 26.4598 | 70.5622 | 0 | 116.3794 | 0 | 377.7238 | 318.5388
|  | Total incl Overhead - As Incurred $ Mar 2017 |  | 0 | 373.2355 | 445.959 | 1478.0749 | 320.0229 | 857.3342 | 0 | 1570.863 | 0 | 5045.4896 | 4226.295
|  | Total overheads (As incurred) - Cumulative |  | 0 | 29.0023 | 59.185 | 164.3224 | 190.7822 | 261.3444 | 261.3444 | 377.7238 | 377.7238
|  | Labour & Material Escalation - Cumulative |  | 0 | 0 | 2.6919 | 19.6044 | 24.9414 | 43.7272 | 43.7272 | 96.5142 | 96.5142
Expenditure By Asset Class - As Incurred
| Asset class breakdown | Secondary |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| (fully absorbed) | Switchgear |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| (as incurred) | Transformers |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Reactive |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Lines and towers |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Establishment |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Communications |  | 0 | 373.2355 | 445.959 | 1478.0749 | 320.0229 | 857.3342 | 0 | 1570.863 | 0 | 5045.4896 | 4226.295
|  | Non System |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Land |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Easements |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Total incl Overhead - As Incurred $ Mar 2017 |  | 0 | 373.2355 | 445.959 | 1478.0749 | 320.0229 | 857.3342 | 0 | 1570.863 | 0 | 5045.4896 | 4226.295
|  |  | Check | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| As Commissioned Capex | Direct Expenditure (As Commissioned) - $ 2015/16 |  | 0 | 338.5066 | 406.1676 | 1333.185 | 283.3425 | 754.8975 | 0 | 1377.5 | 0 | 4493.5993 | 3748.925
|  | Labour & Material Escalation - $ 2015/16 |  | 0 | 0 | 2.6919 | 16.9125 | 5.337 | 18.7859 | 0 | 52.787 | 0 | 96.5142 | 93.8223
|  | Total Direct Expenditure - $ 2015/16 |  | 0 | 338.5066 | 408.8595 | 1350.0975 | 288.6795 | 773.6834 | 0 | 1430.287 | 0 | 4590.1134 | 3842.7473
|  | Total Direct Expenditure - $ Mar 2017 |  | 0 | 344.2332 | 415.7763 | 1372.9375 | 293.5631 | 786.772 | 0 | 1454.4835 | 0 | 4667.7657 | 3907.7562
|  | Total overheads (As Commissioned) |  | 0 | 29.0023 | 30.1827 | 105.1374 | 26.4598 | 70.5622 | 0 | 116.3794 | 0 | 377.7238 | 318.5388
|  | Total incl Overhead - As commissioned $ Mar 2017 |  | 0 | 373.2355 | 445.959 | 1478.0749 | 320.0229 | 857.3342 | 0 | 1570.863 | 0 | 5045.4896 | 4226.295
|  | Total overheads (As Comm) - Cumulative |  | 0 | 29.0023 | 59.185 | 164.3224 | 190.7822 | 261.3444 | 261.3444 | 377.7238 | 377.7238
|  | Total real cost escalation (As Comm) - Cumulative |  | 0 | 0 | 2.6919 | 19.6044 | 24.9414 | 43.7272 | 43.7272 | 96.5142 | 96.5142
Expenditure By Asset Class - As Commissioned
| Asset class breakdown | Secondary |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| (fully absorbed) | Switchgear |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| (as commissioned) | Transformers |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Reactive |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Lines and towers |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Establishment |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Communications |  | 0 | 373.2355 | 445.959 | 1478.0749 | 320.0229 | 857.3342 | 0 | 1570.863 | 0 | 5045.4896 | 4226.295
|  | Non System |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Land |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Easements |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Total incl Overhead - As commissioned $ Mar 2017 |  | 0 | 373.2355 | 445.959 | 1478.0749 | 320.0229 | 857.3342 | 0 | 1570.863 | 0 | 5045.4896 | 4226.295
|  |  | Check | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0
| Expenditure splits for RIN |  |  |  | 2015-16 | 2016-17 | 2017-18 | 2018-19 | 2019-20 | 2020-21 | 2021-22 | 2022-23
| Repex Category | Transmission Towers | bar: 2015-16 to 2022-23
Transmission Tower Support Structures | bar: 2015-16 to 2022-23
Conductors | bar: 2015-16 to 2022-23
Transmission Cables | bar: 2015-16 to 2022-23
Substation Switchbays | bar: 2015-16 to 2022-23
Substation Power Transformers | bar: 2015-16 to 2022-23
Substation Reactive Plant | bar: 2015-16 to 2022-23
|  | Scada Network Control And Protection Systems |  |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
Other | bar: 2015-16 to 2022-23
|  | Total |  |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
| Direct Expenditures | Materials - $ Mar 2017 |  |  | 2015-16 | 2016-17 | 2017-18 | 2018-19 | 2019-20 | 2020-21 | 2021-22 | 2022-23 | Total | 2017-22 Total
| (As Incurred) | Transmission Towers |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Transmission Tower Support Structures |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Conductors |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Transmission Cables |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Substation Switchbays |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Substation Power Transformers |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Substation Reactive Plant |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Scada Network Control And Protection Systems |  |  | 137.6933 | 165.2156 | 542.2956 | 115.2544 | 307.0673 | 0 | 560.3214 | 0 | 1827.8475 | 1524.9387
|  | Other |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Total Materials |  |  | 137.6933 | 165.2156 | 542.2956 | 115.2544 | 307.0673 | 0 | 560.3214 | 0 | 1827.8475 | 1524.9387
|  | Labour (Internal) - $ Mar 2017 |  |  | 2015-16 | 2016-17 | 2017-18 | 2018-19 | 2019-20 | 2020-21 | 2021-22 | 2022-23 | Total | 2017-22 Total
|  | Transmission Towers |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Transmission Tower Support Structures |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Conductors |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Transmission Cables |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Substation Switchbays |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Substation Power Transformers |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Substation Reactive Plant |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Scada Network Control And Protection Systems |  |  | 34.4233 | 41.8208 | 138.3755 | 29.6472 | 79.6415 | 0 | 147.9608 | 0 | 471.869 | 395.625
|  | Other |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Total Internal Labour |  |  | 34.4233 | 41.8208 | 138.3755 | 29.6472 | 79.6415 | 0 | 147.9608 | 0 | 471.869 | 395.625
|  | Labour (External) - $ Mar 2017 |  |  | 2015-16 | 2016-17 | 2017-18 | 2018-19 | 2019-20 | 2020-21 | 2021-22 | 2022-23 | Total | 2017-22 Total
|  | Transmission Towers |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Transmission Tower Support Structures |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Conductors |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Transmission Cables |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Substation Switchbays |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Substation Power Transformers |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Substation Reactive Plant |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Scada Network Control And Protection Systems |  |  | 172.1166 | 208.74 | 692.2665 | 148.6616 | 400.0632 | 0 | 746.2013 | 0 | 2368.0492 | 1987.1926
|  | Other |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Total External Labour |  |  | 172.1166 | 208.74 | 692.2665 | 148.6616 | 400.0632 | 0 | 746.2013 | 0 | 2368.0492 | 1987.1926
|  | Total Direct - $ Mar 2017 |  |  | 2015-16 | 2016-17 | 2017-18 | 2018-19 | 2019-20 | 2020-21 | 2021-22 | 2022-23 | Total | 2017-22 Total
|  | Transmission Towers |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Transmission Tower Support Structures |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Conductors |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Transmission Cables |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Substation Switchbays |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Substation Power Transformers |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Substation Reactive Plant |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Scada Network Control And Protection Systems |  |  | 344.2332 | 415.7763 | 1372.9375 | 293.5631 | 786.772 | 0 | 1454.4835 | 0 | 4667.7657 | 3907.7562
|  | Other |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Total Direct - $ Mar 2017 |  |  | 344.2332 | 415.7763 | 1372.9375 | 293.5631 | 786.772 | 0 | 1454.4835 | 0 | 4667.7657 | 3907.7562

## Proj_41
Go To: | Table of Contents
Master Inputs
|  |  |  | Business case? | 0
| Project name | Other station works
| Project category 1 | Network |  |  | Shaded cells = Inputs
| Project category 2 | Replacement - Other
| Regulatory classification | Prescribed
| Overhead Category | Repex_OHD |  | $000's | $000's | $000's | $000's | $000's | $000's | $000's | $000's | $000's | Project | 2017-22
|  |  |  | Prior | 2015-16 | 2016-17 | 2017-18 | 2018-19 | 2019-20 | 2020-21 | 2021-22 | 2022-23 | Total | Total | Check
| Project timing | Direct Expenditure (As incurred) - $ 2015/16 |  | 4835.9026 | 6614.1253 | 2182.8864 | 0 | 0 | 0 | 0 | 0 | 0 | 13632.9143 | 0 | ok
| (excluding real cost escalators) | Assumed year commissioned (no BC) |  | x | bar: 2015-16 to 2022-23
|  | Direct Expenditure (As Commissioned) - $ 2015/16 |  | 4835.9026 | 6614.1253 | 2182.8864 | 0 | 0 | 0 | 0 | 0 | 0 | 13632.9143 | 0 | ok
| Asset class | Secondary |  | 17.18% | 17.18% | 17.18% | 17.18% | 17.18% | 17.18% | 17.18% | 17.18% | 17.18%
|  | Switchgear |  | 30.93% | 30.93% | 30.93% | 30.93% | 30.93% | 30.93% | 30.93% | 30.93% | 30.93%
|  | Transformers |  | 44% | 44% | 44% | 44% | 44% | 44% | 44% | 44% | 44%
|  | Reactive |  | 0% | bar: 2015-16 to 2022-23
|  | Lines and towers |  | 0% | bar: 2015-16 to 2022-23
|  | Establishment |  | 7.895% | 7.895% | 7.895% | 7.895% | 7.895% | 7.895% | 7.895% | 7.895% | 7.895%
|  | Communications |  | 0% | bar: 2015-16 to 2022-23
Non System
Land
Easements
|  |  | Total | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
| Input costs % | Labour - internal |  | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10%
|  | Labour - external |  | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50%
|  | Materials |  | 40% | 40% | 40% | 40% | 40% | 40% | 40% | 40% | 40%
|  |  | Total | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
Material Escalation
| (By Asset Class) | Secondary |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Switchgear |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Transformers |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Reactive |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Lines and towers |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Establishment |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Communications |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Non System |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Land |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Easements |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Total Material escalation |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Labour Escalation | Internal Labour |  | 0 | 0 | 2.7316 | 0 | 0 | 0 | 0 | 0 | 0 | 2.7316 | 0
|  | External Labour |  | 0 | 0 | 11.7354 | 0 | 0 | 0 | 0 | 0 | 0 | 11.7354 | 0
|  | Total Labour Escalation |  | 0 | 0 | 14.467 | 0 | 0 | 0 | 0 | 0 | 0 | 14.467 | 0
|  | Total Escalation |  | 0 | 0 | 14.467 | 0 | 0 | 0 | 0 | 0 | 0 | 14.467 | 0
|  | Escalation factors |  | 0 | 0 | 0.0066275 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0010612 | 0
| Direct Expenditure (Escalated) | Total labour - internal |  | 491.7713 | 672.6018 | 224.7593 | 0 | 0 | 0 | 0 | 0 | 0 | 1389.1325 | 0
| (as incurred) | Total labour - external |  | 2458.8565 | 3363.0092 | 1121.8414 | 0 | 0 | 0 | 0 | 0 | 0 | 6943.7071 | 0
|  | Total materials |  | 1967.0852 | 2690.4073 | 887.926 | 0 | 0 | 0 | 0 | 0 | 0 | 5545.4185 | 0
|  | Total Direct - As Incurred $ Mar 2017 |  | 4917.713 | 6726.0184 | 2234.5267 | 0 | 0 | 0 | 0 | 0 | 0 | 13878.258 | 0 | ok
| Capitalised Overheads | Overhead rate (applied to direct expenditure) |  | 8.008% | 8.425% | 7.259% | 7.658% | 9.013% | 8.969% | 7.948% | 8.001% | 8.318%
|  | Total overhead (as incurred) |  | 393.8189 | 566.6794 | 162.2125 | 0 | 0 | 0 | 0 | 0 | 0 | 1122.7109 | 0
|  | Total incl Overhead - As Incurred $ Mar 2017 |  | 5311.5319 | 7292.6978 | 2396.7392 | 0 | 0 | 0 | 0 | 0 | 0 | 15000.9689 | 0
|  | Total overheads (As incurred) - Cumulative |  | 393.8189 | 960.4983 | 1122.7109 | 1122.7109 | 1122.7109 | 1122.7109 | 1122.7109 | 1122.7109 | 1122.7109
|  | Labour & Material Escalation - Cumulative |  | 0 | 0 | 14.467 | 14.467 | 14.467 | 14.467 | 14.467 | 14.467 | 14.467
Expenditure By Asset Class - As Incurred
| Asset class breakdown | Secondary |  | 912.5041 | 1252.862 | 411.7521 | 0 | 0 | 0 | 0 | 0 | 0 | 2577.1182 | 0
| (fully absorbed) | Switchgear |  | 1642.7191 | 2255.4423 | 741.2493 | 0 | 0 | 0 | 0 | 0 | 0 | 4639.4107 | 0
| (as incurred) | Transformers |  | 2336.9818 | 3208.6604 | 1054.5237 | 0 | 0 | 0 | 0 | 0 | 0 | 6600.1659 | 0
|  | Reactive |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Lines and towers |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Establishment |  | 419.3269 | 575.733 | 189.2142 | 0 | 0 | 0 | 0 | 0 | 0 | 1184.2741 | 0
|  | Communications |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Non System |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Land |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Easements |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Total incl Overhead - As Incurred $ Mar 2017 |  | 5311.5319 | 7292.6978 | 2396.7392 | 0 | 0 | 0 | 0 | 0 | 0 | 15000.9689 | 0
|  |  | Check | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| As Commissioned Capex | Direct Expenditure (As Commissioned) - $ 2015/16 |  | 4835.9026 | 6614.1253 | 2182.8864 | 0 | 0 | 0 | 0 | 0 | 0 | 13632.9143 | 0
|  | Labour & Material Escalation - $ 2015/16 |  | 0 | 0 | 14.467 | 0 | 0 | 0 | 0 | 0 | 0 | 14.467 | 0
|  | Total Direct Expenditure - $ 2015/16 |  | 4835.9026 | 6614.1253 | 2197.3534 | 0 | 0 | 0 | 0 | 0 | 0 | 13647.3813 | 0
|  | Total Direct Expenditure - $ Mar 2017 |  | 4917.713 | 6726.0184 | 2234.5267 | 0 | 0 | 0 | 0 | 0 | 0 | 13878.258 | 0
|  | Total overheads (As Commissioned) |  | 393.8189 | 566.6794 | 162.2125 | 0 | 0 | 0 | 0 | 0 | 0 | 1122.7109 | 0
|  | Total incl Overhead - As commissioned $ Mar 2017 |  | 5311.5319 | 7292.6978 | 2396.7392 | 0 | 0 | 0 | 0 | 0 | 0 | 15000.9689 | 0
|  | Total overheads (As Comm) - Cumulative |  | 393.8189 | 960.4983 | 1122.7109 | 1122.7109 | 1122.7109 | 1122.7109 | 1122.7109 | 1122.7109 | 1122.7109
|  | Total real cost escalation (As Comm) - Cumulative |  | 0 | 0 | 14.467 | 14.467 | 14.467 | 14.467 | 14.467 | 14.467 | 14.467
Expenditure By Asset Class - As Commissioned
| Asset class breakdown | Secondary |  | 912.5041 | 1252.862 | 411.7521 | 0 | 0 | 0 | 0 | 0 | 0 | 2577.1182 | 0
| (fully absorbed) | Switchgear |  | 1642.7191 | 2255.4423 | 741.2493 | 0 | 0 | 0 | 0 | 0 | 0 | 4639.4107 | 0
| (as commissioned) | Transformers |  | 2336.9818 | 3208.6604 | 1054.5237 | 0 | 0 | 0 | 0 | 0 | 0 | 6600.1659 | 0
|  | Reactive |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Lines and towers |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Establishment |  | 419.3269 | 575.733 | 189.2142 | 0 | 0 | 0 | 0 | 0 | 0 | 1184.2741 | 0
|  | Communications |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Non System |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Land |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Easements |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Total incl Overhead - As commissioned $ Mar 2017 |  | 5311.5319 | 7292.6978 | 2396.7392 | 0 | 0 | 0 | 0 | 0 | 0 | 15000.9689 | 0
|  |  | Check | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0
| Expenditure splits for RIN |  |  |  | 2015-16 | 2016-17 | 2017-18 | 2018-19 | 2019-20 | 2020-21 | 2021-22 | 2022-23
| Repex Category | Transmission Towers | bar: 2015-16 to 2022-23
Transmission Tower Support Structures | bar: 2015-16 to 2022-23
Conductors | bar: 2015-16 to 2022-23
Transmission Cables | bar: 2015-16 to 2022-23
|  | Substation Switchbays |  |  | 30.93% | 30.93% | 30.93% | 30.93% | 30.93% | 30.93% | 30.93% | 30.93%
|  | Substation Power Transformers |  |  | 44% | 44% | 44% | 44% | 44% | 44% | 44% | 44%
Substation Reactive Plant | bar: 2015-16 to 2022-23
|  | Scada Network Control And Protection Systems |  |  | 17.18% | 17.18% | 17.18% | 17.18% | 17.18% | 17.18% | 17.18% | 17.18%
|  | Other |  |  | 7.895% | 7.895% | 7.895% | 7.895% | 7.895% | 7.895% | 7.895% | 7.895%
|  | Total |  |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
| Direct Expenditures | Materials - $ Mar 2017 |  |  | 2015-16 | 2016-17 | 2017-18 | 2018-19 | 2019-20 | 2020-21 | 2021-22 | 2022-23 | Total | 2017-22 Total
| (As Incurred) | Transmission Towers |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Transmission Tower Support Structures |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Conductors |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Transmission Cables |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Substation Switchbays |  |  | 832.0732 | 274.6125 | 0 | 0 | 0 | 0 | 0 | 0 | 1106.6857 | 0
|  | Substation Power Transformers |  |  | 1183.7325 | 390.672 | 0 | 0 | 0 | 0 | 0 | 0 | 1574.4045 | 0
|  | Substation Reactive Plant |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Scada Network Control And Protection Systems |  |  | 462.2033 | 152.5428 | 0 | 0 | 0 | 0 | 0 | 0 | 614.7461 | 0
|  | Other |  |  | 212.3983 | 70.0987 | 0 | 0 | 0 | 0 | 0 | 0 | 282.4969 | 0
|  | Total Materials |  |  | 2690.4073 | 887.926 | 0 | 0 | 0 | 0 | 0 | 0 | 3578.3333 | 0
|  | Labour (Internal) - $ Mar 2017 |  |  | 2015-16 | 2016-17 | 2017-18 | 2018-19 | 2019-20 | 2020-21 | 2021-22 | 2022-23 | Total | 2017-22 Total
|  | Transmission Towers |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Transmission Tower Support Structures |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Conductors |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Transmission Cables |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Substation Switchbays |  |  | 208.0183 | 69.5122 | 0 | 0 | 0 | 0 | 0 | 0 | 277.5305 | 0
|  | Substation Power Transformers |  |  | 295.9331 | 98.8902 | 0 | 0 | 0 | 0 | 0 | 0 | 394.8233 | 0
|  | Substation Reactive Plant |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Scada Network Control And Protection Systems |  |  | 115.5508 | 38.6129 | 0 | 0 | 0 | 0 | 0 | 0 | 154.1638 | 0
|  | Other |  |  | 53.0996 | 17.744 | 0 | 0 | 0 | 0 | 0 | 0 | 70.8435 | 0
|  | Total Internal Labour |  |  | 672.6018 | 224.7593 | 0 | 0 | 0 | 0 | 0 | 0 | 897.3612 | 0
|  | Labour (External) - $ Mar 2017 |  |  | 2015-16 | 2016-17 | 2017-18 | 2018-19 | 2019-20 | 2020-21 | 2021-22 | 2022-23 | Total | 2017-22 Total
|  | Transmission Towers |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Transmission Tower Support Structures |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Conductors |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Transmission Cables |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Substation Switchbays |  |  | 1040.0915 | 346.9565 | 0 | 0 | 0 | 0 | 0 | 0 | 1387.048 | 0
|  | Substation Power Transformers |  |  | 1479.6657 | 493.5907 | 0 | 0 | 0 | 0 | 0 | 0 | 1973.2564 | 0
|  | Substation Reactive Plant |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Scada Network Control And Protection Systems |  |  | 577.7542 | 192.7287 | 0 | 0 | 0 | 0 | 0 | 0 | 770.4829 | 0
|  | Other |  |  | 265.4978 | 88.5655 | 0 | 0 | 0 | 0 | 0 | 0 | 354.0633 | 0
|  | Total External Labour |  |  | 3363.0092 | 1121.8414 | 0 | 0 | 0 | 0 | 0 | 0 | 4484.8506 | 0
|  | Total Direct - $ Mar 2017 |  |  | 2015-16 | 2016-17 | 2017-18 | 2018-19 | 2019-20 | 2020-21 | 2021-22 | 2022-23 | Total | 2017-22 Total
|  | Transmission Towers |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Transmission Tower Support Structures |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Conductors |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Transmission Cables |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Substation Switchbays |  |  | 2080.1831 | 691.0812 | 0 | 0 | 0 | 0 | 0 | 0 | 2771.2643 | 0
|  | Substation Power Transformers |  |  | 2959.3313 | 983.153 | 0 | 0 | 0 | 0 | 0 | 0 | 3942.4843 | 0
|  | Substation Reactive Plant |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Scada Network Control And Protection Systems |  |  | 1155.5083 | 383.8845 | 0 | 0 | 0 | 0 | 0 | 0 | 1539.3928 | 0
|  | Other |  |  | 530.9957 | 176.4081 | 0 | 0 | 0 | 0 | 0 | 0 | 707.4037 | 0
|  | Total Direct - $ Mar 2017 |  |  | 6726.0184 | 2234.5267 | 0 | 0 | 0 | 0 | 0 | 0 | 8960.5451 | 0

## Proj_42
Go To: | Table of Contents
Master Inputs
|  |  |  | Business case? | 0
| Project name | ERTS B1, B3 & B4 Transformer replacements
| Project category 1 | Network |  |  | Shaded cells = Inputs
| Project category 2 | Replacement - Major Station
| Regulatory classification | Prescribed
| Overhead Category | Repex_OHD |  | $000's | $000's | $000's | $000's | $000's | $000's | $000's | $000's | $000's | Project | 2017-22
|  |  |  | Prior | 2015-16 | 2016-17 | 2017-18 | 2018-19 | 2019-20 | 2020-21 | 2021-22 | 2022-23 | Total | Total | Check
| Project timing | Direct Expenditure (As incurred) - $ 2015/16 |  | 0 | 0 | 0 | 5067.7926 | 8576.037 | 5456.9407 | 0 | 0 | 0 | 19100.7704 | 19100.7704 | ok
| (excluding real cost escalators) | Assumed year commissioned (no BC) | bar: 2015-16 to 2022-23
|  | Direct Expenditure (As Commissioned) - $ 2015/16 |  | 0 | 0 | 0 | 0 | 13643.8296 | 5456.9407 | 0 | 0 | 0 | 19100.7704 | 19100.7704 | ok
| Asset class | Secondary |  | 0% | bar: 2015-16 to 2022-23
|  | Switchgear |  | 0% | bar: 2015-16 to 2022-23
|  | Transformers |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
|  | Reactive |  | 0% | bar: 2015-16 to 2022-23
|  | Lines and towers |  | 0% | bar: 2015-16 to 2022-23
|  | Establishment |  | 0% | bar: 2015-16 to 2022-23
|  | Communications |  | 0.333% | bar: 2015-16 to 2022-23
|  | Non System |  | 0% | bar: 2015-16 to 2022-23
|  | Land |  | 0% | bar: 2015-16 to 2022-23
|  | Easements |  | 0% | bar: 2015-16 to 2022-23
|  |  | Total | 100.3% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
| Input costs % | Labour - internal |  | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10%
|  | Labour - external |  | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50%
|  | Materials |  | 40% | 40% | 40% | 40% | 40% | 40% | 40% | 40% | 40%
|  |  | Total | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
Material Escalation
| (By Asset Class) | Secondary |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Switchgear |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Transformers |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Reactive |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Lines and towers |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Establishment |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Communications |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Non System |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Land |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Easements |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Total Material escalation |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Labour Escalation | Internal Labour |  | 0 | 0 | 0 | 10.4723 | 24.8121 | 20.4342 | 0 | 0 | 0 | 55.7187 | 55.7187
|  | External Labour |  | 0 | 0 | 0 | 53.8167 | 136.724 | 115.3635 | 0 | 0 | 0 | 305.9042 | 305.9042
|  | Total Labour Escalation |  | 0 | 0 | 0 | 64.289 | 161.5361 | 135.7977 | 0 | 0 | 0 | 361.6229 | 361.6229
|  | Total Escalation |  | 0 | 0 | 0 | 64.289 | 161.5361 | 135.7977 | 0 | 0 | 0 | 361.6229 | 361.6229
|  | Escalation factors |  | 0 | 0 | 0 | 0.012686 | 0.018836 | 0.024885 | 0 | 0 | 0 | 0.018932 | 0.018932
| Direct Expenditure (Escalated) | Total labour - internal |  | 0 | 0 | 0 | 526.0021 | 897.3439 | 575.7057 | 0 | 0 | 0 | 1999.0517 | 1999.0517
| (as incurred) | Total labour - external |  | 0 | 0 | 0 | 2631.4901 | 4499.5972 | 2891.9438 | 0 | 0 | 0 | 10023.0311 | 10023.0311
|  | Total materials |  | 0 | 0 | 0 | 2061.4104 | 3488.4481 | 2219.703 | 0 | 0 | 0 | 7769.5615 | 7769.5615
|  | Total Direct - As Incurred $ Mar 2017 |  | 0 | 0 | 0 | 5218.9026 | 8885.3893 | 5687.3524 | 0 | 0 | 0 | 19791.6443 | 19791.6443 | ok
| Capitalised Overheads | Overhead rate (applied to direct expenditure) |  | 8.008% | 8.425% | 7.259% | 7.658% | 9.013% | 8.969% | 7.948% | 8.001% | 8.318%
|  | Total overhead (as incurred) |  | 0 | 0 | 0 | 399.6554 | 800.8678 | 510.0745 | 0 | 0 | 0 | 1710.5977 | 1710.5977
|  | Total incl Overhead - As Incurred $ Mar 2017 |  | 0 | 0 | 0 | 5618.558 | 9686.257 | 6197.427 | 0 | 0 | 0 | 21502.242 | 21502.242
|  | Total overheads (As incurred) - Cumulative |  | 0 | 0 | 0 | 399.6554 | 1200.5232 | 1710.5977 | 1710.5977 | 1710.5977 | 1710.5977
|  | Labour & Material Escalation - Cumulative |  | 0 | 0 | 0 | 64.289 | 225.8252 | 361.6229 | 361.6229 | 361.6229 | 361.6229
Expenditure By Asset Class - As Incurred
| Asset class breakdown | Secondary |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| (fully absorbed) | Switchgear |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| (as incurred) | Transformers |  | 0 | 0 | 0 | 5618.558 | 9686.257 | 6197.427 | 0 | 0 | 0 | 21502.242 | 21502.242
|  | Reactive |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Lines and towers |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Establishment |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Communications |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Non System |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Land |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Easements |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Total incl Overhead - As Incurred $ Mar 2017 |  | 0 | 0 | 0 | 5618.558 | 9686.257 | 6197.427 | 0 | 0 | 0 | 21502.242 | 21502.242
|  |  | Check | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| As Commissioned Capex | Direct Expenditure (As Commissioned) - $ 2015/16 |  | 0 | 0 | 0 | 0 | 13643.8296 | 5456.9407 | 0 | 0 | 0 | 19100.7704 | 19100.7704
|  | Labour & Material Escalation - $ 2015/16 |  | 0 | 0 | 0 | 0 | 225.8252 | 135.7977 | 0 | 0 | 0 | 361.6229 | 361.6229
|  | Total Direct Expenditure - $ 2015/16 |  | 0 | 0 | 0 | 0 | 13869.6548 | 5592.7384 | 0 | 0 | 0 | 19462.3932 | 19462.3932
|  | Total Direct Expenditure - $ Mar 2017 |  | 0 | 0 | 0 | 0 | 14104.2918 | 5687.3524 | 0 | 0 | 0 | 19791.6443 | 19791.6443
|  | Total overheads (As Commissioned) |  | 0 | 0 | 0 | 0 | 1200.5232 | 510.0745 | 0 | 0 | 0 | 1710.5977 | 1710.5977
|  | Total incl Overhead - As commissioned $ Mar 2017 |  | 0 | 0 | 0 | 0 | 15304.815 | 6197.427 | 0 | 0 | 0 | 21502.242 | 21502.242
|  | Total overheads (As Comm) - Cumulative |  | 0 | 0 | 0 | 0 | 1200.5232 | 1710.5977 | 1710.5977 | 1710.5977 | 1710.5977
|  | Total real cost escalation (As Comm) - Cumulative |  | 0 | 0 | 0 | 0 | 225.8252 | 361.6229 | 361.6229 | 361.6229 | 361.6229
Expenditure By Asset Class - As Commissioned
| Asset class breakdown | Secondary |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| (fully absorbed) | Switchgear |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| (as commissioned) | Transformers |  | 0 | 0 | 0 | 0 | 15304.815 | 6197.427 | 0 | 0 | 0 | 21502.242 | 21502.242
|  | Reactive |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Lines and towers |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Establishment |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Communications |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Non System |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Land |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Easements |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Total incl Overhead - As commissioned $ Mar 2017 |  | 0 | 0 | 0 | 0 | 15304.815 | 6197.427 | 0 | 0 | 0 | 21502.242 | 21502.242
|  |  | Check | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0
| Expenditure splits for RIN |  |  |  | 2015-16 | 2016-17 | 2017-18 | 2018-19 | 2019-20 | 2020-21 | 2021-22 | 2022-23
| Repex Category | Transmission Towers | bar: 2015-16 to 2022-23
Transmission Tower Support Structures | bar: 2015-16 to 2022-23
Conductors | bar: 2015-16 to 2022-23
Transmission Cables | bar: 2015-16 to 2022-23
Substation Switchbays | bar: 2015-16 to 2022-23
|  | Substation Power Transformers |  |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
Substation Reactive Plant | bar: 2015-16 to 2022-23
Scada Network Control And Protection Systems | bar: 2015-16 to 2022-23
Other | bar: 2015-16 to 2022-23
|  | Total |  |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
| Direct Expenditures | Materials - $ Mar 2017 |  |  | 2015-16 | 2016-17 | 2017-18 | 2018-19 | 2019-20 | 2020-21 | 2021-22 | 2022-23 | Total | 2017-22 Total
| (As Incurred) | Transmission Towers |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Transmission Tower Support Structures |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Conductors |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Transmission Cables |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Substation Switchbays |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Substation Power Transformers |  |  | 0 | 0 | 2061.4104 | 3488.4481 | 2219.703 | 0 | 0 | 0 | 7769.5615 | 7769.5615
|  | Substation Reactive Plant |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Scada Network Control And Protection Systems |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Other |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Total Materials |  |  | 0 | 0 | 2061.4104 | 3488.4481 | 2219.703 | 0 | 0 | 0 | 7769.5615 | 7769.5615
|  | Labour (Internal) - $ Mar 2017 |  |  | 2015-16 | 2016-17 | 2017-18 | 2018-19 | 2019-20 | 2020-21 | 2021-22 | 2022-23 | Total | 2017-22 Total
|  | Transmission Towers |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Transmission Tower Support Structures |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Conductors |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Transmission Cables |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Substation Switchbays |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Substation Power Transformers |  |  | 0 | 0 | 526.0021 | 897.3439 | 575.7057 | 0 | 0 | 0 | 1999.0517 | 1999.0517
|  | Substation Reactive Plant |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Scada Network Control And Protection Systems |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Other |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Total Internal Labour |  |  | 0 | 0 | 526.0021 | 897.3439 | 575.7057 | 0 | 0 | 0 | 1999.0517 | 1999.0517
|  | Labour (External) - $ Mar 2017 |  |  | 2015-16 | 2016-17 | 2017-18 | 2018-19 | 2019-20 | 2020-21 | 2021-22 | 2022-23 | Total | 2017-22 Total
|  | Transmission Towers |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Transmission Tower Support Structures |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Conductors |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Transmission Cables |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Substation Switchbays |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Substation Power Transformers |  |  | 0 | 0 | 2631.4901 | 4499.5972 | 2891.9438 | 0 | 0 | 0 | 10023.0311 | 10023.0311
|  | Substation Reactive Plant |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Scada Network Control And Protection Systems |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Other |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Total External Labour |  |  | 0 | 0 | 2631.4901 | 4499.5972 | 2891.9438 | 0 | 0 | 0 | 10023.0311 | 10023.0311
|  | Total Direct - $ Mar 2017 |  |  | 2015-16 | 2016-17 | 2017-18 | 2018-19 | 2019-20 | 2020-21 | 2021-22 | 2022-23 | Total | 2017-22 Total
|  | Transmission Towers |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Transmission Tower Support Structures |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Conductors |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Transmission Cables |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Substation Switchbays |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Substation Power Transformers |  |  | 0 | 0 | 5218.9026 | 8885.3893 | 5687.3524 | 0 | 0 | 0 | 19791.6443 | 19791.6443
|  | Substation Reactive Plant |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Scada Network Control And Protection Systems |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Other |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Total Direct - $ Mar 2017 |  |  | 0 | 0 | 5218.9026 | 8885.3893 | 5687.3524 | 0 | 0 | 0 | 19791.6443 | 19791.6443

## Proj_43
Go To: | Table of Contents
Master Inputs
|  |  |  | Business case? | 0
| Project name | Buildings & Property
| Project category 1 | Non Network |  |  | Shaded cells = Inputs
| Project category 2 | Non Network - Premises
| Regulatory classification | Prescribed
| Overhead Category | Non_IT_OHD |  | $000's | $000's | $000's | $000's | $000's | $000's | $000's | $000's | $000's | Project | 2017-22
|  |  |  | Prior | 2015-16 | 2016-17 | 2017-18 | 2018-19 | 2019-20 | 2020-21 | 2021-22 | 2022-23 | Total | Total | Check
| Project timing | Direct Expenditure (As incurred) - $ 2015/16 |  | 131.3762 | 0 | 517.7863 | 213 | 574.9 | 91.75 | 201.53 | 979.33 | 0 | 2709.6725 | 2060.51 | ok
| (excluding real cost escalators) | Assumed year commissioned (no BC) |  | x | bar: 2015-16 to 2022-23
|  | Direct Expenditure (As Commissioned) - $ 2015/16 |  | 131.3762 | 0 | 517.7863 | 213 | 574.9 | 91.75 | 201.53 | 979.33 | 0 | 2709.6725 | 2060.51 | ok
| Asset class | Secondary
Switchgear
Transformers
Reactive
Lines and towers
Establishment
Communications
|  | Non System |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
Land
Easements
|  |  | Total | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
| Input costs % | Labour - internal |  | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10%
|  | Labour - external |  | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50%
|  | Materials |  | 40% | 40% | 40% | 40% | 40% | 40% | 40% | 40% | 40%
|  |  | Total | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
Material Escalation
| (By Asset Class) | Secondary |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Switchgear |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Transformers |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Reactive |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Lines and towers |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Establishment |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Communications |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Non System |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Land |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Easements |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Total Material escalation |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Labour Escalation | Internal Labour |  | 0 | 0 | 0.64795 | 0.44015 | 1.6633 | 0.34357 | 0.94178 | 5.5094 | 0 | 9.5461 | 8.8982
|  | External Labour |  | 0 | 0 | 2.7837 | 2.2619 | 9.1654 | 1.9397 | 5.4053 | 32.0194 | 0 | 53.5752 | 50.7916
|  | Total Labour Escalation |  | 0 | 0 | 3.4316 | 2.7021 | 10.8287 | 2.2832 | 6.347 | 37.5288 | 0 | 63.1214 | 59.6898
|  | Total Escalation |  | 0 | 0 | 3.4316 | 2.7021 | 10.8287 | 2.2832 | 6.347 | 37.5288 | 0 | 63.1214 | 59.6898
|  | Escalation factors |  | 0 | 0 | 0.0066275 | 0.012686 | 0.018836 | 0.024885 | 0.031494 | 0.038321 | 0 | 0.023295 | 0.028968
| Direct Expenditure (Escalated) | Total labour - internal |  | 13.3599 | 0 | 53.3135 | 22.1079 | 60.154 | 9.6796 | 21.4516 | 105.1924 | 0 | 285.2589 | 218.5855
| (as incurred) | Total labour - external |  | 66.7994 | 0 | 266.1037 | 110.6019 | 301.6333 | 48.6236 | 107.9664 | 530.5099 | 0 | 1432.238 | 1099.335
|  | Total materials |  | 53.4395 | 0 | 210.6183 | 86.6414 | 233.8503 | 37.3209 | 81.9757 | 398.359 | 0 | 1102.2051 | 838.1473
|  | Total Direct - As Incurred $ Mar 2017 |  | 133.5988 | 0 | 530.0355 | 219.3512 | 595.6376 | 95.624 | 211.3938 | 1034.0613 | 0 | 2819.702 | 2156.0678 | ok
| Capitalised Overheads | Overhead rate (applied to direct expenditure) |  | 0% | bar: 2015-16 to 2022-23
|  | Total overhead (as incurred) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Total incl Overhead - As Incurred $ Mar 2017 |  | 133.5988 | 0 | 530.0355 | 219.3512 | 595.6376 | 95.624 | 211.3938 | 1034.0613 | 0 | 2819.702 | 2156.0678
|  | Total overheads (As incurred) - Cumulative |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Labour & Material Escalation - Cumulative |  | 0 | 0 | 3.4316 | 6.1337 | 16.9624 | 19.2456 | 25.5926 | 63.1214 | 63.1214
Expenditure By Asset Class - As Incurred
| Asset class breakdown | Secondary |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| (fully absorbed) | Switchgear |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| (as incurred) | Transformers |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Reactive |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Lines and towers |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Establishment |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Communications |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Non System |  | 133.5988 | 0 | 530.0355 | 219.3512 | 595.6376 | 95.624 | 211.3938 | 1034.0613 | 0 | 2819.702 | 2156.0678
|  | Land |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Easements |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Total incl Overhead - As Incurred $ Mar 2017 |  | 133.5988 | 0 | 530.0355 | 219.3512 | 595.6376 | 95.624 | 211.3938 | 1034.0613 | 0 | 2819.702 | 2156.0678
|  |  | Check | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| As Commissioned Capex | Direct Expenditure (As Commissioned) - $ 2015/16 |  | 131.3762 | 0 | 517.7863 | 213 | 574.9 | 91.75 | 201.53 | 979.33 | 0 | 2709.6725 | 2060.51
|  | Labour & Material Escalation - $ 2015/16 |  | 0 | 0 | 3.4316 | 2.7021 | 10.8287 | 2.2832 | 6.347 | 37.5288 | 0 | 63.1214 | 59.6898
|  | Total Direct Expenditure - $ 2015/16 |  | 131.3762 | 0 | 521.2179 | 215.7021 | 585.7287 | 94.0332 | 207.877 | 1016.8588 | 0 | 2772.7939 | 2120.1998
|  | Total Direct Expenditure - $ Mar 2017 |  | 133.5988 | 0 | 530.0355 | 219.3512 | 595.6376 | 95.624 | 211.3938 | 1034.0613 | 0 | 2819.702 | 2156.0678
|  | Total overheads (As Commissioned) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Total incl Overhead - As commissioned $ Mar 2017 |  | 133.5988 | 0 | 530.0355 | 219.3512 | 595.6376 | 95.624 | 211.3938 | 1034.0613 | 0 | 2819.702 | 2156.0678
|  | Total overheads (As Comm) - Cumulative |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Total real cost escalation (As Comm) - Cumulative |  | 0 | 0 | 3.4316 | 6.1337 | 16.9624 | 19.2456 | 25.5926 | 63.1214 | 63.1214
Expenditure By Asset Class - As Commissioned
| Asset class breakdown | Secondary |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| (fully absorbed) | Switchgear |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| (as commissioned) | Transformers |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Reactive |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Lines and towers |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Establishment |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Communications |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Non System |  | 133.5988 | 0 | 530.0355 | 219.3512 | 595.6376 | 95.624 | 211.3938 | 1034.0613 | 0 | 2819.702 | 2156.0678
|  | Land |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Easements |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Total incl Overhead - As commissioned $ Mar 2017 |  | 133.5988 | 0 | 530.0355 | 219.3512 | 595.6376 | 95.624 | 211.3938 | 1034.0613 | 0 | 2819.702 | 2156.0678
|  |  | Check | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0

## Proj_44
Go To: | Table of Contents
Master Inputs
|  |  |  | Business case? | 0
| Project name | Non Network - Other
| Project category 1 | Non Network |  |  | Shaded cells = Inputs
| Project category 2 | Non Network - Other
| Regulatory classification | Prescribed
| Overhead Category | Non_IT_OHD |  | $000's | $000's | $000's | $000's | $000's | $000's | $000's | $000's | $000's | Project | 2017-22
|  |  |  | Prior | 2015-16 | 2016-17 | 2017-18 | 2018-19 | 2019-20 | 2020-21 | 2021-22 | 2022-23 | Total | Total | Check
| Project timing | Direct Expenditure (As incurred) - $ 2015/16 |  | 2153.2519 | 1549.7952 | 2527.7625 | 2838.704 | 2838.704 | 2838.704 | 2838.704 | 2838.704 | 0 | 20424.3294 | 14193.5199 | ok
| (excluding real cost escalators) | Assumed year commissioned (no BC) |  | x | bar: 2015-16 to 2022-23
|  | Direct Expenditure (As Commissioned) - $ 2015/16 |  | 2153.2519 | 1549.7952 | 2527.7625 | 2838.704 | 2838.704 | 2838.704 | 2838.704 | 2838.704 | 0 | 20424.3294 | 14193.5199 | ok
| Asset class | Secondary
Switchgear
Transformers
Reactive
Lines and towers
Establishment
Communications
|  | Non System |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
Land
Easements
|  |  | Total | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
| Input costs % | Labour - internal |  | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10%
|  | Labour - external |  | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50%
|  | Materials |  | 40% | 40% | 40% | 40% | 40% | 40% | 40% | 40% | 40%
|  |  | Total | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
Material Escalation
| (By Asset Class) | Secondary |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Switchgear |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Transformers |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Reactive |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Lines and towers |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Establishment |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Communications |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Non System |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Land |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Easements |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Total Material escalation |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Labour Escalation | Internal Labour |  | 0 | 0 | 3.1632 | 5.866 | 8.2129 | 10.6299 | 13.2657 | 15.9696 | 0 | 57.1073 | 53.9441
|  | External Labour |  | 0 | 0 | 13.5895 | 30.1452 | 45.2562 | 60.0122 | 76.1372 | 92.8119 | 0 | 317.9522 | 304.3627
|  | Total Labour Escalation |  | 0 | 0 | 16.7526 | 36.0113 | 53.4691 | 70.642 | 89.4029 | 108.7815 | 0 | 375.0595 | 358.3069
|  | Total Escalation |  | 0 | 0 | 16.7526 | 36.0113 | 53.4691 | 70.642 | 89.4029 | 108.7815 | 0 | 375.0595 | 358.3069
|  | Escalation factors |  | 0 | 0 | 0.0066275 | 0.012686 | 0.018836 | 0.024885 | 0.031494 | 0.038321 | 0 | 0.018363 | 0.025244
| Direct Expenditure (Escalated) | Total labour - internal |  | 218.9679 | 157.6013 | 260.2692 | 294.638 | 297.0246 | 299.4824 | 302.1628 | 304.9125 | 0 | 2135.0588 | 1498.2203
| (as incurred) | Total labour - external |  | 1094.8395 | 788.0067 | 1299.082 | 1474.0188 | 1489.3854 | 1504.391 | 1520.7888 | 1537.7456 | 0 | 10708.258 | 7526.3296
|  | Total materials |  | 875.8716 | 630.4054 | 1028.2102 | 1154.6909 | 1154.6909 | 1154.6909 | 1154.6909 | 1154.6909 | 0 | 8307.9415 | 5773.4543
|  | Total Direct - As Incurred $ Mar 2017 |  | 2189.6791 | 1576.0135 | 2587.5614 | 2923.3476 | 2941.1008 | 2958.5643 | 2977.6425 | 2997.349 | 0 | 21151.2583 | 14798.0043 | ok
| Capitalised Overheads | Overhead rate (applied to direct expenditure) |  | 0% | bar: 2015-16 to 2022-23
|  | Total overhead (as incurred) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Total incl Overhead - As Incurred $ Mar 2017 |  | 2189.6791 | 1576.0135 | 2587.5614 | 2923.3476 | 2941.1008 | 2958.5643 | 2977.6425 | 2997.349 | 0 | 21151.2583 | 14798.0043
|  | Total overheads (As incurred) - Cumulative |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Labour & Material Escalation - Cumulative |  | 0 | 0 | 16.7526 | 52.7639 | 106.233 | 176.8751 | 266.278 | 375.0595 | 375.0595
Expenditure By Asset Class - As Incurred
| Asset class breakdown | Secondary |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| (fully absorbed) | Switchgear |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| (as incurred) | Transformers |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Reactive |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Lines and towers |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Establishment |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Communications |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Non System |  | 2189.6791 | 1576.0135 | 2587.5614 | 2923.3476 | 2941.1008 | 2958.5643 | 2977.6425 | 2997.349 | 0 | 21151.2583 | 14798.0043
|  | Land |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Easements |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Total incl Overhead - As Incurred $ Mar 2017 |  | 2189.6791 | 1576.0135 | 2587.5614 | 2923.3476 | 2941.1008 | 2958.5643 | 2977.6425 | 2997.349 | 0 | 21151.2583 | 14798.0043
|  |  | Check | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| As Commissioned Capex | Direct Expenditure (As Commissioned) - $ 2015/16 |  | 2153.2519 | 1549.7952 | 2527.7625 | 2838.704 | 2838.704 | 2838.704 | 2838.704 | 2838.704 | 0 | 20424.3294 | 14193.5199
|  | Labour & Material Escalation - $ 2015/16 |  | 0 | 0 | 16.7526 | 36.0113 | 53.4691 | 70.642 | 89.4029 | 108.7815 | 0 | 375.0595 | 358.3069
|  | Total Direct Expenditure - $ 2015/16 |  | 2153.2519 | 1549.7952 | 2544.5151 | 2874.7152 | 2892.1731 | 2909.346 | 2928.1069 | 2947.4855 | 0 | 20799.3889 | 14551.8268
|  | Total Direct Expenditure - $ Mar 2017 |  | 2189.6791 | 1576.0135 | 2587.5614 | 2923.3476 | 2941.1008 | 2958.5643 | 2977.6425 | 2997.349 | 0 | 21151.2583 | 14798.0043
|  | Total overheads (As Commissioned) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Total incl Overhead - As commissioned $ Mar 2017 |  | 2189.6791 | 1576.0135 | 2587.5614 | 2923.3476 | 2941.1008 | 2958.5643 | 2977.6425 | 2997.349 | 0 | 21151.2583 | 14798.0043
|  | Total overheads (As Comm) - Cumulative |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Total real cost escalation (As Comm) - Cumulative |  | 0 | 0 | 16.7526 | 52.7639 | 106.233 | 176.8751 | 266.278 | 375.0595 | 375.0595
Expenditure By Asset Class - As Commissioned
| Asset class breakdown | Secondary |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| (fully absorbed) | Switchgear |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| (as commissioned) | Transformers |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Reactive |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Lines and towers |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Establishment |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Communications |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Non System |  | 2189.6791 | 1576.0135 | 2587.5614 | 2923.3476 | 2941.1008 | 2958.5643 | 2977.6425 | 2997.349 | 0 | 21151.2583 | 14798.0043
|  | Land |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Easements |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Total incl Overhead - As commissioned $ Mar 2017 |  | 2189.6791 | 1576.0135 | 2587.5614 | 2923.3476 | 2941.1008 | 2958.5643 | 2977.6425 | 2997.349 | 0 | 21151.2583 | 14798.0043
|  |  | Check | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0

## Proj_45
Go To: | Table of Contents
Master Inputs
|  |  |  | Business case? | 0
| Project name | IT Strategy
| Project category 1 | Non Network |  |  | Shaded cells = Inputs
| Project category 2 | Non Network - IT
| Regulatory classification | Prescribed
| Overhead Category | IT_OHD |  | $000's | $000's | $000's | $000's | $000's | $000's | $000's | $000's | $000's | Project | 2017-22
|  |  |  | Prior | 2015-16 | 2016-17 | 2017-18 | 2018-19 | 2019-20 | 2020-21 | 2021-22 | 2022-23 | Total | Total | Check
| Project timing | Direct Expenditure (As incurred) - $ 2015/16 |  | 30117.3368 | 7878.0357 | 17538.2019 | 23279.633 | 21004.214 | 12452.477 | 10346.502 | 8754.113 | 0 | 131370.5134 | 75836.939 | ok
| (excluding real cost escalators) | Assumed year commissioned (no BC) |  | X | bar: 2015-16 to 2022-23
|  | Direct Expenditure (As Commissioned) - $ 2015/16 |  | 6264.4346 | 31730.9379 | 17538.2019 | 23279.633 | 21004.214 | 12452.477 | 10346.502 | 8754.113 | 0 | 131370.5134 | 75836.939 | ok
| Asset class | Secondary
Switchgear
Transformers
Reactive
Lines and towers
Establishment
Communications
|  | Non System |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
Land
Easements
|  |  | Total | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
| Input costs % | Labour - internal |  | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10%
|  | Labour - external |  | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50%
|  | Materials |  | 40% | 40% | 40% | 40% | 40% | 40% | 40% | 40% | 40%
|  |  | Total | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
Material Escalation
| (By Asset Class) | Secondary |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Switchgear |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Transformers |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Reactive |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Lines and towers |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Establishment |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Communications |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Non System |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Land |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Easements |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Total Material escalation |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Labour Escalation | Internal Labour |  | 0 | 0 | 21.9469 | 48.1062 | 60.7692 | 46.6299 | 48.3507 | 49.2478 | 0 | 275.0507 | 253.1038
|  | External Labour |  | 0 | 0 | 94.2868 | 247.2148 | 334.861 | 263.2539 | 277.5048 | 286.2173 | 0 | 1503.3385 | 1409.0517
|  | Total Labour Escalation |  | 0 | 0 | 116.2337 | 295.321 | 395.6302 | 309.8838 | 325.8555 | 335.465 | 0 | 1778.3892 | 1662.1555
|  | Total Escalation |  | 0 | 0 | 116.2337 | 295.321 | 395.6302 | 309.8838 | 325.8555 | 335.465 | 0 | 1778.3892 | 1662.1555
|  | Escalation factors |  | 0 | 0 | 0.0066275 | 0.012686 | 0.018836 | 0.024885 | 0.031494 | 0.038321 | 0 | 0.013537 | 0.021917
| Direct Expenditure (Escalated) | Total labour - internal |  | 3062.6841 | 801.1311 | 1805.8083 | 2416.2662 | 2197.7521 | 1313.7327 | 1101.3223 | 940.3018 | 0 | 13638.9985 | 7969.3751
| (as incurred) | Total labour - external |  | 15313.4203 | 4005.6554 | 9013.3323 | 12088.1277 | 11020.3002 | 6599.2771 | 5542.9678 | 4742.1637 | 0 | 68325.2444 | 39992.8364
|  | Total materials |  | 12250.7362 | 3204.5243 | 7133.9603 | 9469.3846 | 8543.8194 | 5065.2557 | 4208.6147 | 3560.8836 | 0 | 53437.1788 | 30847.9579
|  | Total Direct - As Incurred $ Mar 2017 |  | 30626.8406 | 8011.3108 | 17953.1009 | 23973.7784 | 21761.8717 | 12978.2654 | 10852.9049 | 9243.3491 | 0 | 135401.4217 | 78810.1694 | ok
| Capitalised Overheads | Overhead rate (applied to direct expenditure) |  | 4.88% | 10.6% | 8.752% | 6.367% | 6.177% | 9.075% | 7.593% | 7.593% | 7.361%
|  | Total overhead (as incurred) |  | 1494.5393 | 849.1962 | 1571.2419 | 1526.3528 | 1344.2263 | 1177.7394 | 824.0168 | 701.8098 | 0 | 9489.1225 | 5574.1451
|  | Total incl Overhead - As Incurred $ Mar 2017 |  | 32121.3799 | 8860.507 | 19524.3428 | 25500.1312 | 23106.0979 | 14156.0048 | 11676.9217 | 9945.1589 | 0 | 144890.5442 | 84384.3145
|  | Total overheads (As incurred) - Cumulative |  | 1494.5393 | 2343.7355 | 3914.9774 | 5441.3303 | 6785.5565 | 7963.2959 | 8787.3127 | 9489.1225 | 9489.1225
|  | Labour & Material Escalation - Cumulative |  | 0 | 0 | 116.2337 | 411.5547 | 807.1849 | 1117.0687 | 1442.9242 | 1778.3892 | 1778.3892
Expenditure By Asset Class - As Incurred
| Asset class breakdown | Secondary |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| (fully absorbed) | Switchgear |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| (as incurred) | Transformers |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Reactive |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Lines and towers |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Establishment |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Communications |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Non System |  | 32121.3799 | 8860.507 | 19524.3428 | 25500.1312 | 23106.0979 | 14156.0048 | 11676.9217 | 9945.1589 | 0 | 144890.5442 | 84384.3145
|  | Land |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Easements |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Total incl Overhead - As Incurred $ Mar 2017 |  | 32121.3799 | 8860.507 | 19524.3428 | 25500.1312 | 23106.0979 | 14156.0048 | 11676.9217 | 9945.1589 | 0 | 144890.5442 | 84384.3145
|  |  | Check | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| As Commissioned Capex | Direct Expenditure (As Commissioned) - $ 2015/16 |  | 6264.4346 | 31730.9379 | 17538.2019 | 23279.633 | 21004.214 | 12452.477 | 10346.502 | 8754.113 | 0 | 131370.5134 | 75836.939
|  | Labour & Material Escalation - $ 2015/16 |  | 0 | 0 | 116.2337 | 295.321 | 395.6302 | 309.8838 | 325.8555 | 335.465 | 0 | 1778.3892 | 1662.1555
|  | Total Direct Expenditure - $ 2015/16 |  | 6264.4346 | 31730.9379 | 17654.4356 | 23574.954 | 21399.8442 | 12762.3608 | 10672.3575 | 9089.578 | 0 | 133148.9027 | 77499.0945
|  | Total Direct Expenditure - $ Mar 2017 |  | 6370.4119 | 32267.7395 | 17953.1009 | 23973.7784 | 21761.8717 | 12978.2654 | 10852.9049 | 9243.3491 | 0 | 135401.4217 | 78810.1694
|  | Total overheads (As Commissioned) |  | 310.8656 | 2032.8699 | 1571.2419 | 1526.3528 | 1344.2263 | 1177.7394 | 824.0168 | 701.8098 | 0 | 9489.1225 | 5574.1451
|  | Total incl Overhead - As commissioned $ Mar 2017 |  | 6681.2775 | 34300.6094 | 19524.3428 | 25500.1312 | 23106.0979 | 14156.0048 | 11676.9217 | 9945.1589 | 0 | 144890.5442 | 84384.3145
|  | Total overheads (As Comm) - Cumulative |  | 310.8656 | 2343.7355 | 3914.9774 | 5441.3303 | 6785.5565 | 7963.2959 | 8787.3127 | 9489.1225 | 9489.1225
|  | Total real cost escalation (As Comm) - Cumulative |  | 0 | 0 | 116.2337 | 411.5547 | 807.1849 | 1117.0687 | 1442.9242 | 1778.3892 | 1778.3892
Expenditure By Asset Class - As Commissioned
| Asset class breakdown | Secondary |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| (fully absorbed) | Switchgear |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| (as commissioned) | Transformers |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Reactive |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Lines and towers |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Establishment |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Communications |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Non System |  | 6681.2775 | 34300.6094 | 19524.3428 | 25500.1312 | 23106.0979 | 14156.0048 | 11676.9217 | 9945.1589 | 0 | 144890.5442 | 84384.3145
|  | Land |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Easements |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Total incl Overhead - As commissioned $ Mar 2017 |  | 6681.2775 | 34300.6094 | 19524.3428 | 25500.1312 | 23106.0979 | 14156.0048 | 11676.9217 | 9945.1589 | 0 | 144890.5442 | 84384.3145
|  |  | Check | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0

## Proj_46
Go To: | Table of Contents
Master Inputs
|  |  |  | Business case? | 0
| Project name | Motor Vehicles
| Project category 1 | Non Network |  |  | Shaded cells = Inputs
| Project category 2 | Non Network - Vehicles
| Regulatory classification | Prescribed
| Overhead Category | Non_IT_OHD |  | $000's | $000's | $000's | $000's | $000's | $000's | $000's | $000's | $000's | Project | 2017-22
|  |  |  | Prior | 2015-16 | 2016-17 | 2017-18 | 2018-19 | 2019-20 | 2020-21 | 2021-22 | 2022-23 | Total | Total | Check
| Project timing | Direct Expenditure (As incurred) - $ 2015/16 |  | 792.9599 | 670.1585 | 872.8106 | 1867.8901 | 1465.7382 | 2021.3429 | 1697.5047 | 1697.5047 | 0 | 11085.9096 | 8749.9806 | ok
| (excluding real cost escalators) | Assumed year commissioned (no BC) |  | x | bar: 2015-16 to 2022-23
|  | Direct Expenditure (As Commissioned) - $ 2015/16 |  | 792.9599 | 670.1585 | 872.8106 | 1867.8901 | 1465.7382 | 2021.3429 | 1697.5047 | 1697.5047 | 0 | 11085.9096 | 8749.9806 | ok
| Asset class | Secondary
Switchgear
Transformers
Reactive
Lines and towers
Establishment
Communications
|  | Non System |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
Land
Easements
|  |  | Total | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
| Input costs % | Labour - internal |  | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10%
|  | Labour - external |  | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50%
|  | Materials |  | 40% | 40% | 40% | 40% | 40% | 40% | 40% | 40% | 40%
|  |  | Total | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
Material Escalation
| (By Asset Class) | Secondary |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Switchgear |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Transformers |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Reactive |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Lines and towers |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Establishment |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Communications |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Non System |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Land |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Easements |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Total Material escalation |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Labour Escalation | Internal Labour |  | 0 | 0 | 1.0922 | 3.8599 | 4.2407 | 7.5692 | 7.9327 | 9.5496 | 0 | 34.2442 | 33.152
|  | External Labour |  | 0 | 0 | 4.6923 | 19.8358 | 23.3676 | 42.7326 | 45.529 | 55.5002 | 0 | 191.6575 | 186.9652
|  | Total Labour Escalation |  | 0 | 0 | 5.7845 | 23.6957 | 27.6083 | 50.3018 | 53.4617 | 65.0498 | 0 | 225.9017 | 220.1172
|  | Total Escalation |  | 0 | 0 | 5.7845 | 23.6957 | 27.6083 | 50.3018 | 53.4617 | 65.0498 | 0 | 225.9017 | 220.1172
|  | Escalation factors |  | 0 | 0 | 0.0066275 | 0.012686 | 0.018836 | 0.024885 | 0.031494 | 0.038321 | 0 | 0.020377 | 0.025156
| Direct Expenditure (Escalated) | Total labour - internal |  | 80.6375 | 68.1496 | 89.8683 | 193.8742 | 153.3658 | 213.2511 | 180.6891 | 182.3333 | 0 | 1162.1689 | 923.5135
| (as incurred) | Total labour - external |  | 403.1873 | 340.7479 | 448.5598 | 969.9163 | 769.0302 | 1071.2248 | 909.4101 | 919.5501 | 0 | 5831.6264 | 4639.1314
|  | Total materials |  | 322.5498 | 272.5983 | 355.0305 | 759.7959 | 596.2138 | 822.2154 | 690.4888 | 690.4888 | 0 | 4509.3813 | 3559.2026
|  | Total Direct - As Incurred $ Mar 2017 |  | 806.3746 | 681.4958 | 893.4586 | 1923.5864 | 1518.6098 | 2106.6913 | 1780.588 | 1792.3722 | 0 | 11503.1765 | 9121.8476 | ok
| Capitalised Overheads | Overhead rate (applied to direct expenditure) |  | 0% | bar: 2015-16 to 2022-23
|  | Total overhead (as incurred) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Total incl Overhead - As Incurred $ Mar 2017 |  | 806.3746 | 681.4958 | 893.4586 | 1923.5864 | 1518.6098 | 2106.6913 | 1780.588 | 1792.3722 | 0 | 11503.1765 | 9121.8476
|  | Total overheads (As incurred) - Cumulative |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Labour & Material Escalation - Cumulative |  | 0 | 0 | 5.7845 | 29.4802 | 57.0885 | 107.3903 | 160.8519 | 225.9017 | 225.9017
Expenditure By Asset Class - As Incurred
| Asset class breakdown | Secondary |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| (fully absorbed) | Switchgear |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| (as incurred) | Transformers |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Reactive |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Lines and towers |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Establishment |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Communications |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Non System |  | 806.3746 | 681.4958 | 893.4586 | 1923.5864 | 1518.6098 | 2106.6913 | 1780.588 | 1792.3722 | 0 | 11503.1765 | 9121.8476
|  | Land |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Easements |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Total incl Overhead - As Incurred $ Mar 2017 |  | 806.3746 | 681.4958 | 893.4586 | 1923.5864 | 1518.6098 | 2106.6913 | 1780.588 | 1792.3722 | 0 | 11503.1765 | 9121.8476
|  |  | Check | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| As Commissioned Capex | Direct Expenditure (As Commissioned) - $ 2015/16 |  | 792.9599 | 670.1585 | 872.8106 | 1867.8901 | 1465.7382 | 2021.3429 | 1697.5047 | 1697.5047 | 0 | 11085.9096 | 8749.9806
|  | Labour & Material Escalation - $ 2015/16 |  | 0 | 0 | 5.7845 | 23.6957 | 27.6083 | 50.3018 | 53.4617 | 65.0498 | 0 | 225.9017 | 220.1172
|  | Total Direct Expenditure - $ 2015/16 |  | 792.9599 | 670.1585 | 878.5951 | 1891.5858 | 1493.3464 | 2071.6446 | 1750.9664 | 1762.5545 | 0 | 11311.8113 | 8970.0978
|  | Total Direct Expenditure - $ Mar 2017 |  | 806.3746 | 681.4958 | 893.4586 | 1923.5864 | 1518.6098 | 2106.6913 | 1780.588 | 1792.3722 | 0 | 11503.1765 | 9121.8476
|  | Total overheads (As Commissioned) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Total incl Overhead - As commissioned $ Mar 2017 |  | 806.3746 | 681.4958 | 893.4586 | 1923.5864 | 1518.6098 | 2106.6913 | 1780.588 | 1792.3722 | 0 | 11503.1765 | 9121.8476
|  | Total overheads (As Comm) - Cumulative |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Total real cost escalation (As Comm) - Cumulative |  | 0 | 0 | 5.7845 | 29.4802 | 57.0885 | 107.3903 | 160.8519 | 225.9017 | 225.9017
Expenditure By Asset Class - As Commissioned
| Asset class breakdown | Secondary |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| (fully absorbed) | Switchgear |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| (as commissioned) | Transformers |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Reactive |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Lines and towers |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Establishment |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Communications |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Non System |  | 806.3746 | 681.4958 | 893.4586 | 1923.5864 | 1518.6098 | 2106.6913 | 1780.588 | 1792.3722 | 0 | 11503.1765 | 9121.8476
|  | Land |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Easements |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Total incl Overhead - As commissioned $ Mar 2017 |  | 806.3746 | 681.4958 | 893.4586 | 1923.5864 | 1518.6098 | 2106.6913 | 1780.588 | 1792.3722 | 0 | 11503.1765 | 9121.8476
|  |  | Check | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0

## Outputs-->
Table of Contents
Outputs Section

## 5.1(a)_Direct_Fcast
Table of Contents
As Incurred Capex - Direct Cost Forecast Summary (Real March 2017)
[10 empty] | Efficiency factor --> |  | 0.89%
As Incurred - $000's, $ Mar 2017 | [8 empty] | As Incurred - $000's, $ Mar 2017
(Including real costs escalators, excluding Efficiency factors) | [8 empty] | (Including real cost escalators and Efficiency factors)
Total - All Categories | 2015-16 | 2016-17 | 2017-18 | 2018-19 | 2019-20 | 2020-21 | 2021-22 | Total | Total - All Categories | 2015-16 | 2016-17 | 2017-18 | 2018-19 | 2019-20 | 2020-21 | 2021-22 | Total
|  |  | Y1 | Y2 | Y3 | Y4 | Y5 | 2017-22 |  |  |  | Y1 | Y2 | Y3 | Y4 | Y5 | 2017-22
Total labour - internal | 13294.9011 | 16496.1447 | 17162.7493 | 15200.7253 | 14539.5248 | 13067.8554 | 11134.9156 | 71105.7705 | Total labour - internal | 13294.9011 | 16496.1447 | 17010.0009 | 15065.4389 | 14410.123 | 12951.5515 | 11035.8149 | 70472.9291
Total labour - external | 66474.5054 | 82337.22 | 85862.0237 | 76221.7719 | 73036.4348 | 65770.6638 | 56156.0063 | 357046.9006 | Total labour - external | 66474.5054 | 82337.22 | 85097.8517 | 75543.3982 | 72386.4105 | 65185.3049 | 55656.2178 | 353869.1831
Total materials | 53179.6043 | 65169.0676 | 67261.08 | 59093.2225 | 56058.9006 | 49937.7579 | 42167.46 | 274518.421 | Total materials | 53179.6043 | 65169.0676 | 66662.4564 | 58567.2928 | 55559.9764 | 49493.3118 | 41792.1696 | 272075.207
Total Direct - $Mar 2017 | 132949.0107 | 164002.4322 | 170285.8531 | 150515.7197 | 143634.8602 | 128776.2771 | 109458.3819 | 702671.092 | Total Direct - $Mar 2017 | 132949.0107 | 164002.4322 | 168770.309 | 149176.1298 | 142356.5099 | 127630.1683 | 108484.2023 | 696417.3193
IT & Non System | 2015-16 | 2016-17 | 2017-18 | 2018-19 | 2019-20 | 2020-21 | 2021-22 | Total | IT & Non System | 2015-16 | 2016-17 | 2017-18 | 2018-19 | 2019-20 | 2020-21 | 2021-22 | Total
|  |  | Y1 | Y2 | Y3 | Y4 | Y5 | 2017-22 |  |  |  | Y1 | Y2 | Y3 | Y4 | Y5 | 2017-22
Total labour - internal | 1026.882 | 2209.2593 | 2926.8863 | 2708.2965 | 1836.1458 | 1605.6259 | 1532.74 | 10609.6945 | Total labour - internal | 1026.882 | 2209.2593 | 2900.837 | 2684.1926 | 1819.8041 | 1591.3358 | 1519.0986 | 10515.2682
Total labour - external | 5134.41 | 11027.0778 | 14642.6646 | 13580.3491 | 9223.5163 | 8081.1332 | 7729.9693 | 53257.6325 | Total labour - external | 5134.41 | 11027.0778 | 14512.3448 | 13459.484 | 9141.427 | 8009.2111 | 7661.1726 | 52783.6395
Total materials | 4107.528 | 8727.8193 | 11470.5127 | 10528.5743 | 7079.4828 | 6135.7701 | 5804.4222 | 41018.7621 | Total materials | 4107.528 | 8727.8193 | 11368.4251 | 10434.87 | 7016.4754 | 6081.1617 | 5752.7629 | 40653.6952
Total Direct - $Mar 2017 | 10268.82 | 21964.1564 | 29040.0636 | 26817.2199 | 18139.145 | 15822.5291 | 15067.1315 | 104886.0891 | Total Direct - $Mar 2017 | 10268.82 | 21964.1564 | 28781.607 | 26578.5467 | 17977.7066 | 15681.7086 | 14933.034 | 103952.6029
Network Replacement | 2015-16 | 2016-17 | 2017-18 | 2018-19 | 2019-20 | 2020-21 | 2021-22 | Total | Network Replacement | 2015-16 | 2016-17 | 2017-18 | 2018-19 | 2019-20 | 2020-21 | 2021-22 | Total
|  |  | Y1 | Y2 | Y3 | Y4 | Y5 | 2017-22 |  |  |  | Y1 | Y2 | Y3 | Y4 | Y5 | 2017-22
Total labour - internal | 12268.0191 | 14286.8853 | 14235.863 | 12492.4288 | 12703.379 | 11462.2295 | 9602.1756 | 60496.076 | Total labour - internal | 12268.0191 | 14286.8853 | 14109.1638 | 12381.2462 | 12590.3189 | 11360.2157 | 9516.7163 | 59957.661
Total labour - external | 61340.0953 | 71310.1422 | 71219.3592 | 62641.4228 | 63812.9184 | 57689.5307 | 48426.037 | 303789.2681 | Total labour - external | 61340.0953 | 71310.1422 | 70585.5069 | 62083.9141 | 63244.9835 | 57176.0938 | 47995.0453 | 301085.5436
Total materials | 49072.0763 | 56441.2483 | 55790.5673 | 48564.6481 | 48979.4178 | 43801.9878 | 36363.0378 | 233499.6588 | Total materials | 49072.0763 | 56441.2483 | 55294.0313 | 48132.4228 | 48543.5009 | 43412.1501 | 36039.4068 | 231421.5119
Total Direct - $Mar 2017 | 122680.1907 | 142038.2759 | 141245.7895 | 123698.4998 | 125495.7152 | 112953.748 | 94391.2504 | 597785.0029 | Total Direct - $Mar 2017 | 122680.1907 | 142038.2759 | 139988.702 | 122597.5831 | 124378.8033 | 111948.4596 | 93551.1683 | 592464.7164
Total Repex Direct - $2015/16 | 120639.3003 | 139675.347 | 138896.0444 | 121640.6689 | 123407.9861 | 111074.6653 | 92820.9708 | 587840.3356

## 5.1(b)_Total_Fcast
Table of Contents
Forecast Capex by Asset Class - As Incurred Capex (Total incl Overhead)
[10 empty] | Output for PTRM model | Efficiency factor --> |  | 0.89%
As Incurred - $000's, $ Mar 2017 | [9 empty] | As Incurred - $m, Mar 2017
(Before Efficiency factors are applied) |  |  | Forecast Period (Real Mar 2017) | [6 empty] | (Including Efficiency factors) |  |  | Forecast Period (Real Mar 2017)
| 2015-16 | 2016-17 | 2017-18 | 2018-19 | 2019-20 | 2020-21 | 2021-22 | 2022-23 | TOTAL |  | 2015-16 | 2016-17 | 2017-18 | 2018-19 | 2019-20 | 2020-21 | 2021-22 | 2022-23 | TOTAL
Asset class | Year -2 | Year -1 | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 | Year 6 |  | Asset class | Year -2 | Year -1 | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 | Year 6
Secondary | 26538.959 | 23662.1203 | 31648.3176 | 25756.1124 | 24251.2371 | 23247.425 | 22515.7507 | 0 | 127418.8429 | Secondary | 26.539 | 23.6621 | 31.3666 | 25.5269 | 24.0354 | 23.0405 | 22.3154 | 0 | 126.2848
Switchgear | 39181.5632 | 49908.7033 | 48334.4159 | 37542.1655 | 41191.6339 | 37512.0926 | 29646.2367 | 0 | 194226.5446 | Switchgear | 39.1816 | 49.9087 | 47.9042 | 37.208 | 40.825 | 37.1782 | 29.3824 | 0 | 192.4979
Transformers | 25115.6609 | 26688.2002 | 27838.5261 | 25288.7546 | 25514.4871 | 19593.2847 | 15618.5207 | 0 | 113853.5731 | Transformers | 25.1157 | 26.6882 | 27.5908 | 25.0637 | 25.2874 | 19.4189 | 15.4795 | 0 | 112.8403
Reactive | 962.1785 | 10633.5832 | 181.8234 | 185.2308 | 186.2542 | 185.7 | 187.0211 | 0 | 926.0295 | Reactive | 0.96218 | 10.6336 | 0.18021 | 0.18358 | 0.1846 | 0.18405 | 0.18536 | 0 | 0.91779
Lines and towers | 24939.4578 | 9683.3391 | 12032.9001 | 14836.0939 | 10940.7639 | 11001.0762 | 10763.3412 | 0 | 59574.1753 | Lines and towers | 24.9395 | 9.6833 | 11.9258 | 14.7041 | 10.8434 | 10.9032 | 10.6675 | 0 | 59.044
Establishment | 10877.7435 | 16387.0472 | 20720.5237 | 17573.9418 | 18561.2176 | 16363.2508 | 13045.0275 | 0 | 86263.9614 | Establishment | 10.8777 | 16.387 | 20.5361 | 17.4175 | 18.396 | 16.2176 | 12.9289 | 0 | 85.4962
Communications | 5400.6595 | 15386.3646 | 11305.6656 | 13665.5314 | 16105.2998 | 14028.7734 | 10167.9975 | 0 | 65273.2677 | Communications | 5.4007 | 15.3864 | 11.205 | 13.5439 | 15.962 | 13.9039 | 10.0775 | 0 | 64.6923
Inventory | [9 empty] | Inventory | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Forecast Period (Real Mar 2017) 2017-18 Year 1 to Forecast Period (Real Mar 2017) 2021-22 Year 5
IT | 8860.507 | 19524.3428 | 25500.1312 | 23106.0979 | 14156.0048 | 11676.9217 | 9945.1589 | 0 | 84384.3145 | IT | 8.8605 | 19.5243 | 25.2732 | 22.9005 | 14.03 | 11.573 | 9.8566 | 0 | 83.6333
Vehicles | 681.4958 | 893.4586 | 1923.5864 | 1518.6098 | 2106.6913 | 1780.588 | 1792.3722 | 0 | 9121.8476 | Vehicles | 0.6815 | 0.89346 | 1.9065 | 1.5051 | 2.0879 | 1.7647 | 1.7764 | 0 | 9.0407
Other Non System | 1576.0135 | 2587.5614 | 2923.3476 | 2941.1008 | 2958.5643 | 2977.6425 | 2997.349 | 0 | 14798.0043 | Other Non System | 1.576 | 2.5876 | 2.8973 | 2.9149 | 2.9322 | 2.9511 | 2.9707 | 0 | 14.6663
Premises | 0 | 530.0355 | 219.3512 | 595.6376 | 95.624 | 211.3938 | 1034.0613 | 0 | 2156.0678 | Premises | 0 | 0.53004 | 0.2174 | 0.59034 | 0.094773 | 0.20951 | 1.0249 | 0 | 2.1369
Land | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Land | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Easements | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Easements | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TOTAL CAPEX | 144134.2386 | 175884.7563 | 182628.5888 | 163009.2766 | 156067.778 | 138578.1487 | 117712.8366 | 0 | 757996.6286 | TOTAL CAPEX | 144.1342 | 175.8848 | 181.0032 | 161.5585 | 154.6788 | 137.3448 | 116.6652 | 0 | 751.2505
Check | 1.3397e-06 | 7.9993e-06 | 2.3155e-05 | 2.4731e-05 | 2.9522e-05 | 1.8117e-05 | 8.1514e-06 | 0
Output for RFM model
As Incurred - $m, Nominal
[10 empty] | (Including Efficiency factors) |  |  | Forecast Period (Nominal)
[11 empty] | 2015-16 | 2016-17 | 2017-18 | 2018-19 | 2019-20 | 2020-21 | 2021-22 | 2022-23 | TOTAL
[10 empty] | Asset class | Year -2 | Year -1 | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 | Year 6
[10 empty] | Secondary | 26.0975 | 23.6184 | 31.8253 | 26.3275 | 25.1982 | 24.5538 | 24.1734 |  | 132.0781
[10 empty] | Switchgear | 38.5297 | 49.8165 | 48.6047 | 38.375 | 42.8001 | 39.62 | 31.8288 |  | 201.2286
[10 empty] | Transformers | 24.6978 | 26.6389 | 27.9942 | 25.8497 | 26.5108 | 20.6943 | 16.7684 |  | 117.8174
[10 empty] | Reactive | 0.94617 | 10.6139 | 0.18284 | 0.18934 | 0.19353 | 0.19614 | 0.20079 |  | 0.96263
[10 empty] | Lines and towers | 24.5246 | 9.6654 | 12.1002 | 15.1652 | 11.368 | 11.6193 | 11.5557 |  | 61.8084
[10 empty] | Establishment | 10.6968 | 16.3568 | 20.8364 | 17.9638 | 19.286 | 17.2828 | 14.0054 |  | 89.3743
[10 empty] | Communications | 5.3108 | 15.3579 | 11.3689 | 13.9687 | 16.7342 | 14.8171 | 10.9166 |  | 67.8054
[10 empty] | Inventory | 0 | 0 | 0 | 0 | 0 | 0 | 0
[10 empty] | IT | 8.7131 | 19.4883 | 25.6427 | 23.6187 | 14.7088 | 12.3331 | 10.6773 |  | 86.9806
[10 empty] | Vehicles | 0.67016 | 0.89181 | 1.9343 | 1.5523 | 2.189 | 1.8806 | 1.9243 |  | 9.4806
[10 empty] | Other Non System | 1.5498 | 2.5828 | 2.9397 | 3.0063 | 3.0741 | 3.145 | 3.218 |  | 15.3831
[10 empty] | Premises | 0 | 0.52906 | 0.22058 | 0.60885 | 0.099358 | 0.22327 | 1.1102 |  | 2.2622
[10 empty] | Land | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[10 empty] | Easements | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[10 empty] | TOTAL CAPEX | 141.7364 | 175.5596 | 183.6497 | 166.6253 | 162.1621 | 146.3653 | 126.3789 | 0 | 785.1814
Note on 2015-16 As Incurred and As Commissioned Capex
The 2015-16 As Incurred and As Commissioned Capex values presented in these output sheets are not used as inputs into the RAB Roll Forward model.
The reported Capex values in AusNet Sevices' submitted 2015-16 regulatory accounts (adjusted for provisions) are used for RFM inputs. See AusNet Services' Revised Proposal RFM for further details.

## 5.1(c)_Total_Fcast
Table of Contents
Forecast Capex by Driver - As Incurred Capex (Total incl Overhead)
[11 empty] | Efficiency factor --> |  | 0.89%
As Incurred - $000's, $ Mar 2017 | [9 empty] | As Incurred - $m, Mar 2017
(Before Efficiency factors are applied) |  |  | Forecast Period (Real Mar 2017) | [6 empty] | (Including Efficiency factors) |  |  | Forecast Period (Real Mar 2017)
| 2015-16 | 2016-17 | 2017-18 | 2018-19 | 2019-20 | 2020-21 | 2021-22 | 2022-23 | TOTAL |  | 2015-16 | 2016-17 | 2017-18 | 2018-19 | 2019-20 | 2020-21 | 2021-22 | 2022-23 | TOTAL
Project Driver | Year -2 | Year -1 | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 | Year 6 |  | Project Driver | Year -2 | Year -1 | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 | Year 6
Replacement - Major Station CBD | 34218.1521 | 32306.9037 | 35834.6096 | 25966.2604 | 29522.4231 | 18117.0745 | 8151.3818 | 0 | 117591.7494 | Replacement - Major Station CBD | 34.2182 | 32.3069 | 35.5157 | 25.7352 | 29.2597 | 17.9558 | 8.0788 | 0 | 116.5452
Replacement - Major Station | 34097.5933 | 59427.1315 | 52857.8525 | 39504.8051 | 42080.8846 | 42331.6768 | 35061.8893 | 0 | 211837.1083 | Replacement - Major Station | 34.0976 | 59.4271 | 52.3874 | 39.1532 | 41.7064 | 41.9549 | 34.7498 | 0 | 209.9518
Replacement - Other | 43471.7216 | 45171.6098 | 48930.1948 | 55548.2313 | 50493.3773 | 48326.5615 | 44118.6167 | 0 | 247416.9817 | Replacement - Other | 43.4717 | 45.1716 | 48.4947 | 55.0539 | 50.044 | 47.8965 | 43.726 | 0 | 245.215
Security and Compliance | 21228.7554 | 15443.7129 | 14439.5155 | 13828.5335 | 14654.2085 | 13156.29 | 14612.0076 | 0 | 70690.5551 | Security and Compliance | 21.2288 | 15.4437 | 14.311 | 13.7055 | 14.5238 | 13.0392 | 14.482 | 0 | 70.0614
Non Network - Other | 1576.0135 | 2587.5614 | 2923.3476 | 2941.1008 | 2958.5643 | 2977.6425 | 2997.349 | 0 | 14798.0043 | Non Network - Other | 1.576 | 2.5876 | 2.8973 | 2.9149 | 2.9322 | 2.9511 | 2.9707 | 0 | 14.6663
Non Network - Vehicles | 681.4958 | 893.4586 | 1923.5864 | 1518.6098 | 2106.6913 | 1780.588 | 1792.3722 | 0 | 9121.8476 | Non Network - Vehicles | 0.6815 | 0.89346 | 1.9065 | 1.5051 | 2.0879 | 1.7647 | 1.7764 | 0 | 9.0407
Non Network - Premises | 0 | 530.0355 | 219.3512 | 595.6376 | 95.624 | 211.3938 | 1034.0613 | 0 | 2156.0678 | Non Network - Premises | 0 | 0.53004 | 0.2174 | 0.59034 | 0.094773 | 0.20951 | 1.0249 | 0 | 2.1369
Non Network - IT | 8860.507 | 19524.3428 | 25500.1312 | 23106.0979 | 14156.0048 | 11676.9217 | 9945.1589 | 0 | 84384.3145 | Non Network - IT | 8.8605 | 19.5243 | 25.2732 | 22.9005 | 14.03 | 11.573 | 9.8566 | 0 | 83.6333
TOTAL CAPEX | 144134.2386 | 175884.7563 | 182628.5887 | 163009.2765 | 156067.778 | 138578.1487 | 117712.8366 | 0 | 757996.6285 | TOTAL CAPEX | 144.1342 | 175.8848 | 181.0032 | 161.5585 | 154.6788 | 137.3448 | 116.6652 | 0 | 751.2505
[10 empty] | Check | -1.3397e-09 | -7.9992e-09 | -2.2949e-08 | -2.451e-08 | -2.926e-08 | -1.7956e-08 | -8.0788e-09 | 0 | -1.0275e-07
As Incurred - $m, Nominal
[10 empty] | (Including Efficiency factors) |  |  | Forecast Period (Nominal)
[11 empty] | 2015-16 | 2016-17 | 2017-18 | 2018-19 | 2019-20 | 2020-21 | 2021-22 | 2022-23 | TOTAL
[10 empty] | Project Driver | Year -2 | Year -1 | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 | Year 6
[10 empty] | Replacement - Major Station CBD | 33.6489 | 32.2472 | 36.035 | 26.5423 | 30.6753 | 19.1351 | 8.7515 |  | 121.1391
[10 empty] | Replacement - Major Station | 33.5304 | 59.3173 | 53.1534 | 40.3811 | 43.7241 | 44.7104 | 37.6432 |  | 219.6123
[10 empty] | Replacement - Other | 42.7485 | 45.0881 | 49.2038 | 56.7805 | 52.4651 | 51.0422 | 47.3667 |  | 256.8582
[10 empty] | Security and Compliance | 20.8756 | 15.4152 | 14.5202 | 14.1353 | 15.2264 | 13.8956 | 15.6878 |  | 73.4653
[10 empty] | Non Network - Other | 1.5498 | 2.5828 | 2.9397 | 3.0063 | 3.0741 | 3.145 | 3.218 |  | 15.3831
[10 empty] | Non Network - Vehicles | 0.67016 | 0.89181 | 1.9343 | 1.5523 | 2.189 | 1.8806 | 1.9243 |  | 9.4806
[10 empty] | Non Network - Premises | 0 | 0.52906 | 0.22058 | 0.60885 | 0.099358 | 0.22327 | 1.1102 |  | 2.2622
[10 empty] | Non Network - IT | 8.7131 | 19.4883 | 25.6427 | 23.6187 | 14.7088 | 12.3331 | 10.6773 |  | 86.9806
[11 empty] | 141.7364 | 175.5596 | 183.6497 | 166.6253 | 162.1621 | 146.3653 | 126.3789 | 0 | 785.1814
[10 empty] | Check | -1.3174e-09 | -7.9845e-09 | -2.3284e-08 | -2.5279e-08 | -3.0675e-08 | -1.9135e-08 | -8.7515e-09 | 0 | -1.0713e-07
Note on 2015-16 As Incurred and As Commissioned Capex
The 2015-16 As Incurred and As Commissioned Capex values presented in these output sheets are not used as inputs into the RAB Roll Forward model.
The reported Capex values in AusNet Sevices' submitted 2015-16 regulatory accounts (adjusted for provisions) are used for RFM inputs. See AusNet Services' Revised Proposal RFM for further details.

## 5.1(d)_Repl_Fcast
Table of Contents
Asset Replacement - As Incurred (Total incl Overhead) | [8 empty] | Efficiency factor |  |  | 0.89%
As Incurred - $000's, $ Mar 2017 | [8 empty] | As Incurred - $m, $ Mar 2017
(Before Efficiency factors are applied) |  |  | Forecast Period (Real Mar 2017) | [5 empty] | (Including Efficiency factors) |  |  | Forecast Period (Real Mar 2017)
Asset Replacement Expenditure - | 2015-16 | 2016-17 | 2017-18 | 2018-19 | 2019-20 | 2020-21 | 2021-22 |  | Asset Replacement Expenditure - | 2015-16 | 2016-17 | 2017-18 | 2018-19 | 2019-20 | 2020-21 | 2021-22
Excluding Major Stations | Year -2 | Year -1 | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 | TOTAL | Excluding Major Stations | Year -2 | Year -1 | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 | TOTAL
Lines | 7657.4301 | 449.9587 | 4241.0873 | 8268.6202 | 4317.917 | 4305.0698 | 4335.6958 | 25468.3902 | Lines | 7.6574 | 0.44996 | 4.2033 | 8.195 | 4.2795 | 4.2668 | 4.2971 | 25.2417
Stations | 10414.3735 | 16054.0446 | 11985.2694 | 14041.8495 | 14005.86 | 13964.1881 | 14063.5284 | 68060.6954 | Stations | 10.4144 | 16.054 | 11.8786 | 13.9169 | 13.8812 | 13.8399 | 13.9384 | 67.455
Secondary and Protection | 20440.4884 | 14017.5523 | 23066.078 | 19977.8188 | 17041.1217 | 16169.489 | 17239.0093 | 93493.5169 | Secondary and Protection | 20.4405 | 14.0176 | 22.8608 | 19.8 | 16.8895 | 16.0256 | 17.0856 | 92.6614
Communications | 4959.4296 | 14650.0542 | 9637.76 | 13259.9427 | 15128.4786 | 13887.8147 | 8480.3833 | 60394.3792 | Communications | 4.9594 | 14.6501 | 9.552 | 13.1419 | 14.9938 | 13.7642 | 8.4049 | 59.8569
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
TOTAL CAPEX | 43471.7216 | 45171.6098 | 48930.1948 | 55548.2313 | 50493.3773 | 48326.5615 | 44118.6167 | 247416.9817 | TOTAL CAPEX | 43.4717 | 45.1716 | 48.4947 | 55.0539 | 50.044 | 47.8965 | 43.726 | 245.215
Check | 0 | 0 | 0 | 0 | 0 | 0 | 0
Security & Compliance - As Incurred (Total incl Overhead) | [8 empty] | Efficiency factor |  |  | 0.89%
As Commissioned - $000's, $ Mar 2017 | [8 empty] | As Incurred - $m, Mar 2017
(Before Efficiency factors are applied) | Forecast Period (Real Mar 2017) 2017-18: Forecast Period (Real Mar 2017) |  | (Including Efficiency factors) |  |  | Forecast Period (Real Mar 2017)
| 2015-16 | 2016-17 | 2017-18 | 2018-19 | 2019-20 | 2020-21 | 2021-22 |  |  | 2015-16 | 2016-17 | 2017-18 | 2018-19 | 2019-20 | 2020-21 | 2021-22
Security & Compliance Expenditure | Year -2 | Year -1 | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 | TOTAL | Security & Compliance Expenditure | Year -2 | Year -1 | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 | TOTAL
Tower fall arrest | 7570.7551 | 5602.4853 | 4782.8436 | 4872.4735 | 4899.3935 | 4884.8162 | 4919.5665 | 24359.0932 | Tower fall arrest | 7.5708 | 5.6025 | 4.7403 | 4.8291 | 4.8558 | 4.8413 | 4.8758 | 24.1423
Instrument transformer replacement | 1425.2939 | 2849.7382 | 1640.8457 | 1671.595 | 1680.8304 | 1675.8294 | 1687.7511 | 8356.8516 | Instrument transformer replacement | 1.4253 | 2.8497 | 1.6262 | 1.6567 | 1.6659 | 1.6609 | 1.6727 | 8.2825
Power transformers - improved safe access | 11.4375 | 1099.899 | 554.3398 | 564.728 | 567.8481 | 566.1586 | 570.1862 | 2823.2607 | Power transformers - improved safe access | 0.011437 | 1.0999 | 0.54941 | 0.5597 | 0.56279 | 0.56112 | 0.56511 | 2.7981
Insulator replacement | 6201.8621 | 700.5356 | 1257.4222 | 1208.4152 | 1215.0916 | 1211.4763 | 1011.3564 | 5903.7617 | Insulator replacement | 6.2019 | 0.70054 | 1.2462 | 1.1977 | 1.2043 | 1.2007 | 1.0024 | 5.8512
Fire protection and infrastructure | 2917.7541 | 2607.7604 | 1945.7326 | 1982.1954 | 1993.1469 | 1987.2166 | 2001.3535 | 9909.645 | Fire protection and infrastructure | 2.9178 | 2.6078 | 1.9284 | 1.9646 | 1.9754 | 1.9695 | 1.9835 | 9.8214
Infrastructure security systems | 1510.0005 | 1937.3536 | 2771.6989 | 2823.6402 | 2839.2405 | 2830.7929 | 2850.931 | 14116.3034 | Infrastructure security systems | 1.51 | 1.9374 | 2.747 | 2.7985 | 2.814 | 2.8056 | 2.8256 | 13.9907
Comms - safety and security | 373.2355 | 445.959 | 1478.0749 | 320.0229 | 857.3342 | 0 | 1570.863 | 4226.295 | Comms - safety and security | 0.37324 | 0.44596 | 1.4649 | 0.31717 | 0.8497 | 0 | 1.5569 | 4.1887
Station structure fall arrests | 1218.4168 | 199.9816 | 8.5578 | 385.4634 | 601.3233 | 0 | 0 | 995.3445 | Station structure fall arrests | 1.2184 | 0.19998 | 0.0084816 | 0.38203 | 0.59597 | 0 | 0 | 0.98649
Other | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Other | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TOTAL CAPEX | 21228.7554 | 15443.7129 | 14439.5155 | 13828.5335 | 14654.2085 | 13156.29 | 14612.0076 | 70690.5551 | TOTAL CAPEX | 21.2288 | 15.4437 | 14.311 | 13.7055 | 14.5238 | 13.0392 | 14.482 | 70.0614
Check | 0 | 0 | 0 | 0 | 0 | 0 | 0

## 5.2(a)_Total_Fcast
Table of Contents
Forecast Capex by Asset Class - As Commissioned Capex (Total incl Overhead)
[10 empty] | Output for PTRM model | Efficiency factor --> |  | 0.89%
As Commissioned - $000's, $ Mar 2017 | [9 empty] | As Commissioned - $m, $ Mar 2017
(Before Efficiency factors are applied) |  |  | Forecast Period (Real Mar 2017) | [6 empty] | (Including Efficiency factors) |  |  | Forecast Period (Real Mar 2017)
| 2015-16 | 2016-17 | 2017-18 | 2018-19 | 2019-20 | 2020-21 | 2021-22 | 2022-23 | TOTAL |  | 2015-16 | 2016-17 | 2017-18 | 2018-19 | 2019-20 | 2020-21 | 2021-22 | 2022-23 | TOTAL
Asset class | Year -2 | Year -1 | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 | Year 6 |  | Asset class | Year -2 | Year -1 | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 | Year 6
Secondary | 24158.397 | 22936.0076 | 33838.3063 | 28361.0294 | 27918.6843 | 23322.2635 | 22510.5335 | 0 | 135950.817 | Secondary | 24.1584 | 22.936 | 33.5371 | 28.1086 | 27.6702 | 23.1147 | 22.3102 | 0 | 134.7409
Switchgear | 27122.4069 | 54410.0622 | 66093.8902 | 50232.5724 | 55419.0554 | 37715.2604 | 29615.7978 | 0 | 239076.5762 | Switchgear | 27.1224 | 54.4101 | 65.5057 | 49.7855 | 54.9258 | 37.3796 | 29.3522 | 0 | 236.9488
Transformers | 21765.1961 | 29049.2957 | 31417.2038 | 39020.9275 | 34104.9772 | 19789.0315 | 15608.6928 | 0 | 139940.8328 | Transformers | 21.7652 | 29.0493 | 31.1376 | 38.6736 | 33.8014 | 19.6129 | 15.4698 | 0 | 138.6954
Reactive | 962.1785 | 10633.5832 | 181.8234 | 185.2308 | 186.2542 | 185.7 | 187.0211 | 0 | 926.0295 | Reactive | 0.96218 | 10.6336 | 0.18021 | 0.18358 | 0.1846 | 0.18405 | 0.18536 | 0 | 0.91779
Lines and towers | 22745.5697 | 11164.9061 | 14199.0137 | 18267.9812 | 11228.8029 | 11010.4557 | 10763.3412 | 0 | 65469.5946 | Lines and towers | 22.7456 | 11.1649 | 14.0726 | 18.1054 | 11.1289 | 10.9125 | 10.6675 | 0 | 64.8869
Establishment | 7734.7097 | 14987.4557 | 23389.6013 | 21358.8314 | 23889.305 | 16403.6436 | 13029.4517 | 0 | 98070.833 | Establishment | 7.7347 | 14.9875 | 23.1814 | 21.1687 | 23.6767 | 16.2577 | 12.9135 | 0 | 97.198
Communications | 5341.5311 | 15364.1332 | 11320.0345 | 13698.4778 | 16173.0014 | 14030.978 | 10167.9975 | 0 | 65390.4892 | Communications | 5.3415 | 15.3641 | 11.2193 | 13.5766 | 16.0291 | 13.9061 | 10.0775 | 0 | 64.8085
Inventory | [9 empty] | Inventory | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Forecast Period (Real Mar 2017) 2017-18 Year 1 to Forecast Period (Real Mar 2017) 2021-22 Year 5
IT | 34300.6094 | 19524.3428 | 25500.1312 | 23106.0979 | 14156.0048 | 11676.9217 | 9945.1589 | 0 | 84384.3145 | IT | 34.3006 | 19.5243 | 25.2732 | 22.9005 | 14.03 | 11.573 | 9.8566 | 0 | 83.6333
Vehicles | 681.4958 | 893.4586 | 1923.5864 | 1518.6098 | 2106.6913 | 1780.588 | 1792.3722 | 0 | 9121.8476 | Vehicles | 0.6815 | 0.89346 | 1.9065 | 1.5051 | 2.0879 | 1.7647 | 1.7764 | 0 | 9.0407
Other Non System | 1576.0135 | 2587.5614 | 2923.3476 | 2941.1008 | 2958.5643 | 2977.6425 | 2997.349 | 0 | 14798.0043 | Other Non System | 1.576 | 2.5876 | 2.8973 | 2.9149 | 2.9322 | 2.9511 | 2.9707 | 0 | 14.6663
Premises | 0 | 530.0355 | 219.3512 | 595.6376 | 95.624 | 211.3938 | 1034.0613 | 0 | 2156.0678 | Premises | 0 | 0.53004 | 0.2174 | 0.59034 | 0.094773 | 0.20951 | 1.0249 | 0 | 2.1369
Land | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Land | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Easements | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Easements | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TOTAL CAPEX | 146388.1076 | 182080.8419 | 211006.2895 | 199286.4967 | 188236.9648 | 139103.8786 | 117651.7768 | 0 | 855285.4064 | TOTAL CAPEX | 146.3881 | 182.0808 | 209.1283 | 197.5128 | 186.5617 | 137.8659 | 116.6047 | 0 | 847.6734
Check | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Output for RFM model
As Commissioned - $m, Nominal
[10 empty] | (Including Efficiency factors) |  |  | Forecast Period (Nominal)
[11 empty] | 2015-16 | 2016-17 | 2017-18 | 2018-19 | 2019-20 | 2020-21 | 2021-22 | 2022-23 | TOTAL
[10 empty] | Asset class | Year -2 | Year -1 | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 | Year 6
[10 empty] | Secondary | 23.7565 | 22.8936 | 34.0275 | 28.9902 | 29.0089 | 24.6328 | 24.1678 | 0 | 140.8271
[10 empty] | Switchgear | 26.6712 | 54.3095 | 66.4634 | 51.3469 | 57.5831 | 39.8346 | 31.7961 | 0 | 247.0242
[10 empty] | Transformers | 21.4031 | 28.9956 | 31.5929 | 39.8865 | 35.4367 | 20.901 | 16.7578 | 0 | 144.575
[10 empty] | Reactive | 0.94617 | 10.6139 | 0.18284 | 0.18934 | 0.19353 | 0.19614 | 0.20079 | 0 | 0.96263
[10 empty] | Lines and towers | 22.3672 | 11.1443 | 14.2784 | 18.6732 | 11.6673 | 11.6292 | 11.5557 | 0 | 67.8038
[10 empty] | Establishment | 7.606 | 14.9598 | 23.5204 | 21.8326 | 24.8222 | 17.3254 | 13.9887 | 0 | 101.4893
[10 empty] | Communications | 5.2527 | 15.3357 | 11.3833 | 14.0024 | 16.8045 | 14.8194 | 10.9166 | 0 | 67.9262
[10 empty] | Inventory | 0 | 0 | 0 | 0 | 0 | 0 | 0
[10 empty] | IT | 33.73 | 19.4883 | 25.6427 | 23.6187 | 14.7088 | 12.3331 | 10.6773 | 0 | 86.9806
[10 empty] | Vehicles | 0.67016 | 0.89181 | 1.9343 | 1.5523 | 2.189 | 1.8806 | 1.9243 | 0 | 9.4806
[10 empty] | Other Non System | 1.5498 | 2.5828 | 2.9397 | 3.0063 | 3.0741 | 3.145 | 3.218 | 0 | 15.3831
[10 empty] | Premises | 0 | 0.52906 | 0.22058 | 0.60885 | 0.099358 | 0.22327 | 1.1102 | 0 | 2.2622
[10 empty] | Land | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[10 empty] | Easements | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[10 empty] | TOTAL CAPEX | 143.9528 | 181.7443 | 212.186 | 203.7073 | 195.5875 | 146.9206 | 126.3134 | 0 | 884.7148
Note on 2015-16 As Incurred and As Commissioned Capex
The 2015-16 As Incurred and As Commissioned Capex values presented in these output sheets are not used as inputs into the RAB Roll Forward model.
The reported Capex values in AusNet Sevices' submitted 2015-16 regulatory accounts (adjusted for provisions) are used for RFM inputs. See AusNet Services' Revised Proposal RFM for further details.

## 5.2(b)_Total_Fcast
Table of Contents
Forecast Capex by Driver - As Commissioned Capex (Total incl Overhead)
[11 empty] | Efficiency factor |  | 0.89%
As Commissioned - $000's, $ Mar 2017 | [9 empty] | As Commissioned - $m, $ Mar 2017
(Before Efficiency factors are applied) |  |  | Forecast Period (Real Mar 2017) | [6 empty] | (Including Efficiency factors) |  |  | Forecast Period (Real Mar 2017)
| 2015-16 | 2016-17 | 2017-18 | 2018-19 | 2019-20 | 2020-21 | 2021-22 | 2022-23 | TOTAL |  | 2015-16 | 2016-17 | 2017-18 | 2018-19 | 2019-20 | 2020-21 | 2021-22 | 2022-23 | TOTAL
Project Driver | Year -2 | Year -1 | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 | Year 6 |  | Project Driver | Year -2 | Year -1 | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 | Year 6
Replacement - Major Station CBD | 34771.3998 | 40691.7408 | 58245.8013 | 44674.7742 | 41359.9597 | 17980.7405 | 8090.322 | 0 | 170351.5978 | Replacement - Major Station CBD | 34.7714 | 40.6917 | 57.7274 | 44.2772 | 40.9919 | 17.8207 | 8.0183 | 0 | 168.8355
Replacement - Major Station | 12470.3223 | 57226.9425 | 58858.807 | 54891.0448 | 62412.5349 | 42993.7407 | 35061.8893 | 0 | 254218.0166 | Replacement - Major Station | 12.4703 | 57.2269 | 58.335 | 54.4025 | 61.8571 | 42.6111 | 34.7498 | 0 | 251.9555
Replacement - Other | 41323.7004 | 45171.6098 | 48904.3071 | 57722.1402 | 50493.3773 | 48326.5615 | 44118.6167 | 0 | 249565.0028 | Replacement - Other | 41.3237 | 45.1716 | 48.4691 | 57.2084 | 50.044 | 47.8965 | 43.726 | 0 | 247.3439
Security and Compliance | 21264.5665 | 15455.1504 | 14430.9577 | 13837.0913 | 14654.2085 | 13156.29 | 14612.0076 | 0 | 70690.5551 | Security and Compliance | 21.2646 | 15.4552 | 14.3025 | 13.7139 | 14.5238 | 13.0392 | 14.482 | 0 | 70.0614
Non Network - Other | 1576.0135 | 2587.5614 | 2923.3476 | 2941.1008 | 2958.5643 | 2977.6425 | 2997.349 | 0 | 14798.0043 | Non Network - Other | 1.576 | 2.5876 | 2.8973 | 2.9149 | 2.9322 | 2.9511 | 2.9707 | 0 | 14.6663
Non Network - Vehicles | 681.4958 | 893.4586 | 1923.5864 | 1518.6098 | 2106.6913 | 1780.588 | 1792.3722 | 0 | 9121.8476 | Non Network - Vehicles | 0.6815 | 0.89346 | 1.9065 | 1.5051 | 2.0879 | 1.7647 | 1.7764 | 0 | 9.0407
Non Network - Premises | 0 | 530.0355 | 219.3512 | 595.6376 | 95.624 | 211.3938 | 1034.0613 | 0 | 2156.0678 | Non Network - Premises | 0 | 0.53004 | 0.2174 | 0.59034 | 0.094773 | 0.20951 | 1.0249 | 0 | 2.1369
Non Network - IT | 34300.6094 | 19524.3428 | 25500.1312 | 23106.0979 | 14156.0048 | 11676.9217 | 9945.1589 | 0 | 84384.3145 | Non Network - IT | 34.3006 | 19.5243 | 25.2732 | 22.9005 | 14.03 | 11.573 | 9.8566 | 0 | 83.6333
TOTAL CAPEX | 146388.1076 | 182080.8419 | 211006.2895 | 199286.4967 | 188236.9648 | 139103.8786 | 117651.7768 | 0 | 855285.4064 | TOTAL CAPEX | 146.3881 | 182.0808 | 209.1283 | 197.5128 | 186.5617 | 137.8659 | 116.6047 | 0 | 847.6734
[10 empty] | Check | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
As Commissioned - $m, Nominal
[10 empty] | (Including Efficiency factors) |  |  | Forecast Period (Nominal)
[11 empty] | 2015-16 | 2016-17 | 2017-18 | 2018-19 | 2019-20 | 2020-21 | 2021-22 | 2022-23 | TOTAL
[10 empty] | Project Driver | Year -2 | Year -1 | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 | Year 6
[10 empty] | Replacement - Major Station CBD | 34.1929 | 40.6165 | 58.5715 | 45.6658 | 42.975 | 18.9911 | 8.6859 |  | 174.8894
[10 empty] | Replacement - Major Station | 12.2629 | 57.1212 | 59.1879 | 56.1087 | 64.8497 | 45.4097 | 37.6432 |  | 263.1992
[10 empty] | Replacement - Other | 40.6362 | 45.0881 | 49.1777 | 59.0026 | 52.4651 | 51.0422 | 47.3667 |  | 259.0543
[10 empty] | Security and Compliance | 20.9108 | 15.4266 | 14.5116 | 14.144 | 15.2264 | 13.8956 | 15.6878 |  | 73.4655
[10 empty] | Non Network - Other | 1.5498 | 2.5828 | 2.9397 | 3.0063 | 3.0741 | 3.145 | 3.218 |  | 15.3831
[10 empty] | Non Network - Vehicles | 0.67016 | 0.89181 | 1.9343 | 1.5523 | 2.189 | 1.8806 | 1.9243 |  | 9.4806
[10 empty] | Non Network - Premises | 0 | 0.52906 | 0.22058 | 0.60885 | 0.099358 | 0.22327 | 1.1102 |  | 2.2622
[10 empty] | Non Network - IT | 33.73 | 19.4883 | 25.6427 | 23.6187 | 14.7088 | 12.3331 | 10.6773 |  | 86.9806
[10 empty] | TOTAL CAPEX | 143.9528 | 181.7443 | 212.186 | 203.7073 | 195.5875 | 146.9206 | 126.3134 | 0 | 884.7148
[10 empty] | Check | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Note on 2015-16 As Incurred and As Commissioned Capex
The 2015-16 As Incurred and As Commissioned Capex values presented in these output sheets are not used as inputs into the RAB Roll Forward model.
The reported Capex values in AusNet Sevices' submitted 2015-16 regulatory accounts (adjusted for provisions) are used for RFM inputs. See AusNet Services' Revised Proposal RFM for further details.

## RIN_Outputs-->
Table of Contents
RIN Outputs

## 2.1 Exp Summary
Table of Contents
Table 2.1.1 - Prescribed transmission services capex (as incurred)
Forecast ($0's. real March 2017)
|  | 2015-16 | 2016-17 | 2017-18 | 2018-19 | 2019-20 | 2020-21 | 2021-22
| Replacement expenditure | 122680190.6983 | 142038275.8506 | 139988702.012 | 122597583.132 | 124378803.3278 | 111948459.6475 | 93551168.295
Connections
Augmentation Expenditure
| Non-network | 10268820.0428 | 21964156.3988 | 28781606.9878 | 26578546.6841 | 17977706.5974 | 15681708.6051 | 14933034.008
| capitalised network overheads | 5789286.107 | 5703515.542 | 5871784.946 | 5943534.8013 | 5914687.1087 | 4663024.7404 | 3926875.2375
| capitalised corporate overheads | 5395941.7898 | 6178808.5038 | 6361100.3582 | 6438829.3681 | 6407577.7011 | 5051610.1355 | 4254114.8406
balancing item
| TOTAL CAPEX | 144134238.6378 | 175884756.2952 | 181003194.304 | 161558493.9854 | 154678774.7351 | 137344803.1285 | 116665192.3811
| Check | -0.0013397 | -0.0079993 | -0.022949 | -0.02451 | -0.02926 | -0.017956 | -0.0080788
Note on 2015-16 As Incurred Capex
The 2015-16 As Incurred Capex values presented in these RIN output sheets (in real $Mar 2017) do not reflect actual expenditures for several reasons including:-
  i. Actual Direct capital expenditures incurred on the Network Capability Incentive Scheme (NCIPAP) are excluded from this model;
  ii. Actual incurred Inventory capex is excluded from this model; and
  iii. RIN category allocations in this model are based on historical RIN allocations. The 2015-16 actual RIN allocations have not been updated in the model.
The reported 2015-16 actual expenditures are contained in AusNet Sevices' re-submitted 2015-16 Category Analysis RIN.

## 2.6 Non Network
Table of Contents
|  |  |  | Direct Costs only |  |  | Efficiency | 0.89%
2.6.1 NON-NETWORK EXPENDITURE
EXPENDITURE Forecast ($0's. real March 2017)
| SERVICE SUBCATEGORY | ASSET CATEGORY | ASSET REPORTING CATEGORY | 2015-16 | 2016-17 | 2017-18 | 2018-19 | 2019-20 | 2020-21 | 2021-22 | Allocators
| IT & COMMUNICATIONS | Client device expenditure | Opex
|  |  | Capex | 0 | 0 | 950416.4706 | 560772.9659 | 0 | 0 | 91610.8326
|  | Recurrent expenditure | Opex
|  |  | Capex | 5527804.4352 | 15619197.7858 | 13543434.7054 | 17448666.5149 | 8489420.8558 | 4625215.0285 | 5954704.1215
|  | Non-recurrent expenditure | Opex
|  |  | Capex | 2483506.3405 | 2333903.1174 | 9266560.5879 | 3558751.5142 | 4373338.0166 | 6131098.9912 | 3114768.3097
| MOTOR VEHICLES | Car | Opex
|  |  | Capex | 170373.942 | 223364.6496 | 476616.6091 | 376273.5487 | 521985.4253 | 441185.1846 | 444105.0132 | 25% | 3 Yr Historical Avg split per CA RIN's
|  | Light commercial vehicle | Opex
|  |  | Capex | 511121.8259 | 670093.9487 | 1429849.8272 | 1128820.646 | 1565956.2759 | 1323555.5539 | 1332315.0397 | 75% | as above
|  | Elevated work platform (LCV) | Opex
Capex
|  | Elevated work platform (HCV) | Opex
Capex
|  | Heavy commercial vehicle | Opex
Capex
| BUILDINGS AND PROPERTY | Total buildings and property expenditure | Opex
|  |  | Capex | 0 | 530035.4621 | 217398.9472 | 590336.4441 | 94772.9618 | 209512.3516 | 1024858.1064
| OTHER | Other expenditure | Opex
|  |  | Capex | 359331.0778 | 970335.5382 | 362166.2301 | 364365.6313 | 366529.1328 | 368892.6869 | 371334.0731
| OTHER - TNSP nominated | Tools and Equipment | Opex
|  |  | Capex | 1216682.4214 | 1617225.8971 | 2535163.6104 | 2550559.419 | 2565703.9293 | 2582248.8084 | 2599338.5117 | 77.2% | Select tools & equip (FY16)
|  |  | Opex | [7 empty] | 62.5% | Select tools & equip (FY17)
|  |  | Capex | [7 empty] | 87.5% | Test tools & Equip split per Non Network forecast v0_2 (FY18-FY22)
Opex
Capex
Opex
Capex
Opex
Capex
Opex
Capex
Opex
Capex
Opex
Capex
Opex
Capex
Opex
Capex
Opex
Capex
|  | Total | Opex | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Total | Capex | 10268820.0428 | 21964156.3988 | 28781606.9878 | 26578546.6841 | 17977706.5974 | 15681708.6051 | 14933034.008
|  |  | Check | 0 | 0 | 0 | 0 | 0 | 0 | 0

## 2.10 Overheads
Table of Contents
Capitalised Overheads - Prescribed Transmission Services
Historicals per Category Analysis RIN's
| $Nominal | 2012/13 | 2013/14 | 2014/15 | 2015/16
| Capitalised Network Overheads | 6590621.7074 | 6323658.3623 | 7312340.3577 | 9031843.1666
| Capitalised Corporate Overheads | 9325225.6389 | 7912417.3229 | 5664015.5063 | 8418188.1981
| Total Overheads - Nominal | 15915847.3463 | 14236075.6853 | 12976355.864 | 17450031.3647
Note, the above values include Connections related capitalised overhead
| Historical splits | 2012/13 | 2013/14 | 2014/15 | 2015/16 | Avg
| Capitalised Network Overheads | 41.41% | 44.42% | 56.35% | 51.76% | 48%
| Capitalised Corporate Overheads | 58.59% | 55.58% | 43.65% | 48.24% | 52%
| Total Overheads | 100% | 100% | 100% | 100% | 100%
Forecast Capitalised Overheads (excl Efficiency)
|  | Actual | Actual | Actual | Actual | Forecast | Forecast | Forecast | Forecast | Forecast | Forecast
| Real $2015/16 | 2012/13 | 2013/14 | 2014/15 | 2015/16 | 2016/17 | 2017/18 | 2018/19 | 2019/20 | 2020/21 | 2021/22
| Capitalised Network Overheads | 5360330.512 | 4469674.6694 | 6062298.1391 | 5692976.3566 | 5608632.6586 | 5825953.7448 | 5897143.569 | 5868521.0421 | 4626628.3079 | 3896224.6924
| Capitalised Corporate Overheads | 7584457.6949 | 5592637.8776 | 4695753.8879 | 5306175.6602 | 6076018.7135 | 6311449.8902 | 6388572.1998 | 6357564.4623 | 5012180.6668 | 4220910.0835
| Total Overheads - $2015/16 | 12944788.2069 | 10062312.547 | 10758052.027 | 10999152.0168 | 11684651.3722 | 12137403.6351 | 12285715.7688 | 12226085.5044 | 9638808.9747 | 8117134.7759
| Check | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Note, the above values exclude Connections related capitalised overhead
Forecast Capitalised Overheads (Incl Efficiency)
| Efficiency factor (applies to 2017-22) | 2012/13: 0.89%
|  | Actual | Actual | Actual | Forecast | Forecast | Forecast | Forecast | Forecast | Forecast | Forecast | Total
| Real $ Mar 2017 | 2012/13 | 2013/14 | 2014/15 | 2015/16 | 2016/17 | 2017/18 | 2018/19 | 2019/20 | 2020/21 | 2021/22 | 2017-22
| Capitalised Network Overheads | 5451012.7951 | 4545289.4664 | 6164855.8144 | 5789286.107 | 5703515.542 | 5871784.946 | 5943534.8013 | 5914687.1087 | 4663024.7404 | 3926875.2375 | 26319906.8339
| Capitalised Corporate Overheads | 7712766.1898 | 5687250.1725 | 4775193.3333 | 5395941.7898 | 6178808.5038 | 6361100.3582 | 6438829.3681 | 6407577.7011 | 5051610.1355 | 4254114.8406 | 28513232.4034
| Total Overheads - $ Mar 2017 | 13163778.9849 | 10232539.639 | 10940049.1477 | 11185227.8968 | 11882324.0458 | 12232885.3042 | 12382364.1693 | 12322264.8098 | 9714634.8759 | 8180990.078 | 54833139.2372
Note, the above values exclude Connections related capitalised overhead
TABLE 2.10.1 - NETWORK OVERHEADS EXPENDITURE
[5 empty] | EXPENDITURE Forecast ($0's. real March 2017) | [6 empty] | Allocators
[5 empty] | 2015-16 | 2016-17 | 2017-18 | 2018-19 | 2019-20 | 2020-21 | 2021-22
| MAINTENANCE SUPPORT | MAINTENANCE |  |  | 1846782.2681 | 1819421.4579 | 1873099.3978 | 1895987.6016 | 1886785.1877 | 1487504.8922 | 1252673.2008 | 31.9% | Based on FY14/15 Actual splits
| NETWORK MONITORING & CONTROL | OPERATIONS |  |  | 1099964.3603 | 1083667.953 | 1115639.1397 | 1129271.6122 | 1123790.5507 | 885974.7007 | 746106.2951 | 19%
| ASSET MANAGEMENT SUPPORT | ASSET MANAGEMENT SUPPORT |  |  | 2813593.048 | 2771908.5534 | 2853687.4838 | 2888557.9134 | 2874537.9348 | 2266230.0239 | 1908461.3654 | 48.6%
|  | ASSET WORKS PROGRAM |  |  | 28946.4305 | 28517.5777 | 29358.9247 | 29717.674 | 29573.4355 | 23315.1237 | 19634.3762 | 0.5%
| Total Overhead Expenditure - Prescribed Services |  |  |  | 5789286.107 | 5703515.542 | 5871784.946 | 5943534.8013 | 5914687.1087 | 4663024.7404 | 3926875.2375
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
TABLE 2.10.2 - CORPORATE OVERHEADS EXPENDITURE
EXPENDITURE Forecast ($0's. real March 2017)
[5 empty] | 2015-16 | 2016-17 | 2017-18 | 2018-19 | 2019-20 | 2020-21 | 2021-22
| CORPORATE OVERHEADS | OH&S |  |  | 113314.7776 | 129754.9786 | 133583.1075 | 135215.4167 | 134559.1317 | 106083.8128 | 89336.4117 | 2.1% | Based on FY14/15 Actual splits
|  | FINANCE |  |  | 296776.7984 | 339834.4677 | 349860.5197 | 354135.6152 | 352416.7736 | 277838.5575 | 233976.3162 | 5.5%
|  | HR |  |  | 410091.576 | 469589.4463 | 483443.6272 | 489351.032 | 486975.9053 | 383922.3703 | 323312.7279 | 7.6%
|  | IT SUPPORT |  |  | 1467696.1668 | 1680635.913 | 1730219.2974 | 1751361.5881 | 1742861.1347 | 1374037.9568 | 1157119.2366 | 27.2%
|  | OTHER |  |  | 3108062.4709 | 3558993.6982 | 3663993.8063 | 3708765.716 | 3690764.7558 | 2909727.438 | 2450370.1482 | 57.6%
| Total Overhead Expenditure - Prescribed Services |  |  |  | 5395941.7898 | 6178808.5038 | 6361100.3582 | 6438829.3681 | 6407577.7011 | 5051610.1355 | 4254114.8406
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0

## 2.12 Input Tables
Table of Contents
[5 empty] | Efficiency | 0.89%
| 2.12 Input Tables | Capex As Incurred
|  |  |  | -2 | -1 | 1 | 2 | 3 | 4 | 5 | -2 | -1 | 1 | 2 | 3 | 4 | 5 | -2 | -1 | 1 | 2 | 3 | 4 | 5 | -2 | -1 | 1 | 2 | 3 | 4 | 5
|  |  |  | DIRECT MATERIAL EXPENDITURE Forecast ($0's. real March 2017) | [6 empty] | DIRECT LABOUR EXPENDITURE Forecast ($0's. real March 2017) | [6 empty] | CONTRACT EXPENDITURE Forecast ($0's. real March 2017) | [6 empty] | OTHER EXPENDITURE Forecast ($0's. real March 2017) | [6 empty] | RELATED PARTY CONTRACT MARGIN EXPENDITURE Forecast ($0's. real March 2017) | [6 empty] | RELATED PARTY CONTRACT MARGIN Forecast ($0's. real March 2017) | [6 empty] | TOTAL EXPENDITURE Forecast ($0's. real March 2017) | [6 empty] | Check - Total Expenditure ($0's, real March 2017)
|  |  |  | 2015-16 | 2016-17 | 2017-18 | 2018-19 | 2019-20 | 2020-21 | 2021-22 | 2015-16 | 2016-17 | 2017-18 | 2018-19 | 2019-20 | 2020-21 | 2021-22 | 2015-16 | 2016-17 | 2017-18 | 2018-19 | 2019-20 | 2020-21 | 2021-22 | 2015-16 | 2016-17 | 2017-18 | 2018-19 | 2019-20 | 2020-21 | 2021-22 | 2015-16 | 2016-17 | 2017-18 | 2018-19 | 2019-20 | 2020-21 | 2021-22 | 2015-16 | 2016-17 | 2017-18 | 2018-19 | 2019-20 | 2020-21 | 2021-22 | 2015-16 | 2016-17 | 2017-18 | 2018-19 | 2019-20 | 2020-21 | 2021-22 | 2015-16 | 2016-17 | 2017-18 | 2018-19 | 2019-20 | 2020-21 | 2021-22
| AUGMENTATION | Subtransmission Substations, Switching Stations , Zone Substations
Subtransmission Lines
HV Feeders
Other Assets
| CONNECTIONS | All New Customer Connections
| REPLACEMENT | Transmission Towers | REPLACEMENT | 1439785.9644 | 542808.8097 | 327869.0459 | 1505468.1999 | 90228.5203 | 106760.1351 | 87801.18 | 359946.4911 | 137400.3492 | 83661.0748 | 387256.0614 | 23401.8112 | 27937.2977 | 23185.1463 | 1799732.4555 | 685806.4727 | 418540.7044 | 1941837.8111 | 117554.3824 | 140608.7348 | 116928.1624 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 3599464.9111 | 1366015.6316 | 830070.8252 | 3834562.0723 | 231184.7139 | 275306.1677 | 227914.4887 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Transmission Tower Support Structures | REPLACEMENT | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Conductors | REPLACEMENT | 2953988.4848 | 969035.3201 | 775689.2288 | 518170.8211 | 521558.7941 | 538090.4089 | 445337.8708 | 738497.1212 | 245290.4025 | 197929.6168 | 133290.621 | 135272.3109 | 140809.0384 | 117597.7781 | 3692485.606 | 1224318.1817 | 990204.8403 | 668365.9562 | 679513.7696 | 708693.4794 | 593073.3378 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 7384971.2121 | 2438643.9043 | 1963823.686 | 1319827.3983 | 1336344.8746 | 1387592.9267 | 1156008.9866 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Transmission Cables | REPLACEMENT | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Substation Switchbays | REPLACEMENT | 14005287.3449 | 18415714.6595 | 17572624.8597 | 13262668.6641 | 14408650.1363 | 13355689.256 | 10480596.0032 | 3501321.8362 | 4661541.1923 | 4483938.6394 | 3411595.6951 | 3737050.2104 | 3494954.9927 | 2767549.9514 | 17506609.1812 | 23267154.2701 | 22432306.0646 | 17106938.2199 | 18772334.5497 | 17590147.9212 | 13957407.3105 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 35013218.3623 | 46344410.122 | 44488869.5636 | 33781202.5791 | 36918034.8964 | 34440792.1699 | 27205553.2652 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Substation Power Transformers | REPLACEMENT | 9265618.9092 | 9887244.3674 | 10122861.6537 | 9026537.7092 | 9057070.8118 | 6975932.3742 | 5521490.2118 | 2316404.7273 | 2502742.7797 | 2583011.4096 | 2321923.134 | 2349056.1616 | 1825481.951 | 1458027.7651 | 11582023.6365 | 12491942.0319 | 12922322.7991 | 11642937.5446 | 11800020.2455 | 9187671.2612 | 7353177.9895 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 23164047.2729 | 24881929.1789 | 25628195.8624 | 22991398.3879 | 23206147.2188 | 17989085.5864 | 14332695.9664 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Substation Reactive Plant | REPLACEMENT | 354964.9389 | 3939450.199 | 66116.0574 | 66116.0574 | 66116.0574 | 66116.0574 | 66116.0574 | 88741.2347 | 997186.8981 | 16870.5784 | 17007.23 | 17147.9649 | 17301.4392 | 17458.8823 | 443706.1736 | 4977259.7597 | 84400.347 | 85280.2206 | 86139.4189 | 87078.3385 | 88049.262 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 887412.3471 | 9913896.8568 | 167386.9828 | 168403.5081 | 169403.4412 | 170495.8351 | 171624.2017 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Scada Network Control And Protection Systems | REPLACEMENT | 11783099.5923 | 14466390.0247 | 15619261.8632 | 14071114.2383 | 14325665.7279 | 13271702.2113 | 11554423.0857 | 2945774.8981 | 3661854.7936 | 3985506.5675 | 3619554.5539 | 3715527.2435 | 3472977.0225 | 3051109.2155 | 14728874.4904 | 18277418.7513 | 19938743.6662 | 18149716.9278 | 18664218.1708 | 17479532.5489 | 15387463.5752 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 29457748.9807 | 36405663.5696 | 39543512.0969 | 35840385.72 | 36705411.1421 | 34224211.7827 | 29992995.8764 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Other | REPLACEMENT | 9269331.0453 | 8220604.9179 | 10809608.5749 | 9682347.0853 | 10074210.8981 | 9097859.6778 | 7883642.364 | 2317332.7613 | 2080868.9296 | 2758245.9622 | 2490618.9298 | 2612863.2176 | 2380753.9615 | 2081787.5276 | 11586663.8066 | 10386242.7473 | 13798988.4793 | 12488837.4736 | 13125202.952 | 11982361.5563 | 10498945.6259 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 23173327.6132 | 20687716.5948 | 27366843.0164 | 24661803.4888 | 25812277.0677 | 23460975.1956 | 20464375.5175 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| NON-NETWORK EXPENDITURE | It And Communications | NON-NETWORK | 3204524.3103 | 7133960.3334 | 9385107.0286 | 8467779.3865 | 5020174.9064 | 4171158.0523 | 3529191.695 | 801131.0776 | 1805808.277 | 2394761.4188 | 2178192.0693 | 1302040.4766 | 1091520.5783 | 931933.0982 | 4005655.3879 | 9013332.2928 | 11980543.3165 | 10922219.5392 | 6540543.4894 | 5493635.3891 | 4699958.4707 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 8011310.7757 | 17953100.9032 | 23760411.7638 | 21568190.995 | 12862758.8724 | 10756314.0197 | 9161083.2639 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Motor Vehicles | NON-NETWORK | 272598.3071 | 355030.4894 | 753033.7323 | 590907.4896 | 814897.6933 | 684343.4032 | 684343.4032 | 68149.5768 | 89868.3153 | 192148.7015 | 152000.8905 | 211353.1502 | 179080.9405 | 180710.5771 | 340747.8839 | 448559.7936 | 961284.0025 | 762185.8146 | 1061690.8577 | 901316.3948 | 911366.0726 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 681495.7679 | 893458.5982 | 1906466.4363 | 1505094.1947 | 2087941.7012 | 1764740.7385 | 1776420.0529 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Buildings And Property | NON-NETWORK | 0 | 210618.3206 | 85870.2453 | 231769.0331 | 36988.709 | 81246.1528 | 394813.6496 | 0 | 53313.4877 | 21911.178 | 59618.6375 | 9593.4499 | 21260.7258 | 104256.1412 | 0 | 266103.6538 | 109617.5239 | 298948.7735 | 48190.8029 | 107005.473 | 525788.3156 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 530035.4621 | 217398.9472 | 590336.4441 | 94772.9618 | 209512.3516 | 1024858.1064 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Other | NON-NETWORK | 630405.3997 | 1028210.1537 | 1144414.1171 | 1144414.1171 | 1144414.1171 | 1144414.1171 | 1144414.1171 | 157601.3499 | 260269.2361 | 292015.7188 | 294381.0461 | 296817.0492 | 299473.5618 | 302198.7712 | 788006.7496 | 1299082.0455 | 1460900.0046 | 1476129.8872 | 1491001.8958 | 1507253.8164 | 1524059.6965 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 1576013.4992 | 2587561.4353 | 2897329.8404 | 2914925.0503 | 2932233.0621 | 2951141.4953 | 2970672.5848 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Total Repex (from above) |  | DIRECT MATERIAL EXPENDITURE Forecast ($0's. real March 2017) 2015-16: 49072076.2798; DIRECT MATERIAL EXPENDITURE Forecast ($0's. real March 2017) 2016-17: 56441248.2983; DIRECT MATERIAL EXPENDITURE Forecast ($0's. real March 2017) 2017-18: 55294031.2836; DIRECT MATERIAL EXPENDITURE Forecast ($0's. real March 2017) 2018-19: 48132422.7752; DIRECT MATERIAL EXPENDITURE Forecast ($0's. real March 2017) 2019-20: 48543500.9458; DIRECT MATERIAL EXPENDITURE Forecast ($0's. real March 2017) 2020-21: 43412150.1207; DIRECT MATERIAL EXPENDITURE Forecast ($0's. real March 2017) 2021-22: 36039406.773; DIRECT LABOUR EXPENDITURE Forecast ($0's. real March 2017) 2015-16: 12268019.07; DIRECT LABOUR EXPENDITURE Forecast ($0's. real March 2017) 2016-17: 14286885.3451; DIRECT LABOUR EXPENDITURE Forecast ($0's. real March 2017) 2017-18: 14109163.8488; DIRECT LABOUR EXPENDITURE Forecast ($0's. real March 2017) 2018-19: 12381246.2253; DIRECT LABOUR EXPENDITURE Forecast ($0's. real March 2017) 2019-20: 12590318.9201; DIRECT LABOUR EXPENDITURE Forecast ($0's. real March 2017) 2020-21: 11360215.703; DIRECT LABOUR EXPENDITURE Forecast ($0's. real March 2017) 2021-22: 9516716.2662; CONTRACT EXPENDITURE Forecast ($0's. real March 2017) 2015-16: 61340095.3498; CONTRACT EXPENDITURE Forecast ($0's. real March 2017) 2016-17: 71310142.2147; CONTRACT EXPENDITURE Forecast ($0's. real March 2017) 2017-18: 70585506.901; CONTRACT EXPENDITURE Forecast ($0's. real March 2017) 2018-19: 62083914.1539; CONTRACT EXPENDITURE Forecast ($0's. real March 2017) 2019-20: 63244983.4888; CONTRACT EXPENDITURE Forecast ($0's. real March 2017) 2020-21: 57176093.8404; CONTRACT EXPENDITURE Forecast ($0's. real March 2017) 2021-22: 47995045.2633; OTHER EXPENDITURE Forecast ($0's. real March 2017) 2021-22: REPLACEMENT | 122680190.6995 | 142038275.8581 | 139988702.0334 | 122597583.1544 | 124378803.3547 | 111948459.6641 | 93551168.3025 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Check |  | DIRECT MATERIAL EXPENDITURE Forecast ($0's. real March 2017) 2015-16: 0.00049424; DIRECT MATERIAL EXPENDITURE Forecast ($0's. real March 2017) 2016-17: 0.0029635; DIRECT MATERIAL EXPENDITURE Forecast ($0's. real March 2017) 2017-18: 0.0084197; DIRECT MATERIAL EXPENDITURE Forecast ($0's. real March 2017) 2018-19: 0.0088273; DIRECT MATERIAL EXPENDITURE Forecast ($0's. real March 2017) 2019-20: 0.01048; DIRECT MATERIAL EXPENDITURE Forecast ($0's. real March 2017) 2020-21: 0.0064503; DIRECT MATERIAL EXPENDITURE Forecast ($0's. real March 2017) 2021-22: 0.0028817; DIRECT LABOUR EXPENDITURE Forecast ($0's. real March 2017) 2015-16: 0.00012356; DIRECT LABOUR EXPENDITURE Forecast ($0's. real March 2017) 2016-17: 0.00075015; DIRECT LABOUR EXPENDITURE Forecast ($0's. real March 2017) 2017-18: 0.0021484; DIRECT LABOUR EXPENDITURE Forecast ($0's. real March 2017) 2018-19: 0.0022707; DIRECT LABOUR EXPENDITURE Forecast ($0's. real March 2017) 2019-20: 0.0027181; DIRECT LABOUR EXPENDITURE Forecast ($0's. real March 2017) 2020-21: 0.0016879; DIRECT LABOUR EXPENDITURE Forecast ($0's. real March 2017) 2021-22: 0.00076095; CONTRACT EXPENDITURE Forecast ($0's. real March 2017) 2015-16: 0.00061778; CONTRACT EXPENDITURE Forecast ($0's. real March 2017) 2016-17: 0.0037442; CONTRACT EXPENDITURE Forecast ($0's. real March 2017) 2017-18: 0.010748; CONTRACT EXPENDITURE Forecast ($0's. real March 2017) 2018-19: 0.011386; CONTRACT EXPENDITURE Forecast ($0's. real March 2017) 2019-20: 0.013654; CONTRACT EXPENDITURE Forecast ($0's. real March 2017) 2020-21: 0.0084954; CONTRACT EXPENDITURE Forecast ($0's. real March 2017) 2021-22: 0.0038376; OTHER EXPENDITURE Forecast ($0's. real March 2017) 2021-22: Check | 0.0012356 | 0.0074579 | 0.021316 | 0.022484 | 0.026851 | 0.016634 | 0.0074803
|  | Total Non Network (from above) |  | DIRECT MATERIAL EXPENDITURE Forecast ($0's. real March 2017) 2015-16: 4107528.0171; DIRECT MATERIAL EXPENDITURE Forecast ($0's. real March 2017) 2016-17: 8727819.2972; DIRECT MATERIAL EXPENDITURE Forecast ($0's. real March 2017) 2017-18: 11368425.1233; DIRECT MATERIAL EXPENDITURE Forecast ($0's. real March 2017) 2018-19: 10434870.0262; DIRECT MATERIAL EXPENDITURE Forecast ($0's. real March 2017) 2019-20: 7016475.4257; DIRECT MATERIAL EXPENDITURE Forecast ($0's. real March 2017) 2020-21: 6081161.7253; DIRECT MATERIAL EXPENDITURE Forecast ($0's. real March 2017) 2021-22: 5752762.8648; DIRECT LABOUR EXPENDITURE Forecast ($0's. real March 2017) 2015-16: 1026882.0043; DIRECT LABOUR EXPENDITURE Forecast ($0's. real March 2017) 2016-17: 2209259.316; DIRECT LABOUR EXPENDITURE Forecast ($0's. real March 2017) 2017-18: 2900837.017; DIRECT LABOUR EXPENDITURE Forecast ($0's. real March 2017) 2018-19: 2684192.6434; DIRECT LABOUR EXPENDITURE Forecast ($0's. real March 2017) 2019-20: 1819804.1259; DIRECT LABOUR EXPENDITURE Forecast ($0's. real March 2017) 2020-21: 1591335.8065; DIRECT LABOUR EXPENDITURE Forecast ($0's. real March 2017) 2021-22: 1519098.5877; CONTRACT EXPENDITURE Forecast ($0's. real March 2017) 2015-16: 5134410.0214; CONTRACT EXPENDITURE Forecast ($0's. real March 2017) 2016-17: 11027077.7856; CONTRACT EXPENDITURE Forecast ($0's. real March 2017) 2017-18: 14512344.8475; CONTRACT EXPENDITURE Forecast ($0's. real March 2017) 2018-19: 13459484.0144; CONTRACT EXPENDITURE Forecast ($0's. real March 2017) 2019-20: 9141427.0459; CONTRACT EXPENDITURE Forecast ($0's. real March 2017) 2020-21: 8009211.0733; CONTRACT EXPENDITURE Forecast ($0's. real March 2017) 2021-22: 7661172.5555; OTHER EXPENDITURE Forecast ($0's. real March 2017) 2021-22: NON-NETWORK | 10268820.0428 | 21964156.3988 | 28781606.9878 | 26578546.6841 | 17977706.5974 | 15681708.6051 | 14933034.008 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Check |  | DIRECT MATERIAL EXPENDITURE Forecast ($0's. real March 2017) 2015-16: 0; DIRECT MATERIAL EXPENDITURE Forecast ($0's. real March 2017) 2016-17: 0; DIRECT MATERIAL EXPENDITURE Forecast ($0's. real March 2017) 2017-18: 0; DIRECT MATERIAL EXPENDITURE Forecast ($0's. real March 2017) 2018-19: 0; DIRECT MATERIAL EXPENDITURE Forecast ($0's. real March 2017) 2019-20: 0; DIRECT MATERIAL EXPENDITURE Forecast ($0's. real March 2017) 2020-21: 0; DIRECT MATERIAL EXPENDITURE Forecast ($0's. real March 2017) 2021-22: 0; DIRECT LABOUR EXPENDITURE Forecast ($0's. real March 2017) 2015-16: 0; DIRECT LABOUR EXPENDITURE Forecast ($0's. real March 2017) 2016-17: 0; DIRECT LABOUR EXPENDITURE Forecast ($0's. real March 2017) 2017-18: 0; DIRECT LABOUR EXPENDITURE Forecast ($0's. real March 2017) 2018-19: 0; DIRECT LABOUR EXPENDITURE Forecast ($0's. real March 2017) 2019-20: 0; DIRECT LABOUR EXPENDITURE Forecast ($0's. real March 2017) 2020-21: 0; DIRECT LABOUR EXPENDITURE Forecast ($0's. real March 2017) 2021-22: 0; CONTRACT EXPENDITURE Forecast ($0's. real March 2017) 2015-16: 0; CONTRACT EXPENDITURE Forecast ($0's. real March 2017) 2016-17: 0; CONTRACT EXPENDITURE Forecast ($0's. real March 2017) 2017-18: 0; CONTRACT EXPENDITURE Forecast ($0's. real March 2017) 2018-19: 0; CONTRACT EXPENDITURE Forecast ($0's. real March 2017) 2019-20: 0; CONTRACT EXPENDITURE Forecast ($0's. real March 2017) 2020-21: 0; CONTRACT EXPENDITURE Forecast ($0's. real March 2017) 2021-22: 0; OTHER EXPENDITURE Forecast ($0's. real March 2017) 2021-22: Check | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Error_Chks
Table of Contents
Error Checks Summary
No | Project Description | Project Inputs | As-Comm Forecast | Escalation Check
1 | FBTS Refurbishment | ok | ok | ok | Proj_1!R54
2 | HWPS 220kV Switchyard Redevelopment Stage 4 | ok | ok | ok | Proj_2!R54
3 | RTS Redevelopment Project | ok | ok | ok | Proj_3!R54
4 | HTS Rebuild | ok | ok | ok | Proj_4!R54
5 | SMTS H2 Transformer Replacement | ok | ok | ok | Proj_5!R54
6 | Other committed projects | ok | ok | ok | Proj_6!R54
7 | RWTS B4 220/66kV Transformer and 66kV CB Replacement | ok | ok | ok | Proj_7!R54
8 | TSTS B2 Transformer and 66kV CB Replacement | ok | ok | ok | Proj_8!R54
9 | SVTS Redevelopment Stage 1 | ok | ok | ok | Proj_9!R54
10 | WMTS Redevelopment | ok | ok | ok | Proj_10!R54
11 | HYTS 500kV and 275kV CB Replacement | ok | ok | ok | Proj_11!R54
12 | FBTS Transformer and Circuit Breaker Replacement | ok | ok | ok | Proj_12!R54
13 | Glenrowan Terminal Station Redevelopment Project | ok | ok | ok | Proj_13!R54
14 | Ringwood Terminal Station (RWTS) 220kV Circuit Breaker Replacements | ok | ok | ok | Proj_14!R54
15 | HWPS CB Replacement Stage 3 | ok | ok | ok | Proj_15!R54
16 | MWTS B2 Transformer Replacement | ok | ok | ok | Proj_16!R54
17 | TTS Bus Tie CB Replacement | ok | ok | ok | Proj_17!R54
18 | YPS 220kV CB Replacement | ok | ok | ok | Proj_18!R54
19 | Other station transformer replacement | ok | ok | ok | Proj_19!R54
20 | Power transformers - Bushings replacement | ok | ok | ok | Proj_20!R54
21 | Power transformers - life extension | ok | ok | ok | Proj_21!R54
22 | Power transformers - improved safe access | ok | ok | ok | Proj_22!R54
23 | Circuit breakers | ok | ok | ok | Proj_23!R54
24 | Instrument transformers | ok | ok | ok | Proj_24!R54
25 | Disconnectors | ok | ok | ok | Proj_25!R54
26 | Syn Cons | ok | ok | ok | Proj_26!R54
27 | Reactive plant | ok | ok | ok | Proj_27!R54
28 | On-line monitoring | ok | ok | ok | Proj_28!R54
29 | Fire protection systems | ok | ok | ok | Proj_29!R54
30 | Civils | ok | ok | ok | Proj_30!R54
31 | Infrastructure security | ok | ok | ok | Proj_31!R54
32 | Structure fall arrests | ok | ok | ok | Proj_32!R54
33 | Earth wires (incl. OPGW) | ok | ok | ok | Proj_33!R54
34 | Conductor | ok | ok | ok | Proj_34!R54
35 | Insulators | ok | ok | ok | Proj_35!R54
36 | Towers | ok | ok | ok | Proj_36!R54
37 | Tower fall arrests | ok | ok | ok | Proj_37!R54
38 | Secondary & Protection program | ok | ok | ok | Proj_38!R54
39 | Comms program | ok | ok | ok | Proj_39!R54
40 | Comms program - safety and security | ok | ok | ok | Proj_40!R54
41 | Other station works | ok | ok | ok | Proj_41!R54
42 | ERTS B1, B3 & B4 Transformer replacements | ok | ok | ok | Proj_42!R54
43 | Buildings & Property | ok | ok | ok | Proj_43!R54
44 | Non Network - Other | ok | ok | ok | Proj_44!R54
45 | IT Strategy | ok | ok | ok | Proj_45!R54
46 | Motor Vehicles | ok | ok | ok | Proj_46!R54