## All works
AusNet Services - REFCL CAPEX Forecast
Kalkallo Zone Substation works - Revised solution
Asset Class | 2021 Jan-Jun | 2021 Jul-Dec | 2022 Jan-Jun | 2022 Jul-Dec | 2023 Jan-Jun | 2023 Jul-Dec | 2024 Jan-Jun | 2024 Jul-Dec | 2025 Jan-Jun | 2025 Jul-Dec | 2026 Jan-Jun | TOTAL
Subtransmission | 1032.9741 | 3817.8551 | 5338.1774 | 6858.4998 | 3446.5873 | 0 | 0 | 0 | 0 | 0 | 0 | 20494.0937
Distribution system assets | 602.7321 | 2227.6878 | 3114.7836 | 4001.8795 | 2011.056 | 0 | 0 | 0 | 0 | 0 | 0 | 11958.139
SCADA/Network control | 288.0167 | 1064.5049 | 1488.4054 | 1912.3059 | 960.987 | 0 | 0 | 0 | 0 | 0 | 0 | 5714.22
Land | 0 | 650.0873 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 650.0873
Total ($2019) | 1923.7229 | 7760.1351 | 9941.3665 | 12772.6852 | 6418.6304 | 0 | 0 | 0 | 0 | 0 | 0 | 38816.5401
| TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE
Input for Capex model (2021-26) - Mid $2018
| Jan-Jun 2021 | 2022-06-01 | 2023-06-01 | 2024-06-01 | 2025-06-01 | 2026-06-01
Subtransmission | 1011.949 | 8969.6708 | 10095.3376 | 0 | 0 | 0 | 20076.9573
Distribution system assets | 590.4641 | 5233.7308 | 5890.5483 | 0 | 0 | 0 | 11714.7433
SCADA/Network control | 282.1544 | 2500.9485 | 2814.81 | 0 | 0 | 0 | 5597.9129
Land | 0 | 636.8555 | 0 | 0 | 0 | 0 | 636.8555
Total Direct | 1884.5675 | 17341.2055 | 18800.6959 | 0 | 0 | 0 | 38026.4689
| 4.956% | 45.6% | 49.44% | 0% | 0% | 0%
CPI - $2018 to $2019 | 102.1%

## Summary
Capex Summary by Asset Class - KLO
real $2019
Purpose | Asset Class | P50 Total | 2021 Jan-Jun | 2021 Jul-Dec | 2022 Jan-Jun | 2022 Jul-Dec | 2023 Jan-Jun | 2023 Jul-Dec | 2024 Jan-Jun | 2024 Jul-Dec | 2025 Jan-Jun | 2025 Jul-Dec | 2026 Jan-Jun | Total | check
Augmentation | Subtransmission | 20494.0937 | 1032.9741 | 3817.8551 | 5338.1774 | 6858.4998 | 3446.5873 | 0 | 0 | 0 | 0 | 0 | 0 | 20494.0937 | 0
Augmentation | Distribution system assets | 9280.9734 | 467.7936 | 1728.9572 | 2417.4517 | 3105.9463 | 1560.8246 | 0 | 0 | 0 | 0 | 0 | 0 | 9280.9734 | 0
Augmentation | SCADA/Network control | 5714.22 | 288.0167 | 1064.5049 | 1488.4054 | 1912.3059 | 960.987 | 0 | 0 | 0 | 0 | 0 | 0 | 5714.22 | 0
Non-Network | Land | 650.0873 | 0 | 650.0873 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 650.0873 | 0
Total |  |  | 1788.7844 | 7261.4045 | 9244.0346 | 11876.752 | 5968.3989 | 0 | 0 | 0 | 0 | 0 | 0 | 36139.3745 | 0
Purpose | Asset Class | P50 Total | 2021 Jan-Jun | 2021 Jul-Dec | 2022 Jan-Jun | 2022 Jul-Dec | 2023 Jan-Jun | 2023 Jul-Dec | 2024 Jan-Jun | 2024 Jul-Dec | 2025 Jan-Jun | 2025 Jul-Dec | 2026 Jan-Jun | Total | check
Replacement | Subtransmission | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Replacement | Distribution system assets | 2677.1656 | 134.9385 | 498.7305 | 697.3319 | 895.9332 | 450.2314 | 0 | 0 | 0 | 0 | 0 | 0 | 2677.1656 | 0
Replacement | SCADA/Network control | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total |  |  | 134.9385 | 498.7305 | 697.3319 | 895.9332 | 450.2314 | 0 | 0 | 0 | 0 | 0 | 0 | 2677.1656 | 0
Grand Total |  |  | 1923.7229 | 7760.1351 | 9941.3665 | 12772.6852 | 6418.6304 | 0 | 0 | 0 | 0 | 0 | 0 | 38816.5401
| Direct Cost Composition |  | Materials | Int Labour | Contracts - Design | Contracts - Construct | Other | P50 Total - $2019 | P50 Total - $2020
| KLO |  | 15263.8114 | 2701.6439 | 3386.258 | 16257.3194 | 1207.5074 | 38816.5401 | 39459.4162
| <Spare> |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Total |  | 15263.8114 | 2701.6439 | 3386.258 | 16257.3194 | 1207.5074 | 38816.5401 | 39459.4162
| CPI - $2019 to $2020 | 101.6%
| Proposed real wage escalator CY20 | 100.9%
| Escalator |  | 101.6% | 102.5% | 101.6% | 101.6% | 101.6%

## Phasing
High level phasing of revised KLO solution
| 2021 Jan-Jun | 2021 Jul-Dec | 2022 Jan-Jun | 2022 Jul-Dec | 2023 Jan-Jun | 2023 Jul-Dec | 2024 Jan-Jun | 2024 Jul-Dec | 2025 Jan-Jun | 2025 Jul-Dec | 2026 Jan-Jun | TOTAL
Program phasing - 6 monthly
KLO | 5.04% | 18.63% | 26.05% | 33.47% | 16.82% | [6 empty] | 100%
<spare> | [11 empty] | 0%
0 | [11 empty] | 0%
0 | [11 empty] | 0%
0 | [11 empty] | 0%
0 | [11 empty] | 0%
0 | [11 empty] | 0%
0 | [11 empty] | 0%
0 | [11 empty] | 0%

## KLO_Det
Confidential
KLO Volumes & Unit Rates
KLO |  |  |  |  | Materials |  |  | Total Direct ($k, $2019) | [6 empty] | Total Internal Labour (hours)
|  | Asset Class | Expenditure Class |  | $/Unit ($2019) | QTY | UOM | Materials | Int Labour | Contracts - Design | Contracts - Construct | Other | P50 Total | Chk | Project Engineer | Asset Management Engineer | Project Manager | Front Line Leader | Project Engineer Build | Site Manager Build | Operational Staff | Total Hours
Labour rates | [14 empty] | 162.4874 | 151.7974 | 176.3843 | 229.8341 | 162.4874 | 162.4874 | 133.6245
Design - Internal/External |  | Allocation | Allocation | [5 empty] | 0 | 3300 |  |  | 3300 |  | 0
Project Management & Engineering
| Project Establishment | Allocation | Allocation | [5 empty] | 95.7008 |  | 0 |  | 95.7008 |  | 253 | 234 | 56 | 40 |  |  |  | 583
| Project Management | Allocation | Allocation | [5 empty] | 2410.5699 |  |  |  | 2410.5699 |  | 1080 |  | 6912 | 420 | 2481.75 | 3072 | 127 | 14092.75
| Project Close-out, Testing & Commissioning | Allocation | Allocation | [5 empty] | 30.3766 |  | 0 |  | 30.3766 |  | 48 |  | 128 |  |  |  |  | 176
| Community Engagement | Allocation | Allocation | [5 empty] | 0 |  | 0 |  | 0 | [8 empty] | 0
Remote REFCL & Isolation Substation works
Primary Plant
| 66kV Bay - Ring Bus | Subtransmission | Augmentation | SubtransmissionAugmentation | 185.475 |  | ea | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 66kV Exit - Line Feeder | Subtransmission | Augmentation | SubtransmissionAugmentation | 74.1545 |  | ea | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 66kV Exit - Transformer | Subtransmission | Augmentation | SubtransmissionAugmentation | 37.494 |  | ea | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Power transformer - 66/22kV 15/20MVA | Subtransmission | Augmentation | SubtransmissionAugmentation | 787.0745 |  | ea | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 22kV Indoor Switchgear - Transformers | Subtransmission | Augmentation | SubtransmissionAugmentation | 41.2559 |  | ea | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 22kV Neutral Earthing Resistors | Subtransmission | Augmentation | SubtransmissionAugmentation | 106.8132 |  | ea | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Earth Grid | Subtransmission | Augmentation | SubtransmissionAugmentation | 58.2657 |  | ea | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Station service transformer (200 kVA) | Subtransmission | Augmentation | SubtransmissionAugmentation | 47.7187 | 2 | ea | 95.4374 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Station service transformer (1 MVA) | Subtransmission | Augmentation | SubtransmissionAugmentation | 169.008 |  | ea | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Station service transformer (500 kVA) | Subtransmission | Augmentation | SubtransmissionAugmentation | 72.619 |  | ea | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Capacitance reducing isolation substation (5 / 7.5 MVA) | Subtransmission | Augmentation | SubtransmissionAugmentation | 907.5436 | 4 | ea | 3630.1742 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Capacitance reducing isolation substation (12.5 MVA) | Subtransmission | Augmentation | SubtransmissionAugmentation | 1184.6455 | 2 | ea | 2369.2911 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| New ACR unit and control box | Subtransmission | Augmentation | SubtransmissionAugmentation | 37.6039 | 8 | ea | 300.8314 | 79.9918 | 76.6864 |  |  |  | -981.4249 | 149.239 | 170.9987 | 168.8653 | 0 | 0 | 0 | 0 | 489.103 | 30.31% | 32.45% | 37.24%
| AC changeover board - Station | Subtransmission | Augmentation | SubtransmissionAugmentation | 39.295 |  | ea | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| AC C/O board footing | Subtransmission | Augmentation | SubtransmissionAugmentation | 0 |  | ea | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Arc Suppression Coil | SCADA/Network control | Augmentation | SCADA/Network controlAugmentation | 1158.3 | 3 | ea | 3474.9 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| ASC footing | Subtransmission | Augmentation | SubtransmissionAugmentation | 0 | 2 | ea | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 22kV switchboard - Metro | Subtransmission | Augmentation | SubtransmissionAugmentation | 1354 |  | ea | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 22kV switchboard - Rural | Subtransmission | Augmentation | SubtransmissionAugmentation | 1461.1163 |  | ea | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 22kV switchboard (no building) - Rural | Subtransmission | Augmentation | SubtransmissionAugmentation | 700 |  | ea | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 22kV Capacitor Bank - Modify | Subtransmission | Augmentation | SubtransmissionAugmentation | 91.2924 |  | ea | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Cap Bank footing | Subtransmission | Augmentation | SubtransmissionAugmentation | 0 |  | ea | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 22kV Dead Tank Circuit Breaker | Subtransmission | Augmentation | SubtransmissionAugmentation | 107.006 |  | ea | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 22kV U/S Isolator | Subtransmission | Augmentation | SubtransmissionAugmentation | 7.664 | 4 | ea | 30.656 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 22kV Current Transformer | Subtransmission | Augmentation | SubtransmissionAugmentation | 27.163 | 2 | ea | 54.326 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 22kV Zero Sequence CTs | Subtransmission | Augmentation | SubtransmissionAugmentation | 0 |  | ea | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 22kV Voltage Transformer | Subtransmission | Augmentation | SubtransmissionAugmentation | 0 | 2 | ea | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 22KV Surge Arrestor | Subtransmission | Augmentation | SubtransmissionAugmentation | 0.62 | 2 | ea | 1.24 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Primary Cable Testing | Subtransmission | Augmentation | SubtransmissionAugmentation | 0 | 2 | ea | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Neutral Bus | Subtransmission | Augmentation | SubtransmissionAugmentation | 93.854 |  | ea | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Type 3 REFCL control room | Subtransmission | Augmentation | SubtransmissionAugmentation | 109.1759 | 2 | ea | 218.3518 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Battery Room (single battery set) | Subtransmission | Augmentation | SubtransmissionAugmentation | 227.63 |  | ea | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| New Control Building | Subtransmission | Augmentation | SubtransmissionAugmentation | 369.039 |  | ea | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Primary Cables - 22kV | Subtransmission | Augmentation | SubtransmissionAugmentation | 0.13829 | 0 | p/mtr | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Feeder Exit Cables - 22kV | Subtransmission | Augmentation | SubtransmissionAugmentation | 0.05 |  | p/mtr | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Other | Subtransmission | Augmentation | SubtransmissionAugmentation | 0 |  | ea | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 22kV Capacitor Bank (2x3 MVAr) - type 4 | Subtransmission | Augmentation | SubtransmissionAugmentation | 465.78 |  | ea | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| One Tilt Slab control room | Subtransmission | Augmentation | SubtransmissionAugmentation | 0 |  | ea | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SCADA / Protection & Control/ Comms
| 66kV Line Protection Panel | SCADA/Network control | Augmentation | SCADA/Network controlAugmentation | 76.7296 |  | ea | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 66kV Substation Protection Panel (transformer & bus) | SCADA/Network control | Augmentation | SCADA/Network controlAugmentation | 223.6578 |  | ea | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 66/22kV Transformer Voltage Control & Regulation Cubicle | SCADA/Network control | Augmentation | SCADA/Network controlAugmentation | 252.1155 |  | ea | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Neutral Bus controller - 1 GFN | SCADA/Network control | Augmentation | SCADA/Network controlAugmentation | 48.9823 |  | ea | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Protection – GFN panels | SCADA/Network control | Augmentation | SCADA/Network controlAugmentation | 6.2431 |  | ea | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 22kV Line Protection Panel | SCADA/Network control | Augmentation | SCADA/Network controlAugmentation | 63.4714 | 2 | ea | 126.9428 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 66/22kV Transformer Protection Panel | SCADA/Network control | Augmentation | SCADA/Network controlAugmentation | 47.4106 | 2 | ea | 94.8212 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Power Quality/Switchgear Interface | SCADA/Network control | Augmentation | SCADA/Network controlAugmentation | 98.0077 |  | ea | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 22kV Protection & Control Modifications | SCADA/Network control | Augmentation | SCADA/Network controlAugmentation | 5 |  | ea | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| SCIMS system - small | SCADA/Network control | Augmentation | SCADA/Network controlAugmentation | 92.2396 | 2 | ea | 184.4793 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Other protection works | SCADA/Network control | Augmentation | SCADA/Network controlAugmentation | 5 |  | ea | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Other AC & DC supplies |  | Subtransmission | Augmentation | SubtransmissionAugmentation | 22.8982 | 0 | ea | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Metering & System Monitoring |  | Subtransmission | Augmentation | SubtransmissionAugmentation | 4.5 |  | ea | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Infrastructure - Services |  | Subtransmission | Augmentation | SubtransmissionAugmentation | 15 | 0 | ea | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Civil works
| Earthworks | Subtransmission | Augmentation | SubtransmissionAugmentation | 0 |  | ea | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Buildings | Subtransmission | Augmentation | SubtransmissionAugmentation | 0 |  | ea | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 22kV switchyard - install new puraceptor | Subtransmission | Augmentation | SubtransmissionAugmentation | 131.3953 |  | ea | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| - Other | Subtransmission | Augmentation | SubtransmissionAugmentation | 0 |  | ea | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Construction delivery & site control |  | Subtransmission | Augmentation | SubtransmissionAugmentation | 0 |  | ea | 0 | 0
Land purchase |  | Land | Non-Network | LandNon-Network | 0 |  | ea | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Subtotal Remote REFCL & Isolation Substation works | [7 empty] | 10951.4395 | 2616.6391 | 3376.6864 | 9063.9926 | 499.0079 | 26507.7656
Check | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0
Feeder works |  |  |  |  | Material $/Unit | QTY | UOM | Materials | Int Labour | Contracts - Design | Contracts - Construct | Other | P50 Total
22KV LINES KLO14
Overhead 22kV lines
| Decommission and remove existing conductor (route length) at various locations - includes AAC, ASCR, Steel | Distribution system assets | Replacement | Distribution system assetsReplacement | 0 | 12.395 | km | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Install 151mm2 Covered Aluminium Conductor | Distribution system assets | Augmentation | Distribution system assetsAugmentation | 131.4797 | 3.175 | km | 417.4479 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Install 62mm2 Covered Steel Conductor | Distribution system assets | Augmentation | Distribution system assetsAugmentation | 111.563 | 9.3 | km | 1037.5359 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Surge Arrestor | Distribution system assets | Augmentation | Distribution system assetsAugmentation | 0.3785 | 90 | ea | 34.0653 | 17.4881 | 0 |  |  |  | -118.6703 | 2.769 | 0 | 31.842 | 0 | 0 | 0 | 85.4763 | 120.0872 | 2.573% | 0% | 32.12% | 0% | 0% | 0% | 65.31% | 100% | TRUE | 0.19431
| Cross Arms 22kV HV - Intermediate & Strain (Replacement) | Distribution system assets | Replacement | Distribution system assetsReplacement | 0.66462 | 31 | ea | 20.6031 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Concrete Poles 15.5m Replacement (includes installation), per pole | Distribution system assets | Replacement | Distribution system assetsReplacement | 6.06 | 20 | km | 121.2 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Vegetation Clearing - Light 22kV Line (1.01km):-
| Vegetation Clearing | Subtransmission | Augmentation | SubtransmissionAugmentation | 0 | 1.005 | km | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Subtotal 22kV Overhead Lines | [6 empty] | 1630.8521 | 17.4881 | 0 | 2374.5527 | 270.2159 | 4293.1088
Underground feeders
| 22kV Underground Cable 300mm2 XLPE | Distribution system assets | Augmentation | Distribution system assetsAugmentation | 0.064197 | 200 | p/m | 12.8395 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 22kV Underground Cable 185mm2 XLPE | Distribution system assets | Augmentation | Distribution system assetsAugmentation | 0.043775 | 450 | p/m | 19.6986 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 22KV cable terminations | Distribution system assets | Augmentation | Distribution system assetsAugmentation | 3.1912 | 8 | ea | 25.5293 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Concrete Poles 15.5m Replacement (includes installation), per pole | Distribution system assets | Replacement | Distribution system assetsReplacement | 6.06 | 4 | ea | 24.24 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Install new ACR for switching | Distribution system assets | Augmentation | Distribution system assetsAugmentation | 22.6039 | 1 | ea | 22.6039 | 20.3508 | 4.7858 |  |  |  | -80.3688 | 37.9681 | 43.504 | 42.9612 | 0 | 0 | 0 | 0 | 124.4334 | 30.31% | 32.45% | 37.24% | 0% | 0% | 0% | 0% | 100% | TRUE | 20.3508
| Subtotal Underground feeders | [6 empty] | 104.9113 | 20.3508 | 4.7858 | 529.591 | 7.9687 | 667.6077
22KV LINES KLO24
Overhead 22kV lines
| Decommission and remove existing conductor (route length) at various locations - includes AAC, ASCR, Steel | Distribution system assets | Replacement | Distribution system assetsReplacement | 0 | 16.08 | km | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Install 151mm2 Covered Aluminium Conductor | Distribution system assets | Augmentation | Distribution system assetsAugmentation | 131.4797 | 9.81 | km | 1289.8154 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Install 62mm2 Covered Steel Conductor | Distribution system assets | Augmentation | Distribution system assetsAugmentation | 111.563 | 6.99 | km | 779.8253 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Surge Arrestor | Distribution system assets | Augmentation | Distribution system assetsAugmentation | 0.3785 | 138 | ea | 52.2334 | 26.815 | 0 |  |  |  | -181.9611 | 4.2458 | 0 | 48.8243 | 0 | 0 | 0 | 131.0636 | 184.1337 | 2.573% | 0% | 32.12% | 0% | 0% | 0% | 65.31% | 100% | TRUE | 0.19431
| Cross Arms 22kV HV - Intermediate & Strain (Replacement) | Distribution system assets | Replacement | Distribution system assetsReplacement | 0.66462 | 0 | ea | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Concrete Poles 15.5m Replacement (includes installation), per pole | Distribution system assets | Replacement | Distribution system assetsReplacement | 6.06 | 64 | km | 387.84 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Vegetation Clearing - Light 22kV Line (1.01km):-
| Vegetation Clearing | Subtransmission | Augmentation | SubtransmissionAugmentation | 0 | 16.08 | km | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Subtotal 22kV Overhead Lines | [6 empty] | 2509.7142 | 26.815 | 0 | 3995.4021 | 423.0064 | 6954.9378
Underground feeders
| 22kV Underground Cable 300mm2 XLPE | Distribution system assets | Augmentation | Distribution system assetsAugmentation | 0.064197 | 200 | p/m | 12.8395 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 22kV Underground Cable 185mm2 XLPE | Distribution system assets | Augmentation | Distribution system assetsAugmentation | 0.043775 | 150 | p/m | 6.5662 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 22KV cable terminations | Distribution system assets | Augmentation | Distribution system assetsAugmentation | 3.1912 | 4 | ea | 12.7647 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Concrete Poles 15.5m Replacement (includes installation), per pole | Distribution system assets | Replacement | Distribution system assetsReplacement | 6.06 | 2 | ea | 12.12 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Install new ACR for switching | Distribution system assets | Augmentation | Distribution system assetsAugmentation | 22.6039 | 1 | ea | 22.6039 | 20.3508 | 4.7858 |  |  |  | -80.3688 | 37.9681 | 43.504 | 42.9612 | 0 | 0 | 0 | 0 | 124.4334 | 30.31% | 32.45% | 37.24% | 0% | 0% | 0% | 0% | 100% | TRUE | 20.3508
| Subtotal Underground feeders | [6 empty] | 66.8943 | 20.3508 | 4.7858 | 293.7809 | 7.3085 | 393.1202
Subtotal feeder works | [7 empty] | 4312.3719 | 85.0048 | 9.5716 | 7193.3267 | 708.4995 | 12308.7745
Check | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0
Grand Total | [7 empty] | 15263.8114 | 2701.6439 | 3386.258 | 16257.3194 | 1207.5074 | 38816.5401
Check | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0
| Remote REFCL & Isolation Substation works | Subtransmission | Augmentation | SubtransmissionAugmentation |  |  |  | 7070.2963 | 79.9918 | 76.6864 | 7999.5687 | 481.6011 | 15708.1444
|  | Subtransmission | Replacement | SubtransmissionReplacement |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
|  | SCADA/Network control | Augmentation | SCADA/Network controlAugmentation |  |  |  | 3881.1432 | 0 | 0 | 557.4769 | 17.4068 | 4456.027
|  | SCADA/Network control | Replacement | SCADA/Network controlReplacement |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Land | Non-Network | LandNon-Network |  |  |  | 0 | 0 | 0 | 506.947 | 0 | 506.947
[8 empty] | 10951.4395 | 79.9918 | 76.6864 | 9063.9926 | 499.0079 | 20671.1183
| Design, Project Management & Engineering costs allocation | Subtransmission | Augmentation | SubtransmissionAugmentation |  |  |  |  | 1927.6181 | 2507.6958 | 0 |  | 4435.3139
|  | Subtransmission | Replacement | SubtransmissionReplacement |  |  |  |  | 0 | 0 | 0 |  | 0
|  | SCADA/Network control | Augmentation | SCADA/Network controlAugmentation |  |  |  |  | 546.8194 | 711.3737 | 0 |  | 1258.1931
|  | SCADA/Network control | Replacement | SCADA/Network controlReplacement |  |  |  |  | 0 | 0 | 0 |  | 0
|  | Land | Non-Network | LandNon-Network |  |  |  |  | 62.2098 | 80.9306 | 0 |  | 143.1403
[8 empty] | 0 | 2536.6473 | 3300 | 0 | 0 | 5836.6473
| Total Remote REFCL & Isolation Substation works | Subtransmission | Augmentation | SubtransmissionAugmentation |  |  |  | 7070.2963 | 2007.6099 | 2584.3822 | 7999.5687 | 481.6011 | 20143.4583
|  | Subtransmission | Replacement | SubtransmissionReplacement |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
|  | SCADA/Network control | Augmentation | SCADA/Network controlAugmentation |  |  |  | 3881.1432 | 546.8194 | 711.3737 | 557.4769 | 17.4068 | 5714.22
|  | SCADA/Network control | Replacement | SCADA/Network controlReplacement |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Land | Non-Network | LandNon-Network |  |  |  | 0 | 62.2098 | 80.9306 | 506.947 | 0 | 650.0873
[8 empty] | 10951.4395 | 2616.6391 | 3376.6864 | 9063.9926 | 499.0079 | 26507.7656
[8 empty] | 0 | 0 | 0 | 0 | 0 | 0
| 22KV LINES KLO14 | Subtransmission | Augmentation | SubtransmissionAugmentation |  |  |  | 0 | 0 | 0 | 20.6256 | 0 | 20.6256
|  | Subtransmission | Replacement | SubtransmissionReplacement |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Distribution system assets | Augmentation | Distribution system assetsAugmentation |  |  |  | 1569.7204 | 37.8389 | 4.7858 | 2074.4464 | 271.5846 | 3958.3761
|  | Distribution system assets | Replacement | Distribution system assetsReplacement |  |  |  | 166.0431 | 0 | 0 | 809.0716 | 6.6 | 981.7147
[8 empty] | 1735.7634 | 37.8389 | 4.7858 | 2904.1437 | 278.1846 | 4960.7165
[8 empty] | 1.7053e-13 | 0 | 0 | 0 | 5.1514e-14 | 0
| 22KV LINES KLO24 | Subtransmission | Augmentation | SubtransmissionAugmentation |  |  |  | 0 | 0 | 0 | 330.0098 | 0 | 330.0098
|  | Subtransmission | Replacement | SubtransmissionReplacement |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Distribution system assets | Augmentation | Distribution system assetsAugmentation |  |  |  | 2176.6485 | 47.1659 | 4.7858 | 2681.8323 | 412.1649 | 5322.5973
|  | Distribution system assets | Replacement | Distribution system assetsReplacement |  |  |  | 399.96 | 0 | 0 | 1277.3409 | 18.15 | 1695.4509
[8 empty] | 2576.6085 | 47.1659 | 4.7858 | 4289.183 | 430.3149 | 7348.058
[8 empty] | -3.6948e-13 | 0 | 0 | 0 | -3.0198e-14 | -5.1159e-13
Note on G50: AST: Average unit rate across all cable types, excluding feeder exit cable

## Spare_Det
<spare> Volumes & Unit Rates
<spare> |  |  |  |  | Materials |  |  | Total Direct ($k, $2019) | [6 empty] | Total Internal Labour (hours)
|  | Asset Class | Expenditure Class |  | $/Unit ($2019) | QTY | UOM | Materials | Int Labour | Contracts - Design | Contracts - Construct | Other | P50 Total | Chk | Project Engineer | Asset Management Engineer | Project Manager | Front Line Leader | Project Engineer Build | Site Manager Build | Operational Staff | Total Hours
Labour rates | [14 empty] | 162.4874 | 151.7974 | 176.3843 | 229.8341 | 162.4874 | 162.4874 | 133.6245
Design - Internal/External |  | Allocation | Allocation | [5 empty] | 0 |  |  |  | 0 |  | 0
Project Management & Engineering
| Project Establishment | Allocation | Allocation | [5 empty] | 0 |  | 0 |  | 0 | [8 empty] | 0
| Project Management | Allocation | Allocation | [5 empty] | 0 |  |  |  | 0 | [8 empty] | 0
| Project Close-out, Testing & Commissioning | Allocation | Allocation | [5 empty] | 0 |  | 0 |  | 0 | [8 empty] | 0
| Community Engagement | Allocation | Allocation | [5 empty] | 0 |  | 0 |  | 0 | [8 empty] | 0
Remote REFCLs
Primary Plant
| 66kV Bay - Ring Bus | Subtransmission | Augmentation | SubtransmissionAugmentation | 185.475 |  | ea | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 66kV Exit - Line Feeder | Subtransmission | Augmentation | SubtransmissionAugmentation | 74.1545 |  | ea | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 66kV Exit - Transformer | Subtransmission | Augmentation | SubtransmissionAugmentation | 37.494 |  | ea | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Power transformer - 66/22kV 15/20MVA | Subtransmission | Augmentation | SubtransmissionAugmentation | 787.0745 |  | ea | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 22kV Indoor Switchgear - Transformers | Subtransmission | Augmentation | SubtransmissionAugmentation | 41.2559 |  | ea | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 22kV Neutral Earthing Resistors | Subtransmission | Augmentation | SubtransmissionAugmentation | 106.8132 |  | ea | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Earth Grid | Subtransmission | Augmentation | SubtransmissionAugmentation | 58.2657 |  | ea | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Station service transformer (200 kVA) | Subtransmission | Augmentation | SubtransmissionAugmentation | 47.7187 |  | ea | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Station service transformer (1 MVA) | Subtransmission | Augmentation | SubtransmissionAugmentation | 169.008 |  | ea | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Station service transformer (500 kVA) | Subtransmission | Augmentation | SubtransmissionAugmentation | 72.619 |  | ea | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Capacitance reducing isolation substation (12.5 MVA) | Subtransmission | Augmentation | SubtransmissionAugmentation | 1184.6455 |  | ea | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| AC changeover board - Station | Subtransmission | Augmentation | SubtransmissionAugmentation | 39.295 |  | ea | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| AC C/O board footing | Subtransmission | Augmentation | SubtransmissionAugmentation | 0 |  | ea | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Arc Suppression Coil | SCADA/Network control | Augmentation | SCADA/Network controlAugmentation | 1158.3 |  | ea | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| ASC footing | Subtransmission | Augmentation | SubtransmissionAugmentation | 0 |  | ea | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 22kV switchboard - Metro | Subtransmission | Augmentation | SubtransmissionAugmentation | 1354 |  | ea | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 22kV switchboard - Rural | Subtransmission | Augmentation | SubtransmissionAugmentation | 1461.1163 |  | ea | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 22kV switchboard (no building) - Rural | Subtransmission | Augmentation | SubtransmissionAugmentation | 700 |  | ea | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 22kV Capacitor Bank - Modify | Subtransmission | Augmentation | SubtransmissionAugmentation | 91.2924 |  | ea | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Cap Bank footing | Subtransmission | Augmentation | SubtransmissionAugmentation | 0 |  | ea | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 22kV Dead Tank Circuit Breaker | Subtransmission | Augmentation | SubtransmissionAugmentation | 107.006 |  | ea | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 22kV U/S Isolator | Subtransmission | Augmentation | SubtransmissionAugmentation | 7.664 |  | ea | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 22kV Current Transformer | Subtransmission | Augmentation | SubtransmissionAugmentation | 27.163 |  | ea | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 22kV Zero Sequence CTs | Subtransmission | Augmentation | SubtransmissionAugmentation | 0 |  | ea | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 22kV Voltage Transformer | Subtransmission | Augmentation | SubtransmissionAugmentation | 0 |  | ea | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 22KV Surge Arrestor | Subtransmission | Augmentation | SubtransmissionAugmentation | 0.62 |  | ea | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Primary Cable Testing | Subtransmission | Augmentation | SubtransmissionAugmentation | 0 |  | ea | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Neutral Bus | Subtransmission | Augmentation | SubtransmissionAugmentation | 93.854 |  | ea | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Type 3 REFCL control room | Subtransmission | Augmentation | SubtransmissionAugmentation | 109.1759 |  | ea | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Battery Room (single battery set) | Subtransmission | Augmentation | SubtransmissionAugmentation | 227.63 |  | ea | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| New Control Building | Subtransmission | Augmentation | SubtransmissionAugmentation | 369.039 |  | ea | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Primary Cables - 22kV | Subtransmission | Augmentation | SubtransmissionAugmentation | 0 |  | p/mtr | 0 | 0 |  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Feeder Exit Cables - 22kV | Subtransmission | Augmentation | SubtransmissionAugmentation | 0.05 |  | p/mtr | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Other | Subtransmission | Augmentation | SubtransmissionAugmentation | 0 |  | ea | 0 | 0 |  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 22kV Capacitor Bank (2x3 MVAr) - type 4 | Subtransmission | Augmentation | SubtransmissionAugmentation | 465.78 |  | ea | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| One Tilt Slab control room | Subtransmission | Augmentation | SubtransmissionAugmentation | 0 |  | ea | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[15 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SCADA / Protection & Control/ Comms | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 66kV Line Protection Panel | SCADA/Network control | Augmentation | SCADA/Network controlAugmentation | 76.7296 |  | ea | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 66kV Substation Protection Panel (transformer & bus) | SCADA/Network control | Augmentation | SCADA/Network controlAugmentation | 223.6578 |  | ea | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 66/22kV Transformer Voltage Control & Regulation Cubicle | SCADA/Network control | Augmentation | SCADA/Network controlAugmentation | 252.1155 |  | ea | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Neutral Bus controller - 1 GFN | SCADA/Network control | Augmentation | SCADA/Network controlAugmentation | 48.9823 |  | ea | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Protection – GFN panels | SCADA/Network control | Augmentation | SCADA/Network controlAugmentation | 6.2431 |  | ea | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Power Quality/Switchgear Interface | SCADA/Network control | Augmentation | SCADA/Network controlAugmentation | 98.0077 |  | ea | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 22kV Protection & Control Modifications | SCADA/Network control | Augmentation | SCADA/Network controlAugmentation | 0 |  | ea | 0 | 0 |  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| SCIMS system - small | SCADA/Network control | Augmentation | SCADA/Network controlAugmentation | 92.2396 |  | ea | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Other protection works | SCADA/Network control | Augmentation | SCADA/Network controlAugmentation | 0 |  | ea | 0 | 0 |  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Other AC & DC supplies |  | Subtransmission | Augmentation | SubtransmissionAugmentation | 0 |  | ea | 0 | 0 |  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Metering & System Monitoring |  | Subtransmission | Augmentation | SubtransmissionAugmentation |  |  | ea | 0 | 0 |  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Infrastructure - Services |  | Subtransmission | Augmentation | SubtransmissionAugmentation |  |  | ea | 0 | 0 |  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Civil works | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Earthworks | Subtransmission | Augmentation | SubtransmissionAugmentation | 0 |  | ea | 0 | 0 |  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Buildings | Subtransmission | Augmentation | SubtransmissionAugmentation | 0 |  | ea | 0 | 0 |  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 22kV switchyard - install new puraceptor | Subtransmission | Augmentation | SubtransmissionAugmentation | 131.3953 |  | ea | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| - Other | Subtransmission | Augmentation | SubtransmissionAugmentation | 0 |  | ea | 0 | 0 |  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Construction delivery & site control |  | Subtransmission | Augmentation | SubtransmissionAugmentation | 0 |  | ea | 0 | 0 |  |  |  | 0
Land purchase |  | Land | Non-Network | LandNon-Network | 0 |  | ea | 0 | 0 |  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Subtotal Remote REFCL works | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0
Check | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0
Feeder works |  |  |  |  | Material $/Unit | QTY | UOM | Materials | Int Labour | Contracts - Design | Contracts - Construct | Other | P50 Total
Remote REFCLs
Lines works at <spare> feeders
| 22kV Underground Cable 300mm2 XLPE | Distribution system assets | Augmentation | Distribution system assetsAugmentation | 0.064197 |  | p/mtr | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Install new ACR for switching | Distribution system assets | Augmentation | Distribution system assetsAugmentation | 22.6039 |  | ea | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30.31% | 32.45% | 37.24%
| Concrete Poles 15.5m Replacement (includes installation), per pole | Distribution system assets | Replacement | Distribution system assetsReplacement | 6.06 |  | ea | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Subtotal Lines works | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0
Isolation Transformers
Install three isolation transformers
| Concrete Poles 15.5m Replacement (includes installation), per pole | Distribution system assets | Replacement | Distribution system assetsReplacement | 6.06 |  | ea | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Capacitance reducing isolation substation (300 kVA) | Subtransmission | Augmentation | SubtransmissionAugmentation | 18.9974 |  | ea | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Install new ACR for switching | Distribution system assets | Augmentation | Distribution system assetsAugmentation | 22.6039 |  | ea | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30.31% | 32.45% | 37.24%
| 22kV Underground Cable 185mm2 XLPE | Distribution system assets | Augmentation | Distribution system assetsAugmentation | 0.043775 |  | p/mtr | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Subtotal Install three isolation transformers | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0
Subtotal feeder works | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0
Check | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0
Grand Total | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0
Check | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0
| Remote REFCL works | Subtransmission | Augmentation | SubtransmissionAugmentation |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Subtransmission | Replacement | SubtransmissionReplacement |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
|  | SCADA/Network control | Augmentation | SCADA/Network controlAugmentation |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
|  | SCADA/Network control | Replacement | SCADA/Network controlReplacement |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Land | Non-Network | LandNon-Network |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
[8 empty] | 0 | 0 | 0 | 0 | 0 | 0
| Design, Project Management & Engineering costs allocation | Subtransmission | Augmentation | SubtransmissionAugmentation |  |  |  |  | 0 | 0 | 0 |  | 0
|  | Subtransmission | Replacement | SubtransmissionReplacement |  |  |  |  | 0 | 0 | 0 |  | 0
|  | SCADA/Network control | Augmentation | SCADA/Network controlAugmentation |  |  |  |  | 0 | 0 | 0 |  | 0
|  | SCADA/Network control | Replacement | SCADA/Network controlReplacement |  |  |  |  | 0 | 0 | 0 |  | 0
|  | Land | Non-Network | LandNon-Network |  |  |  |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 | 0 | 0 | 0
| Total Remote works | Subtransmission | Augmentation | SubtransmissionAugmentation |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Subtransmission | Replacement | SubtransmissionReplacement |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
|  | SCADA/Network control | Augmentation | SCADA/Network controlAugmentation |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
|  | SCADA/Network control | Replacement | SCADA/Network controlReplacement |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Land | Non-Network | LandNon-Network |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
[8 empty] | 0 | 0 | 0 | 0 | 0 | 0
[8 empty] | 0 | 0 | 0 | 0 | 0 | 0
| Lines works at <spare> feeders | Subtransmission | Augmentation | SubtransmissionAugmentation |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Subtransmission | Replacement | SubtransmissionReplacement |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Distribution system assets | Augmentation | Distribution system assetsAugmentation |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Distribution system assets | Replacement | Distribution system assetsReplacement |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
[8 empty] | 0 | 0 | 0 | 0 | 0 | 0
[8 empty] | 0 | 0 | 0 | 0 | 0 | 0
| Install three isolation transformers | Subtransmission | Augmentation | SubtransmissionAugmentation |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Subtransmission | Replacement | SubtransmissionReplacement |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Distribution system assets | Augmentation | Distribution system assetsAugmentation |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Distribution system assets | Replacement | Distribution system assetsReplacement |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
[8 empty] | 0 | 0 | 0 | 0 | 0 | 0
[8 empty] | 0 | 0 | 0 | 0 | 0 | 0
Note on G48: AST: Average unit rate across all cable types, excluding feeder exit cable

## #IR004A & CY2020
Table 1: Kalkallo - Actual costs incurred - "Direct Costs basis"
2016 to 2019 actual costs per IR#004A
Direct Expenditure - $Nominal ($0's)
| RIN category | Actual | Actual | Actual | Actual | Forecast
Project Desc |  | CY2016 | CY2017 | CY2018 | CY2019 | CY2020 | TOTAL | Comment
REFCL T3 ZS WORK - KLO | AUGEX | 14214.53 | 3894.61 | 6080.66 | 208981.81 | 40973.51 | 274145.12 | KLO Zone substation works currently in planning phase. LTD costs as at 31 Oct 2020 includes a joint planning report from WSP for the KLO solution (AusNet cost portion $72.5k excl GST)
REFCL T3 SURGE ARRESTORS - KLO | REPEX | 0 | 0 | 0 | 42193.8781 | 44830.9954 | 87024.8735 | Includes 33 sites completed so far for T3 KLO.
REFCL T3 NETWORK BALANCING - KLO | AUGEX | 0 | 0 | 0 | 0 | 0 | 0 | Network balancing not yet commenced for T3 KLO sites
REFCL T1 SURGE ARRESTORS - KLO | REPEX | 0 | 0 | 320854.9 | 16887.1 | 0 | 337742 | Under T1, 127 sites completed for KLO14 transfer feeder and a portion of the feeder has been balanced.
REFCL T1 NETWORK BALANCING - KLO | AUGEX | 0 | 0 | 12898.8876 | 93780.8797 | 0 | 106679.7672
Total KLO costs incurred - $Nominal |  | 14214.53 | 3894.61 | 339834.4476 | 361843.6677 | 85804.5054 | 805591.7607
CPI Index - Mid Year Nominal to $Jun 2021 |  | 1.0891 | 1.0754 | 1.0598 | 1.0389 | 1.0202
Total KLO T3 costs incurred - real $Jun-21 |  | 15480.5512 | 4188.4271 | 6444.1869 | 260958.0488 | 87539.9017 | 374611.1157

## Unit_Rates
| Direct Cost Unit Rates - $000's, Real $2019 |  |  |  | Confidential
Zone Substation works Unit Rates
Primary Plant
|  |  |  | Unit | [8 empty] | Volumes by Station
|  | Category | Description | Rate ($k) | Classification | Asset Class | Expenditure Class | Materials | Contracts | Other |  |  | KLO | <spare>
|  | Station service transformer (500 kVA) | Replace or install new station service transformer (500 kVA) |  | Capex | Subtransmission | Augmentation | 72.619 |  |  |  |  | 0 | 0
|  | Station service transformer (750 kVA) | Replace or install new station service transformer (750 kVA) |  | Capex | Subtransmission | Augmentation | 112.828 |  |  |  |  | 0 | 0
| ASD inserted | Station service transformer (200 kVA) | Replace or install new station service transformer (200 kVA) incl. footing |  | Capex | Subtransmission | Augmentation | 47.7187 |  |  |  |  | 2 | 0
| ASD inserted | Capacitance reducing isolation substation (300 kVA) | Install capacitance reducing isolation substation (300 kVA) |  | Capex | Subtransmission | Augmentation | 18.9974 |  |  |  |  | 0 | 0
| ASD inserted | Capacitance reducing isolation substation (1 MVA) | Install capacitance reducing isolation substation (1 MVA) |  | Capex | Subtransmission | Augmentation | 80.0253 |  |  |  |  | 0 | 0
| ASD inserted | Capacitance reducing isolation substation (5 / 7.5 MVA) | Install capacitance reducing isolation substation (5 / 7.5 MVA) incl. footing |  | Capex | Subtransmission | Augmentation | 907.5436 |  |  |  |  | 4 | 0
|  | Capacitance reducing isolation substation (7.5 MVA) | Install capacitance reducing isolation substation (7.5 MVA) |  | Capex | Subtransmission | Augmentation | 426.8068 |  |  |  |  | 0 | 0
|  | Capacitance reducing isolation substation (10 MVA) | Install capacitance reducing isolation substation (10 MVA) |  | Capex | Subtransmission | Augmentation | 465.0023 |  |  |  |  | 0 | 0
| ASD inserted | Capacitance reducing isolation substation (12.5 MVA) | Install capacitance reducing isolation substation (12.5 MVA) incl. footing |  | Capex | Subtransmission | Augmentation | 1184.6455 |  |  |  |  | 2 | 0
|  | AC changeover board - Station | Installation of outdoor changeover board |  | Capex | Subtransmission | Augmentation | 39.295 |  |  |  |  | 0 | 0
|  | AC changeover board - REFCL | Installation of outdoor changeover board suitable for uprated Station Service Tx, incl. footing |  | Capex | Subtransmission | Augmentation | 42.975 |  |  |  |  | 0 | 0
|  | AC C/O board footing | AC C/O board footing |  | Capex | Subtransmission | Augmentation | 0 |  |  |  |  | 0 | 0
|  | Arc Suppression Coil | Installation of ASC |  | Capex | SCADA/Network control | Augmentation | 1158.3 |  |  |  |  | 3 | 0
|  | ASC footing | Install new footing and associated bunding for GFN ASC unit |  | Capex | Subtransmission | Augmentation | 0 |  |  |  |  | 2 | 0
|  | 22kV switchboard - Metro | Installation of 22 kV switchboard - Metro |  | Capex | Subtransmission | Augmentation | 1354 |  |  |  |  | 0 | 0
|  | 22kV switchboard - Rural | Installation of 22 kV switchboard - Rural |  | Capex | Subtransmission | Augmentation | 1461.1163 |  |  |  |  | 0 | 0
|  | 22kV switchboard (no building) - Rural | Installation of 22 kV switchboard only (no building) - Rural |  | Capex | Subtransmission | Augmentation | 700 |  |  |  |  | 0 | 0
|  | 22kV Capacitor Banks | Installation of 22 kV capacitor banks |  | Capex | Subtransmission | Augmentation | 127.032 |  |  |  |  | 0 | 0
|  | 22kV Capacitor Bank (2x3 MVAr) - type 4 | Installation of 2x3 MVAr Capacitor Bank |  | Capex | Subtransmission | Augmentation | 465.78 |  |  |  |  | 0 | 0
|  | 22kV Capacitor Bank (2x3 MVAr) - type 2 | Installation of 2x3 MVAr Capacitor Bank |  | Capex | Subtransmission | Augmentation | 406.8 |  |  |  |  | 0 | 0
|  | 22kV Capacitor Bank (4 x3 MVAr) - type 3 | Installation of 4x3 MVAr Capacitor Bank |  | Capex | Subtransmission | Augmentation | 686.545 |  |  |  |  | 0 | 0
|  | 22kV Capacitor Bank - Modify | Modify existing capacitor bank |  | Capex | Subtransmission | Augmentation | 91.2924 |  |  |  |  | 0 | 0
|  | Cap Bank footing | Cap Bank footing |  | Capex | Subtransmission | Augmentation | 0 |  |  |  |  | 0 | 0
|  | 22kV Dead Tank Circuit Breaker | 22kV Dead Tank Circuit Breaker 3150A, 40kA |  | Capex | Subtransmission | Augmentation | 107.006 |  |  |  |  | 0 | 0
|  | 22kV U/S Isolator | 22kV Underslung Isolator |  | Capex | Subtransmission | Augmentation | 7.664 |  |  |  |  | 4 | 0
|  | 22KV Feeder Exit | 22KV Feeder Exit |  | Capex | Subtransmission | Augmentation | 0 |  |  |  |  | 0 | 0
|  | 22kV Voltage Transformer | 22kV Voltage Transformer |  | Capex | Subtransmission | Augmentation | 0 |  |  |  |  | 2 | 0
|  | 22kV Current Transformer | 22kV Current Transformer |  | Capex | Subtransmission | Augmentation | 27.163 |  |  |  |  | 2 | 0
|  | 22kV Zero Sequence CTs | Install core balance zero sequence current transformers |  | Capex | Subtransmission | Augmentation | 0 |  |  |  |  | 0 | 0
|  | 22KV Surge Arrestor | 22KV Surge Arrestor |  | Capex | Subtransmission | Augmentation | 0.62 |  |  |  |  | 2 | 0
|  | Transformer Neutral Isolator | Transformer Neutral Isolator |  | Capex | Subtransmission | Augmentation | 26.2223 |  |  |  |  | 0 | 0
|  | Neutral Bus | Installation of neutral bus |  | Capex | Subtransmission | Augmentation | 93.854 |  |  |  |  | 0 | 0
|  | REFCL control room | Installation of the REFCL control room only - no protection panels |  | Capex | Subtransmission | Augmentation | 0 |  |  |  |  | 0 | 0
|  | 2 REFCL control room | Installation of the REFCL control room only - no protection panels - supports 2 GFNs |  | Capex | Subtransmission | Augmentation | 0 |  |  |  |  | 0 | 0
| ASD inserted | Type 3 REFCL control room | Installation of REFCL control room with customised non-standard panels (incl. footing) |  | Capex | Subtransmission | Augmentation | 109.1759 |  |  |  |  | 2 | 0
|  | Battery Room (single battery set) | Installation of modular battery room including batteries (1 set of) |  | Capex | Subtransmission | Augmentation | 227.63 |  |  |  |  | 0 | 0
|  | Battery Room (2 battery sets) | Installation of modular battery room including batteries (2 sets of) |  | Capex | Subtransmission | Augmentation | 174.5855 |  |  |  |  | 0 | 0
|  | New Control Building | Installation of modular control building room |  | Capex | Subtransmission | Augmentation | 369.039 |  |  |  |  | 0 | 0
|  | Primary Cables - 22kV | Tx to Switchboard 22kV 630mm2 XLPE single phase (35mx6) |  | Capex | Subtransmission | Augmentation | 35.7406 |  |  |  |  | 0 | 0
|  | Primary Cables - 22kV | S/S to Switchboard 22kV 185mm2 XLPE single phase (30mx3) |  | Capex | Subtransmission | Augmentation | 11.0467 |  |  |  |  | 0 | 0
|  | Primary Cables - 22kV | ASC to Neutral Bus 22kV 95mm2 XLPE single phase (15m) |  | Capex | Subtransmission | Augmentation | 1.8816 |  |  |  |  | 0 | 0
|  | Feeder Exit Cables - 22kV | Feeder Exit Cables - 22kV 300mm (per metre) |  | Capex | Subtransmission | Augmentation | 0.05 |  |  |  |  | 0 | 0
|  | Primary Cable Testing | Testing of station 22 kV Cables |  | Capex | Subtransmission | Augmentation | 0 |  |  |  |  | 2 | 0
|  | Oil separator | Installation of Oil separator / Puraceptor |  | Capex | Subtransmission | Augmentation | 131.3953 |  |  |  |  | 0 | 0
|  | One Tilt Slab control room | Installation of a tilt slab building |  | Capex | Subtransmission | Augmentation | 0 |  |  |  |  | 0 | 0
|  | ASC only | Installation of a tilt slab building |  | Capex | Subtransmission | Augmentation | 430 |  |  |  |  | 0 | 0
Additional Primary Plant, Secondary and Lines Unit Rates - per IR#004A (14/04/2020)
Unit
|  | Category | Description | Rate ($k) | Classification | Asset Class | Expenditure Class | Materials | Contracts | Other
Primary |  | 66kV Bay - Ring Bus | 66kV Bay - Ring Bus (and 66kV vacant bay) |  | Capex | Subtransmission | Augmentation | 185.475 |  |  |  |  | 0 | 0
Primary |  | 66kV Exit - Line Feeder | 66kV Exit - Line Feeder |  | Capex | Subtransmission | Augmentation | 74.1545 |  |  |  |  | 0 | 0
Primary |  | 66kV Exit - Transformer | 66kV Exit - Transformer |  | Capex | Subtransmission | Augmentation | 37.494 |  |  |  |  | 0 | 0
Primary |  | Power transformer - 66/22kV 15/20MVA | Transformer - 66/22kV 15/20MVA |  | Capex | Subtransmission | Augmentation | 787.0745 |  |  |  |  | 0 | 0
Primary |  | Station service transformer (1 MVA) | Replace or install new station service transformer (1 MVA) |  | Capex | Subtransmission | Augmentation | 169.008 |  |  |  |  | 0 | 0
Primary |  | Decommission existing 10/16MVA Transformer | Decommission existing 10/16MVA Transformer |  | Capex | Subtransmission | Augmentation | 0 |  |  |  |  | 0 | 0
Primary |  | Power transformer - 66/22kV 20/33MVA | Installation of transformer - 66/22kV 20/33MVA |  | Capex | Subtransmission | Augmentation | 1126.5675 |  |  |  |  | 0 | 0
Primary |  | 66kV Surge Arrestor | 66kV Surge Arrestor |  | Capex | Subtransmission | Augmentation | 0.62196 |  |  |  |  | 0 | 0
Primary |  | 66kV 800A Rotary Disconnect | 66kV 800A Rotary Disconnect |  | Capex | Subtransmission | Augmentation | 25.198 |  |  |  |  | 0 | 0
Primary |  | 66kV Dead Tank Circuit Breaker | 66kv Dead Tank Circuit Breaker |  | Capex | Subtransmission | Augmentation | 117.012 |  |  |  |  | 0 | 0
Primary |  | 66kV U/S Isolator | 66kV Unuderslung Isolator |  | Capex | Subtransmission | Augmentation | 23.788 |  |  |  |  | 0 | 0
Primary |  | 22kV Indoor Switchgear - Transformers | 22kV Indoor Switchgear - Transformers |  | Capex | Subtransmission | Augmentation | 41.2559 |  |  |  |  | 0 | 0
Primary |  | 22kV Neutral Earthing Resistors | 22kV Neutral Earthing Resistors |  | Capex | Subtransmission | Augmentation | 106.8132 |  |  |  |  | 0 | 0
Primary |  | Earth Grid | Earth Grid (4,900 m2) |  | Capex | Subtransmission | Augmentation | 58.2657 |  |  |  |  | 0 | 0
Secondary | ASD inserted | 22kV Line Protection Panel | 22kV Line Protection Panel |  | Capex | SCADA/Network control | Augmentation | 63.4714 |  |  |  |  | 2 | 0
Secondary | ASD inserted | 66/22kV Transformer Protection Panel | 66/22kV Transformer Protection Panel |  | Capex | SCADA/Network control | Augmentation | 47.4106 |  |  |  |  | 2 | 0
Secondary |  | 66kV Line Protection Panel | 66kV Line Protection Panel |  | Capex | SCADA/Network control | Augmentation | 76.7296 |  |  |  |  | 0 | 0
Secondary |  | 66kV Substation Protection Panel (transformer & bus) | Substation Protection Panel (66/22kV Transformer & 66kV bus) |  | Capex | SCADA/Network control | Augmentation | 223.6578 |  |  |  |  | 0 | 0
Secondary |  | 66/22kV Transformer Voltage Control & Regulation Cubicle | 66/22kV Transformer Voltage Control & Regulation Cubicle (A-EBERLE) |  | Capex | SCADA/Network control | Augmentation | 252.1155 |  |  |  |  | 0 | 0
Secondary | ASD inserted | High Impedance Busbar Protection cubicle | High Impedance Busbar Protection cubicle |  | Capex | SCADA/Network control | Augmentation | 58.4171 |  |  |  |  | 0 | 0
Lines |  | Concrete Poles 20m (includes installation), per pole | Pole - Concrete 20m, 16kN working load, includes installation |  | Capex | Subtransmission | Augmentation | 5.4308 |  |  |  |  | 0 | 0
Lines |  | Cross Arms 66kV - Intermediate & Strain | Cross Arms 66kV - Intermediate & Strain (incl. insulators & hardware) |  | Capex | Subtransmission | Augmentation | 0.40306 |  |  |  |  | 0 | 0
Lines |  | Cross Arms 22kV HV - Intermediate & Strain | Cross Arms 22kV HV - Intermediate & Strain (incl. insulators & hardware) |  | Capex | Distribution system assets | Augmentation | 0.66462 |  |  |  |  | 0 | 0
| ASD inserted | Cross Arms 22kV HV - Intermediate & Strain (Replacement) | Cross Arms 22kV HV - Intermediate & Strain (incl. insulators & hardware) |  | Capex | Distribution system assets | Replacement | 0.66462 |  |  |  |  | 31 | 0
Lines |  | Cross Arms 22kV LV - Intermediate & Strain | Cross Arms 22kV LV - Intermediate & Strain (Incl. Insulators & Hardware) |  | Capex | Distribution system assets | Augmentation | 0.43615 |  |  |  |  | 0 | 0
Lines |  | Stays | Stays |  | Capex | Subtransmission | Augmentation | 0.24562 |  |  |  |  | 0 | 0
Lines |  | Conductor (19/4.75 AAC) | Conductor (19/4.75 AAC) - Per km, installed |  | Capex | Subtransmission | Augmentation | 15.18 |  |  |  |  | 0 | 0
Lines |  | Conductor (19/3.25 AAC) | Conductor (19/3.25 AAC) - Per km, installed |  | Capex | Distribution system assets | Augmentation | 6.7848 |  |  |  |  | 0 | 0
Lines |  | Supervision, Traffic Control, Set-Up Site & Clean-Up | Supervision, Traffic Control, Set-Up Site & Clean-Up |  | Capex | Subtransmission | Augmentation | 0 |  |  |  |  | 0 | 0
Lines |  | ADSS Fibre Optic Cable | ADSS per km (Installed on Existing Poles) |  | Capex | Subtransmission | Augmentation | 8.72 |  |  |  |  | 0 | 0
Lines |  | OPGW Joint Box (Installed & Terminated on Existing Tower/Pole) | OPGW Joint Box (Installed & Terminated on Existing Tower/Pole) |  | Capex | Subtransmission | Augmentation | 6.795 |  |  |  |  | 0 | 0
Lines |  | Vegetation Clearing | Vegetation Clearing - Light 66kV/22kV Line (Per km) |  | Capex | Subtransmission | Augmentation | 0 |  |  |  |  | 1.005 | 0
Lines |  | <spare> |  |  | Capex | Subtransmission | Augmentation | 0 |  |  |  |  | 0 | 0
Lines |  | Concrete Poles 15.5m (includes installation), per pole | Pole - Concrete 15.5m, 12kN working load (24kN ultimate) |  | Capex | Distribution system assets | Augmentation | 6.06 |  |  |  |  | 0 | 0
Lines | ASD inserted | Concrete Poles 15.5m Replacement (includes installation), per pole | Pole - Concrete 15.5m, 12kN working load (24kN ultimate) |  | Capex | Distribution system assets | Replacement | 6.06 |  |  |  |  | 20 | 0
Lines |  | 22kV Underground Cable (150m) | XLPE 3 Core 22kV Cable |  | Capex | Distribution system assets | Augmentation | 0.061705 |  |  |  |  | 0 | 0
Lines | ASD inserted | Decommission and remove existing conductor (route length) at various locations - includes AAC, ASCR, Steel | Decommission and remove existing conductor (route length) at various locations - includes AAC, ASCR, Steel |  | Capex | Distribution system assets | Replacement | 0 |  |  |  |  | 12.395 | 0
Lines | ASD inserted | Install 151mm2 Covered Aluminium Conductor | Install 151mm2 Covered Aluminium Conductor |  | Capex | Distribution system assets | Augmentation | 131.4797 |  |  |  |  | 3.175 | 0
Lines | ASD inserted | Install 62mm2 Covered Steel Conductor | Intsall 62mm2 Covered Steel Conductor |  | Capex | Distribution system assets | Augmentation | 111.563 |  |  |  |  | 9.3 | 0
Lines | ASD inserted | 22kV Underground Cable 185mm2 XLPE | XLPE 3 Core 22kV Cable (includes trench and install conduit) |  | Capex | Distribution system assets | Augmentation | 0.043775 |  |  |  |  | 450 | 0
Lines | ASD inserted | 22kV Underground Cable 300mm2 XLPE | XLPE 3 Core 22kV Cable (includes trench and install conduit) |  | Capex | Distribution system assets | Augmentation | 0.064197 |  |  |  |  | 200 | 0
Lines | ASD inserted | 22KV cable terminations | 22KV cable terminations |  | Capex | Distribution system assets | Augmentation | 3.1912 |  |  |  |  | 8 | 0
Lines | ASD inserted | Convert existing pole to hybrid fused substation | Convert existing pole to hybrid fused substation |  | Capex | Distribution system assets | Augmentation | 38.1818 |  |  |  |  | 0 | 0
Lines | ASD inserted | Underground HV ABC | Underground HV ABC ($per metre) |  | Capex | Distribution system assets | Augmentation | 0.036479 |  |  |  |  | 0 | 0
Lines |  | Gas Switch | Gas Switch (supply only) |  | Capex | Distribution system assets | Augmentation | 15.42 |  |  |  |  | 0 | 0
Protection & Control
Unit
|  | Category | Description | Rate ($k) | Classification | Asset Class | Expenditure Class | Materials | Contracts | Other
|  | Neutral Bus controller - 1 GFN | Installation of neutral bus controller |  | Capex | SCADA/Network control | Augmentation | 48.9823 |  |  |  |  | 0 | 0
|  | Neutral Bus controller - 2 GFNs | Installation of neutral bus controller |  | Capex | SCADA/Network control | Augmentation | 61.8191 |  |  |  |  | 0 | 0
|  | Protection – GFN panels | Interface, control panel and inverter |  | Capex | SCADA/Network control | Augmentation | 6.2431 |  |  |  |  | 0 | 0
|  | GFN interface relay | GFN interface relay |  | Capex | SCADA/Network control | Augmentation | 8.6956 |  |  |  |  | 0 | 0
|  | Power Quality/Switchgear Interface | Installation of Panel with 2 Power Quality Meters & 1 Switchgear interface relay |  | Capex | SCADA/Network control | Augmentation | 98.0077 |  |  |  |  | 0 | 0
|  | Power Quality Non Std | Installation of Panel with 6 Power Quality Meters |  | Capex | SCADA/Network control | Augmentation | 197.6553 |  |  |  |  | 0 | 0
|  | Switchgear Interface Non Std | Installation of Panel with 3 switchgear interface relays |  | Capex | SCADA/Network control | Augmentation | 164.0238 |  |  |  |  | 0 | 0
|  | Capacitor Bank Prot & Cntl (3x3MVAr) | Installation of Panel for Prot & Cntl of 3 x 3MVAr Capacitor Bank |  | Capex | SCADA/Network control | Augmentation | 41.9661 |  |  |  |  | 0 | 0
|  | Capacitor Bank Prot & Cntl (2x3MVAr) | Installation of Panel for Prot & Cntl of 2 x 3MVAr Capacitor Bank |  | Capex | SCADA/Network control | Augmentation | 33.6836 |  |  |  |  | 0 | 0
|  | Remote Terminal Unit | Install new RTU (existing MD1000 incapable of handling traffic of new relays) |  | Capex | SCADA/Network control | Augmentation | 149.3397 |  |  |  |  | 0 | 0
|  | SCIMS system - small | Install a new Substation Automation panel (SCIMS) in existing control room |  | Capex | SCADA/Network control | Augmentation | 92.2396 |  |  |  |  | 2 | 0
Network Balancing Unit Rates
|  |  |  | Unit | [5 empty] | Contracts - Design | Contracts - Construct
|  | Category | Description | Rate ($k) | Classification | Asset Class | Expenditure Class | Materials | Labour |  |  | Other
|  | Design | Design activities to determine network balancing requirements, validate balancing and record balancing information – per feeder | 23.5834 | Capex | Distribution system assets | Augmentation | 0 | 2.1827 | 3.9889 | 0 | 0 | WYK2 rate
[6 empty] | Distribution system assets | Augmentation | 0 | 8.4884 | 19.7659 | 0 | 0 | Other stations rate |  | 0 | 0
|  | Third conductor installation | Install 3rd conductor – per span |  | Capex | Distribution system assets | Augmentation | [7 empty] | 0 | 0
|  | Unbonding cable | Unbounding cable at either end – per location |  | Capex | Distribution system assets | Augmentation | [7 empty] | 0 | 0
|  | Phase rotation | Rotate phases – per rotation |  | Capex | Distribution system assets | Augmentation | [7 empty] | 0 | 0
|  | Balancing capacitors | Install balancing capacitors (single or three phase) – per installation | 58.5792 | Capex | Distribution system assets | Augmentation | 18.1336 | 3.4598 | 0 | 32.9257 | 4.0601 |  |  | 0 | 0
| Inherent works |  | Activities including the development of balancing capacitor solution, modification of Asset Management Systems - per feeder | 15.0738 | Capex | Distribution system assets | Augmentation | 0 | 6.5904 | 0 | 8.4834 | 0 |  |  | 0 | 0 | Inherent works - various feeder based works
|  |  | Phase plate correction - per feeder and RC sections | 0.56752 | Capex | Distribution system assets | Replacement | 0 | 0 | 0 | 0.56752 | 0 |  |  | 0 | 0 | Phase plate correction
|  |  | Protection reviews for fuse removals and installation of solid link - per fuse | 3.3465 | Capex | Distribution system assets | Replacement | 0 | 0.16261 | 0 | 3.1839 | 0 |  |  | 0 | 0 | Fuse removal and install solid link
|  |  | Installation of fusesaver and remote control unit - per site | 39.1276 | Capex | Distribution system assets | Augmentation | 12.4291 | 3.261 | 1.6352 | 21.8023 | 0 |  |  | 0 | 0 | Install fusesaver and control box - per site
|  | Install new ACR for switching | Install new ACR for switching | 80.3688 | Capex | Distribution system assets | Augmentation | 22.6039 | 20.3508 | 4.7858 | 25.9801 | 6.6482 |  |  | 1 | 0 | Install new ACR for switching
|  |  | Purchase of phase identification tools - G3 Phase ID probe | 13.0922 | Capex | Non-network general assets - Other | Non-network | 13.0922 | 0 | 0 | 0 | 0 |  |  | 0 | 0
|  |  | - Base station | 8.8476 | Capex | Non-network general assets - Other | Non-network | 8.8476 | 0 | 0 | 0 | 0 |  |  | 0 | 0
Line Hardening Unit Rates
|  |  |  | Unit | [5 empty] | Contracts - Design | Contracts - Construct
|  | Category | Description | Rate ($k) | Classification | Asset Class | Expenditure Class | Materials | Labour |  |  | Other
|  | Surge arrestor | Replace surge arrestor on existing structure - per site | 2.6371 | Capex | Distribution system assets | Replacement | 0.75701 | 0.38862 | 0 | 1.4915 | 0 |  |  | 0 | 0
|  |  | - per unit | 1.3186 | Capex | Distribution system assets | Replacement | 0.3785 | 0.19431 | 0 | 0.74574 | 0 |  |  | 0 | 0
|  | Cables | Cable On-Line Testing | 0.32009 | Capex | Distribution system assets | Replacement | 0 | 0.32009 | 0 | 0 | 0 |  |  | 0 | 0
|  |  | Cable Off-Line Testing | 10.6697 | Capex | Distribution system assets | Replacement | 0 | 10.6697 | 0 | 0 | 0 |  |  | 0 | 0
|  |  | Cable - Replace Fitting | 22.5907 | Capex | Distribution system assets | Replacement | 5.2026 | 0 | 0 | 17.3882 | 0 |  |  | 0 | 0
|  |  | Cable - Replace Cable Section - per m | 0.55 | Capex | Distribution system assets | Replacement | 0.05 | 0 | 0 | 0.5 | 0 | $550 per m |  | 0 | 0
|  | Other | CERA Removal and Replacement with 900kVAr Pole Top Capacitor | 70.807 | Capex | Distribution system assets | Augmentation | 31.2155 | 0 | 0 | 39.5915 | 0 |  |  | 0 | 0
Compatible Equipment Unit Rates
|  |  |  | Unit | [5 empty] | Contracts - Design | Contracts - Construct
|  | Category | Description | Rate ($k) | Classification | Asset Class | Expenditure Class | Materials | Labour |  |  | Other
|  | ACR upgrade | Replace control box on ACR | 55.1611 | Capex | Distribution system assets | Replacement | 15 | 2.5 | 4.8 | 32.8611 | 0 |  |  | 0 | 0
|  | ACR replacement | Replace pole-mounted ACR | 67.517 | Capex | Distribution system assets | Replacement | 22.6039 | 7.499 | 4.7858 | 25.9801 | 6.6482 |  |  | 0 | 0
| ASD inserted | New ACR unit and control box | New ACR unit and control box | 122.6781 | Capex | Distribution system assets | Augmentation | 37.6039 | 9.999 | 9.5858 | 58.8412 | 6.6482 | 0 |  | 8 | 0
|  | Voltage regulator upgrade | Replace control box on voltage regulator | 50.2821 | Capex | Distribution system assets | Replacement | 15.156 | 23.7105 | 0 | 11.4156 | 0 |  |  | 0 | 0
|  | Voltage regulator replacement | Replace voltage regulator | 361.8832 | Capex | Distribution system assets | Replacement | 193.2305 | 36.7756 | 0 | 131.8771 | 0 |  |  | 0 | 0
Code Compliance Unit Rates
|  |  |  | Unit | [5 empty] | Contracts - Design | Contracts - Construct
|  | Category | Description | Rate ($k) | Classification | Asset Class | Expenditure Class | Materials | Labour |  |  | Other
|  | Code compliance | Install isolating transformer and associated equipment adjacent to high-voltage customer – per site, 3.0 MVA substation | 0 | Capex | Distribution system assets | Augmentation | [5 empty] | not applicable |  | 0 | 0
|  |  | 5 MVA substation | 0 | Capex | Distribution system assets | Augmentation | [5 empty] | not applicable |  | 0 | 0
|  |  | 7.5 MVA substation | 0 | Capex | Distribution system assets | Augmentation | [5 empty] | not applicable |  | 0 | 0
|  |  | ACR | 96.2512 | Capex | Distribution system assets | Replacement | 32.7402 | 10.5852 | 6.7696 | 36.5557 | 9.6005 |  |  | 0 | 0 | Line Hardening
Reliability maintained Unit Rates
|  |  |  | Unit | [5 empty] | Contracts - Design | Contracts - Construct
|  | Category | Description | Rate ($k) | Classification | Asset Class | Expenditure Class | Materials | Labour |  |  | Other
|  | Remote control switch | Replace remote controlled switch on existing structure - Design |  | Capex | Distribution system assets | Replacement | [7 empty] | 0 | 0
|  |  | - DFA2 software changes to SCADA |  | Capex | SCADA/Network control | Replacement | [7 empty] | 0 | 0
|  |  | - Materials supply and deployment of switches |  | Capex | Distribution system assets | Replacement | [7 empty] | 0 | 0
Live Line Equipment Purchases Unit Rates
|  |  |  | Unit | [5 empty] | Contracts - Design | Contracts - Construct
|  | Category | Description | Rate ($k) | Classification | Asset Class | Expenditure Class | Materials | Labour |  |  | Other
|  | Mid-span Isolator units | Devices used to reduce the outage area in the distribution network. Set of isolators that are cut into a line between two poles (i.e., mid-span) to provide a temporary break in connection. After an outage devices can be re-used elswhere on the network. | 16.8186 | Capex | Non-network general assets - Other | Non-network | 16.8186 | 0 | 0 | 0 | 0
|  | Rigid Hoppers | Cable with clamp at each end that is placed inside an insulating tube. | 1.9867 | Capex | Non-network general assets - Other | Non-network | 1.9867 | 0 | 0 | 0 | 0
|  | Line cut-out tools | Set of tools used to cut into a line, e.g., for temporary installation of mid-span isolators | 1.0617 | Capex | Non-network general assets - Other | Non-network | 1.0617 | 0 | 0 | 0 | 0
|  | New Line Hoses | New Line Hoses (to replace Hard Covers) on 22kV lines | 0.24807 | Opex | Non-network general assets - Other | Non-network | 0.24807 | 0 | 0 | 0 | 0

## Unit_Rates - $2015
Direct Cost Unit Rates - $000's, Real $2015 |  |  |  | Confidential
SOURCE: ASD - Attachment 22 - AST Contingent Project 3 Total Cost Model_CONFIDENTIAL (AER & AST amended)_19.09.19.xlsx
Zone Substation works Unit Rates
Primary Plant
|  |  | Unit | [9 empty] | Volumes by Station
| Category | Description | Rate ($k) | Classification | Asset Class | Expenditure Class | Materials | Contracts | Other |  |  |  | KLO | <spare>
| Station service transformer (500 kVA) | Replace or install new station service transformer (500 kVA) |  | Capex | Subtransmission | Augmentation | 68.5061
| Station service transformer (750 kVA) | Replace or install new station service transformer (750 kVA) |  | Capex | Subtransmission | Augmentation | 106.4377
| Capacitance reducing isolation substation (7.5 MVA) | Install capacitance reducing isolation substation (7.5 MVA) |  | Capex | Subtransmission | Augmentation | 402.6337
| Capacitance reducing isolation substation (10 MVA) | Install capacitance reducing isolation substation (10 MVA) |  | Capex | Subtransmission | Augmentation | 358.3857
| AC changeover board - Station | Installation of outdoor changeover board |  | Capex | Subtransmission | Augmentation | 37.0694
| AC changeover board - REFCL | Installation of outdoor changeover board suitable for uprated Station Service Tx, incl. footing |  | Capex | Subtransmission | Augmentation | 40.541
| AC C/O board footing | AC C/O board footing |  | Capex | Subtransmission | Augmentation | 0
| Arc Suppression Coil | Installation of ASC |  | Capex | SCADA/Network control | Augmentation | 1092.6972
| ASC footing | Install new footing and associated bunding for GFN ASC unit |  | Capex | Subtransmission | Augmentation | 0
| 22kV switchboard - Metro | Installation of 22 kV switchboard - Metro |  | Capex | Subtransmission | Augmentation | 1277.3133
| 22kV switchboard - Rural | Installation of 22 kV switchboard - Rural |  | Capex | Subtransmission | Augmentation | 1378.3628
| 22kV switchboard (no building) - Rural | Installation of 22 kV switchboard only (no building) - Rural |  | Capex | Subtransmission | Augmentation | 660.354
| 22kV Capacitor Banks | Installation of 22 kV capacitor banks |  | Capex | Subtransmission | Augmentation | 119.8372
| 22kV Capacitor Bank (2x3 MVAr) - type 4 | Installation of 2x3 MVAr Capacitor Bank |  | Capex | Subtransmission | Augmentation | 439.3995
| 22kV Capacitor Bank (2x3 MVAr) - type 2 | Installation of 2x3 MVAr Capacitor Bank |  | Capex | Subtransmission | Augmentation | 383.76
| 22kV Capacitor Bank (4 x3 MVAr) - type 3 | Installation of 4x3 MVAr Capacitor Bank |  | Capex | Subtransmission | Augmentation | 647.661
| 22kV Capacitor Bank - Modify | Modify existing capacitor bank |  | Capex | Subtransmission | Augmentation | 86.1219
| Cap Bank footing | Cap Bank footing |  | Capex | Subtransmission | Augmentation | 0
| 22kV Dead Tank Circuit Breaker | 22kV Dead Tank Circuit Breaker 3150A, 40kA |  | Capex | Subtransmission | Augmentation | 100.9455
| 22kV U/S Isolator | 22kV Underslung Isolator |  | Capex | Subtransmission | Augmentation | 7.2299
| 22KV Feeder Exit | 22KV Feeder Exit |  | Capex | Subtransmission | Augmentation | 0
| 22kV Voltage Transformer | 22kV Voltage Transformer |  | Capex | Subtransmission | Augmentation | 0
| 22kV Current Transformer | 22kV Current Transformer |  | Capex | Subtransmission | Augmentation | 25.6246
| 22kV Zero Sequence CTs | Install core balance zero sequence current transformers |  | Capex | Subtransmission | Augmentation | 0
| 22KV Surge Arrestor | 22KV Surge Arrestor |  | Capex | Subtransmission | Augmentation | 0.58488
| Transformer Neutral Isolator | Transformer Neutral Isolator |  | Capex | Subtransmission | Augmentation | 24.7371
| Neutral Bus | Installation of neutral bus |  | Capex | Subtransmission | Augmentation | 88.5384
| REFCL control room | Installation of the REFCL control room only - no protection panels |  | Capex | Subtransmission | Augmentation | 0
| 2 REFCL control room | Installation of the REFCL control room only - no protection panels - supports 2 GFNs |  | Capex | Subtransmission | Augmentation | 0
| Battery Room (single battery set) | Installation of modular battery room including batteries (1 set of) |  | Capex | Subtransmission | Augmentation | 214.7377
| Battery Room (2 battery sets) | Installation of modular battery room including batteries (2 sets of) |  | Capex | Subtransmission | Augmentation | 164.6975
| New Control Building | Installation of modular control building room |  | Capex | Subtransmission | Augmentation | 348.1377
| Primary Cables - 22kV | Tx to Switchboard 22kV 630mm2 XLPE single phase (35mx6) |  | Capex | Subtransmission | Augmentation | 33.7163
| Primary Cables - 22kV | S/S to Switchboard 22kV 185mm2 XLPE single phase (30mx3) |  | Capex | Subtransmission | Augmentation | 10.421
| Primary Cables - 22kV | ASC to Neutral Bus 22kV 95mm2 XLPE single phase (15m) |  | Capex | Subtransmission | Augmentation | 1.775
| Feeder Exit Cables - 22kV | Feeder Exit Cables - 22kV 300mm (per metre) |  | Capex | Subtransmission | Augmentation | 0.047168
| Primary Cable Testing | Testing of station 22 kV Cables |  | Capex | Subtransmission | Augmentation | 0
| Oil separator | Installation of Oil separator / Puraceptor |  | Capex | Subtransmission | Augmentation | 123.9535
| One Tilt Slab control room | Installation of a tilt slab building |  | Capex | Subtransmission | Augmentation
Protection & Control
Unit
| Category | Description | Rate ($k) | Classification | Asset Class | Expenditure Class | Materials | Contracts | Other
| Neutral Bus controller - 1 GFN | Installation of neutral bus controller |  | Capex | SCADA/Network control | Augmentation | 46.2081
| Neutral Bus controller - 2 GFNs | Installation of neutral bus controller |  | Capex | SCADA/Network control | Augmentation | 58.3179
| Protection – GFN panels | Interface, control panel and inverter |  | Capex | SCADA/Network control | Augmentation | 5.8895
| GFN interface relay | GFN interface relay |  | Capex | SCADA/Network control | Augmentation | 8.2031
| Power Quality/Switchgear Interface | Installation of Panel with 2 Power Quality Meters & 1 Switchgear interface relay |  | Capex | SCADA/Network control | Augmentation | 92.4568
| Power Quality Non Std | Installation of Panel with 6 Power Quality Meters |  | Capex | SCADA/Network control | Augmentation | 186.4607
| Switchgear Interface Non Std | Installation of Panel with 3 switchgear interface relays |  | Capex | SCADA/Network control | Augmentation | 154.7339
| Capacitor Bank Prot & Cntl (3x3MVAr) | Installation of Panel for Prot & Cntl of 3 x 3MVAr Capacitor Bank |  | Capex | SCADA/Network control | Augmentation | 39.5892
| Capacitor Bank Prot & Cntl (2x3MVAr) | Installation of Panel for Prot & Cntl of 2 x 3MVAr Capacitor Bank |  | Capex | SCADA/Network control | Augmentation | 31.7758
| Remote Terminal Unit | Install new RTU (existing MD1000 incapable of handling traffic of new relays) |  | Capex | SCADA/Network control | Augmentation | 140.8816
| SCIMS system - small | Install a new Substation Automation panel (SCIMS) in existing control room |  | Capex | SCADA/Network control | Augmentation | 87.0154
Network Balancing Unit Rates
|  |  | Unit | [5 empty] | Contracts - Design | Contracts - Construct
| Category | Description | Rate ($k) | Classification | Asset Class | Expenditure Class | Materials | Labour |  |  | Other
| Design | Design activities to determine network balancing requirements, validate balancing and record balancing information – per feeder | 23.5834 | Capex | Distribution system assets | Augmentation | 0 | 2.008 | 3.6591 | 0 | 0 | WYK2 rate
[5 empty] | Distribution system assets | Augmentation | 0 | 7.8091 | 18.1319 | 0 | 0 | Other stations rate
| Third conductor installation | Install 3rd conductor – per span |  | Capex | Distribution system assets | Augmentation
| Unbonding cable | Unbounding cable at either end – per location |  | Capex | Distribution system assets | Augmentation
| Phase rotation | Rotate phases – per rotation |  | Capex | Distribution system assets | Augmentation
| Balancing capacitors | Install balancing capacitors (single or three phase) – per installation | 54.3234 | Capex | Distribution system assets | Augmentation | 17.1066 | 3.1829 | 0 | 30.2038 | 3.8301
| Inherent works | Activities including the development of balancing capacitor solution, modification of Asset Management Systems - per feeder | 13.8451 | Capex | Distribution system assets | Augmentation | 0 | 6.0629 | 0 | 7.7821 | 0 |  |  |  | Inherent works - various feeder based works
|  | Phase plate correction - per feeder and RC sections | 0.5206 | Capex | Distribution system assets | Replacement | 0 | 0 | 0 | 0.5206 | 0 |  |  |  | Phase plate correction
|  | Protection reviews for fuse removals and installation of solid link - per fuse | 3.0703 | Capex | Distribution system assets | Replacement | 0 | 0.1496 | 0 | 2.9207 | 0 |  |  |  | Fuse removal and install solid link
|  | Installation of fusesaver and remote control unit - per site | 36.2252 | Capex | Distribution system assets | Augmentation | 11.7252 | 3 | 1.5 | 20 | 0 |  |  |  | Install fusesaver and control box - per site
|  | Install new ACR for switching | 62.7168 | Capex | Distribution system assets | Augmentation | 21.3237 | 6.8988 | 4.3902 | 23.8324 | 6.2717 |  |  |  | Install new ACR for switching
|  | Purchase of phase identification tools - G3 Phase ID probe | 12.3507 | Capex | Non-network general assets - Other | Non-network | 12.3507 | 0 | 0 | 0 | 0
|  | - Base station | 8.3465 | Capex | Non-network general assets - Other | Non-network | 8.3465 | 0 | 0 | 0 | 0
Line Hardening Unit Rates
|  |  | Unit | [5 empty] | Contracts - Design | Contracts - Construct
| Category | Description | Rate ($k) | Classification | Asset Class | Expenditure Class | Materials | Labour |  |  | Other
| Surge arrestor | Replace surge arrestor on existing structure - per site | 2.4398 | Capex | Distribution system assets | Replacement | 0.71413 | 0.35752 | 0 | 1.3682 | 0
|  | - per unit | 1.2199 | Capex | Distribution system assets | Replacement | 0.35707 | 0.17876 | 0 | 0.6841 | 0
| Cables | Cable On-Line Testing | 0.29448 | Capex | Distribution system assets | Replacement | 0 | 0.29448 | 0 | 0 | 0
|  | Cable Off-Line Testing | 9.8158 | Capex | Distribution system assets | Replacement | 0 | 9.8158 | 0 | 0 | 0
|  | Cable - Replace Fitting | 20.8587 | Capex | Distribution system assets | Replacement | 4.9079 | 0 | 0 | 15.9507 | 0
|  | Cable - Replace Cable Section - per m | 0.50583 | Capex | Distribution system assets | Replacement | 0.047168 | 0 | 0 | 0.45867 | 0 | $550 per m
| Other | CERA Removal and Replacement with 900kVAr Pole Top Capacitor | 65.7661 | Capex | Distribution system assets | Augmentation | 29.4475 | 0 | 0 | 36.3186 | 0
Compatible Equipment Unit Rates
|  |  | Unit | [5 empty] | Contracts - Design | Contracts - Construct
| Category | Description | Rate ($k) | Classification | Asset Class | Expenditure Class | Materials | Labour |  |  | Other
| ACR upgrade | Replace control box on ACR | 50.9982 | Capex | Distribution system assets | Replacement | 14.1504 | 2.2999 | 4.4032 | 30.1446 | 0
| ACR replacement | Replace pole-mounted ACR | 62.7168 | Capex | Distribution system assets | Replacement | 21.3237 | 6.8988 | 4.3902 | 23.8324 | 6.2717
| Voltage regulator upgrade | Replace control box on voltage regulator | 46.5825 | Capex | Distribution system assets | Replacement | 14.2976 | 21.813 | 0 | 10.4719 | 0
| Voltage regulator replacement | Replace voltage regulator | 337.0942 | Capex | Distribution system assets | Replacement | 182.2864 | 33.8325 | 0 | 120.9753 | 0
Code Compliance Unit Rates
|  |  | Unit | [5 empty] | Contracts - Design | Contracts - Construct
| Category | Description | Rate ($k) | Classification | Asset Class | Expenditure Class | Materials | Labour |  |  | Other
| Code compliance | Install isolating transformer and associated equipment adjacent to high-voltage customer – per site, 3.0 MVA substation | 0 | Capex | Distribution system assets | Augmentation | [5 empty] | not applicable
|  | 5 MVA substation | 0 | Capex | Distribution system assets | Augmentation | [5 empty] | not applicable
|  | 7.5 MVA substation | 0 | Capex | Distribution system assets | Augmentation | [5 empty] | not applicable
|  | ACR | 89.4244 | Capex | Distribution system assets | Replacement | 30.8859 | 9.738 | 6.21 | 33.5338 | 9.0568 |  |  |  | Line Hardening
Reliability maintained Unit Rates
|  |  | Unit | [5 empty] | Contracts - Design | Contracts - Construct
| Category | Description | Rate ($k) | Classification | Asset Class | Expenditure Class | Materials | Labour |  |  | Other
| Remote control switch | Replace remote controlled switch on existing structure - Design |  | Capex | Distribution system assets | Replacement
|  | - DFA2 software changes to SCADA |  | Capex | SCADA/Network control | Replacement
|  | - Materials supply and deployment of switches |  | Capex | Distribution system assets | Replacement
Live Line Equipment Purchases Unit Rates
|  |  | Unit | [5 empty] | Contracts - Design | Contracts - Construct
| Category | Description | Rate ($k) | Classification | Asset Class | Expenditure Class | Materials | Labour |  |  | Other
| Mid-span Isolator units | Devices used to reduce the outage area in the distribution network. Set of isolators that are cut into a line between two poles (i.e., mid-span) to provide a temporary break in connection. After an outage devices can be re-used elswhere on the network. | 15.866 | Capex | Non-network general assets - Other | Non-network | 15.866 | 0 | 0 | 0 | 0
| Rigid Hoppers | Cable with clamp at each end that is placed inside an insulating tube. | 1.8742 | Capex | Non-network general assets - Other | Non-network | 1.8742 | 0 | 0 | 0 | 0
| Line cut-out tools | Set of tools used to cut into a line, e.g., for temporary installation of mid-span isolators | 1.0015 | Capex | Non-network general assets - Other | Non-network | 1.0015 | 0 | 0 | 0 | 0
| New Line Hoses | New Line Hoses (to replace Hard Covers) on 22kV lines | 0.23402 | Opex | Non-network general assets - Other | Non-network | 0.23402 | 0 | 0 | 0 | 0

## Escalators
Escalators
SOURCE: ASD - Attachment 22 - AST Contingent Project 3 Total Cost Model_CONFIDENTIAL (AER & AST amended)_19.09.19.xlsx
CPI | Sep Qtr | Jun Qtr | Jun Qtr | Jun Qtr | Jun Qtr | Forecast | Forecast | Forecast | Forecast | Forecast | Forecast
| 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 | 2022 | 2023 | 2024 | 2025
Actual Inflation - 8 cities, 1 year lagged (Jun to Jun) | 2.308% | 1.511% | 1.023% | 1.934% | 2.078% | 2.25% | 2.45% | 2.45% | 2.45% | 2.45% | 2.45%
Decision Inflation (Amended) |  | 2.349% | 2.349% | 2.349% | 2.349% | 2.349% | 2.349% | 2.349% | 2.349% | 2.349% | 2.349%
Index - $2014 to Nominal (using outturn inflation) | 1.0231 | 1.0385 | 1.0492 | 1.0694 | 1.0917
Index - $2015 to nominal (using outturn inflation) | 1 | 1.0151 | 1.0255 | 1.0453 | 1.067
Index - $2015 to nominal (using Decision inflation) | 1 | 1.0235 | 1.0475 | 1.0722 | 1.0973 | 1.1231 | 1.1495 | 1.1765 | 1.2042 | 1.2325 | 1.2614
Index - $2016 to nominal (using Decision inflation) |  | 1 | 1.0235 | 1.0475 | 1.0722 | 1.0973 | 1.1231 | 1.1495 | 1.1765 | 1.2042 | 1.2325
Conversion factor - Mid Year $Nominal to End $2015 | 1.0066 | 0.99163 | 0.98158 | 0.96296 | 0.94336
(8 cities, 1 year lagged)
Actual Wage Price Growth
2015
EGWWS WPI (Vic) real rate of change | 1.897%
Construction WPI (Aus) real rate of change | 0.2341%
(source: ABS WPI industry data adjusted for actual inflation)
Forecast Wage Price Growth
Real escalation value (%)
Cost Drivers |  | 2016 | 2017 | 2018 | 2019 | 2020
Labour escalators
Electricity Gas Water and Waste Services Wage Price Index (Internal labour) |  | 0.4 | 0.37 | 0.79 | 0.96 | 1.02
Construction Wage Price Index (External labour) |  | 0.36 | 0.39 | 0.97 | 1.09 | 1.16
(source: AER information request #049 - AusNet Services - Real escalation input cost indices, 8th March 2016)
Labour index for Capital costs
| 2015 | 2016 | 2017 | 2018 | 2019 | 2020
Internal labour index (applied to labour costs in $2015) | 1 | 1.004 | 1.0077 | 1.0157 | 1.0254 | 1.0359
External labour index (applied to labour costs in $2015) | 1 | 1.0036 | 1.0075 | 1.0173 | 1.0284 | 1.0403
Labour index for Operating & Maintenance costs
| 2015 | 2016 | 2017 | 2018 | 2019 | 2020
WPI - EGWWS (Vic) | 1.897% | 0.4014% | 0.3716% | 0.785% | 0.9574% | 1.019%
Labour index (applied to labour costs in $2015) | 1 | 1.004 | 1.0077 | 1.0157 | 1.0254 | 1.0358
Labour / Non Labour splits |  | 2016 | 2017 | 2018 | 2019 | 2020
Labour |  | 0.62 | 0.62 | 0.62 | 0.62 | 0.62
Non Labour |  | 0.38 | 0.38 | 0.38 | 0.38 | 0.38
(source: EDPR Final Decision Opex model - rate of change)
Thousands | 1000

## Lab_Rates
Internal Labour rates
Labour rates effective from 22-01-2014 (source: Expert Estimator tool) | $/hr | Notes
Operational Staff Labour Rate (Tester/Controller/Operator/Applicant, etc) | 125
Engineering & Professional Services Labour Rate | 152
Asset Management Engineer | 142
Project Manager | 165
Front Line Leader | 215
Site Manager Build | 152
Regulation & Network Strategy team | 152
Legal team | 152

## Rpt_Cat
RAB / Asset Class |  | Benchmark Expenditure Categories | Cost Classification
Subtransmission |  | Replacement | Capex
Distribution system assets |  | Connections | Opex
SCADA/Network control |  | Augmentation
Non-network general assets - IT |  | Non-network
Non-network general assets - Other |  | Capitalised network overheads
Land |  | Capitalised corporate overheads
Cap Cons
Station / REFCL no | Short Nm
Kalkallo Zone Substation works | KLO
<spare> | <spare>