## All works
AusNet Services - REFCL Augmentation Program Forecast
1. REFCL Augmentation Program Forecast (including WOTS, BDL, ELM, RWN, KMS, WGI, BGE, LDL)
Asset Class | 2021 Jan-Jun | 2021 Jul-Dec | 2022 Jan-Jun | 2022 Jul-Dec | 2023 Jan-Jun | 2023 Jul-Dec | 2024 Jan-Jun | 2024 Jul-Dec | 2025 Jan-Jun | 2025 Jul-Dec | 2026 Jan-Jun | TOTAL
Subtransmission | 0 | 7342.8797 | 10421.0302 | 13443.9978 | 8187.1196 | 2930.2414 | 1883.5747 | 836.908 | 836.908 | 836.908 | 418.454 | 47138.0213
Distribution system assets | 0 | 483.7625 | 1206.7958 | 1913.2332 | 1017.0869 | 120.9406 | 60.4703 | 0 | 0 | 0 | 0 | 4802.2895
SCADA/Network control | 0 | 2745.4229 | 3354.6356 | 3963.2634 | 2372.0779 | 780.8924 | 662.2519 | 543.6114 | 543.6114 | 543.6114 | 271.8057 | 15781.184
Land | 0 | 480.8951 | 428.3999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 909.295
Total ($2019) | 0 | 11052.9602 | 15410.8616 | 19320.4945 | 11576.2845 | 3832.0745 | 2606.2969 | 1380.5193 | 1380.5193 | 1380.5193 | 690.2597 | 68630.7898
check | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
In real $2018 | 0 | 10827.9884 | 15097.1892 | 18927.2455 | 11340.661 | 3754.0765 | 2553.2484 | 1352.4203 | 1352.4203 | 1352.4203 | 676.2101 | 67233.8799 | <-- Input for EPDR modelling
Input for Capex model (2021-26)
REAL $2018 | Jan-Jun 2021 | 2022-06-01 | 2023-06-01 | 2024-06-01 | 2025-06-01 | 2026-06-01
Subtransmission | 0 | 17402.3435 | 21190.8381 | 4715.8358 | 1639.7471 | 1229.8103 | 46178.5749
Distribution system assets | 0 | 1656.1488 | 2870.6765 | 177.7185 | 0 | 0 | 4704.5438
SCADA/Network control | 0 | 5975.8981 | 6206.3919 | 1413.7706 | 1065.0934 | 798.8201 | 15459.9741
Land | 0 | 890.7872 | 0 | 0 | 0 | 0 | 890.7872
Total Direct | 0 | 25925.1776 | 30267.9064 | 6307.3249 | 2704.8406 | 2028.6304 | 67233.8799
| 0% | 38.56% | 45.02% | 9.381% | 4.023% | 3.017%
CPI - $2018 to $2019 | 102.1%

## Summary
Capex Summary by Asset Class
real $2019
Subtransmission |  | P50 Total | 2021 Jan-Jun | 2021 Jul-Dec | 2022 Jan-Jun | 2022 Jul-Dec | 2023 Jan-Jun | 2023 Jul-Dec | 2024 Jan-Jun | 2024 Jul-Dec | 2025 Jan-Jun | 2025 Jul-Dec | 2026 Jan-Jun | Total | check
<Spare> | Subtransmission | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WOTS | Subtransmission | 8167.257 | 0 | 1640.2444 | 2041.8143 | 2443.3841 | 1426.7226 | 410.0611 | 205.0306 | 0 | 0 | 0 | 0 | 8167.257 | 0
BDL | Subtransmission | 11729.5525 | 0 | 2151.4114 | 2509.8317 | 2868.2519 | 2125.6089 | 1382.9658 | 691.4829 | 0 | 0 | 0 | 0 | 11729.5525 | 0
ELM | Subtransmission | 7033.8133 | 0 | 1349.4009 | 1508.0405 | 1666.6801 | 1252.428 | 838.1758 | 419.0879 | 0 | 0 | 0 | 0 | 7033.8133 | 0
RWN | Subtransmission | 3347.6319 | 0 | 0 | 0 | 0 | 0 | 0 | 418.454 | 836.908 | 836.908 | 836.908 | 418.454 | 3347.6319 | 0
KMS | Subtransmission | 2011.3361 | 0 | 1005.6681 | 628.5425 | 251.417 | 125.7085 | 0 | 0 | 0 | 0 | 0 | 0 | 2011.3361 | 0
WGI | Subtransmission | 7055.9904 | 0 | 705.599 | 1763.9976 | 2822.3962 | 1499.398 | 176.3998 | 88.1999 | 0 | 0 | 0 | 0 | 7055.9904 | 0
BGE | Subtransmission | 4905.5579 | 0 | 490.5558 | 1226.3895 | 1962.2232 | 1042.4311 | 122.6389 | 61.3195 | 0 | 0 | 0 | 0 | 4905.5579 | 0
LDL | Subtransmission | 2886.8821 | 0 | 0 | 742.4141 | 1429.6453 | 714.8227 | 0 | 0 | 0 | 0 | 0 | 0 | 2886.8821 | 0
Total |  |  | 0 | 7342.8797 | 10421.0302 | 13443.9978 | 8187.1196 | 2930.2414 | 1883.5747 | 836.908 | 836.908 | 836.908 | 418.454 | 47138.0213 | 0
Distribution system assets |  | P50 Total | 2021 Jan-Jun | 2021 Jul-Dec | 2022 Jan-Jun | 2022 Jul-Dec | 2023 Jan-Jun | 2023 Jul-Dec | 2024 Jan-Jun | 2024 Jul-Dec | 2025 Jan-Jun | 2025 Jul-Dec | 2026 Jan-Jun | Total | check
<Spare> | Distribution system assets | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WOTS | Distribution system assets | 896.0957 | 0 | 179.9645 | 224.0239 | 268.0834 | 156.5373 | 44.9911 | 22.4956 | 0 | 0 | 0 | 0 | 896.0957 | 0
BDL | Distribution system assets | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
ELM | Distribution system assets | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
RWN | Distribution system assets | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
KMS | Distribution system assets | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WGI | Distribution system assets | 482.3241 | 0 | 48.2324 | 120.581 | 192.9296 | 102.4939 | 12.0581 | 6.0291 | 0 | 0 | 0 | 0 | 482.3241 | 0
BGE | Distribution system assets | 2555.6567 | 0 | 255.5657 | 638.9142 | 1022.2627 | 543.0771 | 63.8914 | 31.9457 | 0 | 0 | 0 | 0 | 2555.6567 | 0
LDL | Distribution system assets | 868.213 | 0 | 0 | 223.2767 | 429.9575 | 214.9787 | 0 | 0 | 0 | 0 | 0 | 0 | 868.213 | 0
Total |  |  | 0 | 483.7625 | 1206.7958 | 1913.2332 | 1017.0869 | 120.9406 | 60.4703 | 0 | 0 | 0 | 0 | 4802.2895 | 0
SCADA/Network control |  | P50 Total | 2021 Jan-Jun | 2021 Jul-Dec | 2022 Jan-Jun | 2022 Jul-Dec | 2023 Jan-Jun | 2023 Jul-Dec | 2024 Jan-Jun | 2024 Jul-Dec | 2025 Jan-Jun | 2025 Jul-Dec | 2026 Jan-Jun | Total | check
<Spare> | SCADA/Network control | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WOTS | SCADA/Network control | 3954.094 | 0 | 794.1076 | 988.5235 | 1182.9394 | 690.7332 | 198.5269 | 99.2634 | 0 | 0 | 0 | 0 | 3954.094 | 0
BDL | SCADA/Network control | 2171.7811 | 0 | 398.3438 | 464.707 | 531.0701 | 393.5663 | 256.0625 | 128.0313 | 0 | 0 | 0 | 0 | 2171.7811 | 0
ELM | SCADA/Network control | 1907.2589 | 0 | 365.8978 | 408.9138 | 451.9299 | 339.603 | 227.2762 | 113.6381 | 0 | 0 | 0 | 0 | 1907.2589 | 0
RWN | SCADA/Network control | 2174.4455 | 0 | 0 | 0 | 0 | 0 | 0 | 271.8057 | 543.6114 | 543.6114 | 543.6114 | 271.8057 | 2174.4455 | 0
KMS | SCADA/Network control | 1581.933 | 0 | 790.9665 | 494.3541 | 197.7416 | 98.8708 | 0 | 0 | 0 | 0 | 0 | 0 | 1581.933 | 0
WGI | SCADA/Network control | 1870.8157 | 0 | 187.0816 | 467.7039 | 748.3263 | 397.5483 | 46.7704 | 23.3852 | 0 | 0 | 0 | 0 | 1870.8157 | 0
BGE | SCADA/Network control | 2090.2566 | 0 | 209.0257 | 522.5641 | 836.1026 | 444.1795 | 52.2564 | 26.1282 | 0 | 0 | 0 | 0 | 2090.2566 | 0
LDL | SCADA/Network control | 30.5993 | 0 | 0 | 7.8692 | 15.1534 | 7.5767 | 0 | 0 | 0 | 0 | 0 | 0 | 30.5993 | 0
Total |  |  | 0 | 2745.4229 | 3354.6356 | 3963.2634 | 2372.0779 | 780.8924 | 662.2519 | 543.6114 | 543.6114 | 543.6114 | 271.8057 | 15781.184 | 0
Land |  | P50 Total | 2021 Jan-Jun | 2021 Jul-Dec | 2022 Jan-Jun | 2022 Jul-Dec | 2023 Jan-Jun | 2023 Jul-Dec | 2024 Jan-Jun | 2024 Jul-Dec | 2025 Jan-Jun | 2025 Jul-Dec | 2026 Jan-Jun | Total | check
<Spare> | Land | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WOTS | Land | 270.0717 | 0 | 270.0717 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 270.0717 | 0
BDL | Land | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
ELM | Land | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
RWN | Land | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
KMS | Land | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WGI | Land | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
BGE | Land | 210.8233 | 0 | 210.8233 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 210.8233 | 0
LDL | Land | 428.3999 | 0 | 0 | 428.3999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 428.3999 | 0
Total |  |  | 0 | 480.8951 | 428.3999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 909.295 | 0
ALL Classes |  | P50 Total | 2021 Jan-Jun | 2021 Jul-Dec | 2022 Jan-Jun | 2022 Jul-Dec | 2023 Jan-Jun | 2023 Jul-Dec | 2024 Jan-Jun | 2024 Jul-Dec | 2025 Jan-Jun | 2025 Jul-Dec | 2026 Jan-Jun | Total | check
<Spare> |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
WOTS |  | 13287.5184 | 0 | 2884.3882 | 3254.3617 | 3894.4069 | 2273.993 | 653.5791 | 326.7896 | 0 | 0 | 0 | 0 | 13287.5184 | 0 | TRUE
BDL |  | 13901.3336 | 0 | 2549.7552 | 2974.5386 | 3399.3221 | 2519.1752 | 1639.0283 | 819.5142 | 0 | 0 | 0 | 0 | 13901.3336 | 0 | TRUE
ELM |  | 8941.0721 | 0 | 1715.2988 | 1916.9544 | 2118.61 | 1592.031 | 1065.452 | 532.726 | 0 | 0 | 0 | 0 | 8941.0721 | 0 | TRUE
RWN |  | 5522.0774 | 0 | 0 | 0 | 0 | 0 | 0 | 690.2597 | 1380.5193 | 1380.5193 | 1380.5193 | 690.2597 | 5522.0774 | 0 | TRUE
KMS |  | 3593.2692 | 0 | 1796.6346 | 1122.8966 | 449.1586 | 224.5793 | 0 | 0 | 0 | 0 | 0 | 0 | 3593.2692 | 0 | TRUE
WGI |  | 9409.1302 | 0 | 940.913 | 2352.2825 | 3763.6521 | 1999.4402 | 235.2283 | 117.6141 | 0 | 0 | 0 | 0 | 9409.1302 | 0 | TRUE
BGE |  | 9762.2946 | 0 | 1165.9705 | 2387.8678 | 3820.5885 | 2029.6876 | 238.7868 | 119.3934 | 0 | 0 | 0 | 0 | 9762.2946 | 0 | TRUE
LDL |  | 4214.0943 | 0 | 0 | 1401.9599 | 1874.7563 | 937.3781 | 0 | 0 | 0 | 0 | 0 | 0 | 4214.0943 | 0 | TRUE
Total - $2019 |  |  | 0 | 11052.9602 | 15410.8616 | 19320.4945 | 11576.2845 | 3832.0745 | 2606.2969 | 1380.5193 | 1380.5193 | 1380.5193 | 690.2597 | 68630.7898 | 0
Check |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Direct Cost Composition |  |  | Materials | Int Labour | Contracts - Design | Contracts - Construct | Other | P50 Total - $2019 | P50 Total - $2020
<Spare> |  |  | 0 | 0 | 0 | 0 | 0 | 0
WOTS |  |  | 5917.9925 | 1041.9639 | 1273.929 | 4818.5016 | 235.1314 | 13287.5184 | 13512.2327
BDL |  |  | 6415.1894 | 695.5994 | 900 | 5771.9785 | 118.5663 | 13901.3336 | 14131.4859
ELM |  |  | 3837.7455 | 653.9513 | 800 | 3574.7334 | 74.6419 | 8941.0721 | 9091.6896
RWN |  |  | 2349.837 | 556.7374 | 550 | 2000.0105 | 65.4925 | 5522.0774 | 5617.015
KMS |  |  | 1456.1939 | 283.3855 | 300 | 1511.9676 | 41.7222 | 3593.2692 | 3654.0576
WGI |  |  | 3485.2725 | 1027.9258 | 1023.929 | 3696.5583 | 175.4445 | 9409.1302 | 9571.8889
BGE |  |  | 3440.8795 | 786.7358 | 823.929 | 4573.238 | 137.5123 | 9762.2946 | 9927.6571
LDL |  |  | 1101.4715 | 414.5045 | 469.1716 | 2100.8975 | 128.0492 | 4214.0943 | 4286.4147
Total |  |  | 28004.5819 | 5460.8035 | 6140.9586 | 28047.8854 | 976.5603 | 68630.7898 | 69792.4415
[8 empty] | 0 | 0
|  |  | CY2018 | CY2019 | CY2020
CPI Actual - 1 year lagged |  |  | 1.934% | 2.078% | 1.593%
Proposed real wage escalator |  |  |  | 1.491% | 0.8948%
|  |  | Materials | Int Labour | Contracts - Design | Contracts - Construct | Other | P50 Total - $2020
Total costs |  |  | 28450.6726 | 5616.2076 | 6238.7792 | 28494.6659 | 992.1161 | 69792.4415 | TRUE
Escalator - $2019 to $2020 |  |  | 101.6% | 102.8% | 101.6% | 101.6% | 101.6%

## Phasing
High level phasing of total REFCL Augex program and revised KLO solution
| 2021 Jan-Jun | 2021 Jul-Dec | 2022 Jan-Jun | 2022 Jul-Dec | 2023 Jan-Jun | 2023 Jul-Dec | 2024 Jan-Jun | 2024 Jul-Dec | 2025 Jan-Jun | 2025 Jul-Dec | 2026 Jan-Jun | TOTAL
Program phasing - 6 monthly (excl. Land)
<Spare> | [11 empty] | 0%
WOTS |  | 20.08% | 25% | 29.92% | 17.47% | 5.021% | 2.51% |  |  |  |  | 100%
BDL |  | 18.34% | 21.4% | 24.45% | 18.12% | 11.79% | 5.895% |  |  |  |  | 100%
ELM |  | 19.18% | 21.44% | 23.7% | 17.81% | 11.92% | 5.958% |  |  |  |  | 100%
RWN | [6 empty] | 12.5% | 25% | 25% | 25% | 12.5% | 100%
KMS |  | 50% | 31.25% | 12.5% | 6.25% | [6 empty] | 100%
WGI |  | 10% | 25% | 40% | 21.25% | 2.5% | 1.25% |  |  |  |  | 100%
BGE |  | 10% | 25% | 40% | 21.25% | 2.5% | 1.25% |  |  |  |  | 100%
LDL |  |  | 25.72% | 49.52% | 24.76% | [6 empty] | 100%

## Spare_Det
<Spare> Volumes & Unit Rates
<Spare> |  |  |  |  | Materials |  |  | Total Direct ($k, $2019) | [6 empty] | Total Internal Labour (hours)
|  | Asset Class | Expenditure Class |  | $/Unit ($2019) | QTY | UOM | Materials | Int Labour | Contracts - Design | Contracts - Construct | Other | P50 Total | Chk | Project Engineer | Asset Management Engineer | Project Manager | Front Line Leader | Project Engineer Build | Site Manager Build | Operational Staff | Total Hours
Labour rates | [14 empty] | 162.4874 | 151.7974 | 176.3843 | 229.8341 | 162.4874 | 162.4874 | 133.6245
Design - Internal/External |  | Allocation | Allocation | [5 empty] | 0 |  |  |  | 0 |  | 0
Project Management & Engineering
| Project Establishment | Allocation | Allocation | [5 empty] | 0 |  | 0 |  | 0 | [8 empty] | 0
| Project Management | Allocation | Allocation | [5 empty] | 0 |  |  |  | 0 | [8 empty] | 0
| Project Close-out, Testing & Commissioning | Allocation | Allocation | [5 empty] | 0 |  | 0 |  | 0 | [8 empty] | 0
| Community Engagement | Allocation | Allocation | [5 empty] | 0 |  | 0 |  | 0 | [8 empty] | 0
Zone Substation works
Primary Plant
| 66kV Bay - Ring Bus | Subtransmission | Augmentation | SubtransmissionAugmentation | 185.475 |  | ea | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 66kV Exit - Line Feeder | Subtransmission | Augmentation | SubtransmissionAugmentation | 74.1545 |  | ea | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 66kV Exit - Transformer | Subtransmission | Augmentation | SubtransmissionAugmentation | 37.494 |  | ea | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Power transformer - 66/22kV 15/20MVA | Subtransmission | Augmentation | SubtransmissionAugmentation | 787.0745 |  | ea | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 22kV Indoor Switchgear - Transformers | Subtransmission | Augmentation | SubtransmissionAugmentation | 41.2559 |  | ea | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 22kV Neutral Earthing Resistors | Subtransmission | Augmentation | SubtransmissionAugmentation | 106.8132 |  | ea | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Earth Grid | Subtransmission | Augmentation | SubtransmissionAugmentation | 58.2657 |  | ea | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Station service transformer (1 MVA) | Subtransmission | Augmentation | SubtransmissionAugmentation | 169.008 |  | ea | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Station service transformer (500 kVA) | Subtransmission | Augmentation | SubtransmissionAugmentation | 72.619 |  | ea | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| AC changeover board - Station | Subtransmission | Augmentation | SubtransmissionAugmentation | 39.295 |  | ea | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| AC C/O board footing | Subtransmission | Augmentation | SubtransmissionAugmentation | 0 |  | ea | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Arc Suppression Coil | SCADA/Network control | Augmentation | SCADA/Network controlAugmentation | 1158.3 |  | ea | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| ASC footing | Subtransmission | Augmentation | SubtransmissionAugmentation | 0 |  | ea | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 22kV switchboard - Metro | Subtransmission | Augmentation | SubtransmissionAugmentation | 1354 |  | ea | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 22kV switchboard - Rural | Subtransmission | Augmentation | SubtransmissionAugmentation | 1461.1163 |  | ea | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 22kV switchboard (no building) - Rural | Subtransmission | Augmentation | SubtransmissionAugmentation | 700 |  | ea | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 22kV Capacitor Bank - Modify | Subtransmission | Augmentation | SubtransmissionAugmentation | 91.2924 |  | ea | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Cap Bank footing | Subtransmission | Augmentation | SubtransmissionAugmentation | 0 |  | ea | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 22kV Dead Tank Circuit Breaker | Subtransmission | Augmentation | SubtransmissionAugmentation | 107.006 |  | ea | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 22kV U/S Isolator | Subtransmission | Augmentation | SubtransmissionAugmentation | 7.664 |  | ea | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 22kV Current Transformer | Subtransmission | Augmentation | SubtransmissionAugmentation | 27.163 |  | ea | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 22kV Zero Sequence CTs | Subtransmission | Augmentation | SubtransmissionAugmentation | 0 |  | ea | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 22kV Voltage Transformer | Subtransmission | Augmentation | SubtransmissionAugmentation | 0 |  | ea | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 22KV Surge Arrestor | Subtransmission | Augmentation | SubtransmissionAugmentation | 0.62 |  | ea | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Primary Cable Testing | Subtransmission | Augmentation | SubtransmissionAugmentation | 0 |  | ea | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Neutral Bus | Subtransmission | Augmentation | SubtransmissionAugmentation | 93.854 |  | ea | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| REFCL control room | Subtransmission | Augmentation | SubtransmissionAugmentation | 0 |  | ea | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Battery Room (single battery set) | Subtransmission | Augmentation | SubtransmissionAugmentation | 227.63 |  | ea | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| New Control Building | Subtransmission | Augmentation | SubtransmissionAugmentation | 369.039 |  | ea | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Primary Cables - 22kV | Subtransmission | Augmentation | SubtransmissionAugmentation | 0.90165 |  | p/mtr | 0 | 0 |  |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Feeder Exit Cables - 22kV | Subtransmission | Augmentation | SubtransmissionAugmentation | 0.05 |  | p/mtr | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Other | Subtransmission | Augmentation | SubtransmissionAugmentation | 0 |  | ea | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 22kV Capacitor Bank (2x3 MVAr) - type 4 | Subtransmission | Augmentation | SubtransmissionAugmentation | 465.78 |  | ea | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| One Tilt Slab control room | Subtransmission | Augmentation | SubtransmissionAugmentation | 0 |  | ea | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SCADA / Protection & Control/ Comms
| 66kV Line Protection Panel | SCADA/Network control | Augmentation | SCADA/Network controlAugmentation | 76.7296 |  | ea | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 66kV Substation Protection Panel (transformer & bus) | SCADA/Network control | Augmentation | SCADA/Network controlAugmentation | 223.6578 |  | ea | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 66/22kV Transformer Voltage Control & Regulation Cubicle | SCADA/Network control | Augmentation | SCADA/Network controlAugmentation | 252.1155 |  | ea | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Neutral Bus controller - 1 GFN | SCADA/Network control | Augmentation | SCADA/Network controlAugmentation | 48.9823 |  | ea | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Protection – GFN panels | SCADA/Network control | Augmentation | SCADA/Network controlAugmentation | 6.2431 |  | ea | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Power Quality/Switchgear Interface | SCADA/Network control | Augmentation | SCADA/Network controlAugmentation | 98.0077 |  | ea | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 22kV Protection & Control Modifications | SCADA/Network control | Augmentation | SCADA/Network controlAugmentation | 5 |  | ea | 0 | 0 |  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| SCIMS system - small | SCADA/Network control | Augmentation | SCADA/Network controlAugmentation | 92.2396 |  | ea | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Other protection works | SCADA/Network control | Augmentation | SCADA/Network controlAugmentation | 5 |  | ea | 0 | 0 |  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Other AC & DC supplies |  | Subtransmission | Augmentation | SubtransmissionAugmentation | 30.9158 |  | ea | 0 | 0 |  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Metering & System Monitoring |  | Subtransmission | Augmentation | SubtransmissionAugmentation | 4.5 |  | ea | 0 | 0 |  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Infrastructure - Services |  | Subtransmission | Augmentation | SubtransmissionAugmentation | 15.0462 |  | ea | 0 | 0 |  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Civil works
| Earthworks | Subtransmission | Augmentation | SubtransmissionAugmentation | 0 |  | ea | 0 | 0 |  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Buildings | Subtransmission | Augmentation | SubtransmissionAugmentation | 0 |  | ea | 0 | 0 |  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 22kV switchyard - install new puraceptor | Subtransmission | Augmentation | SubtransmissionAugmentation | 131.3953 |  | ea | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| - Other | Subtransmission | Augmentation | SubtransmissionAugmentation | 0 |  | ea | 0 | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Construction delivery & site control |  | Subtransmission | Augmentation | SubtransmissionAugmentation | 0 |  | ea | 0 | 0 |  |  |  | 0
Land purchase |  | Land | Non-Network | LandNon-Network | 0 |  | ea | 0 | 0 |  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Subtotal Substation works | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
Check | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0
Feeder works |  |  |  |  | Material $/Unit | QTY | UOM | Materials | Int Labour | Contracts - Design | Contracts - Construct | Other | P50 Total
66kV/22kV Overhead Lines
New 66 kV Pole Line construction (5km): -
| Concrete Poles 20m (includes installation), per pole | Subtransmission | Augmentation | SubtransmissionAugmentation | 5.4308 |  | ea | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Cross Arms 66kV - Intermediate & Strain | Subtransmission | Augmentation | SubtransmissionAugmentation | 0.40306 |  | ea | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Conductor (19/4.75 AAC) | Subtransmission | Augmentation | SubtransmissionAugmentation | 15.18 |  | km | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Cross Arms 22kV LV - Intermediate & Strain | Distribution system assets | Augmentation | Distribution system assetsAugmentation | 0.43615 |  | ea | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Conductor (19/3.25 AAC) | Distribution system assets | Augmentation | Distribution system assetsAugmentation | 6.7848 |  | km | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Stays | Subtransmission | Augmentation | SubtransmissionAugmentation | 0.24562 |  | ea | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Supervision, Traffic Control, Set-Up Site & Clean-Up | Subtransmission | Augmentation | SubtransmissionAugmentation | 0 |  | km | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
66kV Line - Replace X-Arms & Insulators (/km): -
| Cross Arms 66kV - Intermediate & Strain | Subtransmission | Augmentation | SubtransmissionAugmentation | 0.40306 |  | ea | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Supervision, Traffic Control, Set-Up Site & Clean-Up | Subtransmission | Augmentation | SubtransmissionAugmentation | 0 |  | km | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
ADSS Cable Installed on Existing Poles (5km): -
| ADSS Fibre Optic Cable | Subtransmission | Augmentation | SubtransmissionAugmentation | 8.72 |  | km | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| OPGW Joint Box (Installed & Terminated on Existing Tower/Pole) | Subtransmission | Augmentation | SubtransmissionAugmentation | 6.795 |  | ea | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Vegetation Clearing - Light 66kV Line (5km):-
| Vegetation Clearing | Subtransmission | Augmentation | SubtransmissionAugmentation | 0 |  | km | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Subtotal 66kV/22kV Overhead Lines | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0
Feeder Cut-in works
22kV Underground Cable (150m) to NEW pole including gas switch and surge diverters: -
| Surge arrestor | Distribution system assets | Augmentation | Distribution system assetsAugmentation | 0.3785 |  | ea | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.573% | 0% | 32.12% | 0% | 0% | 0% | 65.31% | 100% | TRUE | 1.08
| Gas Switch | Distribution system assets | Augmentation | Distribution system assetsAugmentation | 15.42 |  | ea | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Concrete Poles 15.5m (includes installation), per pole | Distribution system assets | Augmentation | Distribution system assetsAugmentation | 6.06 |  | ea | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 22kV Underground Cable (150m) | Distribution system assets | Augmentation | Distribution system assetsAugmentation | 0.061705 |  | p/mtr | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Subtotal Feeder Cut-in works | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0
Subtotal feeder works | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0
Check | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0
Grand Total | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0
Check | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0
| Zone Substation works | Subtransmission | Augmentation | SubtransmissionAugmentation |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Subtransmission | Replacement | SubtransmissionReplacement |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
|  | SCADA/Network control | Augmentation | SCADA/Network controlAugmentation |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
|  | SCADA/Network control | Replacement | SCADA/Network controlReplacement |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Land | Non-Network | LandNon-Network |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
[8 empty] | 0 | 0 | 0 | 0 | 0 | 0
| Design, Project Management & Engineering costs allocation | Subtransmission | Augmentation | SubtransmissionAugmentation |  |  |  |  | 0 | 0 | 0 |  | 0
|  | Subtransmission | Replacement | SubtransmissionReplacement |  |  |  |  | 0 | 0 | 0 |  | 0
|  | SCADA/Network control | Augmentation | SCADA/Network controlAugmentation |  |  |  |  | 0 | 0 | 0 |  | 0
|  | SCADA/Network control | Replacement | SCADA/Network controlReplacement |  |  |  |  | 0 | 0 | 0 |  | 0
|  | Land | Non-Network | LandNon-Network |  |  |  |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 0 | 0 | 0 | 0 | 0
| Total Substation works | Subtransmission | Augmentation | SubtransmissionAugmentation |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Subtransmission | Replacement | SubtransmissionReplacement |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
|  | SCADA/Network control | Augmentation | SCADA/Network controlAugmentation |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
|  | SCADA/Network control | Replacement | SCADA/Network controlReplacement |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Land | Non-Network | LandNon-Network |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
[8 empty] | 0 | 0 | 0 | 0 | 0 | 0
[8 empty] | 0 | 0 | 0 | 0 | 0 | 0
| 66kV Overhead Lines | Subtransmission | Augmentation | SubtransmissionAugmentation |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Subtransmission | Replacement | SubtransmissionReplacement |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Distribution system assets | Augmentation | Distribution system assetsAugmentation |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Distribution system assets | Replacement | Distribution system assetsReplacement |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
[8 empty] | 0 | 0 | 0 | 0 | 0 | 0
[8 empty] | 0 | 0 | 0 | 0 | 0 | 0
| Feeder Cut-in works | Subtransmission | Augmentation | SubtransmissionAugmentation |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Subtransmission | Replacement | SubtransmissionReplacement |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Distribution system assets | Augmentation | Distribution system assetsAugmentation |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Distribution system assets | Replacement | Distribution system assetsReplacement |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
[8 empty] | 0 | 0 | 0 | 0 | 0 | 0
[8 empty] | 0 | 0 | 0 | 0 | 0 | 0
Note on G46: AST: Average unit rate across all cable types, excluding feeder exit cable

## WOTS_Det
Confidential
WOTS Volumes & Unit Rates
WOTS |  |  |  |  | Materials |  |  | Total Direct ($k, $2019) | [6 empty] | Total Internal Labour (hours)
|  | Asset Class | Expenditure Class |  | $/Unit ($2019) | QTY | UOM | Materials | Int Labour | Contracts - Design | Contracts - Construct | Other | P50 Total | Chk | Project Engineer | Asset Management Engineer | Project Manager | Front Line Leader | Project Engineer Build | Site Manager Build | Operational Staff | Total Hours
Labour rates | [14 empty] | 162.4874 | 151.7974 | 176.3843 | 229.8341 | 162.4874 | 162.4874 | 133.6245
Design - Internal/External |  | Allocation | Allocation | [5 empty] | 0 | 1250 |  |  | 1250 |  | 0
Project Management & Engineering
| Project Establishment | Allocation | Allocation | [5 empty] | 105.6168 |  | 0 |  | 105.6168 |  | 478 | 92 | 48 | 24 |  |  |  | 642
| Project Management | Allocation | Allocation | [5 empty] | 820.4822 |  |  |  | 820.4822 |  | 192 |  | 1136 | 304 | 573.5 | 2560 | 74 | 4839.5
| Project Close-out, Testing & Commissioning | Allocation | Allocation | [5 empty] | 14.1107 |  | 0 |  | 14.1107 |  |  |  | 80 |  |  |  |  | 80
| Community Engagement | Allocation | Allocation | [5 empty] | 0 |  | 0 |  | 0 | [8 empty] | 0
Remote REFCL at WOTS11 & WOTS25 works
Primary Plant
| 66kV Bay - Ring Bus | Subtransmission | Augmentation | SubtransmissionAugmentation | 185.475 |  | ea | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 66kV Exit - Line Feeder | Subtransmission | Augmentation | SubtransmissionAugmentation | 74.1545 |  | ea | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 66kV Exit - Transformer | Subtransmission | Augmentation | SubtransmissionAugmentation | 37.494 |  | ea | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Power transformer - 66/22kV 15/20MVA | Subtransmission | Augmentation | SubtransmissionAugmentation | 787.0745 |  | ea | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 22kV Indoor Switchgear - Transformers | Subtransmission | Augmentation | SubtransmissionAugmentation | 41.2559 |  | ea | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 22kV Neutral Earthing Resistors | Subtransmission | Augmentation | SubtransmissionAugmentation | 106.8132 |  | ea | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Earth Grid | Subtransmission | Augmentation | SubtransmissionAugmentation | 58.2657 |  | ea | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Station service transformer (200 kVA) | Subtransmission | Augmentation | SubtransmissionAugmentation | 47.7187 | 2 | ea | 95.4374 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Station service transformer (1 MVA) | Subtransmission | Augmentation | SubtransmissionAugmentation | 169.008 |  | ea | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Station service transformer (500 kVA) | Subtransmission | Augmentation | SubtransmissionAugmentation | 72.619 |  | ea | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Capacitance reducing isolation substation (12.5 MVA) | Subtransmission | Augmentation | SubtransmissionAugmentation | 1184.6455 | 2 | ea | 2369.2911 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| AC changeover board - Station | Subtransmission | Augmentation | SubtransmissionAugmentation | 39.295 |  | ea | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| AC C/O board footing | Subtransmission | Augmentation | SubtransmissionAugmentation | 0 |  | ea | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Arc Suppression Coil | SCADA/Network control | Augmentation | SCADA/Network controlAugmentation | 1158.3 | 2 | ea | 2316.6 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| ASC footing | Subtransmission | Augmentation | SubtransmissionAugmentation | 0 | 2 | ea | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 22kV switchboard - Metro | Subtransmission | Augmentation | SubtransmissionAugmentation | 1354 |  | ea | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 22kV switchboard - Rural | Subtransmission | Augmentation | SubtransmissionAugmentation | 1461.1163 |  | ea | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 22kV switchboard (no building) - Rural | Subtransmission | Augmentation | SubtransmissionAugmentation | 700 |  | ea | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 22kV Capacitor Bank - Modify | Subtransmission | Augmentation | SubtransmissionAugmentation | 91.2924 |  | ea | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Cap Bank footing | Subtransmission | Augmentation | SubtransmissionAugmentation | 0 |  | ea | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 22kV Dead Tank Circuit Breaker | Subtransmission | Augmentation | SubtransmissionAugmentation | 107.006 |  | ea | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 22kV U/S Isolator | Subtransmission | Augmentation | SubtransmissionAugmentation | 7.664 | 4 | ea | 30.656 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 22kV Current Transformer | Subtransmission | Augmentation | SubtransmissionAugmentation | 27.163 | 2 | ea | 54.326 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 22kV Zero Sequence CTs | Subtransmission | Augmentation | SubtransmissionAugmentation | 0 |  | ea | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 22kV Voltage Transformer | Subtransmission | Augmentation | SubtransmissionAugmentation | 0 | 2 | ea | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 22KV Surge Arrestor | Subtransmission | Augmentation | SubtransmissionAugmentation | 0.62 | 2 | ea | 1.24 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Primary Cable Testing | Subtransmission | Augmentation | SubtransmissionAugmentation | 0 | 2 | ea | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Neutral Bus | Subtransmission | Augmentation | SubtransmissionAugmentation | 93.854 |  | ea | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Type 3 REFCL control room | Subtransmission | Augmentation | SubtransmissionAugmentation | 109.1759 | 2 | ea | 218.3518 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Battery Room (single battery set) | Subtransmission | Augmentation | SubtransmissionAugmentation | 227.63 |  | ea | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| New Control Building | Subtransmission | Augmentation | SubtransmissionAugmentation | 369.039 |  | ea | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Primary Cables - 22kV | Subtransmission | Augmentation | SubtransmissionAugmentation | 0.065963 | 120 | p/mtr | 7.9156 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Feeder Exit Cables - 22kV | Subtransmission | Augmentation | SubtransmissionAugmentation | 0.05 |  | p/mtr | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Other | Subtransmission | Augmentation | SubtransmissionAugmentation | 0 |  | ea | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 22kV Capacitor Bank (2x3 MVAr) - type 4 | Subtransmission | Augmentation | SubtransmissionAugmentation | 465.78 |  | ea | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| One Tilt Slab control room | Subtransmission | Augmentation | SubtransmissionAugmentation | 0 |  | ea | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[15 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SCADA / Protection & Control/ Comms | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 66kV Line Protection Panel | SCADA/Network control | Augmentation | SCADA/Network controlAugmentation | 76.7296 |  | ea | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 66kV Substation Protection Panel (transformer & bus) | SCADA/Network control | Augmentation | SCADA/Network controlAugmentation | 223.6578 |  | ea | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 66/22kV Transformer Voltage Control & Regulation Cubicle | SCADA/Network control | Augmentation | SCADA/Network controlAugmentation | 252.1155 |  | ea | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Neutral Bus controller - 1 GFN | SCADA/Network control | Augmentation | SCADA/Network controlAugmentation | 48.9823 |  | ea | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Protection – GFN panels | SCADA/Network control | Augmentation | SCADA/Network controlAugmentation | 6.2431 |  | ea | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 22kV Line Protection Panel | SCADA/Network control | Augmentation | SCADA/Network controlAugmentation | 63.4714 | 2 | ea | 126.9428 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 66/22kV Transformer Protection Panel | SCADA/Network control | Augmentation | SCADA/Network controlAugmentation | 47.4106 | 2 | ea | 94.8212 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Power Quality/Switchgear Interface | SCADA/Network control | Augmentation | SCADA/Network controlAugmentation | 98.0077 |  | ea | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 22kV Protection & Control Modifications | SCADA/Network control | Augmentation | SCADA/Network controlAugmentation | 0 |  | ea | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| SCIMS system - small | SCADA/Network control | Augmentation | SCADA/Network controlAugmentation | 92.2396 | 2 | ea | 184.4793 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Other protection works | SCADA/Network control | Augmentation | SCADA/Network controlAugmentation | 0 |  | ea | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Other AC & DC supplies |  | Subtransmission | Augmentation | SubtransmissionAugmentation | 22.8982 | 8 | ea | 183.1858 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Metering & System Monitoring |  | Subtransmission | Augmentation | SubtransmissionAugmentation | 4.5 |  | ea | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Infrastructure - Services |  | Subtransmission | Augmentation | SubtransmissionAugmentation | 15.0462 |  | ea | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Civil works | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Earthworks | Subtransmission | Augmentation | SubtransmissionAugmentation | 0 |  | ea | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Buildings | Subtransmission | Augmentation | SubtransmissionAugmentation | 0 |  | ea | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 22kV switchyard - install new puraceptor | Subtransmission | Augmentation | SubtransmissionAugmentation | 131.3953 |  | ea | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| - Other | Subtransmission | Augmentation | SubtransmissionAugmentation | 0 |  | ea | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Construction delivery & site control |  | Subtransmission | Augmentation | SubtransmissionAugmentation | 0 |  | ea | 0 | 0
Land purchase |  | Land | Non-Network | LandNon-Network | 0 |  | ea | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Subtotal Remote REFCL works | [7 empty] | 5683.2469 | 940.2098 | 1250 | 4219.2766 | 195.4658 | 12288.199
Check | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0
Feeder works |  |  |  |  | Material $/Unit | QTY | UOM | Materials | Int Labour | Contracts - Design | Contracts - Construct | Other | P50 Total
Remote REFCLs
Lines works at WOTS11 & WOTS25
| 22kV Underground Cable 300mm2 XLPE | Distribution system assets | Augmentation | Distribution system assetsAugmentation | 0.064197 | 400 | p/mtr | 25.679 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Install new ACR for switching | Distribution system assets | Augmentation | Distribution system assetsAugmentation | 22.6039 | 2 | ea | 45.2078 | 40.7017 | 9.5716 |  |  |  | -160.7376 | 75.9362 | 87.008 | 85.9225 | 0 | 0 | 0 | 0 | 248.8667 | 30.31% | 32.45% | 37.24%
| Concrete Poles 15.5m Replacement (includes installation), per pole | Distribution system assets | Replacement | Distribution system assetsReplacement | 6.06 | 2 | ea | 12.12 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Subtotal Lines works at WOTS11 & WOTS25 | [6 empty] | 83.0068 | 40.7017 | 9.5716 | 327.4055 | 13.8464 | 474.5319
Isolation Transformers
Install three isolation transformers
| Concrete Poles 15.5m Replacement (includes installation), per pole | Distribution system assets | Replacement | Distribution system assetsReplacement | 6.06 | 2 | ea | 12.12 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Concrete Poles 15.5m (includes installation), per pole | Distribution system assets | Augmentation | Distribution system assetsAugmentation | 6.06 | 1 | ea | 6.06 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Capacitance reducing isolation substation (300 kVA) | Subtransmission | Augmentation | SubtransmissionAugmentation | 18.9974 | 3 | ea | 56.9922 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Install new ACR for switching | Distribution system assets | Augmentation | Distribution system assetsAugmentation | 22.6039 | 3 | ea | 67.8118 | 61.0525 | 14.3574 |  |  |  | -241.1065 | 113.9043 | 130.512 | 128.8837 | 0 | 0 | 0 | 0 | 373.3001 | 30.31% | 32.45% | 37.24%
| 22kV Underground Cable 185mm2 XLPE | Distribution system assets | Augmentation | Distribution system assetsAugmentation | 0.043775 | 200 | p/mtr | 8.7549 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Subtotal Install three isolation transformers | [6 empty] | 151.7388 | 61.0525 | 14.3574 | 271.8195 | 25.8192 | 524.7875
Subtotal feeder works | [7 empty] | 234.7456 | 101.7541 | 23.929 | 599.225 | 39.6656 | 999.3194
Check | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0
Grand Total | [7 empty] | 5917.9925 | 1041.9639 | 1273.929 | 4818.5016 | 235.1314 | 13287.5184
Check | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0
| Remote REFCL at WOTS11 & WOTS25 works | Subtransmission | Augmentation | SubtransmissionAugmentation |  |  |  | 2960.4036 | 0 | 0 | 3486.9047 | 179.4171 | 6626.7255
|  | Subtransmission | Replacement | SubtransmissionReplacement |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
|  | SCADA/Network control | Augmentation | SCADA/Network controlAugmentation |  |  |  | 2722.8432 | 0 | 0 | 510.4369 | 16.0486 | 3249.3288
|  | SCADA/Network control | Replacement | SCADA/Network controlReplacement |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Land | Non-Network | LandNon-Network |  |  |  | 0 | 0 | 0 | 221.935 | 0 | 221.935
[8 empty] | 5683.2469 | 0 | 0 | 4219.2766 | 195.4658 | 10097.9893
| Design, Project Management & Engineering costs allocation | Subtransmission | Augmentation | SubtransmissionAugmentation |  |  |  |  | 617.0052 | 820.3026 | 0 |  | 1437.3078
|  | Subtransmission | Replacement | SubtransmissionReplacement |  |  |  |  | 0 | 0 | 0 |  | 0
|  | SCADA/Network control | Augmentation | SCADA/Network controlAugmentation |  |  |  |  | 302.5405 | 402.2247 | 0 |  | 704.7652
|  | SCADA/Network control | Replacement | SCADA/Network controlReplacement |  |  |  |  | 0 | 0 | 0 |  | 0
|  | Land | Non-Network | LandNon-Network |  |  |  |  | 20.6641 | 27.4727 | 0 |  | 48.1367
[8 empty] | 0 | 940.2098 | 1250 | 0 | 0 | 2190.2098
| Total Remote REFCL at WOTS11 & WOTS25 works | Subtransmission | Augmentation | SubtransmissionAugmentation |  |  |  | 2960.4036 | 617.0052 | 820.3026 | 3486.9047 | 179.4171 | 8064.0333
|  | Subtransmission | Replacement | SubtransmissionReplacement |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
|  | SCADA/Network control | Augmentation | SCADA/Network controlAugmentation |  |  |  | 2722.8432 | 302.5405 | 402.2247 | 510.4369 | 16.0486 | 3954.094
|  | SCADA/Network control | Replacement | SCADA/Network controlReplacement |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Land | Non-Network | LandNon-Network |  |  |  | 0 | 20.6641 | 27.4727 | 221.935 | 0 | 270.0717
[8 empty] | 5683.2469 | 940.2098 | 1250 | 4219.2766 | 195.4658 | 12288.199
[8 empty] | 0 | 0 | 0 | 0 | 0 | 0
| Lines works at WOTS11 & WOTS25 | Subtransmission | Augmentation | SubtransmissionAugmentation |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Subtransmission | Replacement | SubtransmissionReplacement |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Distribution system assets | Augmentation | Distribution system assetsAugmentation |  |  |  | 70.8868 | 40.7017 | 9.5716 | 307.8835 | 13.2964 | 442.3399
|  | Distribution system assets | Replacement | Distribution system assetsReplacement |  |  |  | 12.12 | 0 | 0 | 19.522 | 0.55 | 32.192
[8 empty] | 83.0068 | 40.7017 | 9.5716 | 327.4055 | 13.8464 | 474.5319
[8 empty] | 0 | 0 | 0 | 0 | 0 | 0
| Install three isolation transformers | Subtransmission | Augmentation | SubtransmissionAugmentation |  |  |  | 56.9922 | 0 | 0 | 41.182 | 5.0496 | 103.2237
|  | Subtransmission | Replacement | SubtransmissionReplacement |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Distribution system assets | Augmentation | Distribution system assetsAugmentation |  |  |  | 82.6267 | 61.0525 | 14.3574 | 211.1155 | 20.2196 | 389.3717
|  | Distribution system assets | Replacement | Distribution system assetsReplacement |  |  |  | 12.12 | 0 | 0 | 19.522 | 0.55 | 32.192
[8 empty] | 151.7388 | 61.0525 | 14.3574 | 271.8195 | 25.8192 | 524.7875
[8 empty] | 0 | 0 | 0 | 0 | 0 | 0
Note on G48: AST: Average unit rate across all cable types, excluding feeder exit cable

## BDL_Det
Confidential
BDL Volumes & Unit Rates
BDL |  |  |  |  | Materials |  |  | Total Direct ($k, $2019) | [6 empty] | Total Internal Labour (hours)
|  | Asset Class | Expenditure Class |  | $/Unit ($2019) | QTY | UOM | Materials | Int Labour | Contracts - Design | Contracts - Construct | Other | P50 Total | Chk | Project Engineer | Asset Management Engineer | Project Manager | Front Line Leader | Project Engineer Build | Site Manager Build | Operational Staff | Total Hours
Labour rates | [14 empty] | 162.4874 | 151.7974 | 176.3843 | 229.8341 | 162.4874 | 162.4874 | 133.6245
Design - Internal/External |  | Allocation | Allocation | [5 empty] | 0 | 900 |  |  | 900 |  | 0
Project Management & Engineering
| Project Establishment | Allocation | Allocation | [5 empty] | 70.5195 |  | 0 |  | 70.5195 |  | 302 | 92 | 32 | 8 |  |  |  | 434
| Project Management | Allocation | Allocation | [5 empty] | 550.9691 |  |  |  | 550.9691 |  | 192 |  | 1056 | 240 | 515 | 1152 | 56 | 3211
| Project Close-out, Testing & Commissioning | Allocation | Allocation | [5 empty] | 14.1107 |  | 0 |  | 14.1107 |  |  |  | 80 |  |  |  |  | 80
| Community Engagement | Allocation | Allocation | [5 empty] | 60 |  | 0 |  | 60 | [8 empty] | 0
Zone Substation works
Primary Plant
| 66kV Bay - Ring Bus | Subtransmission | Augmentation | SubtransmissionAugmentation | 185.475 |  | ea | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 66kV Exit - Line Feeder | Subtransmission | Augmentation | SubtransmissionAugmentation | 74.1545 |  | ea | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 66kV Exit - Transformer | Subtransmission | Augmentation | SubtransmissionAugmentation | 37.494 |  | ea | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Power transformer - 66/22kV 15/20MVA | Subtransmission | Augmentation | SubtransmissionAugmentation | 787.0745 |  | ea | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Power transformer - 66/22kV 20/33MVA | Subtransmission | Augmentation | SubtransmissionAugmentation | 1126.5675 | 2 | ea | 2253.135 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Decommission existing 10/16MVA Transformer | Subtransmission | Augmentation | SubtransmissionAugmentation | 0 | 3 | ea | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 22kV Indoor Switchgear - Transformers | Subtransmission | Augmentation | SubtransmissionAugmentation | 41.2559 |  | ea | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 22kV Neutral Earthing Resistors | Subtransmission | Augmentation | SubtransmissionAugmentation | 106.8132 |  | ea | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Earth Grid | Subtransmission | Augmentation | SubtransmissionAugmentation | 58.2657 |  | ea | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Station service transformer (1 MVA) | Subtransmission | Augmentation | SubtransmissionAugmentation | 169.008 | 2 | ea | 338.016 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Station service transformer (500 kVA) | Subtransmission | Augmentation | SubtransmissionAugmentation | 72.619 |  | ea | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| AC changeover board - Station | Subtransmission | Augmentation | SubtransmissionAugmentation | 39.295 |  | ea | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| AC C/O board footing | Subtransmission | Augmentation | SubtransmissionAugmentation | 0 |  | ea | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Arc Suppression Coil | SCADA/Network control | Augmentation | SCADA/Network controlAugmentation | 1158.3 | 1 | ea | 1158.3 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| ASC footing | Subtransmission | Augmentation | SubtransmissionAugmentation | 0 | 1 | ea | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 22kV switchboard - Metro | Subtransmission | Augmentation | SubtransmissionAugmentation | 1354 | 1 | ea | 1354 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 22kV switchboard - Rural | Subtransmission | Augmentation | SubtransmissionAugmentation | 1461.1163 |  | ea | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 22kV switchboard (no building) - Rural | Subtransmission | Augmentation | SubtransmissionAugmentation | 700 |  | ea | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 22kV Capacitor Bank - Modify | Subtransmission | Augmentation | SubtransmissionAugmentation | 91.2924 |  | ea | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Cap Bank footing | Subtransmission | Augmentation | SubtransmissionAugmentation | 0 | 1 | ea | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 66kV Dead Tank Circuit Breaker | Subtransmission | Augmentation | SubtransmissionAugmentation | 117.012 | 1 | ea | 117.012 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 66kV U/S Isolator | Subtransmission | Augmentation | SubtransmissionAugmentation | 23.788 | 2 | ea | 47.576 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 66kV 800A Rotary Disconnect | Subtransmission | Augmentation | SubtransmissionAugmentation | 25.198 | 2 | ea | 50.396 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 22kV Dead Tank Circuit Breaker | Subtransmission | Augmentation | SubtransmissionAugmentation | 107.006 |  | ea | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 22kV U/S Isolator | Subtransmission | Augmentation | SubtransmissionAugmentation | 7.664 |  | ea | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 22kV Current Transformer | Subtransmission | Augmentation | SubtransmissionAugmentation | 27.163 |  | ea | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 22kV Zero Sequence CTs | Subtransmission | Augmentation | SubtransmissionAugmentation | 0 |  | ea | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 22kV Voltage Transformer | Subtransmission | Augmentation | SubtransmissionAugmentation | 0 |  | ea | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 66kV Surge Arrestor | Subtransmission | Augmentation | SubtransmissionAugmentation | 0.62196 | 6 | ea | 3.7318 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 22KV Surge Arrestor | Subtransmission | Augmentation | SubtransmissionAugmentation | 0.62 |  | ea | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Primary Cable Testing | Subtransmission | Augmentation | SubtransmissionAugmentation | 0 |  | ea | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Neutral Bus | Subtransmission | Augmentation | SubtransmissionAugmentation | 93.854 | 1 | ea | 93.854 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| REFCL control room | Subtransmission | Augmentation | SubtransmissionAugmentation | 0 | 1 | ea | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Battery Room (single battery set) | Subtransmission | Augmentation | SubtransmissionAugmentation | 227.63 |  | ea | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| New Control Building | Subtransmission | Augmentation | SubtransmissionAugmentation | 369.039 |  | ea | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Primary Cables - 22kV | Subtransmission | Augmentation | SubtransmissionAugmentation | 0.15716 | 900 | p/mtr | 141.4449 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Feeder Exit Cables - 22kV | Subtransmission | Augmentation | SubtransmissionAugmentation | 0.05 |  | p/mtr | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Other | Subtransmission | Augmentation | SubtransmissionAugmentation | 15.0889 | 12 | ea | 181.0663 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 22kV Capacitor Bank (2x3 MVAr) - type 4 | Subtransmission | Augmentation | SubtransmissionAugmentation | 465.78 | 1 | ea | 465.78 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| One Tilt Slab control room | Subtransmission | Augmentation | SubtransmissionAugmentation | 0 |  | ea | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[15 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SCADA / Protection & Control/ Comms | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 66kV Line Protection Panel | SCADA/Network control | Augmentation | SCADA/Network controlAugmentation | 76.7296 |  | ea | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 66kV Substation Protection Panel (transformer & bus) | SCADA/Network control | Augmentation | SCADA/Network controlAugmentation | 223.6578 |  | ea | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 66/22kV Transformer Voltage Control & Regulation Cubicle | SCADA/Network control | Augmentation | SCADA/Network controlAugmentation | 252.1155 |  | ea | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Neutral Bus controller - 1 GFN | SCADA/Network control | Augmentation | SCADA/Network controlAugmentation | 48.9823 | 1 | ea | 48.9823 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Protection – GFN panels | SCADA/Network control | Augmentation | SCADA/Network controlAugmentation | 6.2431 |  | ea | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Power Quality/Switchgear Interface | SCADA/Network control | Augmentation | SCADA/Network controlAugmentation | 98.0077 |  | ea | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 22kV Protection & Control Modifications | SCADA/Network control | Augmentation | SCADA/Network controlAugmentation | 1.5 | 22 | ea | 33 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| SCIMS system - small | SCADA/Network control | Augmentation | SCADA/Network controlAugmentation | 92.2396 |  | ea | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Other protection works | SCADA/Network control | Augmentation | SCADA/Network controlAugmentation | 24.579 | 5 | ea | 122.8952 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Other AC & DC supplies |  | Subtransmission | Augmentation | SubtransmissionAugmentation | 30.9158 |  | ea | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Metering & System Monitoring |  | Subtransmission | Augmentation | SubtransmissionAugmentation | 4.5 |  | ea | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Infrastructure - Services |  | Subtransmission | Augmentation | SubtransmissionAugmentation | 6 | 1 | ea | 6 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Civil works | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Earthworks | Subtransmission | Augmentation | SubtransmissionAugmentation | 0 | 1 | ea | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Buildings | Subtransmission | Augmentation | SubtransmissionAugmentation | 0 | 1 | ea | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 22kV switchyard - install new puraceptor | Subtransmission | Augmentation | SubtransmissionAugmentation | 131.3953 |  | ea | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| - Other | Subtransmission | Augmentation | SubtransmissionAugmentation | 0 | 1 | ea | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Construction delivery & site control |  | Subtransmission | Augmentation | SubtransmissionAugmentation | 0 | 1 | ea | 0 | 0
Land purchase |  | Land | Non-Network | LandNon-Network | 0 |  | ea | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Subtotal Substation works | [7 empty] | 6415.1894 | 695.5994 | 900 | 5771.9785 | 118.5663 | 13901.3336 | 0
Check | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0
Feeder works |  |  |  |  | Material $/Unit | QTY | UOM | Materials | Int Labour | Contracts - Design | Contracts - Construct | Other | P50 Total
66kV/22kV Overhead Lines
New 66 kV Pole Line construction (6km): -
| Concrete Poles 20m (includes installation), per pole | Subtransmission | Augmentation | SubtransmissionAugmentation | 5.4308 |  | ea | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Cross Arms 66kV - Intermediate & Strain | Subtransmission | Augmentation | SubtransmissionAugmentation | 0.40306 |  | ea | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Conductor (19/4.75 AAC) | Subtransmission | Augmentation | SubtransmissionAugmentation | 15.18 |  | km | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Cross Arms 22kV LV - Intermediate & Strain | Distribution system assets | Augmentation | Distribution system assetsAugmentation | 0.43615 |  | ea | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Conductor (19/3.25 AAC) | Distribution system assets | Augmentation | Distribution system assetsAugmentation | 6.7848 |  | km | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Stays | Subtransmission | Augmentation | SubtransmissionAugmentation | 0.24562 |  | ea | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Supervision, Traffic Control, Set-Up Site & Clean-Up | Subtransmission | Augmentation | SubtransmissionAugmentation | 0 |  | km | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
66kV Line - Replace X-Arms & Insulators (1km): -
| Cross Arms 66kV - Intermediate & Strain | Subtransmission | Augmentation | SubtransmissionAugmentation | 0.40306 |  | ea | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Supervision, Traffic Control, Set-Up Site & Clean-Up | Subtransmission | Augmentation | SubtransmissionAugmentation | 0 |  | km | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
ADSS Cable Installed on Existing Poles (40km): -
| ADSS Fibre Optic Cable | Subtransmission | Augmentation | SubtransmissionAugmentation | 8.72 |  | km | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| OPGW Joint Box (Installed & Terminated on Existing Tower/Pole) | Subtransmission | Augmentation | SubtransmissionAugmentation | 6.795 |  | ea | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Vegetation Clearing - Light 66kV Line (6km):-
| Vegetation Clearing | Subtransmission | Augmentation | SubtransmissionAugmentation | 0 |  | km | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Subtotal 66kV/22kV Overhead Lines | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0
Feeder Cut-in works
22kV Underground Cable (150m) to NEW pole including gas switch and surge diverters: -
| Surge arrestor | Distribution system assets | Augmentation | Distribution system assetsAugmentation | 0.3785 |  | ea | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.573% | 0% | 32.12% | 0% | 0% | 0% | 65.31% | 100% | TRUE | 1.08
| Gas Switch | Distribution system assets | Augmentation | Distribution system assetsAugmentation | 15.42 |  | ea | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Concrete Poles 15.5m (includes installation), per pole | Distribution system assets | Augmentation | Distribution system assetsAugmentation | 6.06 |  | ea | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 22kV Underground Cable (150m) | Distribution system assets | Augmentation | Distribution system assetsAugmentation | 0.061705 |  | p/mtr | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Subtotal Feeder Cut-in works | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0
Subtotal feeder works | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0
Check | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0
Grand Total | [7 empty] | 6415.1894 | 695.5994 | 900 | 5771.9785 | 118.5663 | 13901.3336
Check | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0
| Zone Substation works | Subtransmission | Augmentation | SubtransmissionAugmentation |  |  |  | 5052.0119 | 0 | 0 | 5214.5862 | 116.6328 | 10383.2309
|  | Subtransmission | Replacement | SubtransmissionReplacement |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
|  | SCADA/Network control | Augmentation | SCADA/Network controlAugmentation |  |  |  | 1363.1775 | 0 | 0 | 557.3923 | 1.9336 | 1922.5034
|  | SCADA/Network control | Replacement | SCADA/Network controlReplacement |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Land | Non-Network | LandNon-Network |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
[8 empty] | 6415.1894 | 0 | 0 | 5771.9785 | 118.5663 | 12305.7342
| Design, Project Management & Engineering costs allocation | Subtransmission | Augmentation | SubtransmissionAugmentation |  |  |  |  | 586.9271 | 759.3946 | 0 |  | 1346.3217
|  | Subtransmission | Replacement | SubtransmissionReplacement |  |  |  |  | 0 | 0 | 0 |  | 0
|  | SCADA/Network control | Augmentation | SCADA/Network controlAugmentation |  |  |  |  | 108.6723 | 140.6054 | 0 |  | 249.2777
|  | SCADA/Network control | Replacement | SCADA/Network controlReplacement |  |  |  |  | 0 | 0 | 0 |  | 0
|  | Land | Non-Network | LandNon-Network |  |  |  |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 695.5994 | 900 | 0 | 0 | 1595.5994
| Total Substation works | Subtransmission | Augmentation | SubtransmissionAugmentation |  |  |  | 5052.0119 | 586.9271 | 759.3946 | 5214.5862 | 116.6328 | 11729.5525
|  | Subtransmission | Replacement | SubtransmissionReplacement |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
|  | SCADA/Network control | Augmentation | SCADA/Network controlAugmentation |  |  |  | 1363.1775 | 108.6723 | 140.6054 | 557.3923 | 1.9336 | 2171.7811
|  | SCADA/Network control | Replacement | SCADA/Network controlReplacement |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Land | Non-Network | LandNon-Network |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
[8 empty] | 6415.1894 | 695.5994 | 900 | 5771.9785 | 118.5663 | 13901.3336
[8 empty] | 0 | 0 | 0 | 0 | 0 | 0
| 66kV Overhead Lines | Subtransmission | Augmentation | SubtransmissionAugmentation |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Subtransmission | Replacement | SubtransmissionReplacement |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Distribution system assets | Augmentation | Distribution system assetsAugmentation |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Distribution system assets | Replacement | Distribution system assetsReplacement |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
[8 empty] | 0 | 0 | 0 | 0 | 0 | 0
[8 empty] | 0 | 0 | 0 | 0 | 0 | 0
| Feeder Cut-in works | Subtransmission | Augmentation | SubtransmissionAugmentation |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Subtransmission | Replacement | SubtransmissionReplacement |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Distribution system assets | Augmentation | Distribution system assetsAugmentation |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Distribution system assets | Replacement | Distribution system assetsReplacement |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
[8 empty] | 0 | 0 | 0 | 0 | 0 | 0
[8 empty] | 0 | 0 | 0 | 0 | 0 | 0
Note on G52: AST: Average unit rate across all cable types, excluding feeder exit cable

## ELM_Det
Confidential
ELM Volumes & Unit Rates
ELM |  |  |  |  | Materials |  |  | Total Direct ($k, $2019) | [6 empty] | Total Internal Labour (hours)
|  | Asset Class | Expenditure Class |  | $/Unit ($2019) | QTY | UOM | Materials | Int Labour | Contracts - Design | Contracts - Construct | Other | P50 Total | Chk | Project Engineer | Asset Management Engineer | Project Manager | Front Line Leader | Project Engineer Build | Site Manager Build | Operational Staff | Total Hours
Labour rates | [14 empty] | 162.4874 | 151.7974 | 176.3843 | 229.8341 | 162.4874 | 162.4874 | 133.6245
Design - Internal/External |  | Allocation | Allocation | [5 empty] | 0 | 800 |  |  | 800 |  | 0
Project Management & Engineering
| Project Establishment | Allocation | Allocation | [5 empty] | 70.5195 |  | 0 |  | 70.5195 |  | 302 | 92 | 32 | 8 |  |  | 0 | 434
| Project Management | Allocation | Allocation | [5 empty] | 509.321 |  |  |  | 509.321 |  | 192 |  | 904 | 208 | 707 | 960 | 0 | 2971
| Project Close-out, Testing & Commissioning | Allocation | Allocation | [5 empty] | 14.1107 |  | 0 |  | 14.1107 |  |  |  | 80 |  |  |  | 0 | 80
| Community Engagement | Allocation | Allocation | [5 empty] | 60 |  | 0 |  | 60 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Zone Substation works
Primary Plant
| 66kV Bay - Ring Bus | Subtransmission | Augmentation | SubtransmissionAugmentation | 185.475 |  | ea | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 66kV Exit - Line Feeder | Subtransmission | Augmentation | SubtransmissionAugmentation | 74.1545 |  | ea | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 66kV Exit - Transformer | Subtransmission | Augmentation | SubtransmissionAugmentation | 37.494 |  | ea | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Power transformer - 66/22kV 15/20MVA | Subtransmission | Augmentation | SubtransmissionAugmentation | 787.0745 |  | ea | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 22kV Indoor Switchgear - Transformers | Subtransmission | Augmentation | SubtransmissionAugmentation | 41.2559 |  | ea | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 22kV Neutral Earthing Resistors | Subtransmission | Augmentation | SubtransmissionAugmentation | 106.8132 |  | ea | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Earth Grid | Subtransmission | Augmentation | SubtransmissionAugmentation | 58.2657 |  | ea | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Station service transformer (1 MVA) | Subtransmission | Augmentation | SubtransmissionAugmentation | 169.008 | 2 | ea | 338.016 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Station service transformer (500 kVA) | Subtransmission | Augmentation | SubtransmissionAugmentation | 72.619 |  | ea | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| AC changeover board - Station | Subtransmission | Augmentation | SubtransmissionAugmentation | 39.295 |  | ea | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| AC C/O board footing | Subtransmission | Augmentation | SubtransmissionAugmentation | 0 |  | ea | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Arc Suppression Coil | SCADA/Network control | Augmentation | SCADA/Network controlAugmentation | 1158.3 | 1 | ea | 1158.3 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| ASC footing | Subtransmission | Augmentation | SubtransmissionAugmentation | 0 | 1 | ea | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 22kV switchboard - Metro | Subtransmission | Augmentation | SubtransmissionAugmentation | 1354 | 1 | ea | 1354 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 22kV switchboard - Rural | Subtransmission | Augmentation | SubtransmissionAugmentation | 1461.1163 |  | ea | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 22kV switchboard (no building) - Rural | Subtransmission | Augmentation | SubtransmissionAugmentation | 700 |  | ea | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 22kV Capacitor Bank - Modify | Subtransmission | Augmentation | SubtransmissionAugmentation | 91.2924 |  | ea | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Cap Bank footing | Subtransmission | Augmentation | SubtransmissionAugmentation | 0 | 1 | ea | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 22kV Dead Tank Circuit Breaker | Subtransmission | Augmentation | SubtransmissionAugmentation | 107.006 |  | ea | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 22kV U/S Isolator | Subtransmission | Augmentation | SubtransmissionAugmentation | 7.664 | 2 | ea | 15.328 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 22kV Current Transformer | Subtransmission | Augmentation | SubtransmissionAugmentation | 27.163 |  | ea | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 22kV Zero Sequence CTs | Subtransmission | Augmentation | SubtransmissionAugmentation | 0 |  | ea | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 22kV Voltage Transformer | Subtransmission | Augmentation | SubtransmissionAugmentation | 0 |  | ea | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 22KV Surge Arrestor | Subtransmission | Augmentation | SubtransmissionAugmentation | 0.62 |  | ea | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Primary Cable Testing | Subtransmission | Augmentation | SubtransmissionAugmentation | 0 |  | ea | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Neutral Bus | Subtransmission | Augmentation | SubtransmissionAugmentation | 93.854 | 1 | ea | 93.854 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| REFCL control room | Subtransmission | Augmentation | SubtransmissionAugmentation | 0 | 1 | ea | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Battery Room (single battery set) | Subtransmission | Augmentation | SubtransmissionAugmentation | 227.63 |  | ea | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| New Control Building | Subtransmission | Augmentation | SubtransmissionAugmentation | 369.039 |  | ea | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Primary Cables - 22kV | Subtransmission | Augmentation | SubtransmissionAugmentation | 0.10164 | 580 | p/mtr | 58.9533 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Feeder Exit Cables - 22kV | Subtransmission | Augmentation | SubtransmissionAugmentation | 0.05 |  | p/mtr | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Other | Subtransmission | Augmentation | SubtransmissionAugmentation | 37.322 | 6 | ea | 223.932 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 22kV Capacitor Bank (2x3 MVAr) - type 4 | Subtransmission | Augmentation | SubtransmissionAugmentation | 465.78 | 1 | ea | 465.78 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| One Tilt Slab control room | Subtransmission | Augmentation | SubtransmissionAugmentation | 0 |  | ea | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SCADA / Protection & Control/ Comms
| 66kV Line Protection Panel | SCADA/Network control | Augmentation | SCADA/Network controlAugmentation | 76.7296 |  | ea | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 66kV Substation Protection Panel (transformer & bus) | SCADA/Network control | Augmentation | SCADA/Network controlAugmentation | 223.6578 |  | ea | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 66/22kV Transformer Voltage Control & Regulation Cubicle | SCADA/Network control | Augmentation | SCADA/Network controlAugmentation | 252.1155 |  | ea | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Neutral Bus controller - 1 GFN | SCADA/Network control | Augmentation | SCADA/Network controlAugmentation | 48.9823 | 1 | ea | 48.9823 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Protection – GFN panels | SCADA/Network control | Augmentation | SCADA/Network controlAugmentation | 6.2431 |  | ea | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Power Quality/Switchgear Interface | SCADA/Network control | Augmentation | SCADA/Network controlAugmentation | 98.0077 |  | ea | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 22kV Protection & Control Modifications | SCADA/Network control | Augmentation | SCADA/Network controlAugmentation | 1 | 17 | ea | 17 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| SCIMS system - small | SCADA/Network control | Augmentation | SCADA/Network controlAugmentation | 92.2396 |  | ea | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Other protection works | SCADA/Network control | Augmentation | SCADA/Network controlAugmentation | 5.6667 | 3 | ea | 17 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Other AC & DC supplies |  | Subtransmission | Augmentation | SubtransmissionAugmentation | 39.6 | 1 | ea | 39.6 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Metering & System Monitoring |  | Subtransmission | Augmentation | SubtransmissionAugmentation | 1 | 1 | ea | 1 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Infrastructure - Services |  | Subtransmission | Augmentation | SubtransmissionAugmentation | 6 | 1 | ea | 6 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Civil works
| Earthworks | Subtransmission | Augmentation | SubtransmissionAugmentation | 0 | 1 | ea | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Buildings | Subtransmission | Augmentation | SubtransmissionAugmentation | 0 | 1 | ea | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 22kV switchyard - install new puraceptor | Subtransmission | Augmentation | SubtransmissionAugmentation | 131.3953 |  | ea | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| - Other | Subtransmission | Augmentation | SubtransmissionAugmentation | 0 | 1 | ea | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Construction delivery & site control |  | Subtransmission | Augmentation | SubtransmissionAugmentation | 0 | 1 | ea | 0 | 0
Land purchase |  | Land | Non-Network | LandNon-Network | 0 |  | ea | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Subtotal Substation works | [7 empty] | 3837.7455 | 653.9513 | 800 | 3574.7334 | 74.6419 | 8941.0721 | 0
Check | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0
Feeder works |  |  |  |  | Material $/Unit | QTY | UOM | Materials | Int Labour | Contracts - Design | Contracts - Construct | Other | P50 Total
66kV/22kV Overhead Lines
New 66 kV Pole Line construction (5km): -
| Concrete Poles 20m (includes installation), per pole | Subtransmission | Augmentation | SubtransmissionAugmentation | 5.4308 |  | ea | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Cross Arms 66kV - Intermediate & Strain | Subtransmission | Augmentation | SubtransmissionAugmentation | 0.40306 |  | ea | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Conductor (19/4.75 AAC) | Subtransmission | Augmentation | SubtransmissionAugmentation | 15.18 |  | km | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Cross Arms 22kV LV - Intermediate & Strain | Distribution system assets | Augmentation | Distribution system assetsAugmentation | 0.43615 |  | ea | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Conductor (19/3.25 AAC) | Distribution system assets | Augmentation | Distribution system assetsAugmentation | 6.7848 |  | km | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Stays | Subtransmission | Augmentation | SubtransmissionAugmentation | 0.24562 |  | ea | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Supervision, Traffic Control, Set-Up Site & Clean-Up | Subtransmission | Augmentation | SubtransmissionAugmentation | 0 |  | km | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
66kV Line - Replace X-Arms & Insulators (/km): -
| Cross Arms 66kV - Intermediate & Strain | Subtransmission | Augmentation | SubtransmissionAugmentation | 0.40306 |  | ea | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Supervision, Traffic Control, Set-Up Site & Clean-Up | Subtransmission | Augmentation | SubtransmissionAugmentation | 0 |  | km | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
ADSS Cable Installed on Existing Poles (5km): -
| ADSS Fibre Optic Cable | Subtransmission | Augmentation | SubtransmissionAugmentation | 8.72 |  | km | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| OPGW Joint Box (Installed & Terminated on Existing Tower/Pole) | Subtransmission | Augmentation | SubtransmissionAugmentation | 6.795 |  | ea | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Vegetation Clearing - Light 66kV Line (5km):-
| Vegetation Clearing | Subtransmission | Augmentation | SubtransmissionAugmentation | 0 |  | km | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Subtotal 66kV/22kV Overhead Lines | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0
Feeder Cut-in works
22kV Underground Cable (150m) to NEW pole including gas switch and surge diverters: -
| Surge arrestor | Distribution system assets | Augmentation | Distribution system assetsAugmentation | 0.3785 |  | ea | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.573% | 0% | 32.12% | 0% | 0% | 0% | 65.31% | 100% | TRUE | 1.08
| Gas Switch | Distribution system assets | Augmentation | Distribution system assetsAugmentation | 15.42 |  | ea | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Concrete Poles 15.5m (includes installation), per pole | Distribution system assets | Augmentation | Distribution system assetsAugmentation | 6.06 |  | ea | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 22kV Underground Cable (150m) | Distribution system assets | Augmentation | Distribution system assetsAugmentation | 0.061705 |  | p/mtr | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Subtotal Feeder Cut-in works | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0
Subtotal feeder works | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0
Check | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0
Grand Total | [7 empty] | 3837.7455 | 653.9513 | 800 | 3574.7334 | 74.6419 | 8941.0721
Check | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0
| Zone Substation works | Subtransmission | Augmentation | SubtransmissionAugmentation |  |  |  | 2596.4633 | 0 | 0 | 3220.839 | 72.7083 | 5890.0107
|  | Subtransmission | Replacement | SubtransmissionReplacement |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
|  | SCADA/Network control | Augmentation | SCADA/Network controlAugmentation |  |  |  | 1241.2823 | 0 | 0 | 353.8944 | 1.9336 | 1597.1102
|  | SCADA/Network control | Replacement | SCADA/Network controlReplacement |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Land | Non-Network | LandNon-Network |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
[8 empty] | 3837.7455 | 0 | 0 | 3574.7334 | 74.6419 | 7487.1209
| Design, Project Management & Engineering costs allocation | Subtransmission | Augmentation | SubtransmissionAugmentation |  |  |  |  | 514.4541 | 629.3485 | 0 |  | 1143.8026
|  | Subtransmission | Replacement | SubtransmissionReplacement |  |  |  |  | 0 | 0 | 0 |  | 0
|  | SCADA/Network control | Augmentation | SCADA/Network controlAugmentation |  |  |  |  | 139.4972 | 170.6515 | 0 |  | 310.1486
|  | SCADA/Network control | Replacement | SCADA/Network controlReplacement |  |  |  |  | 0 | 0 | 0 |  | 0
|  | Land | Non-Network | LandNon-Network |  |  |  |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 653.9513 | 800 | 0 | 0 | 1453.9513
| Total Substation works | Subtransmission | Augmentation | SubtransmissionAugmentation |  |  |  | 2596.4633 | 514.4541 | 629.3485 | 3220.839 | 72.7083 | 7033.8133
|  | Subtransmission | Replacement | SubtransmissionReplacement |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
|  | SCADA/Network control | Augmentation | SCADA/Network controlAugmentation |  |  |  | 1241.2823 | 139.4972 | 170.6515 | 353.8944 | 1.9336 | 1907.2589
|  | SCADA/Network control | Replacement | SCADA/Network controlReplacement |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Land | Non-Network | LandNon-Network |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
[8 empty] | 3837.7455 | 653.9513 | 800 | 3574.7334 | 74.6419 | 8941.0721
[8 empty] | 0 | 0 | 0 | 0 | 0 | 0
| 66kV Overhead Lines | Subtransmission | Augmentation | SubtransmissionAugmentation |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Subtransmission | Replacement | SubtransmissionReplacement |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Distribution system assets | Augmentation | Distribution system assetsAugmentation |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Distribution system assets | Replacement | Distribution system assetsReplacement |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
[8 empty] | 0 | 0 | 0 | 0 | 0 | 0
[8 empty] | 0 | 0 | 0 | 0 | 0 | 0
| Feeder Cut-in works | Subtransmission | Augmentation | SubtransmissionAugmentation |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Subtransmission | Replacement | SubtransmissionReplacement |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Distribution system assets | Augmentation | Distribution system assetsAugmentation |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Distribution system assets | Replacement | Distribution system assetsReplacement |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
[8 empty] | 0 | 0 | 0 | 0 | 0 | 0
[8 empty] | 0 | 0 | 0 | 0 | 0 | 0
Note on G46: AST: Average unit rate across all cable types, excluding feeder exit cable

## RWN_Det
Confidential
RWN Volumes & Unit Rates
RWN |  |  |  |  | Materials |  |  | Total Direct ($k, $2019) | [6 empty] | Total Internal Labour (hours)
|  | Asset Class | Expenditure Class |  | $/Unit ($2019) | QTY | UOM | Materials | Int Labour | Contracts - Design | Contracts - Construct | Other | P50 Total | Chk | Project Engineer | Asset Management Engineer | Project Manager | Front Line Leader | Project Engineer Build | Site Manager Build | Operational Staff | Total Hours
Labour rates | [14 empty] | 162.4874 | 151.7974 | 176.3843 | 229.8341 | 162.4874 | 162.4874 | 133.6245
Design - Internal/External |  | Allocation | Allocation | [5 empty] | 0 | 550 |  |  | 550
Project Management & Engineering
| Project Establishment | Allocation | Allocation | [5 empty] | 52.5967 |  | 0 |  | 52.5967 |  | 180 | 111 | 16 | 16 |  |  |  | 323
| Project Management | Allocation | Allocation | [5 empty] | 487.6525 |  | 0 |  | 487.6525 |  | 108 |  | 976 |  | 634 | 1152 | 58 | 2928
| Project Close-out, Testing & Commissioning | Allocation | Allocation | [5 empty] | 16.4882 |  | 0 |  | 16.4882 |  | 32 |  | 64 |  |  |  |  | 96
| Community Engagement | Allocation | Allocation | [7 empty] | 0 |  | 0 | [8 empty] | 0
Zone Substation works
Primary Plant
| Station service transformer (500 kVA) | Subtransmission | Augmentation | SubtransmissionAugmentation | 72.619 |  | ea | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Station service transformer (750 kVA) | Subtransmission | Augmentation | SubtransmissionAugmentation | 112.828 | 2 | ea | 225.656 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Capacitance reducing isolation substation (10 MVA) | Subtransmission | Augmentation | SubtransmissionAugmentation | 465.0023 |  | ea | 0 | 0 |  |  |  |  | 0
| AC changeover board - Station | Subtransmission | Augmentation | SubtransmissionAugmentation | 39.295 |  | ea | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| AC changeover board - REFCL | Subtransmission | Augmentation | SubtransmissionAugmentation | 42.975 |  | ea | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| AC C/O board footing | Subtransmission | Augmentation | SubtransmissionAugmentation | 0 |  | ea | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Arc Suppression Coil | SCADA/Network control | Augmentation | SCADA/Network controlAugmentation | 1158.3 | 1 | ea | 1158.3 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| ASC footing | Subtransmission | Augmentation | SubtransmissionAugmentation | 0 | 1 | ea | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 22kV switchboard - Metro | Subtransmission | Augmentation | SubtransmissionAugmentation | 1354 |  | ea | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 22kV switchboard - Rural | Subtransmission | Augmentation | SubtransmissionAugmentation | 1461.1163 |  | ea | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 22kV switchboard (no building) - Rural | Subtransmission | Augmentation | SubtransmissionAugmentation | 700 |  | ea | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 22kV Capacitor Bank - Modify | Subtransmission | Augmentation | SubtransmissionAugmentation | 91.2924 |  | ea | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Cap Bank footing | Subtransmission | Augmentation | SubtransmissionAugmentation | 0 |  | ea | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 22kV Dead Tank Circuit Breaker | Subtransmission | Augmentation | SubtransmissionAugmentation | 107.006 | 1 | ea | 107.006 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 22kV U/S Isolator | Subtransmission | Augmentation | SubtransmissionAugmentation | 7.664 | 2 | ea | 15.328 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 22kV Current Transformer | Subtransmission | Augmentation | SubtransmissionAugmentation | 27.163 |  | ea | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 22kV Zero Sequence CTs | Subtransmission | Augmentation | SubtransmissionAugmentation | 0 | 1 | ea | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 22kV Voltage Transformer | Subtransmission | Augmentation | SubtransmissionAugmentation | 0 | 1 | ea | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 22KV Surge Arrestor | Subtransmission | Augmentation | SubtransmissionAugmentation | 0.62 | 3 | ea | 1.86 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Primary Cable Testing | Subtransmission | Augmentation | SubtransmissionAugmentation | 0 | 1 | ea | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Neutral Bus | Subtransmission | Augmentation | SubtransmissionAugmentation | 93.854 | 1 | ea | 93.854 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| REFCL control room | Subtransmission | Augmentation | SubtransmissionAugmentation | 0 |  | ea | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Battery Room (2 battery sets) | Subtransmission | Augmentation | SubtransmissionAugmentation | 174.5855 |  | ea | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| New Control Building | Subtransmission | Augmentation | SubtransmissionAugmentation | 369.039 |  | ea | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Primary Cables - 22kV | Subtransmission | Augmentation | SubtransmissionAugmentation | 0.045836 | 500 | p/mtr | 22.918 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Feeder Exit Cables - 22kV | Subtransmission | Augmentation | SubtransmissionAugmentation | 0.05 |  | p/mtr | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Other | Subtransmission | Augmentation | SubtransmissionAugmentation | 0 |  | ea | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 22kV Capacitor Bank (2x3 MVAr) - type 2 | Subtransmission | Augmentation | SubtransmissionAugmentation | 406.8 | 1 | ea | 406.8 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| One Tilt Slab control room | Subtransmission | Augmentation | SubtransmissionAugmentation | 0 |  | ea | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SCADA / Protection & Control/ Comms
| Neutral Bus controller - 2 GFNs | SCADA/Network control | Augmentation | SCADA/Network controlAugmentation | 61.8191 | 1 | ea | 61.8191 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Protection – GFN panels | SCADA/Network control | Augmentation | SCADA/Network controlAugmentation | 6.2431 |  | ea | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| GFN interface relay | SCADA/Network control | Augmentation | SCADA/Network controlAugmentation | 8.6956 |  | ea | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| High Impedance Busbar Protection cubicle | SCADA/Network control | Augmentation | SCADA/Network controlAugmentation | 58.4171 | 2 | ea | 116.8341 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Capacitor Bank Prot & Cntl (2x3MVAr) | SCADA/Network control | Augmentation | SCADA/Network controlAugmentation | 33.6836 | 1 | ea | 33.6836 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Power Quality/Switchgear Interface | SCADA/Network control | Augmentation | SCADA/Network controlAugmentation | 98.0077 |  | ea | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 22kV Protection & Control Modifications | SCADA/Network control | Augmentation | SCADA/Network controlAugmentation | 2.5455 | 11 | ea | 28 | 0 | [5 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0
| Other protection works | SCADA/Network control | Augmentation | SCADA/Network controlAugmentation | 13.4667 | 3 | ea | 40.4 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Other AC & DC supplies |  | Subtransmission | Augmentation | SubtransmissionAugmentation | 5.1862 | 3 | ea | 15.5585 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Metering & System Monitoring |  | Subtransmission | Augmentation | SubtransmissionAugmentation | 0 |  | ea | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Infrastructure - Services |  | Subtransmission | Augmentation | SubtransmissionAugmentation | 10.2842 | 2 | ea | 20.5683 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Civil works
| Earthworks | Subtransmission | Augmentation | SubtransmissionAugmentation | 1.2514 | 1 | ea | 1.2514 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Buildings | Subtransmission | Augmentation | SubtransmissionAugmentation | 0 |  | ea | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 22kV switchyard - install new puraceptor | Subtransmission | Augmentation | SubtransmissionAugmentation | 131.3953 |  | ea | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| - Other | Subtransmission | Augmentation | SubtransmissionAugmentation | 0 |  | ea | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Construction delivery & site control |  | Subtransmission | Augmentation | SubtransmissionAugmentation | 0 |  | ea | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Land purchase |  | Land | Non-Network | LandNon-Network | 0 |  | ea | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Subtotal Substation works | [7 empty] | 2349.837 | 556.7374 | 550 | 2000.0105 | 65.4925 | 5522.0774
Check
Feeder works |  |  |  |  | Material $/Unit | QTY | UOM | Materials | Int Labour | Contracts - Design | Contracts - Construct | Other | P50 Total
Network Balancing | [31 empty] | Total hrs p/unit
| Design Labour - internal / external | Distribution system assets | Augmentation | Distribution system assetsAugmentation | 0 | 0 | feeders |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27.2% | 72.8% | 0% | 0% | 0% | 0% | 0% | 100% | TRUE | 54.4153
| Third conductor installation | Distribution system assets | Augmentation | Distribution system assetsAugmentation |  | 0 | spans | [6 empty] | 0 | [8 empty] | 0% | 14.07% | 24.32% | 0% | 17.6% | 44% | 0% | 100% | TRUE
| Unbonding cable | Distribution system assets | Augmentation | Distribution system assetsAugmentation |  | 0 | location | [6 empty] | 0 | [8 empty] | 0% | 11.32% | 25.1% | 0% | 18.17% | 45.41% | 0% | 100% | TRUE
| Phase rotation | Distribution system assets | Augmentation | Distribution system assetsAugmentation |  | 0 | rotations | [6 empty] | 0 | [8 empty] | 0% | 17.74% | 23.28% | 0% | 16.85% | 42.13% | 0% | 100% | TRUE
| Balancing capacitors | Distribution system assets | Augmentation | Distribution system assetsAugmentation | 18.1336 | 0 | installations | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 6.924% | 26.35% | 0% | 19.07% | 47.66% | 0% | 100% | TRUE | 20.2193
| Inherent works - various feeder based works | Distribution system assets | Augmentation | Distribution system assetsAugmentation | 0 | 0 | feeders | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 100% | TRUE | 46.3981
| Phase plate correction | Distribution system assets | Replacement | Distribution system assetsReplacement | 0 | 0 | feeders & RC sections | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 | [9 empty] | 0
| Fuse removal and install solid link | Distribution system assets | Replacement | Distribution system assetsReplacement | 0 | 0 | fuses | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 100% | TRUE | 1.2069
| Install fusesaver and control box - per site | Distribution system assets | Augmentation | Distribution system assetsAugmentation | 12.4291 | 0 | sites | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 100% | TRUE | 23.0218
| Install new ACR for switching | Distribution system assets | Augmentation | Distribution system assetsAugmentation | 22.6039 | 0 | ACRs | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30.31% | 32.45% | 37.24% | 0% | 0% | 0% | 0% | 100% | TRUE | 42.966
| Subtotal Network Balancing | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0
Line Hardening
| Surge arrestor replacement | Distribution system assets | Replacement | Distribution system assetsReplacement | 0.3785 | 0 | ea | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.573% | 0% | 32.12% | 0% | 0% | 0% | 65.31% | 100% | TRUE | 1.08
| Cable On-Line Testing | Distribution system assets | Replacement | Distribution system assetsReplacement | 0 | 0 | ea | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 100% |  |  | 100% | TRUE | 1.8482
| Cable Off-Line Testing | Distribution system assets | Replacement | Distribution system assetsReplacement | 0 | 0 | ea | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 100% |  |  | 100% | TRUE | 61.6082
| Cable - Replace Fitting | Distribution system assets | Replacement | Distribution system assetsReplacement | 5.2026 | 0 | ea | 0 | 0 |  | 0 |  | 0 | 0 | [7 empty] | 0 | [7 empty] | 0% | FALSE
| Cable - Replace Cable Section - per m | Distribution system assets | Replacement | Distribution system assetsReplacement | 0.05 | 0 | m | 0 | 0 |  | 0 |  | 0 | 0 | [7 empty] | 0 | [7 empty] | 0% | FALSE
Compatible Equipment
| ACR upgrade | Distribution system assets | Replacement | Distribution system assetsReplacement | 15 | 0 | ea | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30.31% | 32.45% | 37.24% | 0% | 0% | 0% | 0% | 100% | TRUE | 14.42
| ACR replacement | Distribution system assets | Replacement | Distribution system assetsReplacement | 22.6039 | 0 | ea | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30.31% | 32.45% | 37.24% | 0% | 0% | 0% | 0% | 100% | TRUE | 42.966
| Voltage regulator upgrade | Distribution system assets | Replacement | Distribution system assetsReplacement | 15.156 | 0 | ea | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11.82% | 49.78% | 38.4% | 0% | 0% | 0% | 0% | 100% | TRUE | 144.7042
| Voltage regulator replacement | Distribution system assets | Replacement | Distribution system assetsReplacement | 193.2305 | 0 | ea | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 69.94% | 4.845% | 25.21% | 0% | 0% | 0% | 0% | 100% | TRUE | 220.4113
Distribution Code | [21 empty] | 0
| HV customers isolation substation (3.0 MVA) | Distribution system assets | Augmentation | Distribution system assetsAugmentation | 0 | 0 | ea | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18.11% | 21.48% | 60.41% | 0% | 0% | 0% | 0% | 100% | TRUE | 469.7767
| HV customers isolation substation (5.0 MVA) | Distribution system assets | Augmentation | Distribution system assetsAugmentation | 0 | 0 | ea | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18.11% | 42.96% | 38.93% | 0% | 0% | 0% | 0% | 100% | TRUE | 500.1505
| HV customers isolation substation (7.5 MVA) | Distribution system assets | Augmentation | Distribution system assetsAugmentation | 0 | 0 | ea | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18.11% | 42.96% | 38.93% | 0% | 0% | 0% | 0% | 100% | TRUE | 416.1112
| Line Hardening | Distribution system assets | Replacement | Distribution system assetsReplacement | 32.7402 | 0 | ea | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30.31% | 32.45% | 37.24% | 0% | 0% | 0% | 0% | 100% | TRUE | 61.06
Subtotal feeder works | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0
Check
Grand Total | [7 empty] | 2349.837 | 556.7374 | 550 | 2000.0105 | 65.4925 | 5522.0774
Check
| Zone Substation works | Subtransmission | Augmentation | SubtransmissionAugmentation |  |  |  | 910.8002 | 0 | 0 | 1702.3388 | 63.5589 | 2676.6979
|  | Subtransmission | Replacement | SubtransmissionReplacement |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
|  | SCADA/Network control | Augmentation | SCADA/Network controlAugmentation |  |  |  | 1439.0368 | 0 | 0 | 297.6717 | 1.9336 | 1738.6421
|  | SCADA/Network control | Replacement | SCADA/Network controlReplacement |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Land | Non-Network | LandNon-Network |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
[8 empty] | 2349.837 | 0 | 0 | 2000.0105 | 65.4925 | 4415.34
| Design, Project Management & Engineering costs allocation | Subtransmission | Augmentation | SubtransmissionAugmentation |  |  |  |  | 337.5092 | 333.4248 | 0 |  | 670.934
|  | Subtransmission | Replacement | SubtransmissionReplacement |  |  |  |  | 0 | 0 | 0 |  | 0
|  | SCADA/Network control | Augmentation | SCADA/Network controlAugmentation |  |  |  |  | 219.2282 | 216.5752 | 0 |  | 435.8034
|  | SCADA/Network control | Replacement | SCADA/Network controlReplacement |  |  |  |  | 0 | 0 | 0 |  | 0
|  | Land | Non-Network | LandNon-Network |  |  |  |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 556.7374 | 550 | 0 | 0 | 1106.7374
| Total Substation works | Subtransmission | Augmentation | SubtransmissionAugmentation |  |  |  | 910.8002 | 337.5092 | 333.4248 | 1702.3388 | 63.5589 | 3347.6319
|  | Subtransmission | Replacement | SubtransmissionReplacement |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
|  | SCADA/Network control | Augmentation | SCADA/Network controlAugmentation |  |  |  | 1439.0368 | 219.2282 | 216.5752 | 297.6717 | 1.9336 | 2174.4455
|  | SCADA/Network control | Replacement | SCADA/Network controlReplacement |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Land | Non-Network | LandNon-Network |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
[8 empty] | 2349.837 | 556.7374 | 550 | 2000.0105 | 65.4925 | 5522.0774
[8 empty] | 0 | 0 | 0 | 0 | 0 | 0
| Network Balancing | Distribution system assets | Augmentation | Distribution system assetsAugmentation |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Distribution system assets | Replacement | Distribution system assetsReplacement |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
[8 empty] | 0 | 0 | 0 | 0 | 0 | 0
[8 empty] | 0 | 0 | 0 | 0 | 0 | 0
Note on G41: AST: Average unit rate across all cable types, excluding feeder exit cable

## KMS_Det
Confidential
KMS Volumes & Unit Rates
KMS |  |  |  |  | Materials |  |  | Total Direct ($k, $2019) | [6 empty] | Total Internal Labour (hours)
|  | Asset Class | Expenditure Class |  | $/Unit ($2019) | QTY | UOM | Materials | Int Labour | Contracts - Design | Contracts - Construct | Other | P50 Total | Chk | Project Engineer | Asset Management Engineer | Project Manager | Front Line Leader | Project Engineer Build | Site Manager Build | Operational Staff | Total Hours
Labour rates | [14 empty] | 162.4874 | 151.7974 | 176.3843 | 229.8341 | 162.4874 | 162.4874 | 133.6245
Design - Internal/External |  | Allocation | Allocation | [5 empty] | 0 | 300 |  |  | 300
Project Management & Engineering
| Project Establishment | Allocation | Allocation | [5 empty] | 70.5195 |  | 0 |  | 70.5195 |  | 302 | 92 | 32 | 8 |  |  |  | 434
| Project Management | Allocation | Allocation | [5 empty] | 198.7552 |  | 0 |  | 198.7552 |  | 96 |  | 296 | 120 | 213.5 | 384 | 47 | 1156.5
| Project Close-out, Testing & Commissioning | Allocation | Allocation | [5 empty] | 14.1107 |  | 0 |  | 14.1107 |  |  |  | 80 |  |  |  |  | 80
| Community Engagement | Allocation | Allocation | [7 empty] | 0 |  | 0 | [8 empty] | 0
Zone Substation works
Primary Plant
| Station service transformer (500 kVA) | Subtransmission | Augmentation | SubtransmissionAugmentation | 72.619 |  | ea | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Station service transformer (750 kVA) | Subtransmission | Augmentation | SubtransmissionAugmentation | 112.828 |  | ea | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Capacitance reducing isolation substation (10 MVA) | Subtransmission | Augmentation | SubtransmissionAugmentation | 465.0023 |  | ea | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| AC changeover board - Station | Subtransmission | Augmentation | SubtransmissionAugmentation | 39.295 |  | ea | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| AC changeover board - REFCL | Subtransmission | Augmentation | SubtransmissionAugmentation | 42.975 | 1 | ea | 42.975 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| AC C/O board footing | Subtransmission | Augmentation | SubtransmissionAugmentation | 0 |  | ea | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Arc Suppression Coil | SCADA/Network control | Augmentation | SCADA/Network controlAugmentation | 1158.3 | 1 | ea | 1158.3 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| ASC footing | Subtransmission | Augmentation | SubtransmissionAugmentation | 0 |  | ea | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 22kV switchboard - Metro | Subtransmission | Augmentation | SubtransmissionAugmentation | 1354 |  | ea | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 22kV switchboard - Rural | Subtransmission | Augmentation | SubtransmissionAugmentation | 1461.1163 |  | ea | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 22kV switchboard (no building) - Rural | Subtransmission | Augmentation | SubtransmissionAugmentation | 700 |  | ea | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 22kV Capacitor Bank - Modify | Subtransmission | Augmentation | SubtransmissionAugmentation | 91.2924 |  | ea | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Cap Bank footing | Subtransmission | Augmentation | SubtransmissionAugmentation | 0 |  | ea | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 22kV Dead Tank Circuit Breaker | Subtransmission | Augmentation | SubtransmissionAugmentation | 107.006 |  | ea | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 22kV U/S Isolator | Subtransmission | Augmentation | SubtransmissionAugmentation | 7.664 |  | ea | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 22kV Current Transformer | Subtransmission | Augmentation | SubtransmissionAugmentation | 27.163 |  | ea | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 22kV Zero Sequence CTs | Subtransmission | Augmentation | SubtransmissionAugmentation | 0 |  | ea | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 22kV Voltage Transformer | Subtransmission | Augmentation | SubtransmissionAugmentation | 0 |  | ea | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 22KV Surge Arrestor | Subtransmission | Augmentation | SubtransmissionAugmentation | 0.62 |  | ea | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Primary Cable Testing | Subtransmission | Augmentation | SubtransmissionAugmentation | 0 |  | ea | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Neutral Bus | Subtransmission | Augmentation | SubtransmissionAugmentation | 93.854 |  | ea | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Type 3 REFCL control room | Subtransmission | Augmentation | SubtransmissionAugmentation | 109.1759 | 1 | ea | 109.1759 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Battery Room (2 battery sets) | Subtransmission | Augmentation | SubtransmissionAugmentation | 174.5855 |  | ea | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| New Control Building | Subtransmission | Augmentation | SubtransmissionAugmentation | 369.039 |  | ea | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Primary Cables - 22kV | Subtransmission | Augmentation | SubtransmissionAugmentation | 0.044469 | 2600 | p/mtr | 115.62 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Feeder Exit Cables - 22kV | Subtransmission | Augmentation | SubtransmissionAugmentation | 0.05 |  | p/mtr | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Other | Subtransmission | Augmentation | SubtransmissionAugmentation | 0.66 | 4 | ea | 2.64 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 22kV Capacitor Bank (2x3 MVAr) - type 2 | Subtransmission | Augmentation | SubtransmissionAugmentation | 406.8 |  | ea | 0 | 0 |  |  |  |  | 0 | [7 empty] | 0
| ASC only | Subtransmission | Augmentation | SubtransmissionAugmentation | 430 | 0 | ea | 0 | 0 |  |  |  |  | 0
[15 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
SCADA / Protection & Control/ Comms | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Neutral Bus controller - 1 GFN | SCADA/Network control | Augmentation | SCADA/Network controlAugmentation | 48.9823 |  | ea | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Protection – GFN panels | SCADA/Network control | Augmentation | SCADA/Network controlAugmentation | 6.2431 |  | ea | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| GFN interface relay | SCADA/Network control | Augmentation | SCADA/Network controlAugmentation | 8.6956 |  | ea | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Power Quality/Switchgear Interface | SCADA/Network control | Augmentation | SCADA/Network controlAugmentation | 98.0077 |  | ea | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 22kV Protection & Control Modifications | SCADA/Network control | Augmentation | SCADA/Network controlAugmentation | 4 | 1 | ea | 4 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Other protection works | SCADA/Network control | Augmentation | SCADA/Network controlAugmentation | 20 | 1 | ea | 20 | 0 | [12 empty] | 0
Other AC & DC supplies |  | Subtransmission | Augmentation | SubtransmissionAugmentation | 54.7113 |  | ea | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
Infrastructure - Services |  | Subtransmission | Augmentation | SubtransmissionAugmentation | 3.483 | 1 | ea | 3.483 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Civil works | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Earthworks | Subtransmission | Augmentation | SubtransmissionAugmentation | 0 | 1 | ea | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Buildings | Subtransmission | Augmentation | SubtransmissionAugmentation | 0 | 1 | ea | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 22kV switchyard - install new puraceptor | Subtransmission | Augmentation | SubtransmissionAugmentation | 131.3953 |  | ea | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| - Other | Subtransmission | Augmentation | SubtransmissionAugmentation | 0 |  | ea | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Construction delivery & site control |  | Subtransmission | Augmentation | SubtransmissionAugmentation | 0 | 1 | ea | 0 | 0
Land purchase |  | Land | Non-Network | LandNon-Network | 0 |  | ea | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Subtotal Substation works | [7 empty] | 1456.1939 | 283.3855 | 300 | 1511.9676 | 41.7222 | 3593.2692
Check
Feeder works |  |  |  |  | Material $/Unit | QTY | UOM | Materials | Int Labour | Contracts - Design | Contracts - Construct | Other | P50 Total
Network Balancing | [31 empty] | Total hrs p/unit
| Design Labour - internal / external | Distribution system assets | Augmentation | Distribution system assetsAugmentation | 0 | 0 | feeders |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27.2% | 72.8% | 0% | 0% | 0% | 0% | 0% | 100% | TRUE | 54.4153
| Third conductor installation | Distribution system assets | Augmentation | Distribution system assetsAugmentation |  | 0 | spans | [6 empty] | 0 | [8 empty] | 0% | 14.07% | 24.32% | 0% | 17.6% | 44% | 0% | 100% | TRUE
| Unbonding cable | Distribution system assets | Augmentation | Distribution system assetsAugmentation |  | 0 | location | [6 empty] | 0 | [8 empty] | 0% | 11.32% | 25.1% | 0% | 18.17% | 45.41% | 0% | 100% | TRUE
| Phase rotation | Distribution system assets | Augmentation | Distribution system assetsAugmentation |  | 0 | rotations | [6 empty] | 0 | [8 empty] | 0% | 17.74% | 23.28% | 0% | 16.85% | 42.13% | 0% | 100% | TRUE
| Balancing capacitors | Distribution system assets | Augmentation | Distribution system assetsAugmentation | 18.1336 | 0 | installations | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 6.924% | 26.35% | 0% | 19.07% | 47.66% | 0% | 100% | TRUE | 20.2193
| Inherent works - various feeder based works | Distribution system assets | Augmentation | Distribution system assetsAugmentation | 0 | 0 | feeders | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 100% | TRUE | 46.3981
| Phase plate correction | Distribution system assets | Replacement | Distribution system assetsReplacement | 0 | 0 | feeders & RC sections | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 | [9 empty] | 0
| Fuse removal and install solid link | Distribution system assets | Replacement | Distribution system assetsReplacement | 0 | 0 | fuses | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 100% | TRUE | 1.2069
| Install fusesaver and control box - per site | Distribution system assets | Augmentation | Distribution system assetsAugmentation | 12.4291 | 0 | sites | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 100% | TRUE | 23.0218
| Install new ACR for switching | Distribution system assets | Augmentation | Distribution system assetsAugmentation | 22.6039 | 0 | ACRs | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30.31% | 32.45% | 37.24% | 0% | 0% | 0% | 0% | 100% | TRUE | 42.966
| Subtotal Network Balancing | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0
Line Hardening
| Surge arrestor replacement | Distribution system assets | Replacement | Distribution system assetsReplacement | 0.3785 | 0 | ea | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.573% | 0% | 32.12% | 0% | 0% | 0% | 65.31% | 100% | TRUE | 1.08
| Cable On-Line Testing | Distribution system assets | Replacement | Distribution system assetsReplacement | 0 | 0 | ea | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 100% |  |  | 100% | TRUE | 1.8482
| Cable Off-Line Testing | Distribution system assets | Replacement | Distribution system assetsReplacement | 0 | 0 | ea | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 100% |  |  | 100% | TRUE | 61.6082
| Cable - Replace Fitting | Distribution system assets | Replacement | Distribution system assetsReplacement | 5.2026 | 0 | ea | 0 | 0 |  | 0 |  | 0 | 0 | [7 empty] | 0
| Cable - Replace Cable Section - per m | Distribution system assets | Replacement | Distribution system assetsReplacement | 0.05 | 0 | m | 0 | 0 |  | 0 |  | 0 | 0 | [7 empty] | 0
Compatible Equipment
| ACR upgrade | Distribution system assets | Replacement | Distribution system assetsReplacement | 15 | 0 | ea | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30.31% | 32.45% | 37.24% | 0% | 0% | 0% | 0% | 100% | TRUE | 14.42
| ACR replacement | Distribution system assets | Replacement | Distribution system assetsReplacement | 22.6039 | 0 | ea | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30.31% | 32.45% | 37.24% | 0% | 0% | 0% | 0% | 100% | TRUE | 42.966
| Voltage regulator upgrade | Distribution system assets | Replacement | Distribution system assetsReplacement | 15.156 | 0 | ea | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11.82% | 49.78% | 38.4% | 0% | 0% | 0% | 0% | 100% | TRUE | 144.7042
| Voltage regulator replacement | Distribution system assets | Replacement | Distribution system assetsReplacement | 193.2305 | 0 | ea | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 69.94% | 4.845% | 25.21% | 0% | 0% | 0% | 0% | 100% | TRUE | 220.4113
Distribution Code
| HV customers isolation substation (3.0 MVA) | Distribution system assets | Augmentation | Distribution system assetsAugmentation | 0 | 0 | ea | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18.11% | 21.48% | 60.41% | 0% | 0% | 0% | 0% | 100% | TRUE | 469.7767
| HV customers isolation substation (5.0 MVA) | Distribution system assets | Augmentation | Distribution system assetsAugmentation | 0 | 0 | ea | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18.11% | 42.96% | 38.93% | 0% | 0% | 0% | 0% | 100% | TRUE | 500.1505
| HV customers isolation substation (7.5 MVA) | Distribution system assets | Augmentation | Distribution system assetsAugmentation | 0 | 0 | ea | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18.11% | 42.96% | 38.93% | 0% | 0% | 0% | 0% | 100% | TRUE | 416.1112
| Line Hardening | Distribution system assets | Replacement | Distribution system assetsReplacement | 32.7402 | 0 | ea | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30.31% | 32.45% | 37.24% | 0% | 0% | 0% | 0% | 100% | TRUE | 61.06
Subtotal feeder works | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0
Check
Grand Total | [7 empty] | 1456.1939 | 283.3855 | 300 | 1511.9676 | 41.7222 | 3593.2692
Check
| Zone Substation works | Subtransmission | Augmentation | SubtransmissionAugmentation |  |  |  | 273.8939 | 0 | 0 | 1370.5276 | 40.364 | 1684.7855
|  | Subtransmission | Replacement | SubtransmissionReplacement |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
|  | SCADA/Network control | Augmentation | SCADA/Network controlAugmentation |  |  |  | 1182.3 | 0 | 0 | 141.44 | 1.3582 | 1325.0982
|  | SCADA/Network control | Replacement | SCADA/Network controlReplacement |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Land | Non-Network | LandNon-Network |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
[8 empty] | 1456.1939 | 0 | 0 | 1511.9676 | 41.7222 | 3009.8837
| Design, Project Management & Engineering costs allocation | Subtransmission | Augmentation | SubtransmissionAugmentation |  |  |  |  | 158.6253 | 167.9253 | 0 |  | 326.5506
|  | Subtransmission | Replacement | SubtransmissionReplacement |  |  |  |  | 0 | 0 | 0 |  | 0
|  | SCADA/Network control | Augmentation | SCADA/Network controlAugmentation |  |  |  |  | 124.7602 | 132.0747 | 0 |  | 256.8349
|  | SCADA/Network control | Replacement | SCADA/Network controlReplacement |  |  |  |  | 0 | 0 | 0 |  | 0
|  | Land | Non-Network | LandNon-Network |  |  |  |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 283.3855 | 300 | 0 | 0 | 583.3855
| Total Substation works | Subtransmission | Augmentation | SubtransmissionAugmentation |  |  |  | 273.8939 | 158.6253 | 167.9253 | 1370.5276 | 40.364 | 2011.3361
|  | Subtransmission | Replacement | SubtransmissionReplacement |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
|  | SCADA/Network control | Augmentation | SCADA/Network controlAugmentation |  |  |  | 1182.3 | 124.7602 | 132.0747 | 141.44 | 1.3582 | 1581.933
|  | SCADA/Network control | Replacement | SCADA/Network controlReplacement |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Land | Non-Network | LandNon-Network |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
[8 empty] | 1456.1939 | 283.3855 | 300 | 1511.9676 | 41.7222 | 3593.2692
[8 empty] | 0 | 0 | 0 | 0 | 0 | 0
| Network Balancing | Distribution system assets | Augmentation | Distribution system assetsAugmentation |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Distribution system assets | Replacement | Distribution system assetsReplacement |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
[8 empty] | 0 | 0 | 0 | 0 | 0 | 0
[8 empty] | 0 | 0 | 0 | 0 | 0 | 0
Note on G41: AST: Average unit rate across all cable types, excluding feeder exit cable

## WGI_Det
Confidential
WGI Volumes & Unit Rates
WGI |  |  |  |  | Materials |  |  | Total Direct ($k, $2019) | [6 empty] | Total Internal Labour (hours)
|  | Asset Class | Expenditure Class |  | $/Unit ($2019) | QTY | UOM | Materials | Int Labour | Contracts - Design | Contracts - Construct | Other | P50 Total | Chk | Project Engineer | Asset Management Engineer | Project Manager | Front Line Leader | Project Engineer Build | Site Manager Build | Operational Staff | Total Hours
Labour rates | [14 empty] | 162.4874 | 151.7974 | 176.3843 | 229.8341 | 162.4874 | 162.4874 | 133.6245
Design - Internal/External |  | Allocation | Allocation | [5 empty] | 0 | 1000 |  |  | 1000
Project Management & Engineering
| Project Establishment | Allocation | Allocation | [5 empty] | 67.2997 |  | 0 |  | 67.2997 |  | 228 | 150 | 32 | 8 |  |  |  | 418
| Project Management | Allocation | Allocation | [5 empty] | 831.0952 |  | 0 |  | 831.0952 |  | 108 |  | 2120 |  | 1254 | 1440 | 14 | 4936
| Project Close-out, Testing & Commissioning | Allocation | Allocation | [5 empty] | 27.7768 |  | 0 |  | 27.7768 |  | 32 |  | 128 |  |  |  |  | 160
| Community Engagement | Allocation | Allocation | [7 empty] | 0 |  | 0 | [8 empty] | 0
Zone Substation works
Primary Plant
| Station service transformer (500 kVA) | Subtransmission | Augmentation | SubtransmissionAugmentation | 72.619 |  | ea | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Station service transformer (750 kVA) | Subtransmission | Augmentation | SubtransmissionAugmentation | 112.828 | 2 | ea | 225.656 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Capacitance reducing isolation substation (10 MVA) | Subtransmission | Augmentation | SubtransmissionAugmentation | 465.0023 |  | ea | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Power transformer - 66/22kV 20/33MVA | Subtransmission | Augmentation | SubtransmissionAugmentation | 1126.5675 | 1 | ea | 1126.5675 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| AC changeover board - Station | Subtransmission | Augmentation | SubtransmissionAugmentation | 39.295 |  | ea | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| AC changeover board - REFCL | Subtransmission | Augmentation | SubtransmissionAugmentation | 42.975 |  | ea | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| AC C/O board footing | Subtransmission | Augmentation | SubtransmissionAugmentation | 0 |  | ea | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Arc Suppression Coil | SCADA/Network control | Augmentation | SCADA/Network controlAugmentation | 1158.3 | 1 | ea | 1158.3 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| ASC footing | Subtransmission | Augmentation | SubtransmissionAugmentation | 0 | 1 | ea | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 22kV switchboard - Metro | Subtransmission | Augmentation | SubtransmissionAugmentation | 1354 |  | ea | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 22kV switchboard - Rural | Subtransmission | Augmentation | SubtransmissionAugmentation | 1461.1163 |  | ea | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 22kV switchboard (no building) - Rural | Subtransmission | Augmentation | SubtransmissionAugmentation | 700 |  | ea | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 22kV Capacitor Bank - Modify | Subtransmission | Augmentation | SubtransmissionAugmentation | 91.2924 |  | ea | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Cap Bank footing | Subtransmission | Augmentation | SubtransmissionAugmentation | 0 |  | ea | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 22kV Dead Tank Circuit Breaker | Subtransmission | Augmentation | SubtransmissionAugmentation | 107.006 |  | ea | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 22kV U/S Isolator | Subtransmission | Augmentation | SubtransmissionAugmentation | 7.664 |  | ea | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 22kV Current Transformer | Subtransmission | Augmentation | SubtransmissionAugmentation | 27.163 | 4 | ea | 108.652 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 22kV Zero Sequence CTs | Subtransmission | Augmentation | SubtransmissionAugmentation | 0 |  | ea | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 22kV Voltage Transformer | Subtransmission | Augmentation | SubtransmissionAugmentation | 0 |  | ea | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 22KV Surge Arrestor | Subtransmission | Augmentation | SubtransmissionAugmentation | 0.62 |  | ea | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Primary Cable Testing | Subtransmission | Augmentation | SubtransmissionAugmentation | 0 | 1 | ea | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Neutral Bus | Subtransmission | Augmentation | SubtransmissionAugmentation | 93.854 | 1 | ea | 93.854 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Transformer Neutral Isolator | Subtransmission | Augmentation | SubtransmissionAugmentation | 26.2223 | 1 | ea | 26.2223 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Type 3 REFCL control room | Subtransmission | Augmentation | SubtransmissionAugmentation | 109.1759 | 1 | ea | 109.1759 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Battery Room (2 battery sets) | Subtransmission | Augmentation | SubtransmissionAugmentation | 174.5855 |  | ea | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| New Control Building | Subtransmission | Augmentation | SubtransmissionAugmentation | 369.039 |  | ea | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Primary Cables - 22kV | Subtransmission | Augmentation | SubtransmissionAugmentation | 0.14106 | 1120 | p/mtr | 157.9824 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Feeder Exit Cables - 22kV | Subtransmission | Augmentation | SubtransmissionAugmentation | 0.05 |  | p/mtr | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Other | Subtransmission | Augmentation | SubtransmissionAugmentation | 4.5718 | 7 | ea | 32.0023 | 0
| 22kV Capacitor Bank (2x3 MVAr) - type 2 | Subtransmission | Augmentation | SubtransmissionAugmentation | 406.8 |  | ea | 0 | 0 |  |  |  |  | 0
| One Tilt Slab control room | Subtransmission | Augmentation | SubtransmissionAugmentation | 0 |  | ea | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[15 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SCADA / Protection & Control/ Comms | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Neutral Bus controller - 1 GFN | SCADA/Network control | Augmentation | SCADA/Network controlAugmentation | 48.9823 |  | ea | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Neutral Bus controller - 2 GFNs | SCADA/Network control | Augmentation | SCADA/Network controlAugmentation | 61.8191 | 1 | ea | 61.8191 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Protection – GFN panels | SCADA/Network control | Augmentation | SCADA/Network controlAugmentation | 6.2431 | 1 | ea | 6.2431 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| GFN interface relay | SCADA/Network control | Augmentation | SCADA/Network controlAugmentation | 8.6956 |  | ea | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Power Quality/Switchgear Interface | SCADA/Network control | Augmentation | SCADA/Network controlAugmentation | 98.0077 |  | ea | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 22kV Protection & Control Modifications | SCADA/Network control | Augmentation | SCADA/Network controlAugmentation | 6.1429 | 7 | ea | 43 | 0
| Other protection works | SCADA/Network control | Augmentation | SCADA/Network controlAugmentation | 22.5 | 2 | ea | 45 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Other AC & DC supplies |  | Subtransmission | Augmentation | SubtransmissionAugmentation | 7.5192 | 6 | ea | 45.115 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Infrastructure - Services |  | Subtransmission | Augmentation | SubtransmissionAugmentation | 0 |  | ea | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Civil works | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Earthworks | Subtransmission | Augmentation | SubtransmissionAugmentation | 1.0538 | 7 | ea | 7.3764 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Buildings | Subtransmission | Augmentation | SubtransmissionAugmentation | 0 |  | ea | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 22kV switchyard - install new puraceptor | Subtransmission | Augmentation | SubtransmissionAugmentation | 131.3953 |  | ea | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| - Other | Subtransmission | Augmentation | SubtransmissionAugmentation | 0 |  | ea | 0 | 0
Construction delivery & site control |  | Subtransmission | Augmentation | SubtransmissionAugmentation | 0 |  | ea | 0 | 0
Land purchase |  | Land | Non-Network | LandNon-Network | 0 |  | ea | 0 | 0
Subtotal Substation works | [7 empty] | 3246.966 | 926.1717 | 1000 | 3449.2164 | 132.4125 | 8754.7665
Check
Feeder works |  |  |  |  | Material $/Unit | QTY | UOM | Materials | Int Labour | Contracts - Design | Contracts - Construct | Other | P50 Total
Isolation Transformers
Install five isolation transformers
| Concrete Poles 15.5m Replacement (includes installation), per pole | Distribution system assets | Replacement | Distribution system assetsReplacement | 6.06 | 5 | ea | 30.3 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Capacitance reducing isolation substation (300 kVA) | Subtransmission | Augmentation | SubtransmissionAugmentation | 18.9974 | 5 | ea | 94.9869 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Install new ACR for switching | Distribution system assets | Augmentation | Distribution system assetsAugmentation | 22.6039 | 5 | ea | 113.0196 | 101.7541 | 23.929 |  |  |  | -401.8441 | 189.8405 | 217.5201 | 214.8062 | 0 | 0 | 0 | 0 | 622.1668 | 30.31% | 32.45% | 37.24%
| Subtotal Install five isolation transformers | [6 empty] | 238.3065 | 101.7541 | 23.929 | 247.342 | 43.032 | 654.3636
Subtotal feeder works | [7 empty] | 238.3065 | 101.7541 | 23.929 | 247.342 | 43.032 | 654.3636
Check
Grand Total | [7 empty] | 3485.2725 | 1027.9258 | 1023.929 | 3696.5583 | 175.4445 | 9409.1302
Check
| Zone Substation works | Subtransmission | Augmentation | SubtransmissionAugmentation |  |  |  | 1932.6038 | 0 | 0 | 3306.3022 | 130.4789 | 5369.3849
|  | Subtransmission | Replacement | SubtransmissionReplacement |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
|  | SCADA/Network control | Augmentation | SCADA/Network controlAugmentation |  |  |  | 1314.3622 | 0 | 0 | 142.9142 | 1.9336 | 1459.2099
|  | SCADA/Network control | Replacement | SCADA/Network controlReplacement |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Land | Non-Network | LandNon-Network |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
[8 empty] | 3246.966 | 0 | 0 | 3449.2164 | 132.4125 | 6828.5948
| Design, Project Management & Engineering costs allocation | Subtransmission | Augmentation | SubtransmissionAugmentation |  |  |  |  | 728.2571 | 786.3089 | 0 |  | 1514.566
|  | Subtransmission | Replacement | SubtransmissionReplacement |  |  |  |  | 0 | 0 | 0 |  | 0
|  | SCADA/Network control | Augmentation | SCADA/Network controlAugmentation |  |  |  |  | 197.9147 | 213.6911 | 0 |  | 411.6057
|  | SCADA/Network control | Replacement | SCADA/Network controlReplacement |  |  |  |  | 0 | 0 | 0 |  | 0
|  | Land | Non-Network | LandNon-Network |  |  |  |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 926.1717 | 1000 | 0 | 0 | 1926.1717
| Total Substation works | Subtransmission | Augmentation | SubtransmissionAugmentation |  |  |  | 1932.6038 | 728.2571 | 786.3089 | 3306.3022 | 130.4789 | 6883.9509
|  | Subtransmission | Replacement | SubtransmissionReplacement |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
|  | SCADA/Network control | Augmentation | SCADA/Network controlAugmentation |  |  |  | 1314.3622 | 197.9147 | 213.6911 | 142.9142 | 1.9336 | 1870.8157
|  | SCADA/Network control | Replacement | SCADA/Network controlReplacement |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Land | Non-Network | LandNon-Network |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
[8 empty] | 3246.966 | 926.1717 | 1000 | 3449.2164 | 132.4125 | 8754.7665
[8 empty] | 0 | 0 | 0 | 0 | 0 | 0
| Install five isolation transformers | Subtransmission | Augmentation | SubtransmissionAugmentation |  |  |  | 94.9869 | 0 | 0 | 68.6367 | 8.4159 | 172.0395
|  | Distribution system assets | Augmentation | Distribution system assetsAugmentation |  |  |  | 113.0196 | 101.7541 | 23.929 | 129.9003 | 33.2411 | 401.8441
|  | Distribution system assets | Replacement | Distribution system assetsReplacement |  |  |  | 30.3 | 0 | 0 | 48.805 | 1.375 | 80.48
[8 empty] | 238.3065 | 101.7541 | 23.929 | 247.342 | 43.032 | 654.3636
[8 empty] | 0 | 0 | 0 | 0 | 0 | 0

## BGE_Det
Confidential
BGE Volumes & Unit Rates
BGE |  |  |  |  | Materials |  |  | Total Direct ($k, $2019) | [6 empty] | Total Internal Labour (hours)
|  | Asset Class | Expenditure Class |  | $/Unit ($2019) | QTY | UOM | Materials | Int Labour | Contracts - Design | Contracts - Construct | Other | P50 Total | Chk | Project Engineer | Asset Management Engineer | Project Manager | Front Line Leader | Project Engineer Build | Site Manager Build | Operational Staff | Total Hours
Labour rates | [14 empty] | 162.4874 | 151.7974 | 176.3843 | 229.8341 | 162.4874 | 162.4874 | 133.6245
Design - Internal/External |  | Allocation | Allocation | [5 empty] | 0 | 800 |  |  | 800
Project Management & Engineering
| Project Establishment | Allocation | Allocation | [5 empty] | 49.4004 |  | 0 |  | 49.4004 |  | 134 | 142 | 24 | 8 |  |  |  | 308
| Project Management | Allocation | Allocation | [5 empty] | 616.2708 |  | 0 |  | 616.2708 |  | 96 |  | 1296 | 312 | 952.5 | 864 | 39 | 3559.5
| Project Close-out, Testing & Commissioning | Allocation | Allocation | [5 empty] | 19.3103 |  | 0 |  | 19.3103 |  | 32 |  | 80 |  |  |  |  | 112
| Community Engagement | Allocation | Allocation | [7 empty] | 0 |  | 0 | [8 empty] | 0
Remote REFCL at BGE13 works
Primary Plant
| Station service transformer (500 kVA) | Subtransmission | Augmentation | SubtransmissionAugmentation | 72.619 |  | ea | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Station service transformer (750 kVA) | Subtransmission | Augmentation | SubtransmissionAugmentation | 112.828 |  | ea | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Station service transformer (200 kVA) | Subtransmission | Augmentation | SubtransmissionAugmentation | 47.7187 | 1 | ea | 47.7187 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Capacitance reducing isolation substation (10 MVA) | Subtransmission | Augmentation | SubtransmissionAugmentation | 465.0023 |  | ea | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Capacitance reducing isolation substation (12.5 MVA) | Subtransmission | Augmentation | SubtransmissionAugmentation | 1184.6455 | 1 | ea | 1184.6455 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| AC changeover board - Station | Subtransmission | Augmentation | SubtransmissionAugmentation | 39.295 |  | ea | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| AC changeover board - REFCL | Subtransmission | Augmentation | SubtransmissionAugmentation | 42.975 |  | ea | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| AC C/O board footing | Subtransmission | Augmentation | SubtransmissionAugmentation | 0 |  | ea | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Arc Suppression Coil | SCADA/Network control | Augmentation | SCADA/Network controlAugmentation | 1158.3 | 1 | ea | 1158.3 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| ASC footing | Subtransmission | Augmentation | SubtransmissionAugmentation | 0 | 1 | ea | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 22kV switchboard - Metro | Subtransmission | Augmentation | SubtransmissionAugmentation | 1354 |  | ea | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 22kV switchboard - Rural | Subtransmission | Augmentation | SubtransmissionAugmentation | 1461.1163 |  | ea | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 22kV switchboard (no building) - Rural | Subtransmission | Augmentation | SubtransmissionAugmentation | 700 |  | ea | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 22kV Capacitor Bank - Modify | Subtransmission | Augmentation | SubtransmissionAugmentation | 91.2924 |  | ea | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Cap Bank footing | Subtransmission | Augmentation | SubtransmissionAugmentation | 0 |  | ea | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 22kV Dead Tank Circuit Breaker | Subtransmission | Augmentation | SubtransmissionAugmentation | 107.006 |  | ea | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 22kV U/S Isolator | Subtransmission | Augmentation | SubtransmissionAugmentation | 7.664 | 2 | ea | 15.328 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 22kV Current Transformer | Subtransmission | Augmentation | SubtransmissionAugmentation | 27.163 | 1 | ea | 27.163 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 22kV Zero Sequence CTs | Subtransmission | Augmentation | SubtransmissionAugmentation | 0 |  | ea | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 22kV Voltage Transformer | Subtransmission | Augmentation | SubtransmissionAugmentation | 0 | 1 | ea | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 22KV Surge Arrestor | Subtransmission | Augmentation | SubtransmissionAugmentation | 0.62 | 1 | ea | 0.62 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Primary Cable Testing | Subtransmission | Augmentation | SubtransmissionAugmentation | 0 | 1 | ea | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Neutral Bus | Subtransmission | Augmentation | SubtransmissionAugmentation | 93.854 |  | ea | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Type 3 REFCL control room | Subtransmission | Augmentation | SubtransmissionAugmentation | 109.1759 | 1 | ea | 109.1759 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Battery Room (2 battery sets) | Subtransmission | Augmentation | SubtransmissionAugmentation | 174.5855 |  | ea | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| New Control Building | Subtransmission | Augmentation | SubtransmissionAugmentation | 369.039 |  | ea | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Primary Cables - 22kV | Subtransmission | Augmentation | SubtransmissionAugmentation | 0.052373 | 50 | p/mtr | 2.6187 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Feeder Exit Cables - 22kV | Subtransmission | Augmentation | SubtransmissionAugmentation | 0.05 |  | p/mtr | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Other | Subtransmission | Augmentation | SubtransmissionAugmentation | 0 |  | ea | 0 | 0
| 22kV Capacitor Bank (2x3 MVAr) - type 2 | Subtransmission | Augmentation | SubtransmissionAugmentation | 406.8 |  | ea | 0 | 0 |  |  |  |  | 0
| One Tilt Slab control room | Subtransmission | Augmentation | SubtransmissionAugmentation | 0 |  | ea | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[15 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SCADA / Protection & Control/ Comms | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Neutral Bus controller - 1 GFN | SCADA/Network control | Augmentation | SCADA/Network controlAugmentation | 48.9823 |  | ea | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Protection – GFN panels | SCADA/Network control | Augmentation | SCADA/Network controlAugmentation | 6.2431 |  | ea | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 22kV Line Protection Panel | SCADA/Network control | Augmentation | SCADA/Network controlAugmentation | 63.4714 | 1 | ea | 63.4714 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 66/22kV Transformer Protection Panel | SCADA/Network control | Augmentation | SCADA/Network controlAugmentation | 47.4106 | 1 | ea | 47.4106 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| GFN interface relay | SCADA/Network control | Augmentation | SCADA/Network controlAugmentation | 8.6956 |  | ea | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Power Quality/Switchgear Interface | SCADA/Network control | Augmentation | SCADA/Network controlAugmentation | 98.0077 |  | ea | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 22kV Protection & Control Modifications | SCADA/Network control | Augmentation | SCADA/Network controlAugmentation | 0 |  | ea | 0 | 0 | [12 empty] | 0
| SCIMS system - small | SCADA/Network control | Augmentation | SCADA/Network controlAugmentation | 92.2396 | 1 | ea | 92.2396 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Other protection works | SCADA/Network control | Augmentation | SCADA/Network controlAugmentation | 0 |  | ea | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
Other AC & DC supplies |  | Subtransmission | Augmentation | SubtransmissionAugmentation | 22.8982 | 4 | ea | 91.5929 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Infrastructure - Services |  | Subtransmission | Augmentation | SubtransmissionAugmentation | 15 | 3 | ea | 45 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Civil works | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Earthworks | Subtransmission | Augmentation | SubtransmissionAugmentation | 0 |  | ea | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Buildings | Subtransmission | Augmentation | SubtransmissionAugmentation | 0 |  | ea | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 22kV switchyard - install new puraceptor | Subtransmission | Augmentation | SubtransmissionAugmentation | 131.3953 |  | ea | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| - Other | Subtransmission | Augmentation | SubtransmissionAugmentation | 0 |  | ea | 0 | 0
Construction delivery & site control |  | Subtransmission | Augmentation | SubtransmissionAugmentation | 0 |  | ea | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Land purchase |  | Land | Non-Network | LandNon-Network | 0 |  | ea | 0 | 0
Subtotal Remote REFCL works | [7 empty] | 2885.2843 | 684.9816 | 800 | 2543.4809 | 94.2079 | 7007.9547
Check
Feeder works |  |  |  |  | Material $/Unit | QTY | UOM | Materials | Int Labour | Contracts - Design | Contracts - Construct | Other | P50 Total
Remote REFCLs
Lines works at BGE13
| 22kV Underground Cable 300mm2 XLPE | Distribution system assets | Augmentation | Distribution system assetsAugmentation | 0.064197 | 200 | p/mtr | 12.8395 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Install new ACR for switching | Distribution system assets | Augmentation | Distribution system assetsAugmentation | 22.6039 | 1 | ea | 22.6039 | 20.3508 | 4.7858 |  |  |  | -80.3688 | 37.9681 | 43.504 | 42.9612 | 0 | 0 | 0 | 0 | 124.4334 | 30.31% | 32.45% | 37.24%
| Concrete Poles 15.5m (includes installation), per pole | Distribution system assets | Augmentation | Distribution system assetsAugmentation | 6.06 | 2 | ea | 12.12 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 22KV cable terminations | Distribution system assets | Augmentation | Distribution system assetsAugmentation | 3.1912 | 2 | ea | 6.3823 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Subtotal Lines works at BGE13 | [6 empty] | 53.9457 | 20.3508 | 4.7858 | 176.5429 | 7.2533 | 262.8786
Isolation Transformers
Install four isolation transformers
| Concrete Poles 15.5m Replacement (includes installation), per pole | Distribution system assets | Replacement | Distribution system assetsReplacement | 6.06 | 4 | ea | 24.24 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Concrete Poles 15.5m (includes installation), per pole | Distribution system assets | Augmentation | Distribution system assetsAugmentation | 6.06 | 1 | ea | 6.06 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Capacitance reducing isolation substation (300 kVA) | Subtransmission | Augmentation | SubtransmissionAugmentation | 18.9974 | 3 | ea | 56.9922 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Capacitance reducing isolation substation (1 MVA) | Subtransmission | Augmentation | SubtransmissionAugmentation | 80.0253 | 1 | ea | 80.0253 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Install new ACR for switching | Distribution system assets | Augmentation | Distribution system assetsAugmentation | 22.6039 | 4 | ea | 90.4157 | 81.4033 | 19.1432 |  |  |  | -321.4753 | 151.8724 | 174.0161 | 171.845 | 0 | 0 | 0 | 0 | 497.7335 | 30.31% | 32.45% | 37.24%
| Decommission and remove existing conductor (route length) at various locations - includes AAC, ASCR, Steel | Distribution system assets | Replacement | Distribution system assetsReplacement | 0 | 1.835 | p/km | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 22kV Underground Cable 185mm2 XLPE | Distribution system assets | Augmentation | Distribution system assetsAugmentation | 0.043775 | 2000 | p/mtr | 87.5492 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 22KV cable terminations | Distribution system assets | Augmentation | Distribution system assetsAugmentation | 3.1912 | 49 | ea | 156.3672 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Subtotal Install four isolation transformers | [6 empty] | 501.6495 | 81.4033 | 19.1432 | 1853.2142 | 36.0511 | 2491.4612
Subtotal feeder works | [7 empty] | 555.5952 | 101.7541 | 23.929 | 2029.7571 | 43.3044 | 2754.3399
Check
Grand Total | [7 empty] | 3440.8795 | 786.7358 | 823.929 | 4573.238 | 137.5123 | 9762.2946
Check
| Remote REFCL works | Subtransmission | Augmentation | SubtransmissionAugmentation |  |  |  | 1523.8627 | 0 | 0 | 2099.4445 | 86.1836 | 3709.4907
|  | Subtransmission | Replacement | SubtransmissionReplacement |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
|  | SCADA/Network control | Augmentation | SCADA/Network controlAugmentation |  |  |  | 1361.4216 | 0 | 0 | 277.8865 | 8.0243 | 1647.3324
|  | SCADA/Network control | Replacement | SCADA/Network controlReplacement |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Land | Non-Network | LandNon-Network |  |  |  | 0 | 0 | 0 | 166.15 | 0 | 166.15
[8 empty] | 2885.2843 | 0 | 0 | 2543.4809 | 94.2079 | 5522.9731
| Design, Project Management & Engineering costs allocation | Subtransmission | Augmentation | SubtransmissionAugmentation |  |  |  |  | 460.0662 | 537.3179 | 0 |  | 997.3841
|  | Subtransmission | Replacement | SubtransmissionReplacement |  |  |  |  | 0 | 0 | 0 |  | 0
|  | SCADA/Network control | Augmentation | SCADA/Network controlAugmentation |  |  |  |  | 204.3089 | 238.6153 | 0 |  | 442.9242
|  | SCADA/Network control | Replacement | SCADA/Network controlReplacement |  |  |  |  | 0 | 0 | 0 |  | 0
|  | Land | Non-Network | LandNon-Network |  |  |  |  | 20.6066 | 24.0667 | 0 |  | 44.6733
[8 empty] | 0 | 684.9816 | 800 | 0 | 0 | 1484.9816
| Total Remote REFCL works | Subtransmission | Augmentation | SubtransmissionAugmentation |  |  |  | 1523.8627 | 460.0662 | 537.3179 | 2099.4445 | 86.1836 | 4706.8748
|  | Subtransmission | Replacement | SubtransmissionReplacement |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
|  | SCADA/Network control | Augmentation | SCADA/Network controlAugmentation |  |  |  | 1361.4216 | 204.3089 | 238.6153 | 277.8865 | 8.0243 | 2090.2566
|  | SCADA/Network control | Replacement | SCADA/Network controlReplacement |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Land | Non-Network | LandNon-Network |  |  |  | 0 | 20.6066 | 24.0667 | 166.15 | 0 | 210.8233
[8 empty] | 2885.2843 | 684.9816 | 800 | 2543.4809 | 94.2079 | 7007.9547
[8 empty] | 0 | 0 | 0 | 0 | 0 | 0
| Lines works at BGE13 | Distribution system assets | Augmentation | Distribution system assetsAugmentation |  |  |  | 53.9457 | 20.3508 | 4.7858 | 176.5429 | 7.2533 | 262.8786
|  | Distribution system assets | Replacement | Distribution system assetsReplacement |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
[8 empty] | 53.9457 | 20.3508 | 4.7858 | 176.5429 | 7.2533 | 262.8786
[8 empty] | 0 | 0 | 0 | 0 | 0 | 0
| Install four isolation transformers | Subtransmission | Augmentation | SubtransmissionAugmentation |  |  |  | 137.0174 | 0 | 0 | 54.933 | 6.7328 | 198.6831
|  | Subtransmission | Replacement | SubtransmissionReplacement |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Distribution system assets | Augmentation | Distribution system assetsAugmentation |  |  |  | 340.392 | 81.4033 | 19.1432 | 1686.9881 | 28.2183 | 2156.145
|  | Distribution system assets | Replacement | Distribution system assetsReplacement |  |  |  | 24.24 | 0 | 0 | 111.2931 | 1.1 | 136.6331
[8 empty] | 501.6495 | 81.4033 | 19.1432 | 1853.2142 | 36.0511 | 2491.4612
[8 empty] | 0 | 0 | 0 | 0 | 0 | 0

## LDL_Det
Confidential
LDL Volumes & Unit Rates
LDL |  |  |  |  | Materials |  |  | Total Direct ($k, $2019) | [6 empty] | Total Internal Labour (hours)
|  | Asset Class | Expenditure Class |  | $/Unit ($2019) | QTY | UOM | Materials | Int Labour | Contracts - Design | Contracts - Construct | Other | P50 Total | Chk | Project Engineer | Asset Management Engineer | Project Manager | Front Line Leader | Project Engineer Build | Site Manager Build | Operational Staff | Total Hours
Labour rates | [14 empty] | 162.4874 | 151.7974 | 176.3843 | 229.8341 | 162.4874 | 162.4874 | 133.6245
Design - Internal/External |  | Allocation | Allocation | [5 empty] | 0 | 450 |  |  | 450
Project Management & Engineering
| Project Establishment | Allocation | Allocation | [5 empty] | 78.6973 |  | 0 |  | 78.6973 |  | 398 | 31 | 32 | 16 |  |  |  | 477
| Project Management | Allocation | Allocation | [5 empty] | 301.6985 |  | 0 |  | 301.6985 |  | 96 |  | 472 | 128 | 261.5 | 768 | 46 | 1771.5
| Project Close-out, Testing & Commissioning | Allocation | Allocation | [5 empty] | 14.1107 |  | 0 |  | 14.1107 |  |  |  | 80 |  |  |  |  | 80
| Community Engagement | Allocation | Allocation | [7 empty] | 0 |  | 0 | [8 empty] | 0
Isolation Substation at LDL11 works
Primary Plant
| Station service transformer (500 kVA) | Subtransmission | Augmentation | SubtransmissionAugmentation | 72.619 |  | ea | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Station service transformer (750 kVA) | Subtransmission | Augmentation | SubtransmissionAugmentation | 112.828 |  | ea | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Capacitance reducing isolation substation (5 / 7.5 MVA) | Subtransmission | Augmentation | SubtransmissionAugmentation | 907.5436 | 1 | ea | 907.5436 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Capacitance reducing isolation substation (10 MVA) | Subtransmission | Augmentation | SubtransmissionAugmentation | 465.0023 |  | ea | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| New ACR unit and control box | Subtransmission | Augmentation | SubtransmissionAugmentation | 37.6039 | 2 | ea | 75.2078 | 19.998 | 19.1716 |  |  |  | -245.3562 | 37.3098 | 42.7497 | 42.2163 | 0 | 0 | 0 | 0 | 122.2757 | 30.31% | 32.45% | 37.24%
| AC changeover board - Station | Subtransmission | Augmentation | SubtransmissionAugmentation | 39.295 |  | ea | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| AC changeover board - REFCL | Subtransmission | Augmentation | SubtransmissionAugmentation | 42.975 |  | ea | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| AC C/O board footing | Subtransmission | Augmentation | SubtransmissionAugmentation | 0 |  | ea | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Arc Suppression Coil | SCADA/Network control | Augmentation | SCADA/Network controlAugmentation | 1158.3 |  | ea | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| ASC footing | Subtransmission | Augmentation | SubtransmissionAugmentation | 0 |  | ea | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 22kV switchboard - Metro | Subtransmission | Augmentation | SubtransmissionAugmentation | 1354 |  | ea | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 22kV switchboard - Rural | Subtransmission | Augmentation | SubtransmissionAugmentation | 1461.1163 |  | ea | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 22kV switchboard (no building) - Rural | Subtransmission | Augmentation | SubtransmissionAugmentation | 700 |  | ea | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 22kV Capacitor Bank - Modify | Subtransmission | Augmentation | SubtransmissionAugmentation | 91.2924 |  | ea | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Cap Bank footing | Subtransmission | Augmentation | SubtransmissionAugmentation | 0 |  | ea | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 22kV Dead Tank Circuit Breaker | Subtransmission | Augmentation | SubtransmissionAugmentation | 107.006 |  | ea | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 22kV U/S Isolator | Subtransmission | Augmentation | SubtransmissionAugmentation | 7.664 |  | ea | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 22kV Current Transformer | Subtransmission | Augmentation | SubtransmissionAugmentation | 27.163 |  | ea | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 22kV Zero Sequence CTs | Subtransmission | Augmentation | SubtransmissionAugmentation | 0 |  | ea | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 22kV Voltage Transformer | Subtransmission | Augmentation | SubtransmissionAugmentation | 0 |  | ea | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 22KV Surge Arrestor | Subtransmission | Augmentation | SubtransmissionAugmentation | 0.62 |  | ea | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Primary Cable Testing | Subtransmission | Augmentation | SubtransmissionAugmentation | 0 | 1 | ea | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Neutral Bus | Subtransmission | Augmentation | SubtransmissionAugmentation | 93.854 |  | ea | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| REFCL control room | Subtransmission | Augmentation | SubtransmissionAugmentation | 0 |  | ea | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Battery Room (2 battery sets) | Subtransmission | Augmentation | SubtransmissionAugmentation | 174.5855 |  | ea | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| New Control Building | Subtransmission | Augmentation | SubtransmissionAugmentation | 369.039 |  | ea | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Primary Cables - 22kV | Subtransmission | Augmentation | SubtransmissionAugmentation | 0.050552 | 120 | p/mtr | 6.0663 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Feeder Exit Cables - 22kV | Subtransmission | Augmentation | SubtransmissionAugmentation | 0.05 |  | p/mtr | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Other | Subtransmission | Augmentation | SubtransmissionAugmentation | 0 |  | ea | 0 | 0
| 22kV Capacitor Bank (2x3 MVAr) - type 2 | Subtransmission | Augmentation | SubtransmissionAugmentation | 406.8 |  | ea | 0 | 0 |  |  |  |  | 0
| One Tilt Slab control room | Subtransmission | Augmentation | SubtransmissionAugmentation | 0 |  | ea | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[15 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SCADA / Protection & Control/ Comms | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Neutral Bus controller - 1 GFN | SCADA/Network control | Augmentation | SCADA/Network controlAugmentation | 48.9823 |  | ea | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Protection – GFN panels | SCADA/Network control | Augmentation | SCADA/Network controlAugmentation | 6.2431 |  | ea | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| GFN interface relay | SCADA/Network control | Augmentation | SCADA/Network controlAugmentation | 8.6956 |  | ea | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Power Quality/Switchgear Interface | SCADA/Network control | Augmentation | SCADA/Network controlAugmentation | 98.0077 |  | ea | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 22kV Protection & Control Modifications | SCADA/Network control | Augmentation | SCADA/Network controlAugmentation | 2 | 1 | ea | 2 | 0 | [12 empty] | 0
| Other protection works | SCADA/Network control | Augmentation | SCADA/Network controlAugmentation | 0 |  | ea | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
Other AC & DC supplies |  | Subtransmission | Augmentation | SubtransmissionAugmentation | 54.7113 |  | ea | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Infrastructure - Services |  | Subtransmission | Augmentation | SubtransmissionAugmentation | 0 |  | ea | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Civil works | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Earthworks | Subtransmission | Augmentation | SubtransmissionAugmentation | 0 |  | ea | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Buildings | Subtransmission | Augmentation | SubtransmissionAugmentation | 0 |  | ea | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 22kV switchyard - install new puraceptor | Subtransmission | Augmentation | SubtransmissionAugmentation | 131.3953 |  | ea | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| - Other | Subtransmission | Augmentation | SubtransmissionAugmentation | 0 |  | ea | 0 | 0
Construction delivery & site control |  | Subtransmission | Augmentation | SubtransmissionAugmentation | 0 |  | ea | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Land purchase |  | Land | Non-Network | LandNon-Network | 0 |  | ea | 0 | 0
Subtotal Isolation Substation works | [7 empty] | 990.8177 | 414.5045 | 469.1716 | 1344.9624 | 126.4251 | 3345.8813
Check
Feeder works |  |  |  |  | Material $/Unit | QTY | UOM | Materials | Int Labour | Contracts - Design | Contracts - Construct | Other | P50 Total
LDL11 Lines works
| Underground HV ABC | Distribution system assets | Augmentation | Distribution system assetsAugmentation | 0.036479 | 940 | p/mtr | 34.2902 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Convert existing pole to hybrid fused substation | Distribution system assets | Augmentation | Distribution system assetsAugmentation | 38.1818 | 2 | ea | 76.3636 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Subtotal LDL11 Lines works | [6 empty] | 110.6538 | 0 | 0 | 755.9351 | 1.6241 | 868.213
Subtotal feeder works | [7 empty] | 110.6538 | 0 | 0 | 755.9351 | 1.6241 | 868.213
Check
Grand Total | [7 empty] | 1101.4715 | 414.5045 | 469.1716 | 2100.8975 | 128.0492 | 4214.0943
Check
| Isolation Substation works | Subtransmission | Augmentation | SubtransmissionAugmentation |  |  |  | 988.8177 | 19.998 | 19.1716 | 1003.8154 | 126.4251 | 2158.2278
|  | Subtransmission | Replacement | SubtransmissionReplacement |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Distribution system assets | Augmentation | Distribution system assetsAugmentation |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
|  | SCADA/Network control | Augmentation | SCADA/Network controlAugmentation |  |  |  | 2 | 0 | 0 | 20.876 | 0 | 22.876
|  | SCADA/Network control | Replacement | SCADA/Network controlReplacement |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Land | Non-Network | LandNon-Network |  |  |  | 0 | 0 | 0 | 320.271 | 0 | 320.271
[8 empty] | 990.8177 | 19.998 | 19.1716 | 1344.9624 | 126.4251 | 2501.3748
| Design, Project Management & Engineering costs allocation | Subtransmission | Augmentation | SubtransmissionAugmentation |  |  |  |  | 340.3868 | 388.2675 | 0 |  | 728.6543
|  | Subtransmission | Replacement | SubtransmissionReplacement |  |  |  |  | 0 | 0 | 0 |  | 0
|  | Distribution system assets | Augmentation | Distribution system assetsAugmentation |  |  |  |  | 0 | 0 | 0 |  | 0
|  | SCADA/Network control | Augmentation | SCADA/Network controlAugmentation |  |  |  |  | 3.6079 | 4.1154 | 0 |  | 7.7233
|  | SCADA/Network control | Replacement | SCADA/Network controlReplacement |  |  |  |  | 0 | 0 | 0 |  | 0
|  | Land | Non-Network | LandNon-Network |  |  |  |  | 50.5118 | 57.6171 | 0 |  | 108.1289
[8 empty] | 0 | 394.5066 | 450 | 0 | 0 | 844.5066
| Total Isolation Substation works | Subtransmission | Augmentation | SubtransmissionAugmentation |  |  |  | 988.8177 | 360.3848 | 407.4391 | 1003.8154 | 126.4251 | 2886.8821
|  | Subtransmission | Replacement | SubtransmissionReplacement |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Distribution system assets | Augmentation | Distribution system assetsAugmentation |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
|  | SCADA/Network control | Augmentation | SCADA/Network controlAugmentation |  |  |  | 2 | 3.6079 | 4.1154 | 20.876 | 0 | 30.5993
|  | SCADA/Network control | Replacement | SCADA/Network controlReplacement |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Land | Non-Network | LandNon-Network |  |  |  | 0 | 50.5118 | 57.6171 | 320.271 | 0 | 428.3999
[8 empty] | 990.8177 | 414.5045 | 469.1716 | 1344.9624 | 126.4251 | 3345.8813
[8 empty] | 0 | 0 | 0 | 0 | 0 | 0
| LDL11 Lines works | Distribution system assets | Augmentation | Distribution system assetsAugmentation |  |  |  | 110.6538 | 0 | 0 | 755.9351 | 1.6241 | 868.213
|  | Distribution system assets | Replacement | Distribution system assetsReplacement |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
[8 empty] | 110.6538 | 0 | 0 | 755.9351 | 1.6241 | 868.213
[8 empty] | 0 | 0 | 0 | 0 | 0 | 0

## Single GFN costs
Confidential
This estimate is for the addition of a single GFN in a new Zone Substation that has been built to meet REFCL requirements. |  |  |  |  | Materials |  |  | Total Direct ($k, $2019) | [6 empty] | Total Internal Labour (hours)
|  | Asset Class | Expenditure Class |  | $/Unit ($2019) | QTY | UOM | Materials | Int Labour | Contracts - Design | Contracts - Construct | Other | P50 Total | Chk | Project Engineer | Asset Management Engineer | Project Manager | Front Line Leader | Project Engineer Build | Site Manager Build | Operational Staff | Total Hours
Labour rates | [14 empty] | 162.4874 | 151.7974 | 176.3843 | 229.8341 | 162.4874 | 162.4874 | 133.6245
Design - Internal/External @ 18% |  | Allocation | Allocation | [5 empty] | 0 | 0 |  |  | 0 | 18%
Project Management & Engineering
| Project Establishment | Allocation | Allocation | [7 empty] | 0 |  | 0 | [8 empty] | 0
| Project Management | Allocation | Allocation | [5 empty] | 0 |  | 0 |  | 0 | 13% | [7 empty] | 0
| Project Close-out, Testing & Commissioning | Allocation | Allocation | [7 empty] | 0 |  | 0 | [8 empty] | 0
| Community Engagement | Allocation | Allocation | [7 empty] | 0 |  | 0 | [8 empty] | 0
Zone Substation works
Primary Plant
| Station service transformer (500 kVA) | Subtransmission | Augmentation | SubtransmissionAugmentation | 72.619 |  | ea | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Station service transformer (750 kVA) | Subtransmission | Augmentation | SubtransmissionAugmentation | 112.828 |  | ea | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Capacitance reducing isolation substation (10 MVA) | Subtransmission | Augmentation | SubtransmissionAugmentation | 465.0023 |  | ea | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| AC changeover board - Station | Subtransmission | Augmentation | SubtransmissionAugmentation | 39.295 |  | ea | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| AC changeover board - REFCL | Subtransmission | Augmentation | SubtransmissionAugmentation | 42.975 | 1 | ea | 42.975 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| AC C/O board footing | Subtransmission | Augmentation | SubtransmissionAugmentation | 0 | 1 | ea | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Arc Suppression Coil | SCADA/Network control | Augmentation | SCADA/Network controlAugmentation | 1158.3 | 1 | ea | 1158.3 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| ASC footing | Subtransmission | Augmentation | SubtransmissionAugmentation | 0 | 1 | ea | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 22kV switchboard - Metro | Subtransmission | Augmentation | SubtransmissionAugmentation | 1354 |  | ea | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 22kV switchboard - Rural | Subtransmission | Augmentation | SubtransmissionAugmentation | 1461.1163 |  | ea | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 22kV switchboard (no building) - Rural | Subtransmission | Augmentation | SubtransmissionAugmentation | 700 |  | ea | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 22kV Capacitor Bank - Modify | Subtransmission | Augmentation | SubtransmissionAugmentation | 91.2924 |  | ea | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Cap Bank footing | Subtransmission | Augmentation | SubtransmissionAugmentation | 0 | 0 | ea | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 22kV Dead Tank Circuit Breaker | Subtransmission | Augmentation | SubtransmissionAugmentation | 107.006 |  | ea | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 22kV U/S Isolator | Subtransmission | Augmentation | SubtransmissionAugmentation | 7.664 |  | ea | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 22kV Current Transformer | Subtransmission | Augmentation | SubtransmissionAugmentation | 27.163 |  | ea | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 22kV Zero Sequence CTs | Subtransmission | Augmentation | SubtransmissionAugmentation | 0 | 9 | ea | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 22kV Voltage Transformer | Subtransmission | Augmentation | SubtransmissionAugmentation | 0 |  | ea | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 22KV Surge Arrestor | Subtransmission | Augmentation | SubtransmissionAugmentation | 0.62 |  | ea | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Primary Cable Testing | Subtransmission | Augmentation | SubtransmissionAugmentation | 0 | 2 | ea | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Neutral Bus | Subtransmission | Augmentation | SubtransmissionAugmentation | 93.854 | 1 | ea | 93.854 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| REFCL control room | Subtransmission | Augmentation | SubtransmissionAugmentation | 0 | 1 | ea | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Battery Room (2 battery sets) | Subtransmission | Augmentation | SubtransmissionAugmentation | 174.5855 |  | ea | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| New Control Building | Subtransmission | Augmentation | SubtransmissionAugmentation | 369.039 |  | ea | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Primary Cables - 22kV | Subtransmission | Augmentation | SubtransmissionAugmentation | 11.1825 | 1 | p/mtr | 11.1825 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Feeder Exit Cables - 22kV | Subtransmission | Augmentation | SubtransmissionAugmentation | 0.05 | 0 | p/mtr | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Other | Subtransmission | Augmentation | SubtransmissionAugmentation | 0 | 1 | ea | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 22kV Capacitor Bank (2x3 MVAr) - type 2 | Subtransmission | Augmentation | SubtransmissionAugmentation | 406.8 |  | ea | 0 | 0 |  |  |  |  | 0 | [7 empty] | 0
| ASC only | Subtransmission | Augmentation | SubtransmissionAugmentation | 430 |  | ea | 0 | 0
[15 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
SCADA / Protection & Control/ Comms | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Neutral Bus controller - 1 GFN | SCADA/Network control | Augmentation | SCADA/Network controlAugmentation | 48.9823 |  | ea | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Protection – GFN panels | SCADA/Network control | Augmentation | SCADA/Network controlAugmentation | 6.2431 |  | ea | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| GFN interface relay | SCADA/Network control | Augmentation | SCADA/Network controlAugmentation | 8.6956 |  | ea | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Power Quality/Switchgear Interface | SCADA/Network control | Augmentation | SCADA/Network controlAugmentation | 98.0077 |  | ea | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 22kV Protection & Control Modifications | SCADA/Network control | Augmentation | SCADA/Network controlAugmentation | 297.298 | 1 | ea | 297.298 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Other protection works | SCADA/Network control | Augmentation | SCADA/Network controlAugmentation | 0 |  | ea | 0 | 0 | [12 empty] | 0
Other AC & DC supplies |  | Subtransmission | Augmentation | SubtransmissionAugmentation | 54.7113 |  | ea | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
Civil works | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Earthworks, Buildings | Subtransmission | Augmentation | SubtransmissionAugmentation | 0 |  | ea | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 22kV switchyard - install new puraceptor | Subtransmission | Augmentation | SubtransmissionAugmentation | 131.3953 |  | ea | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| - Other | Subtransmission | Augmentation | SubtransmissionAugmentation | 2.403 | 1 | ea | 2.403 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Construction delivery & site control |  | Subtransmission | Augmentation | SubtransmissionAugmentation | 0 |  | ea | 0 | 0
Land purchase |  | Land | Non-Network | LandNon-Network | 0 |  | ea | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Subtotal Substation works | [7 empty] | 1606.0125 | 341.7837 | 473.2389 | 1625.6508 | 1.3582 | 4048.0441 | 0
Check
Feeder works |  |  |  |  | Material $/Unit | QTY | UOM | Materials | Int Labour | Contracts - Design | Contracts - Construct | Other | P50 Total
Network Balancing | [31 empty] | Total hrs p/unit
| Design Labour - internal / external | Distribution system assets | Augmentation | Distribution system assetsAugmentation | 0 | 0 | feeders |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27.2% | 72.8% | 0% | 0% | 0% | 0% | 0% | 100% | TRUE | 54.4153
| Third conductor installation | Distribution system assets | Augmentation | Distribution system assetsAugmentation |  | 0 | spans | [6 empty] | 0 | [8 empty] | 0% | 14.07% | 24.32% | 0% | 17.6% | 44% | 0% | 100% | TRUE
| Unbonding cable | Distribution system assets | Augmentation | Distribution system assetsAugmentation |  | 0 | location | [6 empty] | 0 | [8 empty] | 0% | 11.32% | 25.1% | 0% | 18.17% | 45.41% | 0% | 100% | TRUE
| Phase rotation | Distribution system assets | Augmentation | Distribution system assetsAugmentation |  | 0 | rotations | [6 empty] | 0 | [8 empty] | 0% | 17.74% | 23.28% | 0% | 16.85% | 42.13% | 0% | 100% | TRUE
| Balancing capacitors | Distribution system assets | Augmentation | Distribution system assetsAugmentation | 18.1336 | 0 | installations | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 6.924% | 26.35% | 0% | 19.07% | 47.66% | 0% | 100% | TRUE | 20.2193
| Inherent works - various feeder based works | Distribution system assets | Augmentation | Distribution system assetsAugmentation | 0 | 0 | feeders | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 100% | TRUE | 46.3981
| Phase plate correction | Distribution system assets | Replacement | Distribution system assetsReplacement | 0 | 0 | feeders & RC sections | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 | [9 empty] | 0
| Fuse removal and install solid link | Distribution system assets | Replacement | Distribution system assetsReplacement | 0 | 0 | fuses | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 100% | TRUE | 1.2069
| Install fusesaver and control box - per site | Distribution system assets | Augmentation | Distribution system assetsAugmentation | 12.4291 | 0 | sites | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 100% | TRUE | 23.0218
| Install new ACR for switching | Distribution system assets | Augmentation | Distribution system assetsAugmentation | 22.6039 | 0 | ACRs | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30.31% | 32.45% | 37.24% | 0% | 0% | 0% | 0% | 100% | TRUE | 42.966
| Subtotal Network Balancing | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0
Line Hardening
| Surge arrestor replacement | Distribution system assets | Replacement | Distribution system assetsReplacement | 0.3785 | 0 | ea | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.573% | 0% | 32.12% | 0% | 0% | 0% | 65.31% | 100% | TRUE | 1.08
| Cable On-Line Testing | Distribution system assets | Replacement | Distribution system assetsReplacement | 0 | 0 | ea | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 100% |  |  | 100% | TRUE | 1.8482
| Cable Off-Line Testing | Distribution system assets | Replacement | Distribution system assetsReplacement | 0 | 0 | ea | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 100% |  |  | 100% | TRUE | 61.6082
| Cable - Replace Fitting | Distribution system assets | Replacement | Distribution system assetsReplacement | 5.2026 | 0 | ea | 0 | 0 |  | 0 |  | 0 | 0 | [7 empty] | 0
| Cable - Replace Cable Section - per m | Distribution system assets | Replacement | Distribution system assetsReplacement | 0.05 | 0 | m | 0 | 0 |  | 0 |  | 0 | 0 | [7 empty] | 0
Compatible Equipment
| ACR upgrade | Distribution system assets | Replacement | Distribution system assetsReplacement | 15 | 0 | ea | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30.31% | 32.45% | 37.24% | 0% | 0% | 0% | 0% | 100% | TRUE | 14.42
| ACR replacement | Distribution system assets | Replacement | Distribution system assetsReplacement | 22.6039 | 0 | ea | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30.31% | 32.45% | 37.24% | 0% | 0% | 0% | 0% | 100% | TRUE | 42.966
| Voltage regulator upgrade | Distribution system assets | Replacement | Distribution system assetsReplacement | 15.156 | 0 | ea | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11.82% | 49.78% | 38.4% | 0% | 0% | 0% | 0% | 100% | TRUE | 144.7042
| Voltage regulator replacement | Distribution system assets | Replacement | Distribution system assetsReplacement | 193.2305 | 0 | ea | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 69.94% | 4.845% | 25.21% | 0% | 0% | 0% | 0% | 100% | TRUE | 220.4113
Distribution Code
| HV customers isolation substation (3.0 MVA) | Distribution system assets | Augmentation | Distribution system assetsAugmentation | 0 | 0 | ea | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18.11% | 21.48% | 60.41% | 0% | 0% | 0% | 0% | 100% | TRUE | 469.7767
| HV customers isolation substation (5.0 MVA) | Distribution system assets | Augmentation | Distribution system assetsAugmentation | 0 | 0 | ea | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18.11% | 42.96% | 38.93% | 0% | 0% | 0% | 0% | 100% | TRUE | 500.1505
| HV customers isolation substation (7.5 MVA) | Distribution system assets | Augmentation | Distribution system assetsAugmentation | 0 | 0 | ea | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18.11% | 42.96% | 38.93% | 0% | 0% | 0% | 0% | 100% | TRUE | 416.1112
| Line Hardening | Distribution system assets | Replacement | Distribution system assetsReplacement | 32.7402 | 0 | ea | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30.31% | 32.45% | 37.24% | 0% | 0% | 0% | 0% | 100% | TRUE | 61.06
Subtotal feeder works | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0
Check
Grand Total | [7 empty] | 1606.0125 | 341.7837 | 473.2389 | 1625.6508 | 1.3582 | 4048.0441
Check
| Zone Substation works | Subtransmission | Augmentation | SubtransmissionAugmentation |  |  |  | 150.4145 | 0 | 0 | 1507.7228 | 0 | 1658.1373
|  | Subtransmission | Replacement | SubtransmissionReplacement |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
|  | SCADA/Network control | Augmentation | SCADA/Network controlAugmentation |  |  |  | 1455.598 | 0 | 0 | 117.928 | 1.3582 | 1574.8842
|  | SCADA/Network control | Replacement | SCADA/Network controlReplacement |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Land | Non-Network | LandNon-Network |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
[8 empty] | 1606.0125 | 0 | 0 | 1625.6508 | 1.3582 | 3233.0215
| Design, Project Management & Engineering costs allocation | Subtransmission | Augmentation | SubtransmissionAugmentation |  |  |  |  | 175.2924 | 242.7126 | 0 |  | 418.0051
|  | Subtransmission | Replacement | SubtransmissionReplacement |  |  |  |  | 0 | 0 | 0 |  | 0
|  | SCADA/Network control | Augmentation | SCADA/Network controlAugmentation |  |  |  |  | 166.4912 | 230.5263 | 0 |  | 397.0175
|  | SCADA/Network control | Replacement | SCADA/Network controlReplacement |  |  |  |  | 0 | 0 | 0 |  | 0
|  | Land | Non-Network | LandNon-Network |  |  |  |  | 0 | 0 | 0 |  | 0
[8 empty] | 0 | 341.7837 | 473.2389 | 0 | 0 | 815.0226
| Total Substation works | Subtransmission | Augmentation | SubtransmissionAugmentation |  |  |  | 150.4145 | 175.2924 | 242.7126 | 1507.7228 | 0 | 2076.1424
|  | Subtransmission | Replacement | SubtransmissionReplacement |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
|  | SCADA/Network control | Augmentation | SCADA/Network controlAugmentation |  |  |  | 1455.598 | 166.4912 | 230.5263 | 117.928 | 1.3582 | 1971.9017
|  | SCADA/Network control | Replacement | SCADA/Network controlReplacement |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Land | Non-Network | LandNon-Network |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
[8 empty] | 1606.0125 | 341.7837 | 473.2389 | 1625.6508 | 1.3582 | 4048.0441
[8 empty] | 0 | 0 | 0 | 0 | 0 | 0
| Network Balancing | Distribution system assets | Augmentation | Distribution system assetsAugmentation |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Distribution system assets | Replacement | Distribution system assetsReplacement |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
[8 empty] | 0 | 0 | 0 | 0 | 0 | 0
[8 empty] | 0 | 0 | 0 | 0 | 0 | 0

## Unit_Rates
| Direct Cost Unit Rates - $000's, Real $2019 |  |  |  | Confidential
[7 empty] | Proposed real wage escalator CY20 - internal labour | 1.0089
| Zone Substation works Unit Rates | [5 empty] | Actual CPI (1 year lagged) - $2019 to 2020 | 1.0159
Primary Plant
|  |  |  | Unit | [11 empty] | Volumes by Station
|  | Category | Description | Rate ($k) | Classification | Asset Class | Expenditure Class | Materials | Contracts | Other |  |  | WOTS | BDL | ELM | RWN | KMS | WGI | BGE | LDL
|  | Station service transformer (500 kVA) | Replace or install new station service transformer (500 kVA) |  | Capex | Subtransmission | Augmentation | 72.619 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Station service transformer (750 kVA) | Replace or install new station service transformer (750 kVA) |  | Capex | Subtransmission | Augmentation | 112.828 |  |  |  |  | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0
| ASD inserted | Station service transformer (200 kVA) | Replace or install new station service transformer (200 kVA) incl. footing |  | Capex | Subtransmission | Augmentation | 47.7187 |  |  |  |  | 2 | 0 | 0 | 0 | 0 | 0 | 1 | 0
| ASD inserted | Capacitance reducing isolation substation (300 kVA) | Install capacitance reducing isolation substation (300 kVA) |  | Capex | Subtransmission | Augmentation | 18.9974 |  |  |  |  | 3 | 0 | 0 | 0 | 0 | 5 | 3 | 0
| ASD inserted | Capacitance reducing isolation substation (1 MVA) | Install capacitance reducing isolation substation (1 MVA) |  | Capex | Subtransmission | Augmentation | 80.0253 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0
| ASD inserted | Capacitance reducing isolation substation (5 / 7.5 MVA) | Install capacitance reducing isolation substation (5 / 7.5 MVA) incl. footing |  | Capex | Subtransmission | Augmentation | 907.5436 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
|  | Capacitance reducing isolation substation (7.5 MVA) | Install capacitance reducing isolation substation (7.5 MVA) |  | Capex | Subtransmission | Augmentation | 426.8068 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Capacitance reducing isolation substation (10 MVA) | Install capacitance reducing isolation substation (10 MVA) |  | Capex | Subtransmission | Augmentation | 465.0023 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| ASD inserted | Capacitance reducing isolation substation (12.5 MVA) | Install capacitance reducing isolation substation (12.5 MVA) incl. footing |  | Capex | Subtransmission | Augmentation | 1184.6455 |  |  |  |  | 2 | 0 | 0 | 0 | 0 | 0 | 1 | 0
|  | AC changeover board - Station | Installation of outdoor changeover board |  | Capex | Subtransmission | Augmentation | 39.295 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | AC changeover board - REFCL | Installation of outdoor changeover board suitable for uprated Station Service Tx, incl. footing |  | Capex | Subtransmission | Augmentation | 42.975 |  |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0
|  | AC C/O board footing | AC C/O board footing |  | Capex | Subtransmission | Augmentation | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Arc Suppression Coil | Installation of ASC |  | Capex | SCADA/Network control | Augmentation | 1158.3 |  |  |  |  | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 0
|  | ASC footing | Install new footing and associated bunding for GFN ASC unit |  | Capex | Subtransmission | Augmentation | 0 |  |  |  |  | 2 | 1 | 1 | 1 | 0 | 1 | 1 | 0
|  | 22kV switchboard - Metro | Installation of 22 kV switchboard - Metro |  | Capex | Subtransmission | Augmentation | 1354 |  |  |  |  | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 22kV switchboard - Rural | Installation of 22 kV switchboard - Rural |  | Capex | Subtransmission | Augmentation | 1461.1163 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 22kV switchboard (no building) - Rural | Installation of 22 kV switchboard only (no building) - Rural |  | Capex | Subtransmission | Augmentation | 700 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 22kV Capacitor Banks | Installation of 22 kV capacitor banks |  | Capex | Subtransmission | Augmentation | 127.032 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 22kV Capacitor Bank (2x3 MVAr) - type 4 | Installation of 2x3 MVAr Capacitor Bank |  | Capex | Subtransmission | Augmentation | 465.78 |  |  |  |  | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 22kV Capacitor Bank (2x3 MVAr) - type 2 | Installation of 2x3 MVAr Capacitor Bank |  | Capex | Subtransmission | Augmentation | 406.8 |  |  |  |  | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0
|  | 22kV Capacitor Bank (4 x3 MVAr) - type 3 | Installation of 4x3 MVAr Capacitor Bank |  | Capex | Subtransmission | Augmentation | 686.545 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 22kV Capacitor Bank - Modify | Modify existing capacitor bank |  | Capex | Subtransmission | Augmentation | 91.2924 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Cap Bank footing | Cap Bank footing |  | Capex | Subtransmission | Augmentation | 0 |  |  |  |  | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 22kV Dead Tank Circuit Breaker | 22kV Dead Tank Circuit Breaker 3150A, 40kA |  | Capex | Subtransmission | Augmentation | 107.006 |  |  |  |  | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0
|  | 22kV U/S Isolator | 22kV Underslung Isolator |  | Capex | Subtransmission | Augmentation | 7.664 |  |  |  |  | 4 | 0 | 2 | 2 | 0 | 0 | 2 | 0
|  | 22KV Feeder Exit | 22KV Feeder Exit |  | Capex | Subtransmission | Augmentation | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 22kV Voltage Transformer | 22kV Voltage Transformer |  | Capex | Subtransmission | Augmentation | 0 |  |  |  |  | 2 | 0 | 0 | 1 | 0 | 0 | 1 | 0
|  | 22kV Current Transformer | 22kV Current Transformer |  | Capex | Subtransmission | Augmentation | 27.163 |  |  |  |  | 2 | 0 | 0 | 0 | 0 | 4 | 1 | 0
|  | 22kV Zero Sequence CTs | Install core balance zero sequence current transformers |  | Capex | Subtransmission | Augmentation | 0 |  |  |  |  | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0
|  | 22KV Surge Arrestor | 22KV Surge Arrestor |  | Capex | Subtransmission | Augmentation | 0.62 |  |  |  |  | 2 | 0 | 0 | 3 | 0 | 0 | 1 | 0
|  | Transformer Neutral Isolator | Transformer Neutral Isolator |  | Capex | Subtransmission | Augmentation | 26.2223 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0
|  | Neutral Bus | Installation of neutral bus |  | Capex | Subtransmission | Augmentation | 93.854 |  |  |  |  | 0 | 1 | 1 | 1 | 0 | 1 | 0 | 0
|  | REFCL control room | Installation of the REFCL control room only - no protection panels |  | Capex | Subtransmission | Augmentation | 0 |  |  |  |  | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | 2 REFCL control room | Installation of the REFCL control room only - no protection panels - supports 2 GFNs |  | Capex | Subtransmission | Augmentation | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| ASD inserted | Type 3 REFCL control room | Installation of REFCL control room with customised non-standard panels (incl. footing) |  | Capex | Subtransmission | Augmentation | 109.1759 |  |  |  |  | 2 | 0 | 0 | 0 | 1 | 1 | 1 | 0
|  | Battery Room (single battery set) | Installation of modular battery room including batteries (1 set of) |  | Capex | Subtransmission | Augmentation | 227.63 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Battery Room (2 battery sets) | Installation of modular battery room including batteries (2 sets of) |  | Capex | Subtransmission | Augmentation | 174.5855 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | New Control Building | Installation of modular control building room |  | Capex | Subtransmission | Augmentation | 369.039 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Primary Cables - 22kV | Tx to Switchboard 22kV 630mm2 XLPE single phase (35mx6) |  | Capex | Subtransmission | Augmentation | 35.7406 |  |  |  |  | 120 | 900 | 580 | 500 | 2600 | 1120 | 50 | 120
|  | Primary Cables - 22kV | S/S to Switchboard 22kV 185mm2 XLPE single phase (30mx3) |  | Capex | Subtransmission | Augmentation | 11.0467
|  | Primary Cables - 22kV | ASC to Neutral Bus 22kV 95mm2 XLPE single phase (15m) |  | Capex | Subtransmission | Augmentation | 1.8816
|  | Feeder Exit Cables - 22kV | Feeder Exit Cables - 22kV 300mm (per metre) |  | Capex | Subtransmission | Augmentation | 0.05 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Primary Cable Testing | Testing of station 22 kV Cables |  | Capex | Subtransmission | Augmentation | 0 |  |  |  |  | 2 | 0 | 0 | 1 | 0 | 1 | 1 | 1
|  | Oil separator | Installation of Oil separator / Puraceptor |  | Capex | Subtransmission | Augmentation | 131.3953 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | One Tilt Slab control room | Installation of a tilt slab building |  | Capex | Subtransmission | Augmentation | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | ASC only | Installation of a tilt slab building |  | Capex | Subtransmission | Augmentation | 430 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Additional Primary Plant, Secondary and Lines Unit Rates - per IR#004A (14/04/2020)
Unit
|  | Category | Description | Rate ($k) | Classification | Asset Class | Expenditure Class | Materials | Contracts | Other
Primary |  | 66kV Bay - Ring Bus | 66kV Bay - Ring Bus (and 66kV vacant bay) |  | Capex | Subtransmission | Augmentation | 185.475 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Primary |  | 66kV Exit - Line Feeder | 66kV Exit - Line Feeder |  | Capex | Subtransmission | Augmentation | 74.1545 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Primary |  | 66kV Exit - Transformer | 66kV Exit - Transformer |  | Capex | Subtransmission | Augmentation | 37.494 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Primary |  | Power transformer - 66/22kV 15/20MVA | Transformer - 66/22kV 15/20MVA |  | Capex | Subtransmission | Augmentation | 787.0745 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Primary |  | Station service transformer (1 MVA) | Replace or install new station service transformer (1 MVA) |  | Capex | Subtransmission | Augmentation | 169.008 |  |  |  |  | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0
Primary |  | Decommission existing 10/16MVA Transformer | Decommission existing 10/16MVA Transformer |  | Capex | Subtransmission | Augmentation | 0 |  |  |  |  | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0
Primary |  | Power transformer - 66/22kV 20/33MVA | Installation of transformer - 66/22kV 20/33MVA |  | Capex | Subtransmission | Augmentation | 1126.5675 |  |  |  |  | 0 | 2 | 0 | 0 | 0 | 1 | 0 | 0
Primary |  | 66kV Surge Arrestor | 66kV Surge Arrestor |  | Capex | Subtransmission | Augmentation | 0.62196 |  |  |  |  | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0
Primary |  | 66kV 800A Rotary Disconnect | 66kV 800A Rotary Disconnect |  | Capex | Subtransmission | Augmentation | 25.198 |  |  |  |  | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0
Primary |  | 66kV Dead Tank Circuit Breaker | 66kv Dead Tank Circuit Breaker |  | Capex | Subtransmission | Augmentation | 117.012 |  |  |  |  | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0
Primary |  | 66kV U/S Isolator | 66kV Unuderslung Isolator |  | Capex | Subtransmission | Augmentation | 23.788 |  |  |  |  | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0
Primary |  | 22kV Indoor Switchgear - Transformers | 22kV Indoor Switchgear - Transformers |  | Capex | Subtransmission | Augmentation | 41.2559 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Primary |  | 22kV Neutral Earthing Resistors | 22kV Neutral Earthing Resistors |  | Capex | Subtransmission | Augmentation | 106.8132 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Primary |  | Earth Grid | Earth Grid (4,900 m2) |  | Capex | Subtransmission | Augmentation | 58.2657 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Secondary | ASD inserted | 22kV Line Protection Panel | 22kV Line Protection Panel |  | Capex | SCADA/Network control | Augmentation | 63.4714 |  |  |  |  | 2 | 0 | 0 | 0 | 0 | 0 | 1 | 0
Secondary | ASD inserted | 66/22kV Transformer Protection Panel | 66/22kV Transformer Protection Panel |  | Capex | SCADA/Network control | Augmentation | 47.4106 |  |  |  |  | 2 | 0 | 0 | 0 | 0 | 0 | 1 | 0
Secondary |  | 66kV Line Protection Panel | 66kV Line Protection Panel |  | Capex | SCADA/Network control | Augmentation | 76.7296 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Secondary |  | 66kV Substation Protection Panel (transformer & bus) | Substation Protection Panel (66/22kV Transformer & 66kV bus) |  | Capex | SCADA/Network control | Augmentation | 223.6578 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Secondary |  | 66/22kV Transformer Voltage Control & Regulation Cubicle | 66/22kV Transformer Voltage Control & Regulation Cubicle (A-EBERLE) |  | Capex | SCADA/Network control | Augmentation | 252.1155 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Secondary | ASD inserted | High Impedance Busbar Protection cubicle | High Impedance Busbar Protection cubicle |  | Capex | SCADA/Network control | Augmentation | 58.4171 |  |  |  |  | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0
Lines |  | Concrete Poles 20m (includes installation), per pole | Pole - Concrete 20m, 16kN working load, includes installation |  | Capex | Subtransmission | Augmentation | 5.4308 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Lines |  | Cross Arms 66kV - Intermediate & Strain | Cross Arms 66kV - Intermediate & Strain (incl. insulators & hardware) |  | Capex | Subtransmission | Augmentation | 0.40306 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Lines |  | Cross Arms 22kV HV - Intermediate & Strain | Cross Arms 22kV HV - Intermediate & Strain (incl. insulators & hardware) |  | Capex | Distribution system assets | Augmentation | 0.66462 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Lines |  | Cross Arms 22kV LV - Intermediate & Strain | Cross Arms 22kV LV - Intermediate & Strain (Incl. Insulators & Hardware) |  | Capex | Distribution system assets | Augmentation | 0.43615 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Lines |  | Stays | Stays |  | Capex | Subtransmission | Augmentation | 0.24562 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Lines |  | Conductor (19/4.75 AAC) | Conductor (19/4.75 AAC) - Per km, installed |  | Capex | Subtransmission | Augmentation | 15.18 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Lines |  | Conductor (19/3.25 AAC) | Conductor (19/3.25 AAC) - Per km, installed |  | Capex | Distribution system assets | Augmentation | 6.7848 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Lines |  | Supervision, Traffic Control, Set-Up Site & Clean-Up | Supervision, Traffic Control, Set-Up Site & Clean-Up |  | Capex | Subtransmission | Augmentation | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Lines |  | ADSS Fibre Optic Cable | ADSS per km (Installed on Existing Poles) |  | Capex | Subtransmission | Augmentation | 8.72 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Lines |  | OPGW Joint Box (Installed & Terminated on Existing Tower/Pole) | OPGW Joint Box (Installed & Terminated on Existing Tower/Pole) |  | Capex | Subtransmission | Augmentation | 6.795 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Lines |  | Vegetation Clearing | Vegetation Clearing - Light 66kV/22kV Line (Per km) |  | Capex | Subtransmission | Augmentation | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Lines |  | <spare> |  |  | Capex | Subtransmission | Augmentation | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Lines |  | Concrete Poles 15.5m (includes installation), per pole | Pole - Concrete 15.5m, 12kN working load (24kN ultimate) |  | Capex | Distribution system assets | Augmentation | 6.06 |  |  |  |  | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
Lines | ASD inserted | Concrete Poles 15.5m Replacement (includes installation), per pole | Pole - Concrete 15.5m, 12kN working load (24kN ultimate) |  | Capex | Distribution system assets | Replacement | 6.06 |  |  |  |  | 2 | 0 | 0 | 0 | 0 | 5 | 4 | 0
Lines |  | 22kV Underground Cable (150m) | XLPE 3 Core 22kV Cable |  | Capex | Distribution system assets | Augmentation | 0.061705 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Lines | ASD inserted | Decommission and remove existing conductor (route length) at various locations - includes AAC, ASCR, Steel | Decommission and remove existing conductor (route length) at various locations - includes AAC, ASCR, Steel |  | Capex | Distribution system assets | Replacement | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 1.835 | 0
Lines | ASD inserted | 22kV Underground Cable 185mm2 XLPE | XLPE 3 Core 22kV Cable (includes trench and install conduit) - per m |  | Capex | Distribution system assets | Augmentation | 0.043775 |  |  |  |  | 200 | 0 | 0 | 0 | 0 | 0 | 2000 | 0
Lines | ASD inserted | 22kV Underground Cable 300mm2 XLPE | XLPE 3 Core 22kV Cable (includes trench and install conduit) - per m |  | Capex | Distribution system assets | Augmentation | 0.064197 |  |  |  |  | 400 | 0 | 0 | 0 | 0 | 0 | 200 | 0
Lines | ASD inserted | 22KV cable terminations | 22KV cable terminations |  | Capex | Distribution system assets | Augmentation | 3.1912 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0
Lines | ASD inserted | Convert existing pole to hybrid fused substation | Convert existing pole to hybrid fused substation |  | Capex | Distribution system assets | Augmentation | 38.1818 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2
Lines | ASD inserted | Underground HV ABC | Underground HV ABC ($per metre) |  | Capex | Distribution system assets | Augmentation | 0.036479 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 940
Lines |  | Gas Switch | Gas Switch (supply only) |  | Capex | Distribution system assets | Augmentation | 15.42 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Protection & Control
Unit
|  | Category | Description | Rate ($k) | Classification | Asset Class | Expenditure Class | Materials | Contracts | Other
|  | Neutral Bus controller - 1 GFN | Installation of neutral bus controller |  | Capex | SCADA/Network control | Augmentation | 48.9823 |  |  |  |  | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  | Neutral Bus controller - 2 GFNs | Installation of neutral bus controller |  | Capex | SCADA/Network control | Augmentation | 61.8191 |  |  |  |  | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0
|  | Protection – GFN panels | Interface, control panel and inverter |  | Capex | SCADA/Network control | Augmentation | 6.2431 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0
|  | GFN interface relay | GFN interface relay |  | Capex | SCADA/Network control | Augmentation | 8.6956 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Power Quality/Switchgear Interface | Installation of Panel with 2 Power Quality Meters & 1 Switchgear interface relay |  | Capex | SCADA/Network control | Augmentation | 98.0077 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Power Quality Non Std | Installation of Panel with 6 Power Quality Meters |  | Capex | SCADA/Network control | Augmentation | 197.6553 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Switchgear Interface Non Std | Installation of Panel with 3 switchgear interface relays |  | Capex | SCADA/Network control | Augmentation | 164.0238 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Capacitor Bank Prot & Cntl (3x3MVAr) | Installation of Panel for Prot & Cntl of 3 x 3MVAr Capacitor Bank |  | Capex | SCADA/Network control | Augmentation | 41.9661 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Capacitor Bank Prot & Cntl (2x3MVAr) | Installation of Panel for Prot & Cntl of 2 x 3MVAr Capacitor Bank |  | Capex | SCADA/Network control | Augmentation | 33.6836 |  |  |  |  | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0
|  | Remote Terminal Unit | Install new RTU (existing MD1000 incapable of handling traffic of new relays) |  | Capex | SCADA/Network control | Augmentation | 149.3397 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | SCIMS system - small | Install a new Substation Automation panel (SCIMS) in existing control room |  | Capex | SCADA/Network control | Augmentation | 92.2396 |  |  |  |  | 2 | 0 | 0 | 0 | 0 | 0 | 1 | 0
Network Balancing Unit Rates
|  |  |  | Unit | [5 empty] | Contracts - Design | Contracts - Construct
|  | Category | Description | Rate ($k) | Classification | Asset Class | Expenditure Class | Materials | Labour |  |  | Other
|  | Design | Design activities to determine network balancing requirements, validate balancing and record balancing information – per feeder | 23.5834 | Capex | Distribution system assets | Augmentation | 0 | 2.1827 | 3.9889 | 0 | 0 | WOTS: WYK2 rate
[6 empty] | Distribution system assets | Augmentation | 0 | 8.4884 | 19.7659 | 0 | 0 | Other stations rate |  |  | 0 | 0 | 0 | 0 | 0
|  | Third conductor installation | Install 3rd conductor – per span |  | Capex | Distribution system assets | Augmentation | [8 empty] | 0 | 0 | 0 | 0 | 0
|  | Unbonding cable | Unbounding cable at either end – per location |  | Capex | Distribution system assets | Augmentation | [8 empty] | 0 | 0 | 0 | 0 | 0
|  | Phase rotation | Rotate phases – per rotation |  | Capex | Distribution system assets | Augmentation | [8 empty] | 0 | 0 | 0 | 0 | 0
|  | Balancing capacitors | Install balancing capacitors (single or three phase) – per installation | 58.5792 | Capex | Distribution system assets | Augmentation | 18.1336 | 3.4598 | 0 | 32.9257 | 4.0601 |  |  |  | 0 | 0 | 0 | 0 | 0
| Inherent works |  | Activities including the development of balancing capacitor solution, modification of Asset Management Systems - per feeder | 15.0738 | Capex | Distribution system assets | Augmentation | 0 | 6.5904 | 0 | 8.4834 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | Inherent works - various feeder based works
|  |  | Phase plate correction - per feeder and RC sections | 0.56752 | Capex | Distribution system assets | Replacement | 0 | 0 | 0 | 0.56752 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | Phase plate correction
|  |  | Protection reviews for fuse removals and installation of solid link - per fuse | 3.3465 | Capex | Distribution system assets | Replacement | 0 | 0.16261 | 0 | 3.1839 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | Fuse removal and install solid link
|  |  | Installation of fusesaver and remote control unit - per site | 39.1276 | Capex | Distribution system assets | Augmentation | 12.4291 | 3.261 | 1.6352 | 21.8023 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | Install fusesaver and control box - per site
|  | Install new ACR for switching | Install new ACR for switching | 80.3688 | Capex | Distribution system assets | Augmentation | 22.6039 | 20.3508 | 4.7858 | 25.9801 | 6.6482 |  |  |  | 0 | 0 | 0 | 0 | 0 | Install new ACR for switching
|  |  | Purchase of phase identification tools - G3 Phase ID probe | 13.0922 | Capex | Non-network general assets - Other | Non-network | 13.0922 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0
|  |  | - Base station | 8.8476 | Capex | Non-network general assets - Other | Non-network | 8.8476 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0
Line Hardening Unit Rates
|  |  |  | Unit | [5 empty] | Contracts - Design | Contracts - Construct
|  | Category | Description | Rate ($k) | Classification | Asset Class | Expenditure Class | Materials | Labour |  |  | Other
|  | Surge arrestor | Replace surge arrestor on existing structure - per site | 2.6371 | Capex | Distribution system assets | Replacement | 0.75701 | 0.38862 | 0 | 1.4915 | 0
|  |  | - per unit | 1.3186 | Capex | Distribution system assets | Replacement | 0.3785 | 0.19431 | 0 | 0.74574 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0
|  | Cables | Cable On-Line Testing | 0.32009 | Capex | Distribution system assets | Replacement | 0 | 0.32009 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0
|  |  | Cable Off-Line Testing | 10.6697 | Capex | Distribution system assets | Replacement | 0 | 10.6697 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0
|  |  | Cable - Replace Fitting | 22.5907 | Capex | Distribution system assets | Replacement | 5.2026 | 0 | 0 | 17.3882 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0
|  |  | Cable - Replace Cable Section - per m | 0.55 | Capex | Distribution system assets | Replacement | 0.05 | 0 | 0 | 0.5 | 0 | $550 per m |  |  | 0 | 0 | 0 | 0 | 0
|  | Other | CERA Removal and Replacement with 900kVAr Pole Top Capacitor | 70.807 | Capex | Distribution system assets | Augmentation | 31.2155 | 0 | 0 | 39.5915 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0
Compatible Equipment Unit Rates
|  |  |  | Unit | [5 empty] | Contracts - Design | Contracts - Construct
|  | Category | Description | Rate ($k) | Classification | Asset Class | Expenditure Class | Materials | Labour |  |  | Other
|  | ACR upgrade | Replace control box on ACR | 55.1611 | Capex | Distribution system assets | Replacement | 15 | 2.5 | 4.8 | 32.8611 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0
|  | ACR replacement | Replace pole-mounted ACR | 67.517 | Capex | Distribution system assets | Replacement | 22.6039 | 7.499 | 4.7858 | 25.9801 | 6.6482 |  |  |  | 0 | 0 | 0 | 0 | 0
| ASD inserted | New ACR unit and control box | New ACR unit and control box | 122.6781 | Capex | Distribution system assets | Augmentation | 37.6039 | 9.999 | 9.5858 | 58.8412 | 6.6482 | 0 |  |  | 0 | 0 | 0 | 0 | 2
|  | Voltage regulator upgrade | Replace control box on voltage regulator | 50.2821 | Capex | Distribution system assets | Replacement | 15.156 | 23.7105 | 0 | 11.4156 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0
|  | Voltage regulator replacement | Replace voltage regulator | 361.8832 | Capex | Distribution system assets | Replacement | 193.2305 | 36.7756 | 0 | 131.8771 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0
Code Compliance Unit Rates
|  |  |  | Unit | [5 empty] | Contracts - Design | Contracts - Construct
|  | Category | Description | Rate ($k) | Classification | Asset Class | Expenditure Class | Materials | Labour |  |  | Other
|  | Code compliance | Install isolating transformer and associated equipment adjacent to high-voltage customer – per site, 3.0 MVA substation | 0 | Capex | Distribution system assets | Augmentation | [5 empty] | not applicable |  |  | 0 | 0 | 0 | 0 | 0
|  |  | 5 MVA substation | 0 | Capex | Distribution system assets | Augmentation | [5 empty] | not applicable |  |  | 0 | 0 | 0 | 0 | 0
|  |  | 7.5 MVA substation | 0 | Capex | Distribution system assets | Augmentation | [5 empty] | not applicable |  |  | 0 | 0 | 0 | 0 | 0
|  |  | ACR | 96.2512 | Capex | Distribution system assets | Replacement | 32.7402 | 10.5852 | 6.7696 | 36.5557 | 9.6005 |  |  |  | 0 | 0 | 0 | 0 | 0 | Line Hardening
Reliability maintained Unit Rates
|  |  |  | Unit | [5 empty] | Contracts - Design | Contracts - Construct
|  | Category | Description | Rate ($k) | Classification | Asset Class | Expenditure Class | Materials | Labour |  |  | Other
|  | Remote control switch | Replace remote controlled switch on existing structure - Design |  | Capex | Distribution system assets | Replacement
|  |  | - DFA2 software changes to SCADA |  | Capex | SCADA/Network control | Replacement
|  |  | - Materials supply and deployment of switches |  | Capex | Distribution system assets | Replacement
Live Line Equipment Purchases Unit Rates
|  |  |  | Unit | [5 empty] | Contracts - Design | Contracts - Construct
|  | Category | Description | Rate ($k) | Classification | Asset Class | Expenditure Class | Materials | Labour |  |  | Other
|  | Mid-span Isolator units | Devices used to reduce the outage area in the distribution network. Set of isolators that are cut into a line between two poles (i.e., mid-span) to provide a temporary break in connection. After an outage devices can be re-used elswhere on the network. | 16.8186 | Capex | Non-network general assets - Other | Non-network | 16.8186 | 0 | 0 | 0 | 0
|  | Rigid Hoppers | Cable with clamp at each end that is placed inside an insulating tube. | 1.9867 | Capex | Non-network general assets - Other | Non-network | 1.9867 | 0 | 0 | 0 | 0
|  | Line cut-out tools | Set of tools used to cut into a line, e.g., for temporary installation of mid-span isolators | 1.0617 | Capex | Non-network general assets - Other | Non-network | 1.0617 | 0 | 0 | 0 | 0
|  | New Line Hoses | New Line Hoses (to replace Hard Covers) on 22kV lines | 0.24807 | Opex | Non-network general assets - Other | Non-network | 0.24807 | 0 | 0 | 0 | 0

## Unit_Rates - $2015
Direct Cost Unit Rates - $000's, Real $2015 |  |  |  | Confidential
SOURCE: ASD - Attachment 22 - AST Contingent Project 3 Total Cost Model_CONFIDENTIAL (AER & AST amended)_19.09.19.xlsx
Zone Substation works Unit Rates
Primary Plant
Unit
| Category | Description | Rate ($k) | Classification | Asset Class | Expenditure Class | Materials | Contracts | Other
| Station service transformer (500 kVA) | Replace or install new station service transformer (500 kVA) |  | Capex | Subtransmission | Augmentation | 68.5061
| Station service transformer (750 kVA) | Replace or install new station service transformer (750 kVA) |  | Capex | Subtransmission | Augmentation | 106.4377
| Capacitance reducing isolation substation (7.5 MVA) | Install capacitance reducing isolation substation (7.5 MVA) |  | Capex | Subtransmission | Augmentation | 402.6337
| Capacitance reducing isolation substation (10 MVA) | Install capacitance reducing isolation substation (10 MVA) |  | Capex | Subtransmission | Augmentation | 358.3857
| AC changeover board - Station | Installation of outdoor changeover board |  | Capex | Subtransmission | Augmentation | 37.0694
| AC changeover board - REFCL | Installation of outdoor changeover board suitable for uprated Station Service Tx, incl. footing |  | Capex | Subtransmission | Augmentation | 40.541
| AC C/O board footing | AC C/O board footing |  | Capex | Subtransmission | Augmentation | 0
| Arc Suppression Coil | Installation of ASC |  | Capex | SCADA/Network control | Augmentation | 1092.6972
| ASC footing | Install new footing and associated bunding for GFN ASC unit |  | Capex | Subtransmission | Augmentation | 0
| 22kV switchboard - Metro | Installation of 22 kV switchboard - Metro |  | Capex | Subtransmission | Augmentation | 1277.3133
| 22kV switchboard - Rural | Installation of 22 kV switchboard - Rural |  | Capex | Subtransmission | Augmentation | 1378.3628
| 22kV switchboard (no building) - Rural | Installation of 22 kV switchboard only (no building) - Rural |  | Capex | Subtransmission | Augmentation | 660.354
| 22kV Capacitor Banks | Installation of 22 kV capacitor banks |  | Capex | Subtransmission | Augmentation | 119.8372
| 22kV Capacitor Bank (2x3 MVAr) - type 4 | Installation of 2x3 MVAr Capacitor Bank |  | Capex | Subtransmission | Augmentation | 439.3995
| 22kV Capacitor Bank (2x3 MVAr) - type 2 | Installation of 2x3 MVAr Capacitor Bank |  | Capex | Subtransmission | Augmentation | 383.76
| 22kV Capacitor Bank (4 x3 MVAr) - type 3 | Installation of 4x3 MVAr Capacitor Bank |  | Capex | Subtransmission | Augmentation | 647.661
| 22kV Capacitor Bank - Modify | Modify existing capacitor bank |  | Capex | Subtransmission | Augmentation | 86.1219
| Cap Bank footing | Cap Bank footing |  | Capex | Subtransmission | Augmentation | 0
| 22kV Dead Tank Circuit Breaker | 22kV Dead Tank Circuit Breaker 3150A, 40kA |  | Capex | Subtransmission | Augmentation | 100.9455
| 22kV U/S Isolator | 22kV Underslung Isolator |  | Capex | Subtransmission | Augmentation | 7.2299
| 22KV Feeder Exit | 22KV Feeder Exit |  | Capex | Subtransmission | Augmentation | 0
| 22kV Voltage Transformer | 22kV Voltage Transformer |  | Capex | Subtransmission | Augmentation | 0
| 22kV Current Transformer | 22kV Current Transformer |  | Capex | Subtransmission | Augmentation | 25.6246
| 22kV Zero Sequence CTs | Install core balance zero sequence current transformers |  | Capex | Subtransmission | Augmentation | 0
| 22KV Surge Arrestor | 22KV Surge Arrestor |  | Capex | Subtransmission | Augmentation | 0.58488
| Transformer Neutral Isolator | Transformer Neutral Isolator |  | Capex | Subtransmission | Augmentation | 24.7371
| Neutral Bus | Installation of neutral bus |  | Capex | Subtransmission | Augmentation | 88.5384
| REFCL control room | Installation of the REFCL control room only - no protection panels |  | Capex | Subtransmission | Augmentation | 0
| 2 REFCL control room | Installation of the REFCL control room only - no protection panels - supports 2 GFNs |  | Capex | Subtransmission | Augmentation | 0
| Battery Room (single battery set) | Installation of modular battery room including batteries (1 set of) |  | Capex | Subtransmission | Augmentation | 214.7377
| Battery Room (2 battery sets) | Installation of modular battery room including batteries (2 sets of) |  | Capex | Subtransmission | Augmentation | 164.6975
| New Control Building | Installation of modular control building room |  | Capex | Subtransmission | Augmentation | 348.1377
| Primary Cables - 22kV | Tx to Switchboard 22kV 630mm2 XLPE single phase (35mx6) |  | Capex | Subtransmission | Augmentation | 33.7163
| Primary Cables - 22kV | S/S to Switchboard 22kV 185mm2 XLPE single phase (30mx3) |  | Capex | Subtransmission | Augmentation | 10.421
| Primary Cables - 22kV | ASC to Neutral Bus 22kV 95mm2 XLPE single phase (15m) |  | Capex | Subtransmission | Augmentation | 1.775
| Feeder Exit Cables - 22kV | Feeder Exit Cables - 22kV 300mm (per metre) |  | Capex | Subtransmission | Augmentation | 0.047168
| Primary Cable Testing | Testing of station 22 kV Cables |  | Capex | Subtransmission | Augmentation | 0
| Oil separator | Installation of Oil separator / Puraceptor |  | Capex | Subtransmission | Augmentation | 123.9535
| One Tilt Slab control room | Installation of a tilt slab building |  | Capex | Subtransmission | Augmentation
Protection & Control
Unit
| Category | Description | Rate ($k) | Classification | Asset Class | Expenditure Class | Materials | Contracts | Other
| Neutral Bus controller - 1 GFN | Installation of neutral bus controller |  | Capex | SCADA/Network control | Augmentation | 46.2081
| Neutral Bus controller - 2 GFNs | Installation of neutral bus controller |  | Capex | SCADA/Network control | Augmentation | 58.3179
| Protection – GFN panels | Interface, control panel and inverter |  | Capex | SCADA/Network control | Augmentation | 5.8895
| GFN interface relay | GFN interface relay |  | Capex | SCADA/Network control | Augmentation | 8.2031
| Power Quality/Switchgear Interface | Installation of Panel with 2 Power Quality Meters & 1 Switchgear interface relay |  | Capex | SCADA/Network control | Augmentation | 92.4568
| Power Quality Non Std | Installation of Panel with 6 Power Quality Meters |  | Capex | SCADA/Network control | Augmentation | 186.4607
| Switchgear Interface Non Std | Installation of Panel with 3 switchgear interface relays |  | Capex | SCADA/Network control | Augmentation | 154.7339
| Capacitor Bank Prot & Cntl (3x3MVAr) | Installation of Panel for Prot & Cntl of 3 x 3MVAr Capacitor Bank |  | Capex | SCADA/Network control | Augmentation | 39.5892
| Capacitor Bank Prot & Cntl (2x3MVAr) | Installation of Panel for Prot & Cntl of 2 x 3MVAr Capacitor Bank |  | Capex | SCADA/Network control | Augmentation | 31.7758
| Remote Terminal Unit | Install new RTU (existing MD1000 incapable of handling traffic of new relays) |  | Capex | SCADA/Network control | Augmentation | 140.8816
| SCIMS system - small | Install a new Substation Automation panel (SCIMS) in existing control room |  | Capex | SCADA/Network control | Augmentation | 87.0154
Network Balancing Unit Rates
|  |  | Unit | [5 empty] | Contracts - Design | Contracts - Construct
| Category | Description | Rate ($k) | Classification | Asset Class | Expenditure Class | Materials | Labour |  |  | Other
| Design | Design activities to determine network balancing requirements, validate balancing and record balancing information – per feeder | 23.5834 | Capex | Distribution system assets | Augmentation | 0 | 2.008 | 3.6591 | 0 | 0 | WYK2 rate
[5 empty] | Distribution system assets | Augmentation | 0 | 7.8091 | 18.1319 | 0 | 0 | Other stations rate
| Third conductor installation | Install 3rd conductor – per span |  | Capex | Distribution system assets | Augmentation
| Unbonding cable | Unbounding cable at either end – per location |  | Capex | Distribution system assets | Augmentation
| Phase rotation | Rotate phases – per rotation |  | Capex | Distribution system assets | Augmentation
| Balancing capacitors | Install balancing capacitors (single or three phase) – per installation | 54.3234 | Capex | Distribution system assets | Augmentation | 17.1066 | 3.1829 | 0 | 30.2038 | 3.8301
| Inherent works | Activities including the development of balancing capacitor solution, modification of Asset Management Systems - per feeder | 13.8451 | Capex | Distribution system assets | Augmentation | 0 | 6.0629 | 0 | 7.7821 | 0 |  | Inherent works - various feeder based works
|  | Phase plate correction - per feeder and RC sections | 0.5206 | Capex | Distribution system assets | Replacement | 0 | 0 | 0 | 0.5206 | 0 |  | Phase plate correction
|  | Protection reviews for fuse removals and installation of solid link - per fuse | 3.0703 | Capex | Distribution system assets | Replacement | 0 | 0.1496 | 0 | 2.9207 | 0 |  | Fuse removal and install solid link
|  | Installation of fusesaver and remote control unit - per site | 36.2252 | Capex | Distribution system assets | Augmentation | 11.7252 | 3 | 1.5 | 20 | 0 |  | Install fusesaver and control box - per site
|  | Install new ACR for switching | 62.7168 | Capex | Distribution system assets | Augmentation | 21.3237 | 6.8988 | 4.3902 | 23.8324 | 6.2717 |  | Install new ACR for switching
|  | Purchase of phase identification tools - G3 Phase ID probe | 12.3507 | Capex | Non-network general assets - Other | Non-network | 12.3507 | 0 | 0 | 0 | 0
|  | - Base station | 8.3465 | Capex | Non-network general assets - Other | Non-network | 8.3465 | 0 | 0 | 0 | 0
Line Hardening Unit Rates
|  |  | Unit | [5 empty] | Contracts - Design | Contracts - Construct
| Category | Description | Rate ($k) | Classification | Asset Class | Expenditure Class | Materials | Labour |  |  | Other
| Surge arrestor | Replace surge arrestor on existing structure - per site | 2.4398 | Capex | Distribution system assets | Replacement | 0.71413 | 0.35752 | 0 | 1.3682 | 0
|  | - per unit | 1.2199 | Capex | Distribution system assets | Replacement | 0.35707 | 0.17876 | 0 | 0.6841 | 0
| Cables | Cable On-Line Testing | 0.29448 | Capex | Distribution system assets | Replacement | 0 | 0.29448 | 0 | 0 | 0
|  | Cable Off-Line Testing | 9.8158 | Capex | Distribution system assets | Replacement | 0 | 9.8158 | 0 | 0 | 0
|  | Cable - Replace Fitting | 20.8587 | Capex | Distribution system assets | Replacement | 4.9079 | 0 | 0 | 15.9507 | 0
|  | Cable - Replace Cable Section - per m | 0.50583 | Capex | Distribution system assets | Replacement | 0.047168 | 0 | 0 | 0.45867 | 0 | $550 per m
| Other | CERA Removal and Replacement with 900kVAr Pole Top Capacitor | 65.7661 | Capex | Distribution system assets | Augmentation | 29.4475 | 0 | 0 | 36.3186 | 0
Compatible Equipment Unit Rates
|  |  | Unit | [5 empty] | Contracts - Design | Contracts - Construct
| Category | Description | Rate ($k) | Classification | Asset Class | Expenditure Class | Materials | Labour |  |  | Other
| ACR upgrade | Replace control box on ACR | 50.9982 | Capex | Distribution system assets | Replacement | 14.1504 | 2.2999 | 4.4032 | 30.1446 | 0
| ACR replacement | Replace pole-mounted ACR | 62.7168 | Capex | Distribution system assets | Replacement | 21.3237 | 6.8988 | 4.3902 | 23.8324 | 6.2717
| Voltage regulator upgrade | Replace control box on voltage regulator | 46.5825 | Capex | Distribution system assets | Replacement | 14.2976 | 21.813 | 0 | 10.4719 | 0
| Voltage regulator replacement | Replace voltage regulator | 337.0942 | Capex | Distribution system assets | Replacement | 182.2864 | 33.8325 | 0 | 120.9753 | 0
Code Compliance Unit Rates
|  |  | Unit | [5 empty] | Contracts - Design | Contracts - Construct
| Category | Description | Rate ($k) | Classification | Asset Class | Expenditure Class | Materials | Labour |  |  | Other
| Code compliance | Install isolating transformer and associated equipment adjacent to high-voltage customer – per site, 3.0 MVA substation | 0 | Capex | Distribution system assets | Augmentation | [5 empty] | not applicable
|  | 5 MVA substation | 0 | Capex | Distribution system assets | Augmentation | [5 empty] | not applicable
|  | 7.5 MVA substation | 0 | Capex | Distribution system assets | Augmentation | [5 empty] | not applicable
|  | ACR | 89.4244 | Capex | Distribution system assets | Replacement | 30.8859 | 9.738 | 6.21 | 33.5338 | 9.0568 |  | Line Hardening
Reliability maintained Unit Rates
|  |  | Unit | [5 empty] | Contracts - Design | Contracts - Construct
| Category | Description | Rate ($k) | Classification | Asset Class | Expenditure Class | Materials | Labour |  |  | Other
| Remote control switch | Replace remote controlled switch on existing structure - Design |  | Capex | Distribution system assets | Replacement
|  | - DFA2 software changes to SCADA |  | Capex | SCADA/Network control | Replacement
|  | - Materials supply and deployment of switches |  | Capex | Distribution system assets | Replacement
Live Line Equipment Purchases Unit Rates
|  |  | Unit | [5 empty] | Contracts - Design | Contracts - Construct
| Category | Description | Rate ($k) | Classification | Asset Class | Expenditure Class | Materials | Labour |  |  | Other
| Mid-span Isolator units | Devices used to reduce the outage area in the distribution network. Set of isolators that are cut into a line between two poles (i.e., mid-span) to provide a temporary break in connection. After an outage devices can be re-used elswhere on the network. | 15.866 | Capex | Non-network general assets - Other | Non-network | 15.866 | 0 | 0 | 0 | 0
| Rigid Hoppers | Cable with clamp at each end that is placed inside an insulating tube. | 1.8742 | Capex | Non-network general assets - Other | Non-network | 1.8742 | 0 | 0 | 0 | 0
| Line cut-out tools | Set of tools used to cut into a line, e.g., for temporary installation of mid-span isolators | 1.0015 | Capex | Non-network general assets - Other | Non-network | 1.0015 | 0 | 0 | 0 | 0
| New Line Hoses | New Line Hoses (to replace Hard Covers) on 22kV lines | 0.23402 | Opex | Non-network general assets - Other | Non-network | 0.23402 | 0 | 0 | 0 | 0

## Escalators
Escalators
SOURCE: ASD - Attachment 22 - AST Contingent Project 3 Total Cost Model_CONFIDENTIAL (AER & AST amended)_19.09.19.xlsx
CPI | Sep Qtr | Jun Qtr | Jun Qtr | Jun Qtr | Jun Qtr | Forecast | Forecast | Forecast | Forecast | Forecast | Forecast
| 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 | 2022 | 2023 | 2024 | 2025
Actual Inflation - 8 cities, 1 year lagged (Jun to Jun) | 2.308% | 1.511% | 1.023% | 1.934% | 2.078% | 2.25% | 2.45% | 2.45% | 2.45% | 2.45% | 2.45%
Decision Inflation (Amended) |  | 2.349% | 2.349% | 2.349% | 2.349% | 2.349% | 2.349% | 2.349% | 2.349% | 2.349% | 2.349%
Index - $2014 to Nominal (using outturn inflation) | 1.0231 | 1.0385 | 1.0492 | 1.0694 | 1.0917
Index - $2015 to nominal (using outturn inflation) | 1 | 1.0151 | 1.0255 | 1.0453 | 1.067
Index - $2015 to nominal (using Decision inflation) | 1 | 1.0235 | 1.0475 | 1.0722 | 1.0973 | 1.1231 | 1.1495 | 1.1765 | 1.2042 | 1.2325 | 1.2614
Index - $2016 to nominal (using Decision inflation) |  | 1 | 1.0235 | 1.0475 | 1.0722 | 1.0973 | 1.1231 | 1.1495 | 1.1765 | 1.2042 | 1.2325
Conversion factor - Mid Year $Nominal to End $2015 | 1.0066 | 0.99163 | 0.98158 | 0.96296 | 0.94336
(8 cities, 1 year lagged)
Actual Wage Price Growth
2015
EGWWS WPI (Vic) real rate of change | 1.897%
Construction WPI (Aus) real rate of change | 0.2341%
(source: ABS WPI industry data adjusted for actual inflation)
Forecast Wage Price Growth
Real escalation value (%)
Cost Drivers |  | 2016 | 2017 | 2018 | 2019 | 2020
Labour escalators
Electricity Gas Water and Waste Services Wage Price Index (Internal labour) |  | 0.4 | 0.37 | 0.79 | 0.96 | 1.02
Construction Wage Price Index (External labour) |  | 0.36 | 0.39 | 0.97 | 1.09 | 1.16
(source: AER information request #049 - AusNet Services - Real escalation input cost indices, 8th March 2016)
Labour index for Capital costs
| 2015 | 2016 | 2017 | 2018 | 2019 | 2020
Internal labour index (applied to labour costs in $2015) | 1 | 1.004 | 1.0077 | 1.0157 | 1.0254 | 1.0359
External labour index (applied to labour costs in $2015) | 1 | 1.0036 | 1.0075 | 1.0173 | 1.0284 | 1.0403
Labour index for Operating & Maintenance costs
| 2015 | 2016 | 2017 | 2018 | 2019 | 2020
WPI - EGWWS (Vic) | 1.897% | 0.4014% | 0.3716% | 0.785% | 0.9574% | 1.019%
Labour index (applied to labour costs in $2015) | 1 | 1.004 | 1.0077 | 1.0157 | 1.0254 | 1.0358
Labour / Non Labour splits |  | 2016 | 2017 | 2018 | 2019 | 2020
Labour |  | 0.62 | 0.62 | 0.62 | 0.62 | 0.62
Non Labour |  | 0.38 | 0.38 | 0.38 | 0.38 | 0.38
(source: EDPR Final Decision Opex model - rate of change)
Thousands | 1000

## Lab_Rates
Internal Labour rates
Labour rates effective from 22-01-2014 (source: Expert Estimator tool) | $/hr | Notes
Operational Staff Labour Rate (Tester/Controller/Operator/Applicant, etc) | 125
Engineering & Professional Services Labour Rate | 152
Asset Management Engineer | 142
Project Manager | 165
Front Line Leader | 215
Site Manager Build | 152
Regulation & Network Strategy team | 152
Legal team | 152

## Rpt_Cat
RAB / Asset Class |  | Benchmark Expenditure Categories | Cost Classification
Subtransmission |  | Replacement | Capex
Distribution system assets |  | Connections | Opex
SCADA/Network control |  | Augmentation
Non-network general assets - IT |  | Non-network
Non-network general assets - Other |  | Capitalised network overheads
Land |  | Capitalised corporate overheads
Cap Cons
Station / REFCL no | Short Nm
spare | <Spare>
Two remote REFCLs, one on WOTS11 and one on WOTS25. Also, installation of three 300kVA isolation transformers on WOTS25. | WOTS
Installation of isolation transformers at 12 proposed locations & BDL feeder swap | BDL
Installation of three 7.5MVA isolation transformers at the proposed locations | ELM
Install additional GFN | RWN
Upsize ASC | KMS
Installation of 300kVA isolation transformers at 5 proposed locations | WGI
Revised solution - Bus 1 - Install remote REFCL on BGE13 and transfer 5A of capacitive current from BGE13 to FGY. Bus 2 - Install 4 pole-top isolation transformers on BGE22. | BGE
Isolating transformer and UG works | LDL