## SUMMARY Staged Funding
| PROJECT COST SUMMARY | UNCERTAINTY ADJUSTED ESTIMATE
| Project Number: | TD-0003546
| Project Title: | TD-0003546 – SVC Replacement Project
| Estimate Type: | Planning
| Revision: | Draft Rev A
| Issued Date: | 2019-10-16
Summary Staged Funding
| PROJECT EXPENDITURE FORECASTS | IDEA | PLAN | BUILD | CLOSE | TOTAL
1 | DESIGN | 0 | 1970888.4239 | 492722.106 | 0 | 2463610.5299
2 | INTERNAL LABOUR | 0 | 754480.7248 | 1293395.5282 | 107782.9607 | 2155659.2136
3 | MATERIALS | 0 | 0 | 17861176.3416 | 0 | 17861176.3416
4 | PLANT & EQUIPMENT | 0 | 0 | 923853.9487 | 0 | 923853.9487
5 | CONTRACTS | 0 | 0 | 13857809.2306 | 0 | 13857809.2306
6 | METER COSTS | 0 | 0 | 0 | 0 | 0
7 | OTHER - RISK ALLOWANCE | 0 | 0 | 2794658.1948 | 0 | 2794658.1948
8 | PROJECT DIRECT EXPENDITURE P(50) | 0 | 2725369.1487 | 37223615.3499 | 107782.9607 | 40056767.4593
9 | DELIVERY RISK ADJUSTMENT [P(90)-P(50)] |  |  |  |  | 0
10 | PROJECT DIRECT EXPENDITURE PLUS RISK P(90) | 0 | 2725369.1487 | 37223615.3499 | 107782.9607 | 40056767.4593
11 | OVERHEADS | 0 | 258910.0691 | 3536243.4582 | 10239.3813 | 3805392.9086
12 | FINANCE CHARGES (IDC) | 0 | 937766.9626 | 352030.9279 | 0 | 1289797.8905
13 | OPERATING EXPENDITURE | 0 | 0 | 0 | 0 | 0
14 | WRITTEN DOWN VALUES | 0 | 0 | 0 | 0 | 0
15 | TOTAL EXPENDITURE FOR APPROVAL | 0 | 3922046.1804 | 41111889.7361 | 118022.3419 | 45151958.2584