## Sheet4
RINs Schedule 1 - 4.2.b. Basis for top-down capex adjustment
Project ID | Title | Project Comp Date Schedule | P50 ('000) | Sum of Current P50+CFC | Actual ('000) | Difference | %
X465 | X465 - Stage 4 - Environmental Improvements | 2013-11-01 | 5600 | 0 | 3544.41 | 2055.59 | 36.71%
X497 | X497 - Redevelopment of BETS | 2014-04-10 | 13713 | 15709.5 | 14700.63 | -987.63 | -7.202%
X508 | X508 - Development of the A to P for redevelopment of GTS | 2013-01-07 | 18218 | 0 | 20669.68 | -2451.68 | -13.46%
X549 | X549 - Purchase Infrared Cameras | 2012-05-17 | 42 | 0 | 37.92 | 4.08 | 9.714%
X558 | X558 - Purchase of Hathaway BCM200 CB Monitor | 2013-08-07 | 4.4 | 0 | 4.82 | -0.42 | -9.545%
X625 | X625 - Modifications to controls of 2-3 220kV Bus Tie CB | 2013-10-21 | 74 | 0 | 66.87 | 7.13 | 9.635%
X668 | X668 - Replacement of Worn Out 16mm diameter pin Insulators and Hardware on Road Crossings | 2007-11-23 | 1925 | 1220.79 | 995.37 | 929.63 | 48.29%
X706 | X706 - Rebuild of 220 / 66 kV Keilor Terminal Station | 2013-06-06 | 26305 | 0 | 31481.71 | -5176.71 | -19.68%
X709 | X709 - SYTS By- Pass on MLTS Lines 1 & 2 - Secondary & Comms work - Upgrade - following installation of new Digital Distance Relays | 2013-08-23 | 60 | 0 | 73.33 | -13.33 | -22.22%
X710 | X710 - Replacement of Toshiba CBF Relays at LYPS and HWTS | 2013-10-21 | 154 | 0 | 160.85 | -6.85 | -4.448%
X711 | X711 - Redevelopment of HWPS 220kV Switchyard, Stage 1 | 2013-07-12 | 5647 | 0 | 6280.13 | -633.13 | -11.21%
X724 | X724 - Replacement of No.1 Shunt Reactor at HOTS | 2013-10-29 | 336.4 | 0 | 495.04 | -158.64 | -47.16%
X768 | X768 - Security CBTS | 2012-05-18 | 747.7 | 0 | 684.39 | 63.31 | 8.467%
X773 | X773 - Electric Fence Upgrade at MWTS | 2013-08-23 | 723 | 0 | 781.49 | -58.49 | -8.09%
X785 | X785 - TTS Rebuild | 2013-07-30 | 32558 | 0 | 47753.56 | -15195.56 | -46.67%
X792 | X792 - Development of Protection & Control design standards | 2012-05-17 | 300 | 0 | 207.45 | 92.55 | 30.85%
X7A0 | X7A0 - Replacement of Shunt Reactor Radiators (242 kV) at MLTS | 2013-10-29 | 210.4 | 0 | 178.72 | 31.68 | 15.06%
X7B2 | X7B2 - Ladders and Screens Stage 4 - 330kv tower safe access | 2009-09-03 | 6457 | 6962.54 | 4317.28 | 2139.72 | 33.14%
X7B4 | X7B4 - Install 50V Dc earth monitoring | 2013-10-21 | 90 | 0 | 48.24 | 41.76 | 46.4%
X7C5 | X7C5 - Install Isolation of Telstra Services at Richmond and ROCC | 2013-03-08 | 199.75 | 0 | 217.78 | -18.03 | -9.026%
X7E4 | X7E4 - Install and commission digital communications MLTS, HYTS, APD and TGTS via OPGW and Radio (5 hops). | 2013-10-21 | 23882.56 | 0 | 22136.88 | 1745.68 | 7.309%
X7E5 | X7E5 - Install and commission digital communications SYTS, SMTS, via OPGW. | 2013-10-21 | 2209.3 | 0 | 1805.42 | 403.88 | 18.28%
X7E9 | X7E9 - KTS 500 kV CT & CB | 2013-08-20 | 8889.7 | 0 | 7051.58 | 1838.12 | 20.68%
X7G1 | X7G1 - DC Supply Upgrade at HYTS | 2012-01-13 | 185.9 | 0 | 159.38 | 26.52 | 14.27%
X7G3 | X7G3 - Replacement of Surge Arresters at Various Terminal Stations | 2012-03-22 | 1763 | 0 | 1892.72 | -129.72 | -7.358%
X7G5 | X7G5 - Insulator Replacement Program - 08-09 to 13-14 | 2008-10-29 | 13023.6 | 13765.38 | 10579.17 | 2444.43 | 18.77%
X7H1 | X7H1 - Comms Battery duplication at ROCC | 2013-08-23 | 363.7 | 0 | 444.86 | -81.16 | -22.32%
X7H4 | X7H4 - Upgrade protection signalling DDTS - MSS & WOTS - Jindera & add DEF to DDTS - MSS | 2013-07-08 | 265 | 0 | 336.96 | -71.96 | -27.15%
X7H7 | X7H7 - LV COMMS REPLACEMENT OF PDH WITH SDH | 2014-12-31 | 745 | 770.3 | 768.29 | -23.29 | -3.126%
X801 | X801 - LADDERS AND SCREENS STAGE 3 (66KV SAFE TOWER ACCESS) | 2014-01-03 | 11208 | 11345.21 | 6102.65 | 5105.35 | 45.55%
X803 | X803 - Battery Replacements at Various Sites | 2014-07-22 | 512.23 | 525.66 | 520.54 | -8.31 | -1.622%
X811 | X811 - CT Replacement Program - Stage 5 | 2012-09-17 | 6333.66 | 0 | 7991.37 | -1657.71 | -26.17%
X824 | X824 - Establishment of Protection & Control Scheme Modules for Training, Testing, Investigations & Contingency Management | 2013-10-30 | 450 | 0 | 457.69 | -7.69 | -1.709%
X825 | X825 - Install OPGW TTS - KTS | 2013-09-12 | 1787.2 | 0 | 1654.49 | 132.71 | 7.426%
X828 | X828 - Replacement of Corroded steel groundwire & fittings along freeways and major road crossings | 2013-04-15 | 1006 | 0 | 1804.22 | -798.22 | -79.35%
X832 | X832 - Installation of dampers on YPS lines | 2010-07-19 | 293 | 298.28 | 237.96 | 55.04 | 18.78%
X833 | X833 - Replacement of concrete ploes on Yallourn Power Station | 2009-04-15 | 166 | 169.42 | 151.55 | 14.45 | 8.705%
X837 | X837 - Laser Mapping of Existing Lines, Stage 1 | 2013-03-05 | 740 | 0 | 464.63 | 275.37 | 37.21%
X846 | X846 - Replace ATS - BLTS Radio Links | 2011-09-01 | 329.4 | 0 | 309.58 | 19.82 | 6.017%
X849 | X849 - Replace Jeeralang Hill - Relay House A Radio Links | 2013-08-23 | 199 | 0 | 233.07 | -34.07 | -17.12%
X850 | X850 - Replace Jeeralang Hill - HWTS radio links | 2013-08-23 | 199 | 0 | 189.63 | 9.37 | 4.709%
X851 | X851 - Replace KTS - Mt Macedon Radio Links | 2015-03-31 | 266 | 276 | 191.37 | 74.63 | 28.06%
X854 | X854 - Replace Mt Macedon - One Tree Hill Radio Links | 2013-08-05 | 266 | 276 | 174.71 | 91.29 | 34.32%
X858 | X858 - Replace SYTS - Mt Blackwood Radio Links | 2014-12-01 | 266 | 276 | 202.11 | 63.89 | 24.02%
X859 | X859 - Replace YPS - Jeeralang Hill Radio Links | 2013-08-23 | 191 | 0 | 169.51 | 21.49 | 11.25%
X860 | X860 - Replacement of PDH with SDH at SVTS and HTS | 2012-10-16 | 170 | 0 | 195.71 | -25.71 | -15.12%
X861 | X861 - Communications Infrastructure Replacement at 20 Terminal Stations - MDF Interface and Cabling | 2014-09-30 | 752 | 832 | 827.33 | -75.33 | -10.02%
X864 | X864 - Install OPGW HWTS-LYPS | 2014-05-26 | 1781 | 1938.71 | 1870.78 | -89.78 | -5.041%
X876 | X876 - Replace security fence at GTS | 2013-09-05 | 579 | 0 | 640.1 | -61.1 | -10.55%
X877 | X877 - Replace security fence at MTS | 2013-08-23 | 425 | 0 | 464.64 | -39.64 | -9.327%
X879 | X879 - Upgrade Microsol RTU to CPR41 | 2013-03-04 | 206.6 | 0 | 207.6 | -1 | -0.484%
X884 | X884 - Update the ADG Serial Server Standard | 2009-07-27 | 90 | 90 | 65.95 | 24.05 | 26.72%
X892 | X892 - HYTS - APD Ground Wire Replacement | 2012-07-13 | 750 | 0 | 732.54 | 17.46 | 2.328%
X894 | X894 - Fence Upgrade at YPS JLTS LYPS LY | 2009-03-30 | 1092 | 1113.5 | 1164.89 | -72.89 | -6.675%
X895 | X895 - Fence Upgrade at RCTS TBTS TSTS BATS | 2009-03-30 | 1666.7 | 1712.67 | 659.13 | 1007.57 | 60.45%
X896 | X896 - Install CB fail remote trips between YPS HWPS and ROTS. | 2013-01-29 | 92 | 0 | 83.03 | 8.97 | 9.75%
X8A4 | X8A4 - PAPL replacement | 2013-02-18 | 206 | 0 | 205.78 | 0.22 | 0.1068%
X8B7 | X8B7 - EHV Protection Replacement | 2009-03-30 | 1900 | 2021.19 | 1979.36 | -79.36 | -4.177%
X8B8 | X8B8 - Bay Control and Instrumentation Upgrades | 2009-11-24 | 360 | 650 | 523.69 | -163.69 | -45.47%
X907 | X907 - Tyree CVT Replacement program | 2011-05-03 | 1231 | 0 | 1143.01 | 87.99 | 7.148%
X918 | X918 - HWPS - Replace Bus protection | 2010-03-31 | 184 | 467 | 467.63 | -283.63 | -154.1%
X923 | X923 - Repair of the Failed ex TTS B1 Transformer | 2014-05-15 | 3957 | 3935 | 3525.33 | 431.67 | 10.91%
X931 | X931 - Fire suppression for the Mary Street cable riser | 2013-02-11 | 186 | 0 | 225.26 | -39.26 | -21.11%
X933 | X933 - Install fall arrest system on Radio communications Poles | 2013-09-12 | 144 | 0 | 134.28 | 9.72 | 6.75%
X936 | X936 - FBTS - Replace Sub MG FDR CT's - High Acetylene | 2012-09-05 | 90 | 0 | 96.75 | -6.75 | -7.5%
X937 | X937 - Implementation of Corporate GIS for Communications Network - Stage 1 | 2013-08-23 | 628 | 0 | 662.86 | -34.86 | -5.551%
X941 | X941 - HYTS & APD 2L Protection Replacement | 2013-08-01 | 1145 | 0 | 1528.83 | -383.83 | -33.52%
X943 | X943 - ACD Gates Installation on EHV Towers | 2010-11-19 | 1225 | 1289.15 | 572.64 | 652.36 | 53.25%
X945 | X945 - Transformer Misting of 220/66kV Transformers | 2013-10-10 | 45 | 0 | 34.86 | 10.14 | 22.53%
X946 | X946 - WMTS 250 V Battery Duplication | 2014-03-31 | 280 | 289.27 | 265.47 | 14.53 | 5.189%
X947 | X947 - HTS MicroSCADA Remedial Action | 2014-12-31 | 530 | 1240 | 1093.2 | -563.2 | -106.3%
XA01 | XA01 - BETS-KGTS tower replacement | 2011-01-17 | 3332 | 3439.06 | 1728.42 | 1603.58 | 48.13%
XA02 | XA02 - Stage II - Replacement of Switchbays at HOTS | 2013-06-25 | 6745 | 0 | 7002.59 | -257.59 | -3.819%
XA03 | XA03 - DDTS 220 Switchyard Refurbishment | 2013-06-25 | 9332 | 0 | 8494.74 | 837.26 | 8.972%
XA04 | XA04 - Replacement of surge arresters at various stations | 2013-08-06 | 762.3 | 0 | 630.82 | 131.48 | 17.25%
XA05 | XA05 - Install Misting Units at Transformers at KTS, WMTS & RTS | 2013-10-10 | 55 | 0 | 41.66 | 13.34 | 24.25%
XA06 | XA06 - Replacement of Country Spare 230 KV 150 MVA Transformer | 2013-07-22 | 3920 | 0 | 3273.12 | 646.88 | 16.5%
XA07 | XA07 - VAT Timer Replacements at Various Stations | 2013-07-08 | 777 | 0 | 220.96 | 556.04 | 71.56%
XA10 | XA10 - Power System Quality Monitor Stage 1 | 2013-07-11 | 148 | 0 | 92.77 | 55.23 | 37.32%
XA17 | XA17 - New pad for storage of Ex TTS B3 Asea Transformer | 2013-07-22 | 249 | 0 | 219.5 | 29.5 | 11.85%
XA18 | XA18 - Retrofitting of Earth Switch at TGTS | 2012-06-21 | 254 | 0 | 257.76 | -3.76 | -1.48%
XA20 | XA20 - Replacement of Y Bias Diff Protection for 220kV Reactor No.1 at MLTS | 2013-08-29 | 19 | 0 | 4.22 | 14.78 | 77.79%
XA22 | XA22 - YPS-YWPS OPGW installation | 2013-08-23 | 820 | 0 | 851.22 | -31.22 | -3.807%
XA32 | XA32 - Removal of Asbestos and replacement of floor at TSTS | 2013-04-17 | 110 | 0 | 147.04 | -37.04 | -33.67%
XA33 | XA33 - EPSY LV AC standby supply | 2012-04-30 | 137.8 | 0 | 165.13 | -27.33 | -19.83%
XA35 | XA35 - Fire Hydrant Replacement in North | 2011-08-25 | 1206 | 1230.77 | 1197.23 | 8.77 | 0.7272%
XA40 | XA40 - Upgrade protection on JLTS - MWTS Lines | 2013-06-24 | 1421 | 0 | 997.41 | 423.59 | 29.81%
XA46 | XA46 - CBTS Replace e-Terra Control system | 2013-07-11 | 522 | 0 | 392.8 | 129.2 | 24.75%
XA55 | XA55 - CT Replacements Stage 6 - inc CVT Replacements | 2015-02-09 | 2464 | 3465 | 3063.38 | -599.38 | -24.33%
XA57 | XA57 - HTS Security Fence Upgrade | 2012-03-20 | 728 | 0 | 528.6 | 199.4 | 27.39%
XA62 | XA62 - MLTS Modify A2 Transformer Tripping | 2012-05-31 | 49 | 0 | 9.64 | 39.36 | 80.33%
XA64 | XA64 - Asea 150MVA Transformer Cooling Improvements | 2012-06-05 | 1231 | 0 | 738.85 | 492.15 | 39.98%
XA68 | XA68 - Tower replacement T464 RWTS-TTS and T464 TSTS-TTS | 2011-09-20 | 1569 | 2178 | 1072.08 | 496.92 | 31.67%
XA77 | XA77 - Replace GNTS - Taminick Radio Links | 2014-12-31 | 266 | 276 | 181.56 | 84.44 | 31.74%
XA78 | XA78 - Replace SHTS - Mt Major Radio Links | 2014-12-01 | 266 | 276 | 188.77 | 77.23 | 29.03%
XA81 | XA81 - MWTS Protection Upgrade | 2015-01-28 | 118 | 207 | 189.78 | -71.78 | -60.83%
XA82 | XA82 - LY Protection Upgrade | 2014-11-21 | 587 | 732 | 591.46 | -4.46 | -0.7598%
XB05 | XB05 - Electrical bonding of out of service (OOS) 66kV subsidiary circuits to EHV towers | 2012-12-06 | 452 | 0 | 425.6 | 26.4 | 5.841%
XB09 | XB09 - Station facilites upgrade/replacement | 2013-09-03 | 344 | 0 | 200.85 | 143.15 | 41.61%
XB14 | XB14 - Review ROTS 415 V AC Supplies Protection Grading | 2013-04-16 | 46 | 0 | 20.27 | 25.73 | 55.93%
XB21 | XB21 - Replacement of 12 towers on BETS-KGTS 220 kV line | 2013-09-04 | 7347 | 0 | 5423.65 | 1923.35 | 26.18%
XB22 | XB22 - Electrical bonding of earth wires on 500kV towers | 2013-10-31 | 2226 | 0 | 1501.49 | 724.51 | 32.55%
XB33 | XB33 - Installation of Directional Earth Fault Functionality for 220kV MBTS-DDTS and MBTS-EPS Lines | 2013-10-30 | 327 | 0 | 337.98 | -10.98 | -3.358%
XB34 | XB34 - Repair of KTS 500/220/22 kV Auto transformer English Electric Serial No AFV1719/800 [ex A2 White phase] | 2013-03-14 | 2222 | 0 | 2237.64 | -15.64 | -0.7039%
XB35 | XB35 - Fire Hydrant Replacements in Central | 2014-11-14 | 1517 | 1577.46 | 1603.88 | -86.88 | -5.727%
XB39 | XB39 - Provide Standby VT supply to X and Y Prot of 66kV LV1 and HCP feeders at ATS | 2013-07-17 | 45.5 | 0 | 38.95 | 6.55 | 14.4%
XB42 | XB42 - Sync Con refurb - Ladders-Landings and Handrails | 2014-10-14 | 305 | 652.34 | 625.83 | -320.83 | -105.2%
XB45 | XB45 - Sync Con refurb - On-Line Condition Monitoring Equipment | 2014-09-05 | 777 | 811 | 725.2 | 51.8 | 6.667%
XB46 | XB46 - Sync Con refurb - Fire Deluge System | 2014-07-01 | 512 | 538 | 450.9 | 61.1 | 11.93%
XB47 | XB47 - Sync Con refurb - OH and S issues | 2014-10-31 | 100 | 105 | 100.76 | -0.76 | -0.76%
XB58 | XB58 - Upgrade of FIP at HYTS | 2013-04-29 | 37.2 | 0 | 27.78 | 9.42 | 25.32%
XB60 | XB60 - Upgrade RWN1 & 266kV Protection at Ringwood Terminal Station | 2013-06-17 | 432 | 0 | 390.31 | 41.69 | 9.65%
XB62 | XB62 - Replace protection BLTS FBTS and TSTS Syn Conds | 2014-12-04 | 2197 | 3202 | 3141.08 | -944.08 | -42.97%
XB63 | XB63 - Flinders Street Comms Battery Replacement | 2013-08-23 | 56 | 0 | 57.82 | -1.82 | -3.25%
XC02 | XC02 - Replace-Install retainer walls-hand rails at BETS and DDTS | 2014-05-27 | 1342 | 1276.81 | 1044.09 | 297.91 | 22.2%
XC06 | XC06 - Replace Ageing Non-Compliant Current Check Relays | 2013-03-22 | 93.36 | 93.36 | 89.13 | 4.23 | 4.531%
XC55 | XC55 - Replace air conditioning units at YPS and HWTS | 2013-04-29 | 67.5 | 0 | 58.37 | 9.13 | 13.53%
XC75 | XC75 - Upgrade access security systems at HTS, RWTS, and TSTS | 2013-11-01 | 147 | 0 | 131.35 | 15.65 | 10.65%
XCA3 | XCA3 - Replace ADSS RWTS-BRA (917) | 2014-12-31 | 523 | 427.95 | 363.21 | 159.79 | 30.55%
XCA7 | XCA7 - Install fibre cable C452-WMTS | 2014-12-01 | 184 | 185.72 | 181.04 | 2.96 | 1.609%
XCCM | XCCM - Replacement of main gate at HWTS depot | 2013-05-06 | 89 | 0 | 82.19 | 6.81 | 7.652%
XCCQ | XCCQ - Lantronix Serial Server Replacement - EPSY and KTS | 2014-04-01 | 109 | 110.51 | 104.39 | 4.61 | 4.229%
XD01 | XD01 - Cross arms and insulator replacement for Sync Condensor at Templestowe terminal station | 2013-11-15 | 277 | 158.65 | 104.98 | 172.02 | 62.1%
XD02 | XD02 - Replacement of Red Phase 66kV No 1 Capacitor Bank Series Reactor at SVTS | 2014-09-30 | 81 | 80.8 | 73.73 | 7.27 | 8.975%
X344 | NEM Metering upgrade - Stage 3 - Various Locations | 2009-07-31 | 1844 |  | 1742 | 102 | 5.531%
X376 | WMTS - Modify SF6 De-energisation Controls - was V223 | 2011-04-04 | 37.5 |  | 23 | 14.5 | 38.67%
X456 | Partial Discharge Sensors for SMTS GIS | 2010-02-26 | 253.3 |  | 240 | 13.3 | 5.251%
X491 | SCIMS Work Scope Additions at Various Sites | 2011-09-20 | 1003.7 |  | 1221 | -217.3 | -21.65%
X523 | Laser Survey fo Transmision Lines 2005 | 2010-04-01 | 412 |  | 354 | 58 | 14.08%
X569 | OPGW WOTS-T401 JSS Line & DDTS-MSS | 2009-06-02 | 4245 |  | 5061 | -816 | -19.22%
X657 | Early Storm Response | 2010-10-25 | 99 |  | 90 | 9 | 9.091%
X707 | Replacement of RTU and Local Alarm System at SMTS | 2010-07-02 | 1358 |  | 1175 | 183 | 13.48%
X715 | Replacement of RTUs and HMIs at HYTS | 2009-04-01 | 930 |  | 1997 | -1067 | -114.7%
X727 | TTS - B2 Transformer Replacement | 2010-04-01 | 5275 |  | 5538 | -263 | -4.986%
X741 | CT Replacements Stage 4 (Tyree 06/550/3, GEC FMJL, ASEA IMBA, Modern Products) | 2010-10-29 | 4468 |  | 4411 | 57 | 1.276%
X742 | Fence Upgrade at YPS | 2009-09-01 | 275 |  | 306 | -31 | -11.27%
X744 | Fencing Upgrade at LYPS & LY | 2009-07-31 | 533 |  | 579 | -46 | -8.63%
X745 | Fence Upgrade at JLTS | 2009-05-14 | 282 |  | 279 | 3 | 1.064%
X751 | Security RWTS | 2009-07-31 | 509 |  | 583 | -74 | -14.54%
X753 | Fence Upgrade at RCTS | 2010-05-03 | 568 |  | 604 | -36 | -6.338%
X755 | Fence Upgrade at TBTS | 2010-03-30 | 509 |  | 385 | 124 | 24.36%
X759 | Security BTS | 2009-12-15 | 282 |  | 540 | -258 | -91.49%
X765 | Fence Upgrade at BATS | 2009-12-01 | 141 |  | 54 | 87 | 61.7%
X779 | Fence Upgrade at TSTS | 2010-07-02 | 457 |  | 485 | -28 | -6.127%
X7B6 | BLTS Replace LV & LVN Protection | 2011-06-20 | 403 |  | 410 | -7 | -1.737%
X7D2 | Sealing of cable entries into relay, control and communications buildings | 2011-03-23 | 1547 |  | 453 | 1094 | 70.72%
X7D5 | DDTS Add control and monitoring to 3 Lines and 1 Cap bank | 2012-03-07 | 180 |  | 193 | -13 | -7.222%
X7D7 | ERTS Replace prot and control on 9 66Kv Feeders | 2011-12-16 | 543 |  | 217 | 326 | 60.04%
X7D8 | HWTS Replace 4 Transformer Y protections. | 2011-10-20 | 691 |  | 234 | 457 | 66.14%
X7D9 | MLTS & SYTS Replace 'X' prot on 3 500kV Lines | 2011-10-12 | 518 |  | 1310 | -792 | -152.9%
X7E0 | SVTS Replace 3 Transformer protections | 2011-07-12 | 685 |  | 261 | 424 | 61.9%
X7E1 | Replace Y prot on three Transformers. | 2011-04-15 | 518 |  | 202 | 316 | 61%
X7E2 | TSTS Replace 66kV Bus prots. | 2011-03-21 | 407 |  | 547 | -140 | -34.4%
X7E3 | WOTS Upgrade Transformer prot | 2010-05-06 | 173 |  | 223 | -50 | -28.9%
X7E6 | HWTS Replace RTU | 2012-01-05 | 860 |  | 857 | 3 | 0.3488%
X7E8 | HWTS 500 kV CT & CB | 2010-10-29 | 13774 |  | 11352 | 2422 | 17.58%
X7G2 | Replace 2 – OS10 CBs at Morwell Terminal Station | 2010-07-02 | 190 |  | 174 | 16 | 8.421%
X7G9 | CM on Wheels | 2009-06-01 | 342 |  | 315 | 27 | 7.895%
X804 | Station Services AC Supply Upgrades | 2011-03-23 | 811 |  | 1620 | -809 | -99.75%
X829 | Replacement of ground-wire suspension hardware on the YPS-ROTS & ROTS-MTS circuits | 2011-08-06 | 217 |  | 155 | 62 | 28.57%
X831 | Replace worn/corroded hardware & plates and bond ground-wire on 500 kV circuits | 2011-05-17 | 590 |  | 377 | 213 | 36.1%
X841 | Over-arching Network Management System - Stage 1 | 2011-03-21 | 205 |  | 152 | 53 | 25.85%
X842 | Facilities - hydrants, fire suppression | 2012-03-29 | 1035 |  | 1113 | -78 | -7.536%
X847 | Replace BETS - One Tree Hill Radio Links | 2011-06-20 | 188.4 |  | 166 | 22.4 | 11.89%
X853 | Replace Mt Baranduda - WOTS Radio Links | 2011-06-20 | 199 |  | 188 | 11 | 5.528%
X870 | 16mm Insulator Replacement Project FY 2008 - 2010 | 2012-01-25 | 13023 |  | 10586 | 2437 | 18.71%
X878 | Fencing Works at TTS | 2009-07-15 | 111 |  | 116 | -5 | -4.505%
X886 | SVTS battery room expansion | 2011-03-15 | 169 |  | 205 | -36 | -21.3%
X888 | Replacement of Overcurrent Protection of 66kV Capacitor #1 at ERTS | 2011-04-29 | 45 |  | 29 | 16 | 35.56%
X8C0 | System Asset Air Conditioning | 2011-06-15 | 106 |  | 89 | 17 | 16.04%
X900 | Expansion of Relays / SCIMS Test Bed with New Relay Types | 2011-02-04 | 54 |  | 142 | -88 | -163%
X905 | SMTS CVT Replacement Hot Weather damage | 2011-03-23 | 566 |  | 354 | 212 | 37.46%
X909 | Replace collapsed T493 DDTS-SMTS No.1 330kV | 2010-04-20 | 811 |  | 709 | 102 | 12.58%
X910 | Install bypass microwave radio between Taminick and Mt Baranduda to provide alternate protection circuit for WOTS-DDTS | 2010-05-12 | 245 |  | 242 | 3 | 1.224%
X919 | Mt Stanley Rebuild | 2012-04-04 | 912 |  | 915 | -3 | -0.3289%
X925 | Replace Cockatoo - Mt toole-Be-Wong Radio Links | 2011-08-25 | 341 |  | 352 | -11 | -3.226%
X927 | Repalcement of Thomastown PABX | 2011-06-20 | 171 |  | 94 | 77 | 45.03%
X938 | 66kV Switchyard Equipment Replacement | 2011-06-14 | 2117 |  | 1136 | 981 | 46.34%
XA19 | Development of Synchronous Condenser Refurbishment (Life Extension) Scope And Estimate | 2012-03-08 | 177 |  | 120 | 57 | 32.2%
XA27 | SHTS TRANSORMER FIRE WALL INSTALLATION | 2011-06-28 | 273 |  | 139 | 134 | 49.08%
XA30 | RWTS - ASEA 150 MVA Trans Cooling Mods to reduce Trans Operating Temperatures | 2011-06-23 | 133 |  | 90 | 43 | 32.33%
XA34 | Replacement of HWTS A1 Station Services transformers | 2011-10-14 | 237 |  | 281 | -44 | -18.57%
XA41 | Replacement of roof at TBTS | 2011-05-24 | 120 |  | 88 | 32 | 26.67%
XB02 | FBTS: Replace DLF 1 66kV Feeder Y Prot | 2011-06-02 | 62 |  | 26 | 36 | 58.06%
XB11 | Replace failed Mitsubishi 220 kV CB at SMTS | 2011-11-24 | 143 |  | 122 | 21 | 14.69%
|  | Total | 334937.76 |  | 331945.64 | 2992.12 | 0.8933%