## Intro
Accenture was engaged to conduct an Impact Assessment on the business to determine remediation activities required for CP-PAL to remain compliant in light of the NER Meter Contestability Rule Changes. Remediation activities are assigned an -Impact Level, which describes the severity of the issue; and -Priority, which determines the order in which activities need to be completed
Contents
1. Effort Summary
2. Impact Summary
3. Compliance Impacts Assessment
Document Title: | NER Change Impact Assessment
Author: | Gary Kew
Reviewers: | Michael Clemets, Tony Histon
Approvers: | Frank Ochel
Version: | 2.1
| Process Impact Level | Priority | Systems Impact Level
Very High (VH) | Substantial effort and resources required to change or create new business process | N/A | Fundamental change to the way the system currently operates
High (H) | Significant effort and resources required to change or create new business process | Required Process or System change by Dec 2017. No workaround for issue | Significant change to the way the system currently operates
Medium (M) | Moderate effort and resources required to change or create new business process | Required Process or System change by Dec 2017. Workaround exists for the issue | Moderate change to the way the system currently operates
Low (L) | Minor effort and resources required to change or create new business process | Process or System change required after Dec 2017. | Slight change to the way the system currently operates

## 1. Effort Summary
| Using Accenture Estimating tools and models, a work-day effort was derived for each Impact level of Very High, High, Medium and Low. This was used as the basis for estimating the total amount of effort required to remediate all issues and produce a recommended roadmap of projected activities | [10 empty] | Effort | Process | Systems
[12 empty] | Very High (VH) | 65 | 650
[12 empty] | High (H) | 26 | 130
[12 empty] | Medium (M) | 15 | 65
[12 empty] | Low (L) | 6 | 26
Effort Summary
Effort (Process + Systems) | #REF! | Work days | [10 empty] | Internal | External
Includes Analyse (additional), Build, Test (SIT, UAT), Deploy | [11 empty] | Onshore rates | 1000 | 1700
[12 empty] | Offshore rates | N/A | 500
Total Effort | #REF! | Work days |  | *Work Days calculations are rounded to nearest 10 days
Total Cost | #REF! | Million AUD |  | *All cost calculations rounded up to nearest 10,000 AUD
*ensure that total percentage of onshore and offshore equals 100%
|  | 2015 | 2016 |  |  |  | 2017 |  |  |  | 2018 |  | Onshore |  | Offshore
|  | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Internal | External
Pre-Mobilisation Activities | Effort | [14 empty] | total %
Plan, Resourcing, Budget | 280 | [11 empty] | 60% | 40% | 0% | 100% | bar: 2015 Q4
Blueprinting | 420 | 2016 Q1: 1; 2016 Q3: 0.5 | 60% | 40% | 0% | 100%
Work Packages | Effort
Manage Regulation & Compliance | #REF! | 2016 Q1: 1; 2016 Q2: 1; 2017 Q4: 0.5 | 25% | 35% | 40% | 100%
Meter Asset Management | #REF! | [11 empty] | 25% | 35% | 40% | 100% | bar: 2016 Q3; 2017 Q3 to 2018 Q2
Meter Data Management | #REF! | [11 empty] | 25% | 35% | 40% | 100% | bar: 2016 Q2; 2016 Q4 to 2017 Q1
Operate the Network | #REF! | [11 empty] | 25% | 35% | 40% | 100% | bar: 2016 Q2 to 2016 Q3; 2017 Q1 to 2017 Q2
Manage Network Data & Smart Infrastructure | #REF! | [11 empty] | 25% | 35% | 40% | 100% | bar: 2017 Q1 to 2017 Q3
Manage Revenue | #REF! | [11 empty] | 25% | 35% | 40% | 100% | bar: 2016 Q4 to 2017 Q2
Market Interactions | #REF! | [11 empty] | 25% | 35% | 40% | 100% | bar: 2016 Q4 to 2017 Q4
Connections, Adds & Alts, Abolishments | 270 | [11 empty] | 25% | 35% | 40% | 100% | bar: 2016 Q4 to 2017 Q4
Scheduling (Multi-Party) | #REF! | [11 empty] | 25% | 35% | 40% | 100% | bar: 2017 Q1 to 2017 Q3
Training / OCM | Effort
Training / OCM | #REF! | [11 empty] | 25% | 35% | 40% | 100% | bar: 2017 Q3 to 2018 Q1
Additional Testing | Effort
Industry Testing | 100 | 2017 Q4: 0.66667 | 60% | 40% | 0% | 100%
Regression Testing | 150 | [11 empty] | 25% | 35% | 40% | 100% | bar: 2017 Q4
Project Management | Effort
Project Management | #REF! | [11 empty] | 60% | 40% | 0% | 100% | bar: 2015 Q4 to 2018 Q2
PMO | #REF! | [11 empty] | 60% | 40% | 0% | 100% | bar: 2015 Q4 to 2018 Q2
Post Go-Live | Effort
Exceptions & Automation | 280 | [11 empty] | 25% | 35% | 40% | 100% | bar: 2018 Q1 to 2018 Q2
Additional accreditation | 280 | [11 empty] | 60% | 40% | 0% | 100% | bar: 2018 Q1 to 2018 Q2
Cost/ Year ($ '000) |  | 2015 Q4: #REF!; 2016 Q1: #REF!; 2017 Q1: #REF!; 2018 Q1: #REF!
PMO |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
Plan , Resourcing, Budget |  | 2015 Q4: 358400 | 168000 | 190400 | 0
Blueprinting (2 FTE, 4 PTE) |  | 2016 Q1: 358400; 2016 Q3: 179200 | 252000 | 285600 | 0
Manage Regulation & Compliance |  | 2016 Q1: #REF!; 2016 Q2: #REF!; 2017 Q4: #REF! | #REF! | #REF! | #REF!
Meter Asset Management |  | 2016 Q3: #REF!; 2017 Q3: #REF!; 2017 Q4: #REF!; 2018 Q1: #REF!; 2018 Q2: #REF! | #REF! | #REF! | #REF!
Meter Data Management |  | 2016 Q2: #REF!; 2016 Q4: #REF!; 2017 Q1: #REF! | #REF! | #REF! | #REF!
Operate the Network |  | 2016 Q2: #REF!; 2016 Q3: #REF!; 2017 Q1: #REF!; 2017 Q2: #REF! | #REF! | #REF! | #REF!
Manage Network Data & Smart Infrastructure |  | 2017 Q1: #REF!; 2017 Q2: #REF!; 2017 Q3: #REF! | #REF! | #REF! | #REF!
Manage Revenue |  | 2016 Q4: #REF!; 2017 Q1: #REF!; 2017 Q2: #REF! | #REF! | #REF! | #REF!
Market Interactions |  | 2016 Q4: #REF!; 2017 Q1: #REF!; 2017 Q2: #REF!; 2017 Q3: #REF!; 2017 Q4: #REF! | #REF! | #REF! | #REF!
End to End |  | 2016 Q4: 56430; 2017 Q1: 56430; 2017 Q2: 56430; 2017 Q3: 56430; 2017 Q4: 56430 | 67500 | 160650 | 54000
Scheduling (Multi-Party) |  | 2017 Q1: #REF!; 2017 Q2: #REF!; 2017 Q3: #REF! | #REF! | #REF! | #REF!
Operational Change Management |  | 2017 Q3: #REF!; 2017 Q4: #REF!; 2018 Q1: #REF! | #REF! | #REF! | #REF!
Industry Testing |  | 2017 Q4: 128000 | 60000 | 68000 | 0
Regression Testing |  | 2017 Q4: 156750 | 37500 | 89250 | 30000
Project Management |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
Exceptions & Automation |  | 2018 Q1: 146300; 2018 Q2: 146300 | 70000 | 166600 | 56000
Additional accreditation |  | 2018 Q1: 179200; 2018 Q2: 179200 | 168000 | 190400 | 0
Cost / Quarter ($ '000) |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
Total Cost | [12 empty] | #REF! | #REF! | #REF!
Detailed Effort (Click button to expand)
Includes only those processes that are impacted by rule changes (see impact summary)
Data
Area | Process | Capability | Process. | OMS. | CRM. | CIS. | SAP. | UIQ. | MTS. | IEE. | BI. | CFE. | Click. | USB.
1. Manage the Asset Infrastructure |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2. Meter Management
| 2.1 Meter Asset Management |  | 138 | 65 | 91 | 390 | 169 | 117 | 91 | 52 | 273 | 26 | 130 | 325
| 2.2 Meter Data Management |  | 15 | 0 | 0 | 0 | 0 | 0 | 65 | 65 | 0 | 0 | 0 | 26
3. Market Interactions |  |  | 225 | 0 | 26 | 936 | 0 | 0 | 910 | 0 | 260 | 65 | 0 | 975
4. Plan, Manage & Execute
| 4.1 Plan Work & Enterprise Resources |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 4.2 Manage & Execute Work |  | 153 | 195 | 195 | 78 | 286 | 26 | 52 | 0 | 221 | 286 | 325 | 182
|  | E2E - New Connections | 15 | 0 | 0 | 0 | 65 | 0 | 26 | 0 | 0 | 26 | 65 | 65
|  | E2E - Maintenance / Replacement & Network Augmentation | 15 | 0 | 0 | 26 | 0 | 26 | 0 | 0 | 0 | 0 | 0 | 0
|  | E2E - Additions and Alterations | 26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | E2E - Emergency & Repair | 26 | 65 | 65 | 0 | 26 | 0 | 26 | 0 | 26 | 0 | 65 | 0
|  | E2E - Abolishment | 15 | 0 | 0 | 26 | 65 | 0 | 0 | 0 | 65 | 65 | 65 | 26
|  | E2E - Retailer initiated work | 15 | 65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 65 | 65 | 26
|  | Schedule | 41 | 65 | 130 | 26 | 130 | 0 | 0 | 0 | 130 | 130 | 65 | 65
| 4.3 Plan & Manage Supply Chain |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5. Operate the Network |  |  | 112 | 260 | 26 | 0 | 0 | 156 | 65 | 0 | 195 | 26 | 0 | 130
6. Manage Network Data & Smart Infrastructure |  |  | 73 | 130 | 0 | 52 | 26 | 52 | 52 | 0 | 91 | 0 | 0 | 91
7. Manage Revenue |  |  | 84 | 26 | 65 | 143 | 26 | 0 | 26 | 0 | 91 | 0 | 0 | 26
8. Manage Regulation & Compliance |  |  | 32 | 0 | 0 | 130 | 26 | 26 | 65 | 65 | 0 | 26 | 26 | 65
Total Result |  |  | 832 | 676 | 403 | 1729 | 533 | 377 | 1326 | 182 | 1131 | 429 | 481 | 1820

## 2. Impacts Summary
The Impacts Summary aggregates the total number of process and system remediation activities shown in "3.Compliance Impacts Assessemnt" and broken down by the Impact level of Very High, High, Medium, and Low
Impacts Summary
Process Summary | [5 empty] | Systems Summary
Process Area | Level
Area | VH | H | M | L | Total Result | Systems | VH | H | M | L | Grand Total
1. Manage the Asset Infrastructure | [5 empty] | DMS | 0 | 2 | 6 | 1 | 9
2. Meter Management | 1 | 2 | 2 | 1 | 6 | CIS | 1 | 5 | 3 | 9 | 18
3. Market Interactions | 3 |  | 2 |  | 5 | CRM | 0 | 1 | 3 | 3 | 7
4. Plan, Manage & Execute |  | 3 | 5 |  | 8 | SAP | 0 | 1 | 3 | 8 | 12
5. Operate the Network | 1 | 1 | 1 | 1 | 4 | UIQ | 0 | 1 | 1 | 7 | 9
6. Manage Network Data & Smart Infrastructure |  | 2 | 1 | 1 | 4 | MTS | 1 | 2 | 4 | 6 | 13
7. Manage Revenue |  | 3 |  | 1 | 4 | IEE | 0 | 0 | 2 | 2 | 4
8. Manage Regulation & Compliance |  | 1 |  | 1 | 2 | BI | 0 | 3 | 9 | 6 | 18
Total Result | 5 | 12 | 11 | 5 | 33 | CFE/E2E | 0 | 1 | 3 | 4 | 8
[6 empty] | Click | 0 | 0 | 7 | 1 | 8
Note: There are 33 individual impacts across 28 processes. | [5 empty] | USB | 1 | 3 | 10 | 5 | 19
[6 empty] | Grand Total | 3 | 19 | 51 | 52 | 125

## 3.Compliance Impacts Assessment
|  |  |  | Legend |  | This page details the identified impacts to the business and links them to the Contestability rule change and operational approach. Remediation activities for Process, Systems and People have been recommended, together with corresponding Impact level and Priority |  |  |  | *NOTE: System header explanation below OMS - Refers to customisation of Outage Management System CIS - Refers to customisation to Customer Data, Billing and some scheduling only CRM - Refers to customisation to the Customer Relationship Management system SAP - Refers to customisation to the Meter Asset and Work Management components of SAP UIQ - Refers to customisation to the AMI Network system MTS - Refers to customisation of the market transaction gateway IEE - Refers to customisation to the Meter Data Management system BI - Refers to customisation to the Business Intelligence and Analytics systems CFE/E2E - Refers to customisation to the CFE / E2E systems Click - Refers to customisation to the Click Scheduling systems USB - Refers to customisation to the Universal Service Bus
|  |  |  | VH | Very High
|  |  |  | H | High
|  |  |  | M | Medium
|  |  |  | L | Low
Impact Assessment
Analysis | [6 empty] | Process Impact |  |  | System Impact
ID | Rule Change | Area | Process | Capability | Title | Description of Change | Description | Level | Priority | Description | OMS | CIS | CRM | SAP | UIQ | MTS | IEE | BI | CFE/ E2E | Click | USB | Priority
1 | N/A | 1. Manage the Asset Infrastructure | 1.1 Manage Investments | Long & Medium Term Planning | N/A | Refers to assets which are NOT meters (e.g. poles, wires, etc). Minimal impact expected from the Meter Contestability rule change |  | N/A | N/A | [12 empty] | N/A
2 | N/A | 1. Manage the Asset Infrastructure | 1.1 Manage Investments | Investment Analysis | N/A | Refers to assets which are NOT meters (e.g. poles, wires, etc). Minimal impact expected from the Meter Contestability rule change |  | N/A | N/A | [12 empty] | N/A
3 | N/A | 1. Manage the Asset Infrastructure | 1.1 Manage Investments | Asset Investment Review | N/A | Refers to assets which are NOT meters (e.g. poles, wires, etc). Minimal impact expected from the Meter Contestability rule change |  | N/A | N/A | [12 empty] | N/A
4 | N/A | 1. Manage the Asset Infrastructure | 1.1 Manage Investments | Capital & OM Budgeting | N/A | Refers to assets which are NOT meters (e.g. poles, wires, etc). Minimal impact expected from the Meter Contestability rule change |  | N/A | N/A | [12 empty] | N/A
5 | N/A | 1. Manage the Asset Infrastructure | 1.2 Manage Asset Programs | Asset Planning | N/A | Refers to assets which are NOT meters (e.g. poles, wires, etc). Minimal impact expected from the Meter Contestability rule change |  | N/A | N/A | [12 empty] | N/A
6 | N/A | 1. Manage the Asset Infrastructure | 1.2 Manage Asset Programs | Construction Project Design & Estimation | N/A | Refers to assets which are NOT meters (e.g. poles, wires, etc). Minimal impact expected from the Meter Contestability rule change |  | N/A | N/A | [12 empty] | N/A
7 | N/A | 1. Manage the Asset Infrastructure | 1.2 Manage Asset Programs | Maintenance Forecasting | N/A | Refers to assets which are NOT meters (e.g. poles, wires, etc). Minimal impact expected from the Meter Contestability rule change |  | N/A | N/A | [12 empty] | N/A
8 | N/A | 1. Manage the Asset Infrastructure | 1.2 Manage Asset Programs | Project Sourcing | N/A | Refers to assets which are NOT meters (e.g. poles, wires, etc). Minimal impact expected from the Meter Contestability rule change |  | N/A | N/A | [12 empty] | N/A
9 | N/A | 1. Manage the Asset Infrastructure | 1.3 Manage Asset Strategy | Net. Analysis & Long Term Planning | N/A | Refers to assets which are NOT meters (e.g. poles, wires, etc). Minimal impact expected from the Meter Contestability rule change |  | N/A | N/A | [12 empty] | N/A
10 | N/A | 1. Manage the Asset Infrastructure | 1.3 Manage Asset Strategy | Reg./Asset Strat. Policy/Compliance | N/A | Refers to assets which are NOT meters (e.g. poles, wires, etc). Minimal impact expected from the Meter Contestability rule change |  | N/A | N/A | [12 empty] | N/A
11 | N/A | 1. Manage the Asset Infrastructure | 1.3 Manage Asset Strategy | Asset Risk Management | N/A | Refers to assets which are NOT meters (e.g. poles, wires, etc). Minimal impact expected from the Meter Contestability rule change |  | N/A | N/A | [12 empty] | N/A
12 | N/A | 1. Manage the Asset Infrastructure | 1.3 Manage Asset Strategy | Asset Perf. Condition & Predictive Management | N/A | Refers to assets which are NOT meters (e.g. poles, wires, etc). Minimal impact expected from the Meter Contestability rule change |  | N/A | N/A | [12 empty] | N/A
13 | Roles & Responsibilities | 2. Meter Management | 2.1 Meter Asset Management | Provide Meter Assets | Meter Exchange between CP-PAL and third party meters | At scale processes required for handling churn data in scenarios where a CP-PAL meter is removed by a third party MP while CP-PAL is still the active MDP. | Develop processes for "transitional procedures", considering: -Collecting final meter information to fulfil MDP obligations. -flagging and handling the "loss" of the meter in systems -Will CP-PAL attend the site during a meter exchange -defining the business rules for the process | VH | H | Change in system to -Flag the site which has undergone meter exchange and stop all data collection processes -Supress alerts for "missing meter" on the site -Remove site from route planning and scheduling in regards to metering services |  | H | M | L | M | M | L | H | L | M | M | H
14 | Access to Network Devices | 2. Meter Management | 2.1 Meter Asset Management | Manage Meter Assets | Downgrade meter to be used as a network device | New processes required for classification of meters as "network devices" where third party meters are installed and the CP-PAL meter is retained. | Develop new processes which must consider: - Removal of any metrology-related logic associated with collected data. - CP-PAL's rights to use consumption data for network operational purposes. - Handling of network device faults and ongoing testing/maintenance requirements. - Function of the network device (including for load control). - Approach to handling network device removal by an incoming MP who has justified removal on the basis of space constraints or safety reasons. -business rules | M | M | Enable systems to reclassify a meter to a network device, with considerations for: -The degree of functionality and data collection that must be disabled, changed or restricted | [10 empty] | M | M | bar: CIS to MTS; BI
15 | Access to Network Devices | 2. Meter Management | 2.1 Meter Asset Management | Manage Meter Assets | Logical Conversion of type 5 meters to type 4 | The Derogation expiry in Dec 2017 will also mean the expiry of the rule to allow all VIC AMI meters to be classified as type 5 meters. These meters will need to be reclassified as type 4. | Develop new processes which must consider: - Bulk reclassification requirements - Exception handling and manual workaround -all validation and workflow impacts of the reclassification -accreditation requirements -exception handling | H | H | Enable bulk reclassification of VIC AMI type 5 meters to type 4, considering, -ability to perform mass updates for MSATS Reconfiguration of current workflows and validation rules | [10 empty] | M | H | bar: CIS; SAP; BI
16 | Cost Recovery regulated metering services | 2. Meter Management | 2.1 Meter Asset Management | Manage Meter Assets | Managing retrieved meters | Revised processes required for handling an increased volume of "returned meters" including any requirements for final reads (in particular for non AMI sites), asset refurbishment and disposal. | Develop procedures for handling increased volumes of meters returning from the field, including considerations for storing, refurbishment or redeploy into the field. Revise material demand planning for new meters | L | L | Current systems able to handle meter returns, not of increased volumes | [11 empty] | L | bar: SAP; BI
17 | Roles & Responsibilities | 2. Meter Management | 2.1 Meter Asset Management | Administer Meter Point | Revise current validation rules and workflows | Current system rules and workflows cause issues once the rule change come into effect. (e.g. automated rules may wrongly assign new connection sites with type 4 meter as large site, when the actual site is small customer, or assign wrong tariff, etc.) | Revise current processes to ensure that the systems will function correctly when the new rules come into affect on December 2016, including: -automated site type allocation -automated tariff allocation -automated billing of retailers | H | M | Ensure that systems will function correctly when the new rules come into affect on December 2016 , considering: -automated site type allocation -automated tariff allocation -automated billing of retailers | M | H |  | M | L |  | L | L |  | M | H | M
18 | Roles & Responsibilities | 2. Meter Management | 2.2 Meter Data Management | Manage Meter Data | Third party metering data | Third party MDP's will provide an increasing number of meter reads. Consequently, processes for meter data management, network billing, etc. need to account for reads incoming from NEM participants, rather than solely from internal reading capability. | Revise current meter read processes to account for receiving data from NEM participants, taking into consideration: -the frequency of publishing of meter data from third parties. -validating that the data received is correct -exception handling for large volumes of exceptions -process for handling missing data at scale | M | H | System updates to allow metering data to be received from external NEM participants Automation of PMDR process | [10 empty] | L | M | bar: MTS to IEE
19 | Roles & Responsibilities | 3. Market Interactions | 3.1 Manage Network Customer | B2B & CATS transactions | Handle new outgoing B2B market transactions | When meters on CP-PAL site becomes contestable, there will be a need for CP-PAL to raise B2B market Service Orders (10 in total) to external Service Providers (previously CP-PAL will be receiving these Service Orders but not raising them) | Develop procedures for raising B2B service orders . Including: -Which of the 10 Service Orders will need to be raised -Exception management for failed Service Orders -Define business rules -Apply AEMO guidelines and procedures | VH | H | Update systems to be able to raise and track Service Orders when previously CP-PAL only needed to receive and not raise these Service Orders. | [10 empty] | H | M | bar: CIS; MTS; BI
20 | Roles & Responsibilities | 3. Market Interactions | 3.1 Manage Network Customer | B2B & CATS transactions | Handling new incoming B2B market transactions | With the introduction of the new MC role, CP-PAL will need to define how market transactions and B2B communications will be handled (e.g. incoming requests, etc.) | Develop processes for handling new and existing market transactions, taking into consideration: -changes in business rules, workflows and validations -new MC role Change requests | VH | H | Enable systems to receive new B2B transactions from the market, taking into consideration increased volume of messages. -revise workflows and validation | [10 empty] | H | M | bar: CIS; MTS; BI
21 | Minimum Service Specification | 3. Market Interactions | 3.1 Manage Network Customer | B2B & CATS transactions | Shared Market Protocol | Current systems and processes will require changes with the introduction of the shared market protocol | Develop processes for handling the shared market protocol, considering changes to: - Service Order (B2B) Processes. - Role Appointment Processes. - Connection Point Management Process - Objection processes. - Jurisdictional differences | VH | M | Enable systems to accommodate -real time or near real time message transfer capabilities -changes to the B2B e-hub -security | [10 empty] | VH | M | bar: CIS; MTS; BI
22 | Roles & Responsibilities | 3. Market Interactions | 3.1 Manage Network Customer | B2B & CATS transactions | Automate off-market Metering Requests | Currently CitiPower handles off-market metering requests via manual paperwork. Manual process can’t be scaled up to handle the increasing volumes of meter requests and automation is required | Develop procedures for automatic processing of Metering Requests forms that come in from retailers. | M | L | Automate systems to be able to receive, and action metering request forms, as well as sending out automated notifications upon receipt, cancellation and closure of the metering work | [8 empty] | M |  | M | L | bar: CIS to CRM; BI
23 | Roles & Responsibilities | 3. Market Interactions | 3.1 Manage Network Customer | Service Provider Liaison | N/A | No immediate impact determined, but may be impacted in the future |  | N/A | N/A | [12 empty] | N/A
24 | Consumer Arrangements | 3. Market Interactions | 3.2 Manage Consumer | End-user Management | Handle customer contact | Develop supporting materials for customer service around the implications of a contestable metering market to CP-PAL's role and responsibilities, particularly around differentiating between a CP-PAL issue and a retailer issue (meter issue and network issue) | Develop training procedures, processes and scripts for customer service desk, escalation team, and claims team, considering the following scenarios: - claims and queries relating to outages initiated by retailer - enquiries relating to faults in non-CP-PAL meters -complaints (e.g. customer does not want both network device and third party meter on premise) -increased volumes of customer contact leading to increased costs | M | M | N/A | [11 empty] | N/A
25 | N/A | 4. Plan, Manage & Execute | 4.1 Plan Work & Enterprise Resources | Integrated Resource & Supply Chain Planning | N/A | No immediate impact determined, but may be impacted in the future |  | N/A | N/A | [12 empty] | N/A
26 | Roles & Responsibilities | 4. Plan, Manage & Execute | 4.1 Plan Work & Enterprise Resources | Contractor Strategy | N/A | No immediate impact determined, but may be impacted in the future |  | N/A | N/A | [12 empty] | N/A
27 | Roles & Responsibilities | 4. Plan, Manage & Execute | 4.1 Plan Work & Enterprise Resources | Delivery Performance Management | N/A | No immediate impact determined, but may be impacted in the future |  | N/A | N/A | [12 empty] | N/A
28 | Roles & Responsibilities | 4. Plan, Manage & Execute | 4.2 Manage & Execute Work | E2E - New Connections | Third party meter New connections | Revision of new connections process in the context of third party meter providers installing meters at mass market sites. CP-PAL will be expected to allocate NMI in such instances, but third parties will be responsible for installing meters and maintaining connection point details. | Revise processes for third party new connections, taking into consideration - "Allocate NMI" SO more suitable in these cases (previously using "Create NMI" SO) - System implications of creating all required information in the system with the exception of metering information -CP-PAL responsibilities of attending the new connection site | M | H | System changes to recognise that metering work is performed by third party and not by CP-PAL | [8 empty] | L | M | M | H | bar: SAP; MTS
29 | Roles & Responsibilities | 4. Plan, Manage & Execute | 4.2 Manage & Execute Work | Schedule | Multi-party appointment capabilities required | There is no scalable process for facilitating "multi-party" appointments for scenarios where network representatives, electricians and metering service providers need to be on-site simultaneously to facilitate new connections. | Develop process for multi-party appointment capability, i.e.: - Customer upgrading supply (single phase to three phase). -Electricians, networks and meter providers need to be booked at the same time. | H | M | Enable three way appointment capability for Customer upgrading supply (single phase to three phase). Electricians, networks and meter providers need to be booked at the same time. | M | L | H | H |  |  |  | H | H | M | M | M
30 | Roles & Responsibilities | 4. Plan, Manage & Execute | 4.2 Manage & Execute Work | Schedule | Route Planning | As increasing volumes of work are appointment based, a revision of the current routing plans is needed to ensure continued operational efficiency (e.g. routing based on time and type of work as opposed to geographical) | Revise field work routing plans and truck equipment, taking into consideration: -increasing appointment based work -sites require third party service provider to attend work as well | M | M | Any system change requirements already covered in line item ID29 "Multi-party appointment capabilities required" | [11 empty] | N/A
31 | Roles & Responsibilities | 4. Plan, Manage & Execute | 4.2 Manage & Execute Work | E2E - Maintenance / Replacement & Network Augmentation | Inspecting third party metering work | Before manual re-energisation of a site with a third party meter, CP-PAL will need to perform checks and inspections on the site and metering installation for safety issues. There will be cases when CP-PAL is unable to re-energise the site (e.g. a metering work initiated by third party market participant found to be unsafe or non-compliant). CP-PAL will need to coordinate with market participant to ensure customer is back on supply as soon as possible | Develop procedures for site inspection of a site with third party meter, with consideration for: -handling cases where site cannot be re-energised (e.g. site defect, testing issue) -equipping customer care with capability and knowledge to handle customer left off-supply -coordination with third party market participants to get customer back on supply | M | H | Systems must be able to identify sites with third party meter and quickly identify the service provider who performed the work. | [11 empty] | M | bar: CIS; UIQ
32 | Roles & Responsibilities | 4. Plan, Manage & Execute | 4.2 Manage & Execute Work | E2E - Additions and Alterations | Handling of adds and alts for non-CP-PAL meters | CP-PAL will still be responsible for facilitating adds and alts within their distribution area. Processes are required to manage adds and alts work where a third party MC's meter is involved (e.g. processes for testing, gaining access to the meter, wiring and meter boards) | Develop new process to define how CP-PAL handles cases where a network job at a site requires moving or removing of a non-CP-PAL meter, with considerations for: -coordinating with MC to send an external service provider to remove the meter -obtaining authorisation from MC for CP-PAL to perform work at the site with the possibility of having to temporarily remove the meter | H | M | Any system change requirements already covered in line item ID29 "Multi-party appointment capabilities required" | [11 empty] | N/A
33 | Roles & Responsibilities | 4. Plan, Manage & Execute | 4.2 Manage & Execute Work | E2E - Emergency & Repair | Emergency and Outage management | Process required for handling instances for isolated and mass outages, which require meter replacement. Events such as HVI faults may result in a larger number of CP-PAL and/or non-CP-PAL meters becoming faulty. Any meter requiring replacement will become contestable. CP-PAL may not be able to restore supply without the involvement of a third party MC's. | Develop process for outage handling with possible procedures for: -coordinating site attendances with external service providers -pre-agreements with third parties on handling faulty meters -full replacement of broken meters (essentially CP-PAL will be new appointed MC) -temporary replacement of meters (where CP-PAL places new meters first and the incumbent MC will arrange for replacing them at a later date) | H | H | Enable systems to flag sites with non- CP-PAL meters which may require attendance by external meter service providers | [9 empty] | M |  | L | bar: OMS; CRM to SAP; MTS; BI
34 | Roles & Responsibilities | 4. Plan, Manage & Execute | 4.2 Manage & Execute Work | E2E - Abolishment | Handling Site Abolishment | Site abolishment processes require re-design considering that third party meters may be present on site for mass market customers. Processes must account for scenarios where: -third party meter is removed by CP-PAL -third party meter is left on site | Develop procedures for meter abolishment, taking into consideration: - provision of notice to third party MP's prior to site de-energisation - removal of third party meters by CP-PAL and logistics requirements for meter return. - non-removal of third party meters (leave on site) -meter does not belong to CP-PAL but the network device within does | M | M | Current systems able to handle site abolishments, but not increased volumes of abolishment. | [8 empty] | M | M | L | M | bar: CIS; SAP; BI
35 | Roles & Responsibilities | 4. Plan, Manage & Execute | 4.2 Manage & Execute Work | E2E - Retailer initiated work | Planned outages with DNSP involvement | CP-PAL will at times need to be involved to effect an interruption to customer supply for the third party MC to undertake work on the metering equipment (e.g. where a common service fuse is used to isolate supply across multiple dwellings). CP-PAL will still be expected to send out customer notification in these cases. | Develop process to handle requests for interruption at a site where CP-PAL is not MC, considering: -possibility of having to attend site twice (once to de-energise, and another to re-energise) -branding for customer notifications, contact details for enquiries and party responsible for issues (i.e., CP-PAL, FRMP, or MP, etc.). | M | M | Enable systems to handle planned outages as initiated by third party. | [8 empty] | M | M | L | L | bar: OMS
36 | N/A | 4. Plan, Manage & Execute | 4.3 Plan & Manage Supply Chain | Plan Material Demand | N/A | No immediate impact determined, but may be impacted in the future |  | N/A | N/A | [12 empty] | N/A
37 | N/A | 4. Plan, Manage & Execute | 4.3 Plan & Manage Supply Chain | Procure Material and Service | N/A | No immediate impact determined, but may be impacted in the future |  | N/A | N/A | [12 empty] | N/A
38 | N/A | 4. Plan, Manage & Execute | 4.3 Plan & Manage Supply Chain | Manage Materials | N/A | No immediate impact determined, but may be impacted in the future |  | N/A | N/A | [12 empty] | N/A
39 | N/A | 4. Plan, Manage & Execute | 4.3 Plan & Manage Supply Chain | Receipt, Store & Deliver | N/A | No immediate impact determined, but may be impacted in the future |  | N/A | N/A | [12 empty] | N/A
40 | N/A | 4. Plan, Manage & Execute | 4.3 Plan & Manage Supply Chain | Pay Supplier | N/A | No immediate impact determined, but may be impacted in the future |  | N/A | N/A | [12 empty] | N/A
41 | N/A | 4. Plan, Manage & Execute | 4.3 Plan & Manage Supply Chain | Manage Supply Chain Systems | N/A | No immediate impact determined, but may be impacted in the future |  | N/A | N/A | [12 empty] | N/A
42 | N/A | 5. Operate the Network | 5.1 Enable Smart Network Operations | Perform Operational Planning | N/A | No immediate impact determined, but may be impacted in the future |  | N/A | N/A | [12 empty] | N/A
43 | N/A | 5. Operate the Network | 5.1 Enable Smart Network Operations | Provide Operational Support | N/A | Covered under the "Additions & Alterations" Capability |  | N/A | N/A | [12 empty] | N/A
44 | Minimum Service Specification | 5. Operate the Network | 5.1 Enable Smart Network Operations | Real Time Operation & Control | No outage notification in minimum service specification | As of September 2015, the minimum service specification does not currently include the need for "outage notification" functionality. This may result in loss of "last gasp" outage notification, supply restoration and ability to "ping" meter to confirm supply as new MC's may install meters without the outage notification functionality | Revise and potentially alter OMS escalation/restoration rules to accommodate potential "gaps" in network Negotiate arrangements with other MSP's to publish last gasps supply restoration and a "meter ping service". Process to ensure CP-PAL meters and third party meters are communicating to each other to maintain network quality and accurate outage capabilities | M | H | Enable systems to accommodate for meters with no outage notification functionality Enable systems to receive outage notification data from external sources | [10 empty] | M | H | bar: OMS
45 | Roles & Responsibilities | 5. Operate the Network | 5.1 Enable Smart Network Operations | Manage Planned Events | Planned outages with NO DNSP involvement | Retailers will be able to arrange for remote de-energisation on sites with the MC, without the involvement of the DNSP. In these cases CP-PAL will still need to know of any planned outages initiated by retailers to avoid mistakenly treating unpowered sites as a fault | Develop process to receive and store information regarding planned outages initiated by external parties, with procedures to: -suppress fault notifications for that site -CP-PAL being sent "copies" of Service Orders sent between external parties | H | H | Enable systems to -receive and distinguish Service Orders for "information only" and does not trigger work orders being created in the system -validate Service Orders. (i.e. any ongoing CP-PAL work at the site) - integrate with DMS systems to supress fault notifications for a period of time | [10 empty] | M | M | bar: OMS; CRM; UIQ to MTS; BI
46 | N/A | 5. Operate the Network | 5.1 Enable Smart Network Operations | Manage Un-planned Events | N/A | Covered under the "Emergency & Repair Capability |  | N/A | N/A | [12 empty] | N/A
47 | Access to Network Devices | 5. Operate the Network | 5.1 Enable Smart Network Operations | Manage Network Quality | Meter Removals affect network quality | Removal of meters may limit CP-PAL's ability to monitor network quality (THD, voltage, phase balance etc.). This will be especially prevalent in low density AMI deployment areas where removal of a single meter will cause loss of communication with adjacent meters. Alternative means of network monitoring may be required (e.g. network devices at customer premises). | Develop procedures for maintaining network quality in the event of increasing loss of meter on premise with considerations for: - active measures for preventing loss of network quality (e.g. installing network devices at sites) -identifying -revision of the AMI network design -reactive measures where network comm relays deployed to reconnect disconnected meters to the CP-PAL network (use of SSN Cellular "Micro AP's" to provide communications network "infill".) -"renting" comms assets from other DNSP's in the area | VH | M | Enable system to detect potential loss of meter network connectivity due to a meter being disconnected and notify CP-PAL Enable systems to use "rented" comms assets belonging to other DNSPs | [11 empty] | M | bar: OMS; UIQ; BI
48 | All | 5. Operate the Network | 5.1 Enable Smart Network Operations | Manage Distributed Generation | Solar pre-approval | CP-PAL in its LNSP capacity will need to pre-approve sites prior to customers being able to install solar capabilities at their premises. New processes will be required for CP-PAL and the MC to co-ordinate activities such that the solar installation does not cause negative impacts to the grid | Develop procedures and steps expected of market participants, customers and MCs to follow to provide solar installations for customer, including consideration for fees and charges involved | L | L | Changes to Solar portal to reflect new changes | [8 empty] | L |  |  | M
49 | N/A | 6. Manage Network Data & Smart Infrastructure | 6.1 Manage Governance and Architecture | Manage Information Strategy & Architecture | N/A | No immediate impact determined, but may be impacted in the future |  | N/A | N/A | [12 empty] | N/A
50 | N/A | 6. Manage Network Data & Smart Infrastructure | 6.1 Manage Governance and Architecture | Manage Data / Information Governance and Audit | N/A | No immediate impact determined, but may be impacted in the future |  | N/A | N/A | [12 empty] | N/A
51 | N/A | 6. Manage Network Data & Smart Infrastructure | 6.2 Manage Data & Analytics/Modelling | Network Assets Data | N/A | No immediate impact determined, but may be impacted in the future |  | N/A | N/A | [12 empty] | N/A
52 | All | 6. Manage Network Data & Smart Infrastructure | 6.2 Manage Data & Analytics/Modelling | Process Meter Data | Meter data analytics | New reporting and analytics capabilities required to support CP-PAL Operation as the metering services landscape changes with the implementation of the rule change | Define scope and types of new or updated reports and analytics required to support the network operations and performance monitoring. | M | M | Define the new or updated reports required to further support the network operations and performance monitoring. Develop new processes and reports to: -analyse meter churn trends - analyse consumer data - discover inefficiencies | [11 empty] | M | bar: BI
53 | Roles & Responsibilities | 6. Manage Network Data & Smart Infrastructure | 6.3 Manage Communications Infrastructure & Security | Manage Comms. Environment | Pre-emptive actions for potential meter removal sites | There will be an increasing reliance on third parties to provide information to CP-PAL when a meter exchange is to be performed. Failing to do so may have adverse effects on the network (i.e. fault truck dispatched, insufficient meter data to fulfil obligations, loss of comms with adjacent meters, etc.). Some pre-emptive actions can be taken to minimise the adverse impacts | Develop processes to: -Identify in advance when a meter is to be exchanged by third party (e.g. through planned outage notifications, CATS transaction stating a change in premise MC, etc.) -perform pro-active steps (i.e. change data interval collection to shorter intervals, check if comms to adjacent meters will be affected, etc.) -other follow up activities ( e.g. meter return process, install relay to prevent comms loss with adjacent meters. etc.) | H | M | Enable systems to collect data and identify sites where meter removal will be performed by third party and: -automatically shorten the data collection interval from 4 hours to half hourly -notify user to validate if truck fault dispatches to premise are false alarms | [10 empty] | M | H | bar: OMS to CIS; UIQ to MTS
54 | Minimum Service Specification | 6. Manage Network Data & Smart Infrastructure | 6.3 Manage Communications Infrastructure & Security | Manage Comms. Environment | Lower specced meters | The rules specify a minimum service specification of all installed smart meters. Current CP-PAL meters have more functionality than the minimum specifications. There is a possibility that other MCs will install lower specced meters (e.g. no load control, outage notification, etc.). | Define process for identifying the potential functionality that will be lost with lower specced meters, recording them in the system and mitigation actions if required (e.g. installing network device at premise) | L | M | Potential system change to record missing functionality within third party meters installed on CP-PAL patch | [10 empty] | L | L | bar: CIS; MTS
55 | Additional Consultation (17 Sep 15) | 6. Manage Network Data & Smart Infrastructure | 6.3 Manage Communications Infrastructure & Security | Manage Security & Configuration Management | Remote de-en / re-en through network device | New process required for a re-en / de-en performed remotely through the use of the network device (which may be a meter) . CP-PAL will be able to perform this activity where a site needs to be de-energised for safety, security or network reliability reasons (subject to jurisdiction rules) | Develop process for performing a re-en / de-en remotely using a network device, considering the scenarios: - meter does not belong to CP-PAL - what constitutes a safety reason - how will the market be informed - establish guidelines for installations where the old meter remains as a network device | H | L | Enable systems to perform re-en / de-en remotely using a connected network device. Enable systems to send transaction to the market to inform of the de-en | [11 empty] | L | bar: SAP to UIQ; BI
56 | Cost Recovery regulated metering services | 7. Manage Revenue | 7.1 Manage Tariff & Charges | Manage Network Charges | STPIS exemption | There is a need to revise the STPIS exemption business rules to account for planned and unplanned outages at third party metering sites | Revise current processes to ensure that STPIS exemptions can be applied for the appropriate scenarios: - Customer left off supply due to faulty third party meter installation - Outage caused by retailer or third party at a site | H | H | Enable systems to flag sites or cases (work orders) which are exempt from STIPS | [11 empty] | H | bar: OMS to CIS; BI
57 | Cost Recovery regulated metering services | 7. Manage Revenue | 7.1 Manage Tariff & Charges | Manage Non-Network Charges | Third party billing capability | Billing capabilities need to be updated to allow for more robust billing capabilities (e.g automatic calculation of fees) | Develop procedures for automated fee calculation considering scenarios : -within Victoria where smart meters already exist and the exit fee is higher | H | H | Enable systems to automatically calculateand bill third parties | [11 empty] | H | bar: CIS to CRM; BI
58 | Cost Recovery regulated metering services | 7. Manage Revenue | 7.1 Manage Tariff & Charges | Manage Tariffs and Forecasting | Third Party MCs may propose tariffs | Third Party MCs can propose a tariff they deem suitable when a new meter is installed / replaced at a customer premise. This may help avoid LNSPs charging incorrect tariffs based on the type of service offered to the customer. CP-PAL needs the ability to check (and possibly object) to tariffs proposed by market participants | Updated procedures required to validate proposed tariffs, and then accepting or objecting to them | L | L | System changes to validate proposed tariff against a set of protocols and accept or reject tariff | [10 empty] | L | L | bar: CIS; MTS
59 | Cost Recovery regulated metering services | 7. Manage Revenue | 7.1 Manage Tariff & Charges | Manage Revenue from Incentives | Standard charges for services to third party MC and external metering service providers | There is no standard fee structure agreed with third party MC and third party Metering Service Providers. No rules regarding which charges will be passed through vs "absorbed" | New Business Rules required to: - Determine the rates for services provided on site with third party meter - Determine fees for fault truck dispatched in error - Determine which charges/rates are levied on customers - Reconcile Metering Service Provider invoices against work completion details outlining services performed/materials used. | H | H | Create billing processes to bill third party market transactions | [11 empty] | M | bar: CIS; SAP
60 | N/A | 8. Manage Regulation & Compliance | 8.1 Manage Regulatory Affairs | Regulated Revenue / Strategy | N/A | No immediate impact determined, but may be impacted in the future |  | N/A | N/A | [12 empty] | N/A
61 | Roles & Responsibilities | 8. Manage Regulation & Compliance | 8.1 Manage Regulatory Affairs | Manage Accreditation/Compliance | Manage accreditation of contractors | There is a requirement that CP-PAL acting under the capacity of default MC, must be responsible for ensuring all contractors and service providers are sufficiently accredited and abide by the AER service specifications. CP-PAL needs to confirm the MC registration requirements and responsibilities as the Responsible Person for metering services. | Develop procedures for ensuring all contractors and service providers working for CP-PAL are sufficiently accredited | L | M | N/A | [11 empty] | N/A
62 | Roles & Responsibilities | 8. Manage Regulation & Compliance | 8.1 Manage Regulatory Affairs | Manage Accreditation/Compliance | New accreditation required | To remain compliant, CP-PAL will need additional accreditation for type 4 meters. | Manage Process for updating accreditation and registration, with consideration for : -work instructions for current transformer connected sites. -updating commissioning processes -VES rules | H | H | Enable systems to support handling type 4 meters |  | H |  | L | L | M | M |  | L | L | M | M

## Cost (Raw table)
|  |  | Effort | Process | Systems
|  |  | Very High (VH) | 65 | 650
|  |  | High (H) | 26 | 130
|  |  | Medium (M) | 15 | 65
|  |  | Low (L) | 6 | 26
Impact Assessment
Analysis | [5 empty] | Process | System | [10 empty] | Total
ID | Area | Process | Capability | Title | Comments | Effort | OMS | CIS | CRM | SAP | UIQ | MTS | IEE | BI | CFE/ E2E | Click | USB
1 | 1. Manage the Asset Infrastructure | 1.1 Manage Investments | Long & Medium Term Planning | N/A |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | 1. Manage the Asset Infrastructure | 1.1 Manage Investments | Investment Analysis | N/A |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | 1. Manage the Asset Infrastructure | 1.1 Manage Investments | Asset Investment Review | N/A |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | 1. Manage the Asset Infrastructure | 1.1 Manage Investments | Capital & OM Budgeting | N/A |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | 1. Manage the Asset Infrastructure | 1.2 Manage Asset Programs | Asset Planning | N/A |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | 1. Manage the Asset Infrastructure | 1.2 Manage Asset Programs | Construction Project Design & Estimation | N/A |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | 1. Manage the Asset Infrastructure | 1.2 Manage Asset Programs | Maintenance Forecasting | N/A |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8 | 1. Manage the Asset Infrastructure | 1.2 Manage Asset Programs | Project Sourcing | N/A |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9 | 1. Manage the Asset Infrastructure | 1.3 Manage Asset Strategy | Net. Analysis & Long Term Planning | N/A |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10 | 1. Manage the Asset Infrastructure | 1.3 Manage Asset Strategy | Reg./Asset Strat. Policy/Compliance | N/A |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11 | 1. Manage the Asset Infrastructure | 1.3 Manage Asset Strategy | Asset Risk Management | N/A |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12 | 1. Manage the Asset Infrastructure | 1.3 Manage Asset Strategy | Asset Perf. Condition & Predictive Management | N/A |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13 | 2. Meter Management | 2.1 Meter Asset Management | Provide Meter Assets | Meter Exchange between CP-PAL and third party meters |  | 65 | 0 | 130 | 65 | 26 | 65 | 65 | 26 | 130 | 26 | 65 | 65 | 728
14 | 2. Meter Management | 2.1 Meter Asset Management | Manage Meter Assets | Downgrade meter to be used as a network device |  | 15 | 0 | 65 | 26 | 26 | 26 | 26 | 0 | 65 | 0 | 0 | 65 | 314
15 | 2. Meter Management | 2.1 Meter Asset Management | Manage Meter Assets | Logical Conversion of type 5 meters to type 4 |  | 26 | 0 | 65 | 0 | 26 | 0 | 0 | 0 | 26 | 0 | 0 | 65 | 208
16 | 2. Meter Management | 2.1 Meter Asset Management | Manage Meter Assets | Managing retrieved meters |  | 6 | 0 | 0 | 0 | 26 | 0 | 0 | 0 | 26 | 0 | 0 | 0 | 58
17 | 2. Meter Management | 2.1 Meter Asset Management | Administer Meter Point | Revise current validation rules and workflows |  | 26 | 65 | 130 | 0 | 65 | 26 | 0 | 26 | 26 | 0 | 65 | 130 | 559
18 | 2. Meter Management | 2.2 Meter Data Management | Manage Meter Data | Third party metering data |  | 15 | 0 | 0 | 0 | 0 | 0 | 65 | 65 | 0 | 0 | 0 | 26 | 171
19 | 3. Market Interactions | 3.1 Manage Network Customer | B2B & CATS transactions | Handle new outgoing B2B market transactions |  | 65 | 0 | 130 | 0 | 0 | 0 | 130 | 0 | 65 | 0 | 0 | 130 | 520
20 | 3. Market Interactions | 3.1 Manage Network Customer | B2B & CATS transactions | Handling new incoming B2B market transactions |  | 65 | 0 | 130 | 0 | 0 | 0 | 130 | 0 | 65 | 0 | 0 | 130 | 520
21 | 3. Market Interactions | 3.1 Manage Network Customer | B2B & CATS transactions | Shared Market Protocol |  | 65 | 0 | 650 | 0 | 0 | 0 | 650 | 0 | 65 | 0 | 0 | 650 | 2080
22 | 3. Market Interactions | 3.1 Manage Network Customer | B2B & CATS transactions | Automate off-market Metering Requests |  | 15 | 0 | 26 | 26 | 0 | 0 | 0 | 0 | 65 | 65 | 0 | 65 | 262
23 | 3. Market Interactions | 3.1 Manage Network Customer | Service Provider Liaison | N/A |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24 | 3. Market Interactions | 3.2 Manage Consumer | End-user Management | Handle customer contact |  | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15
25 | 4. Plan, Manage & Execute | 4.1 Plan Work & Enterprise Resources | Integrated Resource & Supply Chain Planning | N/A |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
26 | 4. Plan, Manage & Execute | 4.1 Plan Work & Enterprise Resources | Contractor Strategy | N/A |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
27 | 4. Plan, Manage & Execute | 4.1 Plan Work & Enterprise Resources | Delivery Performance Management | N/A |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
28 | 4. Plan, Manage & Execute | 4.2 Manage & Execute Work | E2E - New Connections | Third party meter New connections |  | 15 | 0 | 0 | 0 | 65 | 0 | 26 | 0 | 0 | 26 | 65 | 65 | 262
29 | 4. Plan, Manage & Execute | 4.2 Manage & Execute Work | Schedule | Multi-party appointment capabilities required |  | 26 | 65 | 26 | 130 | 130 | 0 | 0 | 0 | 130 | 130 | 65 | 65 | 767
30 | 4. Plan, Manage & Execute | 4.2 Manage & Execute Work | Schedule | Route Planning |  | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15
31 | 4. Plan, Manage & Execute | 4.2 Manage & Execute Work | E2E - Maintenance / Replacement & Network Augmentation | Inspecting third party metering work |  | 15 | 0 | 26 | 0 | 0 | 26 | 0 | 0 | 0 | 0 | 0 | 0 | 67
32 | 4. Plan, Manage & Execute | 4.2 Manage & Execute Work | E2E - Additions and Alterations | Handling of adds and alts for non-CP-PAL meters |  | 26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26
33 | 4. Plan, Manage & Execute | 4.2 Manage & Execute Work | E2E - Emergency & Repair | Emergency and Outage management |  | 26 | 65 | 0 | 65 | 26 | 0 | 26 | 0 | 26 | 0 | 65 | 0 | 299
34 | 4. Plan, Manage & Execute | 4.2 Manage & Execute Work | E2E - Abolishment | Handling Site Abolishment |  | 15 | 0 | 26 | 0 | 65 | 0 | 0 | 0 | 65 | 65 | 65 | 26 | 327
35 | 4. Plan, Manage & Execute | 4.2 Manage & Execute Work | E2E - Retailer initiated work | Planned outages with DNSP involvement |  | 15 | 65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 65 | 65 | 26 | 236
36 | 4. Plan, Manage & Execute | 4.3 Plan & Manage Supply Chain | Plan Material Demand | N/A |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
37 | 4. Plan, Manage & Execute | 4.3 Plan & Manage Supply Chain | Procure Material and Service | N/A |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
38 | 4. Plan, Manage & Execute | 4.3 Plan & Manage Supply Chain | Manage Materials | N/A |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
39 | 4. Plan, Manage & Execute | 4.3 Plan & Manage Supply Chain | Receipt, Store & Deliver | N/A |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
40 | 4. Plan, Manage & Execute | 4.3 Plan & Manage Supply Chain | Pay Supplier | N/A |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
41 | 4. Plan, Manage & Execute | 4.3 Plan & Manage Supply Chain | Manage Supply Chain Systems | N/A |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
42 | 5. Operate the Network | 5.1 Enable Smart Network Operations | Perform Operational Planning | N/A |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
43 | 5. Operate the Network | 5.1 Enable Smart Network Operations | Provide Operational Support | N/A |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
44 | 5. Operate the Network | 5.1 Enable Smart Network Operations | Real Time Operation & Control | No outage notification in minimum service specification |  | 15 | 130 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 65 | 210
45 | 5. Operate the Network | 5.1 Enable Smart Network Operations | Manage Planned Events | Planned outages with NO DNSP involvement |  | 26 | 65 | 0 | 26 | 0 | 26 | 65 | 0 | 65 | 0 | 0 | 65 | 338
46 | 5. Operate the Network | 5.1 Enable Smart Network Operations | Manage Un-planned Events | N/A |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
47 | 5. Operate the Network | 5.1 Enable Smart Network Operations | Manage Network Quality | Meter Removals affect network quality |  | 65 | 65 | 0 | 0 | 0 | 130 | 0 | 0 | 130 | 0 | 0 | 0 | 390
48 | 5. Operate the Network | 5.1 Enable Smart Network Operations | Manage Distributed Generation | Solar pre-approval |  | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26 | 0 | 0 | 32
49 | 6. Manage Network Data & Smart Infrastructure | 6.1 Manage Governance and Architecture | Manage Information Strategy & Architecture | N/A |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
50 | 6. Manage Network Data & Smart Infrastructure | 6.1 Manage Governance and Architecture | Manage Data / Information Governance and Audit | N/A |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
51 | 6. Manage Network Data & Smart Infrastructure | 6.2 Manage Data & Analytics/Modelling | Network Assets Data | N/A |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
52 | 6. Manage Network Data & Smart Infrastructure | 6.2 Manage Data & Analytics/Modelling | Process Meter Data | Meter data analytics |  | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 65 | 0 | 0 | 0 | 80
53 | 6. Manage Network Data & Smart Infrastructure | 6.3 Manage Communications Infrastructure & Security | Manage Comms. Environment | Pre-emptive actions for potential meter removal sites |  | 26 | 130 | 26 | 0 | 0 | 26 | 26 | 0 | 0 | 0 | 0 | 65 | 299
54 | 6. Manage Network Data & Smart Infrastructure | 6.3 Manage Communications Infrastructure & Security | Manage Comms. Environment | Lower specced meters |  | 6 | 0 | 26 | 0 | 0 | 0 | 26 | 0 | 0 | 0 | 0 | 26 | 84
55 | 6. Manage Network Data & Smart Infrastructure | 6.3 Manage Communications Infrastructure & Security | Manage Security & Configuration Management | Remote de-en / re-en through network device |  | 26 | 0 | 0 | 0 | 26 | 26 | 0 | 0 | 26 | 0 | 0 | 0 | 104
56 | 7. Manage Revenue | 7.1 Manage Tariff & Charges | Manage Network Charges | STPIS exemption |  | 26 | 26 | 26 | 0 | 0 | 0 | 0 | 0 | 26 | 0 | 0 | 0 | 104
57 | 7. Manage Revenue | 7.1 Manage Tariff & Charges | Manage Non-Network Charges | Third party billing capability |  | 26 | 0 | 65 | 65 | 0 | 0 | 0 | 0 | 65 | 0 | 0 | 0 | 221
58 | 7. Manage Revenue | 7.1 Manage Tariff & Charges | Manage Tariffs and Forecasting | Third Party MCs may propose tariffs |  | 6 | 0 | 26 | 0 | 0 | 0 | 26 | 0 | 0 | 0 | 0 | 26 | 84
59 | 7. Manage Revenue | 7.1 Manage Tariff & Charges | Manage Revenue from Incentives | Standard charges for services to third party MC and external metering service providers |  | 26 | 0 | 26 | 0 | 26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 78
60 | 8. Manage Regulation & Compliance | 8.1 Manage Regulatory Affairs | Regulated Revenue / Strategy | N/A |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
61 | 8. Manage Regulation & Compliance | 8.1 Manage Regulatory Affairs | Manage Accreditation/Compliance | Manage accreditation of contractors |  | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6
62 | 8. Manage Regulation & Compliance | 8.1 Manage Regulatory Affairs | Manage Accreditation/Compliance | New accreditation required |  | 26 | 0 | 130 | 0 | 26 | 26 | 65 | 65 | 0 | 26 | 26 | 65 | 455
0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## List (hidden)
Impact | Priority
VH | H
H | M
M | L
L | N/A
N/A

## DPCache_Cost (Raw table) (hidden)
ID | Area | Process | Capability | Title | Comments | Effort | Effort2 | OMS | CIS | CRM | SAP | UIQ | MTS | IEE | BI | CFE/ E2E | Click | USB
0 | 1. Manage the Asset Infrastructure | 1.1 Manage Investments | Long & Medium Term Planning | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 1. Manage the Asset Infrastructure | 1.1 Manage Investments | Investment Analysis | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 1. Manage the Asset Infrastructure | 1.1 Manage Investments | Asset Investment Review | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 1. Manage the Asset Infrastructure | 1.1 Manage Investments | Capital & OM Budgeting | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 1. Manage the Asset Infrastructure | 1.2 Manage Asset Programs | Asset Planning | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 1. Manage the Asset Infrastructure | 1.2 Manage Asset Programs | Construction Project Design & Estimation | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 1. Manage the Asset Infrastructure | 1.2 Manage Asset Programs | Maintenance Forecasting | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 1. Manage the Asset Infrastructure | 1.2 Manage Asset Programs | Project Sourcing | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 1. Manage the Asset Infrastructure | 1.3 Manage Asset Strategy | Net. Analysis & Long Term Planning | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 1. Manage the Asset Infrastructure | 1.3 Manage Asset Strategy | Reg./Asset Strat. Policy/Compliance | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 1. Manage the Asset Infrastructure | 1.3 Manage Asset Strategy | Asset Risk Management | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 1. Manage the Asset Infrastructure | 1.3 Manage Asset Strategy | Asset Perf. Condition & Predictive Management | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1 | 2. Meter Management | 2.1 Meter Asset Management | Provide Meter Assets | Meter Exchange between CP-PAL and third party meters |  | 65 | 26 | 0 | 130 | 65 | 26 | 65 | 65 | 26 | 130 | 26 | 65 | 65
2 | 2. Meter Management | 2.1 Meter Asset Management | Manage Meter Assets | Downgrade meter to be used as a network device |  | 15 | 6 | 0 | 65 | 26 | 26 | 26 | 26 | 0 | 65 | 0 | 0 | 65
3 | 2. Meter Management | 2.1 Meter Asset Management | Manage Meter Assets | Logical Conversion of type 5 meters to type 4 |  | 26 | 26 | 0 | 65 | 0 | 26 | 0 | 0 | 0 | 26 | 0 | 0 | 65
4 | 2. Meter Management | 2.1 Meter Asset Management | Manage Meter Assets | Managing retrieved meters |  | 6 | 6 | 0 | 0 | 0 | 26 | 0 | 0 | 0 | 26 | 0 | 0 | 0
5 | 2. Meter Management | 2.1 Meter Asset Management | Administer Meter Point | Review current validation rules and workflows |  | 26 | 6 | 65 | 130 | 0 | 65 | 26 | 0 | 26 | 26 | 0 | 65 | 130
6 | 2. Meter Management | 2.2 Meter Data Management | Manage Meter Data | Third party metering data |  | 15 | 6 | 0 | 0 | 0 | 0 | 0 | 65 | 65 | 0 | 0 | 0 | 26
7 | 2. Meter Management | 2.2 Meter Data Management | Publish Meter Data | Self-Service Portal for consumers (To Be removed - see comments) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8 | 2. Meter Management | 2.2 Meter Data Management | Publish Meter Data | Customer data access management (To Be removed - see comments) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9 | 3. Market Interactions | 3.1 Manage Network Customer | B2B & CATS transactions | Handle new outgoing B2B market transactions |  | 65 | 6 | 0 | 130 | 0 | 0 | 0 | 130 | 0 | 65 | 0 | 0 | 130
10 | 3. Market Interactions | 3.1 Manage Network Customer | B2B & CATS transactions | Handling new incoming B2B market transactions |  | 65 | 6 | 0 | 130 | 0 | 0 | 0 | 130 | 0 | 65 | 0 | 0 | 130
11 | 3. Market Interactions | 3.1 Manage Network Customer | B2B & CATS transactions | Shared Market Protocol |  | 65 | 26 | 0 | 650 | 0 | 0 | 0 | 650 | 0 | 65 | 0 | 0 | 650
12 | 3. Market Interactions | 3.1 Manage Network Customer | B2B & CATS transactions | Automate off-market Metering Requests |  | 15 | 0 | 0 | 26 | 26 | 0 | 0 | 0 | 0 | 65 | 65 | 0 | 65
10 | 3. Market Interactions | 3.1 Manage Network Customer | Service Provider Liaison | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13 | 3. Market Interactions | 3.2 Manage Consumer | End-user Management | Handle customer contact |  | 15 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14 | 3. Market Interactions | 3.2 Manage Consumer | Third Party Liaison | Provide meter data to third parties (To Be removed - see comments) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 4. Plan, Manage & Execute | 4.1 Plan Work & Enterprise Resources | Integrated Resource & Supply Chain Planning | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14 | 4. Plan, Manage & Execute | 4.1 Plan Work & Enterprise Resources | Contractor Strategy | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15 | 4. Plan, Manage & Execute | 4.1 Plan Work & Enterprise Resources | Delivery Performance Management | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15 | 4. Plan, Manage & Execute | 4.2 Manage & Execute Work | E2E - New Connections | Third party meter New connections |  | 15 | 6 | 0 | 0 | 0 | 65 | 0 | 26 | 0 | 0 | 26 | 65 | 65
16 | 4. Plan, Manage & Execute | 4.2 Manage & Execute Work | Schedule | Multi-party appointment capabilities required |  | 26 | 15 | 65 | 26 | 130 | 130 | 0 | 0 | 0 | 130 | 130 | 65 | 65
17 | 4. Plan, Manage & Execute | 4.2 Manage & Execute Work | Schedule | Route Planning |  | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
18 | 4. Plan, Manage & Execute | 4.2 Manage & Execute Work | E2E - Maintenance / Replacement & Network Augmentation | Inspecting third party metering work |  | 15 | 15 | 0 | 26 | 0 | 0 | 26 | 0 | 0 | 0 | 0 | 0 | 0
19 | 4. Plan, Manage & Execute | 4.2 Manage & Execute Work | E2E - Additions and Alterations | Handling of adds and alts for non-CP-PAL meters |  | 26 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20 | 4. Plan, Manage & Execute | 4.2 Manage & Execute Work | E2E - Emergency & Repair | Emergency and Outage management |  | 26 | 6 | 65 | 0 | 65 | 26 | 0 | 26 | 0 | 26 | 0 | 65 | 0
21 | 4. Plan, Manage & Execute | 4.2 Manage & Execute Work | E2E - Abolishment | Handling Site Abolishment |  | 15 | 6 | 0 | 26 | 0 | 65 | 0 | 0 | 0 | 65 | 65 | 65 | 26
22 | 4. Plan, Manage & Execute | 4.2 Manage & Execute Work | E2E - Retailer initiated work | Planned outages with DNSP involvement |  | 15 | 0 | 65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 65 | 65 | 26
0 | 4. Plan, Manage & Execute | 4.3 Plan & Manage Supply Chain | Plan Material Demand | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 4. Plan, Manage & Execute | 4.3 Plan & Manage Supply Chain | Procure Material and Service | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 4. Plan, Manage & Execute | 4.3 Plan & Manage Supply Chain | Manage Materials | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 4. Plan, Manage & Execute | 4.3 Plan & Manage Supply Chain | Receipt, Store & Deliver | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 4. Plan, Manage & Execute | 4.3 Plan & Manage Supply Chain | Pay Supplier | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 4. Plan, Manage & Execute | 4.3 Plan & Manage Supply Chain | Manage Supply Chain Systems | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 5. Operate the Network | 5.1 Enable Smart Network Operations | Perform Operational Planning | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 5. Operate the Network | 5.1 Enable Smart Network Operations | Provide Operational Support | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23 | 5. Operate the Network | 5.1 Enable Smart Network Operations | Real Time Operation & Control | No outage notification in minimum service specification |  | 15 | 15 | 130 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 65
24 | 5. Operate the Network | 5.1 Enable Smart Network Operations | Manage Planned Events | Planned outages with NO DNSP involvement |  | 26 | 6 | 65 | 0 | 26 | 0 | 26 | 65 | 0 | 65 | 0 | 0 | 65
0 | 5. Operate the Network | 5.1 Enable Smart Network Operations | Manage Un-planned Events | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
25 | 5. Operate the Network | 5.1 Enable Smart Network Operations | Manage Network Quality | Meter Removals affect network quality |  | 65 | 0 | 65 | 0 | 0 | 0 | 130 | 0 | 0 | 130 | 0 | 0 | 0
26 | 5. Operate the Network | 5.1 Enable Smart Network Operations | Manage Distributed Generation | Solar pre-approval |  | 6 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26 | 0 | 0
0 | 6. Manage Network Data & Smart Infrastructure | 6.1 Manage Governance and Architecture | Manage Information Strategy & Architecture | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 6. Manage Network Data & Smart Infrastructure | 6.1 Manage Governance and Architecture | Manage Data / Information Governance and Audit | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 6. Manage Network Data & Smart Infrastructure | 6.2 Manage Data & Analytics/Modelling | Network Assets Data | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
27 | 6. Manage Network Data & Smart Infrastructure | 6.2 Manage Data & Analytics/Modelling | Process Meter Data | Meter data analytics |  | 15 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 65 | 0 | 0 | 0
28 | 6. Manage Network Data & Smart Infrastructure | 6.3 Manage Communications Infrastructure & Security | Manage Comms. Environment | Pre-emptive actions for potential meter removal sites |  | 26 | 15 | 130 | 26 | 0 | 0 | 26 | 26 | 0 | 0 | 0 | 0 | 65
29 | 6. Manage Network Data & Smart Infrastructure | 6.3 Manage Communications Infrastructure & Security | Manage Comms. Environment | Lower specced meters |  | 6 | 0 | 0 | 26 | 0 | 0 | 0 | 26 | 0 | 0 | 0 | 0 | 26
30 | 6. Manage Network Data & Smart Infrastructure | 6.3 Manage Communications Infrastructure & Security | Manage Security & Configuration Management | Remote de-en / re-en through network device |  | 26 | 6 | 0 | 0 | 0 | 26 | 26 | 0 | 0 | 26 | 0 | 0 | 0
31 | 7. Manage Revenue | 7.1 Manage Tariff & Charges | Manage Network Charges | STPIS exemption |  | 26 | 0 | 26 | 26 | 0 | 0 | 0 | 0 | 0 | 26 | 0 | 0 | 0
32 | 7. Manage Revenue | 7.1 Manage Tariff & Charges | Manage Non-Network Charges | Third party billing capability |  | 26 | 6 | 0 | 65 | 65 | 0 | 0 | 0 | 0 | 65 | 0 | 0 | 0
33 | 7. Manage Revenue | 7.1 Manage Tariff & Charges | Manage Tariffs and Forecasting | Third Party MCs may propose tariffs |  | 6 | 6 | 0 | 26 | 0 | 0 | 0 | 26 | 0 | 0 | 0 | 0 | 26
34 | 7. Manage Revenue | 7.1 Manage Tariff & Charges | Manage Revenue from Incentives | Standard charges for services to third party MC and external metering service providers |  | 26 | 0 | 0 | 26 | 0 | 26 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 8. Manage Regulation & Compliance | 8.1 Manage Regulatory Affairs | Regulated Revenue / Strategy | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35 | 8. Manage Regulation & Compliance | 8.1 Manage Regulatory Affairs | Manage Accreditation/Compliance | Manage accreditation of contractors |  | 6 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
36 | 8. Manage Regulation & Compliance | 8.1 Manage Regulatory Affairs | Manage Accreditation/Compliance | New accreditation required |  | 26 | 6 | 0 | 130 | 0 | 26 | 26 | 65 | 65 | 0 | 26 | 26 | 65

## DPCache_3.Compliance Impacts As (hidden)
ID | Rule Change | Area | Process | Capability | Title | Description of Change | CitiPower | Powercor | SAPN | Description | Level | Priority | Description2 | Level2 | Priority2 | Description3 | DMS | CIS | CRM | SAP | UIQ | MTS | IEE | BI | CFE/ E2E | Click | USB | Priority3 | Comments / Notes | . | CSG | Metering | IT | Tariff/ Regulatory
|  | 1. Manage the Asset Infrastructure | 1.1 Manage Investments | Long & Medium Term Planning | [6 empty] | N/A | N/A |  | N/A | N/A | [12 empty] | N/A
|  | 1. Manage the Asset Infrastructure | 1.1 Manage Investments | Investment Analysis | [6 empty] | N/A | N/A |  | N/A | N/A | [12 empty] | N/A
|  | 1. Manage the Asset Infrastructure | 1.1 Manage Investments | Asset Investment Review | [6 empty] | N/A | N/A |  | N/A | N/A | [12 empty] | N/A
|  | 1. Manage the Asset Infrastructure | 1.1 Manage Investments | Capital & OM Budgeting | [6 empty] | N/A | N/A |  | N/A | N/A | [12 empty] | N/A
|  | 1. Manage the Asset Infrastructure | 1.2 Manage Asset Programs | Asset Planning | [6 empty] | N/A | N/A |  | N/A | N/A | [12 empty] | N/A
|  | 1. Manage the Asset Infrastructure | 1.2 Manage Asset Programs | Construction Project Design & Estimation | [6 empty] | N/A | N/A |  | N/A | N/A | [12 empty] | N/A
|  | 1. Manage the Asset Infrastructure | 1.2 Manage Asset Programs | Maintenance Forecasting | [6 empty] | N/A | N/A |  | N/A | N/A | [12 empty] | N/A
|  | 1. Manage the Asset Infrastructure | 1.2 Manage Asset Programs | Project Sourcing | [6 empty] | N/A | N/A |  | N/A | N/A | [12 empty] | N/A
|  | 1. Manage the Asset Infrastructure | 1.3 Manage Asset Strategy | Net. Analysis & Long Term Planning | [6 empty] | N/A | N/A |  | N/A | N/A | [12 empty] | N/A
|  | 1. Manage the Asset Infrastructure | 1.3 Manage Asset Strategy | Reg./Asset Strat. Policy/Compliance | [6 empty] | N/A | N/A |  | N/A | N/A | [12 empty] | N/A
|  | 1. Manage the Asset Infrastructure | 1.3 Manage Asset Strategy | Asset Risk Management | [6 empty] | N/A | N/A |  | N/A | N/A | [12 empty] | N/A
|  | 1. Manage the Asset Infrastructure | 1.3 Manage Asset Strategy | Asset Perf. Condition & Predictive Management | [6 empty] | N/A | N/A |  | N/A | N/A | [12 empty] | N/A
1 | Roles & Responsibilities | 2. Meter Management | 2.1 Meter Asset Management | Provide Meter Assets | Meter Exchange between CP-PAL and third party meters | At scale processes required for handling churn data in scenarios where a CP-PAL meter is removed by a third party MP while CP-PAL is still the active MDP. | YES | YES | YES | Develop processes for "transitional procedures", considering: -Collecting final meter information to fulfil MDP obligations. -flagging and handling the "loss" of the meter in systems -Will CP-PAL attend the site during a meter exchange -defining the business rules for the process | VH | H | Training employees on new system functionalities and process change | H | H | Possible change in system to -Flag the site which has undergone meter exchange and stop all data collection processes -Supress alerts for "missing meter" on the site -Remove site from route planning and scheduling in regards to metering services |  | H | M | L | M | M | L | H | L | M | M | H | David Rofe/Vannasone Sihathep: There is a need for updating existing and new BI report Gary: Additional BI requirements now captured Binu: SAP BI Data Warehouse sources data from various systems such as SAP, UIQ, MTS, CIS, IEE. If SAP, IEE, UIQ and CIS are going to be highly impacted then BI will likely be highly impacted as well. Gary: BI impact captured as "H" |  | 1 | 1 | 1
2 | Access to Network Devices | 2. Meter Management | 2.1 Meter Asset Management | Manage Meter Assets | Downgrade meter to be used as a network device | New processes required for classification of meters as "network devices" where third party meters are installed and the CP-PAL meter is retained. | YES | YES |  | Develop new processes which must consider: - Removal of any metrology-related logic associated with collected data. - CP-PAL's rights to use consumption data for different business purposes. - Handling of network device faults and ongoing testing/maintenance requirements. - Function of the network device (including for load control). - Approach to handling network device removal by an incoming MP who has justified removal on the basis of space constraints or safety reasons. -business rules | M | M | Training on new system functionalities | L | L | Enable systems to reclassify a meter to a network device, with considerations for: -The degree of functionality and data collection that must be disabled, changed or restricted | [10 empty] | M | M | David Rofe/Vannasone Sihathep: May need a change to CIS will need to show meter onsite is a network device. Gary: Impact to CIS now captured Sam Mavraganis: Could see an increase in meters being removed/dumped as not requiring smart meters at site/house etc. May see as obtaining a third party meter in avoiding a smart meter at property and therefore see CP/PAL meter as a threat as "network device" - ombudsman/customer complaints increasing Gary: impact to customer complaints now captured in line item ID11 "Handle Customer Contact" Binu: SAP BI Data Warehouse sources data from various systems such as SAP, UIQ, MTS, CIS, IEE. If SAP, IEE, UIQ and CIS are going to be highly impacted then BI will likely be highly impacted as well. Gary: BI Impact captured (mostly low to medium impact on other systems so BI impact is "M") |  |  | 1 | 1 | bar: CIS to MTS; BI
3 | Access to Network Devices | 2. Meter Management | 2.1 Meter Asset Management | Manage Meter Assets | Logical Conversion of type 5 meters to type 4 | The Derogation expiry in Dec 2017 will also mean the expiry of the rule to allow all VIC AMI meters to be classified as type 5 meters. These meters will need to be reclassified as type 4. | YES | YES | YES | Develop new processes which must consider: - Bulk reclassification requirements - Exception handling and manual workaround -all validation and workflow impacts of the reclassification -accreditation requirements -exception handling | H | H | Back Office support required to handle exceptions: | H | H | Enable bulk reclassification of VIC AMI type 5 meters to type 4, considering, -ability to perform mass updates for MSATS? Possible reconfiguration of current workflows and validation rules | [10 empty] | M | H | Binu: SAP BI Data Warehouse sources data from various systems such as SAP, UIQ, MTS, CIS, IEE. If SAP, IEE, UIQ and CIS is going to be highly impacted then BI will likely be highly impacted as well. Gary: BI impact captured as L |  |  |  | 1 | bar: CIS; SAP; BI
4 | Cost Recovery regulated metering services | 2. Meter Management | 2.1 Meter Asset Management | Manage Meter Assets | Managing retrieved meters | Revised processes required for handling an increased volume of "returned meters" including any requirements for final reads (in particular for non AMI sites), asset refurbishment and disposal. | YES | YES | YES | Develop procedures for handling increased volumes of meters returning from the field, including considerations for storing, reselling, refurbishment or redeploy into the field. Review material demand planning for new meters | L | L | Train employees to be able to -handle large volumes of incoming "returned meters" | L | L | Current systems able to handle meter returns, but may need to consider the scenario of increased volumes | [11 empty] | L | David Rofe/Vannasone Sihathep: Potential non compliance if meter data isn't provided from the new MC. Gary: Capturing of data for removed meters captured in line item ID1 "Meter Exchange between CP-PAL and third party meters' Binu: BI Data warehousing systems may be affected, we expect new reporting requirements to provide analysis of returned meters. Gary: Bi requirements captured |  |  | 1 | 1 | bar: SAP; BI
5 | Roles & Responsibilities | 2. Meter Management | 2.1 Meter Asset Management | Administer Meter Point | Review current validation rules and workflows | Current system rules and workflows may cause issues once the rule change come into effect. (e.g. automated rules may wrongly assign new connection sites with type 4 meter as large site, when the actual site is small customer, or assign wrong tariff, etc.) | YES | YES | ? | Review current processes to ensure that the systems will function correctly when the new rules come into affect on December 2016, including: -automated site type allocation -automated tariff allocation -automated billing of retailers | H | M | Train employees on any changes that are made to system rules and workflows. | L | L | Test current systems to ensure that they will function correctly when the new rules come into affect on December 2016 , considering: -automated site type allocation -automated tariff allocation -automated billing of retailers | M | H |  | M | L |  | L | L |  | M | H | M |  |  |  |  | 1
6 | Roles & Responsibilities | 2. Meter Management | 2.2 Meter Data Management | Manage Meter Data | Third party metering data | Third party MDP's will provide an increasing number of meter reads. Consequently, processes for meter data management, network billing, etc. need to account for reads incoming from NEM participants, rather than solely from internal reading capability. | YES | YES |  | Revise current meter read processes to account for receiving data from NEM participants, taking into consideration: -the frequency of publishing of meter data from third parties. -validating that the data received is correct -exception handling for large volumes of exceptions -process for handling missing data at scale | M | H | Training for employees to be able to: -monitor incoming data from market participants -validate the incoming data and handle exceptions | L | M | System updates to allow metering data to be received from external NEM participants Automation of PMDR process | [10 empty] | L | M |  |  |  | 1 | 1 | bar: MTS to IEE
7 | Consumer Arrangements | 2. Meter Management | 2.2 Meter Data Management | Publish Meter Data | Self-Service Portal for consumers (To Be removed - see comments) | The rules stipulate that consumers must be given access to their metering data. A self-service portal is the most efficient method to provide this information NOTE: Already being delivered in a separate parallel project | YES | YES | YES | Develop self-service portal for customers, with consideration for: -the type of data customers will have access to -additional services (consumption analysis, comparison charts) -authentication and authorisation | N/A | N/A | Train employees to be able to: -understand the rules around the type and amount of data that can be provided to the customer -answer customer queries around the self-service portal, and their metering data | N/A | N/A | Design and develop self-service portal for customers, along with updated FAQs., with consideration for: -data privacy | [11 empty] | N/A | A parallel project is already underway to deliver these requirements All new reporting requirements will be handled outside of SAP B I |  | 1 |  | 1
8 | Consumer Arrangements | 2. Meter Management | 2.2 Meter Data Management | Publish Meter Data | Customer data access management (To Be removed - see comments) | After a customer churn, metering data will no longer be supplied to the customer by CP-PAL. Processes need to account for data de-provisioning, historical data, and compliance. NOTE: Already being delivered in a separate parallel project | YES | YES | YES | Develop processes to account for customer churning away from CP-PAL, with consideration for - removing customer access to new data - provisioning of historical data - informing the customer - compliance with the rules and regulations | N/A | N/A | N/A | N/A | N/A | Enable systems to support customer de-provisioning, storage of customer historical data | [11 empty] | N/A | A parallel project is already underway to deliver these requirements Self service portal will take care of the data extraction for third party hence no involvement of SAP BI tool sets. |  |  |  | 1
9 | Roles & Responsibilities | 3. Market Interactions | 3.1 Manage Network Customer | B2B & CATS transactions | Customer data access management (To Be removed - see comments) | When meters on CP-PAL site becomes contestable, there may be a need for CP-PAL to raise B2B market Service Orders (10 in total) to external Service Providers (previously CP-PAL will be receiving these Service Orders but not raising them) | YES | YES |  | Develop procedures for raising B2B service orders . Including: -Which of the 10 Service Orders will need to be raised -Exception management for failed Service Orders -Define business rules -Apply AEMO guidelines and procedures | VH | H | Train employees to be able to: -raise, monitor and close B2B market transactions (e.g. Service Orders) | L | L | Update systems to be able to raise and track Service Orders when previously CP-PAL only needed to receive and not raise these Service Orders. | [10 empty] | H | M | VG: This should be Medium as we may need to change Click to include options not our meter etc. How about Remote Energisation. Do we require changes (USB?) Gary: Changes for Click now captured in line ID22 "Planned outages with DNSP involvement". Remote energisation of CP-PAL meters assumed to be part of BAU activities and not costed as part of this project. Binu: SAP BI Data Warehouse sources data from various systems such as SAP, UIQ, MTS, CIS, IEE. If SAP, IEE, UIQ and CIS is going to be highly impacted then BI will likely be highly impacted as well. Gary: BI Impact captured (only MTS impacted so BI impact is "L") |  | 1 |  | 1 | bar: CIS; MTS; BI
10 | Roles & Responsibilities | 3. Market Interactions | 3.1 Manage Network Customer | B2B & CATS transactions | Handling new incoming B2B market transactions | With the introduction of the new MC role, CP-PAL will need to define how market transactions and B2B communications will be handled (e.g. incoming requests, etc.) | YES | YES | YES | Develop processes for handling new and existing market transactions, taking into consideration: -changes in business rules, workflows and validations -new MC role Change requests | VH | H | Training on new system functionalities | L | H | Enable systems to receive new B2B transactions from the market, taking into consideration increased volume of messages. -review workflows and validation | [10 empty] | H | M |  |  | 1 |  | 1 | bar: CIS; MTS; BI
11 | Minimum Service Specification | 3. Market Interactions | 3.1 Manage Network Customer | B2B & CATS transactions | Shared Market Protocol | Current systems and processes will require changes with the introduction of the shared market protocol | YES | YES | YES | Develop processes for handling the shared market protocol, considering changes to: - Service Order (B2B) Processes. - Role Appointment Processes. - Connection Point Management Process - Objection processes. - Jurisdictional differences | VH | M | Training on changes brought about by shared market protocol (process and systems) | H | M | Enable systems to accommodate -real time or near real time message transfer capabilities -changes to the B2B e-hub -security | [10 empty] | VH | M |  |  | 1 |  | 1 | bar: CIS; MTS; BI
12 | Roles & Responsibilities | 3. Market Interactions | 3.1 Manage Network Customer | B2B & CATS transactions | Automate off-market Metering Requests | Currently CitiPower handles off-market metering requests via manual paperwork. Manual process can’t be scaled up to handle the increasing volumes of meter requests and automation is required | YES | YES | YES | Develop procedures for automatic processing of Metering Requests forms that come in from retailers. | M | L | N/A | N/A | N/A | Automate systems to be able to receive, and action metering request forms, as well as sending out automated notifications upon receipt, cancellation and closure of the metering work | [8 empty] | M |  | M | L | David Rofe/Vannasone Sihathep: Change to system will require changes to MTS. Gary: Impact o MTS not required as advised by Eugene Binu: We expect new reporting requirements for CRM/CIS hence BI impact is M Gary: BI Impact captured |  | 1 |  | 1 | bar: CIS to CRM; BI
10 | Roles & Responsibilities | 3. Market Interactions | 3.1 Manage Network Customer | Service Provider Liaison | [6 empty] | N/A | N/A |  | N/A | N/A | [12 empty] | N/A
13 | Consumer Arrangements | 3. Market Interactions | 3.2 Manage Consumer | End-user Management | Handle customer contact | Training required for customer service around the implications of a contestable metering market to CP-PAL's role and responsibilities, particularly around differentiating between a CP-PAL issue and a retailer issue (meter issue and network issue) | YES | YES | YES | Develop training procedures, processes and scripts for customer service desk, escalation team, and claims team, considering the following scenarios: - claims and queries relating to outages initiated by retailer - enquiries relating to faults in non-CP-PAL meters -complaints (e.g. customer does not want both network device and third party meter on premise) -increased volumes of customer contact leading to increased costs | M | M | Train customer service employees to be able to: -understand the implications of the new rule change -CP-PAL's new roles and responsibilities in light of the change -differentiate between a meter issue and network issue (for premises with a third party MC) | M | M | N/A | [11 empty] | N/A | VG: Is CFE impacted here? Gary: This is mainly to do with employee training hence no system impacts Embah Beaton: Additional phone calls and emails from confused customers including RECs. Increase cost from increased call duration and the cost of additional EWOV complaints. Gary: Volume impacts now captured in the process description Embah Beaton: Removal of our meters without prior notification may lead IVR to provide incorrect messages to customers. Potential for fault trucks to sent when their not required. Gary: This is captured in line litem ID25 "Planned outages with NO DNSP involvement" |  | 1
14 | Consumer Arrangements | 3. Market Interactions | 3.2 Manage Consumer | Third Party Liaison | Provide meter data to third parties (To Be removed - see comments) | Customers will be able to agree to make data available to third parties. MC and MDP are not obligated to provide the data but the data may be provided upon commercial agreement with the MC/MDP/ third party provider. | YES | YES |  | Develop procedures for providing data to third parties, including: -format of file -Degree of information that can be readily provided and information that is restricted -the fees involved | N/A | N/A | Train employees to be able to: -understand the rules around the type and amount of data that can be provided to third parties | N/A | N/A | Update systems to easily extract customer metering information to be provided to third party, considering the possibility of allowing metering data to be accessed via self-service portal | [11 empty] | N/A | A parallel project is already underway to deliver these requirements |  | 1 |  | 1
|  | 4. Plan, Manage & Execute | 4.1 Plan Work & Enterprise Resources | Integrated Resource & Supply Chain Planning | [6 empty] | N/A | N/A |  | N/A | N/A | [12 empty] | N/A
14 | Roles & Responsibilities | 4. Plan, Manage & Execute | 4.1 Plan Work & Enterprise Resources | Contractor Strategy | [6 empty] | N/A | N/A |  | N/A | N/A | [12 empty] | N/A |  |  | 1 | 1 | 1 | 1
15 | Roles & Responsibilities | 4. Plan, Manage & Execute | 4.1 Plan Work & Enterprise Resources | Delivery Performance Management | [6 empty] | N/A | N/A |  | N/A | N/A | [12 empty] | N/A |  |  |  | 1
15 | Roles & Responsibilities | 4. Plan, Manage & Execute | 4.2 Manage & Execute Work | E2E - New Connections | Third party meter New connections | Revision of new connections process in the context of third party meter providers installing meters at mass market sites. CP-PAL will be expected to allocate NMI in such instances, but third parties will be responsible for installing meters and maintaining connection point details. | YES | YES | ? | Revise processes for third party new connections, taking into consideration - "Allocate NMI" SO may be more suitable in these cases (previously using "Create NMI" SO) - System implications of creating all required information in the system with the exception of metering information -CP-PAL responsibilities of attending the new connection site | M | H | Train employees to be able to: -identify if the MP for the site is third party -understand procedures for handling new connections with third party MP | L | H | System changes to recognise that metering work is performed by third party and not by CP-PAL | [8 empty] | L | M | M | H |  |  | 1 | 1 | 1 | bar: SAP; MTS
16 | Roles & Responsibilities | 4. Plan, Manage & Execute | 4.2 Manage & Execute Work | Schedule | Multi-party appointment capabilities required | There is no scalable process for facilitating "multi-party" appointments for scenarios where network representatives, electricians and metering service providers need to be on-site simultaneously to facilitate new connections. | YES | YES |  | Develop process for multi-party appointment capability, i.e.: - Customer upgrading supply (single phase to three phase). -Electricians, networks and meter providers need to be booked at the same time. | H | M | Schedulers needed to manually coordinate appointments for exceptional cases Train employees to be able to : -perform advanced scheduling between multiple parties -liaising with external parties to organise scheduling | M | M | Enable three way appointment capability for Customer upgrading supply (single phase to three phase). Electricians, networks and meter providers need to be booked at the same time. | M | L | H | H |  |  |  | H | H | M | M | M | VG: This is a High impact to Click, - SAP, Click and CFE. Gary: High impact now captured Sam Mavraganis: Shared portal to facilitate appointments? Charges-who to charge? Must have retailer involvement? Gary: These are valid points that must be addressed in the detailed process and technical design phase. However at this stage it will be kept as High Impact Binu: SAP BI Data Warehouse sources data from various systems such as SAP, UIQ, MTS, CIS, IEE. If SAP, IEE, UIQ and CIS is going to be highly impacted then BI will likely be highly impacted as well. Gary: BI Impacts captured as H |  | 1 | 1 | 1
17 | Roles & Responsibilities | 4. Plan, Manage & Execute | 4.2 Manage & Execute Work | Schedule | Route Planning | As increasing volumes of work are appointment based, a review of the current routing plans is needed to ensure continued operational efficiency (e.g. routing based on time and type of work as opposed to geographical) | YES | YES |  | Review field work routing plans and truck equipment, taking into consideration: -increasing appointment based work, hence reducing efficiency (is extra after hours work required?) -sites may require third party service provider to attend work as well | M | M | Planners may require training on new planning requirements. May require additional appointment based field workforce | N/A | N/A | As above | [11 empty] | N/A |  |  | 1
18 | Roles & Responsibilities | 4. Plan, Manage & Execute | 4.2 Manage & Execute Work | E2E - Maintenance / Replacement & Network Augmentation | Inspecting third party metering work | Before manual re-energisation of a site with a third party meter, CP-PAL will need to perform checks and inspections on the site and metering installation for safety issues. There will be cases when CP-PAL is unable to re-energise the site (e.g. a metering work initiated by third party market participant found to be unsafe or non-compliant). CP-PAL will need to coordinate with market participant to ensure customer is back on supply as soon as possible | YES | YES |  | Develop procedures for site inspection of a site with third party meter, with consideration for: -handling cases where site cannot be re-energised (e.g. site defect, testing issue) -equipping customer care with capability and knowledge to handle customer left off-supply -coordination with third party market participants to get customer back on supply | M | H | Train employees to be able to : -handle customer while they are off-supply -liaise with correct market participant to fix issue | M | M | Systems must be able to identify sites with third party meter and quickly identify the service provider who performed the work. | [11 empty] | M |  |  | 1 | 1 | 1 | bar: CIS; UIQ
19 | Roles & Responsibilities | 4. Plan, Manage & Execute | 4.2 Manage & Execute Work | E2E - Additions and Alterations | Handling of adds and alts for non-CP-PAL meters | CP-PAL will still be responsible for facilitating adds and alts within their distribution area. Processes are required to manage adds and alts work where a third party MC's meter is involved (e.g. processes for testing, gaining access to the meter, wiring and meter boards) | YES | YES | ? | Develop new process to define how CP-PAL handles cases where a network job at a site requires moving or removing of a non-CP-PAL meter, with considerations for: -coordinating with MC to send an external service provider to remove the meter -obtaining authorisation from MC for CP-PAL to perform work at the site with the possibility of having to temporarily remove the meter | H | M | Train employees to be able to: -Identify third party meters -understand protocol of handling third party meters | L | L | Any system change requirements already covered in line item ID16 "Multi-party appointment capabilities required" | [11 empty] | N/A | VG: This is a High impact to Click, - SAP, Click and CFE. Gary: Impacts already captured in line item ID16 "Multi-party appointment capabilities required" |  | 1 | 1
20 | Roles & Responsibilities | 4. Plan, Manage & Execute | 4.2 Manage & Execute Work | E2E - Emergency & Repair | Emergency and Outage management | Process required for handling instances for isolated and mass outages, which may require meter replacement. Events such as HVI faults may result in a larger number of CP-PAL and/or non-CP-PAL meters becoming faulty. Any meter requiring replacement will become contestable. CP-PAL may not be able to restore supply without the involvement of a third party MC's. | YES | YES |  | Develop process for outage handling with possible procedures for: -coordinating site attendances with external service providers -pre-agreements with third parties on handling faulty meters -full replacement of broken meters (essentially CP-PAL will be new appointed MC) -temporary replacement of meters (where CP-PAL places new meters first and the incumbent MC will arrange for replacing them at a later date) | H | H | Train employees on handling: -outages and other emergency situations for sites with a third party MC | L | H | Enable systems to flag sites with non- CP-PAL meters which may require attendance by external meter service providers | [9 empty] | M |  | L | Mustafa: UIQ will be slightly impacted (L) if non CPPAL meters are required to be flagged in UIQ. Gary: Impact to UIQ now captured Binu: SAP BI Data Warehouse sources data from various systems such as SAP, UIQ, MTS, CIS, IEE. If SAP, IEE, UIQ and CIS is going to be highly impacted then BI will likely be highly impacted as well. Gary: BI Impacts captured as L (as other systems are low to medium impact) |  | 1 | 1 | 1 | bar: DMS; CRM to SAP; MTS; BI
21 | Roles & Responsibilities | 4. Plan, Manage & Execute | 4.2 Manage & Execute Work | E2E - Abolishment | Handling Site Abolishment | Site abolishment processes require re-design considering that third party meters may be present on site for mass market customers. Processes must account for scenarios where: -third party meter is removed by CP-PAL -third party meter is left on site | YES | YES |  | Develop procedures for meter abolishment, taking into consideration: - provision of notice to third party MP's prior to site de-energisation - removal of third party meters by CP-PAL and logistics requirements for meter return. - non-removal of third party meters (leave on site) -meter does not belong to CP-PAL but the network device within does | M | M | Train employees to be able to: -Identifying third party meters -understanding protocol of handling third party meters | L | L | Current systems able to handle site abolishments within CP-PAL patch, but may need to consider increased volumes of abolishment. | [8 empty] | M | M | L | M | VG:CFE impacts? We are building an abolishment process. Changes maybe required Gary: Impact to CFE now captured Sam Mavraganis: there needs to be a difference between removing meters and an abolishment process as is current. Abolishment process includes removal of service and metering. If there is a 3rd party meter and removal of CP/PAL meter is required - we should charge for removal of a meter? There is a proposed rumour we may not be charging for an abolishment process? Higher volume of CP/PAL meters being ripped off and dumped - loss of data/reads Gary: Correct. Charges for Meter removal and exchange is covered in line item ID34 "Charges for services to MC and external metering service providers". Loss of data / reads is covered in line item ID26 "Meter Removals affect network quality" Binu: SAP BI Data Warehouse sources data from various systems such as SAP, UIQ, MTS, CIS, IEE. If SAP, IEE, UIQ and CIS is going to be highly impacted then BI will likely be highly impacted as well. Gary: BI impact captured as "H" |  | 1 | 1 | 1 | bar: CIS; SAP; BI
22 | Roles & Responsibilities | 4. Plan, Manage & Execute | 4.2 Manage & Execute Work | E2E - Retailer initiated work | Planned outages with DNSP involvement | CP-PAL will at times need to be involved to effect an interruption to customer supply for the third party MC to undertake work on the metering equipment (e.g. where a common service fuse is used to isolate supply across multiple dwellings). CP-PAL will still be expected to send out customer notification in these cases. | YES | YES | ? | Develop process to handle requests for interruption at a site where CP-PAL is not MC, considering: -possibility of having to attend site twice (once to de-energise, and another to re-energise) -branding for customer notifications, contact details for enquiries and party responsible for issues (i.e., CP-PAL, FRMP, or MP, etc.). | M | M | (Similar training as "Handling Site abolishment" ) | N/A | N/A | Enable systems to handle planned outages as initiated by third party. | [8 empty] | M | M | L | L |  |  |  | 1 | 1 | bar: DMS
|  | 4. Plan, Manage & Execute | 4.3 Plan & Manage Supply Chain | Plan Material Demand | [6 empty] | N/A | N/A |  | N/A | N/A | [12 empty] | N/A
|  | 4. Plan, Manage & Execute | 4.3 Plan & Manage Supply Chain | Procure Material and Service | [6 empty] | N/A | N/A |  | N/A | N/A | [12 empty] | N/A
|  | 4. Plan, Manage & Execute | 4.3 Plan & Manage Supply Chain | Manage Materials | [6 empty] | N/A | N/A |  | N/A | N/A | [12 empty] | N/A
|  | 4. Plan, Manage & Execute | 4.3 Plan & Manage Supply Chain | Receipt, Store & Deliver | [6 empty] | N/A | N/A |  | N/A | N/A | [12 empty] | N/A
|  | 4. Plan, Manage & Execute | 4.3 Plan & Manage Supply Chain | Pay Supplier | [6 empty] | N/A | N/A |  | N/A | N/A | [12 empty] | N/A
|  | 4. Plan, Manage & Execute | 4.3 Plan & Manage Supply Chain | Manage Supply Chain Systems | [6 empty] | N/A | N/A |  | N/A | N/A | [12 empty] | N/A
|  | 5. Operate the Network | 5.1 Enable Smart Network Operations | Perform Operational Planning | [6 empty] | N/A | N/A |  | N/A | N/A | [12 empty] | N/A
|  | 5. Operate the Network | 5.1 Enable Smart Network Operations | Provide Operational Support |  | Covered under the "Additions & Alterations" Capability |  |  |  |  | N/A | N/A |  | N/A | N/A | [12 empty] | N/A
23 | Minimum Service Specification | 5. Operate the Network | 5.1 Enable Smart Network Operations | Real Time Operation & Control | No outage notification in minimum service specification | As of September 2015, the minimum service specification does not currently include the need for "outage notification" functionality. This may result in loss of "last gasp" outage notification, supply restoration and ability to "ping" meter to confirm supply as new MC's may install meters without the outage notification functionality | YES | YES |  | Review and potentially alter OMS escalation/restoration rules to accommodate potential "gaps" in network Negotiate arrangements with other MSP's to publish last gasps supply restoration and a "meter ping service". Process to ensure CP-PAL meters and third party meters are communicating to each other to maintain network quality and accurate outage capabilities | M | H | Train employees to be able to : -identify potential outages and perform investigation to validate | M | H | Enable systems to accommodate for meters with no outage notification functionality Enable systems to receive outage notification data from external sources | [10 empty] | M | H |  |  |  | 1 | 1 | bar: DMS
24 | Roles & Responsibilities | 5. Operate the Network | 5.1 Enable Smart Network Operations | Manage Planned Events | Planned outages with NO DNSP involvement | Retailers will be able to arrange for remote de-energisation on sites with the MC, without the involvement of the DNSP. In these cases CP-PAL will still need to know of any planned outages initiated by retailers to avoid mistakenly treating unpowered sites as a fault | YES | YES |  | Develop process to receive and store information regarding planned outages initiated by external parties, with procedures to: -suppress fault notifications for that site -CP-PAL being sent "copies" of Service Orders sent between external parties | H | H | Train employees to be able to: -understand the new system changes -manually flag sites and planned outage and suppress fault flags | L | M | Enable systems to -receive and distinguish Service Orders for "information only" and does not trigger work orders being created in the system -validate Service Orders. (i.e. any ongoing CP-PAL work at the site) - integrate with DMS systems to supress fault notifications for a period of time | [10 empty] | M | M | David Rofe/Vannasone Sihathep: B.I reports may need to be modified to allow to prevent false notification of missing data. Gary: BI Impact now captured Binu: SAP BI Data Warehouse sources data from various systems such as SAP, UIQ, MTS, CIS, IEE. If SAP, IEE, UIQ and CIS is going to be highly impacted then BI will likely be highly impacted as well. Gary: BI Impacts captured as M (as other systems are low to medium impact) |  |  | 1 | 1 | bar: DMS; CRM; UIQ to MTS; BI
|  | 5. Operate the Network | 5.1 Enable Smart Network Operations | Manage Un-planned Events |  | Covered under the "Emergency & Repair Capability |  |  |  |  | N/A | N/A |  | N/A | N/A | [12 empty] | N/A
25 | Access to Network Devices | 5. Operate the Network | 5.1 Enable Smart Network Operations | Manage Network Quality | Meter Removals affect network quality | Removal of meters may limit CP-PAL's ability to monitor network quality (THD, voltage, phase balance etc.). This will be especially prevalent in low density AMI deployment areas where removal of a single meter may cause loss of communication with adjacent meters. Alternative means of network monitoring may be required (e.g. network devices at customer premises). | YES | YES |  | Develop procedures for maintaining network quality in the event of increasing loss of meter on premise with possible considerations for: - active measures for preventing loss of network quality (e.g. installing network devices at sites) -identifying -review of the AMI network design -reactive measures where network comm relays deployed to reconnect disconnected meters to the CP-PAL network (use of SSN Cellular "Micro AP's" to provide communications network "infill".) -"renting" comms assets from other DNSP's in the area | VH | M | Train employees to be able to" -detect drop in network quality (e.g. reports, "gaps" in the network) -perform steps to mitigate network quality issue | N/A | N/A | Enable system to detect potential loss of meter network connectivity due to a meter being disconnected and notify CP-PAL Enable systems to use "rented" comms assets belonging to other DNSPs | [11 empty] | M | VG : MAM impact Gary: Impact to MAM captured in line item ID1 "Meter Exchange between CP-PAL and third party meters" Mustafa: UIQ will be slightly impacted (L) if meters are removed as this reduces our ability to communicate to meters thus monitor network quality Gary: Impact to UIQ now captured as "H" and refers to not just UIQ but the change in the AMI network as a whole. Binu: SAP BI Data Warehouse sources data from various systems such as SAP, UIQ, MTS, CIS, IEE. If SAP, IEE, UIQ and CIS is going to be highly impacted then BI will likely be highly impacted as well. Gary: BI Impacts captured as H (as other systems are low to medium impact) |  |  | 1 | 1 | bar: DMS; UIQ; BI
26 | All | 5. Operate the Network | 5.1 Enable Smart Network Operations | Manage Distributed Generation | Solar pre-approval | CP-PAL in its LNSP capacity will need to pre-approve sites prior to customers being able to install solar capabilities at their premises. New processes will be required for CP-PAL and the MC to co-ordinate activities such that the solar installation does not cause negative impacts to the grid | YES | YES |  | Develop procedures and steps expected of market participants, customers and MCs to follow to provide solar installations for customer, including consideration for fees and charges involved | L | L | Train employees to coordinate activities between CP-PAL, MC and customer for solar installations | L | L | Changes to Solar portal to reflect new changes | [8 empty] | L |  |  | M | Sam Mavraganis: New E2E solar portal needs to be updated? Gary: Impact to CFE /E2E captured as "L" |  | 1 | 1 |  | 1
|  | 6. Manage Network Data & Smart Infrastructure | 6.1 Manage Governance and Architecture | Manage Information Strategy & Architecture | [6 empty] | N/A | N/A |  | N/A | N/A | [12 empty] | N/A
|  | 6. Manage Network Data & Smart Infrastructure | 6.1 Manage Governance and Architecture | Manage Data / Information Governance and Audit | [6 empty] | N/A | N/A |  | N/A | N/A | [12 empty] | N/A
|  | 6. Manage Network Data & Smart Infrastructure | 6.2 Manage Data & Analytics/Modelling | Network Assets Data | [6 empty] | N/A | N/A |  | N/A | N/A | [12 empty] | N/A
27 | All | 6. Manage Network Data & Smart Infrastructure | 6.2 Manage Data & Analytics/Modelling | Process Meter Data | Meter data analytics | New reporting and analytics capabilities required to support CP-PAL Operation and Strategy as the metering services landscape changes with the implementation of the rule change | YES | YES |  | Define the new or updated reports required to further support the network operations and performance monitoring. Develop new processes and reports to: -analyse meter churn trends - analyse consumer data - discover inefficiencies | M | M | Train employees on running an reading the new reports that can be generated | L | L | Enable Business Intelligence changes to support new reports and analytics, taking into consideration increased volume of data (e.g. metering data has intervals of half an hour or less) | [11 empty] | M | CP-PAL has a current parallel project to improve their reporting and analytics systems but will require further enhancements to meet the Contestable Metering compliance operations |  | 1 | 1 | 1 | 1 | bar: BI
28 | Roles & Responsibilities | 6. Manage Network Data & Smart Infrastructure | 6.3 Manage Communications Infrastructure & Security | Manage Comms. Environment | Pre-emptive actions for potential meter removal sites | There will be an increasing reliance on third parties to provide information to CP-PAL when a meter exchange is to be performed. Failing to do so may have adverse effects on the network (i.e. fault truck dispatched, insufficient meter data to fulfil obligations, loss of comms with adjacent meters, etc.). Some pre-emptive actions can be taken to minimise the adverse impacts | YES | YES | YES | Develop processes to: -Identify in advance when a meter is to be exchanged by third party (e.g. through planned outage notifications, CATS transaction stating a change in premise MC, etc.) -perform pro-active steps (i.e. change data interval collection to shorter intervals, check if comms to adjacent meters will be affected, etc.) -other follow up activities ( e.g. meter return process, install relay to prevent comms loss with adjacent meters. etc.) | H | M | Train employees to be able to identify potential meter removal sites and perform follow up actions | M | M | Enable systems to collect data and identify sites where meter removal will potentially be performed by third party and potentially: -automatically shorten the data collection interval from 4 hours to half hourly -notify user to validate if truck fault dispatches to premise are false alarms | [10 empty] | M | H |  |  |  | 1 | 1 | bar: DMS to CIS; UIQ to MTS
29 | Minimum Service Specification | 6. Manage Network Data & Smart Infrastructure | 6.3 Manage Communications Infrastructure & Security | Manage Comms. Environment | Lower specced meters | The rules specify a minimum service specification of all installed smart meters. Current CP-PAL meters have more functionality than the minimum specifications. There is a possibility that other MCs will install lower specced meters (e.g. no load control, outage notification, etc.). | YES | YES |  | Define process for identifying the potential functionality that will be lost with lower specced meters, recording them in the system and mitigation actions if required (e.g. installing network device at premise) | L | M | N/A | N/A | N/A | Potential system change to record missing functionality within third party meters installed on CP-PAL patch | [10 empty] | L | L | [5 empty] | 1 | bar: CIS; MTS
30 | Additional Consultation (17 Sep 15) | 6. Manage Network Data & Smart Infrastructure | 6.3 Manage Communications Infrastructure & Security | Manage Security & Configuration Management | Remote de-en / re-en through network device | New process required for a re-en / de-en performed remotely through the use of the network device (which may be a meter) . CP-PAL will be able to perform this activity where a site needs to be de-energised for safety, security or network reliability reasons (subject to jurisdiction rules) | YES | YES |  | Develop process for performing a re-en / de-en remotely using a network device, considering the scenarios: - meter does not belong to CP-PAL - what constitutes a safety reason - how will the market be informed - establish guidelines for installations where the old meter remains as a network device | H | L | Train employees on how to perform a re-en, the scenarios when a remote re-en/de-en can be performed, and handling of existing third party meters as network device | L | L | Enable systems to perform re-en / de-en remotely using a connected network device. Enable systems to send transaction to the market to inform of the de-en | [11 empty] | L | Sam Mavraganis: third party meter needs to be communicating to CP/PAL meter in order to know outage/de-en. Life support customers need to be listed for both meters Gary: meter communication between CP-PAL and third party meters now captured in line item ID5 "Third party metering data". Binu: SAP BI Data Warehouse sources data from various systems such as SAP, UIQ, MTS, CIS, IEE. If SAP, IEE, UIQ and CIS is going to be highly impacted then BI will likely be highly impacted as well. Gary: BI Impacts captured as L (as other systems are low impact) |  | 1 | 1 | 1 | bar: SAP to UIQ; BI
31 | Cost Recovery regulated metering services | 7. Manage Revenue | 7.1 Manage Tariff & Charges | Manage Network Charges | STPIS exemption | There is a need to review the STPIS exemption business rules to account for planned and unplanned outages at third party metering sites | YES | YES |  | Review current processes to ensure that STPIS exemptions can be applied for the appropriate scenarios: - Customer left off supply due to faulty third party meter installation - Outage caused by retailer or third party at a site | H | H | N/A | N/A | N/A | Enable systems to flag sites or cases (work orders) which are exempt from STIPS | [11 empty] | H |  |  |  |  | 1 | 1 | bar: DMS to CIS; BI
32 | Cost Recovery regulated metering services | 7. Manage Revenue | 7.1 Manage Tariff & Charges | Manage Non-Network Charges | Third party billing capability | Current billing capabilities need to be reviewed and updated to allow for more robust billing capabilities. (e.g automatic calculation of fees). There are currently some billing being performed manually and this may need to be automated to accomodate increasing volumes. | YES | YES |  | Develop procedures for automated fee calculation considering scenarios : -within Victoria where smart meters already exist and the exit fee is higher -business rules -possible renting of pole space | H | H | Train employees to be able to: -understand the automated changes to the system -perform exit fee calculation manually if required | L | H | Enable systems to automatically calculateand bill third parties | [11 empty] | H | Binu: SAP BI Data Warehouse sources data from various systems such as SAP, UIQ, MTS, CIS, IEE. If SAP, IEE, UIQ and CIS is going to be highly impacted then BI will likely be highly impacted as well. Gary: BI Impacts captured as M (as other systems are low to medium impact) |  |  |  | 1 | 1 | bar: CIS to CRM; BI
33 | Cost Recovery regulated metering services | 7. Manage Revenue | 7.1 Manage Tariff & Charges | Manage Tariffs and Forecasting | Third Party MCs may propose tariffs | Third Party MCs may propose a tariff they deem suitable when a new meter is installed / replaced at a customer premise. This may help avoid LNSPs charging incorrect tariffs based on the type of service offered to the customer. CP-PAL needs the ability to check (and possibly object) to tariffs proposed by market participants | YES | YES |  | Updated procedures required to validate proposed tariffs, and then accepting or objecting to them | L | L | Training on new system functionalities | L | L | System changes to validate proposed tariff against a set of protocols and accept or reject tariff | [10 empty] | L | L | CP-PAL has a current parallel running project to review current tariffs and introduce new tariffs while retiring some legacy tariffs. |  |  |  | 1 | 1 | bar: CIS; MTS
34 | Cost Recovery regulated metering services | 7. Manage Revenue | 7.1 Manage Tariff & Charges | Manage Revenue from Incentives | Standard charges for services to third party MC and external metering service providers | There is no standard fee structure agreed with third party MC and third party Metering Service Providers. No rules regarding which charges will be passed through vs "absorbed" | YES | YES | YES | New Business Rules required to: - Determine the rates for services provided on site with third party meter - Determine fees for fault truck dispatched in error - Determine which charges/rates are levied on customers and any appropriate margin for services. - Reconcile Metering Service Provider invoices against work completion details outlining services performed/materials used. | H | H |  | N/A | N/A | Possible updates to billing systems with new billing capability to bill third party market participants | [11 empty] | M |  |  |  |  | 1 | 1 | bar: CIS; SAP
|  | 8. Manage Regulation & Compliance | 8.1 Manage Regulatory Affairs | Regulated Revenue / Strategy | [6 empty] | N/A | N/A |  | N/A | N/A | [12 empty] | N/A
35 | Roles & Responsibilities | 8. Manage Regulation & Compliance | 8.1 Manage Regulatory Affairs | Manage Accreditation/Compliance | Manage accreditation of contractors | There is a requirement that CP-PAL acting under the capacity of default MC, must be responsible for ensuring all contractors and service providers are sufficiently accredited and abide by the AER service specifications. CP-PAL needs to confirm the MC registration requirements and responsibilities as the Responsible Person for metering services. | YES | YES |  | Develop procedures for ensuring all contractors and service providers working for CP-PAL are sufficiently accredited, particularly when operating off-patch and having to employ third party service providers | L | M | Train employees to be able to: -validate and track accreditation of engaged metering service providers | L | L | N/A | [11 empty] | N/A | [5 empty] | 1
36 | Roles & Responsibilities | 8. Manage Regulation & Compliance | 8.1 Manage Regulatory Affairs | Manage Accreditation/Compliance | New accreditation required | To remain competitive in current patch and in the contestable market, CP-PAL will need additional accreditation for type 4 meters. | YES | YES |  | Manage Process for updating accreditation and registration, with consideration for : -work instructions for current transformer connected sites. -updating commissioning processes -VES rules | H | H | Necessary training for CP-PAL to receive type 4 accreditation | L | L | Enable systems to support handling type 4 meters |  | H |  | L | L | M | M |  | L | L | M | M | David Rofe/Vannasone Sihathep: To ensure compliance, additional validation sets may be required. Gary: additional validation now captured as a process requirement |  |  |  |  | 1