## Summary of Costs
CAPITAL EXPENDITURE | 2016 | 2017 | 2018 | 2019 | 2020 | TOTAL
1. RIN CATALOGUE DEFINITION | 2829658.35 |  |  |  |  | 2829658.35
2. ASSET MASTER DATA IMPROVEMENT | 1951434.2824 | 600441.3176 |  |  |  | 2551875.6
3. RIN RULES ENGINE | 1573187.9643 | 629275.1857 |  |  |  | 2202463.15
4. LABOUR MODEL | 677788.53 | 451859.02 |  |  |  | 1129647.55
5. RIN REPORTING ASSET | 624341.5333 | 1248683.0667 |  |  |  | 1873024.6
SUB TOTAL | [5 empty] | 10586669.25
TOTAL CAPITAL EXPENDITURE | 7656410.66 | 2930258.59 |  |  |  | 10586669.25
6. RIN GOVERNANCE |  | 523600 | 1096810 | 1096810 | 1096810 | 3814030
7. DATA ELEMENT MATURITY |  |  | 192099.775 | 192099.775 | 192099.775 | 576299.325
SUB TOTAL | [5 empty] | 4390329.325
Increased external audit costs | 51412.5 | 98603.125 | 159001.4062 | 138543.8359 | 119109.1441 | 566670.0113
TOTAL OPERATING EXPENDITURE | 51412.5 | 622203.125 | 1447911.1812 | 1427453.6109 | 1408018.9191 | 4956999.3363
TOTAL | 7707823.16 | 3552461.715 | 1447911.1812 | 1427453.6109 | 1408018.9191 | 15543668.5863
Capital expenditure: allocation | 2016 | 2017 | 2018 | 2019 | 2020 | TOTAL
CitiPower | 3828205.33 | 1465129.295 | 0 | 0 | 0 | 5293334.625
Operating expenditure: allocation | 2016 | 2017 | 2018 | 2019 | 2020 | TOTAL
CitiPower | 25706.25 | 311101.5625 | 723955.5906 | 713726.8055 | 704009.4596 | 2478499.6682
TOTAL | [5 empty] | 7771834.2932

## High Level Road Map
| 2015 | [5 empty] | 2016 | [11 empty] | 2017 | [11 empty] | 2018 | [11 empty] | 2019 | [11 empty] | 2020
| J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D
1. RIN CATALOGUE DEFINITION
SCOPE | bar: 2016 F
DESIGN | bar: 2016 M to 2016 J
IMPLEMENT | bar: 2016 J
2. ASSET MASTER DATA IMPROVEMENT
SCOPE | bar: 2016 M
DESIGN | bar: 2016 J to 2016 A
IMPLEMENT | bar: 2016 S to 2017 F
SYSTEM & BUSINESS PROCESS IMPROVEMENT | bar: 2016 A to 2017 F
3. RIN RULES ENGINE
SCOPE | bar: 2016 J
DESIGN | bar: 2016 A to 2016 S
IMPLEMENT | bar: 2016 O to 2017 F
SYSTEM & BUSINESS PROCESS IMPROVEMENT | bar: 2016 S to 2017 F
4. LABOUR MODEL
SCOPE | bar: 2016 S
DESIGN | bar: 2016 O to 2016 N
IMPLEMENT | bar: 2016 D to 2017 F
SYSTEM & BUSINESS PROCESS IMPROVEMENT | bar: 2016 N to 2017 F
5. RIN REPORTING ASSET
SCOPE | bar: 2016 O
DESIGN | bar: 2016 N to 2016 D
IMPLEMENT | bar: 2017 J to 2017 J
6. RIN GOVERNANCE
GOVERNANCE | bar: 2017 J to 2020 D
7. DATA ELEMENT MATURITY
PROCESS | bar: 2018 J to 2020 D
Catalogue defined
Master data improved
RIN rules engine
Labour model delivered
RIN reporting asset

## 1 Detail Cat Definition
| Effort (days) | [5 empty] | Cost
1. RIN CATALOGUE DEFINITION | Network | Info Tech - IT | Corporate | Regulatory | Customer Services Group - CSG | External | Total
SCOPE
Establish RIN definition stakeholder group | 0 | 3.9 | 3.9 | 3.9 | 0 | 0 | 8365.5
Agree charter and deliverables | 0 | 3.9 | 3.9 | 3.9 | 0 | 2.6 | 10965.5
Agree governance model and design decision authority | 78 | 26 | 26 | 26 | 26 | 36 | 151206
Establish project team and kick-off |  | 1.3 | 1.3 | 1.3 | 0 | 1.3 | 4088.5
TOTAL | 78 | 35.1 | 35.1 | 35.1 | 26 | 39.9 | 174625.5
DESIGN
Engage RIN definition stakeholders across CP/PAL - workshops | 127 | 49 | 39 | 39 | 39 | 47 | 232754
Establish primary data sources (DBoRs) | 22 | 30 | 3.9 | 1.3 | 9.15 | 38 | 79612.625
Establish Asset-related master data requirements | 88 | 62 | 13 | 13 | 13 | 78 | 199033.5
Repex - RIN catalogue - business rules | 150 | 62 | 0 | 15 | 0 | 51 | 196800
Augex - RIN catalogue - business rules | 150 | 62 | 0 | 12 | 7.99 | 49 | 196010.725
Maintenance - RIN catalogue - business rules | 150 | 62 | 0 | 15 | 0 | 49 | 194800
Connections - RIN catalogue - business rules | 80 | 62 | 0 | 12 | 46.8 | 36 | 156237
Metering - RIN catalogue - business rules | 80 | 33 | 0 | 12 | 46.8 | 36 | 136662
Non-Network, Labour & Overheads - RIN catalogue - business rules | 30 | 36 | 26 | 13 | 13 | 36 | 113107.5
Establish Asset and Labour-related mapping rules | 88 | 36 | 26 | 13 | 26 | 49 | 167596
Establish apportionment / allocation methodology for each business area | 196 | 69 | 58.5 | 0 | 58.5 | 49 | 285003.25
Establish approtionment logic (volume and cost) by RIN Category | 108 | 62 | 32.5 | 0 | 32.5 | 75 | 221537.25
TOTAL | 1269 | 625 | 198.9 | 145.3 | 292.74 | 593 | 2179153.85
IMPLEMENT
Distribute compiled RIN catalogues to stakeholders for review and comment | 69 | 36 | 19.5 | 26 | 19.5 | 36 | 144824.25
Finalise catalogue post-feedback | 0 | 20 | 0 | 10.4 | 0 | 36 | 57144
Confirm catalogue publication and delivery approach | 0 | 7 | 0 | 7 | 0 | 9 | 18870
Agree deployment and sustain / administration protocols | 8 | 8 | 6 | 6 | 6 | 6 | 27741
DEPLOY | 0 | 8 | 0 | 0 | 0 | 7 | 12400
TOTAL | 77 | 79 | 25.5 | 49.4 | 25.5 | 94 | 260979.25
SUSTAIN
Year 1 only | 0 | 318.37 | 0 | 0 | 0 | 0 | 214899.75
TOTAL | 0 | 318.37 | 0 | 0 | 0 | 0 | 214899.75
1. RIN CATALOGUE DEFINITION |  |  |  |  | TOTAL |  | 2829658.35
Labour Split | Network | Info Tech - IT | Corporate | Regulatory | Customer Services Group - CSG | External
EXTERNAL LABOUR | [5 empty] | 726.9
INTERNAL LABOUR | 1424 | 1057.47 | 259.5 | 229.8 | 344.24
Breakdown by year $'s | 2016 | 2017 | 2018 | 2019 | 2020
IT Internal | 713792.25
Network | 882168
Corporate | 359635.5
CSG | 147162.6
External | 726900
Breakdown by hours | 2016 | 2017 | 2018 | 2019 | 2020
IT Internal | 1057.47 | 0
NS | 1424 | 0
Corporate | 489.3 | 0
CSG | 344.24 | 0
External | 726.9 | 0
Project Months | 12 | 0

## 2 Detail Asset Master Data
| Effort (days) | [5 empty] | Cost
2. ASSET MASTER DATA IMPROVEMENT | Network | Info Tech - IT | Corporate | Regulatory | Customer Services Group - CSG | External | Total
SCOPE
Agree charter and deliverables | 3.9 | 3.9 | 1.3 | 1.3 | 1.3 | 0 | 7515.3
Confirm scope against RIN catalogue requirements | 3.9 | 2.6 | 1.3 | 1.3 | 1.3 | 2.6 | 9237.8
Establish detailed project plan | 0 | 6.5 | 0 | 0 | 0 | 6.5 | 10887.5
Establish project team and kick-off | 0 | 1.3 | 0 | 0 | 0 | 1.3 | 2177.5
TOTAL | 7.8 | 14.3 | 2.6 | 2.6 | 2.6 | 10.4 | 29818.1
DESIGN
Establish the asset master data governance model | 62.4 | 54 | 20.8 | 20.8 | 20.8 | 88 | 202574.8
Confirm Asset-related DBoRs and intermediate systems | 19.5 | 16 | 12 | 15 | 15 | 13 | 62137.75
Review front-line business process affecting asset master data capture | 19.5 | 36 | 6.5 | 6.5 | 6.5 | 62 | 110714
Confirm the various data stewards (roles) involved in front-line data capture | 19.5 | 13 | 6.5 | 13 | 6.5 | 36 | 73966.5
Establish the asset master data information flows (across systems) | 31.2 | 20.8 | 0 | 0 | 10.4 | 69 | 106814.4
Profile the asset DBoRs to establish data quality issues | 31.2 | 20.8 | 0 | 0 | 2.6 | 49 | 83479.9
Perform root-cause analysis to confirm the basis for RIN-C DQ issues | 31.2 | 20.8 | 0 | 0 | 10.4 | 78 | 115814.4
Confirm asset mapping rules (as per RIN catalogue) | 15.6 | 16 | 0 | 10.4 | 5.2 | 62 | 92331.2
Establish the asset master data target operating model | 31.2 | 20.8 | 0 | 0 | 10.4 | 62 | 99814.4
Develop and finalise the asset master data remediation plan | 7.8 | 13 | 2.6 | 13 | 2.6 | 36 | 62184.6
TOTAL | 269.1 | 231.2 | 48.4 | 78.7 | 90.4 | 555 | 1009831.95
IMPLEMENT
Execute data remediation activities | 15.6 | 10.4 | 9 | 9 | 9 | 166 | 199761.7
Design (or update) key asset master data quality controls | 0 | 19.5 | 0 | 19.5 | 0 | 88 | 115495
Specify asset data quality montoring and compliance (reporting) | 0 | 19.5 | 0 | 19.5 | 0 | 62 | 89495
Implement front-line changes for asset data capture | 0 | 19.5 | 0 | 0 | 0 | 166 | 179162.5
Implement asset data store synchronisation | 0 | 19.5 | 0 | 0 | 0 | 114 | 127162.5
Implement DQ reporting / monitoring | 7.8 | 19.5 | 2.6 | 0 | 2.6 | 62 | 83017.1
Implement asset MDM operating model - roles / process changes | 39 | 19.5 | 13 | 19.5 | 13 | 75 | 141768
TOTAL | 62.4 | 127.4 | 24.6 | 67.5 | 24.6 | 733 | 935861.8
SYSTEM & BUSINESS PROCESS IMPROVEMENT
Identify key enabling bus & sys improvement initiatives to support asset MDM | 39 | 39 | 13 | 0 | 13 | 30 | 95598
Implement front-line bus & system improvement | 78 | 52 | 26 | 0 | 26 | 52 | 165646
Implement back-office bus & system improvement | 39 | 52 | 13 | 0 | 13 | 62 | 136373
TOTAL | 156 | 143 | 52 | 0 | 52 | 144 | 397617
SUSTAIN
Year 1 only est | 0 | 264.81 | 0 | 0 | 0 | 0 | 178746.75
TOTAL |  | 264.81 | 0 | 0 | 0 | 0 | 178746.75
2. ASSET MASTER DATA IMPROVEMENT |  |  |  |  | TOTAL |  | 2551875.6
Labour Split | Network | Info Tech - IT | Corporate | Regulatory | Customer Services Group - CSG | External
EXTERNAL LABOUR | [5 empty] | 1264.9
INTERNAL LABOUR | 495.3 | 780.71 | 127.6 | 148.8 | 169.6
Breakdown by year $'s | 2016 | 2017 | 2018 | 2019 | 2020
IT Internal | 402984.1324 | 123995.1176
Network | 234641.0912 | 72197.2588
Corporate | 155353.0588 | 47800.9412
CSG | 55444.2353 | 17059.7647
External | 967276.4706 | 297623.5294
Breakdown by hours | 2016 | 2017 | 2018 | 2019 | 2020
IT Internal | 597.0135 | 183.6965
Network | 378.7588 | 116.5412
Corporate | 211.3647 | 65.0353
CSG | 129.6941 | 39.9059
External | 967.2765 | 297.6235
Project Months | 13 | 4

## 3 RIN Rules Engine
| Effort (days) | [5 empty] | Cost
3. RIN RULES ENGINE | Network | Info Tech - IT | Corporate | Regulatory | Customer Services Group - CSG | External | Total
SCOPE
Agree charter and deliverables | 3.9 | 3.9 | 1.3 | 3.9 | 1.3 | 0 | 9426.3
Confirm scope against RIN catalogue requirements | 3.9 | 2.6 | 1.3 | 2.6 | 1.3 | 2.6 | 10193.3
Establish detailed project plan | 0 | 6.5 | 0 | 2.6 | 0 | 6.5 | 12798.5
Establish project team and kick-off | 0 | 1.3 | 0 | 0 | 0 | 1.3 | 2177.5
TOTAL | 7.8 | 14.3 | 2.6 | 9.1 | 2.6 | 10.4 | 34595.6
DESIGN
Establish solution architecture for target solution | 0 | 20.8 | 0 | 0 | 0 | 62 | 76040
Confirm key design constructs with solution team | 3.9 | 13 | 1.3 | 6.5 | 4 | 36 | 54634.05
Design business rules - functional | 15.6 | 26 | 5.2 | 10.4 | 5.2 | 114 | 154903.2
Design business rules - technical | 3.9 | 13 | 1.3 | 10.4 | 1.3 | 114 | 134346.3
Confirm all data fields and attributes required to support apportionment | 31.2 | 20.8 | 10.4 | 20.8 | 10.4 | 62 | 122746.4
TOTAL | 54.6 | 93.6 | 18.2 | 48.1 | 20.9 | 388 | 542669.95
IMPLEMENT
Source and integrate all required data for allocation model | 14 | 70 | 10 | 17 | 10 | 205 | 285043
Iterate / prototype the apportionment rules with business stakeholders | 78 | 36 | 26 | 26 | 25 | 140 | 261528.5
Establish reconciliation of allocation outputs with SAP GL | 0 | 28 | 0 | 12.15 | 0 | 43 | 70830.25
Establsih mappings for all data elements to align with RIN-C requirements | 18 | 25 | 13 | 13 | 13 | 87 | 139693.5
Establish audit / traceability reporting for business rules | 0 | 23 | 0 | 12.01 | 0 | 67 | 91352.35
Establish reporting views to support data extracts for RIN-C reporting | 0 | 31 | 0 | 0 | 0 | 88 | 108925
TOTAL | 110 | 213 | 49 | 80.16 | 48 | 630 | 957372.6
SYSTEM & BUSINESS PROCESS IMPROVEMENT
Identify key enabling bus & sys improvement initiatives to support allocations | 39 | 39 | 13 | 0 | 13 | 42 | 107598
Implement front-line bus & system improvement | 78 | 52 | 26 | 0 | 26 | 114 | 227646
Implement back-office bus & system improvement | 39 | 52 | 13 | 0 | 13 | 115 | 189373
TOTAL | 156 | 143 | 52 | 0 | 52 | 271 | 524617
SUSTAIN
Year 1 only est | 0 | 212.16 | 0 | 0 | 0 | 0 | 143208
TOTAL | 0 | 212.16 | 0 | 0 | 0 | 0 | 143208
3. RIN RULES ENGINE |  |  |  |  | TOTAL |  | 2202463.15
Labour Split | Network | Info Tech - IT | Corporate | Regulatory | Customer Services Group - CSG | External
EXTERNAL LABOUR | [5 empty] | 1141.4
INTERNAL LABOUR | 328.4 | 676.06 | 121.8 | 137.36 | 123.5
Breakdown by year $'s | 2016 | 2017 | 2018 | 2019 | 2020
IT Internal | 325957.5 | 130383
Network | 145317 | 58126.8
Corporate | 136059 | 54423.6
CSG | 37711.6071 | 15084.6429
External | 815285.7143 | 326114.2857
Breakdown by hours | 2016 | 2017 | 2018 | 2019 | 2020
IT Internal | 482.9 | 193.16
Network | 234.5714 | 93.8286
Corporate | 185.1143 | 74.0457
CSG | 88.2143 | 35.2857
External | 815.2857 | 326.1143
Project Months | 10 | 4

## 4. Labour Model
| Effort (days) | [5 empty] | Cost
4. LABOUR MODEL | Network | Info Tech - IT | Corporate | Regulatory | Customer Services Group - CSG | External | Total
SCOPE
Agree charter and deliverables | 3.9 | 3.9 | 1.3 | 2.6 | 1.3 | 0 | 8470.8
Confirm scope against RIN catalogue requirements | 3.9 | 2.6 | 1.3 | 2.6 | 1.3 | 2.6 | 10193.3
Establish detailed project plan | 0 | 6.5 | 0 | 1.3 | 0 | 6.5 | 11843
Establish project team and kick-off | 0 | 1.3 | 0 | 0 | 0 | 1.3 | 2177.5
TOTAL | 7.8 | 14.3 | 2.6 | 6.5 | 2.6 | 10.4 | 32684.6
DESIGN
Establish solution architecture for target solution | 0 | 10.4 | 0 | 0 | 0 | 20 | 27020
Confirm key design constructs with solution team | 0 | 13 | 7.8 | 13 | 0 | 20 | 44063
Design business rules - functional | 14 | 13 | 26 | 10 | 10 | 49 | 97183
Design business rules - technical | 0 | 13 | 13 | 0 | 0 | 48 | 66330
Confirm all data fields and attributes required to support apportionment | 0 | 19.5 | 19.5 | 10 | 0 | 49 | 83845
TOTAL | 14 | 68.9 | 66.3 | 33 | 10 | 186 | 318441
IMPLEMENT
Source and integrate all HR/Payroll required data for allocation model | 0 | 26 | 13 | 0 | 0 | 62 | 89105
Iterate / prototype the apportionment rules with business stakeholders | 14 | 13 | 26 | 0 | 10 | 62 | 102833
Establish reconciliation of allocation outputs with SAP GL (Labour costs) | 0 | 14 | 13 | 14 | 0 | 36 | 65295
Establish mappings for all labour data elements to align with RIN-C requirements | 14 | 14 | 26 | 14 | 9 | 36 | 87370.5
Establish a centralised capability to maintain labour position mappings | 0 | 14 | 13 | 14 | 0 | 30 | 59295
Establish audit / traceability reporting for business rules | 0 | 14 | 14 | 14 | 0 | 23 | 53030
Establish reporting views to support data extracts for RIN-C reporting | 0 | 14 | 0 | 0 | 0 | 23 | 32450
TOTAL | 28 | 109 | 105 | 56 | 19 | 272 | 489378.5
SYSTEM & BUSINESS PROCESS IMPROVEMENT
Identify key enabling bus & sys improvement initiatives to support labour | 7.8 | 13 | 13 | 0 | 2.6 | 23 | 47273.6
Implement front-line bus & system improvement | 39 | 19.5 | 13 | 0 | 13 | 36 | 88435.5
Implement back-office bus & system improvement | 7.8 | 26 | 26 | 0 | 2.6 | 43 | 85603.6
TOTAL | 54.6 | 58.5 | 52 | 0 | 18.2 | 102 | 221312.7
SUSTAIN
Year 1 only est | 0 | 100.49 | 0 | 0 | 0 | 0 | 67830.75
TOTAL | 0 | 100.49 | 0 | 0 | 0 | 0 | 67830.75
4. LABOUR MODEL |  |  |  |  | TOTAL |  | 1129647.55
Labour Split | Network | Info Tech - IT | Corporate | Regulatory | Customer Services Group - CSG | External
EXTERNAL LABOUR | [5 empty] | 430.4
INTERNAL LABOUR | 104.4 | 351.19 | 225.9 | 95.5 | 49.8
Breakdown by year $'s | 2016 | 2017 | 2018 | 2019 | 2020
IT Internal | 142231.95 | 94821.3
Network | 38805.48 | 25870.32
Corporate | 141737.4 | 94491.6
CSG | 12773.7 | 8515.8
External | 258240 | 172160
Breakdown by hours | 2016 | 2017 | 2018 | 2019 | 2020
IT Internal | 210.714 | 140.476
Network | 62.64 | 41.76
Corporate | 192.84 | 128.56
CSG | 29.88 | 19.92
External | 258.24 | 172.16
Project Months | 6 | 4

## 5 RIN Reporting Asset
| Effort (days) | [5 empty] | Cost
5. RIN REPORTING ASSET | Network | Info Tech - IT | Corporate | Regulatory | Customer Services Group - CSG | External | Total
SCOPE
Agree charter and deliverables | 3.9 | 3.9 | 1.3 | 3.9 | 1.3 | 0 | 9426.3
Confirm scope against RIN catalogue requirements | 3.9 | 2.6 | 1.3 | 2.6 | 1.3 | 2.6 | 10193.3
Establish detailed project plan | 0 | 6.5 | 0 | 3.9 | 0 | 6.5 | 13754
Establish project team and kick-off | 0 | 1.3 | 0 | 1.3 | 0 | 1.3 | 3133
TOTAL | 7.8 | 14.3 | 2.6 | 11.7 | 2.6 | 10.4 | 36506.6
DESIGN
Establish solution architecture for target solution | 0 | 45 | 0 | 0 | 0 | 62 | 92375
Confirm key design constructs with solution team | 0 | 13 | 0 | 0 | 0 | 36 | 44775
Design RIN reporting solution - functional | 19.5 | 49 | 13 | 0 | 17 | 88 | 149977.75
Design RIN reporting solution - technical | 0 | 26 | 2.6 | 0 | 0 | 88 | 107461
Define the process and mechanism for capture of manual inputs | 19.5 | 19.5 | 6.5 | 0 | 17 | 72 | 109287.75
Define the attestation and review process to support RIN reporting | 58.5 | 32.5 | 19.5 | 32.5 | 19.5 | 75 | 179734.5
Confirm the RIN-C reporting data model design | 58.5 | 32.5 | 19.5 | 26 | 19.5 | 114 | 213957
Confirm all of the required integration from RIN rules engine and Labour model | 5 | 23 | 0 | 13 | 0 | 40 | 68177.5
Confirm all of the end-state RIN-C formatted views for template reporting | 14 | 26 | 10 | 19.5 | 10 | 46 | 98180.5
TOTAL | 175 | 266.5 | 71.1 | 91 | 83 | 621 | 1063926
IMPLEMENT
Integrate data from all nominated data sources | 0 | 65 | 0 | 0 | 0 | 218 | 261875
Develop the table level extracts for all RIN tabs | 0 | 13 | 0 | 0 | 0 | 62 | 70775
Regression test the RIN reporting extacts against 2013 RIN (where feasible) | 0 | 26 | 13 | 0 | 0 | 62 | 89105
Establish the attestation and review process to support RIN reporting | 58.5 | 32.5 | 19.5 | 32.5 | 19.5 | 62 | 166734.5
Deploy | 0 | 13 | 0 | 26 | 0 | 36 | 63885
TOTAL | 58.5 | 149.5 | 32.5 | 58.5 | 19.5 | 440 | 652374.5
SUSTAIN
Year 1 only est. @ 10% of project cost | 0 | 178.1 | 0 | 0 | 0 | 0 | 120217.5
TOTAL | 0 | 178.1 | 0 | 0 | 0 | 0 | 120217.5
5. RIN REPORTING ASSET |  |  |  |  | TOTAL |  | 1873024.6
Labour Split | Network | Info Tech - IT | Corporate | Regulatory | Customer Services Group - CSG | External
EXTERNAL LABOUR | [5 empty] | 907.4
INTERNAL LABOUR | 241.3 | 608.4 | 106.2 | 161.2 | 105.1
Breakdown by year $'s | 2016 | 2017 | 2018 | 2019 | 2020
IT Internal | 136890 | 273780
Network | 49828.45 | 99656.9
Corporate | 65513 | 131026
CSG | 14976.75 | 29953.5
External | 302466.6667 | 604933.3333
Breakdown by hours | 2016 | 2017 | 2018 | 2019 | 2020
IT Internal | 202.8 | 405.6
NS | 80.4333 | 160.8667
Corporate | 89.1333 | 178.2667
CSG | 35.0333 | 70.0667
External | 302.4667 | 604.9333
Project Months | 3 | 6

## 6 RIN Governance
6. RIN GOVERNANCE |  | Days per year allocated to Group | [5 empty] | $'s
|  | Network | Info Tech - IT | Corporate | Regulatory | Customer Services Group - CSG | External | Total Remuneration
Role | Number of positions
Data Architect | 1 |  |  | 0 | 0 | 0 | 220 | 220000
Regulation Data Governance | 1 |  | 0 | 0 | 220 | 0 | 0 | 161700
Data Analyst (Financial) | 1 |  | 220 | 0 | 0 | 0 | 0 | 148500
Data Analyst (Physical data) | 1 |  | 220 | 0 | 0 | 0 | 0 | 148500
Business Data Analyst (Networks) | 2 | 220 | 0 | 0 | 0 | 0 | 0 | 136290
Business Data Analyst (Non-Networks) | 1 |  | 44 | 132 | 0 | 44 | 0 | 145530
TOTAL | 7 |  | 484 | 132 | 220 | 44 | 220 | 960520
Years Required |  | 2016 | 2017 | 2018 | 2019 | 2020 | TOTAL YEARS | TOTAL COST
Data Architect |  | 0 | 1 | 1 | 1 | 1 | 4 | 880000
Regulation Data Governance |  | 0 | 0.5 | 1 | 1 | 1 | 3.5 | 565950
Data Analyst (Financial) |  | 0 | 0.5 | 1 | 1 | 1 | 3.5 | 519750
Data Analyst (Physical data) |  | 0 | 1 | 1 | 1 | 1 | 4 | 594000
Business Data Analyst (Networks) |  | 0 | 0 | 2 | 2 | 2 | 6 | 817740
Business Data Analyst (Non-Networks) |  | 0 | 0 | 1 | 1 | 1 | 3 | 436590
3814030
Cost Profile |  | 2016 | 2017 | 2018 | 2019 | 2020 | TOTAL COST
Operational Support |  | 0 | 523600 | 1096810 | 1096810 | 1096810 | 3814030

## 7 Data Element maturity
Cost
7. DATA ELEMENT MATURITY | Network | Info Tech - IT | Corporate | Regulatory | Customer Services Group - CSG | External | Total
Process
Review Business Rules | 57 | 25 | 10 | 5.115 | 13.1 | 24 | 92896.275
Implementation | 33 | 24 | 10.5 | 24 | 11 | 32.5 | 99203.5
TOTAL | 90 | 49 | 20.5 | 29.115 | 24.1 | 56.5 | 192099.775
Years Required | 2016 | 2017 | 2018 | 2019 | 2020 | TOTAL YEARS | TOTAL COST
Data Element review | 0 | 0 | 1 | 1 | 1 | 3 | 576299.325
Cost Profile | 2016 | 2017 | 2018 | 2019 | 2020 | TOTAL COST
Data Element review | 0 | 0 | 192099.775 | 192099.775 | 192099.775 | 576299.325

## Labour Rates
Labour Rate Assumption 2016 - 2020 |  | 7.5 hour day
7.5h day
Networks Mhr Rate ($/Mhr) | 82.6 | 619.5
IT Internal Mhr Rate ($/Mhr) | 90 | 675
Corporate Mhr Rate ($/Mhr) | 98 | 735
CSG Mhr Rate ($/Mhr) | 57 | 427.5
Blended external rate |  | 1000