## Run Extract (hidden)
[12 empty] | 1 | 2 | 3 | 4 | 5 | 6
[12 empty] | Option 1 | Option 2 | Option 3 | Option 4 | Option 5 | Option 6
[10 empty] | Address | Value Metric | 1: Age Based Replacement Program; 2: Delayed Targeted Replacement program; 3: Targeted Replacement program
[11 empty] | UARM - Environment and Community - Fire Risk | 1: 138162367.9362; 2: 118219479.7262; 3: 132094061.1562
[11 empty] | UARM - Safety & People - Worker | 1: 18222014.7689; 2: 15591778.9818; 3: 17421675.4534
Notes | [10 empty] | UARM - Network Performance Risk | 1: 5383472645.2679; 2: 4606401473.4981; 3: 5147022126.4892
Need to open the .xlsm Investment Summary report from Copperleaf in the Trusted folder Save in the preferred location as an .xlsx Need to test environment - other and when two of the same value models have been selected with a different name | [10 empty] | UARM - Financial Risk | 1: 204874544.4511; 2: 175302163.8124; 3: 195876134.8088
[11 empty] | UARM - Safety & People - Public | 1: 18222014.7689; 2: 15591778.9818; 3: 17421675.4534
[11 empty] | Terminal Value | 1: 8220134.611; 2: 7624012.5265; 3: 9382689.841
[11 empty] | Total Investment Cost | 1: 24639155.3055; 2: 14740623.7284; 3: 20965055.2073
Options
| Option | 2025 | 2026 | 2027 | 2028 | 2029
| Baseline | 105748992.61 | 121512483.39 | 139309185.14 | 159360578.48 | 181907771.95
| Age Based Replacement Program | 24924140.41 | 10391264.18 | 4673808.24 | 2032067.04 | 192547.01
| Delayed Targeted Replacement program | 105748992.61 | 121512483.39 | 139309185.14 | 159360578.48 | 181907771.95
| Targeted Replacement program | 62360688.18 | 42796082.19 | 36526870.3 | 33245874.33 | 27783833.34
Option Breakdown | [7 empty] | Folder and File Paths
| Option 3 |  |  |  |  | Greater 0 | (Multiple Items)
| Recommended Option - Value | [6 empty] | This File Path | \\TNAD.tasnetworks.com.au\user$\user_folders\BahramabadiM\My Documents\Trusted\InvestmentTemplate.xlsm
| Value Function Measure | Value | Value in % | Greater 0 |  | Row Labels | Sum of Value in % | Folder Path | H:\RPSAM\SAM\R24 IES\final draft\
Option 3 | UARM - Environment and Community - Fire Risk | 132094.0612 | 2.38% | 1 | K20 | Terminal Value | 0.17% | File Name | InvestmentSummary_R24_T_TL_RENTL_Insulator Renewal.xlsx
Option 3 | UARM - Safety & People - Worker | 17421.6755 | 0.31% | 1 | K21 | Total Investment Cost | 0.38% | File Path | H:\RPSAM\SAM\R24 IES\final draft\InvestmentSummary_R24_T_TL_RENTL_Insulator Renewal.xlsx
Option 3 | UARM - Network Performance Risk | 5147022.1265 | 92.9% | 1 | K22 | UARM - Environment and Community - Fire Risk | 2.38%
Option 3 | UARM - Financial Risk | 195876.1348 | 3.54% | 1 | K23 | UARM - Financial Risk | 3.54%
Option 3 | UARM - Safety & People - Public | 17421.6755 | 0.31% | 1 | K24 | UARM - Network Performance Risk | 92.9%
Option 3 | Terminal Value | 9382.6898 | 0.17% | 1 | K25 | UARM - Safety & People - Public | 0.31%
Option 3 | Total Investment Cost | -20965.0552 | 0.38% | 1 | K26 | UARM - Safety & People - Worker | 0.31%
Option 3 |  |  |  | 0 | K27
Option 3 |  |  |  | 0 | K28
Option 3 |  |  |  | 0 | K29
Option 3 |  |  |  | 0 | K30 |  |  | 1 | InvestmentSummary_R24_D_ND_PRHVR_Augment_HV_Fdr_TRIP.xlsx
Option 3 |  |  |  | 0 | K31 |  |  | 2 | InvestmentSummary_R24_D_OH_REPOL_Basic Fleet Pole Replacement.xlsx
Option 3 |  |  |  | 0 | K32 |  |  | 3 | InvestmentSummary_R24_T_ND_AUGSB_W Coast Reliability Improvement.xlsx
Option 3 |  |  |  | 0 | K33 |  |  | 4 | InvestmentSummary_R24_T_ND_AUGSB_Upper Derwent 110 kV Losses.xlsx
| Total | 5498253.308 | 99.99% |  |  |  |  | 5 | InvestmentSummary_R24_D_OH_SIWES_Bird_Mitigation.xlsx
[8 empty] | 6 | InvestmentSummary_R24_D_SB_REGMS_GMS_Replacement of GMS.xlsx
[8 empty] | 7 | InvestmentSummary_R24_D_OH_REPOL_Complex Design.xlsx
Start | Option 1 |  |  |  |  | Greater 0 | 1 | 8 | InvestmentSummary_R24_D_PQ_PQTXV_Power_Quality_LV_Tformers.xlsx
| Value Function Measure | Value | Value in % | Greater 0 |  |  |  | 9 | InvestmentSummary_R24_D_ND_PQLVV_Aug_HV_LV_Conductor.xlsx
Option 1 | UARM - Environment and Community - Fire Risk | 138162.3679 | 2.38% | 1 | K20 | Row Labels | Sum of Value in % | 10 | InvestmentSummary_R24_D_CA_SOLCP_Crossover_Extension_OH.xlsx
Option 1 | UARM - Safety & People - Worker | 18222.0148 | 0.31% | 1 | K21 | Terminal Value | 0.14% | 11 | InvestmentSummary_R24_D_CI_SOIRR_Irrigation_Supply.xlsx
Option 1 | UARM - Network Performance Risk | 5383472.6453 | 92.89% | 1 | K22 | Total Investment Cost | 0.43% | 12 | InvestmentSummary_R24_D_AMIPD_AM Improvement Program.xlsx
Option 1 | UARM - Financial Risk | 204874.5445 | 3.53% | 1 | K23 | UARM - Environment and Community - Fire Risk | 2.38% | 13 | InvestmentSummary_R24_D_CI_SOPOR_Permanent_Residence_OH.xlsx
Option 1 | UARM - Safety & People - Public | 18222.0148 | 0.31% | 1 | K24 | UARM - Financial Risk | 3.53% | 14 | InvestmentSummary_R24_D_CI_SUPOR_Permanent_Residence_UG.xlsx
Option 1 | Terminal Value | 8220.1346 | 0.14% | 1 | K25 | UARM - Network Performance Risk | 92.89% | 15 | InvestmentSummary_R24_D_CI_SOGSI_General_Supply_OH.xlsx
Option 1 | Total Investment Cost | -24639.1553 | 0.43% | 1 | K26 | UARM - Safety & People - Public | 0.31% | 16 | InvestmentSummary_R24_D_CI_SUGSI_General_Supply_UG.xlsx
Option 1 |  |  |  | 0 | K27 | UARM - Safety & People - Worker | 0.31% | 17 | InvestmentSummary_R24_D_CI_SUSBD_Subdivision_UG.xlsx
Option 1 |  |  |  | 0 | K28 |  |  | 18 | InvestmentSummary_R24_D_CI_SOSDI_Subdivision_OH.xlsx
Option 1 |  |  |  | 0 | K29 |  |  | 19 | InvestmentSummary_R24_D_CI_SUSUB_Augment_Dist_Substations.xlsx
Option 1 |  |  |  | 0 | K30 |  |  | 20 | InvestmentSummary_R24_T_ND_LAEMP_SELA.xlsx
Option 1 |  |  |  | 0 | K31 |  |  | 21 | InvestmentSummary_R24_D_CA_DESDB_Prelim_Drive_by_Design.xlsx
Option 1 |  |  |  | 0 | K32 |  |  | 22 | InvestmentSummary_R24_D_CI_SUMPR_Major_Commercial.xlsx
Option 1 |  |  |  | 0 | K33 |  |  | 23 | InvestmentSummary_R24_D_CI_EASEN_Easements_Non_Major_Comm.xlsx
| Total | 5746534.5665 | 99.99% |  |  |  |  | 24 | InvestmentSummary_R24_D_ND_PRHVR_Rosebery_Supply_Improve.xlsx
[8 empty] | 25 | InvestmentSummary_R24_D_ND_CAHVF_Huonville_Supply_Improvement.xlsx
[8 empty] | 26 | InvestmentSummary_R24_D_ND_CAHVF_Aug_Fdr_Network_Access.xlsx
[8 empty] | 27 | InvestmentSummary_R24_D_ND_PRHVR_Deloraine_Supply_Improve.xlsx
| Option 2 |  |  |  |  | Greater 0 | 1 | 28 | InvestmentSummary_R24_D_ND_CALVF_Augment_LV_Fdr_Capacity.xlsx
| Value Function Measure | Value | Value in % | Greater 0 |  |  |  | 29 | InvestmentSummary_R24_D_ND_CAHVF_Augment_HV_Fdr_Trunk.xlsx
Option 2 | UARM - Environment and Community - Fire Risk | 118219.4797 | 2.39% | 1 | K20 | Row Labels | Sum of Value in % | 30 | InvestmentSummary_R24_D_ND_CAHVF_Aug_Pole_Mtd_Regulator.xlsx
Option 2 | UARM - Safety & People - Worker | 15591.779 | 0.31% | 1 | K21 | Terminal Value | 0.15% | 31 | InvestmentSummary_R24_D_ND_CAHVF_Aug_Grnd_Mtd_Regulator.xlsx
Option 2 | UARM - Network Performance Risk | 4606401.4735 | 92.99% | 1 | K22 | Total Investment Cost | 0.3% | 32 | InvestmentSummary_R24_D_ND_CAHVF_22kV_Emu_Bay_Feeders.xlsx
Option 2 | UARM - Financial Risk | 175302.1638 | 3.54% | 1 | K23 | UARM - Environment and Community - Fire Risk | 2.39% | 33 | InvestmentSummary_R24_D_ND_CAHVF_Augment_HV_Fdr_Capacity.xlsx
Option 2 | UARM - Safety & People - Public | 15591.779 | 0.31% | 1 | K24 | UARM - Financial Risk | 3.54% | 34 | InvestmentSummary_R24_D_ND_CAHVF_Aug_SubStd_Cond_Capacity.xlsx
Option 2 | Terminal Value | 7624.0125 | 0.15% | 1 | K25 | UARM - Network Performance Risk | 92.99% | 35 | InvestmentSummary_R24_D_ND_LANDZ_LandAcq_ZoneSubs.xlsx
Option 2 | Total Investment Cost | -14740.6237 | 0.3% | 1 | K26 | UARM - Safety & People - Public | 0.31% | 36 | InvestmentSummary_R24_D_ND_CATXU_Aug_Dist_Sub.xlsx
Option 2 |  |  |  | 0 | K27 | UARM - Safety & People - Worker | 0.31% | 37
Option 2 |  |  |  | 0 | K28 |  |  | 38
Option 2 |  |  |  | 0 | K29 |  |  | 39
Option 2 |  |  |  | 0 | K30 |  |  | 40
Option 2 |  |  |  | 0 | K31 |  |  | 41
Option 2 |  |  |  | 0 | K32 |  |  | 42
Option 2 |  |  |  | 0 | K33 |  |  | 43
| Total | 4923990.0638 | 99.99%
| Option 3 |  |  |  |  | Greater 0 | 1
| Value Function Measure | Value | Value in % | Greater 0
Option 3 | UARM - Environment and Community - Fire Risk | 132094.0612 | 2.38% | 1 | K20 | Row Labels | Sum of Value in %
Option 3 | UARM - Safety & People - Worker | 17421.6755 | 0.31% | 1 | K21 | Terminal Value | 0.17%
Option 3 | UARM - Network Performance Risk | 5147022.1265 | 92.9% | 1 | K22 | Total Investment Cost | 0.38%
Option 3 | UARM - Financial Risk | 195876.1348 | 3.54% | 1 | K23 | UARM - Environment and Community - Fire Risk | 2.38%
Option 3 | UARM - Safety & People - Public | 17421.6755 | 0.31% | 1 | K24 | UARM - Financial Risk | 3.54%
Option 3 | Terminal Value | 9382.6898 | 0.17% | 1 | K25 | UARM - Network Performance Risk | 92.9%
Option 3 | Total Investment Cost | -20965.0552 | 0.38% | 1 | K26 | UARM - Safety & People - Public | 0.31%
Option 3 |  |  |  | 0 | K27 | UARM - Safety & People - Worker | 0.31%
Option 3 |  |  |  | 0 | K28
Option 3 |  |  |  | 0 | K29
Option 3 |  |  |  | 0 | K30
Option 3 |  |  |  | 0 | K31
Option 3 |  |  |  | 0 | K32
Option 3 |  |  |  | 0 | K33
| Total | 5498253.308 | 99.99%
| Option 4 |  |  |  |  | Greater 0 | 0
| Value Function Measure | Value | Value in % | Greater 0
Option 4 |  |  |  | 0 | K20 | Row Labels | Sum of Value in %
Option 4 |  |  |  | 0 | K21 |  | 0%
Option 4 |  |  |  | 0 | K22
Option 4 |  |  |  | 0 | K23
Option 4 |  |  |  | 0 | K24
Option 4 |  |  |  | 0 | K25
Option 4 |  |  |  | 0 | K26
Option 4 |  |  |  | 0 | K27
Option 4 |  |  |  | 0 | K28
Option 4 |  |  |  | 0 | K29
Option 4 |  |  |  | 0 | K30
Option 4 |  |  |  | 0 | K31
Option 4 |  |  |  | 0 | K32
Option 4 |  |  |  | 0 | K33
| Total | 0 | 0%
| Option 5 |  |  |  |  | Greater 0 | 0
| Value Function Measure | Value | Value in % | Greater 0
Option 5 |  |  |  | 0 | K20 | Row Labels | Sum of Value in %
Option 5 |  |  |  | 0 | K21 |  | 0%
Option 5 |  |  |  | 0 | K22
Option 5 |  |  |  | 0 | K23
Option 5 |  |  |  | 0 | K24
Option 5 |  |  |  | 0 | K25
Option 5 |  |  |  | 0 | K26
Option 5 |  |  |  | 0 | K27
Option 5 |  |  |  | 0 | K28
Option 5 |  |  |  | 0 | K29
Option 5 |  |  |  | 0 | K30
Option 5 |  |  |  | 0 | K31
Option 5 |  |  |  | 0 | K32
Option 5 |  |  |  | 0 | K33
| Total | 0 | 0%
| Option 6 |  |  |  |  | Greater 0 | 0
| Value Function Measure | Value | Value in % | Greater 0
Option 6 |  |  |  | 0 | K20 | Row Labels | Sum of Value in %
Option 6 |  |  |  | 0 | K21 |  | 0%
Option 6 |  |  |  | 0 | K22
Option 6 |  |  |  | 0 | K23
Option 6 |  |  |  | 0 | K24
Option 6 |  |  |  | 0 | K25
Option 6 |  |  |  | 0 | K26
Option 6 |  |  |  | 0 | K27
Option 6 |  |  |  | 0 | K28
Option 6 |  |  |  | 0 | K29
Option 6 |  |  |  | 0 | K30
Option 6 |  |  |  | 0 | K31
Option 6 |  |  |  | 0 | K32
Option 6 |  |  |  | 0 | K33
| Total | 0 | 0%

## Summary
Investment Evaluation Summary |  |  |  | Investment Code |  | Report Start Year |  | NPV Period | Base Fiscal Year | Currency Scale
|  |  |  | PRJ000643 |  | 2025 |  | 25 | FY23 | Literal
|  |  |  | Investment Name | [5 empty] | Scenario
|  |  |  | R24_T_TL_RENTL_Insulator Renewal | [5 empty] | Approved
Value Function |  | TasNetworks Value Function |  | Version |  | 0.1 |  | Date |  | 2022-11-03
Investment Description
Description |  | Transmission Line Insulator Assembly Replacement Program | [9 empty] | TRUE
Functional Area |  | RENTL |  |  | Department |  |  | Asset Strategy
Works Initiator |  |  |  |  | Portfolio |  |  | Tx - Renewal
Investment Category |  | Prescribed Services - Asset Renewal |  |  | Needs Item Reference
Investment Type |  | Network Project |  |  | Document No.
Investment Stage |  | Gate 2 – Investment Evaluation Summary |  |  | Project Zone Location |  |  | URL Link
PPM ID |  |  |  |  | Regulatory Test Required |  |  | No
Investment Summary
Problem Definition |  | Insulators are a vital component of the transmission system and represent an inherent operational, environmental (initiating bushfires) and safety risk when they are not able to perform to design specifications or no longer provide a reliable level of insulation between the conductor and the supporting structure. The consequence of an insulator failure is likely to vary between an insulator flashover resulting in a transmission line fault outage and a conductor dropping to the ground initiating bushfires, injuring the public or causing damage to third party property. In the event that insulator failure occurs there is also the additional requirement for extended transmission line circuit outages and associated impact on system availability and security of the transmission network in order to facilitate asset repairs. The transmission line insulator assembly replacement program proposes to mitigate the risk of insulator assembly failure, improve circuit reliability and reduce the lifecycle costs of insulator assemblies through the assessment of various investment mitigation strategies. | [9 empty] | TRUE
Recommendation |  | Targeted replacement program is recommended for approval as it best satisfies the customer and business needs. | [9 empty] | TRUE
Alternative Spend Profile
Name |  | Status | 2025 | 2026 | 2027 | 2028 | 2029 | R24 Expenditure | Total Expenditure | NPV | Alternative Start Date
Age Based Replacement Program |  | Candidate | 4676250 | 4676250 | 4676250 | 4676250 | 4676250 | 23381250 | 29491875 | 5738314431.89 | 4547400%
Delayed Targeted Replacement program |  | Candidate | 0 | 0 | 0 | 0 | 0 | 0 | 21500000 | 4916366051.27 | 4547400%
Targeted Replacement program |  | Recommended | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 7500000 | 28500000 | 5488870618.15 | 4547400%
0
0
0
Leader Endorsement
Name |  |  | Governance |  | Signature |  |  | Comments |  |  | Date
|  |  | Submission | [7 empty] | 4486800%
|  |  | Endorsement | [7 empty] | 4486800%
|  |  | Approval | [7 empty] | 4486800%
Investment Attachments
Date | Attachment Name |  | Description

## Investment Overview
Investment Evaluation Summary |  | Copperleaf Investment Code |  | Report Start Year | NPV Period | Base Fiscal Year | Currency Scale
|  | PRJ000643 |  | 2025 | 25 | FY23 | Literal
|  | Investment Name |  |  |  |  | Scenario
|  | R24_T_TL_RENTL_Insulator Renewal |  |  |  |  | Approved
Value Function | TasNetworks Value Function | Version |  | 0.1 | Date |  | 2022-11-03
Functional Area | RENTL |  | Department |  | Asset Strategy
Works Initiator |  |  | Portfolio |  | Tx - Renewal
Investment Category | Prescribed Services - Asset Renewal |  | Needs Item Reference
Investment Type | Network Project |  | Document No.
Investment Stage | Gate 2 – Investment Evaluation Summary |  | Project Zone Location |  | URL Link
PPM ID |  |  | Regulatory Test Required |  | No
Investment Overview
01. Overview | Background |  | TasNetworks has approximately 42,000 insulator assemblies in service across the transmission network, comprising predominantly glass or porcelain disc insulator assemblies. An insulator’s main function is to provide both a reliable mechanical connection for the energised and suspended conductor. They also provide electrical isolation from the supporting structure, to ensure that there is no flow of current through the support structure to the ground. And they also provide separation from the other phase conductors. Insulators must therefore be maintained in a serviceable state to mitigate the risk of the conductor falling to ground, flashover or breaching the required electrical clearance to support structures, other phase conductors or ground. Insulator integrity is reliant on maintaining the key properties; mechanical strength, insulation resistance, dielectric strength and free from unwanted impurities. The economic life of porcelain and glass insulator assemblies is 60 years, compared to 45 years for synthetic/composite insulator assemblies. Environmental factors such as pollution, corrosion and lightning strikes may result in accelerated insulator degradation and premature ageing. This can lead to insulator assembly failure prior to their expected economic life. While economic age is not the predominant driver for asset replacement decisions, it is important to recognise that the probability of failure increases significantly towards the end of their useful life. Transmission line insulator assemblies are currently assessed periodically. Condition assessment identifies the need to replace those insulators found to be at end of life where there is evidence to suggest that disc and fitting integrity have deteriorated to such an extent that both the mechanical and electrical characteristics of the insulator assemblies are compromised. TasNetworks currently applies a condition based assessment to its insulator assemblies to determine the likely end of life. This condition based approach has identified approximately 4000 insulator strings across a number of transmission circuits in the transmission network will require replacement in the regulatory period 2024-29. |  |  |  |  | TRUE
| Problem Definition |  | Insulators are a vital component of the transmission system and represent an inherent operational, environmental (initiating bushfires) and safety risk when they are not able to perform to design specifications or no longer provide a reliable level of insulation between the conductor and the supporting structure. The consequence of an insulator failure is likely to vary between an insulator flashover resulting in a transmission line fault outage and a conductor dropping to the ground initiating bushfires, injuring the public or causing damage to third party property. In the event that insulator failure occurs there is also the additional requirement for extended transmission line circuit outages and associated impact on system availability and security of the transmission network in order to facilitate asset repairs. The transmission line insulator assembly replacement program proposes to mitigate the risk of insulator assembly failure, improve circuit reliability and reduce the lifecycle costs of insulator assemblies through the assessment of various investment mitigation strategies. |  |  |  |  | FALSE
02. Customer Needs and Impact | Customer Needs and impact |  | TasNetworks has a customer and stakeholder engagement strategy to inform the existing program of work and the upcoming revenue submission. The feedback obtained informs the approach taken by TasNetworks to align our investments with customer needs and impacts. Customer needs addressed by this investment include: - affordability; and - supply reliability and safety of the current network; Consumers have also identified safety, restoration of faults/emergencies and supply reliability as the highest performing services offered by TasNetworks. The correct operation of insulator assemblies are critical to enable TasNetworks to offer services that also meet these top priorities. |  |  |  |  | TRUE

## Objectives and Analysis
Investment Evaluation Summary |  | Copperleaf Investment Code |  | Report Start Year | NPV Period | Base Fiscal Year | Currency Scale
|  | PRJ000643 |  | 2025 | 25 | FY23 | Literal
|  | Investment Name |  |  |  |  | Scenario
|  | R24_T_TL_RENTL_Insulator Renewal |  |  |  |  | Approved
Value Function | TasNetworks Value Function | Version |  | 0.1 | Date |  | 2022-11-03
Functional Area | RENTL |  | Department |  | Asset Strategy
Works Initiator |  |  | Portfolio |  | Tx - Renewal
Investment Category | Prescribed Services - Asset Renewal |  | Needs Item Reference
Investment Type | Network Project |  | Document No.
Investment Stage | Gate 2 – Investment Evaluation Summary |  | Project Zone Location |  | URL Link
PPM ID |  |  | Regulatory Test Required |  | No
Objectives and Analysis
03. Business Performance Objectives | Safety and Wellbeing |  | Performance Measure: Significant incidents Investment impact on performance: Replacement of insulator assemblies reduces the risk of a dropped conductor resulting in bushfire starts and injury. Performance Measure: Reportable incidents Investment impact on performance: Replacement of insulator assemblies reduces the risk of a dropped conductor resulting in bushfire starts and injury. |  |  |  |  | TRUE
| Our Customers |  | Performance Measure: Customer net promoter score Investment impact on performance: Replacement of insulator assemblies reduces the risk of a dropped conductor resulting in bushfire starts and injury. |  |  |  |  | FALSE
| Our People |  | Performance Measure: Employee engagement Investment impact on performance: Maintain our vision of ‘powering a bright future.’ |  |  |  |  | FALSE
| Our Business - Sustained Cost Management |  | Performance Measure: Capital expenditure Investment impact on performance: Replacement reduces our total cost when compared to managing end of life insulator failures. Performance Measure: Operational expenditure Investment impact on performance: Replacement reduces our operational cost in replacing insulators in poor condition in a planned way prior to failure. |  |  |  |  | FALSE
| Our Business - Network Service |  | Performance Measure: Service incentive bonuses earned - transmission Investment impact on performance: Replacement of insulator assemblies will reduce the risk of failure and therefore minimise prolonged outages. |  |  |  |  | FALSE
04. Business Risks | Death or Injury (Employee) |  | Failed insulator string results in dropped conductor and subsequent injury or death. |  |  |  |  | FALSE
| Death or Injury (Public) |  | Failed insulator string results in dropped conductor and subsequent injury or death. |  |  |  |  | FALSE
| Sustainable and Predictable Pricing | [6 empty] | FALSE
| Widespread Power Disruption |  | Failed insulator assembly results in the loss of supply to customers on radial transmission lines. |  |  |  |  | FALSE
| Bushfire Start |  | Failed insulator string results in dropped conductor and subsequent bushfire start. |  |  |  |  | FALSE
| Loss of Major Industrial |  | Failed insulator string results in dropped conductor and subsequent loss or limit of supply to a major industrial. |  |  |  |  | FALSE
| Customer Focus | [6 empty] | FALSE
| Business Continuity Management | [6 empty] | FALSE
| Cyber Security | [6 empty] | FALSE
| Private Assets | [6 empty] | FALSE
Energy Policy and Regulation
Project Marinus (D&A)
Tasmanian Power System Complexity
| Emerging Complexity of the NEM | [6 empty] | FALSE
05. Strategic Objectives | Strategic Objectives |  | The strategic objective is to manage the risk to customers by developing a risk based strategic plan. This includes a condition/risk based approach to manage the assets to maintain reliability and security of the network and effectively manage the safety risk associated with maintaining the asset. |  |  |  |  | FALSE
| Strategic Document #1 |  | TasNetworks Towards 2030 Strategic Objective: Safety: We see ways to continually reduce safety risks over the next decade How the proposed investment will address the strategic goal: This investment is aimed at mitigating the risk of safety related incidents including bushfires caused by our assets and therefore minimising any liability associated with potential legal action. Strategic Objective: We continually assess what value means to our customers to better serve all our stakeholders How the proposed investment will address the strategic goal: The forward demand in this area has been reviewed with Network Planning and the most appropriate customer centric option selected. Strategic Objective: Ensuring our electricity network remains resilient and fit-for-purpose by proactively maintaining assets, designing out risks, and making prudent investments of long-term value. How the proposed investment will address the strategic goal: The long-term impact of asset maintenance and renewal has been reviewed out to 2050. The analysis clearly demonstrates work should be done to mitigate risks to customers now and into the future. Strategic Objective: To ensure our capital is used wisely, we will streamline our investment planning to achieve optimised investment strategies and have the best delivery model. How the proposed investment will address the strategic goal: Investment planning has been developed to align all asset categories. The plan has been developed out to 2050 to ensure the long-term objectives of optimising investment strategies is achieved. |  |  |  |  | FALSE
| Strategic Document #2 |  | TasNetworks Three Year Business Plan 2021-2024 Strategic Objective: Minimising costs and risk of events that can adversely impact our network. How the proposed investment will address the strategic goal: This investment is aimed at mitigating the risks caused by our assets and therefore delivering safe and reliable power. |  |  |  |  | FALSE
| Strategic Document #3 |  | Insulator Assemblies Asset Management Plan |  |  |  |  | FALSE
| Strategic Document #4 | [6 empty] | FALSE
| Strategic Document #5 | [6 empty] | FALSE
06. Project Objectives | Project Objectives |  | The transmission line insulator assembly replacement program proposes to mitigate the risk of insulator assembly failure, improve circuit reliability and reduce the lifecycle costs of insulator assemblies. |  |  |  |  | FALSE
07. Options Analysis | Benchmarking |  | TasNetworks participates in various formal benchmarking forums with the aim to benchmark asset management practices against international and national transmission companies. Key benchmarking forums include: - International Transmission Operations & Maintenance Study (ITOMS); and - Australian Energy Regulator (AER) Regulatory Information Notices (RIN). TasNetworks also works closely with transmission companies in other key industry forums such as CIGRE (International Council on Large Electric Systems) to compare asset management and performance. Neither benchmarking forum reports on insulator performance specifically, however TasNetworks has the lowest expenditure per circuit km of transmission lines in the reported voltage ranges in ITOMS and approximately average circuit performance. This suggests that TasNetworks' transmission line strategies are in line with delivering acceptable performance and prudent expenditure. |  |  |  |  | TRUE
| Expert Findings |  | Condition assessment reports are used on a continual basis to determine the likely insulator replacements. This condition assessment is an ongoing program and will continue through the 2024-2029 regulatory period. |  |  |  |  | FALSE
08. Investment Timing | Investment Timing |  | The program will continue for the whole regulatory period at a fairly constant rate (there will be minor variance year to year based on the transmission lines included in programmed replacements). With transmission lines of varying ages it is expected that the program will continue indefinitely and with the increasing use of better condition data volumes will be adjusted accordingly. |  |  |  |  | TRUE
09. Expected Outcomes and Benefits | Expected Outcomes and Benefits |  | The benefits to TasNetworks from implementation of the preferred option will be: - reduce business risk by replacing end of life insulator assemblies; - alignment with strategic asset management plans; - achieve reliable transmission line insulator assembly performance consistent with prescribed service standards; - operation and maintenance cost savings due to planned replacement of porcelain insulators; - compliance with relevant Australian standards; and - meet performance objectives identified in TasNetworks' Corporate Plan. |  |  |  |  | TRUE
10. Assumptions | Assumptions |  | In developing the program the unit volumes have been derived from the transmission lines likely to require insulator replacement in a 20 year period. Annual volumes have been compared with recent historical replacement volumes to provide a sustainable program over a longer timeframe. Unit values are based on historical unit costs with these unit costs applied to the program volumes to determine annual costs. |  |  |  |  | TRUE
11. Regulatory Considerations | Regulatory Investment Test |  | The asset replacements within this program do not require a Regulatory Investment Test for Transmission (RIT-T) as per the requirements of the NER.
| Meet or manage the expected demand for Standard Control Services (Distribution)/Prescribed Services (Transmission). |  | No
| Comply with all applicable regulatory obligations associated with the provision of Standard Control Services (Distribution)/Prescribed Services (Transmission). |  | No
| Maintain the quality, reliability and security of supply of Standard Control Services (Distribution)/Prescribed Services (Transmission). |  | Yes
| Maintain the reliability and security of the system through the supply of Standard Control Services (Distribution)/Prescribed Services (Transmission). |  | Yes
| Maintain the safety of the system through the supply of Standard Control Services (Distribution)/Prescribed Services (Transmission). |  | Yes
12. Recommendation | Recommendation |  | Targeted replacement program is recommended for approval as it best satisfies the customer and business needs. |  |  |  |  | TRUE

## Economic Analysis
alternative
| Investment Evaluation Summary |  |  |  | Investment Code |  | Report Start Year |  | Number of Years | Base Fiscal Year | Currency Scale
[5 empty] | PRJ000643 |  | 2025 |  | 25 | FY23 | Literal
[5 empty] | Investment Name | [5 empty] | Scenario
[5 empty] | R24_T_TL_RENTL_Insulator Renewal | [5 empty] | Approved
autofit | Value Function |  |  | TasNetworks Value Function | Version |  | 0.1 |  | Date |  | 2022-11-03
Economic Analysis
| Parameter |  |  |  | Value | Unit | Source of Values
75679 | NPV Period |  |  |  | 25 | Years | TasNetworks requirement
autofit | First Fiscal Year of Forecast |  |  |  | FY23 | - | TasNetworks requirement
| Weighted Average Cost of Capital (WACC) |  |  |  | 2.82 | % | 2019-24 Revenue determination and ISP 2022 draft data
| Voluntary load shedding assumed? |  |  |  | No | - | N/A
| Reduction in system losses considered? |  |  |  | No | - | N/A
| Value of Customer Reliability applied |  |  | Very large business customer - Services | 10.93 | $/kWh | AER - Values of Customer Reliability - Annual adjustment summary - December 2021
|  |  |  | Residential | 17.08 | $/kWh
|  |  |  | Very large business customer - Metals | 20.6 | $/kWh
|  |  |  | Very large business customer - Transmission | 27.43 | $/kWh
|  |  |  | Very large business customer - Mines | 36.47 | $/kWh
|  |  |  | Business customer - Agricultural | 39.28 | $/kWh
|  |  |  | Business customer - Commercial | 46.18 | $/kWh
|  |  |  | Very large business customer - Distribution | 58.8 | $/kWh
|  |  |  | Business customer - Industrial | 66.16 | $/kWh
autofit |  |  |  | Very large business customer - Industrial | 122.39 | $/kWh
Sensitivity to Project Timing
|  | 1 | Navigate to Copperleaf Portfolio and search for your Investment
|  | 2 | Navigate to the Value Comparison Page for your Investment through the breadcrumb menu
|  | 3 | Once on the Value Comparison Page, select "Value by Start Date" in the drop-down menu in the top-left corner of the page
|  | 4 | This screen will show the value change over time for each option in your investment
|  | 5 | With the snipping tool on your PC, take a screenshot of the chart and copy + paste it in this section of the report
Options Considered
| Options Summary |  |  |  | R24 Expenditure ($M) | NPV ($M) | Preferred Option | Reason for selection/rejection
| Age Based Replacement Program |  |  |  | 23.3813 | 5738.3144 | No | Whilst this option mitigates the risk of insulator failure it has been rejected as it does not comply with TasNetworks’ preferred asset replacement strategy to only replace assets identified as being in poor condition and creates an unsustainable increase in volume in the 2024 to 2029 period. The application of this strategy to TasNetworks’ insulator population would result in the replacement of 12,500 insulator strings at a cost of approximately $23.4m, compared to the required 4,000 insulators and $7.5m for targeted replacement. While this option would reduce TasNetworks’ risk exposure due to condition based insulator failure, the cost of achieving this outcome is not commensurate with the risk benefit obtained. TasNetworks' preferred asset risk management strategy is to target investment at those poorly performing assets that will result in the maintenance of risk at current levels, as opposed to significantly reducing or increasing its risk exposure.
| Delayed Targeted Replacement program |  |  |  | 0 | 4916.3661 | No | This option has been rejected as it does not manage risk to an acceptable level for the 2024-29 regulatory period and is has a lower NPV value compared to the selected option.
| Targeted Replacement program |  |  |  | 7.5 | 5488.8706 | Yes | This option has been selected as it mitigates the risk of insulator failure, maintains circuit reliability, reduces the lifecycle costs of insulator assemblies, and is the most favourable option economically. This option results in TasNetworks managing its fleet of insulators in a strategic manner, undertaking staged insulator replacements as they approach end of life, rather than deferring replacements until such time that defect and failure rates present an unacceptable risk to TasNetworks and its customers. It should also be noted that contractor resourcing limitations within Tasmania are such that insulator replacement programs larger than that proposed in this IES (resulting from deferral of this program) are not practical and will result in an increase in TasNetworks' risk profile.
0
0
0
NPV Components

## Needs Assessment (hidden)
Needs Assessment Form |  | Copperleaf Investment Code |  | Report Start Year | NPV Period | Base Fiscal Year | Currency Scale
|  | PRJ000643 |  | 2025 | 25 | FY23 | Literal
|  | Investment Name |  |  |  |  | Scenario
|  | R24_T_TL_RENTL_Insulator Renewal |  |  |  |  | Approved
Value Function | TasNetworks Value Function | Version |  | 0.1 | Date |  | 2022-11-03
Functional Area | RENTL |  | Department |  | Asset Strategy
Works Initiator |  |  | Portfolio |  | Tx - Renewal
Investment Category | Prescribed Services - Asset Renewal |  | Needs Item Reference
Investment Type | Network Project |  | Document No.
Investment Stage | Gate 2 – Investment Evaluation Summary |  | Project Zone Location
PPM ID |  |  | Regulatory Test Required |  | No
Investment Overview
01. Overview | Background |  | TasNetworks has approximately 42,000 insulator assemblies in service across the transmission network, comprising predominantly glass or porcelain disc insulator assemblies. An insulator’s main function is to provide both a reliable mechanical connection for the energised and suspended conductor. They also provide electrical isolation from the supporting structure, to ensure that there is no flow of current through the support structure to the ground. And they also provide separation from the other phase conductors. Insulators must therefore be maintained in a serviceable state to mitigate the risk of the conductor falling to ground, flashover or breaching the required electrical clearance to support structures, other phase conductors or ground. Insulator integrity is reliant on maintaining the key properties; mechanical strength, insulation resistance, dielectric strength and free from unwanted impurities. The economic life of porcelain and glass insulator assemblies is 60 years, compared to 45 years for synthetic/composite insulator assemblies. Environmental factors such as pollution, corrosion and lightning strikes may result in accelerated insulator degradation and premature ageing. This can lead to insulator assembly failure prior to their expected economic life. While economic age is not the predominant driver for asset replacement decisions, it is important to recognise that the probability of failure increases significantly towards the end of their useful life. Transmission line insulator assemblies are currently assessed periodically. Condition assessment identifies the need to replace those insulators found to be at end of life where there is evidence to suggest that disc and fitting integrity have deteriorated to such an extent that both the mechanical and electrical characteristics of the insulator assemblies are compromised. TasNetworks currently applies a condition based assessment to its insulator assemblies to determine the likely end of life. This condition based approach has identified approximately 4000 insulator strings across a number of transmission circuits in the transmission network will require replacement in the regulatory period 2024-29. |  |  |  |  | TRUE
| Problem Definition |  | Insulators are a vital component of the transmission system and represent an inherent operational, environmental (initiating bushfires) and safety risk when they are not able to perform to design specifications or no longer provide a reliable level of insulation between the conductor and the supporting structure. The consequence of an insulator failure is likely to vary between an insulator flashover resulting in a transmission line fault outage and a conductor dropping to the ground initiating bushfires, injuring the public or causing damage to third party property. In the event that insulator failure occurs there is also the additional requirement for extended transmission line circuit outages and associated impact on system availability and security of the transmission network in order to facilitate asset repairs. The transmission line insulator assembly replacement program proposes to mitigate the risk of insulator assembly failure, improve circuit reliability and reduce the lifecycle costs of insulator assemblies through the assessment of various investment mitigation strategies. |  |  |  |  | FALSE
02. Customer Needs and Impact | Customer Needs and impact |  | TasNetworks has a customer and stakeholder engagement strategy to inform the existing program of work and the upcoming revenue submission. The feedback obtained informs the approach taken by TasNetworks to align our investments with customer needs and impacts. Customer needs addressed by this investment include: - affordability; and - supply reliability and safety of the current network; Consumers have also identified safety, restoration of faults/emergencies and supply reliability as the highest performing services offered by TasNetworks. The correct operation of insulator assemblies are critical to enable TasNetworks to offer services that also meet these top priorities. |  |  |  |  | TRUE
03. Business Objectives | Business Objectives
04. Project Objectives | Project Objectives |  | The transmission line insulator assembly replacement program proposes to mitigate the risk of insulator assembly failure, improve circuit reliability and reduce the lifecycle costs of insulator assemblies. |  |  |  |  | FALSE
05. Risk Objective | Risk if not progressed | [6 empty] | TRUE
06. Investment Timing | Investment Timing |  | The program will continue for the whole regulatory period at a fairly constant rate (there will be minor variance year to year based on the transmission lines included in programmed replacements). With transmission lines of varying ages it is expected that the program will continue indefinitely and with the increasing use of better condition data volumes will be adjusted accordingly. |  |  |  |  | TRUE
07. Business Consulatation | Business Consulatation | [6 empty] | TRUE

## Option 1
alternative
| Investment Evaluation Summary |  |  |  |  | Investment Code |  | Report Start Year |  | Number of Years | Base Fiscal Year | Currency Scale
[6 empty] | PRJ000643 |  | 2025 |  | 25 | FY23 | Literal
[6 empty] | Investment Name | [5 empty] | Scenario
[6 empty] | R24_T_TL_RENTL_Insulator Renewal | [5 empty] | Approved
autofit | Value Function |  | TasNetworks Value Function |  |  | Version |  | 0.1 |  | Date |  | 2022-11-03
Alternative Overview
75679 | Alternative Name |  | Age Based Replacement Program
autofit | Description |  | This option considers the viability of replacing all insulators that have exceeded their economic life of either 45 or 60 years for composite/synthetic or porcelain and glass insulators respectively.
autofit | Alternative Status |  | Candidate
autofit | Alternative Start Date |  | 4547400%
| Reason for selection/rejection |  | Whilst this option mitigates the risk of insulator failure it has been rejected as it does not comply with TasNetworks’ preferred asset replacement strategy to only replace assets identified as being in poor condition and creates an unsustainable increase in volume in the 2024 to 2029 period. The application of this strategy to TasNetworks’ insulator population would result in the replacement of 12,500 insulator strings at a cost of approximately $23.4m, compared to the required 4,000 insulators and $7.5m for targeted replacement. While this option would reduce TasNetworks’ risk exposure due to condition based insulator failure, the cost of achieving this outcome is not commensurate with the risk benefit obtained. TasNetworks' preferred asset risk management strategy is to target investment at those poorly performing assets that will result in the maintenance of risk at current levels, as opposed to significantly reducing or increasing its risk exposure.
Alternative Spend Profile and Alternative Value
| Name |  | Account Type |  |  | 2025 | 2026 | 2027 | 2028 | 2029 | R24 Expenditure | Total Expenditure | NPV
| Age Based Replacement Program |  | Capex |  |  | 4676250 | 4676250 | 4676250 | 4676250 | 4676250 | 23381250 | 29491875 | 5738314431.89
|  |  | Opex |  |  | 0 | 0 | 0 | 0 | 0 | 0
[9 empty] | Value Function Measure |  |  | Value | Value in %
[9 empty] | UARM - Environment and Community - Fire Risk |  |  | 138162.3679 | 2.38%
[9 empty] | UARM - Safety & People - Worker |  |  | 18222.0148 | 0.31%
[9 empty] | UARM - Network Performance Risk |  |  | 5383472.6453 | 92.89%
[9 empty] | UARM - Financial Risk |  |  | 204874.5445 | 3.53%
[9 empty] | UARM - Safety & People - Public |  |  | 18222.0148 | 0.31%
[9 empty] | Terminal Value |  |  | 8220.1346 | 0.14%
[9 empty] | Total Investment Cost |  |  | -24639.1553 | 0.43%
[9 empty] | Total |  |  | 5746534.5665
Alternative Value Details
| Value Model | Value Measure |  | Type | Impact Year | Value | Unit | 2025 | 2026 | 2027 | 2028 | 2029
75679PRJ000652 / R24_D_OH_REPOL_Basic Fleet Pole ReplacInvestment CostInvestment CostCAPEX CostFALSE | Investment Cost | CAPEX Cost |  | Outcome | 2024 | 0 | Dollar | 4676250 | 4676250 | 4676250 | 4676250 | 4676250
75679PRJ000652 / R24_D_OH_REPOL_Basic Fleet Pole ReplacInvestment CostInvestment CostOPEX CostFALSE | Investment Cost | Total Investment Cost |  | Outcome | 2024 | -24639.1553 | Dollar | 4676250 | 4676250 | 4676250 | 4676250 | 4676250
75679PRJ000652 / R24_D_OH_REPOL_Basic Fleet Pole ReplacInvestment CostInvestment CostTotal Investment CostFALSE | Terminal Value | Terminal Value |  | Outcome | 2048 | 8220.1346 | Dollar | 0 | 0 | 0 | 0 | 0
75679PRJ000652 / R24_D_OH_REPOL_Basic Fleet Pole ReplacTerminal ValueTerminal ValueTerminal ValueFALSE | UARM - PA to Investment | UARM - Environment and Community - Fire Risk |  | Baseline |  | 0 | Dollar | 2535250.55 | 2913168.08 | 3339830.28 | 3820546.97 | 4361098.55
75679PRJ000652 / R24_D_OH_REPOL_Basic Fleet Pole ReplacUARM - PA to InvestmentUARM - PA to InvestmentUARM - Environment and Community - Fire RiskTRUE | UARM - PA to Investment | UARM - Environment and Community - Fire Risk |  | Outcome | 2024 | 138162.3679 | Dollar | 597537.05 | 249122.54 | 112050.95 | 48717.24 | 4616.17
75679PRJ000652 / R24_D_OH_REPOL_Basic Fleet Pole ReplacUARM - PA to InvestmentUARM - PA to InvestmentUARM - Environment and Community - Fire RiskFALSE | UARM - PA to Investment | UARM - Safety & People - Worker |  | Baseline |  | 0 | Dollar | 334370.16 | 384213.1 | 440484.9 | 503885.86 | 575178.35
75679PRJ000652 / R24_D_OH_REPOL_Basic Fleet Pole ReplacUARM - PA to InvestmentUARM - PA to InvestmentUARM - Safety & People - WorkerTRUE | UARM - PA to Investment | UARM - Safety & People - Worker |  | Outcome | 2024 | 18222.0148 | Dollar | 78808.21 | 32856.38 | 14778.22 | 6425.24 | 608.82
75679PRJ000652 / R24_D_OH_REPOL_Basic Fleet Pole ReplacUARM - PA to InvestmentUARM - PA to InvestmentUARM - Safety & People - WorkerFALSE | UARM - PA to Investment | UARM - Network Performance Risk |  | Baseline |  | 0 | Dollar | 98785596.71 | 113511087.76 | 130135906.19 | 148866948.52 | 169929446.66
75679PRJ000652 / R24_D_OH_REPOL_Basic Fleet Pole ReplacUARM - PA to InvestmentUARM - PA to InvestmentUARM - Network Performance RiskTRUE | UARM - PA to Investment | UARM - Network Performance Risk |  | Outcome | 2024 | 5383472.6453 | Dollar | 23282927.07 | 9707016.65 | 4366045.71 | 1898258.79 | 179868.1
75679PRJ000652 / R24_D_OH_REPOL_Basic Fleet Pole ReplacUARM - PA to InvestmentUARM - PA to InvestmentUARM - Network Performance RiskFALSE | UARM - PA to Investment | UARM - Financial Risk |  | Baseline |  | 0 | Dollar | 3759405.03 | 4319801.35 | 4952478.87 | 5665311.27 | 6466870.04
| UARM - PA to Investment | UARM - Financial Risk |  | Outcome | 2024 | 204874.5445 | Dollar | 886059.87 | 369412.23 | 166155.14 | 72240.53 | 6845.1
| UARM - PA to Investment | UARM - Safety & People - Public |  | Baseline |  | 0 | Dollar | 334370.16 | 384213.1 | 440484.9 | 503885.86 | 575178.35
| UARM - PA to Investment | UARM - Safety & People - Public |  | Outcome | 2024 | 18222.0148 | Dollar | 78808.21 | 32856.38 | 14778.22 | 6425.24 | 608.82
75679PRJ000652 / R24_D_OH_REPOL_Basic Fleet Pole ReplacUARM - PA to InvestmentUARM - PA to InvestmentUARM - Environment and Community - Other RiskTRUE
75679PRJ000652 / R24_D_OH_REPOL_Basic Fleet Pole ReplacUARM - PA to InvestmentUARM - PA to InvestmentUARM - Environment and Community - Other RiskFALSE
75679PRJ000652 / R24_D_OH_REPOL_Basic Fleet Pole ReplacUARM - PA to InvestmentUARM - PA to InvestmentUARM - Financial RiskTRUE
75679PRJ000652 / R24_D_OH_REPOL_Basic Fleet Pole ReplacUARM - PA to InvestmentUARM - PA to InvestmentUARM - Financial RiskFALSE
75679PRJ000652 / R24_D_OH_REPOL_Basic Fleet Pole ReplacUARM - PA to InvestmentUARM - PA to InvestmentUARM - Safety & People - PublicTRUE | [6 empty] | Baseline | 105748992.61 | 121512483.39 | 139309185.14 | 159360578.48 | 181907771.95
75679PRJ000652 / R24_D_OH_REPOL_Basic Fleet Pole ReplacUARM - PA to InvestmentUARM - PA to InvestmentUARM - Safety & People - PublicFALSE | [6 empty] | Outcome | 24924140.41 | 10391264.18 | 4673808.24 | 2032067.04 | 192547.01
Note: Based on the characteristics of the value model, Financial Benefits & Costs was excluded from the chart above - please refer to the "Economic Analysis" sheet for the full breakdown of Investment Value.

## Option 2
alternative
| Investment Evaluation Summary |  |  |  |  | Investment Code |  | Report Start Year |  | Number of Years | Base Fiscal Year | Currency Scale
[6 empty] | PRJ000643 |  | 2025 |  | 25 | FY23 | Literal
[6 empty] | Investment Name | [5 empty] | Scenario
[6 empty] | R24_T_TL_RENTL_Insulator Renewal | [5 empty] | Approved
autofit | Value Function |  | TasNetworks Value Function |  |  | Version |  | 0.1 |  | Date |  | 2022-11-03
Alternative Overview
75679 | Alternative Name |  | Delayed Targeted Replacement program
autofit | Description |  | Pausing the existing targeted replacement program and restarting in the next regulatory period (2029).
autofit | Alternative Status |  | Candidate
autofit | Alternative Start Date |  | 4547400%
| Reason for selection/rejection |  | This option has been rejected as it does not manage risk to an acceptable level for the 2024-29 regulatory period and is has a lower NPV value compared to the selected option.
Alternative Spend Profile and Alternative Value
| Name |  | Account Type |  |  | 2025 | 2026 | 2027 | 2028 | 2029 | R24 Expenditure | Total Expenditure | NPV
| Delayed Targeted Replacement program |  | Capex |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 21500000 | 4916366051.27
|  |  | Opex |  |  | 0 | 0 | 0 | 0 | 0 | 0
[9 empty] | Value Function Measure |  |  | Value | Value in %
[9 empty] | UARM - Environment and Community - Fire Risk |  |  | 118219.4797 | 2.39%
[9 empty] | UARM - Safety & People - Worker |  |  | 15591.779 | 0.31%
[9 empty] | UARM - Network Performance Risk |  |  | 4606401.4735 | 92.99%
[9 empty] | UARM - Financial Risk |  |  | 175302.1638 | 3.54%
[9 empty] | UARM - Safety & People - Public |  |  | 15591.779 | 0.31%
[9 empty] | Terminal Value |  |  | 7624.0125 | 0.15%
[9 empty] | Total Investment Cost |  |  | -14740.6237 | 0.3%
[9 empty] | Total |  |  | 4923990.0638
Alternative Value Details
| Value Model | Value Measure |  | Type | Impact Year | Value | Unit | 2025 | 2026 | 2027 | 2028 | 2029
75679PRJ000652 / R24_D_OH_REPOL_Basic Fleet Pole ReplacInvestment CostInvestment CostCAPEX CostFALSE | Investment Cost | CAPEX Cost |  | Outcome | 2029 | 0 | Dollar | 0 | 0 | 0 | 0 | 0
75679PRJ000652 / R24_D_OH_REPOL_Basic Fleet Pole ReplacInvestment CostInvestment CostOPEX CostFALSE | Investment Cost | Total Investment Cost |  | Outcome | 2029 | -14740.6237 | Dollar | 0 | 0 | 0 | 0 | 0
75679PRJ000652 / R24_D_OH_REPOL_Basic Fleet Pole ReplacInvestment CostInvestment CostTotal Investment CostFALSE | Terminal Value | Terminal Value |  | Outcome | 2048 | 7624.0125 | Dollar | 0 | 0 | 0 | 0 | 0
75679PRJ000652 / R24_D_OH_REPOL_Basic Fleet Pole ReplacTerminal ValueTerminal ValueTerminal ValueFALSE | UARM - PA to Investment | UARM - Environment and Community - Fire Risk |  | Baseline |  | 0 | Dollar | 2535250.55 | 2913168.08 | 3339830.28 | 3820546.97 | 4361098.55
75679PRJ000652 / R24_D_OH_REPOL_Basic Fleet Pole ReplacUARM - PA to InvestmentUARM - PA to InvestmentUARM - Environment and Community - Fire RiskTRUE | UARM - PA to Investment | UARM - Environment and Community - Fire Risk |  | Outcome | 2024 | 118219.4797 | Dollar | 2535250.55 | 2913168.08 | 3339830.28 | 3820546.97 | 4361098.55
75679PRJ000652 / R24_D_OH_REPOL_Basic Fleet Pole ReplacUARM - PA to InvestmentUARM - PA to InvestmentUARM - Environment and Community - Fire RiskFALSE | UARM - PA to Investment | UARM - Safety & People - Worker |  | Baseline |  | 0 | Dollar | 334370.16 | 384213.1 | 440484.9 | 503885.86 | 575178.35
75679PRJ000652 / R24_D_OH_REPOL_Basic Fleet Pole ReplacUARM - PA to InvestmentUARM - PA to InvestmentUARM - Safety & People - WorkerTRUE | UARM - PA to Investment | UARM - Safety & People - Worker |  | Outcome | 2024 | 15591.779 | Dollar | 334370.16 | 384213.1 | 440484.9 | 503885.86 | 575178.35
75679PRJ000652 / R24_D_OH_REPOL_Basic Fleet Pole ReplacUARM - PA to InvestmentUARM - PA to InvestmentUARM - Safety & People - WorkerFALSE | UARM - PA to Investment | UARM - Network Performance Risk |  | Baseline |  | 0 | Dollar | 98785596.71 | 113511087.76 | 130135906.19 | 148866948.52 | 169929446.66
75679PRJ000652 / R24_D_OH_REPOL_Basic Fleet Pole ReplacUARM - PA to InvestmentUARM - PA to InvestmentUARM - Network Performance RiskTRUE | UARM - PA to Investment | UARM - Network Performance Risk |  | Outcome | 2024 | 4606401.4735 | Dollar | 98785596.71 | 113511087.76 | 130135906.19 | 148866948.52 | 169929446.66
75679PRJ000652 / R24_D_OH_REPOL_Basic Fleet Pole ReplacUARM - PA to InvestmentUARM - PA to InvestmentUARM - Network Performance RiskFALSE | UARM - PA to Investment | UARM - Financial Risk |  | Baseline |  | 0 | Dollar | 3759405.03 | 4319801.35 | 4952478.87 | 5665311.27 | 6466870.04
| UARM - PA to Investment | UARM - Financial Risk |  | Outcome | 2024 | 175302.1638 | Dollar | 3759405.03 | 4319801.35 | 4952478.87 | 5665311.27 | 6466870.04
| UARM - PA to Investment | UARM - Safety & People - Public |  | Baseline |  | 0 | Dollar | 334370.16 | 384213.1 | 440484.9 | 503885.86 | 575178.35
| UARM - PA to Investment | UARM - Safety & People - Public |  | Outcome | 2024 | 15591.779 | Dollar | 334370.16 | 384213.1 | 440484.9 | 503885.86 | 575178.35
75679PRJ000652 / R24_D_OH_REPOL_Basic Fleet Pole ReplacUARM - PA to InvestmentUARM - PA to InvestmentUARM - Environment and Community - Other RiskTRUE
75679PRJ000652 / R24_D_OH_REPOL_Basic Fleet Pole ReplacUARM - PA to InvestmentUARM - PA to InvestmentUARM - Environment and Community - Other RiskFALSE
75679PRJ000652 / R24_D_OH_REPOL_Basic Fleet Pole ReplacUARM - PA to InvestmentUARM - PA to InvestmentUARM - Financial RiskTRUE
75679PRJ000652 / R24_D_OH_REPOL_Basic Fleet Pole ReplacUARM - PA to InvestmentUARM - PA to InvestmentUARM - Financial RiskFALSE
75679PRJ000652 / R24_D_OH_REPOL_Basic Fleet Pole ReplacUARM - PA to InvestmentUARM - PA to InvestmentUARM - Safety & People - PublicTRUE | [6 empty] | Baseline | 105748992.61 | 121512483.39 | 139309185.14 | 159360578.48 | 181907771.95
75679PRJ000652 / R24_D_OH_REPOL_Basic Fleet Pole ReplacUARM - PA to InvestmentUARM - PA to InvestmentUARM - Safety & People - PublicFALSE | [6 empty] | Outcome | 105748992.61 | 121512483.39 | 139309185.14 | 159360578.48 | 181907771.95
Note: Based on the characteristics of the value model, Financial Benefits & Costs was excluded from the chart above - please refer to the "Economic Analysis" sheet for the full breakdown of Investment Value.

## Option 3
alternative
| Investment Evaluation Summary |  |  |  |  | Investment Code |  | Report Start Year |  | Number of Years | Base Fiscal Year | Currency Scale
[6 empty] | PRJ000643 |  | 2025 |  | 25 | FY23 | Literal
[6 empty] | Investment Name | [5 empty] | Scenario
[6 empty] | R24_T_TL_RENTL_Insulator Renewal | [5 empty] | Approved
autofit | Value Function |  | TasNetworks Value Function |  |  | Version |  | 0.1 |  | Date |  | 2022-11-03
Alternative Overview
75679 | Alternative Name |  | Targeted Replacement program
autofit | Description |  | Continue TasNetworks' established insulator assembly replacement program, replacing insulator assemblies identified as being at end of life with new insulators.
autofit | Alternative Status |  | Recommended
autofit | Alternative Start Date |  | 4547400%
| Reason for selection/rejection |  | This option has been selected as it mitigates the risk of insulator failure, maintains circuit reliability, reduces the lifecycle costs of insulator assemblies, and is the most favourable option economically. This option results in TasNetworks managing its fleet of insulators in a strategic manner, undertaking staged insulator replacements as they approach end of life, rather than deferring replacements until such time that defect and failure rates present an unacceptable risk to TasNetworks and its customers. It should also be noted that contractor resourcing limitations within Tasmania are such that insulator replacement programs larger than that proposed in this IES (resulting from deferral of this program) are not practical and will result in an increase in TasNetworks' risk profile.
Alternative Spend Profile and Alternative Value
| Name |  | Account Type |  |  | 2025 | 2026 | 2027 | 2028 | 2029 | R24 Expenditure | Total Expenditure | NPV
| Targeted Replacement program |  | Capex |  |  | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 7500000 | 28500000 | 5488870618.15
|  |  | Opex |  |  | 0 | 0 | 0 | 0 | 0 | 0
[9 empty] | Value Function Measure |  |  | Value | Value in %
[9 empty] | UARM - Environment and Community - Fire Risk |  |  | 132094.0612 | 2.38%
[9 empty] | UARM - Safety & People - Worker |  |  | 17421.6755 | 0.31%
[9 empty] | UARM - Network Performance Risk |  |  | 5147022.1265 | 92.9%
[9 empty] | UARM - Financial Risk |  |  | 195876.1348 | 3.54%
[9 empty] | UARM - Safety & People - Public |  |  | 17421.6755 | 0.31%
[9 empty] | Terminal Value |  |  | 9382.6898 | 0.17%
[9 empty] | Total Investment Cost |  |  | -20965.0552 | 0.38%
[9 empty] | Total |  |  | 5498253.308
Alternative Value Details
| Value Model | Value Measure |  | Type | Impact Year | Value | Unit | 2025 | 2026 | 2027 | 2028 | 2029
75679PRJ000652 / R24_D_OH_REPOL_Basic Fleet Pole ReplacInvestment CostInvestment CostCAPEX CostFALSE | Investment Cost | CAPEX Cost |  | Outcome | 2024 | 0 | Dollar | 1500000 | 1500000 | 1500000 | 1500000 | 1500000
75679PRJ000652 / R24_D_OH_REPOL_Basic Fleet Pole ReplacInvestment CostInvestment CostOPEX CostFALSE | Investment Cost | Total Investment Cost |  | Outcome | 2024 | -20965.0552 | Dollar | 1500000 | 1500000 | 1500000 | 1500000 | 1500000
75679PRJ000652 / R24_D_OH_REPOL_Basic Fleet Pole ReplacInvestment CostInvestment CostTotal Investment CostFALSE | Terminal Value | Terminal Value |  | Outcome | 2048 | 9382.6898 | Dollar | 0 | 0 | 0 | 0 | 0
75679PRJ000652 / R24_D_OH_REPOL_Basic Fleet Pole ReplacTerminal ValueTerminal ValueTerminal ValueFALSE | UARM - PA to Investment | UARM - Environment and Community - Fire Risk |  | Baseline |  | 0 | Dollar | 2535250.55 | 2913168.08 | 3339830.28 | 3820546.97 | 4361098.55
75679PRJ000652 / R24_D_OH_REPOL_Basic Fleet Pole ReplacUARM - PA to InvestmentUARM - PA to InvestmentUARM - Environment and Community - Fire RiskTRUE | UARM - PA to Investment | UARM - Environment and Community - Fire Risk |  | Outcome | 2024 | 132094.0612 | Dollar | 1495049.41 | 1026003.07 | 875703.55 | 797044.2 | 666095.98
75679PRJ000652 / R24_D_OH_REPOL_Basic Fleet Pole ReplacUARM - PA to InvestmentUARM - PA to InvestmentUARM - Environment and Community - Fire RiskFALSE | UARM - PA to Investment | UARM - Safety & People - Worker |  | Baseline |  | 0 | Dollar | 334370.16 | 384213.1 | 440484.9 | 503885.86 | 575178.35
75679PRJ000652 / R24_D_OH_REPOL_Basic Fleet Pole ReplacUARM - PA to InvestmentUARM - PA to InvestmentUARM - Safety & People - WorkerTRUE | UARM - PA to Investment | UARM - Safety & People - Worker |  | Outcome | 2024 | 17421.6755 | Dollar | 197179.69 | 135317.91 | 115495.15 | 105120.89 | 87850.34
75679PRJ000652 / R24_D_OH_REPOL_Basic Fleet Pole ReplacUARM - PA to InvestmentUARM - PA to InvestmentUARM - Safety & People - WorkerFALSE | UARM - PA to Investment | UARM - Network Performance Risk |  | Baseline |  | 0 | Dollar | 98785596.71 | 113511087.76 | 130135906.19 | 148866948.52 | 169929446.66
75679PRJ000652 / R24_D_OH_REPOL_Basic Fleet Pole ReplacUARM - PA to InvestmentUARM - PA to InvestmentUARM - Network Performance RiskTRUE | UARM - PA to Investment | UARM - Network Performance Risk |  | Outcome | 2024 | 5147022.1265 | Dollar | 58254340.21 | 39978031.11 | 34121636.42 | 31056688.61 | 25954313.96
75679PRJ000652 / R24_D_OH_REPOL_Basic Fleet Pole ReplacUARM - PA to InvestmentUARM - PA to InvestmentUARM - Network Performance RiskFALSE | UARM - PA to Investment | UARM - Financial Risk |  | Baseline |  | 0 | Dollar | 3759405.03 | 4319801.35 | 4952478.87 | 5665311.27 | 6466870.04
| UARM - PA to Investment | UARM - Financial Risk |  | Outcome | 2024 | 195876.1348 | Dollar | 2216939.18 | 1521412.19 | 1298540.03 | 1181899.74 | 987722.72
| UARM - PA to Investment | UARM - Safety & People - Public |  | Baseline |  | 0 | Dollar | 334370.16 | 384213.1 | 440484.9 | 503885.86 | 575178.35
| UARM - PA to Investment | UARM - Safety & People - Public |  | Outcome | 2024 | 17421.6755 | Dollar | 197179.69 | 135317.91 | 115495.15 | 105120.89 | 87850.34
75679PRJ000652 / R24_D_OH_REPOL_Basic Fleet Pole ReplacUARM - PA to InvestmentUARM - PA to InvestmentUARM - Environment and Community - Other RiskTRUE
75679PRJ000652 / R24_D_OH_REPOL_Basic Fleet Pole ReplacUARM - PA to InvestmentUARM - PA to InvestmentUARM - Environment and Community - Other RiskFALSE
75679PRJ000652 / R24_D_OH_REPOL_Basic Fleet Pole ReplacUARM - PA to InvestmentUARM - PA to InvestmentUARM - Financial RiskTRUE
75679PRJ000652 / R24_D_OH_REPOL_Basic Fleet Pole ReplacUARM - PA to InvestmentUARM - PA to InvestmentUARM - Financial RiskFALSE
75679PRJ000652 / R24_D_OH_REPOL_Basic Fleet Pole ReplacUARM - PA to InvestmentUARM - PA to InvestmentUARM - Safety & People - PublicTRUE | [6 empty] | Baseline | 105748992.61 | 121512483.39 | 139309185.14 | 159360578.48 | 181907771.95
75679PRJ000652 / R24_D_OH_REPOL_Basic Fleet Pole ReplacUARM - PA to InvestmentUARM - PA to InvestmentUARM - Safety & People - PublicFALSE | [6 empty] | Outcome | 62360688.18 | 42796082.19 | 36526870.3 | 33245874.33 | 27783833.34
Note: Based on the characteristics of the value model, Financial Benefits & Costs was excluded from the chart above - please refer to the "Economic Analysis" sheet for the full breakdown of Investment Value.

## Option 4 (hidden)
alternative
| Investment Evaluation Summary |  |  |  |  | Investment Code |  | Report Start Year |  | Number of Years | Base Fiscal Year | Currency Scale
[6 empty] | PRJ000643 |  | 2025 |  | 25 | FY23 | Literal
[6 empty] | Investment Name | [5 empty] | Scenario
[6 empty] | R24_T_TL_RENTL_Insulator Renewal | [5 empty] | Approved
autofit | Value Function |  | TasNetworks Value Function |  |  | Version |  | 0.1 |  | Date |  | 2022-11-03
Alternative Overview
75679 | Alternative Name
autofit | Description
autofit | Alternative Status
autofit | Alternative Start Date
Reason for selection/rejection
Alternative Spend Profile and Alternative Value
| Name |  | Account Type |  |  | 2025 | 2026 | 2027 | 2028 | 2029 | R24 Expenditure | Total Expenditure | NPV
0
0
[9 empty] | Value Function Measure |  |  | Value | Value in %
[9 empty] | Total |  |  | 0
Alternative Value Details
| Value Model | Value Measure |  | Type | Impact Year | Value | Unit | 2025 | 2026 | 2027 | 2028 | 2029
75679PRJ000652 / R24_D_OH_REPOL_Basic Fleet Pole ReplacInvestment CostInvestment CostCAPEX CostFALSE
75679PRJ000652 / R24_D_OH_REPOL_Basic Fleet Pole ReplacInvestment CostInvestment CostOPEX CostFALSE
75679PRJ000652 / R24_D_OH_REPOL_Basic Fleet Pole ReplacInvestment CostInvestment CostTotal Investment CostFALSE
75679PRJ000652 / R24_D_OH_REPOL_Basic Fleet Pole ReplacTerminal ValueTerminal ValueTerminal ValueFALSE
75679PRJ000652 / R24_D_OH_REPOL_Basic Fleet Pole ReplacUARM - PA to InvestmentUARM - PA to InvestmentUARM - Environment and Community - Fire RiskTRUE
75679PRJ000652 / R24_D_OH_REPOL_Basic Fleet Pole ReplacUARM - PA to InvestmentUARM - PA to InvestmentUARM - Environment and Community - Fire RiskFALSE
75679PRJ000652 / R24_D_OH_REPOL_Basic Fleet Pole ReplacUARM - PA to InvestmentUARM - PA to InvestmentUARM - Safety & People - WorkerTRUE
75679PRJ000652 / R24_D_OH_REPOL_Basic Fleet Pole ReplacUARM - PA to InvestmentUARM - PA to InvestmentUARM - Safety & People - WorkerFALSE
75679PRJ000652 / R24_D_OH_REPOL_Basic Fleet Pole ReplacUARM - PA to InvestmentUARM - PA to InvestmentUARM - Network Performance RiskTRUE
75679PRJ000652 / R24_D_OH_REPOL_Basic Fleet Pole ReplacUARM - PA to InvestmentUARM - PA to InvestmentUARM - Network Performance RiskFALSE
75679PRJ000652 / R24_D_OH_REPOL_Basic Fleet Pole ReplacUARM - PA to InvestmentUARM - PA to InvestmentUARM - Environment and Community - Other RiskTRUE
75679PRJ000652 / R24_D_OH_REPOL_Basic Fleet Pole ReplacUARM - PA to InvestmentUARM - PA to InvestmentUARM - Environment and Community - Other RiskFALSE
75679PRJ000652 / R24_D_OH_REPOL_Basic Fleet Pole ReplacUARM - PA to InvestmentUARM - PA to InvestmentUARM - Financial RiskTRUE
75679PRJ000652 / R24_D_OH_REPOL_Basic Fleet Pole ReplacUARM - PA to InvestmentUARM - PA to InvestmentUARM - Financial RiskFALSE
75679PRJ000652 / R24_D_OH_REPOL_Basic Fleet Pole ReplacUARM - PA to InvestmentUARM - PA to InvestmentUARM - Safety & People - PublicTRUE | [6 empty] | Baseline | 0 | 0 | 0 | 0 | 0
75679PRJ000652 / R24_D_OH_REPOL_Basic Fleet Pole ReplacUARM - PA to InvestmentUARM - PA to InvestmentUARM - Safety & People - PublicFALSE | [6 empty] | Outcome | 0 | 0 | 0 | 0 | 0
Note: Based on the characteristics of the value model, Financial Benefits & Costs was excluded from the chart above - please refer to the "Economic Analysis" sheet for the full breakdown of Investment Value.

## Option 5 (hidden)
alternative
| Investment Evaluation Summary |  |  |  |  | Investment Code |  | Report Start Year |  | Number of Years | Base Fiscal Year | Currency Scale
[6 empty] | PRJ000643 |  | 2025 |  | 25 | FY23 | Literal
[6 empty] | Investment Name | [5 empty] | Scenario
[6 empty] | R24_T_TL_RENTL_Insulator Renewal | [5 empty] | Approved
autofit | Value Function |  | TasNetworks Value Function |  |  | Version |  | 0.1 |  | Date |  | 2022-11-03
Alternative Overview
75679 | Alternative Name
autofit | Description
autofit | Alternative Status
autofit | Alternative Start Date
Reason for selection/rejection
Alternative Spend Profile and Alternative Value
| Name |  | Account Type |  |  | 2025 | 2026 | 2027 | 2028 | 2029 | R24 Expenditure | Total Expenditure | NPV
0
0
[9 empty] | Value Function Measure |  |  | Value | Value in %
[9 empty] | Total |  |  | 0
Alternative Value Details
| Value Model | Value Measure |  | Type | Impact Year | Value | Unit | 2025 | 2026 | 2027 | 2028 | 2029
75679PRJ000652 / R24_D_OH_REPOL_Basic Fleet Pole ReplacInvestment CostInvestment CostCAPEX CostFALSE
75679PRJ000652 / R24_D_OH_REPOL_Basic Fleet Pole ReplacInvestment CostInvestment CostOPEX CostFALSE
75679PRJ000652 / R24_D_OH_REPOL_Basic Fleet Pole ReplacInvestment CostInvestment CostTotal Investment CostFALSE
75679PRJ000652 / R24_D_OH_REPOL_Basic Fleet Pole ReplacTerminal ValueTerminal ValueTerminal ValueFALSE
75679PRJ000652 / R24_D_OH_REPOL_Basic Fleet Pole ReplacUARM - PA to InvestmentUARM - PA to InvestmentUARM - Environment and Community - Fire RiskTRUE
75679PRJ000652 / R24_D_OH_REPOL_Basic Fleet Pole ReplacUARM - PA to InvestmentUARM - PA to InvestmentUARM - Environment and Community - Fire RiskFALSE
75679PRJ000652 / R24_D_OH_REPOL_Basic Fleet Pole ReplacUARM - PA to InvestmentUARM - PA to InvestmentUARM - Safety & People - WorkerTRUE
75679PRJ000652 / R24_D_OH_REPOL_Basic Fleet Pole ReplacUARM - PA to InvestmentUARM - PA to InvestmentUARM - Safety & People - WorkerFALSE
75679PRJ000652 / R24_D_OH_REPOL_Basic Fleet Pole ReplacUARM - PA to InvestmentUARM - PA to InvestmentUARM - Network Performance RiskTRUE
75679PRJ000652 / R24_D_OH_REPOL_Basic Fleet Pole ReplacUARM - PA to InvestmentUARM - PA to InvestmentUARM - Network Performance RiskFALSE
75679PRJ000652 / R24_D_OH_REPOL_Basic Fleet Pole ReplacUARM - PA to InvestmentUARM - PA to InvestmentUARM - Environment and Community - Other RiskTRUE
75679PRJ000652 / R24_D_OH_REPOL_Basic Fleet Pole ReplacUARM - PA to InvestmentUARM - PA to InvestmentUARM - Environment and Community - Other RiskFALSE
75679PRJ000652 / R24_D_OH_REPOL_Basic Fleet Pole ReplacUARM - PA to InvestmentUARM - PA to InvestmentUARM - Financial RiskTRUE
75679PRJ000652 / R24_D_OH_REPOL_Basic Fleet Pole ReplacUARM - PA to InvestmentUARM - PA to InvestmentUARM - Financial RiskFALSE
75679PRJ000652 / R24_D_OH_REPOL_Basic Fleet Pole ReplacUARM - PA to InvestmentUARM - PA to InvestmentUARM - Safety & People - PublicTRUE | [6 empty] | Baseline | 0 | 0 | 0 | 0 | 0
75679PRJ000652 / R24_D_OH_REPOL_Basic Fleet Pole ReplacUARM - PA to InvestmentUARM - PA to InvestmentUARM - Safety & People - PublicFALSE | [6 empty] | Outcome | 0 | 0 | 0 | 0 | 0
Note: Based on the characteristics of the value model, Financial Benefits & Costs was excluded from the chart above - please refer to the "Economic Analysis" sheet for the full breakdown of Investment Value.

## Option 6 (hidden)
alternative
| Investment Evaluation Summary |  |  |  |  | Investment Code |  | Report Start Year |  | Number of Years | Base Fiscal Year | Currency Scale
[6 empty] | PRJ000643 |  | 2025 |  | 25 | FY23 | Literal
[6 empty] | Investment Name | [5 empty] | Scenario
[6 empty] | R24_T_TL_RENTL_Insulator Renewal | [5 empty] | Approved
autofit | Value Function |  | TasNetworks Value Function |  |  | Version |  | 0.1 |  | Date |  | 2022-11-03
Alternative Overview
75679 | Alternative Name
autofit | Description
autofit | Alternative Status
autofit | Alternative Start Date
Reason for selection/rejection
Alternative Spend Profile and Alternative Value
| Name |  | Account Type |  |  | 2025 | 2026 | 2027 | 2028 | 2029 | R24 Expenditure | Total Expenditure | NPV
0
0
[9 empty] | Value Function Measure |  |  | Value | Value in %
[9 empty] | Total |  |  | 0
Alternative Value Details
| Value Model | Value Measure |  | Type | Impact Year | Value | Unit | 2025 | 2026 | 2027 | 2028 | 2029
75679PRJ000652 / R24_D_OH_REPOL_Basic Fleet Pole ReplacInvestment CostInvestment CostCAPEX CostFALSE
75679PRJ000652 / R24_D_OH_REPOL_Basic Fleet Pole ReplacInvestment CostInvestment CostOPEX CostFALSE
75679PRJ000652 / R24_D_OH_REPOL_Basic Fleet Pole ReplacInvestment CostInvestment CostTotal Investment CostFALSE
75679PRJ000652 / R24_D_OH_REPOL_Basic Fleet Pole ReplacTerminal ValueTerminal ValueTerminal ValueFALSE
75679PRJ000652 / R24_D_OH_REPOL_Basic Fleet Pole ReplacUARM - PA to InvestmentUARM - PA to InvestmentUARM - Environment and Community - Fire RiskTRUE
75679PRJ000652 / R24_D_OH_REPOL_Basic Fleet Pole ReplacUARM - PA to InvestmentUARM - PA to InvestmentUARM - Environment and Community - Fire RiskFALSE
75679PRJ000652 / R24_D_OH_REPOL_Basic Fleet Pole ReplacUARM - PA to InvestmentUARM - PA to InvestmentUARM - Safety & People - WorkerTRUE
75679PRJ000652 / R24_D_OH_REPOL_Basic Fleet Pole ReplacUARM - PA to InvestmentUARM - PA to InvestmentUARM - Safety & People - WorkerFALSE
75679PRJ000652 / R24_D_OH_REPOL_Basic Fleet Pole ReplacUARM - PA to InvestmentUARM - PA to InvestmentUARM - Network Performance RiskTRUE
75679PRJ000652 / R24_D_OH_REPOL_Basic Fleet Pole ReplacUARM - PA to InvestmentUARM - PA to InvestmentUARM - Network Performance RiskFALSE
75679PRJ000652 / R24_D_OH_REPOL_Basic Fleet Pole ReplacUARM - PA to InvestmentUARM - PA to InvestmentUARM - Environment and Community - Other RiskTRUE
75679PRJ000652 / R24_D_OH_REPOL_Basic Fleet Pole ReplacUARM - PA to InvestmentUARM - PA to InvestmentUARM - Environment and Community - Other RiskFALSE
75679PRJ000652 / R24_D_OH_REPOL_Basic Fleet Pole ReplacUARM - PA to InvestmentUARM - PA to InvestmentUARM - Financial RiskTRUE
75679PRJ000652 / R24_D_OH_REPOL_Basic Fleet Pole ReplacUARM - PA to InvestmentUARM - PA to InvestmentUARM - Financial RiskFALSE
75679PRJ000652 / R24_D_OH_REPOL_Basic Fleet Pole ReplacUARM - PA to InvestmentUARM - PA to InvestmentUARM - Safety & People - PublicTRUE | [6 empty] | Baseline | 0 | 0 | 0 | 0 | 0
75679PRJ000652 / R24_D_OH_REPOL_Basic Fleet Pole ReplacUARM - PA to InvestmentUARM - PA to InvestmentUARM - Safety & People - PublicFALSE | [6 empty] | Outcome | 0 | 0 | 0 | 0 | 0
Note: Based on the characteristics of the value model, Financial Benefits & Costs was excluded from the chart above - please refer to the "Economic Analysis" sheet for the full breakdown of Investment Value.

## TextFormatting (hidden)
Index | 8
Column Width | 238
Font | Calibri
Font Size | 11
Font Colour
Text | Sheet | Group | Field | Row Height | Row Number
Transmission Line Insulator Assembly Replacement Program | Investment Summary | Header | Description | 15 | 9
TasNetworks has approximately 42,000 insulator assemblies in service across the transmission network, comprising predominantly glass or porcelain disc insulator assemblies. An insulator’s main function is to provide both a reliable mechanical connection for the energised and suspended conductor. They also provide electrical isolation from the supporting structure, to ensure that there is no flow of current through the support structure to the ground. And they also provide separation from the other phase conductors. Insulators must therefore be maintained in a serviceable state to mitigate the risk of the conductor falling to ground, flashover or breaching the required electrical clearance to support structures, other phase conductors or ground. Insulator integrity is reliant on maintaining the key properties; mechanical strength, insulation resistance, dielectric strength and free from unwanted impurities. The economic life of porcelain and glass insulator assemblies is 60 years, compared to 45 years for synthetic/composite insulator assemblies. Environmental factors such as pollution, corrosion and lightning strikes may result in accelerated insulator degradation and premature ageing. This can lead to insulator assembly failure prior to their expected economic life. While economic age is not the predominant driver for asset replacement decisions, it is important to recognise that the probability of failure increases significantly towards the end of their useful life. Transmission line insulator assemblies are currently assessed periodically. Condition assessment identifies the need to replace those insulators found to be at end of life where there is evidence to suggest that disc and fitting integrity have deteriorated to such an extent that both the mechanical and electrical characteristics of the insulator assemblies are compromised. TasNetworks currently applies a condition based assessment to its insulator assemblies to determine the likely end of life. This condition based approach has identified approximately 4000 insulator strings across a number of transmission circuits in the transmission network will require replacement in the regulatory period 2024-29. | Investment Summary | 0.1 Overview | Background | 360 | 16
Insulators are a vital component of the transmission system and represent an inherent operational, environmental (initiating bushfires) and safety risk when they are not able to perform to design specifications or no longer provide a reliable level of insulation between the conductor and the supporting structure. The consequence of an insulator failure is likely to vary between an insulator flashover resulting in a transmission line fault outage and a conductor dropping to the ground initiating bushfires, injuring the public or causing damage to third party property. In the event that insulator failure occurs there is also the additional requirement for extended transmission line circuit outages and associated impact on system availability and security of the transmission network in order to facilitate asset repairs. The transmission line insulator assembly replacement program proposes to mitigate the risk of insulator assembly failure, improve circuit reliability and reduce the lifecycle costs of insulator assemblies through the assessment of various investment mitigation strategies. | Investment Summary | 0.1 Overview | Problem Definition | 195 | 17
TasNetworks has a customer and stakeholder engagement strategy to inform the existing program of work and the upcoming revenue submission. The feedback obtained informs the approach taken by TasNetworks to align our investments with customer needs and impacts. Customer needs addressed by this investment include: - affordability; and - supply reliability and safety of the current network; Consumers have also identified safety, restoration of faults/emergencies and supply reliability as the highest performing services offered by TasNetworks. The correct operation of insulator assemblies are critical to enable TasNetworks to offer services that also meet these top priorities. | Investment Summary | 02. Customer Needs and Impact | Customer Needs and impact | 165 | 18
Performance Measure: Significant incidents Investment impact on performance: Replacement of insulator assemblies reduces the risk of a dropped conductor resulting in bushfire starts and injury. Performance Measure: Reportable incidents Investment impact on performance: Replacement of insulator assemblies reduces the risk of a dropped conductor resulting in bushfire starts and injury. | Objectives and Analysis | 03. Business Performance Objectives | Safety and Wellbeing | 135 | 17
Performance Measure: Customer net promoter score Investment impact on performance: Replacement of insulator assemblies reduces the risk of a dropped conductor resulting in bushfire starts and injury. | Objectives and Analysis | 03. Business Performance Objectives | Our Customers | 60 | 18
Performance Measure: Employee engagement Investment impact on performance: Maintain our vision of ‘powering a bright future.’ | Objectives and Analysis | 03. Business Performance Objectives | Our People | 45 | 19
Performance Measure: Capital expenditure Investment impact on performance: Replacement reduces our total cost when compared to managing end of life insulator failures. Performance Measure: Operational expenditure Investment impact on performance: Replacement reduces our operational cost in replacing insulators in poor condition in a planned way prior to failure. | Objectives and Analysis | 03. Business Performance Objectives | Our Business - Sustained Cost Management | 135 | 20
Performance Measure: Service incentive bonuses earned - transmission Investment impact on performance: Replacement of insulator assemblies will reduce the risk of failure and therefore minimise prolonged outages. | Objectives and Analysis | 03. Business Performance Objectives | Our Business - Network Service | 60 | 21
Failed insulator string results in dropped conductor and subsequent injury or death. | Objectives and Analysis | 04. Business Risks | Death or Injury (Employee) | 15 | 23
Failed insulator string results in dropped conductor and subsequent injury or death. | Objectives and Analysis | 04. Business Risks | Death or Injury (Public) | 15 | 24
| Objectives and Analysis | 04. Business Risks | Sustainable and Predictable Pricing | 15 | 25
Failed insulator assembly results in the loss of supply to customers on radial transmission lines. | Objectives and Analysis | 04. Business Risks | Widespread Power Disruption | 15 | 26
Failed insulator string results in dropped conductor and subsequent bushfire start. | Objectives and Analysis | 04. Business Risks | Bushfire Start | 15 | 27
Failed insulator string results in dropped conductor and subsequent loss or limit of supply to a major industrial. | Objectives and Analysis | 04. Business Risks | Loss of Major Industrial | 15 | 28
| Objectives and Analysis | 04. Business Risks | Customer Focus | 15 | 29
| Objectives and Analysis | 04. Business Risks | Business Continuity Management | 15 | 30
| Objectives and Analysis | 04. Business Risks | Cyber Security | 15 | 31
| Objectives and Analysis | 04. Business Risks | Private Assets | 15 | 32
| Objectives and Analysis | 04. Business Risks | Energy Policy and Regulation | 15 | 33
| Objectives and Analysis | 04. Business Risks | Project Marinus (D&A) | 15 | 34
| Objectives and Analysis | 04. Business Risks | Tasmanian Power System Complexity | 15 | 35
| Objectives and Analysis | 04. Business Risks | Emerging Complexity of the NEM | 15 | 36
The strategic objective is to manage the risk to customers by developing a risk based strategic plan. This includes a condition/risk based approach to manage the assets to maintain reliability and security of the network and effectively manage the safety risk associated with maintaining the asset. | Objectives and Analysis | 05. Strategic Objectives | Strategic Objectives | 45 | 38
TasNetworks Towards 2030 Strategic Objective: Safety: We see ways to continually reduce safety risks over the next decade How the proposed investment will address the strategic goal: This investment is aimed at mitigating the risk of safety related incidents including bushfires caused by our assets and therefore minimising any liability associated with potential legal action. Strategic Objective: We continually assess what value means to our customers to better serve all our stakeholders How the proposed investment will address the strategic goal: The forward demand in this area has been reviewed with Network Planning and the most appropriate customer centric option selected. Strategic Objective: Ensuring our electricity network remains resilient and fit-for-purpose by proactively maintaining assets, designing out risks, and making prudent investments of long-term value. How the proposed investment will address the strategic goal: The long-term impact of asset maintenance and renewal has been reviewed out to 2050. The analysis clearly demonstrates work should be done to mitigate risks to customers now and into the future. Strategic Objective: To ensure our capital is used wisely, we will streamline our investment planning to achieve optimised investment strategies and have the best delivery model. How the proposed investment will address the strategic goal: Investment planning has been developed to align all asset categories. The plan has been developed out to 2050 to ensure the long-term objectives of optimising investment strategies is achieved. | Objectives and Analysis | 05. Strategic Objectives | Strategic Document #1 | 390 | 39
TasNetworks Three Year Business Plan 2021-2024 Strategic Objective: Minimising costs and risk of events that can adversely impact our network. How the proposed investment will address the strategic goal: This investment is aimed at mitigating the risks caused by our assets and therefore delivering safe and reliable power. | Objectives and Analysis | 05. Strategic Objectives | Strategic Document #2 | 90 | 40
Insulator Assemblies Asset Management Plan | Objectives and Analysis | 05. Strategic Objectives | Strategic Document #3 | 15 | 41
| Objectives and Analysis | 05. Strategic Objectives | Strategic Document #4 | 15 | 42
| Objectives and Analysis | 05. Strategic Objectives | Strategic Document #5 | 15 | 43
The transmission line insulator assembly replacement program proposes to mitigate the risk of insulator assembly failure, improve circuit reliability and reduce the lifecycle costs of insulator assemblies. | Objectives and Analysis | 06. Project Objectives | Project Objectives | 30 | 44
TasNetworks participates in various formal benchmarking forums with the aim to benchmark asset management practices against international and national transmission companies. Key benchmarking forums include: - International Transmission Operations & Maintenance Study (ITOMS); and - Australian Energy Regulator (AER) Regulatory Information Notices (RIN). TasNetworks also works closely with transmission companies in other key industry forums such as CIGRE (International Council on Large Electric Systems) to compare asset management and performance. Neither benchmarking forum reports on insulator performance specifically, however TasNetworks has the lowest expenditure per circuit km of transmission lines in the reported voltage ranges in ITOMS and approximately average circuit performance. This suggests that TasNetworks' transmission line strategies are in line with delivering acceptable performance and prudent expenditure. | Objectives and Analysis | 07. Options Analysis | Benchmarking | 195 | 45
Condition assessment reports are used on a continual basis to determine the likely insulator replacements. This condition assessment is an ongoing program and will continue through the 2024-2029 regulatory period. | Objectives and Analysis | 07. Options Analysis | Expert Findings | 30 | 46
The program will continue for the whole regulatory period at a fairly constant rate (there will be minor variance year to year based on the transmission lines included in programmed replacements). With transmission lines of varying ages it is expected that the program will continue indefinitely and with the increasing use of better condition data volumes will be adjusted accordingly. | Objectives and Analysis | 08. Investment Timing | Investment Timing | 60 | 47
The benefits to TasNetworks from implementation of the preferred option will be: - reduce business risk by replacing end of life insulator assemblies; - alignment with strategic asset management plans; - achieve reliable transmission line insulator assembly performance consistent with prescribed service standards; - operation and maintenance cost savings due to planned replacement of porcelain insulators; - compliance with relevant Australian standards; and - meet performance objectives identified in TasNetworks' Corporate Plan. | Objectives and Analysis | 09. Expected Outcomes and Benefits | Expected Outcomes and Benefits | 120 | 48
In developing the program the unit volumes have been derived from the transmission lines likely to require insulator replacement in a 20 year period. Annual volumes have been compared with recent historical replacement volumes to provide a sustainable program over a longer timeframe. Unit values are based on historical unit costs with these unit costs applied to the program volumes to determine annual costs. | Objectives and Analysis | 10. Assumptions | Assumptions | 90 | 49
The asset replacements within this program do not require a Regulatory Investment Test for Transmission (RIT-T) as per the requirements of the NER. | Objectives and Analysis | 11. Regulatory Considerations | Regulatory Investment Test | 30 | 50
No | Objectives and Analysis | 11. Regulatory Considerations | Meet or manage the expected demand for Standard Control Services (Distribution)/Prescribed Services (Transmission). | 15 | 51
No | Objectives and Analysis | 11. Regulatory Considerations | Comply with all applicable regulatory obligations associated with the provision of Standard Control Services (Distribution)/Prescribed Services (Transmission). | 15 | 52
Yes | Objectives and Analysis | 11. Regulatory Considerations | Maintain the quality, reliability and security of supply of Standard Control Services (Distribution)/Prescribed Services (Transmission). | 15 | 53
Yes | Objectives and Analysis | 11. Regulatory Considerations | Maintain the reliability and security of the system through the supply of Standard Control Services (Distribution)/Prescribed Services (Transmission). | 15 | 54
Yes | Objectives and Analysis | 11. Regulatory Considerations | Maintain the safety of the system through the supply of Standard Control Services (Distribution)/Prescribed Services (Transmission). | 15 | 55
Targeted replacement program is recommended for approval as it best satisfies the customer and business needs. | Objectives and Analysis | 12. Recommendation | Recommendation | 15 | 56
This option considers the viability of replacing all insulators that have exceeded their economic life of either 45 or 60 years for composite/synthetic or porcelain and glass insulators respectively. | Option 1 | Description |  | 15
Whilst this option mitigates the risk of insulator failure it has been rejected as it does not comply with TasNetworks’ preferred asset replacement strategy to only replace assets identified as being in poor condition and creates an unsustainable increase in volume in the 2024 to 2029 period. The application of this strategy to TasNetworks’ insulator population would result in the replacement of 12,500 insulator strings at a cost of approximately $23.4m, compared to the required 4,000 insulators and $7.5m for targeted replacement. While this option would reduce TasNetworks’ risk exposure due to condition based insulator failure, the cost of achieving this outcome is not commensurate with the risk benefit obtained. TasNetworks' preferred asset risk management strategy is to target investment at those poorly performing assets that will result in the maintenance of risk at current levels, as opposed to significantly reducing or increasing its risk exposure. | Option 1 | Reason for selection/rejection |  | 75
Pausing the existing targeted replacement program and restarting in the next regulatory period (2029). | Option 2 | Description |  | 15
This option t has been rejected as it does not manage risk to an acceptable level for the 2024-29 regulatory period and is has a lower NPV value compared to the selected option. | Option 2 | Reason for selection/rejection |  | 15
Continue TasNetworks' established insulator assembly replacement program, replacing insulator assemblies identified as being at end of life with new insulators. | Option 3 | Description |  | 15
This option has been selected as it mitigates the risk of insulator failure, maintains circuit reliability, reduces the lifecycle costs of insulator assemblies, and is the most favourable option economically. This option results in TasNetworks managing its fleet of insulators in a strategic manner, undertaking staged insulator replacements as they approach end of life, rather than deferring replacements until such time that defect and failure rates present an unacceptable risk to TasNetworks and its customers. It should also be noted that contractor resourcing limitations within Tasmania are such that insulator replacement programs larger than that proposed in this IES (resulting from deferral of this program) are not practical and will result in an increase in TasNetworks' risk profile. | Option 3 | Reason for selection/rejection |  | 60
| Option 4 | Description
| Option 4 | Reason for selection/rejection
| Option 5 | Description
| Option 5 | Reason for selection/rejection
| Option 6 | Description
| Option 6 | Reason for selection/rejection