## Year_Summary
Powercor REFCLs North Western Geelong
Summary by Year
(real 2021 dollars)
Option3
OPEX
| Incremental operating costs before wage escalation |  |  | 2021/22 | 2022/23 | 2023/24 | 2024/25 | 2025/26
| Incremental technical support | $m real 2021 |  | 0 | 0 | 0.015668 | 0.015668 | 0.015668
| Incremental re-balancing works | $m real 2021 |  | 0 | 0 | 0.094553 | 0.094553 | 0.094553
| Incremental compliance testing | $m real 2021 |  | 0 | 0 | 0.0098944 | 0.0098944 | 0.0098944
| Total | $m real 2021 |  | 0 | 0 | 0.12011 | 0.12011 | 0.12011
CAPEX
| Capex by category |  | Allocation | 2021/22 | 2022/23 | 2023/24 | 2024/25 | 2025/26
| Capex categorised directly | $m real 2021 | Direct | 2.0924 | 46.5937 | 0 | 0 | 0
| Other capex | $m real 2021 | Pro-rata | 0 | 4.1128 | 0 | 0 | 0
| Total capex | $m real 2021 |  | 2.0924 | 50.7065 | 0 | 0 | 0
|  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
| Percentage capex by category (directly categorised) |  |  | 2021/22 | 2022/23 | 2023/24 | 2024/25 | 2025/26
| Distribution | % |  | 100% | 76.02% | 0% | 0% | 0%
| SCADA/Network control | % |  | 0% | 23.98% | 0% | 0% | 0%
| Total % | % |  | 100% | 100% | 0% | 0% | 0%
| Incremental contingent project capex by category |  |  | 2021/22 | 2022/23 | 2023/24 | 2024/25 | 2025/26
| Distribution | $m real 2021 |  | 2.0924 | 38.5463 | 0 | 0 | 0
| SCADA/Network control | $m real 2021 |  | 0 | 12.1602 | 0 | 0 | 0
| Total project capex | $m real 2021 |  | 2.0924 | 50.7065 | 0 | 0 | 0
| Total capex ($m 2021) |  |  | 2021/22 | 2022/23 | 2023/24 | 2024/25 | 2025/26
| Distribution | $m real 2021 |  | 2.0924 | 38.5463 | 0 | 0 | 0
| SCADA/Network control | $m real 2021 |  | 0 | 12.1602 | 0 | 0 | 0
| Total capex | $m real 2021 |  | 2.0924 | 50.7065 | 0 | 0 | 0
| Augmentation already accounted for ($m 2021) |  |  | 2021/22 | 2022/23 | 2023/24 | 2024/25 | 2025/26
| GL013 new feeder to Batesford |  |  | 1.8893 | 0.87348 | 0 | 0 | 0
| GL12 3rd Phase Barrabool Road - Stage 2 to pole 136 (5km) |  |  | 0.14663 | 0.14663 | 0 | 0 | 0
| GL15 P124A Moorabool Valley regulator to 3 x 200A |  |  | 0 | 0 | 0.10626 | 0.10626 | 0
| GL Tx 1 22 kV CB augmentation |  |  | 0 | 0 | 0.20189 | 0.20189 | 0
| GL Tx 2 22 kV CB augmentation |  |  | 0 | 0 | 0 | 0.20189 | 0.20189
| Total capex | $m real 2021 |  | 2.0359 | 1.0201 | 0.30814 | 0.51003 | 0.20189
| Total capex requirement ($m 2021) |  |  | 2021/22 | 2022/23 | 2023/24 | 2024/25 | 2025/26
| Total capex |  |  | 2.0924 | 50.7065 | 0 | 0 | 0
| Less augmentation already accounted for |  |  | 2.0359 | 1.0201 | 0.30814 | 0.51003 | 0.20189
| Total capex | $m real 2021 |  | 0.05646 | 49.6864 | -0.30814 | -0.51003 | -0.20189

## Cost_Summary
Powercor REFCLs North Western Geelong
Cost summary by site
(real 2021 dollars)
Costs ($000s 2021)
|  |  |  | Option 1 | Option 2 | Option 3
|  |  |  | CRO + GL | BBN 2GFN | GHP 2GFN
1 GFN CRO
| Design & Procurement |  |  | 2 GFN GL
|  |  | Design & Procurement | 2373.9314 | 2092.3762 | 2092.3762
Feeder works
|  |  | Surge arrestor sites (single phase) | 1229.2679 | 691.7386 | 691.7386
|  |  | Surge arrestor sites (three phase) | 3315.4472 | 1886.6909 | 1886.6909
|  |  | ACRs | 281.9272 | 120.6366 | 120.6366
|  |  | ACR/gas switch control box replacement | 136.0897 | 85.0561 | 85.0561
|  |  | Admittance balancing units (single phase) | 456.7422 | 228.9647 | 228.9647
|  |  | Admittance balancing units (three phase) | 1674.3522 | 768.8597 | 768.8597
|  |  | Re-phasing | 49.2 | 38.0333 | 38.0333
|  |  | Fusesavers | 772.4161 | 469.3351 | 469.3351
|  |  | HV Regulators upgrade (control box) | 15.5389 | 0 | 0
|  |  | HV Regulators upgrade (close delta) | 735.2433 | 735.6044 | 735.6044
|  |  | Distribution switchgear (installed) | 2366.1725 | 1183.0863 | 1183.0863
|  |  | UG cable replacement | 1773.3129 | 2538.1694 | 2538.1694
|  |  | Test Sites | 30.1478 | 15.0739 | 15.0739
|  |  | HV Customers (total) | 796.5453 | 0 | 0
|  |  | HV Customers (generation signalling) | 0 | 0 | 0
|  |  | 22kV feeder works | 6371.4431 | 8851.9926 | 8851.9926
|  |  | 66kV Line works (Overhead) | 135.2999 | 11934 | 8874
|  |  | 3rd phase line extension | 1068.6062 | 0 | 0
|  |  | Asset resilience testing | 755.4552 | 601.8985 | 601.8985
|  |  | Distribution Comms | 82.4713 | 4896 | 3366
|  |  | Other distribution materials | 1907.8276 | 612 | 612
Substation
Primary Plant
|  |  | GFN | 6927.5486 | 4002.8178 | 4002.8178
|  |  | GFN enclosure | 483.9897 | 0 | 0
|  |  | Indoor switch room (incl GFN enclosure and switchboard) | 1834.6712 | 1834.6712 | 1834.6712
|  |  | RMU | 148.7479 | 0 | 0
|  |  | 66/22kV transformer | 2245.6591 | 4491.3183 | 4491.3183
|  |  | 66kV circuit breaker | 131.58 | 964.6952 | 964.6952
|  |  | 66kV bus extension | 208.08 | 0 | 0
|  |  | Station service transformer (500kVA) | 146.345 | 146.345 | 146.345
|  |  | Station service transformer (750kVA) | 0 | 0 | 0
|  |  | Cap bank | 688.3677 | 405.3838 | 405.3838
|  |  | AC board (Including change over) | 53.777 | 0 | 0
|  |  | Control room | 935.5078 | 935.5078 | 935.5078
|  |  | 22kV circuit breaker (outdoor) | 381.9185 | 0 | 0
|  |  | Voltage transformer | 36.7833 | 0 | 0
|  |  | Current transformer (post type) | 152.9398 | 0 | 0
|  |  | Current transformer (core balance type) | 0 | 0 | 0
|  |  | Other primary materials | 738.0413 | 407.905 | 407.905
|  |  | SCADA / Protection & Control/ Comms | 2903.6155 | 2337.9008 | 2337.9008
|  |  | Commissioning | 740.4884 | 219.101 | 219.101
|  |  | ESV observed compliance | 98.9436 | 49.4718 | 49.4718
|  |  | Construction delivery & site control | 1353.9547 | 152.9141 | 152.9141
Contracts
|  |  | Traffic control | 1164.4997 | 660.212 | 660.212
|  |  | Line survey | 296.9199 | 40.6262 | 40.6262
|  |  | Civil works | 4098.1541 | 1989.166 | 1989.166
|  |  | Mob/Demob | 72.9696 | 40.8 | 40.8
|  |  | Other | 1212.07 | 960.5 | 960.5
| Total capital cost |  |  | 53383.01 | 57388.8522 | 52798.8522
|  |  | Augex already accounted for |  | -4074.8902 | -4074.8902
| Total required capex |  |  | 53383.01 | 53313.962 | 48723.962

## Project_inputs
Powercor REFCLs North Western Geelong
Project inputs
(real 2021 dollars)
MAJOR ITEM UNIT COSTS
(real 2021 dollars)
Feeder works
|  |  | Surge arrestor sites (single phase) | 397.3281 | $/ea
|  |  | Surge arrestor sites (three phase) | 590.7364 | $/ea
|  |  | ACRs | 27103.4493 | $/ea
|  |  | ACR/gas switch control box replacement | 9411.251 | $/ea
|  |  | Admittance balancing units (single phase) | 19288.4609 | $/ea
|  |  | Admittance balancing units (three phase) | 24307.4371 | $/ea
|  |  | Re-phasing | 228.0957 | $/ea
|  |  | Fusesavers | 12540.0097 | $/ea
|  |  | HV Regulators upgrade (control box) | 15538.8905 | $/ea
|  |  | HV Regulators upgrade (close delta) | 162190.7825 | $/ea
|  |  | Distribution switchgear (installed) | 107553.2957 | $/ea
|  |  | UG cable replacement | 473.0096 | $/m
|  |  | Test Sites | 1118.8359 | $/ea
|  |  | HV Customers (total) | 27103.4493 | $/ea
|  |  | HV Customers (generation signalling) | 68410.8509 | $/ea
|  |  | 22kV feeder works | 306000 | $/ea
|  |  | 66kV Line works (Overhead) | 306000 | $/km
3rd phase line extension
Asset resilience testing
|  |  | Distribution Comms |  | $/km
Other distribution materials
Substation
Primary Plant
|  |  | GFN | 1290638.4354 | $/ea
|  |  | GFN enclosure | 161329.9051 | $/ea
|  |  | Indoor switch room (incl GFN enclosure and switchboard) | 1281303.0825 | $/ea
|  |  | RMU | 74373.925 | $/ea
|  |  | 66/22kV transformer | 754800 | $/ea
|  |  | 66kV circuit breaker | 94860 | $/ea
|  |  | 66kV bus extension | 208080 | $/ea
|  |  | Station service transformer (500kVA) | 73172.4807 | $/ea
|  |  | Station service transformer (750kVA) | 87926.1752 | $/ea
|  |  | Cap bank | 344183.8486 | $/ea
|  |  | AC board (Including change over) | 53776.9854 | $/ea
|  |  | Control room | 935507.8479 | $/ea
|  |  | 22kV circuit breaker (outdoor) | 76383.6902 | $/ea
|  |  | Voltage transformer | 18391.6638 | $/ea
|  |  | Current transformer (post type) | 15293.9766 | $/ea
|  |  | Current transformer (core balance type) | 5203.1054 | $/ea
OPEX
(real 2021 dollars)
|  | Incremental technical support |  | 15667.8954 | $ pa/ZSS | Included in 2021 - 2026 price reset step change model
|  | Incremental re-balancing works |  | 30029.9677 | $ pa/ZSS | Included in 2021 - 2026 price reset step change model
|  | Incremental re-balancing works - per feeder cost |  | 3226.1313 | $ pa/feeder | Included in 2021 - 2026 price reset step change model
|  | Incremental compliance testing |  | 9894.36 | $ pa/feeder | Included in 2021 - 2026 price reset step change model
| Feeders |  |  | Feeders by ZSS
|  | Option1 |  | 10
|  | Option2 |  | 5
|  | Option3 |  | 5
TIMING
|  | First year of project |  | 2021/22
| Project timing |  |  |  | Design & Procurement | Construction | Commissioning | Operation
|  | Option1 |  |  | 2021/22 | 2022/23 | 2022/23 | 2022/23
|  | Option2 |  |  | 2021/22 | 2022/23 | 2022/23 | 2022/23
|  | Option3 |  |  | 2021/22 | 2022/23 | 2022/23 | 2022/23

## Asset_groups
Powercor REFCLs North Western Geelong
Asset groups
(real 2021 dollars)
|  |  |  | Type | Allocation Basis | Depreciation category
Design & Procurement Labour
|  |  | Design & Procurement | Capex | Direct | Distribution
Feeder works
|  |  | Surge arrestor sites (single phase) | Capex | Direct | Distribution
|  |  | Surge arrestor sites (three phase) | Capex | Direct | Distribution
|  |  | ACRs | Capex | Direct | Distribution
|  |  | ACR/gas switch control box replacement | Capex | Direct | Distribution
|  |  | Admittance balancing units (single phase) | Capex | Direct | SCADA/Network control
|  |  | Admittance balancing units (three phase) | Capex | Direct | SCADA/Network control
|  |  | Re-phasing | Capex | Direct | Distribution
|  |  | Fusesavers | Capex | Direct | SCADA/Network control
|  |  | HV Regulators upgrade (control box) | Capex | Direct | Distribution
|  |  | HV Regulators upgrade (close delta) | Capex | Direct | Distribution
|  |  | Distribution switchgear (installed) | Capex | Direct | Distribution
|  |  | UG cable replacement | Capex | Direct | Distribution
|  |  | Test Sites | Capex | Direct | Distribution
|  |  | HV Customers (total) | Capex | Direct | Distribution
|  |  | HV Customers (generation signalling) | Capex | Direct | SCADA/Network control
|  |  | 22kV feeder works | Capex | Direct | Distribution
|  |  | 66kV Line works (Overhead) | Capex | Direct | Distribution
|  |  | 3rd phase line extension | Capex | Direct | Distribution
|  |  | Asset resilience testing | Capex | Direct | Distribution
|  |  | Distribution Comms | Capex | Direct | SCADA/Network control
|  |  | Other distribution materials | Capex | Direct | Distribution
Substation
Primary Plant
|  |  | GFN | Capex | Direct | SCADA/Network control
|  |  | GFN enclosure | Capex | Direct | Distribution
|  |  | Indoor switch room (incl GFN enclosure and switchboard) | Capex | Direct | Distribution
|  |  | RMU | Capex | Direct | Distribution
|  |  | 66/22kV transformer | Capex | Direct | Distribution
|  |  | 66kV circuit breaker | Capex | Direct | Distribution
|  |  | 66kV bus extension | Capex | Direct | Distribution
|  |  | Station service transformer (500kVA) | Capex | Direct | Distribution
|  |  | Station service transformer (750kVA) | Capex | Direct | Distribution
|  |  | Cap bank | Capex | Direct | Distribution
|  |  | AC board (Including change over) | Capex | Direct | Distribution
|  |  | Control room | Capex | Direct | Distribution
|  |  | 22kV circuit breaker (outdoor) | Capex | Direct | Distribution
|  |  | Voltage transformer | Capex | Direct | Distribution
|  |  | Current transformer (post type) | Capex | Direct | Distribution
|  |  | Current transformer (core balance type) | Capex | Direct | Distribution
|  |  | Other primary materials | Capex | Direct | Distribution
|  |  | SCADA / Protection & Control/ Comms | Capex | Direct | SCADA/Network control
|  |  | Commissioning | Capex | Pro-rata
|  |  | ESV observed compliance | Capex | Pro-rata
|  |  | Construction delivery & site control | Capex | Pro-rata
Contracts
|  |  | Traffic control | Capex | Pro-rata
|  |  | Line survey | Capex | Pro-rata
|  |  | Civil works | Capex | Pro-rata
|  |  | Mob/Demob | Capex | Pro-rata
|  |  | Other | Capex | Pro-rata

## Option1_volumes
Powercor REFCLs North Western Geelong
Volumes: |  |  | Option1
(real 2021 dollars)
Resource partner rates used |  |  |  | Geelong
Design & Procurement |  |  |  | 2021/22
Construction |  |  |  | 2022/23
[5 empty] | Materials |  | Contracts ($) | Labour ($) | Labour (hours)
| Year incurred |  |  |  | 2022/23 | 2022/23 | 2022/23 | 2022/23 | 2021/22 | 2022/23 | 2022/23 | 2022/23 | 2022/23
[5 empty] | Unit cost (ea) | Qty | Contracts | Other Labour ($) | Design & Procure | Live Linework | General Linework | Sub Tester | Fitter
| Labour Rates ($/hr) | [7 empty] | 221.697 | 180.5661 | 169.6129 | 261.2691 | 184.4855
| Design & Procurement (hours) | [7 empty] | 10708
Feeder works
|  |  | Surge arrestor sites (single phase) |  | 397.3281 | 558 |  |  |  | 5580 | 0 | 0 | 0
|  |  | Surge arrestor sites (three phase) |  | 590.7364 | 1629 |  |  |  | 13032 | 0 | 0 | 0
|  |  | ACRs |  | 27103.4493 | 7 |  |  |  | 337 | 0 | 120 | 0
|  |  | ACR/gas switch control box replacement |  | 9411.251 | 8 |  |  |  | 0 | 112 | 160 | 0
|  |  | Admittance balancing units (single phase) |  | 19288.4609 | 22 |  |  |  | 0 | 191 | 0 | 0
|  |  | Admittance balancing units (three phase) |  | 24307.4371 | 63 |  |  |  | 0 | 843 | 0 | 0
|  |  | Re-phasing |  | 228.0957 | 36 |  |  |  | 227 | 0 | 0 | 0
|  |  | Fusesavers |  | 12540.0097 | 55 |  |  |  | 406 | 0 | 36 | 0
|  |  | HV Regulators upgrade (control box) |  | 15538.8905 | 1 |  |  |  | 0 | 0 | 0 | 0
|  |  | HV Regulators upgrade (close delta) |  | 162190.7825 | 4 |  |  |  | 450 | 0 | 20 | 0
|  |  | Distribution switchgear (installed) |  | 107553.2957 | 22 |  |  |  | 0 | 0 | 0 | 0
|  |  | UG cable replacement |  | 473.0096 | 3749 |  |  |  | 0 | 0 | 0 | 0
|  |  | Test Sites |  | 1118.8359 | 10 |  |  |  | 105 | 0 | 0 | 0
|  |  | HV Customers (total) |  | 27103.4493 | 11 | 115613.2413 | 34000 | 320 | 960 | 0 | 400 | 0
|  |  | HV Customers (generation signalling) |  | 68410.8509
|  |  | 22kV feeder works |  | 306000 | 17.4 | 567607 |  |  | 72 | 2750
|  |  | 66kV Line works (Overhead) |  | 306000 |  |  |  |  | 336 | 440 | 0 | 0
|  |  | 3rd phase line extension |  | 269316.6058 | 2.8 |  |  |  | 841 | 804.99 | 100 | 0
|  |  | Asset resilience testing |  | 755455.1723 | 1 |  |  |  | 0 | 0 | 0 | 0
|  |  | Distribution Comms |  | 40468.0213 | 1 |  | 42003.2512
|  |  | Other distribution materials |  | 1623835 | 1 |  |  |  | 650 |  | 320 | 450
Substation
Primary Plant
|  |  | GFN |  | 1290638.4354 | 3 | [6 empty] | 16563
|  |  | GFN enclosure |  | 161329.9051 | 3
|  |  | Indoor switch room (incl GFN enclosure and switchboard) |  | 1281303.0825 | 1 | 112200 |  |  |  |  | 700 | 1400
|  |  | RMU |  | 74373.925 | 2
|  |  | 66/22kV transformer |  | 754800 | 1 | 224400 |  |  |  |  | 4000 | 1200
|  |  | 66kV circuit breaker |  | 94860 | 1 | 36720
|  |  | 66kV bus extension |  | 208080 | 1
|  |  | Station service transformer (500kVA) |  | 73172.4807 | 2
|  |  | Station service transformer (750kVA) |  | 87926.1752
|  |  | Cap bank |  | 344183.8486 | 2
|  |  | AC board (Including change over) |  | 53776.9854 | 1
|  |  | Control room |  | 935507.8479 | 1
|  |  | 22kV circuit breaker (outdoor) |  | 76383.6902 | 5
|  |  | Voltage transformer |  | 18391.6638 | 2
|  |  | Current transformer (post type) |  | 15293.9766 | 10
|  |  | Current transformer (core balance type) |  | 5203.1054
|  |  | Other primary materials |  | 738041.3454 | 1
|  |  | SCADA / Protection & Control/ Comms |  | 1414443.8972 | 1 |  | 31035.7356 |  |  |  | 4764 | 1157
|  |  | Commissioning |  |  |  |  | 740488.3686
|  |  | ESV observed compliance |  |  |  |  | 98943.5995
|  |  | Construction delivery & site control |  |  |  |  | 1353954.6784
Contracts
|  |  | Traffic control |  |  |  | 1164499.672
|  |  | Line survey |  |  |  | 296919.9424
|  |  | Civil works |  |  |  | 4098154.1072
|  |  | Mob/Demob |  |  |  | 72969.6121
|  |  | Other |  |  |  | 1212070

## Option2_volumes
Powercor REFCLs North Western Geelong
Volumes: |  |  | Option2
(real 2021 dollars)
Resource partner rates used |  |  |  | Geelong
Design & Procurement |  |  |  | 2021/22
Construction |  |  |  | 2022/23
[5 empty] | Materials |  | Contracts ($) | Labour ($) | Labour (hours)
| Year incurred |  |  |  | 2022/23 | 2022/23 | 2022/23 | 2022/23 | 2021/22 | 2022/23 | 2022/23 | 2022/23 | 2022/23
[5 empty] | Unit cost (ea) | Qty | Contracts | Other Labour ($) | Design & Procure | Live Linework | General Linework | Sub Tester | Fitter
| Labour Rates ($/hr) | [7 empty] | 221.697 | 180.5661 | 169.6129 | 261.2691 | 184.4855
| Design & Procurement (hours) | [7 empty] | 9438
Feeder works
|  |  | Surge arrestor sites (single phase) |  | 397.3281 | 314 |  |  |  | 3140
|  |  | Surge arrestor sites (three phase) |  | 590.7364 | 927 |  |  |  | 7416
|  |  | ACRs |  | 27103.4493 | 3 |  |  |  | 144 |  | 51
|  |  | ACR/gas switch control box replacement |  | 9411.251 | 5 |  |  |  |  | 70 | 100
|  |  | Admittance balancing units (single phase) |  | 19288.4609 | 11 |  |  |  |  | 99
|  |  | Admittance balancing units (three phase) |  | 24307.4371 | 29 |  |  |  |  | 377
|  |  | Re-phasing |  | 228.0957 | 29 |  |  |  | 174
|  |  | Fusesavers |  | 12540.0097 | 34 |  |  |  | 238
|  |  | HV Regulators upgrade (control box) |  | 15538.8905
|  |  | HV Regulators upgrade (close delta) |  | 162190.7825 | 4 |  |  |  | 452 |  | 20
|  |  | Distribution switchgear (installed) |  | 107553.2957 | 11
|  |  | UG cable replacement |  | 473.0096 | 5366
|  |  | Test Sites |  | 1118.8359 | 5 |  |  |  | 52.5
|  |  | HV Customers (total) |  | 27103.4493
|  |  | HV Customers (generation signalling) |  | 68410.8509
|  |  | 22kV feeder works |  | 306000 | 28 |  |  |  | 650 |  | 320 | 450
|  |  | 66kV Line works (Overhead) |  | 306000 | 39
|  |  | 3rd phase line extension |  | 0
|  |  | Asset resilience testing |  | 12806.3509 | 47
|  |  | Distribution Comms |  | 153000 | 32
|  |  | Other distribution materials |  | 612000 | 1
Substation
Primary Plant
|  |  | GFN |  | 1290638.4354 | 2 | 91800 | 306000 |  |  |  | 1800 | 3000
|  |  | GFN enclosure |  | 161329.9051
|  |  | Indoor switch room (incl GFN enclosure and switchboard) |  | 1281303.0825 | 1 | 112200 |  |  |  |  | 700 | 1400
|  |  | RMU |  | 74373.925
|  |  | 66/22kV transformer |  | 754800 | 2 | 448800 |  |  |  |  | 8000 | 2400
|  |  | 66kV circuit breaker |  | 94860 | 4 | 146880 |  |  |  |  | 1000 | 960
|  |  | 66kV bus extension |  | 208080
|  |  | Station service transformer (500kVA) |  | 73172.4807 | 2
|  |  | Station service transformer (750kVA) |  | 87926.1752
|  |  | Cap bank |  | 344183.8486 | 1 | 61200
|  |  | AC board (Including change over) |  | 53776.9854
|  |  | Control room |  | 935507.8479 | 1
|  |  | 22kV circuit breaker (outdoor) |  | 76383.6902
|  |  | Voltage transformer |  | 18391.6638
|  |  | Current transformer (post type) |  | 15293.9766
|  |  | Current transformer (core balance type) |  | 5203.1054
|  |  | Other primary materials |  | 407905 | 1
|  |  | SCADA / Protection & Control/ Comms |  | 2337900.7575 | 1
|  |  | Commissioning |  |  |  |  | 219101
|  |  | ESV observed compliance |  |  |  |  | 49471.7998
|  |  | Construction delivery & site control |  |  |  |  | 152914.1449
Contracts
|  |  | Traffic control |  |  |  | 660212
|  |  | Line survey |  |  |  | 40626.1578
|  |  | Civil works |  |  |  | 1989166
|  |  | Mob/Demob |  |  |  | 40800
|  |  | Other |  |  |  | 960500
|  |  | Land Acquisition |  |  |  | 700000
|  |  | Environmental Assessments, crane hire, additional day hire |  |  |  | 260500

## Option3_volumes
Powercor REFCLs North Western Geelong
Volumes: |  |  | Option3
(real 2021 dollars)
Resource partner rates used |  |  |  | Geelong
Design & Procurement |  |  |  | 2021/22
Construction |  |  |  | 2022/23
[5 empty] | Materials |  | Contracts ($) | Labour ($) | Labour (hours)
| Year incurred |  |  |  | 2022/23 | 2022/23 | 2022/23 | 2022/23 | 2021/22 | 2022/23 | 2022/23 | 2022/23 | 2022/23
[5 empty] | Unit cost (ea) | Qty | Contracts | Other Labour ($) | Design & Procure | Live Linework | General Linework | Sub Tester | Fitter
| Labour Rates ($/hr) | [7 empty] | 221.697 | 180.5661 | 169.6129 | 261.2691 | 184.4855
| Design & Procurement (hours) | [7 empty] | 9438
Feeder works
|  |  | Surge arrestor sites (single phase) |  | 397.3281 | 314 |  |  |  | 3140
|  |  | Surge arrestor sites (three phase) |  | 590.7364 | 927 |  |  |  | 7416
|  |  | ACRs |  | 27103.4493 | 3 |  |  |  | 144 |  | 51
|  |  | ACR/gas switch control box replacement |  | 9411.251 | 5 |  |  |  |  | 70 | 100
|  |  | Admittance balancing units (single phase) |  | 19288.4609 | 11 |  |  |  |  | 99
|  |  | Admittance balancing units (three phase) |  | 24307.4371 | 29 |  |  |  |  | 377
|  |  | Re-phasing |  | 228.0957 | 29 |  |  |  | 174
|  |  | Fusesavers |  | 12540.0097 | 34 |  |  |  | 238
|  |  | HV Regulators upgrade (control box) |  | 15538.8905
|  |  | HV Regulators upgrade (close delta) |  | 162190.7825 | 4 |  |  |  | 452 |  | 20
|  |  | Distribution switchgear (installed) |  | 107553.2957 | 11
|  |  | UG cable replacement |  | 473.0096 | 5366
|  |  | Test Sites |  | 1118.8359 | 5 |  |  |  | 52.5
|  |  | HV Customers (total) |  | 27103.4493
|  |  | HV Customers (generation signalling) |  | 68410.8509
|  |  | 22kV feeder works |  | 306000 | 28 |  |  |  | 650 |  | 320 | 450
|  |  | 66kV Line works (Overhead) |  | 306000 | 29
|  |  | 3rd phase line extension |  | 0
|  |  | Asset resilience testing |  | 12806.3509 | 47
|  |  | Distribution Comms |  | 153000 | 22
|  |  | Other distribution materials |  | 612000 | 1
Substation
Primary Plant
|  |  | GFN |  | 1290638.4354 | 2 | 91800 | 306000 |  |  |  | 1800 | 3000
|  |  | GFN enclosure |  | 161329.9051
|  |  | Indoor switch room (incl GFN enclosure and switchboard) |  | 1281303.0825 | 1 | 112200 |  |  |  |  | 700 | 1400
|  |  | RMU |  | 74373.925
|  |  | 66/22kV transformer |  | 754800 | 2 | 448800 |  |  |  |  | 8000 | 2400
|  |  | 66kV circuit breaker |  | 94860 | 4 | 146880 |  |  |  |  | 1000 | 960
|  |  | 66kV bus extension |  | 208080
|  |  | Station service transformer (500kVA) |  | 73172.4807 | 2
|  |  | Station service transformer (750kVA) |  | 87926.1752
|  |  | Cap bank |  | 344183.8486 | 1 | 61200
|  |  | AC board (Including change over) |  | 53776.9854
|  |  | Control room |  | 935507.8479 | 1
|  |  | 22kV circuit breaker (outdoor) |  | 76383.6902
|  |  | Voltage transformer |  | 18391.6638
|  |  | Current transformer (post type) |  | 15293.9766
|  |  | Current transformer (core balance type) |  | 5203.1054
|  |  | Other primary materials |  | 407905 | 1
|  |  | SCADA / Protection & Control/ Comms |  | 2337900.7575 | 1
|  |  | Commissioning |  |  |  |  | 219101
|  |  | ESV observed compliance |  |  |  |  | 49471.7998
|  |  | Construction delivery & site control |  |  |  |  | 152914.1449
Contracts
|  |  | Traffic control |  |  |  | 660212
|  |  | Line survey |  |  |  | 40626.1578
|  |  | Civil works |  |  |  | 1989166
|  |  | Mob/Demob |  |  |  | 40800
|  |  | Other |  |  |  | 960500
|  |  | Land Acquisition |  |  |  | 700000
|  |  | Environmental Assessments, crane hire, additional day hire |  |  |  | 260500

## Option1_cost
Powercor REFCLs North Western Geelong
Costs: |  |  | Option1
(real 2021 dollars)
Design & Procurement |  |  | 2021/22
Construction |  |  | 2022/23
Commissioning |  |  | 2022/23
|  |  |  | 2021/22 | 2021/22 | 2021/22 | 2022/23 | 2022/23 | 2022/23 | 2023/24 | 2023/24 | 2023/24 | 2024/25 | 2024/25 | 2024/25 | 2025/26 | 2025/26 | 2025/26 | 2021/22 | 2022/23 | 2023/24 | 2024/25 | 2025/26 | Total
|  |  |  | Materials | Labour | Contracts | Materials | Labour | Contracts | Materials | Labour | Contracts | Materials | Labour | Contracts | Materials | Labour | Contracts | Total | Total | Total | Total | Total | Total Cost
Design & Procurement
|  |  | Design & Procurement | 0 | 2373931.3618 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2373931.3618 | 0 | 0 | 0 | 0 | 2373931.3618 | Direct
Feeder works
|  |  | Surge arrestor sites (single phase) | 0 | 0 | 0 | 221709.0532 | 1007558.8865 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1229267.9397 | 0 | 0 | 0 | 1229267.9397
|  |  | Surge arrestor sites (three phase) | 0 | 0 | 0 | 962309.6222 | 2353137.5285 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3315447.1507 | 0 | 0 | 0 | 3315447.1507
|  |  | ACRs | 0 | 0 | 0 | 189724.145 | 92203.0749 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 281927.2199 | 0 | 0 | 0 | 281927.2199
|  |  | ACR/gas switch control box replacement | 0 | 0 | 0 | 75290.008 | 60799.7016 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 136089.7096 | 0 | 0 | 0 | 136089.7096
|  |  | Admittance balancing units (single phase) | 0 | 0 | 0 | 424346.1397 | 32396.0556 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 456742.1953 | 0 | 0 | 0 | 456742.1953
|  |  | Admittance balancing units (three phase) | 0 | 0 | 0 | 1531368.5347 | 142983.6379 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1674352.1726 | 0 | 0 | 0 | 1674352.1726
|  |  | Re-phasing | 0 | 0 | 0 | 8211.4464 | 40988.5067 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 49199.9531 | 0 | 0 | 0 | 49199.9531
|  |  | Fusesavers | 0 | 0 | 0 | 689700.533 | 82715.529 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 772416.062 | 0 | 0 | 0 | 772416.062
|  |  | HV Regulators upgrade (control box) | 0 | 0 | 0 | 15538.8905 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15538.8905 | 0 | 0 | 0 | 15538.8905
|  |  | HV Regulators upgrade (close delta) | 0 | 0 | 0 | 648763.1301 | 86480.1316 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 735243.2617 | 0 | 0 | 0 | 735243.2617
|  |  | Distribution switchgear (installed) | 0 | 0 | 0 | 2366172.5058 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2366172.5058 | 0 | 0 | 0 | 2366172.5058
|  |  | UG cable replacement | 0 | 0 | 0 | 1773312.938 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1773312.938 | 0 | 0 | 0 | 1773312.938
|  |  | Test Sites | 0 | 0 | 0 | 11188.3585 | 18959.4414 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30147.7999 | 0 | 0 | 0 | 30147.7999
|  |  | HV Customers (total) | 0 | 0 | 0 | 298137.9421 | 382794.1552 | 115613.2413 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 796545.3386 | 0 | 0 | 0 | 796545.3386
|  |  | HV Customers (generation signalling) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 22kV feeder works | 0 | 0 | 0 | 5324400 | 479436.1148 | 567607 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6371443.1148 | 0 | 0 | 0 | 6371443.1148
|  |  | 66kV Line works (Overhead) | 0 | 0 | 0 | 0 | 135299.8693 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 135299.8693 | 0 | 0 | 0 | 135299.8693
|  |  | 3rd phase line extension | 0 | 0 | 0 | 754086.4962 | 314519.6642 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1068606.1604 | 0 | 0 | 0 | 1068606.1604
|  |  | Asset resilience testing | 0 | 0 | 0 | 755455.1723 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 755455.1723 | 0 | 0 | 0 | 755455.1723
|  |  | Distribution Comms | 0 | 0 | 0 | 40468.0213 | 42003.2512 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 82471.2725 | 0 | 0 | 0 | 82471.2725
|  |  | Other distribution materials | 0 | 0 | 0 | 1623835 | 283992.5669 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1907827.5669 | 0 | 0 | 0 | 1907827.5669
Substation
Primary Plant
|  |  | GFN | 0 | 0 | 0 | 3871915.3061 | 3055633.2593 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6927548.5655 | 0 | 0 | 0 | 6927548.5655
|  |  | GFN enclosure | 0 | 0 | 0 | 483989.7152 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 483989.7152 | 0 | 0 | 0 | 483989.7152
|  |  | Indoor switch room (incl GFN enclosure and switchboard) | 0 | 0 | 0 | 1281303.0825 | 441168.0884 | 112200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1834671.1708 | 0 | 0 | 0 | 1834671.1708
|  |  | RMU | 0 | 0 | 0 | 148747.8501 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 148747.8501 | 0 | 0 | 0 | 148747.8501
|  |  | 66/22kV transformer | 0 | 0 | 0 | 754800 | 1266459.1367 | 224400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2245659.1367 | 0 | 0 | 0 | 2245659.1367
|  |  | 66kV circuit breaker | 0 | 0 | 0 | 94860 | 0 | 36720 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 131580 | 0 | 0 | 0 | 131580
|  |  | 66kV bus extension | 0 | 0 | 0 | 208080 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 208080 | 0 | 0 | 0 | 208080
|  |  | Station service transformer (500kVA) | 0 | 0 | 0 | 146344.9614 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 146344.9614 | 0 | 0 | 0 | 146344.9614
|  |  | Station service transformer (750kVA) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Cap bank | 0 | 0 | 0 | 688367.6971 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 688367.6971 | 0 | 0 | 0 | 688367.6971
|  |  | AC board (Including change over) | 0 | 0 | 0 | 53776.9854 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53776.9854 | 0 | 0 | 0 | 53776.9854
|  |  | Control room | 0 | 0 | 0 | 935507.8479 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 935507.8479 | 0 | 0 | 0 | 935507.8479
|  |  | 22kV circuit breaker (outdoor) | 0 | 0 | 0 | 381918.4511 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 381918.4511 | 0 | 0 | 0 | 381918.4511
|  |  | Voltage transformer | 0 | 0 | 0 | 36783.3277 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36783.3277 | 0 | 0 | 0 | 36783.3277
|  |  | Current transformer (post type) | 0 | 0 | 0 | 152939.7661 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 152939.7661 | 0 | 0 | 0 | 152939.7661
|  |  | Current transformer (core balance type) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
|  |  | Other primary materials | 0 | 0 | 0 | 738041.3454 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 738041.3454 | 0 | 0 | 0 | 738041.3454
|  |  | SCADA / Protection & Control/ Comms | 0 | 0 | 0 | 1414443.8972 | 1489171.6157 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2903615.5128 | 0 | 0 | 0 | 2903615.5128
|  |  | Commissioning | 0 | 0 | 0 | 0 | 740488.3686 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 740488.3686 | 0 | 0 | 0 | 740488.3686
|  |  | ESV observed compliance | 0 | 0 | 0 | 0 | 98943.5995 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 98943.5995 | 0 | 0 | 0 | 98943.5995
|  |  | Construction delivery & site control | 0 | 0 | 0 | 0 | 1353954.6784 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1353954.6784 | 0 | 0 | 0 | 1353954.6784
Contracts
|  |  | Traffic control | 0 | 0 | 0 | 0 | 0 | 1164499.672 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1164499.672 | 0 | 0 | 0 | 1164499.672
|  |  | Line survey | 0 | 0 | 0 | 0 | 0 | 296919.9424 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 296919.9424 | 0 | 0 | 0 | 296919.9424
|  |  | Civil works | 0 | 0 | 0 | 0 | 0 | 4098154.1072 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4098154.1072 | 0 | 0 | 0 | 4098154.1072
|  |  | Mob/Demob | 0 | 0 | 0 | 0 | 0 | 72969.6121 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 72969.6121 | 0 | 0 | 0 | 72969.6121
|  |  | Other | 0 | 0 | 0 | 0 | 0 | 1212070 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1212070 | 0 | 0 | 0 | 1212070
|  | Total construction |  | 0 | 2373931.3618 | 0 | 29105838.1699 | 14002086.8621 | 7901153.5751 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2373931.3618 | 51009078.6071 | 0 | 0 | 0 | 53383009.9689

## Option2_cost
Powercor REFCLs North Western Geelong
Costs: |  |  | Option2
(real 2021 dollars)
Design & Procurement |  |  | 2021/22
Construction |  |  | 2022/23
Commissioning |  |  | 2022/23
|  |  |  | 2021/22 | 2021/22 | 2021/22 | 2022/23 | 2022/23 | 2022/23 | 2023/24 | 2023/24 | 2023/24 | 2024/25 | 2024/25 | 2024/25 | 2025/26 | 2025/26 | 2025/26 | 2021/22 | 2022/23 | 2023/24 | 2024/25 | 2025/26 | Total
|  |  |  | Materials | Labour | Contracts | Materials | Labour | Contracts | Materials | Labour | Contracts | Materials | Labour | Contracts | Materials | Labour | Contracts | Total | Total | Total | Total | Total | Total Cost
Design & Procurement
|  |  | Design & Procurement | 0 | 2092376.1853 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2092376.1853 | 0 | 0 | 0 | 0 | 2092376.1853
Feeder works
|  |  | Surge arrestor sites (single phase) | 0 | 0 | 0 | 124761.0084 | 566977.5813 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 691738.5897 | 0 | 0 | 0 | 691738.5897
|  |  | Surge arrestor sites (three phase) | 0 | 0 | 0 | 547612.6579 | 1339078.2621 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1886690.92 | 0 | 0 | 0 | 1886690.92
|  |  | ACRs | 0 | 0 | 0 | 81310.3478 | 39326.2456 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120636.5934 | 0 | 0 | 0 | 120636.5934
|  |  | ACR/gas switch control box replacement | 0 | 0 | 0 | 47056.255 | 37999.8135 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 85056.0685 | 0 | 0 | 0 | 85056.0685
|  |  | Admittance balancing units (single phase) | 0 | 0 | 0 | 212173.0699 | 16791.6728 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 228964.7426 | 0 | 0 | 0 | 228964.7426
|  |  | Admittance balancing units (three phase) | 0 | 0 | 0 | 704915.6747 | 63944.0468 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 768859.7216 | 0 | 0 | 0 | 768859.7216
|  |  | Re-phasing | 0 | 0 | 0 | 6614.7763 | 31418.5029 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 38033.2792 | 0 | 0 | 0 | 38033.2792
|  |  | Fusesavers | 0 | 0 | 0 | 426360.3295 | 42974.7339 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 469335.0634 | 0 | 0 | 0 | 469335.0634
|  |  | HV Regulators upgrade (control box) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | HV Regulators upgrade (close delta) | 0 | 0 | 0 | 648763.1301 | 86841.2638 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 735604.3939 | 0 | 0 | 0 | 735604.3939
|  |  | Distribution switchgear (installed) | 0 | 0 | 0 | 1183086.2529 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1183086.2529 | 0 | 0 | 0 | 1183086.2529
|  |  | UG cable replacement | 0 | 0 | 0 | 2538169.4386 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2538169.4386 | 0 | 0 | 0 | 2538169.4386
|  |  | Test Sites | 0 | 0 | 0 | 5594.1793 | 9479.7207 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15073.9 | 0 | 0 | 0 | 15073.9
|  |  | HV Customers (total) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | HV Customers (generation signalling) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 22kV feeder works | 0 | 0 | 0 | 8568000 | 283992.5669 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8851992.5669 | 0 | 0 | 0 | 8851992.5669
|  |  | 66kV Line works (Overhead) | 0 | 0 | 0 | 11934000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11934000 | 0 | 0 | 0 | 11934000
|  |  | 3rd phase line extension | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Asset resilience testing | 0 | 0 | 0 | 601898.4913 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 601898.4913 | 0 | 0 | 0 | 601898.4913
|  |  | Distribution Comms | 0 | 0 | 0 | 4896000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4896000 | 0 | 0 | 0 | 4896000
|  |  | Other distribution materials | 0 | 0 | 0 | 612000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 612000 | 0 | 0 | 0 | 612000
Substation
Primary Plant
|  |  | GFN | 0 | 0 | 0 | 2581276.8708 | 1329740.9301 | 91800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4002817.8008 | 0 | 0 | 0 | 4002817.8008
|  |  | GFN enclosure | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Indoor switch room (incl GFN enclosure and switchboard) | 0 | 0 | 0 | 1281303.0825 | 441168.0884 | 112200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1834671.1708 | 0 | 0 | 0 | 1834671.1708
|  |  | RMU | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 66/22kV transformer | 0 | 0 | 0 | 1509600 | 2532918.2735 | 448800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4491318.2735 | 0 | 0 | 0 | 4491318.2735
|  |  | 66kV circuit breaker | 0 | 0 | 0 | 379440 | 438375.2111 | 146880 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 964695.2111 | 0 | 0 | 0 | 964695.2111
|  |  | 66kV bus extension | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Station service transformer (500kVA) | 0 | 0 | 0 | 146344.9614 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 146344.9614 | 0 | 0 | 0 | 146344.9614
|  |  | Station service transformer (750kVA) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Cap bank | 0 | 0 | 0 | 344183.8486 | 0 | 61200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 405383.8486 | 0 | 0 | 0 | 405383.8486
|  |  | AC board (Including change over) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Control room | 0 | 0 | 0 | 935507.8479 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 935507.8479 | 0 | 0 | 0 | 935507.8479
|  |  | 22kV circuit breaker (outdoor) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Voltage transformer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Current transformer (post type) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Current transformer (core balance type) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Other primary materials | 0 | 0 | 0 | 407905 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 407905 | 0 | 0 | 0 | 407905
|  |  | SCADA / Protection & Control/ Comms | 0 | 0 | 0 | 2337900.7575 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2337900.7575 | 0 | 0 | 0 | 2337900.7575
|  |  | Commissioning | 0 | 0 | 0 | 0 | 219101 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 219101 | 0 | 0 | 0 | 219101
|  |  | ESV observed compliance | 0 | 0 | 0 | 0 | 49471.7998 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 49471.7998 | 0 | 0 | 0 | 49471.7998
|  |  | Construction delivery & site control | 0 | 0 | 0 | 0 | 152914.1449 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 152914.1449 | 0 | 0 | 0 | 152914.1449
Contracts
|  |  | Traffic control | 0 | 0 | 0 | 0 | 0 | 660212 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 660212 | 0 | 0 | 0 | 660212
|  |  | Line survey | 0 | 0 | 0 | 0 | 0 | 40626.1578 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40626.1578 | 0 | 0 | 0 | 40626.1578
|  |  | Civil works | 0 | 0 | 0 | 0 | 0 | 1989166 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1989166 | 0 | 0 | 0 | 1989166
|  |  | Civil works | 0 | 0 | 0 | 0 | 0 | 40800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40800 | 0 | 0 | 0 | 40800
|  |  | Other | 0 | 0 | 0 | 0 | 0 | 960500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 960500 | 0 | 0 | 0 | 960500
|  | Total construction |  | 0 | 2092376.1853 | 0 | 43061777.9801 | 7682513.8581 | 4552184.1578 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2092376.1853 | 55296475.996 | 0 | 0 | 0 | 57388852.1813

## Option3_cost
Powercor REFCLs North Western Geelong
Costs: |  |  | Option3
(real 2021 dollars)
Design & Procurement |  |  | 2021/22
Construction |  |  | 2022/23
Commissioning |  |  | 2022/23
|  |  |  | 2021/22 | 2021/22 | 2021/22 | 2022/23 | 2022/23 | 2022/23 | 2023/24 | 2023/24 | 2023/24 | 2024/25 | 2024/25 | 2024/25 | 2025/26 | 2025/26 | 2025/26 | 2021/22 | 2022/23 | 2023/24 | 2024/25 | 2025/26 | Total
|  |  |  | Materials | Labour | Contracts | Materials | Labour | Contracts | Materials | Labour | Contracts | Materials | Labour | Contracts | Materials | Labour | Contracts | Total | Total | Total | Total | Total | Total Cost
Design & Procurement
|  |  | Design & Procurement | 0 | 2092376.1853 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2092376.1853 | 0 | 0 | 0 | 0 | 2092376.1853
Feeder works
|  |  | Surge arrestor sites (single phase) | 0 | 0 | 0 | 124761.0084 | 566977.5813 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 691738.5897 | 0 | 0 | 0 | 691738.5897
|  |  | Surge arrestor sites (three phase) | 0 | 0 | 0 | 547612.6579 | 1339078.2621 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1886690.92 | 0 | 0 | 0 | 1886690.92
|  |  | ACRs | 0 | 0 | 0 | 81310.3478 | 39326.2456 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120636.5934 | 0 | 0 | 0 | 120636.5934
|  |  | ACR/gas switch control box replacement | 0 | 0 | 0 | 47056.255 | 37999.8135 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 85056.0685 | 0 | 0 | 0 | 85056.0685
|  |  | Admittance balancing units (single phase) | 0 | 0 | 0 | 212173.0699 | 16791.6728 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 228964.7426 | 0 | 0 | 0 | 228964.7426
|  |  | Admittance balancing units (three phase) | 0 | 0 | 0 | 704915.6747 | 63944.0468 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 768859.7216 | 0 | 0 | 0 | 768859.7216
|  |  | Re-phasing | 0 | 0 | 0 | 6614.7763 | 31418.5029 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 38033.2792 | 0 | 0 | 0 | 38033.2792
|  |  | Fusesavers | 0 | 0 | 0 | 426360.3295 | 42974.7339 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 469335.0634 | 0 | 0 | 0 | 469335.0634
|  |  | HV Regulators upgrade (control box) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | HV Regulators upgrade (close delta) | 0 | 0 | 0 | 648763.1301 | 86841.2638 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 735604.3939 | 0 | 0 | 0 | 735604.3939
|  |  | Distribution switchgear (installed) | 0 | 0 | 0 | 1183086.2529 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1183086.2529 | 0 | 0 | 0 | 1183086.2529
|  |  | UG cable replacement | 0 | 0 | 0 | 2538169.4386 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2538169.4386 | 0 | 0 | 0 | 2538169.4386
|  |  | Test Sites | 0 | 0 | 0 | 5594.1793 | 9479.7207 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15073.9 | 0 | 0 | 0 | 15073.9
|  |  | HV Customers (total) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | HV Customers (generation signalling) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 22kV feeder works | 0 | 0 | 0 | 8568000 | 283992.5669 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8851992.5669 | 0 | 0 | 0 | 8851992.5669
|  |  | 66kV Line works (Overhead) | 0 | 0 | 0 | 8874000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8874000 | 0 | 0 | 0 | 8874000
|  |  | 3rd phase line extension | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Asset resilience testing | 0 | 0 | 0 | 601898.4913 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 601898.4913 | 0 | 0 | 0 | 601898.4913
|  |  | Distribution Comms | 0 | 0 | 0 | 3366000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3366000 | 0 | 0 | 0 | 3366000
|  |  | Other distribution materials | 0 | 0 | 0 | 612000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 612000 | 0 | 0 | 0 | 612000
Substation
Primary Plant
|  |  | GFN | 0 | 0 | 0 | 2581276.8708 | 1329740.9301 | 91800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4002817.8008 | 0 | 0 | 0 | 4002817.8008
|  |  | GFN enclosure | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Indoor switch room (incl GFN enclosure and switchboard) | 0 | 0 | 0 | 1281303.0825 | 441168.0884 | 112200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1834671.1708 | 0 | 0 | 0 | 1834671.1708
|  |  | RMU | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 66/22kV transformer | 0 | 0 | 0 | 1509600 | 2532918.2735 | 448800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4491318.2735 | 0 | 0 | 0 | 4491318.2735
|  |  | 66kV circuit breaker | 0 | 0 | 0 | 379440 | 438375.2111 | 146880 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 964695.2111 | 0 | 0 | 0 | 964695.2111
|  |  | 66kV bus extension | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Station service transformer (500kVA) | 0 | 0 | 0 | 146344.9614 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 146344.9614 | 0 | 0 | 0 | 146344.9614
|  |  | Station service transformer (750kVA) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Cap bank | 0 | 0 | 0 | 344183.8486 | 0 | 61200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 405383.8486 | 0 | 0 | 0 | 405383.8486
|  |  | AC board (Including change over) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Control room | 0 | 0 | 0 | 935507.8479 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 935507.8479 | 0 | 0 | 0 | 935507.8479
|  |  | 22kV circuit breaker (outdoor) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Voltage transformer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Current transformer (post type) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Current transformer (core balance type) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Other primary materials | 0 | 0 | 0 | 407905 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 407905 | 0 | 0 | 0 | 407905
|  |  | SCADA / Protection & Control/ Comms | 0 | 0 | 0 | 2337900.7575 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2337900.7575 | 0 | 0 | 0 | 2337900.7575
|  |  | Commissioning | 0 | 0 | 0 | 0 | 219101 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 219101 | 0 | 0 | 0 | 219101
|  |  | ESV observed compliance | 0 | 0 | 0 | 0 | 49471.7998 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 49471.7998 | 0 | 0 | 0 | 49471.7998
|  |  | Construction delivery & site control | 0 | 0 | 0 | 0 | 152914.1449 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 152914.1449 | 0 | 0 | 0 | 152914.1449
Contracts
|  |  | Traffic control | 0 | 0 | 0 | 0 | 0 | 660212 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 660212 | 0 | 0 | 0 | 660212
|  |  | Line survey | 0 | 0 | 0 | 0 | 0 | 40626.1578 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40626.1578 | 0 | 0 | 0 | 40626.1578
|  |  | Civil works | 0 | 0 | 0 | 0 | 0 | 1989166 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1989166 | 0 | 0 | 0 | 1989166
|  |  | Civil works | 0 | 0 | 0 | 0 | 0 | 40800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40800 | 0 | 0 | 0 | 40800
|  |  | Other | 0 | 0 | 0 | 0 | 0 | 960500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 960500 | 0 | 0 | 0 | 960500
|  | Total construction |  | 0 | 2092376.1853 | 0 | 38471777.9801 | 7682513.8581 | 4552184.1578 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2092376.1853 | 50706475.996 | 0 | 0 | 0 | 52798852.1813

## Labour_rates
Powercor REFCLs North Western Geelong
Labour Rates
(real 2021 dollars)
Design & Procurement RATES
| Design & Procurement Rates |  | 2021/22 | 2022/23 | 2023/24 | 2024/25 | 2025/26
| Design & Procurement | 2021 $/hr | 221.697 | 221.697 | 221.697 | 221.697 | 221.697
GEELONG RESOURCE PARTNER RATES
| Rate per person per hour (with vehicles allocated) |  | 2021/22 | 2022/23 | 2023/24 | 2024/25 | 2025/26
| Live Linework | 2021 $/hr | 180.5661 | 180.5661 | 180.5661 | 180.5661 | 180.5661
| General Linework | 2021 $/hr | 169.6129 | 169.6129 | 169.6129 | 169.6129 | 169.6129
| Sub Tester | 2021 $/hr | 261.2691 | 261.2691 | 261.2691 | 261.2691 | 261.2691
| Fitter | 2021 $/hr | 184.4855 | 184.4855 | 184.4855 | 184.4855 | 184.4855