## Output
Powercor
Mitigating REFCL reliability impacts cost model
Total REFCL smart ACR replacement program costs
| Forecast direct capex ($m, 2021) | 2021/22 | 2022/23 | 2023/24 | 2024/25 | 2025/26 | Total
| T1 | 3.4336 | 0 | 0 |  |  | 3.4336
| T2 | 5.2866 | 0 | 0 |  |  | 5.2866
| T3 | 0 | 4.2406 | 0 |  |  | 4.2406
| Total Cost | 8.7202 | 4.2406 | 0 | 0 | 0 | 12.9608

## Calcs
Powercor
Mitigating REFCL reliability impacts cost model
| ZSS | Tranche | Quantity replaced | Installed | Total Material Cost | Labour Cost ($) |  | Total
[6 empty] | Live Linework | Subtester
| CDN | T1 | 9 | 2021/22 | 240479.363 | 176603.7298 | 100138.6608 | 517221.7536
| CLC | T1 | 18 | 2021/22 | 480958.726 | 353207.4597 | 200277.3215 | 1034443.5072
| CMN | T1 | 7 | 2021/22 | 187039.5045 | 121457.0811 | 78044.7054 | 386541.291
| GSB | T1 | 7 | 2021/22 | 187039.5045 | 121457.0811 | 78044.7054 | 386541.291
| MRO | T1 | 9 | 2021/22 | 240479.363 | 156159.1042 | 100343.1927 | 496981.6599
| WIN | T1 | 2 | 2021/22 | 53439.8584 | 39245.2733 | 22253.0357 | 114938.1675
| WND | T1 | 9 | 2021/22 | 240479.363 | 156159.1042 | 100343.1927 | 496981.6599
| BAN | T2 | 25 | 2021/22 | 667998.2305 | 513484.8094 | 277723.6056 | 1459206.6455
| BAS | T2 | 23 | 2021/22 | 614558.3721 | 472406.0247 | 255505.7171 | 1342470.1139
| BET | T2 | 12 | 2021/22 | 320639.1507 | 208212.139 | 133790.9236 | 662642.2132
| BGO | T2 | 6 | 2021/22 | 160319.5753 | 104106.0695 | 66895.4618 | 331321.1066
| CTN | T2 | 20 | 2021/22 | 534398.5844 | 347020.2316 | 222984.8726 | 1104403.6886
| EHK | T2 | 7 | 2021/22 | 187039.5045 | 121457.0811 | 78044.7054 | 386541.291
| ART | T3 | 6 | 2022/23 | 160319.5753 | 131242.3341 | 81316.7239 | 372878.6333
| CRO | T3 | 3 | 2022/23 | 80159.7877 | 51896.8578 | 31288.2801 | 163344.9256
| GL | T3 | 7 | 2022/23 | 187039.5045 | 121457.0811 | 78044.7054 | 386541.291
| HTN | T3 | 14 | 2022/23 | 374079.0091 | 296262.7836 | 180853.8972 | 851195.6899
| KRT | T3 | 4 | 2022/23 | 106879.7169 | 84646.5096 | 51672.5421 | 243198.7685
| MBN | T3 | 3 | 2022/23 | 80159.7877 | 69014.6343 | 39463.756 | 188638.1779
| STL | T3 | 10 | 2022/23 | 267199.2922 | 218737.2235 | 135527.8731 | 621464.3889
| TRG | T3 | 14 | 2022/23 | 374079.0091 | 296262.7836 | 180853.8972 | 851195.6899
| WPD | T3 | 20 | 2022/23 | 534398.5844 | 17298.9526 | 10429.4267 | 562126.9637
| Total |  | 235 |  | 6279183.3669 | 4177794.3488 | 2503841.2019 | 12960818.9176

## Inputs
Powercor
Mitigating REFCL reliability impacts cost model
Inflation |  | Dec 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2020/21
|  | Actual | Actual | Actual | Actual | Actual | Actual | Forecast
Annual CPI - 12 months lagged |  |  | 1.511% | 1.023% | 1.934% | 2.078% | 1.593% | 2%
Cumulative CPI from 2015 (end of year) |  | 1 | 1.0075 | 1.0178 | 1.0375 | 1.0591 | 1.0759 | 1.0975
Cost inputs are in: |  | Dec 2015: Dec 2015; 2016: dollars (end of year, from T3 CPA)
To convert from actual: |  | Dec 2015: Dec 2015; 2016: dollars (end of calendar year)
To: |  | Dec 2015: 2020/21; 2016: dollars (end of financial year)
Multiply by: |  | Dec 2015: 1.0975
Materials
Material unit rates: |  | Dec 2015: 24347; 2016: ($, 2015)
Material unit rates: |  | Dec 2015: 26719.9292; 2016: ($, 2021)
Labour rates
| ZSS | Dec 2015: Labour cost ($/ph, 2015)
|  | Live Lineworker | Sub Tester
| Ballarat | Dec 2015: 194.9515; 2016: 253.0597
| Bendigo | Dec 2015: 164.6887; 2016: 253.9777
| Colac | Dec 2015: 186.25; 2016: 253.46
| Geelong | Dec 2015: 164.1945; 2016: 237.5804
| Horsham | Dec 2015: 207.6164; 2016: 308.73
| Mildura | Dec 2015: 218.3528; 2016: 299.659
| Warrnambool | Dec 2015: 200.8575; 2016: 294.2727
Volumes and labour rates applied
| ZSS | Tranche | Labour Location | ACR volumes | ACRs volumes | Year installed | Hours |  | Labour cost ($2021)
|  | 2017: (Total on ZSS); 2018: (Replaced in CP3); 2020: Live lineworker; 2020/21: Sub tester | Live Lineworker | Sub Tester
| CDN | T1 | Colac | 9 |  | 2021/22 | 864 | 360 | 204.4025 | 278.1629
| CLC | T1 | Colac | 18 |  | 2021/22 | 1728 | 720 | 204.4025 | 278.1629
| CMN | T1 | Bendigo | 7 |  | 2021/22 | 672 | 280 | 180.7397 | 278.7311
| GSB | T1 | Bendigo | 7 |  | 2021/22 | 672 | 280 | 180.7397 | 278.7311
| MRO | T1 | Bendigo | 9 |  | 2021/22 | 864 | 360 | 180.7397 | 278.7311
| WIN | T1 | Colac | 2 |  | 2021/22 | 192 | 80 | 204.4025 | 278.1629
| WND | T1 | Bendigo | 9 |  | 2021/22 | 864 | 360 | 180.7397 | 278.7311
| BAN | T2 | Ballarat | 25 |  | 2021/22 | 2400 | 1000 | 213.952 | 277.7236
| BAS | T2 | Ballarat | 23 |  | 2021/22 | 2208 | 920 | 213.952 | 277.7236
| BET | T2 | Bendigo | 12 |  | 2021/22 | 1152 | 480 | 180.7397 | 278.7311
| BGO | T2 | Bendigo | 6 |  | 2021/22 | 576 | 240 | 180.7397 | 278.7311
| CTN | T2 | Bendigo | 20 |  | 2021/22 | 1920 | 800 | 180.7397 | 278.7311
| EHK | T2 | Bendigo | 7 |  | 2021/22 | 672 | 280 | 180.7397 | 278.7311
| ART | T3 | Horsham | 7 | 1 | 2022/23 | 576 | 240 | 227.8513 | 338.8197
| CRO | T3 | Geelong | 6 | 3 | 2022/23 | 288 | 120 | 180.1974 | 260.7357
| GL | T3 | Bendigo | 8 | 1 | 2022/23 | 672 | 280 | 180.7397 | 278.7311
| HTN | T3 | Warrnambool | 15 | 1 | 2022/23 | 1344 | 560 | 220.4336 | 322.9534
| KRT | T3 | Warrnambool | 7 | 3 | 2022/23 | 384 | 160 | 220.4336 | 322.9534
| MBN | T3 | Mildura | 4 | 1 | 2022/23 | 288 | 120 | 239.6341 | 328.8646
| STL | T3 | Horsham | 11 | 1 | 2022/23 | 960 | 400 | 227.8513 | 338.8197
| TRG | T3 | Warrnambool | 19 | 5 | 2022/23 | 1344 | 560 | 220.4336 | 322.9534
| WPD | T3 | Geelong | 22 | 2 | 2022/23 | 96 | 40 | 180.1974 | 260.7357