## Index
Revenue Reset Information Pro Formas
INDEX | Click on orange box for link to pages
Historic Opex |  | Historic Capex
Table 1.1 | Historic Opex by Category - Summary | Table 3.1 | Historic Capex by Category
1.2 | Historic Opex by Category 02 | 3.2 | Historic Capex by Asset Class
1.3 | Historic Opex by Category 02/03 | 3.3 | Historic Capex - Network
1.4 | Historic Opex by Category 03/04 | 3.4 | Historic Capex - Non-Network
1.5 | Historic Opex by Category 04/05
1.6 | Historic Opex by Category 05/06
1.7 | Historic Opex by Category 06/07
Forecast Opex |  | Forecast Capex
Table 2.1 | Forecast Opex by Category - Summary | Table 4.1 | Forecast Capex by Category
2.2 | Forecast Opex by Category 07/08 | 4.2 | Forecast Capex by Asset Class
2.3 | Forecast Opex by Category 08/09 | 4.3.1 | Forecast Capex - Network/Common
2.4 | Forecast Opex by Category 09/10 | 4.3.2 | Forecast Capex - Network/Varied
2.5 | Forecast Opex by Category 10/11 | 4.4 | Forecast Capex - Non Network
2.6 | Forecast Opex by Category 11/12
Commentary |  | Instructions / Definitions
Table 5.1 | Commentary on Opex | Table 6.1 | Opex Instructions
5.2 | Commentary on Historic Capex | 6.2 | Historic Capex Instructions
|  | 6.3 | Forecast Capex Instructions

## Historic Opex Summary
|  | Home |  | Link to Opex instructions - Table 6.1 |  |  | Link to Opex Commentary - Table 5.1
1.1 HISTORIC OPEX by expenditure category
($m, nominal)
| Financial year | 2002 (6mths) | 2002/03 | 2003/04 | 2004/05 | 2005/06* | 2006/07* | Total | Revenue Cap Allowance | Key cost drivers and explanation for material differences over time
Direct Operations & Maintenance
Maintenance
Communications
Labour |  | 0.387 | 0.915 | 0.88 | 1.058 | 1.166 | 1.433 | 5.839
Materials |  | 0.137 | 0.322 | 0.309 | 0.371 | 0.397 | 0.439 | 1.975
Sub-Totals |  | 0.524 | 1.237 | 1.189 | 1.429 | 1.563 | 1.872 | 7.814
Lines
Labour |  | 1.127 | 2.924 | 3.126 | 3.758 | 3.92 | 4.351 | 19.206
Materials |  | 0.519 | 1.346 | 1.437 | 1.729 | 1.743 | 1.747 | 8.521
Sub-Totals |  | 1.646 | 4.27 | 4.563 | 5.487 | 5.663 | 6.098 | 27.727
Secondary Systems
Labour |  | 1.144 | 2.099 | 2.626 | 2.773 | 3.098 | 3.646 | 15.386
Materials |  | 0.113 | 0.208 | 0.261 | 0.274 | 0.296 | 0.315 | 1.467
Sub-Totals |  | 1.257 | 2.307 | 2.887 | 3.047 | 3.394 | 3.961 | 16.853
Substations
Labour |  | 2.053 | 5.316 | 7.249 | 5.973 | 7.488 | 8.701 | 36.78
Materials |  | 0.995 | 2.58 | 3.516 | 2.898 | 3.513 | 3.684 | 17.186
Sub-Totals |  | 3.048 | 7.896 | 10.765 | 8.871 | 11.001 | 12.385 | 53.966
Easements
Labour |  | 1.495 | 3.511 | 3.801 | 4.748 | 5.275 | 6.208 | 25.038
Materials |  | 0.291 | 0.684 | 0.74 | 0.925 | 1.027 | 1.209 | 4.876
Sub-Totals |  | 1.786 | 4.195 | 4.541 | 5.673 | 6.302 | 7.417 | 29.914
Summary
Sub-Total Labour |  | 6.206 | 14.765 | 17.682 | 18.31 | 20.947 | 24.339 | 102.249
Sub-Total Materials |  | 2.055 | 5.14 | 6.263 | 6.197 | 6.976 | 7.394 | 34.025
Total Maintenance |  | 8.261 | 19.905 | 23.945 | 24.507 | 27.923 | 31.733 | 136.274
Refurbishment
Labour |  | 5.743 | 9.876 | 10.417 | 10.944 | 11.68 | 13.561 | 62.221
Materials |  | 1.719 | 2.956 | 3.117 | 3.275 | 3.496 | 4.058 | 18.621
Total Operational Refurbishment |  | 7.462 | 12.832 | 13.534 | 14.219 | 15.176 | 17.619 | 80.842
New Requirements | [6 empty] | 1.944 | 1.944
Field Support
Field Support |  | 0 | 0.703 | 0.767 | 0.934 | 1.022 | 1.147 | 4.573
Other Support |  | 1.825 | 3.356 | 3.943 | 3.472 | 3.892 | 4.303 | 20.791
Direct Charges |  | 1.108 | 2.241 | 2.383 | 2.792 | 2.959 | 3.126 | 14.609
Total Field Support |  | 2.933 | 6.3 | 7.093 | 7.198 | 7.873 | 8.576 | 39.973
Total Network Maintenance |  | 18.656 | 39.037 | 44.572 | 45.924 | 50.972 | 59.872 | 259.033 | 244.124 | Network maintenance costs have been higher than the Revenue Cap Allowance for the following reasons: - Larger network than forecast to be maintained - Wage parity-based labour costs - Compliance obligations - Restricted ability to obtain network outages
Operations
Network Switching |  | 1.619 | 5.501 | 5.709 | 5.036 | 5.645 | 6.098 | 29.608
Asset Monitoring |  | 0.76 | 1.228 | 1.343 | 1.487 | 1.667 | 1.8 | 8.285
NMS Support |  | 0 | 0 | 0 | 1.463 | 1.64 | 1.771 | 4.874
Total Operations |  | 2.379 | 6.729 | 7.052 | 7.986 | 8.952 | 9.669 | 42.767 | 39.911 | Operations costs have been higher than the Revenue Cap Allowance because of: - The network being operated is larger than forecast - Labour cost increases to maintain wage parity
Total Direct Operations & Maintenance |  | 21.035 | 45.766 | 51.624 | 53.91 | 59.924 | 69.541 | 301.8
Other Controllable
Asset Manager Support
Grid Planning |  | 1.342 | 2.545 | 2.931 | 3.29 | 3.672 | 3.949 | 17.729
Network Support |  | 0.377 | 7.577 | 7.831 | 8.074 | 9.011 | 9.69 | 42.56
IT Support |  | 4.496 | 6.431 | 4.964 | 5.366 | 5.989 | 6.441 | 33.687
Customer & Regulatory Support |  | 1.5075 | 2.274 | 3.222 | 4.061 | 5.766 | 5.874 | 22.7045
Sub-Totals |  | 7.7225 | 18.827 | 18.948 | 20.791 | 24.438 | 25.954 | 116.6805
Corporate Support
Corporate Suppport |  | 6.0705 | 6.362 | 5.232 | 10.452 | 7.641 | 8.06 | 43.8175
Sub-Totals |  | 6.0705 | 6.362 | 5.232 | 10.452 | 7.641 | 8.06 | 43.8175
Insurance
Insurance |  | 0 | 2.241 | 2.505 | 2.346 | 2.804 | 3.456 | 13.352
Total Other Controllable |  | 13.793 | 27.43 | 26.685 | 33.589 | 34.883 | 37.47 | 173.85 | 156.916 | Other Controllable costs have benn greater than the Revenue Cap Allowance as a result of: - A larger than forecast network combined with higher than forecast demand requiring greater planning and technical support effort - Maintainng wage parity for labour costs
Summary
Total Labour1 |  | 28.477 | 0 | 0 | 0 | 0 | 0 | 28.477
Total Maintenance Materials2 |  | 3.774 | 0 | 0 | 0 | 0 | 0 | 3.774
Total Other Materials3 |  | 2.576 | 0 | 0 | 0 | 0 | 0 | 2.576
TOTAL OPEX (exc. Grid Support) |  | 34.828 | 73.196 | 78.309 | 87.499 | 94.807 | 107.011 | 475.65 | 440.964 | Total Opex exceeds the Revenue Cap Allowance due to: - A larger network than forecast, from higher than forecast demand growth - Wage parity-based labour costs - Compliance obligations for safety and vegetation management - Restricted ability to obtain network outages
Revenue Cap Allowance (exc. Grid Support) |  | 32.821 | 72.406 | 77.724 | 81.488 | 85.688 | 90.837 | 440.964
Grid Support |  | 18.407 | 10.7 | 11.18 | 15.32 | 13.48 | 16.38 | 85.467 | 89.107
Grand Total |  | 53.235 | 83.896 | 89.489 | 102.819 | 108.287 | 123.391 | 561.117
Other Allowances |  | 0.73 | 2.968 | 3.037 | 3.108 | 3.18 | 3.254 | 16.277
Revenue Cap Allowance |  | 55.551 | 80.574 | 97.378 | 100.023 | 102.349 | 110.473 | 546.348
1 Total Labour is the total combination of all labour aspects from all line items. | [5 empty] | *Note that values in these columns are estimates only
2Total Maintenance Materials is sourced only from Sub-Total Materials.
3The Total Other Materials are material costs sourced from the opex line items below Field Support.
Labour includes the labour component of both inhouse and external maintenance service providers. Note that labour does not equate to salaries.
Powerlink does not have the actual split between labour and materials for external maintenance service providers, so an allocation based on known splits has been made.

## Historic Opex by Category 2002
| Home |  | Link to Opex instructions - Table 6.1
1.2 HISTORIC OPEX by expenditure category
Half Year Ended 30 June 2002
($m, nominal) | Half Year Ended 30 June 2002
| Field Maintenance |  |  | Operational Refurbishment |  | Network Monitoring & Control | Support / Corporate
| Routine | Condition-Based | Corrective |  | Maintenance Support |  | Network | Non-Network | TOTAL | Revenue Cap Allowance | Key cost drivers and explanation for material differences over time
Direct Operations & Maintenance
Maintenance
Communications
Labour | 0.189 | 0.05 | 0.148 | [5 empty] | 0.387
Materials | 0.067 | 0.018 | 0.052 | [5 empty] | 0.137
Sub-Totals | 0.256 | 0.068 | 0.2 | [5 empty] | 0.524
Lines
Labour | 0.352 | 0.595 | 0.18 | [5 empty] | 1.127
Materials | 0.162 | 0.274 | 0.083 | [5 empty] | 0.519
Sub-Totals | 0.514 | 0.869 | 0.263 | [5 empty] | 1.646
Secondary Systems
Labour | 0.699 | 0.054 | 0.391 | [5 empty] | 1.144
Materials | 0.069 | 0.005 | 0.039 | [5 empty] | 0.113
Sub-Totals | 0.768 | 0.059 | 0.43 | [5 empty] | 1.257
Substations
Labour | 0.872 | 0.512 | 0.669 | [5 empty] | 2.053
Materials | 0.423 | 0.248 | 0.324 | [5 empty] | 0.995
Sub-Totals | 1.295 | 0.76 | 0.993 | [5 empty] | 3.048
Easements
Labour |  | 1.495 | [6 empty] | 1.495
Materials |  | 0.291 | [6 empty] | 0.291
Sub-Totals |  | 1.786 | [6 empty] | 1.786
Summary
Sub-Total Labour | 2.112 | 2.706 | 1.388 | [5 empty] | 6.206
Sub-Total Materials | 0.721 | 0.836 | 0.498 | [5 empty] | 2.055
Total Maintenance | 2.833 | 3.542 | 1.886 | [5 empty] | 8.261
Refurbishment
Sub-Total Labour |  |  |  | 5.743 |  |  |  |  | 5.743
Sub-Total Materials |  |  |  | 1.719 |  |  |  |  | 1.719
Total Operational Refurbishment |  |  |  | 7.462 |  |  |  |  | 7.462
New Requirements
Field Support
Field Support |  |  |  |  | 0 |  |  |  | 0
Other Support |  |  |  |  | 1.825 |  |  |  | 1.825
Direct Charges |  |  |  |  | 1.108 |  |  |  | 1.108
Total Field Support |  |  |  |  | 2.933 |  |  |  | 2.933
Total Field Maintenance | 2.833 | 3.542 | 1.886 | 7.462 | 2.933 | 0 | 0 | 0 | 18.656 | 18.244
Operations
Network Switching | [5 empty] | 1.619 |  |  | 1.619
Asset Monitoring | [5 empty] | 0.76 |  |  | 0.76
NMS Support | [5 empty] | 0 |  |  | 0
Total Operations | [5 empty] | 2.379 |  |  | 2.379 | 2.441
Total Direct Operations & Maintenance | 2.833 | 3.542 | 1.886 | 7.462 | 2.933 | 2.379 | 0 | 0 | 21.035
Other Controllable
Asset Manager Support
Grid Planning | [6 empty] | 1.342 |  | 1.342
Network Support | [6 empty] | 0.377 |  | 0.377
IT Support | [7 empty] | 4.496 | 4.496
Customer & Regulatory Support | [6 empty] | 1.5075 |  | 1.5075
Sub-Totals | [6 empty] | 3.2265 | 4.496 | 7.7225
Corporate Support
Corporate Suppport | [7 empty] | 6.0705 | 6.0705
Sub-Totals | [7 empty] | 6.0705 | 6.0705
Insurance
Insurance | [6 empty] | 0 |  | 0
Sub-Totals | [6 empty] | 0 |  | 0
Total Other Controllable | 0 | 0 | 0 | 0 | 0 | 0 | 3.2265 | 10.5665 | 13.793 | 12.137
Summary
Total Labour1 | 2.112 | 2.706 | 1.388 | 5.743 | 1.643 | 2.141 | 2.9035 | 9.8405 | 28.477
Total Maintenance Materials2 | 0.721 | 0.836 | 0.498 | 1.719 |  |  |  |  | 3.774
Total Other Materials3 |  |  |  |  | 1.29 | 0.238 | 0.322 | 0.726 | 2.576
TOTAL OPEX (exc. Grid Support) | 2.833 | 3.542 | 1.886 | 7.462 | 2.933 | 2.379 | 3.2265 | 10.5665 | 34.828 | 32.821
Grid Support | [8 empty] | 18.407 | 22
Other Allowances | [9 empty] | 0.73
Grand Total | [8 empty] | 53.235 | 55.551
1 Total Labour is the total combination of all labour aspects from all line items.
2Total Maintenance Materials is sourced only from Sub-Total Materials.
3The Total Other Materials are material costs sourced from the opex line items below Field Support.
Labour includes the labour component of both inhouse and external maintenance service providers. Note that labour does not equate to salaries.
Powerlink does not have the actual split between labour and materials for external maintenance service providers, so an allocation based on known splits has been made.

## Historic Opex by Category 02-03
| Home |  | Link to Opex instructions - Table 6.1
1.3 HISTORIC OPEX by expenditure category
Year Ended 30 June 2003
($m, nominal) | Year Ended 30 June 2003
| Field Maintenance |  |  | Operational Refurbishment |  | Network Monitoring & Control | Support / Corporate
| Routine | Condition-Based | Corrective |  | Maintenance Support |  | Network | Non-Network | TOTAL | Revenue Cap Allowance | Key cost drivers and explanation for material differences over time
Direct Operations & Maintenance
Maintenance
Communications
Labour | 0.305 | 0.392 | 0.218 | [5 empty] | 0.915
Materials | 0.107 | 0.138 | 0.077 | [5 empty] | 0.322
Sub-Totals | 0.412 | 0.53 | 0.295 | [5 empty] | 1.237
Lines
Labour | 0.873 | 1.587 | 0.464 | [5 empty] | 2.924
Materials | 0.402 | 0.73 | 0.214 | [5 empty] | 1.346
Sub-Totals | 1.275 | 2.317 | 0.678 | [5 empty] | 4.27
Secondary Systems
Labour | 0.886 | 0.391 | 0.822 | [5 empty] | 2.099
Materials | 0.088 | 0.039 | 0.081 | [5 empty] | 0.208
Sub-Totals | 0.974 | 0.43 | 0.903 | [5 empty] | 2.307
Substations
Labour | 1.542 | 1.714 | 2.06 | [5 empty] | 5.316
Materials | 0.748 | 0.832 | 1 | [5 empty] | 2.58
Sub-Totals | 2.29 | 2.546 | 3.06 | [5 empty] | 7.896
Easements
Labour |  | 3.511 | [6 empty] | 3.511
Materials |  | 0.684 | [6 empty] | 0.684
Sub-Totals |  | 4.195 | [6 empty] | 4.195
Summary
Sub-Total Labour | 3.606 | 7.595 | 3.564 | [5 empty] | 14.765
Sub-Total Materials | 1.345 | 2.423 | 1.372 | [5 empty] | 5.14
Total Maintenance | 4.951 | 10.018 | 4.936 | [5 empty] | 19.905
Refurbishment
Sub-Total Labour |  |  |  | 9.876 |  |  |  |  | 9.876
Sub-Total Materials |  |  |  | 2.956 |  |  |  |  | 2.956
Total Operational Refurbishment |  |  |  | 12.832 |  |  |  |  | 12.832
New Requirements
Field Support
Field Support |  |  |  |  | 0.703 |  |  |  | 0.703
Other Support |  |  |  |  | 3.356 |  |  |  | 3.356
Direct Charges |  |  |  |  | 2.241 |  |  |  | 2.241
Total Field Support |  |  |  |  | 6.3 |  |  |  | 6.3
Total Network Maintenance | 4.951 | 10.018 | 4.936 | 12.832 | 6.3 | 0 | 0 | 0 | 39.037 | 39.21
Operations
Network Switching | [5 empty] | 5.501 |  |  | 5.501
Asset Monitoring | [5 empty] | 1.228 |  |  | 1.228
NMS Support | [5 empty] | 0 |  |  | 0
Total Operations | [5 empty] | 6.729 |  |  | 6.729 | 6.7
Total Direct Operations & Maintenance | 4.951 | 10.018 | 4.936 | 12.832 | 6.3 | 6.729 | 0 | 0 | 45.766
Other Controllable
Asset Manager Support
Grid Planning | [6 empty] | 2.545 |  | 2.545
Network Support | [6 empty] | 7.577 |  | 7.577
IT Support | [7 empty] | 6.431 | 6.431
Customer & Regulatory Support | [6 empty] | 2.274 |  | 2.274
Sub-Totals | [6 empty] | 12.396 | 6.431 | 18.827
Corporate Support
Corporate Suppport | [7 empty] | 6.362 | 6.362
Sub-Totals | [7 empty] | 6.362 | 6.362
Insurance
Insurance | [6 empty] | 2.241 |  | 2.241
Sub-Totals | [6 empty] | 2.241 |  | 2.241
Total Other Controllable | 0 | 0 | 0 | 0 | 0 | 0 | 14.637 | 12.793 | 27.43 | 26.493
Summary
Total Labour1 | 3.606 | 7.595 | 3.564 | 9.876 | 3.653 | 6.056 | 11.157 | 11.893 | 57.4
Total Maintenance Materials2 | 1.345 | 2.423 | 1.372 | 2.956 |  |  |  |  | 8.096
Total Other Materials3 |  |  |  |  | 2.646 | 0.673 | 3.48 | 0.898 | 7.697
TOTAL OPEX (exc. Grid Support) | 4.951 | 10.018 | 4.936 | 12.832 | 6.3 | 6.729 | 14.637 | 12.793 | 73.196 | 72.406
Grid Support | [8 empty] | 10.7 | 5.2
Other Allowances | [9 empty] | 2.968
Grand Total | [8 empty] | 83.896 | 80.574
1 Total Labour is the total combination of all labour aspects from all line items.
2Total Maintenance Materials is sourced only from Sub-Total Materials.
3The Total Other Materials are material costs sourced from the opex line items below Field Support.
Labour includes the labour component of both inhouse and external maintenance service providers. Note that labour does not equate to salaries.
Powerlink does not have the actual split between labour and materials for external maintenance service providers, so an allocation based on known splits has been made.

## Historic Opex by Category 03-04
| Home |  | Link to Opex instructions - Table 6.1
1.4 HISTORIC OPEX by expenditure category
Year Ended 30 June 2004
($m, nominal) | Year Ended 30 June 2004
| Field Maintenance |  |  | Operational Refurbishment |  | Network Monitoring & Control | Support / Corporate
| Routine | Condition-Based | Corrective |  | Maintenance Support |  | Network | Non-Network | TOTAL | Revenue Cap Allowance | Key cost drivers and explanation for material differences over time
Direct Operations & Maintenance
Maintenance
Communications
Labour | 0.231 | 0.287 | 0.362 | [5 empty] | 0.88
Materials | 0.081 | 0.101 | 0.127 | [5 empty] | 0.309
Sub-Totals | 0.312 | 0.388 | 0.489 | [5 empty] | 1.189
Lines
Labour | 1.035 | 1.36 | 0.731 | [5 empty] | 3.126
Materials | 0.476 | 0.625 | 0.336 | [5 empty] | 1.437
Sub-Totals | 1.511 | 1.985 | 1.067 | [5 empty] | 4.563
Secondary Systems
Labour | 1.087 | 0.239 | 1.3 | [5 empty] | 2.626
Materials | 0.108 | 0.024 | 0.129 | [5 empty] | 0.261
Sub-Totals | 1.195 | 0.263 | 1.429 | [5 empty] | 2.887
Substations
Labour | 1.732 | 1.605 | 3.912 | [5 empty] | 7.249
Materials | 0.84 | 0.778 | 1.898 | [5 empty] | 3.516
Sub-Totals | 2.572 | 2.383 | 5.81 | [5 empty] | 10.765
Easements
Labour |  | 3.801 | [6 empty] | 3.801
Materials |  | 0.74 | [6 empty] | 0.74
Sub-Totals |  | 4.541 | [6 empty] | 4.541
Summary
Sub-Total Labour | 4.085 | 7.292 | 6.305 | [5 empty] | 17.682
Sub-Total Materials | 1.505 | 2.268 | 2.49 | [5 empty] | 6.263
Total Maintenance | 5.59 | 9.56 | 8.795 | [5 empty] | 23.945
Refurbishment
Sub-Total Labour |  |  |  | 10.417 |  |  |  |  | 10.417
Sub-Total Materials |  |  |  | 3.117 |  |  |  |  | 3.117
Total Operational Refurbishment |  |  |  | 13.534 |  |  |  |  | 13.534
New Requirements
Field Support
Field Support |  |  |  |  | 0.767 |  |  |  | 0.767
Other Support |  |  |  |  | 3.943 |  |  |  | 3.943
Direct Charges |  |  |  |  | 2.383 |  |  |  | 2.383
Total Field Support |  |  |  |  | 7.093 |  |  |  | 7.093
Total Network Maintenance | 5.59 | 9.56 | 8.795 | 13.534 | 7.093 | 0 | 0 | 0 | 44.572 | 42.75
Operations
Network Switching | [5 empty] | 5.709 |  |  | 5.709
Asset Monitoring | [5 empty] | 1.343 |  |  | 1.343
NMS Support | [5 empty] | 0 |  |  | 0
Total Operations | [5 empty] | 7.052 |  |  | 7.052 | 7.13
Total Direct Operations & Maintenance | 5.59 | 9.56 | 8.795 | 13.534 | 7.093 | 7.052 | 0 | 0 | 51.624
Other Controllable
Asset Manager Support
Grid Planning | [6 empty] | 2.931 |  | 2.931
Network Support | [6 empty] | 7.831 |  | 7.831
IT Support | [7 empty] | 4.964 | 4.964
Customer & Regulatory Support | [6 empty] | 3.222 |  | 3.222
Sub-Totals | [6 empty] | 13.984 | 4.964 | 18.948
Corporate Support
Corporate Suppport | [7 empty] | 5.232 | 5.232
Sub-Totals | [7 empty] | 5.232 | 5.232
Insurance
Insurance | [6 empty] | 2.505 |  | 2.505
Sub-Totals | [6 empty] | 2.505 |  | 2.505
Total Other Controllable | 0 | 0 | 0 | 0 | 0 | 0 | 16.489 | 10.196 | 26.685 | 27.845
Summary
Total Labour1 | 4.085 | 7.292 | 6.305 | 10.417 | 4.24 | 6.347 | 12.585 | 9.525 | 60.796
Total Maintenance Materials2 | 1.505 | 2.268 | 2.49 | 3.117 |  |  |  |  | 9.38
Total Other Materials3 |  |  |  |  | 2.853 | 0.705 | 3.903 | 0.67 | 8.131
TOTAL OPEX (exc. Grid Support) | 5.59 | 9.56 | 8.795 | 13.534 | 7.093 | 7.052 | 16.489 | 10.196 | 78.309 | 77.724
Grid Support | [8 empty] | 11.18 | 16.617
Other Allowances | [9 empty] | 3.037
Grand Total | [8 empty] | 89.489 | 97.378
1 Total Labour is the total combination of all labour aspects from all line items.
2Total Maintenance Materials is sourced only from Sub-Total Materials.
3The Total Other Materials are material costs sourced from the opex line items below Field Support.
Labour includes the labour component of both inhouse and external maintenance service providers. Note that labour does not equate to salaries.
Powerlink does not have the actual split between labour and materials for external maintenance service providers, so an allocation based on known splits has been made.

## Historic Opex by Category 04-05
| Home |  | Link to Opex instructions - Table 6.1
1.5 HISTORIC OPEX by expenditure category
Year Ended 30 June 2005
($m, nominal) | Year Ended 30 June 2005
| Field Maintenance |  |  | Operational Refurbishment |  | Network Monitoring & Control | Support / Corporate
| Routine | Condition-Based | Corrective |  | Maintenance Support |  | Network | Non-Network | TOTAL | Revenue Cap Allowance | Key cost drivers and explanation for material differences over time
Direct Operations & Maintenance
Maintenance
Communications
Labour | 0.232 | 0.451 | 0.375 | [5 empty] | 1.058
Materials | 0.081 | 0.158 | 0.132 | [5 empty] | 0.371
Sub-Totals | 0.313 | 0.609 | 0.507 | [5 empty] | 1.429
Lines
Labour | 1.013 | 2.172 | 0.573 | [5 empty] | 3.758
Materials | 0.466 | 0.999 | 0.264 | [5 empty] | 1.729
Sub-Totals | 1.479 | 3.171 | 0.837 | [5 empty] | 5.487
Secondary Systems
Labour | 0.899 | 0.62 | 1.254 | [5 empty] | 2.773
Materials | 0.089 | 0.061 | 0.124 | [5 empty] | 0.274
Sub-Totals | 0.988 | 0.681 | 1.378 | [5 empty] | 3.047
Substations
Labour | 1.779 | 1.522 | 2.672 | [5 empty] | 5.973
Materials | 0.863 | 0.739 | 1.296 | [5 empty] | 2.898
Sub-Totals | 2.642 | 2.261 | 3.968 | [5 empty] | 8.871
Easements
Labour |  | 4.748 | [6 empty] | 4.748
Materials |  | 0.925 | [6 empty] | 0.925
Sub-Totals |  | 5.673 | [6 empty] | 5.673
Summary
Sub-Total Labour | 3.923 | 9.513 | 4.874 | [5 empty] | 18.31
Sub-Total Materials | 1.499 | 2.882 | 1.816 | [5 empty] | 6.197
Total Maintenance | 5.422 | 12.395 | 6.69 | [5 empty] | 24.507
Refurbishment
Sub-Total Labour |  |  |  | 10.944 |  |  |  |  | 10.944
Sub-Total Materials |  |  |  | 3.275 |  |  |  |  | 3.275
Total Operational Refurbishment |  |  |  | 14.219 |  |  |  |  | 14.219
New Requirements
Field Support
Field Support |  |  |  |  | 0.934 |  |  |  | 0.934
Other Support |  |  |  |  | 3.472 |  |  |  | 3.472
Direct Charges |  |  |  |  | 2.792 |  |  |  | 2.792
Total Field Support |  |  |  |  | 7.198 |  |  |  | 7.198
Total Network Maintenance | 5.422 | 12.395 | 6.69 | 14.219 | 7.198 | 0 | 0 | 0 | 45.924 | 45.13
Operations
Network Switching | [5 empty] | 5.036 |  |  | 5.036
Asset Monitoring | [5 empty] | 1.487 |  |  | 1.487
NMS Support | [5 empty] | 1.463 |  |  | 1.463
Total Operations | [5 empty] | 7.986 |  |  | 7.986 | 7.48
Total Direct Operations & Maintenance | 5.422 | 12.395 | 6.69 | 14.219 | 7.198 | 7.986 | 0 | 0 | 53.91
Other Controllable
Asset Manager Support
Grid Planning | [6 empty] | 3.29 |  | 3.29
Network Support | [6 empty] | 8.074 |  | 8.074
IT Support | [7 empty] | 5.366 | 5.366
Customer & Regulatory Support | [6 empty] | 4.061 |  | 4.061
Sub-Totals | [6 empty] | 15.425 | 5.366 | 20.791
Corporate Support
Corporate Suppport | [7 empty] | 10.452 | 10.452
Sub-Totals | [7 empty] | 10.452 | 10.452
Insurance
Insurance | [6 empty] | 2.346 |  | 2.346
Sub-Totals | [6 empty] | 2.346 |  | 2.346
Total Other Controllable | 0 | 0 | 0 | 0 | 0 | 0 | 17.771 | 15.818 | 33.589 | 28.872
Summary
Total Labour1 | 3.923 | 9.513 | 4.874 | 10.944 | 3.965 | 7.186 | 13.883 | 14.908 | 69.196
Total Maintenance Materials2 | 1.499 | 2.882 | 1.816 | 3.275 |  |  |  |  | 9.472
Total Other Materials3 |  |  |  |  | 3.232 | 0.799 | 3.889 | 0.911 | 8.831
TOTAL OPEX (exc. Grid Support) | 5.422 | 12.395 | 6.69 | 14.219 | 7.198 | 7.986 | 17.771 | 15.818 | 87.499 | 81.488
Grid Support | [8 empty] | 15.32 | 15.427
Other Allowances | [9 empty] | 3.108
Grand Total | [8 empty] | 102.819 | 100.023
1 Total Labour is the total combination of all labour aspects from all line items.
2Total Maintenance Materials is sourced only from Sub-Total Materials.
3The Total Other Materials are material costs sourced from the opex line items below Field Support.
Labour includes the labour component of both inhouse and external maintenance service providers. Note that labour does not equate to salaries.
Powerlink does not have the actual split between labour and materials for external maintenance service providers, so an allocation based on known splits has been made.

## Historic Opex by Category 05-06
| Home |  | Link to Opex instructions - Table 6.1
1.6 HISTORIC OPEX by expenditure category
Year Ended 30 June 2006
($m, nominal) - estimate | Year Ended 30 June 2006
| Field Maintenance |  |  | Operational Refurbishment |  | Network Monitoring & Control | Support / Corporate
| Routine | Condition-Based | Corrective |  | Maintenance Support |  | Network | Non-Network | TOTAL | Revenue Cap Allowance | Key cost drivers and explanation for material differences over time
Direct Operations & Maintenance
Maintenance
Communications
Labour | 0.279 | 0.461 | 0.426 | [5 empty] | 1.166
Materials | 0.095 | 0.157 | 0.145 | [5 empty] | 0.397
Sub-Totals | 0.374 | 0.618 | 0.571 | [5 empty] | 1.563
Lines
Labour | 1.028 | 2.224 | 0.668 | [5 empty] | 3.92
Materials | 0.457 | 0.989 | 0.297 | [5 empty] | 1.743
Sub-Totals | 1.485 | 3.213 | 0.965 | [5 empty] | 5.663
Secondary Systems
Labour | 1.17 | 0.65 | 1.278 | [5 empty] | 3.098
Materials | 0.112 | 0.062 | 0.122 | [5 empty] | 0.296
Sub-Totals | 1.282 | 0.712 | 1.4 | [5 empty] | 3.394
Substations
Labour | 2.646 | 1.834 | 3.008 | [5 empty] | 7.488
Materials | 1.242 | 0.86 | 1.411 | [5 empty] | 3.513
Sub-Totals | 3.888 | 2.694 | 4.419 | [5 empty] | 11.001
Easements
Labour |  | 5.275 | [6 empty] | 5.275
Materials |  | 1.027 | [6 empty] | 1.027
Sub-Totals |  | 6.302 | [6 empty] | 6.302
Summary
Sub-Total Labour | 5.123 | 10.444 | 5.38 | [5 empty] | 20.947
Sub-Total Materials | 1.906 | 3.095 | 1.975 | [5 empty] | 6.976
Total Maintenance | 7.029 | 13.539 | 7.355 | [5 empty] | 27.923
Refurbishment
Sub-Total Labour |  |  |  | 11.68 |  |  |  |  | 11.68
Sub-Total Materials |  |  |  | 3.496 |  |  |  |  | 3.496
Total Operational Refurbishment |  |  |  | 15.176 |  |  |  |  | 15.176
New Requirements
Field Support
Field Support |  |  |  |  | 1.022 |  |  |  | 1.022
Other Support |  |  |  |  | 3.892 |  |  |  | 3.892
Direct Charges |  |  |  |  | 2.959 |  |  |  | 2.959
Total Field Support |  |  |  |  | 7.873 |  |  |  | 7.873
Total Network Maintenance | 7.029 | 13.539 | 7.355 | 15.176 | 7.873 | 0 | 0 | 0 | 50.972 | 47.6
Operations
Network Switching | [5 empty] | 5.645 |  |  | 5.645
Asset Monitoring | [5 empty] | 1.667 |  |  | 1.667
NMS Support | [5 empty] | 1.64 |  |  | 1.64
Total Operations | [5 empty] | 8.952 |  |  | 8.952 | 7.87
Total Direct Operations & Maintenance | 7.029 | 13.539 | 7.355 | 15.176 | 7.873 | 8.952 | 0 | 0 | 59.924
Other Controllable
Asset Manager Support
Grid Planning | [6 empty] | 3.672 |  | 3.672
Network Support | [6 empty] | 9.011 |  | 9.011
IT Support | [7 empty] | 5.989 | 5.989
Customer & Regulatory Support | [6 empty] | 5.766 |  | 5.766
Sub-Totals | [6 empty] | 18.449 | 5.989 | 24.438
Corporate Support
Corporate Suppport | [7 empty] | 7.641 | 7.641
Sub-Totals | [7 empty] | 7.641 | 7.641
Insurance
Insurance | [6 empty] | 2.804 |  | 2.804
Sub-Totals | [6 empty] | 2.804 |  | 2.804
Total Other Controllable | 0 | 0 | 0 | 0 | 0 | 0 | 21.253 | 13.63 | 34.883 | 30.217
Summary
Total Labour1 | 5.123 | 10.444 | 5.38 | 11.68 | 4.457 | 8.124 | 16.727 | 12.689 | 74.624
Total Maintenance Materials2 | 1.906 | 3.095 | 1.975 | 3.496 |  |  |  |  | 10.472
Total Other Materials3 |  |  |  |  | 3.414 | 0.828 | 4.525 | 0.94 | 9.707
TOTAL OPEX (exc. Grid Support) | 7.029 | 13.539 | 7.355 | 15.176 | 7.873 | 8.952 | 21.253 | 13.63 | 94.807 | 85.688
Grid Support | [8 empty] | 13.48 | 13.481
Other Allowances | [9 empty] | 3.18
Grand Total | [8 empty] | 108.287 | 102.349
1 Total Labour is the total combination of all labour aspects from all line items.
2Total Maintenance Materials is sourced only from Sub-Total Materials.
3The Total Other Materials are material costs sourced from the opex line items below Field Support.
Labour includes the labour component of both inhouse and external maintenance service providers. Note that labour does not equate to salaries.
Powerlink does not have the actual split between labour and materials for external maintenance service providers, so an allocation based on known splits has been made.

## Historic Opex by Category 06-07
| Home |  | Link to Opex instructions - Table 6.1
1.7 HISTORIC OPEX by expenditure category
Year Ended 30 June 2007
($m, nominal) - estimate | Year Ended 30 June 2007
| Field Maintenance |  |  | Operational Refurbishment |  | Network Monitoring & Control | Support / Corporate
| Routine | Condition-Based | Corrective |  | Maintenance Support |  | Network | Non-Network | TOTAL | Revenue Cap Allowance | Key cost drivers and explanation for material differences over time
Direct Operations & Maintenance
Maintenance
Communications
Labour | 0.353 | 0.541 | 0.539 | [5 empty] | 1.433
Materials | 0.108 | 0.166 | 0.165 | [5 empty] | 0.439
Sub-Totals | 0.461 | 0.707 | 0.704 | [5 empty] | 1.872
Lines
Labour | 1.183 | 2.404 | 0.764 | [5 empty] | 4.351
Materials | 0.475 | 0.965 | 0.307 | [5 empty] | 1.747
Sub-Totals | 1.658 | 3.369 | 1.071 | [5 empty] | 6.098
Secondary Systems
Labour | 1.404 | 0.715 | 1.527 | [5 empty] | 3.646
Materials | 0.121 | 0.062 | 0.132 | [5 empty] | 0.315
Sub-Totals | 1.525 | 0.777 | 1.659 | [5 empty] | 3.961
Substations
Labour | 3.105 | 2.109 | 3.487 | [5 empty] | 8.701
Materials | 1.315 | 0.893 | 1.476 | [5 empty] | 3.684
Sub-Totals | 4.42 | 3.002 | 4.963 | [5 empty] | 12.385
Easements
Labour |  | 6.208 | [6 empty] | 6.208
Materials |  | 1.209 | [6 empty] | 1.209
Sub-Totals |  | 7.417 | [6 empty] | 7.417
Summary
Sub-Total Labour | 6.045 | 11.977 | 6.317 | [5 empty] | 24.339
Sub-Total Materials | 2.019 | 3.295 | 2.08 | [5 empty] | 7.394
Total Maintenance | 8.064 | 15.272 | 8.397 | [5 empty] | 31.733
Refurbishment
Sub-Total Labour |  |  |  | 13.561 |  |  |  |  | 13.561
Sub-Total Materials |  |  |  | 4.058 |  |  |  |  | 4.058
Total Operational Refurbishment |  |  |  | 17.619 |  |  |  |  | 17.619
New Requirements | 0.648 | 0.648 | 0.648
Field Support
Field Support |  |  |  |  | 1.147 |  |  |  | 1.147
Other Support |  |  |  |  | 4.303 |  |  |  | 4.303
Direct Charges |  |  |  |  | 3.126 |  |  |  | 3.126
Total Field Support |  |  |  |  | 8.576 |  |  |  | 8.576
Total Network Maintenance | 8.712 | 15.92 | 9.045 | 17.619 | 8.576 | 0 | 0 | 0 | 59.872 | 51.19
Operations
Network Switching | [5 empty] | 6.098 |  |  | 6.098
Asset Monitoring | [5 empty] | 1.8 |  |  | 1.8
NMS Support | [5 empty] | 1.771 |  |  | 1.771
Total Operations | [5 empty] | 9.669 |  |  | 9.669 | 8.29
Total Direct Operations & Maintenance | 8.712 | 15.92 | 9.045 | 17.619 | 8.576 | 9.669 | 0 | 0 | 69.541
Other Controllable
Asset Manager Support
Grid Planning | [6 empty] | 3.949 |  | 3.949
Network Support | [6 empty] | 9.69 |  | 9.69
IT Support | [7 empty] | 6.441 | 6.441
Customer & Regulatory Support | [6 empty] | 5.874 |  | 5.874
Sub-Totals | [6 empty] | 19.513 | 6.441 | 25.954
Corporate Support
Corporate Suppport | [7 empty] | 8.06 | 8.06
Sub-Totals | [7 empty] | 8.06 | 8.06
Insurance
Insurance | [6 empty] | 3.456 |  | 3.456
Sub-Totals | [6 empty] | 3.456 |  | 3.456
Total Other Controllable | 0 | 0 | 0 | 0 | 0 | 0 | 22.969 | 14.501 | 37.47 | 31.352
Summary
Total Labour1 | 6.5375 | 12.4695 | 6.8095 | 13.561 | 4.978 | 8.813 | 17.764 | 13.532 | 84.4644
Total Maintenance Materials2 | 2.1745 | 3.4505 | 2.2355 | 4.058 |  |  |  |  | 11.9186
Total Other Materials3 |  |  |  |  | 3.6 | 0.856 | 5.205 | 0.967 | 10.628
TOTAL OPEX (exc. Grid Support) | 8.712 | 15.92 | 9.045 | 17.619 | 8.576 | 9.669 | 22.969 | 14.501 | 107.011 | 90.837
Grid Support | [8 empty] | 16.38 | 16.382
Other Allowances | [9 empty] | 3.254
Grand Total | [8 empty] | 123.391 | 110.473
1 Total Labour is the total combination of all labour aspects from all line items.
2Total Maintenance Materials is sourced only from Sub-Total Materials.
3The Total Other Materials are material costs sourced from the opex line items below Field Support.
Labour includes the labour component of both inhouse and external maintenance service providers. Note that labour does not equate to salaries.
Powerlink does not have the actual split between labour and materials for external maintenance service providers, so an allocation based on known splits has been made.

## Forecast Opex Summary
|  | Home |  | Link to Opex instructions - Table 6.1 |  |  | Link to Opex Commentary - Table 5.1
2.1 FORECAST OPEX by expenditure category
$ million, real (06/07) | Financial year | 2007/08 | 2008/09 | 2009/10 | 2010/11 | 2011/12 | Total | Key cost drivers and explanation for material differences over time
Direct Operations & Maintenance
Maintenance
Communications
Labour |  | 1.585 | 1.893 | 2.158 | 2.287 | 2.572 | 10.495
Materials |  | 0.479 | 0.563 | 0.631 | 0.658 | 0.729 | 3.06
Sub-Totals |  | 2.064 | 2.456 | 2.789 | 2.945 | 3.301 | 13.555
Lines
Labour |  | 4.703 | 4.954 | 5.24 | 5.535 | 5.852 | 26.284
Materials |  | 1.855 | 1.924 | 2.004 | 2.08 | 2.171 | 10.034
Sub-Totals |  | 6.558 | 6.878 | 7.244 | 7.615 | 8.023 | 36.318
Secondary Systems
Labour |  | 3.972 | 4.234 | 4.49 | 4.877 | 5.441 | 23.014
Materials |  | 0.337 | 0.354 | 0.369 | 0.393 | 0.434 | 1.887
Sub-Totals |  | 4.309 | 4.588 | 4.859 | 5.27 | 5.875 | 24.901
Substations
Labour |  | 9.585 | 10.672 | 11.567 | 12.433 | 13.3 | 57.557
Materials |  | 3.988 | 4.373 | 4.666 | 4.941 | 5.204 | 23.172
Sub-Totals |  | 13.573 | 15.045 | 16.233 | 17.374 | 18.504 | 80.729
Easements
Labour |  | 7.117 | 7.795 | 8.565 | 9.397 | 10.312 | 43.186
Materials |  | 1.189 | 1.282 | 1.387 | 1.499 | 1.62 | 6.977
Sub-Totals |  | 8.306 | 9.077 | 9.952 | 10.896 | 11.932 | 50.163
Summary
Sub-Total Labour |  | 26.962 | 29.548 | 32.02 | 34.529 | 37.477 | 160.536
Sub-Total Materials |  | 7.848 | 8.496 | 9.057 | 9.571 | 10.158 | 45.13
Total Maintenance |  | 34.81 | 38.044 | 41.077 | 44.1 | 47.635 | 205.666
Refurbishment
Sub-Total Labour |  | 14.798 | 15.642 | 16.534 | 17.477 | 18.473 | 82.924
Sub-Total Materials |  | 3.798 | 3.953 | 4.115 | 4.283 | 4.458 | 20.607
Total Operational Refurbishment |  | 18.596 | 19.595 | 20.649 | 21.76 | 22.931 | 103.531
New Requirements |  | 1.866 | 1.938 | 2.01 | 2.079 | 2.154 | 10.047
Field Support
Field Support |  | 1.199 | 1.248 | 1.298 | 1.349 | 1.404 | 6.498
Other Support |  | 4.499 | 4.685 | 4.872 | 5.064 | 5.269 | 24.389
Direct Charges |  | 3.354 | 3.562 | 3.755 | 3.942 | 4.146 | 18.759
Total Field Support |  | 9.052 | 9.495 | 9.925 | 10.355 | 10.819 | 49.646
Total Network Maintenance |  | 64.324 | 69.072 | 73.661 | 78.294 | 83.539 | 368.89 | Forecast increases in Network Maintenance costs are expected from network growth, maintaining wage parity, increased costs of materials, increased vagetation management and safety compliance costs, and increased costs in obtaining access to the network.
Operations
Network Switching |  | 6.374 | 6.638 | 6.903 | 7.175 | 7.464 | 34.554
Asset Monitoring |  | 1.882 | 1.96 | 2.038 | 2.118 | 2.204 | 10.202
NMS Support |  | 1.851 | 1.928 | 2.005 | 2.084 | 2.168 | 10.036
Total Operations |  | 10.107 | 10.526 | 10.946 | 11.377 | 11.836 | 54.792 | Operations costs.will be driven by significant increase in the size and complexity of the network in conjunction with the cost of maintaiining wage parity.
Total Direct Operations & Maintenance |  | 74.431 | 79.598 | 84.607 | 89.671 | 95.375 | 423.682
Other Controllable
Asset Manager Support
Grid Planning |  | 4.082 | 4.209 | 4.338 | 4.47 | 4.608 | 21.707
Network Support |  | 10.018 | 10.33 | 10.645 | 10.969 | 11.308 | 53.27
IT Support |  | 6.658 | 6.865 | 7.075 | 7.29 | 7.516 | 35.404
Customer & Regulatory Support |  | 4.246 | 4.378 | 5.321 | 8.239 | 5.924 | 28.108
Sub-Totals |  | 25.004 | 25.782 | 27.379 | 30.968 | 29.356 | 138.489
Corporate Support
Corporate Suppport |  | 8.239 | 8.409 | 8.578 | 8.75 | 8.933 | 42.909
Sub-Totals |  | 8.239 | 8.409 | 8.578 | 8.75 | 8.933 | 42.909
Insurance | [6 empty] | 0
Insurance |  | 4.928 | 5.103 | 5.283 | 5.45 | 5.6 | 26.364
Total Other Controllable |  | 38.171 | 39.294 | 41.24 | 45.168 | 43.889 | 207.762
Summary
Total Labour1 |  | 88.3338 | 93.3743 | 99.1157 | 106.7958 | 110.2486 | 497.8682
Total Maintenance Materials2 |  | 12.0752 | 12.8947 | 13.6343 | 14.3322 | 15.1114 | 68.0478
Total Other Materials3 |  | 12.196 | 12.62 | 13.1 | 13.709 | 13.905 | 65.53
TOTAL OPEX (exc. Grid Support) |  | 112.602 | 118.892 | 125.847 | 134.839 | 139.264 | 631.444 | The major drivers of Network Maintenance costs are anticipated to be: - Network growth - Wage Parity - Increased material costs - Vagetation Management costs - Network access
Grid Support |  | 24.03 | 17.34 | 22.15 | 8.22 | 8.3 | 80.04
Other Allowances |  | 15.06 | 14.37 | 14.45 | 14.57 | 13.96 | 72.41
Grand Total |  | 151.692 | 150.602 | 162.447 | 157.629 | 161.524 | 783.894
1 Total Labour is the total combination of all labour aspects from all line items. |  | 3.596 | 3.621 | 3.644 | 3.667 | 3.691
2Total Maintenance Materials is sourced only from Sub-Total Materials.
3The Total Other Materials are material costs sourced from the opex line items below Field Support.
Labour includes the labour component of both inhouse and external maintenance service providers. Note that labour does not equate to salaries.
Powerlink does not have the actual split between labour and materials for external maintenance service providers, so an allocation based on known splits has been made.
Field Support, Operations and Other controllable will be split into labour/other materials, the materials component of these items will be small.

## Forecast Opex by Category 07-08
| Home |  | Link to Opex instructions - Table 6.1 |  |  |  | Link to Opex Commentary - Table 5.1
2.2 FORECAST OPEX by expenditure category
Year Ended 30 June 2008
Year Ended 30 June 2008
| Field Maintenance |  |  | Operational Refurbishment |  | Network Monitoring & Control | Support / Corporate
$ million, real (06/07) | Routine | Condition-Based | Corrective |  | Maintenance Support |  | Network | Non-Network | TOTAL | Key cost drivers and explanation for material differences over time
Direct Operations & Maintenance
Maintenance
Communications
Labour | 0.397 | 0.582 | 0.606 | [5 empty] | 1.585
Materials | 0.12 | 0.176 | 0.183 | [5 empty] | 0.479
Sub-Totals | 0.517 | 0.758 | 0.789 | [5 empty] | 2.064
Lines
Labour | 1.299 | 2.565 | 0.839 | [5 empty] | 4.703
Materials | 0.512 | 1.012 | 0.331 | [5 empty] | 1.855
Sub-Totals | 1.811 | 3.577 | 1.17 | [5 empty] | 6.558
Secondary Systems
Labour | 1.542 | 0.752 | 1.678 | [5 empty] | 3.972
Materials | 0.131 | 0.064 | 0.142 | [5 empty] | 0.337
Sub-Totals | 1.673 | 0.816 | 1.82 | [5 empty] | 4.309
Substations
Labour | 3.443 | 2.309 | 3.833 | [5 empty] | 9.585
Materials | 1.432 | 0.961 | 1.595 | [5 empty] | 3.988
Sub-Totals | 4.875 | 3.27 | 5.428 | [5 empty] | 13.573
Easements
Labour |  | 7.117 | [6 empty] | 7.117
Materials |  | 1.189 | [6 empty] | 1.189
Sub-Totals |  | 8.306 | [6 empty] | 8.306
Summary
Sub-Total Labour | 6.681 | 13.325 | 6.956 | [5 empty] | 26.962
Sub-Total Materials | 2.195 | 3.402 | 2.251 | [5 empty] | 7.848
Total Maintenance | 8.876 | 16.727 | 9.207 | [5 empty] | 34.81
Refurbishment
Sub-Total Labour |  |  |  | 14.798 |  |  |  |  | 14.798
Sub-Total Materials |  |  |  | 3.798 |  |  |  |  | 3.798
Total Operational Refurbishment |  |  |  | 18.596 |  |  |  |  | 18.596
New Requirements | 0.622 | 0.622 | 0.622 | [5 empty] | 1.866
Field Support
Field Support |  |  |  |  | 1.199 |  |  |  | 1.199
Other Support |  |  |  |  | 4.499 |  |  |  | 4.499
Direct Charges |  |  |  |  | 3.354 |  |  |  | 3.354
Total Field Support |  |  |  |  | 9.052 |  |  |  | 9.052
| 9.498 | 17.349 | 9.829 | 18.596 | 9.052 | 0 | 0 | 0 | 64.324
Operations
Network Switching | [5 empty] | 6.374 |  |  | 6.374
Asset Monitoring | [5 empty] | 1.882 |  |  | 1.882
NMS Support | [5 empty] | 1.851 |  |  | 1.851
Total Operations | [5 empty] | 10.107 |  |  | 10.107
Total Direct Operations & Maintenance | 9.498 | 17.349 | 9.829 | 18.596 | 9.052 | 10.107 | 0 | 0 | 74.431
Other Controllable
Asset Manager Support
Grid Planning | [6 empty] | 4.082 |  | 4.082
Network Support | [6 empty] | 10.018 |  | 10.018
IT Support | [7 empty] | 6.658 | 6.658
Customer & Regulatory Support | [6 empty] | 4.246 |  | 4.246
Sub-Totals | [6 empty] | 18.346 | 6.658 | 25.004
Corporate Support
Corporate Suppport | [7 empty] | 8.239 | 8.239
Sub-Totals | [7 empty] | 8.239 | 8.239
Insurance
Insurance | [6 empty] | 4.928 |  | 4.928
Sub-Totals | [6 empty] | 4.928 |  | 4.928
Total Other Controllable | 0 | 0 | 0 | 0 | 0 | 0 | 23.274 | 14.897 | 38.171
Summary
Total Labour1 | 7.1599 | 13.8039 | 7.4349 | 14.798 | 5.217 | 9.236 | 16.763 | 13.921 | 88.3338
Total Maintenance Materials2 | 2.3381 | 3.5451 | 2.3941 | 3.798 |  |  |  |  | 12.0752
Total Other Materials3 |  |  |  |  | 3.836 | 0.872 | 6.512 | 0.976 | 12.196
TOTAL OPEX (exc. Grid Support) | 9.498 | 17.349 | 9.829 | 18.596 | 9.052 | 10.107 | 23.274 | 14.897 | 112.602
Grid Support | [8 empty] | 24.03
Other Allowances | [8 empty] | 15.06
Grand Total | [8 empty] | 151.692
1 Total Labour is the total combination of all labour aspects from all line items.
2Total Maintenance Materials is sourced only from Sub-Total Materials.
3The Total Other Materials are material costs sourced from the opex line items below Field Support.
Labour includes the labour component of both inhouse and external maintenance service providers. Note that labour does not equate to salaries.
Powerlink does not have the actual split between labour and materials for external maintenance service providers, so an allocation based on known splits has been made.
Field Support, Operations and Other controllable will be split into labour/other materials, the materials component of these items will be small.

## Forecast Opex by Category 08-09
| Home |  | Link to Opex instructions - Table 6.1 |  |  |  | Link to Opex Commentary - Table 5.1
2.3 FORECAST OPEX by expenditure category
Year Ended 30 June 2009
Year Ended 30 June 2009
| Field Maintenance |  |  | Operational Refurbishment |  | Network Monitoring & Control | Support / Corporate
$ million, real (06/07) | Routine | Condition-Based | Corrective |  | Maintenance Support |  | Network | Non-Network | TOTAL | Key cost drivers and explanation for material differences over time
Direct Operations & Maintenance
Maintenance
Communications
Labour | 0.483 | 0.674 | 0.736 | [5 empty] | 1.893
Materials | 0.144 | 0.2 | 0.219 | [5 empty] | 0.563
Sub-Totals | 0.627 | 0.874 | 0.955 | [5 empty] | 2.456
Lines
Labour | 1.39 | 2.668 | 0.896 | [5 empty] | 4.954
Materials | 0.54 | 1.036 | 0.348 | [5 empty] | 1.924
Sub-Totals | 1.93 | 3.704 | 1.244 | [5 empty] | 6.878
Secondary Systems
Labour | 1.656 | 0.776 | 1.802 | [5 empty] | 4.234
Materials | 0.138 | 0.065 | 0.151 | [5 empty] | 0.354
Sub-Totals | 1.794 | 0.841 | 1.953 | [5 empty] | 4.588
Substations
Labour | 3.856 | 2.556 | 4.26 | [5 empty] | 10.672
Materials | 1.58 | 1.047 | 1.746 | [5 empty] | 4.373
Sub-Totals | 5.436 | 3.603 | 6.006 | [5 empty] | 15.045
Easements
Labour |  | 7.795 | [6 empty] | 7.795
Materials |  | 1.282 | [6 empty] | 1.282
Sub-Totals |  | 9.077 | [6 empty] | 9.077
Summary
Sub-Total Labour | 7.385 | 14.469 | 7.694 | [5 empty] | 29.548
Sub-Total Materials | 2.402 | 3.63 | 2.464 | [5 empty] | 8.496
Total Maintenance | 9.787 | 18.099 | 10.158 | [5 empty] | 38.044
Refurbishment
Sub-Total Labour |  |  |  | 15.642 |  |  |  |  | 15.642
Sub-Total Materials |  |  |  | 3.953 |  |  |  |  | 3.953
Total Operational Refurbishment |  |  |  | 19.595 |  |  |  |  | 19.595
New Requirements | 0.646 | 0.646 | 0.646 | [5 empty] | 1.938
Field Support
Field Support |  |  |  |  | 1.248 |  |  |  | 1.248
Other Support |  |  |  |  | 4.685 |  |  |  | 4.685
Direct Charges |  |  |  |  | 3.562 |  |  |  | 3.562
Total Field Support |  |  |  |  | 9.495 |  |  |  | 9.495
| 10.433 | 18.745 | 10.804 | 19.595 | 9.495 | 0 | 0 | 0 | 69.072
Operations
Network Switching | [5 empty] | 6.638 |  |  | 6.638
Asset Monitoring | [5 empty] | 1.96 |  |  | 1.96
NMS Support | [5 empty] | 1.928 |  |  | 1.928
Total Operations | [5 empty] | 10.526 |  |  | 10.526
Total Direct Operations & Maintenance | 10.433 | 18.745 | 10.804 | 19.595 | 9.495 | 10.526 | 0 | 0 | 79.598
Other Controllable
Asset Manager Support
Grid Planning | [6 empty] | 4.209 |  | 4.209
Network Support | [6 empty] | 10.33 |  | 10.33
IT Support | [7 empty] | 6.865 | 6.865
Customer & Regulatory Support | [6 empty] | 4.378 |  | 4.378
Sub-Totals | [6 empty] | 18.917 | 6.865 | 25.782
Corporate Support
Corporate Suppport | [7 empty] | 8.409 | 8.409
Sub-Totals | [7 empty] | 8.409 | 8.409
Insurance
Insurance | [6 empty] | 5.103 |  | 5.103
Sub-Totals | [6 empty] | 5.103 |  | 5.103
Total Other Controllable | 0 | 0 | 0 | 0 | 0 | 0 | 24.02 | 15.274 | 39.294
Summary
Total Labour1 | 7.8824 | 14.9664 | 8.1914 | 15.642 | 5.443 | 9.638 | 17.321 | 14.29 | 93.3743
Total Maintenance Materials2 | 2.5506 | 3.7786 | 2.6126 | 3.953 |  |  |  |  | 12.8947
Total Other Materials3 |  |  |  |  | 4.051 | 0.888 | 6.699 | 0.982 | 12.62
TOTAL OPEX (exc. Grid Support) | 10.433 | 18.745 | 10.804 | 19.595 | 9.495 | 10.526 | 24.02 | 15.274 | 118.892
Grid Support | [8 empty] | 17.34
Other Allowances | [8 empty] | 14.37
Grand Total | [8 empty] | 150.602
1 Total Labour is the total combination of all labour aspects from all line items.
2Total Maintenance Materials is sourced only from Sub-Total Materials.
3The Total Other Materials are material costs sourced from the opex line items below Field Support.
Labour includes the labour component of both inhouse and external maintenance service providers. Note that labour does not equate to salaries.
Powerlink does not have the actual split between labour and materials for external maintenance service providers, so an allocation based on known splits has been made.
Field Support, Operations and Other controllable will be split into labour/other materials, the materials component of these items will be small.

## Forecast Opex by Category 09-10
| Home |  | Link to Opex instructions - Table 6.1 |  |  |  | Link to Opex Commentary - Table 5.1
2.4 FORECAST OPEX by expenditure category
Year Ended 30 June 2010
Year Ended 30 June 2010
| Field Maintenance |  |  | Operational Refurbishment |  | Network Monitoring & Control | Support / Corporate
$ million, real (06/07) | Routine | Condition-Based | Corrective |  | Maintenance Support |  | Network | Non-Network | TOTAL | Key cost drivers and explanation for material differences over time
Direct Operations & Maintenance
Maintenance
Communications
Labour | 0.56 | 0.747 | 0.851 | [5 empty] | 2.158
Materials | 0.164 | 0.218 | 0.249 | [5 empty] | 0.631
Sub-Totals | 0.724 | 0.965 | 1.1 | [5 empty] | 2.789
Lines
Labour | 1.492 | 2.787 | 0.961 | [5 empty] | 5.24
Materials | 0.571 | 1.066 | 0.367 | [5 empty] | 2.004
Sub-Totals | 2.063 | 3.853 | 1.328 | [5 empty] | 7.244
Secondary Systems
Labour | 1.768 | 0.797 | 1.925 | [5 empty] | 4.49
Materials | 0.145 | 0.066 | 0.158 | [5 empty] | 0.369
Sub-Totals | 1.913 | 0.863 | 2.083 | [5 empty] | 4.859
Substations
Labour | 4.204 | 2.754 | 4.609 | [5 empty] | 11.567
Materials | 1.696 | 1.111 | 1.859 | [5 empty] | 4.666
Sub-Totals | 5.9 | 3.865 | 6.468 | [5 empty] | 16.233
Easements
Labour |  | 8.565 | [6 empty] | 8.565
Materials |  | 1.387 | [6 empty] | 1.387
Sub-Totals |  | 9.952 | [6 empty] | 9.952
Summary
Sub-Total Labour | 8.024 | 15.65 | 8.346 | [5 empty] | 32.02
Sub-Total Materials | 2.576 | 3.848 | 2.633 | [5 empty] | 9.057
Total Maintenance | 10.6 | 19.498 | 10.979 | [5 empty] | 41.077
Refurbishment
Sub-Total Labour |  |  |  | 16.534 |  |  |  |  | 16.534
Sub-Total Materials |  |  |  | 4.115 |  |  |  |  | 4.115
Total Operational Refurbishment |  |  |  | 20.649 |  |  |  |  | 20.649
New Requirements | 0.67 | 0.67 | 0.67 | [5 empty] | 2.01
Field Support
Field Support |  |  |  |  | 1.298 |  |  |  | 1.298
Other Support |  |  |  |  | 4.872 |  |  |  | 4.872
Direct Charges |  |  |  |  | 3.755 |  |  |  | 3.755
Total Field Support |  |  |  |  | 9.925 |  |  |  | 9.925
| 11.27 | 20.168 | 11.649 | 20.649 | 9.925 | 0 | 0 | 0 | 73.661
Operations
Network Switching | [5 empty] | 6.903 |  |  | 6.903
Asset Monitoring | [5 empty] | 2.038 |  |  | 2.038
NMS Support | [5 empty] | 2.005 |  |  | 2.005
Total Operations | [5 empty] | 10.946 |  |  | 10.946
Total Direct Operations & Maintenance | 11.27 | 20.168 | 11.649 | 20.649 | 9.925 | 10.946 | 0 | 0 | 84.607
Other Controllable
Asset Manager Support
Grid Planning | [6 empty] | 4.338 |  | 4.338
Network Support | [6 empty] | 10.645 |  | 10.645
IT Support | [7 empty] | 7.075 | 7.075
Customer & Regulatory Support | [6 empty] | 5.321 |  | 5.321
Sub-Totals | [6 empty] | 20.304 | 7.075 | 27.379
Corporate Support
Corporate Suppport | [7 empty] | 8.578 | 8.578
Sub-Totals | [7 empty] | 8.578 | 8.578
Insurance
Insurance | [6 empty] | 5.283 |  | 5.283
Sub-Totals | [6 empty] | 5.283 |  | 5.283
Total Other Controllable | 0 | 0 | 0 | 0 | 0 | 0 | 25.587 | 15.653 | 41.24
Summary
Total Labour1 | 8.5399 | 16.1659 | 8.8619 | 16.534 | 5.673 | 10.045 | 18.632 | 14.664 | 99.1157
Total Maintenance Materials2 | 2.7301 | 4.0021 | 2.7871 | 4.115 |  |  |  |  | 13.6343
Total Other Materials3 |  |  |  |  | 4.254 | 0.901 | 6.956 | 0.989 | 13.1
TOTAL OPEX (exc. Grid Support) | 11.27 | 20.168 | 11.649 | 20.649 | 9.925 | 10.946 | 25.587 | 15.653 | 125.847
Grid Support | [8 empty] | 22.15
Other Allowances | [8 empty] | 14.45
Grand Total | [8 empty] | 162.447
1 Total Labour is the total combination of all labour aspects from all line items.
2Total Maintenance Materials is sourced only from Sub-Total Materials.
3The Total Other Materials are material costs sourced from the opex line items below Field Support.
Labour includes the labour component of both inhouse and external maintenance service providers. Note that labour does not equate to salaries.
Powerlink does not have the actual split between labour and materials for external maintenance service providers, so an allocation based on known splits has been made.
Field Support, Operations and Other controllable will be split into labour/other materials, the materials component of these items will be small.

## Forecast Opex by Category 10-11
| Home |  | Link to Opex instructions - Table 6.1 |  |  |  | Link to Opex Commentary - Table 5.1
2.5 FORECAST OPEX by expenditure category
Year Ended 30 June 2011
Year Ended 30 June 2011
| Field Maintenance |  |  | Operational Refurbishment |  | Network Monitoring & Control | Support / Corporate
$ million, real (06/07) | Routine | Condition-Based | Corrective |  | Maintenance Support |  | Network | Non-Network | TOTAL | Key cost drivers and explanation for material differences over time
Direct Operations & Maintenance
Maintenance
Communications
Labour | 0.601 | 0.774 | 0.912 | [5 empty] | 2.287
Materials | 0.173 | 0.223 | 0.262 | [5 empty] | 0.658
Sub-Totals | 0.774 | 0.997 | 1.174 | [5 empty] | 2.945
Lines
Labour | 1.599 | 2.907 | 1.029 | [5 empty] | 5.535
Materials | 0.602 | 1.092 | 0.386 | [5 empty] | 2.08
Sub-Totals | 2.201 | 3.999 | 1.415 | [5 empty] | 7.615
Secondary Systems
Labour | 1.933 | 0.838 | 2.106 | [5 empty] | 4.877
Materials | 0.156 | 0.066 | 0.171 | [5 empty] | 0.393
Sub-Totals | 2.089 | 0.904 | 2.277 | [5 empty] | 5.27
Substations
Labour | 4.545 | 2.943 | 4.945 | [5 empty] | 12.433
Materials | 1.806 | 1.17 | 1.965 | [5 empty] | 4.941
Sub-Totals | 6.351 | 4.113 | 6.91 | [5 empty] | 17.374
Easements
Labour |  | 9.397 | [6 empty] | 9.397
Materials |  | 1.499 | [6 empty] | 1.499
Sub-Totals |  | 10.896 | [6 empty] | 10.896
Summary
Sub-Total Labour | 8.678 | 16.859 | 8.992 | [5 empty] | 34.529
Sub-Total Materials | 2.737 | 4.05 | 2.784 | [5 empty] | 9.571
Total Maintenance | 11.415 | 20.909 | 11.776 | [5 empty] | 44.1
Refurbishment
Sub-Total Labour |  |  |  | 17.477 |  |  |  |  | 17.477
Sub-Total Materials |  |  |  | 4.283 |  |  |  |  | 4.283
Total Operational Refurbishment |  |  |  | 21.76 |  |  |  |  | 21.76
New Requirements | 0.693 | 0.693 | 0.693 | [5 empty] | 2.079
Field Support
Field Support |  |  |  |  | 1.349 |  |  |  | 1.349
Other Support |  |  |  |  | 5.064 |  |  |  | 5.064
Direct Charges |  |  |  |  | 3.942 |  |  |  | 3.942
Total Field Support |  |  |  |  | 10.355 |  |  |  | 10.355
| 12.108 | 21.602 | 12.469 | 21.76 | 10.355 | 0 | 0 | 0 | 78.294
Operations
Network Switching | [5 empty] | 7.175 |  |  | 7.175
Asset Monitoring | [5 empty] | 2.118 |  |  | 2.118
NMS Support | [5 empty] | 2.084 |  |  | 2.084
Total Operations | [5 empty] | 11.377 |  |  | 11.377
Total Direct Operations & Maintenance | 12.108 | 21.602 | 12.469 | 21.76 | 10.355 | 11.377 | 0 | 0 | 89.671
Other Controllable
Asset Manager Support
Grid Planning | [6 empty] | 4.47 |  | 4.47
Network Support | [6 empty] | 10.969 |  | 10.969
IT Support | [7 empty] | 7.29 | 7.29
Customer & Regulatory Support | [6 empty] | 8.239 |  | 8.239
Sub-Totals | [6 empty] | 23.678 | 7.29 | 30.968
Corporate Support
Corporate Suppport | [7 empty] | 8.75 | 8.75
Sub-Totals | [7 empty] | 8.75 | 8.75
Insurance
Insurance | [6 empty] | 5.45 |  | 5.45
Sub-Totals | [6 empty] | 5.45 |  | 5.45
Total Other Controllable | 0 | 0 | 0 | 0 | 0 | 0 | 29.128 | 16.04 | 45.168
Summary
Total Labour1 | 9.2116 | 17.3926 | 9.5256 | 17.477 | 5.908 | 10.462 | 21.773 | 15.046 | 106.7958
Total Maintenance Materials2 | 2.8964 | 4.2094 | 2.9434 | 4.283 |  |  |  |  | 14.3322
Total Other Materials3 |  |  |  |  | 4.446 | 0.915 | 7.354 | 0.994 | 13.709
TOTAL OPEX (exc. Grid Support) | 12.108 | 21.602 | 12.469 | 21.76 | 10.355 | 11.377 | 29.128 | 16.04 | 134.839
Grid Support | [8 empty] | 8.22
Other Allowances | [8 empty] | 14.57
Grand Total | [8 empty] | 157.629
1 Total Labour is the total combination of all labour aspects from all line items.
2Total Maintenance Materials is sourced only from Sub-Total Materials.
3The Total Other Materials are material costs sourced from the opex line items below Field Support.
Labour includes the labour component of both inhouse and external maintenance service providers. Note that labour does not equate to salaries.
Powerlink does not have the actual split between labour and materials for external maintenance service providers, so an allocation based on known splits has been made.
Field Support, Operations and Other controllable will be split into labour/other materials, the materials component of these items will be small.

## Forecast Opex by Category 11-12
| Home |  | Link to Opex instructions - Table 6.1 |  |  |  | Link to Opex Commentary - Table 5.1
2.6 FORECAST OPEX by expenditure category
Year Ended 30 June 2012
Year Ended 30 June 2012
| Field Maintenance |  |  | Operational Refurbishment |  | Network Monitoring & Control | Support / Corporate
$ million, real (06/07) | Routine | Condition-Based | Corrective |  | Maintenance Support |  | Network | Non-Network | TOTAL | Key cost drivers and explanation for material differences over time
Direct Operations & Maintenance
Maintenance
Communications
Labour | 0.685 | 0.849 | 1.038 | [5 empty] | 2.572
Materials | 0.194 | 0.241 | 0.294 | [5 empty] | 0.729
Sub-Totals | 0.879 | 1.09 | 1.332 | [5 empty] | 3.301
Lines
Labour | 1.714 | 3.036 | 1.102 | [5 empty] | 5.852
Materials | 0.636 | 1.126 | 0.409 | [5 empty] | 2.171
Sub-Totals | 2.35 | 4.162 | 1.511 | [5 empty] | 8.023
Secondary Systems
Labour | 2.17 | 0.905 | 2.366 | [5 empty] | 5.441
Materials | 0.173 | 0.072 | 0.189 | [5 empty] | 0.434
Sub-Totals | 2.343 | 0.977 | 2.555 | [5 empty] | 5.875
Substations
Labour | 4.888 | 3.132 | 5.28 | [5 empty] | 13.3
Materials | 1.913 | 1.225 | 2.066 | [5 empty] | 5.204
Sub-Totals | 6.801 | 4.357 | 7.346 | [5 empty] | 18.504
Easements
Labour |  | 10.312 | [6 empty] | 10.312
Materials |  | 1.62 | [6 empty] | 1.62
Sub-Totals |  | 11.932 | [6 empty] | 11.932
Summary
Sub-Total Labour | 9.457 | 18.234 | 9.786 | [5 empty] | 37.477
Sub-Total Materials | 2.916 | 4.284 | 2.958 | [5 empty] | 10.158
Total Maintenance | 12.373 | 22.518 | 12.744 | [5 empty] | 47.635
Refurbishment
Sub-Total Labour |  |  |  | 18.473 |  |  |  |  | 18.473
Sub-Total Materials |  |  |  | 4.458 |  |  |  |  | 4.458
Total Operational Refurbishment |  |  |  | 22.931 |  |  |  |  | 22.931
New Requirements | 0.718 | 0.718 | 0.718 | [5 empty] | 2.154
Field Support
Field Support |  |  |  |  | 1.404 |  |  |  | 1.404
Other Support |  |  |  |  | 5.269 |  |  |  | 5.269
Direct Charges |  |  |  |  | 4.146 |  |  |  | 4.146
Total Field Support |  |  |  |  | 10.819 |  |  |  | 10.819
| 13.091 | 23.236 | 13.462 | 22.931 | 10.819 | 0 | 0 | 0 | 83.539
Operations
Network Switching | [5 empty] | 7.464 |  |  | 7.464
Asset Monitoring | [5 empty] | 2.204 |  |  | 2.204
NMS Support | [5 empty] | 2.168 |  |  | 2.168
Total Operations | [5 empty] | 11.836 |  |  | 11.836
Total Direct Operations & Maintenance | 13.091 | 23.236 | 13.462 | 22.931 | 10.819 | 11.836 | 0 | 0 | 95.375
Other Controllable
Asset Manager Support
Grid Planning | [6 empty] | 4.608 |  | 4.608
Network Support | [6 empty] | 11.308 |  | 11.308
IT Support | [7 empty] | 7.516 | 7.516
Customer & Regulatory Support | [6 empty] | 5.924 |  | 5.924
Sub-Totals | [6 empty] | 21.84 | 7.516 | 29.356
Corporate Support
Corporate Suppport | [7 empty] | 8.933 | 8.933
Sub-Totals | [7 empty] | 8.933 | 8.933
Insurance
Insurance | [6 empty] | 5.6 |  | 5.6
Sub-Totals | [6 empty] | 5.6 |  | 5.6
Total Other Controllable | 0 | 0 | 0 | 0 | 0 | 0 | 27.44 | 16.449 | 43.889
Summary
Total Labour1 | 10.0099 | 18.7869 | 10.3389 | 18.473 | 6.159 | 10.908 | 20.126 | 15.447 | 110.2486
Total Maintenance Materials2 | 3.0811 | 4.4491 | 3.1231 | 4.458 |  |  |  |  | 15.1114
Total Other Materials3 |  |  |  |  | 4.659 | 0.93 | 7.314 | 1.002 | 13.905
TOTAL OPEX (exc. Grid Support) | 13.091 | 23.236 | 13.462 | 22.931 | 10.819 | 11.836 | 27.44 | 16.449 | 139.264
Grid Support | [8 empty] | 8.3
Other Allowances | [8 empty] | 13.96
Grand Total | [8 empty] | 161.524
1 Total Labour is the total combination of all labour aspects from all line items.
2Total Maintenance Materials is sourced only from Sub-Total Materials.
3The Total Other Materials are material costs sourced from the opex line items below Field Support.
Labour includes the labour component of both inhouse and external maintenance service providers. Note that labour does not equate to salaries.
Powerlink does not have the actual split between labour and materials for external maintenance service providers, so an allocation based on known splits has been made.
Field Support, Operations and Other controllable will be split into labour/other materials, the materials component of these items will be small.

## Historic Capex by Category
3.1 HISTORIC CAPEX by project category |  |  | Home |  |  |  | Link to Historic Capex Instructions - Table 6.2 |  |  |  | Link to Historic Capex Commentary - Table 5.2
($m, nominal & exclusive of FDC)
Project Category |  |  |  | 2001/02 | 2002 | 2002/03 | 2003/04 | 2004/05 | 2005/06* | 2006/07* | TOTAL
(6 months)
NETWORK
LOAD DRIVEN | Augmentation |  |  | 84.04 | 31.817 | 99.272 | 100.142 | 129.801 | 153.999 | 88.992 | 656.246
| Easements |  |  | 4.874 | 1.924 | 2.402 | 3.004 | 14.492 | 19.73 | 22.99 | 67.492
| Connections |  |  | 10.925 | 8.231 | 31.411 | 10.542 | 5.723 | 9.46 | 18.378 | 86.439
| Other |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
NON-LOAD DRIVEN | Replacements |  |  | 7.017 | 5.246 | 13.16 | 9.484 | 14.045 | 25.736 | 94.983 | 164.425
| Security/Compliance |  |  | 0.4 | 0.4 | 0.019 | 1.108 | 0.004 | 1.094 | 2.892 | 5.517
| Other |  |  | 14.992 | 9.483 | 18.357 | 10.657 | 16.142 | 6.737 | 5.341 | 72.226
NON NETWORK
BUSINESS IT |  | Information Technology |  | 2.609 | 1.915 | 7.469 | 2.776 | 2.112 | 10.626 | 6.629 | 32.221
SUPPORT THE BUSINESS |  | Commercial Buildings |  | 0.211 | 0.211 | 3.371 | 5.006 | 0.931 | 19.35 | 6.446 | 35.315
|  | Motor Vehicles |  | 0.873 | 0.505 | 1.481 | 2.095 | 1.534 | 2.975 | 4.094 | 13.052
|  | Tools |  | 2.433 | 2.416 | 1.109 | 0.803 | 2.514 | 2.334 | 2.177 | 11.37
Subtotal historic capex (excluding FDC) |  |  |  | 128.374 | 62.148 | 178.051 | 145.617 | 187.298 | 252.041 | 252.922 | 1144.303
FDC |  |  |  | 14.887 | 6.557 | 20.217 | 17.359 | 22.097 | 26.674 | 28.572 | 129.806
TOTAL HISTORIC CAPEX |  |  |  | 143.261 | 68.705 | 198.268 | 162.976 | 209.395 | 278.715 | 281.494 | 1274.109
Note these values are based on capitalisations. | [8 empty] | *Note that values in these columns are estimates only

## Hist Capex by Asset Class
3.2 HISTORIC CAPEX by asset class | Home |  |  | Link to Capex Instructions - Table 6.2
($m, nominal) | 2001/02 |  |  | 2002 (6 months) |  |  | 2002/03 |  |  | 2003/04 |  |  | 2004/05 |  |  | 2005/06* |  |  | 2006/07* |  |  | TOTAL
Asset class
| Cost | FDC | Subtotal | Cost | FDC | Subtotal | Cost | FDC | Subtotal | Cost | FDC | Subtotal | Cost | FDC | Subtotal | Cost | FDC | Subtotal | Cost | FDC | Subtotal | Cost | FDC | TOTAL
Transmission Lines (steel tower, steel pole, concrete pole) | 41.023 | 5.295 | 46.318 | 5.5656 | 0.693 | 6.2586 | 50.355 | 6.262 | 56.617 | 99.743 | 12.515 | 112.258 | 87.04 | 10.848 | 97.888 | 59.675 | 7.427 | 67.102 | 54.664 | 6.803 | 61.467 | 392.5 | 49.15 | 441.65
Transmission Lines (wood pole) | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0.066 | 0.007 | 0.073 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.066 | 0.007 | 0.073
Transmission Lines (underground) | 2.754 | 0.343 | 3.097 | 2.4146 | 0.3005 | 2.7151 | 2.376 | 0.296 | 2.672 | 0.926 | 0.115 | 1.041 | 0.006 | 0.001 | 0.007 | 0 | 0 | 0 | 91.161 | 0 | 91.161 | 97.223 | 0.755 | 97.978
Substations Primary Plant | 47.188 | 5.849 | 53.037 | 33.6138 | 4.1832 | 37.7971 | 71.248 | 9.043 | 80.291 | 15.185 | 2.195 | 17.38 | 53.489 | 6.84 | 60.329 | 103.622 | 12.896 | 116.518 | 54.872 | 11.345 | 66.217 | 345.604 | 48.168 | 393.772
Substations Secondary Systems | 15.472 | 1.907 | 17.379 | 6.7926 | 0.84534 | 7.6379 | 24.16 | 3.11 | 27.27 | 12.179 | 1.547 | 13.726 | 18.457 | 2.308 | 20.765 | 31.73 | 3.949 | 35.679 | 0 | 6.829 | 6.829 | 101.998 | 19.65 | 121.648
Communications (buildings, towers and site infrastructure) | 0 | 0 | 0 | 0 | 0 | 0 | 0.054 | 0.004 | 0.058 | 0.465 | 0.032 | 0.497 | 0.017 | 0.001 | 0.018 | 0 | 0 | 0 | 12.017 | 0 | 12.017 | 12.553 | 0.037 | 12.59
Communications (other assets) | 6.374 | 0.446 | 6.82 | 5.8827 | 0.40267 | 6.2854 | 6.413 | 0.497 | 6.91 | 4.546 | 0.418 | 4.964 | 1.574 | 0.148 | 1.722 | 5.941 | 0.407 | 6.348 | 0 | 0.823 | 0.823 | 24.848 | 2.739 | 27.587
Network Switching Centres | 1.053 | 0.131 | 1.184 | 0.2687 | 0.018393 | 0.28709 | 1.585 | 0.373 | 1.958 | 0.352 | 0.044 | 0.396 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.99 | 0.548 | 3.538
Land | 5.222 | 0.516 | 5.738 | 1.7278 | 0 | 1.7278 | 0.366 | 0.046 | 0.412 | 2.201 | 0.274 | 2.475 | 0.994 | 0.126 | 1.12 | 0 | 0 | 0 | 22.278 | 0 | 22.278 | 31.061 | 0.962 | 32.023
Easements | 3.223 | 0.401 | 3.624 | 0.91671 | 0.11409 | 1.0308 | 4.604 | 0.586 | 5.19 | 1.346 | 0.212 | 1.558 | 14.665 | 1.825 | 16.49 | 16.04 | 1.996 | 18.036 | 0 | 2.772 | 2.772 | 39.878 | 7.792 | 47.67
Houses | 0 | 0 | 0 | 0 | 0 | 0 | 0.082 | 0 | 0.082 | 0.059 | 0 | 0.059 | 0.068 | 0 | 0.068 | 0 | 0 | 0 | 4.874 | 0 | 4.874 | 5.083 | 0 | 5.083
Commercial Buildings | 0 | 0 | 0 | 0 | 0 | 0 | 2.801 | 0 | 2.801 | 4.739 | 0 | 4.739 | 0.428 | 0 | 0.428 | 18.5 | 0 | 18.5 | 6.629 | 0 | 6.629 | 33.097 | 0 | 33.097
Computer equipment | 2.633 | 0 | 2.633 | 1.9386 | 0 | 1.9386 | 7.483 | 0 | 7.483 | 2.802 | 0 | 2.802 | 3.078 | 0 | 3.078 | 10.626 | 0 | 10.626 | 0.154 | 0 | 0.154 | 26.776 | 0 | 26.776
Office Furniture and Misc | 0.017 | 0 | 0.017 | 0.016789 | 0 | 0.016789 | 0.141 | 0 | 0.141 | 0.141 | 0 | 0.141 | 0.161 | 0 | 0.161 | 0.6 | 0 | 0.6 | 0 | 0 | 0 | 1.06 | 0 | 1.06
Office Machines | 0.204 | 0 | 0.204 | 0.20428 | 0 | 0.20428 | 0.071 | 0 | 0.071 | 0.043 | 0 | 0.043 | 0.051 | 0 | 0.051 | 0 | 0 | 0 | 4.094 | 0 | 4.094 | 4.463 | 0 | 4.463
Vehicles | 2.409 | 0 | 2.409 | 2.0411 | 0 | 2.0411 | 1.6 | 0 | 1.6 | 2.111 | 0 | 2.111 | 1.534 | 0 | 1.534 | 2.975 | 0 | 2.975 | 2.176 | 0 | 2.176 | 12.805 | 0 | 12.805
Moveable Plant | 0.803 | 0 | 0.803 | 0.76596 | 0 | 0.76596 | 1.966 | 0 | 1.966 | 0.55 | 0 | 0.55 | 2.404 | 0 | 2.404 | 2.334 | 0 | 2.334 | 0 | 0 | 0 | 8.057 | 0 | 8.057
Other | 0 | 0 | 0 | 0 | 0 | 0 | 2.747 | 0 | 2.747 | -1.837 | 0 | -1.837 | 3.332 | 0 | 3.332 | 0 | 0 | 0 | 0 | 0 | 0 | 4.242 | 0 | 4.242
TOTAL CAPEX | 128.375 | 14.888 | 143.263 | 62.1492 | 6.5572 | 68.7065 | 178.052 | 20.217 | 198.269 | 145.617 | 17.359 | 162.976 | 187.298 | 22.097 | 209.395 | 252.043 | 26.675 | 278.718 | 252.919 | 28.572 | 281.491 | 1144.304 | 129.808 | 1274.112
Note that these values are based on capitalisations | [15 empty] | *Note that values in these columns are estimates only

## Hist Capex - Network
3.3 HISTORIC CAPEX - NETWORK - by project
[5 empty] | Home |  |  | Link to Historic Capex Instructions - Table 6.2 |  |  | Link to Historic Capex Commentary - Table 5.2
($m, nominal)
Yearly capitalisations by project (exclusive of FDC)
Project ID | Project Name | Commissioning Date | Category^ |  | 2002 (6 mths) | 2002/03 | 2003/04 | 2004/05 | 2005/06* | 2006/07* | TOTAL | REASON FOR PROJECT | Business Case (Y/N) | Business Case Cost Estimate | Reason for Variance from Cost Estimate / Expected Commissioning Date
CP.00771 | Belmont 275kV Line Reinforcement | 2004-01-08 | Augmentation |  |  | 2.049 | 71.785 | 4.823 | 2.476 |  | 81.133 | Reliability | Reg Test | $63.8m ($2001/02) $66.2m (escal) | Additional environmental requirements and delays in project delivery due to property owner legal action impacting on access to site for construction. Project confirmed to satisfy Reg Test at outturn cost.
CP.00762 | Darling Downs Transmission Reinforcement | 2005-04-01 | Augmentation |  |  |  |  | 67.811 | 13.125 |  | 80.936 | Reliability | Reg Test | $71.3m ($2002/03) $73.0m (escal) | Prolongation costs due to: protracted legal challenges delaying access to site, complex and extended public consultation and Reg Test, and fatal construction accident. Project confirmed to satisfy Reg Test at outturn cost.
CP.01002 | Gold Coast Transmission Reinforcement | 2006-10-01 | Augmentation | [5 empty] | 22.333 | 45.835 | 68.168 | Reliability | Reg Test | $45.4m ($2003/04) $46.9m (escal) | Access to site delays for vegetation clearing to enable construction resulting in acceleration costs. Higher project costs due to increases in construction input costs, eg. Labour, steel, aluminium, contractor margins, etc. Project confirmed to satisfy Reg Test at forecast outturn cost.
CP.01094 | Belmont-Murarrie Transmission Line Reinforcement | 2006-10-01 | Augmentation | [5 empty] | 39.925 | 7.765 | 47.69 | Reliability | Reg Test | $39.5m ($2003/04) $42.6m (escal) | Higher project costs due to increases in construction input costs, eg labour, steel, aluminium, contractor margins, etc.
CP.01121 & CP.01038 & CP.01081 | Goodna, Algester and Summner Sub Establishments | 2006-10-01 | Augmentation | [5 empty] | 15.222 | 24.094 | 39.316 | Reliability | Reg Test | $34.9m ($04/05) $35.3m (escal) | Input cost increases.
CP.00753 | Stanwell - Broadsound 275kV Line Reinfor | 2002-11-01 | Augmentation |  |  | 37.122 | 0.198 | 0.051 |  |  | 37.371 | Reliability | Reg Test | $38.8m ($00/01) $39.2m (escal)
CP.00384 | LILYVALE 275KV REINFORCEMENT | 2004-12-01 | Augmentation |  |  |  |  | 25.378 | 0.408 |  | 25.786 | Reliability | Reg Test | $23.1m ($2002/03) $23.8m (escal)
CP.00667 | MOLENDINAR 275KV ESTABLISHMENT | 2003-11-01 | Augmentation |  |  | 4.301 | 18.248 | 0.437 | 0.376 |  | 23.362 | Reliability | Reg Test | $22.9m ($2001/02) $23.8m (escal)
CP.00707 & CP.00742 | Cairns Reinforcement | 2002-04-01 | Augmentation |  | 10.118 | 10.1 | 2.646 | 0.052 |  |  | 22.916 | Reliability | Consultation | $44m (escal) | Prolongation costs and contractor claims resulting from prolonged bad weather.
CP.01136 | Goodna 275kV Substation Establishment | 2006-10-01 | Augmentation | [5 empty] | 15.894 | 4.845 | 20.739 | Reliability | Reg Test | $18.3m ($2004/05) $19.2m (escal)
CP.01142 | Molendinar 110kV Busbar Establishment | 2006-12-01 | Replacement | [6 empty] | 17.01 | 17.01 | Age/obsolescence/condition | Bus Case | $17.2m ($2004/05) $17.6m (escal)
CP.00755 | Murrarie 110kV Establishment | 2003-04-01 | Connection |  | 0.376 | 14.883 | 0.848 | 0.003 | 0.023 |  | 16.133 | Connection | Board Memo | $22.6m ($01/02) $22.8m (escal)
CP.01092 | South Pine 275kV Substation Refurbishment | 2006-08-01 | Replacement | [6 empty] | 15.943 | 15.943 | Age/obsolescence/condition | Bus Case | $13.9m ($2002/03) $14.3m (escal)
CP.00668 | Woree 132kV SVC | 2005-12-01 | Augmentation | [5 empty] | 14.783 | 0.006 | 14.789 | Reliability | Bus Case | $16.9m ($2003/04) $17.8m (escal)
CP.00177 | Gladstone Sth Substation Rebuild | 2003-10-01 | Replacement |  | 3.701 | 4.472 | 5.418 | 0.017 | 0.001 |  | 13.609 | Age/obsolescence/condition | Bus Case | $13.1m ($2000/01) $13.6m (escal)
CP.00836 | Cairns 132kV Substation Rebuild | 2006-10-01 | Replacement | [6 empty] | 12.837 | 12.837 | Age/Obsolescence/Condition | Bus Case | $10.8m ($2003/04) $11.0m (escal) | Cost increase due to increase in contractor costs and additional work associated with complex staging and demolition.
CP.01068 | Middle Ridge 110kV Substation Rebuild & Sec Sys Replacement | 2006-06-01 | Replacement | [5 empty] | 12.783 |  | 12.783 | Age/Obsolescence/Condition | Bus Case | $7.98m ($2002/03) $8.29m (escal) | Changes to scope and implementation strategy due to complexity of in situ replacement and to maintain reliable supply. Project confirmed to be least cost solution. Commissioning delayed due to unavailability of feeders.
CP.00752 | SVC 132kV Secondary Systems Refurbishment | 2008-06-01 | Replacement | [6 empty] | 12.389 | 12.389 | Age/Obsolescence/Condition | Board Memo | $27.6m ($2004/05) $28.9m (escal) | Partial capitalisations for project to be commissioned in 2008.
CP.01199 | QR Mindi Establishment | 2007-02-01 | Connection | [6 empty] | 11.983 | 11.983 | Connection | Bus Case | $11.4m ($2005/06) $11.8m (escal)
CP.00510 | Alan Sherriff 132/11kV Substatn Estab and Garbutt Sub Rebuild | 2003-02-01 | Augmentation & Connection & Replacement |  |  | 3.799 | 0.124 | 7.433 | 0.045 |  | 11.401 | Reliability Age/Obsolescence/Condition | Consultation | $10.84m ($2001/02) $11.13m (escal)
CP.00868 | Strathmore 132kV Reinforcement | 2002-11-01 | Augmentation |  | 1.564 | 8.178 | 0.157 |  |  |  | 9.899 | Reliability | Consultation | $8.8m ($1999/00) $9.4m (escal)
CP.00525 | EDMONTON 132KV ESTABLISHMENT | 2005-01-01 | Augmentation & Connection |  |  |  | 0.187 | 9.407 | 0.082 |  | 9.676 | Reliability/Connection | Reg Test | $8.5m (2002/03 $8.76m (escal) | Late delivery of transformers resulted in increased commissioning costs and delay in commissioning.
CP.00891 | Nebo 275kV Transformer Augmentation | 2005-11-01 | Augmentation |  |  |  |  | 3.78 | 5.873 | 0.01 | 9.663 | Reliability | Reg Test APR | $7.7m (2002/03) $8.0m (escal) | Higher project costs due to increases in construction input costs, eg labour, steel, aluminium, contractor margins, etc.
CP.01034 | Millmerran - Middle Ridge Easement Acq | 2004-02-01 | Easement |  |  |  |  | 7.076 | 1.203 |  | 8.279 | Reliability - Demand Growth | Bus Case | $4.85m (escal) | Cost overrun and delay in designation due to partial realignment of route.
CP.00837 | Ingham 132kV Substation Rebuild | 2005-05-01 | Replacement |  |  |  |  | 6.415 | 1.234 |  | 7.649 | Age/Obsolescence/Condition | Bus Case | $6.2m ($2002/03) $6.4m (escal) | Cost over-runs primarily due to change to scope of communications facility to improve visual amenity and reduce reliance on aged equipment.
CP.00704 | Springdale-Tarong Easement Acquisition | 2006-09-01 | Easement | [6 empty] | 7.175 | 7.175 | Strategic Easement | Board Memo | $8.2m (escal) | Designation delayed as no confirmation on construction timing.
CP.00567 | Rocklea 275kV Transformer Augmentation | 2002-03-01 | Augmentation |  | 4.705 | 1.442 | 0.741 | 0.032 | 0.204 |  | 7.124 | Reliability | Reg Test APR | $7.7m ($1999/00) $7.9m (escal)
CP.00359 | QAL West 132kV Substation Establishment | 2002-11-01 | Connection |  |  | 6.901 | 0.207 |  |  |  | 7.108 | Connection | Bus Case | $7.02m ($2001/02) $7.06m (escal)
CP.01246 | Mackay - Proserpine Line Refurb | 2007-02-01 | Replacement | [6 empty] | 7.071 | 7.071 | Age/Obsolescence/Condition | Bus Case | $5.0m ($2005/06) $5.3m (escal) | Input cost increases.
CP.00892 | Loganlea 2nd 275kV Transformer | 2002-11-01 | Augmentation |  |  | 0.213 | 0.043 | 4.105 | 2.378 |  | 6.739 | Reliability | Reg Test - APR | $8.89m (escal)
CP.00055 | Woolooga Transformer Reinforcement | 2003-06-01 | Augmentation |  | 0.207 | 6.145 | 0.141 | 0.014 |  |  | 6.507 | Reliability | Reg Test APR | $5.9m ($2000/01) $6.21m (escal)
CP.00463 | Bulli Creek 330/132kV Extension (Goondiwindi) | 2004-02-01 | Connection |  |  | 3.121 | 3.198 | 0.132 | 0.055 |  | 6.506 | Connection | Bus Case | $5.98m ($2001/02) $6.17m (escal) | Powerlink conductors erected and ready for commissionig on time. However, delays caused by connection of distribution line.
CP.00615 | Palmwoods Transformer Reinforcement | 2003-07-01 | Augmentation |  |  | 6.34 | -0.041 | 0.004 | 0.046 |  | 6.349 | Reliability | Reg Test APR | $5.8m ($2000/01) $6.1m (escal) | Delay in commissioning due to late delivery of transformer and access limitations for protection alterations.
CP.01042 | Ross - Chalumbin 275kV Line Switching | 2006-06-01 | Other |  |  |  |  | 5.233 | 0.938 |  | 6.171 | Upgrade (non-standard layout) | Bus Case | $6.5m (escal) | Delay in commissioning due to access difficulties.
CP.00886 | South Pine Transformer Augmentation | 2006-06-01 | Replacement | [5 empty] | 6.038 | 0.036 | 6.074 | Age/Obsolescence/Condition | Bus Case | $6.01m ($2003/04) $6.41m (escal)
CP.00833 | Innisfail 132kV Substation Rebuild | 2003-07-01 | Replacement |  |  | 4.492 | 1.089 |  |  |  | 5.581 | Age/Obsolescence/Condition | Bus Case | $5.5m ($2000/01) $5.7m (escal) | Delay in commissioning due to outage restrictions.
CP.00863 | Blackwall - Greenbank Easement Acq | 2006-12-01 | Easement |  |  |  |  | 4.983 |  | 0.579 | 5.562 | Load Growth/Reliability | Approval Memo | $4.9m (escal) | Additional costs and delay associated with route investigations and acquisitions.
CP.01157 & CP.01114 & CP.01140 & CP.01174 | SEQ Shunt Cap Banks | 2005-10-01 | Augmentation | [5 empty] | 5.519 |  | 5.519 | Demand Growth/Reliability | Reg Test - APR | $4.3m ($2003/04) | Increased contract costs
CP.01100 | Middle Ridge - Greenbank Easement Acquis | 2006-10-01 | Easement | [6 empty] | 5.45 | 5.45 | Demand Growth - Reliability | Bus Case | $5.5m (escal)
CP.01079 | Bundamba 110kV Substation Establishment | 2005-05-01 | Connection |  |  |  |  | 5.061 | 0.074 |  | 5.135 | Connection | Bus Case | $3.96m (escal) | Delay in commissioning due to land designation process. Cost over-runs due to change in location of substation site which required additional civil works and transmission line structures.
CP.00821 | SWANBANK TRANSFORMER REPLACEMENT | 2002-07-01 | Augmentation |  | 2.641 | 2.37 | 0.028 |  |  |  | 5.039 | Reliability | Bus Case - APR | $5.15m ($1999/00) $5.31m (escal) | Minor delay in commissioning due to design issues.
CP.00795 | Blackwater Transformer Augmentation | 2006-10-01 | Connection | [5 empty] | 2.012 | 2.99 | 5.002 | Connection | Bus Case | $5.08m (escal)
CP.00432 | Kemmis 132/66kV Substation Establishment | 2003-04-01 | Augmentation & Connection |  |  | 4.421 | 0.543 | 0.014 | 0.006 |  | 4.984 | Demand Growth | Bus Case | $5.69m (escal)
CP.01245 | Mackay - Pioneer Valley Line Life Extension | 2007-10-01 | Replacement | [6 empty] | 4.914 | 4.914 | Age/Obsolescence/Condition | Bus Case | $5.27m (escal)
CP.01203 | South Pine 275kV T2 Transformer Replacement | 2006-10-01 | Replacement | [6 empty] | 4.896 | 4.896 | Age/Obsolescence/Condition | Bus Case | $4.91m (escal)
CP.00618 | Kareeya-Innisfail Line Replacement easement acquisition | 2006-04-01 | Easement |  |  |  |  | -0.805 | 5.6 |  | 4.795 | Age/Obsolescence/Condition | Board Memo | $5.9m (escal) | Delay due to difficulties associated with acquisition of the easement.
CP.00756 & CP.00889 & CP.01075 | SEQ Cap Banks (Murrarie, Molendinar, Ashgrove West) | Oct 04/05 | Augmentation |  |  |  |  | 1.265 | 3.32 |  | 4.585 | Reliability | Reg Test - APR | $4.2m (escal)
CP.01226 | Ebenezer Substation Site Acquisition | 2006-12-01 | Easement | [6 empty] | 4.5 | 4.5 | Strategic Easement | Bus Case | $3.3m (escal) | Additional costs due to rapidly increasing land values.
CP.00879 | Dan Gleeson Transformer No.2 Stage 1 | 2005-09-01 | Connection |  |  | 0.163 | 0.01 | 0.007 | 4.182 |  | 4.362 | Connection | Bus Case | $4.06m (escal) | Costs associated with transformer design and civil works at Egans Hill.
CP.01288 | Mudgeeraba 110kV Substation Refurbishment | 2007-10-01 | Replacement | [6 empty] | 4.353 | 4.353 | Fault Ratings | Bus Case | $4.31m (escal)
CP.01187 | Molendinar 275/110kV Transformer Reinforcement | 2006-10-01 | Augmentation | [5 empty] | 4.307 |  | 4.307 | Reliability | Reg Test APR | $6.9m ($2004/05)
CP.01060 | Calvale 275kV Transformer (System Spare) | 2004-07-01 | Other - Insurance Spare |  |  |  |  | 3.74 | 0.537 |  | 4.277 | Insurance Spare | Bus Case | $4.34m (escal)
| Insurance Spares |  |  |  |  | 2.747 | -1.837 | 3.332 |  |  | 4.242
CP.00790 | Pioneer Valley Transf Reinf | 2004-08-01 | Augmentation & Connection |  |  |  |  | 3.948 | 0.024 |  | 3.972 | Load Growth/Reliability | Reg Test - APR | $3.5m (2002/03) $3.5m (escal) | Scope change to address contract variations related to unexpected site conditions and secondary systems testing and commissioning.
CP.00431 | Biloela Transmission Reinforcement | 2006-10-01 | Replacement | [6 empty] | 3.968 | 3.968 | Age/Obsolescence/Condition | Bus Case | $3.39m (escal)
CP.00854 | Loganlea 275kV Reinforcement | 2002-03-01 | Augmentation |  | 1.489 | 2.156 | 0.206 | -0.003 |  |  | 3.848 | Reliability | Consultation | $19m (escal) | Substantial changes to the transmission line route and substation arrangement. Due to line construction delays commissioning was postponed until March to minimise risk of loss of supply over the summer peak period.
CP.00867 | North QLD Communications Reinforcement | 2001-12-01 | Other |  | 3.585 | 0.092 |  |  |  |  | 3.677 | Comms Reinforcement | Bus Case | $3.6m ($1999/00) $3.7m (escal)
CP.00318 | Moranbah-Collinsville Fibre Optic | 2004-11-01 | Other - OPGW Repl |  |  | 2.269 | 1.007 | 0.096 | 0.021 |  | 3.393 | Age/Obsolescence/Condition | Bus Case | $3.73m (escal) | Delay in commissioning due to equipment failure.
CP.01066 | Rockhampton Secondary System Replacement | 2006-10-01 | Replacement | [6 empty] | 3.37 | 3.37 | Age/Obsolescence/Condition | Bus Case | $2.3m (escal) | Change in scope to accommodate primary plant concerns in relation to clearances.
CP.01043 | Nebo - Pioneer Valley 132kV Easement Acquisition | 2006-06-01 | Easement | [5 empty] | 3.324 |  | 3.324 | Load Growth/Reliability | Bus Case | $3.19m (escal)
CP.00184 | Calvale-Baralaba Fibre Optic | 2003-03-01 | Other |  |  | 3.243 | 0.08 |  |  |  | 3.323 | Communications system development | Approval Memo | $4.07m (escal)
CP.01063 | Blackwater Secondary Systems Replacement | 2006-10-01 | Replacement | [6 empty] | 3.303 | 3.303 | Age/Obsolescence/Condition | Bus Case | $3.56m (escal)
CP.00898 | Mt England 275kV Line Switching | 2003-07-01 | Other |  | 0.859 | 1.858 | 0.442 |  |  |  | 3.159 | Improved switching function | Approval Memo | $3.9m (escal)
CP.01256 | Belmont 3rd 110/33kV Transf | 2006-11-01 | Augmentation | [6 empty] | 3.153 | 3.153 | Load Growth/Reliability | Bus Case | $2.68m (escal) | Transformer position changed resulting in increased costs.
CP.01061 | Ross - Dan Gleeson 132kV Line Uprate | 2004-10-01 | Replacement |  |  |  |  | 3.123 | 0.015 |  | 3.138 | Age/Obsolescence/Condition Reliability | Bus Case | $2.78m (escal)
CP.01071 | Alan Sherriff-Bohle River 132kV Line Rebuild | 2004-09-01 | Replacement |  |  |  |  | 3.059 | 0.015 |  | 3.074 | Age/Obsolescence/Condition | Bus Case | $2.02m (escal) | Higher dismantling and construction costs
CP.00733 | National Grid Interconnector | 2000-07-01 | Augmentation |  | 0.215 | 2.715 | 0.065 |  | 0.031 |  | 3.026 | Reliability | Board Memo | $249m ($1997/98) $267m (escal) | Majority of project capitalised prior to current regulatory period.
CP.01244 | Mackay Area Telecommunications Reinforcement | 2006-11-01 | Other | [6 empty] | 2.934 | 2.934 | Communications system development | Bus Case | $2.01m (escal)
CP.00866 | Abermain Transformer Replacement | 2003-10-01 | Connection |  |  | 1.4 | 1.287 | 0.027 |  |  | 2.714 | Connection | Approval Memo | $4.3m (escal) | Delay in commissioning due to delay in equipment manufacture and concerns with oil samples.
CP.00322 | Moranbah-Nebo Fibre Optic | 2004-11-01 | Other - OPGW Repl |  |  |  | 2.523 | 0.045 | 0.011 |  | 2.579 | Standard Specification/Age | Bus Case | $2.43m (escal) | Minor delay in commissioning due to equipment failure.
CP.00750 | Mudgeerabla 275kV Bus Establishment | 2006-06-01 | Other |  | 0.179 | 0.303 | 1.352 | 0.533 | 0.155 |  | 2.522 | Reliability | Bus Case | $4.9m escal | Scope change to meet current standards for a substation supplying the load levels occurring on the Gold Coast. Delay in commissioning to allow integration of design and implementation with other projects in the area.
CP.00203 | Collinsville-Strathmore-Clare FibreOptic | 2002-06-01 | Other |  | 1.897 | 0.233 | 0.358 |  |  |  | 2.488 | Communications system development | Approval Memo | $3.2m (escal)
CP.01037 | Barron Gorge 132kV Line Maintenance | 2003-12-01 | Replacement |  |  |  | 2.443 | 0.02 |  |  | 2.463 | Age/Obsolescence/Condition | Bus Case | $4.97m (escal) | Partial project completed.
CP.00897 | Blackwall 275kV Capacitor Bank No 6 | 2002-11-01 | Augmentation |  | 0.212 | 2.091 |  |  |  |  | 2.303 | Reliability | Approval Memo | $2.55m (escal)
CP.00734 | Blackwall 275kV Capacitor Bank No 1 | 2002-08-01 | Augmentation |  | 2.208 | 0.088 |  |  |  |  | 2.296 | Reliability | Approval Memo | $2.39m (escal)
CP.00845 | Gladstone Area Comms Bearers | 2003-05-01 | Other |  |  | 1.731 | 0.545 | 0.01 |  |  | 2.286 | Comms Development | Bus Case | $3.34m (escal)
CP.00748 | Gladstone South Transformer Reinforcement | 2002-02-01 | Connection |  | 2.055 | 0.162 | 0.007 |  |  |  | 2.224 | Reliability | Approval Memo | $2.24m (escal) | Delay in commissioning due to outage restrictions and works associated with upgrade of 11kV network.
CP.01052 | Calvale-Gladstone Area Easement Acquisition | 2006-08-01 | Easement |  |  |  | 0.008 |  | 2.168 |  | 2.176 | Load Growth/Reliability | Bus Case | $1.98m (escal) | Finalisation of cultural heritage and realignment issues.
CP.00278 | Blackwater - Dysart Fibre Optic | 2004-11-01 | Other - OPGW Repl |  |  |  | 2.094 | 0.07 |  |  | 2.164 | Comms reliability Age/Obsolescence/Condition | Bus Case | $3.61m (escal) | Delay in commissioning due to equipment failure.
CP.00601 | NETWORK SWITCHING CENTRE | 1905-06-23 | Replacement |  | 0.269 | 1.585 | 0.301 |  |  |  | 2.155 | obsolescence | Bus Case | $15.65m ($1992/93) | Majority of project capitalised prior to current regulatory period.
CP.00344 | Lilyvale 132kV Capacitor Banks | 2002-12-01 | Augmentation |  |  | 2.036 | 0.07 |  |  |  | 2.106 | Reliability | Reg Test - APR Bus Case | $2.0m (escal)
CP.00791 | MACKAY TRANSFORMER REINFORCE | 2002-11-01 | Connection |  |  | 2.006 | 0.054 |  |  |  | 2.06 | Connection | Approval Memo | $2.52m (escal)
CP.00331 | Clare-Townsville South Fibre Optic | 2004-11-01 | Other - OPGW Repl |  |  |  | 1.793 | 0.223 | 0.007 |  | 2.023 | Standard Specification/Age | Bus Case | $1.95m (escal) | Delay in commissioning due to equipment failure.
CP.01058 | West End Transmission Reinforcement | 2003-11-01 | Connection |  |  |  | 1.989 | 0.016 |  |  | 2.005 | Connection | Bus Case | $2.99m (escal)
CP.01257 | South Pine 100kV Extension (Brendale) | 2006-10-01 | Connection | [6 empty] | 2.003 | 2.003 | Load Growth/Reliability | Bus Case | $2.1m (escal)
CP.00252 | Baralaba - Blackwater Fibre Optic | 2002-06-01 | Other - OPGW Repl |  |  | 1.572 | 0.391 | 0.006 |  |  | 1.969 | Age/Obsolescence/Condition | Bus Case | $3.30m (escal)
CP.00864 | Cairns Transformer Replacement | 2001-12-01 | Connection |  | 1.972 | -0.072 | 0.005 |  |  |  | 1.905 | Demand growth | Approval Memo | $4.122m (escal) | Delay in commissioning due to failure of earthing transformer.
CP.01032 | Palmwoods 275kV Capacitor Bank | 2004-03-01 | Augmentation |  |  |  | 1.808 | 0.088 |  |  | 1.896 | Load Growth/Reliability | Reg Test - APR | $1.9m (2001/02) $2m (escal)
CP.01077 | Algester Substation Site Acquisition | 2005-10-01 | Easement |  |  |  | 1.618 | 0.11 | 0.064 |  | 1.792 | Load Growth/Reliability | Bus Case | $1.5m (escal) | Additional costs and delay associated with purchase and environmental/planning approval works.
CP.00877 | Proserpine 132/66kV Transf Augmtn | 2003-06-01 | Connection |  |  | 1.551 | 0.201 |  |  |  | 1.752 | Connection | Bus Case | $1.76m (escal) | Minor delay in commissioning due to late delivery of transformer and delays in final testing.
CP.01004 | Mudgeeraba 110kV Extension (Varsity Lakes) | 2005-09-01 | Connection | [5 empty] | 1.716 |  | 1.716 | Load Growth/Reliability | Bus Case | $1.36m (escal) | Cost overrun due to civil/electrical price increase from estimate.
CP.00884 | Middle Ridge 110kV Capacitor Banks | 2002-04-01 | Augmentation |  | 1.703 | 0.003 |  |  |  |  | 1.706 | Reliability | Approval Memo | $1.9m (escal) | Delay in commissioning due to delay in equipment delivery.
CP.00875 | Loganlea 110kV Capacitor Banks | 2002-08-01 | Augmentation |  | 1.636 | 0.012 | 0.027 |  |  |  | 1.675 | Reliability | Approval Memo | $1.82m (escal) | Delay in commissioning due to equipment defects.
CP.00383 | Ross - Yabulu Easement & Sub Site Acquisition | 2007-04-01 | Easement |  |  |  | 0.185 |  | 1.488 |  | 1.673 | Load Growth/Reliability | Bus Case | $1.25m (escal) | Cost overrun due mainly to property owner compensation.
CP.01298 | Relocation of NOC Infrastructure | 2006-10-01 | Security/Compliance | [6 empty] | 1.648 | 1.648 | Security | Bus Case | $1.61m (escal)
CP.00861 | Innisfail - Edmonton Line Replacement | 2007-04-01 | Easement | [6 empty] | 1.644 | 1.644 | Age/Obsolescence/Condition | Approval Memo | $1.65m (escal)
CP.01048 | Greenbank to Belmont Easement Clearance | 2004-10-01 | Easement | [5 empty] | 1.634 |  | 1.634 | Load Growth/Reliability | Bus Case | $1.85m (escal)
CP.01027 | Banyo Substation Site Acquisition | 2002-06-01 | Easement |  | 1.616 | 0.005 |  |  |  |  | 1.621 | Strategic Easement | Bus Case | $1.7m (escal)
CP.01033 | Mt England 275kV Capacitor Bank | 2003-12-01 | Augmentation |  |  |  | 1.595 | 0.018 |  |  | 1.613 | Load Growth/Reliability | Reg Test - APR | $1.7m ($2001/02) $1.8m (escal)
CP.01001 | Mudgeeraba 275kV Capacitor Bank #4 | 2002-12-01 | Augmentation |  |  | 1.583 | 0.027 |  |  |  | 1.61 | Reliabillity/Load Growth | Bus Case | $2.13m (escal)
CP.01051 | Blackwater 132kV Ext (Rolleston) | 2005-06-01 | Connection |  |  |  |  | 1.357 | 0.238 |  | 1.595 | Connection | Bus Case | $1.12m (escal) | Cost increases due to increases in input costs
CP.00632 | Wurdong 275kV Cap Bank No.2 | 2004-05-01 | Augmentation |  |  |  | 1.539 | 0.055 |  |  | 1.594 | Reliability | Reg Test - APR Bus Case | $1.8m ($2001/02) $1.93m (escal)
CP.01050 | Ashgrove West Secondary Systems Replacement | 2006-06-01 | Replacement | [5 empty] | 1.576 |  | 1.576 | Age/Obsolescence/Condition | Bus Case | $1.29m (escal) | Cost overrun due to increased input costs.
CP.00295 | Dysart - Moranbah Fibre Optic | 2004-11-01 | Other - OPGW Repl |  |  |  | 1.356 | 0.172 |  |  | 1.528 | Comms reliability Age/Obsolescence/Condition | Bus Case | $2.29m (escal) | Delay in commissioning due to equipment failure.
CP.01252 | Woree Substation Site Expansion | 2007-06-01 | Easement | [6 empty] | 1.5 | 1.5 | Load Growth/Reliability | Bus Case | $1.00m ($2004/05) | Additional costs associated with land purchase and subsequent closure of adjacent road.
CP.00809 | Brisbane Area Fibre Optics | 2002-05-01 | Other - OPGW Repl |  | 0.174 | 1.315 | 0.001 |  |  |  | 1.49 | Age/Obsolescence/Condition | Approval Memo | $3.6m (escal) | Increased costs associated with scope change to extend OPGW length. Delay in commissioning due to delay in required commissioning of another project.
CP.01236 | Greenbank 275kV Capacitor Bank No. 2 | 2006-10-01 | Augmentation | [5 empty] | 1.017 | 0.471 | 1.488 | Demand Growth/Reliability | Reg Test APR | $1.4m ($2004/05) $1.5m (escal)
CP.00345 | Stanwell - Broadsound Easement Legal Clearance | 2002-01-01 | Easement |  |  | 1.462 |  |  |  |  | 1.462 | Load Growth/Reliability | Approval Memo | $0.61m (escal) | Cost overruns due to increase in cultural heritage work and unexpected costs associated with new legislation (Vegetation Management Act).
CP.00381 | Townsville Area Easements | 2006-06-01 | Easement | [5 empty] | 1.435 |  | 1.435 | Reliability | Approval Memo | $0.50m | Delays and costs associated with dealing with the Department of Defence and change in alignment resulting in increased compensation costs.
CP.00799 | UPPER KEDRON ESTABLISH | 2000-11-01 | Augmentation & Connection |  | 1.131 | 0.296 |  |  |  |  | 1.427 | Load Growth/Reliability | Board Memo | $9.8m (escal) | Majority of project capitalised prior to current regulatory period.
CP.00382 | STRATHMORE 275KV ESTABLISHMENT | 2001-11-01 | Augmentation |  | 1.365 | 0.052 | 0.002 |  |  |  | 1.419 | Reliabillity | Bd Memo | $8.8m (199/00) $9.4m (escal) | Delay in commissioning due to overtime bans and extended excavation times due to rock on site.
CP.00731 | Nebo 275Kv Cap Bank No. 3 | 2001-09-01 | Augmentation |  | 1.385 | [5 empty] | 1.385 | Load Growth/Reliability | Approval Memo | $1.82m (escal)
CP.01221 | Ross 132kV Extension (Milchester Bypass) | 2007-06-01 | Connection | [6 empty] | 1.37 | 1.37 | Connection | Prelim Scope | $1.37m (escal)
CP.01029 | Broadsound - Lilyvale Easement Clearance | 2003-09-01 | Easement |  |  |  |  | 1.363 |  |  | 1.363 | Load Growth/Reliability | Bus Case | $0.7m (escal) | Cost overrun and delay in commissioning due to the additional environmental management and cultural heritage management issues.
CP.01220 | Ems Front End Processor Upgrade | 2006-06-01 | Replacement | [5 empty] | 1.195 | 0.145 | 1.34 | Age/Obsolescence/Condition | Bus Case | $1.12m (escal) | Cost overrun resulting from supplier cost increases.
CP.00117 | Operational WAN Stage 3 | 2003-05-01 | Other |  | 0.196 | 1.083 | 0.043 |  |  |  | 1.322 | Asset Monitoring | Approval Memo | $1.32m (escal) | Delay in commissioning due to unavailability of resources.
CP.01241 | Gladstone South 132kV Capacitor Bank | 2006-10-01 | Augmentation | [6 empty] | 1.286 | 1.286 | Reliability | Reg Test - APR Bus Case | $1.2m ($2004/05) $1.3m (escal)
CP.00876 | Loganlea 110kV Ext(B Plains & Beenleigh) | 2002-07-01 | Connection |  | 0.978 | 0.292 | 0.009 |  |  |  | 1.279 | Connection | Bus Case | $1.65m (escal) | Delays due to completion of pre-requisite distributor component of works.
CP.01197 | Townsville Sth 2nd 132kV Capacitor Bank | 2006-10-01 | Augmentation | [6 empty] | 1.253 | 1.253 | Reliability | Reg Test - APR Bus Case | $1.21m ($2004/05) $1.27m (escal)
CP.01231 | Belmont Third 110kV Capacitor Bank No.3 | 2005-12-01 | Augmentation | [5 empty] | 1.253 |  | 1.253 | Demand Growth/Reliability | Reg Test - Individual Report | $1.11m (escal) | Increased input costs
CP.01234 | Molendinar 110kV Capacitor Bank No.2 | 2006-10-01 | Augmentation | [5 empty] | 0.975 | 0.273 | 1.248 | Demand Growth/Reliability | Reg Test APR Bus Case | $1.2m ($2004/05) $1.2m (escal)
CP.01111 | Fujitsu PLC Equipment Replacement | 2006-05-01 | Replacement | [6 empty] | 1.246 | 1.246 | Age/Obsolescence/Condition | Bus Case | $1.29m (escal)
CP.01080 | Alligator Creek 132kV Capacitor Bank | 2004-10-01 | Augmentation |  |  |  |  | 1.205 | 0.003 |  | 1.208 | Load Growth/Reliability | Bus Case | $1.07m (escal) | Cost overrun largely due to additional costs associated with automation design, testing and pre-commissioning and civil works.
CP.01272 | NSC WALLBOARD PROCUREMENT & INSTALLATION | 2006-10-01 | Replacement | [6 empty] | 1.188 | 1.188 | Age/Obsolescence/Condition | Bus Case | $1.19m (escal)
CP.01233 | Ashgrove West 110kV Capacitor Bank No. 2 | 2005-11-01 | Augmentation | [5 empty] | 1.186 |  | 1.186 | Demand Growth/Reliability | Reg Test - Individual Report Bus Case | $1.26m (escal)
CP.01232 | South Pine Third 110kV Capacitor Bank No.3 | 2005-11-01 | Augmentation | [5 empty] | 1.175 |  | 1.175 | Demand Growth/Reliability | Reg Test - Individual Report Bus Case | $1.15m (escal)
CP.01239 | Moranbah Transformer Replacement | 2006-01-01 | Other - Insurance Spare |  |  |  |  | 1.161 |  |  | 1.161 | Insurance Spare | Bus Case | $1.33m (escal)
CP.01222 | Runcorn 110/33kV Spare Transformer | 2005-01-01 | Other | [5 empty] | 1.141 |  | 1.141 | System Spare | Bus Case | $0.87m (escal) | Increased input costs
CP.00448 | Molendinar 275kV Easements | 2005-05-01 | Easement |  | 0.266 | 0.522 | 0.156 | 0.156 |  |  | 1.1 | Load Growth/Reliability | Approval Memo | $3.17m ($1991/92) | Majority of project capitalised prior to current regulatory period.
CP.01205 | Type 1 Telecomm Tower Upgrade | 2006-05-01 | Security/Compliance | [5 empty] | 1.094 |  | 1.094 | Security/Compliance | Bus Case | $1.03m (escal) | Delay in commissioning to avoid penalty costs potentially charged by contract tenderers.
CP.00829 | Rockhampton Area Fibre Optic Installation | 2001-03-01 | Other |  | 1.09 | 0.002 |  |  |  |  | 1.092 | Communications system development | Approval Memo | $1.05m (escal)
CP.01240 | Gladstone Substn Conversion to Freehold | 2005-06-01 | Easement | [5 empty] | 1.072 |  | 1.072 | Prevent encroachment | Bus Case | $1.08m ($2004/05)
CP.01055 | Belmont - Murarrie 110kV Line Acquisition | 2003-03-01 | Other - Purchase |  |  | 1.063 |  |  |  |  | 1.063 | Connection | Bus Case | $1.1m (escal)
CP.01003 | Abermain 110kV Capacitor Bank | 2003-05-01 | Augmentation |  |  | 1.031 | 0.002 |  |  |  | 1.033 | Reliability | Bus Case | $0.9m (escal) | Minor delay in commissioning due to outage cancellations. Increase in costs associated with input cost increases.
CP.00896 | Operational WAN Stage 2 | 2001-05-01 | Other |  | 0.984 | 0.035 |  |  |  |  | 1.019 | Asset Monitoring | Approval Memo | $1.26m (escal)
CP.00782 | Tarong Transmission | 2002-01-01 | Connection |  | 0.924 | 0.083 | 0.006 | 0.002 |  |  | 1.015 | Connection | Approval Memo | $1.35m (escal)
CP.01076 | Rockhampton 132kV Capacitor Bank | 2005-10-01 | Augmentation | [5 empty] | 1.004 |  | 1.004 | Reliability/Demand Growth | Bus Case | $1m ($2002/03)
CP.01216 | Blackwater 132kV Capacitor Bank No.1 | 2005-11-01 | Augmentation | [5 empty] | 1 |  | 1 | Reliability | Bus Case | $0.89m (escal) | Cost overrun due to higher costs associated with construction, testing and commissiong. Minor delay in commissioning with no system impact.
CP.01229 | Tower Security - Initial Phase | 2007-06-01 | Security/Compliance | [6 empty] | 1 | 1 | Security | Bus Case | $1.00m (escal)
CP.01011 | Operational WAN Stage 4 | 2006-05-01 | Other | [5 empty] | 0.998 |  | 0.998 | Asset Monitoring | Bus Case | $0.73m (escal)
CP.01093 | South Pine 110kV Bus Coupler | 2005-10-14 | Very small | [5 empty] | 0.972 |  | 0.972 | Condition | Bus Case | $0.905m (escal) | Technology changes
CP.01254 | Ingham Microwave Radio Establishment | 2006-12-01 | Other | [6 empty] | 0.945 | 0.945 | Reliability | Bus Case | $0.936m (escal)
CP.00865 | Townsville Sth Transformer | 2001-07-01 | Connection |  | 0.666 | 0.003 | 1.39 | -1.122 |  |  | 0.937 | Reliability | Approval Memo | $1.87m (escal)
CP.00576 | Chalumbin 132kV Cap Bank No 1 | 2001-12-20 | Augmentation |  | 0.831 | 0.1 |  |  |  |  | 0.931 | Reliability | Approval Memo | $1.0m (escal)
CP.01131 | Tully - Innisfail 132kV Transmission Line | 2007-10-01 | Replacement |  |  |  |  | 0.898 |  |  | 0.898 | Age/Condition | Bus Case | $55.10m (escal) | Partial capitalisations for project to be commissioned in 2008.
CP.01237 | Barron Gorge Secondary Systems Replacement | 2006-04-01 | Replacement | [5 empty] | 0.879 |  | 0.879 | Age/Obsolescence/Condition | Bus Case | $0.94m (escal)
CP.01089 | Greenbank/Maudsland Easement Clearance | 2005-05-01 | Easement | [5 empty] | 0.877 |  | 0.877 | Reliability | Bus Case | $8.0m (escal) | Finalisation of cultural heritage and realignment issues.
CP.01059 | Feeder 701 Easement Transfer | 2003-06-01 | Easement |  |  |  | 0.866 | 0.004 |  |  | 0.87 | Reliability | Bus Case | $1.31m (escal)
CP.01097 | Operational Data Logging, Analysis and V | 2004-11-12 | Other |  |  |  |  | 0.865 |  |  | 0.865 | Data requirements | Bus Case | $0.96m (escal)
CP.01308 | Kareeya 132kV Substation Refurbishment | 2006-12-01 | Replacement | [6 empty] | 0.861 | 0.861 | Safety | Bus Case | $0.99m (escal)
CP.01009 | Rocklea 110kV Ext. (Archerfield No. 2) | 2005-12-22 | Connection | [5 empty] | 0.819 |  | 0.819 | Reliability | Bus Case | $0.78m (escal)
CP.00593 | TENNYSON 110/33 REDEVELOPMENT | 2000-12-01 | Replacement |  | 0.203 | 0.284 | 0.028 | 0.247 | 0.046 |  | 0.808 | Age/Obsolescence/Condition | Board Memo | $9.72m ($1998/99) $10.2m (escal) | Minor delay in commissioning due to unavailability of resources.
CP.01110 | Swanbank - Abermain 110kV Line Refurbishment | 2006-06-01 | Replacement | [5 empty] | 0.793 |  | 0.793 | Age/Condition | Bus Case | $1.36m (escal)
CP.01152 | Lilyvale - Blackwater Easement Acquisition | 2006-10-01 | Easement | [6 empty] | 0.779 | 0.779 | Reliability | Bus Case | $0.81m (escal)
CP.01273 | EMS HARDWARE REPLACEMENT | 2006-10-01 | Replacement | [6 empty] | 0.754 | 0.754 | Age/Obsolescence/Condition | Bus Case | $0.70m (escal)
CP.01739 | Murarrie - Virginia Fibre Cable Installation - Version 2 | 2006-11-30 | Other | [6 empty] | 0.745 | 0.745 | Communications system development | Bus Case | $0.75m (escal)
CP.01095 | Bundamba Substation Site Acquisition | 2004-08-01 | Easement |  |  |  |  | 0.724 | 0.004 |  | 0.728 | Reliability | Bus Case | $0.57m (escal)
CP.01045 | Townsville West Area Easement Widening | 2004-06-01 | Easement |  |  |  |  | 0.717 |  |  | 0.717 | Age/Obsolescence/Condition | Bus Case | $0.60m (escal) | Environmental Factors
CP.00079 | Substn Protn Upgrade Stage 2 - $220k transfer to OPEX | 2004-08-01 | Security/Compliance |  |  |  | 0.693 | 0.004 |  |  | 0.697 | Compliance | Approval Checklist | $0.69m (escal) | Change of scope
CP.00585 | Middle Ridge 110kV Ext (Torrington) - $136k transfer to OPEX | 2004-01-01 | Connection |  |  | 0.355 | 0.275 | 0.022 |  |  | 0.652 | Reliability | Bus Case | $0.94m (escal)
CP.01040 | Middle Ridge, Abermain & South Coast Revenue Metering | 2004-02-01 | Connection |  |  |  | 0.601 | 0.009 |  |  | 0.61 | Compliance | Bus Case | $0.60m (escal)
CP.01113 | Broadsound - Nebo Easement Acquisition | 2006-10-01 | Easement | [6 empty] | 0.607 | 0.607 | Reliability | Bus Case | $2.90m (escal)
CP.01242 | Acquisition of Line from Energex | 2006-06-01 | Other - Purchase | [6 empty] | 0.56 | 0.56 | Reliability | Bus Case | $0.56m (escal)
CP.00409 | Psymetrix Dynamics Monitor Upgrade | 2006-06-01 | Other |  |  |  |  | 0.631 | -0.082 |  | 0.549 | Compliance | Bus Case | $0.55m (escal)
CP.01086 | Bohle River to Yabulu South Easement Acq | 2005-12-01 | Easement | [5 empty] | 0.546 |  | 0.546 | Age/Obsolescence/Condition | Bus Case | $1.07m (escal)
CP.01307 | Gladstone Sec Sys Upgrade- (Gladstone North) | 2006-02-28 | Connection | [5 empty] | 0.468 | 0.031 | 0.499 | Reliability | Approval memo | $0.5m (escal)
CP.00126 | Gladstone - Maurice Hill MW Replacement | 2002-09-01 | Replacement |  |  | 0.481 | 0.001 |  |  |  | 0.482 | Age/Obsolescence/Condition | N | $0.51m (escal)
CP.01303 | Metropolitan Telecomms STM-4 Upgrade | 2006-05-01 | Other | [5 empty] | 0.439 |  | 0.439 | Reliability | Bus Case | $0.42m (escal)
CP.01010 | Ashgrove West Prot Mods (Milton) | 2003-07-01 | Connection |  |  | 0.432 |  | 0.005 |  |  | 0.437 | Reliability | Bus Case | $0.39m (escal)
CP.01287 | Wide Bay Area 275kV Substation Site Acq | 2006-08-01 | Easement | [6 empty] | 0.427 | 0.427 | Reliability | Bus Case | $0.43m (escal)
CP.01228 | Brisbane-Townsville Telecomms | 2004-12-01 | Other |  |  |  | 0.4 | 0.026 |  |  | 0.426 | Communications system development | Bus Case | $0.51m (escal)
CP.00156 | Communication Sites Alarm Facilities Upg | 2002-05-01 | Security/Compliance |  | 0.4 | 0.019 |  |  |  |  | 0.419 | Compliance | Approval Memo | $0.47m (escal)
CP.01047 | Chalumbin 18kV Reactor Replacement | 2003-07-01 | Replacement |  |  | 0.323 | 0.095 |  |  |  | 0.418 | Age/Obsolescence/Condition | Bus Case | $0.49m (escal)
CP.00830 | Operational Telephone Network Development | 2002-02-01 | Other |  | 0.41 | [5 empty] | 0.41 | Age/Obsolescence/Condition | N | $0.45m (escal)
CP.00212 | South East Queensland Revenue Metering | 2002-07-01 | Connection |  | 0.302 | 0.096 |  |  |  |  | 0.398 | Compliance | Approval Memo | $0.34m (escal) | Regulatory Requirements / Technology Changes
CP.01056 | Turkinje Secondary System Mods (Craiglie Fdrs) | 2004-02-07 | Connection |  |  |  | 0.394 | 0.003 |  |  | 0.397 | Reliability | Bus Case | $0.41m (escal)
CP.01225 | Rockhampton 132kV Bus Coupler | 2005-10-21 | Replacement | [5 empty] | 0.393 |  | 0.393 | Age/Obsolescence/Condition | Bus Case | $0.40m (escal)
CP.01213 | Mt Gravatt - Eagle Heights Microwave Radio Upgrade | 2006-12-01 | Replacement | [6 empty] | 0.388 | 0.388 | Reliability | Bus Case | $0.40m (escal)
CP.00639 | Nebo/Ross Easement Acquisition | 2007-08-01 | Easement |  | 0.009 | 0.055 | 0.17 | 0.146 |  |  | 0.38 | Reliability | N | $0.82m (escal)
CP.01106 | Upgrade 50V Supplies at Critical Comms Sites | 2006-04-01 | Other | [5 empty] | 0.371 |  | 0.371 | Reliability | Bus Case | $0.41m (escal)
CP.01227 | Ergon SCADA ICCP Link Stages 1 & 2 | 2006-06-01 | Other | [5 empty] | 0.371 |  | 0.371 | Age/Obsolescence/Condition | Bus Case | $0.37m (escal)
CP.00433 | Central Region Winch Up Tower Replacement | 2003-09-01 | Security/Compliance |  |  |  | 0.36 |  |  |  | 0.36 | Safety | Bus Case | $0.30m (escal) | Environmental Factors
CP.00084 | Middle Ridge Transformer Uprating | 2003-01-01 | Augmentation |  |  | 0.351 | 0.001 |  |  |  | 0.352 | Reliability | Bus Case | $0.32m (escal)
CP.00812 | South Pine - Mt Glorious Microwave Replacement | 2002-12-01 | Replacement |  |  | 0.345 | 0.005 |  |  |  | 0.35 | Age/Obsolescence/Condition | Bus Case | $0.41m (escal)
CP.00550 | QAL Secondary Systems Refurbishment | 2003-01-01 | Replacement |  |  | 0.263 | 0.07 | 0.007 |  |  | 0.34 | Reliability | Approval Memo | $0.35m (escal)
CP.00338 | TULLY SECONDARY SYSTEMS ENHANCEMENT | 2001-12-21 | Replacement |  |  | 0.306 | 0.032 |  |  |  | 0.338 | Age/Obsolescence/Condition | Approval Memo | $0.35m (escal)
CP.00831 | Barron Gorge Microwave Replace | 2001-08-01 | Replacement |  | 0.334 | [5 empty] | 0.334 | Age/Obsolescence/Condition | Approved Quote | $0.46m (escal)
CP.01105 | Winch Up Twr Replacement Hope Mt and Dawson Range | 2005-07-01 | Replacement | [5 empty] | 0.329 |  | 0.329 | Safety | Bus Case | $0.30m (escal)
CP.00827 | COMMS NTWK MANAGMT SYS UPGRADE | 2002-08-30 | Other |  |  | 0.324 |  |  |  |  | 0.324 | Age/Obsolescence/Condition | N | $0.37m (escal)
CP.00781 | CARDWELL TRANSFORMER | 2000-11-01 | Connection |  | 0.308 | 0.007 |  |  |  |  | 0.315 | Reliability | Approval Memo | $1.78m (escal)
CP.01238 | Central Region Comms RTU Upgrade | 2006-11-01 | Replacement | [6 empty] | 0.312 | 0.312 | Age/Obsolescence/Condition | Bus Case | $0.40m (escal)
CP.00858 | Comms Z12 Cable Carrier Replacement | 2002-08-30 | Replacement |  |  | 0.298 |  |  |  |  | 0.298 | Age/Obsolescence/Condition | Approved Quote | $0.34m (escal) | Technology changes
CP.00186 | Mudgeeraba 110kV Bay Uprating | 2002-06-01 | Connection |  | 0.256 | 0.015 |  |  |  |  | 0.271 | Reliability | Approval memo | $0.30m (escal) | Environmental Factors
CP.01099 | Telecommunications Synchronisation | 2006-04-01 | Other | [5 empty] | 0.266 |  | 0.266 | Reliability | Bus Case | $0.41m (escal)
CP.00811 | BARRON GORGE PILOT CABLE | 2000-02-01 | Replacement |  | 0.264 | [5 empty] | 0.264 | Age/Obsolescence/Condition | N | $1.30m (escal) | Regulatory Requirements
CP.01088 | Alligator Ck Local Facility & NSC Link | 2004-10-01 | Replacement |  |  |  |  | 0.258 |  |  | 0.258 | Age/Obsolescence/Condition | Bus Case | $0.25m (escal)
CP.01096 | Ashgrove West System Spare Transformer | 2006-06-01 | Other - Insurance Spare | [5 empty] | 0.25 |  | 0.25 | Reliability | Bus Case | $1.23m (escal)
CP.00130 | Tarong 66kV Feeder Protection Upgrade | 2002-05-01 | Replacement |  |  | 0.246 |  |  |  |  | 0.246 | Age/Condition | Approval Memo | $0.26m (escal)
CP.00506 | Murphys Creek - Blackwall 275kV Line & M | 2001-10-01 | Easement |  |  | 0.244 |  |  |  |  | 0.244 | Reliability | N
CP.01107 | Replacement of Mt Archer Comms Poles | 2007-06-01 | Security/Compliance | [6 empty] | 0.244 | 0.244 | Compliance | N | $0.24m (escal)
CP.00608 | Cairns Reinforcement Stage 1 (Property Only) | 1998-06-04 | Augmentation |  | 0.203 | 0.007 |  |  |  |  | 0.21 | Reliability | Board Memo | $51.9m (escal) | Majority of project capitalised prior to current regulatory period.
CP.01263 | Mudgeeraba X-Protection Relay Replacement | 2006-10-01 | Replacement | [5 empty] | 0.204 |  | 0.204 | Age/Obsolescence/Condition | Bus Case | $0.22m (escal)
CP.01217 | Nebo - QR Mindi Easement Acquisition | 2006-03-01 | Easement | [5 empty] | 0.201 |  | 0.201 | Reliability | Bus Case | $0.41m (escal)
CP.01262 | El Arish Substation Site Acquisition | 2006-09-01 | Easement | [6 empty] | 0.201 | 0.201 | Reliability | Bus Case | $0.21m (escal)
CP.01025 | Middle Ridge Prot Mods (Postman's Ridge) | 2004-06-16 | Connection |  |  |  |  | 0.198 |  |  | 0.198 | Age/Obsolescence/Condition | Approved Quote | $0.20m (escal)
CP.00662 | ABERMAIN 110KV LINE SWITCHING | 2001-05-01 | Augmentation |  | 0.005 | 0.192 |  |  |  |  | 0.197 | Reliability | Approval Memo | $2.41m (escal)
CP.01304 | Test Sticks & Detectors Replacement | 2006-06-01 | Replacement | [5 empty] | 0.18 |  | 0.18 | Age/Obsolescence/Condition | Bus Case | $0.18m (escal)
CP.00229 | Mt Stuart Comms Building Upgrade | 2001-10-01 | Replacement |  | 0.162 | 0.007 |  |  |  |  | 0.169 | Age/Obsolescence/Condition | Approval Memo | $0.17m (escal)
CP.01215 | LAN Extensions to Telecomms Repeaters | 2006-09-01 | Other | [6 empty] | 0.157 | 0.157 | Access to remote sites | N | $0.17m (escal)
CP.00213 | Tully Falls Repeater Building | 2002-02-01 | Replacement |  | 0.141 | [5 empty] | 0.141 | Age/Obsolescence/Condition | N | $0.15m (escal)
CP.00798 | Swanbank E PS Transmission | 2001-11-01 | Very small |  | 0.13 |  |  | 0.002 |  |  | 0.132 |  | N | $5.7m (escal)
CP.01196 | Townsville East Easement & Sub Site Acquisition | 2006-12-01 | Easement | [6 empty] | 0.129 | 0.129 | Reliability | Y | $1.55m (escal)
CP.01211 | Develop QR Fibre Network | 2004-11-24 | Other | [5 empty] | 0.123 |  | 0.123 | Reliability | Y | $0.12m (escal)
CP.01083 | Ashgrove West - CBD Fibre Optic | 2003-09-01 | Other |  |  |  | 0.107 |  |  |  | 0.107 | Security | N | $0.09m (escal)
CP.00339 | Barron Gorge - Cairns Easement Acquisition | 2004-12-01 | Easement | [5 empty] | 0.105 |  | 0.105 | Compliance | N | $0.12m (escal)
CP.00777 | Substn/NSC Seq Event Recording | 2003-02-01 | Other |  |  | 0.104 |  |  |  |  | 0.104 | Reliability | N | $0.30m (escal)
CP.00655 | CALVALE/TARONG TRANSM REINF | 1998-11-01 | Augmentation |  | 0.05 | 0.042 |  |  |  |  | 0.092 | Reliability | N |  | Majority of project capitalised prior to current regulatory period.
CP.01031 | Pioneer Valley Transformer Storage | 2002-11-01 | Other - Insurance Spare |  |  | 0.092 |  |  |  |  | 0.092 | Reliability |  | $0.14m (escal)
CP.00894 | Broadsound 275kV Circuit Breaker | 2001-09-01 | Very small |  | 0.091 | -0.001 |  |  |  |  | 0.09 | Reliability | Approval Memo | $0.92m (escal) | Rock on the site increasing civil works costs.
CP.00190 | Gladstone PS Switchyard Stub Protection | 2001-04-05 | Other |  |  | 0.082 |  |  |  |  | 0.082 | Age/Obsolescence/Condition | N | $0.18m (escal)
CP.00871 | Woree Substation Property Acquisition | 2000-06-30 | Easement |  | 0.029 | 0.053 |  |  |  |  | 0.082 | Reliability | N | $1.20m (escal)
CP.00670 | Pioneer Valley 132kV Establishment | 1998-09-01 | Connection |  | 0.08 | [5 empty] | 0.08 | reliability |  | $3.71m (escal) | Majority of project capitalised prior to current regulatory period.
CP.00895 | Townsville South 132 | 2000-12-01 | Augmentation |  | 0.08 | [5 empty] | 0.08 | reliability |  | $1.15m (escal) | Majority of project capitalised prior to current regulatory period.
CP.00407 | Kelly Mt. Repeater Building Upgrade | 2002-02-01 | Replacement |  | 0.074 | [5 empty] | 0.074 | Communications system development |  | $0.09m (escal)
CP.00074 | Kamerunga Underground Fibre Cable | 2001-10-01 | Replacement |  | 0.073 | [5 empty] | 0.073 | Replacement |  | $0.20m (escal)
CP.00179 | Ross & Lilyvale Revenue Metering | 2003-05-27 | Connection |  |  | 0.03 | 0.033 |  | 0.006 |  | 0.069 | Compliance |  | $0.11m (escal)
CP.00447 | Greenbank Easements | 1997-05-01 | Easement |  | 0.001 | 0.047 |  | 0.019 |  |  | 0.067 | reliability |  | $7.1m (escal)
CP.00872 | Ross-Townsville Zinc Fast Trip Scheme | 2000-10-31 | Other |  | 0.064 |  | 0.001 |  |  |  | 0.065 | reliability |  | $0.07m (escal)
CP.00001 | MINOR CAPITAL WORKS | 2000-07-01 | Other |  |  | 0.063 |  |  |  |  | 0.063
CP.00738 | DISTURBANCE RECORDERS STAGE 3 | 2000-11-01 | Other |  |  | 0.06 |  |  |  |  | 0.06 | compliance
CP.00412 | Mt Gravatt Comms Site Upgrade | 2002-02-01 | Replacement |  |  | 0.058 |  |  |  |  | 0.058 | Replacement |  | $0.09m (escal)
CP.01054 | Banyo NSC Back-up Facility | 2003-04-01 | Security/Compliance |  |  |  | 0.056 |  |  |  | 0.056 | security |  | $0.05m (escal)
CP.00596 | LILYVALE TRANSFORMER | 2002-04-17 | Connection |  | 0.002 | 0.053 |  |  |  |  | 0.055 | Reliability | Approval Memo | $1.89m (escal) | Changes in materials costs
CP.01253 | Nebo Reactors 33kV Underground Cables | 2005-05-01 | Replacement | [5 empty] | 0.055 |  | 0.055 | replacement |  | $0.16m (escal)
CP.01297 | Maryborough Mux Installations | 2006-04-01 | Other | [5 empty] | 0.049 |  | 0.049 | compliance |  | $0.05m (escal)
CP.01296 | Rockhampton- TVille Telecomms Service | 2006-05-01 | Other | [5 empty] | 0.035 |  | 0.035 | Communications system development |  | $0.04m (escal)
CP.00487 | TURKINJE TRANSFORMER REPLACE | 1999-12-01 | Connection |  | 0.032 | [5 empty] | 0.032 | reliability |  | $3.07m (escal) | Majority of project capitalised prior to current regulatory period.
CP.00779 | SOUTH PINE/UPPER KEDRON REINF | 2001-03-01 | Augmentation |  | 0.006 | 0.026 |  |  |  |  | 0.032 | reliability |  | $5.8m (escal) | project cancelled
CP.00394 | Woree Transformer Storage | 2002-03-01 | Other - Insurance Spare |  | 0.03 | [5 empty] | 0.03 | Spare |  | $0.03m (escal)
CP.00806 | CALVALE/STANWELL COMMS REINF | 2000-04-01 | Other - OPGW Repl |  |  | 0.027 |  |  |  |  | 0.027 | Communications system development |  | $4.20m (escal) | Majority of project capitalised prior to current regulatory period.
CP.01028 | Proserpine 66kV Metering | 2003-07-01 | Connection |  |  |  | 0.02 |  |  |  | 0.02 | compliance |  | $0.02m (escal)
CP.00807 | COMMUNICATIONS PLC R | 1999-06-01 | Replacement |  | 0.016 | [5 empty] | 0.016 | Obsolescence
CP.00638 | PALMWOODS CAPACITOR | 2000-12-01 | Augmentation |  | 0.013 | [5 empty] | 0.013 | reliability |  | $1.33m (escal) | Majority of project capitalised prior to current regulatory period.
CP.00862 | Middle Ridge UV Loadshed Scheme | 2000-04-01 | Other |  | 0.013 | [5 empty] | 0.013 | reliablity |  | $0.02m (escal)
CP.00374 | SOUTH PINE TRANSFORMER | 2000-06-01 | Augmentation |  | 0.01 | 0.001 |  |  |  |  | 0.011 | reliability |  | $4.78m (escal)
CP.00603 | Swanbank/Greenbank Easement Acq |  | Easement |  |  | 0.011 |  |  |  |  | 0.011 | reliability |  | $0.17m (escal)
CP.00105 | Dan Gleeson RTU Install | 2001-09-01 | Replacement |  | 0.01 | [5 empty] | 0.01 | Age/Obsolescence/Condition | N | $0.20m (escal)
CP.00454 | Runcorn 33kV Plant Uprating | 2003-05-01 | Connection |  |  | 0.004 | 0.006 |  |  |  | 0.01 | Fault Ratings |  | $0.18m (escal)
CP.01219 | Tully Substation Property Extension | TBC | Easement | [5 empty] | 0.009 |  | 0.009 | reliability |  | $0.35m (escal)
CP.01235 | Loganlea 275kV cap Bank No. 1 | na - proj cancelled | Augmentation | [5 empty] | 0.008 |  | 0.008 |  |  | $1.10m (escal)
CP.00123 | Belmont Protection Modifications (Clevel | 2001-04-01 | Connection |  | 0.007 | [5 empty] | 0.007 | compliance |  | $0.06m (escal)
CP.00410 | Blackwall Easements | 1998-10-01 | Easement |  | 0.003 | 0.002 |  |  |  |  | 0.005 | reliability |  | $4.90m (escal) | Majority of project capitalised prior to current regulatory period.
CP.01230 | NSC Power System Forecasting Tool | Deferred | Other | [5 empty] | 0.002 |  | 0.002
CP.00223 | LOGANLEA 110KV EXT(B | 2000-01-01 | Connection |  | 0.001 | [5 empty] | 0.001 | reliability |  | $0.70m (escal)
CP.00788 | MUDGEERABA TRANSFORMER | 2001-06-01 | Augmentation | [7 empty] | 0 | compliance |  | $0.40m (escal)
CP.00840 | Mt England CB Replacement (Wivenhoe) | 1999-10-01 | Connection | [7 empty] | 0
CP.00658 | TULLY TRANSFORMER AUGMENTATION | 2001-08-01 | Connection |  | 0.053 | -0.072 |  |  |  |  | -0.019 | reliability |  | $5.1m (escal) | Majority of project capitalised prior to current regulatory period.
CP.00713 | BLACKWALL ESTABLISHMENT | 2000-02-01 | Augmentation |  | 0.039 | 0.012 |  | -0.114 |  |  | -0.063 | Reliability | Bd Memo | $71.32m (escal) | Majority of project capitalised prior to current regulatory period.
|  |  |  | Subtotal | 57.101 | 164.564 | 134.932 | 180.209 | 216.755 | 233.576 | 987.137
|  |  | ^refers to Categories set out in table 3.1 (e.g Augmentation, Replacement etc) | [5 empty] | *Note that values in these columns are estimates only

## Hist Capex - Non-Network
3.4 HISTORIC CAPEX - Non-Network - by project
[5 empty] | Home |  |  | Link to Historic Capex Instructions - Table 6.2 |  |  | Link to Historic Capex Commentary - Table 5.2
($m, nominal)
Yearly capitalisations by project (exclusive of FDC)
Project ID | Project Name | Commissioning Date | Category^ |  | 2002 (6 mths) | 2002/03 | 2003/04 | 2004/05 | 2005/06* | 2006/07* | TOTAL | REASON FOR PROJECT | Reg Test / Business Case (Y/N) | Reg Test / Business Case Cost Estimate | Reason for Variance from Cost Estimate / Expected Commissioning Date
CP.98201 | Virginia Office Complex | 2006-06-01 | STB | [5 empty] | 16.895 | 3.334 | 20.229 | Resource requirements | Bus Case | $21.00m ($2004/05)
CP.98100 | Non-System Assets - Fleet | Annual | STB |  | 0.506 | 1.481 | 2.095 | 1.534 | 2.975 | 4.094 | 12.685 | Annual Cycle | Annual Budget
CP.98200 | NN - BUILDINGS | Annual | STB |  |  | 2.931 | 4.622 | 0.576 | 2.205 | 1.695 | 12.029 |  | Annual Budget
CP.99204 | Tools and Equipment | Various | STB |  | 0.317 | 0.154 | 0.358 | 0.446 | 1.809 | 1.661 | 4.745 |  | Purchase as required | na
CP.96502 | Electronic Document & Records Management System | 2006-09-01 | Bus IT | [5 empty] | 3.792 | 0.824 | 4.616 | Compliance | Bus Case | $4.95 (escal)
CP.96211 | Upgrade Desktop Server Configuration | 2003-12-01 | Bus IT |  | 0.549 | 2.701 |  | 0.031 |  |  | 3.281 | Rationalisation | Bus Case | $2.5m ($2002/03) | Additional purchases of servers and labour cost of installation.
CP.99206 | NN - Live Substation Work Network | n/a | STB |  | 1.535 | 0.765 | 0.016 |  |  |  | 2.316 | Network access limitations | Bus Case
CP.96256 | Desktop Replacement Program 01/02 | 2002-06-01 | Bus IT |  | 1.253 | 0.789 |  |  |  |  | 2.042 | Obsolescence | Bus Case | $1.00m (escal) | Additional costs of laptops, printers and associated labour.
CP.96700 | 06/07 Desktop replacement |  | Bus IT | [6 empty] | 1.9 | 1.9
CP.96300 | Desktop Replacement Program 2002 - 2003 | 2003-06-01 | Bus IT |  |  | 0.741 | 1.009 | 0.002 |  |  | 1.752 | obsolescence | Bus Case | $1.5m (escal) | Additional costs for computers and printers.
CP.98500 | LAND Acquisition | Various | STB |  | 0.078 | 0.352 | 0.239 | 0.293 | 0.25 | 0.257 | 1.469 | Load Growth/Reliability | Various | N/A
CP.01085 | Transmission Line Emergency Restoration | 2005-12-01 | STB |  |  |  |  | 1.226 | 0.171 |  | 1.397 | Emergency Restoration | Bus Case | $1.13m (escal) | Cost overruns due to purchase of additional equipment required to improve utilisation of the system and additional training costs.
CP.96600 | Desktop and IT Asset Replacement Program 2005-06 | 2006-06-01 | Bus IT | [5 empty] | 1.37 |  | 1.37 | IT Replacement | Bus Case | $1.5m (escal)
CP.99205 | Tools & Equipment - Operations | Various | STB |  | 0.35 | 0.055 | 0.211 | 0.211 | 0.175 | 0.324 | 1.326 |  | Various | N/A
CP.96500 | Desktop & IT Asset Replacement 2004-05 | 2005-06-01 | Bus IT |  |  |  |  | 1.067 | 0.25 |  | 1.317 | Replacement | Bus Case | $1.4m (escal)
CP.96400 | Desktop Replacement Program 2003 - 2004 | 2004-06-01 | Bus IT |  |  |  | 1.223 | 0.049 |  |  | 1.272 | Obsolescence | Bus Case | $1.3m (escal)
CP.99203 | Tools & Equipment Engineering | Various | STB |  | 0.122 | 0.129 | 0.193 | 0.501 | 0.154 | 0.166 | 1.265 |  | Various | N/A
CP.96212 | Enhance Security Services | 2002-12-01 | Bus IT |  |  | 1.28 | -0.066 |  |  |  | 1.214 | Security | Bus Case | $1.1m ($2001/02)
CP.96501 | Outage Management (PAWS replacement & Resource Allocation) |  | Bus IT | [6 empty] | 1.15 | 1.15
CP.01295 | New Virginia Mux & PABX | 2006-07-01 | STB | [6 empty] | 0.937 | 0.937 | Security | Bus Case | $0.93 (escal)
CP.96231 | ASSET CONDITION MONITORING SYS | 2002-12-01 | Bus IT |  | 0.01 | 0.832 |  |  |  |  | 0.842 | Plant condition |  | $0.920 (escal)
CP.96514 | Drawing Management Upgrade to SmartPlan | 2006-05-01 | Bus IT | [5 empty] | 0.72 |  | 0.72 | Replacement | Bus Case | $0.78m (escal)
CP.96285 | Implement SAP Enterprise Portal | 2004-08-01 | Bus IT |  |  |  |  | 0.702 |  |  | 0.702 | Obsolescence | Bus Case | $0.77m (escal)
CP.96650 | Identity Management |  | Bus IT | [6 empty] | 0.6 | 0.6
CP.96603 | Operational Security Management Toolset | 2006-04-01 | Bus IT | [5 empty] | 0.461 |  | 0.461 | Security | Bus Case | $0.46m (escal)
CP.96507 | LIS/GIS Corridor Issues & Community Infr | 2006-06-01 | Bus IT | [5 empty] | 0.452 |  | 0.452 | Reliability | Bus Case | $0.45m (escal)
CP.96569 | OSTRAC Replacement / Network Operations Console |  | Bus IT | [6 empty] | 0.41 | 0.41
CP.96404 | Rationalise Disaster Recovery | 2006-06-01 | Bus IT | [5 empty] | 0.392 |  | 0.392 | Security | Bus Case | $0.43m (escal)
CP.96604 | Computer Based Learning & Assessment | 2007-11-30 | Bus IT | [6 empty] | 0.391 | 0.391
CP.96506 | Incident Management System | 2006-06-30 | Bus IT | [5 empty] | 0.38 |  | 0.38
CP.96403 | Re-Inforce LAN Capacity | 2004-08-31 | Bus IT | [5 empty] | 0.354 |  | 0.354 | Age/Obsolescence/Condition | Bus Case | $0.35m (escal)
CP.98700 | OFFICE EQUIP - NON SYSTEM ASSETS | Various | STB |  | 0.133 | 0.088 | 0.061 | 0.061 |  |  | 0.343 | Obsolescence | various
CP.96565 | Work Tracking / Disputes & Claims Management | 2007-05-31 | Bus IT | [6 empty] | 0.3 | 0.3
CP.96405 | Upgrade SAN | 2005-12-01 | Bus IT | [5 empty] | 0.291 |  | 0.291 |  | Bus Case | $0.22m (escal)
CP.96516 | Upgrade SAP Netweaver Infrastructure | 2006-04-01 | Bus IT | [5 empty] | 0.29 |  | 0.29 | Replacement | Bus Case | $0.28m (escal)
CP.96283 | OHASIS Hazzard Management System St 1 | 2002-10-01 | Bus IT |  |  | 0.28 |  |  |  |  | 0.28 | Compliance | Bus Case | $0.37m (escal)
CP.96512 | Enterprise Architecture Tool | 2005-12-01 | Bus IT | [5 empty] | 0.28 |  | 0.28 | Replacement | Bus Case | $0.28m (escal)
CP.96001 | BIS PR001 Maintain Computing Platform 00 | 2001-12-01 | Bus IT |  | 0.045 | 0.225 |  |  |  |  | 0.27 | Obsolescence
CP.96568 | Redevelop the DIMA | [8 empty] | 0.27 | 0.27
CP.96150 | Implement LIMS | 2002-03-31 | Bus IT |  |  |  | 0.232 |  |  |  | 0.232 | New Requirements | approval memo | $0.17m (escal)
CP.01305 | Virginia Telstra Connection | 2006-10-01 | STB | [6 empty] | 0.223 | 0.223 | Security | Bus Case | $0.22m (escal)
CP.96407 | Software Testing Tool | 2005-09-01 | Bus IT | [5 empty] | 0.222 |  | 0.222 | Security | Bus Case | $0.22m (escal)
CP.96664 | Develop System-Level Policies | 2006-09-30 | Bus IT | [6 empty] | 0.211 | 0.211
CP.96662 | Enhanced Internal Network Integrity and Security | 2006-11-30 | Bus IT | [6 empty] | 0.204 | 0.204
CP.99200 | NN - TOOLS & EQUIP | Various | STB |  | 0.089 |  |  | 0.11 |  |  | 0.199
CP.96408 | IT Asset Tracking Tool | 2005-04-01 | Bus IT |  |  |  |  | 0.193 |  |  | 0.193 | Compliance | Bus Case | $0.20m (escal)
CP.96259 | BIS PR259 IMPLEMENT TOWER STRUCTURE ANAL |  | Bus IT |  | 0.012 | 0.17 |  |  |  |  | 0.182
CP.96515 | Enhance IT Design Development Environment | 2005-12-01 | Bus IT | [5 empty] | 0.177 |  | 0.177 | Network Security | Bus Case | $0.15m (escal)
CP.96504 | Audit Management Application | 2005-09-01 | Bus IT |  |  |  |  | 0.006 | 0.16 |  | 0.166 | Improve audit process | Bus Case | $0.17m (escal)
CP.96555 | Improve Drawing Retrieval (In AIM) | 2005-11-15 | Bus IT | [5 empty] | 0.161 |  | 0.161 | Improve drawing retrieval | Bus Case | $0.14m (escal)
CP.96508 | POW Enhancements | 2005-10-01 | Bus IT | [5 empty] | 0.156 |  | 0.156 | Portal development | Bus Case | $0.15m (escal)
CP.96402 | Building Cabling Implementation | 2004-02-28 | Bus IT |  |  |  | 0.141 | 0.009 |  |  | 0.15 | Telecomms cabling | Bus Case | $0.15m (escal)
CP.96511 | Two - Factor Authentication | 2005-11-01 | Bus IT | [5 empty] | 0.149 |  | 0.149 | Computer network security | Bus Case | $0.22m (escal)
CP.96401 | MSP Interface | 2003-09-30 | Bus IT | [5 empty] | 0.148 |  | 0.148 | SAP access | Bus Case | $0.15m (escal)
CP.96234 | Extend Powerlink Web Site | 2002-12-01 | Bus IT |  |  | 0.147 |  |  |  |  | 0.147 |  | approval memo
CP.96406 | SAP XI Licensing | 2003-12-31 | Bus IT |  |  |  | 0.143 |  |  |  | 0.143 | SAP Licences | Bus Case | $0.15m (escal)
CP.96668 | Exchange 2003 Upgrade | 2006-08-31 | Bus IT | [6 empty] | 0.132 | 0.132
CP.96652 | Implement SOE Management Toolset | 2006-01-01 | Bus IT | [5 empty] | 0.13 |  | 0.13 | Computer network management | Bus Case | $0.13m (escal)
CP.96563 | TOIAL Stage 2 - Assessments | 2007-02-28 | Bus IT | [6 empty] | 0.125 | 0.125
CP.96129 | BIS PR129 Land Information System Ext |  | Bus IT |  |  | 0.123 |  |  |  |  | 0.123
CP.96301 | Additional SAP Licences | 2002-12-31 | Bus IT |  |  | 0.121 |  |  |  |  | 0.121 | SAP Licences | Bus Case | $0.18m (escal)
CP.96509 | Concord Library Replacement | 2005-06-30 | Bus IT | [5 empty] | 0.116 |  | 0.116 | Replacement | Bus Case | $0.18m (escal)
CP.96669 | Security Audit | 2006-10-31 | Bus IT | [6 empty] | 0.108 | 0.108
CP.96800 | Minor IT Projects | Various | Bus IT | [5 empty] | 0.101 |  | 0.101
CP.96271 | Implement Help Desk Management System | 2002-11-01 | Bus IT |  |  |  | 0.094 |  |  |  | 0.094 | It Management | Bus Case | $0.10m (escal)
CP.01044 | Belmont Storage Shed | 2003-07-01 | STB |  |  |  | 0.084 |  |  |  | 0.084 | Security | N | $0.09m (escal)
CP.96239 | Desktop Replacement Program 00 | 2001-01-01 | Bus IT |  | 0.047 | 0.036 |  |  |  |  | 0.083 | Obsolescence | Bus Case
CP.96513 | Replace Reflection X (with Bluezone X) | 2005-05-01 | Bus IT | [5 empty] | 0.073 |  | 0.073 | Obsolescence |  | $0.09m (escal)
CP.99207 | NN - TOOLS NETWORK BUSINESS UNIT | Various | STB |  |  |  | 0.019 | 0.002 | 0.025 | 0.026 | 0.072
| Expenditure not through projects |  |  |  |  | 0.057 |  |  |  |  | 0.057
CP.96510 | Tax Management Application | 2004-11-01 | Bus IT |  |  |  |  | 0.052 |  |  | 0.052 | Compliance |  | $0.08m (escal)
CP.96255 | BIS PR255 TRANSFORMER & LINES RATING SYS |  | Bus IT |  |  | 0.034 |  |  |  |  | 0.034 | Compliance
CP.99209 | NN TOOLS & EQUIPMENT PLANNING & ER&D | Various | STB |  | 0.003 | 0.006 | 0.001 | 0.018 |  |  | 0.028
CP.96601 | Replace Grid DB |  | Bus IT | [6 empty] | 0.005 | 0.005 | Obsolescence |  | $1.14m (escal) | Majority of project capitalised prior to current regulatory period.
CP.99208 | NN - Tools Engineering | Various | STB |  |  |  | 0.005 |  |  |  | 0.005
|  |  |  | Subtotal | 5.049 | 13.497 | 10.68 | 7.089 | 35.284 | 19.347 | 90.946
|  |  | ^refers to Categories set out in table 3.1 (e.g Augmentation, Replacement etc) | [5 empty] | *Note that values in these columns are estimates only

## Forecast Capex by Category
4.1 FORECAST CAPEX by project category |  |  | Home |  | Link to Forecast Capex Instructions - Table 6.3
$m, real (06/07)
WORKING
Project Category |  |  | 2007/08 | 2008/09 | 2009/10 | 2010/11 | 2011/12 | TOTAL
[10 empty] | PLQ1 | PLQ2
NETWORK
LOAD DRIVEN | Augmentation |  | 364.258 | 364.14 | 172.366 | 177.192 | 144.758 | 1222.714 | 88.992 | 2170.28
| Easements |  | 20.31 | 15.702 | 11.591 | 19.244 | 37.223 | 104.07 | 22.99 | 215.428
| Connections |  | 23.696 | 7.558 | 12.272 | 11.014 | 14.49 | 69.03 | 18.378 | 148.88
| Other |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
NON-LOAD DRIVEN | Replacements |  | 113.716 | 93.584 | 208.065 | 196.385 | 201.048 | 812.798 | 94.983 | 1626.995
| Security/Compliance |  | 2.633 | 33.022 | 23.379 | 37.001 | 19.816 | 115.851 | 2.892 | 201.572
| Other |  | 2.637 | 7.357 | 5.507 | 5.323 | 0.234 | 21.058 | 5.341 | 40.1
NON NETWORK
BUSINESS IT |  | Information Technology | 11.903 | 11.198 | 11.052 | 10.887 | 12.341 | 57.381 | 6.629 | 110.193
SUPPORT THE BUSINESS |  | Commercial Buildings | 2.568 | 5.695 | 6.209 | 3.595 | 1.541 | 19.608 | 6.446 | 39.967
|  | Motor Vehicles | 2.69 | 2.915 | 4.222 | 4.365 | 4.32 | 18.512 | 4.094 | 38.203
|  | Tools | 1.892 | 1.846 | 1.44 | 1.486 | 1.553 | 8.217 | 2.177 | 16.765
TOTAL FORECAST CAPEX |  |  | 546.303 | 543.017 | 456.103 | 466.492 | 437.324 | 2449.239

## Forecast Capex by Asset Class
4.2 FORECAST CAPEX by asset class | Home |  |  | Link to Capex Instructions - Table 6.3
($m, real 06/07) | 2007/08 | 2008/09 | 2009/10 | 2010/11 | 2011/12 | TOTAL
Asset class
Transmission Lines (steel tower, steel pole, concrete pole) | 230.052 | 269.237 | 182.607 | 197.585 | 107.135 | 986.616
Transmission Lines (underground) | 11.241 | 18.256 | 26.731 | 13.129 | 66.985 | 136.342
Substations Primary Plant | 198.477 | 158.589 | 145.431 | 98.562 | 93.953 | 695.012
Substations Secondary Systems | 57.997 | 41.508 | 55.669 | 91.378 | 103.722 | 350.274
Communications (buildings, towers and site infrastructure) | 0.102 | 4.414 | 0.197 | 4.05 | 0.097 | 8.86
Communications (other assets) | 8.654 | 13.398 | 10.952 | 22.21 | 8.453 | 63.667
Network Switching Centres | 0.419 | 0.258 | 0.003 | 0 | 0 | 0.68
Easements | 20.31 | 15.702 | 11.591 | 19.244 | 37.223 | 104.07
Land | 0.257 | 0.257 | 0.257 | 0.257 | 0.257 | 1.285
Commercial Buildings | 2.568 | 5.695 | 6.209 | 3.595 | 1.541 | 19.608
Houses | 0 | 0 | 0 | 0 | 0 | 0
Computer equipment | 11.903 | 11.198 | 11.052 | 10.887 | 12.341 | 57.381
Office Furniture and Misc | 0.154 | 0.154 | 0.154 | 0.154 | 0.154 | 0.77
Office Machines | 0 | 0 | 0 | 0 | 0 | 0
Vehicles | 2.69 | 2.915 | 4.222 | 4.365 | 4.32 | 18.512
Moveable Plant | 1.481 | 1.435 | 1.029 | 1.075 | 1.142 | 6.162
Other | 0 | 0 | 0 | 0 | 0 | 0
TOTAL CAPEX | 546.305 | 543.016 | 456.104 | 466.491 | 437.323 | 2449.239

## Forecast Capex - Network Common
4.3(a) FORECAST CAPEX - Network - by project
[7 empty] | Home |  | Provided for information only |  |  |  | Link to Forecast Capex Instructions - Table 6.3
$m, real (06/07) | [10 empty] | Yearly expenditure by project
No. Scenarios | Probability | Project No. | Project Name | Earliest date | Latest date | Date Diff | Category |  | 2005/06 | 2006/07 | 2007/08 | 2008/09 | 2009/10 | 2010/11 | 2011/12 | TOTAL | Reason for project | Reg test/BC (RT/BC) | Reg test/BC cost est
40 | 100% | CP.01094 | Belmont Murarrie Transmission Reinforcement | 2006-10-30 | 2006-10-30 | 0 | Augmentation |  | 28.3093 | 2.8408 | 0.098295 | 0 | 0 | 0 | 0 | 0.098295 | Reliability | RT | $39.5m ($2003/04) $42.6m (escal)
40 | 100% | CP.01187 | Molendinar 275/110kV Transformer Reinforcement | 2006-10-31 | 2006-10-31 | 0 | Augmentation |  | 3.7167 | 0.35137 | 0.010229 | 0 | 0 | 0 | 0 | 0.010229 | Reliability | RT | $6.9m ($2004/05)
40 | 100% | CP.01124 | Mackay Transmission Reinforcement | 2007-10-30 | 2007-10-30 | 0 | Augmentation |  | 5.2618 | 27.8005 | 13.6313 | 0.017128 | 0 | 0 | 0 | 13.6484 | Reliability | RT | $44.7m (2005/06) $51.4m (escal)
40 | 100% | CP.01144 | Townsville East Substation Establishment | 2007-10-30 | 2007-10-30 | 0 | Augmentation |  | 1.211 | 16.322 | 6.4916 | 0.008545 | 0 | 0 | 0 | 6.5002 | Reliability | RT | $23.4m (2005/06) $24.3m (escal)
40 | 100% | CP.01294 | Strathmore 275kV SVC | 2007-10-30 | 2007-10-30 | 0 | Augmentation |  | 1.0486 | 20 | 16.4989 | 0 | 0 | 0 | 0 | 16.4989 | Reliability | RT | $36.3m (2005/06) $38.0m (escal)
40 | 100% | CP.01035 | Ross to Townsville South Transmission Reinforcement | 2007-10-31 | 2007-10-31 | 0 | Augmentation |  | 0.75697 | 10.3868 | 5.1404 | 0 | 0 | 0 | 0 | 5.1404 | Reliability | RT | $16.2m (2005/06) $17.3m (escal)
40 | 100% | CP.01138 | SEQ Augmentation | 2007-10-31 | 2007-10-31 | 0 | Augmentation |  | 3.8485 | 46.2326 | 48.251 | 0.047026 | 0 | 0 | 0 | 48.298 | Reliability | RT | $94.84m (2005/06) $99.87m (escal)
40 | 100% | CP.01186 | North Qld Transmission Reinforcement - Stage 1 | 2007-10-31 | 2007-10-31 | 0 | Augmentation |  | 4.0126 | 60.1836 | 26.2538 | 0.057213 | 0 | 0 | 0 | 26.311 | Reliability | RT | $87.5m (2005/06) $91.2m (escal)
40 | 100% | CP.01204 | Lilyvale to Blackwater 132kV Transmission Line | 2007-10-31 | 2007-10-31 | 0 | Augmentation |  | 1.2537 | 14.8938 | 10.1171 | 0 | 0 | 0 | 0 | 10.1171 | Reliability | RT | $28.8m (2005/06) $30.29m (escal)
40 | 100% | CP.01247 | Mudgeeraba to Terranora 110kV Line Uprating | 2007-10-31 | 2007-10-31 | 0 | Augmentation |  | 0 | 0.111 | 0.13118 | 0 | 0 | 0 | 0 | 0.13118 | Reliability | BC | $0.27m (2005/06) $0.283m (escal)
40 | 100% | CP.01119/A | Oakey 110/33kV Substation Establishment | 2007-11-30 | 2007-11-30 | 0 | Augmentation |  | 0.19926 | 2.0418 | 0.20237 | 0 | 0 | 0 | 0 | 0.20237 | Reliability
40 | 100% | CP.01198 | Wide Bay Transmission Reinforcement | 2007-12-31 | 2007-12-31 | 0 | Augmentation |  | 4.3165 | 28.5631 | 3.1443 | 0.025376 | 0 | 0 | 0 | 3.1697 | Reliability
40 | 100% | CP.01090 | Woree 275kV Reinforcement | 2008-04-30 | 2008-04-30 | 0 | Augmentation |  | 0.41491 | 2.696 | 10.0214 | 3.6155 | 0 | 0 | 0 | 13.6369 | Reliability | BC | $12.4m (2005/06) $13.43m (escal)
40 | 100% | CP.01137/B | Ross to Yabulu Transmission Reinforcement | 2008-09-30 | 2008-09-30 | 0 | Augmentation |  | 0 | 7.6046 | 25.9838 | 2.0418 | 0 | 0 | 0 | 28.0256 | Reliability
40 | 100% | CP.01101 | NQ Transmission Reinforcement - Stage 2 | 2008-10-31 | 2008-10-31 | 0 | Augmentation |  | 2.991 | 19.4053 | 42.0954 | 45.2636 | 0.013693 | 0 | 0 | 87.3727 | Reliability | RT | $94.6m (2005/06) $102.5m (escal)
40 | 100% | CP.01266 | Abermain 275kV Substation Establishment | 2008-10-31 | 2008-10-31 | 0 | Augmentation |  | 2.2528 | 6.1928 | 11.1236 | 1.1082 | 0.002459 | 0 | 0 | 12.2343 | Reliability | RT | $19.6m (2004/05) $21.6m (escal)
40 | 100% | CP.01317 | Ashgrove West 3rd 110kV 50MVAr Capacitor Bank | 2009-05-31 | 2009-05-31 | 0 | Augmentation |  | 0 | 0.15767 | 0.069885 | 1.6564 | 0 | 0 | 0 | 1.7263 | Reliability
40 | 100% | CP.01316 | Rocklea 4th 110kV 50MVAr Capacitor Bank | 2009-07-31 | 2009-07-31 | 0 | Augmentation |  | 0 | 0 | 0.20469 | 1.626 | 0.055288 | 0 | 0 | 1.886 | Reliability
40 | 100% | CP.01930 | Belmont 4th 110kV 50MVAr Capacitor Bank | 2010-07-31 | 2010-07-31 | 0 | Augmentation |  | 0 | 0 | 0 | 0.20641 | 1.64 | 0.05577 | 0 | 1.9021 | Reliability
40 | 100% | CP.01929 | South Pine 4th 110kV 50MVAr Capacitor Bank | 2010-07-31 | 2010-07-31 | 0 | Augmentation |  | 0 | 0 | 0 | 0.20641 | 1.64 | 0.05577 | 0 | 1.9021 | Reliability
40 | 100% | CP.01931 | Loganlea 4th 110kV 50MVAr Capacitor Bank | 2010-09-30 | 2010-09-30 | 0 | Augmentation |  | 0 | 0 | 0 | 0.19211 | 1.3506 | 0.36217 | 0 | 1.9049 | Reliability
40 | 100% | CP.01933 | Moreton North 2nd 110kV 50MVAr Capacitor Bank | 2011-05-31 | 2011-05-31 | 0 | Augmentation |  | 0 | 0 | 0 | 0.16042 | 0.071076 | 1.6851 | 0 | 1.9166 | Reliability
40 | 100% | CP.01199 | QR Mindi Establishment | 2007-02-28 | 2007-02-28 | 0 | Connection |  | 3.5456 | 8.5273 | 0.11078 | 0 | 0 | 0 | 0 | 0.11078 | Connection | BC | $11.4m ($2005/06) $11.8m (escal)
40 | 100% | CP.01300 | Loganlea 110kV Extensions (Browns Plains) | 2007-07-31 | 2007-07-31 | 0 | Connection |  | 0.2629 | 0.79664 | 0.011641 | 0 | 0 | 0 | 0 | 0.011641 | Reliability | BC | $1.057m (2005/06) $1.11m (escal)
40 | 100% | CP.01258 | Rocklea/Tennyson 110kV Series Reactor | 2007-09-30 | 2007-09-30 | 0 | Connection |  | 0.24206 | 0.8317 | 0.065399 | 0 | 0 | 0 | 0 | 0.065399 | Reliability
40 | 100% | CP.01192 | Biloela Transformer Augmentation | 2007-10-30 | 2007-10-30 | 0 | Connection |  | 0.24443 | 6.1887 | 0.4158 | 0 | 0 | 0 | 0 | 0.4158 | Reliability | BC | $6.88m (escal)
40 | 100% | CP.01267 | Mudgeeraba 110/33kV Substation Establishment | 2007-10-31 | 2007-10-31 | 0 | Connection |  | 0.2534 | 3.363 | 0.042352 | 0 | 0 | 0 | 0 | 0.042352 | Reliability | BC | $4.68m (escal)
40 | 100% | CP.01531 | Bundamba 110/11kV Transformer | 2008-06-30 | 2008-06-30 | 0 | Connection |  | 0 | 3.3007 | 1.5462 | 0 | 0 | 0 | 0 | 1.5462 | Reliability
40 | 100% | CP.01628 | Alligator Creek 132kV Feeders Bays for Louisa Creek | 2008-09-30 | 2008-09-30 | 0 | Connection |  | 0 | 0.97783 | 3.3444 | 0.26305 | 0 | 0 | 0 | 3.6075 | Reliability
40 | 100% | CP.01821 | North Goonyella Upgrade | 2011-05-31 | 2011-05-31 | 0 | Connection |  | 0 | 0 | 0 | 0.49562 | 1.9095 | 5.2571 | 0 | 7.6622 | Reliability
40 | 100% | CP.01100 | Middle Ridge to Greenbank Easement Acquisition | 2006-10-31 | 2006-10-31 | 0 | Easements |  | 0 | 0 | 0.015145 | 0 | 0 | 0 | 0 | 0.015145 | Construction | BC | $5.5m (escal)
40 | 100% | CP.01693/A | Alligator Creek Additional Land and Rights Acquisition (TE) | 2008-03-31 | 2008-03-31 | 0 | Easements |  | 0.025954 | 0.14288 | 0.034984 | 0 | 0 | 0 | 0 | 0.034984 | Construction
40 | 100% | CP.01078 | Nudgee 275/110kV Easement Acquisition | 2009-07-31 | 2009-07-31 | 0 | Easements |  | 0.49707 | 3.2502 | 3.3039 | 0 | 0 | 0 | 0 | 3.3039 | Construction | BC | $6.2m (escal)
40 | 100% | CP.01693/B | Alligator Creek Additional Land and Rights Acquisition (Compensation) | 2009-08-31 | 2009-08-31 | 0 | Easements |  | 0 | 0 | 0.00139 | 0.004617 | 0 | 0 | 0 | 0.006007 | Construction
40 | 100% | CP.01808/A | Walkamin 275/132kV Substation and Easement Acquisition (TE) | 2009-09-30 | 2009-09-30 | 0 | Easements |  | 0 | 0 | 0.34436 | 0.26502 | 0.045325 | 0 | 0 | 0.65471 | Strategic
40 | 100% | CP.01694/A | Brisbane West Transition Site Easement Acquisition (TE) | 2009-10-31 | 2009-10-31 | 0 | Easements |  | 0 | 0 | 0.41147 | 0.40715 | 0.077369 | 0 | 0 | 0.89599 | Construction
40 | 100% | CP.01681/A | Midpoint Ross Chalumbin Site Acquisition (TE) | 2010-07-31 | 2010-07-31 | 0 | Easements |  | 0 | 0 | 0 | 0.22355 | 0.10323 | 0.01177 | 0 | 0.33855 | Strategic
40 | 100% | CP.01808/B | Walkamin 275/132kV Substation and Easement Acquisition (Compensation) | 2010-09-30 | 2010-09-30 | 0 | Easements |  | 0 | 0 | 0 | 0.020667 | 0.33951 | 0 | 0 | 0.36018 | Strategic
40 | 100% | CP.01694/B | Brisbane West Transition Site Easement Acquisition (Compensation) | 2010-10-31 | 2010-10-31 | 0 | Easements |  | 0 | 0 | 0 | 0.051029 | 1.2248 | 0.062343 | 0 | 1.3381 | Construction
40 | 100% | CP.01681/B | Midpoint Ross Chalumbin Site Acquisition (Compensation) | 2011-07-31 | 2011-07-31 | 0 | Easements |  | 0 | 0 | 0 | 0 | 0.12093 | 0.17511 | 0 | 0.29604 | Strategic
40 | 100% | CP.01813/A | Stockleigh 275/110kV Substation and Easement Acquisition (TE) | 2011-09-30 | 2011-09-30 | 0 | Easements |  | 0 | 0 | 0 | 0 | 0.4362 | 0.3357 | 0.057413 | 0.82932 | Strategic
40 | 100% | CP.01865/A | South Coast 500kV Double Circuit Easement Acquisition (TE) | 2011-10-31 | 2011-10-31 | 0 | Easements |  | 0 | 0 | 0 | 0 | 1.7889 | 1.7701 | 0.33637 | 3.8954 | Strategic
40 | 100% | CP.00705/A | South Coast No. 1 275/110kV Substation Land Acquisition (TE component) | 2011-10-31 | 2011-10-31 | 0 | Easements |  | 0 | 0 | 0 | 0 | 0.31133 | 0.30806 | 0.058538 | 0.67792 | Strategic
40 | 100% | CP.01846/A | Kenilworth to Existing Eastern Corridor 275kV Double Circuit Easement Acquisition (TE) | 2012-07-31 | 2012-07-31 | 0 | Easements |  | 0 | 0 | 0 | 0 | 0 | 1.9173 | 0.88536 | 2.8027 | Strategic
40 | 100% | CP.01964/A | Beenleigh 275/110kV Land and Easement Acquisition (TE) | 2012-08-31 | 2012-08-31 | 0 | Easements |  | 0 | 0 | 0 | 0 | 0 | 2.9475 | 1.7643 | 4.7118 | Strategic
40 | 100% | CP.01831/A | Murarrie to Nudgee 275kV Cable Easement Acquisition (TE) | 2012-08-31 | 2012-08-31 | 0 | Easements |  | 0 | 0 | 0 | 0 | 0 | 1.8195 | 1.0891 | 2.9085 | Strategic
40 | 100% | CP.01813/B | Stockleigh 275/110kV Substation and Easement Acquisition (Compensation) | 2012-09-30 | 2012-09-30 | 0 | Easements |  | 0 | 0 | 0 | 0 | 0 | 0.12524 | 2.0575 | 2.1827 | Strategic
40 | 100% | CP.01865/B | South Coast 500kV Double Circuit Easement Acquisition (Compensation) | 2012-10-31 | 2012-10-31 | 0 | Easements |  | 0 | 0 | 0 | 0 | 0 | 0.46757 | 11.2222 | 11.6897 | Strategic
40 | 100% | CP.00705/B | South Coast No. 1 275/110kV Substation Land Acquisition (Compensation) | 2012-10-31 | 2012-10-31 | 0 | Easements |  | 0 | 0 | 0 | 0 | 0 | 0.073743 | 1.7699 | 1.8436 | Strategic
40 | 100% | CP.01219/A | Tully 275kV Substation Land Acquisition (TE component) | 2012-10-31 | 2012-10-31 | 0 | Easements |  | 0 | 0 | 0 | 0 | 0 | 0.14333 | 0.14182 | 0.28515 | Strategic
40 | 100% | CP.01867/A | Nebo to Moranbah 275kV Double Circuit Easement Acquisition (TE) | 2013-05-31 | 2013-05-31 | 0 | Easements |  | 0 | 0 | 0 | 0 | 0 | 0 | 1.8267 | 1.8267 | Strategic
40 | 100% | CP.01810/A | Ripley 110/33kV Substation and Easement Acquisition (TE) | 2013-05-31 | 2013-05-31 | 0 | Easements |  | 0 | 0 | 0 | 0 | 0 | 0 | 1.0925 | 1.0925 | Strategic
40 | 100% | CP.01846/B | Kenilworth to Existing Eastern Corridor 275kV Double Circuit Easement Acquisition (Compensation) | 2013-07-31 | 2013-07-31 | 0 | Easements |  | 0 | 0 | 0 | 0 | 0 | 0 | 1.179 | 1.179 | Strategic
40 | 100% | CP.01964/B | Beenleigh 275/110kV Land and Easement Acquisition (Compensation) | 2013-08-31 | 2013-08-31 | 0 | Easements |  | 0 | 0 | 0 | 0 | 0 | 0 | 3.6183 | 3.6183 | Strategic
40 | 100% | CP.01831/B | Murarrie to Nudgee 275kV Cable Easement Acquisition (Compensation) | 2013-08-31 | 2013-08-31 | 0 | Easements |  | 0 | 0 | 0 | 0 | 0 | 0 | 1.7299 | 1.7299 | Strategic
40 | 100% | CP.01219/B | Tully 275kV Substation Land Acquisition (Compensation) | 2013-10-31 | 2013-10-31 | 0 | Easements |  | 0 | 0 | 0 | 0 | 0 | 0 | 0.026896 | 0.026896 | Strategic
40 | 100% | CP.01926 | Alligator Creek 132/33kV Transformer Replacements | 2008-10-31 | 2008-10-31 | 0 | Augmentation |  | 0 | 3.3786 | 12.918 | 0.52747 | 0 | 0 | 0 | 13.4455 | Operational
40 | 100% | CP.01067 | Clare Substation Rebuild | 2009-10-31 | 2009-10-31 | 0 | Augmentation |  | 0 | 0 | 2.0189 | 8.7831 | 1.3824 | 0 | 0 | 12.1844 | Reliability
40 | 100% | CP.01960/A | Yabulu South to Tully Easement Widening/Acquisition (TE) | 2009-05-30 | 2009-05-30 | 0 | Easements |  | 0 | 0 | 4.4215 | 1.1343 | 0 | 0 | 0 | 5.5558 | Construction
40 | 100% | CP.01828/A | Easement Clearance for Rebuild of Transmission Feeders from Strathmore to Collinsville (TE) | 2009-06-30 | 2009-06-30 | 0 | Easements |  | 0 | 0 | 0.58805 | 0.21943 | 0 | 0 | 0 | 0.80748 | Construction
40 | 100% | CP.01960/B | Yabulu South to Tully Easement Widening/Acquisition (Compensation) | 2010-02-28 | 2010-02-28 | 0 | Easements |  | 0 | 0 | 0 | 4.1958 | 1.257 | 0 | 0 | 5.4528 | Construction
40 | 100% | CP.01828/B | Easement Clearance for Rebuild of Transmission Feeders from Strathmore to Collinsville (Compensation) | 2010-06-30 | 2010-06-30 | 0 | Easements |  | 0 | 0 | 0 | 0.039366 | 0.027519 | 0 | 0 | 0.066885 | Construction
40 | 100% | CP.01851/A | Dysart Substation Extension (TE) | 2011-10-31 | 2011-10-31 | 0 | Easements |  | 0 | 0 | 0 | 0 | 0.10322 | 0.10214 | 0.019409 | 0.22477 | Construction
40 | 100% | CP.01851/B | Dysart Substation Extension (Compensation) | 2012-10-31 | 2012-10-31 | 0 | Easements |  | 0 | 0 | 0 | 0 | 0 | 0.000123 | 0.002963 | 0.003086 | Construction
40 | 100% | CP.01313 | Ross to Chalumbin OPGW Retrofit | 2007-08-31 | 2007-08-31 | 0 | Other |  | 0.97909 | 7.2899 | 0.084059 | 0 | 0 | 0 | 0 | 0.084059 | Operational
40 | 100% | CP.01312 | Minnipi Parklands to Charlotte St Fibre Cable Installation | 2007-10-31 | 2007-10-31 | 0 | Other |  | 0.27093 | 0.20988 | 0.00228 | 0 | 0 | 0 | 0 | 0.00228 | Operational
40 | 100% | CP.01309 | Replacement of Quiescent PLC Equipment | 2007-12-31 | 2007-12-31 | 0 | Other |  | 0.099623 | 0.26536 | 0.003196 | 0 | 0 | 0 | 0 | 0.003196 | Obsolescence/Operational
40 | 100% | CP.01924 | Spare 330/275kV Transformer (at Braemar) | 2009-08-30 | 2009-08-30 | 0 | Other |  | 0 | 0 | 1.6533 | 5.3453 | 0.034881 | 0 | 0 | 7.0335 | Operational
40 | 100% | CP.01623 | Kamerunga Bus Section circuit breaker | 2009-10-31 | 2009-10-31 | 0 | Other |  | 0 | 0 | 0.15899 | 0.69257 | 0.10915 | 0 | 0 | 0.96071 | Operational
40 | 100% | CP.01736 | Fujitsu TP1 - DE11 PLC Replacement - Version 2 | 2009-10-31 | 2009-10-31 | 0 | Other |  | 0 | 0 | 0.73531 | 0.56431 | 0.006101 | 0 | 0 | 1.3057 | Operational
40 | 100% | CP.01803 | EMS FEPs Update | 2010-09-30 | 2010-09-30 | 0 | Other |  | 0 | 0 | 0 | 0.31099 | 0.12473 | 0.001846 | 0 | 0.43757 | Reliability/Operational
40 | 100% | CP.01622 | Cardwell Substation Line Switching | 2010-10-31 | 2010-10-31 | 0 | Other |  | 0 | 0 | 0 | 0.44358 | 1.9245 | 0.30207 | 0 | 2.6702 | Operational
40 | 100% | CP.01301 | Power Quality Monitoring - Stages 1 and 2 | 2011-09-30 | 2011-09-30 | 0 | Other |  | 0 | 0 | 0 | 0 | 2.7237 | 1.0865 | 0.015994 | 3.8262 | Operational
40 | 100% | CP.01745 | Virginia to Mt Gravatt Microwave Radio Replacement | 2011-10-30 | 2011-10-30 | 0 | Other |  | 0 | 0 | 0 | 0 | 0.2565 | 0.19784 | 0.00215 | 0.4565 | Obsolescence/Operational
40 | 100% | CP.01738 | Mt Gravatt to Tennyson Microwave Radio Installation | 2011-10-31 | 2011-10-31 | 0 | Other |  | 0 | 0 | 0 | 0 | 0.28621 | 0.22058 | 0.002395 | 0.50918 | Operational
40 | 100% | CP.01805 | EMS Gen4 Update to Gen5 | 2012-04-30 | 2012-04-30 | 0 | Other |  | 0 | 0 | 0 | 0 | 0.04095 | 3.1745 | 0.076966 | 3.2924 | Reliability/Operational
40 | 100% | CP.01806 | EMS DIMA Upgrade | 2012-09-30 | 2012-09-30 | 0 | Other |  | 0 | 0 | 0 | 0 | 0 | 0.34006 | 0.13636 | 0.47642 | Reliability/Operational
40 | 100% | CP.01245 | Mackay to Pioneer Val Transmission Line Life Extension | 2006-10-31 | 2006-10-31 | 0 | Replacement |  | 0.11414 | 4.8031 | 0.65601 | 0.003977 | 0 | 0 | 0 | 0.65998 | Safety/Reliability | BC | $5.27m (escal)
40 | 100% | CP.01246 | Mackay to Proserpine Transmission Line Life Extension | 2006-10-31 | 2006-10-31 | 0 | Replacement |  | 1.1878 | 5.9139 | 0.009795 | 0 | 0 | 0 | 0 | 0.009795 | Safety/Reliability | BC | $5.0m ($2005/06) $5.3m (escal)
40 | 100% | CP.01213 | Mt Gravatt to Eagle Hts Microwave Upgrade | 2006-12-30 | 2006-12-30 | 0 | Replacement |  | 0.30068 | 0.091689 | 0.000974 | 0 | 0 | 0 | 0 | 0.000974 | Obsolescence | BC | $0.40m (escal)
40 | 100% | CP.01203 | South Pine 275kV 2T Transformer Replacement | 2007-03-30 | 2007-03-30 | 0 | Replacement |  | 0.82095 | 4.0544 | 0.001023 | 0 | 0 | 0 | 0 | 0.001023 | Reliability | BC | $4.91m (escal)
40 | 100% | CP.01142 | Molendinar 110kV Substation Replacement | 2007-06-01 | 2007-06-01 | 0 | Replacement |  | 10.2783 | 6.6244 | 0.000639 | 0 | 0 | 0 | 0 | 0.000639 | Reliability | BC | $17.2m ($2004/05) $17.6m (escal)
40 | 100% | CP.01022 | Townsville South Secondary Systems Upgrade | 2007-07-30 | 2007-07-30 | 0 | Replacement |  | 1.2723 | 6.7486 | 2.4058 | 0 | 0 | 0 | 0 | 2.4058 | Obsolescence | BC | $10.24m (2005/06) $10.513m (escal)
40 | 100% | CP.01286 | Tarong Substation Refurbishment | 2007-10-30 | 2007-10-30 | 0 | Replacement |  | 1.5397 | 19.369 | 2.8275 | 0.011247 | 0 | 0 | 0 | 2.8388 | Safety | BC | $22.56m (2005/06) $23.859m (escal)
40 | 100% | CP.01310 | Metropolitan Communications Loop Replacement Stage 1 | 2007-10-31 | 2007-10-31 | 0 | Replacement |  | 0.41412 | 0.31948 | 0.003461 | 0 | 0 | 0 | 0 | 0.003461 | Obsolescence
40 | 100% | CP.01087 | Bohle River to Townsville GT 132kV Line | 2007-10-31 | 2007-10-31 | 0 | Replacement |  | 3.1219 | 12.9625 | 1.8819 | 0 | 0 | 0 | 0 | 1.8819 | Safety | BC | $17.1m (2004/05) $18.024m (escal)
40 | 100% | CP.00752 | SVC Secondary Systems Replacement | 2008-06-30 | 2008-06-30 | 0 | Replacement |  | 7.2175 | 6.2924 | 10.2559 | 0 | 0 | 0 | 0 | 10.2559 | Reliability | Board Memo | $27.6m ($2004/05) $28.9m (escal)
40 | 100% | CP.01131 | Kareeya to Innisfail Transmission Line Replacement | 2008-06-30 | 2008-06-30 | 0 | Replacement |  | 2.4142 | 7.497 | 19.1384 | 18.5973 | 0 | 0 | 0 | 37.7357 | Safety/Reliability | BC | $53.12m (2005/06) $55.096m (escal)
40 | 100% | CP.01131 | Kareeya to Innisfail Transmission Line Decommissioning | 2008-06-30 | 2008-06-30 | 0 | Replacement |  | 0 | 0 | 5.4416 | 0 | 0 | 0 | 0 | 5.4416 | Safety/Reliability
40 | 100% | CP.01037 | Barron Gorge 132kV Line Maintenance | 2008-07-29 | 2008-07-29 | 0 | Replacement |  | 0 | 0.568 | 4.7809 | 0.04438 | 0 | 0 | 0 | 4.8253 | Safety/Reliability
40 | 100% | CP.01574 | Alligator Creek Secondary Systems Replacement | 2008-07-31 | 2008-07-31 | 0 | Replacement |  | 0 | 0.69968 | 2.9828 | 0.23003 | 0 | 0 | 0 | 3.2129 | Obsolescence/Safety
40 | 100% | CP.01737 | Marconi Network Management System Replacement | 2008-07-31 | 2008-07-31 | 0 | Replacement |  | 0 | 0.62988 | 0.07744 | 0.000788 | 0 | 0 | 0 | 0.078228 | Obsolescence/Reliability
40 | 100% | CP.01134 | South Pine 110kV Substation Refurbishment | 2008-10-30 | 2008-10-30 | 0 | Replacement |  | 3.3731 | 17.205 | 9.8811 | 2.6188 | 0.040398 | 0 | 0 | 12.5403 | Safety
40 | 100% | CP.01177 | Belmont 110kV Substation Refurbishment | 2008-10-30 | 2008-10-30 | 0 | Replacement |  | 0.55553 | 8.7434 | 19.7373 | 3.4945 | 0.030694 | 0 | 0 | 23.2625 | Safety
40 | 100% | CP.01130 | QAL 132/11KV Transformer Replacements | 2008-12-30 | 2008-12-30 | 0 | Replacement |  | 0 | 3.5888 | 17.9828 | 0.72281 | 0 | 0 | 0 | 18.7056 | Operational
40 | 100% | CP.01165 | West Darra Switchyard Replacement | 2009-02-28 | 2009-02-28 | 0 | Replacement |  | 0 | 2.0244 | 9.6726 | 11.0466 | 0 | 0 | 0 | 20.7192 | Operational
40 | 100% | CP.01064 | Gin Gin Secondary Systems Replacement | 2009-07-30 | 2009-07-30 | 0 | Replacement |  | 0 | 0 | 1.6099 | 6.8656 | 0.53009 | 0 | 0 | 9.0056 | Obsolescence/Safety
40 | 100% | CP.01545 | Abermain No. 2 Transformer | 2009-08-31 | 2009-08-31 | 0 | Replacement |  | 0 | 0 | 0.83624 | 2.7063 | 0.017677 | 0 | 0 | 3.5602 | Operational
40 | 100% | CP.01733 | Cairns Area Microwave Radio Replacement | 2009-10-31 | 2009-10-31 | 0 | Replacement |  | 0 | 0 | 0.2682 | 0.20703 | 0.002252 | 0 | 0 | 0.47748 | Obsolescence/Operational
40 | 100% | CP.01735 | Eagle Heights to Mudgeeraba Microwave Radio Replacement | 2009-10-31 | 2009-10-31 | 0 | Replacement |  | 0 | 0 | 0.2235 | 0.17253 | 0.001876 | 0 | 0 | 0.3979 | Obsolescence
40 | 100% | CP.01740 | Nokia Network Management System Replacement | 2009-10-31 | 2009-10-31 | 0 | Replacement |  | 0 | 0 | 0.37139 | 0.28569 | 0.003096 | 0 | 0 | 0.66017 | Obsolescence
40 | 100% | CP.01648 | Swanbank to Redbank Plains to West Darra 110kV Transmission Line Life Extension | 2009-12-30 | 2009-12-30 | 0 | Replacement |  | 0 | 0 | 0.33037 | 3.154 | 0.65235 | 0 | 0 | 4.1368 | Safety
40 | 100% | CP.01798 | Wurdong to South Pine Earthwire Replacement | Various | Various |  | Replacement |  | 0 | 0 | 1.4145 | 6.661 | 11.578 | 4.691 | 15.3937 | 39.7381 | Safety/Reliability
40 | 100% | CP.01018/A | Swanbank A Rebuild | 2010-05-30 | 2010-05-30 | 0 | Replacement |  | 0 | 0 | 0.92519 | 3.5617 | 9.7981 | 0 | 0 | 14.285 | Operational
40 | 100% | CP.01743 | Nokia SDH Multiplexer Equipment Replacement | Various | Various |  | Replacement |  | 0 | 0 | 0 | 1.6038 | 0.16245 | 1.6153 | 0.16364 | 3.5452 | Obsolescence/Operational
40 | 100% | CP.01147 | Belmont No. 5 Transformer Replacement | 2010-08-30 | 2010-08-30 | 0 | Replacement |  | 0 | 0 | 0 | 1.3708 | 4.4318 | 0.028918 | 0 | 5.8316 | Reliability
40 | 100% | CP.01741 | Nokia PDH Primary Digital Multiplexer Equipment Replacement | Various | Various |  | Replacement |  | 0 | 0 | 0 | 3.5205 | 1.2588 | 4.3662 | 0.44058 | 9.5861 | Obsolescence/Operational
40 | 100% | CP.01169 | Innisfail to Edmonton Line Replacement | 2010-08-31 | 2010-08-31 | 0 | Replacement |  | 0 | 0 | 0 | 6.8197 | 50.4108 | 0.58127 | 0 | 57.8118 | Environmental
40 | 100% | CP.01814 | Substation Underground Cables Replacement | 2010-08-31 | 2010-08-31 | 0 | Replacement |  | 0 | 0 | 0 | 0.42571 | 3.1195 | 0.035654 | 0 | 3.5809 | Obsolescence/Reliability
40 | 100% | CP.01780 | Gladstone PS Switchyard Rebuild | 2010-10-30 | 2010-10-30 | 0 | Replacement |  | 0 | 0 | 0 | 11.4219 | 49.7223 | 7.8311 | 0 | 68.9754 | Operational
40 | 100% | CP.01212 | Mt Stuart to Garbutt Microwave Radio Replacement | 2010-10-31 | 2010-10-31 | 0 | Replacement |  | 0 | 0 | 0 | 0.41743 | 0.32036 | 0.003464 | 0 | 0.74125 | Operational
40 | 100% | CP.01548 | Kareeya Substation Redevelopment | 2010-10-31 | 2010-10-31 | 0 | Replacement |  | 0 | 0 | 0 | 1.4487 | 6.3235 | 0.99864 | 0 | 8.7708 | Reliability
40 | 100% | CP.01572 | Cardwell Secondary Systems Replacement | 2010-11-30 | 2010-11-30 | 0 | Replacement |  | 0 | 0 | 0 | 0.048579 | 0.71631 | 0.22934 | 0 | 0.99423 | Obsolescence/Safety
40 | 100% | CP.01652 | West Darra to Rocklea 110kV Transmission Line Life Extension | 2010-11-30 | 2010-11-30 | 0 | Replacement |  | 0 | 0 | 0 | 0.26852 | 2.7126 | 0.26678 | 0 | 3.2479 | Safety
40 | 100% | CP.00881 | Yabulu to Ingham Line Replacement | 2011-02-28 | 2011-02-28 | 0 | Replacement |  | 0 | 0 | 0 | 5.5902 | 41.6384 | 27.029 | 0 | 74.2576 | Reliability/Safety
40 | 100% | CP.01024 | Belmont Secondary Systems 110kV Replacement | 2011-03-30 | 2011-03-30 | 0 | Replacement |  | 0 | 0 | 0 | 0.25296 | 4.1058 | 6.9116 | 0 | 11.2703 | Obsolescence/Safety
40 | 100% | CP.01581 | North Goonyella Secondary Systems Replacement | 2011-03-30 | 2011-03-30 | 0 | Replacement |  | 0 | 0 | 0 | 0.010924 | 0.1777 | 0.29978 | 0 | 0.4884 | Obsolescence/Safety
40 | 100% | CP.01016 | Nebo Secondary Systems Replacement | 2011-06-30 | 2011-06-30 | 0 | Replacement |  | 0 | 0 | 0 | 0 | 2.5673 | 9.1447 | 0 | 11.712 | Obsolescence/Safety
40 | 100% | CP.01178 | Kamerunga Secondary Systems Replacement | 2011-06-30 | 2011-06-30 | 0 | Replacement |  | 0 | 0 | 0 | 0 | 0.84339 | 3.0107 | 0 | 3.8541 | Obsolescence/Safety
40 | 100% | CP.01654 | Richlands to Runcorn 110kV Transmission Line Life Extension | 2011-06-30 | 2011-06-30 | 0 | Replacement |  | 0 | 0 | 0 | 0 | 0.93963 | 3.0587 | 0 | 3.9983 | Safety/Reliability
40 | 100% | CP.01017 | Tarong Partial Secondary Systems Replacement | 2011-07-30 | 2011-07-30 | 0 | Replacement |  | 0 | 0 | 0 | 0 | 4.7412 | 20.2254 | 1.5621 | 26.5287 | Obsolescence/Safety
40 | 100% | CP.01127 | Loganlea 110kV Secondary Systems Replacement | 2011-08-30 | 2011-08-30 | 0 | Replacement |  | 0 | 0 | 0 | 0 | 0.9085 | 5.5209 | 0.97412 | 7.4036 | Obsolescence/Safety
40 | 100% | CP.01293 | Ross Secondary Systems Replacement | 2011-08-31 | 2011-08-31 | 0 | Replacement |  | 0 | 0 | 0 | 0 | 0.93004 | 5.6636 | 1.0014 | 7.595 | Obsolescence/Safety
40 | 100% | CP.01804 | EMS Wallboard Replacement | 2011-09-30 | 2011-09-30 | 0 | Replacement |  | 0 | 0 | 0 | 0 | 0.82058 | 0.32777 | 0.004832 | 1.1532 | Obsolescence
40 | 100% | CP.01549 | Moura Switchyard Replacement | 2011-10-31 | 2011-10-31 | 0 | Replacement |  | 0 | 0 | 0 | 0 | 0.88741 | 3.8751 | 0.61221 | 5.3747 | Obsolescence
40 | 100% | CP.01815 | Power station pilot cable Replacement | 2011-10-31 | 2011-10-31 | 0 | Replacement |  | 0 | 0 | 0 | 0 | 0.30997 | 0.23876 | 0.002591 | 0.55133 | Reliability/Obsolescence
40 | 100% | CP.01817 | UHF/VHF Radio Replacement | 2011-10-31 | 2011-10-31 | 0 | Replacement |  | 0 | 0 | 0 | 0 | 0.43474 | 0.33424 | 0.00362 | 0.77261 | Obsolescence
40 | 100% | CP.01651 | West Darra to Upper Kedron 110kV Transmission Line Life Extension | 2011-11-30 | 2011-11-30 | 0 | Replacement |  | 0 | 0 | 0 | 0 | 0.26524 | 2.6797 | 0.26357 | 3.2085 | Safety
40 | 100% | CP.00882 | Ingham to Cardwell Line Replacement | 2011-12-30 | 2011-12-30 | 0 | Replacement |  | 0 | 0 | 0 | 0 | 3.3137 | 31.8163 | 6.6188 | 41.7488 | Reliability/Safety
40 | 100% | CP.01021 | Lilyvale Secondary Systems Replacement | 2012-02-28 | 2012-02-28 | 0 | Replacement |  | 0 | 0 | 0 | 0 | 0.25033 | 5.7152 | 3.5905 | 9.5561 | Obsolescence/Safety
40 | 100% | CP.01655 | Runcorn to Belmont 110kV Transmission Line Life Extension | 2012-02-28 | 2012-02-28 | 0 | Replacement |  | 0 | 0 | 0 | 0 | 0.23843 | 1.7667 | 1.1408 | 3.146 | Safety/Reliability
40 | 100% | CP.01653 | Sumner Tee to Richlands 110kV Transmission Line Life Extension | 2012-03-30 | 2012-03-30 | 0 | Replacement |  | 0 | 0 | 0 | 0 | 0.13783 | 0.82567 | 0.88354 | 1.847 | Safety
40 | 100% | CP.01712 | Upper Kedron to West Ashgrove 110kV Transmission Line Life Extension | 2012-03-31 | 2012-03-31 | 0 | Replacement |  | 0 | 0 | 0 | 0 | 0.11844 | 0.70993 | 0.76015 | 1.5885 | Safety/Reliability
40 | 100% | CP.01918 | Strathmore iPASS Secondary Systems Replacement | 2012-04-30 | 2012-04-30 | 0 | Replacement |  | 0 | 0 | 0 | 0 | 0.099472 | 1.8122 | 4.3423 | 6.2539 | Obsolescence
40 | 100% | CP.01163 | Swanbank B 275kV Rebuild | 2012-05-30 | 2012-05-30 | 0 | Replacement |  | 0 | 0 | 0 | 0 | 2.4323 | 9.4018 | 25.9711 | 37.8051 | Operational
40 | 100% | CP.01166 | Palmwoods Secondary Systems Replacement | 2012-05-30 | 2012-05-30 | 0 | Replacement |  | 0 | 0 | 0 | 0 | 0.072019 | 2.0065 | 6.2169 | 8.2954 | Obsolescence/Safety
40 | 100% | CP.00880 | Cardwell to Tully Replacement | 2012-06-30 | 2012-06-30 | 0 | Replacement |  | 0 | 0 | 0 | 0 | 0 | 10.9399 | 35.8188 | 46.7587 | Reliability/Safety
40 | 100% | CP.01133 | Belmont No4 Transformer Replacement | 2012-06-30 | 2012-06-30 | 0 | Replacement |  | 0 | 0 | 0 | 0 | 0 | 4.049 | 1.9038 | 5.9528 | Reliability
40 | 100% | CP.01292 | Broadsound Secondary Systems Replacement | 2012-06-30 | 2012-06-30 | 0 | Replacement |  | 0 | 0 | 0 | 0 | 0 | 1.3222 | 4.7213 | 6.0435 | Obsolescence/Safety
40 | 100% | CP.01507 | Telecomms to Brisbane to Gladstone Microwave Radio Replacement | 2012-06-30 | 2012-06-30 | 0 | Replacement |  | 0 | 0 | 0 | 0 | 0 | 1.9026 | 0.19235 | 2.0949 | Obsolescence/Operational
40 | 100% | CP.01509 | Wilkes Knob to Mt Glorious Microwave Radio Replacement | 2012-06-30 | 2012-06-30 | 0 | Replacement |  | 0 | 0 | 0 | 0 | 0 | 0.50604 | 0.051286 | 0.55733 | Obsolescence
40 | 100% | CP.01582 | Stanwell Secondary Systems Replacement | 2012-07-30 | 2012-07-30 | 0 | Replacement |  | 0 | 0 | 0 | 0 | 0 | 2.8581 | 12.145 | 15.0031 | Obsolescence/Safety
40 | 100% | CP.01148 | Wurdong Secondary Systems Replacement | 2012-08-30 | 2012-08-30 | 0 | Replacement |  | 0 | 0 | 0 | 0 | 0 | 0.80151 | 4.879 | 5.6805 | Obsolescence/Safety
40 | 100% | CP.01807 | EMS Hardware Replacement | 2012-08-30 | 2012-08-30 | 0 | Replacement |  | 0 | 0 | 0 | 0 | 0 | 1.6233 | 0.58107 | 2.2043 | Obsolescence
40 | 100% | CP.01919 | Blackwall and Loganlea iPASS Secondary Systems Replacement | 2012-08-30 | 2012-08-30 | 0 | Replacement |  | 0 | 0 | 0 | 0 | 0 | 2.7169 | 16.4953 | 19.2122 | Obsolescence
40 | 100% | CP.01135 | Redbank Plains Secondary Systems Replacement | 2012-09-30 | 2012-09-30 | 0 | Replacement |  | 0 | 0 | 0 | 0 | 0 | 0.19079 | 1.6587 | 1.8495 | Obsolescence/Safety
40 | 100% | CP.01566 | Chalumbin Secondary Systems Replacement | 2012-10-30 | 2012-10-30 | 0 | Replacement |  | 0 | 0 | 0 | 0 | 0 | 0.7168 | 7.7284 | 8.4452 | Obsolescence/Safety
40 | 100% | CP.01679 | Mudgeeraba 110kV Rebuild | 2012-10-31 | 2012-10-31 | 0 | Replacement |  | 0 | 0 | 0 | 0 | 0 | 3.594 | 15.6609 | 19.2549 | Operational
40 | 100% | CP.01800 | Metropolitan Communications Loop Replacement - Stage 2 | 2012-10-31 | 2012-10-31 | 0 | Replacement |  | 0 | 0 | 0 | 0 | 0 | 0.19913 | 0.15399 | 0.35312 | Obsolescence
40 | 100% | CP.01650 | South Pine to Upper Kedron 110kV Transmission Line Life Extension | 2012-11-30 | 2012-11-30 | 0 | Replacement |  | 0 | 0 | 0 | 0 | 0 | 0.25993 | 2.6262 | 2.8862 | Safety
40 | 100% | CP.01942 | Collinsville to Proserpine 132kV Transmission Line Life Extension | 2013-01-30 | 2013-01-30 | 0 | Replacement |  | 0 | 0 | 0 | 0 | 0 | 1.3445 | 11.2782 | 12.6226 | Reliability
40 | 100% | CP.01563 | Bouldercombe Secondary Systems Replacement | 2013-01-31 | 2013-01-31 | 0 | Replacement |  | 0 | 0 | 0 | 0 | 0 | 0.33871 | 6.963 | 7.3017 | Obsolescence/Safety
40 | 100% | CP.01162 | Callemondah Secondary Systems Replacement | 2013-06-30 | 2013-06-30 | 0 | Replacement |  | 0 | 0 | 0 | 0 | 0 | 0 | 0.75728 | 0.75728 | Obsolescence/Safety
40 | 100% | CP.01920 | Bulli Creek, Millmerran and Braemar iPASS Secondary Systems Replacement | 2013-07-30 | 2013-07-30 | 0 | Replacement |  | 0 | 0 | 0 | 0 | 0 | 0 | 6.1349 | 6.1349 | Obsolescence
40 | 100% | CP.01635 | Abermain Secondary Systems Replacement | 2013-10-30 | 2013-10-30 | 0 | Replacement |  | 0 | 0 | 0 | 0 | 0 | 0 | 0.31218 | 0.31218 | Obsolescence/Safety
40 | 100% | CP.01822 | Ashgrove West Cables Replacement | 2013-10-31 | 2013-10-31 | 0 | Replacement |  | 0 | 0 | 0 | 0 | 0 | 0 | 1.0397 | 1.0397 | Safety
40 | 100% | CP.01717 | Transmission Line Structure Security Upgrade | Various | Various |  | Security/Compliance |  | 0 | 0 | 2.5124 | 20.7346 | 3.1004 | 21.6861 | 0.49495 | 48.5284 | Operational/Safety
40 | 100% | CP.01668 | Communications Site Access and Security | Various | Various |  | Security/Compliance |  | 0 | 0 | 0.1205 | 5.2105 | 0.24566 | 5.224 | 0.12518 | 10.9258 | Operational/Safety
40 | 100% | CP.01714 | Substation Access Security | Various | Various |  | Security/Compliance |  | 0 | 0 | 0 | 6.4778 | 17.3148 | 6.765 | 18.0856 | 48.6431 | Operational/Safety
40 | 100% | CP.01880 | Moreton West 120MVAr No. 1 | 2007-10-31 | 2007-10-31 | 0 | Augmentation |  | 0.24554 | 1.6684 | 0.59044 | 0 | 0 | 0 | 0 | 0.59044 | Reliability
40 | 100% | CP.01837 | Palmwoods 350MVAr SVC | 2008-10-31 | 2008-10-31 | 0 | Augmentation |  | 0 | 12.0129 | 20.0283 | 0 | 0 | 0 | 0 | 20.0283 | Reliability
40 | 100% | CP.01970/A | Braemar to Halys 1st 500kV Double Circuit Line Easement Widening (TE) | 2008-10-31 | 2008-10-31 | 0 | Easements |  | 0 | 0.79062 | 0.78401 | 0.14898 | 0 | 0 | 0 | 0.933 | Construction
40 | 100% | CP.01967/A | 500kV Braemar Substation Extension (TE) | 2008-10-31 | 2008-10-31 | 0 | Easements |  | 0 | 0.099583 | 0.098751 | 0.018765 | 0 | 0 | 0 | 0.11752 | Construction
40 | 100% | CP.01991/A | Land Acquisition for Larcom Creek 132kV Remote Bus Establishment (TE) | 2008-10-31 | 2008-10-31 | 0 | Easements |  | 0 | 0.20742 | 0.20569 | 0.039087 | 0 | 0 | 0 | 0.24478 | Construction
40 | 100% | CP.01970/B | Braemar to Halys 1st 500kV Double Circuit Line Easement Widening (Compensation) | 2009-05-31 | 2009-05-31 | 0 | Easements |  | 0 | 0 | 0.38082 | 0.22032 | 0 | 0 | 0 | 0.60114 | Construction
40 | 100% | CP.01967/B | 500kV Braemar Substation Extension (Compensation) | 2009-05-31 | 2009-05-31 | 0 | Easements |  | 0 | 0 | 0.094086 | 0.054431 | 0 | 0 | 0 | 0.14852 | Construction
40 | 100% | CP.01991/B | Land Acquisition for Larcom Creek 132kV Remote Bus Establishment (Compensation) | 2009-10-31 | 2009-10-31 | 0 | Easements |  | 0 | 0 | 0.033324 | 0.79981 | 0.040712 | 0 | 0 | 0.87384 | Construction
40 | 100% | CP.01866/A | Easement Acquisition for 3rd 500kV Double Circuit into South East Queensland (TE) | 2013-10-31 | 2013-10-31 | 0 | Easements |  | 0 | 0 | 0 | 0 | 0 | 0 | 3.1686 | 3.1686 | Construction
[8 empty] | Subtotal | 98.8703 | 427.2206 | 390.2663 | 207.5075 | 248.174 | 253.0592 | 252.0339 | 1351.0409

## Forecast Capex - Network Varied
4.3(b) FORECAST CAPEX - Network - by project
[7 empty] | Home |  | Provided for information only |  |  |  | Link to Forecast Capex Instructions - Table 6.3
$m, real (06/07) | [10 empty] | Yearly expenditure by project
[11 empty] | (based on median commissioning date) | [8 empty] | Scenarios & scenario probabilities
No. Scenarios | Probability | Project No. | Project Name | Earliest date | Latest date | Date Diff | Category |  | 2005/06 | 2006/07 | 2007/08 | 2008/09 | 2009/10 | 2010/11 | 2011/12 | TOTAL | Reason for project | Reg test/BC (RT/BC) | Reg test/BC cost est | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40
[20 empty] | 7.876% | 1.097% | 6.78% | 1.097% | 3.789% | 0.499% | 2.293% | 0.499% | 10.87% | 1.496% | 10.07% | 1.496% | 5.882% | 0.897% | 5.583% | 0.798% | 6.68% | 0.798% | 4.885% | 0.698% | 3.789% | 0.499% | 2.891% | 0.499% | 3.39% | 0.399% | 2.891% | 0.399% | 1.695% | 0.299% | 1.595% | 0.299% | 1.994% | 0.299% | 1.994% | 0.299% | 1.097% | 0.199% | 1.196% | 0.199%
40 | 100% | CP.01528/A | Molendinar 275/110kV Transformer Augmentation | 2008-03-31 | 2012-03-31 | 1461 | Augmentation |  | 0 | 0 | 2.7715 | 14.2151 | 0.78526 | 0 | 0 | 17.7719 | Reliability |  |  | 2012-03-31 | 2012-03-31 | 2012-03-31 | 2012-03-31 | 2012-03-31 | 2012-03-31 | 2012-03-31 | 2012-03-31 | 2010-03-31 | 2010-03-31 | 2010-03-31 | 2010-03-31 | 2010-03-31 | 2010-03-31 | 2010-03-31 | 2010-03-31 | 2010-03-31 | 2010-03-31 | 2010-03-31 | 2010-03-31 | 2010-03-31 | 2010-03-31 | 2010-03-31 | 2010-03-31 | 2010-03-31 | 2010-03-31 | 2010-03-31 | 2010-03-31 | 2010-03-31 | 2010-03-31 | 2010-03-31 | 2010-03-31 | 2008-03-31 | 2008-03-31 | 2008-03-31 | 2008-03-31 | 2008-03-31 | 2008-03-31 | 2008-03-31 | 2008-03-31
40 | 100% | CP.01756 | Runcorn 110kV Feeder Bays | 2008-05-31 | 2011-05-31 | 1095 | Augmentation |  | 0 | 0 | 0.14075 | 0.54283 | 1.4961 | 0 | 0 | 2.1797 | Reliability |  |  | 2011-05-31 | 2011-05-31 | 2011-05-31 | 2011-05-31 | 2011-05-31 | 2011-05-31 | 2011-05-31 | 2011-05-31 | 2010-05-31 | 2010-05-31 | 2010-05-31 | 2010-05-31 | 2010-05-31 | 2010-05-31 | 2010-05-31 | 2010-05-31 | 2010-05-31 | 2010-05-31 | 2010-05-31 | 2010-05-31 | 2010-05-31 | 2010-05-31 | 2010-05-31 | 2010-05-31 | 2010-05-31 | 2010-05-31 | 2010-05-31 | 2010-05-31 | 2010-05-31 | 2010-05-31 | 2010-05-31 | 2010-05-31 | 2008-05-31 | 2008-05-31 | 2008-05-31 | 2008-05-31 | 2008-05-31 | 2008-05-31 | 2008-05-31 | 2008-05-31
40 | 100% | CP.01754 | Richlands 110kV Feeder Bays | 2008-06-30 | 2011-06-30 | 1095 | Augmentation |  | 0 | 0 | 0 | 0.70452 | 1.8581 | 0 | 0 | 2.5626 | Reliability |  |  | 2011-06-30 | 2011-06-30 | 2011-06-30 | 2011-06-30 | 2011-06-30 | 2011-06-30 | 2011-06-30 | 2011-06-30 | 2010-06-30 | 2010-06-30 | 2010-06-30 | 2010-06-30 | 2010-06-30 | 2010-06-30 | 2010-06-30 | 2010-06-30 | 2010-06-30 | 2010-06-30 | 2010-06-30 | 2010-06-30 | 2010-06-30 | 2010-06-30 | 2010-06-30 | 2010-06-30 | 2010-06-30 | 2010-06-30 | 2010-06-30 | 2010-06-30 | 2010-06-30 | 2010-06-30 | 2010-06-30 | 2010-06-30 | 2008-06-30 | 2008-06-30 | 2008-06-30 | 2008-06-30 | 2008-06-30 | 2008-06-30 | 2008-06-30 | 2008-06-30
40 | 100% | CP.01631/A | West Darra 110/11kV Transformer | 2008-06-30 | 2014-06-30 | 2191 | Augmentation |  | 0 | 0 | 0.62611 | 1.6529 | 0 | 0 | 0 | 2.279 | Reliability |  |  | 2014-06-30 | 2014-06-30 | 2014-06-30 | 2014-06-30 | 2014-06-30 | 2014-06-30 | 2014-06-30 | 2014-06-30 | 2009-06-30 | 2009-06-30 | 2009-06-30 | 2009-06-30 | 2009-06-30 | 2009-06-30 | 2009-06-30 | 2009-06-30 | 2009-06-30 | 2009-06-30 | 2009-06-30 | 2009-06-30 | 2009-06-30 | 2009-06-30 | 2009-06-30 | 2009-06-30 | 2009-06-30 | 2009-06-30 | 2009-06-30 | 2009-06-30 | 2009-06-30 | 2009-06-30 | 2009-06-30 | 2009-06-30 | 2008-06-30 | 2008-06-30 | 2008-06-30 | 2008-06-30 | 2008-06-30 | 2008-06-30 | 2008-06-30 | 2008-06-30
40 | 100% | CP.01189/B | South Pine to Sandgate 275kV Double Circuit Operating at 110kV | 2008-07-31 | 2013-07-31 | 1826 | Augmentation |  | 0 | 0 | 4.9223 | 27.6135 | 0.16656 | 0 | 0 | 32.7024 | Reliability |  |  | 2013-07-31 | 2013-07-31 | 2013-07-31 | 2013-07-31 | 2013-07-31 | 2013-07-31 | 2013-07-31 | 2013-07-31 | 2009-07-31 | 2009-07-31 | 2009-07-31 | 2009-07-31 | 2009-07-31 | 2009-07-31 | 2009-07-31 | 2009-07-31 | 2009-07-31 | 2009-07-31 | 2009-07-31 | 2009-07-31 | 2009-07-31 | 2009-07-31 | 2009-07-31 | 2009-07-31 | 2009-07-31 | 2009-07-31 | 2009-07-31 | 2009-07-31 | 2009-07-31 | 2009-07-31 | 2009-07-31 | 2009-07-31 | 2008-07-31 | 2008-07-31 | 2008-07-31 | 2008-07-31 | 2008-07-31 | 2008-07-31 | 2008-07-31 | 2008-07-31
8 | 7.277% | CP.01516/A | South East Brisbane No. 1 110/11kV Substation Establishment - Stage 1 and 2 | 2008-07-31 | 2008-07-31 | 0 | Augmentation |  | 0 | 2.3071 | 6.9095 | 0.10045 | 0 | 0 | 0 | 7.0099 | Reliability |  |  | Scenarios & scenario probabilities 33: 2008-07-31; Scenarios & scenario probabilities 34: 2008-07-31; Scenarios & scenario probabilities 35: 2008-07-31; Scenarios & scenario probabilities 36: 2008-07-31; Scenarios & scenario probabilities 37: 2008-07-31; Scenarios & scenario probabilities 38: 2008-07-31; Scenarios & scenario probabilities 39: 2008-07-31; Scenarios & scenario probabilities 40: 2008-07-31
8 | 7.277% | CP.01764 | Braemar 275/132kV Substation Establishment | 2008-08-31 | 2008-08-31 | 0 | Augmentation |  | 0 | 5.8824 | 18.9634 | 0.12329 | 0 | 0 | 0 | 19.0867 | Reliability |  |  | Scenarios & scenario probabilities 33: 2008-08-31; Scenarios & scenario probabilities 34: 2008-08-31; Scenarios & scenario probabilities 35: 2008-08-31; Scenarios & scenario probabilities 36: 2008-08-31; Scenarios & scenario probabilities 37: 2008-08-31; Scenarios & scenario probabilities 38: 2008-08-31; Scenarios & scenario probabilities 39: 2008-08-31; Scenarios & scenario probabilities 40: 2008-08-31
40 | 100% | CP.01559 | Edmonton 1st 132kV 30MVAr Capacitor Bank | 2008-08-31 | 2009-08-31 | 365 | Augmentation |  | 0 | 0.23587 | 1.7891 | 0.22498 | 0 | 0 | 0 | 2.0141 | Reliability |  |  | 2009-08-31 | 2009-08-31 | 2009-08-31 | 2009-08-31 | 2009-08-31 | 2009-08-31 | 2009-08-31 | 2009-08-31 | 2008-08-31 | 2008-08-31 | 2008-08-31 | 2008-08-31 | 2008-08-31 | 2008-08-31 | 2008-08-31 | 2008-08-31 | 2008-08-31 | 2008-08-31 | 2008-08-31 | 2008-08-31 | 2008-08-31 | 2008-08-31 | 2008-08-31 | 2008-08-31 | 2008-08-31 | 2008-08-31 | 2008-08-31 | 2008-08-31 | 2008-08-31 | 2008-08-31 | 2008-08-31 | 2008-08-31 | 2008-08-31 | 2008-08-31 | 2008-08-31 | 2008-08-31 | 2008-08-31 | 2008-08-31 | 2008-08-31 | 2008-08-31
40 | 100% | CP.01932 | Moreton North 1st 110kV 50MVAr Capacitor Bank | 2008-08-31 | 2010-08-31 | 730 | Augmentation |  | 0 | 0.1963 | 1.488 | 0.18701 | 0 | 0 | 0 | 1.675 | Reliability |  |  | 2010-08-31 | 2010-08-31 | 2010-08-31 | 2010-08-31 | 2010-08-31 | 2010-08-31 | 2010-08-31 | 2010-08-31 | 2008-08-31 | 2008-08-31 | 2008-08-31 | 2008-08-31 | 2008-08-31 | 2008-08-31 | 2008-08-31 | 2008-08-31 | 2008-08-31 | 2008-08-31 | 2008-08-31 | 2008-08-31 | 2008-08-31 | 2008-08-31 | 2008-08-31 | 2008-08-31 | 2008-08-31 | 2008-08-31 | 2008-08-31 | 2008-08-31 | 2008-08-31 | 2008-08-31 | 2008-08-31 | 2008-08-31 | 2008-08-31 | 2008-08-31 | 2008-08-31 | 2008-08-31 | 2008-08-31 | 2008-08-31 | 2008-08-31 | 2008-08-31
40 | 100% | CP.00364 | Murrarie 275/110kV Transformer Augmentation | 2008-09-30 | 2011-09-30 | 1095 | Augmentation |  | 0 | 0 | 1.9245 | 6.9926 | 0.044213 | 0 | 0 | 8.9613 | Reliability |  |  | 2011-09-30 | 2011-09-30 | 2011-09-30 | 2011-09-30 | 2011-09-30 | 2011-09-30 | 2011-09-30 | 2011-09-30 | 2009-09-30 | 2009-09-30 | 2009-09-30 | 2009-09-30 | 2009-09-30 | 2009-09-30 | 2009-09-30 | 2009-09-30 | 2009-09-30 | 2009-09-30 | 2009-09-30 | 2009-09-30 | 2009-09-30 | 2009-09-30 | 2009-09-30 | 2009-09-30 | 2009-09-30 | 2009-09-30 | 2009-09-30 | 2009-09-30 | 2009-09-30 | 2009-09-30 | 2009-09-30 | 2009-09-30 | 2008-09-30 | 2008-09-30 | 2008-09-30 | 2008-09-30 | 2008-09-30 | 2008-09-30 | 2008-09-30 | 2008-09-30
32 | 76.07% | CP.01533/B | 275kV Double Circuit Line into South West Brisbane | 2008-09-30 | 2012-09-30 | 1461 | Augmentation |  | 0 | 0 | 0 | 0 | 0 | 4.685 | 37.8565 | 42.5415 | Reliability | [10 empty] | 2012-09-30 | 2012-09-30 | 2012-09-30 | 2012-09-30 | 2012-09-30 | 2012-09-30 | 2012-09-30 | 2012-09-30 | 2012-09-30 | 2012-09-30 | 2012-09-30 | 2012-09-30 | 2012-09-30 | 2012-09-30 | 2012-09-30 | 2012-09-30 | 2012-09-30 | 2012-09-30 | 2012-09-30 | 2012-09-30 | 2012-09-30 | 2012-09-30 | 2012-09-30 | 2012-09-30 | 2008-09-30 | 2008-09-30 | 2008-09-30 | 2008-09-30 | 2008-09-30 | 2008-09-30 | 2008-09-30 | 2008-09-30
40 | 100% | CP.00659/A | El Arish 132/22kV Substation Establishment | 2008-09-30 | 2009-09-30 | 365 | Augmentation |  | 0 | 3.1693 | 10.8636 | 0.85619 | 0 | 0 | 0 | 11.7198 | Reliability |  |  | 2009-09-30 | 2009-09-30 | 2009-09-30 | 2009-09-30 | 2009-09-30 | 2009-09-30 | 2009-09-30 | 2009-09-30 | 2008-09-30 | 2008-09-30 | 2008-09-30 | 2008-09-30 | 2008-09-30 | 2008-09-30 | 2008-09-30 | 2008-09-30 | 2008-09-30 | 2008-09-30 | 2008-09-30 | 2008-09-30 | 2008-09-30 | 2008-09-30 | 2008-09-30 | 2008-09-30 | 2008-09-30 | 2008-09-30 | 2008-09-30 | 2008-09-30 | 2008-09-30 | 2008-09-30 | 2008-09-30 | 2008-09-30 | 2008-09-30 | 2008-09-30 | 2008-09-30 | 2008-09-30 | 2008-09-30 | 2008-09-30 | 2008-09-30 | 2008-09-30
32 | 76.07% | CP.01771/B | 275kV Double Circuit Line into Larapinta | 2008-09-30 | 2012-09-30 | 1461 | Augmentation |  | 0 | 0 | 0 | 0 | 0 | 9.6296 | 77.8426 | 87.4721 | Reliability | [10 empty] | 2012-09-30 | 2012-09-30 | 2012-09-30 | 2012-09-30 | 2012-09-30 | 2012-09-30 | 2012-09-30 | 2012-09-30 | 2012-09-30 | 2012-09-30 | 2012-09-30 | 2012-09-30 | 2012-09-30 | 2012-09-30 | 2012-09-30 | 2012-09-30 | 2012-09-30 | 2012-09-30 | 2012-09-30 | 2012-09-30 | 2012-09-30 | 2012-09-30 | 2012-09-30 | 2012-09-30 | 2008-09-30 | 2008-09-30 | 2008-09-30 | 2008-09-30 | 2008-09-30 | 2008-09-30 | 2008-09-30 | 2008-09-30
32 | 76.07% | CP.01537 | Greenbank to Mudgeeraba Rebuild | 2008-09-30 | 2013-09-30 | 1826 | Augmentation |  | 0 | 0 | 0 | 0 | 0 | 0 | 5.9763 | 5.9763 | Reliability | [10 empty] | 2013-09-30 | 2013-09-30 | 2013-09-30 | 2013-09-30 | 2013-09-30 | 2013-09-30 | 2013-09-30 | 2013-09-30 | 2013-09-30 | 2013-09-30 | 2013-09-30 | 2013-09-30 | 2013-09-30 | 2013-09-30 | 2013-09-30 | 2013-09-30 | 2013-09-30 | 2013-09-30 | 2013-09-30 | 2013-09-30 | 2013-09-30 | 2013-09-30 | 2013-09-30 | 2013-09-30 | 2008-09-30 | 2008-09-30 | 2008-09-30 | 2008-09-30 | 2008-09-30 | 2008-09-30 | 2008-09-30 | 2008-09-30
32 | 76.07% | CP.01774 | Larapinta 275kV Connections | 2008-09-30 | 2012-09-30 | 1461 | Augmentation |  | 0 | 0 | 0 | 0 | 0 | 1.6864 | 5.7954 | 7.4818 | Reliability | [10 empty] | 2012-09-30 | 2012-09-30 | 2012-09-30 | 2012-09-30 | 2012-09-30 | 2012-09-30 | 2012-09-30 | 2012-09-30 | 2012-09-30 | 2012-09-30 | 2012-09-30 | 2012-09-30 | 2012-09-30 | 2012-09-30 | 2012-09-30 | 2012-09-30 | 2012-09-30 | 2012-09-30 | 2012-09-30 | 2012-09-30 | 2012-09-30 | 2012-09-30 | 2012-09-30 | 2012-09-30 | 2008-09-30 | 2008-09-30 | 2008-09-30 | 2008-09-30 | 2008-09-30 | 2008-09-30 | 2008-09-30 | 2008-09-30
40 | 100% | CP.01243 | Bouldercombe to Pandoin 132kV Double Circuit Line | 2008-10-31 | 2013-10-31 | 1826 | Augmentation |  | 0 | 0 | 2.2986 | 22.9454 | 1.1012 | 0 | 0 | 26.3451 | Reliability |  |  | 2013-10-31 | 2013-10-31 | 2013-10-31 | 2013-10-31 | 2013-10-31 | 2013-10-31 | 2013-10-31 | 2013-10-31 | 2009-10-31 | 2009-10-31 | 2009-10-31 | 2009-10-31 | 2009-10-31 | 2009-10-31 | 2009-10-31 | 2009-10-31 | 2009-10-31 | 2009-10-31 | 2009-10-31 | 2009-10-31 | 2009-10-31 | 2009-10-31 | 2009-10-31 | 2009-10-31 | 2009-10-31 | 2009-10-31 | 2009-10-31 | 2009-10-31 | 2009-10-31 | 2009-10-31 | 2009-10-31 | 2009-10-31 | 2008-10-31 | 2008-10-31 | 2008-10-31 | 2008-10-31 | 2008-10-31 | 2008-10-31 | 2008-10-31 | 2008-10-31
40 | 100% | CP.01265 | Bowen Transmission Reinforcement | 2008-10-31 | 2010-10-31 | 730 | Augmentation |  | 0 | 7.5885 | 33.0163 | 5.1931 | 0 | 0 | 0 | 38.2094 | Reliability |  |  | 2010-10-31 | 2010-10-31 | 2010-10-31 | 2010-10-31 | 2010-10-31 | 2010-10-31 | 2010-10-31 | 2010-10-31 | 2008-10-31 | 2008-10-31 | 2008-10-31 | 2008-10-31 | 2008-10-31 | 2008-10-31 | 2008-10-31 | 2008-10-31 | 2008-10-31 | 2008-10-31 | 2008-10-31 | 2008-10-31 | 2008-10-31 | 2008-10-31 | 2008-10-31 | 2008-10-31 | 2008-10-31 | 2008-10-31 | 2008-10-31 | 2008-10-31 | 2008-10-31 | 2008-10-31 | 2008-10-31 | 2008-10-31 | 2008-10-31 | 2008-10-31 | 2008-10-31 | 2008-10-31 | 2008-10-31 | 2008-10-31 | 2008-10-31 | 2008-10-31
40 | 100% | CP.01195/A | Larapinta 275/110kV Substation Establishment | 2008-10-31 | 2011-10-31 | 1095 | Augmentation |  | 0 | 0 | 0 | 9.1556 | 39.7134 | 6.2321 | 0 | 55.1012 | Reliability |  |  | 2011-10-31 | 2011-10-31 | 2011-10-31 | 2011-10-31 | 2011-10-31 | 2011-10-31 | 2011-10-31 | 2011-10-31 | 2010-10-31 | 2010-10-31 | 2010-10-31 | 2010-10-31 | 2010-10-31 | 2010-10-31 | 2010-10-31 | 2010-10-31 | 2010-10-31 | 2010-10-31 | 2010-10-31 | 2010-10-31 | 2010-10-31 | 2010-10-31 | 2010-10-31 | 2010-10-31 | 2010-10-31 | 2010-10-31 | 2010-10-31 | 2010-10-31 | 2010-10-31 | 2010-10-31 | 2010-10-31 | 2010-10-31 | 2008-10-31 | 2008-10-31 | 2008-10-31 | 2008-10-31 | 2008-10-31 | 2008-10-31 | 2008-10-31 | 2008-10-31
32 | 76.07% | CP.01523 | Townsville East 132/66kV Transformer | 2009-06-30 | 2011-06-30 | 730 | Augmentation |  | 0 | 0 | 0 | 0 | 3.8824 | 1.8205 | 0 | 5.7029 | Reliability | [10 empty] | 2011-06-30 | 2011-06-30 | 2011-06-30 | 2011-06-30 | 2011-06-30 | 2011-06-30 | 2011-06-30 | 2011-06-30 | 2011-06-30 | 2011-06-30 | 2011-06-30 | 2011-06-30 | 2011-06-30 | 2011-06-30 | 2011-06-30 | 2011-06-30 | 2011-06-30 | 2011-06-30 | 2011-06-30 | 2011-06-30 | 2011-06-30 | 2011-06-30 | 2011-06-30 | 2011-06-30 | 2009-06-30 | 2009-06-30 | 2009-06-30 | 2009-06-30 | 2009-06-30 | 2009-06-30 | 2009-06-30 | 2009-06-30
8 | 7.277% | CP.01687 | North Coast 275/110kV Transformer | 2009-07-31 | 2009-07-31 | 0 | Augmentation |  | 0 | 0 | 3.0266 | 8.3151 | 0.056372 | 0 | 0 | 11.3981 | Reliability |  |  | Scenarios & scenario probabilities 33: 2009-07-31; Scenarios & scenario probabilities 34: 2009-07-31; Scenarios & scenario probabilities 35: 2009-07-31; Scenarios & scenario probabilities 36: 2009-07-31; Scenarios & scenario probabilities 37: 2009-07-31; Scenarios & scenario probabilities 38: 2009-07-31; Scenarios & scenario probabilities 39: 2009-07-31; Scenarios & scenario probabilities 40: 2009-07-31
8 | 7.277% | CP.01520/A | Brisbane South No. 1 110/11kV Substation Establishment - Stage 1 and 2 | 2009-07-31 | 2009-07-31 | 0 | Augmentation |  | 0 | 0 | 3.3223 | 9.9364 | 0.14433 | 0 | 0 | 13.403 | Reliability |  |  | Scenarios & scenario probabilities 33: 2009-07-31; Scenarios & scenario probabilities 34: 2009-07-31; Scenarios & scenario probabilities 35: 2009-07-31; Scenarios & scenario probabilities 36: 2009-07-31; Scenarios & scenario probabilities 37: 2009-07-31; Scenarios & scenario probabilities 38: 2009-07-31; Scenarios & scenario probabilities 39: 2009-07-31; Scenarios & scenario probabilities 40: 2009-07-31
32 | 76.07% | CP.01684 | Swanbank A 275/110kV Transformer Re-connection | 2009-07-31 | 2012-07-31 | 1096 | Augmentation |  | 0 | 0 | 0 | 0 | 0 | 0.54512 | 1.4924 | 2.0375 | Reliability | [10 empty] | 2012-07-31 | 2012-07-31 | 2012-07-31 | 2012-07-31 | 2012-07-31 | 2012-07-31 | 2012-07-31 | 2012-07-31 | 2012-07-31 | 2012-07-31 | 2012-07-31 | 2012-07-31 | 2012-07-31 | 2012-07-31 | 2012-07-31 | 2012-07-31 | 2012-07-31 | 2012-07-31 | 2012-07-31 | 2012-07-31 | 2012-07-31 | 2012-07-31 | 2012-07-31 | 2012-07-31 | 2009-07-31 | 2009-07-31 | 2009-07-31 | 2009-07-31 | 2009-07-31 | 2009-07-31 | 2009-07-31 | 2009-07-31
40 | 100% | CP.01782 | Blackwall to Swanbank Uprate Existing 275kV | 2009-08-30 | 2012-08-30 | 1096 | Augmentation |  | 0 | 0 | 0 | 1.1186 | 8.2276 | 0.0944 | 0 | 9.4406 | Reliability |  |  | 2012-08-30 | 2012-08-30 | 2012-08-30 | 2012-08-30 | 2012-08-30 | 2012-08-30 | 2012-08-30 | 2012-08-30 | 2010-08-30 | 2010-08-30 | 2010-08-30 | 2010-08-30 | 2010-08-30 | 2010-08-30 | 2010-08-30 | 2010-08-30 | 2010-08-30 | 2010-08-30 | 2010-08-30 | 2010-08-30 | 2010-08-30 | 2010-08-30 | 2010-08-30 | 2010-08-30 | 2010-08-30 | 2010-08-30 | 2010-08-30 | 2010-08-30 | 2010-08-30 | 2010-08-30 | 2010-08-30 | 2010-08-30 | 2009-08-30 | 2009-08-30 | 2009-08-30 | 2009-08-30 | 2009-08-30 | 2009-08-30 | 2009-08-30 | 2009-08-30
40 | 100% | CP.01844 | South Pine 275/110kV Transformer Augmentation | 2009-08-31 | 2010-08-31 | 365 | Augmentation |  | 0 | 0 | 3.6753 | 12.5566 | 0.426 | 0 | 0 | 16.6579 | Reliability |  |  | 2010-08-31 | 2010-08-31 | 2010-08-31 | 2010-08-31 | 2010-08-31 | 2010-08-31 | 2010-08-31 | 2010-08-31 | 2009-08-31 | 2009-08-31 | 2009-08-31 | 2009-08-31 | 2009-08-31 | 2009-08-31 | 2009-08-31 | 2009-08-31 | 2009-08-31 | 2009-08-31 | 2009-08-31 | 2009-08-31 | 2009-08-31 | 2009-08-31 | 2009-08-31 | 2009-08-31 | 2009-08-31 | 2009-08-31 | 2009-08-31 | 2009-08-31 | 2009-08-31 | 2009-08-31 | 2009-08-31 | 2009-08-31 | 2009-08-31 | 2009-08-31 | 2009-08-31 | 2009-08-31 | 2009-08-31 | 2009-08-31 | 2009-08-31 | 2009-08-31
32 | 76.07% | CP.00390 | Rocklea 275kV Bus and 275/110kV Transformer Augmentation | 2009-09-30 | 2013-09-30 | 1461 | Augmentation |  | 0 | 0 | 0 | 0 | 0 | 0 | 3.9463 | 3.9463 | Reliability | [10 empty] | 2013-09-30 | 2013-09-30 | 2013-09-30 | 2013-09-30 | 2013-09-30 | 2013-09-30 | 2013-09-30 | 2013-09-30 | 2013-09-30 | 2013-09-30 | 2013-09-30 | 2013-09-30 | 2013-09-30 | 2013-09-30 | 2013-09-30 | 2013-09-30 | 2013-09-30 | 2013-09-30 | 2013-09-30 | 2013-09-30 | 2013-09-30 | 2013-09-30 | 2013-09-30 | 2013-09-30 | 2009-09-30 | 2009-09-30 | 2009-09-30 | 2009-09-30 | 2009-09-30 | 2009-09-30 | 2009-09-30 | 2009-09-30
32 | 76.07% | CP.01760 | Sarina 132/66kV Transformer | 2009-09-30 | 2011-09-30 | 730 | Augmentation |  | 0 | 0 | 0 | 0 | 1.9427 | 7.0551 | 0.044584 | 9.0424 | Reliability | [10 empty] | 2011-09-30 | 2011-09-30 | 2011-09-30 | 2011-09-30 | 2011-09-30 | 2011-09-30 | 2011-09-30 | 2011-09-30 | 2011-09-30 | 2011-09-30 | 2011-09-30 | 2011-09-30 | 2011-09-30 | 2011-09-30 | 2011-09-30 | 2011-09-30 | 2011-09-30 | 2011-09-30 | 2011-09-30 | 2011-09-30 | 2011-09-30 | 2011-09-30 | 2011-09-30 | 2011-09-30 | 2009-09-30 | 2009-09-30 | 2009-09-30 | 2009-09-30 | 2009-09-30 | 2009-09-30 | 2009-09-30 | 2009-09-30
8 | 7.277% | CP.01517/A | South East Brisbane No. 2 110/11kV Substation Establishment - Stage 1 and 2 | 2009-10-31 | 2009-10-31 | 0 | Augmentation |  | 0 | 0 | 2.2278 | 9.6393 | 1.5089 | 0 | 0 | 13.376 | Reliability |  |  | Scenarios & scenario probabilities 33: 2009-10-31; Scenarios & scenario probabilities 34: 2009-10-31; Scenarios & scenario probabilities 35: 2009-10-31; Scenarios & scenario probabilities 36: 2009-10-31; Scenarios & scenario probabilities 37: 2009-10-31; Scenarios & scenario probabilities 38: 2009-10-31; Scenarios & scenario probabilities 39: 2009-10-31; Scenarios & scenario probabilities 40: 2009-10-31
32 | 76.07% | CP.01249 | Mudgeeraba to South Coast Transmission Reinforcement | 2009-10-31 | 2010-10-31 | 365 | Augmentation |  | 0 | 0 | 0 | 2.3223 | 23.023 | 1.0972 | 0 | 26.4425 | Reliability | [10 empty] | 2010-10-31 | 2010-10-31 | 2010-10-31 | 2010-10-31 | 2010-10-31 | 2010-10-31 | 2010-10-31 | 2010-10-31 | 2010-10-31 | 2010-10-31 | 2010-10-31 | 2010-10-31 | 2010-10-31 | 2010-10-31 | 2010-10-31 | 2010-10-31 | 2010-10-31 | 2010-10-31 | 2010-10-31 | 2010-10-31 | 2010-10-31 | 2010-10-31 | 2010-10-31 | 2010-10-31 | 2009-10-31 | 2009-10-31 | 2009-10-31 | 2009-10-31 | 2009-10-31 | 2009-10-31 | 2009-10-31 | 2009-10-31
32 | 76.07% | CP.01264/A | Woolooga to North Coast 275kV Double Circuit and 275/132kV Transformer | 2009-10-31 | 2011-10-31 | 730 | Augmentation |  | 0 | 0 | 0 | 0 | 5.8076 | 57.9561 | 2.7805 | 66.5442 | Reliability | [10 empty] | 2011-10-31 | 2011-10-31 | 2011-10-31 | 2011-10-31 | 2011-10-31 | 2011-10-31 | 2011-10-31 | 2011-10-31 | 2011-10-31 | 2011-10-31 | 2011-10-31 | 2011-10-31 | 2011-10-31 | 2011-10-31 | 2011-10-31 | 2011-10-31 | 2011-10-31 | 2011-10-31 | 2011-10-31 | 2011-10-31 | 2011-10-31 | 2011-10-31 | 2011-10-31 | 2011-10-31 | 2009-10-31 | 2009-10-31 | 2009-10-31 | 2009-10-31 | 2009-10-31 | 2009-10-31 | 2009-10-31 | 2009-10-31
32 | 76.07% | CP.01870 | West Darra 110/11kV Transformer | 2010-06-30 | 2012-06-30 | 731 | Augmentation |  | 0 | 0 | 0 | 0 | 0 | 0.59619 | 1.5743 | 2.1705 | Reliability | [10 empty] | 2012-06-30 | 2012-06-30 | 2012-06-30 | 2012-06-30 | 2012-06-30 | 2012-06-30 | 2012-06-30 | 2012-06-30 | 2012-06-30 | 2012-06-30 | 2012-06-30 | 2012-06-30 | 2012-06-30 | 2012-06-30 | 2012-06-30 | 2012-06-30 | 2012-06-30 | 2012-06-30 | 2012-06-30 | 2012-06-30 | 2012-06-30 | 2012-06-30 | 2012-06-30 | 2012-06-30 | 2010-06-30 | 2010-06-30 | 2010-06-30 | 2010-06-30 | 2010-06-30 | 2010-06-30 | 2010-06-30 | 2010-06-30
32 | 76.07% | CP.01843 | Palmwoods Quad Boost Transformer | 2010-06-30 | 2013-06-30 | 1096 | Augmentation |  | 0 | 0 | 0 | 0 | 0 | 0 | 4.2542 | 4.2542 | Reliability | [10 empty] | 2013-06-30 | 2013-06-30 | 2013-06-30 | 2013-06-30 | 2013-06-30 | 2013-06-30 | 2013-06-30 | 2013-06-30 | 2013-06-30 | 2013-06-30 | 2013-06-30 | 2013-06-30 | 2013-06-30 | 2013-06-30 | 2013-06-30 | 2013-06-30 | 2013-06-30 | 2013-06-30 | 2013-06-30 | 2013-06-30 | 2013-06-30 | 2013-06-30 | 2013-06-30 | 2013-06-30 | 2010-06-30 | 2010-06-30 | 2010-06-30 | 2010-06-30 | 2010-06-30 | 2010-06-30 | 2010-06-30 | 2010-06-30
24 | 68.8% | CP.01520 | Brisbane South No. 1 110/11kV Substation Establishment - Stage 1 | 2010-07-31 | 2010-07-31 | 0 | Augmentation |  | 0 | 0 | 0 | 3.0311 | 9.0628 | 0.1316 | 0 | 12.2255 | Reliability | [10 empty] | 2010-07-31 | 2010-07-31 | 2010-07-31 | 2010-07-31 | 2010-07-31 | 2010-07-31 | 2010-07-31 | 2010-07-31 | 2010-07-31 | 2010-07-31 | 2010-07-31 | 2010-07-31 | 2010-07-31 | 2010-07-31 | 2010-07-31 | 2010-07-31 | 2010-07-31 | 2010-07-31 | 2010-07-31 | 2010-07-31 | 2010-07-31 | 2010-07-31 | 2010-07-31 | 2010-07-31
32 | 76.07% | CP.01934 | Moreton North 3rd 110kV 50MVAr Capacitor Bank | 2010-08-31 | 2013-08-31 | 1096 | Augmentation |  | 0 | 0 | 0 | 0 | 0 | 0 | 0.20499 | 0.20499 | Reliability | [10 empty] | 2013-08-31 | 2013-08-31 | 2013-08-31 | 2013-08-31 | 2013-08-31 | 2013-08-31 | 2013-08-31 | 2013-08-31 | 2013-08-31 | 2013-08-31 | 2013-08-31 | 2013-08-31 | 2013-08-31 | 2013-08-31 | 2013-08-31 | 2013-08-31 | 2013-08-31 | 2013-08-31 | 2013-08-31 | 2013-08-31 | 2013-08-31 | 2013-08-31 | 2013-08-31 | 2013-08-31 | 2010-08-31 | 2010-08-31 | 2010-08-31 | 2010-08-31 | 2010-08-31 | 2010-08-31 | 2010-08-31 | 2010-08-31
32 | 76.07% | CP.01750 | South East Brisbane No. 3 Transition Point | 2010-08-31 | 2013-08-31 | 1096 | Augmentation |  | 0 | 0 | 0 | 0 | 0 | 0 | 0.13314 | 0.13314 | Reliability | [10 empty] | 2013-08-31 | 2013-08-31 | 2013-08-31 | 2013-08-31 | 2013-08-31 | 2013-08-31 | 2013-08-31 | 2013-08-31 | 2013-08-31 | 2013-08-31 | 2013-08-31 | 2013-08-31 | 2013-08-31 | 2013-08-31 | 2013-08-31 | 2013-08-31 | 2013-08-31 | 2013-08-31 | 2013-08-31 | 2013-08-31 | 2013-08-31 | 2013-08-31 | 2013-08-31 | 2013-08-31 | 2010-08-31 | 2010-08-31 | 2010-08-31 | 2010-08-31 | 2010-08-31 | 2010-08-31 | 2010-08-31 | 2010-08-31
24 | 68.8% | CP.01516 | South East Brisbane No. 1 110/11kV Substation Establishment - Stage 1 | 2010-09-30 | 2010-09-30 | 0 | Augmentation |  | 0 | 0 | 0 | 2.0069 | 6.8403 | 0.53651 | 0 | 9.3836 | Reliability | [10 empty] | 2010-09-30 | 2010-09-30 | 2010-09-30 | 2010-09-30 | 2010-09-30 | 2010-09-30 | 2010-09-30 | 2010-09-30 | 2010-09-30 | 2010-09-30 | 2010-09-30 | 2010-09-30 | 2010-09-30 | 2010-09-30 | 2010-09-30 | 2010-09-30 | 2010-09-30 | 2010-09-30 | 2010-09-30 | 2010-09-30 | 2010-09-30 | 2010-09-30 | 2010-09-30 | 2010-09-30
24 | 68.8% | CP.01517 | South East Brisbane No. 2 110/11kV Substation Establishment - Stage 1 | 2010-10-31 | 2010-10-31 | 0 | Augmentation |  | 0 | 0 | 0 | 2.0383 | 8.8171 | 1.3798 | 0 | 12.2352 | Reliability | [10 empty] | 2010-10-31 | 2010-10-31 | 2010-10-31 | 2010-10-31 | 2010-10-31 | 2010-10-31 | 2010-10-31 | 2010-10-31 | 2010-10-31 | 2010-10-31 | 2010-10-31 | 2010-10-31 | 2010-10-31 | 2010-10-31 | 2010-10-31 | 2010-10-31 | 2010-10-31 | 2010-10-31 | 2010-10-31 | 2010-10-31 | 2010-10-31 | 2010-10-31 | 2010-10-31 | 2010-10-31
32 | 76.07% | CP.01748 | Ashgrove West 110/33kV Transformers | 2010-10-31 | 2013-10-31 | 1096 | Augmentation |  | 0 | 0 | 0 | 0 | 0 | 0 | 1.4731 | 1.4731 | Reliability | [10 empty] | 2013-10-31 | 2013-10-31 | 2013-10-31 | 2013-10-31 | 2013-10-31 | 2013-10-31 | 2013-10-31 | 2013-10-31 | 2013-10-31 | 2013-10-31 | 2013-10-31 | 2013-10-31 | 2013-10-31 | 2013-10-31 | 2013-10-31 | 2013-10-31 | 2013-10-31 | 2013-10-31 | 2013-10-31 | 2013-10-31 | 2013-10-31 | 2013-10-31 | 2013-10-31 | 2013-10-31 | 2010-10-31 | 2010-10-31 | 2010-10-31 | 2010-10-31 | 2010-10-31 | 2010-10-31 | 2010-10-31 | 2010-10-31
8 | 7.277% | CP.01980 | SEQ No. 1 110/11kV Substation Establishment | 2011-07-31 | 2011-07-31 | 0 | Augmentation |  | 0 | 0 | 0 | 0 | 3.4658 | 10.3632 | 0.15049 | 13.9794 | Reliability |  |  | Scenarios & scenario probabilities 33: 2011-07-31; Scenarios & scenario probabilities 34: 2011-07-31; Scenarios & scenario probabilities 35: 2011-07-31; Scenarios & scenario probabilities 36: 2011-07-31; Scenarios & scenario probabilities 37: 2011-07-31; Scenarios & scenario probabilities 38: 2011-07-31; Scenarios & scenario probabilities 39: 2011-07-31; Scenarios & scenario probabilities 40: 2011-07-31
8 | 7.277% | CP.01612 | Black River 132/66kV Substation Establishment | 2011-08-31 | 2011-08-31 | 0 | Augmentation |  | 0 | 0 | 0 | 0 | 2.0597 | 7.01 | 0.23691 | 9.3066 | Reliability |  |  | Scenarios & scenario probabilities 33: 2011-08-31; Scenarios & scenario probabilities 34: 2011-08-31; Scenarios & scenario probabilities 35: 2011-08-31; Scenarios & scenario probabilities 36: 2011-08-31; Scenarios & scenario probabilities 37: 2011-08-31; Scenarios & scenario probabilities 38: 2011-08-31; Scenarios & scenario probabilities 39: 2011-08-31; Scenarios & scenario probabilities 40: 2011-08-31
8 | 7.277% | CP.01524 | South West Brisbane No. 1 110/33kV Substation Establishment | 2011-08-31 | 2011-08-31 | 0 | Augmentation |  | 0 | 0 | 0 | 0 | 3.2421 | 10.9954 | 0.37029 | 14.6078 | Reliability |  |  | Scenarios & scenario probabilities 33: 2011-08-31; Scenarios & scenario probabilities 34: 2011-08-31; Scenarios & scenario probabilities 35: 2011-08-31; Scenarios & scenario probabilities 36: 2011-08-31; Scenarios & scenario probabilities 37: 2011-08-31; Scenarios & scenario probabilities 38: 2011-08-31; Scenarios & scenario probabilities 39: 2011-08-31; Scenarios & scenario probabilities 40: 2011-08-31
8 | 7.277% | CP.01543/A | Mudgeeraba 275/110kV Transformer Augmentation | 2011-08-31 | 2011-08-31 | 0 | Augmentation |  | 0 | 0 | 0 | 0 | 3.857 | 12.4808 | 0.081512 | 16.4193 | Reliability |  |  | Scenarios & scenario probabilities 33: 2011-08-31; Scenarios & scenario probabilities 34: 2011-08-31; Scenarios & scenario probabilities 35: 2011-08-31; Scenarios & scenario probabilities 36: 2011-08-31; Scenarios & scenario probabilities 37: 2011-08-31; Scenarios & scenario probabilities 38: 2011-08-31; Scenarios & scenario probabilities 39: 2011-08-31; Scenarios & scenario probabilities 40: 2011-08-31
32 | 76.07% | CP.01554 | North West Brisbane No. 1 110/33kV Substation Establishment | 2011-08-31 | 2013-08-31 | 731 | Augmentation |  | 0 | 0 | 0 | 0 | 0 | 0 | 2.1625 | 2.1625 | Reliability | [10 empty] | 2013-08-31 | 2013-08-31 | 2013-08-31 | 2013-08-31 | 2013-08-31 | 2013-08-31 | 2013-08-31 | 2013-08-31 | 2013-08-31 | 2013-08-31 | 2013-08-31 | 2013-08-31 | 2013-08-31 | 2013-08-31 | 2013-08-31 | 2013-08-31 | 2013-08-31 | 2013-08-31 | 2013-08-31 | 2013-08-31 | 2013-08-31 | 2013-08-31 | 2013-08-31 | 2013-08-31 | 2011-08-31 | 2011-08-31 | 2011-08-31 | 2011-08-31 | 2011-08-31 | 2011-08-31 | 2011-08-31 | 2011-08-31
8 | 7.277% | CP.01594 | Abermain 275/110kV Transformer Augmentation | 2011-09-30 | 2011-09-30 | 0 | Augmentation |  | 0 | 0 | 0 | 0 | 1.9869 | 7.2335 | 0.045825 | 9.2663 | Reliability |  |  | Scenarios & scenario probabilities 33: 2011-09-30; Scenarios & scenario probabilities 34: 2011-09-30; Scenarios & scenario probabilities 35: 2011-09-30; Scenarios & scenario probabilities 36: 2011-09-30; Scenarios & scenario probabilities 37: 2011-09-30; Scenarios & scenario probabilities 38: 2011-09-30; Scenarios & scenario probabilities 39: 2011-09-30; Scenarios & scenario probabilities 40: 2011-09-30
8 | 7.277% | CP.01721 | South Coast to Tweed Transmission Reinforcement | 2011-09-30 | 2011-09-30 | 0 | Augmentation |  | 0 | 0 | 0 | 0 | 1.776 | 14.4499 | 0.3251 | 16.551 | Reliability |  |  | Scenarios & scenario probabilities 33: 2011-09-30; Scenarios & scenario probabilities 34: 2011-09-30; Scenarios & scenario probabilities 35: 2011-09-30; Scenarios & scenario probabilities 36: 2011-09-30; Scenarios & scenario probabilities 37: 2011-09-30; Scenarios & scenario probabilities 38: 2011-09-30; Scenarios & scenario probabilities 39: 2011-09-30; Scenarios & scenario probabilities 40: 2011-09-30
8 | 7.277% | CP.01979 | SEQ No. 1 110/33kV Transformer | 2011-09-30 | 2011-09-30 | 0 | Augmentation |  | 0 | 0 | 0 | 0 | 1.6354 | 5.9638 | 0.037845 | 7.637 | Reliability |  |  | Scenarios & scenario probabilities 33: 2011-09-30; Scenarios & scenario probabilities 34: 2011-09-30; Scenarios & scenario probabilities 35: 2011-09-30; Scenarios & scenario probabilities 36: 2011-09-30; Scenarios & scenario probabilities 37: 2011-09-30; Scenarios & scenario probabilities 38: 2011-09-30; Scenarios & scenario probabilities 39: 2011-09-30; Scenarios & scenario probabilities 40: 2011-09-30
8 | 7.277% | CP.01763 | Tarong 275/132kV Transformer Augmentations | 2011-09-30 | 2011-09-30 | 0 | Augmentation |  | 0 | 0 | 0 | 0 | 1.9178 | 7.0103 | 0.044592 | 8.9727 | Reliability |  |  | Scenarios & scenario probabilities 33: 2011-09-30; Scenarios & scenario probabilities 34: 2011-09-30; Scenarios & scenario probabilities 35: 2011-09-30; Scenarios & scenario probabilities 36: 2011-09-30; Scenarios & scenario probabilities 37: 2011-09-30; Scenarios & scenario probabilities 38: 2011-09-30; Scenarios & scenario probabilities 39: 2011-09-30; Scenarios & scenario probabilities 40: 2011-09-30
32 | 76.07% | CP.01720 | Innisfail 2nd 132kV 20MVAr Capacitor Bank | 2011-09-30 | 2013-09-30 | 731 | Augmentation |  | 0 | 0 | 0 | 0 | 0 | 0 | 0.2157 | 0.2157 | Reliability | [10 empty] | 2013-09-30 | 2013-09-30 | 2013-09-30 | 2013-09-30 | 2013-09-30 | 2013-09-30 | 2013-09-30 | 2013-09-30 | 2013-09-30 | 2013-09-30 | 2013-09-30 | 2013-09-30 | 2013-09-30 | 2013-09-30 | 2013-09-30 | 2013-09-30 | 2013-09-30 | 2013-09-30 | 2013-09-30 | 2013-09-30 | 2013-09-30 | 2013-09-30 | 2013-09-30 | 2013-09-30 | 2011-09-30 | 2011-09-30 | 2011-09-30 | 2011-09-30 | 2011-09-30 | 2011-09-30 | 2011-09-30 | 2011-09-30
32 | 76.07% | CP.01268 | Woree 3rd 132kV 50MVAr Capacitor Bank | 2011-09-30 | 2012-09-30 | 366 | Augmentation |  | 0 | 0 | 0 | 0 | 0 | 0.28109 | 1.9768 | 2.2579 | Reliability | [10 empty] | 2012-09-30 | 2012-09-30 | 2012-09-30 | 2012-09-30 | 2012-09-30 | 2012-09-30 | 2012-09-30 | 2012-09-30 | 2012-09-30 | 2012-09-30 | 2012-09-30 | 2012-09-30 | 2012-09-30 | 2012-09-30 | 2012-09-30 | 2012-09-30 | 2012-09-30 | 2012-09-30 | 2012-09-30 | 2012-09-30 | 2012-09-30 | 2012-09-30 | 2012-09-30 | 2012-09-30 | 2011-09-30 | 2011-09-30 | 2011-09-30 | 2011-09-30 | 2011-09-30 | 2011-09-30 | 2011-09-30 | 2011-09-30
32 | 76.07% | CP.01935 | Moreton North 4th 110kV 50MVAr Capacitor Bank | 2012-05-31 | 2014-05-31 | 730 | Augmentation |  | 0 | 0 | 0 | 0 | 0 | 0 | 0.16465 | 0.16465 | Reliability | [10 empty] | 2014-05-31 | 2014-05-31 | 2014-05-31 | 2014-05-31 | 2014-05-31 | 2014-05-31 | 2014-05-31 | 2014-05-31 | 2014-05-31 | 2014-05-31 | 2014-05-31 | 2014-05-31 | 2014-05-31 | 2014-05-31 | 2014-05-31 | 2014-05-31 | 2014-05-31 | 2014-05-31 | 2014-05-31 | 2014-05-31 | 2014-05-31 | 2014-05-31 | 2014-05-31 | 2014-05-31 | 2012-05-31 | 2012-05-31 | 2012-05-31 | 2012-05-31 | 2012-05-31 | 2012-05-31 | 2012-05-31 | 2012-05-31
8 | 7.277% | CP.01936 | Moreton North 5th 110kV 50MVAr Capacitor Bank | 2012-06-30 | 2012-06-30 | 0 | Augmentation |  | 0 | 0 | 0 | 0 | 0 | 0.22346 | 1.7116 | 1.9351 | Reliability |  |  | Scenarios & scenario probabilities 33: 2012-06-30; Scenarios & scenario probabilities 34: 2012-06-30; Scenarios & scenario probabilities 35: 2012-06-30; Scenarios & scenario probabilities 36: 2012-06-30; Scenarios & scenario probabilities 37: 2012-06-30; Scenarios & scenario probabilities 38: 2012-06-30; Scenarios & scenario probabilities 39: 2012-06-30; Scenarios & scenario probabilities 40: 2012-06-30
8 | 7.277% | CP.01553 | Brisbane West 110/11kV Substation Establishment | 2012-07-31 | 2012-07-31 | 0 | Augmentation |  | 0 | 0 | 0 | 0 | 0 | 2.3761 | 7.117 | 9.4931 | Reliability |  |  | Scenarios & scenario probabilities 33: 2012-07-31; Scenarios & scenario probabilities 34: 2012-07-31; Scenarios & scenario probabilities 35: 2012-07-31; Scenarios & scenario probabilities 36: 2012-07-31; Scenarios & scenario probabilities 37: 2012-07-31; Scenarios & scenario probabilities 38: 2012-07-31; Scenarios & scenario probabilities 39: 2012-07-31; Scenarios & scenario probabilities 40: 2012-07-31
8 | 7.277% | CP.01269 | Woree 4th 132kV 50MVAr Capacitor Bank | 2012-07-31 | 2012-07-31 | 0 | Augmentation |  | 0 | 0 | 0 | 0 | 0 | 0.23551 | 1.8739 | 2.1094 | Reliability |  |  | Scenarios & scenario probabilities 33: 2012-07-31; Scenarios & scenario probabilities 34: 2012-07-31; Scenarios & scenario probabilities 35: 2012-07-31; Scenarios & scenario probabilities 36: 2012-07-31; Scenarios & scenario probabilities 37: 2012-07-31; Scenarios & scenario probabilities 38: 2012-07-31; Scenarios & scenario probabilities 39: 2012-07-31; Scenarios & scenario probabilities 40: 2012-07-31
8 | 7.277% | CP.01766 | Cairns Region 132/22kV Substation Establishment | 2012-08-31 | 2012-08-31 | 0 | Augmentation |  | 0 | 0 | 0 | 0 | 0 | 2.4655 | 14.9983 | 17.4638 | Reliability |  |  | Scenarios & scenario probabilities 33: 2012-08-31; Scenarios & scenario probabilities 34: 2012-08-31; Scenarios & scenario probabilities 35: 2012-08-31; Scenarios & scenario probabilities 36: 2012-08-31; Scenarios & scenario probabilities 37: 2012-08-31; Scenarios & scenario probabilities 38: 2012-08-31; Scenarios & scenario probabilities 39: 2012-08-31; Scenarios & scenario probabilities 40: 2012-08-31
8 | 7.277% | CP.01943 | Moreton South 1st 110kV 50MVAr Capacitor Bank | 2012-08-31 | 2012-08-31 | 0 | Augmentation |  | 0 | 0 | 0 | 0 | 0 | 0.20319 | 1.5401 | 1.7433 | Reliability |  |  | Scenarios & scenario probabilities 33: 2012-08-31; Scenarios & scenario probabilities 34: 2012-08-31; Scenarios & scenario probabilities 35: 2012-08-31; Scenarios & scenario probabilities 36: 2012-08-31; Scenarios & scenario probabilities 37: 2012-08-31; Scenarios & scenario probabilities 38: 2012-08-31; Scenarios & scenario probabilities 39: 2012-08-31; Scenarios & scenario probabilities 40: 2012-08-31
24 | 68.8% | CP.01591 | South East Brisbane No. 2 110/11kV Transformer Bay - Stage 2 | 2012-09-30 | 2012-09-30 | 0 | Augmentation |  | 0 | 0 | 0 | 0 | 0 | 0.35991 | 1.311 | 1.6709 | Reliability | [10 empty] | 2012-09-30 | 2012-09-30 | 2012-09-30 | 2012-09-30 | 2012-09-30 | 2012-09-30 | 2012-09-30 | 2012-09-30 | 2012-09-30 | 2012-09-30 | 2012-09-30 | 2012-09-30 | 2012-09-30 | 2012-09-30 | 2012-09-30 | 2012-09-30 | 2012-09-30 | 2012-09-30 | 2012-09-30 | 2012-09-30 | 2012-09-30 | 2012-09-30 | 2012-09-30 | 2012-09-30
8 | 7.277% | CP.01868 | 275kV Double Circuit to Nudgee | 2012-09-30 | 2012-09-30 | 0 | Augmentation |  | 0 | 0 | 0 | 0 | 0 | 13.6368 | 46.4846 | 60.1214 | Reliability |  |  | Scenarios & scenario probabilities 33: 2012-09-30; Scenarios & scenario probabilities 34: 2012-09-30; Scenarios & scenario probabilities 35: 2012-09-30; Scenarios & scenario probabilities 36: 2012-09-30; Scenarios & scenario probabilities 37: 2012-09-30; Scenarios & scenario probabilities 38: 2012-09-30; Scenarios & scenario probabilities 39: 2012-09-30; Scenarios & scenario probabilities 40: 2012-09-30
8 | 7.277% | CP.01522/A | South West Brisbane No. 2 110/11kV Substation Establishment | 2012-10-31 | 2012-10-31 | 0 | Augmentation |  | 0 | 0 | 0 | 0 | 0 | 2.2627 | 9.7936 | 12.0563 | Reliability |  |  | Scenarios & scenario probabilities 33: 2012-10-31; Scenarios & scenario probabilities 34: 2012-10-31; Scenarios & scenario probabilities 35: 2012-10-31; Scenarios & scenario probabilities 36: 2012-10-31; Scenarios & scenario probabilities 37: 2012-10-31; Scenarios & scenario probabilities 38: 2012-10-31; Scenarios & scenario probabilities 39: 2012-10-31; Scenarios & scenario probabilities 40: 2012-10-31
8 | 7.277% | CP.01620 | Bouldercombe 275/132kV Transformer Augmentation | 2012-10-31 | 2012-10-31 | 0 | Augmentation |  | 0 | 0 | 0 | 0 | 0 | 2.119 | 8.0861 | 10.2051 | Reliability |  |  | Scenarios & scenario probabilities 33: 2012-10-31; Scenarios & scenario probabilities 34: 2012-10-31; Scenarios & scenario probabilities 35: 2012-10-31; Scenarios & scenario probabilities 36: 2012-10-31; Scenarios & scenario probabilities 37: 2012-10-31; Scenarios & scenario probabilities 38: 2012-10-31; Scenarios & scenario probabilities 39: 2012-10-31; Scenarios & scenario probabilities 40: 2012-10-31
8 | 7.277% | CP.01981 | SEQ No. 1 110/33kV Substation Establishment | 2012-10-31 | 2012-10-31 | 0 | Augmentation |  | 0 | 0 | 0 | 0 | 0 | 3.2713 | 14.1797 | 17.451 | Reliability |  |  | Scenarios & scenario probabilities 33: 2012-10-31; Scenarios & scenario probabilities 34: 2012-10-31; Scenarios & scenario probabilities 35: 2012-10-31; Scenarios & scenario probabilities 36: 2012-10-31; Scenarios & scenario probabilities 37: 2012-10-31; Scenarios & scenario probabilities 38: 2012-10-31; Scenarios & scenario probabilities 39: 2012-10-31; Scenarios & scenario probabilities 40: 2012-10-31
8 | 7.277% | CP.01944 | Moreton South 2nd 110kV 50MVAr Capacitor Bank | 2013-05-31 | 2013-05-31 | 0 | Augmentation |  | 0 | 0 | 0 | 0 | 0 | 0.1632 | 0.072331 | 0.23553 | Reliability |  |  | Scenarios & scenario probabilities 33: 2013-05-31; Scenarios & scenario probabilities 34: 2013-05-31; Scenarios & scenario probabilities 35: 2013-05-31; Scenarios & scenario probabilities 36: 2013-05-31; Scenarios & scenario probabilities 37: 2013-05-31; Scenarios & scenario probabilities 38: 2013-05-31; Scenarios & scenario probabilities 39: 2013-05-31; Scenarios & scenario probabilities 40: 2013-05-31
8 | 7.277% | CP.01945 | Moreton South 3rd 110kV 50MVAr Capacitor Bank | 2013-05-31 | 2013-05-31 | 0 | Augmentation |  | 0 | 0 | 0 | 0 | 0 | 0.1632 | 0.072331 | 0.23553 | Reliability |  |  | Scenarios & scenario probabilities 33: 2013-05-31; Scenarios & scenario probabilities 34: 2013-05-31; Scenarios & scenario probabilities 35: 2013-05-31; Scenarios & scenario probabilities 36: 2013-05-31; Scenarios & scenario probabilities 37: 2013-05-31; Scenarios & scenario probabilities 38: 2013-05-31; Scenarios & scenario probabilities 39: 2013-05-31; Scenarios & scenario probabilities 40: 2013-05-31
8 | 7.277% | CP.01982 | SEQ No. 2 110/33kV Substation Establishment | 2013-05-31 | 2013-05-31 | 0 | Augmentation |  | 0 | 0 | 0 | 0 | 0 | 1.2822 | 4.9304 | 6.2126 | Reliability |  |  | Scenarios & scenario probabilities 33: 2013-05-31; Scenarios & scenario probabilities 34: 2013-05-31; Scenarios & scenario probabilities 35: 2013-05-31; Scenarios & scenario probabilities 36: 2013-05-31; Scenarios & scenario probabilities 37: 2013-05-31; Scenarios & scenario probabilities 38: 2013-05-31; Scenarios & scenario probabilities 39: 2013-05-31; Scenarios & scenario probabilities 40: 2013-05-31
8 | 7.277% | CP.01876 | Edmonton 2nd 132kV 30MVAr Capacitor Bank | 2013-06-30 | 2013-06-30 | 0 | Augmentation |  | 0 | 0 | 0 | 0 | 0 | 0 | 1.5197 | 1.5197 | Reliability |  |  | Scenarios & scenario probabilities 33: 2013-06-30; Scenarios & scenario probabilities 34: 2013-06-30; Scenarios & scenario probabilities 35: 2013-06-30; Scenarios & scenario probabilities 36: 2013-06-30; Scenarios & scenario probabilities 37: 2013-06-30; Scenarios & scenario probabilities 38: 2013-06-30; Scenarios & scenario probabilities 39: 2013-06-30; Scenarios & scenario probabilities 40: 2013-06-30
24 | 68.8% | CP.01608 | South East Brisbane No. 1 110/11kV Transformer Bay - Stage 2 | 2013-07-31 | 2013-07-31 | 0 | Augmentation |  | 0 | 0 | 0 | 0 | 0 | 0 | 0.12176 | 0.12176 | Reliability | [10 empty] | 2013-07-31 | 2013-07-31 | 2013-07-31 | 2013-07-31 | 2013-07-31 | 2013-07-31 | 2013-07-31 | 2013-07-31 | 2013-07-31 | 2013-07-31 | 2013-07-31 | 2013-07-31 | 2013-07-31 | 2013-07-31 | 2013-07-31 | 2013-07-31 | 2013-07-31 | 2013-07-31 | 2013-07-31 | 2013-07-31 | 2013-07-31 | 2013-07-31 | 2013-07-31 | 2013-07-31
8 | 7.277% | CP.01839 | South Coast 275/110kV Substation Establishment | 2013-08-31 | 2013-08-31 | 0 | Augmentation |  | 0 | 0 | 0 | 0 | 0 | 0 | 5.2882 | 5.2882 | Reliability |  |  | Scenarios & scenario probabilities 33: 2013-08-31; Scenarios & scenario probabilities 34: 2013-08-31; Scenarios & scenario probabilities 35: 2013-08-31; Scenarios & scenario probabilities 36: 2013-08-31; Scenarios & scenario probabilities 37: 2013-08-31; Scenarios & scenario probabilities 38: 2013-08-31; Scenarios & scenario probabilities 39: 2013-08-31; Scenarios & scenario probabilities 40: 2013-08-31
8 | 7.277% | CP.01986 | CQ No. 1 132/66kV Substation Establishment | 2013-09-30 | 2013-09-30 | 0 | Augmentation |  | 0 | 0 | 0 | 0 | 0 | 0 | 3.5229 | 3.5229 | Reliability |  |  | Scenarios & scenario probabilities 33: 2013-09-30; Scenarios & scenario probabilities 34: 2013-09-30; Scenarios & scenario probabilities 35: 2013-09-30; Scenarios & scenario probabilities 36: 2013-09-30; Scenarios & scenario probabilities 37: 2013-09-30; Scenarios & scenario probabilities 38: 2013-09-30; Scenarios & scenario probabilities 39: 2013-09-30; Scenarios & scenario probabilities 40: 2013-09-30
8 | 7.277% | CP.01595 | South West Brisbane 275/110kV Transformer Augmentation | 2013-10-31 | 2013-10-31 | 0 | Augmentation |  | 0 | 0 | 0 | 0 | 0 | 0 | 2.1515 | 2.1515 | Reliability |  |  | Scenarios & scenario probabilities 33: 2013-10-31; Scenarios & scenario probabilities 34: 2013-10-31; Scenarios & scenario probabilities 35: 2013-10-31; Scenarios & scenario probabilities 36: 2013-10-31; Scenarios & scenario probabilities 37: 2013-10-31; Scenarios & scenario probabilities 38: 2013-10-31; Scenarios & scenario probabilities 39: 2013-10-31; Scenarios & scenario probabilities 40: 2013-10-31
8 | 7.277% | CP.01946 | Moreton South 4th 110kV 50MVAr Capacitor Bank | 2014-05-31 | 2014-05-31 | 0 | Augmentation |  | 0 | 0 | 0 | 0 | 0 | 0 | 0.16465 | 0.16465 | Reliability |  |  | Scenarios & scenario probabilities 33: 2014-05-31; Scenarios & scenario probabilities 34: 2014-05-31; Scenarios & scenario probabilities 35: 2014-05-31; Scenarios & scenario probabilities 36: 2014-05-31; Scenarios & scenario probabilities 37: 2014-05-31; Scenarios & scenario probabilities 38: 2014-05-31; Scenarios & scenario probabilities 39: 2014-05-31; Scenarios & scenario probabilities 40: 2014-05-31
8 | 7.277% | CP.01947 | Moreton South 5th 110kV 50MVAr Capacitor Bank | 2014-05-31 | 2014-05-31 | 0 | Augmentation |  | 0 | 0 | 0 | 0 | 0 | 0 | 0.16465 | 0.16465 | Reliability |  |  | Scenarios & scenario probabilities 33: 2014-05-31; Scenarios & scenario probabilities 34: 2014-05-31; Scenarios & scenario probabilities 35: 2014-05-31; Scenarios & scenario probabilities 36: 2014-05-31; Scenarios & scenario probabilities 37: 2014-05-31; Scenarios & scenario probabilities 38: 2014-05-31; Scenarios & scenario probabilities 39: 2014-05-31; Scenarios & scenario probabilities 40: 2014-05-31
40 | 100% | CP.01259 | Woree 132kV Feeders bays for Cairns North | 2007-07-31 | 2010-07-31 | 1096 | Connection |  | 0 | 0.46659 | 1.4066 | 0.020575 | 0 | 0 | 0 | 1.4272 | Reliability |  |  | 2010-07-31 | 2010-07-31 | 2010-07-31 | 2010-07-31 | 2010-07-31 | 2010-07-31 | 2010-07-31 | 2010-07-31 | 2008-07-31 | 2008-07-31 | 2008-07-31 | 2008-07-31 | 2008-07-31 | 2008-07-31 | 2008-07-31 | 2008-07-31 | 2008-07-31 | 2008-07-31 | 2008-07-31 | 2008-07-31 | 2008-07-31 | 2008-07-31 | 2008-07-31 | 2008-07-31 | 2008-07-31 | 2008-07-31 | 2008-07-31 | 2008-07-31 | 2008-07-31 | 2008-07-31 | 2008-07-31 | 2008-07-31 | 2007-07-31 | 2007-07-31 | 2007-07-31 | 2007-07-31 | 2007-07-31 | 2007-07-31 | 2007-07-31 | 2007-07-31
40 | 100% | CP.01751 | Middle Ridge to Murphys Creek Operating at 110kV | 2008-05-31 | 2009-05-31 | 365 | Connection |  | 0.15842 | 0.4869 | 1.5847 | 0 | 0 | 0 | 0 | 1.5847 | Reliability |  |  | 2009-05-31 | 2009-05-31 | 2009-05-31 | 2009-05-31 | 2009-05-31 | 2009-05-31 | 2009-05-31 | 2009-05-31 | 2008-05-31 | 2008-05-31 | 2008-05-31 | 2008-05-31 | 2008-05-31 | 2008-05-31 | 2008-05-31 | 2008-05-31 | 2008-05-31 | 2008-05-31 | 2008-05-31 | 2008-05-31 | 2008-05-31 | 2008-05-31 | 2008-05-31 | 2008-05-31 | 2008-05-31 | 2008-05-31 | 2008-05-31 | 2008-05-31 | 2008-05-31 | 2008-05-31 | 2008-05-31 | 2008-05-31 | 2008-05-31 | 2008-05-31 | 2008-05-31 | 2008-05-31 | 2008-05-31 | 2008-05-31 | 2008-05-31 | 2008-05-31
40 | 100% | CP.01599 | South Pine 110kV Feeder Bays for Griffin | 2008-05-31 | 2012-05-31 | 1461 | Connection |  | 0.12926 | 0.50272 | 1.3872 | 0 | 0 | 0 | 0 | 1.3872 | Reliability |  |  | 2012-05-31 | 2012-05-31 | 2012-05-31 | 2012-05-31 | 2012-05-31 | 2012-05-31 | 2012-05-31 | 2012-05-31 | 2008-05-31 | 2008-05-31 | 2008-05-31 | 2008-05-31 | 2008-05-31 | 2008-05-31 | 2008-05-31 | 2008-05-31 | 2008-05-31 | 2008-05-31 | 2008-05-31 | 2008-05-31 | 2008-05-31 | 2008-05-31 | 2008-05-31 | 2008-05-31 | 2008-05-31 | 2008-05-31 | 2008-05-31 | 2008-05-31 | 2008-05-31 | 2008-05-31 | 2008-05-31 | 2008-05-31 | 2008-05-31 | 2008-05-31 | 2008-05-31 | 2008-05-31 | 2008-05-31 | 2008-05-31 | 2008-05-31 | 2008-05-31
32 | 76.07% | CP.01659 | Callide A 132kV Feeder Bay for Monto Mine | 2008-06-30 | 2010-06-30 | 730 | Connection |  | 0 | 0 | 0 | 0.8052 | 2.1245 | 0 | 0 | 2.9297 | Reliability | [10 empty] | 2010-06-30 | 2010-06-30 | 2010-06-30 | 2010-06-30 | 2010-06-30 | 2010-06-30 | 2010-06-30 | 2010-06-30 | 2010-06-30 | 2010-06-30 | 2010-06-30 | 2010-06-30 | 2010-06-30 | 2010-06-30 | 2010-06-30 | 2010-06-30 | 2010-06-30 | 2010-06-30 | 2010-06-30 | 2010-06-30 | 2010-06-30 | 2010-06-30 | 2010-06-30 | 2010-06-30 | 2008-06-30 | 2008-06-30 | 2008-06-30 | 2008-06-30 | 2008-06-30 | 2008-06-30 | 2008-06-30 | 2008-06-30
40 | 100% | CP.01600 | Palmwoods 132kV Feeder Bays for Marcoola | 2008-06-30 | 2012-06-30 | 1461 | Connection |  | 0 | 0.70546 | 1.8629 | 0 | 0 | 0 | 0 | 1.8629 | Reliability |  |  | 2012-06-30 | 2012-06-30 | 2012-06-30 | 2012-06-30 | 2012-06-30 | 2012-06-30 | 2012-06-30 | 2012-06-30 | 2008-06-30 | 2008-06-30 | 2008-06-30 | 2008-06-30 | 2008-06-30 | 2008-06-30 | 2008-06-30 | 2008-06-30 | 2008-06-30 | 2008-06-30 | 2008-06-30 | 2008-06-30 | 2008-06-30 | 2008-06-30 | 2008-06-30 | 2008-06-30 | 2008-06-30 | 2008-06-30 | 2008-06-30 | 2008-06-30 | 2008-06-30 | 2008-06-30 | 2008-06-30 | 2008-06-30 | 2008-06-30 | 2008-06-30 | 2008-06-30 | 2008-06-30 | 2008-06-30 | 2008-06-30 | 2008-06-30 | 2008-06-30
32 | 76.07% | CP.01602 | Abermain 110kV Feeder Bay for Wulkuraka | 2008-07-31 | 2009-07-31 | 365 | Connection |  | 0 | 0 | 0.42452 | 1.2772 | 0.018664 | 0 | 0 | 1.7204 | Reliability | [10 empty] | 2009-07-31 | 2009-07-31 | 2009-07-31 | 2009-07-31 | 2009-07-31 | 2009-07-31 | 2009-07-31 | 2009-07-31 | 2009-07-31 | 2009-07-31 | 2009-07-31 | 2009-07-31 | 2009-07-31 | 2009-07-31 | 2009-07-31 | 2009-07-31 | 2009-07-31 | 2009-07-31 | 2009-07-31 | 2009-07-31 | 2009-07-31 | 2009-07-31 | 2009-07-31 | 2009-07-31 | 2008-07-31 | 2008-07-31 | 2008-07-31 | 2008-07-31 | 2008-07-31 | 2008-07-31 | 2008-07-31 | 2008-07-31
40 | 100% | CP.01752 | Woolooga Uprate Feeder Bays for Gympie Circuits | 2008-07-31 | 2013-07-31 | 1826 | Connection |  | 0 | 0 | 0.56791 | 1.7139 | 0.025122 | 0 | 0 | 2.3069 | Reliability |  |  | 2013-07-31 | 2013-07-31 | 2013-07-31 | 2013-07-31 | 2013-07-31 | 2013-07-31 | 2013-07-31 | 2013-07-31 | 2009-07-31 | 2009-07-31 | 2009-07-31 | 2009-07-31 | 2009-07-31 | 2009-07-31 | 2009-07-31 | 2009-07-31 | 2009-07-31 | 2009-07-31 | 2009-07-31 | 2009-07-31 | 2009-07-31 | 2009-07-31 | 2009-07-31 | 2009-07-31 | 2009-07-31 | 2009-07-31 | 2009-07-31 | 2009-07-31 | 2009-07-31 | 2009-07-31 | 2009-07-31 | 2009-07-31 | 2008-07-31 | 2008-07-31 | 2008-07-31 | 2008-07-31 | 2008-07-31 | 2008-07-31 | 2008-07-31 | 2008-07-31
40 | 100% | CP.01285 | Bolingbroke QR Rail Supply | 2008-08-30 | 2010-08-31 | 731 | Connection |  | 0 | 2.1236 | 15.6469 | 0.17973 | 0 | 0 | 0 | 15.8266 | Reliability |  |  | 2010-08-31 | 2010-08-31 | 2010-08-31 | 2010-08-31 | 2010-08-31 | 2010-08-31 | 2010-08-31 | 2010-08-31 | 2008-08-30 | 2008-08-30 | 2008-08-30 | 2008-08-30 | 2008-08-30 | 2008-08-30 | 2008-08-30 | 2008-08-30 | 2008-08-30 | 2008-08-30 | 2008-08-30 | 2008-08-30 | 2008-08-30 | 2008-08-30 | 2008-08-30 | 2008-08-30 | 2008-08-30 | 2008-08-30 | 2008-08-30 | 2008-08-30 | 2008-08-30 | 2008-08-30 | 2008-08-30 | 2008-08-30 | 2008-08-31 | 2008-08-31 | 2008-08-31 | 2008-08-31 | 2008-08-31 | 2008-08-31 | 2008-08-31 | 2008-08-31
32 | 76.07% | CP.01758 | Pioneer Valley Transformer Augmentation | 2009-07-31 | 2011-07-31 | 730 | Connection |  | 0 | 0 | 0 | 0 | 0.72201 | 1.9889 | 0.01352 | 2.7245 | Reliability | [10 empty] | 2011-07-31 | 2011-07-31 | 2011-07-31 | 2011-07-31 | 2011-07-31 | 2011-07-31 | 2011-07-31 | 2011-07-31 | 2011-07-31 | 2011-07-31 | 2011-07-31 | 2011-07-31 | 2011-07-31 | 2011-07-31 | 2011-07-31 | 2011-07-31 | 2011-07-31 | 2011-07-31 | 2011-07-31 | 2011-07-31 | 2011-07-31 | 2011-07-31 | 2011-07-31 | 2011-07-31 | 2009-07-31 | 2009-07-31 | 2009-07-31 | 2009-07-31 | 2009-07-31 | 2009-07-31 | 2009-07-31 | 2009-07-31
32 | 76.07% | CP.01662 | Blackwater 132kV Feeder Bay for Emerald | 2009-08-31 | 2009-08-31 | 0 | Connection |  | 0 | 0 | 0.45043 | 1.5344 | 0.051902 | 0 | 0 | 2.0367 | Reliability | [10 empty] | 2009-08-31 | 2009-08-31 | 2009-08-31 | 2009-08-31 | 2009-08-31 | 2009-08-31 | 2009-08-31 | 2009-08-31 | 2009-08-31 | 2009-08-31 | 2009-08-31 | 2009-08-31 | 2009-08-31 | 2009-08-31 | 2009-08-31 | 2009-08-31 | 2009-08-31 | 2009-08-31 | 2009-08-31 | 2009-08-31 | 2009-08-31 | 2009-08-31 | 2009-08-31 | 2009-08-31 | 2009-08-31 | 2009-08-31 | 2009-08-31 | 2009-08-31 | 2009-08-31 | 2009-08-31 | 2009-08-31 | 2009-08-31
32 | 76.07% | CP.01607 | Pandoin 132kV Feeder Bay Yeppoon | 2009-08-31 | 2011-08-31 | 730 | Connection |  | 0 | 0 | 0 | 0 | 0.3362 | 1.1472 | 0.03887 | 1.5222 | Reliability | [10 empty] | 2011-08-31 | 2011-08-31 | 2011-08-31 | 2011-08-31 | 2011-08-31 | 2011-08-31 | 2011-08-31 | 2011-08-31 | 2011-08-31 | 2011-08-31 | 2011-08-31 | 2011-08-31 | 2011-08-31 | 2011-08-31 | 2011-08-31 | 2011-08-31 | 2011-08-31 | 2011-08-31 | 2011-08-31 | 2011-08-31 | 2011-08-31 | 2011-08-31 | 2011-08-31 | 2011-08-31 | 2009-08-31 | 2009-08-31 | 2009-08-31 | 2009-08-31 | 2009-08-31 | 2009-08-31 | 2009-08-31 | 2009-08-31
40 | 100% | CP.01606 | Clare 132kV Feeder Bay for Millchester | 2010-05-31 | 2014-05-31 | 1461 | Connection |  | 0 | 0 | 0 | 0 | 0.072589 | 0.28067 | 0.77556 | 1.1288 | Reliability |  |  | 2014-05-31 | 2014-05-31 | 2014-05-31 | 2014-05-31 | 2014-05-31 | 2014-05-31 | 2014-05-31 | 2014-05-31 | 2012-05-31 | 2012-05-31 | 2012-05-31 | 2012-05-31 | 2012-05-31 | 2012-05-31 | 2012-05-31 | 2012-05-31 | 2012-05-31 | 2012-05-31 | 2012-05-31 | 2012-05-31 | 2012-05-31 | 2012-05-31 | 2012-05-31 | 2012-05-31 | 2012-05-31 | 2012-05-31 | 2012-05-31 | 2012-05-31 | 2012-05-31 | 2012-05-31 | 2012-05-31 | 2012-05-31 | 2010-05-31 | 2010-05-31 | 2010-05-31 | 2010-05-31 | 2010-05-31 | 2010-05-31 | 2010-05-31 | 2010-05-31
32 | 76.07% | CP.01757 | Collinsville Transformer and 33kV Cable Upgrades | 2010-05-31 | 2013-05-31 | 1096 | Connection |  | 0 | 0 | 0 | 0 | 0 | 0.28202 | 1.0922 | 1.3743 | Reliability | [10 empty] | 2013-05-31 | 2013-05-31 | 2013-05-31 | 2013-05-31 | 2013-05-31 | 2013-05-31 | 2013-05-31 | 2013-05-31 | 2013-05-31 | 2013-05-31 | 2013-05-31 | 2013-05-31 | 2013-05-31 | 2013-05-31 | 2013-05-31 | 2013-05-31 | 2013-05-31 | 2013-05-31 | 2013-05-31 | 2013-05-31 | 2013-05-31 | 2013-05-31 | 2013-05-31 | 2013-05-31 | 2010-05-31 | 2010-05-31 | 2010-05-31 | 2010-05-31 | 2010-05-31 | 2010-05-31 | 2010-05-31 | 2010-05-31
32 | 76.07% | CP.01713 | Tennyson Substation Bus Section and Feeder Bay for CBD | 2010-05-31 | 2013-05-31 | 1096 | Connection |  | 0 | 0 | 0 | 0 | 0 | 0 | 1.3183 | 1.3183 | Reliability | [10 empty] | 2013-05-31 | 2013-05-31 | 2013-05-31 | 2013-05-31 | 2013-05-31 | 2013-05-31 | 2013-05-31 | 2013-05-31 | 2013-05-31 | 2013-05-31 | 2013-05-31 | 2013-05-31 | 2013-05-31 | 2013-05-31 | 2013-05-31 | 2013-05-31 | 2013-05-31 | 2013-05-31 | 2013-05-31 | 2013-05-31 | 2013-05-31 | 2013-05-31 | 2013-05-31 | 2013-05-31 | 2010-05-31 | 2010-05-31 | 2010-05-31 | 2010-05-31 | 2010-05-31 | 2010-05-31 | 2010-05-31 | 2010-05-31
8 | 7.277% | CP.01975/A | Switch Bay Changes for DNSP Works for 5 years - High Load Growth | 2010-06-30 | 2010-06-30 | 0 | Connection |  | 0 | 0 | 0 | 1.5583 | 4.0808 | 0 | 0 | 5.6391 | Reliability |  |  | Scenarios & scenario probabilities 33: 2010-06-30; Scenarios & scenario probabilities 34: 2010-06-30; Scenarios & scenario probabilities 35: 2010-06-30; Scenarios & scenario probabilities 36: 2010-06-30; Scenarios & scenario probabilities 37: 2010-06-30; Scenarios & scenario probabilities 38: 2010-06-30; Scenarios & scenario probabilities 39: 2010-06-30; Scenarios & scenario probabilities 40: 2010-06-30
8 | 23.93% | CP.01973/A | Switch Bay Changes for DNSP Works for 5 years - Light Load Growth | 2010-06-30 | 2010-06-30 | 0 | Connection |  | 0 | 0 | 0 | 0.63146 | 1.6564 | 0 | 0 | 2.2879 | Reliability |  |  | Scenarios & scenario probabilities 1: 2010-06-30; Scenarios & scenario probabilities 2: 2010-06-30; Scenarios & scenario probabilities 3: 2010-06-30; Scenarios & scenario probabilities 4: 2010-06-30; Scenarios & scenario probabilities 5: 2010-06-30; Scenarios & scenario probabilities 6: 2010-06-30; Scenarios & scenario probabilities 7: 2010-06-30; Scenarios & scenario probabilities 8: 2010-06-30
24 | 68.8% | CP.01974/A | Switch Bay Changes for DNSP Works for 5 years - Medium Load Growth | 2010-06-30 | 2010-06-30 | 0 | Connection |  | 0 | 0 | 0 | 0.89737 | 2.3519 | 0 | 0 | 3.2493 | Reliability | [10 empty] | 2010-06-30 | 2010-06-30 | 2010-06-30 | 2010-06-30 | 2010-06-30 | 2010-06-30 | 2010-06-30 | 2010-06-30 | 2010-06-30 | 2010-06-30 | 2010-06-30 | 2010-06-30 | 2010-06-30 | 2010-06-30 | 2010-06-30 | 2010-06-30 | 2010-06-30 | 2010-06-30 | 2010-06-30 | 2010-06-30 | 2010-06-30 | 2010-06-30 | 2010-06-30 | 2010-06-30
32 | 76.07% | CP.01629 | Middle Ridge 110/33kV Transformers | 2010-06-30 | 2013-06-30 | 1096 | Connection |  | 0 | 0 | 0 | 0 | 0 | 0 | 4.7203 | 4.7203 | Reliability | [10 empty] | 2013-06-30 | 2013-06-30 | 2013-06-30 | 2013-06-30 | 2013-06-30 | 2013-06-30 | 2013-06-30 | 2013-06-30 | 2013-06-30 | 2013-06-30 | 2013-06-30 | 2013-06-30 | 2013-06-30 | 2013-06-30 | 2013-06-30 | 2013-06-30 | 2013-06-30 | 2013-06-30 | 2013-06-30 | 2013-06-30 | 2013-06-30 | 2013-06-30 | 2013-06-30 | 2013-06-30 | 2010-06-30 | 2010-06-30 | 2010-06-30 | 2010-06-30 | 2010-06-30 | 2010-06-30 | 2010-06-30 | 2010-06-30
32 | 76.07% | CP.01663 | Proserpine 132kV Feeder Bays for Canonvale | 2010-06-30 | 2012-06-30 | 731 | Connection |  | 0 | 0 | 0 | 0 | 0 | 1.2837 | 3.3879 | 4.6716 | Reliability | [10 empty] | 2012-06-30 | 2012-06-30 | 2012-06-30 | 2012-06-30 | 2012-06-30 | 2012-06-30 | 2012-06-30 | 2012-06-30 | 2012-06-30 | 2012-06-30 | 2012-06-30 | 2012-06-30 | 2012-06-30 | 2012-06-30 | 2012-06-30 | 2012-06-30 | 2012-06-30 | 2012-06-30 | 2012-06-30 | 2012-06-30 | 2012-06-30 | 2012-06-30 | 2012-06-30 | 2012-06-30 | 2010-06-30 | 2010-06-30 | 2010-06-30 | 2010-06-30 | 2010-06-30 | 2010-06-30 | 2010-06-30 | 2010-06-30
32 | 76.07% | CP.01514 | Kamerunga 132/22kV Transformer | 2010-08-31 | 2013-08-31 | 1096 | Connection |  | 0 | 0 | 0 | 0 | 0 | 0 | 0.99537 | 0.99537 | Reliability | [10 empty] | 2013-08-31 | 2013-08-31 | 2013-08-31 | 2013-08-31 | 2013-08-31 | 2013-08-31 | 2013-08-31 | 2013-08-31 | 2013-08-31 | 2013-08-31 | 2013-08-31 | 2013-08-31 | 2013-08-31 | 2013-08-31 | 2013-08-31 | 2013-08-31 | 2013-08-31 | 2013-08-31 | 2013-08-31 | 2013-08-31 | 2013-08-31 | 2013-08-31 | 2013-08-31 | 2013-08-31 | 2010-08-31 | 2010-08-31 | 2010-08-31 | 2010-08-31 | 2010-08-31 | 2010-08-31 | 2010-08-31 | 2010-08-31
8 | 7.277% | CP.01552 | Brisbane West Transition Point | 2010-10-31 | 2010-10-31 | 0 | Connection |  | 0 | 0 | 0 | 0.29995 | 2.9818 | 0.1425 | 0 | 3.4242 | Reliability |  |  | Scenarios & scenario probabilities 33: 2010-10-31; Scenarios & scenario probabilities 34: 2010-10-31; Scenarios & scenario probabilities 35: 2010-10-31; Scenarios & scenario probabilities 36: 2010-10-31; Scenarios & scenario probabilities 37: 2010-10-31; Scenarios & scenario probabilities 38: 2010-10-31; Scenarios & scenario probabilities 39: 2010-10-31; Scenarios & scenario probabilities 40: 2010-10-31
32 | 76.07% | CP.01719 | Molendinar 110/33kV Transformer | 2011-05-31 | 2014-05-31 | 1096 | Connection |  | 0 | 0 | 0 | 0 | 0 | 0 | 0.63157 | 0.63157 | Reliability | [10 empty] | 2014-05-31 | 2014-05-31 | 2014-05-31 | 2014-05-31 | 2014-05-31 | 2014-05-31 | 2014-05-31 | 2014-05-31 | 2014-05-31 | 2014-05-31 | 2014-05-31 | 2014-05-31 | 2014-05-31 | 2014-05-31 | 2014-05-31 | 2014-05-31 | 2014-05-31 | 2014-05-31 | 2014-05-31 | 2014-05-31 | 2014-05-31 | 2014-05-31 | 2014-05-31 | 2014-05-31 | 2011-05-31 | 2011-05-31 | 2011-05-31 | 2011-05-31 | 2011-05-31 | 2011-05-31 | 2011-05-31 | 2011-05-31
8 | 7.277% | CP.01632 | Garbutt 132/66kV 80MVA Transformer | 2011-07-31 | 2011-07-31 | 0 | Connection |  | 0 | 0 | 0 | 0 | 1.3579 | 3.7301 | 0.025284 | 5.1133 | Reliability |  |  | Scenarios & scenario probabilities 33: 2011-07-31; Scenarios & scenario probabilities 34: 2011-07-31; Scenarios & scenario probabilities 35: 2011-07-31; Scenarios & scenario probabilities 36: 2011-07-31; Scenarios & scenario probabilities 37: 2011-07-31; Scenarios & scenario probabilities 38: 2011-07-31; Scenarios & scenario probabilities 39: 2011-07-31; Scenarios & scenario probabilities 40: 2011-07-31
8 | 7.277% | CP.01769 | Murrarie 110kV Bay for Brisbane East 110/33kV Transformer | 2011-09-30 | 2011-09-30 | 0 | Connection |  | 0 | 0 | 0 | 0 | 0.35032 | 1.1984 | 0.094344 | 1.6431 | Reliability |  |  | Scenarios & scenario probabilities 33: 2011-09-30; Scenarios & scenario probabilities 34: 2011-09-30; Scenarios & scenario probabilities 35: 2011-09-30; Scenarios & scenario probabilities 36: 2011-09-30; Scenarios & scenario probabilities 37: 2011-09-30; Scenarios & scenario probabilities 38: 2011-09-30; Scenarios & scenario probabilities 39: 2011-09-30; Scenarios & scenario probabilities 40: 2011-09-30
8 | 7.277% | CP.01983 | CQ No. 1 Feeder Bays | 2011-10-31 | 2011-10-31 | 0 | Connection |  | 0 | 0 | 0 | 0 | 0.23067 | 2.3024 | 0.11048 | 2.6435 | Reliability |  |  | Scenarios & scenario probabilities 33: 2011-10-31; Scenarios & scenario probabilities 34: 2011-10-31; Scenarios & scenario probabilities 35: 2011-10-31; Scenarios & scenario probabilities 36: 2011-10-31; Scenarios & scenario probabilities 37: 2011-10-31; Scenarios & scenario probabilities 38: 2011-10-31; Scenarios & scenario probabilities 39: 2011-10-31; Scenarios & scenario probabilities 40: 2011-10-31
8 | 7.277% | CP.01975/B | Switch Bay Changes for DNSP Works for 5 years - High Load Growth | 2012-06-30 | 2012-06-30 | 0 | Connection |  | 0 | 0 | 0 | 0 | 0 | 1.562 | 4.0906 | 5.6525 | Reliability |  |  | Scenarios & scenario probabilities 33: 2012-06-30; Scenarios & scenario probabilities 34: 2012-06-30; Scenarios & scenario probabilities 35: 2012-06-30; Scenarios & scenario probabilities 36: 2012-06-30; Scenarios & scenario probabilities 37: 2012-06-30; Scenarios & scenario probabilities 38: 2012-06-30; Scenarios & scenario probabilities 39: 2012-06-30; Scenarios & scenario probabilities 40: 2012-06-30
8 | 23.93% | CP.01973/B | Switch Bay Changes for DNSP Works for 5 years - Light Load Growth | 2012-06-30 | 2012-06-30 | 0 | Connection |  | 0 | 0 | 0 | 0 | 0 | 0.59104 | 1.5509 | 2.142 | Reliability |  |  | Scenarios & scenario probabilities 1: 2012-06-30; Scenarios & scenario probabilities 2: 2012-06-30; Scenarios & scenario probabilities 3: 2012-06-30; Scenarios & scenario probabilities 4: 2012-06-30; Scenarios & scenario probabilities 5: 2012-06-30; Scenarios & scenario probabilities 6: 2012-06-30; Scenarios & scenario probabilities 7: 2012-06-30; Scenarios & scenario probabilities 8: 2012-06-30
24 | 68.8% | CP.01974/B | Switch Bay Changes for DNSP Works for 5 years - Medium Load Growth | 2012-06-30 | 2012-06-30 | 0 | Connection |  | 0 | 0 | 0 | 0 | 0 | 0.85694 | 2.2465 | 3.1034 | Reliability | [10 empty] | 2012-06-30 | 2012-06-30 | 2012-06-30 | 2012-06-30 | 2012-06-30 | 2012-06-30 | 2012-06-30 | 2012-06-30 | 2012-06-30 | 2012-06-30 | 2012-06-30 | 2012-06-30 | 2012-06-30 | 2012-06-30 | 2012-06-30 | 2012-06-30 | 2012-06-30 | 2012-06-30 | 2012-06-30 | 2012-06-30 | 2012-06-30 | 2012-06-30 | 2012-06-30 | 2012-06-30
8 | 7.277% | CP.01985 | CQ No. 1 132/33kV Transformer | 2012-07-31 | 2012-07-31 | 0 | Connection |  | 0 | 0 | 0 | 0 | 0 | 2.3149 | 6.3648 | 8.6797 | Reliability |  |  | Scenarios & scenario probabilities 33: 2012-07-31; Scenarios & scenario probabilities 34: 2012-07-31; Scenarios & scenario probabilities 35: 2012-07-31; Scenarios & scenario probabilities 36: 2012-07-31; Scenarios & scenario probabilities 37: 2012-07-31; Scenarios & scenario probabilities 38: 2012-07-31; Scenarios & scenario probabilities 39: 2012-07-31; Scenarios & scenario probabilities 40: 2012-07-31
8 | 7.277% | CP.01977 | SEQ No. 2 Feeder Bays for Energex | 2012-07-31 | 2012-07-31 | 0 | Connection |  | 0 | 0 | 0 | 0 | 0 | 0.35364 | 1.9961 | 2.3497 | Reliability |  |  | Scenarios & scenario probabilities 33: 2012-07-31; Scenarios & scenario probabilities 34: 2012-07-31; Scenarios & scenario probabilities 35: 2012-07-31; Scenarios & scenario probabilities 36: 2012-07-31; Scenarios & scenario probabilities 37: 2012-07-31; Scenarios & scenario probabilities 38: 2012-07-31; Scenarios & scenario probabilities 39: 2012-07-31; Scenarios & scenario probabilities 40: 2012-07-31
8 | 7.277% | CP.01747 | Runcorn 110/11kV Transformer | 2012-08-31 | 2012-08-31 | 0 | Connection |  | 0 | 0 | 0 | 0 | 0 | 1.1011 | 3.5573 | 4.6584 | Reliability |  |  | Scenarios & scenario probabilities 33: 2012-08-31; Scenarios & scenario probabilities 34: 2012-08-31; Scenarios & scenario probabilities 35: 2012-08-31; Scenarios & scenario probabilities 36: 2012-08-31; Scenarios & scenario probabilities 37: 2012-08-31; Scenarios & scenario probabilities 38: 2012-08-31; Scenarios & scenario probabilities 39: 2012-08-31; Scenarios & scenario probabilities 40: 2012-08-31
8 | 7.277% | CP.01976 | SEQ No. 1 Feeder Bays for Energex | 2012-09-30 | 2012-09-30 | 0 | Connection |  | 0 | 0 | 0 | 0 | 0 | 0.25329 | 2.0633 | 2.3166 | Reliability |  |  | Scenarios & scenario probabilities 33: 2012-09-30; Scenarios & scenario probabilities 34: 2012-09-30; Scenarios & scenario probabilities 35: 2012-09-30; Scenarios & scenario probabilities 36: 2012-09-30; Scenarios & scenario probabilities 37: 2012-09-30; Scenarios & scenario probabilities 38: 2012-09-30; Scenarios & scenario probabilities 39: 2012-09-30; Scenarios & scenario probabilities 40: 2012-09-30
8 | 7.277% | CP.01761 | Alligator Creek 132/66kV Transformer | 2012-10-31 | 2012-10-31 | 0 | Connection |  | 0 | 0 | 0 | 0 | 0 | 0.94597 | 3.6117 | 4.5576 | Reliability |  |  | Scenarios & scenario probabilities 33: 2012-10-31; Scenarios & scenario probabilities 34: 2012-10-31; Scenarios & scenario probabilities 35: 2012-10-31; Scenarios & scenario probabilities 36: 2012-10-31; Scenarios & scenario probabilities 37: 2012-10-31; Scenarios & scenario probabilities 38: 2012-10-31; Scenarios & scenario probabilities 39: 2012-10-31; Scenarios & scenario probabilities 40: 2012-10-31
8 | 7.277% | CP.01664 | Kamerunga 132kV Feeder Bays for Kewarra Beach | 2012-10-31 | 2012-10-31 | 0 | Connection |  | 0 | 0 | 0 | 0 | 0 | 0.45025 | 1.9563 | 2.4065 | Reliability |  |  | Scenarios & scenario probabilities 33: 2012-10-31; Scenarios & scenario probabilities 34: 2012-10-31; Scenarios & scenario probabilities 35: 2012-10-31; Scenarios & scenario probabilities 36: 2012-10-31; Scenarios & scenario probabilities 37: 2012-10-31; Scenarios & scenario probabilities 38: 2012-10-31; Scenarios & scenario probabilities 39: 2012-10-31; Scenarios & scenario probabilities 40: 2012-10-31
8 | 7.277% | CP.01765 | Middle Ridge 110kV Feeder Bay for Warwick | 2012-10-31 | 2012-10-31 | 0 | Connection |  | 0 | 0 | 0 | 0 | 0 | 0.028129 | 0.1239 | 0.15203 | Reliability |  |  | Scenarios & scenario probabilities 33: 2012-10-31; Scenarios & scenario probabilities 34: 2012-10-31; Scenarios & scenario probabilities 35: 2012-10-31; Scenarios & scenario probabilities 36: 2012-10-31; Scenarios & scenario probabilities 37: 2012-10-31; Scenarios & scenario probabilities 38: 2012-10-31; Scenarios & scenario probabilities 39: 2012-10-31; Scenarios & scenario probabilities 40: 2012-10-31
24 | 68.8% | CP.01592 | Brisbane South 110/11kV Transformer - Stage 2 | 2013-05-31 | 2013-05-31 | 0 | Connection |  | 0 | 0 | 0 | 0 | 0 | 0.25956 | 1.2945 | 1.554 | Reliability | [10 empty] | 2013-05-31 | 2013-05-31 | 2013-05-31 | 2013-05-31 | 2013-05-31 | 2013-05-31 | 2013-05-31 | 2013-05-31 | 2013-05-31 | 2013-05-31 | 2013-05-31 | 2013-05-31 | 2013-05-31 | 2013-05-31 | 2013-05-31 | 2013-05-31 | 2013-05-31 | 2013-05-31 | 2013-05-31 | 2013-05-31 | 2013-05-31 | 2013-05-31 | 2013-05-31 | 2013-05-31
8 | 7.277% | CP.01978 | SEQ No. 3 Feeder Bays for Energex | 2013-08-31 | 2013-08-31 | 0 | Connection |  | 0 | 0 | 0 | 0 | 0 | 0 | 0.28163 | 0.28163 | Reliability |  |  | Scenarios & scenario probabilities 33: 2013-08-31; Scenarios & scenario probabilities 34: 2013-08-31; Scenarios & scenario probabilities 35: 2013-08-31; Scenarios & scenario probabilities 36: 2013-08-31; Scenarios & scenario probabilities 37: 2013-08-31; Scenarios & scenario probabilities 38: 2013-08-31; Scenarios & scenario probabilities 39: 2013-08-31; Scenarios & scenario probabilities 40: 2013-08-31
8 | 7.277% | CP.01984 | CQ No. 2 Feeder Bays for Ergon | 2013-09-30 | 2013-09-30 | 0 | Connection |  | 0 | 0 | 0 | 0 | 0 | 0 | 0.28839 | 0.28839 | Reliability |  |  | Scenarios & scenario probabilities 33: 2013-09-30; Scenarios & scenario probabilities 34: 2013-09-30; Scenarios & scenario probabilities 35: 2013-09-30; Scenarios & scenario probabilities 36: 2013-09-30; Scenarios & scenario probabilities 37: 2013-09-30; Scenarios & scenario probabilities 38: 2013-09-30; Scenarios & scenario probabilities 39: 2013-09-30; Scenarios & scenario probabilities 40: 2013-09-30
32 | 76.07% | CP.01826/A | 275kV Easement Clearance into South West Brisbane (TE) | 2007-09-30 | 2009-09-30 | 731 | Easements |  | 0 | 0 | 0.69302 | 0.53335 | 0.091216 | 0 | 0 | 1.3176 | Construction | [10 empty] | 2009-09-30 | 2009-09-30 | 2009-09-30 | 2009-09-30 | 2009-09-30 | 2009-09-30 | 2009-09-30 | 2009-09-30 | 2009-09-30 | 2009-09-30 | 2009-09-30 | 2009-09-30 | 2009-09-30 | 2009-09-30 | 2009-09-30 | 2009-09-30 | 2009-09-30 | 2009-09-30 | 2009-09-30 | 2009-09-30 | 2009-09-30 | 2009-09-30 | 2009-09-30 | 2009-09-30 | 2007-09-30 | 2007-09-30 | 2007-09-30 | 2007-09-30 | 2007-09-30 | 2007-09-30 | 2007-09-30 | 2007-09-30
32 | 76.07% | CP.01690/A | Logan to South Coast Line Rebuild Easement Clearance (TE) | 2007-09-30 | 2010-09-30 | 1096 | Easements |  | 0 | 0 | 0 | 2.0503 | 1.5779 | 0.26987 | 0 | 3.8981 | Construction | [10 empty] | 2010-09-30 | 2010-09-30 | 2010-09-30 | 2010-09-30 | 2010-09-30 | 2010-09-30 | 2010-09-30 | 2010-09-30 | 2010-09-30 | 2010-09-30 | 2010-09-30 | 2010-09-30 | 2010-09-30 | 2010-09-30 | 2010-09-30 | 2010-09-30 | 2010-09-30 | 2010-09-30 | 2010-09-30 | 2010-09-30 | 2010-09-30 | 2010-09-30 | 2010-09-30 | 2010-09-30 | 2007-09-30 | 2007-09-30 | 2007-09-30 | 2007-09-30 | 2007-09-30 | 2007-09-30 | 2007-09-30 | 2007-09-30
40 | 100% | CP.01692/A | Bouldercombe to Pandoin 132kV Double Circuit Easement Acquisition (TE) | 2008-01-31 | 2011-01-31 | 1096 | Easements |  | 0.58382 | 1.3774 | 0.31478 | 0 | 0 | 0 | 0 | 0.31478 | Construction |  |  | 2011-01-31 | 2011-01-31 | 2011-01-31 | 2011-01-31 | 2011-01-31 | 2011-01-31 | 2011-01-31 | 2011-01-31 | 2008-01-31 | 2008-01-31 | 2008-01-31 | 2008-01-31 | 2008-01-31 | 2008-01-31 | 2008-01-31 | 2008-01-31 | 2008-01-31 | 2008-01-31 | 2008-01-31 | 2008-01-31 | 2008-01-31 | 2008-01-31 | 2008-01-31 | 2008-01-31 | 2008-01-31 | 2008-01-31 | 2008-01-31 | 2008-01-31 | 2008-01-31 | 2008-01-31 | 2008-01-31 | 2008-01-31 | 2008-01-31 | 2008-01-31 | 2008-01-31 | 2008-01-31 | 2008-01-31 | 2008-01-31 | 2008-01-31 | 2008-01-31
40 | 100% | CP.01670/A | South East Brisbane No. 1 110/11kV Substation Establishment Easement Acquisition (TE) | 2008-03-31 | 2012-03-31 | 1461 | Easements |  | 0.035592 | 0.19593 | 0.047975 | 0 | 0 | 0 | 0 | 0.047975 | Construction |  |  | 2012-03-31 | 2012-03-31 | 2012-03-31 | 2012-03-31 | 2012-03-31 | 2012-03-31 | 2012-03-31 | 2012-03-31 | 2008-03-31 | 2008-03-31 | 2008-03-31 | 2008-03-31 | 2008-03-31 | 2008-03-31 | 2008-03-31 | 2008-03-31 | 2008-03-31 | 2008-03-31 | 2008-03-31 | 2008-03-31 | 2008-03-31 | 2008-03-31 | 2008-03-31 | 2008-03-31 | 2008-03-31 | 2008-03-31 | 2008-03-31 | 2008-03-31 | 2008-03-31 | 2008-03-31 | 2008-03-31 | 2008-03-31 | 2008-03-31 | 2008-03-31 | 2008-03-31 | 2008-03-31 | 2008-03-31 | 2008-03-31 | 2008-03-31 | 2008-03-31
32 | 76.07% | CP.01271/A | Woolooga to North Coast 275kV Double Circuit Easement Clearance and Acquisition (TE component) | 2008-05-31 | 2009-05-31 | 365 | Easements |  | 0 | 0 | 2.19 | 0.5618 | 0 | 0 | 0 | 2.7518 | Construction | [10 empty] | 2009-05-31 | 2009-05-31 | 2009-05-31 | 2009-05-31 | 2009-05-31 | 2009-05-31 | 2009-05-31 | 2009-05-31 | 2009-05-31 | 2009-05-31 | 2009-05-31 | 2009-05-31 | 2009-05-31 | 2009-05-31 | 2009-05-31 | 2009-05-31 | 2009-05-31 | 2009-05-31 | 2009-05-31 | 2009-05-31 | 2009-05-31 | 2009-05-31 | 2009-05-31 | 2009-05-31 | 2008-05-31 | 2008-05-31 | 2008-05-31 | 2008-05-31 | 2008-05-31 | 2008-05-31 | 2008-05-31 | 2008-05-31
40 | 100% | CP.01849/A | Callide A Feeder Bay Land Acquisition (TE) | 2008-06-30 | 2013-06-30 | 1826 | Easements |  | 0 | 0 | 0.21213 | 0.079155 | 0 | 0 | 0 | 0.29129 | Construction |  |  | 2013-06-30 | 2013-06-30 | 2013-06-30 | 2013-06-30 | 2013-06-30 | 2013-06-30 | 2013-06-30 | 2013-06-30 | 2009-06-30 | 2009-06-30 | 2009-06-30 | 2009-06-30 | 2009-06-30 | 2009-06-30 | 2009-06-30 | 2009-06-30 | 2009-06-30 | 2009-06-30 | 2009-06-30 | 2009-06-30 | 2009-06-30 | 2009-06-30 | 2009-06-30 | 2009-06-30 | 2009-06-30 | 2009-06-30 | 2009-06-30 | 2009-06-30 | 2009-06-30 | 2009-06-30 | 2009-06-30 | 2009-06-30 | 2008-06-30 | 2008-06-30 | 2008-06-30 | 2008-06-30 | 2008-06-30 | 2008-06-30 | 2008-06-30 | 2008-06-30
32 | 76.07% | CP.01674/A | Brisbane South 110/11kV Substation Establishment Easement Aquisition (TE) | 2008-07-31 | 2008-07-31 | 0 | Easements |  | 0 | 0.34129 | 0.15794 | 0.018007 | 0 | 0 | 0 | 0.17595 | Construction | [10 empty] | 2008-07-31 | 2008-07-31 | 2008-07-31 | 2008-07-31 | 2008-07-31 | 2008-07-31 | 2008-07-31 | 2008-07-31 | 2008-07-31 | 2008-07-31 | 2008-07-31 | 2008-07-31 | 2008-07-31 | 2008-07-31 | 2008-07-31 | 2008-07-31 | 2008-07-31 | 2008-07-31 | 2008-07-31 | 2008-07-31 | 2008-07-31 | 2008-07-31 | 2008-07-31 | 2008-07-31 | 2008-07-31 | 2008-07-31 | 2008-07-31 | 2008-07-31 | 2008-07-31 | 2008-07-31 | 2008-07-31 | 2008-07-31
32 | 76.07% | CP.01708/A | Kamerunga 132/22kV Transformer Additional Land Acquisition (TE) | 2008-07-31 | 2010-07-31 | 730 | Easements |  | 0 | 0 | 0 | 0.14203 | 0.065583 | 0.007478 | 0 | 0.21509 | Construction | [10 empty] | 2010-07-31 | 2010-07-31 | 2010-07-31 | 2010-07-31 | 2010-07-31 | 2010-07-31 | 2010-07-31 | 2010-07-31 | 2010-07-31 | 2010-07-31 | 2010-07-31 | 2010-07-31 | 2010-07-31 | 2010-07-31 | 2010-07-31 | 2010-07-31 | 2010-07-31 | 2010-07-31 | 2010-07-31 | 2010-07-31 | 2010-07-31 | 2010-07-31 | 2010-07-31 | 2010-07-31 | 2008-07-31 | 2008-07-31 | 2008-07-31 | 2008-07-31 | 2008-07-31 | 2008-07-31 | 2008-07-31 | 2008-07-31
40 | 100% | CP.01682/A | Clare 132kV Feeder Bay for Millchester Additonal Land Acquisition (TE) | 2008-09-30 | 2012-09-30 | 1461 | Easements |  | 0 | 0 | 0 | 0.16021 | 0.1233 | 0.021087 | 0 | 0.30459 | Construction |  |  | 2012-09-30 | 2012-09-30 | 2012-09-30 | 2012-09-30 | 2012-09-30 | 2012-09-30 | 2012-09-30 | 2012-09-30 | 2010-09-30 | 2010-09-30 | 2010-09-30 | 2010-09-30 | 2010-09-30 | 2010-09-30 | 2010-09-30 | 2010-09-30 | 2010-09-30 | 2010-09-30 | 2010-09-30 | 2010-09-30 | 2010-09-30 | 2010-09-30 | 2010-09-30 | 2010-09-30 | 2010-09-30 | 2010-09-30 | 2010-09-30 | 2010-09-30 | 2010-09-30 | 2010-09-30 | 2010-09-30 | 2010-09-30 | 2008-09-30 | 2008-09-30 | 2008-09-30 | 2008-09-30 | 2008-09-30 | 2008-09-30 | 2008-09-30 | 2008-09-30
32 | 76.07% | CP.01690/B | Logan to South Coast Line Rebuild Easement Clearance (Compensation) | 2008-09-30 | 2011-09-30 | 1095 | Easements |  | 0 | 0 | 0 | 0 | 0.45865 | 7.5346 | 0 | 7.9932 | Construction | [10 empty] | 2011-09-30 | 2011-09-30 | 2011-09-30 | 2011-09-30 | 2011-09-30 | 2011-09-30 | 2011-09-30 | 2011-09-30 | 2011-09-30 | 2011-09-30 | 2011-09-30 | 2011-09-30 | 2011-09-30 | 2011-09-30 | 2011-09-30 | 2011-09-30 | 2011-09-30 | 2011-09-30 | 2011-09-30 | 2011-09-30 | 2011-09-30 | 2011-09-30 | 2011-09-30 | 2011-09-30 | 2008-09-30 | 2008-09-30 | 2008-09-30 | 2008-09-30 | 2008-09-30 | 2008-09-30 | 2008-09-30 | 2008-09-30
40 | 100% | CP.01692/B | Bouldercombe to Pandoin 132kV Double Circuit Easement Acquisition (Compensation) | 2008-10-31 | 2012-10-31 | 1461 | Easements |  | 0 | 0 | 0.021552 | 0.51726 | 0.02633 | 0 | 0 | 0.56514 | Construction |  |  | 2012-10-31 | 2012-10-31 | 2012-10-31 | 2012-10-31 | 2012-10-31 | 2012-10-31 | 2012-10-31 | 2012-10-31 | 2009-10-31 | 2009-10-31 | 2009-10-31 | 2009-10-31 | 2009-10-31 | 2009-10-31 | 2009-10-31 | 2009-10-31 | 2009-10-31 | 2009-10-31 | 2009-10-31 | 2009-10-31 | 2009-10-31 | 2009-10-31 | 2009-10-31 | 2009-10-31 | 2009-10-31 | 2009-10-31 | 2009-10-31 | 2009-10-31 | 2009-10-31 | 2009-10-31 | 2009-10-31 | 2009-10-31 | 2008-10-31 | 2008-10-31 | 2008-10-31 | 2008-10-31 | 2008-10-31 | 2008-10-31 | 2008-10-31 | 2008-10-31
40 | 100% | CP.01674/B | Brisbane South 110/11kV Substation Establishment Easement Acquisition (Compensation) | 2008-10-31 | 2011-10-31 | 1095 | Easements |  | 0 | 0 | 0.024462 | 0.59092 | 0.030274 | 0 | 0 | 0.64566 | Construction |  |  | 2011-10-31 | 2011-10-31 | 2011-10-31 | 2011-10-31 | 2011-10-31 | 2011-10-31 | 2011-10-31 | 2011-10-31 | 2009-10-31 | 2009-10-31 | 2009-10-31 | 2009-10-31 | 2009-10-31 | 2009-10-31 | 2009-10-31 | 2009-10-31 | 2009-10-31 | 2009-10-31 | 2009-10-31 | 2009-10-31 | 2009-10-31 | 2009-10-31 | 2009-10-31 | 2009-10-31 | 2009-10-31 | 2009-10-31 | 2009-10-31 | 2009-10-31 | 2009-10-31 | 2009-10-31 | 2009-10-31 | 2009-10-31 | 2008-10-31 | 2008-10-31 | 2008-10-31 | 2008-10-31 | 2008-10-31 | 2008-10-31 | 2008-10-31 | 2008-10-31
32 | 76.07% | CP.01961/A | Sarina 132/66kV Transformer Land Acquisition (TE) | 2008-10-31 | 2009-10-31 | 365 | Easements |  | 0 | 0 | 0.25607 | 0.25338 | 0.048148 | 0 | 0 | 0.55759 | Construction | [10 empty] | 2009-10-31 | 2009-10-31 | 2009-10-31 | 2009-10-31 | 2009-10-31 | 2009-10-31 | 2009-10-31 | 2009-10-31 | 2009-10-31 | 2009-10-31 | 2009-10-31 | 2009-10-31 | 2009-10-31 | 2009-10-31 | 2009-10-31 | 2009-10-31 | 2009-10-31 | 2009-10-31 | 2009-10-31 | 2009-10-31 | 2009-10-31 | 2009-10-31 | 2009-10-31 | 2009-10-31 | 2008-10-31 | 2008-10-31 | 2008-10-31 | 2008-10-31 | 2008-10-31 | 2008-10-31 | 2008-10-31 | 2008-10-31
40 | 100% | CP.01823/A | South Coast to Tweed Transmission Reinforcement Stage 1 and 2 Easement Acquisition (TE) | 2009-01-31 | 2014-01-31 | 1826 | Easements |  | 0 | 1.6583 | 3.837 | 0.87495 | 0 | 0 | 0 | 4.7119 | Construction |  |  | 2014-01-31 | 2014-01-31 | 2014-01-31 | 2014-01-31 | 2014-01-31 | 2014-01-31 | 2014-01-31 | 2014-01-31 | 2009-01-31 | 2009-01-31 | 2009-01-31 | 2009-01-31 | 2009-01-31 | 2009-01-31 | 2009-01-31 | 2009-01-31 | 2009-01-31 | 2009-01-31 | 2009-01-31 | 2009-01-31 | 2009-01-31 | 2009-01-31 | 2009-01-31 | 2009-01-31 | 2009-01-31 | 2009-01-31 | 2009-01-31 | 2009-01-31 | 2009-01-31 | 2009-01-31 | 2009-01-31 | 2009-01-31 | 2009-01-31 | 2009-01-31 | 2009-01-31 | 2009-01-31 | 2009-01-31 | 2009-01-31 | 2009-01-31 | 2009-01-31
40 | 100% | CP.01671/A | South East Brisbane No. 2 110/11kV Substation Establishment Easement Aquisition (TE) | 2009-01-31 | 2014-01-31 | 1826 | Easements |  | 0 | 0.13652 | 0.31588 | 0.07203 | 0 | 0 | 0 | 0.38791 | Construction |  |  | 2014-01-31 | 2014-01-31 | 2014-01-31 | 2014-01-31 | 2014-01-31 | 2014-01-31 | 2014-01-31 | 2014-01-31 | 2009-01-31 | 2009-01-31 | 2009-01-31 | 2009-01-31 | 2009-01-31 | 2009-01-31 | 2009-01-31 | 2009-01-31 | 2009-01-31 | 2009-01-31 | 2009-01-31 | 2009-01-31 | 2009-01-31 | 2009-01-31 | 2009-01-31 | 2009-01-31 | 2009-01-31 | 2009-01-31 | 2009-01-31 | 2009-01-31 | 2009-01-31 | 2009-01-31 | 2009-01-31 | 2009-01-31 | 2009-01-31 | 2009-01-31 | 2009-01-31 | 2009-01-31 | 2009-01-31 | 2009-01-31 | 2009-01-31 | 2009-01-31
40 | 100% | CP.01670/B | South East Brisbane No. 1 110/11kV Substation Establishment Easement Aquisition (Compensation) | 2009-03-31 | 2013-03-31 | 1461 | Easements |  | 0 | 0 | 0.086244 | 0.033099 | 0 | 0 | 0 | 0.11934 | Construction |  |  | 2013-03-31 | 2013-03-31 | 2013-03-31 | 2013-03-31 | 2013-03-31 | 2013-03-31 | 2013-03-31 | 2013-03-31 | 2009-03-31 | 2009-03-31 | 2009-03-31 | 2009-03-31 | 2009-03-31 | 2009-03-31 | 2009-03-31 | 2009-03-31 | 2009-03-31 | 2009-03-31 | 2009-03-31 | 2009-03-31 | 2009-03-31 | 2009-03-31 | 2009-03-31 | 2009-03-31 | 2009-03-31 | 2009-03-31 | 2009-03-31 | 2009-03-31 | 2009-03-31 | 2009-03-31 | 2009-03-31 | 2009-03-31 | 2009-03-31 | 2009-03-31 | 2009-03-31 | 2009-03-31 | 2009-03-31 | 2009-03-31 | 2009-03-31 | 2009-03-31
32 | 76.07% | CP.01961/B | Sarina 132/66kV Transformer Land Acquisition (Compensation) | 2009-03-31 | 2010-03-31 | 365 | Easements |  | 0 | 0 | 0 | 0.24458 | 0.093258 | 0 | 0 | 0.33783 | Construction | [10 empty] | 2010-03-31 | 2010-03-31 | 2010-03-31 | 2010-03-31 | 2010-03-31 | 2010-03-31 | 2010-03-31 | 2010-03-31 | 2010-03-31 | 2010-03-31 | 2010-03-31 | 2010-03-31 | 2010-03-31 | 2010-03-31 | 2010-03-31 | 2010-03-31 | 2010-03-31 | 2010-03-31 | 2010-03-31 | 2010-03-31 | 2010-03-31 | 2010-03-31 | 2010-03-31 | 2010-03-31 | 2009-03-31 | 2009-03-31 | 2009-03-31 | 2009-03-31 | 2009-03-31 | 2009-03-31 | 2009-03-31 | 2009-03-31
32 | 76.07% | CP.01271/B | Woolooga to North Coast 275kV Double Circuit Easement Clearance and Acquisition (Compensation) | 2009-05-31 | 2010-05-31 | 365 | Easements |  | 0 | 0 | 0 | 2.0358 | 1.1778 | 0 | 0 | 3.2135 | Construction | [10 empty] | 2010-05-31 | 2010-05-31 | 2010-05-31 | 2010-05-31 | 2010-05-31 | 2010-05-31 | 2010-05-31 | 2010-05-31 | 2010-05-31 | 2010-05-31 | 2010-05-31 | 2010-05-31 | 2010-05-31 | 2010-05-31 | 2010-05-31 | 2010-05-31 | 2010-05-31 | 2010-05-31 | 2010-05-31 | 2010-05-31 | 2010-05-31 | 2010-05-31 | 2010-05-31 | 2010-05-31 | 2009-05-31 | 2009-05-31 | 2009-05-31 | 2009-05-31 | 2009-05-31 | 2009-05-31 | 2009-05-31 | 2009-05-31
40 | 100% | CP.01849/B | Callide A Feeder Bay Land Acquisition (Compensation) | 2009-06-30 | 2014-06-30 | 1826 | Easements |  | 0 | 0 | 0 | 0.000875 | 0.000612 | 0 | 0 | 0.001487 | Construction |  |  | 2014-06-30 | 2014-06-30 | 2014-06-30 | 2014-06-30 | 2014-06-30 | 2014-06-30 | 2014-06-30 | 2014-06-30 | 2010-06-30 | 2010-06-30 | 2010-06-30 | 2010-06-30 | 2010-06-30 | 2010-06-30 | 2010-06-30 | 2010-06-30 | 2010-06-30 | 2010-06-30 | 2010-06-30 | 2010-06-30 | 2010-06-30 | 2010-06-30 | 2010-06-30 | 2010-06-30 | 2010-06-30 | 2010-06-30 | 2010-06-30 | 2010-06-30 | 2010-06-30 | 2010-06-30 | 2010-06-30 | 2010-06-30 | 2009-06-30 | 2009-06-30 | 2009-06-30 | 2009-06-30 | 2009-06-30 | 2009-06-30 | 2009-06-30 | 2009-06-30
32 | 76.07% | CP.01825/A | Easement Clearance for 275kV Double Circuit into South West Brisbane (TE) | 2009-06-30 | 2013-06-30 | 1461 | Easements |  | 0 | 0 | 0 | 0 | 0 | 0 | 1.0289 | 1.0289 | Construction | [10 empty] | 2013-06-30 | 2013-06-30 | 2013-06-30 | 2013-06-30 | 2013-06-30 | 2013-06-30 | 2013-06-30 | 2013-06-30 | 2013-06-30 | 2013-06-30 | 2013-06-30 | 2013-06-30 | 2013-06-30 | 2013-06-30 | 2013-06-30 | 2013-06-30 | 2013-06-30 | 2013-06-30 | 2013-06-30 | 2013-06-30 | 2013-06-30 | 2013-06-30 | 2013-06-30 | 2013-06-30 | 2009-06-30 | 2009-06-30 | 2009-06-30 | 2009-06-30 | 2009-06-30 | 2009-06-30 | 2009-06-30 | 2009-06-30
8 | 7.277% | CP.01987/B | Easement Acquisition for SEQ No. 1 110kV Bus Establishment (Compensation) | 2009-07-31 | 2009-07-31 | 0 | Easements |  | 0 | 0 | 0.11855 | 0.17278 | 0 | 0 | 0 | 0.29132 | Construction |  |  | Scenarios & scenario probabilities 33: 2009-07-31; Scenarios & scenario probabilities 34: 2009-07-31; Scenarios & scenario probabilities 35: 2009-07-31; Scenarios & scenario probabilities 36: 2009-07-31; Scenarios & scenario probabilities 37: 2009-07-31; Scenarios & scenario probabilities 38: 2009-07-31; Scenarios & scenario probabilities 39: 2009-07-31; Scenarios & scenario probabilities 40: 2009-07-31
8 | 7.277% | CP.01987/A | Easement Acquisition for SEQ No. 1 110kV Bus Establishment (TE) | 2009-07-31 | 2009-07-31 | 0 | Easements |  | 0 | 0 | 0.52684 | 0.24328 | 0.027737 | 0 | 0 | 0.79785 | Construction |  |  | Scenarios & scenario probabilities 33: 2009-07-31; Scenarios & scenario probabilities 34: 2009-07-31; Scenarios & scenario probabilities 35: 2009-07-31; Scenarios & scenario probabilities 36: 2009-07-31; Scenarios & scenario probabilities 37: 2009-07-31; Scenarios & scenario probabilities 38: 2009-07-31; Scenarios & scenario probabilities 39: 2009-07-31; Scenarios & scenario probabilities 40: 2009-07-31
32 | 76.07% | CP.01824/A | South West Brisbane No. 1 110/33kV Substation Establishment Easement Acquisition (TE) | 2009-07-31 | 2013-07-31 | 1461 | Easements |  | 0 | 0 | 0 | 0 | 0 | 0 | 0.46696 | 0.46696 | Construction | [10 empty] | 2013-07-31 | 2013-07-31 | 2013-07-31 | 2013-07-31 | 2013-07-31 | 2013-07-31 | 2013-07-31 | 2013-07-31 | 2013-07-31 | 2013-07-31 | 2013-07-31 | 2013-07-31 | 2013-07-31 | 2013-07-31 | 2013-07-31 | 2013-07-31 | 2013-07-31 | 2013-07-31 | 2013-07-31 | 2013-07-31 | 2013-07-31 | 2013-07-31 | 2013-07-31 | 2013-07-31 | 2009-07-31 | 2009-07-31 | 2009-07-31 | 2009-07-31 | 2009-07-31 | 2009-07-31 | 2009-07-31 | 2009-07-31
32 | 76.07% | CP.01708/B | Kamerunga 132/22kV Transformer Additional Land Acquisition (Compensation) | 2009-07-31 | 2011-07-31 | 730 | Easements |  | 0 | 0 | 0 | 0 | 0.080531 | 0.11661 | 0 | 0.19714 | Construction | [10 empty] | 2011-07-31 | 2011-07-31 | 2011-07-31 | 2011-07-31 | 2011-07-31 | 2011-07-31 | 2011-07-31 | 2011-07-31 | 2011-07-31 | 2011-07-31 | 2011-07-31 | 2011-07-31 | 2011-07-31 | 2011-07-31 | 2011-07-31 | 2011-07-31 | 2011-07-31 | 2011-07-31 | 2011-07-31 | 2011-07-31 | 2011-07-31 | 2011-07-31 | 2011-07-31 | 2011-07-31 | 2009-07-31 | 2009-07-31 | 2009-07-31 | 2009-07-31 | 2009-07-31 | 2009-07-31 | 2009-07-31 | 2009-07-31
32 | 76.07% | CP.01677/A | North West Brisbane No. 1 110/33kV Substation Establishment Site Aquisition (TE) | 2009-08-31 | 2011-08-31 | 730 | Easements |  | 0 | 0 | 0 | 0 | 0.21363 | 0.12788 | 0.018746 | 0.36026 | Construction | [10 empty] | 2011-08-31 | 2011-08-31 | 2011-08-31 | 2011-08-31 | 2011-08-31 | 2011-08-31 | 2011-08-31 | 2011-08-31 | 2011-08-31 | 2011-08-31 | 2011-08-31 | 2011-08-31 | 2011-08-31 | 2011-08-31 | 2011-08-31 | 2011-08-31 | 2011-08-31 | 2011-08-31 | 2011-08-31 | 2011-08-31 | 2011-08-31 | 2011-08-31 | 2011-08-31 | 2011-08-31 | 2009-08-31 | 2009-08-31 | 2009-08-31 | 2009-08-31 | 2009-08-31 | 2009-08-31 | 2009-08-31 | 2009-08-31
32 | 76.07% | CP.01823/B | South Coast to Tweed Transmission Reinforcement Stage 1 and 2 Easement Acquisition (Compensation) | 2009-08-31 | 2010-08-31 | 365 | Easements |  | 0 | 0 | 0 | 0.52487 | 1.7429 | 0 | 0 | 2.2677 | Construction | [10 empty] | 2010-08-31 | 2010-08-31 | 2010-08-31 | 2010-08-31 | 2010-08-31 | 2010-08-31 | 2010-08-31 | 2010-08-31 | 2010-08-31 | 2010-08-31 | 2010-08-31 | 2010-08-31 | 2010-08-31 | 2010-08-31 | 2010-08-31 | 2010-08-31 | 2010-08-31 | 2010-08-31 | 2010-08-31 | 2010-08-31 | 2010-08-31 | 2010-08-31 | 2010-08-31 | 2010-08-31 | 2009-08-31 | 2009-08-31 | 2009-08-31 | 2009-08-31 | 2009-08-31 | 2009-08-31 | 2009-08-31 | 2009-08-31
40 | 100% | CP.01682/B | Clare 132kV Feeder Bay for Millchester Additonal Land Acquisition (Compensation) | 2009-09-30 | 2013-09-30 | 1461 | Easements |  | 0 | 0 | 0 | 0 | 0.000382 | 0.006279 | 0 | 0.006661 | Construction |  |  | 2013-09-30 | 2013-09-30 | 2013-09-30 | 2013-09-30 | 2013-09-30 | 2013-09-30 | 2013-09-30 | 2013-09-30 | 2011-09-30 | 2011-09-30 | 2011-09-30 | 2011-09-30 | 2011-09-30 | 2011-09-30 | 2011-09-30 | 2011-09-30 | 2011-09-30 | 2011-09-30 | 2011-09-30 | 2011-09-30 | 2011-09-30 | 2011-09-30 | 2011-09-30 | 2011-09-30 | 2011-09-30 | 2011-09-30 | 2011-09-30 | 2011-09-30 | 2011-09-30 | 2011-09-30 | 2011-09-30 | 2011-09-30 | 2009-09-30 | 2009-09-30 | 2009-09-30 | 2009-09-30 | 2009-09-30 | 2009-09-30 | 2009-09-30 | 2009-09-30
32 | 76.07% | CP.01852/B | South East Brisbane No. 3 110kV Transition Site Acquisition (Compensation) | 2009-10-31 | 2012-10-31 | 1096 | Easements |  | 0 | 0 | 0 | 0 | 0 | 0.000668 | 0.016032 | 0.0167 | Construction | [10 empty] | 2012-10-31 | 2012-10-31 | 2012-10-31 | 2012-10-31 | 2012-10-31 | 2012-10-31 | 2012-10-31 | 2012-10-31 | 2012-10-31 | 2012-10-31 | 2012-10-31 | 2012-10-31 | 2012-10-31 | 2012-10-31 | 2012-10-31 | 2012-10-31 | 2012-10-31 | 2012-10-31 | 2012-10-31 | 2012-10-31 | 2012-10-31 | 2012-10-31 | 2012-10-31 | 2012-10-31 | 2009-10-31 | 2009-10-31 | 2009-10-31 | 2009-10-31 | 2009-10-31 | 2009-10-31 | 2009-10-31 | 2009-10-31
32 | 76.07% | CP.01852/A | South East Brisbane No. 3 110kV Transition Site Acquisition (TE) | 2009-10-31 | 2011-10-31 | 730 | Easements |  | 0 | 0 | 0 | 0 | 0.25036 | 0.24773 | 0.047074 | 0.54516 | Construction | [10 empty] | 2011-10-31 | 2011-10-31 | 2011-10-31 | 2011-10-31 | 2011-10-31 | 2011-10-31 | 2011-10-31 | 2011-10-31 | 2011-10-31 | 2011-10-31 | 2011-10-31 | 2011-10-31 | 2011-10-31 | 2011-10-31 | 2011-10-31 | 2011-10-31 | 2011-10-31 | 2011-10-31 | 2011-10-31 | 2011-10-31 | 2011-10-31 | 2011-10-31 | 2011-10-31 | 2011-10-31 | 2009-10-31 | 2009-10-31 | 2009-10-31 | 2009-10-31 | 2009-10-31 | 2009-10-31 | 2009-10-31 | 2009-10-31
32 | 76.07% | CP.01671/B | South East Brisbane No. 2 110/11kV Substation Establishment Easement Acquisition (Compensation) | 2010-01-31 | 2010-01-31 | 0 | Easements |  | 0 | 0 | 0 | 0.3674 | 0.083837 | 0 | 0 | 0.45123 | Construction | [10 empty] | 2010-01-31 | 2010-01-31 | 2010-01-31 | 2010-01-31 | 2010-01-31 | 2010-01-31 | 2010-01-31 | 2010-01-31 | 2010-01-31 | 2010-01-31 | 2010-01-31 | 2010-01-31 | 2010-01-31 | 2010-01-31 | 2010-01-31 | 2010-01-31 | 2010-01-31 | 2010-01-31 | 2010-01-31 | 2010-01-31 | 2010-01-31 | 2010-01-31 | 2010-01-31 | 2010-01-31 | 2010-01-31 | 2010-01-31 | 2010-01-31 | 2010-01-31 | 2010-01-31 | 2010-01-31 | 2010-01-31 | 2010-01-31
32 | 76.07% | CP.01677/B | North West Brisbane No. 1 110/33kV Substation Establishment Site Aquisition (Compensation) | 2010-01-31 | 2012-01-31 | 730 | Easements |  | 0 | 0 | 0 | 0 | 0 | 0.8348 | 0.18927 | 1.0241 | Construction | [10 empty] | 2012-01-31 | 2012-01-31 | 2012-01-31 | 2012-01-31 | 2012-01-31 | 2012-01-31 | 2012-01-31 | 2012-01-31 | 2012-01-31 | 2012-01-31 | 2012-01-31 | 2012-01-31 | 2012-01-31 | 2012-01-31 | 2012-01-31 | 2012-01-31 | 2012-01-31 | 2012-01-31 | 2012-01-31 | 2012-01-31 | 2012-01-31 | 2012-01-31 | 2012-01-31 | 2012-01-31 | 2010-01-31 | 2010-01-31 | 2010-01-31 | 2010-01-31 | 2010-01-31 | 2010-01-31 | 2010-01-31 | 2010-01-31
8 | 7.277% | CP.01824/B | South West Brisbane No. 1 110/33kV Substation Establishment Easement Acquisition (Compensation) | 2010-07-31 | 2010-07-31 | 0 | Easements |  | 0 | 0 | 0 | 0.78196 | 1.1397 | 0 | 0 | 1.9216 | Construction |  |  | Scenarios & scenario probabilities 33: 2010-07-31; Scenarios & scenario probabilities 34: 2010-07-31; Scenarios & scenario probabilities 35: 2010-07-31; Scenarios & scenario probabilities 36: 2010-07-31; Scenarios & scenario probabilities 37: 2010-07-31; Scenarios & scenario probabilities 38: 2010-07-31; Scenarios & scenario probabilities 39: 2010-07-31; Scenarios & scenario probabilities 40: 2010-07-31
8 | 7.277% | CP.01990/A | Easement Acquisition for CQ No. 1 132/66kV Substation Establishment (TE) | 2010-07-31 | 2010-07-31 | 0 | Easements |  | 0 | 0 | 0 | 0.31269 | 0.14439 | 0.016463 | 0 | 0.47355 | Construction |  |  | Scenarios & scenario probabilities 33: 2010-07-31; Scenarios & scenario probabilities 34: 2010-07-31; Scenarios & scenario probabilities 35: 2010-07-31; Scenarios & scenario probabilities 36: 2010-07-31; Scenarios & scenario probabilities 37: 2010-07-31; Scenarios & scenario probabilities 38: 2010-07-31; Scenarios & scenario probabilities 39: 2010-07-31; Scenarios & scenario probabilities 40: 2010-07-31
8 | 7.277% | CP.01988/A | Easement Acquisition SEQ No. 1 110/33kV Substation Establishment (TE) | 2010-07-31 | 2010-07-31 | 0 | Easements |  | 0 | 0 | 0 | 0.61422 | 0.28363 | 0.032338 | 0 | 0.93019 | Construction |  |  | Scenarios & scenario probabilities 33: 2010-07-31; Scenarios & scenario probabilities 34: 2010-07-31; Scenarios & scenario probabilities 35: 2010-07-31; Scenarios & scenario probabilities 36: 2010-07-31; Scenarios & scenario probabilities 37: 2010-07-31; Scenarios & scenario probabilities 38: 2010-07-31; Scenarios & scenario probabilities 39: 2010-07-31; Scenarios & scenario probabilities 40: 2010-07-31
32 | 76.07% | CP.01827/A | Black River 132/66kV Substation Establishment Land and Easement Acquisition (TE) | 2010-07-31 | 2012-07-31 | 731 | Easements |  | 0 | 0 | 0 | 0 | 0 | 0.67034 | 0.30954 | 0.97988 | Construction | [10 empty] | 2012-07-31 | 2012-07-31 | 2012-07-31 | 2012-07-31 | 2012-07-31 | 2012-07-31 | 2012-07-31 | 2012-07-31 | 2012-07-31 | 2012-07-31 | 2012-07-31 | 2012-07-31 | 2012-07-31 | 2012-07-31 | 2012-07-31 | 2012-07-31 | 2012-07-31 | 2012-07-31 | 2012-07-31 | 2012-07-31 | 2012-07-31 | 2012-07-31 | 2012-07-31 | 2012-07-31 | 2010-07-31 | 2010-07-31 | 2010-07-31 | 2010-07-31 | 2010-07-31 | 2010-07-31 | 2010-07-31 | 2010-07-31
8 | 7.277% | CP.01853/A | Cairns Region 132/22kV Substation Site Acquisition (TE) | 2010-10-31 | 2010-10-31 | 0 | Easements |  | 0 | 0 | 0 | 0.12884 | 0.12749 | 0.024227 | 0 | 0.28056 | Construction |  |  | Scenarios & scenario probabilities 33: 2010-10-31; Scenarios & scenario probabilities 34: 2010-10-31; Scenarios & scenario probabilities 35: 2010-10-31; Scenarios & scenario probabilities 36: 2010-10-31; Scenarios & scenario probabilities 37: 2010-10-31; Scenarios & scenario probabilities 38: 2010-10-31; Scenarios & scenario probabilities 39: 2010-10-31; Scenarios & scenario probabilities 40: 2010-10-31
8 | 7.277% | CP.01990/B | Easement Acquisition for CQ No. 1 132/66kV Substation Establishment (Compensation) | 2011-07-31 | 2011-07-31 | 0 | Easements |  | 0 | 0 | 0 | 0 | 0.38473 | 0.5571 | 0 | 0.94183 | Construction |  |  | Scenarios & scenario probabilities 33: 2011-07-31; Scenarios & scenario probabilities 34: 2011-07-31; Scenarios & scenario probabilities 35: 2011-07-31; Scenarios & scenario probabilities 36: 2011-07-31; Scenarios & scenario probabilities 37: 2011-07-31; Scenarios & scenario probabilities 38: 2011-07-31; Scenarios & scenario probabilities 39: 2011-07-31; Scenarios & scenario probabilities 40: 2011-07-31
8 | 7.277% | CP.01988/B | Easement Acquisition for SEQ No. 1 110/33kV Substation Establishment (Compensation) | 2011-07-31 | 2011-07-31 | 0 | Easements |  | 0 | 0 | 0 | 0 | 0.40713 | 0.59337 | 0 | 1.0005 | Construction |  |  | Scenarios & scenario probabilities 33: 2011-07-31; Scenarios & scenario probabilities 34: 2011-07-31; Scenarios & scenario probabilities 35: 2011-07-31; Scenarios & scenario probabilities 36: 2011-07-31; Scenarios & scenario probabilities 37: 2011-07-31; Scenarios & scenario probabilities 38: 2011-07-31; Scenarios & scenario probabilities 39: 2011-07-31; Scenarios & scenario probabilities 40: 2011-07-31
8 | 7.277% | CP.01989/A | Easement Acquisition for SEQ No. 2 110/33kV Substation Establishment (TE) | 2011-07-31 | 2011-07-31 | 0 | Easements |  | 0 | 0 | 0 | 0 | 0.63028 | 0.29104 | 0.033183 | 0.9545 | Construction |  |  | Scenarios & scenario probabilities 33: 2011-07-31; Scenarios & scenario probabilities 34: 2011-07-31; Scenarios & scenario probabilities 35: 2011-07-31; Scenarios & scenario probabilities 36: 2011-07-31; Scenarios & scenario probabilities 37: 2011-07-31; Scenarios & scenario probabilities 38: 2011-07-31; Scenarios & scenario probabilities 39: 2011-07-31; Scenarios & scenario probabilities 40: 2011-07-31
32 | 76.07% | CP.01675/A | SEQ No. 2 110/11kV Substation Establishment Easement Acquisition (TE) | 2011-07-31 | 2012-07-31 | 366 | Easements |  | 0 | 0 | 0 | 0 | 0 | 0.37922 | 0.17511 | 0.55433 | Strategic | [10 empty] | 2012-07-31 | 2012-07-31 | 2012-07-31 | 2012-07-31 | 2012-07-31 | 2012-07-31 | 2012-07-31 | 2012-07-31 | 2012-07-31 | 2012-07-31 | 2012-07-31 | 2012-07-31 | 2012-07-31 | 2012-07-31 | 2012-07-31 | 2012-07-31 | 2012-07-31 | 2012-07-31 | 2012-07-31 | 2012-07-31 | 2012-07-31 | 2012-07-31 | 2012-07-31 | 2012-07-31 | 2011-07-31 | 2011-07-31 | 2011-07-31 | 2011-07-31 | 2011-07-31 | 2011-07-31 | 2011-07-31 | 2011-07-31
32 | 76.07% | CP.01827/B | Black River 132/66kV Substation Establishment Land and Easement Acquisition (Compensation) | 2011-07-31 | 2013-07-31 | 731 | Easements |  | 0 | 0 | 0 | 0 | 0 | 0 | 0.13767 | 0.13767 | Construction | [10 empty] | 2013-07-31 | 2013-07-31 | 2013-07-31 | 2013-07-31 | 2013-07-31 | 2013-07-31 | 2013-07-31 | 2013-07-31 | 2013-07-31 | 2013-07-31 | 2013-07-31 | 2013-07-31 | 2013-07-31 | 2013-07-31 | 2013-07-31 | 2013-07-31 | 2013-07-31 | 2013-07-31 | 2013-07-31 | 2013-07-31 | 2013-07-31 | 2013-07-31 | 2013-07-31 | 2013-07-31 | 2011-07-31 | 2011-07-31 | 2011-07-31 | 2011-07-31 | 2011-07-31 | 2011-07-31 | 2011-07-31 | 2011-07-31
40 | 100% | CP.01862/A | South Coast Substation Land Acquisition (TE) | 2011-07-31 | 2012-07-31 | 366 | Easements |  | 0 | 0 | 0 | 0 | 0 | 0.42888 | 0.19804 | 0.62692 | Construction/Strategic |  |  | 2012-07-31 | 2012-07-31 | 2012-07-31 | 2012-07-31 | 2012-07-31 | 2012-07-31 | 2012-07-31 | 2012-07-31 | 2012-07-31 | 2012-07-31 | 2012-07-31 | 2012-07-31 | 2012-07-31 | 2012-07-31 | 2012-07-31 | 2012-07-31 | 2012-07-31 | 2012-07-31 | 2012-07-31 | 2012-07-31 | 2012-07-31 | 2012-07-31 | 2012-07-31 | 2012-07-31 | 2012-07-31 | 2012-07-31 | 2012-07-31 | 2012-07-31 | 2012-07-31 | 2012-07-31 | 2012-07-31 | 2012-07-31 | 2011-07-31 | 2011-07-31 | 2011-07-31 | 2011-07-31 | 2011-07-31 | 2011-07-31 | 2011-07-31 | 2011-07-31
8 | 7.277% | CP.01853/B | Cairns Region 132/22kV Subsatation Land Acquisition (Compensation) | 2011-10-31 | 2011-10-31 | 0 | Easements |  | 0 | 0 | 0 | 0 | 0.02548 | 0.61155 | 0.031129 | 0.66816 | Construction |  |  | Scenarios & scenario probabilities 33: 2011-10-31; Scenarios & scenario probabilities 34: 2011-10-31; Scenarios & scenario probabilities 35: 2011-10-31; Scenarios & scenario probabilities 36: 2011-10-31; Scenarios & scenario probabilities 37: 2011-10-31; Scenarios & scenario probabilities 38: 2011-10-31; Scenarios & scenario probabilities 39: 2011-10-31; Scenarios & scenario probabilities 40: 2011-10-31
8 | 23.93% | CP.01845/A | North West Brisbane Easement Clearance and Acquisition (TE) | 2011-10-31 | 2011-10-31 | 0 | Easements |  | 0 | 0 | 0 | 0 | 0.78234 | 0.77411 | 0.1471 | 1.7036 | Construction |  |  | Scenarios & scenario probabilities 1: 2011-10-31; Scenarios & scenario probabilities 2: 2011-10-31; Scenarios & scenario probabilities 3: 2011-10-31; Scenarios & scenario probabilities 4: 2011-10-31; Scenarios & scenario probabilities 5: 2011-10-31; Scenarios & scenario probabilities 6: 2011-10-31; Scenarios & scenario probabilities 7: 2011-10-31; Scenarios & scenario probabilities 8: 2011-10-31
32 | 76.07% | CP.01856/A | North West Brisbane (Cable Replacement Only) Easement Clearance and Acquisition (TE) | 2011-10-31 | 2011-10-31 | 0 | Easements |  | 0 | 0 | 0 | 0 | 0.33947 | 0.3359 | 0.06383 | 0.7392 | Construction | [10 empty] | 2011-10-31 | 2011-10-31 | 2011-10-31 | 2011-10-31 | 2011-10-31 | 2011-10-31 | 2011-10-31 | 2011-10-31 | 2011-10-31 | 2011-10-31 | 2011-10-31 | 2011-10-31 | 2011-10-31 | 2011-10-31 | 2011-10-31 | 2011-10-31 | 2011-10-31 | 2011-10-31 | 2011-10-31 | 2011-10-31 | 2011-10-31 | 2011-10-31 | 2011-10-31 | 2011-10-31 | 2011-10-31 | 2011-10-31 | 2011-10-31 | 2011-10-31 | 2011-10-31 | 2011-10-31 | 2011-10-31 | 2011-10-31
8 | 7.277% | CP.01989/B | Easement Acquisition for SEQ No. 2 110/33kV Substation Establishment (Compensation) | 2012-07-31 | 2012-07-31 | 0 | Easements |  | 0 | 0 | 0 | 0 | 0 | 0.42968 | 0.62624 | 1.0559 | Construction |  |  | Scenarios & scenario probabilities 33: 2012-07-31; Scenarios & scenario probabilities 34: 2012-07-31; Scenarios & scenario probabilities 35: 2012-07-31; Scenarios & scenario probabilities 36: 2012-07-31; Scenarios & scenario probabilities 37: 2012-07-31; Scenarios & scenario probabilities 38: 2012-07-31; Scenarios & scenario probabilities 39: 2012-07-31; Scenarios & scenario probabilities 40: 2012-07-31
32 | 76.07% | CP.01675/B | SEQ No. 2 110/11kV Substation Establishment Easement Aquisition (Compensation) | 2012-07-31 | 2013-07-31 | 365 | Easements |  | 0 | 0 | 0 | 0 | 0 | 0 | 0.36769 | 0.36769 | Strategic | [10 empty] | 2013-07-31 | 2013-07-31 | 2013-07-31 | 2013-07-31 | 2013-07-31 | 2013-07-31 | 2013-07-31 | 2013-07-31 | 2013-07-31 | 2013-07-31 | 2013-07-31 | 2013-07-31 | 2013-07-31 | 2013-07-31 | 2013-07-31 | 2013-07-31 | 2013-07-31 | 2013-07-31 | 2013-07-31 | 2013-07-31 | 2013-07-31 | 2013-07-31 | 2013-07-31 | 2013-07-31 | 2012-07-31 | 2012-07-31 | 2012-07-31 | 2012-07-31 | 2012-07-31 | 2012-07-31 | 2012-07-31 | 2012-07-31
40 | 100% | CP.01862/B | South Coast Substation Land Acquisition (Compensation) | 2012-07-31 | 2013-07-31 | 365 | Easements |  | 0 | 0 | 0 | 0 | 0 | 0 | 0.66189 | 0.66189 | Construction/Strategic |  |  | 2013-07-31 | 2013-07-31 | 2013-07-31 | 2013-07-31 | 2013-07-31 | 2013-07-31 | 2013-07-31 | 2013-07-31 | 2013-07-31 | 2013-07-31 | 2013-07-31 | 2013-07-31 | 2013-07-31 | 2013-07-31 | 2013-07-31 | 2013-07-31 | 2013-07-31 | 2013-07-31 | 2013-07-31 | 2013-07-31 | 2013-07-31 | 2013-07-31 | 2013-07-31 | 2013-07-31 | 2013-07-31 | 2013-07-31 | 2013-07-31 | 2013-07-31 | 2013-07-31 | 2013-07-31 | 2013-07-31 | 2013-07-31 | 2012-07-31 | 2012-07-31 | 2012-07-31 | 2012-07-31 | 2012-07-31 | 2012-07-31 | 2012-07-31 | 2012-07-31
8 | 7.277% | CP.01864/A | Halys to North Coast 500kV Double Circuit Easement Acquisition (TE) | 2012-08-31 | 2012-08-31 | 0 | Easements |  | 0 | 0 | 0 | 0 | 0 | 1.709 | 1.023 | 2.7319 | Construction/Strategic |  |  | Scenarios & scenario probabilities 33: 2012-08-31; Scenarios & scenario probabilities 34: 2012-08-31; Scenarios & scenario probabilities 35: 2012-08-31; Scenarios & scenario probabilities 36: 2012-08-31; Scenarios & scenario probabilities 37: 2012-08-31; Scenarios & scenario probabilities 38: 2012-08-31; Scenarios & scenario probabilities 39: 2012-08-31; Scenarios & scenario probabilities 40: 2012-08-31
8 | 7.277% | CP.01689/A | Upper Kedron 275/110kV Substation Establishment Easement Clearance (TE) | 2012-10-31 | 2012-10-31 | 0 | Easements |  | 0 | 0 | 0 | 0 | 0 | 0.15607 | 0.15443 | 0.31049 | Construction |  |  | Scenarios & scenario probabilities 33: 2012-10-31; Scenarios & scenario probabilities 34: 2012-10-31; Scenarios & scenario probabilities 35: 2012-10-31; Scenarios & scenario probabilities 36: 2012-10-31; Scenarios & scenario probabilities 37: 2012-10-31; Scenarios & scenario probabilities 38: 2012-10-31; Scenarios & scenario probabilities 39: 2012-10-31; Scenarios & scenario probabilities 40: 2012-10-31
8 | 23.93% | CP.01845/B | North West Brisbane Easement Clearance and Acquisition (Compensation) | 2012-10-31 | 2012-10-31 | 0 | Easements |  | 0 | 0 | 0 | 0 | 0 | 0.010687 | 0.25651 | 0.26719 | Construction |  |  | Scenarios & scenario probabilities 1: 2012-10-31; Scenarios & scenario probabilities 2: 2012-10-31; Scenarios & scenario probabilities 3: 2012-10-31; Scenarios & scenario probabilities 4: 2012-10-31; Scenarios & scenario probabilities 5: 2012-10-31; Scenarios & scenario probabilities 6: 2012-10-31; Scenarios & scenario probabilities 7: 2012-10-31; Scenarios & scenario probabilities 8: 2012-10-31
32 | 76.07% | CP.01856/B | North West Brisbane (Cable Replacement Only) Easement Clearance and Acquisition (Compensation) | 2012-10-31 | 2012-10-31 | 0 | Easements |  | 0 | 0 | 0 | 0 | 0 | 0.010687 | 0.25651 | 0.26719 | Construction | [10 empty] | 2012-10-31 | 2012-10-31 | 2012-10-31 | 2012-10-31 | 2012-10-31 | 2012-10-31 | 2012-10-31 | 2012-10-31 | 2012-10-31 | 2012-10-31 | 2012-10-31 | 2012-10-31 | 2012-10-31 | 2012-10-31 | 2012-10-31 | 2012-10-31 | 2012-10-31 | 2012-10-31 | 2012-10-31 | 2012-10-31 | 2012-10-31 | 2012-10-31 | 2012-10-31 | 2012-10-31 | 2012-10-31 | 2012-10-31 | 2012-10-31 | 2012-10-31 | 2012-10-31 | 2012-10-31 | 2012-10-31 | 2012-10-31
8 | 7.277% | CP.01864/B | Halys to North Coast 500kV Double Circuit Easement Acquisition (Compensation) | 2013-08-31 | 2013-08-31 | 0 | Easements |  | 0 | 0 | 0 | 0 | 0 | 0 | 0.96153 | 0.96153 | Construction/Strategic |  |  | Scenarios & scenario probabilities 33: 2013-08-31; Scenarios & scenario probabilities 34: 2013-08-31; Scenarios & scenario probabilities 35: 2013-08-31; Scenarios & scenario probabilities 36: 2013-08-31; Scenarios & scenario probabilities 37: 2013-08-31; Scenarios & scenario probabilities 38: 2013-08-31; Scenarios & scenario probabilities 39: 2013-08-31; Scenarios & scenario probabilities 40: 2013-08-31
8 | 7.277% | CP.01676/A | South West Brisbane No. 2 110/11kV Substation Establishment Easement Aquisition (TE) | 2013-09-30 | 2013-09-30 | 0 | Easements |  | 0 | 0 | 0 | 0 | 0 | 0 | 0.31131 | 0.31131 | Strategic |  |  | Scenarios & scenario probabilities 33: 2013-09-30; Scenarios & scenario probabilities 34: 2013-09-30; Scenarios & scenario probabilities 35: 2013-09-30; Scenarios & scenario probabilities 36: 2013-09-30; Scenarios & scenario probabilities 37: 2013-09-30; Scenarios & scenario probabilities 38: 2013-09-30; Scenarios & scenario probabilities 39: 2013-09-30; Scenarios & scenario probabilities 40: 2013-09-30
8 | 7.277% | CP.01689/B | Upper Kedron 275/110kV Substation Establishment Easement Clearance (Compensation) | 2013-10-31 | 2013-10-31 | 0 | Easements |  | 0 | 0 | 0 | 0 | 0 | 0 | 0.002802 | 0.002802 | Construction |  |  | Scenarios & scenario probabilities 33: 2013-10-31; Scenarios & scenario probabilities 34: 2013-10-31; Scenarios & scenario probabilities 35: 2013-10-31; Scenarios & scenario probabilities 36: 2013-10-31; Scenarios & scenario probabilities 37: 2013-10-31; Scenarios & scenario probabilities 38: 2013-10-31; Scenarios & scenario probabilities 39: 2013-10-31; Scenarios & scenario probabilities 40: 2013-10-31
40 | 100% | CP.01840 | Gladstone Series Reactors for Gladstone North and BSL | 2010-09-30 | 2012-09-30 | 731 | Security/Compliance |  | 0 | 0 | 0 | 0.78712 | 2.6724 | 0.20878 | 0 | 3.6683 | Fault Level |  |  | 2012-09-30 | 2012-09-30 | 2012-09-30 | 2012-09-30 | 2012-09-30 | 2012-09-30 | 2012-09-30 | 2012-09-30 | 2010-09-30 | 2010-09-30 | 2010-09-30 | 2010-09-30 | 2010-09-30 | 2010-09-30 | 2010-09-30 | 2010-09-30 | 2010-09-30 | 2010-09-30 | 2010-09-30 | 2010-09-30 | 2010-09-30 | 2010-09-30 | 2010-09-30 | 2010-09-30 | 2010-09-30 | 2010-09-30 | 2010-09-30 | 2010-09-30 | 2010-09-30 | 2010-09-30 | 2010-09-30 | 2010-09-30 | 2010-09-30 | 2010-09-30 | 2010-09-30 | 2010-09-30 | 2010-09-30 | 2010-09-30 | 2010-09-30 | 2010-09-30
40 | 100% | CP.00736 | Greenbank 350MVAr SVC | 2007-09-30 | 2010-09-30 | 1096 | Augmentation |  | 0 | 0 | 0 | 10.7213 | 10.6348 | 0 | 0 | 21.3561 | Reliability |  |  | 2010-09-30 | 2010-09-30 | 2010-09-30 | 2010-09-30 | 2010-09-30 | 2010-09-30 | 2010-09-30 | 2010-09-30 | 2009-09-30 | 2010-09-30 | 2009-09-30 | 2010-09-30 | 2009-09-30 | 2010-09-30 | 2009-09-30 | 2010-09-30 | 2010-09-30 | 2010-09-30 | 2010-09-30 | 2010-09-30 | 2009-09-30 | 2010-09-30 | 2010-09-30 | 2010-09-30 | 2010-09-30 | 2010-09-30 | 2010-09-30 | 2010-09-30 | 2010-09-30 | 2010-09-30 | 2010-09-30 | 2010-09-30 | 2007-09-30 | 2007-09-30 | 2007-09-30 | 2007-09-30 | 2007-09-30 | 2007-09-30 | 2007-09-30 | 2007-09-30
40 | 100% | CP.01881 | Moreton West 120MVAr No. 2 | 2007-10-31 | 2009-10-31 | 731 | Augmentation |  | 0.24554 | 1.6684 | 0.59044 | 0 | 0 | 0 | 0 | 0.59044 | Reliability |  |  | 2008-10-31 | 2008-10-31 | 2008-10-31 | 2008-10-31 | 2008-10-31 | 2008-10-31 | 2008-10-31 | 2008-10-31 | 2007-10-31 | 2007-10-31 | 2007-10-31 | 2007-10-31 | 2007-10-31 | 2007-10-31 | 2007-10-31 | 2007-10-31 | 2007-10-31 | 2007-10-31 | 2007-10-31 | 2007-10-31 | 2007-10-31 | 2007-10-31 | 2007-10-31 | 2007-10-31 | 2007-10-31 | 2007-10-31 | 2007-10-31 | 2007-10-31 | 2007-10-31 | 2007-10-31 | 2007-10-31 | 2007-10-31 | 2007-10-31 | 2008-10-31 | 2007-10-31 | 2008-10-31 | 2007-10-31 | 2008-10-31 | 2009-10-31 | 2008-10-31
37 | 96.11% | CP.01886 | Moreton South 120MVAr No. 1 | 2007-10-31 | 2013-10-31 | 2192 | Augmentation |  | 0.24554 | 1.6684 | 0.59044 | 0 | 0 | 0 | 0 | 0.59044 | Reliability |  |  | 2012-10-31 |  | 2013-10-31 | 2011-10-31 | 2013-10-31 |  |  | 2011-10-31 | 2007-10-31 | 2007-10-31 | 2007-10-31 | 2007-10-31 | 2007-10-31 | 2007-10-31 | 2007-10-31 | 2007-10-31 | 2007-10-31 | 2007-10-31 | 2007-10-31 | 2007-10-31 | 2007-10-31 | 2007-10-31 | 2007-10-31 | 2007-10-31 | 2007-10-31 | 2007-10-31 | 2007-10-31 | 2007-10-31 | 2007-10-31 | 2007-10-31 | 2007-10-31 | 2007-10-31 | 2007-10-31 | 2007-10-31 | 2007-10-31 | 2007-10-31 | 2007-10-31 | 2007-10-31 | 2007-10-31 | 2007-10-31
34 | 77.67% | CP.01887 | Moreton South 120MVAr No. 2 | 2007-10-31 | 2013-10-31 | 2192 | Augmentation |  | 0 | 0 | 0.25142 | 1.6975 | 0.6005 | 0 | 0 | 2.5494 | Reliability | [5 empty] | 2013-10-31 |  |  |  | 2013-10-31 | 2011-10-31 | 2009-10-31 | 2011-10-31 | 2009-10-31 | 2010-10-31 | 2009-10-31 | 2011-10-31 | 2009-10-31 | 2011-10-31 | 2009-10-31 | 2009-10-31 | 2009-10-31 | 2011-10-31 | 2009-10-31 | 2009-10-31 | 2009-10-31 | 2009-10-31 | 2009-10-31 | 2009-10-31 | 2009-10-31 | 2009-10-31 | 2009-10-31 | 2009-10-31 | 2009-10-31 | 2007-10-31 | 2007-10-31 | 2007-10-31 | 2007-10-31 | 2007-10-31 | 2007-10-31 | 2007-10-31 | 2007-10-31
27 | 66.1% | CP.01888 | Moreton South 120MVAr No. 3 | 2007-10-31 | 2012-10-31 | 1827 | Augmentation |  | 0 | 0 | 0 | 0 | 0.2557 | 1.7269 | 0.61109 | 2.5937 | Reliability | [10 empty] | 2011-10-31 | 2010-10-31 | 2012-10-31 |  | 2011-10-31 | 2012-10-31 |  |  | 2011-10-31 | 2010-10-31 | 2012-10-31 | 2012-10-31 | 2011-10-31 | 2010-10-31 | 2012-10-31 |  | 2011-10-31 | 2010-10-31 | 2011-10-31 | 2011-10-31 | 2011-10-31 | 2010-10-31 |  | 2011-10-31 | 2008-10-31 | 2007-10-31 | 2008-10-31 | 2007-10-31 | 2008-10-31 | 2007-10-31 | 2007-10-31 | 2007-10-31
21 | 39.98% | CP.01889 | Moreton South 120MVAr No. 4 | 2007-10-31 | 2012-10-31 | 1827 | Augmentation |  | 0 | 0 | 0 | 0.25354 | 1.712 | 0.60573 | 0 | 2.5713 | Reliability |  |  | Scenarios & scenario probabilities 9: 2012-10-31; Scenarios & scenario probabilities 10: 2010-10-31; Scenarios & scenario probabilities 13: 2011-10-31; Scenarios & scenario probabilities 18: 2010-10-31; Scenarios & scenario probabilities 21: 2011-10-31; Scenarios & scenario probabilities 22: 2010-10-31; Scenarios & scenario probabilities 25: 2011-10-31; Scenarios & scenario probabilities 26: 2010-10-31; Scenarios & scenario probabilities 27: 2012-10-31; Scenarios & scenario probabilities 28: 2012-10-31; Scenarios & scenario probabilities 29: 2011-10-31; Scenarios & scenario probabilities 30: 2010-10-31; Scenarios & scenario probabilities 32: 2011-10-31; Scenarios & scenario probabilities 33: 2009-10-31; Scenarios & scenario probabilities 34: 2007-10-31; Scenarios & scenario probabilities 35: 2009-10-31; Scenarios & scenario probabilities 36: 2007-10-31; Scenarios & scenario probabilities 37: 2009-10-31; Scenarios & scenario probabilities 38: 2007-10-31; Scenarios & scenario probabilities 39: 2008-10-31; Scenarios & scenario probabilities 40: 2008-10-31
20 | 58.33% | CP.01908 | Moreton South East 120MVAr No. 1 | 2007-10-31 | 2013-10-31 | 2192 | Augmentation |  | 0 | 0 | 0.25142 | 1.6975 | 0.6005 | 0 | 0 | 2.5494 | Reliability |  |  | Scenarios & scenario probabilities 8: 2010-10-31; Scenarios & scenario probabilities 9: 2011-10-31; Scenarios & scenario probabilities 10: 2009-10-31; Scenarios & scenario probabilities 11: 2011-10-31; Scenarios & scenario probabilities 12: 2009-10-31; Scenarios & scenario probabilities 14: 2009-10-31; Scenarios & scenario probabilities 15: 2011-10-31; Scenarios & scenario probabilities 16: 2009-10-31; Scenarios & scenario probabilities 17: 2011-10-31; Scenarios & scenario probabilities 18: 2009-10-31; Scenarios & scenario probabilities 19: 2012-10-31; Scenarios & scenario probabilities 20: 2009-10-31; Scenarios & scenario probabilities 22: 2009-10-31; Scenarios & scenario probabilities 24: 2009-10-31; Scenarios & scenario probabilities 25: 2013-10-31; Scenarios & scenario probabilities 27: 2012-10-31; Scenarios & scenario probabilities 33: 2007-10-31; Scenarios & scenario probabilities 35: 2007-10-31; Scenarios & scenario probabilities 37: 2007-10-31; Scenarios & scenario probabilities 39: 2007-10-31
15 | 51.84% | CP.01915 | Gladstone Zone 120MVAr No. 1 | 2007-10-31 | 2013-10-31 | 2192 | Augmentation |  | 0 | 0.24919 | 1.6833 | 0.5954 | 0 | 0 | 0 | 2.2787 | Reliability |  |  | Scenarios & scenario probabilities 1: 2011-10-31; Scenarios & scenario probabilities 2: 2008-10-31; Scenarios & scenario probabilities 4: 2008-10-31; Scenarios & scenario probabilities 5: 2011-10-31; Scenarios & scenario probabilities 6: 2008-10-31; Scenarios & scenario probabilities 8: 2008-10-31; Scenarios & scenario probabilities 9: 2007-10-31; Scenarios & scenario probabilities 13: 2007-10-31; Scenarios & scenario probabilities 17: 2007-10-31; Scenarios & scenario probabilities 21: 2007-10-31; Scenarios & scenario probabilities 25: 2007-10-31; Scenarios & scenario probabilities 27: 2011-10-31; Scenarios & scenario probabilities 29: 2007-10-31; Scenarios & scenario probabilities 31: 2011-10-31; Scenarios & scenario probabilities 38: 2013-10-31
19 | 20.24% | CP.01540 | Middle Ridge 330/275kV Transformer Augmentation | 2008-07-31 | 2012-07-31 | 1461 | Augmentation |  | 0 | 0 | 0 | 1.7718 | 4.8243 | 0.03241 | 0 | 6.6285 | Reliability |  |  | Scenarios & scenario probabilities 10: 2010-07-31; Scenarios & scenario probabilities 12: 2011-07-31; Scenarios & scenario probabilities 14: 2012-07-31; Scenarios & scenario probabilities 16: 2011-07-31; Scenarios & scenario probabilities 18: 2010-07-31; Scenarios & scenario probabilities 20: 2012-07-31; Scenarios & scenario probabilities 21: 2011-07-31; Scenarios & scenario probabilities 22: 2010-07-31; Scenarios & scenario probabilities 24: 2011-07-31; Scenarios & scenario probabilities 29: 2010-07-31; Scenarios & scenario probabilities 32: 2012-07-31; Scenarios & scenario probabilities 33: 2008-07-31; Scenarios & scenario probabilities 34: 2008-07-31; Scenarios & scenario probabilities 35: 2008-07-31; Scenarios & scenario probabilities 36: 2008-07-31; Scenarios & scenario probabilities 37: 2008-07-31; Scenarios & scenario probabilities 38: 2008-07-31; Scenarios & scenario probabilities 39: 2008-07-31; Scenarios & scenario probabilities 40: 2008-07-31
19 | 20.24% | CP.01841 | Millmerran Series Line Reactors | 2008-07-31 | 2012-07-31 | 1461 | Augmentation |  | 0 | 0 | 0 | 0.89482 | 2.6695 | 0.038677 | 0 | 3.603 | Reliability |  |  | Scenarios & scenario probabilities 10: 2010-07-31; Scenarios & scenario probabilities 12: 2011-07-31; Scenarios & scenario probabilities 14: 2012-07-31; Scenarios & scenario probabilities 16: 2011-07-31; Scenarios & scenario probabilities 18: 2010-07-31; Scenarios & scenario probabilities 20: 2012-07-31; Scenarios & scenario probabilities 21: 2011-07-31; Scenarios & scenario probabilities 22: 2010-07-31; Scenarios & scenario probabilities 24: 2011-07-31; Scenarios & scenario probabilities 29: 2010-07-31; Scenarios & scenario probabilities 32: 2012-07-31; Scenarios & scenario probabilities 33: 2008-07-31; Scenarios & scenario probabilities 34: 2008-07-31; Scenarios & scenario probabilities 35: 2008-07-31; Scenarios & scenario probabilities 36: 2008-07-31; Scenarios & scenario probabilities 37: 2008-07-31; Scenarios & scenario probabilities 38: 2008-07-31; Scenarios & scenario probabilities 39: 2008-07-31; Scenarios & scenario probabilities 40: 2008-07-31
19 | 43.17% | CP.01836 | Gin Gin 250MVAr SVC | 2008-08-31 | 2011-08-31 | 1095 | Augmentation |  | 0 | 14.4878 | 8.7261 | 0 | 0 | 0 | 0 | 8.7261 | Reliability |  |  | Scenarios & scenario probabilities 10: 2008-08-31; Scenarios & scenario probabilities 11: 2008-08-31; Scenarios & scenario probabilities 12: 2008-08-31; Scenarios & scenario probabilities 14: 2008-08-31; Scenarios & scenario probabilities 15: 2008-08-31; Scenarios & scenario probabilities 16: 2008-08-31; Scenarios & scenario probabilities 17: 2011-08-31; Scenarios & scenario probabilities 18: 2008-08-31; Scenarios & scenario probabilities 19: 2008-08-31; Scenarios & scenario probabilities 20: 2008-08-31; Scenarios & scenario probabilities 22: 2008-08-31; Scenarios & scenario probabilities 23: 2008-08-31; Scenarios & scenario probabilities 24: 2008-08-31; Scenarios & scenario probabilities 26: 2008-08-31; Scenarios & scenario probabilities 27: 2008-08-31; Scenarios & scenario probabilities 28: 2008-08-31; Scenarios & scenario probabilities 30: 2008-08-31; Scenarios & scenario probabilities 31: 2008-08-31; Scenarios & scenario probabilities 32: 2008-08-31
39 | 99.7% | CP.01882 | Moreton West 120MVAr No. 3 | 2008-10-31 | 2011-10-31 | 1095 | Augmentation |  | 0 | 0 | 0.25142 | 1.6975 | 0.6005 | 0 | 0 | 2.5494 | Reliability |  |  | 2009-10-31 | 2009-10-31 | 2009-10-31 | 2009-10-31 | 2009-10-31 | 2009-10-31 | 2009-10-31 | 2009-10-31 | 2010-10-31 | 2009-10-31 | 2011-10-31 | 2009-10-31 | 2011-10-31 | 2009-10-31 | 2011-10-31 | 2009-10-31 | 2009-10-31 | 2009-10-31 | 2009-10-31 | 2009-10-31 | 2010-10-31 | 2009-10-31 | 2009-10-31 | 2009-10-31 | 2010-10-31 | 2009-10-31 | 2009-10-31 | 2009-10-31 | 2010-10-31 | 2009-10-31 | 2009-10-31 | 2009-10-31 | 2008-10-31 | 2010-10-31 | 2008-10-31 |  | 2008-10-31 | 2010-10-31 | 2011-10-31 | 2010-10-31
17 | 34.7% | CP.01896 | Moreton South 120MVAr No. 5 | 2008-10-31 | 2013-10-31 | 1826 | Augmentation |  | 0 | 0 | 0 | 0 | 0.2557 | 1.7269 | 0.61109 | 2.5937 | Reliability |  |  | Scenarios & scenario probabilities 9: 2013-10-31; Scenarios & scenario probabilities 13: 2011-10-31; Scenarios & scenario probabilities 18: 2013-10-31; Scenarios & scenario probabilities 21: 2013-10-31; Scenarios & scenario probabilities 25: 2011-10-31; Scenarios & scenario probabilities 26: 2013-10-31; Scenarios & scenario probabilities 29: 2011-10-31; Scenarios & scenario probabilities 30: 2012-10-31; Scenarios & scenario probabilities 32: 2012-10-31; Scenarios & scenario probabilities 33: 2009-10-31; Scenarios & scenario probabilities 34: 2008-10-31; Scenarios & scenario probabilities 35: 2009-10-31; Scenarios & scenario probabilities 36: 2008-10-31; Scenarios & scenario probabilities 37: 2009-10-31; Scenarios & scenario probabilities 38: 2008-10-31; Scenarios & scenario probabilities 39: 2009-10-31; Scenarios & scenario probabilities 40: 2008-10-31
3 | 13.56% | CP.01909 | Moreton South East 120MVAr No. 2 | 2008-10-31 | 2013-10-31 | 1826 | Augmentation |  | 0 | 0 | 0 | 0 | 0 | 0.25793 | 1.7422 | 2.0001 | Reliability |  |  | Scenarios & scenario probabilities 9: 2013-10-31; Scenarios & scenario probabilities 10: 2012-10-31; Scenarios & scenario probabilities 39: 2008-10-31
8 | 10.97% | CP.01280 | Gladstone Area Transmission Reinforcement | 2009-07-01 | 2009-07-01 | 0 | Augmentation |  | 0 | 0 | 19.2911 | 108.6277 | 0.65773 | 0 | 0 | 128.5765 | Reliability |  |  | Scenarios & scenario probabilities 25: 2009-07-01; Scenarios & scenario probabilities 26: 2009-07-01; Scenarios & scenario probabilities 27: 2009-07-01; Scenarios & scenario probabilities 28: 2009-07-01; Scenarios & scenario probabilities 29: 2009-07-01; Scenarios & scenario probabilities 30: 2009-07-01; Scenarios & scenario probabilities 31: 2009-07-01; Scenarios & scenario probabilities 32: 2009-07-01
8 | 10.97% | CP.01971 | Larcom Creek Remote 132kV bus Establishment | 2009-07-01 | 2009-07-01 | 0 | Augmentation |  | 0 | 0 | 2.3189 | 6.9698 | 0.10175 | 0 | 0 | 9.3905 | Reliability |  |  | Scenarios & scenario probabilities 25: 2009-07-01; Scenarios & scenario probabilities 26: 2009-07-01; Scenarios & scenario probabilities 27: 2009-07-01; Scenarios & scenario probabilities 28: 2009-07-01; Scenarios & scenario probabilities 29: 2009-07-01; Scenarios & scenario probabilities 30: 2009-07-01; Scenarios & scenario probabilities 31: 2009-07-01; Scenarios & scenario probabilities 32: 2009-07-01
32 | 89.03% | CP.01958 | Larcom Creek 275/132kV Substation Establishment | 2009-07-31 | 2009-07-31 | 0 | Augmentation |  | 0 | 0 | 11.797 | 35.4731 | 0.51808 | 0 | 0 | 47.7882 | Reliability |  |  | 2009-07-31 | 2009-07-31 | 2009-07-31 | 2009-07-31 | 2009-07-31 | 2009-07-31 | 2009-07-31 | 2009-07-31 | 2009-07-31 | 2009-07-31 | 2009-07-31 | 2009-07-31 | 2009-07-31 | 2009-07-31 | 2009-07-31 | 2009-07-31 | 2009-07-31 | 2009-07-31 | 2009-07-31 | 2009-07-31 | 2009-07-31 | 2009-07-31 | 2009-07-31 | 2009-07-31 | [8 empty] | 2009-07-31 | 2009-07-31 | 2009-07-31 | 2009-07-31 | 2009-07-31 | 2009-07-31 | 2009-07-31 | 2009-07-31
32 | 76.07% | CP.01792 | Connection Modifications of Circuits from South Pine | 2009-07-31 | 2013-07-31 | 1461 | Augmentation |  | 0 | 0 | 0 | 0 | 0 | 0 | 0.19929 | 0.19929 | Reliability | [10 empty] | 2013-07-31 | 2013-07-31 | 2013-07-31 | 2013-07-31 | 2013-07-31 | 2013-07-31 | 2013-07-31 | 2013-07-31 | 2013-07-31 | 2013-07-31 | 2013-07-31 | 2013-07-31 | 2013-07-31 | 2013-07-31 | 2013-07-31 | 2013-07-31 | 2013-07-31 | 2013-07-31 | 2013-07-31 | 2013-07-31 | 2013-07-31 | 2013-07-31 | 2013-07-31 | 2013-07-31 | 2009-07-31 | 2009-07-31 | 2009-07-31 | 2009-07-31 | 2009-07-31 | 2009-07-31 | 2009-07-31 | 2009-07-31
4 | 2.094% | CP.01706 | Gladstone to Larcom Creek Rebuild | 2009-08-31 | 2011-08-31 | 730 | Augmentation |  | 0 | 0 | 0 | 3.0499 | 22.4661 | 0.25814 | 0 | 25.7741 | Network Limitations |  |  | Scenarios & scenario probabilities 4: 2009-08-31; Scenarios & scenario probabilities 28: 2010-08-31; Scenarios & scenario probabilities 30: 2010-08-31; Scenarios & scenario probabilities 32: 2011-08-31
31 | 71.09% | CP.01705 | Calvale to Wurdong 275kV Double Circuit Line | 2009-09-30 | 2013-09-30 | 1461 | Augmentation |  | 0 | 0 | 0 | 8.2543 | 67.1573 | 1.5109 | 0 | 76.9225 | Network Limitations |  |  | 2009-09-30 | 2011-09-30 | 2009-09-30 |  | 2009-09-30 | 2009-09-30 | 2009-09-30 | 2011-09-30 | 2009-09-30 | 2011-09-30 |  | 2011-09-30 | 2009-09-30 | 2011-09-30 | 2013-09-30 | 2011-09-30 | 2011-09-30 | 2011-09-30 |  | 2011-09-30 | 2009-09-30 | 2011-09-30 |  | 2011-09-30 |  | 2010-09-30 |  |  |  | 2010-09-30 |  | 2011-09-30 | 2011-09-30 | 2009-09-30 | 2009-09-30 | 2009-09-30 | 2009-09-30 | 2009-09-30 | 2009-09-30 | 2009-09-30
21 | 25.12% | CP.00369/A | Establish Halys 275kV Substation and Calvale to Halys 2nd 275kV Double Circuit 1st Stage (single circuit strung) | 2009-10-31 | 2009-10-31 | 0 | Augmentation |  | 0 | 0 | 18.9737 | 189.4629 | 9.0955 | 0 | 0 | 217.5321 | Reliability |  |  | Scenarios & scenario probabilities 10: 2009-10-31; Scenarios & scenario probabilities 12: 2009-10-31; Scenarios & scenario probabilities 14: 2009-10-31; Scenarios & scenario probabilities 15: 2009-10-31; Scenarios & scenario probabilities 16: 2009-10-31; Scenarios & scenario probabilities 18: 2009-10-31; Scenarios & scenario probabilities 20: 2009-10-31; Scenarios & scenario probabilities 22: 2009-10-31; Scenarios & scenario probabilities 23: 2009-10-31; Scenarios & scenario probabilities 24: 2009-10-31; Scenarios & scenario probabilities 30: 2009-10-31; Scenarios & scenario probabilities 31: 2009-10-31; Scenarios & scenario probabilities 32: 2009-10-31; Scenarios & scenario probabilities 33: 2009-10-31; Scenarios & scenario probabilities 34: 2009-10-31; Scenarios & scenario probabilities 35: 2009-10-31; Scenarios & scenario probabilities 36: 2009-10-31; Scenarios & scenario probabilities 37: 2009-10-31; Scenarios & scenario probabilities 38: 2009-10-31; Scenarios & scenario probabilities 39: 2009-10-31; Scenarios & scenario probabilities 40: 2009-10-31
5 | 18.64% | CP.00369/B | Establish Halys 275kV Substation and Calvale to Halys 2nd 275kV Double Circuit 1st Stage (both circuit strung) | 2009-10-31 | 2009-10-31 | 0 | Augmentation |  | 0 | 0 | 22.1097 | 220.5459 | 10.5765 | 0 | 0 | 253.2321 | Reliability |  |  | Scenarios & scenario probabilities 11: 2009-10-31; Scenarios & scenario probabilities 19: 2009-10-31; Scenarios & scenario probabilities 26: 2009-10-31; Scenarios & scenario probabilities 27: 2009-10-31; Scenarios & scenario probabilities 28: 2009-10-31
1 | 1.097% | CP.01957 | Calvale to Larcom Creek 275kV Double Circuit | 2009-10-31 | 2009-10-31 | 0 | Augmentation |  | 0 | 0 | 5.6963 | 56.8052 | 2.7234 | 0 | 0 | 65.2249 | Network Limitations |  |  | Scenarios & scenario probabilities 4: 2009-10-31
25 | 89.93% | CP.01656 | Gladstone to Larcom Creek 275kV Transmission Line Life Extension | 2009-10-31 | 2009-10-31 | 0 | Augmentation |  | 0 | 0 | 0.35862 | 3.5542 | 0.16933 | 0 | 0 | 4.0822 | Network Limitations |  |  | 2009-10-31 | 2009-10-31 | 2009-10-31 |  | 2009-10-31 | 2009-10-31 | 2009-10-31 | 2009-10-31 | 2009-10-31 |  | 2009-10-31 |  | 2009-10-31 |  | 2009-10-31 |  | 2009-10-31 |  | 2009-10-31 |  | 2009-10-31 |  | 2009-10-31 |  | 2009-10-31 | 2009-10-31 | 2009-10-31 |  | 2009-10-31 |  | 2009-10-31 |  | 2009-10-31 |  | 2009-10-31 |  | 2009-10-31 |  | 2009-10-31 | 2009-10-31
17 | 14.46% | CP.00775/B | Braemar to Halys 500kV Double Circuit line Operating at 275kV (Halys already established) | 2009-10-31 | 2012-10-31 | 1096 | Augmentation |  | 0 | 0 | 0 | 11.0676 | 110.4469 | 5.2989 | 0 | 126.8133 | Reliability |  |  | Scenarios & scenario probabilities 10: 2011-10-31; Scenarios & scenario probabilities 12: 2012-10-31; Scenarios & scenario probabilities 14: 2010-10-31; Scenarios & scenario probabilities 16: 2012-10-31; Scenarios & scenario probabilities 18: 2011-10-31; Scenarios & scenario probabilities 22: 2011-10-31; Scenarios & scenario probabilities 24: 2012-10-31; Scenarios & scenario probabilities 26: 2012-10-31; Scenarios & scenario probabilities 30: 2011-10-31; Scenarios & scenario probabilities 33: 2009-10-31; Scenarios & scenario probabilities 34: 2009-10-31; Scenarios & scenario probabilities 35: 2009-10-31; Scenarios & scenario probabilities 36: 2009-10-31; Scenarios & scenario probabilities 37: 2009-10-31; Scenarios & scenario probabilities 38: 2009-10-31; Scenarios & scenario probabilities 39: 2009-10-31; Scenarios & scenario probabilities 40: 2009-10-31
8 | 28.12% | CP.01512/A | Strathmore to Ross 275kV Double Circuit | 2009-10-31 | 2010-10-31 | 365 | Augmentation |  | 0 | 0 | 0 | 12.0053 | 119.8084 | 5.7482 | 0 | 137.5619 | Reliability |  |  | Scenarios & scenario probabilities 9: 2010-10-31; Scenarios & scenario probabilities 13: 2010-10-31; Scenarios & scenario probabilities 25: 2010-10-31; Scenarios & scenario probabilities 29: 2010-10-31; Scenarios & scenario probabilities 33: 2009-10-31; Scenarios & scenario probabilities 35: 2009-10-31; Scenarios & scenario probabilities 37: 2009-10-31; Scenarios & scenario probabilities 39: 2009-10-31
3 | 1.895% | CP.01767 | Gladstone to Wurdong Double Circuit Line | 2009-10-31 | 2011-10-31 | 730 | Augmentation |  | 0 | 0 | 0 | 0 | 1.2079 | 11.9649 | 0.56974 | 13.7425 | Network Limitations |  |  | Scenarios & scenario probabilities 4: 2009-10-31; Scenarios & scenario probabilities 26: 2011-10-31; Scenarios & scenario probabilities 28: 2011-10-31
9 | 21.54% | CP.01762 | Calvale Transformer Augmentation | 2009-10-31 | 2011-10-31 | 730 | Augmentation |  | 0 | 0 | 0 | 1.6611 | 6.3374 | 0.25845 | 0 | 8.2569 | Network Limitations |  |  | Scenarios & scenario probabilities 2: 2009-10-31; Scenarios & scenario probabilities 8: 2009-10-31; Scenarios & scenario probabilities 15: 2010-10-31; Scenarios & scenario probabilities 17: 2009-10-31; Scenarios & scenario probabilities 25: 2011-10-31; Scenarios & scenario probabilities 29: 2011-10-31; Scenarios & scenario probabilities 30: 2010-10-31; Scenarios & scenario probabilities 32: 2011-10-31; Scenarios & scenario probabilities 33: 2009-10-31
33 | 85.84% | CP.01883 | Moreton West 120MVAr No. 4 | 2009-10-31 | 2013-10-31 | 1461 | Augmentation |  | 0 | 0 | 0 | 0 | 0.2557 | 1.7269 | 0.61109 | 2.5937 | Reliability |  |  | 2011-10-31 | 2010-10-31 |  | 2011-10-31 | 2011-10-31 | 2010-10-31 | 2013-10-31 |  | 2010-10-31 | 2012-10-31 | 2011-10-31 | 2011-10-31 | 2013-10-31 | 2010-10-31 | 2011-10-31 | 2011-10-31 | 2009-10-31 | 2011-10-31 | 2011-10-31 | 2011-10-31 | 2010-10-31 | 2011-10-31 | 2011-10-31 | 2011-10-31 |  | 2010-10-31 | 2011-10-31 | 2011-10-31 |  | 2010-10-31 | 2011-10-31 | 2011-10-31 | 2010-10-31 |  | 2011-10-31 |  | 2010-10-31 | 2010-10-31 |  | 2013-10-31
10 | 9.271% | CP.01897 | Moreton South 120MVAr No. 6 | 2009-10-31 | 2012-10-31 | 1096 | Augmentation |  | 0 | 0 | 0 | 0.25354 | 1.712 | 0.60573 | 0 | 2.5713 | Reliability |  |  | Scenarios & scenario probabilities 29: 2011-10-31; Scenarios & scenario probabilities 30: 2012-10-31; Scenarios & scenario probabilities 33: 2010-10-31; Scenarios & scenario probabilities 34: 2009-10-31; Scenarios & scenario probabilities 35: 2010-10-31; Scenarios & scenario probabilities 36: 2009-10-31; Scenarios & scenario probabilities 37: 2010-10-31; Scenarios & scenario probabilities 38: 2009-10-31; Scenarios & scenario probabilities 39: 2010-10-31; Scenarios & scenario probabilities 40: 2009-10-31
2 | 1.894% | CP.01615/D | Auburn River Switching Station (3 switched circuits) | 2010-07-31 | 2011-07-31 | 365 | Augmentation |  | 0 | 0 | 0 | 0 | 3.1435 | 9.4251 | 0.13725 | 12.7059 | Reliability |  |  | Scenarios & scenario probabilities 30: 2010-07-31; Scenarios & scenario probabilities 31: 2011-07-31
3 | 3.689% | CP.01615/C | Auburn River Switching Station (4 switched circuits) | 2010-08-31 | 2011-08-31 | 365 | Augmentation |  | 0 | 0 | 0 | 0 | 6.1542 | 20.9185 | 0.70606 | 27.7788 | Reliability |  |  | Scenarios & scenario probabilities 26: 2010-08-31; Scenarios & scenario probabilities 27: 2011-08-31; Scenarios & scenario probabilities 28: 2011-08-31
26 | 91.03% | CP.01657 | Bouldercombe to Larcom Creek 275kV Transmission Line Life Extension | 2010-10-31 | 2010-10-31 | 0 | Augmentation |  | 0 | 0 | 0 | 0.72132 | 7.1458 | 0.34029 | 0 | 8.2074 | Network Limitations |  |  | 2010-10-31 | 2010-10-31 | 2010-10-31 | 2010-10-31 | 2010-10-31 | 2010-10-31 | 2010-10-31 | 2010-10-31 | 2010-10-31 |  | 2010-10-31 |  | 2010-10-31 |  | 2010-10-31 |  | 2010-10-31 |  | 2010-10-31 |  | 2010-10-31 |  | 2010-10-31 |  | 2010-10-31 | 2010-10-31 | 2010-10-31 |  | 2010-10-31 |  | 2010-10-31 |  | 2010-10-31 |  | 2010-10-31 |  | 2010-10-31 |  | 2010-10-31 | 2010-10-31
40 | 100% | CP.00376 | Palmwoods 275/132kV Transformer Augmentation | 2010-10-31 | 2012-10-31 | 731 | Augmentation |  | 0 | 0 | 0 | 1.7788 | 6.7998 | 0.27785 | 0 | 8.8564 | Reliability |  |  | 2011-10-31 | 2011-10-31 | 2011-10-31 | 2011-10-31 | 2011-10-31 | 2011-10-31 | 2011-10-31 | 2011-10-31 | 2010-10-31 | 2010-10-31 | 2010-10-31 | 2010-10-31 | 2010-10-31 | 2010-10-31 | 2010-10-31 | 2010-10-31 | 2010-10-31 | 2010-10-31 | 2010-10-31 | 2010-10-31 | 2010-10-31 | 2010-10-31 | 2010-10-31 | 2010-10-31 | 2010-10-31 | 2010-10-31 | 2010-10-31 | 2010-10-31 | 2010-10-31 | 2010-10-31 | 2010-10-31 | 2010-10-31 | 2012-10-31 | 2011-10-31 | 2012-10-31 | 2012-10-31 | 2012-10-31 | 2011-10-31 | 2012-10-31 | 2012-10-31
4 | 3.589% | CP.01718 | Braemar 330/275kV Transformer Augmentation | 2010-10-31 | 2012-10-31 | 731 | Augmentation |  | 0 | 0 | 0 | 0 | 3.8064 | 14.5155 | 0.59169 | 18.9136 | Reliability |  |  | Scenarios & scenario probabilities 30: 2012-10-31; Scenarios & scenario probabilities 33: 2011-10-31; Scenarios & scenario probabilities 37: 2011-10-31; Scenarios & scenario probabilities 38: 2010-10-31
12 | 19.14% | CP.01875 | Halys to Blackwall 500kV Double Circuit Operating at 275kV | 2010-10-31 | 2013-10-31 | 1096 | Augmentation |  | 0 | 0 | 0 | 0 | 16.8716 | 168.2793 | 8.0692 | 193.2201 | Reliability |  |  | Scenarios & scenario probabilities 13: 2013-10-31; Scenarios & scenario probabilities 21: 2013-10-31; Scenarios & scenario probabilities 22: 2013-10-31; Scenarios & scenario probabilities 29: 2013-10-31; Scenarios & scenario probabilities 33: 2011-10-31; Scenarios & scenario probabilities 34: 2010-10-31; Scenarios & scenario probabilities 35: 2011-10-31; Scenarios & scenario probabilities 36: 2012-10-31; Scenarios & scenario probabilities 37: 2011-10-31; Scenarios & scenario probabilities 38: 2010-10-31; Scenarios & scenario probabilities 39: 2011-10-31; Scenarios & scenario probabilities 40: 2013-10-31
3 | 0.997% | CP.01707 | Larcom Creek to Bouldercombe Rebuild (both ccts turned in) | 2010-10-31 | 2011-10-31 | 365 | Augmentation |  | 0 | 0 | 0 | 5.3235 | 53.0924 | 2.5456 | 0 | 60.9616 | Network Limitations |  |  | Scenarios & scenario probabilities 28: 2010-10-31; Scenarios & scenario probabilities 30: 2010-10-31; Scenarios & scenario probabilities 32: 2011-10-31
27 | 74.68% | CP.01884 | Moreton West 120MVAr No. 5 | 2010-10-31 | 2013-10-31 | 1096 | Augmentation |  | 0 | 0 | 0 | 0 | 0.2557 | 1.7269 | 0.61109 | 2.5937 | Reliability |  |  | 2011-10-31 | 2012-10-31 |  | 2012-10-31 | 2011-10-31 | 2010-10-31 |  |  | 2011-10-31 | 2012-10-31 | 2012-10-31 | 2011-10-31 |  | 2010-10-31 | 2011-10-31 | 2011-10-31 | 2013-10-31 | 2012-10-31 | 2011-10-31 | 2011-10-31 | 2012-10-31 |  | 2011-10-31 | 2011-10-31 |  | 2012-10-31 | 2011-10-31 | 2011-10-31 |  | 2010-10-31 | 2011-10-31 |  |  |  | 2011-10-31 |  | 2010-10-31 | 2013-10-31
8 | 7.277% | CP.01898 | Moreton South 120MVAr No. 7 | 2010-10-31 | 2011-10-31 | 365 | Augmentation |  | 0 | 0 | 0 | 0 | 0.2557 | 1.7269 | 0.61109 | 2.5937 | Reliability |  |  | Scenarios & scenario probabilities 33: 2011-10-31; Scenarios & scenario probabilities 34: 2010-10-31; Scenarios & scenario probabilities 35: 2011-10-31; Scenarios & scenario probabilities 36: 2010-10-31; Scenarios & scenario probabilities 37: 2011-10-31; Scenarios & scenario probabilities 38: 2010-10-31; Scenarios & scenario probabilities 39: 2011-10-31; Scenarios & scenario probabilities 40: 2010-10-31
8 | 7.277% | CP.01899 | Moreton South 120MVAr No. 8 | 2010-10-31 | 2011-10-31 | 365 | Augmentation |  | 0 | 0 | 0 | 0 | 0.2557 | 1.7269 | 0.61109 | 2.5937 | Reliability |  |  | Scenarios & scenario probabilities 33: 2011-10-31; Scenarios & scenario probabilities 34: 2010-10-31; Scenarios & scenario probabilities 35: 2011-10-31; Scenarios & scenario probabilities 36: 2010-10-31; Scenarios & scenario probabilities 37: 2011-10-31; Scenarios & scenario probabilities 38: 2010-10-31; Scenarios & scenario probabilities 39: 2011-10-31; Scenarios & scenario probabilities 40: 2010-10-31
5 | 2.192% | CP.01900 | Moreton South 120MVAr No. 9 | 2010-10-31 | 2013-10-31 | 1096 | Augmentation |  | 0 | 0 | 0 | 0 | 0.2557 | 1.7269 | 0.61109 | 2.5937 | Reliability |  |  | Scenarios & scenario probabilities 34: 2011-10-31; Scenarios & scenario probabilities 36: 2010-10-31; Scenarios & scenario probabilities 38: 2013-10-31; Scenarios & scenario probabilities 39: 2011-10-31; Scenarios & scenario probabilities 40: 2010-10-31
4 | 1.993% | CP.01901 | Moreton South 120MVAr No. 10 | 2010-10-31 | 2012-10-31 | 731 | Augmentation |  | 0 | 0 | 0 | 0 | 0.2557 | 1.7269 | 0.61109 | 2.5937 | Reliability |  |  | Scenarios & scenario probabilities 34: 2011-10-31; Scenarios & scenario probabilities 36: 2010-10-31; Scenarios & scenario probabilities 39: 2012-10-31; Scenarios & scenario probabilities 40: 2011-10-31
1 | 3.39% | CP.01615 | Auburn River Switching Station (2 switched circuits) | 2011-06-30 | 2011-06-30 | 0 | Augmentation |  | 0 | 0 | 0 | 0 | 4.7526 | 12.528 | 0 | 17.2806 | Reliability |  |  | Scenarios & scenario probabilities 25: 2011-06-30
22 | 61.21% | CP.01544 | South Pine 350MVAr SVC | 2011-07-31 | 2013-07-31 | 731 | Augmentation |  | 0 | 0 | 0 | 0 | 0 | 14.9863 | 7.0694 | 22.0557 | Reliability |  |  | Scenarios & scenario probabilities 9: 2011-07-31; Scenarios & scenario probabilities 11: 2013-07-31; Scenarios & scenario probabilities 13: 2011-07-31; Scenarios & scenario probabilities 15: 2013-07-31; Scenarios & scenario probabilities 17: 2011-07-31; Scenarios & scenario probabilities 21: 2012-07-31; Scenarios & scenario probabilities 22: 2012-07-31; Scenarios & scenario probabilities 23: 2012-07-31; Scenarios & scenario probabilities 25: 2011-07-31; Scenarios & scenario probabilities 28: 2013-07-31; Scenarios & scenario probabilities 29: 2011-07-31; Scenarios & scenario probabilities 30: 2013-07-31; Scenarios & scenario probabilities 31: 2012-07-31; Scenarios & scenario probabilities 32: 2012-07-31; Scenarios & scenario probabilities 33: 2011-07-31; Scenarios & scenario probabilities 34: 2011-07-31; Scenarios & scenario probabilities 35: 2012-07-31; Scenarios & scenario probabilities 36: 2011-07-31; Scenarios & scenario probabilities 37: 2011-07-31; Scenarios & scenario probabilities 38: 2011-07-31; Scenarios & scenario probabilities 39: 2012-07-31; Scenarios & scenario probabilities 40: 2011-07-31
1 | 0.299% | CP.01902 | Moreton South 120MVAr No. 11 | 2011-10-31 | 2011-10-31 | 0 | Augmentation |  | 0 | 0 | 0 | 0 | 0.2557 | 1.7269 | 0.61109 | 2.5937 | Reliability |  |  | Scenarios & scenario probabilities 36: 2011-10-31
6 | 32.3% | CP.00369 | Establish Halys 275kV Substation and Braemar to Halys 500kV Double Circuit Operating at 275kV | 2011-10-31 | 2012-10-31 | 366 | Augmentation |  | 0 | 0 | 0 | 0 | 13.9194 | 138.972 | 6.6706 | 159.562 | Reliability |  |  | Scenarios & scenario probabilities 9: 2011-10-31; Scenarios & scenario probabilities 13: 2011-10-31; Scenarios & scenario probabilities 17: 2011-10-31; Scenarios & scenario probabilities 21: 2012-10-31; Scenarios & scenario probabilities 25: 2011-10-31; Scenarios & scenario probabilities 29: 2011-10-31
20 | 56.33% | CP.01885 | Moreton West 120MVAr No. 6 | 2011-10-31 | 2013-10-31 | 731 | Augmentation |  | 0 | 0 | 0 | 0 | 0 | 0.25793 | 1.7422 | 2.0001 | Reliability |  |  | Scenarios & scenario probabilities 1: 2013-10-31; Scenarios & scenario probabilities 2: 2013-10-31; Scenarios & scenario probabilities 5: 2011-10-31; Scenarios & scenario probabilities 6: 2013-10-31; Scenarios & scenario probabilities 9: 2012-10-31; Scenarios & scenario probabilities 10: 2013-10-31; Scenarios & scenario probabilities 11: 2012-10-31; Scenarios & scenario probabilities 12: 2011-10-31; Scenarios & scenario probabilities 14: 2011-10-31; Scenarios & scenario probabilities 15: 2012-12-31; Scenarios & scenario probabilities 16: 2012-10-31; Scenarios & scenario probabilities 19: 2011-10-31; Scenarios & scenario probabilities 20: 2012-10-31; Scenarios & scenario probabilities 23: 2013-10-31; Scenarios & scenario probabilities 24: 2011-10-31; Scenarios & scenario probabilities 26: 2012-10-31; Scenarios & scenario probabilities 28: 2011-10-31; Scenarios & scenario probabilities 30: 2012-10-31; Scenarios & scenario probabilities 31: 2011-10-31; Scenarios & scenario probabilities 38: 2013-10-31
11 | 19.84% | CP.01904 | Moreton West 120MVAr No. 7 | 2011-10-31 | 2013-10-31 | 731 | Augmentation |  | 0 | 0 | 0 | 0 | 0 | 0.25793 | 1.7422 | 2.0001 | Reliability |  |  | Scenarios & scenario probabilities 5: 2011-10-31; Scenarios & scenario probabilities 6: 2013-10-31; Scenarios & scenario probabilities 12: 2012-10-31; Scenarios & scenario probabilities 14: 2011-10-31; Scenarios & scenario probabilities 15: 2012-12-31; Scenarios & scenario probabilities 16: 2012-10-31; Scenarios & scenario probabilities 19: 2013-10-31; Scenarios & scenario probabilities 20: 2012-10-31; Scenarios & scenario probabilities 24: 2012-10-31; Scenarios & scenario probabilities 28: 2012-10-31; Scenarios & scenario probabilities 30: 2012-10-31
11 | 37.98% | CP.01914 | Tarong 120MVAr No. 1 | 2011-10-31 | 2013-10-31 | 731 | Augmentation |  | 0 | 0 | 0 | 0 | 0 | 0.25793 | 1.7422 | 2.0001 | Reliability |  |  | Scenarios & scenario probabilities 9: 2011-10-31; Scenarios & scenario probabilities 13: 2011-10-31; Scenarios & scenario probabilities 15: 2012-12-31; Scenarios & scenario probabilities 18: 2012-10-31; Scenarios & scenario probabilities 19: 2012-10-31; Scenarios & scenario probabilities 21: 2012-10-31; Scenarios & scenario probabilities 25: 2013-10-31; Scenarios & scenario probabilities 34: 2011-10-31; Scenarios & scenario probabilities 37: 2011-10-31; Scenarios & scenario probabilities 39: 2012-10-31; Scenarios & scenario probabilities 40: 2011-10-31
18 | 36.49% | CP.01772 | South Pine to South West Brisbane 275kV Double Circuit Uprate Existing Line | 2012-06-30 | 2014-06-30 | 730 | Augmentation |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Reliability |  |  | Scenarios & scenario probabilities 9: 2014-06-30; Scenarios & scenario probabilities 10: 2014-06-30; Scenarios & scenario probabilities 13: 2014-06-30; Scenarios & scenario probabilities 14: 2014-06-30; Scenarios & scenario probabilities 21: 2014-06-30; Scenarios & scenario probabilities 22: 2014-06-30; Scenarios & scenario probabilities 25: 2014-06-30; Scenarios & scenario probabilities 26: 2014-06-30; Scenarios & scenario probabilities 29: 2014-06-30; Scenarios & scenario probabilities 30: 2014-06-30; Scenarios & scenario probabilities 33: 2012-06-30; Scenarios & scenario probabilities 34: 2012-06-30; Scenarios & scenario probabilities 35: 2012-06-30; Scenarios & scenario probabilities 36: 2012-06-30; Scenarios & scenario probabilities 37: 2012-06-30; Scenarios & scenario probabilities 38: 2012-06-30; Scenarios & scenario probabilities 39: 2012-06-30; Scenarios & scenario probabilities 40: 2012-06-30
5 | 7.479% | CP.01905 | Moreton West 120MVAr No. 8 | 2012-10-31 | 2013-10-31 | 365 | Augmentation |  | 0 | 0 | 0 | 0 | 0 | 0.25793 | 1.7422 | 2.0001 | Reliability |  |  | Scenarios & scenario probabilities 5: 2012-10-31; Scenarios & scenario probabilities 12: 2012-10-31; Scenarios & scenario probabilities 14: 2012-10-31; Scenarios & scenario probabilities 16: 2013-10-31; Scenarios & scenario probabilities 24: 2012-10-31
4 | 14.95% | CP.01916 | Gladstone Zone 120MVAr No. 2 | 2012-10-31 | 2013-10-31 | 365 | Augmentation |  | 0 | 0 | 0 | 0 | 0 | 0.25793 | 1.7422 | 2.0001 | Reliability |  |  | Scenarios & scenario probabilities 1: 2013-10-31; Scenarios & scenario probabilities 5: 2012-10-31; Scenarios & scenario probabilities 29: 2012-10-31; Scenarios & scenario probabilities 31: 2013-10-31
4 | 0.996% | CP.01873 | Swanbank to Blackwall Line Rebuild | 2013-06-30 | 2013-06-30 | 0 | Augmentation |  | 0 | 0 | 0 | 0 | 0 | 0 | 1.2366 | 1.2366 | Reliability |  |  | Scenarios & scenario probabilities 34: 2013-06-30; Scenarios & scenario probabilities 36: 2013-06-30; Scenarios & scenario probabilities 38: 2013-06-30; Scenarios & scenario probabilities 40: 2013-06-30
2 | 2.293% | CP.01879 | Millmerran to Bulli Creek 500kV Double Circuit Operating at 330kV | 2013-07-31 | 2013-07-31 | 0 | Augmentation |  | 0 | 0 | 0 | 0 | 0 | 0 | 10.8991 | 10.8991 | Reliability |  |  | Scenarios & scenario probabilities 37: 2013-07-31; Scenarios & scenario probabilities 39: 2013-07-31
10 | 7.479% | CP.01706/B | Gladstone to Larcom Creek Rebuild (circuits paralleled) | 2013-08-31 | 2013-08-31 | 0 | Augmentation |  | 0 | 0 | 0 | 0 | 0 | 0 | 1.9376 | 1.9376 | Network Limitations |  |  | Scenarios & scenario probabilities 10: 2013-08-31; Scenarios & scenario probabilities 12: 2013-08-31; Scenarios & scenario probabilities 14: 2013-08-31; Scenarios & scenario probabilities 16: 2013-08-31; Scenarios & scenario probabilities 18: 2013-08-31; Scenarios & scenario probabilities 20: 2013-08-31; Scenarios & scenario probabilities 24: 2013-08-31; Scenarios & scenario probabilities 34: 2013-08-31; Scenarios & scenario probabilities 36: 2013-08-31; Scenarios & scenario probabilities 38: 2013-08-31
4 | 6.281% | CP.01794/C | 3rd 500kV Double Circuit into SEQ | 2013-10-31 | 2013-10-31 | 0 | Augmentation |  | 0 | 0 | 0 | 0 | 0 | 0 | 22.8354 | 22.8354 | Reliability |  |  | Scenarios & scenario probabilities 33: 2013-10-31; Scenarios & scenario probabilities 35: 2013-10-31; Scenarios & scenario probabilities 37: 2013-10-31; Scenarios & scenario probabilities 39: 2013-10-31
10 | 7.479% | CP.01707/A | Larcom Creek to Bouldercombe Rebuild (one circuit turned in) | 2013-10-31 | 2013-10-31 | 0 | Augmentation |  | 0 | 0 | 0 | 0 | 0 | 0 | 5.4364 | 5.4364 | Network Limitations |  |  | Scenarios & scenario probabilities 10: 2013-10-31; Scenarios & scenario probabilities 12: 2013-10-31; Scenarios & scenario probabilities 14: 2013-10-31; Scenarios & scenario probabilities 16: 2013-10-31; Scenarios & scenario probabilities 18: 2013-10-31; Scenarios & scenario probabilities 20: 2013-10-31; Scenarios & scenario probabilities 24: 2013-10-31; Scenarios & scenario probabilities 34: 2013-10-31; Scenarios & scenario probabilities 36: 2013-10-31; Scenarios & scenario probabilities 38: 2013-10-31
1 | 0.199% | CP.01891 | Moreton North 120MVAr No. 1 | 2013-10-31 | 2013-10-31 | 0 | Augmentation |  | 0 | 0 | 0 | 0 | 0 | 0 | 0.26022 | 0.26022 | Reliability |  |  | Scenarios & scenario probabilities 40: 2013-10-31
2 | 1.396% | CP.01906 | Moreton West 120MVAr No. 9 | 2013-10-31 | 2013-10-31 | 0 | Augmentation |  | 0 | 0 | 0 | 0 | 0 | 0 | 0.26022 | 0.26022 | Reliability |  |  | Scenarios & scenario probabilities 14: 2013-10-31; Scenarios & scenario probabilities 24: 2013-10-31
1 | 1.695% | CP.01917 | Gladstone Zone 120MVAr No. 3 | 2013-10-31 | 2013-10-31 | 0 | Augmentation |  | 0 | 0 | 0 | 0 | 0 | 0 | 0.26022 | 0.26022 | Reliability |  |  | Scenarios & scenario probabilities 29: 2013-10-31
3 | 1.895% | CP.01854/A | Easement Acquisition and Clearance Gladstone to Wurdong 275kV Double Circuit (TE) | 2007-10-31 | 2009-10-31 | 731 | Easements |  | 0 | 0 | 0.28322 | 0.28025 | 0.053254 | 0 | 0 | 0.61673 | Construction |  |  | Scenarios & scenario probabilities 4: 2007-10-31; Scenarios & scenario probabilities 26: 2009-10-31; Scenarios & scenario probabilities 28: 2009-10-31
28 | 51.65% | CP.01833/A | Easement Acquisition for Calvale to Halys 2nd 275kV Double Circuit Line (TE) | 2008-05-31 | 2012-10-31 | 1614 | Easements |  | 0 | 3.4668 | 0.89131 | 0 | 0 | 0 | 0 | 0.89131 | Construction |  |  |  |  | 2012-10-31 | 2012-10-31 | [5 empty] | 2008-05-31 | 2008-05-31 | 2008-05-31 |  | 2008-05-31 | 2008-05-31 | 2008-05-31 |  | 2008-05-31 | 2008-05-31 | 2008-05-31 |  | 2008-05-31 | 2008-05-31 | 2008-05-31 |  | 2008-05-31 | 2008-05-31 | 2008-05-31 |  | 2008-05-31 | 2008-05-31 | 2008-05-31 | 2008-05-31 | 2008-05-31 | 2008-05-31 | 2008-05-31 | 2008-05-31 | 2008-05-31 | 2008-05-31 | 2008-05-31
31 | 71.09% | CP.01830/A | Easement Clearance and Acquisition for Calvale to Wurdong 275kV Double Circuit (TE) | 2008-09-30 | 2011-09-30 | 1095 | Easements |  | 0 | 1.3124 | 1.0122 | 0.17312 | 0 | 0 | 0 | 1.1854 | Construction |  |  | 2008-09-30 | 2009-09-30 | 2008-09-30 |  | 2008-09-30 | 2008-09-30 | 2008-09-30 | 2009-09-30 | 2008-09-30 | 2009-09-30 |  | 2009-09-30 | 2008-09-30 | 2009-09-30 | 2011-09-30 | 2009-09-30 | 2009-09-30 | 2009-09-30 |  | 2009-09-30 | 2008-09-30 | 2009-09-30 |  | 2009-09-30 |  | 2008-09-30 |  |  |  | 2008-09-30 |  | 2009-09-30 | 2009-09-30 | 2008-09-30 | 2008-09-30 | 2008-09-30 | 2008-09-30 | 2008-09-30 | 2008-09-30 | 2008-09-30
28 | 51.65% | CP.01833/B | Easement Acquisition for Calvale to Halys 2nd 275kV Double Circuit Line (Compensation) | 2008-10-31 | 2013-10-31 | 1826 | Easements |  | 0 | 0.13844 | 3.3226 | 0.16913 | 0 | 0 | 0 | 3.4917 | Construction |  |  |  |  | 2013-10-31 | 2013-10-31 | [5 empty] | 2008-10-31 | 2008-10-31 | 2008-10-31 |  | 2008-10-31 | 2008-10-31 | 2008-10-31 |  | 2008-10-31 | 2008-10-31 | 2008-10-31 |  | 2008-10-31 | 2008-10-31 | 2008-10-31 |  | 2008-10-31 | 2008-10-31 | 2008-10-31 |  | 2008-10-31 | 2008-10-31 | 2008-10-31 | 2008-10-31 | 2008-10-31 | 2008-10-31 | 2008-10-31 | 2008-10-31 | 2008-10-31 | 2008-10-31 | 2008-10-31
14 | 8.975% | CP.01850/A | Easement Clearance Larcom Creek to Bouldercombe 275kV Double Circuit Line (TE) | 2008-10-31 | 2013-10-31 | 1826 | Easements |  | 0 | 0 | 0 | 0 | 0.53042 | 0.52484 | 0.099734 | 1.155 | Construction |  |  | Scenarios & scenario probabilities 10: 2011-10-31; Scenarios & scenario probabilities 12: 2011-10-31; Scenarios & scenario probabilities 14: 2011-10-31; Scenarios & scenario probabilities 16: 2011-10-31; Scenarios & scenario probabilities 18: 2011-10-31; Scenarios & scenario probabilities 20: 2011-10-31; Scenarios & scenario probabilities 22: 2013-10-31; Scenarios & scenario probabilities 24: 2011-10-31; Scenarios & scenario probabilities 28: 2008-10-31; Scenarios & scenario probabilities 30: 2008-10-31; Scenarios & scenario probabilities 32: 2009-10-31; Scenarios & scenario probabilities 34: 2011-10-31; Scenarios & scenario probabilities 36: 2011-10-31; Scenarios & scenario probabilities 38: 2011-10-31
3 | 1.895% | CP.01854/B | Easement Acquisition and Clearance Gladstone to Wurdong 275kV Double Circuit (Compensation) | 2008-10-31 | 2010-10-31 | 730 | Easements |  | 0 | 0 | 0 | 0.005249 | 0.12598 | 0.006412 | 0 | 0.13764 | Construction |  |  | Scenarios & scenario probabilities 4: 2008-10-31; Scenarios & scenario probabilities 26: 2010-10-31; Scenarios & scenario probabilities 28: 2010-10-31
31 | 71.09% | CP.01830/B | Easement Clearance and Acquisition for Calvale to Wurdong 275kV Double Circuit (Compensation) | 2009-09-30 | 2012-09-30 | 1096 | Easements |  | 0 | 0 | 0.058398 | 0.95935 | 0 | 0 | 0 | 1.0178 | Construction |  |  | 2009-09-30 | 2010-09-30 | 2009-09-30 |  | 2009-09-30 | 2009-09-30 | 2009-09-30 | 2010-09-30 | 2009-09-30 | 2010-09-30 |  | 2010-09-30 | 2009-09-30 | 2010-09-30 | 2012-09-30 | 2010-09-30 | 2010-09-30 | 2010-09-30 |  | 2010-09-30 | 2009-09-30 | 2010-09-30 |  | 2010-09-30 |  | 2009-09-30 |  |  |  | 2009-09-30 |  | 2010-09-30 | 2010-09-30 | 2009-09-30 | 2009-09-30 | 2009-09-30 | 2009-09-30 | 2009-09-30 | 2009-09-30 | 2009-09-30
2 | 2.293% | CP.01878/A | Easement Acquisition Millmerran to Bulli Creek 500kV Double Circuit Line (TE) | 2011-07-31 | 2011-07-31 | 0 | Easements |  | 0 | 0 | 0 | 0 | 0.79762 | 0.36831 | 0.041993 | 1.2079 | Construction |  |  | Scenarios & scenario probabilities 37: 2011-07-31; Scenarios & scenario probabilities 39: 2011-07-31
2 | 2.293% | CP.01966/A | Bulli Creek Substation Extension for 500kV (TE) | 2011-07-31 | 2011-07-31 | 0 | Easements |  | 0 | 0 | 0 | 0 | 0.15226 | 0.070308 | 0.008016 | 0.23058 | Construction |  |  | Scenarios & scenario probabilities 37: 2011-07-31; Scenarios & scenario probabilities 39: 2011-07-31
2 | 2.293% | CP.01968/A | Millmerran Substation Extension for 500kV (TE) | 2011-07-31 | 2011-07-31 | 0 | Easements |  | 0 | 0 | 0 | 0 | 0.20791 | 0.096006 | 0.010946 | 0.31487 | Construction |  |  | Scenarios & scenario probabilities 37: 2011-07-31; Scenarios & scenario probabilities 39: 2011-07-31
2 | 2.293% | CP.01965/A | Widening Existing Easement Bulli Creek to Braemar for Future 500kV (TE) | 2011-07-31 | 2011-07-31 | 0 | Easements |  | 0 | 0 | 0 | 0 | 1.029 | 0.47517 | 0.054177 | 1.5584 | Construction |  |  | Scenarios & scenario probabilities 37: 2011-07-31; Scenarios & scenario probabilities 39: 2011-07-31
2 | 2.293% | CP.01878/B | Easement Acquisition Millmerran to Bulli Creek 500kV Double Circuit Line (Compensation) | 2012-07-31 | 2012-07-31 | 0 | Easements |  | 0 | 0 | 0 | 0 | 0 | 0.26932 | 0.38999 | 0.65931 | Construction |  |  | Scenarios & scenario probabilities 37: 2012-07-31; Scenarios & scenario probabilities 39: 2012-07-31
2 | 2.293% | CP.01966/B | Bulli Creek Substation Extension for 500kV (Compensation) | 2012-07-31 | 2012-07-31 | 0 | Easements |  | 0 | 0 | 0 | 0 | 0 | 0.054537 | 0.078973 | 0.13351 | Construction |  |  | Scenarios & scenario probabilities 37: 2012-07-31; Scenarios & scenario probabilities 39: 2012-07-31
2 | 2.293% | CP.01968/B | Millmerran Substation Extension for 500kV (Compensation) | 2012-07-31 | 2012-07-31 | 0 | Easements |  | 0 | 0 | 0 | 0 | 0 | 0.18179 | 0.26324 | 0.44504 | Construction |  |  | Scenarios & scenario probabilities 37: 2012-07-31; Scenarios & scenario probabilities 39: 2012-07-31
2 | 2.293% | CP.01965/B | Widening Existing Easement Bulli Creek to Braemar for Future 500kV (Compensation) | 2012-07-31 | 2012-07-31 | 0 | Easements |  | 0 | 0 | 0 | 0 | 0 | 0.82564 | 1.1956 | 2.0212 | Construction |  |  | Scenarios & scenario probabilities 37: 2012-07-31; Scenarios & scenario probabilities 39: 2012-07-31
4 | 9.571% | CP.01784 | Calvale 275kV Substation Refurbishment | 2011-10-31 | 2011-10-31 | 0 | Security/Compliance |  | 0 | 0 | 0 | 0 | 7.1567 | 31.1106 | 4.8929 | 43.1602 | Fault Level |  |  | Scenarios & scenario probabilities 25: 2011-10-31; Scenarios & scenario probabilities 27: 2011-10-31; Scenarios & scenario probabilities 29: 2011-10-31; Scenarios & scenario probabilities 31: 2011-10-31
[8 empty] | Subtotal | 1.3982 | 50.3656 | 228.5571 | 848.9615 | 666.8954 | 695.6579 | 414.5321 | 2854.604

## Forecast Capex - Non-Network
4.4 FORECAST CAPEX - Non-Network - by project
[6 empty] | Home |  |  | Link to Forecast Capex Instructions - Table 6.3
($m, real 06/07)
Yearly expenditure by project
Project No. | Project Name | Estimated Commissioning Date | Category^ |  | 2007/08 | 2008/09 | 2009/10 | 2010/11 | 2011/12 | TOTAL | REASON FOR PROJECT | Business Case (Y/N)
| Intra-Regional Flow Forecasting | 2008/09 | Information Technology |  |  | 0.357 |  |  |  | 0.357 | additional requirements
| Outage Impacts and Service Statistics | 2007/08 | Information Technology |  | 0.185 |  |  |  |  | 0.185 | increase in obligations
| Network Master Data Integration | 2008/09 | Information Technology |  | 0.211 | 0.842 |  |  |  | 1.053 | additional requirments
| Network Master Data Change Control | 2008/09 | Information Technology |  |  | 0.314 |  |  |  | 0.314 | increase in obligations
| Ratings Management | 2007/08 | Information Technology |  | 0.167 |  |  |  |  | 0.167 | additional requirements
| Project Reporting Interface | 2007/08 | Information Technology |  | 0.134 |  |  |  |  | 0.134 | additional requirements
| Smart CAD and 3D Drawing Tool | 2008/09 | Information Technology |  | 0.514 | 0.311 |  |  |  | 0.825 | additional requirements
| Field Data Collection & Management | 2007/08 | Information Technology |  | 0.197 |  |  |  |  | 0.197 | additional requirements
| Web-Based Integration of Power System Information (Framework) | 2007/08 | Information Technology |  | 0.318 |  |  |  |  | 0.318 | additional requirements
| Web-Based Integration of Power System Information (Interfaces) | 2008/09 | Information Technology |  | 0.175 | 0.349 |  |  |  | 0.524 | additional requirements
| Strategic Enterprise Management / KPI Reporting | 2008/09 | Information Technology |  |  | 0.255 |  |  |  | 0.255 | increase in obligations
| Digital Network Connectivity Database & Viewer (Replace CNDB) | 2008/09 | Information Technology |  |  | 0.703 |  |  |  | 0.703 | obsolescence
| Redevelop Switching Sheet Program | 2007/08 | Information Technology |  | 0.267 |  |  |  |  | 0.267 | obsolescence
| MSP Mobile Access to SAP and Work Management | 2008/09 | Information Technology |  | 0.308 | 0.329 |  |  |  | 0.637 | additional requirements
| New Starters & Terminations | 2007/08 | Information Technology |  | 0.224 |  |  |  |  | 0.224 | obsolescence
| Replace the Network Plant Register (NPR) and HV Index | 2007/08 | Information Technology |  | 0.167 |  |  |  |  | 0.167 | obsolescence
| Contract Management System (Replace CAPS) | 2007/08 | Information Technology |  | 0.561 |  |  |  |  | 0.561 | obsolescence
| Compliance & Audit Management | 2008/09 | Information Technology |  |  | 0.217 |  |  |  | 0.217 | compliance
| Redevelop the LIS as a Web Application | 2008/09 | Information Technology |  |  | 0.276 |  |  |  | 0.276 | additional requirements
| Capital Projects Forecast past 2008 / 2009 | On-going | Information Technology |  |  |  | 4.147 | 4.004 | 3.883 | 12.034 | various
| Implement Machine Authentication | 2007/08 | Information Technology |  | 0.221 |  |  |  |  | 0.221 | security
| Network Monitoring Tool | 2007/08 | Information Technology |  | 1.34 |  |  |  |  | 1.34 | additional requirements
| PABX Replacement | 2008/09 | Information Technology |  |  | 0.481 |  |  |  | 0.481 | obsolescence
| Recabling of Offices (Fibre to the Desktop) | 2008/09 | Information Technology |  |  | 2.911 |  |  |  | 2.911 | obsolescence
| Reinforce Server Capacity | 2007/08 | Information Technology |  | 1.693 |  |  |  |  | 1.693 | additional requirements
| RFID Deployment | 2008/09 | Information Technology |  |  | 0.467 |  |  |  | 0.467 | additional requirements
| Server OS Upgrade | 2008/09 | Information Technology |  |  | 0.785 |  |  |  | 0.785 | obsolescence
| Upgrade Disaster Recovery Capability | 2007/08 | Information Technology |  | 0.966 |  |  |  |  | 0.966 | security
| VOIP to Remote Offices & Substations | 2008/09 | Information Technology |  |  | 0.763 |  |  |  | 0.763 | additional requirements
| Wireless Deployment | 2007/08 | Information Technology |  | 0.858 |  |  |  |  | 0.858 | additional requirements
| Forecast past 2008 / 2009 | On-going | Information Technology |  |  |  | 5.054 | 5.18 | 5.213 | 15.447 | various
| Desktop/laptop Replacements | On-going | Information Technology |  | 1.345 | 1.192 | 0.722 | 1.274 | 1.192 | 5.725 | obsolescence
| Other Replacements | On-going | Information Technology |  | 2.053 | 0.647 | 1.13 | 0.43 | 2.053 | 6.313 | obsolescence
CP.98100 | Fleet | On-going | Motor Vehicles |  | 2.69 | 2.915 | 4.222 | 4.365 | 4.32 | 18.512 | obsolescence & new requirements
CP.98200 | Buildings | On-going | Commerical Buildings |  | 2.568 | 1.535 | 2.054 | 1.541 | 1.541 | 9.239 | obsolescence
CP.98200 | Office Furniture | On-going | Commerical Buildings |  | 0.154 | 0.154 | 0.154 | 0.154 | 0.154 | 0.77 | obsolescence
CP.98202 | Warehousing and Storage | 2009/10 | Commerical Buildings |  |  | 4.159 | 2.054 |  |  | 6.213 | additional requirements
CP.98500 | Land | On-going | Commerical Buildings |  | 0.257 | 0.257 | 0.257 | 0.257 | 0.257 | 1.285 | new requirements
CP.98700 | Office Equipment | On-going | Commerical Buildings | [6 empty] | 0 | obsolescence
CP.01729 | Live Training Facility | 2010/11 | Commerical Buildings |  |  |  | 2.101 | 2.054 |  | 4.155 | new requirements
CP.99200 | Tools and Equipment | On-going | Tools |  | 1.481 | 1.435 | 1.029 | 1.075 | 1.142 | 6.162 | obsolescence
|  |  |  | Subtotal | 19.054 | 21.654 | 22.924 | 20.334 | 19.755 | 103.721
^refers to the categories used in table 4.1 (eg Information Technology, Motor Vehicles etc)

## Opex Instructions
6.1 OPEX - Instructions and definitions
PURPOSE OF INFORMATION AND USE BY THE AER: | The historic worksheets (1.1 to 1.7) are a key input into the AER's assessment of a TNSP's historic opex performance to assist it in establishing a starting point from which to set efficient opex for the next regulatory period. | Home
The forecast worksheets (2.1 to 2.6) are a key input into the AER's assessment of a TNSPs proposed forecast opex.
Key cost drivers for expenditure are important to the AER's understanding of what has happened in the current regulatory period and any step changes in opex claimed for the next regulatory period.
INSTRUCTIONS | Data to be input on the basis of the definitions provided.
All expenditure must relate to the provision of prescribed services.
Key cost drivers for expenditure: reasons for material changes in costs should be expanded upon in the relevant opex commentary proforma.
Templates must be completed in accordance with the instructions contained in the AER's Information Requirements Guidelines (eg. cost allocation methodology.)
Values for 2005/06 and 2006/07 are estimated values only
DEFINITIONS | Asset Manager Support: those operational activities to support the strategic development and ongoing asset management of the network. Asset Management Support has 4 major sub-elements: Grid Planning, Network Support, Network Customer & Regulatory Support and IT Support.
Asset monitoring: the asset monitoring team performing remote monitoring of Powerlink’s network.
Condition based maintenance: maintenance activities based on inspection/assessment of the condition of an asset.
Corporate Support : the support activities required by Powerlink including finance, accounting, administration, employee relations and corporate governance.
Insurance : includes insurance premiums and self insurance.
Corrective maintenance: activities that restore a failed component to an operational state.
Direct Charges: costs associated with owning and managing assets, which include council rates charges, water charges, electricity bills and permits etc.
Field maintenance: includes all field activities, performed by maintenance service providers, to ensure the item of plant can perform its required functions.
Field Support: field-based activities performed by maintenance service providers which are not directly related to working on an item of plant.
Key cost drivers: significant factors driving expenditure such as age and condition of assets, size of network, CPI, labour costs, legislative requirements.
Operations: includes all activities in operating and monitoring assets in the field.
Network switching: the control centre function and ongoing management of the energy management system (EMS).
NMS support: the telecommunications network management system (NMS).
Non-network: all activities not directly related to the operation and maintenance of the network, including administrative, planning and engineering support costs.
Operational refurbishment: activities that return an asset to its pre-existing condition or function.
Opex: expenditure related to operating and maintaining assets which is not capex.
Other Support: Non field based activities associated with maintenance activities.
Routine maintenance: recurrent activities undertaken to maintain assets.
Return to Historic Opex by Driver - Table 1.1
Links to Historic Opex: | Return to Historic Opex by Category 2002 - Table 1.2
Return to Historic Opex by Category 2003 - Table 1.3
Return to Historic Opex by Category 2004 - Table 1.4
Return to Historic Opex by Category 2005 - Table 1.5
Return to Historic Opex by Category 2006 - Table 1.6
Return to Historic Opex by Category 2007 - Table 1.7
Return to Forecast Opex Summary - Table 2.1
Links to Forecast Opex: | Return to Forecast Opex by Category 2008 - Table 2.2
Return to Forecast Opex by Category 2009 - Table 2.3
Return to Forecast Opex by Category 2010 - Table 2.4
Return to Forecast Opex by Category 2011 - Table 2.5
Return to Forecast Opex by Category 2012 - Table 2.6

## Historic Capex Instructions
6.2 HISTORIC CAPEX - Instructions and definitions
PURPOSE OF INFORMATION AND USE BY THE AER: | The templates are key inputs into the AER's assessment of historic capex and will assist in the analysis of the prudency of expenditure. | Home
Specifying expenditure by project enables the AER to select projects on which to undertake more detailed analysis.
The capex categories are essentially divided between Network and Non-network. Network includes augmentation capex which is subject to the Regulatory Test.
INSTRUCTIONS: | Data to be input on the basis of the definitions provided.
All expenditure must relate to the provision of prescribed services.
Categorisation of capex should be performed according to the primary reason for expenditure.
Capex amounts should be entered on an as-commissioned basis, excluding customer contributions.
Customer contributions are to be noted separately.
Reasons for variance: if actual expenditure materially varies from the amount determined under the Regulatory Test/Business case, or the date of commissioning was later than planned, then reasons should be given on the Historic Capex Commentary pro forma with a brief reference in the 'Reasons for variance' column of Table 3.3 and 3.4.
Templates must be completed according to the instructions contained in the AER's Information Requirements Guidelines.
Values for 2005/06 and 2006/07 are estimated values only.
DEFINITIONS: | Augmentation: are as defined under the National Electricity Rules (NER) as works to enlarge a network or to increase the capability of a network to transmit (or distribute) active energy.
Business case: a detailed cost/benefit analysis undertaken to support an investment.
Capex: expenditure that satisfies one or more of the following requirements - relates to the purchase or construction of a new asset; increases the functionality of the asset; or extends the service life of the asset.
Connections: changes to connections between the transmission and distribution networks.
Easements: land acquisitions and rights of way for transmission lines.
FDC: financing during construction - finance charges up to the point of completion of the project.
IT: Business IT expenditure.
Other (Load Driven): anything else driven by increasing load.
Other (Non-Load Driven): all other projects associated with the network which provides prescribed transmission services such as communications systems enhancements.
Project ID: A unique numerical identifier for a given project
Project Description: A short description of the project
Regulatory Test: the test as promulgated by the ACCC to assess augmentation expenditure. A prudency test must be applied to other capex undertaken in the current regulatory period.
Replacements: replacement or life extension of network assets.
Security/Compliance: projects undertaken to ensure the physical security of assets and compliance with amendments to various technical, safety or environmental legislation.
Support the business: non-network capex relating to commercial buildings, motor vehicles and tools (but excluding IT).
Links to Historic Capex: | Return to Historic Capex by Category - Table 3.1
Return to Historic Capex by Asset Class - Table 3.2
Return to Historic Capex- Network - 3.3
Return to Historic Capex - Non-Network - 3.4

## Forecast Capex Instructions
6.3 FORECAST CAPEX - Instructions and definitions
PURPOSE OF INFORMATION AND USE BY THE AER: | The templates are key inputs into the AER's assessment of forecast capex and will enable an analysis of the proposed expenditure. | Home
Specifying expenditure by project enables the AER to select projects on which to undertake more detailed analysis.
Link to Forecast Capex commentary - Table 5.3
INSTRUCTIONS: | Data to be input on the basis of the definitions provided.
All expenditure must relate to the provision of prescribed services.
Categorisation of capex should be performed according to the primary reason for expenditure.
Capex amounts should be entered on an as-incurred basis, excluding customer contributions.
Customer contributions are to be noted separately.
Templates must be completed according to the instructions contained in the AER's Information Requirements Guidelines.
The TNSP is also requested to provide consultants reports on the probabilistic methodology adopted, including information on theme sets and scenarios upon which the proposed capex spend is based. Further, details on the consultants assumptions, inputs and detailed information on the outcomes are requested.
DEFINITIONS: | Augmentation: are as defined under the National Electricity Rules (NER) as works to enlarge a network or to increase the capability of a network to transmit (or distribute) active energy.
Business case: a detailed cost/benefit analysis undertaken to support an investment.
Capex: expenditure that satisfies one or more of the following requirements - relates to the purchase or construction of a new asset; increases the functionality of the asset; or extends the service life of the asset.
Project ID: a unique identifier for each project
Regulatory Test: the test as promulgated by the ACCC to assess augmentation expenditure. A prudency test must be applied to other capex undertaken in the current regulatory period.
Replacement: capex to replace assets that have reached the end of their useful life.
Scenario ID: Projects must be linked to the scenario(s) under which they are required.
Support the business: non-network capex relating to commercial buildings, motor vehicles and tools (but excluding IT).
Return to Forecast Capex by Category - Table 4.1
Return to Forecast Capex by Asset Class - 4.2
Links to Forecast Capex:
Return to Forecast Capex - Network/Common - Table 4.3.1
Return to Forecast Capex - Network/Varied - Table 4.3.2
Return to Forecast Capex - Non-Networkt - Table 4.4