## Index
Revenue Reset Information Pro Formas
Powerlink pro-forma information statements - 31 May 2011
INDEX | Click on orange box for link to pages
Historic Opex |  | Historic Capex
Table 1.1 | Historic Opex by Category - Summary | Table 3.1 | Historic Capex by Category
1.2 | Historic Opex (Any part year) | 3.2 | Historic Capex by Asset Class
1.3 | Historic Opex 2008 | 3.3 | Historic Capex - Network
1.4 | Historic Opex 2009 | 3.4 | Historic Capex - Non-Network
1.5 | Historic Opex 2010
1.6 | Historic Opex 2011
1.7 | Historic Opex 2012
Forecast Opex |  | Forecast Capex
Table 2.1 | Forecast Opex by Category - Summary | Table 4.1 | Forecast Capex by Category
2.2 | Forecast Opex 2013 | 4.2 | Forecast Capex by Asset Class
2.3 | Forecast Opex 2014 | 4.3 | Forecast Capex - Network
2.4 | Forecast Opex 2015 | 4.4 | Forecast Capex - Non-Network
2.5 | Forecast Opex 2016
2.6 | Forecast Opex 2017
Commentary |  | Instructions/Definitions
Table 5.1 | Commentary on Opex | Table 6.1 | Opex Instructions
5.2 | Commentary on Historic Capex | 6.2 | Historic Capex Instructions
5.3 | Commentary on Forecast Capex | 6.3 | Forecast Capex Instructions
Other matters
Table 7.1 | Weighted Average Cost of Capital | 7.3 | Performance incentive scheme parameters
7.2 | Depreciation | 7.4 | Efficiency Benefit Sharing Scheme parameters

## Historic Opex Summary
Powerlink pro-forma information statements - 31 May 2011
|  |  | Home |  | Opex instructions - Table 6.1 |  |  | Opex Commentary - Table 5.1
1.1 HISTORIC OPEX by expenditure category
| $ million nominal | Financial year | 2007/08 | 2008/09 | 2009/10 | 2010/11 | 2011/12 | Total | Revenue Cap Allowance | Key cost drivers and explanation for material differences over time
Direct Operations & Maintenance
Field Maintenance
Secondary Systems
| Labour |  | 4.76 | 5.2 | 5.26 | 5.6 | 6.39 | 27.21
| Non-Labour |  | 0.31 | 0.34 | 0.38 | 0.4 | 0.42 | 1.84
| Sub-Totals |  | 5.07 | 5.54 | 5.64 | 6 | 6.82 | 29.05
| Substations |  | 0 | 0 | 0 | 0 | 0 | 0
| Labour |  | 8.57 | 11.31 | 13.54 | 14.32 | 16.13 | 63.88
| Non-Labour |  | 2.88 | 3.8 | 4.7 | 4.91 | 5.16 | 21.45
| Sub-Totals |  | 11.45 | 15.12 | 18.24 | 19.23 | 21.29 | 85.33
| Lines |  | 0 | 0 | 0 | 0 | 0 | 0
| Labour |  | 8.17 | 6.7 | 7.42 | 8.08 | 9.04 | 39.4
| Non-Labour |  | 2.03 | 1.67 | 1.9 | 2.04 | 2.16 | 9.79
| Sub-Totals |  | 10.2 | 8.36 | 9.31 | 10.12 | 11.19 | 49.19
| Communications |  | 0 | 0 | 0 | 0 | 0 | 0
| Labour |  | 1.66 | 2.19 | 1.82 | 1.95 | 2.32 | 9.93
| Non-Labour |  | 0.41 | 0.54 | 0.46 | 0.49 | 0.54 | 2.44
| Sub-Totals |  | 2.07 | 2.73 | 2.28 | 2.44 | 2.86 | 12.38
| Land |  | 0 | 0 | 0 | 0 | 0 | 0
| Labour |  | 5.59 | 6.77 | 6.29 | 6.89 | 8.14 | 33.68
| Non-Labour |  | 2.62 | 3.17 | 2.94 | 3.19 | 3.47 | 15.39
| Sub-Totals |  | 8.2 | 9.94 | 9.23 | 10.08 | 11.61 | 49.06
| Summary |  | 0 | 0 | 0 | 0 | 0 | 0
| Sub-Total Labour |  | 28.75 | 32.17 | 34.33 | 36.83 | 42.02 | 174.1
| Sub-Total Non-Labour |  | 8.25 | 9.52 | 10.38 | 11.03 | 11.74 | 50.91
| Total Maintenance |  | 37 | 41.68 | 44.7 | 47.86 | 53.77 | 225.01
| Operational Refurbishment |  | 0 | 0 | 0 | 0 | 0 | 0
| Total Operational Refurbishment |  | 18.61 | 20.25 | 22.19 | 24.42 | 27.04 | 112.51
| Maintenance Support |  | 0 | 0 | 0 | 0 | 0 | 0
| Field Support |  | 1.18 | 1.37 | 1.43 | 1.5 | 1.58 | 7.06
| Other Support |  | 5.57 | 5.34 | 5.36 | 5.64 | 5.92 | 27.84
| Direct charges |  | 3.49 | 3.61 | 4.25 | 4.55 | 4.82 | 20.72
| Total Maintenance Support |  | 10.24 | 10.33 | 11.04 | 11.69 | 12.32 | 55.62
| Network Operations |  | 0 | 0 | 0 | 0 | 0 | 0
| Switching |  | 5.07 | 5.43 | 5.46 | 5.78 | 6.1 | 27.84
| Asset Monitoring Team |  | 1.94 | 1.84 | 2.54 | 2.69 | 2.84 | 11.85
| NMS Support |  | 1.89 | 2.28 | 2.29 | 2.42 | 2.56 | 11.43
| Operations Support |  | 1.47 | 1.93 | 1.9 | 2.01 | 2.12 | 9.43
| Total Network Operations |  | 10.38 | 11.47 | 12.19 | 12.9 | 13.61 | 60.54
| Total Direct Operations & Maintenance |  | 76.23 | 83.73 | 90.12 | 96.87 | 106.73 | 453.69 | 453.18 | No material differences. See section 5.3.2 of the Revenue Proposal
| Other Controllable |  | 0 | 0 | 0 | 0 | 0 | 0
| Asset Management Support |  | 0 | 0 | 0 | 0 | 0 | 0
| Grid Planning |  | 4.22 | 5.51 | 5.33 | 5.62 | 5.89 | 26.58
| Network Support |  | 10.41 | 10.59 | 12.1 | 12.71 | 13.32 | 59.12
| IT Support |  | 7.05 | 8.24 | 8.1 | 8.51 | 8.92 | 40.82
| Customer & Regulatory Support |  | 4.18 | 3.82 | 4.06 | 4.26 | 4.47 | 20.8
| Total Asset Management Support |  | 25.87 | 28.16 | 29.59 | 31.1 | 32.6 | 147.32
| Corporate Support |  | 0 | 0 | 0 | 0 | 0 | 0
| Total Corporate Support |  | 9.07 | 9.66 | 12.71 | 15.1 | 13.79 | 60.33
| Total Other Controllable |  | 34.93 | 37.82 | 42.3 | 46.2 | 46.39 | 207.64 | 204.56
| Total Controllable Operating |  | 111.16 | 121.55 | 132.42 | 143.07 | 153.12 | 661.33 | 657.75 | No material differences. See section 5.3.2 of the Revenue Proposal
| Summary |  | 0 | 0 | 0 | 0 | 0 | 0
| Total Labour |  | 94.23 | 102.63 | 111.67 | 117.3 | 125.93 | 551.75
| Total Maintenance Non-Labour |  | 8.25 | 9.52 | 10.38 | 11.03 | 11.74 | 50.91
| Total Other Non-Labour |  | 8.68 | 9.41 | 10.38 | 14.74 | 15.45 | 58.66
| Other Operating |  | 0 | 0 | 0 | 0 | 0 | 0
| Insurances |  | 5.37 | 5.93 | 6.71 | 7.33 | 7.96 | 33.3
| Network Support |  | 27.3 | 15.1 | 12.7 | 0.2 | 0.4 | 55.7
| Debt Raising |  | 0.2 | 0.2 | 0.3 | 0.2 | 0.3 | 1.2
|  |  | 0 | 0 | 0 | 0 | 0 | 0
| Total Operating Expenditure |  | 144.04 | 142.78 | 152.13 | 150.8 | 161.78 | 751.53 | 787.35 | Network Support requirements influenced by exogenous factors outside
Powerlink's control impacting on the volume of and demand for Network Support.
| Revenue Cap Allowance |  | 143.61 | 147.85 | 163.62 | 161.29 | 170.97 | 787.35

## Hist Opex by Cat. Part Year
Powerlink pro-forma information statements - 31 May 2011
|  | Home |  | Link to Opex instructions - Table 6.1
1.2 HISTORIC OPEX by expenditure category
Any Part Year
Field Maintenance
| $ million, nominal | Routine | Condition-Based | Corrective | TOTAL | Revenue Cap Allowance | Key cost drivers and explanation for material differences over time
System Recurrent
Maintenance
Secondary Systems
Labour
Materials
Sub-Totals
Substations
Labour
Materials
Sub-Totals
Lines
Labour
Materials
Sub-Totals
Communications
Labour
Materials
Sub-Totals
Land
Labour
Materials
Sub-Totals
Summary
Sub-Total Labour
Sub-Total Materials
Total Maintenance
Asset Management Support
Operations
OHS
Taxes and Charges
Insurance
Total System Recurrent
System Non-Recurrent
Asset Works Program
Asset Management Support
Total System Non-Recurrent
Non-System
Finance
HR
IT
Other
Total Non-System
Summary
Total Labour
Total Maintenance Materials
Total Other Materials
TOTAL OPEX
Grand Total
Revenue Cap Allowance
Indicative splits only

## Historic Opex 2008
Powerlink pro-forma information statements - 31 May 2011
|  | Home |  | Opex instructions - Table 6.1
1.3 HISTORIC OPEX by expenditure category
Year Ended 30 June 2008
| ($m, nominal) | Year 1 - Year Ended 30 June 2008
|  | Field Maintenance |  |  | Operational Refurbishment | Maintenance Support | Network Operations | AM Support / Corporate
| $ million, nominal | Routine | Condition-Based | Corrective |  |  |  | Network | Non-Network | TOTAL | Revenue Cap Allowance
Direct Operations & Maintenance
Field Maintenance
Secondary Systems
| Labour | 1.46 | 1.42 | 1.88
| Non-Labour | 0.09 | 0.09 | 0.12
| Sub-Totals | 1.55 | 1.51 | 2 | 0 | 0 | 0 | 0 | 0 | 5.07
Substations
| Labour | 2.86 | 3.37 | 2.34
| Non-Labour | 0.96 | 1.13 | 0.79
| Sub-Totals | 3.82 | 4.5 | 3.13 | 0 | 0 | 0 | 0 | 0 | 11.45
Lines
| Labour | 1.76 | 3.92 | 2.49
| Non-Labour | 0.44 | 0.97 | 0.62
| Sub-Totals | 2.2 | 4.89 | 3.11 | 0 | 0 | 0 | 0 | 0 | 10.2
Communications
| Labour | 0.3 | 0.65 | 0.71
| Non-Labour | 0.07 | 0.16 | 0.18
| Sub-Totals | 0.38 | 0.81 | 0.88 | 0 | 0 | 0 | 0 | 0 | 2.07
Land
| Labour | 3.46 | 2 | 0.13
| Non-Labour | 1.62 | 0.94 | 0.06
| Sub-Totals | 5.08 | 2.93 | 0.19 | 0 | 0 | 0 | 0 | 0 | 8.2
Summary
| Sub-Total Labour | 9.84 | 11.36 | 7.55 | [5 empty] | 28.75
| Sub-Total Non-Labour | 3.19 | 3.3 | 1.76 | [5 empty] | 8.25
| Total Maintenance | 13.03 | 14.66 | 9.31 | [5 empty] | 37
Operational Refurbishment
| Total Operational Refurbishment |  |  |  | 18.61 |  |  |  |  | 18.61
Maintenance Support
| Field Support |  |  |  |  | 1.18
| Other Support |  |  |  |  | 5.57
| Direct charges |  |  |  |  | 3.49
| Total Maintenance Support | 0 | 0 | 0 | 0 | 10.24 | 0 | 0 | 0 | 10.24
Network Operations
| Switching | [5 empty] | 5.07
| Asset Monitoring Team | [5 empty] | 1.94
| NMS Support | [5 empty] | 1.89
| Operations Support | [5 empty] | 1.47
| Total Network Operations | 0 | 0 | 0 | 0 | 0 | 10.38 | 0 | 0 | 10.38
| Total Direct Operations & Maintenance | 13.03 | 14.66 | 9.31 | 18.61 | 10.24 | 10.38 | 0 | 0 | 76.23
Other Controllable
Asset Management Support
| Grid Planning | [6 empty] | 4.22
| Network Support | [6 empty] | 10.41
| IT Support | [6 empty] | 7.05
| Customer & Regulatory Support | [6 empty] | 4.18
| Total Asset Management Support | 0 | 0 | 0 | 0 | 0 | 0 | 25.87 | 0 | 25.87
Corporate Support
| Total Corporate Support | [7 empty] | 9.07 | 9.07
| Total Other Controllable | 0 | 0 | 0 | 0 | 0 | 0 | 25.87 | 9.07 | 34.93
| Total Controllable Operating | 13.03 | 14.66 | 9.31 | 18.61 | 10.24 | 10.38 | 25.87 | 9.07 | 111.16
Summary
| Total Labour | 9.84 | 11.36 | 7.55 | 18.61 | 6.09 | 9.34 | 23.28 | 8.16 | 94.23
| Total Maintenance Non-Labour | 3.19 | 3.3 | 1.76 | [5 empty] | 8.25
| Total Other Non-Labour |  |  |  |  | 4.15 | 1.04 | 2.59 | 0.91 | 8.68
Other Operating
| Insurances | [8 empty] | 5.37
| Network Support | [8 empty] | 27.3
| Debt Raising | [8 empty] | 0.2
| Total Operating Expenditure | [8 empty] | 144.04
| Revenue Cap Allowance | [8 empty] | 143.61

## Historic Opex 2009
Powerlink pro-forma information statements - 31 May 2011
|  | Home |  | Opex instructions - Table 6.1
1.4 HISTORIC OPEX by expenditure category
Year Ended 30 June 2009
| ($m, nominal) | Year 2 - Year Ended 30 June 2009
|  | Field Maintenance |  |  | Operational Refurbishment | Maintenance Support | Network Operations | AM Support / Corporate
| $ million, nominal | Routine | Condition-Based | Corrective |  |  |  | Network | Non-Network | TOTAL | Revenue Cap Allowance
Direct Operations & Maintenance
Field Maintenance
Secondary Systems
| Labour | 1.17 | 1.21 | 2.81
| Non-Labour | 0.08 | 0.08 | 0.18
| Sub-Totals | 1.25 | 1.29 | 3 | 0 | 0 | 0 | 0 | 0 | 5.54
Substations
| Labour | 3.15 | 5.33 | 2.84
| Non-Labour | 1.06 | 1.79 | 0.95
| Sub-Totals | 4.2 | 7.13 | 3.79 | 0 | 0 | 0 | 0 | 0 | 15.12
Lines
| Labour | 1.9 | 3.07 | 1.73
| Non-Labour | 0.47 | 0.76 | 0.43
| Sub-Totals | 2.37 | 3.83 | 2.17 | 0 | 0 | 0 | 0 | 0 | 8.36
Communications
| Labour | 0.34 | 0.6 | 1.25
| Non-Labour | 0.08 | 0.15 | 0.31
| Sub-Totals | 0.42 | 0.75 | 1.56 | 0 | 0 | 0 | 0 | 0 | 2.73
Land
| Labour | 4.29 | 2.4 | 0.08
| Non-Labour | 2.01 | 1.12 | 0.04
| Sub-Totals | 6.29 | 3.53 | 0.12 | 0 | 0 | 0 | 0 | 0 | 9.94
Summary
| Sub-Total Labour | 10.84 | 12.61 | 8.72 | [5 empty] | 32.17
| Sub-Total Non-Labour | 3.69 | 3.91 | 1.91 | [5 empty] | 9.52
| Total Maintenance | 14.53 | 16.52 | 10.63 | [5 empty] | 41.68
Operational Refurbishment
| Total Operational Refurbishment |  |  |  | 20.25 |  |  |  |  | 20.25
Maintenance Support
| Field Support |  |  |  |  | 1.37
| Other Support |  |  |  |  | 5.34
| Direct charges |  |  |  |  | 3.61
| Total Maintenance Support | 0 | 0 | 0 | 0 | 10.33 | 0 | 0 | 0 | 10.33
Network Operations
| Switching | [5 empty] | 5.43
| Asset Monitoring Team | [5 empty] | 1.84
| NMS Support | [5 empty] | 2.28
| Operations Support | [5 empty] | 1.93
| Total Network Operations | 0 | 0 | 0 | 0 | 0 | 11.47 | 0 | 0 | 11.47
| Total Direct Operations & Maintenance | 14.53 | 16.52 | 10.63 | 20.25 | 10.33 | 11.47 | 0 | 0 | 83.73
Other Controllable
Asset Management Support
| Grid Planning | [6 empty] | 5.51
| Network Support | [6 empty] | 10.59
| IT Support | [6 empty] | 8.24
| Customer & Regulatory Support | [6 empty] | 3.82
| Total Asset Management Support | 0 | 0 | 0 | 0 | 0 | 0 | 28.16 | 0 | 28.16
Corporate Support
| Total Corporate Support | [7 empty] | 9.66 | 9.66
| Total Other Controllable | 0 | 0 | 0 | 0 | 0 | 0 | 28.16 | 9.66 | 37.82
| Total Controllable Operating | 14.53 | 16.52 | 10.63 | 20.25 | 10.33 | 11.47 | 28.16 | 9.66 | 121.55
Summary
| Total Labour | 10.84 | 12.61 | 8.72 | 20.25 | 5.85 | 10.32 | 25.35 | 8.69 | 102.63
| Total Maintenance Non-Labour | 3.69 | 3.91 | 1.91 | [5 empty] | 9.52
| Total Other Non-Labour |  |  |  |  | 4.48 | 1.15 | 2.82 | 0.97 | 9.41
Other Operating
| Insurances | [8 empty] | 5.93
| Network Support | [8 empty] | 15.1
| Debt Raising | [8 empty] | 0.2
| Total Operating Expenditure | [8 empty] | 142.78
| Revenue Cap Allowance | [8 empty] | 147.85

## Historic Opex 2010
Powerlink pro-forma information statements - 31 May 2011
|  | Home |  | Opex instructions - Table 6.1
1.5 HISTORIC OPEX by expenditure category
Year Ended 30 June 2010
| ($m, nominal) | Year 3 - Year Ended 30 June 2010
|  | Field Maintenance |  |  | Operational Refurbishment | Maintenance Support | Network Operations | AM Support / Corporate
| $ million, nominal | Routine | Condition-Based | Corrective |  |  |  | Network | Non-Network | TOTAL | Revenue Cap Allowance
Direct Operations & Maintenance
Field Maintenance
Secondary Systems
| Labour | 1.3 | 1.21 | 2.76
| Non-Labour | 0.09 | 0.08 | 0.21
| Sub-Totals | 1.38 | 1.29 | 2.97 | 0 | 0 | 0 | 0 | 0 | 5.64
Substations
| Labour | 2.95 | 6.78 | 3.81
| Non-Labour | 1.01 | 2.38 | 1.3
| Sub-Totals | 3.97 | 9.17 | 5.11 | 0 | 0 | 0 | 0 | 0 | 18.24
Lines
| Labour | 1.92 | 4.16 | 1.34
| Non-Labour | 0.53 | 1.07 | 0.3
| Sub-Totals | 2.45 | 5.23 | 1.63 | 0 | 0 | 0 | 0 | 0 | 9.31
Communications
| Labour | 0.38 | 0.32 | 1.12
| Non-Labour | 0.09 | 0.08 | 0.28
| Sub-Totals | 0.47 | 0.41 | 1.4 | 0 | 0 | 0 | 0 | 0 | 2.28
Land
| Labour | 3.77 | 1.93 | 0.58
| Non-Labour | 1.76 | 0.91 | 0.27
| Sub-Totals | 5.54 | 2.84 | 0.85 | 0 | 0 | 0 | 0 | 0 | 9.23
Summary
| Sub-Total Labour | 10.32 | 14.4 | 9.6 | 0 | 0 | 0 | 0 | 0 | 34.33
| Sub-Total Non-Labour | 3.49 | 4.53 | 2.36 | 0 | 0 | 0 | 0 | 0 | 10.38
| Total Maintenance | 13.81 | 18.93 | 11.96 | 0 | 0 | 0 | 0 | 0 | 44.7
Operational Refurbishment
| Total Operational Refurbishment |  |  |  | 22.19 |  |  |  |  | 22.19
Maintenance Support
| Field Support |  |  |  |  | 1.43
| Other Support |  |  |  |  | 5.36
| Direct charges |  |  |  |  | 4.25
| Total Maintenance Support | 0 | 0 | 0 | 0 | 11.04 | 0 | 0 | 0 | 11.04
Network Operations
| Switching | [5 empty] | 5.46
| Asset Monitoring Team | [5 empty] | 2.54
| NMS Support | [5 empty] | 2.29
| Operations Support | [5 empty] | 1.9
| Total Network Operations | 0 | 0 | 0 | 0 | 0 | 12.19 | 0 | 0 | 12.19
| Total Direct Operations & Maintenance | 13.81 | 18.93 | 11.96 | 22.19 | 11.04 | 12.19 | 0 | 0 | 90.12
Other Controllable
Asset Management Support
| Grid Planning | [6 empty] | 5.33
| Network Support | [6 empty] | 12.1
| IT Support | [6 empty] | 8.1
| Customer & Regulatory Support | [6 empty] | 4.06
| Total Asset Management Support | 0 | 0 | 0 | 0 | 0 | 0 | 29.59 | 0 | 29.59
Corporate Support
| Total Corporate Support | [7 empty] | 12.71 | 12.71
| Total Other Controllable | 0 | 0 | 0 | 0 | 0 | 0 | 29.59 | 12.71 | 42.3
| Total Controllable Operating | 13.81 | 18.93 | 11.96 | 22.19 | 11.04 | 12.19 | 29.59 | 12.71 | 132.42
Summary
| Total Labour | 10.32 | 14.4 | 9.6 | 22.19 | 6.11 | 10.97 | 26.63 | 11.44 | 111.67
| Total Maintenance Non-Labour | 3.49 | 4.53 | 2.36 | [5 empty] | 10.38
| Total Other Non-Labour |  |  |  |  | 4.93 | 1.22 | 2.96 | 1.27 | 10.38
Other Operating
| Insurances | [8 empty] | 6.71
| Network Support | [8 empty] | 12.7
| Debt Raising | [8 empty] | 0.3
| Total Operating Expenditure | [8 empty] | 152.13
| Revenue Cap Allowance | [8 empty] | 163.62

## Historic Opex 2011
Powerlink pro-forma information statements - 31 May 2011
|  | Home |  | Opex instructions - Table 6.1
1.6 HISTORIC OPEX by expenditure category
Year Ended 30 June 2011
| ($m, nominal) | Year 4 - Year Ended 30 June 2011
|  | Field Maintenance |  |  | Operational Refurbishment | Maintenance Support | Network Operations | AM Support / Corporate
| $ million, nominal | Routine | Condition-Based | Corrective |  |  |  | Network | Non-Network | TOTAL | Revenue Cap Allowance
Direct Operations & Maintenance
Field Maintenance
Secondary Systems
| Labour | 1.38 | 1.28 | 2.93
| Non-Labour | 0.09 | 0.09 | 0.22
| Sub-Totals | 1.47 | 1.37 | 3.15 | 0 | 0 | 0 | 0 | 0 | 6
Substations
| Labour | 3.12 | 7.17 | 4.03
| Non-Labour | 1.06 | 2.49 | 1.36
| Sub-Totals | 4.18 | 9.66 | 5.39 | 0 | 0 | 0 | 0 | 0 | 19.23
Lines
| Labour | 2.08 | 4.53 | 1.46
| Non-Labour | 0.57 | 1.15 | 0.32
| Sub-Totals | 2.65 | 5.69 | 1.78 | 0 | 0 | 0 | 0 | 0 | 10.12
Communications
| Labour | 0.4 | 0.34 | 1.2
| Non-Labour | 0.1 | 0.09 | 0.3
| Sub-Totals | 0.51 | 0.43 | 1.5 | 0 | 0 | 0 | 0 | 0 | 2.44
Land
| Labour | 4.13 | 2.12 | 0.64
| Non-Labour | 1.91 | 0.98 | 0.29
| Sub-Totals | 6.05 | 3.1 | 0.93 | 0 | 0 | 0 | 0 | 0 | 10.08
Summary
| Sub-Total Labour | 11.13 | 15.45 | 10.25 | 0 | 0 | 0 | 0 | 0 | 36.83
| Sub-Total Non-Labour | 3.73 | 4.8 | 2.5 | 0 | 0 | 0 | 0 | 0 | 11.03
| Total Maintenance | 14.85 | 20.26 | 12.75 | 0 | 0 | 0 | 0 | 0 | 47.86
Operational Refurbishment
| Total Operational Refurbishment |  |  |  | 24.42 |  |  |  |  | 24.42
Maintenance Support
| Field Support |  |  |  |  | 1.5
| Other Support |  |  |  |  | 5.64
| Direct charges |  |  |  |  | 4.55
| Total Maintenance Support | 0 | 0 | 0 | 0 | 11.69 | 0 | 0 | 0 | 11.69
Network Operations
| Switching | [5 empty] | 5.78
| Asset Monitoring Team | [5 empty] | 2.69
| NMS Support | [5 empty] | 2.42
| Operations Support | [5 empty] | 2.01
| Total Network Operations | 0 | 0 | 0 | 0 | 0 | 12.9 | 0 | 0 | 12.9
| Total Direct Operations & Maintenance | 14.85 | 20.26 | 12.75 | 24.42 | 11.69 | 12.9 | 0 | 0 | 96.87
Other Controllable
Asset Management Support
| Grid Planning | [6 empty] | 5.62
| Network Support | [6 empty] | 12.71
| IT Support | [6 empty] | 8.51
| Customer & Regulatory Support | [6 empty] | 4.26
| Total Asset Management Support | 0 | 0 | 0 | 0 | 0 | 0 | 31.1 | 0 | 31.1
Corporate Support
| Total Corporate Support | [7 empty] | 15.1 | 15.1
| Total Other Controllable | 0 | 0 | 0 | 0 | 0 | 0 | 31.1 | 15.1 | 46.2
| Total Controllable Operating | 14.85 | 20.26 | 12.75 | 24.42 | 11.69 | 12.9 | 31.1 | 15.1 | 143.07
Summary
| Total Labour | 11.13 | 15.45 | 10.25 | 24.42 | 6.44 | 11.62 | 28.03 | 9.97 | 117.3
| Total Maintenance Non-Labour | 3.73 | 4.8 | 2.5 | [5 empty] | 11.03
| Total Other Non-Labour |  |  |  |  | 5.25 | 1.28 | 3.08 | 5.13 | 14.74
Other Operating
| Insurances | [8 empty] | 7.33
| Network Support | [8 empty] | 0.2
| Debt Raising | [8 empty] | 0.2
| Total Operating Expenditure | [8 empty] | 150.8
| Revenue Cap Allowance | [8 empty] | 161.29

## Historic Opex 2012
Powerlink pro-forma information statements - 31 May 2011
|  | Home |  | Opex instructions - Table 6.1
1.7 HISTORIC OPEX by expenditure category
Year Ended 30 June 2012
| ($m, nominal) | Year 5 - Year Ended 30 June 2012
|  | Field Maintenance |  |  | Operational Refurbishment | Maintenance Support | Network Operations | AM Support / Corporate
| $ million, nominal | Routine | Condition-Based | Corrective |  |  |  | Network | Non-Network | TOTAL | Revenue Cap Allowance
Direct Operations & Maintenance
Field Maintenance
Secondary Systems
| Labour | 1.6 | 1.47 | 3.32
| Non-Labour | 0.1 | 0.09 | 0.23
| Sub-Totals | 1.7 | 1.56 | 3.55 | 0 | 0 | 0 | 0 | 0 | 6.82
Substations
| Labour | 3.53 | 8.04 | 4.57
| Non-Labour | 1.11 | 2.62 | 1.43
| Sub-Totals | 4.64 | 10.65 | 5.99 | 0 | 0 | 0 | 0 | 0 | 21.29
Lines
| Labour | 2.33 | 5.05 | 1.65
| Non-Labour | 0.6 | 1.22 | 0.34
| Sub-Totals | 2.93 | 6.28 | 1.99 | 0 | 0 | 0 | 0 | 0 | 11.19
Communications
| Labour | 0.48 | 0.41 | 1.43
| Non-Labour | 0.11 | 0.1 | 0.33
| Sub-Totals | 0.59 | 0.51 | 1.76 | 0 | 0 | 0 | 0 | 0 | 2.86
Land
| Labour | 4.92 | 2.5 | 0.72
| Non-Labour | 2.08 | 1.07 | 0.32
| Sub-Totals | 7 | 3.57 | 1.04 | 0 | 0 | 0 | 0 | 0 | 11.61
Summary
| Sub-Total Labour | 12.86 | 17.47 | 11.69 | 0 | 0 | 0 | 0 | 0 | 42.02
| Sub-Total Non-Labour | 4 | 5.1 | 2.65 | 0 | 0 | 0 | 0 | 0 | 11.74
| Total Maintenance | 16.85 | 22.57 | 14.34 | 0 | 0 | 0 | 0 | 0 | 53.77
Operational Refurbishment
| Total Operational Refurbishment |  |  |  | 27.04 |  |  |  |  | 27.04
Maintenance Support
| Field Support |  |  |  |  | 1.58
| Other Support |  |  |  |  | 5.92
| Direct charges |  |  |  |  | 4.82
| Total Maintenance Support | 0 | 0 | 0 | 0 | 12.32 | 0 | 0 | 0 | 12.32
Network Operations
| Switching | [5 empty] | 6.1
| Asset Monitoring Team | [5 empty] | 2.84
| NMS Support | [5 empty] | 2.56
| Operations Support | [5 empty] | 2.12
| Total Network Operations | 0 | 0 | 0 | 0 | 0 | 13.61 | 0 | 0 | 13.61
| Total Direct Operations & Maintenance | 16.85 | 22.57 | 14.34 | 27.04 | 12.32 | 13.61 | 0 | 0 | 106.73
Other Controllable
Asset Management Support
| Grid Planning | [6 empty] | 5.89
| Network Support | [6 empty] | 13.32
| IT Support | [6 empty] | 8.92
| Customer & Regulatory Support | [6 empty] | 4.47
| Total Asset Management Support | 0 | 0 | 0 | 0 | 0 | 0 | 32.6 | 0 | 32.6
Corporate Support
| Total Corporate Support | [7 empty] | 13.79 | 13.79
| Total Other Controllable | 0 | 0 | 0 | 0 | 0 | 0 | 32.6 | 13.79 | 46.39
| Total Controllable Operating | 16.85 | 22.57 | 14.34 | 27.04 | 12.32 | 13.61 | 32.6 | 13.79 | 153.12
Summary
| Total Labour | 12.86 | 17.47 | 11.69 | 27.04 | 6.77 | 12.28 | 29.42 | 8.4 | 125.93
| Total Maintenance Non-Labour | 4 | 5.1 | 2.65 | [5 empty] | 11.74
| Total Other Non-Labour |  |  |  |  | 5.55 | 1.33 | 3.18 | 5.39 | 15.45
Other Operating
| Insurances | [8 empty] | 7.96
| Network Support | [8 empty] | 0.4
| Debt Raising | [8 empty] | 0.3
| Total Operating Expenditure | [8 empty] | 161.78
| Revenue Cap Allowance | [8 empty] | 170.97

## Forecast Opex Summary
Powerlink pro-forma information statements - 31 May 2011
|  |  | Home |  | Opex instructions - Table 6.1 |  |  | Opex Commentary - Table 5.1
2.1 FORECAST OPEX by expenditure category
| $ million, Real (2011/12) | Financial year | 2012/13 | 2013/14 | 2014/15 | 2015/16 | 2016/17 | Total | Key cost drivers and explanation for material differences over time
Direct Operations & Maintenance
Field Maintenance
Secondary Systems
| Labour |  | 6.85 | 7.35 | 7.93 | 8.47 | 9.06 | 39.66 | Key cost drivers and other factors are detailed in Section 9.6 of the Revenue Proposal
| Non-Labour |  | 0.44 | 0.46 | 0.49 | 0.51 | 0.53 | 2.43
| Sub-Totals |  | 7.29 | 7.82 | 8.42 | 8.98 | 9.59 | 42.09
Substations
| Labour |  | 17.23 | 18.19 | 19.13 | 20 | 21.12 | 95.67
| Non-Labour |  | 5.5 | 5.65 | 5.78 | 5.89 | 6.07 | 28.88
| Sub-Totals |  | 22.72 | 23.84 | 24.91 | 25.89 | 27.19 | 124.55
Lines
| Labour |  | 9.7 | 10.32 | 11.46 | 11.93 | 12.7 | 56.11
| Non-Labour |  | 2.29 | 2.37 | 2.55 | 2.59 | 2.69 | 12.49
| Sub-Totals |  | 11.98 | 12.69 | 14.01 | 14.52 | 15.39 | 68.6
Communications
| Labour |  | 2.72 | 3.02 | 3.23 | 3.5 | 3.78 | 16.26
| Non-Labour |  | 0.62 | 0.67 | 0.7 | 0.74 | 0.78 | 3.5
| Sub-Totals |  | 3.34 | 3.69 | 3.93 | 4.23 | 4.56 | 19.75
Land
| Labour |  | 8.7 | 9.05 | 9.97 | 10.96 | 12.02 | 50.69
| Non-Labour |  | 3.64 | 3.69 | 3.96 | 4.24 | 4.54 | 20.06
| Sub-Totals |  | 12.34 | 12.74 | 13.93 | 15.19 | 16.56 | 70.75
Summary
| Sub-Total Labour |  | 45.2 | 47.94 | 51.72 | 54.86 | 58.68 | 258.39
| Sub-Total Non-Labour |  | 12.48 | 12.84 | 13.47 | 13.96 | 14.6 | 67.36
| Total Maintenance |  | 57.68 | 60.78 | 65.19 | 68.82 | 73.28 | 325.75
Operational Refurbishment
| Total Operational Refurbishment |  | 34.75 | 35.61 | 34.05 | 35.32 | 39.76 | 179.49
Maintenance Support
| Field Support |  | 1.63 | 1.68 | 1.76 | 1.81 | 1.88 | 8.75
| Other Support |  | 6.11 | 6.33 | 6.61 | 6.81 | 7.06 | 32.91
| Direct charges |  | 5.07 | 5.26 | 5.6 | 5.73 | 5.97 | 27.62
| Total Maintenance Support |  | 12.8 | 13.27 | 13.96 | 14.35 | 14.9 | 69.29
Network Operations
| Switching |  | 6.34 | 6.6 | 6.96 | 7.2 | 7.51 | 34.61
| Asset Monitoring Team |  | 2.95 | 3.07 | 3.24 | 3.35 | 3.5 | 16.1
| NMS Support |  | 2.66 | 2.77 | 2.92 | 3.02 | 3.15 | 14.52
| Operations Support |  | 2.2 | 2.29 | 2.42 | 2.5 | 2.61 | 12.03
| Total Network Operations |  | 14.15 | 14.73 | 15.54 | 16.07 | 16.77 | 77.26
| Total Direct Operations & Maintenance |  | 119.38 | 124.39 | 128.75 | 134.56 | 144.71 | 651.79
Other Controllable
Asset Management Support
| Grid Planning |  | 6.08 | 6.29 | 6.57 | 6.77 | 7.02 | 32.74
| Network Support |  | 13.71 | 14.16 | 14.74 | 15.17 | 15.69 | 73.47
| IT Support |  | 9.18 | 9.48 | 9.87 | 10.15 | 10.5 | 49.17
| Customer & Regulatory Support |  | 4.6 | 4.75 | 4.94 | 5.09 | 5.26 | 24.64
| Total Asset Management Support |  | 33.56 | 34.69 | 36.12 | 37.18 | 38.46 | 180.02
Corporate Support
| Total Corporate Support |  | 14.83 | 15.79 | 18.43 | 21.43 | 20.38 | 90.86
| Total Other Controllable |  | 48.39 | 50.47 | 54.56 | 58.62 | 58.84 | 270.88
| Total Controllable Operating |  | 167.78 | 174.87 | 183.3 | 193.17 | 203.55 | 922.67
Summary
| Total Labour |  | 137.68 | 143.45 | 150.35 | 158.45 | 166.9 | 756.83
| Total Maintenance Non-Labour |  | 12.48 | 12.84 | 13.47 | 13.96 | 14.6 | 67.36
| Total Other Non-Labour |  | 17.61 | 18.58 | 19.48 | 20.76 | 22.05 | 98.48
Other Operating
| Insurances |  | 8.88 | 9.43 | 10.06 | 10.73 | 11.44 | 50.54
| Network Support |  | 1.2 | 0.8 | 1.2 | 2.9 | 2.2 | 8.3
| Debt Raising |  | 3.48 | 3.81 | 4.14 | 4.33 | 4.52 | 20.27
| Total Operating Expenditure |  | 181.34 | 188.91 | 198.7 | 211.13 | 221.7 | 1001.78

## Forecast Opex 2013
Powerlink pro-forma information statements - 31 May 2011
|  | Home |  | Opex instructions - Table 6.1
2.2 FORECAST OPEX by expenditure category
Year Ended 30 June 2013
Year 6 - Year Ended 30 June 2013
|  | Field Maintenance |  |  | Operational Refurbishment | Maintenance Support | Network Operations | AM Support / Corporate
| $ million, Real (2011/12) | Routine | Condition-Based | Corrective |  |  |  | Network | Non-Network | TOTAL | Revenue Cap Allowance
Direct Operations & Maintenance
Field Maintenance
Secondary Systems
| Labour | 1.72 | 1.57 | 3.55
| Non-Labour | 0.1 | 0.1 | 0.24
| Sub-Totals | 1.82 | 1.67 | 3.8 | 0 | 0 | 0 | 0 | 0 | 7.29
Substations
| Labour | 3.77 | 8.58 | 4.88
| Non-Labour | 1.26 | 2.74 | 1.5
| Sub-Totals | 5.03 | 11.33 | 6.37 | 0 | 0 | 0 | 0 | 0 | 22.72
Lines
| Labour | 2.47 | 5.47 | 1.76
| Non-Labour | 0.62 | 1.31 | 0.35
| Sub-Totals | 3.09 | 6.78 | 2.11 | 0 | 0 | 0 | 0 | 0 | 11.98
Communications
| Labour | 0.56 | 0.48 | 1.68
| Non-Labour | 0.13 | 0.11 | 0.38
| Sub-Totals | 0.68 | 0.6 | 2.06 | 0 | 0 | 0 | 0 | 0 | 3.34
Land
| Labour | 5.26 | 2.67 | 0.77
| Non-Labour | 2.18 | 1.12 | 0.34
| Sub-Totals | 7.44 | 3.79 | 1.11 | 0 | 0 | 0 | 0 | 0 | 12.34
Summary
| Sub-Total Labour | 13.78 | 18.78 | 12.64 | 0 | 0 | 0 | 0 | 0 | 45.2
| Sub-Total Non-Labour | 4.28 | 5.39 | 2.81 | 0 | 0 | 0 | 0 | 0 | 12.48
| Total Maintenance | 18.06 | 24.16 | 15.45 | 0 | 0 | 0 | 0 | 0 | 57.68
Operational Refurbishment
| Total Operational Refurbishment |  |  |  | 34.75 |  |  |  |  | 34.75
Maintenance Support
| Field Support |  |  |  |  | 1.63
| Other Support |  |  |  |  | 6.11
| Direct charges |  |  |  |  | 5.07
| Total Maintenance Support | 0 | 0 | 0 | 0 | 12.8 | 0 | 0 | 0 | 12.8
Network Operations
| Switching | [5 empty] | 6.34
| Asset Monitoring Team | [5 empty] | 2.95
| NMS Support | [5 empty] | 2.66
| Operations Support | [5 empty] | 2.2
| Total Network Operations | 0 | 0 | 0 | 0 | 0 | 14.15 | 0 | 0 | 14.15
| Total Direct Operations & Maintenance | 18.06 | 24.16 | 15.45 | 34.75 | 12.8 | 14.15 | 0 | 0 | 119.38
Other Controllable
Asset Management Support
| Grid Planning | [6 empty] | 6.08
| Network Support | [6 empty] | 13.71
| IT Support | [6 empty] | 9.18
| Customer & Regulatory Support | [6 empty] | 4.6
| Total Asset Management Support | 0 | 0 | 0 | 0 | 0 | 0 | 33.56 | 0 | 33.56
Corporate Support
| Total Corporate Support | [7 empty] | 14.83 | 14.83
| Total Other Controllable | 0 | 0 | 0 | 0 | 0 | 0 | 33.56 | 14.83 | 48.39
| Total Controllable Operating | 18.06 | 24.16 | 15.45 | 34.75 | 12.8 | 14.15 | 33.56 | 14.83 | 167.78
Summary
| Total Labour | 13.78 | 18.78 | 12.64 | 34.75 | 7 | 12.79 | 30.35 | 7.6 | 137.68
| Total Maintenance Non-Labour | 4.28 | 5.39 | 2.81 | [5 empty] | 12.48
| Total Other Non-Labour |  |  |  |  | 5.81 | 1.36 | 3.22 | 7.23 | 17.61
Other Operating
| Insurances | [8 empty] | 8.88
| Network Support | [8 empty] | 1.2
| Debt Raising | [8 empty] | 3.48
| Total Operating Expenditure | [8 empty] | 181.34

## Forecast Opex 2014
Powerlink pro-forma information statements - 31 May 2011
|  | Home |  | Opex instructions - Table 6.1
2.3 FORECAST OPEX by expenditure category
Year Ended 30 June 2014
Year 7 - Year Ended 30 June 2014
|  | Field Maintenance |  |  | Operational Refurbishment | Maintenance Support | Network Operations | AM Support / Corporate
| $ million, Real (2011/12) | Routine | Condition-Based | Corrective |  |  |  | Network | Non-Network | TOTAL | Revenue Cap Allowance
Direct Operations & Maintenance
Field Maintenance
Secondary Systems
| Labour | 1.85 | 1.69 | 3.81
| Non-Labour | 0.11 | 0.1 | 0.26
| Sub-Totals | 1.96 | 1.79 | 4.07 | 0 | 0 | 0 | 0 | 0 | 7.82
Substations
| Labour | 3.98 | 9.06 | 5.15
| Non-Labour | 1.29 | 2.82 | 1.54
| Sub-Totals | 5.27 | 11.88 | 6.69 | 0 | 0 | 0 | 0 | 0 | 23.84
Lines
| Labour | 2.62 | 5.82 | 1.88
| Non-Labour | 0.64 | 1.36 | 0.37
| Sub-Totals | 3.26 | 7.19 | 2.25 | 0 | 0 | 0 | 0 | 0 | 12.69
Communications
| Labour | 0.62 | 0.54 | 1.87
| Non-Labour | 0.14 | 0.12 | 0.41
| Sub-Totals | 0.75 | 0.66 | 2.28 | 0 | 0 | 0 | 0 | 0 | 3.69
Land
| Labour | 5.47 | 2.78 | 0.8
| Non-Labour | 2.21 | 1.14 | 0.34
| Sub-Totals | 7.69 | 3.91 | 1.14 | 0 | 0 | 0 | 0 | 0 | 12.74
Summary
| Sub-Total Labour | 14.54 | 19.89 | 13.51 | 0 | 0 | 0 | 0 | 0 | 47.94
| Sub-Total Non-Labour | 4.38 | 5.54 | 2.91 | 0 | 0 | 0 | 0 | 0 | 12.84
| Total Maintenance | 18.93 | 25.43 | 16.42 | 0 | 0 | 0 | 0 | 0 | 60.78
Operational Refurbishment
| Total Operational Refurbishment |  |  |  | 35.61 |  |  |  |  | 35.61
Maintenance Support
| Field Support |  |  |  |  | 1.68
| Other Support |  |  |  |  | 6.33
| Direct charges |  |  |  |  | 5.26
| Total Maintenance Support | 0 | 0 | 0 | 0 | 13.27 | 0 | 0 | 0 | 13.27
Network Operations
| Switching | [5 empty] | 6.6
| Asset Monitoring Team | [5 empty] | 3.07
| NMS Support | [5 empty] | 2.77
| Operations Support | [5 empty] | 2.29
| Total Network Operations | 0 | 0 | 0 | 0 | 0 | 14.73 | 0 | 0 | 14.73
| Total Direct Operations & Maintenance | 18.93 | 25.43 | 16.42 | 35.61 | 13.27 | 14.73 | 0 | 0 | 124.39
Other Controllable
Asset Management Support
| Grid Planning | [6 empty] | 6.29
| Network Support | [6 empty] | 14.16
| IT Support | [6 empty] | 9.48
| Customer & Regulatory Support | [6 empty] | 4.75
| Total Asset Management Support | 0 | 0 | 0 | 0 | 0 | 0 | 34.69 | 0 | 34.69
Corporate Support
| Total Corporate Support | [7 empty] | 15.79 | 15.79
| Total Other Controllable | 0 | 0 | 0 | 0 | 0 | 0 | 34.69 | 15.79 | 50.47
| Total Controllable Operating | 18.93 | 25.43 | 16.42 | 35.61 | 13.27 | 14.73 | 34.69 | 15.79 | 174.87
Summary
| Total Labour | 14.54 | 19.89 | 13.51 | 35.61 | 7.26 | 13.35 | 31.44 | 7.84 | 143.45
| Total Maintenance Non-Labour | 4.38 | 5.54 | 2.91 | [5 empty] | 12.84
| Total Other Non-Labour |  |  |  |  | 6.01 | 1.38 | 3.24 | 7.95 | 18.58
Other Operating
| Insurances | [8 empty] | 9.43
| Network Support | [8 empty] | 0.8
| Debt Raising | [8 empty] | 3.81
| Total Operating Expenditure | [8 empty] | 188.91

## Forecast Opex 2015
Powerlink pro-forma information statements - 31 May 2011
|  | Home |  | Opex instructions - Table 6.1
2.4 FORECAST OPEX by expenditure category
Year Ended 30 June 2015
Year 8 - Year Ended 30 June 2015
|  | Field Maintenance |  |  | Operational Refurbishment | Maintenance Support | Network Operations | AM Support / Corporate
| $ million, Real (2011/12) | Routine | Condition-Based | Corrective |  |  |  | Network | Non-Network | TOTAL | Revenue Cap Allowance
Direct Operations & Maintenance
Field Maintenance
Secondary Systems
| Labour | 2 | 1.82 | 4.11
| Non-Labour | 0.11 | 0.11 | 0.27
| Sub-Totals | 2.11 | 1.93 | 4.38 | 0 | 0 | 0 | 0 | 0 | 8.42
Substations
| Labour | 4.19 | 9.53 | 5.41
| Non-Labour | 1.32 | 2.88 | 1.58
| Sub-Totals | 5.51 | 12.41 | 6.99 | 0 | 0 | 0 | 0 | 0 | 24.91
Lines
| Labour | 2.89 | 6.48 | 2.09
| Non-Labour | 0.68 | 1.47 | 0.4
| Sub-Totals | 3.58 | 7.95 | 2.49 | 0 | 0 | 0 | 0 | 0 | 14.01
Communications
| Labour | 0.66 | 0.58 | 2
| Non-Labour | 0.14 | 0.13 | 0.43
| Sub-Totals | 0.8 | 0.7 | 2.43 | 0 | 0 | 0 | 0 | 0 | 3.93
Land
| Labour | 6.03 | 3.06 | 0.88
| Non-Labour | 2.37 | 1.22 | 0.37
| Sub-Totals | 8.4 | 4.28 | 1.25 | 0 | 0 | 0 | 0 | 0 | 13.93
Summary
| Sub-Total Labour | 15.77 | 21.46 | 14.49 | 0 | 0 | 0 | 0 | 0 | 51.72
| Sub-Total Non-Labour | 4.63 | 5.81 | 3.03 | 0 | 0 | 0 | 0 | 0 | 13.47
| Total Maintenance | 20.4 | 27.27 | 17.53 | 0 | 0 | 0 | 0 | 0 | 65.19
Operational Refurbishment
| Total Operational Refurbishment |  |  |  | 34.05 |  |  |  |  | 34.05
Maintenance Support
| Field Support |  |  |  |  | 1.76
| Other Support |  |  |  |  | 6.61
| Direct charges |  |  |  |  | 5.6
| Total Maintenance Support | 0 | 0 | 0 | 0 | 13.96 | 0 | 0 | 0 | 13.96
Network Operations
| Switching | [5 empty] | 6.96
| Asset Monitoring Team | [5 empty] | 3.24
| NMS Support | [5 empty] | 2.92
| Operations Support | [5 empty] | 2.42
| Total Network Operations | 0 | 0 | 0 | 0 | 0 | 15.54 | 0 | 0 | 15.54
| Total Direct Operations & Maintenance | 20.4 | 27.27 | 17.53 | 34.05 | 13.96 | 15.54 | 0 | 0 | 128.75
Other Controllable
Asset Management Support
| Grid Planning | [6 empty] | 6.57
| Network Support | [6 empty] | 14.74
| IT Support | [6 empty] | 9.87
| Customer & Regulatory Support | [6 empty] | 4.94
| Total Asset Management Support | 0 | 0 | 0 | 0 | 0 | 0 | 36.12 | 0 | 36.12
Corporate Support
| Total Corporate Support | [7 empty] | 18.43 | 18.43
| Total Other Controllable | 0 | 0 | 0 | 0 | 0 | 0 | 36.12 | 18.43 | 54.56
| Total Controllable Operating | 20.4 | 27.27 | 17.53 | 34.05 | 13.96 | 15.54 | 36.12 | 18.43 | 183.3
Summary
| Total Labour | 15.77 | 21.46 | 14.49 | 34.05 | 7.6 | 14.12 | 32.83 | 10.02 | 150.35
| Total Maintenance Non-Labour | 4.63 | 5.81 | 3.03 | [5 empty] | 13.47
| Total Other Non-Labour |  |  |  |  | 6.36 | 1.42 | 3.29 | 8.41 | 19.48
Other Operating
| Insurances | [8 empty] | 10.06
| Network Support | [8 empty] | 1.2
| Debt Raising | [8 empty] | 4.14
| Total Operating Expenditure | [8 empty] | 198.7

## Forecast Opex 2016
Powerlink pro-forma information statements - 31 May 2011
|  | Home |  | Opex instructions - Table 6.1
2.5 FORECAST OPEX by expenditure category
Year Ended 30 June 2016
Year 9 - Year Ended 30 June 2016
|  | Field Maintenance |  |  | Operational Refurbishment | Maintenance Support | Network Operations | AM Support / Corporate
| $ million, Real (2011/12) | Routine | Condition-Based | Corrective |  |  |  | Network | Non-Network | TOTAL | Revenue Cap Allowance
Direct Operations & Maintenance
Field Maintenance
Secondary Systems
| Labour | 2.14 | 1.94 | 4.39
| Non-Labour | 0.12 | 0.11 | 0.28
| Sub-Totals | 2.26 | 2.05 | 4.67 | 0 | 0 | 0 | 0 | 0 | 8.98
Substations
| Labour | 4.38 | 9.96 | 5.66
| Non-Labour | 1.34 | 2.94 | 1.61
| Sub-Totals | 5.72 | 12.9 | 7.26 | 0 | 0 | 0 | 0 | 0 | 25.89
Lines
| Labour | 3.01 | 6.74 | 2.18
| Non-Labour | 0.69 | 1.5 | 0.4
| Sub-Totals | 3.7 | 8.24 | 2.58 | 0 | 0 | 0 | 0 | 0 | 14.52
Communications
| Labour | 0.71 | 0.62 | 2.16
| Non-Labour | 0.15 | 0.13 | 0.45
| Sub-Totals | 0.86 | 0.76 | 2.62 | 0 | 0 | 0 | 0 | 0 | 4.23
Land
| Labour | 6.62 | 3.36 | 0.97
| Non-Labour | 2.54 | 1.3 | 0.39
| Sub-Totals | 9.17 | 4.67 | 1.36 | 0 | 0 | 0 | 0 | 0 | 15.19
Summary
| Sub-Total Labour | 16.87 | 22.63 | 15.36 | 0 | 0 | 0 | 0 | 0 | 54.86
| Sub-Total Non-Labour | 4.84 | 5.99 | 3.13 | 0 | 0 | 0 | 0 | 0 | 13.96
| Total Maintenance | 21.71 | 28.62 | 18.49 | 0 | 0 | 0 | 0 | 0 | 68.82
Operational Refurbishment
| Total Operational Refurbishment |  |  |  | 35.32 |  |  |  |  | 35.32
Maintenance Support
| Field Support |  |  |  |  | 1.81
| Other Support |  |  |  |  | 6.81
| Direct charges |  |  |  |  | 5.73
| Total Maintenance Support | 0 | 0 | 0 | 0 | 14.35 | 0 | 0 | 0 | 14.35
Network Operations
| Switching | [5 empty] | 7.2
| Asset Monitoring Team | [5 empty] | 3.35
| NMS Support | [5 empty] | 3.02
| Operations Support | [5 empty] | 2.5
| Total Network Operations | 0 | 0 | 0 | 0 | 0 | 16.07 | 0 | 0 | 16.07
| Total Direct Operations & Maintenance | 21.71 | 28.62 | 18.49 | 35.32 | 14.35 | 16.07 | 0 | 0 | 134.56
Other Controllable
Asset Management Support
| Grid Planning | [6 empty] | 6.77
| Network Support | [6 empty] | 15.17
| IT Support | [6 empty] | 10.15
| Customer & Regulatory Support | [6 empty] | 5.09
| Total Asset Management Support | 0 | 0 | 0 | 0 | 0 | 0 | 37.18 | 0 | 37.18
Corporate Support
| Total Corporate Support | [7 empty] | 21.43 | 21.43
| Total Other Controllable | 0 | 0 | 0 | 0 | 0 | 0 | 37.18 | 21.43 | 58.62
| Total Controllable Operating | 21.71 | 28.62 | 18.49 | 35.32 | 14.35 | 16.07 | 37.18 | 21.43 | 193.17
Summary
| Total Labour | 16.87 | 22.63 | 15.36 | 35.32 | 7.85 | 14.64 | 33.87 | 11.91 | 158.45
| Total Maintenance Non-Labour | 4.84 | 5.99 | 3.13 | [5 empty] | 13.96
| Total Other Non-Labour |  |  |  |  | 6.5 | 1.43 | 3.31 | 9.52 | 20.76
Other Operating
| Insurances | [8 empty] | 10.73
| Network Support | [8 empty] | 2.9
| Debt Raising | [8 empty] | 4.33
| Total Operating Expenditure | [8 empty] | 211.13

## Forecast Opex 2017
Powerlink pro-forma information statements - 31 May 2011
|  | Home |  | Opex instructions - Table 6.1
2.6 FORECAST OPEX by expenditure category
Year Ended 30 June 2017
Year 10 - Year Ended 30 June 2017
|  | Field Maintenance |  |  | Operational Refurbishment | Maintenance Support | Network Operations | AM Support / Corporate
| $ million, Real (2011/12) | Routine | Condition-Based | Corrective |  |  |  | Network | Non-Network | TOTAL | Revenue Cap Allowance
Direct Operations & Maintenance
Field Maintenance
Secondary Systems
| Labour | 2.29 | 2.07 | 4.69
| Non-Labour | 0.12 | 0.12 | 0.29
| Sub-Totals | 2.42 | 2.19 | 4.98 | 0 | 0 | 0 | 0 | 0 | 9.59
Substations
| Labour | 4.63 | 10.52 | 5.98
| Non-Labour | 1.38 | 3.03 | 1.65
| Sub-Totals | 6.01 | 13.55 | 7.63 | 0 | 0 | 0 | 0 | 0 | 27.19
Lines
| Labour | 3.19 | 7.18 | 2.32
| Non-Labour | 0.71 | 1.56 | 0.42
| Sub-Totals | 3.91 | 8.74 | 2.74 | 0 | 0 | 0 | 0 | 0 | 15.39
Communications
| Labour | 0.77 | 0.67 | 2.34
| Non-Labour | 0.16 | 0.14 | 0.48
| Sub-Totals | 0.93 | 0.81 | 2.82 | 0 | 0 | 0 | 0 | 0 | 4.56
Land
| Labour | 7.27 | 3.69 | 1.06
| Non-Labour | 2.72 | 1.4 | 0.42
| Sub-Totals | 9.99 | 5.08 | 1.48 | 0 | 0 | 0 | 0 | 0 | 16.56
Summary
| Sub-Total Labour | 18.15 | 24.14 | 16.39 | 0 | 0 | 0 | 0 | 0 | 58.68
| Sub-Total Non-Labour | 5.1 | 6.24 | 3.26 | 0 | 0 | 0 | 0 | 0 | 14.6
| Total Maintenance | 23.25 | 30.38 | 19.65 | 0 | 0 | 0 | 0 | 0 | 73.28
Operational Refurbishment
| Total Operational Refurbishment |  |  |  | 39.76 |  |  |  |  | 39.76
Maintenance Support
| Field Support |  |  |  |  | 1.88
| Other Support |  |  |  |  | 7.06
| Direct charges |  |  |  |  | 5.97
| Total Maintenance Support | 0 | 0 | 0 | 0 | 14.9 | 0 | 0 | 0 | 14.9
Network Operations
| Switching | [5 empty] | 7.51
| Asset Monitoring Team | [5 empty] | 3.5
| NMS Support | [5 empty] | 3.15
| Operations Support | [5 empty] | 2.61
| Total Network Operations | 0 | 0 | 0 | 0 | 0 | 16.77 | 0 | 0 | 16.77
| Total Direct Operations & Maintenance | 23.25 | 30.38 | 19.65 | 39.76 | 14.9 | 16.77 | 0 | 0 | 144.71
Other Controllable
Asset Management Support
| Grid Planning | [6 empty] | 7.02
| Network Support | [6 empty] | 15.69
| IT Support | [6 empty] | 10.5
| Customer & Regulatory Support | [6 empty] | 5.26
| Total Asset Management Support | 0 | 0 | 0 | 0 | 0 | 0 | 38.46 | 0 | 38.46
Corporate Support
| Total Corporate Support | [7 empty] | 20.38 | 20.38
| Total Other Controllable | 0 | 0 | 0 | 0 | 0 | 0 | 38.46 | 20.38 | 58.84
| Total Controllable Operating | 23.25 | 30.38 | 19.65 | 39.76 | 14.9 | 16.77 | 38.46 | 20.38 | 203.55
Summary
| Total Labour | 18.15 | 24.14 | 16.39 | 39.76 | 8.16 | 15.31 | 35.12 | 9.88 | 166.9
| Total Maintenance Non-Labour | 5.1 | 6.24 | 3.26 | [5 empty] | 14.6
| Total Other Non-Labour |  |  |  |  | 6.75 | 1.46 | 3.35 | 10.5 | 22.05
Other Operating
| Insurances | [8 empty] | 11.44
| Network Support | [8 empty] | 2.2
| Debt Raising | [8 empty] | 4.52
| Total Operating Expenditure | [8 empty] | 221.7

## Historic Capex by Category
Powerlink pro-forma information statements - 31 May 2011
3.1 HISTORIC CAPEX by project category |  |  | Home |  | Link to Historic Capex Instructions - Table 6.2 |  |  |  | Link to Historic Capex Commentary - Table 5.2
$ million nominal
Project Category |  |  |  | 2007/08 | 2008/09 | 2009/10 | 2010/11 | 2011/12 | TOTAL
NETWORK
LOAD DRIVEN | Augmentation |  |  | 410.88 | 344.18 | 207 | 139.12 | 292.99 | 1394.17
| Easements |  |  | 23.04 | 18.92 | 16.48 | 14.34 | 22.11 | 94.89
| Connections |  |  | 22.74 | 27.39 | 30.78 | 12.24 | 16.63 | 109.78
NON-LOAD DRIVEN | Replacements |  |  | 169.31 | 186.85 | 139.81 | 179.13 | 338.89 | 1013.99
| Security/Compliance |  |  | 2.21 | 2.07 | 9.9 | 4.56 | 35.75 | 54.49
| Other |  |  | 7.3 | 16.02 | 11.63 | 27.79 | 49.58 | 112.33
NON NETWORK
BUSINESS IT |  | Information Technology |  | 10.41 | 12.71 | 11.55 | 12.88 | 14.82 | 62.38
SUPPORT THE BUSINESS |  | Commercial Buildings |  | 4.4 | 6.67 | 10.62 | 14.68 | 4.19 | 40.55
|  | Motor Vehicles |  | 0.98 | 1.26 | 3.29 | 3.78 | 4.44 | 13.75
|  | Moveable Plant |  | 1.31 | 1.19 | 1.4 | 1.8 | 1.77 | 7.48
TOTAL FDC
TOTAL HISTORIC CAPEX |  |  |  | 652.57 | 617.26 | 442.46 | 410.33 | 781.19 | 2903.81

## Hist Capex by Asset Class
Powerlink pro-forma information statements - 31 May 2011
3.2 HISTORIC CAPEX by asset class | Home |  |  | Link to Capex Instructions - Table 6.2
$ million nominal
| 2007/08 | 2008/09 | 2009/10 | 2010/11 | 2011/12 | TOTAL
Asset class
| Cost | Cost | Cost | Cost | Cost | Cost
Transmission Lines (Overhead) | 310.32 | 304.47 | 236 | 156.05 | 303.62 | 1310.45
Transmission Lines (Underground) | 0 | 0 | 0 | 0 | 0.06 | 0.06
Transmission Lines (Refit) | 0 | 0 | 4.86 | 1.81 | 27.08 | 33.75
Substations Primary Plant | 204.19 | 176.54 | 85.12 | 128.3 | 240 | 834.15
Substations Secondary Systems | 83.62 | 73.36 | 55.98 | 57.81 | 104.24 | 375
Communications Assets | 13.87 | 16.91 | 13.92 | 12.98 | 45.43 | 103.11
Communications - Civil Works | 0 | 0 | 0.01 | 0 | 0 | 0.01
Network Switching Centres | 0.87 | 4.7 | 3.24 | 5.88 | 11.64 | 26.33
Land | 7.54 | 5.7 | 4.24 | 3.46 | 7.68 | 28.63
Easements | 15.5 | 16.01 | 12.24 | 10.88 | 16.21 | 70.84
0
Commercial Buildings | 4.27 | 3.85 | 10.62 | 14.67 | 4.18 | 37.59
Computer Equipment | 9.86 | 13.06 | 11.55 | 12.91 | 14.82 | 62.2
Office Furniture & Miscellaneous | 0.13 | 0.01 | 0 | 0.01 | 0.01 | 0.15
Office Machines | 0 | 0.03 | 0 | 0 | 0 | 0.03
Vehicles | 0.98 | 1.26 | 3.29 | 3.78 | 4.44 | 13.75
Moveable Plant | 1.43 | 1.36 | 1.4 | 1.8 | 1.77 | 7.77
Insurance Spares | 0 | -0.72 | -0.21 | 1.3 | 0 | 0.37
0
Equity raising costs | 8.74 |  |  |  |  | 8.74
TOTAL CAPEX | 661.3 | 616.54 | 442.25 | 411.63 | 781.19 | 2912.92

## Hist Capex - Network
Powerlink pro-forma information statements - 31 May 2011
3.3 HISTORIC CAPEX - NETWORK - by project
|  |  |  | Home |  |  | Link to Historic Capex Instructions - Table 6.2 |  |  | Link to Historic Capex Commentary - Table 5.2
$M nominal
Yearly expenditure by project
Project ID | Project Description | Commissioning Date | Category^ | 2007/08 | 2008/09 | 2009/10 | 2010/11 | 2011/12 | TOTAL |  | REASON FOR PROJECT | Reg Test / Business Case (Y/N) | Reg Test / Business Case Cost Estimate | Reason for Variance from Cost Estimate / Expected Commissioning Date
CP.00364 | Murarrie 2nd 300MVA275/110kV Transformer | Dec-08 | Augmentation | 2.3 | 1.71 | 0 | 1.45 | 0 | 5.46 |  | Reliability | Reg Test - APR | $9.2m ($2005/06) | Commissioning advanced to maintain reliability of supply by facilitating staged rebuild of another project in the area.
CP.00618 | Kareeya-Innisfail Line Replace Easmt Project | Oct-07 | Easement | 3.73 | 1.2 | 0 | 0 | 0 | 4.93 |  | Age / Condition / Obsolescence | Board Memo | $5.9m (escal) | Higher costs due to significant community opposition and additional legal impediments (eg. EPBC Act).
CP.00659 | El Arish 132/22kV Substation Establishment | Feb-09 | Augmentation | 14.5 | 1.98 | 0.09 | 0 | 0 | 16.57 |  | Reliability | Reg Test | $13.5m ($2005/06) $14.6m (escal) | Slight delay to completion due to industrial action. Higher costs due to increase in materials and labour costs, and wet weather.
CP.00704 | SWQ to SEQ Easement Project No. 1 | Apr-12 | Easement | 1.53 | 1.62 | 0.44 | 0.48 | 0.72 | 4.8 |  | Strategic Easement | Board Memo | $8.2m (escal)
CP.00736 | Greenbank Stat Var Compensator | Dec-08 | Augmentation | 16.02 | 11.58 | 0.05 | 0 | 0 | 27.65 |  | Reliability | Reg Test | $32.9m ($2006/07) | Minor delay in commissioning due to industrial action.
CP.00752 | Nebo & QR SVCs Secondary Systems Replacement | Feb-08 | Replacement | 8.54 | 1.04 | 0.02 | 0 | 0 | 9.6 |  | Age / Condition / Obsolescence | Board Memo | $27.6m ($2004/05) $28.9m (escal)
CP.00836 | Cairns 132kV Substation Replacement | Oct-10 | Replacement | 0.07 | 1.14 | 2.87 | 2.42 | 0.31 | 6.82 |  | Age / Condition / Obsolescence | Bus Case | $10.8m ($2003/04) $11.0m (escal)
CP.00861 | Innisfail Edmonton Easement Project | Dec-08 | Easement | 0.93 | 5 | 1.9 | 0.37 | 0 | 8.19 |  | Age / Condition / Obsolescence | Approval Memo | $1.7m (escal) | Access delayed due to additional legal impediments (eg. EPBC Act and other environmental permits). Higher costs primarily associated with increased land values.
CP.00880 | Tully - Cardwell 132kV Line Replacement | Oct-12 | Replacement | 0 | 0 | 0.03 | 2.28 | 41.1 | 43.41 |  | Age / Condition / Obsolescence | Bus Case | $57.3m (escal)
CP.00881 | Ingham/Yabulu Sth 275/132kV Line Replacement | Oct-11 | Replacement | 0.37 | 6 | 30.19 | 41.25 | 17.7 | 95.51 |  | Age / Condition / Obsolescence | Bus Case | $97.3m (escal)
CP.00882 | Cardwell - Ingham South 132kV Line Replacement | Dec-13 | Replacement | 0.01 | 0 | 0.07 | 1.46 | 6.62 | 8.15 |  | Age / Condition / Obsolescence | Bus Case | $60.3m (escal)
CP.01015 | Woolooga 275/132kV Substn Replacement | Oct-09 | Replacement | 14.53 | 14.1 | 5.59 | 0.16 | 0 | 34.38 |  | Age / Condition / Obsolescence | Bus Case | $33.5m (escal) | Delay in commissioning due to manufacturer defect and industrial action.
CP.01017 | Tarong Secondary Systems Replacement | Aug-11 | Replacement | 0.68 | 4.04 | 8.1 | 1.81 | 0.42 | 15.06 |  | Obsolescence / Safety | Bus Case | $21.9m (escal)
CP.01018 | Swanbank A 110kV Substation Rebuild | Jun-11 | Replacement | 0.12 | 0.88 | 6.58 | 12.34 | 0.04 | 19.94 |  | Operational | Bus Case | $31.2m (escal)
CP.01019 | Moranbah Secondary Systems Replacement | Oct-12 | Replacement | 0 | 0 | 0.21 | 2.12 | 12.28 | 14.61 |  | Age / Condition / Obsolescence | Bus Case | $17.4m (escal)
CP.01021 | Lilyvale Secondary Systems Replacement | Jun-12 | Replacement | 0 | 0.02 | 0.28 | 5.69 | 2.17 | 8.16 |  | Age / Condition / Obsolescence | Bus Case | $10.5m (escal)
CP.01022 | Townsville South Secondary Systems Upgrade | Feb-09 | Replacement | 1.29 | 1.25 | 0.17 | 0 | 0 | 2.71 |  | Obsolescence | Bus Case | $10.2m ($2005/06) $10.5m (escal) | Significant works completed by December 2008. Final commissioning delayed due to reprioritisation of workload.
CP.01030 | South East Brisbane Easement Project | Oct-06 | Easement | 1.34 | 1.45 | 0 | 0 | 0 | 2.78 |  | Reliability | Bus Case | $6.0m ($2001/02)
CP.01035 | Ross-Townsville South Transmission Reinforcement | Jul-08 | Augmentation | 9.28 | 0.17 | 0 | 0 | 0 | 9.45 |  | Reliability | Reg Test | $16.2m ($2005/06) $17.3m (escal) | Delay to completion due to transformer failure at another site (ie. resources diverted) and wet weather. Higher materials and labour costs and prolongation costs.
CP.01063 | Blackwater Secondary Systems Replacement | May-10 | Replacement | 0.59 | 0.3 | 1.34 | 0.26 | 0 | 2.49 |  | Age / Condition / Obsolescence | Bus Case | $3.6m (escal)
CP.01064 | Gin Gin Secondary Systems Replacement | Mar-12 | Replacement | 0.02 | 0.28 | 3.33 | 6.21 | 2.03 | 11.87 |  | Obsolescence / Safety | Bus Case | $12.3m (escal)
CP.01067 | Clare 132kV Substation Replacement | Nov-09 | Replacement | 2.45 | 19.55 | 2.31 | 0.98 | 0 | 25.28 |  | Age / Condition / Obsolescence | Bus Case | $25.8m (escal) | Delay in commissioning caused by wet weather and third parties.
CP.01078 | Nudgee 275/110kV Easement Project | Oct-08 | Easement | 1.01 | 0.29 | 0.84 | 0.4 | 0.42 | 2.96 |  | Reliability | Bus Case | $6.2m (escal)
CP.01087 | Bohle River to Townsville GT 132kV Line | Oct-07 | Replacement | 2.01 | 2.07 | 0.14 | 0 | 0 | 4.21 |  | Safety | Bus Case | $17.1m ($2004/05) $18.0m (escal) | Cost increases due to wet weather, third party delays and higher dismantling costs.
CP.01090 | Woree 275kV Reinforcement | Oct-07 | Augmentation | 8.9 | 0.07 | 0 | 0 | 0 | 8.98 |  | Reliability | Bus Case | $12.4m ($2005/06) $13.4m (escal)
CP.01091 | Garbutt - Alan Sherriff T/L Replacement | Oct-12 | Replacement | 0.01 | 0 | 0 | 0 | 10.85 | 10.86 |  | Age / Condition / Obsolescence
CP.01100 | Middle Ridge - Greenbank Easement Project | Sep-07 | Easement | 1.27 | 1.05 | 0.29 | 0.57 | 0.1 | 3.28 |  | Demand Growth / Reliability | Bus Case | $5.5m (escal)
CP.01101 | NQ Transmission Reinf St2 (Nebo-Strath) | Aug-09 | Augmentation | 58.95 | 72.18 | 5.26 | 0.34 | 0.6 | 137.33 |  | Reliability | Reg Test | $118.9m ($2005/06) $132.2m (escal) | Delay in commissioning due to wet weather and coordination with other projects.
CP.01121 & CP.01038 & CP.01081 | Goodna, Algester and Sumner Sub Establishments | Nov 06/Sep 07 | Augmentation | 1.5 | 0.01 | 0.01 | 0 | 0 | 1.52 |  | Reliability | Reg Test | $34.9m ($2004/05) | Delay in commissioning of Algester due to third party.
CP.01124 | Mackay Transmission Reinforcement | Feb-08 | Augmentation | 18.28 | 0.4 | 0 | 0 | 0 | 18.68 |  | Reliability | Reg Test | $44.7m ($2005/06) $51.4m (escal) | Higher costs due to wet weather (prolongation costs) and increased construction costs. Prolonged period of wet weather also impacted commissioning.
CP.01127 | Loganlea 110kV Secondary Systems Replacement | Jun-14 | Replacement | 0 | 0 | 0 | 0.42 | 6.29 | 6.71 |  | Age / Condition / Obsolescence
CP.01131 | Tully-Innisfail 132kV Transmission Line | Aug-08 | Replacement | 58.08 | 5.25 | 0 | 0 | 0 | 63.33 |  | Age / Condition / Obsolescence | Bus Case | $55.1m (escal) | Higher costs due primarily to wet weather (prolongation costs) and increases in materials costs. Delays due to wet weather and legal access impediments. Reapproved at $99.8m.
CP.01133 | Belmont No 4 Transformer Replacement | Jul-10 | Replacement | 0.03 | 2.19 | 2.08 | 2.22 | 0 | 6.53 |  | Age / Condition / Obsolescence | Bus Case | $7.2m (escal)
CP.01134 | South Pine 110kV Substn Replacement | Oct-10 | Replacement | 14.33 | 20.77 | 14.92 | 5.57 | 0.74 | 56.34 |  | Safety | Bus Case | $48.2m (escal)
CP.01135 | Redbank Plains Secondary System Replacement | Jul-12 | Replacement | 0 | 0 | 0.03 | 0.12 | 3.92 | 4.07 |  | Age / Condition / Obsolescence | Bus Case | $4.6m (escal)
CP.01137 | Ross - Yabulu Transmission Reinforcement | Oct-09 | Augmentation | 22.76 | 15.28 | 1.21 | 0 | 0 | 39.25 |  | Reliability | Reg Test | $39.4m ($2006/07) | Commissioning delayed due to impacts of unreliable flood level data and project coordination.
CP.01138 | SEQ Augmentation | Feb-08 | Augmentation | 47.69 | -3.21 | 0.01 | 0 | 0 | 44.49 |  | Reliability | Reg Test | $94.8m ($2005/06) $99.9m (escal) | Cost increases due to higher construction costs (labour, materials). Lines commissioned in Feb. Transformer commissioned Nov 08. Delay was due to manufacture issues.
CP.01144 | Townsville East Substation Establishment | Sep-08 | Augmentation | 22.08 | 3.06 | 0 | 0 | 0 | 25.14 |  | Reliability | Reg Test | $23.4m ($2005/06) $24.3m (escal) | Delays due to environmental permit process and excessive wet weather. Higher materials and implementation costs (eg. due to wet weather). Reapproved at $35.0m.
CP.01147 | Belmont No 5 Transformer Replacement | Nov-09 | Replacement | 0.05 | 4.58 | 2.87 | 0.01 | 0 | 7.51 |  | Age / Condition / Obsolescence | Bus Case | $8.2m (escal)
CP.01155 | MT England Secondary Systems Replacement | Aug-10 | Replacement | 0.55 | 1.57 | 2.23 | 0.73 | 0 | 5.08 |  | Age / Condition / Obsolescence | Bus Case | $8.4m (escal)
CP.01161 | Rocklea Secondary Systems Replacement | Oct-13 | Replacement | 0 | 0 | 0 | 0.36 | 0.65 | 1.01 |  | Age / Condition / Obsolescence | Bus Case | $9.5m (escal)
CP.01163 | Swanbank B 275kV Substation Rebuild | Mar-13 | Replacement | 0 | 0 | 0.16 | 5.28 | 27.05 | 32.49 |  | Age / Condition / Obsolescence | Bus Case | $52.6m (escal)
CP.01165 | West Darra Substation Rebuild | Apr-09 | Replacement | 5.37 | 5.22 | 0.05 | 0 | 0 | 10.64 |  | Operational | Bus Case | $22.8m (escal) | Critical plant commissioned on time. Delay to final commissioning due to industrial action.
CP.01166 | Palmwoods Sec Systems Replacement | Aug-10 | Replacement | 0.21 | 4.12 | 5.22 | 0.76 | 0 | 10.31 |  | Obsolescence / Safety | Bus Case | $10.3m (escal)
CP.01169 | Innisfail - Edmonton Line Replacement | Aug-09 | Replacement | 28.79 | 54.45 | 2.77 | 0.01 | 0 | 86.02 |  | Environmental / Age / Condition | Bus Case | $83.2m (escal) | Commissioned slightly ahead of schedule due to good weather. Reapproved at $94.7m.
CP.01177 | Belmont 110kV Substation Replacement | Nov-11 | Replacement | 2.16 | 18.37 | 14.5 | 4.46 | 9.25 | 48.74 |  | Safety | Bus Case | $42.3m (escal)
CP.01186 | North Qld Transmission Reinf Stage 1 | Oct-08 | Augmentation | 57.87 | 14.08 | 1.1 | 0 | 0 | 73.04 |  | Reliability | Reg Test | $87.5m (2005/06) $91.2m (escal) | Project completed Oct 08. Remaining works scheduled outside summer peak. Higher costs due to wet weather and input cost increases (steel, aluminium, concrete).
CP.01187 | Molendinar 275/110kV Transformer Reinforcement | Sep-07 | Augmentation | 1.13 | 0.02 | 0 | 0 | 0 | 1.15 |  | Reliability | Reg Test - APR | $6.9m ($2004/05) | Delay in commissioning to effectively coordinate resources for multiple projects in the area.
CP.01191 | Brisbane South Area Easement Project | Jul-14 | Easement | 0.38 | 0.17 | 0.15 | 0.2 | 0.5 | 1.4 |  | Reliability | Bus Case | $14.9m (escal)
CP.01192 | Biloela Transformer Augmentation | Oct-07 | Connection | 0.96 | 0.05 | 0.01 | 0 | 0 | 1.02 |  | Reliability | Bus Case | $6.9m (escal)
CP.01198 | Wide Bay Transmission Reinforcement | Apr-08 | Augmentation | 18.06 | 0.12 | 0 | 0 | 0 | 18.18 |  | Reliability | Reg Test | $35.8m ($2005/06) | Higher costs due to increased construction (labour and materials) costs. Delay in commissioning due to third party.
CP.01203 | South Pine 275kV 2T Transformer Replacement | Mar-09 | Replacement | 2.42 | 0 | 0 | 0.15 | 0 | 2.57 |  | Age / Condition / Obsolescence | Bus Case | $4.9m (escal) | Delay in commissioning to coordinate with substation reconstruction.
CP.01204 | Lilyvale - Blackwater 132kV Transm Line | Oct-07 | Augmentation | 6.84 | 0.2 | 0.31 | 0 | 0 | 7.36 |  | Reliability | Reg Test | $28.8m ($2005/06) $30.3m (escal) | Cost increases due to increased labour and materials costs.
CP.01229 | Tower Bolts (Tarong Region) | Jun-10 | Security / Compliance | 0 | 0 | 1.26 | 0 | 0 | 1.26 |  | Security | Bus Case | $1.0m (escal) | Minor delay in completion due to supplier. Higher procurement costs.
CP.01243 | Pandoin Substation Establishment | Sep-09 | Augmentation | 2.9 | 28.63 | 2.19 | 0.01 | 0 | 33.73 |  | Reliability | Reg Test | $36.8m ($2006/07)
CP.01245 | Mackay-Pioneer Val Transm Line Life Extension | Dec-11 | Replacement | 0.41 | 0.04 | 0.45 | 0.1 | 7.83 | 8.82 |  | Age / Condition / Obsolescence | Bus Case | $5.3m (escal)
CP.01246 | Mackay-Proserpine Transm Line Life Extension | Jul-12 | Replacement | 0.11 | 1.26 | 1.64 | 1.7 | 1.73 | 6.44 |  | Age / Condition / Obsolescence | Bus Case | $5.0m ($2005/06) $5.3m (escal)
CP.01261 | Bowen-Strathmore Easement Project | Mar-08 | Easement | 0.28 | 0.49 | 0.53 | 0.27 | 0 | 1.56 |  | Reliability | Bus Case | $2.6m (escal)
CP.01265 | Bowen Substation Establishment | Oct-10 | Augmentation | 0.07 | 10.96 | 37.7 | 8.16 | 0.01 | 56.89 |  | Reliability | Bus Case | $75.6m (escal)
CP.01266 | Abermain 275kV Substation Establishment | Mar-09 | Augmentation | 16.55 | 3.67 | 0.47 | 0 | 0 | 20.68 |  | Reliability | Reg Test | $19.6m ($2004/05) $21.6m (escal) | Commissioning delayed due to industrial action. Higher costs due mainly to materials, labour and contractor cost increases.
CP.01267 | Mudgeeraba Ext 110/33Kv Establishment | Nov-07 | Connection | 1.58 | 0.01 | 0.08 | 0 | 0 | 1.66 |  | Reliability | Bus Case | $4.7m (escal)
CP.01271 | Woologa to North Coast 275kV DCST Easement Project | Apr-12 | Easement | 1.38 | 1.23 | 1.21 | 1.58 | 1.5 | 6.9 |  | Reliability | Bus Case | $6.9m (escal)
CP.01285 | QR Bolingbroke Rail Supply | Jul-09 | Connection | 12.43 | 20.48 | 0.42 | 0.31 | 0 | 33.63 |  | Reliability / Connection | Bus Case | $39.8m (escal) | Powerlink works completed on time. Minor delay in commissioning due to customer coordinated works.
CP.01286 | Tarong Substation Replacement | Jun-09 | Replacement | 8.97 | 2.44 | 0.72 | 0 | 0 | 12.13 |  | Safety / Fault Levels | Bus Case | $23.9m (escal) | Commissioning delayed due to outage contraints and industrial action. Higher costs due to prolongation costs and sub works.
CP.01292 | Broadsound Secondary Systems Replacement | Nov-12 | Replacement | 0 | 0 | 0.11 | 5.53 | 5.35 | 10.99 |  | Age / Condition / Obsolescence | Bus Case | $13.1m (escal)
CP.01294 | Strathmore 275kV SVC | Oct-07 | Augmentation | 23.88 | 0.71 | 0 | 0 | 0 | 24.6 |  | Reliability | Reg Test | $36.3m ($2005/06) $38.0m (escal)
CP.01301 | Power Quality Monitoring Stages 1&2 | Jun-13 | Other | 0.03 | 0.39 | 0.06 | 0.5 | 0.91 | 1.89 |  | Operational | Bus Case | $4.4m (escal)
CP.01310 | Metropolitan SDH Loop Upgrade | Oct-12 | Replacement | 0 | 0.01 | 0.01 | 0.12 | 3.21 | 3.35 |  | Age / Condition / Obsolescence | Bus Case | $3.4m (escal)
CP.01317 | Ashgrove West 3rd 110kV 50 MVAr Capacitor | Oct-11 | Augmentation | 0.02 | 0.01 | 0.05 | 0.69 | 1.44 | 2.2 |  | Reliability | Reg Test | $2.1m ($2009/10)
CP.01318 | South Pine 275kV 3rd & 4th Cap Banks | Dec-08 | Augmentation | 1.86 | 2.84 | 0.01 | 0 | 0 | 4.7 |  | Reliability | Reg Test | $4.6m ($2005/06) | Commissioning of one cap bank advanced to coordinate with other works on site.
CP.01319 | QAL Connection | Aug-08 | Connection | 4.8 | 0.99 | 0.01 | 0 | 0 | 5.79 |  | Customer Request | Bus Case | $5.9m (escal) | Powerlink works completed as required. Delays due to customer.
CP.01326 | Alligator Creek Transformer Replacement | Feb-09 | Replacement | 7.84 | 3.12 | 0.05 | 0 | 0 | 11.01 |  | Age / Condition / Obsolescence | Bus Case | $13.0m (escal) | Slight delay in commissioning due to industrial action and third party delays.
CP.01327 | South Pine - Sandgate 275kV Transmission Line | May-11 | Augmentation | 3.41 | 28.24 | 11.42 | 4.97 | 0.05 | 48.08 |  | Reliability | Reg Test | $51.8m ($2007/08)
CP.01330 | Woolooga Gin Gin OHEW Replacement | Sep-11 | Replacement | 0.73 | 0.12 | 0 | 1.51 | 0.63 | 3 |  | Age / Condition / Obsolescence | Bus Case | $10.5m (escal)
CP.01333 | Energy Management System (EMS) Upgrade | Apr-11 | Other | 0.66 | 4.41 | 3.13 | 3.88 | 0.33 | 12.41 |  | Age / Condition / Obsolescence | Bus Case | $13.8m (escal)
CP.01334 | EMS DIMA Upgrade | Nov-11 | Other | 0 | 0.1 | 0.24 | 0.85 | 0.53 | 1.71 |  | Age / Condition / Obsolescence | Bus Case | $1.7m (escal)
CP.01336 | Turkinje 132kV Sub Primary Plant Replacement | Nov-08 | Replacement | 1.34 | 1.21 | 0 | 0 | 0 | 2.55 |  | Age / Condition / Obsolescence | Bus Case | $3.4m (escal)
CP.01338 | Ingham to Tully Easement Project | Jun-11 | Easement | 0.3 | 0.46 | 0.92 | 1.05 | 2.63 | 5.36 |  | Age / Condition / Obsolescence | Bus Case | $3.4m (escal)
CP.01345 | Kareeya to Chalumbin ADSS Replacement | Jun-14 | Replacement | 0 | 0 | 0.03 | 0.07 | 1 | 1.11 |  | Age / Condition / Obsolescence | Bus Case | $1.8m (escal)
CP.01347 | Swanbank A/B Switchyard Site | Jun-09 | Easement | 1.09 | 0.38 | 0.06 | 0.03 | 0 | 1.56 |  | Age / Condition / Obsolescence | Bus Case | $1.8m (escal) | Delay in site acquisition due to landowner opposition and additional planning approval requirements.
CP.01350 | Gladstone Switchyard Site | Apr-10 | Easement | 0.05 | 3.81 | 0.68 | 0.06 | 0 | 4.6 |  | Age / Condition / Obsolescence | Bus Case | $6.6m (escal) | Delay in acquisition due to further technical investigation.
CP.01356 | Control Centre Communications Console | Jul-11 | Other | 0 | 0.01 | 0.05 | 0.86 | 0.09 | 1.02 |  | Reliability | Bus Case | $1m (escal)
CP.01357 | Gladstone South Harmonic Filter | Apr-11 | Augmentation | 0.03 | 0.11 | 1.24 | 1.56 | 0.05 | 3 |  | Compliance | Reg Test | $5.6m (escal)
CP.01358 | Infrastructure Expansion for Telecomms | May-10 | Security / Compliance | 1.91 | 1.09 | 0.27 | 0 | 0 | 3.27 |  | Compliance | Bus Case | $3.5m (escal) | Delay in completion due to project complexity and other project dependencies.
CP.01359 | Bouldercombe to South Pine OPGW Retrofit | Jul-11 | Replacement | 2.88 | 7.78 | 6.79 | 5.94 | 0.6 | 23.99 |  | Age / Condition / Obsolescence | Bus Case | $32.2m (escal)
CP.01360 | Moura 132kV Capacitor Bank | Aug-10 | Augmentation | 0.03 | 0.19 | 1.38 | 0.42 | 0 | 2.02 |  | Reliability | Reg Test | $2.3m ($2007/08)
CP.01361 | Gin Gin 132kV Korenan By-Pass Switchgear | Dec-09 | Connection | 0.02 | 0.17 | 1.27 | 0 | 0 | 1.46 |  | Customer Request | Bus Case | $1.8m (escal)
CP.01364 | Gin Gin No. 2 Transformer Replacement | Oct-11 | Replacement | 0.01 | 0.07 | 1.4 | 2.71 | 2.05 | 6.25 |  | Age / Condition / Obsolescence | Bus Case | $8.3m (escal)
CP.01365 | Gin Gin No. 1 Transformer Replacement | Oct-11 | Replacement | 0 | 0.08 | 4.83 | 1.8 | 0.03 | 6.75 |  | Age / Condition / Obsolescence | Bus Case | $8.0m (escal)
CP.01367 | Establish DWDM Network | Apr-09 | Other | 3.75 | 10.52 | 1.36 | 0 | 0 | 15.64 |  | Security | Bus Case | $16.3m (escal) | Delay in commissioning due to implementation of new software version, other project dependencies and industrial action.
CP.01375 | Disaster Recovery Relocation | Feb-10 | Security / Compliance | 0.05 | 0.76 | 4.75 | 0.07 | 0 | 5.63 |  | Security | Bus Case | $5.1 (escal) | Delay in commissioning due to contractor delays.
CP.01377 | Collinsville Transformer Replacement | Jul-08 | Replacement | 1.99 | 0.7 | 0 | 0 | 0 | 2.69 |  | Age / Condition / Obsolescence | Bus Case | $3.5m (escal)
CP.01385 | Tarong Bus Rating Upgrade | Jun-13 | Other | 0 | 0 | 0 | 0.13 | 2.72 | 2.86 |  | Fault levels
CP.01397 | Nebo 275/132kV No. 1 Transformer Replacement | Jul-13 | Replacement | 0 | 0 | 0 | 0 | 5.98 | 5.98 |  | Age / Condition / Obsolescence
CP.01399 | Loganlea 110/33kV Transformer Augmentation | Oct-13 | Connection | 0 | 0 | 0.1 | 0.57 | 4.88 | 5.55 |  | Reliability | Bus Case | $5.9m (escal)
CP.01401 | Woolooga No.1 & 2 Transformers Replacement | Jun-13 | Replacement | 0 | 0 | 0 | 0.39 | 3.75 | 4.14 |  | Age / Condition / Obsolescence | Bus Case | $9.5m (escal)
CP.01403 | Diesel Generator Installation Various Substations | Sep-10 | Security / Compliance | 0 | 0.2 | 2.68 | 0.4 | 0 | 3.28 |  | Reliability | Bus Case | $2.6m (escal)
CP.01415 | Loganlea 110kV Extension (Jimboomba) | Apr-12 | Connection | 0 | 0.06 | 0.07 | 0.29 | 1.46 | 1.87 |  | Reliability | Bus Case | $1.9m (escal)
CP.01420 | Woree - Kamerunga 132kV Line Life Extension | Oct-12 | Replacement | 0.05 | 0.09 | 0.01 | 0.01 | 11.43 | 11.6 |  | Age / Condition / Obsolescence
CP.01422 | Western Downs Substn Site & Easement Project | Jun-11 | Easement | 0 | 0.09 | 1.27 | 0.55 | 0.49 | 2.4 |  | Reliability | Bus Case | $3.3m (escal)
CP.01428 | High Speed Monitoring - Stage 2 | Dec-11 | Other | 0 | 0.05 | 1.19 | 0.8 | 0.01 | 2.06 |  | Compliance | Bus Case | $4.2m (escal)
CP.01429 | South West Queensland Augmentation | Oct-12 | Augmentation | 0 | 0.28 | 7.43 | 83.4 | 67.72 | 158.83 |  | Reliability | Reg Test | $229.2m ($2008/09)
CP.01430 | SWQ to SEQ Easement Project No. 2 | Oct-11 | Easement | 0 | 0.14 | 1.12 | 1.33 | 1.92 | 4.52 |  | Reliability | Bus Case | $8.8m (escal)
CP.01433 | DWDM Network Diversity - Wide Bay | Mar-11 | Other | 0 | 0.04 | 1.33 | 1.38 | 0.01 | 2.75 |  | Security | Bus Case | $3.5m (escal)
CP.01434 | Karana Downs to Upper Kedron OPGW Retrofit | Jun-12 | Other | 0 | 0 | 0 | 0.03 | 2.04 | 2.07 |  | Reliability
CP.01436 | DWDM Network Diversity - North | Jun-11 | Other | 0 | 0.01 | 0.02 | 1.12 | 0.21 | 1.37 |  | Reliability | Bus Case | $1.9m (escal)
CP.01439 | Substation Security Upgrade - North | Dec-11 | Security / Compliance | 0 | 0.01 | 0.07 | 0.82 | 0.8 | 1.7 |  | Security | Bus Case | $1.6m (escal)
CP.01456 | 132/66kV System Spare Transformer No. 1 | Jul-10 | Replacement | 0 | 0.01 | 2.37 | 0.26 | 0 | 2.65 |  | Age / Condition / Obsolescence | Bus Case | $3.3m (escal)
CP.01458 | Central Region SDH Loop | Dec-11 | Other | 0 | 0.02 | 2.29 | 4.88 | 0.66 | 7.85 |  | Age / Condition / Obsolescence | Bus Case | $7.7m (escal)
CP.01466 | Southern Region SDH Loop | Oct-12 | Other | 0 | 0.01 | 0.01 | 0.2 | 3.8 | 4.02 |  | Age / Condition / Obsolescence | Bus Case | $4.4m (escal)
CP.01472 | Northern Region SDH Loop | Jun-12 | Other | 0 | 0.05 | 0.03 | 2 | 1.37 | 3.44 |  | Age / Condition / Obsolescence | Bus Case | $3.5m (escal)
CP.01474 | Kareeya - Innisfail 132kV Line Recovery | May-11 | Replacement | 0 | 0.03 | 7.22 | 0.31 | 0.1 | 7.66 |  | Age / Condition / Obsolescence | Bus Case | $12.8m (escal)
CP.01475 | Kareeya - Tully 132kV Line Recovery | Dec-13 | Replacement | 0 | 0 | 0.02 | 0.09 | 2.24 | 2.35 |  | Age / Condition / Obsolescence | Bus Case | $9.2m (escal)
CP.01484 | Alligator Ck-Louisa Ck Transmission Line | Jun-10 | Connection | 0 | 0 | 22.7 | 0.45 | 0 | 23.15 |  | Reliability | Board Memo | $33.0m
CP.01488 | Molendinar Substation Site Expansion | Oct-12 | Easement | 0 | 0 | 0 | 0.08 | 2.28 | 2.37 |  | Reliability | Bus Case | $2.6m (escal)
CP.01493 | Bulli Creek iPass Secondary System Replacement | Oct-13 | Replacement | 0 | 0 | 0 | 0.04 | 8.29 | 8.33 |  | Age / Condition / Obsolescence | Bus Case | $17.1m (escal)
CP.01502 | Mt England 2nd 275kV 120MVAr Cap Bank | Oct-09 | Augmentation | 0.05 | 1.97 | 0.76 | 0 | 0 | 2.77 |  | Reliability | Reg Test | $2.1m ($2005/06)
CP.01512 | North Qld Transmission Reinf Stage 3 | Oct-10 | Augmentation | 1.39 | 61.41 | 111.77 | 14.17 | 0.1 | 188.84 |  | Reliability | Reg Test | $198.5m (escal) $183.5m ($2007/08)
CP.01519 | South Pine 110kV Fdr Bay For Hays Inlet | Oct-10 | Connection | 0 | 0 | 0.56 | 1.05 | 0 | 1.61 |  | Customer Request | Bus Case | $1.7m (escal)
CP.01531 | Bundamba 110/11kV Transformer Augmentation | Oct-09 | Connection | 0.09 | 2.74 | 2.2 | 0.02 | 0 | 5.05 |  | Reliability | Reg Test | $5.3m ($2005/06)
CP.01544 | South Pine 275kV SVC | Dec-08 | Augmentation | 11.31 | 17.12 | 0 | 0 | 0 | 28.43 |  | Reliability | Reg Test | $29.0m ($2007/08) | Commissioning advanced due to coordinated procurement and site works.
CP.01548 | Kareeya Substation Redevelopment | Oct-12 | Replacement | 0.04 | 0.01 | 0.04 | 0.18 | 5.13 | 5.41 |  | Age / Condition / Obsolescence | Bus Case | $7.9m (escal)
CP.01559 | Edmonton 1st 132kV Capacitor Bank | Dec-08 | Augmentation | 1.48 | 0.38 | 0.02 | 0 | 0 | 1.89 |  | Reliability | Reg Test | $2.0m ($2005/06)
CP.01563 | Bouldercombe Secondary Systems Replacement | Nov-13 | Replacement | 0 | 0 | 0.08 | 3.3 | 9.83 | 13.2 |  | Age / Condition / Obsolescence | Bus Case | $18.7m (escal)
CP.01566 | Chalumbin Secondary Systems Replacement | Dec-13 | Replacement | 0 | 0 | 0 | 0.44 | 6.8 | 7.25 |  | Age / Condition / Obsolescence | Bus Case | $12.5m (escal)
CP.01582 | Stanwell Secondary Systems Replacement | Oct-14 | Replacement | 0 | 0 | 0 | 0 | 1.28 | 1.28 |  | Age / Condition / Obsolescence
CP.01599 | South Pine 110kV Feeder Bays for Griffin | Oct-10 | Connection | 0 | 0.26 | 0.8 | 0.51 | 0 | 1.58 |  | Demand Growth / Reliability | Bus Case | $1.6m (escal)
CP.01600 | Palmwoods 132kV Feeder Bays for Pacific Paradise | Oct-11 | Connection | 0 | 0.02 | 0.06 | 2.07 | 2.15 | 4.3 |  | Reliability | Bus Case | $4.3m (escal)
CP.01620 | Bouldercombe 275/132kV Transformer Reinf | Oct-12 | Augmentation | 0 | 0 | 0.07 | 1.3 | 9.65 | 11.02 |  | Reliability | Reg Test | $13.9m ($2009/10)
CP.01622 | Cardwell Substation Line Switching | Dec-12 | Other | 0 | 0 | 0.03 | 2.29 | 0.2 | 2.51 |  | Age / Condition / Obsolescence | Bus Case | $2.5m (escal)
CP.01628 | Alligator Creek Substation Extn (Louisa Creek) | Nov-09 | Connection | 0.79 | 1.52 | 0.09 | 0 | 0 | 2.4 |  | Reliability | Bus Case | $3.4m (escal) | Commissioning delayed due to wet weather and third party.
CP.01658 | Richlands Primary & Secondary Plant Replacement | Apr-13 | Replacement | 0 | 0 | 0.08 | 0.56 | 12.76 | 13.4 |  | Age / Condition / Obsolescence | Bus Case | $30.0 m (escal)
CP.01668 | Comms Site Access & Security (Part A) | Dec-12 | Security / Compliance | 0 | 0 | 0.01 | 0.02 | 1.18 | 1.2 |  | Security | Bus Case | $1.5m (escal)
CP.01677 | SEQ No.2 Substation Site | Dec-15 | Easement | 1.03 | 0.02 | 0.05 | 0.13 | 0.8 | 2.03 |  | Reliability | Bus Case | $1.2m (escal)
CP.01678 | Woolooga SVC | Nov-08 | Augmentation | 22.1 | 5.65 | 0.05 | 0 | 0 | 27.8 |  | Reliability | Reg Test | $32.8m ($2006/07)
CP.01689 | Upper Kedron 275/110/11kV Substation Site | Sep-14 | Easement | 0 | 0 | 0.88 | 0.15 | 0.35 | 1.39 |  | Reliability | Bus Case | $1.7m (escal)
CP.01705 | Calvale - Stanwell 275kV DCST Transmission Line | Oct-13 | Augmentation | 0 | 0 | 0.16 | 3.78 | 34.38 | 38.33 |  | Reliability | Reg Test | $104.6m ($2009/10) $116.8m (escal)
CP.01719 | Molendinar 3rd 110/33kV 100MVA Transformer | Oct-11 | Connection | 0.13 | 0.03 | 0.25 | 3.56 | 0.91 | 4.87 |  | Reliability | Bus Case | $4.8m (escal)
CP.01725 | Tarong 1st 275kV 200MVAr Capacitor Bank | Nov-09 | Augmentation | 0.07 | 1.06 | 2.38 | 0 | 0 | 3.52 |  | Reliability | Reg Test | $3.2m ($2007/08)
CP.01732 | Runcorn 110kv Substation Replacement | Apr-13 | Replacement | 0 | 0 | 0 | 0.34 | 7.18 | 7.52 |  | Age / Condition / Obsolescence | Bus Case | $15.4m (escal)
CP.01751 | Middle Ridge-Murphys Creek at 110kV Postman | May-11 | Connection | 0.02 | 0.07 | 0.16 | 2.57 | 0.01 | 2.84 |  | Reliability | Bus Case | $4.5m (escal)
CP.01758 | Pioneer Valley 132/66kV Transformer Replacement | Oct-12 | Connection | 0 | 0 | 0 | 0.1 | 4.74 | 4.85 |  | Reliability | Bus Case | $4.9m (escal)
CP.01780 | Calliope River Substation Establishment | Jun-13 | Replacement | 0.07 | 0.57 | 1.37 | 44.01 | 40.52 | 86.54 |  | Age / Condition / Obsolescence | Bus Case | $149.1m (escal)
CP.01788 | Palmwoods Primary Plant Replacement Stage 1 | Oct-13 | Replacement | 0 | 0 | 0 | 0.08 | 2.88 | 2.95 |  | Age / Condition / Obsolescence | Bus Case | $14.0m (escal)
CP.01803 | EMS FEP's Upgrade | Jul-13 | Replacement | 0 | 0 | 0 | 0 | 1.13 | 1.13 |  | Age / Condition / Obsolescence
CP.01807 | EMS Hardware Replacement | Oct-13 | Replacement | 0 | 0 | 0 | 0 | 1.52 | 1.52 |  | Age / Condition / Obsolescence
CP.01811 | North Moreton 275/110kV Substn Site & Easement Project | Oct-15 | Easement | 0 | 0.02 | 0.02 | 0.02 | 1.71 | 1.77 |  | Reliability | Bus Case | $5.4m (escal)
CP.01816 | VOIP Deployment Stage 1 | Jun-13 | Other | 0 | 0 | 0 | 0.01 | 3.32 | 3.33 |  | Strategic
CP.01830 | Calvale - Stanwell Easement Project | Sep-11 | Easement | 0 | 0.07 | 0.37 | 0.65 | 0.52 | 1.61 |  | Reliability | Bus Case | $2.4m (escal)
CP.01843 | Palmwoods Transformer Augmentation | Nov-09 | Augmentation | 0.17 | 3.89 | 2.06 | 0 | 0 | 6.13 |  | Reliability | Reg Test | $6.4m ($2006/07)
CP.01844 | South Pine Transformer No. 6 | Mar-09 | Augmentation | 5.97 | 11.51 | 0.64 | 0 | 0 | 18.12 |  | Reliability | Reg Test | $24.3m ($2007/08) | Minor advancement to commissioning to coordinate works at Sth Pine.
CP.01867 | Northern Bowen Basin Easement Project | Jun-12 | Easement | 0 | 0.04 | 0.46 | 0.4 | 1.02 | 1.92 |  | Reliability | Bus Case | $3.0m (escal)
CP.01875 | Halys-Blackwall 500kV | Oct-14 | Augmentation | 0 | 1.14 | 3.16 | 3.82 | 19.5 | 27.62 |  | Reliability | Reg Test | $387.3m ($2008/09)
CP.01880 | Greenbank 3rd & 4th 275kV Capacitor Banks | Nov-07 | Augmentation | 4.78 | 0.01 | 0 | 0 | 0 | 4.8 |  | Reliability | Reg Test | $6.3m ($2006/07)
CP.01882 | Greenbank 5th 275kV Capacitor bank | Sep-09 | Augmentation | 0.02 | 1.89 | 0.77 | 0 | 0 | 2.68 |  | Reliability | Reg Test | $3.1m ($2006/07)
CP.01886 | Belmont 3rd 275kV Capacitor Bank | Oct-11 | Augmentation | 0.01 | 0.02 | 0.22 | 1.94 | 0.21 | 2.41 |  | Reliability | Reg Test | $2.6m ($2008/09)
CP.01887 | Belmont 4th 275kV Capacitor Bank | Oct-12 | Augmentation | 0.02 | 0.02 | 0.11 | 1.42 | 0.54 | 2.12 |  | Reliability | Reg Test | $2.6m ($2008/09)
CP.01915 & CP.01932 | Southern Queensland Capacitor Bank (Wurdong and Palmwoods) | Oct-07 | Augmentation | 3.53 | 0.09 | 0 | 0 | 0 | 3.62 |  | Reliability | Reg Test | $4.2m ($2006/07) | Increased input costs.
CP.01918 | Strathmore iPASS Secondary Systems Replacement | Mar-13 | Replacement | 0 | 0 | 0 | 0 | 1.6 | 1.6 |  | Age / Condition / Obsolescence | Bus Case | $8.4m (escal)
CP.01919 | Loganlea IPASS Secondary Systems Replacement | Dec-11 | Replacement | 0 | 0.14 | 2 | 4.09 | 2.28 | 8.51 |  | Age / Condition / Obsolescence | Bus Case | $8.4m (escal)
CP.01920 | Braemar iPASS Secondary Systems Replacement | Oct-14 | Replacement | 0 | 0 | 0 | 0 | 1.29 | 1.29 |  | Age / Condition / Obsolescence
CP.01924 | Spare 330/275kV Transformer | Jun-12 | Other | 0 | 0 | 0.04 | 0.09 | 4.93 | 5.06 |  | Reliability | Bus Case | $8.2m (escal)
CP.01925 | Woree-Turkinje 132kV T/L Decommissioning | Sep-09 | Replacement | 0.01 | 0.07 | 3.28 | 0.04 | 0 | 3.39 |  | Environmental / Age / Condition | Bus Case | $3.9m (escal)
CP.01931 | Loganlea 4th 110kV 50 MVAr Capacitor Bank | Apr-12 | Augmentation | 0.01 | 0 | 0.02 | 0.2 | 1.8 | 2.03 |  | Reliability | Reg Test | $1.9m ($2009/10) $2.0m (escal)
CP.01958 | Larcom Creek 275/132kV Substation Establishment | Nov-09 | Augmentation | 0.54 | 39.49 | 11.61 | 0.23 | 0 | 51.87 |  | Reliability | Reg Test | $39.5m ($2005/06)
CP.01960 | Yabulu South to Ingham Easement Project | Oct-10 | Easement | 0.85 | 0.64 | 2.15 | 1.45 | 0.2 | 5.29 |  | Age / Condition / Obsolescence | Bus Case | $2.6m (escal)
CP.01971 | Yarwun Remote132kV bus Establishment Larcom | Nov-09 | Augmentation | 1.41 | 5.13 | 1.92 | 0.15 | 0 | 8.61 |  | Reliability | Bus Case | $9.2m (escal)
CP.01976 | Rocklea 110kV Feeder Bays for Woollongabba | Oct-13 | Connection | 0 | 0 | 0 | 0 | 1.91 | 1.91 |  | Reliability
CP.01983 | Moranbah Substation Extension (Broadlea) | Dec-10 | Connection | 0 | 0.05 | 1.49 | 0.75 | 0 | 2.29 |  | Demand Growth / Reliability | Bus Case | $2.9m (escal)
CP.01995 | Middle Ridge Two 330kV 120MVA Capacitor | Oct-11 | Augmentation | 0.01 | 0.04 | 0.15 | 5.73 | 0.99 | 6.92 |  | Demand Growth / Reliability | Reg Test | $6.7m ($2008/09) $6.9m (escal)
CP.01996 | Millmerran 330kV 200MVAr Capacitor Bank | Oct-11 | Augmentation | 0 | 0.03 | 0.09 | 2.74 | 0.05 | 2.9 |  | Reliability | Reg Test | $3.6m ($2008/09)
CP.02000 | Turkinje 132kV Capacitor | Oct-12 | Augmentation | 0 | 0 | 0 | 0 | 1.58 | 1.58 |  | Reliability | Bus Case | $2.5m (escal)
CP.02012 | Ross SVC Secondary System Replacement | Sep-12 | Replacement | 0 | 0 | 0 | 0.17 | 2.41 | 2.58 |  | Age / Condition / Obsolescence | Bus Case | $8.9m (escal)
CP.02014 | Secure Tower Bolts (North Qld Region) | Oct-11 | Security / Compliance | 0 | 0 | 0.02 | 0.37 | 1.23 | 1.62 |  | Security | Bus Case | $1.6m (escal)
CP.02018 | Accurate Fault Location Stage 1 | Oct-11 | Other | 0 | 0 | 0.75 | 0.58 | 0.11 | 1.45 |  | Reliability | Bus Case | $1.6m (escal)
CP.02022 | Surat Basin Easement Project No.2 | Sep-12 | Easement | 0 | 0 | 0.17 | 0.77 | 0.47 | 1.42 |  | Reliability | Bus Case | $4.5m (escal)
CP.02023 | Surat Basin Easement Project No.1 | Mar-12 | Easement | 0 | 0 | 0.44 | 0.67 | 0.53 | 1.64 |  | Reliability | Bus Case | $3.8m (escal)
CP.02027 | Kemmis 1st 132kV Capacitor Bank | Oct-10 | Augmentation | 0 | 0 | 0.48 | 1.54 | 0 | 2.03 |  | Demand Growth / Reliability | Bus Case | $2.3m (escal)
CP.02030 | Columboola to Wandoan Area Network Augmentation | Mar-13 | Augmentation | 0 | 0 | 0.13 | 1.09 | 45.76 | 46.98 |  | Reliability | Reg Test | $82.6m ($2009/10) $92.5m (escal)
CP.02031 | Columboola to Western Downs Network Augmentation | Mar-14 | Augmentation | 0 | 0 | 0.12 | 0.85 | 3.62 | 4.6 |  | Reliability | Reg Test | $124.0m ($2009/10) $142.0m (escal)
CP.02039 | Collinsville 132kV Substation Replacement | Oct-13 | Replacement | 0 | 0 | 0 | 0 | 10.48 | 10.48 |  | Age / Condition / Obsolescence
CP.02045 | PLVC to Sandgate Fibre Installation | May-12 | Other | 0 | 0 | 0.01 | 0.02 | 1.27 | 1.29 |  | Reliability
CP.02055 | Turkinje OPGW Retrofit | Dec-11 | Replacement | 0 | 0 | 0 | 0.43 | 1.57 | 2 |  | Reliability | Bus Case | $2.0m (escal)
CP.02058 | Replacement of 66kV Equipment at Tarong | Aug-12 | Replacement | 0 | 0 | 0.01 | 1.69 | 3.33 | 5.04 |  | Age / Condition / Obsolescence | Bus Case | $5.6m (escal)
CP.02059 | Woree and Chalumbin Single Pole Auto Reclose Implementation | Oct-12 | Replacement | 0 | 0 | 0 | 0.18 | 4.69 | 4.88 |  | Reliability | Bus Case | $6.1m (escal)
CP.02065 | SCADA and OPSWAN at QR SVC Sites | Dec-11 | Replacement | 0 | 0 | 0 | 0.04 | 1.37 | 1.41 |  | Replacement
CP.02067 | Substation Security Upgrade - Stage 1 | Jun-12 | Security / Compliance | 0 | 0 | 0 | 1.67 | 6.45 | 8.12 |  | Security | Bus Case | $8.3m (escal)
CP.02069 | Substation Security Upgrade - Stage 3 | Mar-13 | Security / Compliance | 0 | 0 | 0 | 0.01 | 5.2 | 5.22 |  | Security
CP.02070 | Substation Security Upgrade - Stage 4 | Aug-13 | Security / Compliance | 0 | 0 | 0 | 0 | 4.22 | 4.22 |  | Security
CP.02081 | Secure Tower Bolts (South East Urban Region) | Jun-12 | Security / Compliance | 0 | 0 | 0 | 0.06 | 3.41 | 3.47 |  | Security | Bus Case | $3.5m (escal)
CP.02083 | Secure Tower Bolts(South Western Region) | Jun-12 | Security / Compliance | 0 | 0 | 0 | 0.05 | 1.43 | 1.48 |  | Security | Bus Case | $1.5m (escal)
CP.02084 | Secure Tower Bolts (NW Southern Region) | Jun-12 | Security / Compliance | 0 | 0 | 0 | 0.03 | 2.61 | 2.64 |  | Security | Bus Case | $2.6m (escal)
CP.02085 | Transmission Structure Signs Upgrade (Southern) | May-12 | Security / Compliance | 0 | 0 | 0 | 0.22 | 1.94 | 2.16 |  | Compliance | Bus Case | $2.2m (escal)
CP.02086 | Transmission Structure Signs Upgrade (Northern) | May-12 | Security / Compliance | 0 | 0 | 0 | 0.02 | 2.98 | 3 |  | Compliance | Bus Case | $3.3m (escal)
CP.02087 | Transmission Structure Signs Upgrade (Central) | May-12 | Security / Compliance | 0 | 0 | 0 | 0.02 | 3.99 | 4.01 |  | Compliance | Bus Case | $4.4m (escal)
CP.02088 | South Pine & Palmwoods Protection Replacement | Oct-11 | Replacement | 0 | 0 | 0 | 0.88 | 1.08 | 1.96 |  | Age / Condition / Obsolescence | Bus Case | $2.0m (escal)
CP.02095 | Chalumbin No. 1 Bus Reactor | Dec-12 | Augmentation | 0 | 0 | 0 | 0.11 | 2.85 | 2.95 |  | Reliability
CP.02098 | MPLS Wide Area Network Deployment | Oct-13 | Other | 0 | 0 | 0 | 0.03 | 8.63 | 8.66 |  | Strategic
CP.02100 | Surat Basin Assets | Jun-12 | Augmentation | 0 | 0 | 0 | 0 | 74.7 | 74.7 |  | Demand Growth / Reliability
CP.02102 | 110/33kV System Spare Transformer | Jun-12 | Other | 0 | 0 | 0 | 0.02 | 2.98 | 3 |  | Age / Condition / Obsolescence
CP.02104 | Loganlea 110/33kV No.1 Transformer Replacement | Jan-11 | Replacement | 0 | 0 | 0 | 2.6 | 0.81 | 3.41 |  | Age / Condition / Obsolescence
CP.02107 | 275kV SVC System Spare Transformer | Jun-12 | Replacement | 0 | 0 | 0 | 0.03 | 4.95 | 4.99 |  | Reliability
CP.02114 | Loganlea Substation Site Expansion | Oct-11 | Easement | 0 | 0 | 0 | 2.05 | 0 | 2.05 |  | Reliability | Bus Case | $2.0m (escal)
CP.02207 | Loganlea 110kV Substation Rebuild | Dec-13 | Replacement | 0 | 0 | 0 | 0.63 | 2.03 | 2.66 |  | Age / Condition / Obsolescence | Bus Case | $8.8m (escal)
CP.02294 | Diesel Generator Installation Stage 2 | Oct-12 | Replacement | 0 | 0 | 0.02 | 0.25 | 2.98 | 3.24 |  | Reliability | Bus Case | $5.0m (escal)
CP.02318 | Accurate Fault Location System Stage 2a | Oct-13 | Other | 0 | 0 | 0 | 0.33 | 2.29 | 2.62 |  | Reliability
CP.02412 | Lilyvale-Blackwater 3rd Cct | Oct-12 | Augmentation | 0 | 0 | 0 | 0.28 | 3.66 | 3.94 |  | Reliability | Bus Case | $4.5m (escal)
CP.02444 | Network Performance Monitoring Tools Automation | Jun-12 | Other | 0 | 0 | 0 | 0 | 1.59 | 1.59 |  | Age / Condition / Obsolescence
CP.02489 | OPSWAN Security Replacement Stage 1 | Jun-13 | Replacement | 0 | 0 | 0 | 0 | 2.64 | 2.64 |  | Age / Condition / Obsolescence
CP.02521 | Ebenezer Training Facility Establishment | May-13 | Other | 0 | 0 | 0 | 3.19 | 4.15 | 7.34 |  | Operational
CP.02523 | Automated Collection of Disturbance Data | Jun-13 | Other | 0 | 0 | 0 | 0 | 2.17 | 2.17 |  | Reliability
CP.02527 | SCADA Protocol Enhancement Stage 1 - Conitel Protocol Conversion | Dec-13 | Other | 0 | 0 | 0 | 0 | 1.07 | 1.07 |  | Age / Condition / Obsolescence
CP.02533 | South Pine to Upper Kedron 110kV T/L Life Extension | Mar-14 | Replacement | 0 | 0 | 0 | 0 | 2.74 | 2.74 |  | Age / Condition / Obsolescence
CP.02534 | West Darra to Upper Kedron 110kV T/L Life Extension | Mar-14 | Replacement | 0 | 0 | 0 | 0 | 3.35 | 3.35 |  | Age / Condition / Obsolescence
| Kogan Creek Asset Transfer | Jun-12 | Augmentation | 0 | 0 | 0 | 0 | 25.43 | 25.43 |  | Demand Growth / Reliability
| Outstanding Easement Compensation | ongoing | Easement | 0 | 0 | 0.51 | 1.9 | 1.2 | 3.61 |  | Demand Growth / Reliability
| Miscellaneous Post Commissioning Works |  |  | 7.73 | 1.93 | 1.8 | 3.4 | 0.53 | 15.39
| Other Projects < $1 million spend in period |  |  | 11.01 | 5.95 | 4.89 | 3.61 | 14.07 | 39.54
|  |  | Subtotal | 636.1 | 599.23 | 416.3 | 379.27 | 757.83 | 2788.73
|  |  | ^refers to Categories set out in table 3.1 (e.g Augmentation, Replacement etc) |  |  |  | *Note that values in these columns are estimates only

## Hist Capex - Non-Network
Powerlink pro-forma information statements - 31 May 2011
3.4 HISTORIC CAPEX - Non-Network - by project
|  |  |  | Home |  |  | Link to Historic Capex Instructions - Table 6.2 |  |  | Link to Historic Capex Commentary - Table 5.2
$ million nominal
Yearly expenditure by project
Project ID | Project Description | Commissioning Date | Category^ | 2007/08 | 2008/09 | 2009/10 | 2010/11 | 2011/12 | TOTAL |  | REASON FOR PROJECT | Business Case (Y/N) | Business Case Cost Estimate | Reason for Variance from Cost Estimate / Expected Commissioning Date
CP.97070 | Workflow Development | Apr-12 | Information Technology | 0 | 0 | 0 | 0 | 0.31 | 0.31 |  | Operational
CP.97069 | Tasks Management | Apr-12 | Information Technology | 0 | 0 | 0 | 0.05 | 0.46 | 0.51 |  | Operational
CP.97068 | Risk Management Tool | Dec-12 | Information Technology | 0 | 0 | 0 | 0 | 0.36 | 0.36 |  | Operational
CP.97067 | Dynamic Line Rating | Apr-12 | Information Technology | 0 | 0 | 0 | 0 | 0.26 | 0.26 |  | Operational
CP.97066 | Protection Settings Extended Functions | Apr-12 | Information Technology | 0 | 0 | 0 | 0 | 0.36 | 0.36 |  | Operational
CP.97065 | Enterprise Data Services | Apr-12 | Information Technology | 0 | 0 | 0 | 0 | 0.62 | 0.62 |  | Operational
CP.97063 | ODMS Improvements for Grid Planning | Apr-12 | Information Technology | 0 | 0 | 0 | 0 | 0.31 | 0.31 |  | Age / Condition / Obsolescence
CP.97062 | Network Master Data Integration Stage 2 | Apr-12 | Information Technology | 0 | 0 | 0 | 0 | 0.36 | 0.36 |  | Operational
CP.97061 | Market Impact Assessment | Jun-12 | Information Technology | 0 | 0 | 0 | 0 | 0.31 | 0.31 |  | Operational
CP.97060 | Project Integration and Reporting | Dec-12 | Information Technology | 0 | 0 | 0 | 0 | 0.36 | 0.36 |  | Operational
CP.97058 | Desktop Replacement Program 2011/2012 | Jun-12 | Information Technology | 0 | 0 | 0 | 0 | 1.33 | 1.33 |  | Age / Condition / Obsolescence
CP.97057 | Data Centre Stage 2 (including UPS Replacements) | Jun-12 | Information Technology | 0 | 0 | 0 | 0 | 0.82 | 0.82 |  | Age / Condition / Obsolescence
CP.97056 | Data Centre Replacement Program 2011 / 2012 | Jun-12 | Information Technology | 0 | 0 | 0 | 0 | 1.03 | 1.03 |  | Age / Condition / Obsolescence
CP.97055 | Ratings Calculation Applications | Apr-13 | Information Technology | 0 | 0 | 0 | 0 | 0.51 | 0.51 |  | Operational
CP.97054 | CAD Data Mining | Apr-12 | Information Technology | 0 | 0 | 0 | 0 | 0.31 | 0.31 |  | Operational
CP.97053 | Budgeting and Resource Tool | Dec-12 | Information Technology | 0 | 0 | 0 | 0 | 0.26 | 0.26 |  | Operational
CP.97052 | Service Statistics Redevelopment | Apr-12 | Information Technology | 0 | 0 | 0 | 0 | 0.41 | 0.41 |  | Compliance
CP.97050 | Desktop Replacement Program 2010/2011 | Jun-11 | Information Technology | 0 | 0 | 0 | 1.26 | 0 | 1.26 |  | Age / Condition / Obsolescence | Bus Case | $1.2m (escal)
CP.97030 | Infrastruct Performance & Capty Mangmet | Jun-10 | Information Technology | 0 | 0 | 0.48 | 0 | 0 | 0.48 |  | Additional requirements | Bus Case | $0.4m (escal)
CP.96944 | Data Centre Replacement Program 2010/11 | Jun-11 | Information Technology | 0 | 0 | 0 | 1.06 | 0 | 1.06 |  | Age / Condition / Obsolescence | Bus Case | $1.0m (escal)
CP.96942 | Service Desk Upgrade | Mar-11 | Information Technology | 0 | 0 | 0 | 0.35 | 0 | 0.35 |  | Strategic | Bus Case | $0.3m (escal)
CP.96939 | Application Deployment | Sep-10 | Information Technology | 0 | 0 | 0.12 | 0.19 | 0 | 0.3 |  | Strategic | Bus Case | $0.4m (escal)
CP.96937 | Contract Management System | Feb-13 | Information Technology | 0 | 0 | 0 | 0.08 | 0.53 | 0.61 |  | Operational
CP.96936 | Enterprise Incident Management | Feb-13 | Information Technology | 0 | 0 | 0 | 0 | 0.46 | 0.46 |  | Age / Condition / Obsolescence
CP.96931 | Replace Operations Guide | Apr-12 | Information Technology | 0 | 0 | 0 | 0.06 | 0.31 | 0.37 |  | Age / Condition / Obsolescence | Bus Case | $0.3m (escal)
CP.96929 | Upgrade PQ Maps | Dec-11 | Information Technology | 0 | 0 | 0.07 | 0.26 | 0.25 | 0.58 |  | Age / Condition / Obsolescence | Bus Case | $0.6m (escal)
CP.96928 | Digital Network Connectivity Database Replacement | Jun-13 | Information Technology | 0 | 0 | 0 | 0.47 | 1 | 1.47 |  | Age / Condition / Obsolescence | Bus Case | $0.4m (escal)
CP.96926 | Redevelop Switching Sheet Program | Apr-12 | Information Technology | 0 | 0 | 0 | 0.41 | 0.6 | 1.01 |  | Age / Condition / Obsolescence | Bus Case | $0.08m (escal)
CP.96925 | Ratings Management | Jun-12 | Information Technology | 0 | 0 | 0 | 0.06 | 0.56 | 0.62 |  | Operational | Bus Case | $0.3m (escal)
CP.96924 | Voltage Stability Assessment Tool | Apr-11 | Information Technology | 0 | 0 | 0 | 0 | 0.37 | 0.37 |  | Strategic | Bus Case | $0.4m (escal)
CP.96923 | Asset Performance Management System | Mar-12 | Information Technology | 0 | 0 | 0 | 0 | 0.36 | 0.36 |  | Operational
CP.96920 | Replace 360 Survey Tool | Apr-11 | Information Technology | 0 | 0 | 0 | 0.25 | 0 | 0.25 |  | Age / Condition / Obsolescence | Bus Case | $0.2m (escal)
CP.96919 | SPF Upgrade | Jun-11 | Information Technology | 0 | 0 | 0.03 | 0.79 | 0 | 0.83 |  | Age / Condition / Obsolescence | Bus Case | $0.8m (escal)
CP.96914 | Wireless Deployment - Stage 1 | Jun-11 | Information Technology | 0 | 0 | 0.03 | 0.51 | 0 | 0.54 |  | Security | Bus Case | $0.6m (escal)
CP.96912 | Internet Upgrade | Aug-11 | Information Technology | 0 | 0 | 0 | 0.28 | 0.14 | 0.42 |  | Strategic | Bus Case | $0.2m (escal)
CP.96907 | Data Centre Replacement Program 2009-2010 | Jun-10 | Information Technology | 0 | 0 | 1.81 | 0 | 0 | 1.81 |  | Age / Condition / Obsolescence | Bus Case | $1.9m (escal)
CP.96906 | Desktop Replacement Program 2009-2010 | Jun-10 | Information Technology | 0 | 0 | 1.48 | 0 | 0 | 1.48 |  | Age / Condition / Obsolescence | Bus Case | $1.4m (escal)
CP.96905 | Development Environment Hardware Replace | Aug-09 | Information Technology | 0 | 1.07 | 0.07 | 0 | 0 | 1.15 |  | Age / Condition / Obsolescence | Bus Case | $1.2m (escal)
CP.96904 | Project Server Improvement Project | Jan-11 | Information Technology | 0 | 0 | 0.7 | 0.37 | 0 | 1.07 |  | Additional requirements | Bus Case | $1.0m (escal)
CP.96901 | VMware Enterprise License | Jun-10 | Information Technology | 0 | 0 | 0.69 | 0 | 0 | 0.69 |  | Operational | Bus Case | $0.7m (escal)
CP.96822 | Environment Work Plan Automation | Mar-12 | Information Technology | 0 | 0 | 0 | 0.53 | 0.02 | 0.55 |  | Operational | Bus Case | $0.08 (escal)
CP.96816 | SAN Augmentation | Jan-11 | Information Technology | 0 | 0 | 0 | 0.73 | 0 | 0.73 |  | Age / Condition / Obsolescence | Bus Case | $0.7m (escal)
CP.96810 | Upgrade Desktop Operating System | Jun-11 | Information Technology | 0 | 0 | 0 | 1.35 | 0.01 | 1.36 |  | Strategic | Bus Case | $0.06m (escal)
CP.96807 | Desktop Replacement Program 2008 - 2009 | Jun-09 | Information Technology | 0 | 1.49 | 0.08 | 0 | 0 | 1.57 |  | Age / Condition / Obsolescence | Bus Case | $2.0m (escal)
CP.96806 | Network Plant Master Data (NPR) | Jun-11 | Information Technology | 0 | 0.04 | 0.32 | 0.13 | 0.01 | 0.5 |  | Operational | Bus Case | $0.5m (escal)
CP.96802 | Data Centre Upgrade | Dec-10 | Information Technology | 0 | 0.27 | 0.5 | 0.24 | 0 | 1.02 |  | Age / Condition / Obsolescence | Bus Case | $0.9m (escal)
CP.96801 | Cyberguard Replacement | Mar-09 | Information Technology | 0 | 0.31 | 0 | 0 | 0 | 0.31 |  | Age / Condition / Obsolescence | Bus Case | $0.3m (escal)
CP.96757 | Data Centre Replacement Prog 2008 - 2009 | Jun-09 | Information Technology | 0 | 0.85 | 0.04 | 0 | 0 | 0.89 |  | Age / Condition / Obsolescence | Bus Case | $0.8m (escal)
CP.96755 | Development and Test Environments Upgrade | Jun-10 | Information Technology | 0.01 | 0.38 | 0.84 | 0 | 0 | 1.23 |  | Additional requirements | Bus Case | $1.1m (escal)
CP.96754 | Patch Deployment | Feb-10 | Information Technology | 0 | 0.29 | 0.1 | 0 | 0 | 0.39 |  | Security | Bus Case | $0.4m (escal)
CP.96753 | Installation of Telstra Next G mobile phone | Jun-07 | Information Technology | 0.54 | 0 | 0 | 0 | 0 | 0.54 |  | Obsolescence | Bus Case | $0.5m (escal)
CP.96744 | Enhance OSI Pi | May-09 | Information Technology | 0.67 | 0.49 | 0 | 0 | 0 | 1.16 |  | Additional requirements | Bus Case | $1.1m (escal)
CP.96742 | Automate Resumption Documents | Dec-09 | Information Technology | 0.08 | 0.07 | 0.12 | 0 | 0 | 0.27 |  | Additional requirements | Bus Case | $0.3m (escal)
CP.96741 | Disaster Recovery Virtualisation | Nov-10 | Information Technology | 0.02 | 0 | 0.09 | 0.82 | 0 | 0.93 |  | Age / Condition / Obsolescence | Bus Case | $1.0m (escal)
CP.96739 | Desktop Replacement Program 2007-2008 | Jun-08 | Information Technology | 1.51 | 0.03 | 0 | 0 | 0 | 1.54 |  | Obsolescence | Bus Case | $1.3m (escal)
CP.96738 | Network Information Screens | Dec-07 | Information Technology | 0.33 | 0 | 0 | 0 | 0 | 0.33 |  | Obsolescence | Bus Case | $0.3m (escal)
CP.96736 | Microsoft Exchange 2007 Upgrade | Dec-09 | Information Technology | 0.03 | 0.69 | 0.26 | 0 | 0 | 0.97 |  | Obsolescence | Bus Case | $0.9m (escal)
CP.96731 | Enhance Enterprise Portal | Oct-09 | Information Technology | 0.03 | 0.45 | 0.34 | 0 | 0 | 0.82 |  | Additional requirements | Bus Case | $0.8m (escal)
CP.96728 | Upgrade Grid Planning's Computing Facility | Sep-08 | Information Technology | 0.23 | 0.24 | 0 | 0 | 0 | 0.47 |  | Obsolescence | Bus Case | $0.9m (escal)
CP.96727 | Integrated Video Conferencing Facilities | Nov-09 | Information Technology | 0 | 0.04 | 0.37 | 0 | 0 | 0.42 |  | Age / Condition / Obsolescence | Bus Case | $0.4m (escal)
CP.96725 | SAN Enhancement | Sep-09 | Information Technology | 0.04 | 1.93 | 0.27 | 0 | 0 | 2.24 |  | Additional requirements | Bus Case | $2.4m (escal)
CP.96709 | Project Estimating Tool | Dec-10 | Information Technology | 0.13 | 0.39 | 0.18 | 0.23 | 0 | 0.93 |  | Obsolescence | Bus Case | $0.8m (escal)
CP.96708 | Web-Based Inergration of Power System In | Apr-12 | Information Technology | 0.03 | 0 | 0 | 0 | 0.41 | 0.44 |  | Operational | Bus Case | $0.03m (escal)
CP.96704 | 802.1X Authentication Client | Jan-10 | Information Technology | 0.03 | 0.22 | 0.41 | 0 | 0 | 0.66 |  | Security | Bus Case | $0.7m (escal)
CP.96703 | Patch Management Tool | Nov-08 | Information Technology | 0.22 | 0.03 | 0 | 0 | 0 | 0.25 |  | Additional requirements | Bus Case | $0.3m (escal)
CP.96655 | Project Scheduling & Reporting | Jun-10 | Information Technology | 0.37 | 0.04 | 0.24 | 0.01 | 0 | 0.65 |  | Additional requirements | Bus Case | $1.5m (escal)
CP.96654 | SAP Upgrade | Mar-09 | Information Technology | 1.71 | 0.27 | 0 | 0 | 0 | 1.98 |  | Obsolescence | Bus Case | $1.8m (escal)
CP.96602 | Redevelop PrSDB | Jun-10 | Information Technology | 0.03 | 0.1 | 0.22 | 0 | 0 | 0.35 |  | Obsolescence | Bus Case | $0.3m (escal)
CP.96601 | Replace Grid DB | Dec-09 | Information Technology | 1.44 | 1.34 | 0.59 | 0 | 0 | 3.37 |  | Obsolescence | Bus Case | $2.0m (escal)
CP.96517 | Configuration Management System | Nov-09 | Information Technology | 0.2 | 0.22 | 0.25 | 0 | 0 | 0.67 |  | Additional requirements | Bus Case | $1.0m (escal)
CP.96506 | Incident Management System | Nov-07 | Information Technology | 0.56 | 0.08 | 0 | 0 | 0 | 0.64 |  | Additional requirements | Bus Case | $1.0m (escal)
CP.96501 | Outage Management System | Dec-12 | Information Technology | 0.05 | 0.31 | 0.2 | 1.05 | 0.63 | 2.24 |  | Additional requirements | Bus Case | $2.2m (escal)
| NN - Buildings | ongoing | Commercial Buildings | 4.4 | 6.67 | 10.62 | 14.68 | 4.19 | 40.55 |  | Replacement
| NN - Tools and Equipment | ongoing | Moveable Plant | 1.31 | 1.19 | 1.4 | 1.8 | 1.77 | 7.48 |  | Replacement
CP.98100 | Fleet * | ongoing | Motor Vehicles | 0.77 | 1.29 | 3.31 | 5.27 | 5.85 | 16.48 |  | Annual Cycle
| Other IT projects < $250K spend in period |  | Information Technology | 2.15 | 1.07 | 0.64 | 1.37 | 0.81 | 6.04
| * Adjusted to include proceeds from fleet disposals 07/08, 08/09 and 09/10 |  | Subtotal | 16.88 | 21.86 | 26.87 | 34.64 | 26.64 | 126.89

## Forecast Capex by Category
Powerlink pro-forma information statements - 31 May 2011
4.1 FORECAST CAPEX by project category |  |  | Home |  | Link to Forecast Capex Instructions - Table 6.3
$ million, real (2011/12 mid year)
Project Category |  |  | 2012/13 | 2013/14 | 2014/15 | 2015/16 | 2016/17 | TOTAL
NETWORK
LOAD DRIVEN | Augmentation |  | 415.04 | 489.19 | 261.27 | 316.06 | 248.08 | 1729.65
| Easements |  | 24.85 | 31.45 | 46.27 | 54.34 | 32.52 | 189.42
| Connections |  | 15.36 | 12.29 | 8.04 | 8.15 | 11.28 | 55.13
NON-LOAD DRIVEN | Replacements |  | 300.06 | 241.47 | 260.02 | 227.11 | 200.38 | 1229.04
| Security/Compliance |  | 18.73 | 18.78 | 8.73 | 2.79 | 1.66 | 50.69
| Other |  | 29.92 | 29.94 | 19.57 | 20.45 | 9.98 | 109.86
NON NETWORK
BUSINESS IT |  | Information Technology | 15.75 | 14.93 | 16.11 | 15.6 | 15.67 | 78.05
SUPPORT THE BUSINESS |  | Commercial Buildings | 5.74 | 3.3 | 3.11 | 2.87 | 3.09 | 18.1
|  | Motor Vehicles | 2.39 | 2.65 | 3.43 | 2.65 | 3.67 | 14.79
|  | Moveable Plant | 1.93 | 1.8 | 1.72 | 1.83 | 1.86 | 9.13
TOTAL HISTORIC CAPEX |  |  | 829.77 | 845.8 | 628.27 | 651.84 | 528.19 | 3483.86

## Forecast Capex by Asset Class
Powerlink pro-forma information statements - 31 May 2011
4.2 FORECAST CAPEX by asset class | Home |  |  | Link to Capex Instructions - Table 6.3
$ million, (2011/12 mid year)
| 2012/13 | 2013/14 | 2014/15 | 2015/16 | 2016/17 | TOTAL
Asset class
Transmission Lines (Overhead) | 386.29 | 418.46 | 207.76 | 233.09 | 215.95 | 1461.54
Transmission Lines (Underground) | 2.11 | 7.57 | 12.74 | 10.7 | 2.97 | 36.1
Transmission Lines (Refit) | 22.01 | 34.92 | 51.55 | 25.83 | 6.98 | 141.28
Substations Primary Plant | 215.08 | 181.61 | 156.89 | 168.73 | 142.31 | 864.62
Substations Secondary Systems | 107.88 | 117.19 | 99.73 | 84.37 | 79.62 | 488.8
Communications Assets | 33.12 | 23.89 | 23.04 | 18.31 | 9.03 | 107.39
Communications - Civil Works | 0 | 0 | 0 | 0 | 0 | 0
Network Switching Centres | 12.57 | 8.04 | 5.93 | 33.52 | 14.52 | 74.58
Land | 3.68 | 4.02 | 3.91 | 0.94 | 0.22 | 12.77
Easements | 21.24 | 27.43 | 42.35 | 53.4 | 32.3 | 176.71
0
Commercial Buildings | 5.73 | 3.29 | 3.1 | 2.87 | 3.09 | 18.07
Computer Equipment | 15.75 | 14.93 | 16.11 | 15.6 | 15.67 | 78.05
Office Furniture & Miscellaneous | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.03
Office Machines | 0 | 0 | 0 | 0 | 0 | 0
Vehicles | 2.39 | 2.65 | 3.43 | 2.65 | 3.67 | 14.79
Moveable Plant | 1.93 | 1.8 | 1.72 | 1.83 | 1.86 | 9.13
Insurance Spares | 0 | 0 | 0 | 0 | 0 | 0
0
Equity raising costs | 24.5 | 0 | 0 | 0 | 0 | 24.5
TOTAL CAPEX | 854.26 | 845.8 | 628.27 | 651.84 | 528.19 | 3508.35

## Forecast Capex - Network
Powerlink pro-forma information statements - 31 May 2011
4.3 FORECAST CAPEX - NETWORK - by project
[5 empty] | Home |  |  | Link to Forecast Capex Instructions - Table 6.3 |  |  | Link to Forecast Capex Commentary - Table 5.3
$ million, (2011/12 mid year)
Yearly expenditure by project
Project ID | Project Description | Estimated Commissioning Date | Category^ | Scenario | 2012/13 | 2013/14 | 2014/15 | 2015/16 | 2016/17 | TOTAL |  | REASON FOR PROJECT | Reg Test / Business Case (Y/N) | Reg Test / Business Case Cost Estimate | Reason for Variance from Cost Estimate / Expected Commissioning Date
CP.00639 | Nebo/Ross Easement Project | Apr-09 | Easement | non scenario | 0.07 | 0 | 0 | 0 | 0 | 0.07 |  | Reliability | Approval Memo | $0.82m (escal)
CP.00880 | Tully - Cardwell 132kV Line Replacement | Oct-12 | Replacement | non scenario | 13.55 | 0 | 0 | 0 | 0 | 13.55 |  | Age / Condition / Obsolescence | Bus Case | $57.3m (escal)
CP.00882 | Cardwell - Ingham South 132kV Line Replacement | Dec-13 | Replacement | non scenario | 34.39 | 16.04 | 0 | 0 | 0 | 50.43 |  | Age / Condition / Obsolescence | Bus Case | $60.3m (escal)
CP.01016 | Nebo Secondary Systems Replacement | Oct-16 | Replacement | non scenario | 0 | 1.44 | 9.77 | 7.56 | 1.26 | 20.03 |  | Age / Condition / Obsolescence
CP.01017 | Tarong Secondary Systems Replacement | Aug-11 | Replacement | non scenario | 0.01 | 0 | 0 | 0 | 0 | 0.01 |  | Obsolescence / Safety | Bus Case | $21.9m (escal)
CP.01019 | Moranbah Secondary Systems Replacement | Oct-12 | Replacement | non scenario | 2.73 | 0 | 0 | 0 | 0 | 2.73 |  | Age / Condition / Obsolescence | Bus Case | $17.4m (escal)
CP.01021 | Lilyvale Secondary Systems Replacement | Jun-12 | Replacement | non scenario | 0.04 | 0 | 0 | 0 | 0 | 0.04 |  | Age / Condition / Obsolescence | Bus Case | $10.5m (escal)
CP.01064 | Gin Gin Secondary Systems Replacement | Mar-12 | Replacement | non scenario | 0.17 | 0 | 0 | 0 | 0 | 0.17 |  | Obsolescence / Safety | Bus Case | $12.3m (escal)
CP.01078 | Nudgee 275/110kV Easement Project | Oct-08 | Easement | non scenario | 1.46 | 0 | 0 | 0 | 0 | 1.46 |  | Reliability | Bus Case | $6.2m (escal)
CP.01091 | Garbutt - Alan Sherriff T/L Replacement | Oct-12 | Replacement | non scenario | 1.86 | 0 | 0 | 0 | 0 | 1.86 |  | Age / Condition / Obsolescence
CP.01100 | Middle Ridge - Greenbank Easement Project | Sep-07 | Easement | non scenario | 0.98 | 0 | 0 | 0 | 0 | 0.98 |  | Demand Growth / Reliability | Bus Case | $5.5m (escal)
CP.01127 | Loganlea 110kV Secondary Systems Replacement | Jun-14 | Replacement | non scenario | 2.55 | 2.32 | 0.04 | 0 | 0 | 4.91 |  | Age / Condition / Obsolescence
CP.01128 | Mackay Substation Replacement | Oct-15 | Replacement | non scenario | 0 | 10.08 | 17.7 | 3.49 | 0 | 31.27 |  | Age / Condition / Obsolescence
CP.01129 | Mackay Secondary Systems Replacement | Oct-15 | Replacement | non scenario | 0.74 | 5.17 | 4.03 | 0.67 | 0 | 10.61 |  | Age / Condition / Obsolescence
CP.01132 | Rockhampton Substation Replacement | Jun-15 | Replacement | non scenario | 0.15 | 3.04 | 2.46 | 0 | 0 | 5.66 |  | Age / Condition / Obsolescence
CP.01135 | Redbank Plains Secondary System Replacement | Jul-12 | Replacement | non scenario | 0.52 | 0 | 0 | 0 | 0 | 0.52 |  | Age / Condition / Obsolescence | Bus Case | $4.6m (escal)
CP.01146 | Blackwater Substation Replacement | Jul-15 | Replacement | non scenario | 0.17 | 7 | 6.45 | 0.19 | 0 | 13.81 |  | Age / Condition / Obsolescence
CP.01148 | Wurdong Secondary Systems Replacement | Oct-15 | Replacement | non scenario | 0.64 | 4.54 | 3.53 | 0.59 | 0 | 9.3 |  | Age / Condition / Obsolescence
CP.01151 | Calvale Secondary Systems Replacement | Oct-18 | Replacement | non scenario | 0 | 0 | 0 | 1.2 | 8.17 | 9.36 |  | Age / Condition / Obsolescence
CP.01161 | Rocklea Secondary Systems Replacement | Oct-13 | Replacement | non scenario | 5.59 | 2.63 | 0 | 0 | 0 | 8.22 |  | Age / Condition / Obsolescence | Bus Case | $9.5m (escal)
CP.01162 | Callemondah Secondary Systems Replacement | Jul-17 | Replacement | non scenario | 0 | 0 | 0.87 | 2.19 | 1.35 | 4.41 |  | Age / Condition / Obsolescence
CP.01163 | Swanbank B 275kV Substation Rebuild | Mar-13 | Replacement | non scenario | 15.18 | 0.01 | 0 | 0 | 0 | 15.19 |  | Age / Condition / Obsolescence | Bus Case | $52.6m (escal)
CP.01164 | Newlands Secondary Systems Replacement | Jun-16 | Replacement | non scenario | 0 | 1.33 | 2.39 | 1.51 | 0 | 5.23 |  | Age / Condition / Obsolescence
CP.01178 | Kamerunga Secondary Systems Replacement | Oct-17 | Replacement | non scenario | 0 | 0 | 0.26 | 1.78 | 1.39 | 3.43 |  | Age / Condition / Obsolescence
CP.01179 | Turkinje Secondary Systems Replacement | Jun-17 | Replacement | non scenario | 0 | 0 | 1.48 | 2.66 | 1.69 | 5.82 |  | Age / Condition / Obsolescence
CP.01191 | Brisbane South Area Easement Project | Jul-14 | Easement | non scenario | 1.27 | 7.08 | 6.22 | 0.91 | 0 | 15.48 |  | Reliability | Bus Case | $14.9m (escal)
CP.01246 | Mackay-Proserpine Transm Line Life Extension | Jul-12 | Replacement | non scenario | 0.03 | 0 | 0 | 0 | 0 | 0.03 |  | Age / Condition / Obsolescence | Bus Case | $5.0m ($2005/06) $5.3m (escal)
CP.01271 | Woologa to North Coast 275kV DCST Easement Project | Apr-12 | Easement | non scenario | 1.01 | 1.9 | 4.64 | 2.07 | 0 | 9.63 |  | Reliability | Bus Case | $6.9m (escal)
CP.01292 | Broadsound Secondary Systems Replacement | Nov-12 | Replacement | non scenario | 2.07 | 0 | 0 | 0 | 0 | 2.07 |  | Age / Condition / Obsolescence | Bus Case | $13.1m (escal)
CP.01293 | Ross Secondary Systems Replacement | Oct-18 | Replacement | non scenario | 0 | 0 | 0 | 1.63 | 11.13 | 12.76 |  | Age / Condition / Obsolescence
CP.01301 | Power Quality Monitoring Stages 1&2 | Jun-13 | Other | non scenario | 1.76 | 0.1 | 0 | 0 | 0 | 1.86 |  | Operational | Bus Case | $4.4m (escal)
CP.01310 | Metropolitan SDH Loop Upgrade | Oct-12 | Replacement | non scenario | 0.05 | 0 | 0 | 0 | 0 | 0.05 |  | Age / Condition / Obsolescence | Bus Case | $3.4m (escal)
CP.01338 | Ingham to Tully Easement Project | Jun-11 | Easement | non scenario | 2.44 | 0.48 | 0 | 0 | 0 | 2.91 |  | Age / Condition / Obsolescence | Bus Case | $3.4m (escal)
CP.01345 | Kareeya to Chalumbin ADSS Replacement | Jun-14 | Replacement | non scenario | 0.21 | 0.41 | 0 | 0 | 0 | 0.62 |  | Age / Condition / Obsolescence | Bus Case | $1.8m (escal)
CP.01385 | Tarong Bus Rating Upgrade | Jun-13 | Other | non scenario | 2.21 | 0 | 0 | 0 | 0 | 2.21 |  | Age / Condition / Obsolescence
CP.01393 | Stuart North 132/66kV Substation Site | Jul-19 | Easement | non scenario | 0 | 0 | 0 | 0 | 0.16 | 0.16 |  | Reliability
CP.01396 | Nebo 275/132kV No. 2 Transformer Replacement | Oct-14 | Replacement | non scenario | 3.33 | 10.98 | 1.91 | 0 | 0 | 16.23 |  | Age / Condition / Obsolescence
CP.01397 | Nebo 275/132kV No. 1 Transformer Replacement | Jul-13 | Replacement | non scenario | 8.41 | 0.82 | 0 | 0 | 0 | 9.23 |  | Age / Condition / Obsolescence
CP.01398 | Mackay to Proserpine (Proserpine to Glenella) Decomm | Oct-14 | Replacement | non scenario | 4.36 | 8.25 | 0.79 | 0 | 0 | 13.4 |  | Age / Condition / Obsolescence
CP.01399 | Loganlea 110/33kV Transformer Augmentation | Oct-13 | Connection | non scenario | 0.36 | 0 | 0 | 0 | 0 | 0.36 |  | Reliability | Bus Case | $5.9m (escal)
CP.01401 | Woolooga No.1 & 2 Transformers Replacement | Jun-13 | Replacement | non scenario | 4.98 | 0.29 | 0 | 0 | 0 | 5.27 |  | Age / Condition / Obsolescence | Bus Case | $9.5m (escal)
CP.01415 | Loganlea 110kV Extension (Jimboomba) | Apr-12 | Connection | non scenario | 0 | 0 | 0 | 0.02 | 0 | 0.02 |  | Reliability | Bus Case | $1.9m (escal)
CP.01417 | Blackwall iPASS Sec Sys Replacement | Oct-15 | Replacement | non scenario | 1.85 | 13.12 | 10.15 | 1.68 | 0 | 26.81 |  | Age / Condition / Obsolescence
CP.01420 | Woree - Kamerunga 132kV Line Life Extension | Oct-12 | Replacement | non scenario | 2.83 | 0 | 0 | 0 | 0 | 2.83 |  | Age / Condition / Obsolescence
CP.01422 | Western Downs Substn Site & Easement Project | Jun-11 | Easement | non scenario | 1.4 | 0 | 0 | 0 | 0 | 1.4 |  | Reliability | Bus Case | $3.3m (escal)
CP.01429 | South West Queensland Augmentation | Oct-12 | Augmentation | non scenario | 12.18 | 0.03 | 0 | 0 | 0 | 12.21 |  | Reliability | Reg Test | $229.2m ($2008/09)
CP.01430 | SWQ to SEQ Easement Project No. 2 | Oct-11 | Easement | non scenario | 0.49 | 0.48 | 2.44 | 0 | 0 | 3.41 |  | Reliability | Bus Case | $8.8m (escal)
CP.01435 | DWDM Network Diversity - Far North | Oct-14 | Other | non scenario | 0.76 | 0.84 | 0.13 | 0 | 0 | 1.74 |  | Reliability
CP.01438 | Brisbane North Area 275kV Easement Project | Oct-15 | Easement | non scenario | 0.29 | 0.44 | 1.45 | 7.62 | 2.1 | 11.91 |  | Reliability | Bus Case | $13.4m (escal)
CP.01443 | Tennyson Secondary Systems Replacement | May-15 | Replacement | non scenario | 2.45 | 4.27 | 2.41 | 0 | 0 | 9.13 |  | Age / Condition / Obsolescence
CP.01449 | Townsville Microwave Rationalisation | Jun-14 | Replacement | non scenario | 0.95 | 0.44 | 0 | 0 | 0 | 1.38 |  | Age / Condition / Obsolescence
CP.01451 | EMS Software Upgrade | Jun-17 | Other | non scenario | 0 | 0 | 0 | 3.61 | 1.67 | 5.28 |  | Age / Condition / Obsolescence
CP.01453 | Cardwell Transformers Replacement | Jun-13 | Replacement | non scenario | 4.27 | 0.19 | 0 | 0 | 0 | 4.46 |  | Age / Condition / Obsolescence
CP.01454 | Kamma 275/132kV Substation Site | Oct-17 | Easement | non scenario | 0 | 0 | 0.21 | 0.36 | 0.24 | 0.81 |  | Reliability
CP.01454.2 | Kamma 275/132kV Substation Site | Oct-18 | Easement | non scenario | 0 | 0 | 0 | 0.03 | 0.12 | 0.15 |  | Reliability
CP.01459 | Upper Kedron Secondary Systems Replacement | Oct-15 | Replacement | non scenario | 0.55 | 3.88 | 3.01 | 0.5 | 0 | 7.94 |  | Age / Condition / Obsolescence
CP.01466 | Southern Region SDH Loop | Oct-12 | Other | non scenario | 0.38 | 0 | 0 | 0 | 0 | 0.38 |  | Age / Condition / Obsolescence | Bus Case | $4.4m (escal)
CP.01471 | NMS Common Service Upgrade | Dec-12 | Other | non scenario | 0.37 | 0 | 0 | 0 | 0 | 0.37 |  | Age / Condition / Obsolescence
CP.01473 | Tully Secondary Systems Replacement | Oct-16 | Replacement | non scenario | 0 | 0.55 | 3.74 | 2.9 | 0.48 | 7.68 |  | Age / Condition / Obsolescence
CP.01475 | Kareeya - Tully 132kV Line Recovery | Dec-13 | Replacement | non scenario | 6.64 | 0 | 0 | 0 | 0 | 6.64 |  | Age / Condition / Obsolescence | Bus Case | $9.2m (escal)
CP.01488 | Molendinar Substation Site Expansion | Oct-12 | Easement | non scenario | 0.15 | 0.02 | 0 | 0 | 0 | 0.17 |  | Reliability | Bus Case | $2.6m (escal)
CP.01489 | Cairns Region 132kV Easement Project | Oct-15 | Easement | non scenario | 0.25 | 0.44 | 0.3 | 0.2 | 0 | 1.2 |  | Reliability
CP.01489.2 | Cairns Region 132kV Easement Project | Oct-16 | Easement | non scenario | 0 | 0.95 | 4.18 | 9.12 | 1.6 | 15.84 |  | Reliability
CP.01493 | Bulli Creek iPass Secondary System Replacement | Oct-13 | Replacement | non scenario | 6.61 | 2.26 | 0 | 0 | 0 | 8.88 |  | Age / Condition / Obsolescence | Bus Case | $17.1m (escal)
CP.01494 | Millmerran iPass Secondary System Replacement | Oct-12 | Replacement | non scenario | 0.05 | 0 | 0 | 0 | 0 | 0.05 |  | Age / Condition / Obsolescence
CP.01530 | Fibre Replacement | Jun-15 | Replacement | non scenario | 0 | 2.55 | 1.16 | 0 | 0 | 3.71 |  | Age / Condition / Obsolescence
CP.01548 | Kareeya Substation Redevelopment | Oct-12 | Replacement | non scenario | 2.48 | 0 | 0 | 0 | 0 | 2.48 |  | Age / Condition / Obsolescence | Bus Case | $7.9m (escal)
CP.01549 | Moura Switchyard Replacement | Apr-15 | Replacement | non scenario | 1.31 | 12.21 | 6.9 | 0 | 0 | 20.43 |  | Age / Condition / Obsolescence
CP.01563 | Bouldercombe Secondary Systems Replacement | Nov-13 | Replacement | non scenario | 4.12 | 1.21 | 0.01 | 0 | 0 | 5.34 |  | Age / Condition / Obsolescence | Bus Case | $18.7m (escal)
CP.01566 | Chalumbin Secondary Systems Replacement | Dec-13 | Replacement | non scenario | 2.99 | 2.06 | 0.02 | 0 | 0 | 5.07 |  | Age / Condition / Obsolescence | Bus Case | $12.5m (escal)
CP.01579 | Peak Downs Secondary Systems Replacement | Jun-17 | Replacement | non scenario | 0 | 0 | 0.94 | 1.7 | 1.08 | 3.72 |  | Age / Condition / Obsolescence
CP.01580 | Norwich Park Secondary Systems Replacement | Sep-17 | Replacement | non scenario | 0 | 0 | 0.51 | 1.93 | 1.49 | 3.93 |  | Age / Condition / Obsolescence
CP.01581 | North Goonyella Secondary Systems Replacement | May-16 | Replacement | non scenario | 0 | 0.53 | 0.91 | 0.51 | 0 | 1.95 |  | Age / Condition / Obsolescence
CP.01582 | Stanwell Secondary Systems Replacement | Oct-14 | Replacement | non scenario | 8.86 | 7.07 | 1.17 | 0 | 0 | 17.11 |  | Age / Condition / Obsolescence
CP.01620 | Bouldercombe 275/132kV Transformer Reinf | Oct-12 | Augmentation | non scenario | 2.41 | 0.2 | 0 | 0 | 0 | 2.61 |  | Reliability | Reg Test | $13.9m ($2009/10)
CP.01623 | Kamerunga Bus Section Circuit Breaker | Oct-17 | Other | non scenario | 0 | 0 | 0 | 1.44 | 2.53 | 3.96 |  | Reliability
CP.01635 | Abermain Secondary Systems Replacement | Oct-18 | Replacement | non scenario | 0 | 0 | 0 | 0.68 | 4.62 | 5.3 |  | Age / Condition / Obsolescence
CP.01636 | Wandoo Secondary Systems Replacement | Jun-18 | Replacement | non scenario | 0 | 0 | 0 | 0.92 | 1.66 | 2.58 |  | Age / Condition / Obsolescence
CP.01640 | Dan Gleeson Secondary Systems Replacement | Jun-19 | Replacement | non scenario | 0 | 0 | 0 | 0 | 1.81 | 1.81 |  | Age / Condition / Obsolescence
CP.01653 | Sumner Tee to Richlands 110kV Life Extension | Oct-14 | Replacement | non scenario | 1.57 | 2.92 | 0.28 | 0 | 0 | 4.76 |  | Age / Condition / Obsolescence
CP.01655 | Runcorn to Belmont 110kV Life Extension | Oct-15 | Replacement | non scenario | 0 | 2.62 | 4.86 | 0.46 | 0 | 7.94 |  | Age / Condition / Obsolescence
CP.01658 | Richlands Primary & Secondary Plant Replacement | Apr-13 | Replacement | non scenario | 16.16 | 0 | 0 | 0 | 0 | 16.16 |  | Age / Condition / Obsolescence | Bus Case | $30.0 m (escal)
CP.01666 | Dysart Substation Replacement | Oct-17 | Replacement | non scenario | 0 | 0 | 0 | 4.55 | 8 | 12.55 |  | Age / Condition / Obsolescence
CP.01668 | Comms Site Access & Security (Part A) | Dec-12 | Security / Compliance | non scenario | 0.27 | 0 | 0 | 0 | 0 | 0.27 |  | Security | Bus Case | $1.5m (escal)
CP.01677 | SEQ No.2 Substation Site | Dec-15 | Easement | non scenario | 0.01 | 0 | 0 | 0 | 0 | 0.01 |  | Reliability | Bus Case | $1.2m (escal)
CP.01679 | Mudgeeraba 110kV Replacement | Oct-17 | Replacement | non scenario | 0 | 0 | 0 | 9.52 | 16.74 | 26.26 |  | Age / Condition / Obsolescence
CP.01689 | Upper Kedron 275/110/11kV Substation Site | Sep-14 | Easement | non scenario | 0.05 | 0 | 0 | 0 | 0 | 0.05 |  | Reliability | Bus Case | $1.7m (escal)
CP.01690 | Greenbank to South Coast Line Easement Project | Oct-18 | Easement | non scenario | 0 | 0 | 0 | 0.27 | 0.47 | 0.75 |  | Reliability
CP.01704 | Proserpine Substation Replacement | Oct-16 | Replacement | non scenario | 0 | 0 | 6.18 | 10.82 | 2.14 | 19.15 |  | Age / Condition / Obsolescence
CP.01705 | Calvale - Stanwell 275kV DCST Line | Oct-13 | Augmentation | non scenario | 68.9 | 7.66 | 0 | 0 | 0 | 76.56 |  | Reliability | Reg Test | $104.6m ($2009/10) $116.8m (escal)
CP.01710 | Gin Gin Substation Replacement | Oct-16 | Replacement | non scenario | 0 | 0 | 15.09 | 26.32 | 5.2 | 46.6 |  | Age / Condition / Obsolescence
CP.01732 | Runcorn 110kv Substation Replacement | Apr-13 | Replacement | non scenario | 7.7 | 0 | 0 | 0 | 0 | 7.7 |  | Age / Condition / Obsolescence | Bus Case | $15.4m (escal)
CP.01758 | Pioneer Valley 132/66kV Transformer Replacement | Oct-12 | Connection | non scenario | 0.01 | 0 | 0 | 0 | 0 | 0.01 |  | Reliability | Bus Case | $4.9m (escal)
CP.01780 | Calliope River Substation Establishment | Jun-13 | Replacement | non scenario | 32.38 | 3.69 | 0 | 0 | 0 | 36.06 |  | Age / Condition / Obsolescence | Bus Case | $149.1m (escal)
CP.01788 | Palmwoods Primary Plant Replacement St 1 | Oct-13 | Replacement | non scenario | 9.13 | 1.58 | 0 | 0 | 0 | 10.71 |  | Age / Condition / Obsolescence | Bus Case | $14.0m (escal)
CP.01803 | EMS FEP's Upgrade | Jul-13 | Replacement | non scenario | 0.8 | 0.04 | 0 | 0 | 0 | 0.84 |  | Age / Condition / Obsolescence
CP.01804 | EMS Wallboard Replacement | Dec-13 | Replacement | non scenario | 1.08 | 0.22 | 0 | 0 | 0 | 1.3 |  | Age / Condition / Obsolescence
CP.01807 | EMS Hardware Replacement | Oct-13 | Replacement | non scenario | 1.65 | 0.26 | 0 | 0 | 0 | 1.9 |  | Age / Condition / Obsolescence
CP.01811 | North Moreton 275/110kV Substn Site & Easement Project | Oct-15 | Easement | non scenario | 0.13 | 0.7 | 0.56 | 0.91 | 0.88 | 3.19 |  | Reliability | Bus Case | $5.4m (escal)
CP.01816 | VOIP Deployment Stage 1 | Jun-13 | Other | non scenario | 3.86 | 0 | 0 | 0 | 0 | 3.86 |  | Strategic
CP.01822 | Upper Kedron to Ashgrove West 110kV Replacement | Oct-15 | Replacement | non scenario | 0 | 4.66 | 8.42 | 0.79 | 0 | 13.87 |  | Age / Condition / Obsolescence
CP.01826 | Southern Brisbane 275kV Easement Project No. 1 | Oct-14 | Easement | non scenario | 0.04 | 1.27 | 1.37 | 0 | 0 | 2.68 |  | Reliability | Bus Case | $3.7m (escal)
CP.01830 | Calvale - Stanwell Easement Project | Sep-11 | Easement | non scenario | 0.1 | 0 | 0 | 0 | 0 | 0.1 |  | Reliability | Bus Case | $2.4m (escal)
CP.01831 | Murarrie - Nudgee 275kV Easement Project | Aug-12 | Easement | non scenario | 1.01 | 1.99 | 2.1 | 0 | 0 | 5.1 |  | Reliability | Bus Case | $5.9 m (escal)
CP.01845 | North West Brisbane Cable Replacement Easement Project | Oct-14 | Easement | non scenario | 0.35 | 0.24 | 0.16 | 0 | 0 | 0.75 |  | Age / Condition / Obsolescence
CP.01845.2 | North West Brisbane Easement Project | Oct-15 | Easement | non scenario | 0.28 | 1.21 | 2.66 | 0.48 | 0 | 4.62 |  | Age / Condition / Obsolescence
CP.01855 | South West Brisbane 275kV Easement Project | Oct-17 | Easement | non scenario | 0 | 0 | 0.1 | 0.18 | 0.12 | 0.4 |  | Reliability
CP.01862 | South Moreton 275/110kV Substation Site and Easement Project | Oct-17 | Easement | non scenario | 0 | 0 | 0.1 | 0.18 | 0.12 | 0.4 |  | Strategic
CP.01862.2 | South Moreton 275/110kV Substation Site and Easement Project | Oct-18 | Easement | non scenario | 0 | 0 | 0 | 1.04 | 4.46 | 5.5 |  | Strategic
CP.01867 | Northern Bowen Basin Easement Project | Jun-12 | Easement | non scenario | 1.07 | 0.16 | 0 | 0 | 0 | 1.22 |  | Reliability | Bus Case | $3.0m (escal)
CP.01875 | Halys-Blackwall 500kV | Oct-14 | Augmentation | non scenario | 93.72 | 223.71 | 40.36 | 0.02 | 0 | 357.82 |  | Reliability | Reg Test | $387.3m ($2008/09)
CP.01878 | Millmerran to Bulli Creek Easement Project | Nov-19 | Easement | non scenario | 0 | 0 | 0 | 0 | 0.31 | 0.31 |  | Reliability
CP.01918 | Strathmore iPASS Secondary Systems Replacement | Mar-13 | Replacement | non scenario | 8.2 | 0 | 0 | 0 | 0 | 8.2 |  | Age / Condition / Obsolescence | Bus Case | $8.4m (escal)
CP.01920 | Braemar iPASS Secondary Systems Replacement | Oct-14 | Replacement | non scenario | 8.98 | 7.25 | 1.2 | 0 | 0 | 17.42 |  | Age / Condition / Obsolescence
CP.01921 | Coppabella Secondary Systems Replacement | Jun-17 | Replacement | non scenario | 0 | 0 | 1.34 | 2.41 | 1.53 | 5.29 |  | Age / Condition / Obsolescence
CP.01922 | Grantleigh Secondary Systems Replacement | Jun-17 | Replacement | non scenario | 0 | 0 | 1.21 | 2.16 | 1.37 | 4.74 |  | Age / Condition / Obsolescence
CP.01923 | Gregory Secondary Systems Replacement | Sep-18 | Replacement | non scenario | 0 | 0 | 0 | 0.58 | 2.22 | 2.8 |  | Age / Condition / Obsolescence
CP.01924 | System Spare 330/275kV Transformer | Jun-12 | Other | non scenario | 0.01 | 0 | 0 | 0 | 0 | 0.01 |  | Reliability | Bus Case | $8.2m (escal)
CP.01931 | Loganlea 4th 110kV 50 MVAr Capacitor Bank | Apr-12 | Augmentation | non scenario | 0.01 | 0 | 0 | 0 | 0 | 0.01 |  | Reliability | Reg Test | $1.9m ($2009/10) $2.0m (escal)
CP.01960 | Yabulu South to Ingham Easement Project | Oct-10 | Easement | non scenario | 0.98 | 0 | 0 | 0 | 0 | 0.98 |  | Age / Condition / Obsolescence | Bus Case | $2.6m (escal)
CP.01962 | Callide to Moura 132kV SCST Easement Project | Oct-15 | Easement | non scenario | 0.38 | 0.66 | 0.45 | 0.3 | 0 | 1.79 |  | Reliability
CP.01962.2 | Callide to Moura 132kV SCST Easement Project | Oct-16 | Easement | non scenario | 0 | 0.28 | 1.17 | 2.45 | 0.41 | 4.32 |  | Reliability
CP.01965 | Bulli Creek to Braemar Easement Project | Nov-19 | Easement | non scenario | 0 | 0 | 0 | 0 | 0.35 | 0.35 |  | Strategic
CP.01972 | Pioneer Valley Secondary Systems Replacement | Oct-15 | Replacement | non scenario | 0.55 | 3.86 | 2.99 | 0.49 | 0 | 7.89 |  | Age / Condition / Obsolescence
CP.01976 | Rocklea 110kV Feeder Bays for Woollongabba | Oct-13 | Connection | non scenario | 3.59 | 0.35 | 0 | 0 | 0 | 3.94 |  | Reliability
CP.01999 | Tarong Secondary Systems Replacement - Stage 2 | Jul-18 | Replacement | non scenario | 0 | 0 | 0 | 2.36 | 6 | 8.36 |  | Age / Condition / Obsolescence
CP.02000 | Turkinje 132kV Capacitor Bank | Oct-12 | Augmentation | non scenario | 0.47 | 0 | 0 | 0 | 0 | 0.47 |  | Reliability | Bus Case | $2.5m (escal)
CP.02012 | Ross SVC Secondary System Replacement | Sep-12 | Replacement | non scenario | 6.16 | 0 | 0 | 0 | 0 | 6.16 |  | Age / Condition / Obsolescence | Bus Case | $8.9m (escal)
CP.02022 | Surat Basin Easement Project No.2 | Sep-12 | Easement | non scenario | 2.16 | 0.19 | 0 | 0 | 0 | 2.35 |  | Reliability | Bus Case | $4.5m (escal)
CP.02023 | Surat Basin Easement Project No.1 | Mar-12 | Easement | non scenario | 1.26 | 0 | 0 | 0 | 0 | 1.26 |  | Reliability | Bus Case | $3.8m (escal)
CP.02030 | Columboola to Wandoan Area Network Augmentation | Mar-13 | Augmentation | non scenario | 44.37 | 0 | 0 | 0 | 0 | 44.37 |  | Reliability | Reg Test | $82.6m ($2009/10) $92.5m (escal)
CP.02031 | Columboola to Western Downs Network Augmentation | Mar-14 | Augmentation | non scenario | 61.04 | 71.25 | 0.04 | 0 | 0 | 132.32 |  | Reliability | Reg Test | $124.0m ($2009/10) $142.0m (escal)
CP.02039 | Collinsville 132kV Substation Replacement | Oct-13 | Replacement | non scenario | 18.66 | 3.79 | 0 | 0 | 0 | 22.45 |  | Age / Condition / Obsolescence
CP.02058 | Replacement of 66kV Equipment at Tarong | Aug-12 | Replacement | non scenario | 0.55 | 0 | 0 | 0 | 0 | 0.55 |  | Age / Condition / Obsolescence | Bus Case | $5.6m (escal)
CP.02059 | Woree and Chalumbin Single Pole Auto Reclose Implementation | Oct-12 | Replacement | non scenario | 1.14 | 0 | 0 | 0 | 0 | 1.14 |  | Reliability | Bus Case | $6.1m (escal)
CP.02067 | Substation Security Upgrade - Stage 1 | Jun-12 | Security / Compliance | non scenario | 0.09 | 0.05 | 0.04 | 0 | 0 | 0.18 |  | Security | Bus Case | $8.3m (escal)
CP.02068 | Substation Security Upgrade - Stage 2 | Jun-13 | Security / Compliance | non scenario | 6.54 | 0 | 0 | 0 | 0 | 6.54 |  | Security
CP.02069 | Substation Security Upgrade - Stage 3 | Mar-13 | Security / Compliance | non scenario | 1.94 | 0 | 0 | 0 | 0 | 1.94 |  | Security
CP.02070 | Substation Security Upgrade - Stage 4 | Aug-13 | Security / Compliance | non scenario | 3.67 | 0.34 | 0 | 0 | 0 | 4.01 |  | Security
CP.02071 | Substation Security Upgrade - Stage 5 | Jan-15 | Security / Compliance | non scenario | 2.5 | 5.99 | 1.01 | 0 | 0 | 9.49 |  | Security
CP.02072 | Substation Security Upgrade - Stage 6 | Jun-15 | Security / Compliance | non scenario | 0 | 7.78 | 3.61 | 0 | 0 | 11.39 |  | Security
CP.02073 | CQ 275kV to Lilyvale Easement Project | Jun-15 | Easement | non scenario | 0.75 | 0.66 | 0.78 | 0 | 0 | 2.18 |  | Reliability
CP.02073.2 | CQ 275kV to Lilyvale Easement Project | Jun-16 | Easement | non scenario | 0 | 0.66 | 3.51 | 3.92 | 0 | 8.1 |  | Reliability
CP.02082 | Braemar R-OADM Installation | Apr-14 | Other | non scenario | 0.52 | 0.25 | 0 | 0 | 0 | 0.77 |  | Strategic
CP.02086 | Transmission Structure Signs Upgrade (Northern) | May-12 | Security / Compliance | non scenario | 0.29 | 0 | 0 | 0 | 0 | 0.29 |  | Compliance | Bus Case | $3.3m (escal)
CP.02087 | Transmission Structure Signs Upgrade (Central) | May-12 | Security / Compliance | non scenario | 0.38 | 0 | 0 | 0 | 0 | 0.38 |  | Compliance | Bus Case | $4.4m (escal)
CP.02092 | Townsville Area Easement Project | Jan-13 | Easement | non scenario | 0.01 | 0 | 0 | 0 | 0 | 0.01 |  | Age / Condition / Obsolescence
CP.02095 | Chalumbin No. 1 Bus Reactor | Dec-12 | Augmentation | non scenario | 0.28 | 0 | 0 | 0 | 0 | 0.28 |  | Reliability
CP.02098 | MPLS Wide Area Network Deployment | Oct-13 | Other | non scenario | 6.64 | 2.29 | 0 | 0 | 0 | 8.93 |  | Strategic
CP.02107 | 275kV SVC System Spare Transformer | Jun-12 | Replacement | non scenario | 0.6 | 0 | 0 | 0 | 0 | 0.6 |  | Reliability
CP.02207 | Loganlea 110kV Substation Rebuild | Dec-13 | Replacement | non scenario | 3.21 | 2.67 | 0.04 | 0 | 0 | 5.92 |  | Age / Condition / Obsolescence | Bus Case | $8.8m (escal)
CP.02213 | Woolooga to South Pine 275kV Easement Project | Oct-19 | Easement | non scenario | 0 | 0 | 0 | 0 | 0.4 | 0.4 |  | Reliability
CP.02225 | Northern Microwave Decommissioning | Oct-15 | Replacement | non scenario | 0 | 0.54 | 0.59 | 0.09 | 0 | 1.22 |  | Age / Condition / Obsolescence
CP.02226 | Cairns to Wrights Lookout Microwave Replacement | Oct-15 | Replacement | non scenario | 0 | 0.15 | 0.17 | 0.03 | 0 | 0.35 |  | Age / Condition / Obsolescence
CP.02227 | CQ 275kV DCST Easement Project No.2 | Oct-18 | Easement | non scenario | 0 | 0 | 0 | 0.96 | 1.66 | 2.62 |  | Strategic
CP.02227.2 | CQ 275kV DCST Easement Project No.2 | Oct-19 | Easement | non scenario | 0 | 0 | 0 | 0 | 0.45 | 0.45 |  | Strategic
CP.02247 | OSI PI - hardware replacement | Jun-13 | Replacement | non scenario | 0.17 | 0 | 0 | 0 | 0 | 0.17 |  | Age / Condition / Obsolescence
CP.02254 | Coastal Microwave Decommissioning | Dec-16 | Replacement | non scenario | 0 | 0 | 1.08 | 1.42 | 0.3 | 2.8 |  | Age / Condition / Obsolescence
CP.02255 | Southern Microwave Replacement | Dec-16 | Replacement | non scenario | 0 | 0 | 1.8 | 2.35 | 0.49 | 4.63 |  | Age / Condition / Obsolescence
CP.02266 | PLC Replacement | Jun-17 | Replacement | non scenario | 0 | 0 | 0 | 2.59 | 1.18 | 3.77 |  | Age / Condition / Obsolescence
CP.02267 | DC Power Supply Replacement | Oct-16 | Replacement | non scenario | 0 | 0 | 2.92 | 3.17 | 0.49 | 6.58 |  | Age / Condition / Obsolescence
CP.02272 | Mudgeeraba 275kV Secondary System Replacement | Jun-17 | Replacement | non scenario | 0 | 0 | 3.07 | 5.49 | 3.47 | 12.03 |  | Age / Condition / Obsolescence
CP.02275 | Power Systems Simulator (PSS) Upgrade | Jun-13 | Other | non scenario | 0.28 | 0 | 0 | 0 | 0 | 0.28 |  | Age / Condition / Obsolescence
CP.02278 | Moranbah Transformer No. 2 Replacement | Oct-14 | Replacement | non scenario | 1.53 | 5.03 | 0.88 | 0 | 0 | 7.43 |  | Age / Condition / Obsolescence
CP.02290 | Egans Hill Secondary Systems Replacement | Oct-17 | Replacement | non scenario | 0 | 0 | 0.24 | 1.61 | 1.25 | 3.1 |  | Age / Condition / Obsolescence
CP.02291 | Dingo Secondary Systems Replacement | Sep-17 | Replacement | non scenario | 0 | 0 | 0.63 | 2.39 | 1.86 | 4.88 |  | Age / Condition / Obsolescence
CP.02293 | Rockhampton to Bouldercombe 132kV T/L Life Extension | Dec-15 | Replacement | non scenario | 0 | 3.79 | 8.92 | 1.06 | 0 | 13.77 |  | Age / Condition / Obsolescence
CP.02294 | Diesel Generator Installation Stage 2 | Oct-12 | Replacement | non scenario | 1.72 | 0 | 0 | 0 | 0 | 1.72 |  | Reliability | Bus Case | $5.0m (escal)
CP.02295 | Marconi SMA Mux Replacement | Dec-17 | Replacement | non scenario | 0 | 0 | 0 | 2.33 | 3.04 | 5.38 |  | Age / Condition / Obsolescence
CP.02296 | PDH Mux Replacement | Dec-15 | Replacement | non scenario | 0 | 6.33 | 8.3 | 1.72 | 0 | 16.35 |  | Age / Condition / Obsolescence
CP.02297 | Power Quality Monitoring Stage 3 | Jun-15 | Security / Compliance | non scenario | 1.4 | 2.62 | 1.65 | 0 | 0 | 5.67 |  | Compliance
CP.02298 | Dynamic Line Ratings - External Sources | Jun-13 | Other | non scenario | 0.28 | 0 | 0 | 0 | 0 | 0.28 |  | Reliability
CP.02299 | Power System Disturbance Recorders - Stage 2 | Jul-15 | Other | non scenario | 0.21 | 0.54 | 0.33 | 0 | 0 | 1.09 |  | Reliability
CP.02300 | Operational Digital Networks Common Services | Jun-14 | Replacement | non scenario | 0.31 | 0.14 | 0 | 0 | 0 | 0.46 |  | Age / Condition / Obsolescence
CP.02301 | Accurate Fault Location System Stage 4 | Oct-16 | Other | non scenario | 0 | 0.24 | 1.64 | 1.26 | 0.21 | 3.35 |  | Reliability
CP.02308 | EMS & NMS Security Upgrade - Midterm | Jun-14 | Other | non scenario | 2.2 | 1.01 | 0 | 0 | 0 | 3.21 |  | Age / Condition / Obsolescence
CP.02309 | High Speed Monitoring - Stage 3 | Jun-14 | Security / Compliance | non scenario | 1.51 | 0.7 | 0 | 0 | 0 | 2.21 |  | Compliance
CP.02313 | EMS & NMS Security Upgrade - Replacement | Jun-16 | Other | non scenario | 0 | 0 | 1.5 | 0.69 | 0 | 2.18 |  | Age / Condition / Obsolescence
CP.02315 | Implementation of IEC61850 Process Bus | Jun-15 | Replacement | non scenario | 0.35 | 0.65 | 0.42 | 0 | 0 | 1.41 |  | Age / Condition / Obsolescence
CP.02318 | Accurate Fault Location System Stage 2a | Oct-13 | Other | non scenario | 1.77 | 0.3 | 0 | 0 | 0 | 2.07 |  | Reliability
CP.02319 | Belmont 275kV Secondary System Replacement | Jun-17 | Replacement | non scenario | 0 | 0 | 2.73 | 4.89 | 3.09 | 10.72 |  | Age / Condition / Obsolescence
CP.02320 | Oonooie Secondary System Replacement | Sep-17 | Replacement | non scenario | 0 | 0 | 0.5 | 1.91 | 1.48 | 3.89 |  | Age / Condition / Obsolescence
CP.02321 | SVC Sec Systems Replacement - Blackwall, Braemar, Woree | Oct-18 | Replacement | non scenario | 0 | 0 | 0 | 0 | 0.6 | 0.6 |  | Age / Condition / Obsolescence
CP.02322 | Rocklands Secondary System Replacement | Jul-18 | Replacement | non scenario | 0 | 0 | 0 | 0.73 | 1.85 | 2.58 |  | Age / Condition / Obsolescence
CP.02326 | Accurate Fault Location System Stage 3 | Oct-15 | Other | non scenario | 0.48 | 3.22 | 2.48 | 0.41 | 0 | 6.58 |  | Reliability
CP.02327 | Huawei NMS Platform Initial Upgrade | Dec-13 | Replacement | non scenario | 0.22 | 0.05 | 0 | 0 | 0 | 0.27 |  | Age / Condition / Obsolescence
CP.02328 | Huawei NMS Platform Subsequent Upgrade | Dec-16 | Replacement | non scenario | 0 | 0 | 0.17 | 0.23 | 0.05 | 0.45 |  | Age / Condition / Obsolescence
CP.02330 | MV36/38 NMS Platform Subsequent Upgrade | Dec-15 | Replacement | non scenario | 0 | 0.21 | 0.27 | 0.06 | 0 | 0.53 |  | Age / Condition / Obsolescence
CP.02332 | Castlerock NMS Platform Subsequent Upgrade | Dec-17 | Replacement | non scenario | 0 | 0 | 0 | 0.14 | 0.18 | 0.32 |  | Age / Condition / Obsolescence
CP.02333 | Comms RTU Replacement | Dec-16 | Replacement | non scenario | 0 | 0 | 1.89 | 2.5 | 0.52 | 4.92 |  | Age / Condition / Obsolescence
CP.02335 | Comms Site Infrastructure Expansion | Jun-15 | Other | non scenario | 0 | 7.45 | 3.38 | 0 | 0 | 10.83 |  | Operational
CP.02349 | Kamerunga Primary Plant Replacement | Oct-17 | Replacement | non scenario | 0 | 0 | 0 | 1.07 | 1.88 | 2.94 |  | Age / Condition / Obsolescence
CP.02350 | Bouldercombe Primary Plant Replacement | Oct-18 | Replacement | non scenario | 0 | 0 | 0 | 0 | 8.25 | 8.25 |  | Age / Condition / Obsolescence
CP.02351 | Nebo Primary Plant Replacement | Oct-18 | Replacement | non scenario | 0 | 0 | 0 | 0 | 8.67 | 8.67 |  | Age / Condition / Obsolescence
CP.02353 | Townsville South Primary Plant Replacement | Oct-18 | Replacement | non scenario | 0 | 0 | 0 | 0 | 3.01 | 3.01 |  | Age / Condition / Obsolescence
CP.02355 | Ashgrove West Primary Plant Replacement | Oct-16 | Replacement | non scenario | 0 | 0 | 5.68 | 9.95 | 1.97 | 17.6 |  | Age / Condition / Obsolescence
CP.02356 | Lilyvale Transformer Replacement | Aug-17 | Replacement | non scenario | 0 | 0 | 0 | 5.3 | 10.54 | 15.85 |  | Age / Condition / Obsolescence
CP.02358 | Metro Microwave Decommissioning | Dec-16 | Replacement | non scenario | 0 | 0 | 0.66 | 0.87 | 0.18 | 1.71 |  | Age / Condition / Obsolescence
CP.02361 | Real Time SAN and Back Up Facilities Replacement | Jun-15 | Replacement | non scenario | 0 | 0.71 | 0.33 | 0 | 0 | 1.04 |  | Age / Condition / Obsolescence
CP.02363 | Dynamic Line Ratings | Jun-17 | Other | non scenario | 0 | 0 | 0 | 4.55 | 2.07 | 6.62 |  | Reliability
CP.02364 | EMS Replacement | Jun-17 | Replacement | non scenario | 0 | 0 | 0 | 18.12 | 8.28 | 26.4 |  | Age / Condition / Obsolescence
CP.02365 | Enhanced Contingency Analysis (ECA) | Jun-13 | Other | non scenario | 0.42 | 0 | 0 | 0 | 0 | 0.42 |  | Reliability
CP.02366 | DIMA Developments for Next Generation SCADA Protocol | Jun-17 | Replacement | non scenario | 0 | 0 | 0 | 0.36 | 0.17 | 0.53 |  | Age / Condition / Obsolescence
CP.02367 | EMS Developments for Next Generation SCADA Protocol | Jun-17 | Replacement | non scenario | 0 | 0 | 0 | 0.54 | 0.25 | 0.79 |  | Age / Condition / Obsolescence
CP.02383 | Situational Awareness Application | Jun-17 | Other | non scenario | 0 | 0 | 0 | 0.97 | 0.45 | 1.41 |  | Reliability
CP.02386 | Real Time Flow Forecasting Application | Jun-15 | Other | non scenario | 0 | 0.44 | 0.2 | 0 | 0 | 0.65 |  | Reliability
CP.02387 | EMS Switch Flow Estimation | Jun-14 | Other | non scenario | 0.57 | 0.27 | 0 | 0 | 0 | 0.84 |  | Reliability
CP.02388 | Dynamic Transformer Ratings | Jun-14 | Other | non scenario | 0.31 | 0.14 | 0 | 0 | 0 | 0.45 |  | Reliability
CP.02389 | Market Simulation Application | Jun-17 | Other | non scenario | 0 | 0 | 0 | 0.88 | 0.41 | 1.28 |  | Reliability
CP.02402 | Collinsville - Proserpine 132kV T/L Life Extension Easement Project | Jun-14 | Easement | non scenario | 0.35 | 0.42 | 0 | 0 | 0 | 0.77 |  | Reliability
CP.02403 | Moura Switchyard Site | Apr-15 | Easement | non scenario | 0.37 | 0.22 | 0.29 | 0 | 0 | 0.88 |  | Age / Condition / Obsolescence
CP.02403.2 | Moura Switchyard Site | Apr-16 | Easement | non scenario | 0 | 0.01 | 0.02 | 0.02 | 0 | 0.05 |  | Age / Condition / Obsolescence
CP.02411 | Moranbah Area Easement Project | Oct-14 | Easement | non scenario | 0.16 | 0.11 | 0.07 | 0 | 0 | 0.35 |  | Reliability
CP.02412 | Lilyvale-Blackwater 3rd Cct | Oct-12 | Augmentation | non scenario | 0.49 | 0 | 0 | 0 | 0 | 0.49 |  | Reliability | Bus Case | $4.5m (escal)
CP.02416 | FNQ Tower Painting Easement Requirement | Oct-14 | Easement | non scenario | 0.33 | 0.22 | 0.15 | 0 | 0 | 0.7 |  | Age / Condition / Obsolescence
CP.02435 | Planned Outage/Restoration of Plant/Secondary Systems | Jun-17 | Other | non scenario | 0 | 0 | 0 | 0.84 | 0.39 | 1.23 |  | Age / Condition / Obsolescence
CP.02437 | Phasor Measurement Integration With EMS | Jun-13 | Other | non scenario | 0.16 | 0 | 0 | 0 | 0 | 0.16 |  | Age / Condition / Obsolescence
CP.02439 | Standardise PSS/E Software Versions | Jun-16 | Other | non scenario | 0 | 0 | 0.05 | 0.02 | 0 | 0.07 |  | Age / Condition / Obsolescence
CP.02440 | Implement PSS/O Application | Jun-16 | Other | non scenario | 0 | 0 | 0.55 | 0.26 | 0 | 0.81 |  | Age / Condition / Obsolescence
CP.02441 | Miscellaneous Power Planning and Assessment Tools | Oct-17 | Other | non scenario | 0 | 0 | 0 | 0.28 | 0.31 | 0.6 |  | Age / Condition / Obsolescence
CP.02442 | DIMA enhancement | Oct-16 | Other | non scenario | 0 | 0 | 0.6 | 0.66 | 0.1 | 1.36 |  | Age / Condition / Obsolescence
CP.02445 | Network Performance Monitoring Enhancement | Jun-13 | Other | non scenario | 0.16 | 0 | 0 | 0 | 0 | 0.16 |  | Age / Condition / Obsolescence
CP.02447 | Ashgrove West Secondary Systems Replacement | Oct-16 | Replacement | non scenario | 0 | 0.21 | 1.43 | 1.11 | 0.19 | 2.93 |  | Age / Condition / Obsolescence
CP.02458 | CQ 275kV DCST Easement Project No.1 | Oct-17 | Easement | non scenario | 0 | 0 | 0.78 | 1.36 | 0.92 | 3.06 |  | Reliability
CP.02458.2 | CQ 275kV DCST Easement Project No.1 | Oct-18 | Easement | non scenario | 0 | 0 | 0 | 0.57 | 2.37 | 2.94 |  | Reliability
CP.02461 | Cairns Transformer Replacement | Jun-18 | Replacement | non scenario | 0 | 0 | 0 | 0 | 2.27 | 2.27 |  | Age / Condition / Obsolescence
CP.02462 | Ingham South Transformer Replacement | Jun-18 | Replacement | non scenario | 0 | 0 | 0 | 0 | 4.15 | 4.15 |  | Age / Condition / Obsolescence
CP.02463 | Dysart Transformer Replacement | Oct-18 | Replacement | non scenario | 0 | 0 | 0 | 0 | 2.43 | 2.43 |  | Age / Condition / Obsolescence
CP.02480.2 | Alan Sherriff to Dan Gleeson 132kV Line Decommissioning | Oct-17 | Replacement | non scenario | 0 | 0 | 0 | 1.12 | 2.1 | 3.22 |  | Age / Condition / Obsolescence
CP.02485 | High Speed Monitoring - Stage 4 | Oct-15 | Security / Compliance | non scenario | 0.14 | 0.98 | 0.78 | 0.13 | 0 | 2.03 |  | Compliance
CP.02486 | Accurate Fault Location System Stage 2b | Oct-14 | Other | non scenario | 1.25 | 0.96 | 0.16 | 0 | 0 | 2.37 |  | Reliability
CP.02487 | Port Based Authentication for Secondary Systems | Dec-13 | Other | non scenario | 0.35 | 0.13 | 0 | 0 | 0 | 0.48 |  | Age / Condition / Obsolescence
CP.02488 | Network Access Control (NAC) for Substation Secondary Systems | Dec-15 | Other | non scenario | 0.14 | 2.25 | 2.29 | 0.82 | 0 | 5.5 |  | Reliability
CP.02489 | OPSWAN Security Replacement Stage 1 | Jun-13 | Replacement | non scenario | 3.06 | 0 | 0 | 0 | 0 | 3.06 |  | Age / Condition / Obsolescence
CP.02490 | OpsWAN Security Replacement Stage 2 | Jun-17 | Security / Compliance | non scenario | 0 | 0 | 1.49 | 2.66 | 1.66 | 5.81 |  | Age / Condition / Obsolescence
CP.02497 | Power System Disturbance Recorders Stage 1 | Dec-12 | Other | non scenario | 0.94 | 0 | 0 | 0 | 0 | 0.94 |  | Reliability
CP.02500 | South Pine to Woolooga OHEW Replacement | Oct-17 | Replacement | non scenario | 0 | 0 | 0 | 5.39 | 9.83 | 15.22 |  | Age / Condition / Obsolescence
CP.02504 | Gin Gin to Wurdong OHEW Replacement | Oct-17 | Replacement | non scenario | 0 | 0 | 0 | 4.73 | 8.62 | 13.35 |  | Age / Condition / Obsolescence
CP.02507 | Collinsville to Proserpine T/L Life Extension | Jun-15 | Replacement | non scenario | 5.56 | 14.15 | 16.19 | 0 | 0 | 35.91 |  | Age / Condition / Obsolescence
CP.02508 | West Darra to Sumner Tee 110kV T/L Life Extension | Oct-15 | Replacement | non scenario | 0 | 1.46 | 2.72 | 0.26 | 0 | 4.43 |  | Age / Condition / Obsolescence
CP.02509 | Rocklea to Sumner 110kV T/L Life Extension | Aug-15 | Replacement | non scenario | 0.27 | 4.41 | 5.95 | 0.2 | 0 | 10.84 |  | Age / Condition / Obsolescence
CP.02516 | Garbutt 132kV Transformer Replacement | Oct-17 | Replacement | non scenario | 0 | 0 | 0 | 2.93 | 9.36 | 12.29 |  | Age / Condition / Obsolescence
CP.02518 | Implementation of IEC61850 Process Bus | Jun-17 | Other | non scenario | 0 | 0 | 1.47 | 2.68 | 1.72 | 5.88 |  | Age / Condition / Obsolescence
CP.02520 | Tarong PS 66kV Cable Replacement | Oct-16 | Replacement | non scenario | 0 | 0 | 1.68 | 3.08 | 0.29 | 5.04 |  | Age / Condition / Obsolescence
CP.02522 | Data Management Application | Jun-14 | Other | non scenario | 0.51 | 0.24 | 0 | 0 | 0 | 0.75 |  | Reliability
CP.02523 | Automated Collection of Disturbance Data | Jun-13 | Other | non scenario | 1 | 0 | 0 | 0 | 0 | 1 |  | Reliability
CP.02524 | Intelligent Alarm Processing Stage 1 | Mar-15 | Other | non scenario | 0.69 | 3.08 | 0.49 | 0 | 0 | 4.25 |  | Reliability
CP.02525 | Intelligent Alarm Processing Stage 2 | Dec-15 | Other | non scenario | 0 | 0.76 | 1.01 | 0.21 | 0 | 1.99 |  | Reliability
CP.02526 | Intelligent Alarm Processing Stage 3 | Jun-16 | Other | non scenario | 0 | 0 | 0.59 | 0.27 | 0 | 0.87 |  | Reliability
CP.02527 | SCADA Protocol Enhancement Stage 1 | Dec-13 | Other | non scenario | 1.42 | 0.3 | 0 | 0 | 0 | 1.71 |  | Age / Condition / Obsolescence
CP.02528 | SCADA Protocol Enhancement Stage 2 | Dec-16 | Other | non scenario | 0 | 0 | 0.46 | 0.6 | 0.13 | 1.19 |  | Age / Condition / Obsolescence
CP.02531 | Boyne Island Secondary Systems Replacement | Oct-15 | Replacement | non scenario | 0.1 | 0.67 | 0.52 | 0.09 | 0 | 1.38 |  | Age / Condition / Obsolescence
CP.02532 | Bergin's Hill to Goodna to Belmont 275kV T/L Life Extension | Mar-17 | Replacement | non scenario | 0 | 0 | 6.55 | 12.59 | 5.91 | 25.05 |  | Age / Condition / Obsolescence
CP.02533 | South Pine to Upper Kedron 110kV T/L Life Extension | Mar-14 | Replacement | non scenario | 5.27 | 2.5 | 0 | 0 | 0 | 7.77 |  | Age / Condition / Obsolescence
CP.02534 | West Darra to Upper Kedron 110kV T/L Life Extension | Mar-14 | Replacement | non scenario | 6.47 | 3.06 | 0 | 0 | 0 | 9.53 |  | Age / Condition / Obsolescence
CP.02535 | 132kV Transformer Bay at Chinchilla Substation | Oct-13 | Connection | non scenario | 1.84 | 0.33 | 0 | 0 | 0 | 2.16 |  | Reliability
CP.02548 | Network Data Model Sharing between TNSPs and AEMO | Jun-15 | Security / Compliance | non scenario | 0 | 0.32 | 0.15 | 0 | 0 | 0.47 |  | Compliance
CP.02553 | MPLS Wide Areas Network Deployment Stage 2 | Jun-15 | Other | non scenario | 0 | 4.83 | 2.19 | 0 | 0 | 7.01 |  | Strategic
CP.02554 | VOIP Deployment Stage 2 | Oct-14 | Other | non scenario | 0.28 | 0.31 | 0.05 | 0 | 0 | 0.64 |  | Strategic
CP.02555 | Townsville South to Clare South Easement Project | Jun-14 | Easement | non scenario | 0.41 | 0.48 | 0 | 0 | 0 | 0.89 |  | Age / Condition / Obsolescence
CP.02558 | Moranbah Site Expansion | Oct-17 | Easement | non scenario | 0 | 0 | 0.21 | 0.36 | 0.24 | 0.81 |  | Reliability
CP.02558.2 | Moranbah Site Expansion | Oct-18 | Easement | non scenario | 0 | 0 | 0 | 0.26 | 1.07 | 1.32 |  | Reliability
CP.02565 | Karana Downs to South Pine T/L Life Extension | Oct-16 | Replacement | non scenario | 0 | 0 | 6.08 | 11.26 | 1.07 | 18.41 |  | Age / Condition / Obsolescence
CP.02566 | Southern Brisbane 275kV Easement Project No. 2 | Mar-16 | Easement | non scenario | 0.14 | 1.09 | 0.54 | 0.75 | 0 | 2.52 |  | Reliability
CP.02573 | Operational Digital Networks Common Services Concept - Stage 2 | Jun-18 | Replacement | non scenario | 0 | 0 | 0 | 0 | 2.36 | 2.36 |  | Age / Condition / Obsolescence
CP.02575 | Release and Patch Management for Substation LANs Stage 1 | Jun-14 | Replacement | non scenario | 0.54 | 0.25 | 0 | 0 | 0 | 0.79 |  | Age / Condition / Obsolescence
CP.02583 | OHEW Fault Rating Upgrade Stage 1 | Jun-15 | Replacement | non scenario | 4.41 | 11.31 | 12.6 | 0 | 0 | 28.32 |  | Age / Condition / Obsolescence
CP.02584 | Tarong Substation Transformer Upgrade Options | Oct-14 | Replacement | non scenario | 2.95 | 9.67 | 1.69 | 0 | 0 | 14.31 |  | Age / Condition / Obsolescence
CP.02585 | Belmont Substation Transformer Upgrade Options | Oct-15 | Replacement | non scenario | 0 | 4.02 | 12.85 | 2.23 | 0 | 19.1 |  | Age / Condition / Obsolescence
CP.02589 | Release and Patch Management for Substation LANs - Stage 2 | Jun-17 | Replacement | non scenario | 0 | 0 | 0 | 0.67 | 0.31 | 0.97 |  | Age / Condition / Obsolescence
CP.02591 | CQ-SQ Life Extension Easement Clearance | Jul-18 | Easement | non scenario | 0 | 0 | 0 | 1.18 | 1.2 | 2.38 |  | Age / Condition / Obsolescence
CP.02593 | Black River 132/66kV Easement Project | Oct-19 | Easement | non scenario | 0 | 0 | 0 | 0 | 0.09 | 0.09 |  | Reliability
CP.02594 | Brisbane North Substation Site Expansion | Oct-19 | Easement | non scenario | 0 | 0 | 0 | 0 | 0.22 | 0.22 |  | Reliability
CP.02595 | Wurdong to Boyne Easement Project No.2 | Oct-19 | Easement | non scenario | 0 | 0 | 0 | 0 | 0.12 | 0.12 |  | Age / Condition / Obsolescence
CP.02596 | Ross to Townsville South Easement Project | Oct-19 | Easement | non scenario | 0 | 0 | 0 | 0 | 0.04 | 0.04 |  | Reliability
CP.02599 | Calvale to Surat Basin Easement Project | Nov-18 | Easement | non scenario | 0 | 0 | 0 | 0.9 | 2.61 | 3.51 |  | Reliability
CP.02599.2 | Calvale to Surat Basin Easement Project | Nov-19 | Easement | non scenario | 0 | 0 | 0 | 0 | 1.2 | 1.2 |  | Reliability
CP.02603 | Serene Valley Substation Site | Oct-19 | Easement | non scenario | 0 | 0 | 0 | 0 | 0.22 | 0.22 |  | Strategic
CP.02607 | OHEW Fault Rating Upgrade Stage 2 | Jun-16 | Replacement | non scenario | 0 | 3.15 | 7.77 | 8.64 | 0 | 19.56 |  | Age / Condition / Obsolescence
CP.02608 | OHEW Fault Rating Upgrade Stage 3 | Jun-18 | Replacement | non scenario | 0 | 0 | 0 | 2.83 | 6.99 | 9.82 |  | Age / Condition / Obsolescence
CP.00376 | Palmwoods 275kV Transformer No. 3 | Oct-15 | Augmentation | scenario | 0 | 4.85 | 15.46 | 2.68 | 0 | 22.98 |  | Reliability
CP.00390 | Rocklea 275kV Bus Establishment | Oct-18 | Augmentation | scenario | 0 | 0 | 0 | 0 | 7.95 | 7.95 |  | Reliability
CP.00732 | Ross 2nd 132kV Capacitor Bank | Oct-17 | Augmentation | scenario | 0 | 0 | 0 | 0 | 1.88 | 1.88 |  | Reliability
CP.01156.2 | Stanwell to Broadsound Stringing 2nd 275kV Circuit | Oct-13 | Augmentation | scenario | 32.76 | 3.18 | 0 | 0 | 0 | 35.94 |  | Reliability
CP.01189 | Nudgee 275kV Substation Establishment | Oct-16 | Augmentation | scenario | 0 | 0 | 25.19 | 43.2 | 4.05 | 72.44 |  | Reliability
CP.01195 | Larapinta 275/110kV Substation Establishment | Oct-14 | Augmentation | scenario | 23.28 | 37.05 | 7.26 | 0 | 0 | 67.58 |  | Reliability
CP.01268 | Woree 3rd 132kV Capacitor Bank | Oct-17 | Augmentation | scenario | 0 | 0 | 0 | 0 | 4.92 | 4.92 |  | Reliability
CP.01382 | Wurdong to Boyne 275kV DCST Easement Project No.1 | Oct-17 | Easement | scenario | 0 | 0 | 0.25 | 0.43 | 0.29 | 0.97 |  | Reliability
CP.01382.2 | Wurdong to Boyne 275kV DCST Easement Project No.1 | Oct-18 | Easement | scenario | 0 | 0 | 0 | 0.14 | 0.58 | 0.72 |  | Reliability
CP.01423 | Bulli to SWQ Easement Project | Oct-15 | Easement | scenario | 0.74 | 1.31 | 0.89 | 0.59 | 0 | 3.53 |  | Reliability
CP.01423.2 | Bulli to SWQ Easement Project | Oct-16 | Easement | scenario | 0 | 2.35 | 9.8 | 20.48 | 3.47 | 36.1 |  | Reliability
CP.01432 | SWQ to SEQ Easement Project No. 3 | Oct-17 | Easement | scenario | 0 | 0 | 0.32 | 0.55 | 0.37 | 1.25 |  | Reliability
CP.01432.2 | SWQ to SEQ Easement Project No. 3 | Oct-18 | Easement | scenario | 0 | 0 | 0 | 0.21 | 0.89 | 1.1 |  | Reliability
CP.01442 | Bowen North 2nd 132/66kV Transformer | Oct-14 | Connection | scenario | 2.67 | 8.77 | 1.53 | 0 | 0 | 12.97 |  | Reliability
CP.01465.2 | High Temperature Conductor Upgrade | Oct-13 | Augmentation | scenario | 2.12 | 0.2 | 0 | 0 | 0 | 2.32 |  | Reliability
CP.01470 | Halys to Greenbank 500kV DCST Operating at 275kV | Oct-18 | Augmentation | scenario | 0 | 0 | 0 | 0 | 193.94 | 193.94 |  | Reliability
CP.01477.2 | Western Downs to Halys 1st 500kV DCST Operating at 275kV | Oct-15 | Augmentation | scenario | 0 | 112.24 | 187.75 | 17.36 | 0 | 317.35 |  | Reliability
CP.01523.2 | Townsville East 2nd 132/66kV Transformer | Oct-17 | Connection | scenario | 0 | 0 | 0 | 2.27 | 7.26 | 9.54 |  | Reliability
CP.01525 | Yabulu South 1st 132kV Capacitor Bank | Oct-16 | Augmentation | scenario | 0 | 0 | 0 | 1.83 | 0.53 | 2.36 |  | Reliability
CP.01528 | Molendinar 3rd 275/110kV 375MVA Transformer | Oct-19 | Augmentation | scenario | 0 | 0 | 0 | 0 | 0 | 0 |  | Reliability
CP.01546 | Callide A Switchyard Replacement | Oct-15 | Replacement | scenario | 0 | 11.11 | 19.45 | 3.83 | 0 | 34.39 |  | Age / Condition / Obsolescence
CP.01602 | Abermain 110kV Bay for Wulkuraka | Dec-14 | Connection | scenario | 0.48 | 1.32 | 0.46 | 0 | 0 | 2.26 |  | Reliability
CP.01606 | Clare South 132kV Bays for Milchester No. 2 | Oct-17 | Connection | scenario | 0 | 0 | 0 | 0.91 | 1.61 | 2.52 |  | Reliability
CP.01664 | Kamerunga 132kV Bays to Smithfield | Oct-16 | Connection | scenario | 0 | 0 | 1.79 | 3.12 | 0.62 | 5.52 |  | Reliability
CP.01706.3 | Calliope River to Larcom Creek 275kV SCST to DCST | Oct-16 | Augmentation | scenario | 0 | 0 | 15.42 | 27.07 | 2.53 | 45.02 |  | Reliability
CP.01720 | Innisfail 2nd 132kV Capacitor Bank | Oct-18 | Augmentation | scenario | 0 | 0 | 0 | 0 | 0 | 0 |  | Reliability
CP.01748 | Ashgrove West 2 x 100MVA 110/33kV Transformers | Oct-13 | Connection | scenario | 6.42 | 1.15 | 0 | 0 | 0 | 7.57 |  | Reliability
CP.01762 | Calvale 2nd 275/132kV Transformer | Oct-15 | Augmentation | scenario | 0 | 2.73 | 8.68 | 1.5 | 0 | 12.91 |  | Reliability
CP.01781 | Northern Bowen Basin Augmentation | Oct-14 | Augmentation | scenario | 28.43 | 54.12 | 5.02 | 0 | 0 | 87.56 |  | Reliability
CP.01876 | Edmonton 2nd 132kV Capacitor Bank | Oct-17 | Augmentation | scenario | 0 | 0 | 0 | 0.74 | 2.36 | 3.1 |  | Reliability
CP.01883 | Blackwall 3rd 275kV Capacitor Bank | Oct-17 | Augmentation | scenario | 0 | 0 | 0 | 0 | 3.45 | 3.45 |  | Reliability
CP.01917 | Wurdong 4th 275kV Capacitor Bank | Oct-16 | Augmentation | scenario | 0 | 0 | 0 | 3.66 | 1.06 | 4.72 |  | Reliability
CP.01957 | Calvale to Larcom Creek 275kV DCST | Oct-16 | Augmentation | scenario | 0 | 0 | 38.84 | 70.58 | 6.58 | 116 |  | Reliability
CP.01957.3 | Calvale to Larcom Creek 275kV DCST - One Circuit Strung | Oct-18 | Augmentation | scenario | 0 | 0 | 0 | 0 | 29.27 | 29.27 |  | Reliability
CP.01978 | Mudgeeraba 2 110kV Feeder Bays (Tugun 110kV DCST) | Oct-16 | Connection | scenario | 0 | 0 | 1.4 | 2.44 | 0.48 | 4.32 |  | Reliability
CP.02044 | Peak Downs North Establishment | Oct-18 | Augmentation | scenario | 0 | 0 | 0 | 0 | 13.9 | 13.9 |  | Reliability
CP.02215.2 | Karana Downs to South Pine 275kV High Temperature Conductor Upgrade | Sep-16 | Augmentation | scenario | 0 | 0 | 8.44 | 14.05 | 0.91 | 23.4 |  | Reliability
CP.02218 | Loganlea 3rd 275/110kV Transformer | Oct-19 | Augmentation | scenario | 0 | 0 | 0 | 0 | 0 | 0 |  | Reliability
CP.02222.2 | Bergins Hill to Drewvale 275kV Reinforcement Stage 1 | Oct-16 | Augmentation | scenario | 0 | 0 | 26.29 | 39.52 | 3.7 | 69.51 |  | Reliability
CP.02229.6 | Wurdong Tee Reconfiguration - option a | Oct-16 | Augmentation | scenario | 0 | 0 | 5.23 | 9.25 | 0.87 | 15.35 |  | Reliability
CP.02229.8 | Wurdong Tee Reconfiguration - option b | Oct-16 | Augmentation | scenario | 0 | 0 | 5.17 | 8.66 | 1.71 | 15.53 |  | Reliability
CP.02229.9 | Wurdong Tee New Diameter | Oct-16 | Augmentation | scenario | 0 | 0 | 4.7 | 7.85 | 1.55 | 14.11 |  | Reliability
CP.02233.2 | Broadsound to Nebo 275kV and Series Capacitors | Oct-15 | Augmentation | scenario | 0 | 0 | 41.5 | 11.89 | 0 | 53.39 |  | Reliability
CP.02238 | Tarong 2nd 275kV Capacitor Bank | Oct-15 | Augmentation | scenario | 0 | 0 | 3.87 | 1.11 | 0 | 4.98 |  | Reliability
CP.02239 | Halys 1st 275kV Capacitor Bank | Oct-17 | Augmentation | scenario | 0 | 0 | 0 | 0 | 3.74 | 3.74 |  | Reliability
CP.02258 | Nebo 3rd 275kV Capacitor Bank | Oct-15 | Augmentation | scenario | 0 | 0 | 3.7 | 1.06 | 0 | 4.77 |  | Reliability
CP.02259 | Nebo 4th 275kV Capacitor Bank | Oct-15 | Augmentation | scenario | 0 | 0 | 3.38 | 0.97 | 0 | 4.36 |  | Reliability
CP.02263 | Strathmore 1st 275kV Capacitor Bank | Oct-16 | Augmentation | scenario | 0 | 0 | 0 | 4.39 | 1.27 | 5.66 |  | Reliability
CP.02265 | Yabulu South 2nd 132kV Capacitor Bank | Oct-17 | Augmentation | scenario | 0 | 0 | 0 | 0 | 1.86 | 1.86 |  | Reliability
CP.02271.2 | Stanwell to Broadsound Series Capacitors | Oct-16 | Augmentation | scenario | 0 | 0 | 3.77 | 34.15 | 15.27 | 53.19 |  | Reliability
CP.02273.2 | Nebo to Strathmore Series Capacitors | Oct-16 | Augmentation | scenario | 0 | 0 | 0 | 74.65 | 21.56 | 96.2 |  | Reliability
CP.02283.2 | Wurdong to Boyne 2nd 275kV DCST | Oct-18 | Augmentation | scenario | 0 | 0 | 0 | 0 | 12.74 | 12.74 |  | Reliability
CP.02359.2 | Yabulu South 275kV Transformer | Oct-16 | Augmentation | scenario | 0 | 0 | 3.78 | 12 | 2.09 | 17.87 |  | Reliability
CP.02377 | Gladstone Area 132kV DCST Easement Project | Oct-15 | Easement | scenario | 0.26 | 0.45 | 0.31 | 0.2 | 0 | 1.22 |  | Reliability
CP.02377.2 | Gladstone Area 132kV DCST Easement Project | Oct-16 | Easement | scenario | 0 | 0.06 | 0.27 | 0.57 | 0.1 | 1 |  | Reliability
CP.02401 | Brisbane West 275kV DCST Easement Project | Sep-18 | Easement | scenario | 0 | 0 | 0 | 0.47 | 0.67 | 1.14 |  | Reliability
CP.02405 | Gladstone to Gin Gin 814 Turn-in to Wurdong Easement Project | Oct-15 | Easement | scenario | 0.08 | 0.15 | 0.1 | 0.07 | 0 | 0.4 |  | Strategic
CP.02406 | 132/66kV System Spare Transformer No. 2 | Oct-17 | Replacement | scenario | 0 | 0 | 0 | 0.85 | 2.71 | 3.56 |  | Age / Condition / Obsolescence
CP.02410 | Proserpine 132kV Capacitor Bank | Oct-18 | Augmentation | scenario | 0 | 0 | 0 | 0 | 0 | 0 |  | Reliability
CP.02414 | Larapinta 110/33kV Substation Establishment | Oct-18 | Connection | scenario | 0 | 0 | 0 | 0 | 2.14 | 2.14 |  | Reliability
CP.02421 | Strathmore In-Out Collinsville to Clare South | Oct-17 | Augmentation | scenario | 0 | 0 | 0 | 3.5 | 6.14 | 9.63 |  | Reliability
CP.02432 | Blackstone 110kV Bays for Springfield Central | Oct-15 | Connection | scenario | 0 | 0.63 | 1.11 | 0.22 | 0 | 1.96 |  | Reliability
CP.02446 | Blackstone 2nd 110kV Bay for Springfield Central | Oct-18 | Connection | scenario | 0 | 0 | 0 | 0 | 0.7 | 0.7 |  | Reliability
CP.02453 | Moranbah to Goonyella Riverside 132kV Transmission Line | Oct-14 | Augmentation | scenario | 9.55 | 16.86 | 1.57 | 0 | 0 | 27.99 |  | Reliability
CP.02454 | Ross to Townsville South 132kV Upgrade | Oct-15 | Augmentation | scenario | 0 | 2.32 | 4.07 | 0.8 | 0 | 7.19 |  | Reliability
CP.02467 | Herberton South 132 kV Switching Substation Establishment | Oct-15 | Augmentation | scenario | 0 | 6.52 | 11.23 | 2.21 | 0 | 19.96 |  | Reliability
CP.02468 | Turkinje 2nd 132KV Capacitor Bank | Oct-15 | Augmentation | scenario | 0 | 0 | 2.12 | 0.61 | 0 | 2.74 |  | Reliability
CP.02473 | South Pine 110kV Bay for Brendale 110/11kV | Oct-13 | Augmentation | scenario | 4.41 | 0.89 | 0 | 0 | 0 | 5.3 |  | Reliability
CP.02477.3 | Western Downs to Halys 2nd 500kV DCST (OP 275kV) | Oct-17 | Augmentation | scenario | 0 | 0 | 0 | 105.27 | 182.81 | 288.08 |  | Reliability
CP.02481 | Wandoan South 3rd 275/132kV Transformer and Reactive Support | Oct-16 | Augmentation | scenario | 0 | 0 | 3.99 | 12.66 | 2.21 | 18.85 |  | Reliability
CP.02482 | Wandoan South 2nd 132/66kV Transformer | Oct-15 | Connection | scenario | 0 | 1.22 | 3.88 | 0.67 | 0 | 5.76 |  | Reliability
CP.02484 | Larapinta 275/110kV 2nd Transformer | Oct-16 | Augmentation | scenario | 0 | 0 | 2.85 | 9.02 | 1.57 | 13.44 |  | Reliability
CP.02498 | Blackwall to Karana Downs 275kV Feeder Re-Arrangement | Oct-14 | Augmentation | scenario | 3.23 | 6.13 | 0.58 | 0 | 0 | 9.94 |  | Reliability
CP.02503 | Strathmore to Ross Series Capacitors | Oct-17 | Augmentation | scenario | 0 | 0 | 0 | 4.16 | 38.02 | 42.18 |  | Reliability
CP.02519 | Proserpine 2nd Capacitor Bank | Oct-17 | Augmentation | scenario | 0 | 0 | 0 | 0 | 1.99 | 1.99 |  | Reliability
CP.02530 | Calvale 132kV 300MVA Series Reactor | Oct-15 | Augmentation | scenario | 0 | 1.16 | 3.71 | 0.65 | 0 | 5.52 |  | Reliability
CP.02541 | Townsville South 3rd Transformer | Oct-17 | Connection | scenario | 0 | 0 | 0 | 1.77 | 5.65 | 7.42 |  | Reliability
CP.02543 | Wandoan South Substation 1st 132kV Capacitor Bank | Oct-15 | Augmentation | scenario | 0 | 0 | 2.21 | 0.64 | 0 | 2.84 |  | Reliability
CP.02544 | Wandoan South Substation 2nd 132kV Capacitor Bank | Oct-18 | Augmentation | scenario | 0 | 0 | 0 | 0 | 0 | 0 |  | Reliability
CP.02546 | Middle Ridge 330kV No.4 Transformer Replacement | Oct-18 | Augmentation | scenario | 0 | 0 | 0 | 0 | 5.15 | 5.15 |  | Reliability
CP.02547 | Turkinje 3rd Transformer | Oct-19 | Connection | scenario | 0 | 0 | 0 | 0 | 0 | 0 |  | Reliability
CP.02552 | Proserpine 132kV Bus Coupler Breaker | Oct-14 | Augmentation | scenario | 2.25 | 4.06 | 0.8 | 0 | 0 | 7.12 |  | Reliability
CP.02563 | South West Queensland Easement Deviation | Oct-17 | Easement | scenario | 0 | 0 | 0.52 | 0.91 | 0.62 | 2.05 |  | Reliability
CP.02563.2 | South West Queensland Easement Deviation | Oct-18 | Easement | scenario | 0 | 0 | 0 | 0.95 | 3.92 | 4.87 |  | Reliability
CP.02588 | Wurdong Substation Easement Project | Oct-15 | Easement | scenario | 0.08 | 0.15 | 0.1 | 0.07 | 0 | 0.4 |  | Strategic
CP.02601 | Braemar 3rd 330/275kV Transformer and Braemar 330kV Bus Tie Series Reactor | Oct-16 | Augmentation | scenario | 0 | 0 | 13.58 | 43.12 | 7.51 | 64.22 |  | Reliability
CP.02604 | Townsville South 132kV Capacitor Bank | Oct-15 | Augmentation | scenario | 0 | 0 | 2.27 | 0.66 | 0 | 2.93 |  | Reliability
CP.02606 | Ross 1st 275kV Capacitor Bank | Oct-18 | Augmentation | scenario | 0 | 0 | 0 | 0 | 0 | 0 |  | Reliability
CP.02609 | Herberton South Substation Site | Oct-13 | Easement | scenario | 0.14 | 0.09 | 0 | 0 | 0 | 0.23 |  | Reliability
CP.02609.2 | Herberton South Substation Site | Oct-14 | Easement | scenario | 0.02 | 0.05 | 0.01 | 0 | 0 | 0.08 |  | Reliability
| Outstanding Easement Compensation | ongoing | Easement | non scenario | 0.62 | 0 | 0 | 0 | 0 | 0.62 |  | Demand Growth / Reliability
| Rocklea Feeder Bay | Jul-14 | Connection | non scenario | 0 | 0 | 0.22 | 0 | 0 | 0.22 |  | Reliability
|  |  |  | Subtotal | 775.17 | 886.46 | 849.48 | 895.61 | 851.17 | 4257.89
|  |  | ^refers to Categories set out in table 4.1 (e.g Augmentation, Replacement etc) | ^refers to Categories set out in table 4.1 (e.g Augmentation, Replacement etc)

## Fcst Capex - Non-Network
Powerlink pro-forma information statements - 31 May 2011
4.4 FORECAST CAPEX - Non-Network - by project
[5 empty] | Home |  |  | Link to Forecast Capex Instructions - Table 6.3
$ million, (2011/12 mid year)
Yearly expenditure by project
Project ID | Project Description | Estimated Commissioning Date | Category^ | 2012/13 | 2013/14 | 2014/15 | 2015/16 | 2016/17 | TOTAL | REASON FOR PROJECT | Business Case (Y/N)
CP.96825 | Minor Application Upgrades / Purchases | Jun-13 | Information Technology | 0.41 | 0 | 0 | 0 | 0 | 0.41 | Operational
CP.96826 | Powerlink Alert Management System Replacement | Jun-16 | Information Technology | 0 | 0 | 0 | 1.03 | 0 | 1.03 | Age / Condition / Obsolescence
CP.96827 | SAP Manager Self Service | Apr-13 | Information Technology | 0.26 | 0 | 0 | 0 | 0 | 0.26 | Operational
CP.96828 | Workflow Development | Apr-13 | Information Technology | 0.51 | 0 | 0 | 0 | 0 | 0.51 | Operational
CP.96925 | Ratings Management | Jun-12 | Information Technology | 0.51 | 0 | 0 | 0 | 0 | 0.51 | Operational | Bus Case
CP.96928 | Digital Network Connectivity Database Replacement | Jun-13 | Information Technology | 1 | 0 | 0 | 0 | 0 | 1 | Age / Condition / Obsolescence | Bus Case
CP.96936 | Enterprise Incident Management | Feb-13 | Information Technology | 0.26 | 0 | 0 | 0 | 0 | 0.26 | Age / Condition / Obsolescence
CP.96937 | Contract Management System | Feb-13 | Information Technology | 0.26 | 0 | 0 | 0 | 0 | 0.26 | Age / Condition / Obsolescence
CP.96945 | Improved Access to Operational and Event | Jun-15 | Information Technology | 0 | 0.59 | 0.98 | 0 | 0 | 1.57 | Operational
CP.96947 | Advanced Ratings Management | Jun-15 | Information Technology | 0 | 0 | 1.63 | 0 | 0 | 1.63 | Operational
CP.96948 | SAP PM Exploitation | Apr-13 | Information Technology | 1.03 | 0 | 0 | 0 | 0 | 1.03 | Operational
CP.96949 | Network Equipment Health Index | Jun-13 | Information Technology | 0.58 | 0 | 0 | 0 | 0 | 0.58 | Operational
CP.96950 | Management of Restricted Access Zones | Apr-14 | Information Technology | 0 | 0.8 | 0 | 0 | 0 | 0.8 | Operational | Bus Case
CP.96952 | Extend Asset Performance Data Analysis | Jun-15 | Information Technology | 0 | 0 | 1.26 | 0 | 0 | 1.26 | Operational
CP.96953 | Implement Data Quality Tool | Apr-14 | Information Technology | 0 | 0.58 | 0 | 0 | 0 | 0.58 | Operational
CP.96954 | Secondary Systems and Communications Outage Analysis | Jun-15 | Information Technology | 0 | 0 | 1.44 | 0 | 0 | 1.44 | Operational
CP.96956 | Resource Planning | Jun-13 | Information Technology | 1.39 | 0 | 0 | 0 | 0 | 1.39 | Operational
CP.96957 | Integrated Resource Allocation | Jun-14 | Information Technology | 0 | 1.79 | 0 | 0 | 0 | 1.79 | Operational
CP.96958 | Extended Web Based Integration of Power Systems Information | Jun-17 | Information Technology | 0 | 0 | 0 | 0 | 1.03 | 1.03 | Operational
CP.96959 | High Voltage Index Application | Jun-13 | Information Technology | 0.52 | 0 | 0 | 0 | 0 | 0.52 | Operational
CP.96961 | CAD Data Mining | Jun-17 | Information Technology | 0 | 0 | 0 | 0 | 1.41 | 1.41 | Age / Condition / Obsolescence
CP.96962 | Extend TNDB Network Model | Jun-15 | Information Technology | 0 | 0 | 1.03 | 0 | 0 | 1.03 | Operational
CP.96963 | NPR Master Data Management | Jun-13 | Information Technology | 0.77 | 0 | 0 | 0 | 0 | 0.77 | Age / Condition / Obsolescence
CP.96964 | Implement Data Mining tool | Jun-16 | Information Technology | 0 | 0 | 0 | 1.13 | 0 | 1.13 | Operational
CP.96965 | Implement Enterprise Collaboration and Knowledge Management Tool | Jun-14 | Information Technology | 0.73 | 0.31 | 0 | 0 | 0 | 1.04 | Operational
CP.96967 | Electrical Network Design Tools | Jun-13 | Information Technology | 1.72 | 0 | 0 | 0 | 0 | 1.72 | Operational
CP.96968 | Meter Data Management and Customer Billing | Jun-14 | Information Technology | 0 | 1.05 | 0 | 0 | 0 | 1.05 | Age / Condition / Obsolescence
CP.96969 | Ops Guide Content | Apr-13 | Information Technology | 0.6 | 0 | 0 | 0 | 0 | 0.6 | Operational
CP.96970 | SPF Major Upgrade | Jun-15 | Information Technology | 0 | 0 | 1.05 | 0 | 0 | 1.05 | Age / Condition / Obsolescence
CP.96971 | Master Data Management Tool | Jun-15 | Information Technology | 0 | 0 | 0.95 | 0 | 0 | 0.95 | Operational
CP.96973 | Business Performance Reporting and Analytics | Apr-14 | Information Technology | 0.83 | 0.31 | 0 | 0 | 0 | 1.13 | Operational
CP.96974 | Objective Major Upgrade | Apr-13 | Information Technology | 0.84 | 0 | 0 | 0 | 0 | 0.84 | Age / Condition / Obsolescence
CP.96975 | Osi Pi Major Upgrade | Jun-14 | Information Technology | 0 | 1.23 | 0 | 0 | 0 | 1.23 | Age / Condition / Obsolescence
CP.96976 | PQ Maps Major Upgrade | Apr-14 | Information Technology | 0 | 0.71 | 0 | 0 | 0 | 0.71 | Age / Condition / Obsolescence
CP.96977 | Project Server Major Upgrade | Jun-16 | Information Technology | 0 | 0 | 0 | 1.03 | 0 | 1.03 | Age / Condition / Obsolescence
CP.96978 | SAP Major Upgrade | Jun-16 | Information Technology | 0 | 0 | 0.82 | 1.46 | 0 | 2.28 | Age / Condition / Obsolescence
CP.96979 | Internet Upgrade - External Website | Apr-16 | Information Technology | 0 | 0 | 0 | 0.7 | 0 | 0.7 | Age / Condition / Obsolescence
CP.96980 | Intranet Upgrade - Internal Website | Apr-15 | Information Technology | 0 | 0 | 0.76 | 0 | 0 | 0.76 | Age / Condition / Obsolescence
CP.96981 | SAP PM Exploitation | Apr-16 | Information Technology | 0 | 0 | 0 | 1.03 | 0 | 1.03 | Operational
CP.96982 | Minor Application Upgrades / Purchases (13/14) | Jun-14 | Information Technology | 0 | 0.41 | 0 | 0 | 0 | 0.41 | Operational
CP.96983 | Minor Application Upgrades / Purchases (14/15) | Jun-15 | Information Technology | 0 | 0 | 0.41 | 0 | 0 | 0.41 | Operational
CP.96984 | Minor Application Upgrades / Purchases (15/16) | Jun-16 | Information Technology | 0 | 0 | 0 | 0.41 | 0 | 0.41 | Operational
CP.96985 | Minor Application Upgrades / Purchases (16/17) | Jun-17 | Information Technology | 0 | 0 | 0 | 0 | 0.41 | 0.41 | Operational
CP.96986 | Mobile Working Solutions (13/14) | Jun-14 | Information Technology | 0 | 0.31 | 0 | 0 | 0 | 0.31 | Operational
CP.96987 | Mobile Working Solutions (14/15) | Jun-15 | Information Technology | 0 | 0 | 0.31 | 0 | 0 | 0.31 | Operational
CP.96988 | Mobile Working Solutions (15/16) | Jun-16 | Information Technology | 0 | 0 | 0 | 0.31 | 0 | 0.31 | Operational
CP.96989 | Mobile Working Solutions (16/17) | Jun-17 | Information Technology | 0 | 0 | 0 | 0 | 0.31 | 0.31 | Operational
CP.96995 | Database Consolidation and Augmentation | Jun-17 | Information Technology | 0 | 0 | 0 | 0 | 1.28 | 1.28 | Operational
CP.96996 | ESX Platform Upgrade | Jun-17 | Information Technology | 0 | 0 | 0 | 0.96 | 0.51 | 1.47 | Operational
CP.96997 | Electronic Bulletinboard | Apr-16 | Information Technology | 0 | 0 | 0 | 0.75 | 0 | 0.75 | Operational
CP.96998 | Storage Consolidation | Jun-17 | Information Technology | 0 | 0 | 0 | 0 | 4.77 | 4.77 | Operational
CP.96999 | Fault Tolerant Architecture | Jun-15 | Information Technology | 0 | 0 | 1.54 | 0 | 0 | 1.54 | Operational
CP.97001 | Mobile Working Solutions (12/13) | Jun-13 | Information Technology | 0.31 | 0 | 0 | 0 | 0 | 0.31 | Replacement
CP.97003 | Hierarchical Storage Management | Apr-17 | Information Technology | 0 | 0 | 0 | 0 | 0.51 | 0.51 | Replacement
CP.97004 | NAC Implementation | Jun-17 | Information Technology | 0 | 0 | 0 | 0 | 0.96 | 0.96 | Security
CP.97005 | Application Performance Monitoring | Jun-16 | Information Technology | 0 | 0 | 0 | 1.03 | 0 | 1.03 | Additional requirements
CP.97006 | Unified Communications | Apr-17 | Information Technology | 0 | 0 | 0 | 0 | 0.77 | 0.77 | Additional requirements
CP.97007 | Data Leakage Prevention | Jun-17 | Information Technology | 0 | 0 | 0 | 0 | 0.77 | 0.77 | Security
CP.97008 | Internal Network Monitoring | Jun-16 | Information Technology | 0 | 0 | 0 | 0.77 | 0 | 0.77 | Security
CP.97009 | Microsoft Office 2010 Upgrade | Apr-14 | Information Technology | 0 | 0.52 | 0 | 0 | 0 | 0.52 | Age / Condition / Obsolescence
CP.97010 | Microsoft Windows 10 Upgrade | Jun-14 | Information Technology | 0 | 1.4 | 0 | 0 | 0 | 1.4 | Age / Condition / Obsolescence
CP.97011 | Microsoft Exchange 2010 Upgrade | Jun-16 | Information Technology | 0 | 0 | 0 | 1.04 | 0 | 1.04 | Age / Condition / Obsolescence
CP.97012 | Internet Explorer 10 Upgrade | Apr-15 | Information Technology | 0 | 0 | 0.44 | 0 | 0 | 0.44 | Age / Condition / Obsolescence
CP.97013 | Infrastructure Access Management | Sep-16 | Information Technology | 0 | 0 | 0 | 1.23 | 0.31 | 1.54 | Age / Condition / Obsolescence
CP.97014 | Desktop Replacement 2012 / 2013 | Jun-13 | Information Technology | 1.57 | 0 | 0 | 0 | 0 | 1.57 | Age / Condition / Obsolescence
CP.97015 | Data Centre Replacement 2012 / 2013 | Jun-13 | Information Technology | 1.41 | 0 | 0 | 0 | 0 | 1.41 | Age / Condition / Obsolescence
CP.97016 | Desktop Replacement 2013 / 2014 | Jun-14 | Information Technology | 0 | 1.23 | 0 | 0 | 0 | 1.23 | Age / Condition / Obsolescence
CP.97017 | Data Centre Replacement 2013 / 2014 | Jun-14 | Information Technology | 0 | 1.81 | 0 | 0 | 0 | 1.81 | Age / Condition / Obsolescence
CP.97018 | Desktop Replacement 2014 / 2015 | Jun-15 | Information Technology | 0 | 0 | 1.28 | 0 | 0 | 1.28 | Age / Condition / Obsolescence
CP.97019 | Data Centre Replacement 2014 / 2015 | Jun-15 | Information Technology | 0 | 0 | 1.48 | 0 | 0 | 1.48 | Age / Condition / Obsolescence
CP.97020 | Desktop Replacement 2015 / 2016 | Jun-16 | Information Technology | 0 | 0 | 0 | 1.57 | 0 | 1.57 | Age / Condition / Obsolescence
CP.97021 | Data Centre Replacement 2015 / 2016 | Jun-16 | Information Technology | 0 | 0 | 0 | 1.17 | 0 | 1.17 | Age / Condition / Obsolescence
CP.97022 | Desktop Replacement 2016 / 2017 | Jun-17 | Information Technology | 0 | 0 | 0 | 0 | 1.23 | 1.23 | Age / Condition / Obsolescence
CP.97023 | Data Centre Replacement 2016 / 2017 | Jun-17 | Information Technology | 0 | 0 | 0 | 0 | 1.41 | 1.41 | Age / Condition / Obsolescence
CP.97025 | Microsoft Server 2012 Upgrade | Jun-14 | Information Technology | 0 | 1.87 | 0 | 0 | 0 | 1.87 | Age / Condition / Obsolescence
CP.97026 | Security Appliance Consolidation | Apr-15 | Information Technology | 0 | 0 | 0.74 | 0 | 0 | 0.74 | Security
CP.97055 | Ratings Calculation Applications | Apr-13 | Information Technology | 0.1 | 0 | 0 | 0 | 0 | 0.1 | Operational
CP.97060 | Project Integration and Reporting | Dec-12 | Information Technology | 0.05 | 0 | 0 | 0 | 0 | 0.05 | Operational
CP.97068 | Risk Management Tool | Dec-12 | Information Technology | 0.1 | 0 | 0 | 0 | 0 | 0.1 | Operational
CP.98100 | Fleet | ongoing | Motor Vehicles | 2.97 | 3.71 | 4.38 | 3.53 | 4.66 | 19.25 | Annual Cycle
| NN Tools and Equipment | ongoing | Moveable Plant | 1.93 | 1.8 | 1.72 | 1.83 | 1.86 | 9.13 | Replacement
| NN - Buildings | ongoing | Commercial Buildings | 5.74 | 3.3 | 3.11 | 2.87 | 3.09 | 18.1 | Replacement
|  |  | Subtotal | 26.38 | 23.73 | 25.32 | 23.82 | 25.29 | 124.54
^refers to the categories used in table 4.1 (eg Information Technology, Motor Vehicles etc)

## Commentary on Opex
Powerlink pro-forma information statements - 31 May 2011
5.1 Historic and Forecast Opex Commentary proforma: key cost drivers
This pro forma is designed to allow the TNSP to provide context and background for the quantitative opex templates. | Home
The historic opex tables (1.1 - 1.7) provide a column where the key cost drivers for historic opex should be briefly listed. This commentary pro forma provides opportunity for more detailed explanations regarding material changes in particular expenses over the relevant regulatory period.
The forecast opex tables (2.1 - 2.7) provide a similar column where the key cost drivers for forecast opex should be briefly listed. This commentary pro forma provides the opportunity for more detailed explanations regarding material changes in particular forecast expenses. | Link to Historic Opex Summary - Table 1.1
The commentary should address the following:
>The main cost drivers for the particular opex item (eg changes in CPI, legislative and regulatory requirements, environmental factors). | Link to Forecast Opex Summary - Table 2.1
>Were these increases foreseeable? If not, why not?
>Details of management induced opex efficiencies achieved.
>Major opex risks and mitigation strategies.
>Key Performance Indicators – are these benchmarked against other transmission companies?
In addition, the TNSP is requested to provide:
>Definitions of ‘opex’ and ‘capex’ used by the business. Further, the TNSP should provide definitions for the categories and activities used in the opex templates. These definitions should be added to the definition section in table 6.1
>A discussion on the relationship between opex and capex.
>Details of changes in accounting policies over the past regulatory period and how they may have impacted on opex in general or specific opex items.
Commentary on cost drivers and material changes over the current regulatory period
Chapter five of the Revenue Proposal provides information on Powerlink's historic operating expenditure performance.
Supporting information
Supporting information is provided, or referenced, in Chapter five of the Revenue Proposal.
Commentary on cost drivers and material changes affecting the upcoming regulatory period
Chapter nine of the Revenue Proposal provides information on Powerlink's forecast operating expenditure.
Supporting information
Supporting information is provided, or referenced, in Chapter nine of the Revenue Proposal.

## Commentary on Historic Capex
Powerlink pro-forma information statements - 31 May 2011
5.2 Historic Capex Commentary Proforma: reasons for variance
This pro forma is designed to allow TNSP's to provide context and background for the quantitative historic capex templates. | Home
Tables 3.3 & 3.4 provide a column where reasons for capex cost variances may be briefly listed. This pro forma provides the opportunity for more detailed reasons to be given for material differences between actual project costs and amounts included in the regulatory test/business case assessment.
The commentary should address the following:
Link to Historic Capex by category - Table 3.1
>The main reasons for the project being undertaken (eg. demand growth)
>The main reasons for material cost variances for the particular project (eg changes in material costs, legislative and regulatory requirements, environmental factors, technology changes) and whether they were forseeable.
>The main reason for any material variance in commissioning date (e.g delays in supply of materials, environmental approvals etc) and whether they were forseeable.
>How does the project align with the TNSP's asset management strategy/plan?
>Reference to the project's assessment in the TNSP's Annual Planning Reports. | Link to Historic Capex by Asset Class - Table 3.2
>Details of management induced capex efficiencies which have reduced costs.
>Major project risks and strategies undertaken to mitigate them.
Commentary on reasons for variance
Chapter five of the Revenue Proposal provides information on Powerlink's historic capital expenditure
performance.
Link to Historic Capex - Network - Table 3.3
Supporting information
Supporting information is provided, or referenced, in Chapter five of the Revenue Proposal.
Link to Historic Capex - Non-Network - Table 3.4

## Commentary on Forecast Capex
Powerlink pro-forma information statements - 31 May 2011
5.3 Forecast Capex Commentary Proforma: reasons for project
This pro forma is designed to provide context and background for the quantitative forecast capex templates, by specifying matters that the AER will take into account in assessing the TNSP’s proposed expenditure. | Home
Table 4.3 provides a column where reasons for the project can be provided. This pro forma provides the opportunity for more detailed reasons to be given for factors influencing the proposed spend, including load growth, planned generation and the range of foreseable scenarios and their probabilities of occurring.
The commentary should address the following: | Link to Forecast Capex by category - Table 4.1
>The theme sets upon which the proposed capex spend is based
> The scenarios derived from the above theme sets and their relevant probabilities.
> Project specific information in addition to the cost information provided in the forward capex templates.
In addition, the TNSP is requested to provide: | Link to Forecast by Asset Class - Table 4.2
>Details of its capital expenditure and approvals processes.
>Details of its overall asset management strategy/plan.
>Relevant Annual Planning Reports.
>Consultants reports on the probabilistic methodology adopted, its assumptions, inputs and detailed information on the outcomes.
Link to Forecast Capex - Network - Table 4.3
Theme sets and Scenarios modelled
Chapter eight of the Revenue Proposal provides information on Powerlink's forecast capital expenditure.
Link to Forecast Capex - Non-Network - Table 4.4
Supporting information
Supporting information is provided, or referenced, in Chapter eight of the Revenue Proposal.

## Opex Instructions
Powerlink pro-forma information statements - 31 May 2011
6.1 OPEX - Instructions and definitions
Note: These definitions are a guide only. TNSPs can adapt the definition section as necessary, given consultation with the AER.
PURPOSE OF INFORMATION AND USE BY THE AER: | The historic worksheets (1.1 to 1.7) are a key input into the AER's assessment of a TNSP's historic opex performance to assist it in establishing a starting point from which to set efficient opex for the next regulatory period. | Home
The forecast worksheets (2.1 to 2.6) are a key input into the AER's assessment of a TNSPs proposed forecast opex.
Key cost drivers for expenditure are important to the AER's understanding of what has happened in the current regulatory period and any step changes in opex claimed for the next regulatory period.
INSTRUCTIONS | Data to be input on the basis of the definitions provided.
All expenditure must relate to the provision of prescribed transmission services.
Key cost drivers for expenditure: reasons for material changes in costs should be expanded upon in the relevant opex commentary proforma.
Templates must be completed in accordance with the instructions contained in the AER's Submission Guidelines and Cost Allocation Guidelines.
Values for years 4 and 5 are estimated values only
All cells must be filled out where possible, especially in relation to any commentary on variances.
DEFINITIONS | Asset Manager Support: Asset Management (AM) Support are those operational activities required to support the strategic development and ongoing asset management of the network. Asset Management Support has 4 major sub-elements: Grid Planning, Network Support, Network Customer & Regulatory Support, IT Support, and Operational Support.
Condition based maintenance: usually evolves out of routine maintenance or an inspection regime, where it is identified that the condition of plant or equipment is such that action must be taken to avoid future defects (e.g. operating out of tolerance).
Corporate Support : Corporate Support encompasses the support activities required by Powerlink in order to ensure adequate and effective corporate governance.
Corrective maintenance: activities that restore a failed component to an operational state.
Directing Operating and Maintenance Expenditure are the costs directly associated with maintaining and operating the network and include Field Maintenance, Operational Refurbishment, Maintenance Support and Network Operations.
Field Maintenance: Field maintenance includes all field activities, performed by Maintenance Service Providers, to ensure plant can perform its required functions.
Key cost drivers: significant factors driving expenditure such as network growth, labour and non-labour cost increases, the age and condition of assets and legislative requirements.
Maintenance Support: non-field (non-MSP) based support for maintenance actives and primarily comprises the asset management functions for the maintain/operate phase of an the asset life cycle such as maintenance strategy development, performance management and maintenance auditing and include Field Support, Other Support and Direct Charges.
Network Operations: are activities are the ‘control centre’ functions as well as those additional activities required to ensure the safe, reliable and efficient operational management of the Queensland transmission network and include Switching, Asset Monitoring Team, NMS Support and Operations Support.
Non-network: all activities not directly related to the operation and maintenance of the network, including administrative, planning and engineering support costs.
Other Controllable Costs encompass activities and services integral to managing the network business but not directly related to maintaining or operating the actual network.
Other Operating Expenditure is driven by exogenous events outside of Powerlink’s control and comprise three categories of Insurance, Network Support and Debt Raising Costs.
Operational refurbishment: activities that return an asset to its pre-existing condition or function, or activities undertaken on part of an asset to return that specific component to its pre-existing condition or function.
Opex: expenditure related to operating and maintaining assets which is not capex.
Routine maintenance: recurrent activities undertaken to maintain assets and defined by maintenance plans implemented in Powerlink’s corporate asset management system .
Support/corporate: activities and services integral to managing the network business but not directly related to maintaining or operating the actual network.

## Historic Capex Instructions
Powerlink pro-forma information statements - 31 May 2011
6.2 HISTORIC CAPEX - Instructions and definitions
Note: These definitions are a guide only. TNSPs can adapt the definition section as necessary, given consultation with the AER.
PURPOSE OF INFORMATION AND USE BY THE AER: | The templates are key inputs into the AER's assessment of historic capex and will assist in the analysis of the TNSP's forecast capex claim. | Home
Specifying expenditure by project enables the AER to select projects on which to undertake more detailed analysis.
The capex categories are essentially divided between Network and Non-network. Network includes augmentation capex which is subject to the Regulatory Test.
INSTRUCTIONS: | Data to be input on the basis of the definitions provided.
All expenditure must relate to the provision of prescribed transmission services.
Categorisation of capex should be performed according to the primary reason for expenditure.
Capex amounts should be entered exclusive of customer contributions.
Reasons for variance: if actual expenditure materially varies from the amount determined under the Regulatory Test/Business case, or the date of commissioning was later than planned, then reasons should be given on the Historic Capex Commentary pro forma with a brief reference in the 'Reasons for variance' column of Table 3.3 and 3.4.
Templates must be completed according to the instructions contained in the AER's Submission Guidelines.
Values for years 4 and 5 are estimated values only.
All cells must be filled out where possible, especially in relation to any commentary on variances.
DEFINITIONS: | Augmentation: are as defined under the National Electricity Rules (NER) as works to enlarge a network or to increase the capability of a network to transmit (or distribute) active energy.
Business case: a detailed cost/benefit analysis undertaken to support an investment.
Business IT: Business IT expenditure.
Capex: expenditure that satisfies one or more of the following requirements - relates to the purchase or construction of a new asset; increases the functionality of the asset; or extends the service life of the asset.
Connections: changes to connections between the transmission and distribution networks.
Easements: land acquisitions and rights of way for transmission lines / substations.
Other (Non-Load Driven): all other projects associated with the network which provides prescribed transmission services such as communications system enhancements.
Project ID: A unique numerical identifier for a given project
Project Description: A short description of the project
Regulatory Test: the test as promulgated by the AER to assess augmentation expenditure. A prudency test must be applied to other capex.
Replacements: replacement or life extension of network assets.
Security/Compliance: projects undertaken to ensure the physical security of assets and compliance with amendments to various technical, safety or environmental legislation.
Support the business: non-network capex relating to commercial buildings, motor vehicles and moveable plant (but excluding IT).

## Forecast Capex Instructions
Powerlink pro-forma information statements - 31 May 2011
6.3 FORECAST CAPEX - Instructions and definitions
Note: These definitions are a guide only. TNSPs can adapt the definition section as necessary, given consultation with the AER.
PURPOSE OF INFORMATION AND USE BY THE AER: | The templates are key inputs into the AER's assessment of forecast capex and will enable an analysis of the proposed expenditure. | Home
Specifying expenditure by project enables the AER to select projects on which to undertake more detailed analysis.
Link to Forecast Capex commentary - Table 5.3
INSTRUCTIONS: | Data to be input on the basis of the definitions provided.
All expenditure must relate to the provision of prescribed transmission services.
Categorisation of capex should be performed according to the primary reason for expenditure.
Capex amounts should be entered on an as-incurred basis, excluding customer contributions.
Customer contributions are to be noted separately.
Templates must be completed according to the instructions contained in the AER's Submission Guidelines.
The TNSP is also requested to provide consultants' reports on the probabilistic methodology adopted, including information on theme sets and scenarios upon which the proposed capex spend is based. Further, details on the consultants assumptions, inputs and detailed information on the outcomes are requested.
DEFINITIONS: | Definitions are the same as described in pro forma statement 6.2
Scenario: for scenario projects project timing is dependent on market scenarios (probabilistic planning). The commissioning date for these projects is based on the median date. The forecast capital expenditure is based on costs for the median date.
Information on the probabilistic methodology adopted is contained and referenced in Chapter 8 of the Revenue Proposal.

## WACC
Powerlink pro-forma information statements - 31 May 2011 |  |  |  | Home
7.1 Weighted Average Cost of Capital
Setting the Revenue Cap Forecast - Rate of Return ("WACC")
Notes for the preparation of information on this proforma:
1. | The proforma sets out the minimum inputs required by the AER to model a TNSP's estimate of WACC.
2. | The minimum inputs set out in the proforma are averages for the five-year regulatory period.
3. | A post-tax nominal WACC framework involves the use of a cash flow modelling approach to derive the revenue requirement.
4. | A TNSP shall provide to the AER:
| (a) | an estimate of its post-tax nominal return on equity; post-tax nominal WACC; and pre-tax real WACC.
| (b) | the assumptions underlying the estimation.
| (c) | full and detailed explanations of the basis of any calculations.
| (d) | references to any sources of information or precedents.
Setting the Revenue Cap Forecast - Rate of Return ("WACC")
TNSP: | Powerlink |  | Reporting date: 1 July 2013 to 30 June 2017
Proposed value
%
|  | Nominal risk free rate | 5.62%
|  | Real risk free rate | 3.04%
|  | Inflation Rate | 2.5%
|  | Proportion of debt funding | 60%
|  | Nominal pre-tax cost of debt | 9.96%
|  | Cost of debt margin over the risk free rate | 4.34%
|  | Market risk premium | 6.5%
|  | Corporate tax rate | 30%
|  | Effective tax rate for equity | 22.18%
|  | Proportion of franking credits attributed to shareholders | 65%
|  | Equity beta | 80%
|  | Post-tax nominal return on equity | 10.82%
|  | Nominal vanilla WACC | 10.3%

## Dep. Sched
Powerlink pro-forma information statements - 31 May 2011 |  |  |  | Home
7.2 Depreciation
Inputs for Post-Tax Revenue Model
Values 2011/12 end of year
| Forecast Capital Expenditure (as incurred) |  |  |  | CAPITAL EXPENDITURE
| Asset Class | Opening WDV | Ave Lives Remaining | Standard Lives | 2012/13 | 2013/14 | 2014/15 | 2015/16 | 2016/17
| Transmission Lines (Overhead) | 3392.01 |  |  | 391.08 | 423.65 | 210.34 | 235.98 | 218.63
| Transmission Lines (Underground) | 58.93 |  |  | 2.14 | 7.67 | 12.9 | 10.83 | 3
| Transmission Lines (Refit) | 35.45 |  |  | 22.28 | 35.35 | 52.19 | 26.15 | 7.07
| Substations Primary Plant | 1795.61 |  |  | 217.75 | 183.86 | 158.84 | 170.83 | 144.08
| Substations Secondary Systems | 420.18 |  |  | 109.22 | 118.65 | 100.97 | 85.42 | 80.61
| Communications Assets | 80.3 |  |  | 33.53 | 24.19 | 23.32 | 18.53 | 9.14
| Communications - Civil Works | 17.71 |  |  | 0 | 0 | 0 | 0 | 0
| Network Switching Centres | 20.86 |  |  | 12.72 | 8.14 | 6 | 33.94 | 14.7
| Land | 151.87 |  |  | 3.73 | 4.07 | 3.96 | 0.95 | 0.22
| Easements | 433.72 |  |  | 21.5 | 27.77 | 42.88 | 54.06 | 32.7
| Commercial Buildings | 81.75 |  |  | 5.8 | 3.33 | 3.14 | 2.9 | 3.12
| Computer Equipment | 45.58 |  |  | 15.95 | 15.11 | 16.31 | 15.79 | 15.86
| Office Furniture & Miscellaneous | 0.93 |  |  | 0.01 | 0.01 | 0.01 | 0.01 | 0.01
| Office Machines | 0.75 |  |  | 0 | 0 | 0 | 0 | 0
| Vehicles | 15.35 |  |  | 2.42 | 2.69 | 3.47 | 2.69 | 3.71
| Moveable Plant | 9.04 |  |  | 1.95 | 1.82 | 1.74 | 1.85 | 1.88
| Insurance Spares | 6.52 |  |  | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0
| Equity raising costs | 9.27 |  |  | 24.8
| Total | 6575.81 |  |  | 864.87 | 856.31 | 636.07 | 659.93 | 534.75
| Capitalisation (as commissioned) |  |  |  | CAPITALISATIONS
| Asset Class | Opening WDV | Ave Lives Remaining | Standard Lives | 2012/13 | 2013/14 | 2014/15 | 2015/16 | 2016/17
| Transmission Lines (Overhead) | 2938.17 | 30.3 | 50 | 292.55 | 255.63 | 570.99 | 79.41 | 270.61
| Transmission Lines (Underground) | 51.04 | 30.2 | 45 | 0.06 | 0 | 6.31 | 11.28 | 15.16
| Transmission Lines (Refit) | 9.93 | 15 | 15 | 20.94 | 23.09 | 40.41 | 36.27 | 42.8
| Substations Primary Plant | 1555.36 | 24.9 | 40 | 287.22 | 179.31 | 149.2 | 129.26 | 205.5
| Substations Secondary Systems | 363.96 | 8.4 | 15 | 103.1 | 96.44 | 107.69 | 97 | 103.76
| Communications Assets | 69.56 | 9.2 | 15 | 45.76 | 29.12 | 15.44 | 21.75 | 23.05
| Communications - Civil Works | 15.34 | 18.4 | 40 | 0 | 0 | 0 | 0 | 0
| Network Switching Centres | 18.07 | 10.3 | 12 | 8.89 | 16.11 | 6.34 | 5.86 | 46.81
| Land | 131.55 | n/a | n/a | 7.94 | 0.38 | 9.14 | 3.63 | 0.22
| Easements | 375.69 | n/a | n/a | 18.8 | 7.66 | 33.06 | 41.45 | 47.32
| Commercial Buildings | 70.81 | 27.3 | 40 | 5.8 | 3.33 | 3.14 | 2.9 | 3.12
| Computer Equipment | 39.48 | 3.7 | 5 | 17.37 | 16.69 | 15.48 | 14.41 | 18.08
| Office Furniture & Miscellaneous | 0.81 | 1.8 | 7 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01
| Office Machines | 0.65 | 2.1 | 7 | 0 | 0 | 0 | 0 | 0
| Vehicles | 13.3 | 5 | 7 | 2.42 | 2.69 | 3.47 | 2.69 | 3.71
| Moveable Plant | 7.83 | 4.3 | 7 | 1.95 | 1.82 | 1.74 | 1.85 | 1.88
| Insurance Spares | 6.52 | n/a | n/a | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0
| Equity raising costs | 9.27 | 39 | 43 | 24.8
| Total | 5677.32 |  |  | 837.6 | 632.27 | 962.41 | 447.77 | 782.03
Depreciation Schedule
Values 2011/12 end of year
| Asset Class |  | 2012/13 | 2013/14 | 2014/15 | 2015/16 | 2016/17 | Total
| Transmission Lines (Overhead) |  | 97.04 | 103.11 | 108.42 | 120.26 | 121.91 | 127.53
| Transmission Lines (Underground) |  | 1.69 | 1.69 | 1.69 | 1.84 | 2.1 | 2.45
| Transmission Lines (Refit) |  | 0.66 | 2.11 | 3.71 | 6.5 | 9.01 | 11.97
| Substations Primary Plant |  | 62.51 | 69.96 | 74.61 | 78.48 | 81.83 | 87.16
| Substations Secondary Systems |  | 43.31 | 50.44 | 57.11 | 64.56 | 71.27 | 78.44
| Communications Assets |  | 7.52 | 10.69 | 12.7 | 13.77 | 15.28 | 16.87
| Communications - Civil Works |  | 0.84 | 0.84 | 0.84 | 0.84 | 0.84 | 0.84
| Network Switching Centres |  | 1.75 | 2.52 | 3.91 | 4.46 | 4.97 | 9.01
| Land |  | 0 | 0 | 0 | 0 | 0 | 0
| Easements |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0
| Commercial Buildings |  | 2.6 | 2.75 | 2.83 | 2.92 | 2.99 | 3.07
| Computer Equipment |  | 10.65 | 14.26 | 17.72 | 17.8 | 13.27 | 17.02
| Office Furniture & Miscellaneous |  | 0.45 | 0.36 | 0 | 0 | 0 | 0
| Office Machines |  | 0.31 | 0.31 | 0.02 | 0 | 0 | 0
| Vehicles |  | 2.64 | 3 | 3.4 | 3.91 | 4.31 | 2.32
| Moveable Plant |  | 1.82 | 2.11 | 2.38 | 2.64 | 1.63 | 1.37
| Insurance Spares |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0
| Equity raising costs |  | 0.24 | 0.84 | 0.84 | 0.84 | 0.84 | 0.84
| Total Depreciation |  | 234.05 | 264.99 | 290.18 | 318.82 | 330.23 | 358.88

## STPISP
Powerlink pro-forma information statements - 31 May 2011 |  |  |  |  | Home
7.3 Service Target Performance Incentive Scheme Parameters
Instructions:
TNSPs are required to list all appropriate parameters for the revenue reset period, grouped under the relevant subheading.
TNSPs must list the relevant unit for each parameter, what weighting that sub-parameters is given and the targets for the reset period.
Targets must be provided for each year of the revenue reset period. Proposed caps and collars for those targets should also be included.
These should be included in the format X / Y / Z, where X is the collar, Y is the target and Z is the cap.
Measure | Unit | Weighting Factor(%) | Proposed Collar / Targets / Cap
|  |  | 2013 | 2014 | 2015 | 2016 | 2017
Circuit Availability Parameter
Transmission Lines Availability | % | 0.175 | 97.51 / 98.67 / 99.83 | 97.51 / 98.67 / 99.83 | 97.51 / 98.67 / 99.83 | 97.51 / 98.67 / 99.83 | 97.51 / 98.67 / 99.83
Transformer Availability | % | 0.115 | 98.11 / 98.59 / 99.08 | 98.11 / 98.59 / 99.08 | 98.11 / 98.59 / 99.08 | 98.11 / 98.59 / 99.08 | 98.11 / 98.59 / 99.08
Reactive Plant Availability | % | 0.09 | 94.45 / 97.15 / 99.84 | 94.45 / 97.15 / 99.84 | 94.45 / 97.15 / 99.84 | 94.45 / 97.15 / 99.84 | 94.45 / 97.15 / 99.84
Peak Availability | % | 0.07 | 98.31 / 98.76 / 99.20 | 98.31 / 98.76 / 99.20 | 98.31 / 98.76 / 99.20 | 98.31 / 98.76 / 99.20 | 98.31 / 98.76 / 99.20
Loss of Supply Parameter
Loss of Supply > 0.75 system minutes | Events | 0.3 | 3 / 1 / 0 | 3 / 1 / 0 | 3 / 1 / 0 | 3 / 1 / 0 | 3 / 1 / 0
Loss of Supply > 0.10 system minutes | Events | 0.15 | 10 / 4 / 3 | 10 / 4 / 3 | 10 / 4 / 3 | 10 / 4 / 3 | 10 / 4 / 3
Outage Parameter
Average Outage Duration | Minutes | 0.1 | 1306 / 859 / 412 | 1306 / 859 / 412 | 1306 / 859 / 412 | 1306 / 859 / 412 | 1306 / 859 / 412
Notes:
The Peak Availability Parameter applies to all individual plant of transmission lines, transformers and reactive plant from November to March, with a time period from 07:00 to 22:00 (not including weekends and public holidays).
The Reactive Plant Availability and Average Outage Duration excludes capacitor banks during off-peak periods from 1 April through to 31 October.

## EBSS
Powerlink pro-forma information statements - 31 May 2011 | [5 empty] | Home
7.4 Efficiency Benefit Sharing Scheme Parameters
Year | 2005-06 | 2006-07 | 2007-08 | 2008-09 | 2009-10 | 2010-11 | 2011-12 | 2014-15 | 2015-16 | 2016-17 | 2017-18 | 2018-19
Forecast Inflation Rate | 2.32% | 2.44% | 2.91% | 2.91% | 2.91% | 2.91% | 2.91%
Forecast Inflation Cumulative Index | 0.85 | 0.87 | 0.89 | 0.92 | 0.94 | 0.97 | 1
Actual CPI Inflation Rate | 2.98% | 2.91% | 4.24% | 2.47% | 2.89% | 3.33% | 2.5%
Actual CPI | 0.83 | 0.86 | 0.9 | 0.92 | 0.94 | 0.98 | 1
Target (Decision - nominal $Jun) |  |  | 147.28 | 152.23 | 168.08 | 165.52 | 175.33
Target ($11/12 ($Jun-12)) | 0 | 0 | 166.58 | 167.31 | 179.5 | 171.77 | 176.81
Adjustments to Target*
Debt raising costs (real) |  |  | -2.06 | -2.37 | -2.63 | -2.77 | -2.93
Insurances (real) |  |  | -6.38 | -6.64 | -6.93 | -7.17 | -7.39
Capex efficiencies (real) |  |  | -3.72 | -3.72 | -3.72 | -3.72 | -3.72
Network support costs (real) |  |  | -27.97 | -20.18 | -25.78 | -9.57 | -9.66
Adjusted Target ($11/12 ($Jun-12)) | 0 | 0 | 126.46 | 134.39 | 140.44 | 148.54 | 153.11
Actual (nominal $Dec) |  |  | 146.38 | 151.39 | 168.73 | 165.6 | 176.26
Actual ($11/12 ($Jun-12)) | 0 | 0 | 166.87 | 166.99 | 181.27 | 172.55 | 153.88
Adjustments to Actual*
Debt management costs (real) |  |  | -2.05 | -2.37 | -2.63 | -2.77
Insurances (real) |  |  | -6.38 | -6.64 | -6.93 | -7.17
Capex efficiencies (real) |  |  | -3.72 | -3.72 | -3.72 | -3.72
Network support costs (real) |  |  | -27.97 | -20.18 | -25.78 | -9.57
Adjusted Actual ($11/12 ($Jun-12)) | 0 | 0 | 126.75 | 134.08 | 142.21 | 149.32 | 153.88
Incremental Gain ($11/12 ($Jun-12)) |  |  | -0.3 | 0.61 | -2.08 | 0.99 | 0
Carryover^
Year -4 |  |  |  | -0.3 | -0.3 | -0.3 | -0.3 | -0.3
Year -3 |  |  |  |  | 0.61 | 0.61 | 0.61 | 0.61 | 0.61
Year -2 | [5 empty] | -2.08 | -2.08 | -2.08 | -2.08 | -2.08
Year -1 | [6 empty] | 0.99 | 0.99 | 0.99 | 0.99 | 0.99
Year 0 | [7 empty] | 0 | 0 | 0 | 0 | 0
Total Carryover Amount ($11/12 ($Jun-12)) | [7 empty] | -0.77 | -0.48 | -1.09 | 0.99 | 0
* Additional rows may be added as necessary but are subject to approval by the AER. Adjustments must relate to cost categories approved by the AER to be excluded from the scheme in a relevant revenue determination. See clause 2.3 of the Efficiency Benefit Sharing Scheme guideline.
^ Raw efficiency gains are calculated as per the formulae below. For the purposes of calculating the carry-over amount, the adjusted target and actual amounts are to be used.
For the first application of the scheme, the efficiency carry forward amount for the first year of the regulatory period is expressed mathematically as:
|  |  | E-4 = F-4 – A-4 |  |  | where A-4 is the actual operating cost for year -4 and F-4 is the regulatory target operating cost for that year.
For subsequent applications of the scheme, the efficiency carry forward amount for the first year of the regulatory period is expressed mathematically as:
E-4 = (F-4 – A-4) – (F-5 – A-5) + (F-6 – A-6)
For savings that arose in the second to fifth year of the regulatory period, the efficiency carry forward amount is calculated as:
Et = (Ft – At) – (Ft-1 – At-1)
|  |  | where: | Et is the efficiency benefit/loss in year t;
At, At-1 is the actual operating cost for the years t and t-1 respectively; and
Ft, Ft-1 is the forecast operating cost for the years t and t-1 respectively