## TRACK (hidden)
TOTAL COST
| ESTIMATE - prior to revision |  | 5359390.1793 |  | 4300204.9428
Nominal
Remove Apr-Sept Fcast | Works Delivery resource cost | -31490 | -33053.3446 | 5326336.8346
| Labour related cost |  | -1522.8346 | 5324814
| Project Development Resource cost | -805328 | -786346.25 | 4538467.75
| Project Development labur related | -190466 | -186320.75 | 4352147
| PD - Non-Labour / Consulting costs | -209250 | -202782 | 4149365
| L&E Consutant | -37000 | -35856 | 4113509
| Stakeholder/community - Labour | -2153 | -2103 | 4111406
Insurance cost rephased
Actuals / Historic costs |  | Prior | 1154750 |  | 3185585 | Revised | 2949046.7063
Add Actuals Q4/Q1 |  | 2137628 | 2030835
| Remove: Design costs Q1 20/21 | 265353 | 1765482
| Remove: Design costs Q4 | 58789 | 1706693
|  |  | 6514140.1793 |  | 7485789.9428 |  | 971649.7635
Change to CPI adj |  |  | 188798.9428 | 4113689
Actuals / Historical costs | Prior Forecast (nominal) | 1194845
| Q4 19/20 | 822464
| Q1 20/21 | 991020
| New forecast | 3008329 | 3008361.38

## Overview
Overview of this model
This model is a supporting document to the 'Labour and Indirect Costs forecast for VNI Minor Upgrade Project' document, dated Oct 2020 This model substantiates values documented in the report in relation to the ‘Corporate and Network Overhead’ capital expenditure (Capex) for the Victoria New South Wales Interconnector (VNI) for the remainder of the current regulatory period 2018-19 to 2022-23 (2018-23).
Model structure / Navigation instructions
Below outlines the key components of this model which map to the respective section of the written report (for example, section 4 of the report relates to 'Works Delivery' and this is reflected in the worksheet titled 's4. Works Delivery'.
Reference to VNI Forecast Indirect Capex CPA report | Header worksheets | Description of worksheet | Key Contact
Section 7 | Key assumptions | The Key assumptions worksheet outlines the key assumptions and rates which apply across the below listed categories. With the exception of allocation rates applied to discrete major projects, the rates applied highlighted in Yellow shade are global assumptions as referenced in the Key assumptions worksheet. | Manager People & Culture Operations - TransGrid; Manager, Management Accounting - TransGrid; Service Transition Manager
Section 2 | s2. Historical Indirect Capex | The s2. Historical Indirect Capex worksheet provides a summarised view of the 'costs incurred to date' (i.e. the 'Actuals') that have already been incurred to progress the VNI project. The Actuals have been incurred since FY18 through to 30 Sept 2020 (after which the VNI Forecast costs commence, i.e. from 1 Oct 2020). | Manager, Management Accounting - TransGrid
Section 3 | s3. VNI Summary forecast | The s3. VNI Summary forecast worksheet consolidates details from Section 4 through to Section 6 to provide a summarised overview of the total forecast corporate and network overhead costs for VNI through to the commissioning of the project. | Manager, Management Accounting - TransGrid
Section 4 | s4. Works Delivery | The s4. Works Delivery worsheet provides a summarised view of the forecast costs of the Works Delivery team to complete the VNI project. The Works Delivery team have provided several supporting workpapers, including the Works Delivery project schedule which has been linked to the Works Delivery Res Cost worksheet which provides detailed calculations. | VNI Project Director - TransGrid; Service Management, Works Delivery - TransGrid; Senior Program Manager, Major Projects Delivery - TransGrid
| - Works Delivery Res Cost | This worksheet leverages information from the Works Delivery Labour FTEs worksheet which drive calculations for the labour-related costs (i.e. recruitment, training and IT hardware). | Manager, Management Accounting - TransGrid
| - Works Delivery Labour FTEs | This worksheet captures the Works Delivery labour resource requirements (estimated Full-Time Equivalent (FTE) resourcing effort) to deliver the VNI project. Details include both the total labour resource requirements and the incremental labour resource requirements. These details have been calculated leveraging the Works Delivery Labour Hrs worksheet. | Service Management, Works Delivery
| - Works Delivery Labour Hrs | This worksheet captures the Works Delivery labour resource requirements (estimated number of resource hours) to deliver the VNI project. It is based on the resource plan "VNI Capex Overview 310320" document | Service Management, Works Delivery
Section 5 | s5. Project Development | The s5. Project Development worksheet provides a summarised view of Project Development costs. Details of cost estimates have been captured in the supporting PD-Labour(&related) and PD-Non-Labour worksheets. | VNI Project Director - TransGrid; VNI Senior Project Manager - TransGrid
| - PD-Labour(&related) | This worksheet captures the Project Development labour and labour related resource requirements to support the delivery of the VNI project. These details have been calculated leveraging the Project Development Bottom-up Build and major projects team estimates. | Manager, Management Accounting - TransGrid
| - PD-NonLabour | This worksheet captures the Project Development non-labour related resource requirements to support the delivery of the VNI project. | Manager, Management Accounting - TransGrid
| - PD-Labour Hours | This worksheet captures the Project Development Bottom-up Labour Estimate, provided by the VNI Project team. | VNI Project Director - TransGrid; VNI Senior Project Manager - TransGrid
Section 6.1 | s6.1 Land & Environment | The s6.1 Land & Environment worksheet provides a summarised view of the Land and Environment related costs. Details of cost estimates have been captured in the supporting L&E-Labour(&related) and L&E-Non-Labour worksheets. | Property Portfolio Manager - TransGrid
| - L&E-NonLabour | This worksheet captures the Land and Environment non-labour related resource requirements to support the delivery of the VNI project. | Manager, Management Accounting - TransGrid
Section 6.2 | s6.2 Stakeholder & Comm Egmt | The s6.2 Stakeholder & Comm Egmt worksheet provides a summarised view of the Stakeholder and Community Engagement related costs. Details of cost estimates have been captured in the supporting SHC-Labour(&related). | Community Engagement Manager- TransGrid
| - SHC-Labour(&related) | This worksheet captures the Stakeholder and Community Engagement labour and labour related resource requirements to support the delivery of the VNI project. | Manager, Management Accounting - TransGrid
Section 6.3 | s6.3 Insurance | Worksheet s6.3 Insurance contains all calculations are contained in this worksheet. No summary sheet is required as there is only a single line item listed for Insurance. | Head of Risk - TransGrid

## Key assumptions
Key Assumptions |  | -
The following rates have been applied across the categories of cost estimates.
Any changes made in the black cells link to the corresponding calculations in the worksheets
Escalation and Labour Rate restatement
Costs have been collected in current year rates.
TransGrid's standard labour rates as at 1 July 2019 have been used in labour costing estimates.
In order to restate these figures in 2017/8 costs, discounts have been applied as follows:
| Labour real cost de-escalation | -0.8111% | 0.8111% | Applied to all labour costs to restate the cost estimate in 2017/8 rates
| CPI discount | -1.237% | 1.237% | Applied to all costs (excl labour costs)
| CPI discount - Labour & Labour related | -1.59% | 1.59% | Applied to labour and labour related costs post-deescalation
Allocation of costs to major projects
Project | Major Projects Portfolio | Value | % of Portfolio
A | Project Energy Connect (PEC) | 1500000000 | 46.44%
B | Hume Link (Snowy 2.0) | 1500000000 | 46.44%
C | Queensland Interconnector (QNI) | 180000000 | 5.573%
D | Victorian Interconnector (VNI) | 50000000 | 1.548%
|  | 3230000000 | 100%
Salary assumptions
| Oncosts - contract | 24%
| Oncosts - Enterprise Agreement | 41%
Recruitment fees assumptions
| Recruitment fees as % of annual salary | 15%
| Roles recruited using external recruiter | 50%
Training cost assumptions
| Training cost per annum per employee | 1500
Travel rate assumptions
| Cost per return flight to VNI sites | 1000
| ATO rates for Accom & Meals | 293.65
IT hardware cost assumptions
| IT hardware cost per annum per employee | 2650
Direct cost assumptions
| Share of labour costs that are direct | 70%
| Share of labour related costs that are direct | 70%
| Share of non-labour costs that are direct | 0%
Rates per capex forecast model
Rates
|  |  | 2019 | 2020 | 2021 | 2022 | 2023
| CPI escalation |  | 1.593% | -0.35% | 2.45% | 2.45% | 2.45%
| Labour Rate escalation |  | 0.8111% | 0.9547% | 1.206% | 1.464% | 1.488%
Cumulative factors
|  | 2018 | 2019 | 2020 | 2021 | 2022 | 2023
| Cumulative CPI | 1 | 1.0159 | 1.0124 | 1.0372 | 1.0626 | 1.0886
| Cumulative Labour rate | 1 | 1.0081 | 1.0177 | 1.03 | 1.0451 | 1.0606
CPI Adjustment |  | 2018/9 | 2019/20 | June18 to Sept 20
| Actual inflation rate | 1.59% | -0.35% | 1.237%
(based on RBA CPI rates by quarter)

## s2. Historical Indirect Capex
Historical Indirect Capex
Indirect capex costs has been incurred between 1 July 2018 to 30 Sept 2020:
|  | Nominal values |  |  |  | Restatement to 30 June 2018 Labour rates |  |  |  | Restatement to 2017/8 dollars
| s2. Historical Indirect Capex | 2018-19 | 2019-20 | 2020-21 (Q1) | Total Historical Indirect Capex | 2018-19 | 2019-20 | 2020-21 (Q1) | Total Historical Indirect Capex | 2018-19 | 2019-20 | 2020-21 (Q1) | Total Historical Indirect Capex | $M (rounded)
| Total labour | 66822.81 | 709139.54 | 307237 | 1083199.35 | 66285.1696 | 696782.1204 | 298285.1878 | 1061352.4777 | 65247.7307 | 688265.8958 | 294639.4805 | 1048153.107 | 0.065248 | 0.68827 | 0.29464 | 1.0482
| Labour Related | 21.19 | 60979.52 | 1537 | 62537.71 | 21.19 | 60979.52 | 1492.2172 | 62537.71 | 20.8584 | 60234.2149 | 1473.979 | 61773.2877 | 2.0858e-05 | 0.060234 | 0.001474 | 0.061773
| Travel | 21.19 | 60979.52 | 691 | 61691.71 | 21.19 | 60979.52 | 691 | 61691.71 | 20.8584 | 60234.2149 | 682.5544 | 60937.6277 | 2.0858e-05 | 0.060234 | 0.00068255 | 0.060938
| Sustenance |  |  | 846 | 846 | 0 | 0 | 846 | 846 | 0 | 0 | 835.66 | 835.66 | 0 | 0 | 0.00083566 | 0.00083566
| Non-Labour | 202503.08 | 977844.24 | 682277 | 1862624.32 | 202503.08 | 977844.24 | 682277 | 1862624.32 | 199333.6746 | 965892.8123 | 673938.0602 | 1839164.5471 | 0.19933 | 0.96589 | 0.67394 | 1.8392
| Outsourced / Consulting costs | 180200.08 | 247614.24 | 87938 | 515752.32 | 180200.08 | 247614.24 | 87938 | 515752.32 | 177379.7421 | 244587.8442 | 86863.2024 | 508830.7887 | 0.17738 | 0.24459 | 0.086863 | 0.50883
| Support Cost allocation | 22303 | 495762 | 224444 | 742509 | 22303 | 495762 | 224444 | 742509 | 21953.9325 | 489702.6876 | 221700.796 | 733357.4161 | 0.021954 | 0.4897 | 0.2217 | 0.73336
| Other |  | 234468 | 369895 | 604363 | 0 | 234468 | 369895 | 604363 | 0 | 231602.2805 | 365374.0618 | 596976.3423 | 0 | 0.2316 | 0.36537 | 0.59698
| Total costs incurred | 269347.08 | 1747963.3 | 991051 | 3008361.38 | 268809.4396 | 1735605.8804 | 982054.4049 | 2986469.7249 | 264602.2636 | 1714392.923 | 970051.5197 | 2949046.7063 | 0.2646 | 1.7144 | 0.97005 | 2.949

## s3. VNI Summary forecast
Costs as at current year rates
| Total Estimate of Incremental Corporate Costs | 4395735.2939
| Works Delivery | 3453592.0068
| Project Development | 851858.5347
| Land and Environment Costs | 0
| Stakeholder and Community Engagement | 6459.7523
| Insurance Costs | 83825
|  | 2018-19 | 2019-20 | 2020-21 | 2021-22 | 2022-23 | TOTAL FY20-FY23
Phased
| Works Delivery | 0 | 0 | 1818518.9509 | 1635073.0559 | 0 | 3453592.0068
| Project Development | 0 | 0 | 595503.7116 | 256354.8231 | 0 | 851858.5347
| Other Indirect Capex | 0 | 0 | 39903.3137 | 50381.4387 | 0 | 90284.7523
| Land and Environment Costs | 0 | 0 | 0 | 0 | 0 | 0
| Stakeholder and Community Engagement | 0 | 0 | 3229.8762 | 3229.8762 | 0 | 6459.7523
| Insurance Costs | 0 | 0 | 36673.4375 | 47151.5625 | 0 | 83825
| Phased by Financial Year | 0 | 0 | 2453925.9762 | 1941809.3177 | 0 | 4395735.2939
VNI Summary Forecast
Adjusted cost estimates to 2017-18 base
| Total Estimate of Incremental Corporate Costs | 4300204.9428
| Works Delivery | 3377370.9946
| Project Development | 833724.9932
| Land and Environment Costs | 0
| Stakeholder and Community Engagement | 6308.4827
| Insurance Costs | 82800.4724
|  | 2018-19 | 2019-20 | 2020-21 | 2021-22 | 2022-23 | TOTAL FY20-FY23 | % of total capex
| Phased | 2017/8 $ | 2017/8 $ | 2017/8 $ | 2017/8 $ | 2017/8 $ | 2017/8 $
| Works Delivery | 0 | 0 | 1778596.3774 | 1598774.6172 | 0 | 3377370.9946 | 78.54%
| Project Development | 0 | 0 | 583022.9196 | 250702.0736 | 0 | 833724.9932 | 19.39%
| Other Indirect Capex | 0 | 0 | 39379.448 | 49729.507 | 0 | 89108.955 | 2.072%
| Land and Environment Costs | 0 | 0 | 0 | 0 | 0 | 0 | 0%
| Stakeholder and Community Engagement | 0 | 0 | 3154.2413 | 3154.2413 | 0 | 6308.4827 | 0.1467%
| Insurance Costs | 0 | 0 | 36225.2067 | 46575.2657 | 0 | 82800.4724 | 1.926%
| Phased by Financial Year | 0 | 0 | 2400998.7449 | 1899206.1979 | 0 | 4300204.9428 | 100%
Forecast TransGrid Labour and Indirect Costs
|  | Forecast TransGrid Labour and Indirect Costs | [6 empty] | Forecast Direct Costs | [5 empty] | Forecast Indirect Costs
|  | 2018-19 | 2019-20 | 2020-21 | 2021-22 | 2022-23 | TOTAL FY20-FY23 |  | 2018-19 | 2019-20 | 2020-21 | 2021-22 | 2022-23 | TOTAL FY20-FY23 | 2018-19 | 2019-20 | 2020-21 | 2021-22 | 2022-23 | TOTAL FY20-FY23
| Labour component | 2017/8 $ | 2017/8 $ | 2017/8 $ | 2017/8 $ | 2017/8 $ | 2017/8 $ |  | 2017/8 $ | 2017/8 $ | 2017/8 $ | 2017/8 $ | 2017/8 $ | 2017/8 $ | 2017/8 $ | 2017/8 $ | 2017/8 $ | 2017/8 $ | 2017/8 $ | 2017/8 $
| Works Delivery | 0 | 0 | 1347588.6761 | 1265385.5328 | 0 | 2612974.2089 |  | 0 | 0 | 943312.0732 | 885769.873 | 0 | 1829081.9462 | 0 | 0 | 404276.6028 | 379615.6598 | 0 | 783892.2627
| Project Development | 0 | 0 | 345442.6764 | 202255.9837 | 0 | 547698.6601 |  | 0 | 0 | 241809.8735 | 141579.1886 | 0 | 383389.0621 | 0 | 0 | 103632.8029 | 60676.7951 | 0 | 164309.598
| Other Indirect Capex | 0 | 0 | 3092.5291 | 3092.5291 | 0 | 6185.0581 |  | 0 | 0 | 2164.7703 | 2164.7703 | 0 | 4329.5407 | 0 | 0 | 927.7587 | 927.7587 | 0 | 1855.5174
| Land and Environment Costs | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Stakeholder and Community Engagement | 0 | 0 | 3092.5291 | 3092.5291 | 0 | 6185.0581 |  | 0 | 0 | 2164.7703 | 2164.7703 | 0 | 4329.5407 | 0 | 0 | 927.7587 | 927.7587 | 0 | 1855.5174
| Insurance Costs | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Phased by Financial Year | 0 | 0 | 1696123.8816 | 1470734.0456 | 0 | 3166857.9271 |  | 0 | 0 | 1187286.7171 | 1029513.8319 | 0 | 2216800.549 | 0 | 0 | 508837.1645 | 441220.2137 | 0 | 950057.3781
Labour Related component
| Works Delivery | 0 | 0 | 414530.7283 | 312036.2724 | 0 | 726567.0007 |  | 0 | 0 | 290171.5098 | 218425.3907 | 0 | 508596.9005 | 0 | 0 | 124359.2185 | 93610.8817 | 0 | 217970.1002
| Project Development | 0 | 0 | 137355.3707 | 48446.0899 | 0 | 185801.4606 |  | 0 | 0 | 96148.7595 | 33912.2629 | 0 | 130061.0224 | 0 | 0 | 41206.6112 | 14533.827 | 0 | 55740.4382
| Other Indirect Capex | 0 | 0 | 61.7123 | 61.7123 | 0 | 123.4245 |  | 0 | 0 | 43.1986 | 43.1986 | 0 | 86.3972 | 0 | 0 | 18.5137 | 18.5137 | 0 | 37.0274
| Land and Environment Costs | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Stakeholder and Community Engagement | 0 | 0 | 61.7123 | 61.7123 | 0 | 123.4245 |  | 0 | 0 | 43.1986 | 43.1986 | 0 | 86.3972 | 0 | 0 | 18.5137 | 18.5137 | 0 | 37.0274
| Insurance Costs | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Phased by Financial Year | 0 | 0 | 551947.8113 | 360544.0746 | 0 | 912491.8859 |  | 0 | 0 | 386363.4679 | 252380.8522 | 0 | 638744.3201 | 0 | 0 | 165584.3434 | 108163.2224 | 0 | 273747.5658
Non-Labour component
| Works Delivery | 0 | 0 | 16476.973 | 21352.812 | 0 | 37829.785 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16476.973 | 21352.812 | 0 | 37829.785
| Project Development | 0 | 0 | 100224.8724 | 0 | 0 | 100224.8724 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100224.8724 | 0 | 0 | 100224.8724
| Other Indirect Capex | 0 | 0 | 36225.2067 | 46575.2657 | 0 | 82800.4724 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36225.2067 | 46575.2657 | 0 | 82800.4724
| Land and Environment Costs | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Stakeholder and Community Engagement | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Insurance Costs | 0 | 0 | 36225.2067 | 46575.2657 | 0 | 82800.4724 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36225.2067 | 46575.2657 | 0 | 82800.4724
| Phased by Financial Year | 0 | 0 | 152927.0521 | 67928.0777 | 0 | 220855.1298 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 152927.0521 | 67928.0777 | 0 | 220855.1298
Total Labour and Non-Labour
| Phased by Financial Year | 0 | 0 | 2400998.7449 | 1899206.1979 | 0 | 4300204.9428 |  | 0 | 0 | 1573650.185 | 1281894.6841 | 0 | 2855544.8691 | 0 | 0 | 827348.5599 | 617311.5138 | 0 | 1444660.0737
Actual TransGrid Labour and Indirect Costs
|  | Actual TransGrid Labour and Indirect Costs | [6 empty] | Actual Direct Costs | [5 empty] | Actual Indirect Costs
|  | 2018-19 | 2019-20 | 2020-21 | 2021-22 | 2022-23 | TOTAL FY20-FY23 |  | 2018-19 | 2019-20 | 2020-21 | 2021-22 | 2022-23 | TOTAL FY20-FY23 | 2018-19 | 2019-20 | 2020-21 | 2021-22 | 2022-23 | TOTAL FY20-FY23
| Classification | 2017/8 $ | 2017/8 $ | 2017/8 $ | 2017/8 $ | 2017/8 $ | 2017/8 $ |  | 2017/8 $ | 2017/8 $ | 2017/8 $ | 2017/8 $ | 2017/8 $ | 2017/8 $ | 2017/8 $ | 2017/8 $ | 2017/8 $ | 2017/8 $ | 2017/8 $ | 2017/8 $
| Labour | 65247.7307 | 688265.8958 | 294639.4805 | 0 | 0 | 982905.3763 |  | 45673.4115 | 481786.1271 | 206247.6363 | 0 | 0 | 733707.1749 | 19574.3192 | 206479.7687 | 88391.8441 | 0 | 0 | 314445.9321
| Labour Related | 20.8584 | 60234.2149 | 1473.979 | 0 | 0 | 61708.1939 |  | 14.6008 | 42163.9504 | 1031.7853 | 0 | 0 | 43210.3365 | 6.2575 | 18070.2645 | 442.1937 | 0 | 0 | 18518.7157
| Non-Labour | 199333.6746 | 965892.8123 | 673938.0602 | 0 | 0 | 1639830.8725 |  | 0 | 0 | 0 | 0 | 0 | 0 | 199333.6746 | 965892.8123 | 673938.0602 | 0 | 0 | 1839164.5471
| Phased by Financial Year | 264602.2636 | 1714392.923 | 970051.5197 | 0 | 0 | 2949046.7063 |  | 45688.0123 | 523950.0775 | 207279.4216 | 0 | 0 | 776917.5114 | 218914.2513 | 1190442.8455 | 762772.0981 | 0 | 0 | 2172129.1948
Actual and Forecast TransGrid Labour and Indirect Costs
|  | Actual and Forecast TransGrid Labour and Indirect Costs | [6 empty] | Actual and Forecast Direct Costs | [5 empty] | Actual and Forecast Indirect Costs
|  | 2018-19 | 2019-20 | 2020-21 | 2021-22 | 2022-23 | TOTAL FY19-FY23 |  | 2018-19 | 2019-20 | 2020-21 | 2021-22 | 2022-23 | TOTAL FY19-FY23 | 2018-19 | 2019-20 | 2020-21 | 2021-22 | 2022-23 | TOTAL FY19-FY23
| Total estimate: Actuals + Forecast | 2017/8 $ | 2017/8 $ | 2017/8 $ | 2017/8 $ | 2017/8 $ | 2017/8 $ |  | 2017/8 $ | 2017/8 $ | 2017/8 $ | 2017/8 $ | 2017/8 $ | 2017/8 $ | 2017/8 $ | 2017/8 $ | 2017/8 $ | 2017/8 $ | 2017/8 $ | 2017/8 $
| Actuals | 264602.2636 | 1714392.923 | 970051.5197 | 0 | 0 | 2949046.7063 |  | 45688.0123 | 523950.0775 | 207279.4216 | 0 | 0 | 776917.5114 | 218914.2513 | 1190442.8455 | 762772.0981 | 0 | 0 | 2172129.1948
| Forecast | 0 | 0 | 2400998.7449 | 1899206.1979 | 0 | 4300204.9428 |  | 0 | 0 | 1573650.185 | 1281894.6841 | 0 | 2855544.8691 | 0 | 0 | 827348.5599 | 617311.5138 | 0 | 1444660.0737
| Total estimate of VNI Costs - Actuals + Forecast | 264602.2636 | 1714392.923 | 3371050.2646 | 1899206.1979 | 0 | 7249251.6491 |  | 45688.0123 | 523950.0775 | 1780929.6066 | 1281894.6841 | 0 | 3632462.3805 | 218914.2513 | 1190442.8455 | 1590120.658 | 617311.5138 | 0 | 3616789.2685

## s4. Works Delivery
|  |  |  | Current / Nominal values (2018/9) |  |  |  |  | Restatement to 2017-18 LABOUR rates |  |  |  |  | Restatement to 2017/8 $
s4. Works Delivery | Nominal values | Labour adjusted | Restated estimates | 2019-20 | 2020-21 | 2021-22 | 2022-23 | TOTAL | 2019-20 | 2020-21 | 2021-22 | 2022-23 | TOTAL | 2019-20 | 2020-21 | 2021-22 | 2022-23 | TOTAL
Labour costs
Works Delivery Project Management | 1518974.33 | 1506753.0247 | 1483170.612 | 0 | 707354.638 | 811619.692 | 0 | 1518974.33 | 0 | 701663.4313 | 805089.5935 | 0 | 1506753.0247 | 0 | 690681.5939 | 792489.0181 | 0 | 1483170.612
Site Management | 964212.28 | 956454.4579 | 941484.8488 | 0 | 534689.59 | 429522.69 | 0 | 964212.28 | 0 | 530387.6051 | 426066.8529 | 0 | 956454.4579 | 0 | 522086.4308 | 419398.418 | 0 | 941484.8488
Technical Management | 157757.39 | 156488.1117 | 154038.8933 | 0 | 121058.7 | 36698.69 | 0 | 157757.39 | 0 | 120084.6906 | 36403.4211 | 0 | 156488.1117 | 0 | 118205.2274 | 35833.6658 | 0 | 154038.8933
Technical Fitters | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Support | 35107.37 | 34824.9045 | 34279.8548 | 0 | 17016.52 | 18090.85 | 0 | 35107.37 | 0 | 16879.6091 | 17945.2953 | 0 | 34824.9045 | 0 | 16615.4239 | 17664.4309 | 0 | 34279.8548
Works Delivery - Labour costs | 2676051.37 | 2654520.4988 | 2612974.2089 | 0 | 1380119.448 | 1295931.922 | 0 | 2676051.37 | 0 | 1369015.336 | 1285505.1628 | 0 | 2654520.4988 | 0 | 1347588.6761 | 1265385.5328 | 0 | 2612974.2089
Labour Related costs
Sustenance | 320974.01 | 320974.01 | 315950.3987 | 0 | 198568.468 | 122405.542 | 0 | 320974.01 | 0 | 198568.468 | 122405.542 | 0 | 320974.01 | 0 | 195460.6438 | 120489.7549 | 0 | 315950.3987
Training | 13585.3119 | 13585.3119 | 13372.6862 | 0 | 4615.1722 | 8970.1397 | 0 | 13585.3119 | 0 | 4615.1722 | 8970.1397 | 0 | 13585.3119 | 0 | 4542.9395 | 8829.7467 | 0 | 13372.6862
Recruitment | 139620.1973 | 138496.8464 | 136329.212 | 0 | 74186.3917 | 65433.8055 | 0 | 139620.1973 | 0 | 73589.5057 | 64907.3407 | 0 | 138496.8464 | 0 | 72437.7456 | 63891.4664 | 0 | 136329.212
Travel & Expenses | 241062.53 | 241062.53 | 237289.625 | 0 | 136195.15 | 104867.38 | 0 | 241062.53 | 0 | 136195.15 | 104867.38 | 0 | 241062.53 | 0 | 134063.5397 | 103226.0852 | 0 | 237289.625
IT hardware | 24000.7177 | 24000.7177 | 23625.0789 | 0 | 8153.4709 | 15847.2468 | 0 | 24000.7177 | 0 | 8153.4709 | 15847.2468 | 0 | 24000.7177 | 0 | 8025.8598 | 15599.2192 | 0 | 23625.0789
Works Delivery - Labour Related Costs | 739242.7668 | 738119.416 | 726567.0007 | 0 | 421718.6529 | 317524.1139 | 0 | 739242.7668 | 0 | 421121.7669 | 316997.6491 | 0 | 738119.416 | 0 | 414530.7283 | 312036.2724 | 0 | 726567.0007
Works Delivery - Non-Labour costs | 38297.87 | 38297.87 | 37829.785 | 0 | 16680.85 | 21617.02 | 0 | 38297.87 | 0 | 16680.85 | 21617.02 | 0 | 38297.87 | 0 | 16476.973 | 21352.812 | 0 | 37829.785
TOTAL WORKS DELIVERY | 3453592.0068 | 3430937.7848 | 3377370.9946 | 0 | 1818518.9509 | 1635073.0559 | 0 | 3453592.0068 | 0 | 1806817.9529 | 1624119.8319 | 0 | 3430937.7848 | 0 | 1778596.3774 | 1598774.6172 | 0 | 3377370.9946

## Works Delivery Res Cost
CONFIDENTIAL
[Content removed from public version]

## Works Delivery Labour FTEs
CONFIDENTIAL
[Content removed from public version]

## Works Delivery Labour Hrs
CONFIDENTIAL
[Content removed from public version]

## s5. Project Development
|  |  |  | Current / Nominal values (2018/9) |  |  |  |  | Restatement to 2017-18 LABOUR rates |  |  |  |  | Restatement to 2017/8 $
s5. Project Development | Nominal / Current Rates | Labour adjusted | Restated estimates | 2019-20 | 2020-21 | 2021-22 | 2022-23 | TOTAL | 2019-20 | 2020-21 | 2021-22 | 2022-23 | TOTAL | 2019-20 | 2020-21 | 2021-22 | 2022-23 | TOTAL
Labour costs
Project Management Team | 400616.832 | 397393.5645 | 391173.8995 | 0 | 276339.63 | 124277.202 | 0 | 400616.832 | 0 | 274116.2672 | 123277.2973 | 0 | 397393.5645 | 0 | 269826.0333 | 121347.8662 | 0 | 391173.8995
HV Design | 22628.55 | 22446.4861 | 22095.1728 | 0 | 0 | 22628.55 | 0 | 22628.55 | 0 | 0 | 22446.4861 | 0 | 22446.4861 | 0 | 0 | 22095.1728 | 0 | 22095.1728
VNI Project Management Team | 423245.382 | 419840.0506 | 413269.0723 | 0 | 276339.63 | 146905.752 | 0 | 423245.382 | 0 | 274116.2672 | 145723.7833 | 0 | 419840.0506 | 0 | 269826.0333 | 143443.039 | 0 | 413269.0723
Major Projects team | 48013.2095 | 47626.9067 | 46881.491 | 0 | 27007.4303 | 21005.7792 | 0 | 48013.2095 | 0 | 26790.135 | 20836.7717 | 0 | 47626.9067 | 0 | 26370.8387 | 20510.6523 | 0 | 46881.491
Major Projects Team | 48013.2095 | 47626.9067 | 46881.491 | 0 | 27007.4303 | 21005.7792 | 0 | 48013.2095 | 0 | 26790.135 | 20836.7717 | 0 | 47626.9067 | 0 | 26370.8387 | 20510.6523 | 0 | 46881.491
Other incremental resources required for VNI | 89661.5067 | 88940.1116 | 87548.0969 | 0 | 50434.5975 | 39226.9092 | 0 | 89661.5067 | 0 | 50028.8128 | 38911.2988 | 0 | 88940.1116 | 0 | 49245.8045 | 38302.2924 | 0 | 87548.0969
Subtotal - Other incremental resources | 89661.5067 | 88940.1116 | 87548.0969 | 0 | 50434.5975 | 39226.9092 | 0 | 89661.5067 | 0 | 50028.8128 | 38911.2988 | 0 | 88940.1116 | 0 | 49245.8045 | 38302.2924 | 0 | 87548.0969
TOTAL PROJECT DEVELOPMENT LABOUR | 560920.0982 | 556407.0688 | 547698.6601 | 0 | 353781.6579 | 207138.4403 | 0 | 560920.0982 | 0 | 350935.215 | 205471.8538 | 0 | 556407.0688 | 0 | 345442.6764 | 202255.9837 | 0 | 547698.6601
Labour Related costs
Recruitment | 89206.3057 | 88488.573 | 87103.6254 | 0 | 89206.3057 | 0 | 0 | 89206.3057 | 0 | 88488.573 | 0 | 0 | 88488.573 | 0 | 87103.6254 | 0 | 0 | 87103.6254
Training | 2993.0341 | 2993.0341 | 2946.1896 | 0 | 1542.9567 | 1450.0774 | 0 | 2993.0341 | 0 | 1542.9567 | 1450.0774 | 0 | 2993.0341 | 0 | 1518.8076 | 1427.382 | 0 | 2946.1896
Office Lease costs | 19156.3467 | 19156.3467 | 18856.528 | 0 | 10448.9164 | 8707.4303 | 0 | 19156.3467 | 0 | 10448.9164 | 8707.4303 | 0 | 19156.3467 | 0 | 10285.3789 | 8571.1491 | 0 | 18856.528
Travel & Expenses | 78117.75 | 78117.75 | 76895.1176 | 0 | 39058.875 | 39058.875 | 0 | 78117.75 | 0 | 39058.875 | 39058.875 | 0 | 78117.75 | 0 | 38447.5588 | 38447.5588 | 0 | 76895.1176
Labour Related costs | 189473.4365 | 188755.7038 | 185801.4606 | 0 | 140257.0538 | 49216.3827 | 0 | 189473.4365 | 0 | 139539.3211 | 49216.3827 | 0 | 188755.7038 | 0 | 137355.3707 | 48446.0899 | 0 | 185801.4606
Non-Labour costs
Other consulting costs | 101465 | 101465 | 100224.8724 | 0 | 101465 | 0 | 0 | 101465 | 0 | 101465 | 0 | 0 | 101465 | 0 | 100224.8724 | 0 | 0 | 100224.8724
TOTAL PROJECT DEVELOPMENT - NON-LABOUR | 101465 | 101465 | 100224.8724 | 0 | 101465 | 0 | 0 | 101465 | 0 | 101465 | 0 | 0 | 101465 | 0 | 100224.8724 | 0 | 0 | 100224.8724
TOTAL PROJECT DEVELOPMENT | 851858.5347 | 846627.7727 | 833724.9932 | 0 | 595503.7116 | 256354.8231 | 0 | 851858.5347 | 0 | 591939.5361 | 254688.2366 | 0 | 846627.7727 | 0 | 583022.9196 | 250702.0736 | 0 | 833724.9932

## PD-Labour(&related)
CONFIDENTIAL
[Content removed from public version]

## PD - LabourHours
CONFIDENTIAL
[Content removed from public version]

## PD-NonLabour
CONFIDENTIAL
[Content removed from public version]

## s6.1 Land & Environment
|  |  |  | Current / Nominal values (2018/9) |  |  |  |  | Restatement to 2017-18 LABOUR rates |  |  |  |  | Restatement to 2017/8 $
s6.1 Land & Environment | Current / Nominal Rates | Labour adjusted | Restated estimates | 2019-20 | 2020-21 | 2021-22 | 2022-23 | TOTAL | 2019-20 | 2020-21 | 2021-22 | 2022-23 | TOTAL | 2019-20 | 2020-21 | 2021-22 | 2022-23 | TOTAL
Non-Labour
Environment Consultant | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Non-Labour | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Totals | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## L&E-NonLabour
CONFIDENTIAL
[Content removed from public version]

## s6.2 Stakeholder & Comm Egmt
|  |  |  | Current / Nominal values (2018/9) |  |  |  |  | Restatement to 2017-18 LABOUR rates |  |  |  |  | Restatement to 2017/8 $
s6.2 Stakeholder & Community Engagement | Current Rates | Labour adjusted | Restated estimates | 2019-20 | 2020-21 | 2021-22 | 2022-23 | TOTAL | 2019-20 | 2020-21 | 2021-22 | 2022-23 | TOTAL | 2019-20 | 2020-21 | 2021-22 | 2022-23 | TOTAL
Labour costs
Major Projects | 6334.3653 | 6283.4005 | 6185.0581 | 0 | 3167.1827 | 3167.1827 | 0 | 6334.3653 | 0 | 3141.7003 | 3141.7003 | 0 | 6283.4005 | 0 | 3092.5291 | 3092.5291 | 0 | 6185.0581
Labour | 6334.3653 | 6283.4005 | 6185.0581 | 0 | 3167.1827 | 3167.1827 | 0 | 6334.3653 | 0 | 3141.7003 | 3141.7003 | 0 | 6283.4005 | 0 | 3092.5291 | 3092.5291 | 0 | 6185.0581
Labour Related costs
Training | 125.387 | 125.387 | 123.4245 | 0 | 62.6935 | 62.6935 | 0 | 125.387 | 0 | 62.6935 | 62.6935 | 0 | 125.387 | 0 | 61.7123 | 61.7123 | 0 | 123.4245
Labour related | 125.387 | 125.387 | 123.4245 | 0 | 62.6935 | 62.6935 | 0 | 125.387 | 0 | 62.6935 | 62.6935 | 0 | 125.387 | 0 | 61.7123 | 61.7123 | 0 | 123.4245
Totals | 6459.7523 | 6408.7875 | 6308.4827 | 0 | 3229.8762 | 3229.8762 | 0 | 6459.7523 | 0 | 3204.3938 | 3204.3938 | 0 | 6408.7875 | 0 | 3154.2413 | 3154.2413 | 0 | 6308.4827

## SHC-Labour(&related)
CONFIDENTIAL
[Content removed from public version]

## s6.3. Insurance
INSURANCE | [18 empty] | Cost estimate by month> | [38 empty] | Current / Nominal values (2018/9) |  |  |  |  | Restatement to 2017/8 $
Non-labour costs | [7 empty] | Current $A | [9 empty] | FY19/20 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39
| s6.3 Insurance | Cost Type | Report Reference | Description | Supplier | Assumption / evidence source | Assumption provided by | Total - One off (FY20) | Total Cost to be phased | Recurring? | Start Month | End Month | Duration (Months) | Allocate across Major Projects? | VNI allocation - one off | VNI allocation - Annual cost | Monthly equivalent | One off | 2020-04-01 | 2020-05-01 | 2020-06-01 | 2020-07-01 | 2020-08-01 | 2020-09-01 | 2020-10-01 | 2020-11-01 | 2020-12-01 | 2021-01-01 | 2021-02-01 | 2021-03-01 | 2021-04-01 | 2021-05-01 | 2021-06-01 | 2021-07-01 | 2021-08-01 | 2021-09-01 | 2021-10-01 | 2021-11-01 | 2021-12-01 | 2022-01-01 | 2022-02-01 | 2022-03-01 | 2022-04-01 | 2022-05-01 | 2022-06-01 | 2022-07-01 | 2022-08-01 | 2022-09-01 | 2022-10-01 | 2022-11-01 | 2022-12-01 | 2023-01-01 | 2023-02-01 | 2023-03-01 | 2023-04-01 | 2023-05-01 | 2023-06-01 | 2019-20 | 2020-21 | 2021-22 | 2022-23 | TOTAL | 2019-20 | 2020-21 | 2021-22 | 2022-23 | TOTAL
| Insurance | Insurance | 6.3 | Insurance required during construction phase | [Removed] | [Supplier reference removed] |  |  | 83825 |  | 9 | 24 | 16 | n | 0 | 83825 | 5239.0625 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5239.0625 | 5239.0625 | 5239.0625 | 5239.0625 | 5239.0625 | 5239.0625 | 5239.0625 | 5239.0625 | 5239.0625 | 5239.0625 | 5239.0625 | 5239.0625 | 5239.0625 | 5239.0625 | 5239.0625 | 5239.0625 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36673.4375 | 47151.5625 | 0 | 83825 | 0 | 36225.2067 | 46575.2657 | 0 | 82800.4724
[15 empty] | 0 | 83825 | 5239.0625 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5239.0625 | 5239.0625 | 5239.0625 | 5239.0625 | 5239.0625 | 5239.0625 | 5239.0625 | 5239.0625 | 5239.0625 | 5239.0625 | 5239.0625 | 5239.0625 | 5239.0625 | 5239.0625 | 5239.0625 | 5239.0625 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36673.4375 | 47151.5625 | 0 | 83825 | 0 | 36225.2067 | 46575.2657 | 0 | 82800.4724