## Amendments (December 2021)
Additional AER Changes
Corrections made to the priority project order, and removal of 1 project

## Explanatory notes
TEMPLATE EXPLANATION
This template must be used by the TNSP to report on the implementation of their priority projects for the previous calendar year. This report template is to be submitted by the TNSP to the AER as part of the annual STPIS compliance review.
After the initial report template is filled out and provided by TNSPs in the first STPIS compliance review for the regulatory control period for which the NCIPAP applies, the TNSP will update the report template at the end of each calendar year and provide a updated copy to the AER as part of the annual STPIS compliance review.
The summary worksheet provides an overview of the priority projects and whether, at the time of submitting this NCIPAP reporting template, the TNSP has taken steps to implement any of its priority projects and/or completed any of its priority projects.
One priority project worksheet should be filled out for each priority project in the TNSP's NCIPAP. These worksheets will be used by the TNSP to provide updates on the status of the implementation of the priority projects. If the TNSP successfully implements a priority project, takes steps towards the delivery on a priority project or encounters delays in a priority project in the previous calendar year, the priority project worksheet should be updated to reflect this and the summary should also be updated.
This template also provides worksheet templates for TNSPs which want to, as part of the STPIS compliance review, remove priority projects from their NCIPAP and propose a replacement priority project to be added to the NCIPAP.

## Summary
Priority project name and ranking | Summary of project | Report on steps the TNSP has taken under 5.2 (s) |  |  |  | Have steps been taken in the previous calendar year to implement the priority project? | Priority project completion summary
[7 empty] | Has the priority project been delivered? | Has the priority project improvement target been achieved? | If the priority project has been delivered, has AEMO been notified of any change in the limit? | Constraint definition - the purpose of this question is to define the specific constraints impacted by the project.
s | Explanatory statement: include a short description of the priority project | 5.2 (S) (1) the current value of limit of the transmission circuit and/or injection points which each priority project seeks to address | 5.2 (S) (2) up-to-date actual operational and capital expenditure for each priority project | 5.2 (S) (3) the expected completion date for each priority project. | 5.2 (S) (4) for priority projects which the TNSP intends to proceed with prior to the next annual STPIS compliance review, verification that the assumptions used to justify the material benefit of undertaking the priority project have not materially changed resulting in the priority project no longer having a material benefit (as defined in clause 5.3(d)(2)). This includes whether it sought verification from AEMO or another third party that the key assumptions on which the material benefit of undertaking the priority project is based are still valid. | Explanatory statement: indicate 'yes' or 'no' as to whether any steps have been taken by the TNSP to implement the priority project in the previous calendar year. If steps have been taken by the TNSP to implement the priority project in the previous calendar year, please update the worksheet for the priority project. | Explanatory statement: indicate 'yes' or 'no' as to whether the priority project has been delivered. | Explanatory statement: indicate 'yes' or 'no' as to whether the improvement target has been achieved following the completion of the priority project. If the improvement target has not been achieved despite the completion of the priority project, please provide further information in row 15 of the relevant priority project worksheet. | Explanatory statement: indicate if AEMO has been made aware, for operational purposes, of the change in the limit. | Constraint IDs changed by the project.
Priority Project 1 – Increase capacity for Generation between Darlington Point and Wagga | Upgrade cooler banks of 330/132 kV transformers at Darlington Point Substation to increase their rating | 280 MVA | CAPEX: 0 , OPEX: 0 | ● Project is expected to be completed by June 2025. | No changes in the assumptions which are used to justify material benefit of undertaking this priority project. | No
Priority Project 2 - Increase capacity in Yass Transformers | Develop & implement a dynamic rating system for Yass No.1 and No.2 330/132 kV transformers | 200 MVA | CAPEX: 0 , OPEX: 0 | ● Project is expected to be completed by June 2025. | No changes in the assumptions which are used to justify material benefit of undertaking this priority project. | No
Priority Project 3 – 94T Dynamic ratings | Install a Dynamic Line Rating system on the 94T Molong to Parkes 132 kV line to reduce limitations on the generation in the Central West NSW area | 112 MW summer rating | CAPEX: 0 , OPEX: 0 | ● Project is expected to be completed by June 2024. | No changes in the assumptions which are used to justify material benefit of undertaking this priority project.
Priority Project 4 – Increase capacity for generation X5 Voltage Stability constraints | Install a 20 MVAr capacitor bank at Balranald 220 kV Substation to increase the capacity for generation by 5-10 MW in the Far West NSW network | Subjuect to the constraint equation: Flow east on line X5 < 216 - 0.25 x k x (Murraylink flow) - 5.8 x (status of Buronga 33MVAr reactor) - 4.8 x (Status of Buronga 22 MVAr reactor) + 0.2 x (No. of inverters on0-line at Limondale 1 Solar Farm) Where constant k = 1 if Murraylink is exproting power to South Australia, 0 otherwise | CAPEX: 0 , OPEX: 0 | ● Project is expected to be completed by June 2025. | No changes in the assumptions which are used to justify material benefit of undertaking this priority project. | No
Priority Project 5 – Maintain capacity during Climate Change | Installation of DLR onto transmission lines with maximum contingency loading above 100% | Future de-rating of transmission lines | CAPEX: 0 , OPEX: 0 | ● Project is expected to be completed by June 2028. | No changes in the assumptions which are used to justify material benefit of undertaking this priority project. | No
Priority Project 6 – Darlington Point 330/220 kV Transformer Tripping Scheme | Install tripping scheme to trip remaining 330/220/33 kV transformer at Darlington Point Substation for a loss of one transformer | 125 MVA | CAPEX: 0 , OPEX: 0 | ● Project is expected to be completed by June 2025. | No changes in the assumptions which are used to justify material benefit of undertaking this priority project. | No

## Priority project (template)
Priority project name and ranking | [insert name and ranking]
Priority project description | [insert priority project description – can be taken from the NCIPAP]
Co-ordinated project | [indicate whether the priority project is a co-ordinated project.]
Has the priority project been commenced ? | [indicate the current status of the priority project i.e has it been commenced (if so, please include a brief summary of where the project is at), completed or delayed/deferred]
Date of priority project completion | [insert date of priority project completion]
Limit(s) addressed by priority project | [insert description of the limit(s) which the priority project seeks to address. For priority projects which are co-ordinated projects, please include a description of all relevant limit(s), including the limit(s) located on the other TNSP's network. For the limit(s), please indicate in which TNSP network they are located]
Initial limit value(s) | [insert initial limit value(s) from NCIPAP. For priority projects which are co-ordinated projects, please include all relevant limit value(s), including the limit value(s) of any limit(s) on the other TNSP's network]
Target limit value(s) | [insert priority project improvement target]
Completion limit values | [once the priority project has been completed, insert the new value(s) of the limit(s) which the priority project has sought to address and indicate whether the improvement target has been achieved following the implementation of the priority project]
Estimated capital cost of priority project | [insert cost estimate from NCIPAP]
Estimated operating cost of priority project | [insert estimate from NCIPAP]
Capital expenditure to date | [insert actual capital expenditure spent to date on the implementation/delivery of the priority project. Equipment costs (i.e. isolators, interplant connections, protection relays) should be broken down and individually itemised. For co-ordinated priority projects, only include the capital expenditure of the reporting TNSP]
Operating expenditure to date | [insert actual operating expenditure spent to date. For co-ordinated priority projects, only include the operating expenditure of the reporting TNSP]
Priority project key milestones and dates | [include in this section the key project milestones and the estimated dates in which those milestones will be completed. If applicable the following project milestones should be included: ● Final internal approval to undertake project ● Obtaining planning/environmental approvals ● Procurement of equipment ● Project commencement date – this is the date in which the project implementation will commence i.e date when capital works commence, commencement of study/review. ● Key project delivery dates – include key project implementation steps and estimated dates ● Project completion date For co-ordinated priority projects, include the key project milestones and dates of both TNSPs and indicate which TNSP is reponsible for the milestone. If there is a delay or complication in the implementation of the priority project since the last NCIPAP annual report to the AER which changes the estimated dates for the key project milestones listed, please update the revised estimate date for the relevant key project milestone and indicate that the date for the key project milestone has been revised. Also indicate separately whether any key milestones have been completed and the date in which they have been completed – do not remove any estimated dates]
Priority project update/comments | [include a written summary of the current status of the priority project against the key milestones and where it is up to. If there are any delays or complications with the project have arisen, include a summary here. For co-ordinated priority projects, the reporting TNSP should also include any delays or complications which they are aware the other TNSP is experiencing in the implementation of the project. In the final update on the NCIPAP approved projects in the regulatory control period, the AER may have to make a determination in accordance with clause 5.3(b) of the STPIS on whether to reduce the financial incentive payment if the priority project does not achieve its priority project improvement target. If this may be applicable for this priority project, please include the following information (where relevant): ● If the priority project has not been completed at the end of the regulatory control period – please include details why this has been the case and when the priority project is expected to be completed. Take into account the factors listed in 5.3(e) of the STPIS. ● If the priority project has been completed at the end of the regulatory control period and the priority project improvement target has not been achieved – please include details of why this is the case. Take into account the factors listed in 5.3(e) of the STPIS. ● If the priority project has been completed and the target has been achieved, please confirm whether the improvement target has been achieved because of the implementation of the priority project or it is due to other network augmentation and/or replacement of existing network assets (i.e. if the priority project had not been successfully implemented, would the improvement target have still been achieved?). If it is the latter, please explain why this has been done and state the capital cost of the network augmentation and/or network asset replacement. Take into account the factors listed in 5.3(e) of the STPIS.
● If the priority project has been completed and the target has been achieved but the project has exceeded the estimated capital cost, please explain why this has been the case? Take into account the factors listed in 5.3(e) of the STPIS. ]
EXPLANATORY NOTE
In the first NCIPAP compliance report for a new regulatory control period, please fill out rows 1-3, 7-8, 10-11 and 14 for each priority project.
In following NCIPAP compliance report updates, the worksheet only needs to be updated where:
if during the previous calendar year the TNSP undertakes steps to implement a priority project (in this instance, updates may be needed for rows 4, 12, 13, 14 and 15)
if during the previous calendar year, events occur which result in the priority project key milestone dates being changed (please update this rows 14 and 15 of this worksheet), or
if the priority project has been completed in the previous calendar year (if this is the case, fill out rows 5 and 9 and ensure rows 4, 12, 13, 14 and 15 are up to date)
If this worksheet is updated, please update the summary worksheet to indicate changes have been made.

## Priority project 1
Priority project name and ranking | Priority Project 1 – Increase capacity for Generation between Darlington Point and Wagga
Priority project description | Upgrade cooler banks of 330/132 kV transformers at Darlington Point Substation to increase their rating
Co-ordinated project | No
Has the priority project been commenced ? | No
Date of priority project completion
Limit(s) addressed by priority project | Thermal rating of Darlington Point 330/132 kV transformers
Initial limit value(s) | 280 MVA
Target limit value(s) | 375 MVA
Completion limit values
Estimated capital cost of priority project | 4130000
Estimated operating cost of priority project | 82600
Capital expenditure to date | 0
Operating expenditure to date | 0
Priority project key milestones and dates | ● Project is expected to be completed by June 2025.
Priority project update/comments | payback period: 1 year from project completion; Allows the transformers to operate up to the design rate hence increases the transfer capacity for the renewable generation in the subsystem. Assessment carried out for the remaining useful life of the transformers
EXPLANATORY NOTE
In the first NCIPAP compliance report for a new regulatory control period, please fill out rows 1-3, 7-8, 10-11 and 14 for each priority project.
In following NCIPAP compliance report updates, the worksheet only needs to be updated where:
if during the previous calendar year the TNSP undertakes steps to implement a priority project (in this instance, updates may be needed for rows 4, 12, 13, 14 and 15)
if during the previous calendar year, events occur which result in the priority project key milestone dates being changed (please update this rows 14 and 15 of this worksheet), or
if the priority project has been completed in the previous calendar year (if this is the case, fill out rows 5 and 9 and ensure rows 4, 12, 13, 14 and 15 are up to date)
If this worksheet is updated, please update the summary worksheet to indicate changes have been made.

## Priority project 2
Priority project name and ranking | Priority Project 2 - Increase capacity in Yass Transformers
Priority project description | Develop & implement a dynamic rating system for Yass No.1 and No.2 330/132 kV transformers
Co-ordinated project | No
Has the priority project been commenced ? | No
Date of priority project completion
Limit(s) addressed by priority project | Yass No.1 and No.2 transformers thermal rating
Initial limit value(s) | 200 MVA
Target limit value(s) | 300 MVA (design rate)
Completion limit values
Estimated capital cost of priority project | 1610000
Estimated operating cost of priority project | 32200
Capital expenditure to date | 0
Operating expenditure to date | 0
Priority project key milestones and dates | ● Project is expected to be completed by June 2025.
Priority project update/comments | Payback period: 1 year from project completion
EXPLANATORY NOTE
In the first NCIPAP compliance report for a new regulatory control period, please fill out rows 1-3, 7-8, 10-11 and 14 for each priority project.
In following NCIPAP compliance report updates, the worksheet only needs to be updated where:
if during the previous calendar year the TNSP undertakes steps to implement a priority project (in this instance, updates may be needed for rows 4, 12, 13, 14 and 15)
if during the previous calendar year, events occur which result in the priority project key milestone dates being changed (please update this rows 14 and 15 of this worksheet), or
if the priority project has been completed in the previous calendar year (if this is the case, fill out rows 5 and 9 and ensure rows 4, 12, 13, 14 and 15 are up to date)
If this worksheet is updated, please update the summary worksheet to indicate changes have been made.

## Priority project 3
Priority project name and ranking | Priority Project 3 – 94T Dynamic ratings
Priority project description | Install a Dynamic Line Rating system on the 94T Molong to Parkes 132 kV line to reduce limitations on the generation in the Central West NSW area
Co-ordinated project | No
Has the priority project been commenced ? | No
Date of priority project completion
Limit(s) addressed by priority project | System Normal and contigency rating of Line 94T
Initial limit value(s) | 112 MW summer rating
Target limit value(s) | Dynamic line rating (target maximum is 134 MVA Summer Day)
Completion limit values
Estimated capital cost of priority project | 456000
Estimated operating cost of priority project | 9120
Capital expenditure to date | 0
Operating expenditure to date | 0
Priority project key milestones and dates | ● Project is expected to be completed by June 2024.
Priority project update/comments | payback period: 1 year from project completion; Market benefits expected to deliver by increasing the transfer capacity for the solar farms in the west of Molong.
EXPLANATORY NOTE
In the first NCIPAP compliance report for a new regulatory control period, please fill out rows 1-3, 7-8, 10-11 and 14 for each priority project.
In following NCIPAP compliance report updates, the worksheet only needs to be updated where:
if during the previous calendar year the TNSP undertakes steps to implement a priority project (in this instance, updates may be needed for rows 4, 12, 13, 14 and 15)
if during the previous calendar year, events occur which result in the priority project key milestone dates being changed (please update this rows 14 and 15 of this worksheet), or
if the priority project has been completed in the previous calendar year (if this is the case, fill out rows 5 and 9 and ensure rows 4, 12, 13, 14 and 15 are up to date)
If this worksheet is updated, please update the summary worksheet to indicate changes have been made.

## Priority project 4
Priority project name and ranking | Priority Project 4 – Increase capacity for generation X5 Voltage Stability constraints
Priority project description | Install a 20 MVAr capacitor bank at Balranald 220 kV Substation to increase the capacity for generation by 5-10 MW in the Far West NSW network
Co-ordinated project | No
Has the priority project been commenced ? | No
Date of priority project completion
Limit(s) addressed by priority project | The current binding voltage stability constraint on X5 line flow (east)
Initial limit value(s) | Subjuect to the constraint equation: Flow east on line X5 < 216 - 0.25 x k x (Murraylink flow) - 5.8 x (status of Buronga 33MVAr reactor) - 4.8 x (Status of Buronga 22 MVAr reactor) + 0.2 x (No. of inverters on0-line at Limondale 1 Solar Farm) Where constant k = 1 if Murraylink is exproting power to South Australia, 0 otherwise
Target limit value(s) | Initial limit value plus 5 to 10 MW
Completion limit values
Estimated capital cost of priority project | 5440000
Estimated operating cost of priority project | 108800
Capital expenditure to date | 0
Operating expenditure to date | 0
Priority project key milestones and dates | ● Project is expected to be completed by June 2025.
Priority project update/comments
EXPLANATORY NOTE
In the first NCIPAP compliance report for a new regulatory control period, please fill out rows 1-3, 7-8, 10-11 and 14 for each priority project.
In following NCIPAP compliance report updates, the worksheet only needs to be updated where:
if during the previous calendar year the TNSP undertakes steps to implement a priority project (in this instance, updates may be needed for rows 4, 12, 13, 14 and 15)
if during the previous calendar year, events occur which result in the priority project key milestone dates being changed (please update this rows 14 and 15 of this worksheet), or
if the priority project has been completed in the previous calendar year (if this is the case, fill out rows 5 and 9 and ensure rows 4, 12, 13, 14 and 15 are up to date)
If this worksheet is updated, please update the summary worksheet to indicate changes have been made.

## Priority project 5
Priority project name and ranking | Priority Project 5 – Maintain capacity during Climate Change
Priority project description | Installation of DLR onto transmission lines with maximum contingency loading above 100%
Co-ordinated project | No
Has the priority project been commenced ? | No
Date of priority project completion
Limit(s) addressed by priority project | Long-term increased temperatures due to climate change causing increased stress on the capability of transmission lines in the NSW network
Initial limit value(s) | Future de-rating of transmission lines
Target limit value(s) | Dynamic ratings to account for alteration in ambient weather conditions
Completion limit values
Estimated capital cost of priority project | 5890000
Estimated operating cost of priority project | 0
Capital expenditure to date | 0
Operating expenditure to date | 0
Priority project key milestones and dates | ● Project is expected to be completed by June 2028.
Priority project update/comments
EXPLANATORY NOTE
In the first NCIPAP compliance report for a new regulatory control period, please fill out rows 1-3, 7-8, 10-11 and 14 for each priority project.
In following NCIPAP compliance report updates, the worksheet only needs to be updated where:
if during the previous calendar year the TNSP undertakes steps to implement a priority project (in this instance, updates may be needed for rows 4, 12, 13, 14 and 15)
if during the previous calendar year, events occur which result in the priority project key milestone dates being changed (please update this rows 14 and 15 of this worksheet), or
if the priority project has been completed in the previous calendar year (if this is the case, fill out rows 5 and 9 and ensure rows 4, 12, 13, 14 and 15 are up to date)
If this worksheet is updated, please update the summary worksheet to indicate changes have been made.

## Priority project 6
Priority project name and ranking | Priority Project 6 – Darlington Point 330/220 kV Transformer Tripping Scheme
Priority project description | Install tripping scheme to trip remaining 330/220/33 kV transformer at Darlington Point Substation for a loss of one transformer
Co-ordinated project | No
Has the priority project been commenced ? | No
Date of priority project completion
Limit(s) addressed by priority project | Darlington Point Substation is equipped with 2 x 200 MVA 330/220/33 kV tie transformers. In order to prevent overloading of an in-service 330/220/33 kV transformer at Darlington Point Substation following an outage of the other, the pre-contingent loading is capped at 125 MVA per transformer for ambient temperatures of 45 degrees Celsius.
Initial limit value(s) | 125 MVA
Target limit value(s) | 200 MVA
Completion limit values
Estimated capital cost of priority project | 367000
Estimated operating cost of priority project | 7340
Capital expenditure to date | 0
Operating expenditure to date | 0
Priority project key milestones and dates | ● Project is expected to be completed by June 2025.
Priority project update/comments | The present total transformer capacity at Darlington Point 330/220/33 kV Substation is 250 MVA for normal operating conditions. Generation flowing through those transformers is therefore curtailed to match this 250 MVA capacity under system normal. The amount of renewable generation thereby required to be curtailed (in MWh) is calculated as the Base Case scenario. The preferred option increases the normal transformer capacity to a total of 400 MVA. This reduces the curtailed renewable generation by approximately 60% after implementing the option. The reduction in curtailed MWh provides the market benefit due to fuel savings from off-setting higher-cost thermal generation elsewhere in the market.
EXPLANATORY NOTE
In the first NCIPAP compliance report for a new regulatory control period, please fill out rows 1-3, 7-8, 10-11 and 14 for each priority project.
In following NCIPAP compliance report updates, the worksheet only needs to be updated where:
if during the previous calendar year the TNSP undertakes steps to implement a priority project (in this instance, updates may be needed for rows 4, 12, 13, 14 and 15)
if during the previous calendar year, events occur which result in the priority project key milestone dates being changed (please update this rows 14 and 15 of this worksheet), or
if the priority project has been completed in the previous calendar year (if this is the case, fill out rows 5 and 9 and ensure rows 4, 12, 13, 14 and 15 are up to date)
If this worksheet is updated, please update the summary worksheet to indicate changes have been made.